## Sheet1
Florida Power & Light Company
Docket No. 130223-EI
Staff's First Set of Interrogatories
Interrogatory No. 4
Attachment No. 1
Tab 1 of 1
FLORIDA POWER AND LIGHT COMPANY
UP-FRONT NON-STANDARD METER PROGRAM CAPITAL COSTS
Line
No. |  | Task | Task Description | Estimated | Actual
1 | Customer Information System Changes with Web Enrollment and Billing
2 |  | Data Conversion - Care Center and Customer System Initial configuration | * Conversion of manual postponement list from Excel to customer billing system, development of interfaces to FPL's other operational field systems (i.e. trouble call and distribution work management systems) and additional system functionality for tracking postponed customers. Foundational work for enrollment and billing changes. | 477000 | 467708.19
3 |  | Customer Information System - Billing and Financial components | * Create new service charge to bill initial charges * Create new service charge to bill monthly charges * Ability to adjust, backdate, cancel/replace above fees as needed. * Bill, track and report on charges from enrollment through final accounting. | 808500 | 358506.18
4 |  | Customer Information System - Core functionality | * System functionality to link customers, premises and their opt out requests throughout customer care processes. * Execute opt out functionality with new meter change orders for opt out and smart meters. * Create new workflows for meter reading routing (Reroute to non-smart meter route and issue meter change if applicable) * System functionality for Care Center to forward opt out communication requirements to back office | 251500 | 111455.35
5 |  | Web Enrollment - Enable customer web self-service enroll functionality | * Build new web application for customers to sign up for smart meter opt out on FPL.com | 124000 | 318511.61
6 |  | Customer system automation to enroll in opt out program | * Workflow logic to support system checks for smart meter enrollment status. * Counters for all decision points * Various decision points around previously submitted request, confirmation letter received | 169000 | 411518.85
7 |  | Care Center - Enrollment | * Develop business logic to define customer eligibility * Create care center scripting and functionality for the care center to request letters and other correspondence to be sent to opt out customers. * Generate letter to communicate opt out status to customer, display code status & dates | 122000 | 314383.69
8 |  | Total Customer Information System Changes with Web Enrollment and Billing |  | 1952000 | 1982083.87
9
10 | Systems to Identify and Handle Opt Out Collection Issues
11 |  | Revenue Recovery - Online changes to support Remote Connect Switch | * Data Integrity - Changes to customer information system general maintenance screen for remote connect switch restrictions to ensure opt out accounts are not included | 99000 | 43657.63
12 |  | Total System Changes to Identify and Handle Opt Out Collection Issues |  | 99000 | 43657.63
13 |  | Total |  | 2051000 | 2025741.5