## Scope
Engineering, Design and Survey Work
Design bulkhead for intake and discharge tunnel
Complete Utility Identifications & Documentation
Perform environmental survey of above grade structures
Determine course of action for Intake & Dishcharge tunnel debris
Storm Water Prevention Plan
Decommisioning Work
Remove loose Chemicals and containers
CFC's (Freon)
Radioactive Sources
Batteries in bulk and fixtures
Remove ACM
Ash from Storage Silo
Remove light bulbs and ballasts
Install stop logs
Install bulkhead in intake and discharge tunnels
Install bulkheads in coal conveyor tunnels to remain
Remove structure down to surrounding grade - See Drawing XXX
Backfill all basements, pits and trenches up to surrounding grade elevation
Clarifications
Brick, Block, Concrete, Refractory & Mortar can be utilized as clean fill
Dispose of refractory in Subtitle D Landfill
No below grade concrete removal
No Sewer Cleaning
No cleaning of intake or discharge tunnels
No debris removal or disposal of intake and discharge tunnels
Intake and Discharge Tunnels will be bulkheaded and will not be excavated & collapsed
Caulk, Glazing and Expansion Joint Compound do not contain PCBs
Caulk, Glazing and Expansion Joint Compound do not contain ACM
No Transite or Galbestos removal
No ACM Removal from Stack
No Utility reroutes
No Permit Costs
No removal of soils or coal from Coal Field
No work at the Ash Pond or Landfill
No Soil removal or disposal
Dispose of fly ash as non-hazardous
Removal of Sluice Pipe is limited to immediate in the area of Main Power Block
No PCB Equipment or Oils
No active utilities existing in close proximity to structures to be removed
Prices are based on today scrap prices (July 8)
Ashalt Pavement can be used as clean fill
Bid is based on dropping of stacks
No Maintenance Costs associated with structures to remain
No Taxes associated with structures to remain
No Well Closures
No work in, on or over waterways
No removal of paved surfaces
No Site Security
Bid is based on plant performing their usual cleaning, washing and shutdown for an outage
No Paved Surface Removals