## CAPEX_by_Bus_Unit_BU_Detail_PE
CAPEX by Bus Unit / BU Detail / PE: Admin lock | PE -> Budget Contact | a-YTD-Jun - 2016 | [6 empty] | 2016
|  | CF Gulf - 2016 Official Budget - Live Reforecast | (VID:20160325) CF Gulf - 2016 Official Budget (Preserved) | Dif. (VID:20160325) CF Gulf - 2016 Official Budget (Preserved) | % Dif. (VID:20160325) CF Gulf - 2016 Official Budget (Preserved) |  |  |  |  | CF Gulf - 2016 Official Budget - Live Reforecast | (VID:20160325) CF Gulf - 2016 Official Budget (Preserved) | Dif. (VID:20160325) CF Gulf - 2016 Official Budget (Preserved) | % Dif. (VID:20160325) CF Gulf - 2016 Official Budget (Preserved)
2016-06-01 | Pointer to Budget Contact | YTD Actual | YTD Budget | YTD Variance ($) | YTD Variance (%) | YTD Over/Under Budget | Explanation Required? | YTD Explanation | Year-End Projection | Year-End Prior Projection | Original Budget | Year-End Variance ($) | Year-End Variance (%) | Year-End Over/Under Budget | YE Projection - YE Calculated
Power Generation
Co Generation
FPC-0040: Co-Generation Misc Projects | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 1.5 | 1500000 | 1500000 | -1499998.5 | -100% | Under Budget | -1499998.5 | -1500000
Sub-Total Co Generation |  | 0 | 0 | 0 | 0% | On Budget |  |  | 1.5 | 1500000 | 1500000 | -1499998.5 | -100% | Under Budget | -1499998.5
Environmental Cost Recovery Clause
FPC-0404: FPC-0404 | FPC - Vicki L. Mack: Vicki | 56768.88 | 0 | 56768.88 | 100% | Over Budget | Yes | 2015 carryover: unbudgeted expenses for installation of Smith Water Monitoring Wells | 56769 | 56768.88 | 0 | 56769 | 100% | Over Budget | 0.12
FPC-0406: ECRC - LAND - SMITH CCR WASTE WATER MANAGEMENT | FPC - Vicki L. Mack: Vicki | 0 | 1867500 | -1867500 | -100% | Under Budget | Yes | Duplicate project (Same as PE 1641); dollars will not be spent on PE 0406 | 0 | 6820 | 3750000 | -3750000 | -100% | Under Budget | -6820 | -6820
FPC-0412: ECRC-SMITH DUST MITIGATION WATER TRUCK | FPC - Vicki L. Mack: Vicki | 147165.13 | 100000 | 47165.13 | 47.17% | Over Budget | Yes | Actual cost for piece of equipment more than budget estimate | 147165 | 147165.13 | 100000 | 47165 | 47.16% | Over Budget | -0.13
FPC-0514: ECRC Daniel -Water -Ground Water Well | FPC - Vicki L. Mack: Vicki | 2444.74 | 0 | 2444.74 | 100% | Over Budget | No |  | 2529 | 2444.74 | 0 | 2529 | 100% | Over Budget | 84.26
FPC-1031: ECRC-AIR-CRIST 7 SCR CATALYST REPLACEMENT | FPC - Vicki L. Mack: Vicki | 418655.16 | 152482 | 266173.16 | 174.6% | Over Budget | Yes | project to be completed in Fall | 945000 | 1161134.16 | 894961 | 50039 | 5.591% | Over Budget | -216134.16
FPC-1060: ECRC-AIR-CRIST 7 FGAS MONITORS | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 46000 | 46000 | 46000 | 0 | 0% | On Budget | 0
FPC-1158: ECRC-AIR-CRIST 7 SCR MISC | FPC - Vicki L. Mack: Vicki | 927.94 | 0 | 927.94 | 100% | Over Budget | No |  | 928 | 927.94 | 0 | 928 | 100% | Over Budget | 0.06
FPC-1193: ECRC-WATER-CRIST 4-7 LOW VOLUME WASTE WATER TREATMENT | FPC - Vicki L. Mack: Vicki | 458954.6 | 1504800 | -1045845.4 | -69.5% | Under Budget | Yes | multi-year project, dollars pushed into 2017 | 2500000 | 2430420.6 | 3009600 | -509600 | -16.93% | Under Budget | 69579.4
FPC-1199: ECRC-AIR-CRIST U7 SCR PRECIP RELOCAT | FPC - Vicki L. Mack: Vicki | 1686.81 | 12500 | -10813.19 | -86.51% | Under Budget | Yes | project to be completed in Fall | 25000 | 14186.81 | 25000 | 0 | 0% | On Budget | 10813.19
FPC-1222: ECRC-AIR-CRIST - SCRUBBER | FPC - Vicki L. Mack: Vicki | 848225.89 | 250000 | 598225.89 | 239.3% | Over Budget | Yes | projects started earlier than budgeted | 5573250 | 5738141.89 | 5573250 | 0 | 0% | On Budget | -164891.89
FPC-1233: ECRC-AIR-CRIST SCRUBBER MISCELLANEOUS | FPC - Vicki L. Mack: Vicki | 429300.54 | 0 | 429300.54 | 100% | Over Budget | Yes | 2015 carryover | 429301 | 429300.54 | 0 | 429301 | 100% | Over Budget | 0.46
FPC-1234: ECRC-AIR-CRIST U7 LOW NOX BURNER REPLACEMENT | FPC - Vicki L. Mack: Vicki | 52997.68 | 0 | 52997.68 | 100% | Over Budget | Yes | project started earlier than budgeted | 831288 | 52997.68 | 0 | 831288 | 100% | Over Budget | 778290.32 | 800000
FPC-1279: ECRC-AIR-CRIST U6 CONTROLS - SCR & ID FANS | FPC - Vicki L. Mack: Vicki | 0 | 5500 | -5500 | -100% | Under Budget | No |  | 11000 | 5500 | 11000 | 0 | 0% | On Budget | 5500
FPC-1287: ECRC-AIR-CRIST 4-6 NOX REDUCTION - DEPR - (SNCR) | FPC - Vicki L. Mack: Vicki | 440490.12 | 649252 | -208761.88 | -32.15% | Under Budget | Yes | project to be completed in Fall | 480000 | 746738.12 | 655500 | -175500 | -26.77% | Under Budget | -266738.12
FPC-1288: ECRC-AIR-CRIST-CONSTRUCT GYPSUM STORAGE CELL NO. 1 | FPC - Vicki L. Mack: Vicki | 70434.3 | 341775 | -271340.7 | -79.39% | Under Budget | Yes | 128801 - 2015 Carryover 128802 - Project Canceled 1288 / 128804 - moved to future years | 550797 | 1409905.3 | 1681246 | -1130449 | -67.24% | Under Budget | -859108.3
FPC-1517: ECRC - AIR- DANIEL BROMINE INJECTION | FPC - Vicki L. Mack: Vicki | -19605.63 | 0 | -19605.63 | -100% | Under Budget | Yes | Carry over | -19606 | -19605.63 | 0 | -19606 | -100% | Under Budget | -0.37
FPC-1551: ECRC-AIR-DANIEL 1 & 2 SCRUBBER | FPC - Vicki L. Mack: Vicki | 2802779.74 | 3095703 | -292923.26 | -9.462% | Under Budget | Yes | Plan on being on budget year end | 3095703 | 3416745.74 | 3095703 | 0 | 0% | On Budget | -321042.74
FPC-1601: ECRC-WATER-SMITH RECLAIMED WATER PROJECT UNIT 3 | FPC - Vicki L. Mack: Vicki | 1014073.77 | 340807 | 673266.77 | 197.6% | Over Budget | Yes | 2015 carryover: unbudgeted contractor expenses on project to date…job ongoing | 1765000 | 1172253.77 | 340807 | 1424193 | 417.9% | Over Budget | 592746.23
FPC-1641: ECRC - Smith 1 & 2 Cross Media Retrofit | FPC - Vicki L. Mack: Vicki | 0 | 1867500 | -1867500 | -100% | Under Budget | Yes | Project will not start in 2016 (per Env. Affairs - Jarvis) | 0 | 0 | 3750000 | -3750000 | -100% | Under Budget | 0
FPC-1809: ECRC -AIR-DANIEL 1 & 2 ACTIVATED CARBON INJECTION C01767 | FPC - Vicki L. Mack: Vicki | -49504.37 | 782117 | -831621.37 | -106.3% | Under Budget | Yes | Dec accruals… project pushed out this year | 782117 | 495950.63 | 782117 | 0 | 0% | On Budget | 286166.37
FPC-1909: ECRC-AIR-CIRST MISC SCR COMMON | FPC - Vicki L. Mack: Vicki | 30234.08 | 24996 | 5238.08 | 20.96% | Over Budget | No |  | 50000 | 55238.08 | 50000 | 0 | 0% | On Budget | -5238.08
FPC-1912: ECRC-AIR-CRIST U4-7 DRY BOTTOM ASH | FPC - Vicki L. Mack: Vicki | 0 | 1250004 | -1250004 | -100% | Under Budget | Yes | project started later than anticipated due to study being conducted | 2100000 | 1141662 | 2500000 | -400000 | -16% | Under Budget | 958338 | 950000
FPC-1997: ECRC-LAND-CRIST DISPOSAL OF COAL COMBUSTION RESIDUALS (CCR) | FPC - Vicki L. Mack: Vicki | 137697.54 | 0 | 137697.54 | 100% | Over Budget | Yes | 2015 Carryover | 137698 | 137697.54 | 0 | 137698 | 100% | Over Budget | 0.46
Sub-Total Environmental Cost Recovery Clause |  | 6843726.92 | 12244936 | -5401209.08 | -44.11% | Under Budget |  |  | 19509939 | 18648393.92 | 26265184 | -6755245 | -25.72% | Under Budget | 861545.08
Environmental (Non-Clause)
FPC-0501: Envir Daniel Unit 1 Pyrite Hoppers/Piping Valves | FPC - Vicki L. Mack: Vicki | -876.41 | 0 | -876.41 | -100% | Under Budget | No |  | -1563 | -876.41 | 0 | -1563 | -100% | Under Budget | -686.59
FPC-1033: ENVIR - WASTE - CRIST FLY ASH LANDFILL STORAGE CELL CAPPING | FPC - Vicki L. Mack: Vicki | 0 | 262392 | -262392 | -100% | Under Budget | Yes | offset PE 1220 Governor's Island | 0 | 262608 | 525000 | -525000 | -100% | Under Budget | -262608
FPC-1220: ENVIR-WATER-CRIST GOVERNORS ISLAND HEADWALL | FPC - Vicki L. Mack: Vicki | 2965035.18 | 0 | 2965035.18 | 100% | Over Budget | Yes | PE Approval Letter | 9500000 | 6682259.18 | 0 | 9500000 | 100% | Over Budget | 2817740.82 | 2800000
FPC-1253: ENVIR-WASTE- CRIST-FLY ASH LANDFILL STORAGE CELL DEVELOPMENT | FPC - Vicki L. Mack: Vicki | 42335.9 | 499800 | -457464.1 | -91.53% | Under Budget | Yes | offset PE 1220 Governor's Island except for $40K added to scope in 12/2015. | 42336 | 42534.9 | 1000000 | -957664 | -95.77% | Under Budget | -198.9
FPC-1613: ENVIR-WASTE-SMITH CAP ASH LANDFILL CELLS | FPC - Vicki L. Mack: Vicki | 114.37 | 0 | 114.37 | 100% | Over Budget | No |  | 114 | 114.37 | 0 | 114 | 100% | Over Budget | -0.37
FPC-1701: ENVIR - AIR - SCHERER 3 -MISC ENVIRONMENTAL PROJECTS | FPC - Vicki L. Mack: Vicki | 18526.85 | 51846 | -33319.15 | -64.27% | Under Budget | Yes | Timing. Dollars will be used. | 103730 | 70410.85 | 103730 | 0 | 0% | On Budget | 33319.15
FPC-1727: ENVIR-AIR-SCHERER SELECTIVE CAYALYTIC REDUCT (SCR) | FPC - Vicki L. Mack: Vicki | -25698.39 | 0 | -25698.39 | -100% | Under Budget | Yes | EC&S True up | -25698 | -25698.39 | 0 | -25698 | -100% | Under Budget | 0.39
FPC-1728: ENVIR-AIR-SCHERER SCRUBBER | FPC - Vicki L. Mack: Vicki | -275309.83 | 0 | -275309.83 | -100% | Under Budget | Yes | EC&S True up | -275310 | -275309.83 | 0 | -275310 | -100% | Under Budget | -0.17
FPC-1729: FPC-1729 | FPC - Vicki L. Mack: Vicki | 38617.19 | 0 | 38617.19 | 100% | Over Budget | Yes | Carryover | 38617 | 38617.19 | 0 | 38617 | 100% | Over Budget | -0.19
FPC-1755: ENVIR SCHERER-AIR-HG/PM CEMS | FPC - Vicki L. Mack: Vicki | 679.62 | 0 | 679.62 | 100% | Over Budget | No |  | 680 | 679.62 | 0 | 680 | 100% | Over Budget | 0.38
FPC-1762: ENVIR - Air- Scherer 3 Bromine Injection | FPC - Vicki L. Mack: Vicki | 0 | 558000 | -558000 | -100% | Under Budget | Yes | Still projected to spend. Project not started | 1115000 | 558000 | 1116000 | -1000 | -0.08961% | Under Budget | 557000
FPC-1778: ENVIR - SCHERER - ENVIRONMENTAL SITE PLAN | FPC - Vicki L. Mack: Vicki | -118352.33 | 0 | -118352.33 | -100% | Under Budget | Yes | EC&S True up | -118352 | -118352.33 | 0 | -118352 | -100% | Under Budget | 0.33
FPC-1791: FPC-1791 | FPC - Vicki L. Mack: Vicki | -20664.9 | 0 | -20664.9 | -100% | Under Budget | Yes | EC&S True up | -20665 | -20664.9 | 0 | -20665 | -100% | Under Budget | -0.1
FPC-1798: ENVIR SCHERER 3 SCR CATALYST REPLACEMENT | FPC - Vicki L. Mack: Vicki | 0 | 341780 | -341780 | -100% | Under Budget | Yes | GWO written. Late getting started | 371500 | 0 | 341780 | 29720 | 8.696% | Over Budget | 371500
FPC-1878: Environ - Daniel 1 & 2 Dry Ash Equipment | FPC - Vicki L. Mack: Vicki | 22182.59 | 0 | 22182.59 | 100% | Over Budget | Yes | SCS charges related to load testing, redline draws | 24891 | 22182.59 | 0 | 24891 | 100% | Over Budget | 2708.41
FPC-6756: Envir - Scherer 3 -LAND CCR ASH MANAGEMENT | FPC - Vicki L. Mack: Vicki | 12913.9 | 158790 | -145876.1 | -91.87% | Under Budget | Yes | Late getting started | 323315 | 186424.9 | 317576 | 5739 | 1.807% | Over Budget | 136890.1
FPC-6757: Envir - Scherer 3 New Landfill - Phase 1 | FPC - Vicki L. Mack: Vicki | 4206.07 | 100014 | -95807.93 | -95.79% | Under Budget | Yes | Late getting started | 200000 | 104220.07 | 200028 | -28 | -0.014% | Under Budget | 95779.93
FPC-6759: Envir - Scherer - Land- CCR WW Management | FPC - Vicki L. Mack: Vicki | 11811.16 | 78378 | -66566.84 | -84.93% | Under Budget | Yes | Late getting started | 161895 | 90189.16 | 156756 | 5139 | 3.278% | Over Budget | 71705.84
Sub-Total Environmental (Non-Clause) |  | 2675520.97 | 2051000 | 624520.97 | 30.45% | Over Budget |  |  | 11440490 | 7617338.97 | 3760870 | 7679620 | 204.2% | Over Budget | 3823151.03
Plant Crist
FPC-0803: Crist U 7 BFP Controls Replacement | FPC - Vicki L. Mack: Vicki | 103179.22 | 0 | 103179.22 | 100% | Over Budget | Yes | cancelled | 0 | 969429.22 | 866250 | -866250 | -100% | Under Budget | -969429.22
FPC-0804: Crist Unit 7 BFPT Overspeed Bolt Replacement | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 739511 | 900000 | 890925 | -151414 | -17% | Under Budget | -160489
FPC-0805: Crist U7 Main Turbine Overspeed Bolt Replacement | FPC - Vicki L. Mack: Vicki | 135097.04 | 0 | 135097.04 | 100% | Over Budget | Yes | project pushed forward | 792750 | 1494515.04 | 792750 | 0 | 0% | On Budget | -701765.04
FPC-0806: Crist U6 BFPT Overspeed Bolt Replacement | FPC - Vicki L. Mack: Vicki | 210522.91 | 0 | 210522.91 | 100% | Over Budget | Yes | project pushed forward | 280403 | 490925.91 | 280403 | 0 | 0% | On Budget | -210522.91
FPC-0807: Crist U6 Main Turbine Overspeed Bolt Replacement | FPC - Vicki L. Mack: Vicki | 44788.23 | 0 | 44788.23 | 100% | Over Budget | Yes | project pushed forward | 334031 | 378819.23 | 334031 | 0 | 0% | On Budget | -44788.23
FPC-0808: Crist U7 Airflow Transmitter (Kurz) Replacement | FPC - Vicki L. Mack: Vicki | 20457.68 | 347500 | -327042.32 | -94.11% | Under Budget | Yes | project pushed to end of year | 399000 | 71957.68 | 399000 | 0 | 0% | On Budget | 327042.32
FPC-0809: Crist A Flyash Compressor | FPC - Vicki L. Mack: Vicki | 0 | 68880 | -68880 | -100% | Under Budget | Yes | project pushed to end of year | 68880 | 0 | 68880 | 0 | 0% | On Budget | 68880
FPC-0810: Crist B Flyash Compressor | FPC - Vicki L. Mack: Vicki | 0 | 68880 | -68880 | -100% | Under Budget | Yes | project pushed to end of year | 68880 | 0 | 68880 | 0 | 0% | On Budget | 68880
FPC-0812: Crist U4 Turbine Water Induction Protection (TWIP) | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 787700 | 1969250 | -1969250 | -100% | Under Budget | -787700
FPC-0813: Crist U5 Turbine Water Induction Protection (TWIP) | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 787700 | 1969250 | -1969250 | -100% | Under Budget | -787700
FPC-0816: Crist Common Replace Fencing (Security) | FPC - Vicki L. Mack: Vicki | 0 | 550000 | -550000 | -100% | Under Budget | Yes | project pushed to end of year | 550000 | 0 | 550000 | 0 | 0% | On Budget | 550000
FPC-0817: Crist - Replace Units 6 & 7 Elevator | FPC - Vicki L. Mack: Vicki | 0 | 1300000 | -1300000 | -100% | Under Budget | Yes | project moved to 2017. E&CS this year. | 42000 | 200000 | 1500000 | -1458000 | -97.2% | Under Budget | -158000
FPC-1003: CRIST 7 BOTTOM ASH PIT TRASH HOPPER | FPC - Vicki L. Mack: Vicki | 0 | 7350 | -7350 | -100% | Under Budget | No |  | 0 | 150150 | 157500 | -157500 | -100% | Under Budget | -150150
FPC-1027: CRIST 4 & 5 ASH CONTROLS | FPC - Vicki L. Mack: Vicki | 320.92 | 0 | 320.92 | 100% | Over Budget | No |  | 321 | 320.92 | 0 | 321 | 100% | Over Budget | 0.08
FPC-1041: CRIST 6C 4160 V BUS REPL BREAKERS | FPC - Vicki L. Mack: Vicki | 205648.4 | 40000 | 165648.4 | 414.1% | Over Budget | Yes | SCS drawings underestimated and other SCS work needed. | 203109 | 205648.4 | 40000 | 163109 | 407.8% | Over Budget | -2539.4
FPC-1042: CRIST 7C 4160 VOLT BUS REPLACE BREAKERS | FPC - Vicki L. Mack: Vicki | 158193.6 | 40000 | 118193.6 | 295.5% | Over Budget | Yes | SCS drawings underestimated. | 160000 | 158193.6 | 40000 | 120000 | 300% | Over Budget | 1806.4
FPC-1046: CRIST 4-7 SILO ASH MCC REPLACEMENT | FPC - Vicki L. Mack: Vicki | 66286.16 | 41169 | 25117.16 | 61.01% | Over Budget | Yes | $30K projected to be spent in 2015 was not spent. Added to 2016 budget. | 295260 | 290767.16 | 265650 | 29610 | 11.15% | Over Budget | 4492.84
FPC-1050: CRIST U5 575 VOLT BUS REPLACEMENT | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 15750 | 15750 | -15750 | -100% | Under Budget | -15750
FPC-1059: CRIST 5 -- 2300 VOLT BREAKERS | FPC - Vicki L. Mack: Vicki | 20720.87 | 0 | 20720.87 | 100% | Over Budget | Yes | Accts Payable correction - Siemens invoice. | 20721 | 20720.87 | 0 | 20721 | 100% | Over Budget | 0.13
FPC-1068: CRIST U6 BLOWDOWN TANK REPLACEMENT | FPC - Vicki L. Mack: Vicki | 37161.88 | 0 | 37161.88 | 100% | Over Budget | Yes | Correcting JV - material posted to incorrect GWO. | 37162 | 37161.88 | 0 | 37162 | 100% | Over Budget | 0.12
FPC-1081: CRIST U4 ASSET PROTECTION - PAG | FPC - Vicki L. Mack: Vicki | 367374.4 | 0 | 367374.4 | 100% | Over Budget | Yes | Bid lower than anticipated. | 1681250 | 1551374.4 | 50000 | 1631250 | 3262% | Over Budget | 129875.6
FPC-1089: CRIST 6 REPLACE ASH HOOPER | FPC - Vicki L. Mack: Vicki | 39.31 | 0 | 39.31 | 100% | Over Budget | No |  | 39 | 39.31 | 0 | 39 | 100% | Over Budget | -0.31
FPC-1091: CRIST 7 AIR HEATER BASKETS | FPC - Vicki L. Mack: Vicki | 1462727.4 | 0 | 1462727.4 | 100% | Over Budget | Yes | Progress payment made in 2015. | 1803275 | 2696061.4 | 2000000 | -196725 | -9.836% | Under Budget | -892786.4
FPC-1093: CRIST U5 ASSET PROTECTION - PAG | FPC - Vicki L. Mack: Vicki | 357245.35 | 0 | 357245.35 | 100% | Over Budget | Yes | Bid lower than anticipated. | 1681250 | 1547245.35 | 50000 | 1631250 | 3262% | Over Budget | 134004.65
FPC-1096: CRIST U6 ASSET PROTECTION - PAG | FPC - Vicki L. Mack: Vicki | 126835.59 | 0 | 126835.59 | 100% | Over Budget | Yes | TWIP not budgeted | 165700 | 176835.59 | 50000 | 115700 | 231.4% | Over Budget | -11135.59
FPC-1097: CRIST U7 ASSET PROTECTION - PAG | FPC - Vicki L. Mack: Vicki | 26604.04 | 0 | 26604.04 | 100% | Over Budget | Yes | Actuals will be journaled to PE 1148. | 50000 | 76604.04 | 50000 | 0 | 0% | On Budget | -26604.04
FPC-1100: CRIST - MINOR MISC ADDITIONS | FPC - Vicki L. Mack: Vicki | 581041.34 | 374850 | 206191.34 | 55.01% | Over Budget | Yes | More minor miscellaneous projects needed than budgeted. | 1943303 | 1556191.34 | 750000 | 1193303 | 159.1% | Over Budget | 387111.66
FPC-1108: CRIST 7 FLY ASH CONTROLS | FPC - Vicki L. Mack: Vicki | 67013.02 | 26250 | 40763.02 | 155.3% | Over Budget | Yes | project started earlier. | 315000 | 355763.02 | 315000 | 0 | 0% | On Budget | -40763.02
FPC-1137: CRIST 6 CONTROL SYSTEM UPGRADES | FPC - Vicki L. Mack: Vicki | -141128.39 | 0 | -141128.39 | -100% | Under Budget | Yes | True up of retrofit/ECRC split should have been made in 2015. Will be made in the next couple of months when GWO is unitized. | -141128 | -141128.39 | 0 | -141128 | -100% | Under Budget | 0.39
FPC-1143: CRIST 5 MONITORING SYSTEM UPGRADES | FPC - Vicki L. Mack: Vicki | -1607.47 | 0 | -1607.47 | -100% | Under Budget | No |  | -1607 | -1607.47 | 0 | -1607 | -100% | Under Budget | 0.47
FPC-1144: CRIST 7 CONTROL SYSTEM UPGRADES | FPC - Vicki L. Mack: Vicki | 33548.01 | 0 | 33548.01 | 100% | Over Budget | Yes | True up of retrofit/ECRC split should have been made in 2015. Will be made in the next couple of months when GWO is unitized. | 33548 | 33548.01 | 0 | 33548 | 100% | Over Budget | -0.01
FPC-1148: CRIST - MAJOR MISC ADDITIONS | FPC - Vicki L. Mack: Vicki | 727379.58 | 499800 | 227579.58 | 45.53% | Over Budget | Yes | More major miscellaneous projects needed than budgeted. $1.5M annex a/c, $1.5M U7 gas burners, $560K U6 fill & louvers, $368K coal yard sump pumps, $203K Maint team leader office, $100K PE 0818 new approved PE U6 front & rear wall headers. | 5978925 | 3042579.58 | 1000000 | 4978925 | 497.9% | Over Budget | 2936345.42 | 2900000
FPC-1151: CRIST CLEARWATER HDRS & PIPING | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 300300 | 300300 | 300300 | 0 | 0% | On Budget | 0
FPC-1176: CRIST U4 REPL BREAKERS CABLE & SWITCHES FOR ARC FLASH STUDY | FPC - Vicki L. Mack: Vicki | -10716.51 | 0 | -10716.51 | -100% | Under Budget | Yes | carryover | -10717 | -10716.51 | 0 | -10717 | -100% | Under Budget | -0.49
FPC-1210: CRIST CYBER SECURITY | FPC - Vicki L. Mack: Vicki | 0 | 72582 | -72582 | -100% | Under Budget | Yes | No word from SCS on this yet. Projected to spend by year-end. | 145217 | 72635 | 145217 | 0 | 0% | On Budget | 72582
FPC-1223: CRIST 7 BOTTOM ASH HOPPER | FPC - Vicki L. Mack: Vicki | 267411.54 | 2082265 | -1814853.46 | -87.16% | Under Budget | Yes | Bid lower and progress payment made in 2015. | 5380684 | 5726220.54 | 8446528 | -3065844 | -36.3% | Under Budget | -345536.54
FPC-1254: CRIST COMMON -CONVEYOR BELTS REPLACEMENT | FPC - Vicki L. Mack: Vicki | 11152.37 | 0 | 11152.37 | 100% | Over Budget | Yes | Projected to spend by year end. | 105000 | 116152.37 | 105000 | 0 | 0% | On Budget | -11152.37
FPC-1282: CRIST UNITS 4 5 6 & 7 CHEMICAL FEED SYSTEM | FPC - Vicki L. Mack: Vicki | 13888 | 0 | 13888 | 100% | Over Budget | Yes | Carryover | 13888 | 13888 | 0 | 13888 | 100% | Over Budget | 0
FPC-1925: CRIST PURCHASE MOBILE CRANE TO REPL TEREX | FPC - Vicki L. Mack: Vicki | 3455.09 | 0 | 3455.09 | 100% | Over Budget | No |  | 3455 | 3455.09 | 0 | 3455 | 100% | Over Budget | -0.09
FPC-1936: CRIST DRY AIR LAY-UP SYSTEM FOR UNITS 4-7 | FPC - Vicki L. Mack: Vicki | 14987.76 | 299250 | -284262.24 | -94.99% | Under Budget | Yes | Project moved up to 2015. | 14988 | 83237.76 | 367500 | -352512 | -95.92% | Under Budget | -68249.76
FPC-1937: CRIST U6 PULVERIZER GEARBOX | FPC - Vicki L. Mack: Vicki | 0 | 127635 | -127635 | -100% | Under Budget | Yes | Project will start later than anticipated. | 127636 | 1 | 127636 | 0 | 0% | On Budget | 127635
FPC-1942: CRIST U7 PULVERIZER GEARBOXES | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 127636 | 127636 | 127636 | 0 | 0% | On Budget | 0
FPC-1946: CRIST SILO SUMP PUMP DISCHARGE LINE | FPC - Vicki L. Mack: Vicki | 9622.56 | 0 | 9622.56 | 100% | Over Budget | No |  | 13700 | 9622.56 | 0 | 13700 | 100% | Over Budget | 4077.44
FPC-1953: CRIST U6 & U7 NEW BREAKER BUILDING | FPC - Vicki L. Mack: Vicki | 3928.78 | 0 | 3928.78 | 100% | Over Budget | No |  | 3929 | 3928.78 | 0 | 3929 | 100% | Over Budget | 0.22
FPC-1960: CRIST PURCHASE NEW RADIOS | FPC - Vicki L. Mack: Vicki | 21121.59 | 0 | 21121.59 | 100% | Over Budget | Yes | Carryover | 21122 | 21121.59 | 0 | 21122 | 100% | Over Budget | 0.41
FPC-1963: CRIST Lab Bathrooms | FPC - Vicki L. Mack: Vicki | 0 | 703500 | -703500 | -100% | Under Budget | Yes | Will be done end of year | 703500 | 0 | 703500 | 0 | 0% | On Budget | 703500 | 700000 | 0
FPC-1973: CRIST SWITCHYARD DRAINS | FPC - Vicki L. Mack: Vicki | -23095.94 | 204750 | -227845.94 | -111.3% | Under Budget | Yes | Cancelled. JV to remove dollars. | -23096 | -23095.94 | 204750 | -227846 | -111.3% | Under Budget | -0.06
FPC-1977: CRIST U7 REPLACE PULVERIZER MOTOR | FPC - Vicki L. Mack: Vicki | 123689.65 | 0 | 123689.65 | 100% | Over Budget | Yes | Carryover. | 123690 | 123689.65 | 0 | 123690 | 100% | Over Budget | 0.35
FPC-1978: CRIST REPLACE B SILO COMPRESSOR | FPC - Vicki L. Mack: Vicki | 24080.89 | 0 | 24080.89 | 100% | Over Budget | Yes | Project starting later than anticipated. | 194250 | 24080.89 | 0 | 194250 | 100% | Over Budget | 170169.11
FPC-1979: CRIST ASH TRUCK SCALES | FPC - Vicki L. Mack: Vicki | 1740.54 | 0 | 1740.54 | 100% | Over Budget | No |  | 250000 | 572905.54 | 571165 | -321165 | -56.23% | Under Budget | -322905.54
FPC-1990: CRIST 4&5 COLLING TOWER FIRE PUMP STATION | FPC - Vicki L. Mack: Vicki | 0 | 330750 | -330750 | -100% | Under Budget | Yes | Project starting later than anticipated. | 330750 | 0 | 330750 | 0 | 0% | On Budget | 330750
FPC-1991: CRIST U6 575 VOLT BREAKER REPLACEMENT | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 400523 | 400523 | -400523 | -100% | Under Budget | -400523
FPC-1992: CRIST U7 575 VOLT BREAKER REPLACEMENT | FPC - Vicki L. Mack: Vicki | -2176.62 | 0 | -2176.62 | -100% | Under Budget | No |  | -2177 | 536473.38 | 538650 | -540827 | -100.4% | Under Budget | -538650.38
Sub-Total Plant Crist |  | 5068538.79 | 7185411 | -2116872.21 | -29.46% | Under Budget |  |  | 25325338 | 25955324.79 | 26842674 | -1517336 | -5.653% | Under Budget | -629986.79
Plant Smith excl LTSA
FPC-0400: FPC-0400 | FPC - Vicki L. Mack: Vicki | 199.93 | 0 | 199.93 | 100% | Over Budget | No |  | 200 | 199.93 | 0 | 200 | 100% | Over Budget | 0.07
FPC-0401: FPC-0401 | FPC - Vicki L. Mack: Vicki | 338.36 | 0 | 338.36 | 100% | Over Budget | No |  | 338 | 338.36 | 0 | 338 | 100% | Over Budget | -0.36
FPC-0407: SMITH - CONSTRUCTION SUB TRANSFORMER (LAGUNA BEACH) | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 252045 | 1000000 | -1000000 | -100% | Under Budget | -252045
FPC-0408: SMITH 3 - COOLING TOWER FILL MEDIA REPLACEMENTS | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 125000 | 125000 | 125000 | 0 | 0% | On Budget | 0
FPC-0409: SMITH 3 - DRIFT ELIMINATOR | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 150000 | 150000 | 150000 | 0 | 0% | On Budget | 0
FPC-0410: SMITH 3 - COOLING TOWER DCS CABINET REPLACEMENTS | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 80000 | 80000 | 80000 | 0 | 0% | On Budget | 0
FPC-0413: Smith 3 - Water Mist Fire Protection System | FPC - Vicki L. Mack: Vicki | 21908.58 | 0 | 21908.58 | 100% | Over Budget | Yes | early materials purchases in preparation to begin projecct | 685000 | 706908.58 | 685000 | 0 | 0% | On Budget | -21908.58
FPC-0414: FPC-0414 | FPC - Vicki L. Mack: Vicki | 0.87 | 0 | 0.87 | 0% | On Budget | No |  | 1 | 0.87 | 0 | 1 | 0% | On Budget | 0.13
FPC-1400: SMITH 1&2 - MISC. STEAM PLANT ADDITIONS | FPC - Vicki L. Mack: Vicki | 3943.31 | 262398 | -258454.69 | -98.5% | Under Budget | Yes | Minimal misc. activity on Smith 1 & 2 to date | 524885 | 266545.31 | 525000 | -115 | -0.0219% | Under Budget | 258339.69
FPC-1401: SMITH 3 - AIR COMPRESSOR REPLACEMENT | FPC - Vicki L. Mack: Vicki | 0 | 100000 | -100000 | -100% | Under Budget | Yes | Project not yet started | 100000 | 0 | 100000 | 0 | 0% | On Budget | 100000
FPC-1428: Smith 3 Water Treatment Plant Transformer | FPC - Vicki L. Mack: Vicki | 1.23 | 0 | 1.23 | 100% | Over Budget | No |  | 1 | 1.23 | 0 | 1 | 0% | On Budget | -0.23
FPC-1437: Smith 3 - Admin Bldg. Expansion | FPC - Vicki L. Mack: Vicki | 2968814.62 | 1743000 | 1225814.62 | 70.33% | Over Budget | Yes | overruns for contractor expenses to work on bldg. | 4100000 | 4370956.62 | 3500000 | 600000 | 17.14% | Over Budget | -270956.62
FPC-1477: SMITH 3 - REPLACE INLINE AIR FILTERS | FPC - Vicki L. Mack: Vicki | 0 | 400000 | -400000 | -100% | Under Budget | Yes | Project not yet started - will begin during the next outage, this fall. | 400000 | 266668 | 400000 | 0 | 0% | On Budget | 133332
FPC-1499: Smith U3 - Simulator | FPC - Vicki L. Mack: Vicki | 504.61 | 0 | 504.61 | 100% | Over Budget | No |  | 27000 | 504.61 | 0 | 27000 | 100% | Over Budget | 26495.39
FPC-1600: SMITH 3 - MISC. STEAM PLANT ADDITIONS | FPC - Vicki L. Mack: Vicki | 141010.38 | 499814 | -358803.62 | -71.79% | Under Budget | Yes | Minimal materials/contractor expenses for misc activity on Smith 3 to date | 812245 | 641196.38 | 1000000 | -187755 | -18.78% | Under Budget | 171048.62
FPC-1610: SMITH - CYBER SECURITY | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 39600 | 28634 | 28634 | 10966 | 38.3% | Over Budget | 10966
FPC-1626: SMITH - NERC CIP IMPLEMENTATION | FPC - Vicki L. Mack: Vicki | 0 | 77450 | -77450 | -100% | Under Budget | Yes | Project has not yet started -projected expected to begin during the next outage, this fall | 154900 | 77450 | 154900 | 0 | 0% | On Budget | 77450
FPC-1632: SMITH 3 - REPLACE EVAP COOLER FILL MEDIA | FPC - Vicki L. Mack: Vicki | 0 | 100000 | -100000 | -100% | Under Budget | Yes | Project has not yet started - will begin during the next outage, this fall. | 150000 | 0 | 100000 | 50000 | 50% | Over Budget | 150000
FPC-1648: SMITH 3 - STORM WATER SYSTEM | FPC - Vicki L. Mack: Vicki | -636.12 | 0 | -636.12 | -100% | Under Budget | No |  | -636 | -636.12 | 0 | -636 | -100% | Under Budget | 0.12
FPC-1672: SMITH - PROPERTY LINE FENCING | FPC - Vicki L. Mack: Vicki | 189551.08 | 747000 | -557448.92 | -74.63% | Under Budget | Yes | Project in progress - small materials purchases & contractor work to date…bulk of project has not started | 1500000 | 1192550.08 | 1500000 | 0 | 0% | On Budget | 307449.92
FPC-1679: SMITH 3 - CORROSION PROJECT | FPC - Vicki L. Mack: Vicki | 484986.92 | 498000 | -13013.08 | -2.613% | Under Budget | No |  | 500000 | 986986.92 | 1000000 | -500000 | -50% | Under Budget | -486986.92
Sub-Total Plant Smith excl LTSA |  | 3810623.77 | 4427662 | -617038.23 | -13.94% | Under Budget |  |  | 9348534 | 9145349.77 | 10348534 | -1000000 | -9.663% | Under Budget | 203184.23
Plant Smith - LTSA
FPC-1438: SMITH 3 - LTSA | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 27491875 | 27491875 | 27491875 | 0 | 0% | On Budget | 0
Sub-Total Plant Smith - LTSA |  | 0 | 0 | 0 | 0% | On Budget |  |  | 27491875 | 27491875 | 27491875 | 0 | 0% | On Budget | 0
Plant Daniel
FPC-0503: Daniel Common Emergency Alarm Tone Notification System | FPC - Vicki L. Mack: Vicki | 808.94 | 0 | 808.94 | 100% | Over Budget | No |  | 809 | 808.94 | 0 | 809 | 100% | Over Budget | 0.06
FPC-0506: Daniel 1 & 2 Sump Pump | FPC - Vicki L. Mack: Vicki | 181.39 | 0 | 181.39 | 100% | Over Budget | No |  | 183 | 181.39 | 0 | 183 | 100% | Over Budget | 1.61
FPC-0507: Daniel Units 1 & 2 Termon Heat Trace ( Freeze Protection) | FPC - Vicki L. Mack: Vicki | -186572.16 | 0 | -186572.16 | -100% | Under Budget | Yes | Project added to MPC's Final OB | 127620 | -186572.16 | 0 | 127620 | 100% | Over Budget | 314192.16
FPC-0510: Daniel U1 LED Lighting - Turbine Floor | FPC - Vicki L. Mack: Vicki | 59764.53 | 137448 | -77683.47 | -56.52% | Under Budget | Yes | Project reduced in MPC's Final OB | 114946 | 397316.53 | 475000 | -360054 | -75.8% | Under Budget | -282370.53
FPC-0512: Daniel Common Breakers | FPC - Vicki L. Mack: Vicki | 14231.26 | 0 | 14231.26 | 100% | Over Budget | Yes | Breaker issues are requiring additional time to inspect the breakers. | 17561 | 294231.26 | 280000 | -262439 | -93.73% | Under Budget | -276670.26
FPC-0515: Daniel Conveyor Equipment- Add Camera to Conveyor Belts | FPC - Vicki L. Mack: Vicki | 0 | 150000 | -150000 | -100% | Under Budget | Yes | Project start date pushed back | 0 | 0 | 150000 | -150000 | -100% | Under Budget | 0
FPC-0521: Daniel U2 Aux. Air Beck drives and registers | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 195000 | 195000 | -195000 | -100% | Under Budget | -195000
FPC-0523: Daniel Common Replace Coal yard Switchgear | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 95000 | 95000 | -95000 | -100% | Under Budget | -95000
FPC-0524: Daniel U1 Replace Critical AC | FPC - Vicki L. Mack: Vicki | 2094.72 | 0 | 2094.72 | 100% | Over Budget | No |  | 27638 | 34594.72 | 32500 | -4862 | -14.96% | Under Budget | -6956.72
FPC-0525: Daniel 2 Replace Critical AC | FPC - Vicki L. Mack: Vicki | 21216.93 | 0 | 21216.93 | 100% | Over Budget | Yes | Project cash flows advanced | 158443 | 323914.93 | 302698 | -144255 | -47.66% | Under Budget | -165471.93
FPC-0532: Daniel DEGP R/R S1 CONVEYOR GEARBOX | FPC - Vicki L. Mack: Vicki | 0 | 75000 | -75000 | -100% | Under Budget | Yes | Project start date pushed back | 20609 | 0 | 75000 | -54391 | -72.52% | Under Budget | 20609
FPC-0541: Daniel Generator Rotor Rewind | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 5000 | 5000 | 5000 | 0 | 0% | On Budget | 0
FPC-0543: Daniel U1&2 Common CO2 Tank and Piping | FPC - Vicki L. Mack: Vicki | 24674.36 | 0 | 24674.36 | 100% | Over Budget | Yes | 2015 Carry over and expenses for first fill | 25000 | 24674.36 | 0 | 25000 | 100% | Over Budget | 325.64
FPC-0547: Daniel Common New cables for Ash Sluice Motors | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 102168 | 100000 | 100000 | 2168 | 2.168% | Over Budget | 2168
FPC-0551: Daniel Common Emergency Notification System | FPC - Vicki L. Mack: Vicki | 0 | 187502 | -187502 | -100% | Under Budget | Yes | Project removed from MPC's final budget | 0 | -2 | 187500 | -187500 | -100% | Under Budget | 2
FPC-1500: DANIEL-MISC. STEAM PLANT ADDITIONS & | FPC - Vicki L. Mack: Vicki | 406887.25 | 153030 | 253857.25 | 165.9% | Over Budget | Yes | Projects add to MPC's Final final budget | 614415 | 560040.25 | 306183 | 308232 | 100.7% | Over Budget | 54374.75
FPC-1544: DANIEL WATER TREATMENT PLANT CONTROLS | FPC - Vicki L. Mack: Vicki | 82412.31 | 0 | 82412.31 | 100% | Over Budget | Yes | Gulf's cash flows are not in line with MPC's for this project | 370954 | 422412.31 | 340000 | 30954 | 9.104% | Over Budget | -51458.31
FPC-1545: DANIEL 1&2 ASH HANDLING CONTROLS | FPC - Vicki L. Mack: Vicki | 198300.12 | 378000 | -179699.88 | -47.54% | Under Budget | Yes | MPC's OB had project spread evenly throughout year | 451502 | 198300.12 | 378000 | 73502 | 19.44% | Over Budget | 253201.88
FPC-1564: DANIEL 2 CAPITAL VALVE REPLACEMENTS | FPC - Vicki L. Mack: Vicki | 0 | 37500 | -37500 | -100% | Under Budget | Yes | Project removed from MPC's final budget | 0 | 0 | 37500 | -37500 | -100% | Under Budget | 0
FPC-1581: DANIEL !&2 CONVEYOR DIRECT DRIVE GEARBOXES | FPC - Vicki L. Mack: Vicki | 12439.34 | 0 | 12439.34 | 100% | Over Budget | Yes | 2015 carry over | 15000 | 12439.34 | 0 | 15000 | 100% | Over Budget | 2560.66
FPC-1591: DANIEL RELAY MODERNIZATION | FPC - Vicki L. Mack: Vicki | 115507.71 | 150000 | -34492.29 | -22.99% | Under Budget | Yes | MPC Transmission Project | 150000 | 115507.71 | 150000 | 0 | 0% | On Budget | 34492.29
FPC-1800: Daniel Unit 2 Mill Hoist | FPC - Vicki L. Mack: Vicki | 48676.06 | 0 | 48676.06 | 100% | Over Budget | Yes | 2015 Carry Over. 2015 parts from APC invoiced in 2016. | 52000 | 48676.06 | 0 | 52000 | 100% | Over Budget | 3323.94
FPC-1811: DANIEL 1 EXPANSION JOINTS C01693 | FPC - Vicki L. Mack: Vicki | -839.81 | 0 | -839.81 | -100% | Under Budget | No |  | 976 | -839.81 | 0 | 976 | 100% | Over Budget | 1815.81
FPC-1834: DANIEL 1 REWIND GENERATOR | FPC - Vicki L. Mack: Vicki | -0.01 | 0 | -0.01 | 0% | On Budget | No |  | 0 | -0.01 | 0 | 0 | -100% | On Budget | 0.01
FPC-1861: DANIEL 2 FW HEATER 4 LP | FPC - Vicki L. Mack: Vicki | 3274.1 | 59976 | -56701.9 | -94.54% | Under Budget | Yes | Project removed from MPC's final budget | 0 | 63298.1 | 120000 | -120000 | -100% | Under Budget | -63298.1
FPC-1863: DANIEL 1 BOILER FEED PUMPS | FPC - Vicki L. Mack: Vicki | -548.46 | 0 | -548.46 | -100% | Under Budget | No |  | 0 | -548.46 | 0 | 0 | -100% | On Budget | 548.46
FPC-1874: Daniel 1 & 2 Closed Loop Coolers | FPC - Vicki L. Mack: Vicki | -1551.27 | 0 | -1551.27 | -100% | Under Budget | No |  | -1803 | -1551.27 | 0 | -1803 | -100% | Under Budget | -251.73
FPC-1875: Daniel 1 & 2 CPAT Drum Index | FPC - Vicki L. Mack: Vicki | 1718.35 | 0 | 1718.35 | 100% | Over Budget | No |  | 1800 | 1718.35 | 0 | 1800 | 100% | Over Budget | 81.65
FPC-1879: Daniel 1 & 2 Hot Air Dampers and Cold Air Gates | FPC - Vicki L. Mack: Vicki | -503.89 | 0 | -503.89 | -100% | Under Budget | No |  | -586 | -503.89 | 0 | -586 | -100% | Under Budget | -82.11
FPC-1881: Daniel 1 & 2 Intelligent Sootblowing | FPC - Vicki L. Mack: Vicki | 14381.31 | 0 | 14381.31 | 100% | Over Budget | Yes | 2015 Carry over | 14543 | 51881.31 | 37500 | -22957 | -61.22% | Under Budget | -37338.31
FPC-1882: Daniel 1 & 2 Duct Replacement | FPC - Vicki L. Mack: Vicki | 50093.48 | 0 | 50093.48 | 100% | Over Budget | Yes | Project increased in MPC's final budget and pulled forward from fall | 256399 | 135093.48 | 85000 | 171399 | 201.6% | Over Budget | 121305.52
FPC-1884: Daniel 1 & 2 Air Heater Basket Replacement | FPC - Vicki L. Mack: Vicki | 33254.04 | 0 | 33254.04 | 100% | Over Budget | Yes | Timing of engineering costs ahead of original November projection | 72498 | 87742.04 | 54488 | 18010 | 33.05% | Over Budget | -15244.04
FPC-1888: Daniel 1 & 2 Coal Additive System | FPC - Vicki L. Mack: Vicki | 297576.82 | 0 | 297576.82 | 100% | Over Budget | Yes | Project added to MPC's Final OB | 229309 | 297576.82 | 0 | 229309 | 100% | Over Budget | -68267.82
FPC-1891: Daniel Additional Belt Extension | FPC - Vicki L. Mack: Vicki | 141453.17 | 0 | 141453.17 | 100% | Over Budget | Yes | Project added to MPC's Final OB | 145000 | 141453.17 | 0 | 145000 | 100% | Over Budget | 3546.83
FPC-1897: Daniel IK Soot Blower | FPC - Vicki L. Mack: Vicki | -8084.25 | 0 | -8084.25 | -100% | Under Budget | No |  | -9408 | -8084.25 | 0 | -9408 | -100% | Under Budget | -1323.75
Sub-Total Plant Daniel |  | 1330846.34 | 1328456 | 2390.34 | 0.1799% | Over Budget |  |  | 2962576 | 3408759.34 | 3406369 | -443793 | -13.03% | Under Budget | -446183.34
Plant Scherer
FPC-1700: SCHERER DEPOSITORY | FPC - Vicki L. Mack: Vicki | -715973.76 | 0 | -715973.76 | -100% | Under Budget | Yes | Scherer Depository PE represents the billing account for Scherer Cost. No budget dollars | 0 | -2455973.76 | 0 | 0 | -100% | On Budget | 2455973.76
FPC-1710: SCHERER U3 INSTALL TRIPPER FLOOR DUST EXTRACTION EQUIPMENT | FPC - Vicki L. Mack: Vicki | 252.76 | 0 | 252.76 | 100% | Over Budget | No |  | 253 | 252.76 | 0 | 253 | 100% | Over Budget | 0.24
FPC-1716: SCHERER PORTABLE EQUIPMENT | FPC - Vicki L. Mack: Vicki | 0 | 4932 | -4932 | -100% | Under Budget | No |  | 9871 | 4939 | 9871 | 0 | 0% | On Budget | 4932
FPC-1726: SCHERER REPLACE SUPERHEAT PENDANT PLATEN | FPC - Vicki L. Mack: Vicki | 242612.77 | 243800 | -1187.23 | -0.487% | Under Budget | No |  | 262605 | 242612.77 | 243800 | 18805 | 7.713% | Over Budget | 19992.23
FPC-1731: SCHERER NERC CIP V4 IMPLEMETATION | FPC - Vicki L. Mack: Vicki | 2323.02 | 0 | 2323.02 | 100% | Over Budget | No |  | 2323 | 2323.02 | 0 | 2323 | 100% | Over Budget | -0.02
FPC-1746: SCHERER U3 REPLACE REHEAT REPLACEMENT | FPC - Vicki L. Mack: Vicki | -6750 | 12420 | -19170 | -154.3% | Under Budget | Yes | Project was canceled, charges moved to OM. | 0 | -6750 | 12420 | -12420 | -100% | Under Budget | 6750
FPC-1750: SCHERER MISC ADDITIONS AND IMPROVEMENTS | FPC - Vicki L. Mack: Vicki | 101209.97 | 102138 | -928.03 | -0.9086% | Under Budget | No |  | 204361 | 203432.97 | 204361 | 0 | 0% | On Budget | 928.03
FPC-1751: SCHERER 3 TURBINE CROSSOVER EXPANSION JOINT | FPC - Vicki L. Mack: Vicki | 0 | 25070 | -25070 | -100% | Under Budget | Yes | Delay in start of project | 79750 | 0 | 25070 | 54680 | 218.1% | Over Budget | 79750
FPC-1757: SCHERER 3 REPLACE AIR HEATER BASKETS | FPC - Vicki L. Mack: Vicki | 0 | 49680 | -49680 | -100% | Under Budget | Yes | Have not started project yet however do expect to spend budgeted dollars before year end. | 50000 | 0 | 49680 | 320 | 0.6441% | Over Budget | 50000
FPC-1792: Scherer Unit 3 Rewind Main Generator Stator | FPC - Vicki L. Mack: Vicki | 0 | 745200 | -745200 | -100% | Under Budget | Yes | Will spend dollars this year, wating on invoice to come in. | 745200 | 433334 | 745200 | 0 | 0% | On Budget | 311866
FPC-1794: SCHERER 3 & 4 REPLACE 3D FIXED TRIPPER CHUTES | FPC - Vicki L. Mack: Vicki | 7567.99 | 12449 | -4881.01 | -39.21% | Under Budget | No |  | 12568 | 7567.99 | 12449 | 119 | 0.9559% | Over Budget | 5000.01
FPC-6502: Scherer 3 Replace Voltage Regulator | FPC - Vicki L. Mack: Vicki | 5193.4 | 9200 | -4006.6 | -43.55% | Under Budget | No |  | 9200 | 5193.4 | 9200 | 0 | 0% | On Budget | 4006.6
FPC-6505: Scherer - Misc PE for all Rolling Stock | FPC - Vicki L. Mack: Vicki | 42999.32 | 0 | 42999.32 | 100% | Over Budget | Yes | JV'd over from the EC&S Construction Project it was originally on a Common Environmental GWO and now that the project is over this equipment will still be used for the plant but needed to be moved off of the GWO for Environmental and be placed in a Retro Area | 42999 | 42999.32 | 0 | 42999 | 100% | Over Budget | -0.32
FPC-6507: Scherer 3 Replace Condenser Tube | FPC - Vicki L. Mack: Vicki | 244775.73 | 497950 | -253174.27 | -50.84% | Under Budget | Yes | Expect to be on budget by end year | 497950 | 711441.73 | 497950 | 0 | 0% | On Budget | -213491.73
FPC-6508: Scherer 3 & 4 Replace Crusher House MCC U3 & U4 | FPC - Vicki L. Mack: Vicki | 64690.25 | 59110 | 5580.25 | 9.44% | Over Budget | No |  | 122274 | 64690.25 | 59110 | 63164 | 106.9% | Over Budget | 57583.75
FPC-6513: Scherer 3 & 4 Replace and Move Trestle Feeder | FPC - Vicki L. Mack: Vicki | 0 | 62244 | -62244 | -100% | Under Budget | Yes | Budget dollars should be on 6529 PE. Moved 62,244 See below, dollars are on 6529 | 0 | 0 | 62244 | -62244 | -100% | Under Budget | 0
FPC-6520: Scherer 3 Replace Turbine LP Rotor | FPC - Vicki L. Mack: Vicki | 1630274.42 | 3520150 | -1889875.58 | -53.69% | Under Budget | Yes | Progress payments, should be accurate, one progress payment made in 2015 Dec was budgeted for 2016. | 3221311 | 4199719.42 | 3520150 | -298839 | -8.489% | Under Budget | -978408.42
FPC-6528: Scherer 3 Auto Fire Suppression -Turb/Generatr Lube Oil | FPC - Vicki L. Mack: Vicki | 0 | 11500 | -11500 | -100% | Under Budget | Yes | Project still expected to be on budget | 11500 | 0 | 11500 | 0 | 0% | On Budget | 11500
FPC-6529: Scherer 3 & 4 Vibratory Feeders | FPC - Vicki L. Mack: Vicki | 38907.61 | 0 | 38907.61 | 100% | Over Budget | Yes | Budget dollars should be on 6529 PE. Moved 62,244 See above, budget is on 6513 | 62304 | 38907.61 | 0 | 62304 | 100% | Over Budget | 23396.39
FPC-6534: Scherer 3 Replace BFPT Controls | FPC - Vicki L. Mack: Vicki | 0 | 124200 | -124200 | -100% | Under Budget | Yes | Project still expected to be on budget | 124200 | 0 | 124200 | 0 | 0% | On Budget | 124200
FPC-6542: Scherer 3 Replace Polisher Controls | FPC - Vicki L. Mack: Vicki | 0 | 49680 | -49680 | -100% | Under Budget | Yes | Project still planned to be done and on budget | 49680 | 0 | 49680 | 0 | 0% | On Budget | 49680
FPC-6543: Scherer Common U 1-4 Generation Step Up Spare (GSU) | FPC - Vicki L. Mack: Vicki | 0 | 87468 | -87468 | -100% | Under Budget | Yes | Project still expected to be on budget | 171783 | 87532 | 175000 | -3217 | -1.838% | Under Budget | 84251
Sub-Total Plant Scherer |  | 1658083.48 | 5617191 | -3959107.52 | -70.48% | Under Budget |  |  | 5680132 | 3582222.48 | 5811885 | -131753 | -2.267% | Under Budget | 2097909.52
Renewables
FPC-0091: PERDIDO LANDFILL GAS ENERGY | FPC - Vicki L. Mack: Vicki | 0 | 60000 | -60000 | -100% | Under Budget | Yes | No misc projects done this year | 120000 | 60000 | 120000 | 0 | 0% | On Budget | 60000
FPC-0100: Community Solar One | FPC - Vicki L. Mack: Vicki | 0 | 2320000 | -2320000 | -100% | Under Budget | Yes | Project will be done next year | 0 | -106667 | 3000000 | -3000000 | -100% | Under Budget | 106667 | 106667
Sub-Total Renewables |  | 0 | 2380000 | -2380000 | -100% | Under Budget |  |  | 120000 | -46667 | 3120000 | -3000000 | -96.15% | Under Budget | 166667
Sub-Total Power Generation |  | 21387340.27 | 35234656 | -13847315.73 | -39.3% | Under Budget |  |  | 101878885.5 | 97302597.27 | 108547391 | -6668505.5 | -6.143% | Under Budget | 4576288.23
Power Delivery
New Business Distribution
FPC-2550: CUSTOMER METERING | FPC - Paul C. Pratofiorito: Paul | 161652.78 | 586000 | -424347.22 | -72.41% | Under Budget | Yes | Timing: Waiting on Tower infrastructure work. Instructed to spend $200, 000 on RC/DC meters for Customer Service. May be on budget at year end. | 1046000 | 621652.78 | 1046000 | 0 | 0% | On Budget | 424347.22
FPC-2551: DISTRIBUTION TRANSFORMERS | FPC - Paul C. Pratofiorito: Paul | 3162347.73 | 4478000 | -1315652.27 | -29.38% | Under Budget | Yes | Timing: Early in the year. | 8718000 | 8008142.73 | 8718000 | 0 | 0% | On Budget | 709857.27
FPC-2552: NEW BUSINESS - OVERHEAD CONSTRUCTION | FPC - Paul C. Pratofiorito: Paul | 2753945.32 | 3165000 | -411054.68 | -12.99% | Under Budget | Yes | Timing: Early in the year. | 6025000 | 5932695.32 | 6025000 | 0 | 0% | On Budget | 92304.68
FPC-2553: NEW BUSINESS STREET LIGHTS | FPC - Sarah K. Seckinger: Sarah | 76735.95 | 0 | 76735.95 | 100% | Over Budget | Yes | Charges will be moved to 2553 | 76736 | 76735.95 | 0 | 76736 | 100% | Over Budget | 0.05
FPC-2554: NEW BUSINESS - UNDERGROUND CONSTRUCTION | FPC - Paul C. Pratofiorito: Paul | 3792690.78 | 3628000 | 164690.78 | 4.539% | Over Budget | No |  | 7379000 | 7543690.78 | 7379000 | 0 | 0% | On Budget | -164690.78
FPC-2556: PRIVATE STREET & YARD LIGHTS | FPC - Sarah K. Seckinger: Sarah | 2395354.98 | 4744651 | -2349296.02 | -49.51% | Under Budget | Yes | Timing - anticipate ramping up in Fall | 8743806 | 7727843.98 | 8743806 | 0 | 0% | On Budget | 1015962.02 | 1000000
FPC-2559: NEW BUSINESS - METERING ACC. ENCL. EQUIP. & DEVICES | FPC - Paul C. Pratofiorito: Paul | 58206.3 | 77000 | -18793.7 | -24.41% | Under Budget | Yes | Timing: Plan to be on budget at year end. | 149000 | 130206.3 | 149000 | 0 | 0% | On Budget | 18793.7
FPC-4449: Electric Vehicle Charging Stations | FPC - Sarah K. Seckinger: Sarah | 0 | 411750 | -411750 | -100% | Under Budget | Yes | Timing - still in negotiation with DC fast chargers | 823500 | 411750 | 823500 | 0 | 0% | On Budget | 411750
Sub-Total New Business Distribution |  | 12400933.84 | 17090401 | -4689467.16 | -27.44% | Under Budget |  |  | 32961042 | 30452717.84 | 32884306 | 76736 | 0.2334% | Over Budget | 2508324.16
Energy Conservation Cost Recovery
FPC-2558: ADVANCED ENERGY MANAGEMENT (AEM) | FPC - Sarah K. Seckinger: Sarah | 744903.05 | 1153188 | -408284.95 | -35.4% | Under Budget | Yes | Timing | 2107992 | 1699707.05 | 2107992 | 0 | 0% | On Budget | 408284.95
Sub-Total Energy Conservation Cost Recovery |  | 744903.05 | 1153188 | -408284.95 | -35.4% | Under Budget |  |  | 2107992 | 1699707.05 | 2107992 | 0 | 0% | On Budget | 408284.95
Transmission
FPC-2801: TRANS SUB INFRASTRUCTURE PROJECTS | FPC - Melitta Davis: Melitta | 106257.68 | 350000 | -243742.32 | -69.64% | Under Budget | Yes | Budget timing | 850000 | 606257.68 | 850000 | 0 | 0% | On Budget | 243742.32
FPC-2802: TRANS LINE INFRASTRUCTURE PROJECTS | FPC - Melitta Davis: Melitta | 4033056.58 | 2800000 | 1233056.58 | 44.04% | Over Budget | Yes | Project cost higher than expected | 5073927 | 5247341.58 | 5000000 | 73927 | 1.479% | Over Budget | -173414.58
FPC-2803: ALLIGATOR SWAMP SVC AND ASSOCIATED MODIFICATIONS | FPC - Melitta Davis: Melitta | 165193.26 | 0 | 165193.26 | 100% | Over Budget | Yes | unbudgeted project | 245347 | 165193.26 | 0 | 245347 | 100% | Over Budget | 80153.74
FPC-2808: Greenwood - Long Beach | FPC - Melitta Davis: Melitta | 262302.45 | 0 | 262302.45 | 100% | Over Budget | Yes | Work completed sooner than expected | -1620495 | -1937697.55 | -2200000 | 579505 | -100% | Over Budget | 317202.55
FPC-2813: North Brewton - Alligator Swamp New 230 kV Transmission Line | FPC - Melitta Davis: Melitta | 213068.24 | 0 | 213068.24 | 100% | Over Budget | Yes | settlement project | 216659 | 213068.24 | 0 | 216659 | 100% | Over Budget | 3590.76
FPC-2814: LAGUNA BEACH - SANTA ROSA #2 230KV TL | FPC - Melitta Davis: Melitta | 50518.84 | 0 | 50518.84 | 100% | Over Budget | Yes | settlement project | -89481 | 50518.84 | 0 | -89481 | -100% | Under Budget | -139999.84
FPC-2816: Backbone Fiber Project | FPC - Melitta Davis: Melitta | 47198.01 | 358000 | -310801.99 | -86.82% | Under Budget | Yes | Surveys delayed causing a delay in design | 562337 | 244198.01 | 555000 | 7337 | 1.322% | Over Budget | 318138.99
FPC-2821: ALLIGATOR SWAMP 230KV EXPANSION | FPC - Melitta Davis: Melitta | -501.86 | 0 | -501.86 | -100% | Under Budget | No |  | -502 | -501.86 | 0 | -502 | -100% | Under Budget | -0.14
FPC-2822: TRANSMISSION LN SWITCH REPL PROJ | FPC - Melitta Davis: Melitta | 358688.87 | 240000 | 118688.87 | 49.45% | Over Budget | Yes | project design requested | 501608 | 618688.87 | 500000 | 1608 | 0.3216% | Over Budget | -117080.87 | -110000
FPC-2829: Highland City +/- 100 MVAR Static VAR compensator (SVC) | FPC - Melitta Davis: Melitta | 49280.87 | 0 | 49280.87 | 100% | Over Budget | Yes | settlement project | 49281 | 49280.87 | 0 | 49281 | 100% | Over Budget | 0.13
FPC-2830: TRANSMISSION BREAKER REPLACEMENT | FPC - Melitta Davis: Melitta | 257192.44 | 0 | 257192.44 | 100% | Over Budget | Yes | Budget timing | 535634 | 790192.44 | 533000 | 2634 | 0.4942% | Over Budget | -254558.44
FPC-2835: TRANSMISSION CIP COMPLIANCE | FPC - Melitta Davis: Melitta | 134176.18 | 458487 | -324310.82 | -70.74% | Under Budget | Yes | SCS billing | 905711 | 586939.18 | 911250 | -5539 | -0.6078% | Under Budget | 318771.82
FPC-2836: Transmission Cyber and Physical Security (NON-CIP) | FPC - Melitta Davis: Melitta | 353076.09 | 542500 | -189423.91 | -34.92% | Under Budget | Yes | SCS billing | 862579 | 1105576.09 | 1295000 | -432421 | -33.39% | Under Budget | -242997.09
FPC-2841: GUYED Y TOWER ANCHOR REPLACEMENTS | FPC - Melitta Davis: Melitta | 1244974.27 | 520000 | 724974.27 | 139.4% | Over Budget | Yes | PE exception $1M | 1921494 | 2284974.27 | 1000000 | 921494 | 92.15% | Over Budget | -363480.27
FPC-2867: HOLMES CREEK - HIGHLAND CITY 230KV | FPC - Melitta Davis: Melitta | -11320.97 | 0 | -11320.97 | -100% | Under Budget | Yes | settlement project | -11321 | -11320.97 | 0 | -11321 | -100% | Under Budget | -0.03
FPC-2868: Survey and Renewal of Transmission Corridor Leases | FPC - Melitta Davis: Melitta | 1315139.75 | 0 | 1315139.75 | 100% | Over Budget | Yes | Increase in expenditures for Eglin | 1877707 | 1853139.75 | 538000 | 1339707 | 249% | Over Budget | 24567.25
FPC-2881: BARRY-CRIST 230 KV UPGRADE | FPC - Melitta Davis: Melitta | 2115.59 | 143000 | -140884.41 | -98.52% | Under Budget | Yes | design delayed | 187135 | 47615.59 | 188500 | -1365 | -0.7241% | Under Budget | 139519.41
FPC-2901: Crist 115kV Substation Reliability Upgrade | FPC - Melitta Davis: Melitta | 2412580.14 | 1017939 | 1394641.14 | 137% | Over Budget | Yes | Material cost higher than expected | 3218495 | 3178309.14 | 1917000 | 1301495 | 67.89% | Over Budget | 40185.86
FPC-2905: SMITH CONSTRUCTION | FPC - Melitta Davis: Melitta | 122481.82 | 0 | 122481.82 | 100% | Over Budget | Yes | PE exception $1M | 1065204 | 1052160.82 | 0 | 1065204 | 100% | Over Budget | 13043.18
FPC-2906: 115KV LINE RATING INCREASE | FPC - Melitta Davis: Melitta | 29647.8 | 40000 | -10352.2 | -25.88% | Under Budget | Yes | Construction to start in Oct | 634505 | 605647.8 | 616000 | 18505 | 3.004% | Over Budget | 28857.2
FPC-2908: Fiber Replacements | FPC - Melitta Davis: Melitta | 402496.54 | 389500 | 12996.54 | 3.337% | Over Budget | No |  | 938514 | 1075252.54 | 1062256 | -123742 | -11.65% | Under Budget | -136738.54
FPC-2911: SCS Design - Autodesk | FPC - Melitta Davis: Melitta | 64730.14 | 114409 | -49678.86 | -43.42% | Under Budget | Yes | SCS billing | 214791 | 140000.14 | 189679 | 25112 | 13.24% | Over Budget | 74790.86
FPC-2912: Solar | FPC - Melitta Davis: Melitta | -1142381.97 | -131000 | -1011381.97 | -100% | Under Budget | Yes | Billing not occurring as budgeted | -1156455 | -386881.97 | -200500 | -955955 | -100% | Under Budget | -769573.03
FPC-2914: FPC-2914 | FPC - Melitta Davis: Melitta | 14915.02 | 0 | 14915.02 | 100% | Over Budget | Yes | unbudgeted project | 14915 | 14915.02 | 0 | 14915 | 100% | Over Budget | -0.02
FPC-2915: Smith 230-115kV P&C Reliability | FPC - Melitta Davis: Melitta | 0 | 0 | 0 | 0% | On Budget | No |  | 70275 | 70000 | 70000 | 275 | 0.3929% | Over Budget | 275
FPC-2921: FPC-2921 | FPC - Melitta Davis: Melitta | 132840.35 | 0 | 132840.35 | 100% | Over Budget | Yes | PE exception $2M | 1074341 | 132840.35 | 0 | 1074341 | 100% | Over Budget | 941500.65 | 941501
FPC-3401: DIST SUB INFRASTRUCTURE PROJECTS | FPC - Melitta Davis: Melitta | 460579.77 | 487500 | -26920.23 | -5.522% | Under Budget | No |  | 1010028 | 973079.77 | 1000000 | 10028 | 1.003% | Over Budget | 36948.23
FPC-3420: DESTIN 115 12KV RELIABILITY UPGRADE | FPC - Melitta Davis: Melitta | 799451.48 | 58884 | 740567.48 | 1258% | Over Budget | Yes | Timing (material) | 1877525 | 2569911.48 | 1850384 | 27141 | 1.467% | Over Budget | -692386.48
FPC-3421: Munson Rd Substation Conversion | FPC - Melitta Davis: Melitta | 70556.4 | 95000 | -24443.6 | -25.73% | Under Budget | Yes | Pushed project out to start in Sept due to delay receiving FDEP swale exemptio | 2550459 | 2766056.4 | 2790500 | -240041 | -8.602% | Under Budget | -215597.4
FPC-3428: PROACTIVE TRANSFORMER REPLACEMENT | FPC - Melitta Davis: Melitta | 4894.09 | 0 | 4894.09 | 100% | Over Budget | No |  | 4894 | 4894.09 | 0 | 4894 | 100% | Over Budget | -0.09
FPC-3434: ANTOIOCH NEW SUBSTATION | FPC - Melitta Davis: Melitta | 3310648.85 | 2313000 | 997648.85 | 43.13% | Over Budget | Yes | Project cost higher than expected - damaged transformer | 3463202 | 3382648.85 | 2385000 | 1078202 | 45.21% | Over Budget | 80553.15
FPC-3437: HURLBURT 115/12KV SUBSTATION P & C INFRASTRUCTURE UPGRADE | FPC - Melitta Davis: Melitta | 842255.73 | 0 | 842255.73 | 100% | Over Budget | Yes | additional material purchased due to substation break-in | 887743 | 1692255.73 | 850000 | 37743 | 4.44% | Over Budget | -804512.73
FPC-3490: DEVILLERS LOWSIDE BUS STRUCTURE REBUILD | FPC - Melitta Davis: Melitta | 343.89 | 0 | 343.89 | 100% | Over Budget | No |  | 344 | 343.89 | 0 | 344 | 100% | Over Budget | 0.11
FPC-3494: PACE 115/12KV SUBSTATION P & C INFRASTRUCTURE UPGRADE | FPC - Melitta Davis: Melitta | 0 | 0 | 0 | 0% | On Budget | No |  | 115690 | 125000 | 125000 | -9310 | -7.448% | Under Budget | -9310
FPC-3702: CIRCUIT SWITCHER IMP - TS/DS | FPC - Melitta Davis: Melitta | 122834.64 | 0 | 122834.64 | 100% | Over Budget | Yes | Timing | 350086 | 472834.64 | 350000 | 86 | 0.02457% | Over Budget | -122748.64
FPC-3714: P&C INFRASTRUCTURE PROJECTS | FPC - Melitta Davis: Melitta | 250453.3 | 50000 | 200453.3 | 400.9% | Over Budget | Yes | relay failures on the system | 257132 | 300453.3 | 100000 | 157132 | 157.1% | Over Budget | -43321.3
FPC-3735: Ponce and Carryville Conversion to 115kV | FPC - Melitta Davis: Melitta | 2606.41 | 0 | 2606.41 | 100% | Over Budget | No |  | 2608 | 2606.41 | 0 | 2608 | 100% | Over Budget | 1.59
FPC-3742: System Operations Additions and Improvements | FPC - Melitta Davis: Melitta | 11003.05 | 12280 | -1276.95 | -10.4% | Under Budget | No |  | 177005 | 171003.05 | 172280 | 4725 | 2.743% | Over Budget | 6001.95
FPC-3758: FPC-3758 | FPC - Melitta Davis: Melitta | 21032.37 | 0 | 21032.37 | 100% | Over Budget | Yes | PE exception $312k | 327252 | 21032.37 | 0 | 327252 | 100% | Over Budget | 306219.63
FPC-4395: TCC Furniture | FPC - Melitta Davis: Melitta | 0 | 200000 | -200000 | -100% | Under Budget | Yes | Charged to Facilities | 0 | 0 | 200000 | -200000 | -100% | Under Budget | 0
FPC-4400: TRANSMISSION TOOLS AND TEST EQUIPMENT | FPC - Melitta Davis: Melitta | 1741.72 | 150000 | -148258.28 | -98.84% | Under Budget | Yes | Timing | 143040 | 1741.72 | 150000 | -6960 | -4.64% | Under Budget | 141298.28
Sub-Total Transmission |  | 16516127.83 | 10209499 | 6306628.83 | 61.77% | Over Budget |  |  | 29309213 | 30279569.83 | 22798349 | 6510864 | 28.56% | Over Budget | -970356.83
Distribution
FPC-3402: MISC OVERHEAD LINE IMPROVEMENTS | FPC - Paul C. Pratofiorito: Paul | 2172556.27 | 2916000 | -743443.73 | -25.5% | Under Budget | Yes | Timing: Early in the year. Plan to be on Budget at year-end. | 5746000 | 5002556.27 | 5746000 | 0 | 0% | On Budget | 743443.73
FPC-3403: DISTRIBUTION ADDITIONS/RETIREMENTS DUE TO HWY & JOINT USE | FPC - Paul C. Pratofiorito: Paul | 1325008.86 | 358000 | 967008.86 | 270.1% | Over Budget | Yes | Budget Exception Granted: Increased $402k due to DOT's volume change occurring from their new design build requirements. | 1484000 | 2049008.86 | 1082000 | 402000 | 37.15% | Over Budget | -565008.86
FPC-3404: DISTRIBUTION LINE MINOR PROJECTS | FPC - Paul C. Pratofiorito: Paul | 302088.54 | 412000 | -109911.46 | -26.68% | Under Budget | Yes | Timing: Plan to be on budget at year end. | 1046000 | 936088.54 | 1046000 | 0 | 0% | On Budget | 109911.46
FPC-3405: UNDERGROUND SYSTEM ADDITIONS & IMPROVEMENTS | FPC - Paul C. Pratofiorito: Paul | 1251940.22 | 742000 | 509940.22 | 68.73% | Over Budget | Yes | Expenses have been down for two consecutive months. If monthly expenditures remain at the same level as May, we can come in on budget for this PE. | 2750000 | 2985940.22 | 2476000 | 274000 | 11.07% | Over Budget | -235940.22
FPC-3406: DISTRIBUTION UNDERGROUND CONVERSIONS | FPC - Paul C. Pratofiorito: Paul | -97704.03 | 395000 | -492704.03 | -124.7% | Under Budget | Yes | Timing: Plan to be on budget at year-end. Henderson Beach CIAC collected however waiting on customer to complete duct bank before our work begins. Unknown is PCB Segment II conversion CIAC collection | 774000 | 711295.97 | 774000 | 0 | 0% | On Budget | 62704.03
FPC-3407: MISC CAPITAL ACCRUALS | FPC - Paul C. Pratofiorito: Paul | 191992.4 | 0 | 191992.4 | 100% | Over Budget | Yes | This blanket order PE 3407 was set up exclusively to capture monthly entries for Accounts Payable setups and reversals (SOX). Any variance is a timing difference of Accruals setup the previous month. | 0 | 191992.4 | 0 | 0 | -100% | On Budget | -191992.4
FPC-3408: OVERHEAD LINE IMPROVEMENTS - POLE INSPECTION PROGRAM | FPC - Paul C. Pratofiorito: Paul | 700886.25 | 780000 | -79113.75 | -10.14% | Under Budget | Yes | Timing: Early in the year. Pole replacements will ramp up. | 1806000 | 1726886.25 | 1806000 | 0 | 0% | On Budget | 79113.75
FPC-3409: RIGHT OF WAY ACQUISITION | FPC - Paul C. Pratofiorito: Paul | 146564.34 | 354000 | -207435.66 | -58.6% | Under Budget | Yes | Timing. Work recently started on chosen Feeders. Clearing of easements scheduled for fourth quarter. | 708000 | 500564.34 | 708000 | 0 | 0% | On Budget | 207435.66
FPC-3438: NEW DISTRIBUTION FEEDER FOR SUBMARINE CABLE CROSSING | FPC - Paul C. Pratofiorito: Paul | 50691.19 | 0 | 50691.19 | 100% | Over Budget | Yes | Carryover from 2015, plus seagrass mitigation survey, plan, and application requirements. | 55000 | 50691.19 | 0 | 55000 | 100% | Over Budget | 4308.81
FPC-3498: DSCADA MANAGEMENT SYSTEMS - DSCADA | FPC - Paul C. Pratofiorito: Paul | 56581.78 | 0 | 56581.78 | 100% | Over Budget | Yes | TCMS GWO is still under this PE. This is the transition year, with funding from PE 4412. New Budget Request - $200k to integrate Feeder FLA. | 340000 | 56581.78 | 0 | 340000 | 100% | Over Budget | 283418.22
FPC-3499: SO SMART RELIABILITY IMPROVEMENT PROGRAMS | FPC - Paul C. Pratofiorito: Paul | 666098.5 | 803000 | -136901.5 | -17.05% | Under Budget | Yes | Timing, expect to be on budget at year end. | 2043000 | 1906098.5 | 2043000 | 0 | 0% | On Budget | 136901.5
FPC-3500: ASSET MANAGEMENT IMPROVEMENT PROGRAMS | FPC - Paul C. Pratofiorito: Paul | 295369.32 | 749000 | -453630.68 | -60.56% | Under Budget | Yes | PE Reduced to use the funds to Offset other PE's. | 240000 | 985369.32 | 1439000 | -1199000 | -83.32% | Under Budget | -745369.32
FPC-3501: MISC DISTRIBUTION LINES SPECIFIC FEEDER IMPROVEMENTS | FPC - Paul C. Pratofiorito: Paul | 76801.36 | 45000 | 31801.36 | 70.67% | Over Budget | Yes | Reduced $105k to fund a portion of the new General Plant and $13k for Storm Drill | 547000 | 696801.36 | 665000 | -118000 | -17.74% | Under Budget | -149801.36
FPC-3502: MISC DISTRIBUTION SUBSTATION FEEDER RECONFIGURATIONS & UPGRA | FPC - Paul C. Pratofiorito: Paul | 11916.38 | 99000 | -87083.62 | -87.96% | Under Budget | Yes | Reduced to cover overage in PE 3438. Reduced $62 new General Plant. | 130000 | 104916.38 | 192000 | -62000 | -32.29% | Under Budget | 25083.62
FPC-3520: ANTIOCH ROAD SUB NEW FEEDERS | FPC - Paul C. Pratofiorito: Paul | 229410.89 | 400000 | -170589.11 | -42.65% | Under Budget | Yes | Delayed by TBU. Will be Fall 2016 before Dist. Can complete its work. Plan to come under budget $40k at year-end. | 360000 | 229410.89 | 400000 | -40000 | -10% | Under Budget | 130589.11
FPC-3534: EAST BAY 5542 RECONDUCTOR | FPC - Paul C. Pratofiorito: Paul | 279639.62 | 350000 | -70360.38 | -20.1% | Under Budget | Yes | Project in progress. To be completed by end of June. | 350000 | 279639.62 | 350000 | 0 | 0% | On Budget | 70360.38
FPC-3539: HATHAWAY 8682 - GRAND LAGOON BRIDGE CROSSING | FPC - Paul C. Pratofiorito: Paul | 0 | 700000 | -700000 | -100% | Under Budget | Yes | Timing - Bay County permit received on March 8th. Presently working on Environmental permit. | 700000 | 399999 | 700000 | 0 | 0% | On Budget | 300001
FPC-3637: SANTA ROSA ISLAND ENHANCEMENTS | FPC - Paul C. Pratofiorito: Paul | 842675.62 | 972000 | -129324.38 | -13.3% | Under Budget | Yes | Timing, Expect to be on budget by year end | 972000 | 1309341.62 | 972000 | 0 | 0% | On Budget | -337341.62
FPC-3652: STORM HARDENING - OVERHEAD | FPC - Paul C. Pratofiorito: Paul | 500231.95 | 430000 | 70231.95 | 16.33% | Over Budget | Yes | Expect Storm Hardening to be on budget at year end | 1148000 | 1218231.95 | 1148000 | 0 | 0% | On Budget | -70231.95
FPC-3693: DEVILLIERS SUB - NETWORK UPGRADES | FPC - Paul C. Pratofiorito: Paul | 48606.6 | 120000 | -71393.4 | -59.49% | Under Budget | Yes | Timing. Ahead of schedule. Expect to be on budget at year-end. | 125000 | 53606.6 | 125000 | 0 | 0% | On Budget | 71393.4
FPC-3694: Crystal Beach Feeder 8982 Reconductor | FPC - Paul C. Pratofiorito: Paul | 0 | 185000 | -185000 | -100% | Under Budget | Yes | Timing - Waiting on Customer to decide on conversion. | 185000 | 0 | 185000 | 0 | 0% | On Budget | 185000
FPC-3695: Beulah Feeder 5512 & 5522 Reconductor and Reconfiguration | FPC - Paul C. Pratofiorito: Paul | 211542.78 | 150000 | 61542.78 | 41.03% | Over Budget | Yes | Over due to the labor costs and overheads being quite a bit higher than estimated. The total cost should be about $240,000. | 240000 | 211542.78 | 150000 | 90000 | 60% | Over Budget | 28457.22
FPC-3700: SYSTEM REACTIVE CORRECTIVE CAPACITY | FPC - Paul C. Pratofiorito: Paul | 2410209.09 | 743000 | 1667209.09 | 224.4% | Over Budget | Yes | Budget Exception Granted. To cover the scheduled 2016 Comverge Replacement Plan with SO Smart Equipment. Capacitor bank Comverge control paging system, in conjunction with Marketing’s Energy Select Comverge control paging system was retired April 1st. | 1396000 | 3374712.09 | 1434000 | -38000 | -2.65% | Under Budget | -1978712.09 | -1975000
FPC-4301: TOOLS IMPLEMENTS AND TEST EQUIP. | FPC - Paul C. Pratofiorito: Paul | 122412.17 | 101000 | 21412.17 | 21.2% | Over Budget | Yes | Tools received from ordering in January. Will be on budget prior to year end. | 390000 | 411412.17 | 390000 | 0 | 0% | On Budget | -21412.17
FPC-4308: POWER DELIVERY TECHNOLOGY IMPROVEMENTS | FPC - Paul C. Pratofiorito: Paul | 74344.06 | 71000 | 3344.06 | 4.71% | Over Budget | No |  | 225000 | 353344.06 | 350000 | -125000 | -35.71% | Under Budget | -128344.06
FPC-4392: HR - Training Yard Purchases | FPC - Paul C. Pratofiorito: Paul | 28653.62 | 98000 | -69346.38 | -70.76% | Under Budget | Yes | ARMS III has been delayed, with maximum cost expectations of $131k. | 196000 | 126653.62 | 196000 | 0 | 0% | On Budget | 69346.38
FPC-4408: Cyber Security | FPC - Paul C. Pratofiorito: Paul | 27711.64 | 51000 | -23288.36 | -45.66% | Under Budget | Yes | Revised projection is $215k. $67k in SCS charges, and $138k in shared cost from APCO "system" improvements with the Lancope installation | 215000 | 80711.64 | 104000 | 111000 | 106.7% | Over Budget | 134288.36
FPC-4412: DSCADA MANAGEMENT SYSTEMS | FPC - Paul C. Pratofiorito: Paul | 245884.78 | 276000 | -30115.22 | -10.91% | Under Budget | Yes | Timing: Early in the year, 1st PO issued @ $140k after Tax/Stores. TCMS is being funding through PE 3498. New Forecast of costing expected with May reporting. | 389000 | 608884.78 | 639000 | -250000 | -39.12% | Under Budget | -219884.78
FPC-4413: PINE FOREST OFFICE ROADWAY CONSTRUCTION | FPC - Paul C. Pratofiorito: Paul | 0 | 675000 | -675000 | -100% | Under Budget | Yes | project is in planning stage | 2000000 | 1325000 | 2000000 | 0 | 0% | On Budget | 675000
Sub-Total Distribution |  | 12172114.2 | 12975000 | -802885.8 | -6.188% | Under Budget |  |  | 26560000 | 27887282.2 | 27120000 | -560000 | -2.065% | Under Budget | -1327282.2
Sub-Total Power Delivery |  | 41834078.92 | 41428088 | 405990.92 | 0.98% | Over Budget |  |  | 90938247 | 90319276.92 | 84910647 | 6027600 | 7.099% | Over Budget | 618970.08
General Plant
Transportation
FPC-4304: AUTOMOBILES AUTO TRUCKS & EQUIP. | FPC - Allison R. Gillespie: Allison | 497312.99 | 1586000 | -1088687.01 | -68.64% | Under Budget | Yes | Timing. Early in the year. In addition, there is a $33k increase per truck for AWD projected. Addl $250k funded out of PE 3501. | 3559000 | 3241131.99 | 3309000 | 250000 | 7.555% | Over Budget | 317868.01
Sub-Total Transportation |  | 497312.99 | 1586000 | -1088687.01 | -68.64% | Under Budget |  |  | 3559000 | 3241131.99 | 3309000 | 250000 | 7.555% | Over Budget | 317868.01
Telecommunications/Mobile Systems/Data Network
FPC-4305: TELECOMMUNICATIONS WIRELESS SYSTEM ADDITIONS/IMPROVEMENTS | FPC - Shonda L. Lee: Shonda | 0 | 96000 | -96000 | -100% | Under Budget | Yes | No current projects for this PE | 192000 | 96000 | 192000 | 0 | 0% | On Budget | 96000
FPC-4310: VOICE & DATA CONVERGED NETWORK | FPC - Shonda L. Lee: Shonda | 382170.17 | 288000 | 94170.17 | 32.7% | Over Budget | Yes | Timing; will level out over the next few months. | 576000 | 670170.17 | 576000 | 0 | 0% | On Budget | -94170.17
FPC-4311: TRANSPORT NETWORK | FPC - Shonda L. Lee: Shonda | 100033.41 | 230400 | -130366.59 | -56.58% | Under Budget | Yes | Timing; waiting on a decision from the system telecom group on the status of 2 large projects | 768000 | 637633.41 | 768000 | 0 | 0% | On Budget | 130366.59
FPC-4385: FIELD COMPUTING | FPC - Shonda L. Lee: Shonda | 2365.77 | 108360 | -105994.23 | -97.82% | Under Budget | Yes | Timing | 144480 | 38485.77 | 144480 | 0 | 0% | On Budget | 105994.23
FPC-4386: CSS Data Integration Hub Architecture | FPC - David Oerting: Dave | 144316.15 | 63699 | 80617.15 | 126.6% | Over Budget | Yes | The project extended two vendor resources to complete design work for phase IV. This provides production support and takes advantage of the good progress in transitioning applications to the Hub. Expected year-end variance for the Hub is 115K. Other IT existing capital budgets are being explored as a means for off-setting this overrun; should have more information about the potential off-set by the end of July. | 242400 | 208017.15 | 127400 | 115000 | 90.27% | Over Budget | 34382.85
FPC-4410: Long Term Evolution (LTE) | FPC - Paul C. Pratofiorito: Paul | 469729.93 | 754000 | -284270.07 | -37.7% | Under Budget | Yes | Timing… On track per SCS who is coordinating this effort. | 1500000 | 1367529.93 | 1500000 | 0 | 0% | On Budget | 132470.07
FPC-4417: IT Cyber Security Software | FPC - Shonda L. Lee: Shonda | 93958.47 | 199998 | -106039.53 | -53.02% | Under Budget | Yes | Double accrual by SCS at YE created an under-budget variance; waiting on a decision from IT Security to determine if some of the 2016 work will carry-over to 2017 | 400000 | 293960.47 | 400000 | 0 | 0% | On Budget | 106039.53
FPC-4486: On Line Customer Care | FPC - David Oerting: Dave | 263128.69 | 199920 | 63208.69 | 31.62% | Over Budget | Yes | The primary reason for the overrun is development costs associated with the project, due to enhancements that were not included in the initial estimate from IT. While the O&M costs are higher YTD than what was loaded into the 2016 budget, they still remain within the range of the original project forecasts. The mid-point of the forecasted range is what was loaded into the 2016 budget. The OCC Evolution Oversight and Project Team is actively managing and evaluating the budget, scope, schedule and acting upon project efficiencies. The Project Sponsor has reviewed the budget variance with the Call Center Managers and the System Customer Leadership Team and is scheduled to review with the System Customer Council in July. At this time, we don’t have a year-end projection that is different from the original $400k. | 400000 | 463208.69 | 400000 | 0 | 0% | On Budget | -63208.69
FPC-4586: Customer Kiosks | FPC - David Oerting: Dave | 0 | 500000 | -500000 | -100% | Under Budget | Yes | Delay in purchase of kiosks; expect to implement in Q4. | 500000 | 333332 | 500000 | 0 | 0% | On Budget | 166668
Sub-Total Telecommunications/Mobile Systems/Data Network |  | 1455702.59 | 2440377 | -984674.41 | -40.35% | Under Budget |  |  | 4722880 | 4108337.59 | 4607880 | 115000 | 2.496% | Over Budget | 614542.41
Accounting
FPC-4376: Maximo/Oracle/Powerplant Upgrades | FPC - Carol Stevens: Carol | 0.01 | 59904 | -59903.99 | -100% | Under Budget | Yes | Timing - Powerplant upgrade will start later this year and will be on budget | 119924 | 60020.01 | 119924 | 0 | 0% | On Budget | 59903.99
Sub-Total Accounting |  | 0.01 | 59904 | -59903.99 | -100% | Under Budget |  |  | 119924 | 60020.01 | 119924 | 0 | 0% | On Budget | 59903.99
Corporate Services
FPC-4300: OFFICE FURNITURE & MECHANICAL EQUIP. | FPC - Corporate Services: Shirley | 363212.39 | 202840 | 160372.39 | 79.06% | Over Budget | Yes | Overage offset by other dept PE budgets | 528656 | 485212.39 | 324840 | 203816 | 62.74% | Over Budget | 43443.61
FPC-4302: MISC. BUILDINGS LAND AND EQUIP. | FPC - Corporate Services: Shirley | 251134.83 | 251200 | -65.17 | -0.02594% | Under Budget | No |  | 762850 | 738097.83 | 447000 | 315850 | 70.66% | Over Budget | 24752.17 | 9362
FPC-4303: SECURITY EQUIPMENT | FPC - Corporate Services: Shirley | 56511.07 | 81792 | -25280.93 | -30.91% | Under Budget | Yes | Offset by PE3501 & PE4300 | 222503 | 159311.07 | 184592 | 37911 | 20.54% | Over Budget | 63191.93
FPC-4306: AUDIO & VISUAL EQUIPMENT | FPC - Corporate Services: Shirley | 33384 | 49680 | -16296 | -32.8% | Under Budget | Yes | Offset by PE3501 | 63180 | 33384 | 49680 | 13500 | 27.17% | Over Budget | 29796
FPC-4370: PRINTSHOP EQUIP | FPC - Corporate Services: Shirley | 2981.9 | 24840 | -21858.1 | -88% | Under Budget | Yes | Difference trsf to PE4300 | 16928 | 2981.9 | 24840 | -7912 | -31.85% | Under Budget | 13946.1
FPC-4387: Defuniak Springs Roof | FPC - Corporate Services: Shirley | 55288.87 | 327000 | -271711.13 | -83.09% | Under Budget | Yes | Bid came in under budget | 55289 | 55288.87 | 327000 | -271711 | -83.09% | Under Budget | 0.13
FPC-4398: PANAMA CITY VECHICLE MAINT FACILITY | FPC - Corporate Services: Shirley | 33938.44 | 1600000 | -1566061.56 | -97.88% | Under Budget | Yes | Rec'd approval to begin in May 2016 | 165000 | 257688.44 | 3500000 | -3335000 | -95.29% | Under Budget | -92688.44
FPC-4399: PENS DISTRICT-CONSOL CUST SVC FACIL | FPC - Corporate Services: Shirley | 0 | 4970000 | -4970000 | -100% | Under Budget | Yes | Project not started due to non-approval by upper mgmt | 0 | 136250 | 8200000 | -8200000 | -100% | Under Budget | -136250 | -136250
FPC-4406: Panama City Admin Chiller | FPC - Corporate Services: Shirley | 135149.1 | 150000 | -14850.9 | -9.901% | Under Budget | No |  | 135149 | 135149.1 | 150000 | -14851 | -9.901% | Under Budget | -0.1
FPC-4407: GEN WHSE CONVERGE ROOF | FPC - Corporate Services: Shirley | 0 | 72000 | -72000 | -100% | Under Budget | Yes | Delayed for two months due to contractor's schedule | 45000 | 0 | 72000 | -27000 | -37.5% | Under Budget | 45000
FPC-4411: LAND PURCHASE IN CRESTVIEW | FPC - Corporate Services: Shirley | -665.46 | 0 | -665.46 | -100% | Under Budget | No |  | -665 | -665.46 | 0 | -665 | -100% | Under Budget | 0.46
FPC-4414: FPC-4414 | FPC - Corporate Services: Shirley | 1365.5 | 0 | 1365.5 | 100% | Over Budget | No |  | -1366 | 1365.5 | 0 | -1366 | -100% | Under Budget | -2731.5
FPC-4415: FPC-4415 | FPC - Corporate Services: Shirley | 12318.57 | 0 | 12318.57 | 100% | Over Budget | Yes | Offset in part by other dept PE3502 | 177000 | 12318.57 | 0 | 177000 | 100% | Over Budget | 164681.43
FPC-4419: FPC-4419 | FPC - Corporate Services: Shirley | 62525.2 | 0 | 62525.2 | 100% | Over Budget | Yes | Offset in part by other dept PE4344 & 3501 | 169000 | 62525.2 | 0 | 169000 | 100% | Over Budget | 106474.8
Sub-Total Corporate Services |  | 1007144.41 | 7729352 | -6722207.59 | -86.97% | Under Budget |  |  | 2338524 | 2078907.41 | 13279952 | -10941428 | -82.39% | Under Budget | 259616.59
T&D Warehouse Equipment Replacement
FPC-4344: T&D WAREHOUSE EQUIPMENT REPLACEMENT | FPC - Beverly D. Day: Beverly | 0 | 147000 | -147000 | -100% | Under Budget | Yes | $100K going to help facilities pay for the General Warehouse renov | 47000 | 0 | 147000 | -100000 | -68.03% | Under Budget | 47000
Sub-Total T&D Warehouse Equipment Replacement |  | 0 | 147000 | -147000 | -100% | Under Budget |  |  | 47000 | 0 | 147000 | -100000 | -68.03% | Under Budget | 47000
Sub-Total General Plant |  | 2960160 | 11962633 | -9002473 | -75.25% | Under Budget |  |  | 10787328 | 9488397 | 21463756 | -10676428 | -49.74% | Under Budget | 1298931
Non-Utility
Non-Utility
FPC-4999: NEW PRODUCTS AND SERVICES | FPC - Sarah K. Seckinger: Sarah | 124751.12 | 110022 | 14729.12 | 13.39% | Over Budget | Yes | Timing | 494664 | 509393.12 | 494664 | 0 | 0% | On Budget | -14729.12
Sub-Total Non-Utility |  | 124751.12 | 110022 | 14729.12 | 13.39% | Over Budget |  |  | 494664 | 509393.12 | 494664 | 0 | 0% | On Budget | -14729.12
Sub-Total Non-Utility |  | 124751.12 | 110022 | 14729.12 | 13.39% | Over Budget |  |  | 494664 | 509393.12 | 494664 | 0 | 0% | On Budget | -14729.12
Uncategorized
Uncategorized
FPC-4785: FPC-4785 | FPC - David Oerting: Dave | 21907.48 | 0 | 21907.48 | 100% | Over Budget |  |  | 21907.48 | 21907.48 | 0 | 21907.48 | 100% | Over Budget | 0
FPC-4790: FPC-4790 | FPC - David Oerting: Dave | 11167.99 | 0 | 11167.99 | 100% | Over Budget |  |  | 11167.99 | 11167.99 | 0 | 11167.99 | 100% | Over Budget | 0
Sub-Total Uncategorized |  | 33075.47 | 0 | 33075.47 | 100% | Over Budget |  |  | 33075.47 | 33075.47 | 0 | 33075.47 | 100% | Over Budget | 0
Sub-Total Uncategorized |  | 33075.47 | 0 | 33075.47 | 100% | Over Budget |  |  | 33075.47 | 33075.47 | 0 | 33075.47 | 100% | Over Budget | 0
Total |  | 66339405.78 | 88735399 | -22395993.22 | -25.24% | Under Budget |  |  | 204132199.97 | 197652739.78 | 215416458 | -11284258.03 | -5.238% | Under Budget | 6479460.19 | 6479460
| Sch 73 | 66214654.66 | 88735399
| Non-Utility Reconciling item | 124751.12 | 0
| Adjusted Total | 66339405.78 | 88735399
| Above - per UI | 66339405.78 | 88735399
| Difference | 0 | 0

## Scenario Data
Scenario Data
Scenario | CF Gulf - 2016 Official Budget - Live Reforecast
Software Release | 10.05.1
Version ID | 1
Scenario Comments
Date & Time of Shared Run | Never run
Date & Time Exported | 07/09/2016 14:24:49
Case List | [Logic, CF Actuals - FPC, Empty Tree Case: Admin lock, Structure, CF Permanent, CF PowerPlant - GULF, CF Budworks - GULF - 2016 Official Budget - Live Reforecast, CF Temporary - GULF - 2016 Official Budget - Live Reforecast, CF Environmental - GULF - 2016 Official Budget - Live Reforecast, ¦Blank Data¦: Admin lock, CF Data - GULF - 2016 Official Budget - Live Reforecast]
Start Year | 2015
Actuals Through | 06/2016
Years to Run/Run Monthly | 11 (Monthly: 11)
Scenario Type & User-Defined Scenario Type | Budget
Report Data
CAPEX by Bus Unit / BU Detail / PE: Admin lock
Sequence Set | Capital Sequence: Admin lock
View Name | CF Capital Expenditures by Business Unit: Admin lock
Dataset/Calc | CF Capital Expenditures by Business Unit
Row Headers | Project Class -> Business Unit of Project's Project -> Business Unit Class,Project Class -> Business Unit Detail of Project's Project -> Business Unit Class,Imported: Project -> PE of Project
Column Headers | Year 1 YTD-Jun, Year 1 Annual,User Specified Scenario List
Time Setting
Filters | View filter is CF Project Amount Type = Cash, CIAC, AFUDC Debt & Equity CF Project Amount Type = Cash, CIAC, AFUDC Debt & Equity