## CAPEX_by_Bus_Unit_BU_Detail_PE
CAPEX by Bus Unit / BU Detail / PE: Admin lock | PE -> Budget Contact | a-YTD-Sep - 2016 | [6 empty] | 2016
|  | CF Gulf - 2016 Official Budget - Live Reforecast | (VID:20160325) CF Gulf - 2016 Official Budget (Preserved) | Dif. (VID:20160325) CF Gulf - 2016 Official Budget (Preserved) | % Dif. (VID:20160325) CF Gulf - 2016 Official Budget (Preserved) |  |  |  |  | CF Gulf - 2016 Official Budget - Live Reforecast | (VID:20160325) CF Gulf - 2016 Official Budget (Preserved) | Dif. (VID:20160325) CF Gulf - 2016 Official Budget (Preserved) | % Dif. (VID:20160325) CF Gulf - 2016 Official Budget (Preserved)
2016-09-01 | Pointer to Budget Contact | YTD Actual | YTD Budget | YTD Variance ($) | YTD Variance (%) | YTD Over/Under Budget | Explanation Required? | YTD Explanation | Year-End Projection | Year-End Prior Projection | Original Budget | Year-End Variance ($) | Year-End Variance (%) | Year-End Over/Under Budget | YE Projection - YE Calculated | Reforecast PEs
Power Generation
Co Generation
FPC-0040: Co-Generation Misc Projects | FPC - Vicki L. Mack: Vicki | 0 | 750000 | -750000 | -100% | Under Budget | Yes | Contract not been completed. | 750000 | 187500 | 1500000 | -750000 | -50% | Under Budget | 562500 | 560000
Sub-Total Co Generation |  | 0 | 750000 | -750000 | -100% | Under Budget |  |  | 750000 | 187500 | 1500000 | -750000 | -50% | Under Budget | 562500
Environmental Cost Recovery Clause
FPC-0404: FPC-0404 | FPC - Vicki L. Mack: Vicki | 91730.35 | 0 | 91730.35 | 100% | Over Budget | Yes | 2015 Carryover: unbudgeted expenses for installation of Smith Plant Monitoring Wells | 91730 | 91730.35 | 0 | 91730 | 100% | Over Budget | -0.35
FPC-0406: ECRC - LAND - SMITH CCR WASTE WATER MANAGEMENT | FPC - Vicki L. Mack: Vicki | 0 | 2801250 | -2801250 | -100% | Under Budget | Yes | Duplicate with PE 1641 | 0 | 3750 | 3750000 | -3750000 | -100% | Under Budget | -3750
FPC-0412: ECRC-SMITH DUST MITIGATION WATER TRUCK | FPC - Vicki L. Mack: Vicki | 147165.13 | 100000 | 47165.13 | 47.17% | Over Budget | Yes | Cost of equipment higher than budget estimate | 147165 | 147165.13 | 100000 | 47165 | 47.16% | Over Budget | -0.13
FPC-0514: ECRC Daniel -Water -Ground Water Well | FPC - Vicki L. Mack: Vicki | 12618.02 | 0 | 12618.02 | 100% | Over Budget | Yes | carryover | 12618 | 12618.02 | 0 | 12618 | 100% | Over Budget | -0.02
FPC-1031: ECRC-AIR-CRIST 7 SCR CATALYST REPLACEMENT | FPC - Vicki L. Mack: Vicki | 594693.32 | 228723 | 365970.32 | 160% | Over Budget | Yes | Project started earlier than budgeted to be completed during outage in fall | 945000 | 972307.32 | 894961 | 50039 | 5.591% | Over Budget | -27307.32
FPC-1038: ECRC-AIR-CRIST 6 UPGR PRECIP | FPC - Vicki L. Mack: Vicki | -15710.7 | 0 | -15710.7 | -100% | Under Budget | Yes | controls upgrade, journaled from retrofit | -15711 | -15710.7 | 0 | -15711 | -100% | Under Budget | -0.3
FPC-1060: ECRC-AIR-CRIST 7 FGAS MONITORS | FPC - Vicki L. Mack: Vicki | 0 | 11500 | -11500 | -100% | Under Budget | Yes | not completing | 0 | 34500 | 46000 | -46000 | -100% | Under Budget | -34500
FPC-1158: ECRC-AIR-CRIST 7 SCR MISC | FPC - Vicki L. Mack: Vicki | 927.94 | 0 | 927.94 | 100% | Over Budget | No |  | 928 | 927.94 | 0 | 928 | 100% | Over Budget | 0.06
FPC-1193: ECRC-WATER-CRIST 4-7 LOW VOLUME WASTE WATER TREATMENT | FPC - Vicki L. Mack: Vicki | 1509539.68 | 2257200 | -747660.32 | -33.12% | Under Budget | Yes | multi-year project, dollars pushed into 2017, underruns used to cover PE 1234 | 2500000 | 2495271.68 | 3009600 | -509600 | -16.93% | Under Budget | 4728.32
FPC-1199: ECRC-AIR-CRIST U7 SCR PRECIP RELOCAT | FPC - Vicki L. Mack: Vicki | 36295.39 | 18750 | 17545.39 | 93.58% | Over Budget | Yes | controls upgrade, journaled from retrofit | 36295 | 42545.39 | 25000 | 11295 | 45.18% | Over Budget | -6250.39
FPC-1222: ECRC-AIR-CRIST - SCRUBBER | FPC - Vicki L. Mack: Vicki | 2057201.44 | 2103893 | -46691.56 | -2.219% | Under Budget | No |  | 6339353 | 4839437.44 | 5573250 | 766103 | 13.75% | Over Budget | 1499915.56 | 1500000
FPC-1233: ECRC-AIR-CRIST SCRUBBER MISCELLANEOUS | FPC - Vicki L. Mack: Vicki | 447344.77 | 0 | 447344.77 | 100% | Over Budget | Yes | carryover | 451446 | 447344.77 | 0 | 451446 | 100% | Over Budget | 4101.23
FPC-1234: ECRC-AIR-CRIST U7 LOW NOX BURNER REPLACEMENT | FPC - Vicki L. Mack: Vicki | 282951.94 | 0 | 282951.94 | 100% | Over Budget | Yes | PE approval letter (offset to PE 1288 and 1912) | 1555000 | 1594952.94 | 0 | 1555000 | 100% | Over Budget | -39952.94
FPC-1236: ECRC-AIR-CRIST U7 BURNER CONTROLS | FPC - Vicki L. Mack: Vicki | -59972.69 | 0 | -59972.69 | -100% | Under Budget | Yes | controls upgrade, journaled from retrofit | -59973 | -59972.69 | 0 | -59973 | -100% | Under Budget | -0.31
FPC-1242: ECRC-AIR-CRIST U6 LOW NOX BURNERS | FPC - Vicki L. Mack: Vicki | -62310.83 | 0 | -62310.83 | -100% | Under Budget | Yes | controls upgrade, journaled from retrofit | -62311 | -62310.83 | 0 | -62311 | -100% | Under Budget | -0.17
FPC-1279: ECRC-AIR-CRIST U6 CONTROLS - SCR & ID FANS | FPC - Vicki L. Mack: Vicki | -33247.49 | 8250 | -41497.49 | -503% | Under Budget | Yes | controls upgrade, journaled from retrofit | -33247 | -30497.49 | 11000 | -44247 | -402.2% | Under Budget | -2749.51
FPC-1287: ECRC-AIR-CRIST 4-6 NOX REDUCTION - DEPR - (SNCR) | FPC - Vicki L. Mack: Vicki | 534358.39 | 652378 | -118019.61 | -18.09% | Under Budget | Yes | underbudget on flame scanners | 550000 | 548906.39 | 655500 | -105500 | -16.09% | Under Budget | 1093.61
FPC-1288: ECRC-AIR-CRIST-CONSTRUCT GYPSUM STORAGE CELL NO. 1 | FPC - Vicki L. Mack: Vicki | 84058.83 | 584850 | -500791.17 | -85.63% | Under Budget | Yes | underruns used to cover PE 1234 | 151822 | 373454.83 | 1681246 | -1529424 | -90.97% | Under Budget | -221632.83
FPC-1517: ECRC - AIR- DANIEL BROMINE INJECTION | FPC - Vicki L. Mack: Vicki | -16027.29 | 0 | -16027.29 | -100% | Under Budget | Yes | carryover | 20000 | -16027.29 | 0 | 20000 | 100% | Over Budget | 36027.29
FPC-1551: ECRC-AIR-DANIEL 1 & 2 SCRUBBER | FPC - Vicki L. Mack: Vicki | 2768527.44 | 3095703 | -327175.56 | -10.57% | Under Budget | Yes | Paving Budget started earlier than currernt plan | 4006645 | 3625290.44 | 3095703 | 910942 | 29.43% | Over Budget | 381354.56
FPC-1601: ECRC-WATER-SMITH RECLAIMED WATER PROJECT UNIT 3 | FPC - Vicki L. Mack: Vicki | 1585329.26 | 340807 | 1244522.26 | 365.2% | Over Budget | Yes | 2015 Carryover. Unbudgeted contractor expenses on project to date. Job ongoing | 2500000 | 2084022.26 | 340807 | 2159193 | 633.6% | Over Budget | 415977.74 | 415000
FPC-1641: ECRC - Smith 1 & 2 Cross Media Retrofit | FPC - Vicki L. Mack: Vicki | 0 | 2801250 | -2801250 | -100% | Under Budget | Yes | Job will not start in 2016 per Environmental Affairs | 0 | 0 | 3750000 | -3750000 | -100% | Under Budget | 0
FPC-1809: ECRC -AIR-DANIEL 1 & 2 ACTIVATED CARBON INJECTION C01767 | FPC - Vicki L. Mack: Vicki | -31396.52 | 782117 | -813513.52 | -104% | Under Budget | Yes | Dec accruals .. Project pushed out | 584960 | 241331.48 | 782117 | -197157 | -25.21% | Under Budget | 343628.52 | 344000
FPC-1909: ECRC-AIR-CIRST MISC SCR COMMON | FPC - Vicki L. Mack: Vicki | 30149.68 | 37494 | -7344.32 | -19.59% | Under Budget | No |  | 50000 | 42655.68 | 50000 | 0 | 0% | On Budget | 7344.32
FPC-1912: ECRC-AIR-CRIST U4-7 DRY BOTTOM ASH | FPC - Vicki L. Mack: Vicki | 388436.41 | 1875006 | -1486569.59 | -79.28% | Under Budget | Yes | EWO P00857 setup to collect prelim charges to determine if we proceed with project | 2100000 | 1783764.41 | 2500000 | -400000 | -16% | Under Budget | 316235.59 | 316000
FPC-1997: ECRC-LAND-CRIST DISPOSAL OF COAL COMBUSTION RESIDUALS (CCR) | FPC - Vicki L. Mack: Vicki | 181069.51 | 0 | 181069.51 | 100% | Over Budget | Yes | carryover | 181070 | 181069.51 | 0 | 181070 | 100% | Over Budget | 0.49
Sub-Total Environmental Cost Recovery Clause |  | 10533731.98 | 17699171 | -7165439.02 | -40.48% | Under Budget |  |  | 22052790 | 19378526.98 | 26265184 | -4212394 | -16.04% | Under Budget | 2674263.02
Environmental (Non-Clause)
FPC-0501: Envir Daniel Unit 1 Pyrite Hoppers/Piping Valves | FPC - Vicki L. Mack: Vicki | -876.41 | 0 | -876.41 | -100% | Under Budget | No |  | -1019 | -876.41 | 0 | -1019 | -100% | Under Budget | -142.59
FPC-1033: ENVIR - WASTE - CRIST FLY ASH LANDFILL STORAGE CELL CAPPING | FPC - Vicki L. Mack: Vicki | 0 | 393588 | -393588 | -100% | Under Budget | Yes | Not getting done this year. Dollars will offset PE 1220 | 0 | 54 | 525000 | -525000 | -100% | Under Budget | -54
FPC-1220: ENVIR-WATER-CRIST GOVERNORS ISLAND HEADWALL | FPC - Vicki L. Mack: Vicki | 4866762.58 | 0 | 4866762.58 | 100% | Over Budget | Yes | PE Approval Letter | 8355000 | 7448992.58 | 0 | 8355000 | 100% | Over Budget | 906007.42 | 906007
FPC-1253: ENVIR-WASTE- CRIST-FLY ASH LANDFILL STORAGE CELL DEVELOPMENT | FPC - Vicki L. Mack: Vicki | 41934.13 | 749700 | -707765.87 | -94.41% | Under Budget | Yes | Project not getting done this year except for $40K added to scope. Other dollars to offset PE 1220 | 42934 | 42232.13 | 1000000 | -957066 | -95.71% | Under Budget | 701.87
FPC-1613: ENVIR-WASTE-SMITH CAP ASH LANDFILL CELLS | FPC - Vicki L. Mack: Vicki | 25583.72 | 0 | 25583.72 | 100% | Over Budget | Yes | Unexpected corporate overhead adjustments (in August) to clear PE 4790 per Karen Grove - this is a one time adjustment that impacted multiple PEs in Gulf - JV PLT-20185 | 25584 | 25583.72 | 0 | 25584 | 100% | Over Budget | 0.28
FPC-1701: ENVIR - AIR - SCHERER 3 -MISC ENVIRONMENTAL PROJECTS | FPC - Vicki L. Mack: Vicki | 34926.35 | 77769 | -42842.65 | -55.09% | Under Budget | Yes | Timing. Dollars will be spent | 103730 | 60887.35 | 103730 | 0 | 0% | On Budget | 42842.65
FPC-1727: ENVIR-AIR-SCHERER SELECTIVE CAYALYTIC REDUCT (SCR) | FPC - Vicki L. Mack: Vicki | -25698.39 | 0 | -25698.39 | -100% | Under Budget | Yes | E&CS True Up | -25698 | -25698.39 | 0 | -25698 | -100% | Under Budget | 0.39
FPC-1728: ENVIR-AIR-SCHERER SCRUBBER | FPC - Vicki L. Mack: Vicki | -283663.89 | 0 | -283663.89 | -100% | Under Budget | Yes | E&CS True Up | -284063 | -283663.89 | 0 | -284063 | -100% | Under Budget | -399.11
FPC-1729: FPC-1729 | FPC - Vicki L. Mack: Vicki | 38617.19 | 0 | 38617.19 | 100% | Over Budget | Yes | carryover | 38617 | 38617.19 | 0 | 38617 | 100% | Over Budget | -0.19
FPC-1755: ENVIR SCHERER-AIR-HG/PM CEMS | FPC - Vicki L. Mack: Vicki | -0.05 | 0 | -0.05 | 0% | On Budget | No |  | 0 | -0.05 | 0 | 0 | -100% | On Budget | 0.05
FPC-1762: ENVIR - Air- Scherer 3 Bromine Injection | FPC - Vicki L. Mack: Vicki | 0 | 837000 | -837000 | -100% | Under Budget | Yes | Project not getting done this year | 0 | 0 | 1116000 | -1116000 | -100% | Under Budget | 0
FPC-1778: ENVIR - SCHERER - ENVIRONMENTAL SITE PLAN | FPC - Vicki L. Mack: Vicki | -118352.23 | 0 | -118352.23 | -100% | Under Budget | Yes | E&CS True Up | -118352 | -118352.23 | 0 | -118352 | -100% | Under Budget | 0.23
FPC-1791: FPC-1791 | FPC - Vicki L. Mack: Vicki | -20664.9 | 0 | -20664.9 | -100% | Under Budget | Yes | E&CS True Up | -20665 | -20664.9 | 0 | -20665 | -100% | Under Budget | -0.1
FPC-1798: ENVIR SCHERER 3 SCR CATALYST REPLACEMENT | FPC - Vicki L. Mack: Vicki | 0 | 341780 | -341780 | -100% | Under Budget | Yes | GWO written. Project late getting started | 341780 | 256500 | 341780 | 0 | 0% | On Budget | 85280
FPC-1878: Environ - Daniel 1 & 2 Dry Ash Equipment | FPC - Vicki L. Mack: Vicki | 23115.51 | 0 | 23115.51 | 100% | Over Budget | Yes | SCS charges | 23237 | 23115.51 | 0 | 23237 | 100% | Over Budget | 121.49
FPC-6756: Envir - Scherer 3 -LAND CCR ASH MANAGEMENT | FPC - Vicki L. Mack: Vicki | 71405.48 | 238185 | -166779.52 | -70.02% | Under Budget | Yes | late getting started | 316875 | 158156.48 | 317576 | -701 | -0.2207% | Under Budget | 158718.52
FPC-6757: Envir - Scherer 3 New Landfill - Phase 1 | FPC - Vicki L. Mack: Vicki | 153706.62 | 150021 | 3685.62 | 2.457% | Over Budget | No |  | 350856 | 203713.62 | 200028 | 150828 | 75.4% | Over Budget | 147142.38
FPC-6765: Envir - Scherer CCR Ground Water Monitoring |  |  |  |  | 0% | On Budget |  |  | 70000 |  |  | 70000 | 100% | Over Budget | 70000 | 70000
FPC-6759: Envir - Scherer - Land- CCR WW Management | FPC - Vicki L. Mack: Vicki | 55706 | 117567 | -61861 | -52.62% | Under Budget | Yes | late getting started | 156735 | 94895 | 156756 | -21 | -0.0134% | Under Budget | 61840
Sub-Total Environmental (Non-Clause) |  | 4862501.71 | 2905610 | 1956891.71 | 67.35% | Over Budget |  |  | 9375551 | 7903491.71 | 3760870 | 5614681 | 149.3% | Over Budget | 1472059.29
Plant Crist
FPC-0803: Crist U 7 BFP Controls Replacement | FPC - Vicki L. Mack: Vicki | 611870.36 | 100000 | 511870.36 | 511.9% | Over Budget | Yes | Project moved forward. Scope increased | 1166250 | 1378120.36 | 866250 | 300000 | 34.63% | Over Budget | -211870.36
FPC-0804: Crist Unit 7 BFPT Overspeed Bolt Replacement | FPC - Vicki L. Mack: Vicki | 0 | 294005 | -294005 | -100% | Under Budget | Yes | Project combined with PE0803 | 0 | 62970 | 890925 | -890925 | -100% | Under Budget | -62970
FPC-0805: Crist U7 Main Turbine Overspeed Bolt Replacement | FPC - Vicki L. Mack: Vicki | 572612.67 | 261608 | 311004.67 | 118.9% | Over Budget | Yes | Project pushed forward | 900000 | 907090.67 | 792750 | 107250 | 13.53% | Over Budget | -7090.67
FPC-0806: Crist U6 BFPT Overspeed Bolt Replacement | FPC - Vicki L. Mack: Vicki | 209993.68 | 92533 | 117460.68 | 126.9% | Over Budget | Yes | Project pushed forward | 378562 | 397863.68 | 280403 | 98159 | 35.01% | Over Budget | -19301.68
FPC-0807: Crist U6 Main Turbine Overspeed Bolt Replacement | FPC - Vicki L. Mack: Vicki | 44659.2 | 110230 | -65570.8 | -59.49% | Under Budget | Yes | Less will be spent this year . Dollars moved to 2017 | 128816 | 268460.2 | 334031 | -205215 | -61.44% | Under Budget | -139644.2
FPC-0808: Crist U7 Airflow Transmitter (Kurz) Replacement | FPC - Vicki L. Mack: Vicki | 206631.9 | 372500 | -165868.1 | -44.53% | Under Budget | Yes | pushed to end of year | 399000 | 233131.9 | 399000 | 0 | 0% | On Budget | 165868.1
FPC-0809: Crist A Flyash Compressor | FPC - Vicki L. Mack: Vicki | 0 | 68880 | -68880 | -100% | Under Budget | Yes | Combined with PE 0810. Starting later in year | 166614 | 0 | 68880 | 97734 | 141.9% | Over Budget | 166614
FPC-0810: Crist B Flyash Compressor | FPC - Vicki L. Mack: Vicki | 0 | 68880 | -68880 | -100% | Under Budget | Yes | Combined with PE 0809 | 0 | 0 | 68880 | -68880 | -100% | Under Budget | 0
FPC-0812: Crist U4 Turbine Water Induction Protection (TWIP) | FPC - Vicki L. Mack: Vicki | 0 | 649852 | -649852 | -100% | Under Budget | Yes | GWO set up under PE 1081 | 0 | 140623 | 1969250 | -1969250 | -100% | Under Budget | -140623
FPC-0813: Crist U5 Turbine Water Induction Protection (TWIP) | FPC - Vicki L. Mack: Vicki | 0 | 649852 | -649852 | -100% | Under Budget | Yes | GWO set up under PE 1093 | 0 | 140623 | 1969250 | -1969250 | -100% | Under Budget | -140623
FPC-0816: Crist Common Replace Fencing (Security) | FPC - Vicki L. Mack: Vicki | 0 | 550000 | -550000 | -100% | Under Budget | Yes | Project pushed to end of year. $1.2M budgeted to 2017 | 300000 | 330000 | 550000 | -250000 | -45.45% | Under Budget | -30000
FPC-0817: Crist - Replace Units 6 & 7 Elevator | FPC - Vicki L. Mack: Vicki | 0 | 1500000 | -1500000 | -100% | Under Budget | Yes | Project moved to 2017 - E&CS this year | 42000 | 0 | 1500000 | -1458000 | -97.2% | Under Budget | 42000
FPC-1003: CRIST 7 BOTTOM ASH PIT TRASH HOPPER | FPC - Vicki L. Mack: Vicki | 0 | 113925 | -113925 | -100% | Under Budget | Yes | Moved to 2020 | 0 | 43575 | 157500 | -157500 | -100% | Under Budget | -43575
FPC-1017: FPC-1017 | FPC - Vicki L. Mack: Vicki | 355.38 | 0 | 355.38 | 100% | Over Budget | No |  | 355 | 355.38 | 0 | 355 | 100% | Over Budget | -0.38
FPC-1027: CRIST 4 & 5 ASH CONTROLS | FPC - Vicki L. Mack: Vicki | 319.99 | 0 | 319.99 | 100% | Over Budget | No |  | 320 | 319.99 | 0 | 320 | 100% | Over Budget | 0.01
FPC-1041: CRIST 6C 4160 V BUS REPL BREAKERS | FPC - Vicki L. Mack: Vicki | 241832.83 | 40000 | 201832.83 | 504.6% | Over Budget | Yes | SCS drawings underestimated and additional SCS work needed. | 241833 | 241832.83 | 40000 | 201833 | 504.6% | Over Budget | 0.17
FPC-1042: CRIST 7C 4160 VOLT BUS REPLACE BREAKERS | FPC - Vicki L. Mack: Vicki | 194692.36 | 40000 | 154692.36 | 386.7% | Over Budget | Yes | SCS drawings underestimated | 194692 | 194692.36 | 40000 | 154692 | 386.7% | Over Budget | -0.36
FPC-1046: CRIST 4-7 SILO ASH MCC REPLACEMENT | FPC - Vicki L. Mack: Vicki | 109320.4 | 265650 | -156329.6 | -58.85% | Under Budget | Yes | Project starting later but cost exceeding budget | 350000 | 109320.4 | 265650 | 84350 | 31.75% | Over Budget | 240679.6
FPC-1050: CRIST U5 575 VOLT BUS REPLACEMENT | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 15750 | 15750 | -15750 | -100% | Under Budget | -15750
FPC-1059: CRIST 5 -- 2300 VOLT BREAKERS | FPC - Vicki L. Mack: Vicki | 12158.35 | 0 | 12158.35 | 100% | Over Budget | Yes | carryover | 12158 | 12158.35 | 0 | 12158 | 100% | Over Budget | -0.35
FPC-1068: CRIST U6 BLOWDOWN TANK REPLACEMENT | FPC - Vicki L. Mack: Vicki | 37161.88 | 0 | 37161.88 | 100% | Over Budget | Yes | Journaled from PE 1148 | 37162 | 37161.88 | 0 | 37162 | 100% | Over Budget | 0.12
FPC-1081: CRIST U4 ASSET PROTECTION - PAG | FPC - Vicki L. Mack: Vicki | 655425.92 | 0 | 655425.92 | 100% | Over Budget | Yes | Scope Increased. TWIP added | 1246067 | 1272425.92 | 50000 | 1196067 | 2392% | Over Budget | -26358.92
FPC-1089: CRIST 6 REPLACE ASH HOOPER | FPC - Vicki L. Mack: Vicki | 37.49 | 0 | 37.49 | 100% | Over Budget | No |  | 37 | 37.49 | 0 | 37 | 100% | Over Budget | -0.49
FPC-1091: CRIST 7 AIR HEATER BASKETS | FPC - Vicki L. Mack: Vicki | 1463419.47 | 500000 | 963419.47 | 192.7% | Over Budget | Yes | Project moved up. Some spent in 2015. | 1471047 | 1968087.47 | 2000000 | -528953 | -26.45% | Under Budget | -497040.47
FPC-1093: CRIST U5 ASSET PROTECTION - PAG | FPC - Vicki L. Mack: Vicki | 550033.89 | 0 | 550033.89 | 100% | Over Budget | Yes | Scope Increased. TWIP added | 1193393 | 1170033.89 | 50000 | 1143393 | 2287% | Over Budget | 23359.11
FPC-1096: CRIST U6 ASSET PROTECTION - PAG | FPC - Vicki L. Mack: Vicki | 109330.89 | 0 | 109330.89 | 100% | Over Budget | Yes | U6 TWIP included but not budgeted. Jv to be done | 108723 | 159330.89 | 50000 | 58723 | 117.4% | Over Budget | -50607.89
FPC-1097: CRIST U7 ASSET PROTECTION - PAG | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 50000 | 50000 | -50000 | -100% | Under Budget | -50000
FPC-1100: CRIST - MINOR MISC ADDITIONS | FPC - Vicki L. Mack: Vicki | 1028899.03 | 562275 | 466624.03 | 82.99% | Over Budget | Yes | More minor Miscellaneous jobs than budgeted | 2071830 | 2013874.03 | 750000 | 1321830 | 176.2% | Over Budget | 57955.97
FPC-1108: CRIST 7 FLY ASH CONTROLS | FPC - Vicki L. Mack: Vicki | 313583.01 | 210000 | 103583.01 | 49.33% | Over Budget | Yes | Increased cost in SCS projection. | 386234 | 418583.01 | 315000 | 71234 | 22.61% | Over Budget | -32349.01
FPC-1137: CRIST 6 CONTROL SYSTEM UPGRADES | FPC - Vicki L. Mack: Vicki | -26545.74 | 0 | -26545.74 | -100% | Under Budget | Yes | JV fro Retrofit/ECRC Split for U 6 controls | -26546 | -26545.74 | 0 | -26546 | -100% | Under Budget | -0.26
FPC-1143: CRIST 5 MONITORING SYSTEM UPGRADES | FPC - Vicki L. Mack: Vicki | -1607.47 | 0 | -1607.47 | -100% | Under Budget | No |  | -1607 | -1607.47 | 0 | -1607 | -100% | Under Budget | 0.47
FPC-1144: CRIST 7 CONTROL SYSTEM UPGRADES | FPC - Vicki L. Mack: Vicki | 42035.54 | 0 | 42035.54 | 100% | Over Budget | Yes | JV for Retrofit/ECRC split for U6 Controls | 42036 | 42035.54 | 0 | 42036 | 100% | Over Budget | 0.46
FPC-1148: CRIST - MAJOR MISC ADDITIONS | FPC - Vicki L. Mack: Vicki | 3219807.41 | 749700 | 2470107.41 | 329.5% | Over Budget | Yes | More major miscellaneous jobs needed than budgeted. YTD: Gas Burners $726K, U6 Cooling Tower Fill & Louvers $576K, Maintenance Team Leader Office Bldg $213K, #3 Coal Yard Sump Pump $179K, 7A Primary Air Fan Motor $148K, Elevators $143K, coal bunker level transmitters $132K | 7646204 | 7325358.41 | 1000000 | 6646204 | 664.6% | Over Budget | 320845.59 | 320000
FPC-1151: CRIST CLEARWATER HDRS & PIPING | FPC - Vicki L. Mack: Vicki | 26269.88 | 0 | 26269.88 | 100% | Over Budget | Yes | Cost pushed up, but year end will be less than budget since dollars moved to 2017 | 50000 | 326569.88 | 300300 | -250300 | -83.35% | Under Budget | -276569.88
FPC-1176: CRIST U4 REPL BREAKERS CABLE & SWITCHES FOR ARC FLASH STUDY | FPC - Vicki L. Mack: Vicki | -10716.51 | 0 | -10716.51 | -100% | Under Budget | Yes | carryover | -10717 | -10716.51 | 0 | -10717 | -100% | Under Budget | -0.49
FPC-1208: FPC-1208 | FPC - Vicki L. Mack: Vicki | 8106.27 | 0 | 8106.27 | 100% | Over Budget | No |  | 8106 | 8106.27 | 0 | 8106 | 100% | Over Budget | -0.27
FPC-1210: CRIST CYBER SECURITY | FPC - Vicki L. Mack: Vicki | 0 | 108873 | -108873 | -100% | Under Budget | Yes | Moved to end of year. McAfee portion increased. | 520217 | 36344 | 145217 | 375000 | 258.2% | Over Budget | 483873 | 480000
FPC-1223: CRIST 7 BOTTOM ASH HOPPER | FPC - Vicki L. Mack: Vicki | 832215.23 | 4893615 | -4061399.77 | -82.99% | Under Budget | Yes | Bid lower and progress payment in 2015 | 5081340 | 3152401.23 | 8446528 | -3365188 | -39.84% | Under Budget | 1928938.77 | 1900000
FPC-1254: CRIST COMMON -CONVEYOR BELTS REPLACEMENT | FPC - Vicki L. Mack: Vicki | 11122.89 | 0 | 11122.89 | 100% | Over Budget | Yes | moved to end of year | 105921 | 116122.89 | 105000 | 921 | 0.8771% | Over Budget | -10201.89
FPC-1282: CRIST UNITS 4 5 6 & 7 CHEMICAL FEED SYSTEM | FPC - Vicki L. Mack: Vicki | 13917.74 | 0 | 13917.74 | 100% | Over Budget | Yes | carryover | 13918 | 13917.74 | 0 | 13918 | 100% | Over Budget | 0.26
FPC-1925: CRIST PURCHASE MOBILE CRANE TO REPL TEREX | FPC - Vicki L. Mack: Vicki | 3279.1 | 0 | 3279.1 | 100% | Over Budget | No |  | 3279 | 3279.1 | 0 | 3279 | 100% | Over Budget | -0.1
FPC-1936: CRIST DRY AIR LAY-UP SYSTEM FOR UNITS 4-7 | FPC - Vicki L. Mack: Vicki | 20489.03 | 367500 | -347010.97 | -94.42% | Under Budget | Yes | Done in 2015 . Carryover | 35545 | 20489.03 | 367500 | -331955 | -90.33% | Under Budget | 15055.97
FPC-1937: CRIST U6 PULVERIZER GEARBOX | FPC - Vicki L. Mack: Vicki | 0 | 127635 | -127635 | -100% | Under Budget | Yes | cancelled | 0 | 1 | 127636 | -127636 | -100% | Under Budget | -1
FPC-1942: CRIST U7 PULVERIZER GEARBOXES | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 127636 | 127636 | 127636 | 0 | 0% | On Budget | 0
FPC-1946: CRIST SILO SUMP PUMP DISCHARGE LINE | FPC - Vicki L. Mack: Vicki | 9622.56 | 0 | 9622.56 | 100% | Over Budget | No |  | 9623 | 9622.56 | 0 | 9623 | 100% | Over Budget | 0.44
FPC-1953: CRIST U6 & U7 NEW BREAKER BUILDING | FPC - Vicki L. Mack: Vicki | 4113.18 | 0 | 4113.18 | 100% | Over Budget | No |  | 4113 | 4113.18 | 0 | 4113 | 100% | Over Budget | -0.18
FPC-1960: CRIST PURCHASE NEW RADIOS | FPC - Vicki L. Mack: Vicki | 21124.13 | 0 | 21124.13 | 100% | Over Budget | Yes | carryover | 21124 | 21124.13 | 0 | 21124 | 100% | Over Budget | -0.13
FPC-1963: CRIST Lab Bathrooms | FPC - Vicki L. Mack: Vicki | 0 | 703500 | -703500 | -100% | Under Budget | Yes | Most of project will be done next year. E&CS this year | 50000 | 350002 | 703500 | -653500 | -92.89% | Under Budget | -300002
FPC-1973: CRIST SWITCHYARD DRAINS | FPC - Vicki L. Mack: Vicki | -23095.94 | 204750 | -227845.94 | -111.3% | Under Budget | Yes | Cancelled … moved to 2017 | -23096 | -23095.94 | 204750 | -227846 | -111.3% | Under Budget | -0.06
FPC-1977: CRIST U7 REPLACE PULVERIZER MOTOR | FPC - Vicki L. Mack: Vicki | 123333.35 | 0 | 123333.35 | 100% | Over Budget | Yes | carryover | 123333 | 123333.35 | 0 | 123333 | 100% | Over Budget | -0.35
FPC-1978: CRIST REPLACE B SILO COMPRESSOR | FPC - Vicki L. Mack: Vicki | 35894.7 | 0 | 35894.7 | 100% | Over Budget | Yes | Budgeted for 2015. Moved to 2016 | 230000 | 35894.7 | 0 | 230000 | 100% | Over Budget | 194105.3
FPC-1979: CRIST ASH TRUCK SCALES | FPC - Vicki L. Mack: Vicki | 15644.51 | 571165 | -555520.49 | -97.26% | Under Budget | Yes | Project estimate came back lower than amount budgeted . Pushed to end of year. | 275000 | 15644.51 | 571165 | -296165 | -51.85% | Under Budget | 259355.49
FPC-1990: CRIST 4&5 COLLING TOWER FIRE PUMP STATION | FPC - Vicki L. Mack: Vicki | 0 | 330750 | -330750 | -100% | Under Budget | Yes | Cancelled. Equipment no longer needed | 0 | 0 | 330750 | -330750 | -100% | Under Budget | 0
FPC-1991: CRIST U6 575 VOLT BREAKER REPLACEMENT | FPC - Vicki L. Mack: Vicki | 0 | 21000 | -21000 | -100% | Under Budget | Yes | Moved to 2018/2019 | 0 | 139210 | 400523 | -400523 | -100% | Under Budget | -139210
FPC-1992: CRIST U7 575 VOLT BREAKER REPLACEMENT | FPC - Vicki L. Mack: Vicki | -3409.48 | 449400 | -452809.48 | -100.8% | Under Budget | Yes | Cancelled. Moved to 2017/2018 | -3409 | 85840.52 | 538650 | -542059 | -100.6% | Under Budget | -89249.52
FPC-1994: CRIST WAREHOUSE NEW ROOF | FPC - Vicki L. Mack: Vicki | 259870 | 0 | 259870 | 100% | Over Budget | Yes | Moved up from 2025. Will be offset by decreased to other PE's | 1293627 | 259870 | 0 | 1293627 | 100% | Over Budget | 1033757 | 1000000
Sub-Total Plant Crist |  | 10943809.08 | 14978078 | -4034268.92 | -26.93% | Under Budget |  |  | 26370740 | 23721372.08 | 26842674 | -471934 | -1.758% | Under Budget | 2649367.92
Plant Smith excl LTSA
FPC-0400: FPC-0400 | FPC - Vicki L. Mack: Vicki | 199.93 | 0 | 199.93 | 100% | Over Budget | No |  | 200 | 199.93 | 0 | 200 | 100% | Over Budget | 0.07
FPC-0401: FPC-0401 | FPC - Vicki L. Mack: Vicki | 338.36 | 0 | 338.36 | 100% | Over Budget | No |  | 338 | 338.36 | 0 | 338 | 100% | Over Budget | -0.36
FPC-0407: SMITH - CONSTRUCTION SUB TRANSFORMER (LAGUNA BEACH) | FPC - Vicki L. Mack: Vicki | 0 | 750000 | -750000 | -100% | Under Budget | Yes | Dollars from PE are in Transmission PE 2905 | 0 | -123978 | 1000000 | -1000000 | -100% | Under Budget | 123978
FPC-0408: SMITH 3 - COOLING TOWER FILL MEDIA REPLACEMENTS | FPC - Vicki L. Mack: Vicki | 0 | 80000 | -80000 | -100% | Under Budget | Yes | Timing. Being done in Outage | 125000 | 45000 | 125000 | 0 | 0% | On Budget | 80000
FPC-0409: SMITH 3 - DRIFT ELIMINATOR | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 150000 | 150000 | 150000 | 0 | 0% | On Budget | 0
FPC-0410: SMITH 3 - COOLING TOWER DCS CABINET REPLACEMENTS | FPC - Vicki L. Mack: Vicki | 27342.41 | 60000 | -32657.59 | -54.43% | Under Budget | Yes | Timing - Project in Progress | 80000 | 47342.41 | 80000 | 0 | 0% | On Budget | 32657.59
FPC-0413: Smith 3 - Water Mist Fire Protection System | FPC - Vicki L. Mack: Vicki | 161807.64 | 342500 | -180692.36 | -52.76% | Under Budget | Yes | Timing - Project in Progress | 685000 | 504307.64 | 685000 | 0 | 0% | On Budget | 180692.36
FPC-0414: FPC-0414 | FPC - Vicki L. Mack: Vicki | 0.87 | 0 | 0.87 | 0% | On Budget | No |  | 1 | 0.87 | 0 | 1 | 0% | On Budget | 0.13
FPC-1400: SMITH 1&2 - MISC. STEAM PLANT ADDITIONS | FPC - Vicki L. Mack: Vicki | 3943.31 | 393597 | -389653.69 | -99% | Under Budget | Yes | Minimal misc activity on Smith 1 & 2. Dollars used to fund other projects | 3943 | 135346.31 | 525000 | -521057 | -99.25% | Under Budget | -131403.31
FPC-1401: SMITH 3 - AIR COMPRESSOR REPLACEMENT | FPC - Vicki L. Mack: Vicki | 15701.21 | 100000 | -84298.79 | -84.3% | Under Budget | Yes | Timing. Project cost less than budgeted | 25000 | 15701.21 | 100000 | -75000 | -75% | Under Budget | 9298.79
FPC-1428: Smith 3 Water Treatment Plant Transformer | FPC - Vicki L. Mack: Vicki | 1.23 | 0 | 1.23 | 100% | Over Budget | No |  | 1 | 1.23 | 0 | 1 | 0% | On Budget | -0.23
FPC-1437: Smith 3 - Admin Bldg. Expansion | FPC - Vicki L. Mack: Vicki | 3513899.38 | 2614500 | 899399.38 | 34.4% | Over Budget | Yes | Overruns from Contractor Expenses over what we expected | 3960000 | 4221967.38 | 3500000 | 460000 | 13.14% | Over Budget | -261967.38
FPC-1477: SMITH 3 - REPLACE INLINE AIR FILTERS | FPC - Vicki L. Mack: Vicki | 226910.86 | 400000 | -173089.14 | -43.27% | Under Budget | Yes | Timing. Project in progress just slower getting started | 400000 | 360246.86 | 400000 | 0 | 0% | On Budget | 39753.14
FPC-1485: SMITH 1 & 2 - Steam Inerting System | FPC - Vicki L. Mack: Vicki | 15920.4 | 0 | 15920.4 | 100% | Over Budget | Yes | Unexpected corporate overhead adjustments (in August) to clear PE 4790 per Karen Grove - this is a one time adjustment that impacted multiple PEs in Gulf - JV PLT-20185 | 15920 | 15920.4 | 0 | 15920 | 100% | Over Budget | -0.4
FPC-1499: Smith U3 - Simulator | FPC - Vicki L. Mack: Vicki | 441.19 | 0 | 441.19 | 100% | Over Budget | No |  | 27000 | 441.19 | 0 | 27000 | 100% | Over Budget | 26558.81
FPC-1600: SMITH 3 - MISC. STEAM PLANT ADDITIONS | FPC - Vicki L. Mack: Vicki | 281752.68 | 749717 | -467964.32 | -62.42% | Under Budget | Yes | Minimal materials/contractor expenses for Misc. to date | 382174 | 532035.68 | 1000000 | -617826 | -61.78% | Under Budget | -149861.68
FPC-1610: SMITH - CYBER SECURITY | FPC - Vicki L. Mack: Vicki | 26205.8 | 28634 | -2428.2 | -8.48% | Under Budget | No |  | 40000 | 26205.8 | 28634 | 11366 | 39.69% | Over Budget | 13794.2
FPC-1626: SMITH - NERC CIP IMPLEMENTATION | FPC - Vicki L. Mack: Vicki | 0 | 116175 | -116175 | -100% | Under Budget | Yes | Project anticipated to begin in last quarter. | 15490 | 38725 | 154900 | -139410 | -90% | Under Budget | -23235
FPC-1632: SMITH 3 - REPLACE EVAP COOLER FILL MEDIA | FPC - Vicki L. Mack: Vicki | 94959.84 | 100000 | -5040.16 | -5.04% | Under Budget | No |  | 150000 | 94959.84 | 100000 | 50000 | 50% | Over Budget | 55040.16
FPC-1648: SMITH 3 - STORM WATER SYSTEM | FPC - Vicki L. Mack: Vicki | -636.12 | 0 | -636.12 | -100% | Under Budget | No |  | -636 | -636.12 | 0 | -636 | -100% | Under Budget | 0.12
FPC-1654: FPC-1654 | FPC - Vicki L. Mack: Vicki | -8114.77 | 0 | -8114.77 | -100% | Under Budget | No |  | -8115 | -8114.77 | 0 | -8115 | -100% | Under Budget | -0.23
FPC-1657: FPC-1657 | FPC - Vicki L. Mack: Vicki | 19097.9 | 0 | 19097.9 | 100% | Over Budget | Yes | Unexpected corporate overhead adjustments (in August) to clear PE 4790 per Karen Grove - this is a one time adjustment that impacted multiple PEs in Gulf - JV PLT-20185 | 19098 | 19097.9 | 0 | 19098 | 100% | Over Budget | 0.1
FPC-1672: SMITH - PROPERTY LINE FENCING | FPC - Vicki L. Mack: Vicki | 199396.09 | 1120500 | -921103.91 | -82.2% | Under Budget | Yes | Timing- project in progress- minimal materials purchases & contractor work to dae. | 1040000 | 602644.09 | 1500000 | -460000 | -30.67% | Under Budget | 437355.91 | 437000
FPC-1679: SMITH 3 - CORROSION PROJECT | FPC - Vicki L. Mack: Vicki | 569156.57 | 747000 | -177843.43 | -23.81% | Under Budget | Yes | underruns for Misc contractor expenses | 700000 | 822156.57 | 1000000 | -300000 | -30% | Under Budget | -122156.57
Sub-Total Plant Smith excl LTSA |  | 5148324.78 | 7602623 | -2454298.22 | -32.28% | Under Budget |  |  | 7810414 | 7499909.78 | 10348534 | -2538120 | -24.53% | Under Budget | 310504.22
Plant Smith - LTSA
FPC-1438: SMITH 3 - LTSA | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 28865000 | 28210375 | 27491875 | 1373125 | 4.995% | Over Budget | 654625
Sub-Total Plant Smith - LTSA |  | 0 | 0 | 0 | 0% | On Budget |  |  | 28865000 | 28210375 | 27491875 | 1373125 | 4.995% | Over Budget | 654625
Plant Daniel
FPC-0503: Daniel Common Emergency Alarm Tone Notification System | FPC - Vicki L. Mack: Vicki | 953.99 | 0 | 953.99 | 100% | Over Budget | No |  | 1074 | 953.99 | 0 | 1074 | 100% | Over Budget | 120.01
FPC-0506: Daniel 1 & 2 Sump Pump | FPC - Vicki L. Mack: Vicki | 183.95 | 0 | 183.95 | 100% | Over Budget | No |  | 187 | 183.95 | 0 | 187 | 100% | Over Budget | 3.05
FPC-0507: Daniel Units 1 & 2 Termon Heat Trace ( Freeze Protection) | FPC - Vicki L. Mack: Vicki | -169990.3 | 0 | -169990.3 | -100% | Under Budget | Yes | Project added to MPC's Final OB | -206399 | -169990.3 | 0 | -206399 | -100% | Under Budget | -36408.7
FPC-0510: Daniel U1 LED Lighting - Turbine Floor | FPC - Vicki L. Mack: Vicki | 142501.73 | 314172 | -171670.27 | -54.64% | Under Budget | Yes | Project reduced MPC's Final OB | 163055 | 303329.73 | 475000 | -311945 | -65.67% | Under Budget | -140274.73
FPC-0512: Daniel Common Breakers | FPC - Vicki L. Mack: Vicki | 14898.04 | 92400 | -77501.96 | -83.88% | Under Budget | Yes | Inspection on Breaker issues had delayed project | 16925 | 202498.04 | 280000 | -263075 | -93.96% | Under Budget | -185573.04
FPC-0515: Daniel Conveyor Equipment- Add Camera to Conveyor Belts | FPC - Vicki L. Mack: Vicki | 0 | 150000 | -150000 | -100% | Under Budget | Yes | Not doing this year | 0 | 0 | 150000 | -150000 | -100% | Under Budget | 0
FPC-0521: Daniel U2 Aux. Air Beck drives and registers | FPC - Vicki L. Mack: Vicki | 0 | 64350 | -64350 | -100% | Under Budget | Yes | Not doing this year | 0 | 130650 | 195000 | -195000 | -100% | Under Budget | -130650
FPC-0523: Daniel Common Replace Coal yard Switchgear | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No | Not doing this year | 0 | 95000 | 95000 | -95000 | -100% | Under Budget | -95000
FPC-0524: Daniel U1 Replace Critical AC | FPC - Vicki L. Mack: Vicki | 17156.85 | 10725 | 6431.85 | 59.97% | Over Budget | No |  | 57813 | 38931.85 | 32500 | 25313 | 77.89% | Over Budget | 18881.15
FPC-0525: Daniel 2 Replace Critical AC | FPC - Vicki L. Mack: Vicki | 113083.85 | 99890 | 13193.85 | 13.21% | Over Budget | Yes | Project cash flow advanced | 113084 | 315891.85 | 302698 | -189614 | -62.64% | Under Budget | -202807.85
FPC-0532: Daniel DEGP R/R S1 CONVEYOR GEARBOX | FPC - Vicki L. Mack: Vicki | 0 | 75000 | -75000 | -100% | Under Budget | Yes | Actuals in PE 1581 | 0 | 0 | 75000 | -75000 | -100% | Under Budget | 0
FPC-0539: Daniel Trestle Replacement | FPC - Vicki L. Mack: Vicki | 158706.28 | 0 | 158706.28 | 100% | Over Budget | Yes | Pe Letter | 160712 | 235451.28 | 0 | 160712 | 100% | Over Budget | -74739.28
FPC-0541: Daniel Generator Rotor Rewind | FPC - Vicki L. Mack: Vicki | 1427.96 | 0 | 1427.96 | 100% | Over Budget | No | . | 5000 | 6427.96 | 5000 | 0 | 0% | On Budget | -1427.96
FPC-0543: Daniel U1&2 Common CO2 Tank and Piping | FPC - Vicki L. Mack: Vicki | 25944.78 | 0 | 25944.78 | 100% | Over Budget | Yes | . | 26820 | 25944.78 | 0 | 26820 | 100% | Over Budget | 875.22
FPC-0547: Daniel Common New cables for Ash Sluice Motors | FPC - Vicki L. Mack: Vicki | 0 | 25000 | -25000 | -100% | Under Budget | Yes | . | 96796 | 75000 | 100000 | -3204 | -3.204% | Under Budget | 21796
FPC-0551: Daniel Common Emergency Notification System | FPC - Vicki L. Mack: Vicki | 0 | 187502 | -187502 | -100% | Under Budget | Yes | . | 0 | -2 | 187500 | -187500 | -100% | Under Budget | 2
FPC-1500: DANIEL-MISC. STEAM PLANT ADDITIONS & | FPC - Vicki L. Mack: Vicki | 612226.65 | 229545 | 382681.65 | 166.7% | Over Budget | Yes | . | 1000219 | 940114.65 | 306183 | 694036 | 226.7% | Over Budget | 60104.35
FPC-1544: DANIEL WATER TREATMENT PLANT CONTROLS | FPC - Vicki L. Mack: Vicki | 207792.44 | 112200 | 95592.44 | 85.2% | Over Budget | Yes | . | 331610 | 435592.44 | 340000 | -8390 | -2.468% | Under Budget | -103982.44
FPC-1545: DANIEL 1&2 ASH HANDLING CONTROLS | FPC - Vicki L. Mack: Vicki | 304968.6 | 378000 | -73031.4 | -19.32% | Under Budget | Yes | . | 447513 | 304968.6 | 378000 | 69513 | 18.39% | Over Budget | 142544.4
FPC-1564: DANIEL 2 CAPITAL VALVE REPLACEMENTS | FPC - Vicki L. Mack: Vicki | 0 | 37500 | -37500 | -100% | Under Budget | Yes | . | 0 | 0 | 37500 | -37500 | -100% | Under Budget | 0
FPC-1581: DANIEL !&2 CONVEYOR DIRECT DRIVE GEARBOXES | FPC - Vicki L. Mack: Vicki | -39005.02 | 0 | -39005.02 | -100% | Under Budget | Yes | . | 41265 | -39005.02 | 0 | 41265 | 100% | Over Budget | 80270.02
FPC-1591: DANIEL RELAY MODERNIZATION | FPC - Vicki L. Mack: Vicki | 133018.06 | 150000 | -16981.94 | -11.32% | Under Budget | Yes | . | 150000 | 133018.06 | 150000 | 0 | 0% | On Budget | 16981.94
FPC-1800: Daniel Unit 2 Mill Hoist | FPC - Vicki L. Mack: Vicki | 103543.31 | 0 | 103543.31 | 100% | Over Budget | Yes | . | 122921 | 103543.31 | 0 | 122921 | 100% | Over Budget | 19377.69
FPC-1811: DANIEL 1 EXPANSION JOINTS C01693 | FPC - Vicki L. Mack: Vicki | -839.81 | 0 | -839.81 | -100% | Under Budget | No | . | -973 | -839.81 | 0 | -973 | -100% | Under Budget | -133.19
FPC-1834: DANIEL 1 REWIND GENERATOR | FPC - Vicki L. Mack: Vicki | -0.01 | 0 | -0.01 | 0% | On Budget | No | . | 0 | -0.01 | 0 | 0 | -100% | On Budget | 0.01
FPC-1861: DANIEL 2 FW HEATER 4 LP | FPC - Vicki L. Mack: Vicki | 22534.73 | 89964 | -67429.27 | -74.95% | Under Budget | Yes | . | 24439 | 52570.73 | 120000 | -95561 | -79.63% | Under Budget | -28131.73
FPC-1863: DANIEL 1 BOILER FEED PUMPS | FPC - Vicki L. Mack: Vicki | -548.46 | 0 | -548.46 | -100% | Under Budget | No | . | -548 | -548.46 | 0 | -548 | -100% | Under Budget | 0.46
FPC-1874: Daniel 1 & 2 Closed Loop Coolers | FPC - Vicki L. Mack: Vicki | -1551.27 | 0 | -1551.27 | -100% | Under Budget | No | . | -1803 | -1551.27 | 0 | -1803 | -100% | Under Budget | -251.73
FPC-1875: Daniel 1 & 2 CPAT Drum Index | FPC - Vicki L. Mack: Vicki | 1725.83 | 0 | 1725.83 | 100% | Over Budget | No | . | 1800 | 1725.83 | 0 | 1800 | 100% | Over Budget | 74.17
FPC-1879: Daniel 1 & 2 Hot Air Dampers and Cold Air Gates | FPC - Vicki L. Mack: Vicki | -503.89 | 0 | -503.89 | -100% | Under Budget | No | . | -586 | -503.89 | 0 | -586 | -100% | Under Budget | -82.11
FPC-1881: Daniel 1 & 2 Intelligent Sootblowing | FPC - Vicki L. Mack: Vicki | 37582.91 | 12375 | 25207.91 | 203.7% | Over Budget | Yes | carryover | 38600 | 62707.91 | 37500 | 1100 | 2.933% | Over Budget | -24107.91
FPC-1882: Daniel 1 & 2 Duct Replacement | FPC - Vicki L. Mack: Vicki | 61236.81 | 85000 | -23763.19 | -27.96% | Under Budget | Yes | Project increased in MPC final budget | 86945 | 61236.81 | 85000 | 1945 | 2.288% | Over Budget | 25708.19
FPC-1884: Daniel 1 & 2 Air Heater Basket Replacement | FPC - Vicki L. Mack: Vicki | 157084.81 | 13622 | 143462.81 | 1053% | Over Budget | Yes | Parts to be staged for 2017 Outage | 0 | 197950.81 | 54488 | -54488 | -100% | Under Budget | -197950.81
FPC-1888: Daniel 1 & 2 Coal Additive System | FPC - Vicki L. Mack: Vicki | 305023.9 | 0 | 305023.9 | 100% | Over Budget | Yes | Project added to MPC's Final OB | 306124 | 305023.9 | 0 | 306124 | 100% | Over Budget | 1100.1
FPC-1891: Daniel Additional Belt Extension | FPC - Vicki L. Mack: Vicki | 156098.65 | 0 | 156098.65 | 100% | Over Budget | Yes | Project added to MPC's Final OB | 159145 | 156098.65 | 0 | 159145 | 100% | Over Budget | 3046.35
FPC-1897: Daniel IK Soot Blower | FPC - Vicki L. Mack: Vicki | -218.45 | 0 | -218.45 | -100% | Under Budget | No | carryover | -1700 | -218.45 | 0 | -1700 | -100% | Under Budget | -1481.55
Sub-Total Plant Daniel |  | 2365036.92 | 2127245 | 237791.92 | 11.18% | Over Budget |  |  | 3140038 | 3972155.92 | 3406369 | -266331 | -7.819% | Under Budget | -832117.92
Plant Scherer
FPC-1700: SCHERER DEPOSITORY | FPC - Vicki L. Mack: Vicki | 125852.08 | 0 | 125852.08 | 100% | Over Budget | Yes | Scherer Depository PE represents the Billing account for Scherer Cost. No budget dollars | 0 | 147602.08 | 0 | 0 | -100% | On Budget | -147602.08
FPC-1710: SCHERER U3 INSTALL TRIPPER FLOOR DUST EXTRACTION EQUIPMENT | FPC - Vicki L. Mack: Vicki | 252.76 | 0 | 252.76 | 100% | Over Budget | No |  | 253 | 252.76 | 0 | 253 | 100% | Over Budget | 0.24
FPC-1716: SCHERER PORTABLE EQUIPMENT | FPC - Vicki L. Mack: Vicki | 0 | 7398 | -7398 | -100% | Under Budget | No |  | 9871 | 2473 | 9871 | 0 | 0% | On Budget | 7398
FPC-1726: SCHERER REPLACE SUPERHEAT PENDANT PLATEN | FPC - Vicki L. Mack: Vicki | 255374.64 | 243800 | 11574.64 | 4.748% | Over Budget | No |  | 262605 | 255374.64 | 243800 | 18805 | 7.713% | Over Budget | 7230.36
FPC-1731: SCHERER NERC CIP V4 IMPLEMETATION | FPC - Vicki L. Mack: Vicki | 2329.53 | 0 | 2329.53 | 100% | Over Budget | No |  | 2330 | 2329.53 | 0 | 2330 | 100% | Over Budget | 0.47
FPC-1746: SCHERER U3 REPLACE REHEAT REPLACEMENT | FPC - Vicki L. Mack: Vicki | -6750 | 12420 | -19170 | -154.3% | Under Budget | Yes | Project cancelled | 0 | -6750 | 12420 | -12420 | -100% | Under Budget | 6750
FPC-1750: SCHERER MISC ADDITIONS AND IMPROVEMENTS | FPC - Vicki L. Mack: Vicki | 126295.34 | 153207 | -26911.66 | -17.57% | Under Budget | Yes | Misc projects a little behind. Plan to catch up | 204361 | 177449.34 | 204361 | 0 | 0% | On Budget | 26911.66
FPC-1751: SCHERER 3 TURBINE CROSSOVER EXPANSION JOINT | FPC - Vicki L. Mack: Vicki | 0 | 25070 | -25070 | -100% | Under Budget | Yes | Delay in start of project | 79750 | 59812 | 25070 | 54680 | 218.1% | Over Budget | 19938
FPC-1757: SCHERER 3 REPLACE AIR HEATER BASKETS | FPC - Vicki L. Mack: Vicki | 0 | 49680 | -49680 | -100% | Under Budget | Yes | Delay in start of project | 49680 | 0 | 49680 | 0 | 0% | On Budget | 49680
FPC-1792: Scherer Unit 3 Rewind Main Generator Stator | FPC - Vicki L. Mack: Vicki | 664456.68 | 745200 | -80743.32 | -10.84% | Under Budget | Yes | Project will be completed. Timing | 745200 | 982456.68 | 745200 | 0 | 0% | On Budget | -237256.68
FPC-1794: SCHERER 3 & 4 REPLACE 3D FIXED TRIPPER CHUTES | FPC - Vicki L. Mack: Vicki | 7589.2 | 12449 | -4859.8 | -39.04% | Under Budget | No |  | 12460 | 7589.2 | 12449 | 11 | 0.08836% | Over Budget | 4870.8
FPC-6502: Scherer 3 Replace Voltage Regulator | FPC - Vicki L. Mack: Vicki | 22546.75 | 9200 | 13346.75 | 145.1% | Over Budget | Yes | Project came in over estimate | 27781 | 22546.75 | 9200 | 18581 | 202% | Over Budget | 5234.25
FPC-6505: Scherer - Misc PE for all Rolling Stock | FPC - Vicki L. Mack: Vicki | 43119.82 | 0 | 43119.82 | 100% | Over Budget | Yes | JV'd over from the EC&S Construction Project it was originally on a Common Environmental GWO and now that the project is over this equipment will still be used for the plant but needed to be moved off of the GWO for Environmental and be placed in a Retro Area | 43098 | 43119.82 | 0 | 43098 | 100% | Over Budget | -21.82
FPC-6507: Scherer 3 Replace Condenser Tube | FPC - Vicki L. Mack: Vicki | 490923.37 | 497950 | -7026.63 | -1.411% | Under Budget | No |  | 497950 | 490923.37 | 497950 | 0 | 0% | On Budget | 7026.63
FPC-6508: Scherer 3 & 4 Replace Crusher House MCC U3 & U4 | FPC - Vicki L. Mack: Vicki | 78647.45 | 59110 | 19537.45 | 33.05% | Over Budget | Yes | Project came in over estimate | 107097 | 78647.45 | 59110 | 47987 | 81.18% | Over Budget | 28449.55
FPC-6513: Scherer 3 & 4 Replace and Move Trestle Feeder | FPC - Vicki L. Mack: Vicki | 0 | 62244 | -62244 | -100% | Under Budget | Yes | Dollars in 6529 | 0 | 0 | 62244 | -62244 | -100% | Under Budget | 0
FPC-6520: Scherer 3 Replace Turbine LP Rotor | FPC - Vicki L. Mack: Vicki | 1747944.11 | 3520150 | -1772205.89 | -50.34% | Under Budget | Yes | Progress payment made in 2015 | 2970131 | 2985444.11 | 3520150 | -550019 | -15.62% | Under Budget | -15313.11
FPC-6528: Scherer 3 Auto Fire Suppression -Turb/Generatr Lube Oil | FPC - Vicki L. Mack: Vicki | 0 | 11500 | -11500 | -100% | Under Budget | Yes | Project tabled right now. Not expected to be done this year | 0 | 0 | 11500 | -11500 | -100% | Under Budget | 0
FPC-6529: Scherer 3 & 4 Vibratory Feeders | FPC - Vicki L. Mack: Vicki | 60238.73 | 0 | 60238.73 | 100% | Over Budget | Yes | Budget dollars in PE 6513 | 62471 | 60238.73 | 0 | 62471 | 100% | Over Budget | 2232.27
FPC-6534: Scherer 3 Replace BFPT Controls | FPC - Vicki L. Mack: Vicki | 0 | 124200 | -124200 | -100% | Under Budget | Yes | Project cancelled | 0 | 0 | 124200 | -124200 | -100% | Under Budget | 0
FPC-6542: Scherer 3 Replace Polisher Controls | FPC - Vicki L. Mack: Vicki | 0 | 49680 | -49680 | -100% | Under Budget | Yes | Project delayed but plans to get done this year | 49680 | 0 | 49680 | 0 | 0% | On Budget | 49680
FPC-6543: Scherer Common U 1-4 Generation Step Up Spare (GSU) | FPC - Vicki L. Mack: Vicki | 1505.9 | 131202 | -129696.1 | -98.85% | Under Budget | Yes | Project delayed but plans to get done this year | 106517 | 45303.9 | 175000 | -68483 | -39.13% | Under Budget | 61213.1
Sub-Total Plant Scherer |  | 3620326.36 | 5714460 | -2094133.64 | -36.65% | Under Budget |  |  | 5231235 | 5354813.36 | 5811885 | -580650 | -9.991% | Under Budget | -123578.36
Renewables
FPC-0091: PERDIDO LANDFILL GAS ENERGY | FPC - Vicki L. Mack: Vicki | 0 | 90000 | -90000 | -100% | Under Budget | Yes | No misc work as needed to be done. | 120000 | 30000 | 120000 | 0 | 0% | On Budget | 90000
FPC-0100: Community Solar One | FPC - Vicki L. Mack: Vicki | 0 | 3000000 | -3000000 | -100% | Under Budget | Yes | Moved to 2017 | 0 | 0 | 3000000 | -3000000 | -100% | Under Budget | 0
Sub-Total Renewables |  | 0 | 3090000 | -3090000 | -100% | Under Budget |  |  | 120000 | 30000 | 3120000 | -3000000 | -96.15% | Under Budget | 90000
Sub-Total Power Generation |  | 37473730.83 | 54867187 | -17393456.17 | -31.7% | Under Budget |  |  | 103715768 | 96258144.83 | 108547391 | -4831623 | -4.451% | Under Budget | 7457623.17
Power Delivery
New Business Distribution
FPC-2550: CUSTOMER METERING | FPC - Paul C. Pratofiorito: Paul | 529032.6 | 857000 | -327967.4 | -38.27% | Under Budget | Yes | Timing: Tower infrastructure work, to be completed later in the year. Instructed to spend $200,000 on RC/DC meters for Customer Service. Plan to be on budget at year end. | 1046000 | 718032.6 | 1046000 | 0 | 0% | On Budget | 327967.4
FPC-2551: DISTRIBUTION TRANSFORMERS | FPC - Paul C. Pratofiorito: Paul | 4928577.75 | 7179000 | -2250422.25 | -31.35% | Under Budget | Yes | Timing: Existing stock used to meet needs. Plan to be on Budget at Year-end. | 8718000 | 8011724.75 | 8718000 | 0 | 0% | On Budget | 706275.25 | 700000
FPC-2552: NEW BUSINESS - OVERHEAD CONSTRUCTION | FPC - Paul C. Pratofiorito: Paul | 4270225.42 | 4691000 | -420774.58 | -8.97% | Under Budget | Yes | Customer Growth in the Overhead area is down. | 6025000 | 6071850.42 | 6025000 | 0 | 0% | On Budget | -46850.42
FPC-2553: NEW BUSINESS STREET LIGHTS | FPC - Sarah K. Seckinger: Sarah | 88158.38 | 0 | 88158.38 | 100% | Over Budget | Yes | Working to get these moved to PE 2556 | 88158 | 88158.38 | 0 | 88158 | 100% | Over Budget | -0.38
FPC-2554: NEW BUSINESS - UNDERGROUND CONSTRUCTION | FPC - Paul C. Pratofiorito: Paul | 5494697.09 | 5467000 | 27697.09 | 0.5066% | Over Budget | No |  | 7379000 | 7406697.09 | 7379000 | 0 | 0% | On Budget | -27697.09
FPC-2556: PRIVATE STREET & YARD LIGHTS | FPC - Sarah K. Seckinger: Sarah | 3444808.9 | 7031133 | -3586324.1 | -51.01% | Under Budget | Yes | Timing - anticipated spend in Fall | 6791521 | 6324151.9 | 8743806 | -1952285 | -22.33% | Under Budget | 467369.1 | 467000
FPC-2559: NEW BUSINESS - METERING ACC. ENCL. EQUIP. & DEVICES | FPC - Paul C. Pratofiorito: Paul | 98889.49 | 118000 | -19110.51 | -16.2% | Under Budget | Yes | This PE is driven by the other New Business PE's. With the OH & UG PE's 2552 being under, it is causing this PE to be under. Plan to be on Budget at Year-end. | 149000 | 129889.49 | 149000 | 0 | 0% | On Budget | 19110.51
FPC-4449: Electric Vehicle Charging Stations | FPC - Sarah K. Seckinger: Sarah | 0 | 617625 | -617625 | -100% | Under Budget | Yes | Timing - expecting to spend | 823500 | 493875 | 823500 | 0 | 0% | On Budget | 329625 | 330000
Sub-Total New Business Distribution |  | 18854389.63 | 25960758 | -7106368.37 | -27.37% | Under Budget | Yes |  | 31020179 | 29244379.63 | 32884306 | -1864127 | -5.669% | Under Budget | 1775799.37
Energy Conservation Cost Recovery
FPC-2558: ADVANCED ENERGY MANAGEMENT (AEM) | FPC - Sarah K. Seckinger: Sarah | 1200950.04 | 1696437 | -495486.96 | -29.21% | Under Budget | Yes | Under due to materials | 1807992 | 1912505.04 | 2107992 | -300000 | -14.23% | Under Budget | -104513.04
Sub-Total Energy Conservation Cost Recovery |  | 1200950.04 | 1696437 | -495486.96 | -29.21% | Under Budget |  |  | 1807992 | 1912505.04 | 2107992 | -300000 | -14.23% | Under Budget | -104513.04
Transmission
FPC-2801: TRANS SUB INFRASTRUCTURE PROJECTS | FPC - Melitta Davis: Melitta | 185224.4 | 700000 | -514775.6 | -73.54% | Under Budget | Yes | budget timing | 595452 | 335224.4 | 850000 | -254548 | -29.95% | Under Budget | 260227.6
FPC-2802: TRANS LINE INFRASTRUCTURE PROJECTS | FPC - Melitta Davis: Melitta | 3671083.9 | 4300000 | -628916.1 | -14.63% | Under Budget | Yes | Crew pulled to another job | 5251739 | 4628223.9 | 5000000 | 251739 | 5.035% | Over Budget | 623515.1 | 623515
FPC-2803: ALLIGATOR SWAMP SVC AND ASSOCIATED MODIFICATIONS | FPC - Melitta Davis: Melitta | 96668.93 | 0 | 96668.93 | 100% | Over Budget | Yes | Additional material | 120480 | 96668.93 | 0 | 120480 | 100% | Over Budget | 23811.07
FPC-2808: Greenwood - Long Beach | FPC - Melitta Davis: Melitta | 262739.2 | -2200000 | 2462739.2 | 100% | Over Budget | Yes | DOT payment expected in Oct | -1804204 | -1637260.8 | -2200000 | 395796 | -100% | Over Budget | -166943.2
FPC-2813: North Brewton - Alligator Swamp New 230 kV Transmission Line | FPC - Melitta Davis: Melitta | -63500.94 | 0 | -63500.94 | -100% | Under Budget | Yes | OH Clearing in Aug | -63502 | -63500.94 | 0 | -63502 | -100% | Under Budget | -1.06
FPC-2814: LAGUNA BEACH - SANTA ROSA #2 230KV TL | FPC - Melitta Davis: Melitta | -215906.72 | 0 | -215906.72 | -100% | Under Budget | Yes | OH Clearing in Aug | -215907 | -215906.72 | 0 | -215907 | -100% | Under Budget | -0.28
FPC-2816: Backbone Fiber Project | FPC - Melitta Davis: Melitta | 108497.47 | 555000 | -446502.53 | -80.45% | Under Budget | Yes | Designed delayed | 613138 | 108497.47 | 555000 | 58138 | 10.48% | Over Budget | 504640.53 | 500000
FPC-2821: ALLIGATOR SWAMP 230KV EXPANSION | FPC - Melitta Davis: Melitta | -1066.02 | 0 | -1066.02 | -100% | Under Budget | No |  | -1065 | -1066.02 | 0 | -1065 | -100% | Under Budget | 1.02
FPC-2822: TRANSMISSION LN SWITCH REPL PROJ | FPC - Melitta Davis: Melitta | 384893.35 | 370000 | 14893.35 | 4.025% | Over Budget | No |  | 497536 | 459892.35 | 500000 | -2464 | -0.4928% | Under Budget | 37643.65
FPC-2824: MARIANNA - ALFORD 115KV RECONDUCTOR | FPC - Melitta Davis: Melitta | -256908.64 | 0 | -256908.64 | -100% | Under Budget | Yes | OH Clearing in Aug | -256909 | -256908.64 | 0 | -256909 | -100% | Under Budget | -0.36
FPC-2829: Highland City +/- 100 MVAR Static VAR compensator (SVC) | FPC - Melitta Davis: Melitta | -43426.44 | 0 | -43426.44 | -100% | Under Budget | Yes | OH Clearing in Aug | -43426 | -43426.44 | 0 | -43426 | -100% | Under Budget | 0.44
FPC-2830: TRANSMISSION BREAKER REPLACEMENT | FPC - Melitta Davis: Melitta | 288538.47 | 150000 | 138538.47 | 92.36% | Over Budget | Yes | Material received ahead of budget | 531374 | 671538.47 | 533000 | -1626 | -0.3051% | Under Budget | -140164.47
FPC-2835: TRANSMISSION CIP COMPLIANCE | FPC - Melitta Davis: Melitta | 174514.26 | 687253 | -512738.74 | -74.61% | Under Budget | Yes | SCS billing | 370618 | 230546.26 | 911250 | -540632 | -59.33% | Under Budget | 140071.74 | 140072
FPC-2836: Transmission Cyber and Physical Security (NON-CIP) | FPC - Melitta Davis: Melitta | 539109.22 | 828750 | -289640.78 | -34.95% | Under Budget | Yes | SCS billing | 906709 | 868699.22 | 1295000 | -388291 | -29.98% | Under Budget | 38009.78
FPC-2841: GUYED Y TOWER ANCHOR REPLACEMENTS | FPC - Melitta Davis: Melitta | 1519335.88 | 520000 | 999335.88 | 192.2% | Over Budget | Yes | PE Exception $1M | 1996760 | 2136178.88 | 1000000 | 996760 | 99.68% | Over Budget | -139418.88 | -139419
FPC-2845: FPC-2845 | FPC - Melitta Davis: Melitta | 10.5 | 0 | 10.5 | 100% | Over Budget | No |  | 11 | 10.5 | 0 | 11 | 100% | Over Budget | 0.5
FPC-2853: FPC-2853 | FPC - Melitta Davis: Melitta | -118540.89 | 0 | -118540.89 | -100% | Under Budget | Yes | OH Clearing in Aug | -118541 | -118540.89 | 0 | -118541 | -100% | Under Budget | -0.11
FPC-2867: HOLMES CREEK - HIGHLAND CITY 230KV | FPC - Melitta Davis: Melitta | -370717.67 | 0 | -370717.67 | -100% | Under Budget | Yes | OH Clearing in Aug | -370718 | -393717.67 | 0 | -370718 | -100% | Under Budget | 22999.67
FPC-2868: Survey and Renewal of Transmission Corridor Leases | FPC - Melitta Davis: Melitta | 1463246.8 | 0 | 1463246.8 | 100% | Over Budget | Yes | PE Exception $1.2M | 1512591 | 1960464.8 | 538000 | 974591 | 181.2% | Over Budget | -447873.8 | -447874
FPC-2874: SMITH-LAGUNA 115 KV LINE CONVERSION TO 230KV | FPC - Melitta Davis: Melitta | -82852.61 | 0 | -82852.61 | -100% | Under Budget | Yes | OH Clearing in Aug | -82853 | -82852.61 | 0 | -82853 | -100% | Under Budget | -0.39
FPC-2881: BARRY-CRIST 230 KV UPGRADE | FPC - Melitta Davis: Melitta | 37399.91 | 181000 | -143600.09 | -79.34% | Under Budget | Yes | Designed delayed | 171453 | 44899.91 | 188500 | -17047 | -9.044% | Under Budget | 126553.09
FPC-2882: MOLINO - PINE FOREST 115KV RECONDUCTOR | FPC - Melitta Davis: Melitta | -55514.4 | 0 | -55514.4 | -100% | Under Budget | Yes | OH Clearing in Aug | -55514 | -55514.4 | 0 | -55514 | -100% | Under Budget | 0.4
FPC-2901: Crist 115kV Substation Reliability Upgrade | FPC - Melitta Davis: Melitta | 2837254.45 | 1464053 | 1373201.45 | 93.79% | Over Budget | Yes | Additional material cost | 3283070 | 3223535.45 | 1917000 | 1366070 | 71.26% | Over Budget | 59534.55
FPC-2905: SMITH CONSTRUCTION | FPC - Melitta Davis: Melitta | 732202.54 | 0 | 732202.54 | 100% | Over Budget | Yes | PE Exception $1,012,500 | 1045366 | 1034508.54 | 0 | 1045366 | 100% | Over Budget | 10857.46
FPC-2906: 115KV LINE RATING INCREASE | FPC - Melitta Davis: Melitta | 164564.34 | 269000 | -104435.66 | -38.82% | Under Budget | Yes | Material delayed | 723757 | 511564.34 | 616000 | 107757 | 17.49% | Over Budget | 212192.66
FPC-2908: Fiber Replacements | FPC - Melitta Davis: Melitta | 451215.41 | 414500 | 36715.41 | 8.858% | Over Budget | No |  | 980900 | 1098971.41 | 1062256 | -81356 | -7.659% | Under Budget | -118071.41
FPC-2911: SCS Design - Autodesk | FPC - Melitta Davis: Melitta | 117282.63 | 166985 | -49702.37 | -29.76% | Under Budget | Yes | SCS billing | 211091 | 139976.63 | 189679 | 21412 | 11.29% | Over Budget | 71114.37
FPC-2912: Solar | FPC - Melitta Davis: Melitta | -1131865.51 | -120500 | -1011365.51 | -100% | Under Budget | Yes | Billing not occurring as budgeted | -1131865 | -911865.51 | -200500 | -931365 | -100% | Under Budget | -219999.49
FPC-2914: FPC-2914 | FPC - Melitta Davis: Melitta | 14915.02 | 0 | 14915.02 | 100% | Over Budget | Yes | 2015 carryover | 14915 | 14915.02 | 0 | 14915 | 100% | Over Budget | -0.02
FPC-2915: Smith 230-115kV P&C Reliability | FPC - Melitta Davis: Melitta | 0 | 20000 | -20000 | -100% | Under Budget | Yes | Project moved to 2017 | 0 | 50000 | 70000 | -70000 | -100% | Under Budget | -50000
FPC-2921: FPC-2921 | FPC - Melitta Davis: Melitta | 729293.11 | 0 | 729293.11 | 100% | Over Budget | Yes | PE Exception $2M | 1576701 | 1583131.11 | 0 | 1576701 | 100% | Over Budget | -6430.11
FPC-3401: DIST SUB INFRASTRUCTURE PROJECTS | FPC - Melitta Davis: Melitta | 1202671.12 | 687600 | 515071.12 | 74.91% | Over Budget | Yes | budget timing | 1420895 | 1515071.12 | 1000000 | 420895 | 42.09% | Over Budget | -94176.12
FPC-3420: DESTIN 115 12KV RELIABILITY UPGRADE | FPC - Melitta Davis: Melitta | 1682777.94 | 1143884 | 538893.94 | 47.11% | Over Budget | Yes | Material received ahead of budget | 1992794 | 1790755.94 | 1850384 | 142410 | 7.696% | Over Budget | 202038.06
FPC-3421: Munson Rd Substation Conversion | FPC - Melitta Davis: Melitta | 822318.45 | 2030000 | -1207681.55 | -59.49% | Under Budget | Yes | Project delayed due to FDEP swale exemption | 2128284 | 2257818.45 | 2790500 | -662216 | -23.73% | Under Budget | -129534.45
FPC-3428: PROACTIVE TRANSFORMER REPLACEMENT | FPC - Melitta Davis: Melitta | 4894.09 | 0 | 4894.09 | 100% | Over Budget | No |  | 4894 | 4894.09 | 0 | 4894 | 100% | Over Budget | -0.09
FPC-3434: ANTOIOCH NEW SUBSTATION | FPC - Melitta Davis: Melitta | 3429457.63 | 2367000 | 1062457.63 | 44.89% | Over Budget | Yes | Additional material & labor cost | 3376225 | 3447457.63 | 2385000 | 991225 | 41.56% | Over Budget | -71232.63
FPC-3437: HURLBURT 115/12KV SUBSTATION P & C INFRASTRUCTURE UPGRADE | FPC - Melitta Davis: Melitta | 862557.52 | 433045 | 429512.52 | 99.18% | Over Budget | Yes | Additional material cost | 849791 | 1279512.52 | 850000 | -209 | -0.02459% | Under Budget | -429721.52
FPC-3490: DEVILLERS LOWSIDE BUS STRUCTURE REBUILD | FPC - Melitta Davis: Melitta | 343.89 | 0 | 343.89 | 100% | Over Budget | No |  | 344 | 343.89 | 0 | 344 | 100% | Over Budget | 0.11
FPC-3494: PACE 115/12KV SUBSTATION P & C INFRASTRUCTURE UPGRADE | FPC - Melitta Davis: Melitta | 0 | 0 | 0 | 0% | On Budget | No |  | 107351 | 125000 | 125000 | -17649 | -14.12% | Under Budget | -17649
FPC-3702: CIRCUIT SWITCHER IMP - TS/DS | FPC - Melitta Davis: Melitta | 338004.09 | 255000 | 83004.09 | 32.55% | Over Budget | Yes | budget timing | 433815 | 433004.09 | 350000 | 83815 | 23.95% | Over Budget | 810.91
FPC-3714: P&C INFRASTRUCTURE PROJECTS | FPC - Melitta Davis: Melitta | 257911.85 | 80000 | 177911.85 | 222.4% | Over Budget | Yes | Relay failures | 311046 | 277911.85 | 100000 | 211046 | 211% | Over Budget | 33134.15
FPC-3735: Ponce and Carryville Conversion to 115kV | FPC - Melitta Davis: Melitta | 2606.41 | 0 | 2606.41 | 100% | Over Budget | No |  | 2608 | 2606.41 | 0 | 2608 | 100% | Over Budget | 1.59
FPC-3742: System Operations Additions and Improvements | FPC - Melitta Davis: Melitta | 15974.01 | 87280 | -71305.99 | -81.7% | Under Budget | Yes | EMS upgrade delayed | 60020 | 100974.01 | 172280 | -112260 | -65.16% | Under Budget | -40954.01
FPC-3758: FPC-3758 | FPC - Melitta Davis: Melitta | 106240.67 | 0 | 106240.67 | 100% | Over Budget | Yes | PE Exception $312k | 314763 | 344240.67 | 0 | 314763 | 100% | Over Budget | -29477.67
FPC-3759: Navy Federal Area Solution | FPC - Melitta Davis: Melitta | 0 | 0 | 0 | 0% | On Budget | No |  | 1500000 | 1125000 | 0 | 1500000 | 100% | Over Budget | 375000 | 375000
FPC-4395: TCC Furniture | FPC - Melitta Davis: Melitta | 0 | 200000 | -200000 | -100% | Under Budget | Yes | Underrun to cover Facilities charge | 0 | 0 | 200000 | -200000 | -100% | Under Budget | 0
FPC-4400: TRANSMISSION TOOLS AND TEST EQUIPMENT | FPC - Melitta Davis: Melitta | 1733.66 | 150000 | -148266.34 | -98.84% | Under Budget | Yes | Replace as needed | 142985 | 1733.66 | 150000 | -7015 | -4.677% | Under Budget | 141251.34
Sub-Total Transmission |  | 20165181.28 | 15739850 | 4425331.28 | 28.12% | Over Budget |  |  | 28904972 | 28123211.28 | 22798349 | 6106623 | 26.79% | Over Budget | 781760.72
Distribution
FPC-3402: MISC OVERHEAD LINE IMPROVEMENTS | FPC - Paul C. Pratofiorito: Paul | 3325409.49 | 4449000 | -1123590.51 | -25.25% | Under Budget | Yes | Timing: Goal is to be on Budget at year-end. | 5746000 | 5138409.49 | 5746000 | 0 | 0% | On Budget | 607590.51
FPC-3403: DISTRIBUTION ADDITIONS/RETIREMENTS DUE TO HWY & JOINT USE | FPC - Paul C. Pratofiorito: Paul | 1675774.52 | 741000 | 934774.52 | 126.2% | Over Budget | Yes | Budget Exception Granted: Increased $402k as FDOT's volume change occurred with their new design build requirements. New projection reflects FDOT and municipalities infrastructure road improvements that will drive additional expenditures through the end of the year. Actual includes ($29k) E&S Credit | 2384000 | 2375274.52 | 1082000 | 1302000 | 120.3% | Over Budget | 8725.48
FPC-3404: DISTRIBUTION LINE MINOR PROJECTS | FPC - Paul C. Pratofiorito: Paul | 482854.95 | 713000 | -230145.05 | -32.28% | Under Budget | Yes | Timing: Plan to be on budget at year end. Reduce $358k to balance budget. | 695381 | 815854.95 | 1046000 | -350619 | -33.52% | Under Budget | -120473.95
FPC-3405: UNDERGROUND SYSTEM ADDITIONS & IMPROVEMENTS | FPC - Paul C. Pratofiorito: Paul | 2247219.62 | 1498000 | 749219.62 | 50.01% | Over Budget | Yes | Cable failures, combined with Abnormal situations causing cable replacements have caused this Budget to be over. Plan to come in over, at the NEW Projection. | 3250000 | 3225219.62 | 2476000 | 774000 | 31.26% | Over Budget | 24780.38
FPC-3406: DISTRIBUTION UNDERGROUND CONVERSIONS | FPC - Paul C. Pratofiorito: Paul | 134453.49 | 580000 | -445546.51 | -76.82% | Under Budget | Yes | Timing: Plan to be on budget at year-end. Henderson Beach CIAC collected however waiting on customer to complete duct bank before our work begins. Unknown is PCB Segment II conversion CIAC collection. Actual includes ($186k) E&S Credit | 588000 | 548453.49 | 774000 | -186000 | -24.03% | Under Budget | 39546.51
FPC-3407: MISC CAPITAL ACCRUALS | FPC - Paul C. Pratofiorito: Paul | 24455.75 | 0 | 24455.75 | 100% | Over Budget | Yes | This blanket order PE 3407 was set up exclusively to capture monthly entries for Accounts Payable setups and reversals (SOX). Any variance is a timing difference of Accruals setup the previous month. | 0 | -28420.25 | 0 | 0 | -100% | On Budget | 28420.25
FPC-3408: OVERHEAD LINE IMPROVEMENTS - POLE INSPECTION PROGRAM | FPC - Paul C. Pratofiorito: Paul | 1141499.83 | 1242000 | -100500.17 | -8.092% | Under Budget | No | Projecting to be on budget at year end. | 1806000 | 1705499.83 | 1806000 | 0 | 0% | On Budget | 100500.17
FPC-3409: RIGHT OF WAY ACQUISITION | FPC - Paul C. Pratofiorito: Paul | 452136.42 | 531000 | -78863.58 | -14.85% | Under Budget | Yes | Projecting to be on budget at year end. | 708000 | 629136.42 | 708000 | 0 | 0% | On Budget | 78863.58
FPC-3438: NEW DISTRIBUTION FEEDER FOR SUBMARINE CABLE CROSSING | FPC - Melitta Davis: Melitta | 64643.23 | 0 | 64643.23 | 100% | Over Budget | Yes | Carryover from 2015, plus seagrass mitigation survey, plan, and application requirements. | 65000 | 64643.23 | 0 | 65000 | 100% | Over Budget | 356.77
FPC-3498: DSCADA MANAGEMENT SYSTEMS - DSCADA | FPC - Paul C. Pratofiorito: Paul | 85112.89 | 0 | 85112.89 | 100% | Over Budget | Yes | TCMS GWO is under this PE, with $80k of funding from PE 4412. TCMS expansion in-service 9/27/16 (Simulator and FLISR pending). $40k projected to integrate Feeder FLA. | 120000 | 85112.89 | 0 | 120000 | 100% | Over Budget | 34887.11
FPC-3499: SO SMART RELIABILITY IMPROVEMENT PROGRAMS | FPC - Paul C. Pratofiorito: Paul | 1575276.18 | 1392000 | 183276.18 | 13.17% | Over Budget | Yes | On Schedule. | 2043000 | 2226276.18 | 2043000 | 0 | 0% | On Budget | -183276.18
FPC-3500: ASSET MANAGEMENT IMPROVEMENT PROGRAMS | FPC - Paul C. Pratofiorito: Paul | 146952.25 | 1138000 | -991047.75 | -87.09% | Under Budget | Yes | Plan to come in under budget, matches present state expectations. Actual includes ($301k) E&S Credit | 249000 | 447952.25 | 1439000 | -1190000 | -82.7% | Under Budget | -198952.25
FPC-3501: MISC DISTRIBUTION LINES SPECIFIC FEEDER IMPROVEMENTS | FPC - Paul C. Pratofiorito: Paul | -115835.78 | 205000 | -320835.78 | -156.5% | Under Budget | Yes | Actual includes ($156k) E&S Credit | -115836 | 344164.22 | 665000 | -780836 | -117.4% | Under Budget | -460000.22
FPC-3502: MISC DISTRIBUTION SUBSTATION FEEDER RECONFIGURATIONS & UPGRA | FPC - Paul C. Pratofiorito: Paul | 13151.49 | 144000 | -130848.51 | -90.87% | Under Budget | Yes | Reduced to match expectations. | 50000 | 61151.49 | 192000 | -142000 | -73.96% | Under Budget | -11151.49
FPC-3507: BEULAH SUB - NINE MILE ROAD RECONDUCTOR | FPC - Paul C. Pratofiorito: Paul | -85930.48 | 0 | -85930.48 | -100% | Under Budget | Yes | Anomaly credit caused the Actuals go below $0. Actual includes ($86k) E&S Credit | -85930 | -85930.48 | 0 | -85930 | -100% | Under Budget | 0.48
FPC-3520: ANTIOCH ROAD SUB NEW FEEDERS | FPC - Paul C. Pratofiorito: Paul | 357698.12 | 400000 | -42301.88 | -10.58% | Under Budget | Yes | Will be Fall 2016 before Dist. Can complete its work. Plan to come on budget at year-end. | 400000 | 357698.12 | 400000 | 0 | 0% | On Budget | 42301.88
FPC-3521: AIRPORT 8932 RECONDUCTOR & PHASE ADDITION | FPC - Paul C. Pratofiorito: Paul | -82977.05 | 0 | -82977.05 | -100% | Under Budget | Yes | Actual includes ($83k) E&S Credit | -82977 | -82977.05 | 0 | -82977 | -100% | Under Budget | 0.05
FPC-3529: FPC-3529 | FPC - Paul C. Pratofiorito: Paul | -103421.98 | 0 | -103421.98 | -100% | Under Budget | Yes | Actual includes ($104k) E&S Credit | -103422 | -103421.98 | 0 | -103422 | -100% | Under Budget | -0.02
FPC-3530: MIRAMAR - CRYSTAL BEACH CONFIGURATION | FPC - Paul C. Pratofiorito: Paul | -235238.05 | 0 | -235238.05 | -100% | Under Budget | Yes | Actual includes ($235k) E&S Credit | -235238 | -235238.05 | 0 | -235238 | -100% | Under Budget | 0.05
FPC-3534: EAST BAY 5542 RECONDUCTOR | FPC - Paul C. Pratofiorito: Paul | 215684.76 | 350000 | -134315.24 | -38.38% | Under Budget | Yes | Construction Completed in September. | 215685 | 215684.76 | 350000 | -134315 | -38.38% | Under Budget | 0.24
FPC-3539: HATHAWAY 8682 - GRAND LAGOON BRIDGE CROSSING | FPC - Paul C. Pratofiorito: Paul | 13360 | 700000 | -686640 | -98.09% | Under Budget | Yes | Environmental permit received. Project has been bid. Contractor can't start until 2017. Working to resolve that. BWA Job scheduled to work in January. Charges are oh and permitting and material. | 113360 | 213358 | 700000 | -586640 | -83.81% | Under Budget | -99998
FPC-3637: SANTA ROSA ISLAND ENHANCEMENTS | FPC - Paul C. Pratofiorito: Paul | 649721.27 | 972000 | -322278.73 | -33.16% | Under Budget | Yes | Actual includes ($224k) E&S Credit, which is offset by new $250k to cover reconductor at base of bridge. | 900000 | 883053.27 | 972000 | -72000 | -7.407% | Under Budget | 16946.73
FPC-3650: STORM SUPPORT - OVERHEAD | FPC - Paul C. Pratofiorito: Paul | 1028891.38 | 0 | 1028891.38 | 100% | Over Budget | Yes | Includes Winter Storms | 1028891 | 1028891.38 | 0 | 1028891 | 100% | Over Budget | -0.38
FPC-3651: STORM SUPPORT - UNDERGROUND | FPC - Paul C. Pratofiorito: Paul | 32107.14 | 0 | 32107.14 | 100% | Over Budget | Yes | Includes Winter Storms | 32107 | 32107.14 | 0 | 32107 | 100% | Over Budget | -0.14
FPC-3652: STORM HARDENING - OVERHEAD | FPC - Paul C. Pratofiorito: Paul | 1085270.3 | 804000 | 281270.3 | 34.98% | Over Budget | Yes | Actual includes ($63k) E&S Credit. Increased to cover expectations. | 1750000 | 1429270.3 | 1148000 | 602000 | 52.44% | Over Budget | 320729.7
FPC-3693: DEVILLIERS SUB - NETWORK UPGRADES | FPC - Paul C. Pratofiorito: Paul | 48732.04 | 125000 | -76267.96 | -61.01% | Under Budget | Yes | Timing. Expect to be on budget at year-end. | 125000 | 48732.04 | 125000 | 0 | 0% | On Budget | 76267.96
FPC-3694: Crystal Beach Feeder 8982 Reconductor | FPC - Paul C. Pratofiorito: Paul | 0 | 185000 | -185000 | -100% | Under Budget | Yes | Customer Choice option supercedes the need for this project. | 0 | 0 | 185000 | -185000 | -100% | Under Budget | 0
FPC-3695: Beulah Feeder 5512 & 5522 Reconductor and Reconfiguration | FPC - Paul C. Pratofiorito: Paul | 256899.26 | 150000 | 106899.26 | 71.27% | Over Budget | Yes | Over due to the labor costs and overheads being quite a bit higher than estimated. The total cost should be about $248,000. | 256899 | 256899.26 | 150000 | 106899 | 71.27% | Over Budget | -0.26
FPC-3700: SYSTEM REACTIVE CORRECTIVE CAPACITY | FPC - Paul C. Pratofiorito: Paul | 2917029.88 | 1151000 | 1766029.88 | 153.4% | Over Budget | Yes | Budget Exception Granted: Increased $1.396 million additional to cover the projected 2016 replacements (SO Smart Equipment only, does not cover arrester stations). Open EWO trend indicates $670k additional is needed. | 3500000 | 3212145.88 | 1434000 | 2066000 | 144.1% | Over Budget | 287854.12 | 287854
FPC-4301: TOOLS IMPLEMENTS AND TEST EQUIP. | FPC - Paul C. Pratofiorito: Paul | 224456.51 | 199000 | 25456.51 | 12.79% | Over Budget | Yes | Increased $300k to fund Metering Equipment. | 690000 | 415456.51 | 390000 | 300000 | 76.92% | Over Budget | 274543.49
FPC-4308: POWER DELIVERY TECHNOLOGY IMPROVEMENTS | FPC - Paul C. Pratofiorito: Paul | 139187.13 | 94000 | 45187.13 | 48.07% | Over Budget | Yes | ARMS III has a maximum cost expectations of $231k. PE reduced $100k based on expectations. | 250000 | 395187.13 | 350000 | -100000 | -28.57% | Under Budget | -145187.13
FPC-4392: HR - Training Yard Purchases | FPC - Paul C. Pratofiorito: Paul | 29984.62 | 148000 | -118015.38 | -79.74% | Under Budget | Yes | Timing: Transmission additions to the Training Yard for the new Transmission assessments. Plan to be under budget at Year-End. | 250000 | 77984.62 | 196000 | 54000 | 27.55% | Over Budget | 172015.38
FPC-4408: Cyber Security | FPC - Paul C. Pratofiorito: Paul | 238409.7 | 77000 | 161409.7 | 209.6% | Over Budget | Yes | Revised projection is $241k. $67k in SCS charges, and $193k in shared cost from APCO system improvements with the new ArcSight & Lancope installation. | 241000 | 265409.7 | 104000 | 137000 | 131.7% | Over Budget | -24409.7
FPC-4412: DSCADA MANAGEMENT SYSTEMS | FPC - Paul C. Pratofiorito: Paul | 323215.99 | 454000 | -130784.01 | -28.81% | Under Budget | Yes | Timing: DSCADA equipment replacement projections - $390k, RTAC PO issued @ $140k for Distribution Management, and TCMS enhancement continues is being funding through PE 3498. | 530000 | 508215.99 | 639000 | -109000 | -17.06% | Under Budget | 21784.01
FPC-4413: PINE FOREST OFFICE ROADWAY CONSTRUCTION | FPC - Corporate Services: Shirley | 32831.31 | 1350000 | -1317168.69 | -97.57% | Under Budget | Yes | Project is in the design stage | 1000000 | 1210831.31 | 2000000 | -1000000 | -50% | Under Budget | -210831.31
Sub-Total Distribution |  | 18339016.18 | 19792000 | -1452983.82 | -7.341% | Under Budget |  |  | 28363920 | 27682086.18 | 27120000 | 1243920 | 4.587% | Over Budget | 681833.82
Sub-Total Power Delivery |  | 58559537.13 | 63189045 | -4629507.87 | -7.326% | Under Budget |  |  | 90097063 | 86962182.13 | 84910647 | 5186416 | 6.108% | Over Budget | 3134880.87
General Plant
Transportation
FPC-4304: AUTOMOBILES AUTO TRUCKS & EQUIP. | FPC - Allison R. Gillespie: Allison | 2324535.01 | 3111000 | -786464.99 | -25.28% | Under Budget | Yes | Timing. Start receiving trucks this month. Addl $250k funded out of PE 3501. Plan to spend an additional $300k on light vehicles. Project being $150k over Projection. There will be an additional $50k spent on a charging trailer that has an IT offset. | 3809000 | 2792535.01 | 3309000 | 500000 | 15.11% | Over Budget | 1016464.99 | 1000000
Sub-Total Transportation |  | 2324535.01 | 3111000 | -786464.99 | -25.28% | Under Budget |  |  | 3809000 | 2792535.01 | 3309000 | 500000 | 15.11% | Over Budget | 1016464.99
Telecommunications/Mobile Systems/Data Network
FPC-4305: TELECOMMUNICATIONS WIRELESS SYSTEM ADDITIONS/IMPROVEMENTS | FPC - Shonda L. Lee: Shonda | 0 | 144000 | -144000 | -100% | Under Budget | Yes | $70K underrun to cover Facilities and Fleet; $85K to cover PE 4385; $27K underrun to help fund OCC overrun; $10K permanent underrun | 500 | 48000 | 192000 | -191500 | -99.74% | Under Budget | -47500
FPC-4310: VOICE & DATA CONVERGED NETWORK | FPC - Shonda L. Lee: Shonda | 491521.7 | 432000 | 59521.7 | 13.78% | Over Budget | Yes | Timing | 511000 | 635521.7 | 576000 | -65000 | -11.28% | Under Budget | -124521.7
FPC-4311: TRANSPORT NETWORK | FPC - Shonda L. Lee: Shonda | 273355.36 | 576000 | -302644.64 | -52.54% | Under Budget | Yes | Timing; Under to cover OCC overrun in Cust Serv | 595408 | 465355.36 | 768000 | -172592 | -22.47% | Under Budget | 130052.64
FPC-4385: FIELD COMPUTING | FPC - Shonda L. Lee: Shonda | 11971.7 | 108360 | -96388.3 | -88.95% | Under Budget | Yes | Timing; variance covered by PE 4305 | 230006 | 48091.7 | 144480 | 85526 | 59.2% | Over Budget | 181914.3
FPC-4386: CSS Data Integration Hub Architecture | FPC - David Oerting: Dave | 228266.22 | 95548 | 132718.22 | 138.9% | Over Budget | Yes | Over due to systemwide project overruns. | 242400 | 260118.22 | 127400 | 115000 | 90.27% | Over Budget | -17718.22
FPC-4410: Long Term Evolution (LTE) | FPC - Paul C. Pratofiorito: Paul | 1041275.43 | 1127000 | -85724.57 | -7.606% | Under Budget | No |  | 3558000 | 3157544.43 | 1500000 | 2058000 | 137.2% | Over Budget | 400455.57 | 400456
FPC-4417: IT Cyber Security Software | FPC - Shonda L. Lee: Shonda | 160137.47 | 300001 | -139863.53 | -46.62% | Under Budget | Yes | Timing; | 250000 | 260136.47 | 400000 | -150000 | -37.5% | Under Budget | -10136.47
FPC-4486: On Line Customer Care | FPC - David Oerting: Dave | 390676.19 | 300040 | 90636.19 | 30.21% | Over Budget | Yes | Over due to systemwide project overruns. | 400000 | 490636.19 | 400000 | 0 | 0% | On Budget | -90636.19
FPC-4586: Customer Kiosks | FPC - David Oerting: Dave | 16812.57 | 500000 | -483187.43 | -96.64% | Under Budget | Yes | under due to delay in kiosk purchases | 500000 | 183476.57 | 500000 | 0 | 0% | On Budget | 316523.43 | 315000
Sub-Total Telecommunications/Mobile Systems/Data Network |  | 2614016.64 | 3582949 | -968932.36 | -27.04% | Under Budget |  |  | 6287314 | 5548880.64 | 4607880 | 1679434 | 36.45% | Over Budget | 738433.36
Accounting
FPC-4376: Maximo/Oracle/Powerplant Upgrades | FPC - Carol Stevens: Carol | 0.01 | 89874 | -89873.99 | -100% | Under Budget | Yes | Powerplant upgrade will start in 4th quarter and should be on budget | 119924 | 30050.01 | 119924 | 0 | 0% | On Budget | 89873.99
Sub-Total Accounting |  | 0.01 | 89874 | -89873.99 | -100% | Under Budget |  |  | 119924 | 30050.01 | 119924 | 0 | 0% | On Budget | 89873.99
Corporate Services
FPC-4300: OFFICE FURNITURE & MECHANICAL EQUIP. | FPC - Corporate Services: Shirley | 470763.73 | 279340 | 191423.73 | 68.53% | Over Budget | Yes | Overage offset by other PEs | 520628 | 516263.73 | 324840 | 195788 | 60.27% | Over Budget | 4364.27
FPC-4302: MISC. BUILDINGS LAND AND EQUIP. | FPC - Corporate Services: Shirley | 352114.72 | 386800 | -34685.28 | -8.967% | Under Budget | No |  | 533072 | 562328.72 | 447000 | 86072 | 19.26% | Over Budget | -29256.72 | -26318
FPC-4303: SECURITY EQUIPMENT | FPC - Corporate Services: Shirley | -52332.18 | 184592 | -236924.18 | -128.4% | Under Budget | Yes | SCS charges | 222503 | -52332.18 | 184592 | 37911 | 20.54% | Over Budget | 274835.18
FPC-4306: AUDIO & VISUAL EQUIPMENT | FPC - Corporate Services: Shirley | 36904.28 | 49680 | -12775.72 | -25.72% | Under Budget | Yes | Offset for PE 3501 | 63180 | 36904.28 | 49680 | 13500 | 27.17% | Over Budget | 26275.72
FPC-4360: PINE FOREST NEW OFFICE FACILITY | FPC - Corporate Services: Shirley | 12206 | 0 | 12206 | 100% | Over Budget | Yes | Delayed | 61206 | 12206 | 0 | 61206 | 100% | Over Budget | 49000
FPC-4370: PRINTSHOP EQUIP | FPC - Corporate Services: Shirley | 2980.97 | 24840 | -21859.03 | -88% | Under Budget | Yes | Offset ot PE 4300 | 15311 | 2980.97 | 24840 | -9529 | -38.36% | Under Budget | 12330.03
FPC-4387: Defuniak Springs Roof | FPC - Corporate Services: Shirley | 55288.87 | 327000 | -271711.13 | -83.09% | Under Budget | Yes | Project bid cam in under estimate | 55289 | 55288.87 | 327000 | -271711 | -83.09% | Under Budget | 0.13
FPC-4398: PANAMA CITY VECHICLE MAINT FACILITY | FPC - Corporate Services: Shirley | 133826.54 | 2400000 | -2266173.46 | -94.42% | Under Budget | Yes | Project delayed, currently out for bids | 165000 | 269701.54 | 3500000 | -3335000 | -95.29% | Under Budget | -104701.54
FPC-4399: PENS DISTRICT-CONSOL CUST SVC FACIL | FPC - Corporate Services: Shirley | 0 | 6500000 | -6500000 | -100% | Under Budget | Yes | not approved | 1000000 | 851563 | 8200000 | -7200000 | -87.8% | Under Budget | 148437 | 148437
FPC-4406: Panama City Admin Chiller | FPC - Corporate Services: Shirley | 135149.1 | 150000 | -14850.9 | -9.901% | Under Budget | No |  | 135149 | 135149.1 | 150000 | -14851 | -9.901% | Under Budget | -0.1
FPC-4407: GEN WHSE CONVERGE ROOF | FPC - Corporate Services: Shirley | 14500 | 72000 | -57500 | -79.86% | Under Budget | Yes | Delayed | 45000 | 14500 | 72000 | -27000 | -37.5% | Under Budget | 30500
FPC-4411: LAND PURCHASE IN CRESTVIEW | FPC - Corporate Services: Shirley | -665.46 | 0 | -665.46 | -100% | Under Budget | No |  | -665 | -665.46 | 0 | -665 | -100% | Under Budget | 0.46
FPC-4414: FPC-4414 | FPC - Corporate Services: Shirley | 1365.5 | 0 | 1365.5 | 100% | Over Budget | No |  | 1366 | 1365.5 | 0 | 1366 | 100% | Over Budget | 0.5
FPC-4415: FPC-4415 | FPC - Corporate Services: Shirley | 14148.88 | 0 | 14148.88 | 100% | Over Budget | Yes | Offset PE 3502 | 300000 | 14148.88 | 0 | 300000 | 100% | Over Budget | 285851.12 | 285851
FPC-4418: FPC-4418 | FPC - Corporate Services: Shirley | 13216.15 | 0 | 13216.15 | 100% | Over Budget | Yes | Offset PE 4302 | 13216 | 13216.15 | 0 | 13216 | 100% | Over Budget | -0.15
FPC-4419: FPC-4419 | FPC - Corporate Services: Shirley | 118098.67 | 0 | 118098.67 | 100% | Over Budget | Yes | Offset PE 4344 and 3501 | 120000 | 118098.67 | 0 | 120000 | 100% | Over Budget | 1901.33
FPC-4421: FPC-4421 | FPC - Corporate Services: Shirley | 39972.66 | 0 | 39972.66 | 100% | Over Budget | Yes | Approved by management | 473750 | 39972.66 | 0 | 473750 | 100% | Over Budget | 433777.34 | 433777
FPC-4422: FPC-4422 | FPC - Corporate Services: Shirley | 45081.03 | 0 | 45081.03 | 100% | Over Budget | Yes | Offset PE 283502 | 600000 | 478581.03 | 0 | 600000 | 100% | Over Budget | 121418.97 | 121419
FPC-4426: FPC-4426 Chipley Line Service Facility | FPC - Corporate Services: Shirley |  |  |  | 0% | On Budget | No |  | 80000 |  |  | 80000 | 100% | Over Budget | 80000 | 80000
FPC-4427: FPC-4427 | FPC - Corporate Services: Shirley | 27251.98 | 0 | 27251.98 | 100% | Over Budget | Yes | Offset PE 430201 | 458000 | 27251.98 | 0 | 458000 | 100% | Over Budget | 430748.02 | 430748
FPC-4428: FPC-4428 | FPC - Corporate Services: Shirley | 1008.36 | 0 | 1008.36 | 100% | Over Budget | No |  | 294500 | 1008.36 | 0 | 294500 | 100% | Over Budget | 293491.64 | 293492
Sub-Total Corporate Services |  | 1420879.8 | 10374252 | -8953372.2 | -86.3% | Under Budget |  |  | 5156505 | 3097531.8 | 13279952 | -8123447 | -61.17% | Under Budget | 2058973.2
T&D Warehouse Equipment Replacement
FPC-4344: T&D WAREHOUSE EQUIPMENT REPLACEMENT | FPC - Beverly D. Day: Beverly | 0 | 147000 | -147000 | -100% | Under Budget |  |  | 47000 | 0 | 147000 | -100000 | -68.03% | Under Budget | 47000
Sub-Total T&D Warehouse Equipment Replacement |  | 0 | 147000 | -147000 | -100% | Under Budget |  |  | 47000 | 0 | 147000 | -100000 | -68.03% | Under Budget | 47000
Sub-Total General Plant |  | 6359431.46 | 17305075 | -10945643.54 | -63.25% | Under Budget |  |  | 15419743 | 11468997.46 | 21463756 | -6044013 | -28.16% | Under Budget | 3950745.54
Non-Utility
Non-Utility
FPC-4999: NEW PRODUCTS AND SERVICES | FPC - Sarah K. Seckinger: Sarah | 278979.93 | 302747 | -23767.07 | -7.85% | Under Budget | No |  | 494664 | 470896.93 | 494664 | 0 | 0% | On Budget | 23767.07
Sub-Total Non-Utility |  | 278979.93 | 302747 | -23767.07 | -7.85% | Under Budget |  |  | 494664 | 470896.93 | 494664 | 0 | 0% | On Budget | 23767.07
Sub-Total Non-Utility |  | 278979.93 | 302747 | -23767.07 | -7.85% | Under Budget |  |  | 494664 | 470896.93 | 494664 | 0 | 0% | On Budget | 23767.07
Uncategorized
Uncategorized
FPC-4785: FPC-4785 | FPC - David Oerting: Dave | -464830.08 | 0 | -464830.08 | -100% | Under Budget |  |  | -464830.08 | -464830.08 | 0 | -464830.08 | -100% | Under Budget | 0
FPC-4790: FPC-4790 | FPC - David Oerting: Dave | 3313793.89 | 0 | 3313793.89 | 100% | Over Budget |  |  | 3313793.89 | 3313793.89 | 0 | 3313793.89 | 100% | Over Budget | 0
Sub-Total Uncategorized |  | 2848963.81 | 0 | 2848963.81 | 100% | Over Budget |  |  | 2848963.81 | 2848963.81 | 0 | 2848963.81 | 100% | Over Budget | 0
Sub-Total Uncategorized |  | 2848963.81 | 0 | 2848963.81 | 100% | Over Budget |  |  | 2848963.81 | 2848963.81 | 0 | 2848963.81 | 100% | Over Budget | 0
Total |  | 105520643.16 | 135664054 | -30143410.84 | -22.22% | Under Budget |  |  | 212576201.81 | 198009185.16 | 215416458 | -2840256.19 | -1.318% | Under Budget | 14567016.65 | 14567017
| Sch 73 | 105241663.23 | 135664054 | YTD 2016 Approved Capital Budget
| Non-Utility Reconciling item | 278979.93 | 0
| Adjusted Total | 105520643.16 | 135664054
| Above - per UI | 105520643.16 | 135664054
| Difference | 0 | 0
Note on J339: Keyes, Jeffrey A.: project 4420-01 Customer Education Center is being forecast on this PE until actuals come on this PE
Note on D370: Keyes, Jeffrey A.: Budget Approval

## Scenario Data
Scenario Data
Scenario | CF Gulf - 2016 Official Budget - Live Reforecast
Software Release | 10.09.S
Version ID | 1
Scenario Comments
Date & Time of Shared Run | Never run
Date & Time Exported | 10/07/2016 14:58:47
Case List | [Logic, CF Actuals - FPC, Empty Tree Case: Admin lock, Structure, CF Permanent, CF PowerPlant - GULF, Locked-CF Budworks - GULF - 2016 Official Budget - Live Reforecast, CF Temporary - GULF - 2016 Official Budget - Live Reforecast, CF Environmental - GULF - 2016 Official Budget - Live Reforecast, ¦Blank Data¦: Admin lock, CF Data - GULF - 2016 Official Budget - Live Reforecast]
Start Year | 2015
Actuals Through | 09/2016
Years to Run/Run Monthly | 11 (Monthly: 11)
Scenario Type & User-Defined Scenario Type | Budget
Report Data
CAPEX by Bus Unit / BU Detail / PE: Admin lock
Sequence Set | Capital Sequence: Admin lock: Admin lock
View Name | CF Capital Expenditures by Business Unit: Admin lock
Dataset/Calc | CF Capital Expenditures by Business Unit
Row Headers | Project Class -> Business Unit of Project's Project -> Business Unit Class,Project Class -> Business Unit Detail of Project's Project -> Business Unit Class,Imported: Project -> PE of Project
Column Headers | Year 1 YTD-Sep, Year 1 Annual,User Specified Scenario List
Time Setting
Filters | View filter is CF Project Amount Type = Cash, CIAC, AFUDC Debt & Equity CF Project Amount Type = Cash, CIAC, AFUDC Debt & Equity