## 2015 Review
Rule 25-6.0342 - Gulf Power Company Storm Hardening Plan
[12 empty] | Distribution | Transmission | Effective
|  | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Projected | Totals | Percentage | Percentage | Hardening | Assumed
Activity |  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2007 - 2015 | of Total | of Total | Components | Effectiveness | COMMENTS
| Wooden Pole Inspections. | 998233 | 1397010 | 2612080 | 2174138 | 2701600 | 1415988 | 2047513 | 2362886.07 | 2164878 | 17874326.07 | 8.269% |  | 5362298 | 30% | O&M Capital to do replacement
Ten Storm Hardening Initiatives.
1 | A Three-Year Vegetation Management Cycle for Distribution Circuits | 4548612 | 3662875 | 3907030 | 4907230 | 5912112 | 4290215 | 6609066 | 5930277 | 5308707 | 45076124 | 20.85% |  | 22538062 | 50%
2 | An Audit of Joint-Use Attachment Agreements, 2011 is cost for Pole Count | 251818 | 44161 | 38346 | 0 | 337722 | 0 | 0 | 0 | 0 | 672047
3 | A Six-Year Transmission Structure Inspection Program | 260240 | 171081 | 331130 | 668369 | 305890 | 198796 | TBA | TBA | TBA | 1935506
4 | Hardening of Existing Transmission Structures | 3800106 | 2535525 | 4960523 | 1326200 | 2940400 | 3411400 | 1040000 | 2850000 | 2550000 | 25414154 |  | 100% | 2541415 | 10% | Storm guys on H frames. Replace cross spar on H frames from wood to steel.
5 | Transmission and Distribution GIS | 75000 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 225000
6 | Post-Storm Data Collection and Forensic Analysis | 109480 | 6468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115948
7 | Collection of Detailed Outage Data Differentiating Between the Reliability Performance of Overhead and Underground Systems | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Increased Utility Coordination with Local Governments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Collaborative Research on Effects of Hurricane Winds and Storm Surge | 24130 | 21245 | 2516 | 0 | 32059 | 32059 | 31059 | 30059 | 31059 | 204186
10 | A Natural Disaster Preparedness and Recovery Program | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Compliance with National Electric Safety Code's adoption of Extreme Wind Loading Standards.
1 | New Distribution Facilities - incremental | 154014 | 131493 | 107449 | 146880 | 143864.925 | 119777 | 119870 | 150038 | 152976 | 1226361.925 | 0.5673% |  | 613181 | 50% | Difference between Grade B & C for new construction
| Base amount | 6160538 | 5259728 | 4297955 | 5728305 | 5610732 | 4671291 | 4674921 | 5851463 | 5966053 | 48220986 | 22.31% |  | 24110493 | 50% | Grade C New Distribution
2 | Major planned expansion, rebuild, or relocation of distribution facilities - incremental | 136912 | 178372 | 374124 | 257900 | 289908.825 | 315512 | 313399 | 288383 | 228828 | 2383338.825 | 1.103% |  | 1191669 | 50% | Difference between Grade B & C for new construction
| Base amount | 5476458 | 7134868 | 14964954 | 10058087 | 11306444 | 12304951 | 12222553 | 11246921 | 8924291 | 93639527 | 43.32% |  | 46819764 | 50% | Grade C Distribution
3 | Critical infrastructure and major thoroughfares | 719111 | 357337 | 679082 | 387341 | 1228650 | 1328227 | 1177869 | 697956 | 1169140 | 7744713 | 3.583% |  | 3872357 | 50% | Grade B and Extreme Wind
Mitigating flood and storm surge damage to underground and supporting overhead facilities.
1 | Transmission | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A.
2 | Distribution - piloted project costs | 2572661 | 3967566 | 1507850 | 934590.31 | 1716744 | 1859987 | 884499 | 829255 | 200000 | 14473152.31
3 | Distribution - use of SS equipment | 1143733 | 1143733 | 1143733 | 773348 | 1414805 | 1990428 | 761892.36 | 1736084 | 1298749 | 11406505.36 |  |  |  |  | Pilings under conc pads, ducts, protection of switchgear and transformers.
4 | Distribution - Underground Network Improvements | 0 | 0 | 213052 | 328038 | 251660 | 63160 | 72814 | 58111 | 125000 | 1111835
Placement of new and replacement distribution facilities to facilitate safe and efficient access for installation and maintenance.
Other Key Elements
1 | Feeder Patrols prior to the start of storm season | 50000 | 50000 | 50000 | 573118 | 185881 | 183946 | 258717 | 209076 | 143000 | 1703738
2 | Infrared Patrols prior to the start of storm season | 100000 | 100000 | 100000 | 4447 | 20394 | 17870 | 17686 | 81800 | 27000 | 469197
3 | Wind Monitors to provide needed wind data | 52951 | 98383 | 39199 | 1670 | 0 | 11884 | 4888 | 0 | 0 | 208975
Additional Proposed Storm Hardening Initiatives
1 | Conversion of 4kV Distribution Feeders | 0 | 0 | 0 | 217720 | 151111 | 0 | 0 | 0 | 0 | 368831
2 | Distribution Automation | 0 | 0 | 0 | 3990831 | 6356716 | 4070853 | 5325553 | 3569347 | 2330000 | 25643300
3 | Automated Overhead Faulted Circuit Indicators | 0 | 0 | 0 | 0 | 0 | 119959 | 165265 | 240538 | 75000 | 600762
4 | Distribution Supervisory Control and Data Acquisition | 0 | 0 | 0 | 209605 | 820079 | 1283511 | 686586 | 691873 | 552000 | 4243654
| TOTALS (Less Compliance with NESC Base Amounts) | 14997001 | 13940249 | 16141114 | 16901425.31 | 24809596.75 | 20713572 | 19516676.36 | 19725683.07 | 16356337 | 163101654.49
| DISTRIBUTION TOTALS | 10861655 | 11158643 | 10774461 | 14906856.31 | 21563306.75 | 17103376 | 18476676.36 | 16875683.07 | 13806337 | 135526994.49
| TRANSMISSION TOTALS | 4135346 | 2781606 | 5366653 | 1994569 | 3246290 | 3610196 | 1040000 | 2850000 | 2550000 | 27574660
| TOTAL DISTRIBUTION FACILITY COSTS (exclusive of studies) | 18193878 | 18121683 | 26942674 | 23659881 | 27193311.75 | 24445961 | 27165191 | 26527924.07 | 23914873 | 216165376.82 | 216165376.82 |  | 104507824
| TOTAL TRANSMISSION FACILITY COSTS (exclusive of studies) | 3800106 | 2535525 | 4960523 | 1326200 | 2940400 | 3411400 | 1040000 | 2850000 | 2550000 | 25414154 |  | 25414154 | 2541415
| TOTAL T&D Facility Cost (Exclusive of studies) | 21993984 | 20657208 | 31903197 | 24986081 | 30133711.75 | 27857361 | 28205191 | 29377924.07 | 26464873 | 241579530.82
|  | 2007: FERC 364; 2008: FERC 365; 2009: FERC 368; 2010: TOTAL | FERC 364, 365 & 368 DISTRIBUTION REPLACEMENT VALUE 2014$ | 1315634399
| ESTIMATED DISTRIBUTION LINE INVESTMENT (YEAR-END 2014) | 2007: 500304467; 2008: 424574723; 2009: 390755209; 2010: 1315634399 | FERC 364, 365 & 368 DISTRIBUTION REPLACEMENT VALUE 2015$ @ 3%/year | 1355103431
[11 empty] | TOTAL FERC 364, 365 & 368 REPLACEMENT VALUE 2015$ @ 3%/year | 1355103431
[11 empty] | At completion of project % of hardening / asset value (2015) | 16% |  | 7.7% | 1.5%