## Scholz Data
|  | Total | [5 empty] | 308 Engineering | [6 empty] | 310 Land and Land Rights | [6 empty] | 311 Structure and Imporvements | [6 empty] | 312 Boiler Plant Equipment | [6 empty] | 314 Turbogenerator Units | [6 empty] | 315 Accesory Electric Equipment | [6 empty] | 316 Miscellaneous Power Plant Equipment | [6 empty] | 343 Prime Movers
[10 empty] | Unit 1 |  | Unit 2 |  |  |  |  | Unit 1 |  | Unit 2 |  |  |  |  | Unit 1 |  | Unit 2 |  |  |  |  | Unit 1 |  | Unit 2 |  |  |  |  | Unit 1 |  | Unit 2 |  |  |  |  | Unit 1 |  | Unit 2 |  |  |  |  | Unit 1 |  | Unit 2 |  |  |  |  | Unit 1 |  | Unit 2
| Tasks | Units | Quantity | Unit Cost | Cost |  | 2015 Cossts | % | Total | % | Cost | % | Cost |  | % | Total | % | Cost | % | Cost |  | % | Total | % | Cost | % | Cost |  | % | Total | % | Cost | % | Cost |  | % | Total | % | Cost | % | Cost |  | % | Total | % | Cost | % | Cost |  | % | Total | % | Cost | % | Cost |  | % | Total | % | Cost | % | Cost | wenada Total | FERC Totals | Unit Totals | check
Engineering, Design and Survey Work |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | #REF! | #REF!
| Design bulkhead for intake and discharge tunnel | ls | 1 | 50000 | 50000 |  | 50000 | 100% | 50000 | 50% | 25000 | 50% | 25000 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 50000 | 50000 | #REF! | #REF!
| Perform environmental survey of above grade structures | ls | 1 | 125000 | 125000 |  | 125000 | 100% | 125000 | 50% | 62500 | 50% | 62500 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 125000 | 125000 | #REF! | #REF!
| Storm Water Prevention Plan | ls | 1 | 30000 | 30000 |  | 30000 | 100% | 30000 | 50% | 15000 | 50% | 15000 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 30000 | 30000 | #REF! | #REF!
[7 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | #REF! | #REF!
General |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | #REF! | #REF!
| Mob./Demob. | ls | 1 | 150000 | 150000 |  | 150000 | 12.5% | 18750 | 50% | 9375 | 50% | 9375 |  | 12.5% | 18750 | 50% | 9375 | 50% | 9375 |  | 12.5% | 18750 | 50% | 9375 | 50% | 9375 |  | 12.5% | 18750 | 50% | 9375 | 50% | 9375 |  | 12.5% | 18750 | 50% | 9375 | 50% | 9375 |  | 12.5% | 18750 | 50% | 9375 | 50% | 9375 |  | 12.5% | 18750 | 50% | 9375 | 50% | 9375 |  | 12.5% | 18750 | 50% | 9375 | 50% | 9375 | 150000 | 150000 | #REF! | #REF!
| Pavement Repairs | sf | 100000 | 4.5918 |  |  | 4.5 | [55 empty] | 0 | 0 | #REF! | #REF!
| Utility Disconnects | ls | 1 | 100000 |  |  | 100000 | [55 empty] | 0 | 0 | #REF! | #REF!
| Install Bulkhead in Intake & Discharge Tunnel | ls | 1 | 150000 | 150000 |  | 150000 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 5% | 7500 | 50% | 3750 | 50% | 3750 |  | 95% | 142500 | 50% | 71250 | 50% | 71250 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 150000 | 150000 | #REF! | #REF!
| Install Electrical for Decommisioning Work | ls | 1 | 100000 | 100000 |  | 100000 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 100% | 100000 | 50% | 50000 | 50% | 50000 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 100000 | 100000 | #REF! | #REF!
| Grade and Seeding | sf | 550000 | 0.2551 | 137500 |  | 0.25 |  | 0 |  | 0 |  | 0 |  | 100% | 137500 | 50% | 68750 | 50% | 68750 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 137500 | 137500 | #REF! | #REF!
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | #REF! | #REF!
Unit 1& 2 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | #REF! | #REF!
| Demo | nt | 4134.844 | 244.896 | 1012606.7562 |  | 240 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 60% | 607564.0537 | 50% | 303782.0269 | 50% | 303782.0269 |  | 20% | 202521.3512 | 50% | 101260.6756 | 50% | 101260.6756 |  | 15% | 151891.0134 | 50% | 75945.5067 | 50% | 75945.5067 |  | 5% | 50630.3378 | 50% | 25315.1689 | 50% | 25315.1689 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 1012606.7562 | 1012606.7562 | #REF! | #REF!
| FE Sales | nt | 4134.844 | -108.3696 | -448091.2792 |  | -123.79 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 60% | -268854.7675 | 50% | -134427.3838 | 50% | -134427.3838 |  | 25% | -112022.8198 | 50% | -56011.4099 | 50% | -56011.4099 |  | 15% | -67213.6919 | 50% | -33606.8459 | 50% | -33606.8459 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | -448091.2792 | -448091.2792 | #REF! | #REF!
| AL Sales | lbs | 38293.596 | -0.38793 | -14949.6183 |  | -0.38 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 100% | -14949.6183 | 50% | -7474.8092 | 50% | -7474.8092 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | -14949.6183 | -14949.6183 | #REF! | #REF!
| CU Sales | lbs | 361661.74 | -0.31414 | -133881.6121 |  | -0.37 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 20% | -26776.3224 | 50% | -13388.1612 | 50% | -13388.1612 |  |  | 0 |  | 0 |  | 0 |  | 80% | -107105.2897 | 50% | -53552.6448 | 50% | -53552.6448 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | -133881.6121 | -133881.6121 | #REF! | #REF!
| SS Sales | lbs | 51058.128 | -0.137 | -9391.6324 |  | -0.16 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 100% | -9391.6324 | 50% | -4695.8162 | 50% | -4695.8162 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | -9391.6324 | -9391.6324 | #REF! | #REF!
| Turbine Foundations Concrete | cy | 370.3704 | 107.142 | 38888.8889 |  | 105 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 100% | 38888.8889 | 50% | 19444.4444 | 50% | 19444.4444 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 38888.8889 | 38888.8889 | #REF! | #REF!
| Condenser Tubes (90-10 Cu Ni) | lbs | 60000 | -1.5206 | -94950 |  | -1.52 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 10% | -9495 | 50% | -4747.5 | 50% | -4747.5 |  | 90% | -85455 | 50% | -42727.5 | 50% | -42727.5 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | -94950 | -94950 | #REF! | #REF!
| Transport & Dispose of Combustibles | nt | 287.202 | 66.326 | 18668.128 |  | 65 |  | 0 |  | 0 |  | 0 |  | 14.29% | 2666.8754 | 50% | 1333.4377 | 50% | 1333.4377 |  | 14.29% | 2666.8754 | 50% | 1333.4377 | 50% | 1333.4377 |  | 14.29% | 2666.8754 | 50% | 1333.4377 | 50% | 1333.4377 |  | 14.29% | 2666.8754 | 50% | 1333.4377 | 50% | 1333.4377 |  | 14.29% | 2666.8754 | 50% | 1333.4377 | 50% | 1333.4377 |  | 14.29% | 2666.8754 | 50% | 1333.4377 | 50% | 1333.4377 |  | 14.29% | 2666.8754 | 50% | 1333.4377 | 50% | 1333.4377 | 18668.128 | 18668.1281 | #REF! | #REF!
| 150' Stacks | ea | 1 | 50000 | 50000 |  | 50000 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 80% | 40000 | 50% | 20000 | 50% | 20000 |  | 20% | 10000 | 50% | 5000 | 50% | 5000 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 50000 | 50000 | #REF! | #REF!
| Process and haul brick, block & Concrete | nt | 18000 | 15.306 | 270000 |  | 15 |  | 0 |  | 0 |  | 0 |  | 100% | 270000 | 50% | 135000 | 50% | 135000 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 270000 | 270000 | #REF! | #REF!
| Unit & Service Transformers - Demo | nt | 120 | 244.896 | 29387.52 |  | 240
| Unit & Service Transformers- CU Sales | lbs | 176091.5354 | -0.31414 | -55318.1538 |  | -0.37 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 100% | -55318.1538 | 50% | -27659.0769 | 50% | -27659.0769 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | -55318.1538 | -55318.1538 | #REF! | #REF!
| Unit & Service Transformers - FE Sales | nt | 120 | -108.3696 | -13004.3488 |  | -123.79
| Backfill Basement | cy | 33846.2222 | 35.714 | 1184617.7778 |  | 35 |  | 0 |  | 0 |  | 0 |  | 100% | 1184617.7778 | 50% | 592308.8889 | 50% | 592308.8889 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 1184617.7778 | 1184617.7778 | #REF! | #REF!
[7 empty] | 0 | [57 empty] | #REF!
Unit 1 & 2 Precipitators |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | #REF! | #REF!
| Demo | nt | 700 | 244.896 | 168000 |  | 240 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 80% | 134400 | 50% | 67200 | 50% | 67200 |  | 20% | 33600 | 50% | 16800 | 50% | 16800 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 168000 | 168000 | #REF! | #REF!
| FE Sales | nt | 700 | -108.3696 | -126368.4211 |  | -123.79 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 80% | -101094.7368 | 50% | -50547.3684 | 50% | -50547.3684 |  | 20% | -25273.6842 | 50% | -12636.8421 | 50% | -12636.8421 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | -126368.4211 | -126368.4211 | #REF! | #REF!
0
Ancillary Buildings |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | #REF! | #REF!
| Demo | nt | 120 | 244.896 | 28800 |  | 240 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 60% | 17280 | 50% | 8640 | 50% | 8640 |  | 20% | 5760 | 50% | 2880 | 50% | 2880 |  | 15% | 4320 | 50% | 2160 | 50% | 2160 |  | 5% | 1440 | 50% | 720 | 50% | 720 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 28800 | 28800 | #REF! | #REF!
| Sales | nt | 120 | -108.3696 | -21663.1579 |  | -123.79 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 60% | -12997.8947 | 50% | -6498.9474 | 50% | -6498.9474 |  | 25% | -5415.7895 | 50% | -2707.8947 | 50% | -2707.8947 |  | 15% | -3249.4737 | 50% | -1624.7368 | 50% | -1624.7368 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | -21663.1579 | -21663.1579 | #REF! | #REF!
| Transport & Dispose of Combustibles | nt | 23 | 66.326 | 1495 |  | 65 |  | 0 |  | 0 |  | 0 |  | 14.29% | 213.5714 | 50% | 106.7857 | 50% | 106.7857 |  | 14.29% | 213.5714 | 50% | 106.7857 | 50% | 106.7857 |  | 14.29% | 213.5714 | 50% | 106.7857 | 50% | 106.7857 |  | 14.29% | 213.5714 | 50% | 106.7857 | 50% | 106.7857 |  | 14.29% | 213.5714 | 50% | 106.7857 | 50% | 106.7857 |  | 14.29% | 213.5714 | 50% | 106.7857 | 50% | 106.7857 |  | 14.29% | 213.5714 | 50% | 106.7857 | 50% | 106.7857 | 1495 | 1495 | #REF! | #REF!
[7 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | #REF! | #REF!
| Total |  |  |  | 2627345.8473 | 0 | 0 |  | 223750 |  | 111875 |  | 111875 | 0 |  | 1613748.2246 |  | 806874.1123 |  | 806874.1123 | 0 |  | 476815.9904 |  | 238407.9952 |  | 238407.9952 | 0 |  | 77686.9314 |  | 38843.4657 |  | 38843.4657 | 0 |  | 164423.2947 |  | 82211.6474 |  | 82211.6474 | 0 |  | 11277.3411 |  | 5638.6706 |  | 5638.6706 | 0 |  | 21630.4469 |  | 10815.2234 |  | 10815.2234 | 0 |  | 21630.4469 |  | 10815.2234 |  | 10815.2234 | 2627345.8473 | 2610962.676 | #REF!
[7 empty] | 0 |  | 0 | [53 empty] | 0 | 0 | #REF! | #REF!
[7 empty] | 0 |  | 0 | [53 empty] | #NUM! | #REF!
[7 empty] | 0 |  | 0 | [53 empty] | 0 | 0 | #REF! | #REF!
| Universal Wastes, Grease & Oil Removal | nt | 10616.7516 | 6.1224 | 65000 |  | 6 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 100% | 65000 | 50% | 32500 | 50% | 32500 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 65000 | 65000 | 65000 | 0
| Dispose of Refractory in Subtitle D Landfill | nt | 2489 | 66.326 | 161785 |  | 65 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 100% | 161785 | 50% | 80892.5 | 50% | 80892.5 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 161785 | 161785 | 161785 | 0
0
|  |  |  | 31DEC16 Scrap Values | 2854130.8473 | [60 empty] | 0
|  |  |  | 06NOV15 Scrap Values | 2767687.6203
|  |  |  | August '15 Scrap values | 2526283
327847.8473
| Note: 2016 Salvage Values were escalated from 2015 based on % from Power Advocate. |  |  |  | 2016-12-31 |  |  |  | 2016-12-31
[5 empty] | Unit |  |  |  | ADJ Unit | [56 empty] | 0
[5 empty] | Price |  |  |  | Price | [56 empty] | 0
| * FE is based on the 31DEC15, 2015 Metal Prices Birmingham P&S 5' & under = $151.79 / GT and Escalated to 31DEC2016. |  |  |  | 147.0724 |  |  |  | -108.3696 | [56 empty] | 0
| * AL is based on 31DEC15, 2015 LME Cash Official = $0.68/lb and Escalated to 31DEC2016. |  |  |  | 0.68399 |  |  |  | -0.38793 | [56 empty] | 0
| * CU is based on 31DEC15, LME Cash Official = $2.14/lb and Escalated to 31DEC2016. |  |  |  | 1.9443 |  |  |  | -0.31414 | [56 empty] | 0
| * SS is based on 31DEC15, LME 304 (18-8) Scrap Solids Processor = $0.38 / lb and Escalated to 31DEC2016. |  |  |  | 0.37675 |  |  |  | -0.137 | [56 empty] | 0
| *305 SS - is based on 31DEC15, LME 304 (18-8) Scrap Solids Processor = $0.38 / lb and Escalated to 31DEC2016. |  |  |  | 0.37675 |  |  |  | -0.17125 | [56 empty] | 0
| * Transformers is based on 31DEC15, LME Cash Official = $2.29/lb | [64 empty] | 0
| *Ti is based on 31DEC15, Secondary Market Tin Bearing >85% = $0..25/ lb and Escalated to 31DEC2016. |  |  |  | 0.24659 |  |  |  | -0.16439 | [56 empty] | 0
| * Ad Brass is based of 31DEC15, Secondary Market Yellow Brass = $1.51 and Escalated to 31DEC2016. |  |  |  | 1.3714 |  |  |  | -1.4481 | [56 empty] | 0
| * 90-10 CU-NI is based on 31DEC15, Secondary Market Cupro-Nickel Scrap 90-10 = $1.87 and Escalated to 31DEC2016. |  |  |  | 1.9908 |  |  |  | -1.5206 | [56 empty] | 0
| *304 SS - is based on 31DEC15, LME 304 (18-8) Scrap Solids Processor = $0.38 / lb and Escalated to 31DEC2016. |  |  |  | 0.37675 |  |  |  | -0.2055
| Labor Escalation (4Q15 to 4Q16) |  |  |  | 2.04% |  |  |  | 1.0204

## Scholz Import
[7 empty] | 4944186.1334 | 2854130.8473 |  | 4300349.9429 |  |  |  | 0 | 2854130.8473
WBS | FERC | UNIT | COEL | PLTCODE | QTY | UM | RATE | VALUE | COMMENT | MATERIALS | CLASSIFICATION | NOTES2016 | cRATE2016 | cVALUE2016 | BUCKET | OWNRSHP_PCT | OWNER | CCATDESC | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
3090481 | 309 | C | CLR | SCHOLZ-ASB | 1 | % | 15005.49 | 15005.49 | ADMINISTRATIVE & GENERAL OVERHEAD |  |  | ADMINISTRATIVE & GENERAL OVERHEAD | 15005.49 | 15005.49 | ASB | 1 | GULF | REMOVAL | SCS |  | 3090481CCLRSCHOLZ-ASB1%15005.49ADMINISTRATIVE & GENERAL OVERHEAD
3090481 | 309 | C | CLR | SCHOLZ-ECO | 1 | % | 1680 | 1680 | ADMINISTRATIVE & GENERAL OVERHEAD |  |  | ADMINISTRATIVE & GENERAL OVERHEAD | 1680 | 1680 | ECO | 1 | GULF | REMOVAL | SCS |  | 3090481CCLRSCHOLZ-ECO1%1680ADMINISTRATIVE & GENERAL OVERHEAD
3090481 | 309 | C | CLR | SCHOLZ-NON | 1 | % | 26318.0094 | 26318.0094 | ADMINISTRATIVE & GENERAL OVERHEAD |  |  | ADMINISTRATIVE & GENERAL OVERHEAD | 26318.0094 | 26318.0094 | NON | 1 | GULF | REMOVAL | SCS |  | 3090481CCLRSCHOLZ-NON1%26318.0094289067ADMINISTRATIVE & GENERAL OVERHEAD
311UND | 311 | C | CLR | SCHOLZ-NON | 120 | nt | 244.896 | 28800 | ANCILLARY BUILDINGS - Demo |  |  | ANICILLARY BUILDINGS - Demo | 244.896 | 28800 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 311UNDCCLRSCHOLZ-NON120nt244.896ANCILLARY BUILDINGS - Demo
311UND | 311 | C | CMS | SCHOLZ-NON | 120 | nt | -108.3696 | -21663.1579 | ANCILLARY BUILDINGS - FE SALES | STEEL |  | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -108.3696 | -21663.1579 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 311UNDCCMSSCHOLZ-NON120nt-108.369573131976ANCILLARY BUILDINGS - FE SALES
3080261 | 308 | C | CLR | SCHOLZ-NON | 2000 | MH | 101.26 | 202516 | APC ENGINEERING |  |  | SCS ENGINEERING | 101.26 | 202516 | NON | 1 | GULF | REMOVAL | SCS |  | 3080261CCLRSCHOLZ-NON2000MH101.26APC ENGINEERING
3040000 | 304 | 1 | 1LR | SCHOLZ-ASB | 0 |  |  | 0 | CONTINGENCY |  |  | CONTINGENCY | 0 | 0 | ASB | 1 | GULF | REMOVAL | SCS |  | 304000011LRSCHOLZ-ASB0CONTINGENCY
3040000 | 304 | 2 | 2LR | SCHOLZ-ASB | 0 |  |  | 0 | CONTINGENCY |  |  | CONTINGENCY | 0 | 0 | ASB | 1 | GULF | REMOVAL | SCS |  | 304000022LRSCHOLZ-ASB0CONTINGENCY
3040000 | 304 | C | CLR | SCHOLZ-ASB | 0 |  |  | 0 | CONTINGENCY |  |  | CONTINGENCY | 0 | 0 | ASB | 1 | GULF | REMOVAL | SCS |  | 3040000CCLRSCHOLZ-ASB0CONTINGENCY
3040000 | 304 | 1 | 1LR | SCHOLZ-ECO | 0 |  |  | 0 | CONTINGENCY |  |  | CONTINGENCY | 0 | 0 | ECO | 1 | GULF | REMOVAL | SCS |  | 304000011LRSCHOLZ-ECO0CONTINGENCY
3040000 | 304 | 2 | 2LR | SCHOLZ-ECO | 0 |  |  | 0 | CONTINGENCY |  |  | CONTINGENCY | 0 | 0 | ECO | 1 | GULF | REMOVAL | SCS |  | 304000022LRSCHOLZ-ECO0CONTINGENCY
3040000 | 304 | C | CLR | SCHOLZ-ECO | 0 |  |  | 0 | CONTINGENCY |  |  | CONTINGENCY | 0 | 0 | ECO | 1 | GULF | REMOVAL | SCS |  | 3040000CCLRSCHOLZ-ECO0CONTINGENCY
3040000 | 304 | 1 | 1LR | SCHOLZ-NON | 0 |  |  | 0 | CONTINGENCY |  |  | CONTINGENCY | 0 | 0 | NON | 1 | GULF | REMOVAL | SCS |  | 304000011LRSCHOLZ-NON0CONTINGENCY
3040000 | 304 | 2 | 2LR | SCHOLZ-NON | 0 |  |  | 0 | CONTINGENCY |  |  | CONTINGENCY | 0 | 0 | NON | 1 | GULF | REMOVAL | SCS |  | 304000022LRSCHOLZ-NON0CONTINGENCY
3040000 | 304 | C | CLR | SCHOLZ-NON | 0 |  |  | 0 | CONTINGENCY |  |  | CONTINGENCY | 0 | 0 | NON | 1 | GULF | REMOVAL | SCS |  | 3040000CCLRSCHOLZ-NON0CONTINGENCY
3070201MO | 307 | C | CLR | SCHOLZ-NON | 1 | LT | 150000 | 150000 | CONTRACTOR MOBILIZATION |  |  | CONTRACTOR MOBILIZATION | 150000 | 150000 | NON | 1 | GULF | REMOVAL | BDG |  | 3070201MOCCLRSCHOLZ-NON1LT150000CONTRACTOR MOBILIZATION
3080241 | 308 | C | CLR | SCHOLZ-NON | 1 | ls | 50000 | 50000 | Design bulkhead for intake and discharge tunnel |  |  | Design bulkhead for intake and discharge tunnel | 50000 | 50000 | NON | 1 | GULF | REMOVAL | BDG |  | 3080241CCLRSCHOLZ-NON1ls50000Design bulkhead for intake and discharge tunnel
312UND | 312 | 1 | 1LD | SCHOLZ-NON | 1244.5 | nt | 66.326 | 80892.5 | Dispose of Refractory in Subtitle D Landfill |  |  | Dispose of Refractory in Subtitle D Landfill | 66.326 | 80892.5 | NON | 1 | GULF | DISPOSAL | BDG | MARKUP | 312UND11LDSCHOLZ-NON1244.5nt66.326Dispose of Refractory in Subtitle D Landfill
312UND | 312 | 2 | 2LD | SCHOLZ-NON | 1244.5 | nt | 66.326 | 80892.5 | Dispose of Refractory in Subtitle D Landfill |  |  | Dispose of Refractory in Subtitle D Landfill | 66.326 | 80892.5 | NON | 1 | GULF | DISPOSAL | BDG | MARKUP | 312UND22LDSCHOLZ-NON1244.5nt66.326Dispose of Refractory in Subtitle D Landfill
3110001LC | 311 | C | CLR | SCHOLZ-NON | 550000 | sf | 0.2551 | 137500 | Grade and Seeding |  |  | Grade and Seeding | 0.2551 | 137500 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 3110001LCCCLRSCHOLZ-NON550000sf0.2551Grade and Seeding
314052102 | 314 | C | CLR | SCHOLZ-NON | 1 | ls | 150000 | 150000 | Install Bulkhead in Intake & Discharge Tunnel |  |  | Install Bulkhead in Intake & Discharge Tunnel | 150000 | 150000 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 314052102CCLRSCHOLZ-NON1ls150000Install Bulkhead in Intake & Discharge Tunnel
307UND | 307 | C | CLR | SCHOLZ-NON | 1 | ls | 100000 | 100000 | Install Electrical for Decommissioning Work |  |  | Install Electrical for Decommisioning Work | 100000 | 100000 | NON | 1 | GULF | REMOVAL | BDG |  | 307UNDCCLRSCHOLZ-NON1ls100000Install Electrical for Decommissioning Work
3120000AA | 312 | 1 | 1LR | SCHOLZ-ASB | 113909.5 | SF | 6.5866 | 750274.5 | INSULATION (ASBESTOS) |  |  | SFTNSIDING (ASBESTOS) | 6.5866 | 750274.5 | ASB | 1 | GULF | REMOVAL | SCS | MARKUP | 3120000AA11LRSCHOLZ-ASB113909.5SF6.58658408648971INSULATION (ASBESTOS)
3120000AA | 312 | 1 | 1LD | SCHOLZ-ASB | 285 | TN | 345.389 | 54116 | INSULATION (ASBESTOS) |  |  | SFTNSIDING (ASBESTOS) | 345.389 | 54116 | ASB | 1 | GULF | DISPOSAL | SCS | MARKUP | 3120000AA11LDSCHOLZ-ASB285TN345.38903725058INSULATION (ASBESTOS)
3120000AA | 312 | 2 | 2LR | SCHOLZ-ASB | 113909.5 | SF | 6.5866 | 750274.5 | INSULATION (ASBESTOS) |  |  | SFTNSIDING (ASBESTOS) | 6.5866 | 750274.5 | ASB | 1 | GULF | REMOVAL | SCS | MARKUP | 3120000AA22LRSCHOLZ-ASB113909.5SF6.58658408648971INSULATION (ASBESTOS)
3120000AA | 312 | 2 | 2LD | SCHOLZ-ASB | 285 | TN | 345.389 | 54116 | INSULATION (ASBESTOS) |  |  | SFTNSIDING (ASBESTOS) | 345.389 | 54116 | ASB | 1 | GULF | DISPOSAL | SCS | MARKUP | 3120000AA22LDSCHOLZ-ASB285TN345.38903725058INSULATION (ASBESTOS)
312UND | 312 | 1 | 1LR | SCHOLZ-NON | 0.5 | ea | 50000 | 25000 | Main Power Block - 150' Stacks |  |  | Main Power Block - 150' Stacks | 50000 | 25000 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 312UND11LRSCHOLZ-NON0.5ea50000Main Power Block - 150' Stacks
312UND | 312 | 2 | 2LR | SCHOLZ-NON | 0.5 | ea | 50000 | 25000 | Main Power Block - 150' Stacks |  |  | Main Power Block - 150' Stacks | 50000 | 25000 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 312UND22LRSCHOLZ-NON0.5ea50000Main Power Block - 150' Stacks
312UND | 312 | 1 | 1MS | SCHOLZ-NON | 19146.798 | lbs | -0.38793 | -7474.8092 | Main Power Block - AL Sales | ALUMINUM |  | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -0.38793 | -7474.8092 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 312UND11MSSCHOLZ-NON19146.798lbs-0.387933012716418Main Power Block - AL Sales
312UND | 312 | 2 | 2MS | SCHOLZ-NON | 19146.798 | lbs | -0.38793 | -7474.8092 | Main Power Block - AL Sales | ALUMINUM |  | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -0.38793 | -7474.8092 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 312UND22MSSCHOLZ-NON19146.798lbs-0.387933012716418Main Power Block - AL Sales
311UND | 311 | 1 | 1LR | SCHOLZ-NON | 16923.1111 | cy | 35.714 | 592308.8889 | Main Power Block - Backfill Basement |  |  | Main Power Block - (4) Coal Silos | 35.714 | 592308.8889 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 311UND11LRSCHOLZ-NON16923.1111111111cy35.714Main Power Block - Backfill Basement
311UND | 311 | 2 | 2LR | SCHOLZ-NON | 16923.1111 | cy | 35.714 | 592308.8889 | Main Power Block - Backfill Basement |  |  | Main Power Block - (4) Coal Silos | 35.714 | 592308.8889 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 311UND22LRSCHOLZ-NON16923.1111111111cy35.714Main Power Block - Backfill Basement
314UND | 314 | 1 | 1MS | SCHOLZ-NON | 30000 | lbs | -1.5206 | -47475 | Main Power Block - Condenser Tubes (90-10 Cu Ni) | CUPRO-NICKEL |  | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -1.5206 | -47475 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 314UND11MSSCHOLZ-NON30000lbs-1.52060666331658Main Power Block - Condenser Tubes (90-10 Cu Ni)
314UND | 314 | 2 | 2MS | SCHOLZ-NON | 30000 | lbs | -1.5206 | -47475 | Main Power Block - Condenser Tubes (90-10 Cu Ni) | CUPRO-NICKEL |  | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -1.5206 | -47475 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 314UND22MSSCHOLZ-NON30000lbs-1.52060666331658Main Power Block - Condenser Tubes (90-10 Cu Ni)
312UND | 312 | 1 | 1MS | SCHOLZ-NON | 36166.174 | lbs | -0.31414 | -13388.1612 | Main Power Block - CU Sales | COPPER |  | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -0.31414 | -13388.1612 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 312UND11MSSCHOLZ-NON36166.174lbs-0.314144309790393Main Power Block - CU Sales
315UND | 315 | 1 | 1MS | SCHOLZ-NON | 144664.696 | lbs | -0.31414 | -53552.6448 | Main Power Block - CU Sales | COPPER |  | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -0.31414 | -53552.6448 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 315UND11MSSCHOLZ-NON144664.696lbs-0.314144309790393Main Power Block - CU Sales
312UND | 312 | 2 | 2MS | SCHOLZ-NON | 36166.174 | lbs | -0.31414 | -13388.1612 | Main Power Block - CU Sales | COPPER |  | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -0.31414 | -13388.1612 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 312UND22MSSCHOLZ-NON36166.174lbs-0.314144309790393Main Power Block - CU Sales
315UND | 315 | 2 | 2MS | SCHOLZ-NON | 144664.696 | lbs | -0.31414 | -53552.6448 | Main Power Block - CU Sales | COPPER |  | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -0.31414 | -53552.6448 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 315UND22MSSCHOLZ-NON144664.696lbs-0.314144309790393Main Power Block - CU Sales
311UND | 311 | 1 | 1LR | SCHOLZ-NON | 1240.4532 | nt | 244.896 | 303782.0269 | Main Power Block - DEMO |  |  | Main Power Block - DEMO | 244.896 | 303782.0269 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 311UND11LRSCHOLZ-NON1240.4532nt244.896Main Power Block - DEMO
312UND | 312 | 1 | 1LR | SCHOLZ-NON | 413.4844 | nt | 244.896 | 101260.6756 | Main Power Block - DEMO |  |  | Main Power Block - DEMO | 244.896 | 101260.6756 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 312UND11LRSCHOLZ-NON413.4844nt244.896Main Power Block - DEMO
314UND | 314 | 1 | 1LR | SCHOLZ-NON | 310.1133 | nt | 244.896 | 75945.5067 | Main Power Block - DEMO |  |  | Main Power Block - DEMO | 244.896 | 75945.5067 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 314UND11LRSCHOLZ-NON310.1133nt244.896Main Power Block - DEMO
315UND | 315 | 1 | 1LR | SCHOLZ-NON | 103.3711 | nt | 244.896 | 25315.1689 | Main Power Block - DEMO |  |  | Main Power Block - DEMO | 244.896 | 25315.1689 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 315UND11LRSCHOLZ-NON103.3711nt244.896Main Power Block - DEMO
311UND | 311 | 2 | 2LR | SCHOLZ-NON | 1240.4532 | nt | 244.896 | 303782.0269 | Main Power Block - DEMO |  |  | Main Power Block - DEMO | 244.896 | 303782.0269 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 311UND22LRSCHOLZ-NON1240.4532nt244.896Main Power Block - DEMO
312UND | 312 | 2 | 2LR | SCHOLZ-NON | 413.4844 | nt | 244.896 | 101260.6756 | Main Power Block - DEMO |  |  | Main Power Block - DEMO | 244.896 | 101260.6756 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 312UND22LRSCHOLZ-NON413.4844nt244.896Main Power Block - DEMO
314UND | 314 | 2 | 2LR | SCHOLZ-NON | 310.1133 | nt | 244.896 | 75945.5067 | Main Power Block - DEMO |  |  | Main Power Block - DEMO | 244.896 | 75945.5067 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 314UND22LRSCHOLZ-NON310.1133nt244.896Main Power Block - DEMO
315UND | 315 | 2 | 2LR | SCHOLZ-NON | 103.3711 | nt | 244.896 | 25315.1689 | Main Power Block - DEMO |  |  | Main Power Block - DEMO | 244.896 | 25315.1689 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 315UND22LRSCHOLZ-NON103.3711nt244.896Main Power Block - DEMO
311UND | 311 | 1 | 1MS | SCHOLZ-NON | 1240.4532 | nt | -108.3696 | -134427.3838 | Main Power Block - FE Sales | STEEL |  | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -108.3696 | -134427.3838 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 311UND11MSSCHOLZ-NON1240.4532nt-108.369573131976Main Power Block - FE Sales
312UND | 312 | 1 | 1MS | SCHOLZ-NON | 516.8555 | nt | -108.3696 | -56011.4099 | Main Power Block - FE Sales | STEEL |  | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -108.3696 | -56011.4099 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 312UND11MSSCHOLZ-NON516.8555nt-108.369573131976Main Power Block - FE Sales
314UND | 314 | 1 | 1MS | SCHOLZ-NON | 310.1133 | nt | -108.3696 | -33606.8459 | Main Power Block - FE Sales | STEEL |  | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -108.3696 | -33606.8459 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 314UND11MSSCHOLZ-NON310.1133nt-108.369573131976Main Power Block - FE Sales
311UND | 311 | 2 | 2MS | SCHOLZ-NON | 1240.4532 | nt | -108.3696 | -134427.3838 | Main Power Block - FE Sales | STEEL |  | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -108.3696 | -134427.3838 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 311UND22MSSCHOLZ-NON1240.4532nt-108.369573131976Main Power Block - FE Sales
312UND | 312 | 2 | 2MS | SCHOLZ-NON | 516.8555 | nt | -108.3696 | -56011.4099 | Main Power Block - FE Sales | STEEL |  | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -108.3696 | -56011.4099 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 312UND22MSSCHOLZ-NON516.8555nt-108.369573131976Main Power Block - FE Sales
314UND | 314 | 2 | 2MS | SCHOLZ-NON | 310.1133 | nt | -108.3696 | -33606.8459 | Main Power Block - FE Sales | STEEL |  | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -108.3696 | -33606.8459 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 314UND22MSSCHOLZ-NON310.1133nt-108.369573131976Main Power Block - FE Sales
312UND | 312 | 1 | 1MS | SCHOLZ-NON | 25529.064 | lbs | -0.137 | -4695.8162 | Main Power Block - SS Sales | STAINLESS STEEL |  | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -0.137 | -4695.8162 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 312UND11MSSCHOLZ-NON25529.064lbs-0.13699904Main Power Block - SS Sales
312UND | 312 | 2 | 2MS | SCHOLZ-NON | 25529.064 | lbs | -0.137 | -4695.8162 | Main Power Block - SS Sales | STAINLESS STEEL |  | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -0.137 | -4695.8162 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 312UND22MSSCHOLZ-NON25529.064lbs-0.13699904Main Power Block - SS Sales
314UND | 314 | 1 | 1LR | SCHOLZ-NON | 185.1852 | cy | 107.142 | 19444.4444 | Main Power Block - Turbine Foundations Concrete |  |  | Main Power Block - Turbine Foundations Concrete | 107.142 | 19444.4444 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 314UND11LRSCHOLZ-NON185.185185185185cy107.142Main Power Block - Turbine Foundations Concrete
314UND | 314 | 2 | 2LR | SCHOLZ-NON | 185.1852 | cy | 107.142 | 19444.4444 | Main Power Block - Turbine Foundations Concrete |  |  | Main Power Block - Turbine Foundations Concrete | 107.142 | 19444.4444 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 314UND22LRSCHOLZ-NON185.185185185185cy107.142Main Power Block - Turbine Foundations Concrete
3110061 | 311 | C | CLR | SCHOLZ-NON | 100000 | sf | 2500 | 0 | Pavement Repairs |  |  | Pavement Repairs | 2500 | 0 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 3110061CCLRSCHOLZ-NON100000sf2500Pavement Repairs
3080268EA | 308 | C | CLR | SCHOLZ-NON | 1 | ls | 125000 | 125000 | Perform environmental survey of above grade structures |  |  | Perform environmental survey of above grade structures | 125000 | 125000 | NON | 1 | GULF | REMOVAL | BDG |  | 3080268EACCLRSCHOLZ-NON1ls125000Perform environmental survey of above grade structures
3080268 | 308 | C | CLR | SCHOLZ-ASB | 1 | LT | 1200.4392 | 1200.4392 | PERMITS |  |  | PERMITS | 1200.4392 | 1200.4392 | ASB | 1 | GULF | REMOVAL | SCS |  | 3080268CCLRSCHOLZ-ASB1LT1200.4392PERMITS
3080268 | 308 | C | CLR | SCHOLZ-ECO | 1 | LT | 134.4 | 134.4 | PERMITS |  |  | PERMITS | 134.4 | 134.4 | ECO | 1 | GULF | REMOVAL | SCS |  | 3080268CCLRSCHOLZ-ECO1LT134.4PERMITS
3080268 | 308 | C | CLR | SCHOLZ-NON | 1 | LT | 2105.4408 | 2105.4408 | PERMITS |  |  | PERMITS | 2105.4408 | 2105.4408 | NON | 1 | GULF | REMOVAL | SCS |  | 3080268CCLRSCHOLZ-NON1LT2105.44075431253PERMITS
3070041 | 307 | C | CLR | SCHOLZ-NON | 1 | MY | 135010.76 | 135010.76 | POWER GENERATION SUPERVISION |  |  | POWER GENERATION SUPERVISION | 135010.76 | 135010.76 | NON | 1 | GULF | REMOVAL | SCS |  | 3070041CCLRSCHOLZ-NON1MY135010.76POWER GENERATION SUPERVISION
312UND | 312 | 1 | 1LR | SCHOLZ-ECO | 350 | nt | 244.896 | 84000 | Precipitators - DEMO |  |  | Precipitators - DEMO | 244.896 | 84000 | ECO | 1 | GULF | REMOVAL | BDG | MARKUP | 312UND11LRSCHOLZ-ECO350nt244.896Precipitators - DEMO
312UND | 312 | 2 | 2LR | SCHOLZ-ECO | 350 | nt | 244.896 | 84000 | Precipitators - DEMO |  |  | Precipitators - DEMO | 244.896 | 84000 | ECO | 1 | GULF | REMOVAL | BDG | MARKUP | 312UND22LRSCHOLZ-ECO350nt244.896Precipitators - DEMO
312UND | 312 | 1 | 1MS | SCHOLZ-ECO | 350 | nt | -108.3696 | -63184.2105 | Precipitators - FE Sales | STEEL |  | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -108.3696 | -63184.2105 | ECO | 1 | GULF | SALVAGE | BDG | MARKUP | 312UND11MSSCHOLZ-ECO350nt-108.369573131976Precipitators - FE Sales
312UND | 312 | 2 | 2MS | SCHOLZ-ECO | 350 | nt | -108.3696 | -63184.2105 | Precipitators - FE Sales | STEEL |  | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -108.3696 | -63184.2105 | ECO | 1 | GULF | SALVAGE | BDG | MARKUP | 312UND22MSSCHOLZ-ECO350nt-108.369573131976Precipitators - FE Sales
3111002CN | 311 | 1 | 1LD | SCHOLZ-NON | 9000 | nt | 15.306 | 135000 | Process, haul and backfill brick & block |  |  | Process, haul and backfill brick & block | 15.306 | 135000 | NON | 1 | GULF | DISPOSAL | BDG | MARKUP | 3111002CN11LDSCHOLZ-NON9000nt15.306Process, haul and backfill brick & block
3111002CN | 311 | 2 | 2LD | SCHOLZ-NON | 9000 | nt | 15.306 | 135000 | Process, haul and backfill brick & block |  |  | Process, haul and backfill brick & block | 15.306 | 135000 | NON | 1 | GULF | DISPOSAL | BDG | MARKUP | 3111002CN22LDSCHOLZ-NON9000nt15.306Process, haul and backfill brick & block
3080241 | 308 | C | CLR | SCHOLZ-ASB | 1 | % | 15005.49 | 15005.49 | SCS ENGINEERING |  |  | GPC ENGINEERING | 15005.49 | 15005.49 | ASB | 1 | GULF | REMOVAL | SCS |  | 3080241CCLRSCHOLZ-ASB1%15005.49SCS ENGINEERING
3080241 | 308 | C | CLR | SCHOLZ-ECO | 3 | % | 1680 | 5040 | SCS ENGINEERING |  |  | GPC ENGINEERING | 1680 | 5040 | ECO | 1 | GULF | REMOVAL | SCS |  | 3080241CCLRSCHOLZ-ECO3%1680SCS ENGINEERING
3080241 | 308 | C | CLR | SCHOLZ-NON | 3 | % | 26318.0094 | 78954.0283 | SCS ENGINEERING |  |  | GPC ENGINEERING | 26318.0094 | 78954.0283 | NON | 1 | GULF | REMOVAL | SCS |  | 3080241CCLRSCHOLZ-NON3%26318.0094289067SCS ENGINEERING
3070221 | 307 | C | CLR | SCHOLZ-NON | 2 | MY | 50750.31 | 101500.62 | SECURITY SERVICES |  |  | SECURITY SERVICES | 50750.31 | 101500.62 | NON | 1 | GULF | REMOVAL | SCS |  | 3070221CCLRSCHOLZ-NON2MY50750.31SECURITY SERVICES
3080241SW | 308 | C | CLR | SCHOLZ-NON | 1 | ls | 30000 | 30000 | Storm Water Prevention Plan |  |  | Storm Water Prevention Plan | 30000 | 30000 | NON | 1 | GULF | REMOVAL | BDG |  | 3080241SWCCLRSCHOLZ-NON1ls30000Storm Water Prevention Plan
3070201 | 307 | C | CLR | SCHOLZ-NON | 2 | % | 26318.0094 | -147363.9811 | TEMPORARY CONSTRUCTION SERVICES |  |  | 2% of FERCs 310 and above less "Install Electrical for Decommisioning Work". | 26318.0094 | -147363.9811 | NON | 1 | GULF | REMOVAL | SCS |  | 3070201CCLRSCHOLZ-NON2%26318.0094289067TEMPORARY CONSTRUCTION SERVICES
3070201 | 307 | C | CLR | SCHOLZ-ASB | 1 | % | 15005.49 | 15005.49 | TEMPORARY CONSTRUCTION SERVICES |  |  | TEMPORARY CONSTRUCTION SERVICES | 15005.49 | 15005.49 | ASB | 1 | GULF | REMOVAL | SCS |  | 3070201CCLRSCHOLZ-ASB1%15005.49TEMPORARY CONSTRUCTION SERVICES
3070201 | 307 | C | CLR | SCHOLZ-ECO | 2 | % | 1680 | 3360 | TEMPORARY CONSTRUCTION SERVICES |  |  | TEMPORARY CONSTRUCTION SERVICES | 1680 | 3360 | ECO | 1 | GULF | REMOVAL | SCS |  | 3070201CCLRSCHOLZ-ECO2%1680TEMPORARY CONSTRUCTION SERVICES
311UND | 311 | 1 | 1LD | SCHOLZ-NON | 143.601 | nt | 66.326 | 9334.064 | Transport & Dispose of Combustibles |  |  | Transport & Dispose of Combustibles | 66.326 | 9334.064 | NON | 1 | GULF | DISPOSAL | BDG | MARKUP | 311UND11LDSCHOLZ-NON143.600985nt66.326Transport & Dispose of Combustibles
311UND | 311 | 2 | 2LD | SCHOLZ-NON | 143.601 | nt | 66.326 | 9334.064 | Transport & Dispose of Combustibles |  |  | Transport & Dispose of Combustibles | 66.326 | 9334.064 | NON | 1 | GULF | DISPOSAL | BDG | MARKUP | 311UND22LDSCHOLZ-NON143.600985nt66.326Transport & Dispose of Combustibles
341UND | 341 | C | CLD | SCHOLZ-NON | 23 | nt | 66.326 | 1495 | Transport & Dispose of Combustibles |  |  | Transport & Dispose of Combustibles | 66.326 | 1495 | NON | 1 | GULF | DISPOSAL | BDG | MARKUP | 341UNDCCLDSCHOLZ-NON23nt66.326Transport & Dispose of Combustibles
315UND | 315 | 1 | 1MS | SCHOLZ-NON | 88045.7677 | lbs | -0.31414 | -27659.0769 | Unit & Service Transformers - CU Sales | COPPER | TRANSFORMER | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -0.31414 | -27659.0769 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 315UND11MSSCHOLZ-NON88045.7676968013lbs-0.314144309790393Unit & Service Transformers - CU Sales
315UND | 315 | 2 | 2MS | SCHOLZ-NON | 88045.7677 | lbs | -0.31414 | -27659.0769 | Unit & Service Transformers - CU Sales | COPPER | TRANSFORMER | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -0.31414 | -27659.0769 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 315UND22MSSCHOLZ-NON88045.7676968013lbs-0.314144309790393Unit & Service Transformers - CU Sales
315UND | 315 | 1 | 1LR | SCHOLZ-NON | 60 | nt | 244.896 | 14693.76 | Unit & Service Transformers - Demo |  | TRANSFORMER | Main Substation Transformers - Demo | 244.896 | 14693.76 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 315UND11LRSCHOLZ-NON60nt244.896Unit & Service Transformers - Demo
315UND | 315 | 2 | 2LR | SCHOLZ-NON | 60 | nt | 244.896 | 14693.76 | Unit & Service Transformers - Demo |  | TRANSFORMER | Main Substation Transformers - Demo | 244.896 | 14693.76 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 315UND22LRSCHOLZ-NON60nt244.896Unit & Service Transformers - Demo
315UND | 315 | 1 | 1MS | SCHOLZ-NON | 60 | nt | -108.3696 | -6502.1744 | Unit & Service Transformers - FE Sales | STEEL | TRANSFORMER | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -108.3696 | -6502.1744 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 315UND11MSSCHOLZ-NON60nt-108.369573131976Unit & Service Transformers - FE Sales
315UND | 315 | 2 | 2MS | SCHOLZ-NON | 60 | nt | -108.3696 | -6502.1744 | Unit & Service Transformers - FE Sales | STEEL | TRANSFORMER | Scrap Market Values (MetalPrices.com) as projected to 31DEC16. | -108.3696 | -6502.1744 | NON | 1 | GULF | SALVAGE | BDG | MARKUP | 315UND22MSSCHOLZ-NON60nt-108.369573131976Unit & Service Transformers - FE Sales
3430000FM | 343 | 1 | 1LD | SCHOLZ-NON | 5308.3758 | nt | 6.1224 | 32500 | Universal Wastes, Grease & Oil Removal |  |  | Universal Wastes, Grease & Oil Removal | 6.1224 | 32500 | NON | 1 | GULF | DISPOSAL | BDG | MARKUP | 3430000FM34311LDSCHOLZ-NONntUniversal Wastes, Grease & Oil Removal
3430000FM | 343 | 2 | 2LD | SCHOLZ-NON | 5308.3758 | nt | 6 | 32500 | Universal Wastes, Grease & Oil Removal |  |  | Universal Wastes, Grease & Oil Removal | 6 | 32500 | NON | 1 | GULF | DISPOSAL | BDG | MARKUP | 3430000FM34322LDSCHOLZ-NONntUniversal Wastes, Grease & Oil Removal
3430000FM | 343 | 1 | 1LD | SCHOLZ-NON | 248.9 | nt | 66.326 |  | Universal Wastes, Grease & Oil Removal |  |  | Universal Wastes, Grease & Oil Removal | 66.326 | 0 | NON | 1 | GULF | DISPOSAL | BDG | MARKUP | 3430000FM11LDSCHOLZ-NON248.9nt66.326Universal Wastes, Grease & Oil Removal
3430000FM | 343 | 2 | 2LD | SCHOLZ-NON | 248.9 | nt | 66.326 |  | Universal Wastes, Grease & Oil Removal |  |  | Universal Wastes, Grease & Oil Removal | 66.326 | 0 | NON | 1 | GULF | DISPOSAL | BDG | MARKUP | 3430000FM22LDSCHOLZ-NON248.9nt66.326Universal Wastes, Grease & Oil Removal
311UND | 311 | C | CLR | SCHOLZ-NON | 1 | ls | 100000 | 0 | Utility Disconnects |  |  | Utility Disconnects | 100000 | 0 | NON | 1 | GULF | REMOVAL | BDG | MARKUP | 311UNDCCLRSCHOLZ-NON1ls100000Utility Disconnects
3080361 | 308 | C | CLR | SCHOLZ-ASB | 0.6 | % | 15005.49 | 9003.294 | WRAP-UP AND ALL-RISK INSURANCE |  |  | WRAP-UP AND ALL-RISK INSURANCE | 15005.49 | 9003.294 | ASB | 1 | GULF | REMOVAL | SCS |  | 3080361CCLRSCHOLZ-ASB0.6%15005.49WRAP-UP AND ALL-RISK INSURANCE
3080361 | 308 | C | CLR | SCHOLZ-ECO | 0.6 | % | 1680 | 1008 | WRAP-UP AND ALL-RISK INSURANCE |  |  | WRAP-UP AND ALL-RISK INSURANCE | 1680 | 1008 | ECO | 1 | GULF | REMOVAL | SCS |  | 3080361CCLRSCHOLZ-ECO0.6%1680WRAP-UP AND ALL-RISK INSURANCE
3080361 | 308 | C | CLR | SCHOLZ-NON | 0.6 | % | 26318.0094 | 15790.8057 | WRAP-UP AND ALL-RISK INSURANCE |  |  | WRAP-UP AND ALL-RISK INSURANCE | 26318.0094 | 15790.8057 | NON | 1 | GULF | REMOVAL | SCS |  | 3080361CCLRSCHOLZ-NON0.6%26318.0094289067WRAP-UP AND ALL-RISK INSURANCE

## Scholz
|  | Total |  |  |  |  | 308 Engineering | [6 empty] | 310 Land and Land Rights | [6 empty] | 311 Structure and Imporvements | [6 empty] | 312 Boiler Plant Equipment | [6 empty] | 314 Turbogenerator Units | [6 empty] | 315 Accesory Electric Equipment | [6 empty] | 316 Miscellaneous Power Plant Equipment | [6 empty] | 343 Prime Movers
[9 empty] | Unit 1 |  | Unit 2 |  |  |  |  | Unit 1 |  | Unit 2 |  |  |  |  | Unit 1 |  | Unit 2 |  |  |  |  | Unit 1 |  | Unit 2 |  |  |  |  | Unit 1 |  | Unit 2 |  |  |  |  | Unit 1 |  | Unit 2 |  |  |  |  | Unit 1 |  | Unit 2 |  |  |  |  | Unit 1 |  | Unit 2
| Tasks | Units | Quantity | Unit Cost | Cost |  | % | Total | % | Cost | % | Cost |  | % | Total | % | Cost | % | Cost |  | % | Total | % | Cost | % | Cost |  | % | Total | % | Cost | % | Cost |  | % | Total | % | Cost | % | Cost |  | % | Total | % | Cost | % | Cost |  | % | Total | % | Cost | % | Cost |  | % | Total | % | Cost | % | Cost | wenada Total | FERC Totals | Unit Totals | check
Engineering, Design and Survey Work |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Design bulkhead for intake and discharge tunnel | ls | 1 | 50000 | 50000 |  | 100% | 50000 | 50% | 25000 | 50% | 25000 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 50000 | 50000 | 50000 | 0
| Perform environmental survey of above grade structures | ls | 1 | 125000 | 125000 |  | 100% | 125000 | 50% | 62500 | 50% | 62500 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 125000 | 125000 | 125000 | 0
| Storm Water Prevention Plan | ls | 1 | 30000 | 30000 |  | 100% | 30000 | 50% | 15000 | 50% | 15000 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 30000 | 30000 | 30000 | 0
[8 empty] | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
General |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Mob./Demob. | ls | 1 | 150000 | 150000 |  | 12.5% | 18750 | 50% | 9375 | 50% | 9375 |  | 12.5% | 18750 | 50% | 9375 | 50% | 9375 |  | 12.5% | 18750 | 50% | 9375 | 50% | 9375 |  | 12.5% | 18750 | 50% | 9375 | 50% | 9375 |  | 12.5% | 18750 | 50% | 9375 | 50% | 9375 |  | 12.5% | 18750 | 50% | 9375 | 50% | 9375 |  | 12.5% | 18750 | 50% | 9375 | 50% | 9375 |  | 12.5% | 18750 | 50% | 9375 | 50% | 9375 | 150000 | 150000 | 150000 | 0
| Install Bulkhead in Intake & Discharge Tunnel | ls | 1 | 150000 | 150000 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 5% | 7500 | 50% | 3750 | 50% | 3750 |  | 95% | 142500 | 50% | 71250 | 50% | 71250 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 150000 | 150000 | 150000 | 0
| Install Electrical for Decommisioning Work | ls | 1 | 100000 | 100000 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 100% | 100000 | 50% | 50000 | 50% | 50000 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 100000 | 100000 | 100000 | 0
| Grade and Seeding | sf | 550000 | 0.25 | 137500 |  |  | 0 |  | 0 |  | 0 |  | 100% | 137500 | 50% | 68750 | 50% | 68750 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 137500 | 137500 | 137500 | 0
[5 empty] | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
Unit 1& 2 |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Demo | nt | 4254.844 | 240 | 1021162.56 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 60% | 612697.536 | 50% | 306348.768 | 50% | 306348.768 |  | 20% | 204232.512 | 50% | 102116.256 | 50% | 102116.256 |  | 15% | 153174.384 | 50% | 76587.192 | 50% | 76587.192 |  | 5% | 51058.128 | 50% | 25529.064 | 50% | 25529.064 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 1021162.56 | 1021162.56 | 1021162.56 | 0
| FE Sales | nt | 4254.844 | -180.5263 | -768111.3116 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 60% | -460866.7869 | 50% | -230433.3935 | 50% | -230433.3935 |  | 25% | -192027.8279 | 50% | -96013.9139 | 50% | -96013.9139 |  | 15% | -115216.6967 | 50% | -57608.3484 | 50% | -57608.3484 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | -768111.3116 | -768111.3116 | -768111.3116 | 0
| AL Sales | lbs | 38293.596 | -0.39039 | -14949.6183 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 100% | -14949.6183 | 50% | -7474.8092 | 50% | -7474.8092 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | -14949.6183 | -14949.6183 | -14949.6183 | 0
| CU Sales | lbs | 361661.74 | -0.37018 | -133881.6121 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 20% | -26776.3224 | 50% | -13388.1612 | 50% | -13388.1612 |  |  | 0 |  | 0 |  | 0 |  | 80% | -107105.2897 | 50% | -53552.6448 | 50% | -53552.6448 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | -133881.6121 | -133881.6121 | -133881.6121 | 0
| SS Sales | lbs | 51058.128 | -0.18394 | -9391.6324 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 100% | -9391.6324 | 50% | -4695.8162 | 50% | -4695.8162 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | -9391.6324 | -9391.6324 | -9391.6324 | 0
| Turbine Foundations Concrete | cy | 370.3704 | 105 | 38888.8889 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 100% | 38888.8889 | 50% | 19444.4444 | 50% | 19444.4444 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 38888.8889 | 38888.8889 | 38888.8889 | 0
| Condenser Tubes (90-10 Cu Ni) | lbs | 60000 | -1.5825 | -94950 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 10% | -9495 | 50% | -4747.5 | 50% | -4747.5 |  | 90% | -85455 | 50% | -42727.5 | 50% | -42727.5 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | -94950 | -94950 | -94950 | 0
| Transport & Dispose of Combustibles | nt | 287.202 | 65 | 18668.128 |  |  | 0 |  | 0 |  | 0 |  | 14.29% | 2666.8754 | 50% | 1333.4377 | 50% | 1333.4377 |  | 14.29% | 2666.8754 | 50% | 1333.4377 | 50% | 1333.4377 |  | 14.29% | 2666.8754 | 50% | 1333.4377 | 50% | 1333.4377 |  | 14.29% | 2666.8754 | 50% | 1333.4377 | 50% | 1333.4377 |  | 14.29% | 2666.8754 | 50% | 1333.4377 | 50% | 1333.4377 |  | 14.29% | 2666.8754 | 50% | 1333.4377 | 50% | 1333.4377 |  | 14.29% | 2666.8754 | 50% | 1333.4377 | 50% | 1333.4377 | 18668.128 | 18668.1281 | 18668.1281 | 0
| 150' Stacks | ea | 1 | 50000 | 50000 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 80% | 40000 | 50% | 20000 | 50% | 20000 |  | 20% | 10000 | 50% | 5000 | 50% | 5000 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 50000 | 50000 | 50000 | 0
| Process and haul brick, block & Concrete | nt | 18000 | 15 | 270000 |  |  | 0 |  | 0 |  | 0 |  | 100% | 270000 | 50% | 135000 | 50% | 135000 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 270000 | 270000 | 270000 | 0
| Unit & Service Transformers | nt | 120 | -460.9846 | -55318.1538 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 100% | -55318.1538 | 50% | -27659.0769 | 50% | -27659.0769 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | -55318.1538 | -55318.1538 | -55318.1538 | 0
| Backfill Basement | cy | 33846.2222 | 35 | 1184617.7778 |  |  | 0 |  | 0 |  | 0 |  | 100% | 1184617.7778 | 50% | 592308.8889 | 50% | 592308.8889 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 1184617.7778 | 1184617.7778 | 1184617.7778 | 0
0
Unit 1 & 2 Precipitators |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Demo | nt | 700 | 240 | 168000 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 80% | 134400 | 50% | 67200 | 50% | 67200 |  | 20% | 33600 | 50% | 16800 | 50% | 16800 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 168000 | 168000 | 168000 | 0
| FE Sales | nt | 700 | -180.5263 | -126368.4211 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 80% | -101094.7368 | 50% | -50547.3684 | 50% | -50547.3684 |  | 20% | -25273.6842 | 50% | -12636.8421 | 50% | -12636.8421 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | -126368.4211 | -126368.4211 | -126368.4211 | 0
[5 empty] | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
Ancillary Buildings |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Demo | nt | 120 | 240 | 28800 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 60% | 17280 | 50% | 8640 | 50% | 8640 |  | 20% | 5760 | 50% | 2880 | 50% | 2880 |  | 15% | 4320 | 50% | 2160 | 50% | 2160 |  | 5% | 1440 | 50% | 720 | 50% | 720 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 28800 | 28800 | 28800 | 0
| Sales | nt | 120 | -180.5263 | -21663.1579 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 60% | -12997.8947 | 50% | -6498.9474 | 50% | -6498.9474 |  | 25% | -5415.7895 | 50% | -2707.8947 | 50% | -2707.8947 |  | 15% | -3249.4737 | 50% | -1624.7368 | 50% | -1624.7368 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | -21663.1579 | -21663.1579 | -21663.1579 | 0
| Transport & Dispose of Combustibles | nt | 23 | 65 | 1495 |  |  | 0 |  | 0 |  | 0 |  | 14.29% | 213.5714 | 50% | 106.7857 | 50% | 106.7857 |  | 14.29% | 213.5714 | 50% | 106.7857 | 50% | 106.7857 |  | 14.29% | 213.5714 | 50% | 106.7857 | 50% | 106.7857 |  | 14.29% | 213.5714 | 50% | 106.7857 | 50% | 106.7857 |  | 14.29% | 213.5714 | 50% | 106.7857 | 50% | 106.7857 |  | 14.29% | 213.5714 | 50% | 106.7857 | 50% | 106.7857 |  | 14.29% | 213.5714 | 50% | 106.7857 | 50% | 106.7857 | 1495 | 1495 | 1495 | 0
[8 empty] | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Total |  |  |  | 2299498.4475 | 0 |  | 223750 |  | 111875 |  | 111875 | 0 |  | 1613748.2246 |  | 806874.1123 |  | 806874.1123 | 0 |  | 289937.4532 |  | 144968.7266 |  | 144968.7266 | 0 |  | -606.9159 |  | -303.4579 |  | -303.4579 | 0 |  | 117703.6604 |  | 58851.8302 |  | 58851.8302 | 0 |  | 11705.1313 |  | 5852.5657 |  | 5852.5657 | 0 |  | 21630.4469 |  | 10815.2234 |  | 10815.2234 | 0 |  | 21630.4469 |  | 10815.2234 |  | 10815.2234 | 2299498.4475 | 2299498.4475 | 2299498.4475
[8 empty] | 0 | [53 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | [53 empty] | 0 | 0 | 0 | 0
| Dispose of Refractory in Subtitle D Landfill | nt | 2489 | 65 | 161785 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 100% | 161785 | 50% | 80892.5 | 50% | 80892.5 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 | 161785 | 161785 | 161785 | 0
Unit
Price
| * FE is based on the Aug. 7, 2015 Metal Prices Birmingham P&S 5' & under = $245 / GT | [6 empty] | -180.5263
| * AL is based on Aug. 18, 2015 LME Cash Official = $0.69/lb | [6 empty] | -0.39039
| * CU is baesd on Aug. 18, 2015 LME Cash Official = $2.27/lb | [6 empty] | -0.37018
| * SS is based on Aug. 17, 2015 LME 304 (18-8) Scrap Solids Processor = $0.50 / lb | [6 empty] | -0.18394
| *305 SS - is based on Aug. 17, 2014 LME 304 (18-8) Scrap Solids Processor = $0.50 / lb | [6 empty] | -0.22371
| * Transformers is based on Aug. 18, 2015 LME Cash official for CU = $2.27 | [6 empty] | -460.9846
| *Ti is based on Aug. 13, 2015 Secondary Market Tin Bearing >85% = $0.55 / lb | [6 empty] | -0.36
| * Ad Brass is based of Aug. 14, 2015 Secondary Market Yellow Brass = $1.66 | [6 empty] | -1.7513
| * 90-10 CU-NI is based on Aug. 18, 2015 Secondary Market Cupro-Nickel Scrap 90-10 = $2.07 | [6 empty] | -1.5825
| *304 SS - is based on Aug. 17, 2015 LME 304 (18-8) Scrap Solids Processor = $0.50 / lb | [6 empty] | -0.27326

## Sheet1
3120000AA | 312 | 1 | 1LR | BARRY-ASB | 22961.0656 | SF | 70 | 1607274.5902 | SFTNSIDING (ASBESTOS) | SFTNSIDING (ASBESTOS) | 70 | 1607274.5902 | ASB | 100 | GULF | REMOVAL | SCS | MARKUP | 3120000AA11LRBARRY-ASB22961.0655737705SF70SFTNSIDING (ASBESTOS)
3120000AA | 312 | 1 | 1LD | BARRY-ASB | 47.0702 | TN | 345.389 | 16257.5257 | SFTNSIDING (ASBESTOS) | SFTNSIDING (ASBESTOS) | 345.389 | 16257.5257 | ASB | 100 | GULF | DISPOSAL | SCS | MARKUP | 3120000AA11LDBARRY-ASB47.07018448TN345.38903725058SFTNSIDING (ASBESTOS)
3040000 | 304 | 1 | 1LR | BARRY-ASB | 0 |  |  | 0 | CONTINGENCY |  | 0 | 0 | ASB | 100 | GULF | REMOVAL | SCS |  | 304000011LRBARRY-ASB0CONTINGENCY
3120000AA | 312 | 2 | 2LR | BARRY-ASB | 22961.0656 | SF | 70 | 1607274.5902 | SFTNSIDING (ASBESTOS) | SFTNSIDING (ASBESTOS) | 70 | 1607274.5902 | ASB | 100 | GULF | REMOVAL | SCS | MARKUP | 3120000AA22LRBARRY-ASB22961.0655737705SF70SFTNSIDING (ASBESTOS)
3120000AA | 312 | 2 | 2LD | BARRY-ASB | 47.0702 | TN | 345.389 | 16257.5257 | SFTNSIDING (ASBESTOS) | SFTNSIDING (ASBESTOS) | 345.389 | 16257.5257 | ASB | 100 | GULF | DISPOSAL | SCS | MARKUP | 3120000AA22LDBARRY-ASB47.07018448TN345.38903725058SFTNSIDING (ASBESTOS)
3040000 | 304 | 2 | 2LR | BARRY-ASB | 0 |  |  | 0 | CONTINGENCY |  | 0 | 0 | ASB | 100 | GULF | REMOVAL | SCS |  | 304000022LRBARRY-ASB0CONTINGENCY
3080268 | 308 | C | CLR | BARRY-ASB | 1 | LT | 2571.6393 | 2571.6393 | PERMITS | PERMITS | 2571.6393 | 2571.6393 | ASB | 100 | GULF | REMOVAL | SCS |  | 3080268CCLRBARRY-ASB1LT2571.63934426229PERMITS
3080241 | 308 | C | CLR | BARRY-ASB | 1 | % | 32145.4918 | 32145.4918 | SCS ENGINEERING | GPC ENGINEERING | 32145.4918 | 32145.4918 | ASB | 100 | GULF | REMOVAL | SCS |  | 3080241CCLRBARRY-ASB1%32145.4918032787SCS ENGINEERING
3070201 | 307 | C | CLR | BARRY-ASB | 1 | % | 32145.4918 | 32145.4918 | TEMPORARY CONSTRUCTION SERVICES | TEMPORARY CONSTRUCTION SERVICES | 32145.4918 | 32145.4918 | ASB | 100 | GULF | REMOVAL | SCS |  | 3070201CCLRBARRY-ASB1%32145.4918032787TEMPORARY CONSTRUCTION SERVICES
3080361 | 308 | C | CLR | BARRY-ASB | 0.6 | % | 32145.4918 | 19287.2951 | WRAP-UP AND ALL-RISK INSURANCE | WRAP-UP AND ALL-RISK INSURANCE | 32145.4918 | 19287.2951 | ASB | 100 | GULF | REMOVAL | SCS |  | 3080361CCLRBARRY-ASB0.6%32145.4918032787WRAP-UP AND ALL-RISK INSURANCE
3090481 | 309 | C | CLR | BARRY-ASB | 1 | % | 32145.4918 | 32145.4918 | ADMINISTRATIVE & GENERAL OVERHEAD | ADMINISTRATIVE & GENERAL OVERHEAD | 32145.4918 | 32145.4918 | ASB | 100 | GULF | REMOVAL | SCS |  | 3090481CCLRBARRY-ASB1%32145.4918032787ADMINISTRATIVE & GENERAL OVERHEAD
3040000 | 304 | C | CLR | BARRY-ASB | 0 |  |  | 0 | CONTINGENCY |  | 0 | 0 | ASB | 100 | GULF | REMOVAL | SCS |  | 3040000CCLRBARRY-ASB0CONTINGENCY
3110230 | 311 | C | CLR | BARRY-ASH | 596 | AC | 32100.5185 | 19131909.0199 | Ash Disposal Pond | Ash Disposal Pond | 32100.5185 | 19131909.0199 | ASH | 100 | GULF | REMOVAL | SCS |  | 3110230CCLRBARRY-ASH596AC32100.5184897273Ash Disposal Pond
3040000 | 304 | C | CLR | BARRY-ASH | 0 |  |  | 0 | CONTINGENCY |  | 0 | 0 | ASH | 100 | GULF | REMOVAL | SCS |  | 3040000CCLRBARRY-ASH0CONTINGENCY

## Scrap Values
#REF!
| 11328802 |  |  |  | 2015-11-06 | 2015-11-06 |  | 2015-12-31 |  | 2015-12-31
| #REF! | Unit |  |  | Unit | ADJ Unit |  | Unit |  | ADJ Unit
|  | Price |  | Change | Price | Price | Historical Links | Price |  | Price
* FE is based on the Aug. 7, 2015 Metal Prices Birmingham P&S 5' & under = $245 / GT | 245 | -180.5263 | 73.68% | -56.7363 | 168 | -123.79 | http://www.metalprices.com/historical/database/ferrous-scrap-price-index/fe-spi-5-plate-structural-birmingham | 184 | LME | 135.5789
* AL is based on Aug. 18, 2015 LME Cash Official = $0.69/lb | 0.69 | -0.39039 | 56.58% | -0.010395 | 0.67 | -0.38 | http://www.metalprices.com/historical/database/aluminum/lme-aluminum-cash-official | 0.6829 |  | 0.38638
* CU is baesd on Aug. 18, 2015 LME Cash Official = $2.27/lb | 2.27 | -0.37018 | 16.31% | -0.00018462 | 2.29 | -0.37 | http://www.metalprices.com/historical/database/copper/lme-copper-cash-official | 2.2759 | LME | 0.37115
* SS is based on Aug. 17, 2015 LME 304 (18-8) Scrap Solids Processor = $0.50 / lb | 0.5 | -0.18394 | 36.79% | -0.02394 | 0.44 | -0.16 | http://www.metalprices.com/historical/database/stainless-steel/stainless-steel-304-s-p |  |  | 0
*305 SS - is based on Aug. 17, 2014 LME 304 (18-8) Scrap Solids Processor = $0.50 / lb | 0.5 | -0.22371 | 44.74% | -0.023711 | 0.44 | -0.2 | http://www.metalprices.com/historical/database/stainless-steel/stainless-steel-304-s-p |  |  | 0
* Transformers is based on Aug. 18, 2015 LME Cash official for CU = $2.27 |  | -460.9846 | [7 empty] | 0
*Ti is based on Aug. 13, 2015 Secondary Market Tin Bearing >85% = $0.55 / lb | 0.55 | -0.36 | 65.45% | -0.11 | 0.375 | -0.25 | http://www.metalprices.com/metal/titanium/titanium-scrap-ferro-ti-quality-turnings-non-tin-bearing-gt-85-ti |  |  | 0
* Ad Brass is based of Aug. 14, 2015 Secondary Market Yellow Brass = $1.66 | 1.66 | -1.7513 | 105.5% | -0.0513 | 1.61 | -1.7 | http://www.metalprices.com/historical/database/brass/brass-yellow-brass |  |  | 0
* 90-10 CU-NI is based on Aug. 18, 2015 Secondary Market Cupro-Nickel Scrap 90-10 = $2.07 | 2.07 | -1.5825 | 76.45% | -0.0625 | 1.99 | -1.52 | http://www.metalprices.com/metal/cupro-nickel/cupro-nickel-c706 |  |  | 0
*304 SS - is based on Aug. 17, 2015 LME 304 (18-8) Scrap Solids Processor = $0.50 / lb | 0.5 | -0.27326 | 54.65% | -0.033256 | 0.44 | -0.24 | http://www.metalprices.com/historical/database/stainless-steel/stainless-steel-304-s-p |  |  | 0
| 2015-11-06 | 2015-11-06
| Unit | ADJ Unit
| Price | Price
* FE is based on the 06NOV15, 2015 Metal Prices Birmingham P&S 5' & under = $168 / GT | 168 | -123.79
* AL is based on 06NOV15, 2015 LME Cash Official = $0.67/lb | 0.67 | -0.38
* CU is based on 06NOV15, LME Cash Official = $2.29/lb | 2.29 | -0.37
* SS is based on 06NOV15, LME 304 (18-8) Scrap Solids Processor = $0.44 / lb | 0.44 | -0.16
*305 SS - is based on 06NOV15, LME 304 (18-8) Scrap Solids Processor = $0.44 / lb | 0.44 | -0.2
* Transformers is based on 06NOV15, LME Cash Official = $2.29/lb
*Ti is based on 06NOV15, Secondary Market Tin Bearing >85% = $0.375 / lb | 0.375 | -0.25
* Ad Brass is based of 06NOV15, Secondary Market Yellow Brass = $1.61 | 1.61 | -1.7
* 90-10 CU-NI is based on 06NOV15, Secondary Market Cupro-Nickel Scrap 90-10 = $1.99 | 1.99 | -1.52
*304 SS - is based on 06NOV15, LME 304 (18-8) Scrap Solids Processor = $0.44 / lb | 0.44 | -0.24