## Overview
No. | System | Project | Amount
PCF -1 | Cypress Lakes | Hydro Tank Replacement | 25732
PCF -2 | Cypress Lakes | Sediment Removal from WWTP | 50200
PCF -3 | Eagle Ridge | WWTP EQ tank and headworks | 106387.7
PCF - 4 | Labrador | WWTP Sediment Removal | 61137
PCF - 5 | LUSI | Sludge Dewatering Equipment | 240000
PCF - 6 | LUSI | Oswalt Road WM Relocation | 181400
PCF - 7 | LUSI | SCADA | 458901.96
PCF - 8 | LUSI | TTHM & HAA5 Study | 79250
PCF - 9 | LUSI | Engineering TTHM & HAA5 Remediation - Engineering design and permitting | 0
PCF - 10 | LUSI | US 27 Utility relocations; 8650 ft 16" and 2800 ft 12" | 1806000
PCF - 11 | Longwood | Church Ave Utility Reloc. | 193880
PCF - 12 | Longwood | I&I study | 50000
PCF - 13 | Longwood | I&I Remdiation | 0
PCF - 14 | Mid-County | Electical Improvements and Generator | 0
PCF - 15 | Mid-County | Field Office | 65000
PCF - 16 | Mid-County | Flow Study ( I&I) | 80000
PCF - 17 | Mid-County | Excess I&I Remediation | 0
PCF - 18 | Mid-County | Methonal Pumps and Nutrient Analyzer | 92575.7
PCF - 19 | Mid-County | US Hwy 19 Relocation; 525 ft 6" FM and 190 ft 8" GM | 172879
PCF - 20 | Pennbrooke | WTP Electrical Imp. | 0
PCF - 21 | Sandalhaven | Placida Rd. Utility Relocatio | 217034.4
PCF - 22 | Sanlando | Autumn Dr WM Replacement: 900 ft, 6" pipe | 98970
PCF - 23 | Sanlando | Lift Station RTU Installation | 353200
PCF - 24 | Sanlando | Markham Wood Utility Relocates; 240 ft 10" pipe | 65900
PCF - 25 | Sanlando | Myrtle Lake Hills WM | 684271.16
PCF - 26 | Sanlando | I&I Study and Remediation | 1573884
PCF - 27 | Sanlando | Shadow Hills Flow Diversion | 0
PCF - 28 | Sanlando | Wekive WWTP Blower Replacement | 0
PCF - 29 | Sanlando | Well 2A Lift Station A1 electical improvements; generator | 343437
PCF - 30 | Sanlando | Wekive WWTP Rehabilitation | 1729034.1
PCF - 31 | Tierra Verde | 8th Ave Gravity Main Replacement Ph 2; 40 ft VCP | 84673
PCF - 32 | UIF - Orange Crescent Hts | Crescent HtsWM Replacement | 1806000
PCF - 33 | UIF - Pasco | Orangewood, Buena Vista WM Replacement | 0
PCF - 34 | UIF - Pasco | Summertree Well Abandonment | 0
PCF - 35 | UIF - Pinellas | Lake Tarpon WM Replacement | 800000
PCF - 36 | UIF - Seminole | Electrical Imp. At Little Wekiva and Jansen WTPs | 268830
PCF - 37 | UIF - Seminole & Orange | WM Replacements | 0
PCF - 38 | UIF - Seminole | Bear Lake WM Replacement | 1485270
PCF - 39 | UIF - Seminole | Crystal Lake WM Replacement | 1585933
PCF - 40 | UIF - Seminole | Little Wekiva WM Replacement | 521681
PCF - 41 | UIF - Seminole | Northwestern FM Replacement (Weathersfield) | 120000
PCF - 42 | UIF - Seminole | Oakland Shores WM Replacement | 1571701
PCF - 43 | UIF - Seminole | Phillips WM Replacement | 1188247
PCF - 44 | UIF - Seminole | Ravenna Park WM Replacement | 2160808
PCF - 45 | UIF - Seminole | Ravenna Park /Crystal Lake Interconnect | 646000
PCF - 46 |  | Truck Upgrade | 44000
PCF - 47 |  | GIS Mapping Services | 244321

## Revised Exhibits Staff 7th ROGs
No. | System | Project | Flynn Testimony Amount | Status | Notes | Amount
PCF - 1 | Cypress Lake | Hydro Tank Replacement | 30000 | Signed proposal | per staff 7th ROGs | 25732
PCF - 9 | LUSI | Engineering TTHM & HAA5 Remediation - Engineering design and permitting | 450000 | Signed proposal | per staff 7th ROGs | 330832
PCF - 13 | Longwood | I&I Remdiation | 450000 | Estimate from Traverse signed agreement with insituform | per staff 7th ROGs; Need evidence of bids for work; agreement w Traverse and NTP | 92832
PCF - 17 | Mid-County | Excess I&I Remediation | 600000 | Some invoices some quotes | Hach quote greater than $50k | 58975.26
PCF - 20 | Pennbrooke | WTP Electrical Imp. | 270000 | Agreements; invoices | missing support for Leesburg Elect | 400937
PCF - 27 | Sanlando | Shadow Hills Flow Diversion | 4243423 | bid tabs; unsigned agreeements | nothing really supported | 0
PCF - 33 | UIF - Pasco | Orangewood, Buena Vista WM Replacement | 1200000 | signed agreement; NTP | bid? | 2066888
PCF - 34 | UIF - Pasco | Summertree Well Abandonment | 200000 | no back up |  | 0

## Summary
CAPITAL PROJECTS
UPDATED PER PCF REVISED TESTIMONY
No. | System | Project | Amount | Date Complete | Status | Notes |  | Actual Amount
PCF -1 | Cypress Lakes | Hydro Tank Replacement | 30000 | Feb. 2017 | Not bid | Per Staff ROG 2 bids are pending |  | 25732 | OPC POD 63
PCF -2 | Cypress Lakes | Sediment Removal from WWTP | 50200 | Sept. 2016 | Bid received; | check on if it is done and final amounts; is sediment removal a capital item? | Per Staff ROG UIF is ammotizing over 10 years the cost | 50200 | ok
PCF -3 | Eagle Ridge | WWTP EQ tank and headworks | 350000 | Sept. 2017 | Difficult to tell from documentation | Excel eng $8900; Env. Equip Sales 20262.70; Bob Dean Sup $10450; Davey 38850 | Per Staff ROG 2, project not yet bid | 106387.7 | Documented costs through OPC POD 64,65
PCF - 4 | Labrador | WWTP Sediment Removal | 61137 | Sept. 2016 | Bid received; | check on if it is done and final amounts; is sediment removal a capital item? | Per Staff ROG 2 project is complete. See PCF 2 | 61137 | ok
PCF - 5 | LUSI | Sludge Dewatering Equipment | 245000 | Dec. 2016 | Done | check on if it is done and final amounts; | Per Staff ROG 2 project is complete and in pilot testing | 240000 | no supportin info for tractor equipment
PCF - 6 | LUSI | Oswalt Road WM Relocation | 181400 | Dec. 2016 | Supported by bid forms and pay requests | check on if it is done and final amounts; |  | 181400 | ok
PCF - 7 | LUSI | SCADA | 470000 | Jul. 2016 | Supported by bid forms and pay requests | Looks complete; verfiy during site insp |  | 458901.96 | cost doesn’t match staff
PCF - 8 | LUSI | TTHM & HAA5 Study | 79250 | Sept. 2016 | Done | Ask for copies of Study |  | 79250 | ask for copy of study
PCF - 9 | LUSI | Engineering TTHM & HAA5 Remediation - Engineering design and permitting | 450000 | not done | marked held for future use in revised PCF 9 | Seems high for just engineering services |  | 0
PCF - 10 | LUSI | US 27 Utility relocations; 8650 ft 16" and 2800 ft 12" | 1806000 | Jun. 2017 | Bids received; const. on-going | Seems well documented verify construction during site visit | Per Staff ROG 2 project nearly finished construction; project costs less than bid | 1828908.5 | ok
PCF - 11 | Longwood | Church Ave Utility Reloc. | 193880 | agmt signed 8/2016 | may be under construction; no pay requests provided | Find out status; ask for pay requests; cost seems reasonable | Revised exhibit submitted with Staff POD 2 | 253524 | ok
PCF - 12 | Longwood | I&I study | 50000 | Nov. 2016 | not sure if done | no bid info; double check on cost |  | 50000 | ok
PCF - 13 | Longwood | I&I Remdiation | 450000 | NO PCF-13 PROVIDED IN REVISED EXHIBITS
PCF - 14 | Mid-County | Electical Improvements and Generator | 900000 | Jun. 2017 | Looks like it's in the design phase | APG provide on-site RPR services, two days a week. Is that necessary? Looks like also preliminary quote from APG electric on the drawings. Project sheet shows const. TBD and other costs at 140k | Per Staff ROG 2 construction in process.; ask for bids | 0 | based on OPC POD 69 does not seem to be competitively bid
PCF - 15 | Mid-County | Field Office | 65000 | Jul. 2016 | Done | price seems reasonable |  | 65000
PCF - 16 | Mid-County | Flow Study ( I&I) | 80000 | Jun. 2016 | not sure if done | Ask for copies of Study; Mid County does not have excess I&I by U&U standards | Need price back up ??? | 80000 | check numbers
PCF - 17 | Mid-County | Excess I&I Remediation | 600000 | not done | marked held for future use in revised PCF 17
PCF - 18 | Mid-County | Methonal Pumps and Nutrient Analyzer | 102000 | Nov. 2016 from exhbit PCF 18 | appears to be done | review during site inspections | Tri nova 38608.70; Chem scan 41467; App Spec 29026.9; EMS 12500 | 92575.7 | ok
PCF - 19 | Mid-County | US Hwy 19 Relocation; 525 ft 6" FM and 190 ft 8" GM | 230000 | Jul. 2017 | not done? | needs more supporting documentation for numbers especially engineering | Check status; ask for engineering contracts | 172879 | only allow supported data
PCF - 20 | Pennbrooke | WTP Electrical Imp. | 270000 | held for future use | held for future use
PCF - 21 | Sandalhaven | Placida Rd. Utility Relocatio | 250000 | Dec. 2017 | looks like it's been designed but not constructed | ask for supporting info | Check status; not bid yet; engineering cost provided | 217034.4 | CPH invoice from 2011
PCF - 22 | Sanlando | Autumn Dr WM Replacement: 900 ft, 6" pipe | 98970 | Oct. 2016 | not sure if complete | ask for status |  | 98970
PCF - 23 | Sanlando | Lift Station RTU Installation | 353200 | ??? | lacking documentation | Ammended Exhibit in Staffs 4th POD |  | 584770 | ok
PCF - 24 | Sanlando | Markham Wood Utility Relocates; 240 ft 10" pipe | 65900 | May. 2016 | done | cost reasonable |  | 65900 | ok
PCF - 25 | Sanlando | Myrtle Lake Hills WM | 695450 | Oct. 2016 | done | may have implications for U&U in Sanlando depending on how many have connected. Legal costs legit for capitalization? |  | 684271.16
PCF - 26 | Sanlando | I&I Study and Remediation | 1573884 | not sure | Ammended Exhibit in Staffs 4th ROGs |  |  | 1593982.53
PCF - 27 | Sanlando | Shadow Hills Flow Diversion | 4243423 | Expected Dec. 2017 | Alternatives analysis complete; no design or construction | Cost estimate as sufficient to add to rate base? schedule is imprortant |  | no bids for work
PCF - 28 | Sanlando | Wekive WWTP Blower Replacement | 600000 | Oct. 2017 | held for future use
PCF - 29 | Sanlando | Well 2A Lift Station A1 electical improvements; generator | 343437 | Dec. 2016 | presumably done | pay invoices would be good to ensure project costs; review during inspections |  | 343437
PCF - 30 | Sanlando | Wekive WWTP Rehabilitation | 1803000 | Jun. 2017 | cleaning was underway | verify low bidder still under contract and able to work. get update on status. | Per Staff ROG 4 work under way again; taxes added extra ask abou this in discovery | 1729034.1 | resolved taxes per response to OPC POD 76
PCF - 31 | Tierra Verde | 8th Ave Gravity Main Replacement Ph 2; 40 ft VCP | 84673 | Mar. 2016 | completed | cost reasonable |  | 84673
PCF - 32 | UIF - Orange Crescent Hts | Crescent HtsWM Replacement | 1806000 | Mar.2017 | should be underway |  |  | 1806000
PCF - 33 | UIF - Pasco | Orangewood, Buena Vista WM Replacement | 1200000 | Dec. 2016 | held for future use
PCF - 34 | UIF - Pasco | Summertree Well Abandonment | 200000 |  | held for future use
PCF - 35 | UIF - Pinellas | Lake Tarpon WM Replacement | 800000 | Mar. 2017 | Bids received; | Request Schedule of Values; requests; signed agreement is over $1 million | Revised exhibit submitted with Staff ROG 4 | 1089446 | supported costs
PCF - 36 | UIF - Seminole | Electrical Imp. At Little Wekiva and Jansen WTPs | 323000 | Sep. 2016 | looks complete | submitted info is higher than what’s in the testimony; have someone look at the SCADAONE bids for reasonableness |  | 268830
PCF - 37 | UIF - Seminole & Orange | WM Replacements | 57000 | Sep. 2016 | engineering only | get status update; supporting documentation is higher than the number in the testimony |  | included with other projects
PCF - 38 | UIF - Seminole | Bear Lake WM Replacement | 1485270 | Mar. 2017 | project bid; construction? | get status update; |  | 1485270
PCF - 39 | UIF - Seminole | Crystal Lake WM Replacement | 1585933 | Jun. 2017 | project bid; construction? | get status update; |  | 1585933
PCF - 40 | UIF - Seminole | Little Wekiva WM Replacement | 521681 | Jun. 2017 | project bid; construction? | get status update; |  | 521681
PCF - 41 | UIF - Seminole | Northwestern FM Replacement (Weathersfield) | 120000 | Dec. 2106 | only design contract provided | no bid info; double check on cost; no cost estimate | Per Staff ROG 4 bids provided | 688630.73
PCF - 42 | UIF - Seminole | Oakland Shores WM Replacement | 1571701 | Sep. 2017 | project bid; construction? | get status update; |  | 1571701
PCF - 43 | UIF - Seminole | Phillips WM Replacement | 1188247 | Sep. 2017 | project bid; construction? | get status update; |  | 1188247
PCF - 44 | UIF - Seminole | Ravenna Park WM Replacement | 2160808 | Mar. 2017 | project bid; construction? | get status update; |  | 2160808
PCF - 45 | UIF - Seminole | Ravenna Park /Crystal Lake Interconnect | 646000 | Sept. 2016 | project looks complete | verify it's in service. Ask for supporting documentation on alternative analysis |  | 645835
PCF - 46 |  | Truck Upgrade | 44000 |  |  |  |  | 44000
PCF - 47 |  | GIS Mapping Services | 350000 | 0 |  |  |  | 244321
|  | Original | 30835444
KEY
|  | Project Excluded; no information provided |  |  | 3770000
|  | Amount presented in Flynn's testimony is not unreasonable |  |  | 17016571 |  |  |  |  | 18208703.76
|  | Amount should be lower than Flynn's testimony |  |  | 4905450 | 4239967.02 | 665482.98
|  | Inadequate or too late |  |  | 5143423
|  | Net Adjustments |  |  | 21256538.02

## PCF 20
from revised Flynn exhibit supplied in respone to staff ROG 179
| Agreement w Chinchor |  | 311453 | agreement
| Bailley |  | 19900 | invoice
| SCADA One |  | 69584 | agreement
|  | Total | 400937

## PCF 17
from revised Flynn exhibit supplied in respone to staff ROG 179
| Altair |  | 17550 | invoice
| Altair |  | 22244.49 | invoice
| Altair |  | 2470.61 | invoice
| Hach |  | 58489 | Quote
| Pasco Pipe |  | 1955.16 | reciept
| EES |  | 14755 | proposal
Blue Book Web Page?
|  | Total | 117464.26
|  | less Hach quote | 58489 | should be bid
|  | Net | 58975.26

## ATW - 16
Flynn Exhibit Number | System | Project | Cost per Flynn's Testimony | Recommended Costs | Reason
PCF -1 | Cypress Lakes | Hydro Tank Replacement | 30000 | 25732 | Remainder unsupported
PCF -3 | Eagle Ridge | WWTP EQ tank and headworks | 350000 | 106387.7 | Unsigned agreement with contractor
PCF - 5 | LUSI | Sludge Dewatering Equipment | 245000 | 240000 | Remainder unsupported
PCF - 7 | LUSI | SCADA | 470000 | 458901.96 | Remainder unsupported
PCF - 18 | Mid-County | Methonal Pumps and Nutrient Analyzer | 102000 | 92575.7 | Remainder unsupported
PCF - 19 | Mid-County | US Hwy 19 Relocation; 525 ft 6" FM and 190 ft 8" GM | 230000 | 172879 | Remainder unsupported
PCF - 21 | Sandalhaven | Placida Rd. Utility Relocatio | 250000 | 217034.4 | Remainder unsupported
PCF - 25 | Sanlando | Myrtle Lake Hills WM | 695450 | 684271.16 | Remainder unsupported
PCF - 30 | Sanlando | Wekive WWTP Rehabilitation | 1803000 | 1729034.1 | Adjusted for taxes on equipment only
PCF - 36 | UIF - Seminole | Electrical Imp. At Little Wekiva and Jansen WTPs | 323000 | 268830 | Remainder unsupported
PCF - 37 | UIF - Seminole & Orange | WM Replacements | 57000 | 0 | Included elsewhere
PCF - 47 |  | GIS Mapping Services | 350000 | 244321 | Remainder unsupported
|  | Totals | 4905450 | 4239967.02

## PCF - 31
From Flynn Revised testimony
| Award | 659470
| Kimley Horn | 20000
| Friedman | 324.08
1640
1037.08
684
612
324
72
108
684271.16

## Sheet1
CAPITAL PROJECTS
Exhibit | System | Project | Verified Amount
PCF -2 | Cypress Lakes | Sediment Removal from WWTP | 50200
PCF - 4 | Labrador | WWTP Sediment Removal | 61137
PCF - 6 | LUSI | Oswalt Road WM Relocation | 181400
PCF - 7 | LUSI | SCADA | 458901.96
PCF - 10 | LUSI | US 27 Utility relocations; 8650 ft 16" and 2800 ft 12" | 1794908.5
NONE | LUSI | Flow Splitter | 78000
PCF - 11 | Longwood | Church Ave Utility Reloc. | 253524
PCF - 12 | Longwood | I&I study | 49970
PCF - 15 | Mid-County | Field Office | 65000
PCF - 18 | Mid-County | Methonal Pumps and Nutrient Analyzer | 92575.7
PCF - 23 | Sanlando | Lift Station RTU Installation | 584770
PCF - 24 | Sanlando | Markham Wood Utility Relocates; 240 ft 10" pipe | 65900
PCF - 26 | Sanlando | I&I Study and Remediation | 1593982.53
PCF - 29 | Sanlando | Well 2A Lift Station A1 electical improvements; generator | 343437
PCF - 31 | Tierra Verde | 8th Ave Gravity Main Replacement Ph 2; 40 ft VCP | 84673
PCF - 35 | UIF - Pinellas | Lake Tarpon WM Replacement | 1089446
PCF - 36 | UIF - Seminole | Electrical Imp. At Little Wekiva and Jansen WTPs | 268830
7116655.69

## PCF -3
from Revised PCF Exhibits
| Excel Engineering | 16347 | includes CO
| Environmental Equipment | 20262.7 | driveways
| Bob Dean | 10450 | splitter box
| Environmental Equipment | 7000 | install splitter box
| Davey | 38850 | trees not including continuing maintenance
| Total | 92909.7
from response to OPC POD 65
| Excel Engineering | 33567
| Environmental Equipment | 670363 | did not provide bid forms only a bid comparison
agreement has been delayed until consturction permit is received
| EMS | 17645 | SCADA for flow eq; Estimate
| Volition | 5368.25 | Instrumentation; Quote
| ESR | 13478 | walkway around holding tank; Agreement and invoice
| Armor Aluminun Fab. | 8850 | walkway estimate only
| Mod Space | 52664.5 | missing first 15 pages; no signed agreement or invoices
801935.75
What is actually documented
From revised PCF Exhibit
| Excel Engineering | 16347 | includes CO
| Environmental Equipment | 20262.7 | driveways
| Bob Dean | 10450 | splitter box
| Environmental Equipment | 7000 | install splitter box
| Davey | 38850 | trees not including continuing maintenance
From POD 65
| ESR | 13478 | walkway around holding tank; Agreement and invoice
| Total | 106387.7
By account
| Plant | 47275
59112.7
106387.7

## PCF - 5
From Revised Flynn Testimony
| SolarOrganite | 160000
| Eco 2000 | 40000
| PA Tech | 40000

## PCF - 7
From PCF revised exhibits
| CPH | 58425
| CPH | 35000
| scada one | 288131.34
| scada one | 5772
| scada one | 4040
| scada one | 2951.08
| verizon | 779.84
| bright house | 600
| Avanti | 1228.06
| Avanti | 1328.42
| Avanti | 1125
| ims | 2755.25
| innovative | 360
| innovative | 250
| innovative | 250
| innovative | 250
| innovative | 846
| innovative | 600
| innovative | 465
| innovative | 1640
| KW | 1867.87
7980.8
2989.85
1370
2002.05
| north lake | 16628
3037
| Volition | 12490
| Verizon | 3739.4
458901.96

## PCF - 10 10a
From PCF revised exhibits
| CPH | 62990 | scope
| Traverse | 1706668.5 | pay request total
|  | 59250 | C O s from pay requests
1828908.5
Breakout by account
from pay request
| Water main | Force Main | Reclaimed
| 10650 | 750 | 4400
| 392232.5 | 153604 | 75701
| 157500 | 5500 | 1000
| 19600 |  | 8000
| 4620 |  | 400
| 3250 |  | 500
| 15600 |  | 1200
| 1300 |  | 2150
| 1500 |  | 3500
| 12500 |  | 250
| 45150 |  | 126000
750
| 148500 |  |  | Total
| 813152.5 | 159854 | 223101 | 1196107.5
| 0.67983 | 0.13365 | 0.18652
Allocated amount
| WM | FM | RM
actual | 1243351.0525 | 244424.8024 | 341132.6451 | 1828908.5
requested | 1227777.1145 | 241363.1919 | 336859.6936 | 1806000 | 1806000

## PCF - 12
From revised PCF 12 received Feb 22
| American In-line Insp. | 49970

## PCF - 14
From OPC POD 69
| APG | 999200 | questionable does seem to be competitvely bid
|  | 15000 | permit allowance
UIF did not provide second bid as asked for in POD 69

## PCF 18
From PCF revised exhibits
| ASA | 41467
| tri nova | 38608.7
| EMS | 12500
|  | 92575.7 | clarification per staff ROG 94

## PCF 19
From Revised Flynn Testimony
| Environmental Equip | 107054
| Environmental Equip | 49700
| SPT | 16125
| Total | 172879
Breakdown
|  | FM | GM | Total
| Bid | 107054
| CO |  | 49700
| SPT |  | 16125
| Total | 107054 | 65825 | 172879

## PCF - 21
From PCF revised exhibits
| CPH | 29000 | from 2011????
| Kimley Horn | 19244
Added per OPC POD 72
| Envornmental Equip | 197790.4
217034.4

## PCF - 23
From PCF revised exhibits
| Bailey | 26200
| North Lake | 217250
| Scada One | 341320
584770

## PCF - 26
From Response to staff's 4th discovery
| Traverse | 875013.13
| Insituform | 718969.4
1593982.53

## PCF - 27
From PCF revised exhibits
| Kimley Horn | 236923
| CPH | 23500
from revised Flynn exhibit supplied in respone to staff ROG 179
| FEC (Des Pinar) |  | 3012273 | bid form
| CFT (Longwood FM) |  | 1443012 | bid tab
| Tri Sure (Sabal PS) |  | 2244445 | bid tab
| CES (WWTP demo) |  | 29750 | quote
| Thompson Elec (WWTP demo) |  | 600 | quote
| Terracon (mon well abandonment) |  | 5436 | unsigned auth to proceed
| Tri Sure (Springs FM) |  | 925350 | bid tab
| Evans Contracting (bldg) |  | 106659 | unsigned agreement; not bid?
|  | Total | 7767525

## PCF - 30
From Flynn Revised Exhibits
| Evoqua | 1526000 | low bid: with contract
| ECO 2000 | 158850 | tank cleaning
| ECO 2000 | 10534 | CO
| TAX | ???
No tax shown on ECO 2000 pay requests; it’s a serivce not materials so no tax
For Evoqua only invoices provided tax appears to be paid only on the equipment portion of the project so estiamte 6% of total equipment
56083.5
182912.4
150811.2
171027.9
560835
0.06
| tax | 33650.1
Total
| Evoqua | 1526000 | low bid: with contract
| ECO 2000 | 158850 | tank cleaning
| ECO 2000 | 10534 | CO
| Tax of Evoqua | 33650.1
| Total | 1729034.1

## PCF - 36
From Response to staff's 4th discovery
| Thompson | 83750
| Scada One | 146480
| Bailey | 14700
| Bailey | 12600
| Bailey | 11300
268830