## Int No. 62
Florida Power & Light Company Docket No. 20170007-EI Staff's Third Set of Interrogatories Interrogatory No. 62 Attachment No. 1 Tab 1 of 1
| a. | b. | c. | d.
Activity | Estimated Completion | Type of Activity | Capital | O&M
Implementation of the Nutrient Management Plan and Thermal Efficiency Plan, as directed by the FDEP | Both plans have near term activities targeted to be completed within five years, and long term components that could take longer than 5 years to complete. Please see the NMP and TEP reports for additional detail (Attachment Nos. 2 & 3 respectively). | 74% abatement - 26% remediation | 0 | 1633408
Completion of the Upper Floridan Aquifer Well System to provide up to 14 million gallons per day (MGD) of low salinity freshening water | Complete | 74% abatement - 26% remediation | 8135181 | 0
Permitting and construction activities related to the implementation of the RWS | March 2018 | 74% abatement - 26% remediation | 8630043 | 3430928
Initiation of an analysis with input from the FDEP and other agencies expanding the variable density three demisional groundwater model developed under the 2015 CA to allocate relative contributions of other entities or factors to the movement of the saltwater interface | June 2018 | 100 % Remediation | 654509 | 242625
Design and permitting activities related to the restoration projects in the Barge Basin and Turtle Point Canal | February 2018 | 100% abatement | 2335478 | 0
Implementation of berm and dike maintenance recommendations resulting from the CCS periphery inspection | December 2017 | 100% abatement | 0 | 0
Execution of an agreement with the SFWMD to convey FPL property interests | March 2018 | 100% mitigation | 0 | 0
Depositing $1.5 million into a Florida Department of Financial Services escrow account to finance projects that mitigate saltwater intrusion in the region | December 2017 | 100% mitigation | 0 | 0
Conducting a baseline CSEM survey of the hypersaline plume prior to initiation of RWS | March 2018 | 100% remediation | 0 | 0
Permitting, construction, and other activities related to additional monitoring wells and sampling activities | Permitting complete, construction December 2017 | 100% remediation |  | 1308752
Preparing and submitting the annual monitoring report | September 2017 | 50% remediation, 50% abatement | 0 | 0
Additional activities including regular status meetings with the FDEP as needed to comply with required monitoring and reporting | Ongoing through duration of Consent Order | 40% abatement – 40% remediation – 20% mitigation | 0 | 0
Total |  |  | 19755211 | 6615713