## Sheet1
|  |  |  | DRAFT |  |  |  |  | Filename: 2016 Approach for SE Florida Analyses
|  |  |  | Outline of Approach for 2016 SE Florida Analyses |  |  |  |  | 2016-06-08
I. Initial Set-Up Work: | Development | RAP | TSP | EMT | Eng. & Construction | Project Mgt-T&S | Environmental | Projected Time to Complete | Comments
Provide annual MW and locations for large scale PV outside of SE Fla region for use as a "given" resource in all resource plans that will be developed) | X | [6 empty] | 1 week | Expected week of June 13
Develop FPL System MW resource needs by year thru 2030 to determine how many MW of new generation are needed |  | X | [5 empty] | 2-3 days | Preliminary results show ~3,300 MW needed from 2023 thru 2030
Provide feasible locations for CCs and CTs outside of SE Fla | X |  |  | X | X | X | X | 2 weeks ? | Initial meeting to be held June 14
Provide timelines for securing new gas delivery to sites outside and inside SE Fla. | X |  |  | X |  |  |  | TBD | ---
Determine earliest feasible start year for CCs and CTs at the selected sites | X |  |  | X | X | X | X | TBD | ---
II. Each Analysis Iteration (See Notes below) | Development | RAP | TSP | EMT | Eng. & Construction | Project Mgt-T&S | Environmental | Projected Time to Complete | Comments
Assist with coordination and removing analysis bottlenecks (as needed) | X | [6 empty] | On-going | ---
Provide additional feasible locations for CCs, CTs, modernization/upgrades etc, both inside SF as well as outside, beyond those already identifed in I above. | X |  |  | X | X | X | X | by ????
Create resource plans (type of resources to be added by year and by location, but without costs), then provide to TSP and E&C |  | X | [5 empty] | 2-3 days (assuming all needed informatin is in hand) | ---
Perform load flow analyses for each resource plan to: (i) develop needed SE Fla transmission facilities, then provide to Engineering, and (ii) develop annual and peak loss values, then provide to RAP |  |  | X |  |  |  |  | TBD (Will vary depending on the number of resource plans TSP is asked to evaluate) | ---
Develop capital costs for SE Fla transmission facilities, then provide to RAP (who will add O&M costs) | [5 empty] | X |  | " | This work follows after TSP's work
Develop costs and performance data for generation/gas delivery resources included in the resource plans (as appropriate for the iteration), then provide to RAP | X |  |  | X | X |  |  | " | This work can be proceed concurrently with TSP's work
Determine CPVRR costs for each resource plan |  | X | [5 empty] | 2 to 3 weeks (?) | This work follows delivery of the T/S and E&C results
Develop feasibility/risk/subjective rankings for the different resource plans | X | X | X | X | X | X | X | 1-2 weeks
Review results of this iteration, and recommendations for the next analysis iteration, with VPs | X | X | X | X | X | X | X | Within 1 week of completion of CPVRR cost analyses | Development & team develop PP deck summarizing results and next steps
Notes:
1) At least 3 iterations are projected: (i) with large scale fossil generation added outside of SE Florida only; (ii) with large scale fossil generation added both outside and inside
SE Florida, and (iii) same as (ii) but also with smaller scale solar, battery, etc. inside SE Florida. More iterations may be needed.
2) The team will be able to estimate the time to conduct each iteration once the initial iteration has been completed.
Note on B10: Author: Provide feasible locations, and specifc options that can be built at each site, including MW size