## TUG - 2020
Project Name/Circuit | Project Description | No. of Customers by Project | Number of Miles to Underground | Construction Start | Construction Finish | Capital Cost | O&M
TROPIC TERRACE - A207 | Inverness | 41 | 0.71 | 2020-06-26 | 2020-08-14 | 661584.39 | 8270.08 | 931809
ZUBER - A203 | Ocala | 10 | 0.4252 | 2020-05-19 | 2020-06-30 | 396205.1868 | 4952.7296
REDDICK - A34 | Ocala | 1 | 0.0964 | 2019-12-18 | 2020-01-15 | 89826.3876 | 1122.8672
LAND O LAKES - C141 | Seven Springs | 15 | 0.2548 | 2020-03-20 | 2020-04-13 | 237424.9332 | 2967.9104
MAXIMO - X143 | St. Petersburg | 40 | 0.4381 | 2020-06-01 | 2020-07-13 | 408225.5229 | 5102.9888
ZUBER - A204 | Ocala | 1 | 0.0756 | 2020-08-03 | 2020-09-04 | 70444.7604 | 880.5888
ZUBER - A204 | Ocala | 5 | 0.2423 | 2020-10-01 | 2020-11-11 | 225777.3207 | 2822.3104
ZUBER - A205 | Ocala | 8 | 0.1363 | 2020-10-01 | 2020-11-11 | 127005.5667 | 1587.6224
TARPON SPRINGS - C305 | Seven Springs | 78 | 0.8106 | 2020-07-13 | 2020-09-04 | 755324.3754 | 9441.8688
HIGH SPRINGS - A15 | Monticello | 3 | 0.3114 | 2020-07-01 | 2020-08-12 | 290165.3226 | 3627.1872
PORT ST JOE - N52 | Monticello | 57 | 0.6307 | 2020-07-01 | 2020-08-19 | 587691.9363 | 7346.3936
PIEDMONT - M473 | Apopka | 70 | 0.8807 | 2020-07-13 | 2020-09-04 | 820644.1863 | 10258.3936
SANTOS - A230 | Ocala | 2 | 0.1423 | 2020-05-05 | 2020-06-09 | 132596.4207 | 1657.5104
DINNER LAKE - K1685 | Highlands | 53 | 0.253 | 2020-04-24 | 2020-05-29 | 235747.677 | 2946.944
EUSTIS - M500 | Apopka | 6 | 0.0368 | 2020-03-09 | 2020-04-03 | 34290.5712 | 428.6464
COUNTRY OAKS - K1443 | Lake Wales | 2 | 0.097 | 2020-07-01 | 2020-07-29 | 90385.473 | 1129.856
CLERMONT - K601 | Clermont | 9 | 0.2275 | 2020-07-01 | 2020-08-05 | 211986.5475 | 2649.92
LAKE PLACID - K1320 | Highlands | 7 | 0.1046 | 2020-05-05 | 2020-06-02 | 97467.2214 | 1218.3808
MAXIMO - X143 | St. Petersburg | 7 | 0.1237 | 2020-03-16 | 2020-04-20 | 115264.7733 | 1440.8576
ZUBER - A204 | Ocala | 8 | 0.2809 | 2020-08-03 | 2020-09-14 | 261745.1481 | 3271.9232
COUNTRY OAKS - K1446 | Lake Wales | 42 | 0.3418 | 2020-08-03 | 2020-09-21 | 318492.3162 | 3981.2864
CLERMONT - K603 | Clermont | 53 | 0.4148 | 2020-08-03 | 2020-10-05 | 386514.3732 | 4831.5904
FORTIETH STREET - X84 | St. Petersburg | 9 | 0.0475 | 2020-02-24 | 2020-04-01 | 44260.9275 | 553.28
HAINES CITY - K20 | Lake Wales | 6 | 0.3101 | 2020-05-05 | 2020-06-09 | 288953.9709 | 3612.0448
CARRABELLE - N42 | Monticello | 25 | 0.5065 | 2020-08-03 | 2020-10-05 | 471961.2585 | 5899.712
WOLF LAKE - M564 | Apopka | 1 | 0.0332 | 2020-05-05 | 2020-06-02 | 30936.0588 | 386.7136
PORT RICHEY WEST - C202 | Seven Springs | 30 | 0.2833 | 2020-03-16 | 2020-04-27 | 263981.4897 | 3299.8784
EASTPOINT - N231 | Monticello | 4 | 0.0314 | 2020-07-01 | 2020-07-29 | 29258.8026 | 365.7472
JASPER SOUTH - N191 | Monticello | 1 | 0.2315 | 2020-03-27 | 2020-05-01 | 215713.7835 | 2696.512
DENHAM - C153 | Seven Springs | 5 | 0.2619 | 2020-01-27 | 2020-02-21 | 244040.7771 | 3050.6112
PORT RICHEY WEST - C208 | Seven Springs | 24 | 0.22 | 2020-03-09 | 2020-04-13 | 204997.98 | 2562.56
TRI CITY - J5036 | Clearwater | 15 | 0.4007 | 2020-05-12 | 2020-06-23 | 373375.8663 | 4667.3536
DELTONA EAST - W0130 | Deland | 25 | 0.1124 | 2020-05-12 | 2020-06-16 | 104735.3316 | 1309.2352
BAYVIEW - C652 | Clearwater | 26 | 0.0693 | 2020-06-03 | 2020-06-30 | 64574.3637 | 807.2064
DENHAM - C157 | Seven Springs | 3 | 0.2051 | 2020-02-10 | 2020-03-13 | 191114.0259 | 2389.0048
DENHAM - C155 | Seven Springs | 2 | 0.12 | 2020-06-03 | 2020-07-08 | 111817.08 | 1397.76
PORT RICHEY WEST - C202 | Seven Springs | 20 | 0.2002 | 2020-03-31 | 2020-05-05 | 186548.1618 | 2331.9296
BAYVIEW - C657 | Clearwater | 20 | 0.3879 | 2020-02-24 | 2020-04-08 | 361448.7111 | 4518.2592
VINELAND - K903 | Buena Vista | 5 | 0.1062 | 2020-11-02 | 2020-12-11 | 98958.1158 | 1237.0176
VINELAND - K903 | Buena Vista | 4 | 0.06 | 2020-03-23 | 2020-04-27 | 55908.54 | 698.88
SAFETY HARBOR - C3518 | Clearwater | 6 | 0.1521 | 2020-05-12 | 2020-06-16 | 141728.1489 | 1771.6608
SAFETY HARBOR - C3527 | Clearwater | 16 | 0.2853 | 2020-03-09 | 2020-04-20 | 265845.1077 | 3323.1744
PORT RICHEY WEST - C203 | Seven Springs | 46 | 0.618 | 2020-07-28 | 2020-09-22 | 575857.962 | 7198.464
CASSELBERRY - W0027 | Jamestown | 15 | 0.0699 | 2020-02-06 | 2020-03-09 | 65133.4491 | 814.1952
CASSELBERRY - W0022 | Longwood | 16 | 0.3756 | 2020-05-12 | 2020-06-23 | 349987.4604 | 4374.9888
ZEPHYRHILLS - C855 | Zephyr Hills | 27 | 0.1546 | 2020-03-16 | 2020-04-13 | 144057.6714 | 1800.7808
WEST DAVENPORT - K1521 | Lake Wales | 19 | 0.159 | 2020-03-09 | 2020-04-13 | 148157.631 | 1852.032
INTERCESSION CITY - K967 | Lake Wales | 5 | 0.0745 | 2020-03-23 | 2020-04-20 | 69419.7705 | 867.776
HOMOSASSA - A271 | Inverness | 27 | 0.2404 | 2020-05-05 | 2020-06-09 | 224006.8836 | 2800.1792
HOMOSASSA - A271 | Inverness | 17 | 0.3394 | 2020-07-01 | 2020-08-12 | 316255.9746 | 3953.3312
WINTER GARDEN - K204 | Winter Garden | 16 | 0.1562 | 2020-05-05 | 2020-06-09 | 145548.5658 | 1819.4176
LURAVILLE - A192 | Monticello | 3 | 0.1733 | 2020-03-23 | 2020-04-27 | 161482.4997 | 2018.5984
WINDERMERE - K302 | Buena Vista | 11 | 0.2101 | 2020-05-05 | 2020-06-09 | 195773.0709 | 2447.2448
WINDERMERE - K302 | Winter Garden | 21 | 0.3768 | 2020-06-01 | 2020-07-13 | 351105.6312 | 4388.9664
BAY HILL - K76 | Buena Vista | 2 | 0.0461 | 2020-05-05 | 2020-06-02 | 42956.3949 | 536.9728
WINTER GARDEN - K204 | Winter Garden | 35 | 0.2593 | 2020-05-15 | 2020-06-26 | 241618.0737 | 3020.3264
REDDICK - A36 | Ocala | 1 | 0.0814 | 2020-07-01 | 2020-07-29 | 75849.2526 | 948.1472
REDDICK - A36 | Ocala | 1 | 0.1693 | 2019-12-19 | 2020-01-16 | 157755.2637 | 1972.0064
REDDICK - A36 | Ocala | 1 | 0.0294 | 2020-03-30 | 2020-04-27 | 27395.1846 | 342.4512
ZEPHYRHILLS - C853 | Zephyr Hills | 25 | 0.2512 | 2020-04-06 | 2020-05-11 | 234070.4208 | 2925.9776
LAKEWOOD - K1695 | Highlands | 22 | 0.195 | 2020-04-01 | 2020-05-06 | 181702.755 | 2271.36
DINNER LAKE - K1690 | Highlands | 15 | 0.5 | 2020-05-05 | 2020-06-09 | 465904.5 | 5824
LAKEWOOD - K1695 | Highlands | 18 | 0.4739 | 2020-05-05 | 2020-06-16 | 441584.2851 | 5519.9872
HEMPLE - K2246 | Winter Garden | 12 | 0.1522 | 2020-06-01 | 2020-07-13 | 141821.3298 | 1772.8256
HEMPLE - K2246 | Winter Garden | 4 | 0.1571 | 2020-03-09 | 2020-04-13 | 146387.1939 | 1829.9008
HEMPLE - K2253 | Winter Garden | 25 | 0.4569 | 2020-06-01 | 2020-07-13 | 425743.5321 | 5321.9712
SILVER SPRINGS - A154 | Ocala | 5 | 0.1706 | 2020-05-19 | 2020-06-23 | 158966.6154 | 1987.1488
SILVER SPRINGS - A154 | Ocala | 2 | 0.0782 | 2019-12-17 | 2020-01-14 | 72867.4638 | 910.8736
SILVER SPRINGS - A154 | Ocala | 2 | 0.1134 | 2020-05-01 | 2020-06-05 | 105667.1406 | 1320.8832
CASSELBERRY - W0025 | Longwood | 13 | 0.2293 | 2020-05-12 | 2020-06-16 | 213663.8037 | 2670.8864
ALTAMONTE - M572 | Longwood | 9 | 0.1 | 2020-05-27 | 2020-06-23 | 93180.9 | 1164.8
ALTAMONTE - M573 | Longwood | 17 | 0.2205 | 2020-05-27 | 2020-06-30 | 205463.8845 | 2568.384
ALTAMONTE - M573 | Longwood | 14 | 0.0683 | 2020-03-09 | 2020-04-03 | 63642.5547 | 795.5584
ZEPHYRHILLS - C851 | Zephyr Hills | 13 | 0.0831 | 2019-12-09 | 2020-01-30 | 77433.3279 | 967.9488
ARCHER - A195 | Monticello | 15 | 0.4198 | 2020-04-01 | 2020-05-13 | 391173.4182 | 4889.8304
ZEPHYRHILLS NORTH - C340 | Zephyr Hills | 6 | 0.17 | 2020-02-10 | 2020-03-18 | 158407.53 | 1980.16
ALDERMAN - C5010 | Seven Springs | 23 | 0.1314 | 2020-01-13 | 2020-02-14 | 122439.7026 | 1530.5472
HOMOSASSA - A272 | Inverness | 4 | 0.2 | 2020-05-13 | 2020-06-17 | 186361.8 | 2329.6
ZEPHYRHILLS NORTH - C344 | Zephyr Hills | 18 | 0.3716 | 2020-03-17 | 2020-04-21 | 346260.2244 | 4328.3968
LURAVILLE - A192 | Monticello | 10 | 0.1886 | 2020-05-05 | 2020-06-09 | 175739.1774 | 2196.8128
WELCH ROAD - M552 | Apopka | 11 | 0.4033 | 2020-04-16 | 2020-05-20 | 375798.5697 | 4697.6384
WELCH ROAD - M552 | Apopka | 6 | 0.2187 | 2020-03-30 | 2020-05-04 | 203786.6283 | 2547.4176
CURLEW (HD) - C4988 | Clearwater | 3 | 0.4703 | 2020-04-01 | 2020-05-13 | 438229.7727 | 5478.0544
NORTHEAST - X286 | St. Petersburg | 8 | 0.0476 | 2020-03-09 | 2020-04-13 | 44354.1084 | 554.4448
PERRY - N7 | Monticello | 15 | 0.2355 | 2020-01-13 | 2020-01-28 | 219441.0195 | 2743.104
WILLISTON - A124 | Inverness | 6 | 0.374 | 2020-05-01 | 2020-06-12 | 348496.566 | 4356.352
FORTIETH STREET - X82 | St. Petersburg | 21 | 0.1084 | 2020-05-05 | 2020-06-09 | 101008.0956 | 1262.6432
ALTAMONTE - M578 | Longwood | 16 | 0.2142 | 2020-08-03 | 2020-09-14 | 199593.4878 | 2495.0016
ALTAMONTE - M576 | Longwood | 59 | 0.7807 | 2020-07-01 | 2020-08-05 | 727463.2863 | 9093.5936
LONGWOOD - M143 | Longwood | 8 | 0.0995 | 2020-03-09 | 2020-04-13 | 92714.9955 | 1158.976
NORTH LONGWOOD - M1755 | Longwood | 16 | 0.1309 | 2020-04-14 | 2020-05-11 | 121973.7981 | 1524.7232
LONGWOOD - M144 | Longwood | 10 | 0.0739 | 2020-05-12 | 2020-06-09 | 68860.6851 | 860.7872
ALTAMONTE - M578 | Longwood | 7 | 0.1471 | 2020-03-09 | 2020-04-13 | 137069.1039 | 1713.4208
APOPKA SOUTH - M727 | Apopka | 2 | 0.0853 | 2020-01-21 | 2020-02-04 | 79483.3077 | 993.5744
APOPKA SOUTH - M727 | Apopka | 3 | 0.0986 | 2020-05-01 | 2020-06-05 | 91876.3674 | 1148.4928
APOPKA SOUTH - M727 | Apopka | 2 | 0.0404 | 2020-02-03 | 2020-03-04 | 37645.0836 | 470.5792
PERRY - N9 | Monticello | 6 | 0.134 | 2020-02-18 | 2020-03-26 | 124862.406 | 1560.832
PERRY NORTH - N14 | Monticello | 14 | 0.1503 | 2020-05-05 | 2020-06-09 | 140050.8927 | 1750.6944
LAKE WEIR - A64 | Ocala | 11 | 0.2949 | 2020-07-01 | 2020-08-12 | 274790.4741 | 3434.9952
DISSTON - X62 | Walsingham | 20 | 0.2104 | 2020-02-10 | 2020-04-07 | 196052.6136 | 2450.7392
DISSTON - X65 | Walsingham | 30 | 0.31 | 2020-04-01 | 2020-05-13 | 288860.79 | 3610.88
LAKE WEIR - A64 | Ocala | 5 | 0.1126 | 2020-02-10 | 2020-03-18 | 104921.6934 | 1311.5648
MINNEOLA - K948 | Clermont | 25 | 0.31 | 2020-06-11 | 2020-07-16 | 288860.79 | 3610.88
MINNEOLA - K948 | Clermont | 17 | 0.2349 | 2020-10-01 | 2020-11-04 | 218881.9341 | 2736.1152
LURAVILLE - A192 | Monticello | 22 | 0.449 | 2020-04-01 | 2020-05-13 | 418382.241 | 5229.952
PERRY - N7 | Monticello | 11 | 0.4431 | 2020-04-01 | 2020-05-13 | 412884.5679 | 5161.2288
HOLDER - A48 | Inverness | 1 | 0.0737 | 2020-02-10 | 2020-03-11 | 68674.3233 | 858.4576
WEKIVA - M103 | Apopka | 4 | 0.0824 | 2020-05-27 | 2020-06-23 | 76781.0616 | 959.7952
WALSINGHAM - J553 | Walsingham | 55 | 0.108 | 2020-03-16 | 2020-04-20 | 100635.372 | 1257.984
BROOKSVILLE - A97 | Inverness | 6 | 0.1083 | 2020-03-02 | 2020-03-27 | 100914.9147 | 1261.4784
WALSINGHAM - J553 | Walsingham | 6 | 0.2 | 2020-03-09 | 2020-04-13 | 186361.8 | 2329.6
PINECASTLE - W0392 | Se Orlando | 30 | 0.5849 | 2020-07-01 | 2020-08-19 | 545015.0841 | 6812.9152
LAKE PLACID NORTH - K24 | Highlands | 10 | 0.2159 | 2020-03-09 | 2020-04-13 | 201177.5631 | 2514.8032
KENNETH CITY - X55 | Walsingham | 30 | 0.2218 | 2020-04-01 | 2020-05-06 | 206675.2362 | 2583.5264
CLEARWATER - C16 | Clearwater | 44 | 0.3688 | 2020-04-01 | 2020-05-06 | 343651.1592 | 4295.7824
WEKIVA - M103 | Apopka | 3 | 0.122 | 2020-01-27 | 2020-02-25 | 113680.698 | 1421.056
PIEDMONT - M471 | Apopka | 19 | 0.2058 | 2020-05-19 | 2020-06-23 | 191766.2922 | 2397.1584
PERRY NORTH - N14 | Monticello | 26 | 0.2796 | 2020-05-05 | 2020-06-16 | 260533.7964 | 3256.7808
PERRY - N7 | Monticello | 3 | 0.1805 | 2020-02-18 | 2020-03-26 | 168191.5245 | 2102.464
JASPER SOUTH - N191 | Monticello | 5 | 0.1481 | 2020-05-05 | 2020-06-09 | 138000.9129 | 1725.0688
COLEMAN - A105 | Ocala | 8 | 0.1072 | 2020-06-01 | 2020-07-06 | 99889.9248 | 1248.6656
WILDWOOD - A396 | Ocala | 6 | 0.2631 | 2020-07-01 | 2020-08-12 | 245158.9479 | 3064.5888
WILDWOOD - A396 | Ocala | 2 | 0.1186 | 2020-06-01 | 2020-07-06 | 110512.5474 | 1381.4528
EUSTIS - M503 | Apopka | 3 | 0.0673 | 2020-07-01 | 2020-07-29 | 62710.7457 | 783.9104
EUSTIS - M499 | Apopka | 14 | 0.2674 | 2020-05-05 | 2020-06-09 | 249165.7266 | 3114.6752
FLORA MAR - C4008 | Seven Springs | 62 | 0.7783 | 2020-07-01 | 2020-08-19 | 725226.9447 | 9065.6384
WALSINGHAM - J555 | Walsingham | 28 | 0.233 | 2020-04-01 | 2020-05-06 | 217111.497 | 2713.984
JENNINGS - N195 | Monticello | 1 | 0.081 | 2019-12-19 | 2020-01-14 | 75476.529 | 943.488
EAST CLEARWATER - C903 | Clearwater | 43 | 0.3253 | 2020-05-05 | 2020-06-09 | 303117.4677 | 3789.0944
UMATILLA - M4407 | Apopka | 7 | 0.0817 | 2020-07-01 | 2020-07-29 | 76128.7953 | 951.6416
UMATILLA - M4405 | Apopka | 4 | 0.1329 | 2020-08-03 | 2020-09-04 | 123837.4161 | 1548.0192
LISBON - M1519 | Apopka | 2 | 0.0575 | 2020-07-01 | 2020-07-29 | 53579.0175 | 669.76
LISBON - M1517 | Apopka | 22 | 0.513 | 2020-07-01 | 2020-08-19 | 478018.017 | 5975.424
JASPER SOUTH - N191 | Monticello | 8 | 0.18 | 2020-03-30 | 2020-05-04 | 167725.62 | 2096.64
JASPER SOUTH - N192 | Monticello | 12 | 0.1251 | 2020-05-05 | 2020-06-09 | 116569.3059 | 1457.1648
ZUBER - A202 | Ocala | 2 | 0.2747 | 2020-07-01 | 2020-08-12 | 255967.9323 | 3199.7056
HIGH SPRINGS - A15 | Monticello | 3 | 0.0759 | 2019-12-18 | 2020-01-20 | 70724.3031 | 884.0832
LAKE OF THE HILLS - K1885 | Lake Wales | 8 | 0.218 | 2020-08-03 | 2020-09-04 | 203134.362 | 2539.264
HIGH SPRINGS - A15 | Monticello | 5 | 0.0857 | 2020-03-31 | 2020-04-28 | 79856.0313 | 998.2336
HIGH SPRINGS - A15 | Monticello | 3 | 0.1136 | 2020-06-01 | 2020-07-06 | 105853.5024 | 1323.2128
TRENTON - A90 | Monticello | 1 | 0.1215 | 2020-02-10 | 2020-03-18 | 113214.7935 | 1415.232
TRENTON - A90 | Monticello | 5 | 0.0533 | 2020-07-01 | 2020-07-29 | 49665.4197 | 620.8384
OVIEDO - W0175 | Jamestown | 2 | 0.0575 | 2020-09-01 | 2020-10-06 | 53579.0175 | 669.76
OVIEDO - W0174 | Jamestown | 2 | 0.0402 | 2020-07-01 | 2020-07-29 | 37458.7218 | 468.2496
WINTER SPRINGS - W0192 | Jamestown | 6 | 0.1835 | 2020-06-01 | 2020-07-06 | 170986.9515 | 2137.408
ALAFAYA - W0298 | Jamestown | 6 | 0.1813 | 2020-07-01 | 2020-07-29 | 168936.9717 | 2111.7824
CLERMONT - K603 | Clermont | 59 | 0.4185 | 2020-10-01 | 2020-11-18 | 389962.0665 | 4874.688
TRENTON - A90 | Monticello | 1 | 0.0488 | 2020-07-01 | 2020-07-29 | 45472.2792 | 568.4224
GEORGIA PACIFIC - A45 | Monticello | 8 | 0.18 | 2020-06-01 | 2020-07-06 | 167725.62 | 2096.64
CONWAY - W0407 | Se Orlando | 27 | 0.3217 | 2020-10-01 | 2020-11-18 | 299762.9553 | 3747.1616
CONWAY - W0408 | Se Orlando | 37 | 0.236 | 2020-10-01 | 2020-11-04 | 219906.924 | 2748.928
CONWAY - W0408 | Se Orlando | 25 | 0.3667 | 2020-11-02 | 2020-12-04 | 341694.3603 | 4271.3216
NORTH LONGWOOD - M1751 | Longwood | 3 | 0.1517 | 2020-08-03 | 2020-09-14 | 141355.4253 | 1767.0016
NORTH LONGWOOD - M1758 | Jamestown | 3 | 0.0883 | 2020-10-01 | 2020-11-04 | 82278.7347 | 1028.5184
NORTH LONGWOOD - M1751 | Longwood | 12 | 0.1179 | 2020-09-01 | 2020-10-13 | 109860.2811 | 1373.2992
LAKE EMMA - M426 | Longwood | 7 | 0.0499 | 2020-08-03 | 2020-09-04 | 46497.2691 | 581.2352
EASTPOINT - N231 | Monticello | 38 | 0.1459 | 2020-07-01 | 2020-07-29 | 135950.9331 | 1699.4432
TAVARES EAST - M581 | Apopka | 7 | 0.0498 | 2020-08-03 | 2020-09-04 | 46404.0882 | 580.0704
SKY LAKE - W0363 | Se Orlando | 15 | 0.1085 | 2020-09-01 | 2020-10-06 | 101101.2765 | 1263.808
MAXIMO - X150 | St. Petersburg | 119 | 1.0806 | 2020-07-13 | 2020-09-04 | 1006912.8054 | 12586.8288
PIEDMONT - M473 | Apopka | 25 | 0.2955 | 2020-06-01 | 2020-07-06 | 275349.5595 | 3441.984
MAITLAND - W0087 | Longwood | 12 | 0.163 | 2020-11-02 | 2020-12-04 | 151884.867 | 1898.624
ALTAMONTE - M579 | Longwood | 5 | 0.0394 | 2020-11-02 | 2020-12-04 | 36713.2746 | 458.9312
ALTAMONTE - M579 | Longwood | 3 | 0.0271 | 2020-11-02 | 2020-12-04 | 25252.0239 | 315.6608
MAITLAND - W0087 | Longwood | 7 | 0.0504 | 2020-11-02 | 2020-12-04 | 46963.1736 | 587.0592
MAITLAND - W0079 | Longwood | 4 | 0.0467 | 2020-10-02 | 2020-11-05 | 43515.4803 | 543.9616
PORT ST JOE - N52 | Monticello | 39 | 0.3814 | 2020-07-01 | 2020-08-12 | 355391.9526 | 4442.5472
BOGGY MARSH - K957 | Buena Vista | 1 | 0.2206 | 2020-08-03 | 2020-09-14 | 205557.0654 | 2569.5488
BAY RIDGE - M447 | Apopka | 2 | 0.0966 | 2020-09-01 | 2020-10-06 | 90012.7494 | 1125.1968
BAY RIDGE - M451 | Apopka | 5 | 0.1389 | 2020-11-02 | 2020-12-04 | 129428.2701 | 1617.9072
TAYLOR AVENUE - J2904 | Clearwater | 11 | 0.0914 | 2020-11-02 | 2020-12-04 | 85167.3426 | 1064.6272
MAITLAND - M82 | Longwood | 11 | 0.0676 | 2020-11-02 | 2020-12-04 | 62990.2884 | 787.4048
EATONVILLE - M1135 | Longwood | 7 | 0.1593 | 2020-10-01 | 2020-11-11 | 148437.1737 | 1855.5264
MYRTLE LAKE - M651 | Longwood | 22 | 0.2682 | 2020-10-01 | 2020-11-18 | 249911.1738 | 3123.9936
TROPIC TERRACE - A207 | Inverness | 2 | 0.0519 | 2020-06-11 | 2020-07-09 | 48360.8871 | 604.5312
BEVERLY HILLS - A73 | Inverness | 13 | 0.0842 | 2020-05-12 | 2020-06-09 | 78458.3178 | 980.7616
GE ALACHUA - A186 | Monticello | 3 | 0.1411 | 2020-08-03 | 2020-09-14 | 131478.2499 | 1643.5328
WALSINGHAM - J558 | Walsingham | 5 | 0.1119 | 2019-12-16 | 2020-02-10 | 104269.4271 | 1303.4112
CLEARWATER - C5 | Clearwater | 18 | 0.09 | 2020-03-31 | 2020-05-05 | 83862.81 | 1048.32
LAKE WEIR - A61 | Ocala | 9 | 0.1772 | 2020-03-09 | 2020-04-13 | 165116.5548 | 2064.0256
GEORGIA PACIFIC - A45 | Monticello | 5 | 0.066 | 2020-03-09 | 2020-04-03 | 61499.394 | 768.768
DELAND - W0804 | Deland | 132 | 0.1271 | 2020-03-09 | 2020-04-13 | 118432.9239 | 1480.4608
ST MARKS WEST - N336 | Monticello | 9 | 0.1111 | 2020-03-31 | 2020-05-05 | 103523.9799 | 1294.0928
BELLEAIR - C656 | Clearwater | 8 | 0.0954 | 2020-02-10 | 2020-03-13 | 88894.5786 | 1111.2192
WAUKEENAH - N64 | Monticello | 2 | 0.0696 | 2020-05-05 | 2020-06-02 | 64853.9064 | 810.7008
PERRY NORTH - N14 | Monticello | 1 | 0.0658 | 2020-05-13 | 2020-06-10 | 61313.0322 | 766.4384
ST MARKS WEST - N336 | Monticello | 1 | 0.0833 | 2020-07-01 | 2020-07-29 | 77619.6897 | 970.2784
SUN N' LAKE - K1296 | Highlands | 4 | 0.1168 | 2020-02-24 | 2020-04-01 | 108835.2912 | 1360.4864
LAKEWOOD - K1693 | Highlands | 2 | 0.0509 | 2020-05-01 | 2020-05-29 | 47429.0781 | 592.8832
CLERMONT - K606 | Clermont | 5 | 0.0695 | 2020-01-13 | 2020-02-04 | 64760.7255 | 809.536
ANCLOTE - C4203 | Seven Springs | 8 | 0.0764 | 2020-03-09 | 2020-04-03 | 71190.2076 | 889.9072
CLERMONT - K602 | Clermont | 15 | 0.1045 | 2020-03-18 | 2020-04-22 | 97374.0405 | 1217.216
CLERMONT - K606 | Clermont | 11 | 0.0774 | 2020-05-27 | 2020-06-23 | 72122.0166 | 901.5552
ZUBER - A203 | Ocala | 8 | 0.215 | 2020-03-09 | 2020-04-13 | 200338.935 | 2504.32
LAKE WALES - K53 | Lake Wales | 10 | 0.1659 | 2020-03-16 | 2020-04-13 | 154587.1131 | 1932.4032
LAKE WALES - K58 | Lake Wales | 35 | 0.3446 | 2020-05-05 | 2020-06-16 | 321101.3814 | 4013.9008
REDDICK - A34 | Ocala | 5 | 0.2911 | 2020-04-21 | 2020-06-02 | 271249.5999 | 3390.7328
REDDICK - A34 | Ocala | 2 | 0.08 | 2020-03-16 | 2020-04-13 | 74544.72 | 931.84
SILVER SPRINGS SHORES - A131 | Ocala | 20 | 0.2804 | 2020-05-05 | 2020-06-16 | 261279.2436 | 3266.0992
ZUBER - A202 | Ocala | 6 | 0.0525 | 2020-05-05 | 2020-06-09 | 48919.9725 | 611.52
ZUBER - A202 | Ocala | 2 | 0.1106 | 2020-02-24 | 2020-04-01 | 103058.0754 | 1288.2688
SANTOS - A230 | Ocala | 15 | 0.1996 | 2020-05-05 | 2020-06-09 | 185989.0764 | 2324.9408
SANTOS - A230 | Ocala | 2 | 0.1085 | 2020-01-13 | 2020-01-22 | 101101.2765 | 1263.808
DESOTO CITY - K3222 | Highlands | 1 | 0.1393 | 2020-01-27 | 2020-03-17 | 129800.9937 | 1622.5664
DESOTO CITY - K3222 | Highlands | 1 | 0.0641 | 2020-03-02 | 2020-03-27 | 59728.9569 | 746.6368
DINNER LAKE - K1691 | Highlands | 7 | 0.2331 | 2020-06-17 | 2020-07-22 | 217204.6779 | 2715.1488
CYPRESSWOOD - K562 | Lake Wales | 7 | 0.2461 | 2020-05-05 | 2020-06-09 | 229318.1949 | 2866.5728
HAINES CITY - K21 | Lake Wales | 2 | 0.1331 | 2020-05-13 | 2020-06-17 | 124023.7779 | 1550.3488
HAINES CITY - K21 | Lake Wales | 7 | 0.0515 | 2020-02-10 | 2020-03-13 | 47988.1635 | 599.872
CYPRESSWOOD - K563 | Lake Wales | 3 | 0.0612 | 2020-02-17 | 2020-03-20 | 57026.7108 | 712.8576
SKY LAKE - W0368 | Se Orlando | 49 | 0.3363 | 2020-09-09 | 2020-10-20 | 313367.3667 | 3917.2224
FERN PARK - M907 | Longwood | 47 | 0.4367 | 2020-09-09 | 2020-10-13 | 406920.9903 | 5086.6816
EATONVILLE - M1135 | Longwood | 24 | 0.112 | 2020-06-03 | 2020-06-30 | 104362.608 | 1304.576
OBRIEN - A379 | Monticello | 6 | 1.0237 | 2020-06-10 | 2020-07-22 | 953892.8733 | 11924.0576
|  | 3188 | 45.0033 |  |  | 41934479.9697 | 524198.4384
* Historic Reliability = Outages per OH Line Mile over 10 year period (2007 - 2016)

## Det Cond - 2020
|  |  | 47.59 | 99%
Deteriorated Conductor - Project Level Costs
Location | Unit Count | Customer Count | Project Cost - Capital | Project Cost - O&M | Start Date | Finish Date
APALACHACOLA' - N58 | 5016 |  | 238711.44 | 2387.1144 | 2020-07-06 | 2020-09-25
APALACHACOLA' - N58 | 5280 |  | 251275.2 | 2512.752 | 2020-08-03 | 2020-10-30
APALACHACOLA' - N58 | 5333 |  | 253797.47 | 2537.9747 | 2020-09-07 | 2020-11-27
APALACHACOLA' - N58 Total | 15629 | 1000 | 743784.11 | 7437.8411
APOPKA SOUTH' - M723 | 2851 |  | 135679.09 | 1356.7909 | 2019-11-04 | 2020-05-15
APOPKA SOUTH' - M723 | 5386 |  | 256319.74 | 2563.1974 | 2019-12-16 | 2020-04-10
APOPKA SOUTH' - M723 Total | 8237 | 2209 | 391998.83 | 3919.9883
ARCHER' - A196 | 6178 |  | 294011.02 | 2940.1102 | 2020-06-29 | 2020-10-09
ARCHER' - A196 Total | 6178 | 492 | 294011.02 | 2940.1102
BARBERVILLE' - W0902 | 6864 |  | 326657.76 | 3266.5776 | 2020-01-06 | 2020-04-17
BARBERVILLE' - W0902 Total | 6864 | 1517 | 326657.76 | 3266.5776
BOGGY MARSH' - K959 | 3802 |  | 180937.18 | 1809.3718 | 2019-08-12 | 2020-03-27
BOGGY MARSH' - K959 Total | 3802 | 598 | 180937.18 | 1809.3718
CLARCONA' - M342 | 6125 |  | 291488.75 | 2914.8875 | 2020-01-13 | 2020-03-06
CLARCONA' - M342 Total | 6125 | 1838 | 291488.75 | 2914.8875
DELAND EAST' - W1110 | 6178 |  | 294011.02 | 2940.1102 | 2019-09-30 | 2020-03-27
DELAND EAST' - W1110 | 3115 |  | 148242.85 | 1482.4285 | 2019-09-30 | 2020-03-27
DELAND EAST' - W1110 Total | 9293 | 1810 | 442253.87 | 4422.5387
DUNDEE' - K3245 | 3802 |  | 180937.18 | 1809.3718 | 2020-01-06 | 2020-01-31
DUNDEE' - K3245 Total | 3802 | 1812 | 180937.18 | 1809.3718
DUNEDIN' - C104 | 3260 |  | 155143.4 | 1551.434 | 2019-09-02 | 2020-01-24
DUNEDIN' - C104 | 4763 |  | 226671.17 | 2266.7117 | 2019-09-23 | 2020-02-14
DUNEDIN' - C104 | 3326 |  | 158284.34 | 1582.8434 | 2019-11-11 | 2020-01-31
DUNEDIN' - C104 Total | 11349 | 2127 | 540098.91 | 5400.9891
EAST ORANGE' - W0250 | 4118 |  | 195975.62 | 1959.7562 | 2019-09-23 | 2020-02-28
EAST ORANGE' - W0250 Total | 4118 | 1886 | 195975.62 | 1959.7562
LISBON' - M1517 | 2745.6 |  | 130663.104 | 1306.631 | 2019-09-30 | 2020-02-21
LISBON' - M1517 Total | 2745.6 | 2159 | 130663.104 | 1306.631
LISBON' - M1518 | 6125 |  | 291488.75 | 2914.8875 | 2019-10-28 | 2020-01-31
LISBON - M1518 | 3643 |  | 173370.37 | 1733.7037 | 2020-01-20 | 2020-02-28
LISBON - M1518 Total | 9768 | 1704 | 464859.12 | 4648.5912
LOCKHART' - M402 | 3115 |  | 148242.85 | 1482.4285 | 2019-09-23 | 2020-02-14
LOCKHART' - M402 Total | 3115 | 619 | 148242.85 | 1482.4285
MCINTOSH' - A51 | 5227 |  | 248752.93 | 2487.5293 | 2019-10-28 | 2020-01-31
MCINTOSH' - A51 | 5702 |  | 271358.18 | 2713.5818 | 2019-11-04 | 2020-02-07
MCINTOSH' - A51 | 5702 |  | 271358.18 | 2713.5818 | 2020-01-13 | 2020-03-20
MCINTOSH' - A51 | 5491 |  | 261316.69 | 2613.1669 | 2020-01-20 | 2020-04-17
MCINTOSH' - A51 | 5914 |  | 281447.26 | 2814.4726 | 2020-01-20 | 2020-04-17
MCINTOSH' - A51 | 5438 |  | 258794.42 | 2587.9442 | 2020-02-17 | 2020-05-08
MCINTOSH' - A51 Total | 33474 | 1315 | 1593027.66 | 15930.2766
ORANGE CITY' - W0382 | 4382 |  | 208539.38 | 2085.3938 | 2020-01-13 | 2020-03-20
ORANGE CITY' - W0382 | 3960 |  | 188456.4 | 1884.564 | 2020-03-09 | 2020-05-15
ORANGE CITY' - W0382 | 4277 |  | 203542.43 | 2035.4243 | 2020-05-25 | 2020-08-07
ORANGE CITY' - W0382 Total | 12619 | 1563 | 600538.21 | 6005.3821
PINECASTLE' - W0392 | 3062 |  | 145720.58 | 1457.2058 | 2019-05-01 | 2020-02-14
PINECASTLE' - W0392 Total | 3062 | 1538 | 145720.58 | 1457.2058
SOPCHOPPY' - N327 | 7234 |  | 344266.06 | 3442.6606 | 2019-12-02 | 2020-02-14
SOPCHOPPY' - N327 | 5174 |  | 246230.66 | 2462.3066 | 2020-01-06 | 2020-03-13
SOPCHOPPY' - N327 | 6917 |  | 329180.03 | 3291.8003 | 2020-02-10 | 2020-05-15
SOPCHOPPY' - N327 | 8818 |  | 419648.62 | 4196.4862 | 2020-02-17 | 2020-04-30
SOPCHOPPY' - N327 | 7128 |  | 339221.52 | 3392.2152 | 2020-04-01 | 2020-06-01
SOPCHOPPY' - N327 Total | 35271 | 1463 | 1678546.89 | 16785.4689
ST MARKS WEST' - N332 | 5280 |  | 251275.2 | 2512.752 | 2020-04-01 | 2020-06-26
ST MARKS WEST' - N332 | 5650 |  | 268883.5 | 2688.835 | 2020-06-29 | 2020-08-28
ST MARKS WEST' - N332 | 5280 |  | 251275.2 | 2512.752 | 2020-08-31 | 2020-10-30
ST MARKS WEST' - N332 Total | 16210 | 1105 | 771433.9 | 7714.339
TARPON SPRINGS' - C303 | 5808 |  | 276402.72 | 2764.0272 | 2019-09-09 | 2020-02-07
TARPON SPRINGS' - C303 | 5755 |  | 273880.45 | 2738.8045 | 2019-09-23 | 2020-03-13
TARPON SPRINGS' - C303 | 5755 |  | 273880.45 | 2738.8045 | 2020-01-06 | 2020-04-24
TARPON SPRINGS' - C303 Total | 17318 | 1985 | 824163.62 | 8241.6362
WAUKEENAH' - N64 | 5280 |  | 251275.2 | 2512.752 | 2020-06-01 | 2020-09-04
WAUKEENAH' - N64 | 5755 |  | 273880.45 | 2738.8045 | 2020-06-01 | 2020-09-04
WAUKEENAH' - N64 | 4541 |  | 216106.19 | 2161.0619 | 2020-09-07 | 2020-11-13
WAUKEENAH' - N64 | 3907 |  | 185934.13 | 1859.3413 | 2020-09-07 | 2020-11-13
WAUKEENAH' - N64 Total | 19483 | 649 | 927195.97 | 9271.9597
WEST LAKE WALES' - K866 | 5755 |  | 273880.45 | 2738.8045 | 2019-12-16 | 2020-01-31
WEST LAKE WALES' - K866 | 7920 |  | 376912.8 | 3769.128 | 2020-03-02 | 2020-06-01
WEST LAKE WALES' - K866 | 4277 |  | 203542.43 | 2035.4243 | 2020-04-01 | 2020-06-01
WEST LAKE WALES' - K866 | 5755 |  | 273880.45 | 2738.8045 | 2020-04-01 | 2020-06-01
WEST LAKE WALES' - K866 Total | 23707 | 1073 | 1128216.13 | 11282.1613
ZELLWOOD' - M33 | 3749 |  | 178414.91 | 1784.1491 | 2019-10-14 | 2020-02-28
ZELLWOOD' - M33 | 6442 |  | 306574.78 | 3065.7478 | 2019-10-14 | 2020-03-27
ZELLWOOD' - M33 | 2904 |  | 138201.36 | 1382.0136 | 2019-11-04 | 2020-04-17
ZELLWOOD' - M33 | 6072 |  | 288966.48 | 2889.6648 | 2019-11-07 | 2020-04-03
ZELLWOOD' - M33 | 5227 |  | 248752.93 | 2487.5293 | 2019-12-02 | 2020-04-10
ZELLWOOD' - M33 | 2640 |  | 125637.6 | 1256.376 | 2019-12-02 | 2020-02-21
ZELLWOOD' - M33 | 5702 |  | 271358.18 | 2713.5818 | 2019-12-18 | 2020-04-10
ZELLWOOD' - M33 | 6970 |  | 331702.3 | 3317.023 | 2020-01-13 | 2020-05-01
ZELLWOOD' - M33 | 5966 |  | 283921.94 | 2839.2194 | 2020-03-02 | 2020-06-12
ZELLWOOD' - M33 Total | 45672 | 1226 | 2173530.48 | 21735.3048
ZEPHYRHILLS' - C855 | 5861 |  | 278924.99 | 2789.2499 | 2020-10-12 | 2020-11-27
ZEPHYRHILLS' - C855 Total | 5861 | 3133 | 278924.99 | 2789.2499
Grand Total | 303702.6 | 34821 | 14453206.734 | 144532.0673

## SOG - 2020
SOG - Project Level Costs
Substation | Customer Count | Unit Count | Project Cost - Capital | Project Cost - O&M | Start Date | Finish Date
WEST DAVENPORT - K1526 |  | 1 | 64619 | 1400 | 20-Apr-20* | 2020-04-24
WEST DAVENPORT - K1526 Total | 3797 | 1 | 64619 | 1400 | 20-Apr-20* | 2020-04-24
EAST ORANGE - W0252 |  | 1 | 64619 | 1400 | 13-Feb-20 A | 13-Feb-20 A
EAST ORANGE - W0252 |  | 1 | 64619 | 1400 | 23-Mar-20* | 2020-04-03
EAST ORANGE - W0252 Total | 1571 | 2 | 129238 | 2800 | 13-Feb-20 A | 2020-04-03
EAST ORANGE - W0253 |  | 1 | 40000 | 814 | 18-Nov-19 A | 17-Feb-20 A
EAST ORANGE - W0253 Total | 1231 | 1 | 40000 | 814 | 18-Nov-19 A | 17-Feb-20 A
EAST ORANGE - W0274 |  | 1 | 64619 | 1400 | 15-Oct-19 A | 2020-04-09
EAST ORANGE - W0274 Total | 2399 | 1 | 64619 | 1400 | 15-Oct-19 A | 2020-04-09
SUNFLOWER - W0471 |  | 1 | 64619 | 1400 | 06-Apr-20* | 2020-04-13
SUNFLOWER - W0471 |  | 1 | 40000 | 814 | 15-Nov-19 A | 2020-04-24
SUNFLOWER - W0471 Total | 1340 | 2 | 104619 | 2214 | 15-Nov-19 A | 2020-04-24
POINCIANA - K1236 |  | 1 | 64619 | 1400 | 14-Nov-19 A | 11-Mar-20 A
POINCIANA - K1236 Total | 2461 | 1 | 64619 | 1400 | 14-Nov-19 A | 11-Mar-20 A
POINCIANA - K1508 |  | 1 | 64619 | 1400 | 10-Dec-19 A | 06-Feb-20 A
POINCIANA - K1508 Total | 2288 | 1 | 64619 | 1400 | 10-Dec-19 A | 06-Feb-20 A
LONGWOOD - M142 |  | 1 | 64619 | 1400 | 20-Jan-20 A | 29-Jan-20 A
LONGWOOD - M142 |  | 1 | 64619 | 1400 | 22-Jan-20 A | 22-Jan-20 A
LONGWOOD - M142 |  | 1 | 64619 | 1400 | 23-Jan-20 A | 23-Jan-20 A
LONGWOOD - M142 |  | 1 | 64619 | 1400 | 27-Jan-20 A | 27-Jan-20 A
LONGWOOD - M142 |  | 1 | 64619 | 1400 | 27-Jan-20 A | 27-Jan-20 A
LONGWOOD - M142 |  | 1 | 64619 | 1400 | 28-Jan-20 A | 28-Jan-20 A
LONGWOOD - M142 |  | 1 | 64619 | 1400 | 29-Jan-20 A | 31-Jan-20 A
LONGWOOD - M142 |  | 1 | 64619 | 1400 | 21-Feb-20 A | 28-Feb-20 A
LONGWOOD - M142 Total | 2406 | 8 | 516952 | 11200 | 20-Jan-20 A | 28-Feb-20 A
LONGWOOD - M143 |  | 1 | 64619 | 1400 | 21-Jan-20 A | 22-Jan-20 A
LONGWOOD - M143 |  | 1 | 64619 | 1400 | 23-Jan-20 A | 27-Jan-20 A
LONGWOOD - M143 |  | 1 | 64619 | 1400 | 28-Jan-20 A | 29-Jan-20 A
LONGWOOD - M143 Total | 852 | 3 | 193857 | 4200 | 21-Jan-20 A | 29-Jan-20 A
CASSELBERRY - W0019 |  | 1 | 64619 | 1400 | 22-Jan-20 A | 19-Feb-20 A
CASSELBERRY - W0019 |  | 1 | 64619 | 1400 | 03-Mar-20 A | 03-Mar-20 A
CASSELBERRY - W0019 |  | 1 | 64619 | 1400 | 04-Mar-20 A | 05-Mar-20 A
CASSELBERRY - W0019 Total | 1816 | 3 | 193857 | 4200 | 22-Jan-20 A | 05-Mar-20 A
WINTER SPRINGS - W0187 |  | 1 | 64619 | 1400 | 2020-05-06 | 2020-05-06
WINTER SPRINGS - W0187 Total | 1302 | 1 | 64619 | 1400 | 2020-05-06 | 2020-05-06
WINTER SPRINGS - W0188 |  | 1 | 64619 | 1400 | 04-Feb-20 A | 20-Feb-20 A
WINTER SPRINGS - W0188 |  | 1 | 64619 | 1400 | 18-Feb-20 A | 20-Feb-20 A
WINTER SPRINGS - W0188 |  | 1 | 40000 | 814 | 20-Apr-20* | 2020-04-24
WINTER SPRINGS - W0188 Total | 2348 | 3 | 169238 | 3614 | 04-Feb-20 A | 2020-04-24
DELTONA EAST - W0121 |  | 1 | 64619 | 1400 | 2020-04-30 | 2020-04-30
DELTONA EAST - W0121 |  | 1 | 64619 | 1400 | 2020-05-01 | 2020-05-01
DELTONA EAST - W0121 |  | 1 | 64619 | 1400 | 2020-05-05 | 2020-05-05
DELTONA EAST - W0121 |  | 1 | 64619 | 1400 | 2020-05-21 | 2020-05-21
DELTONA EAST - W0121 Total | 1492 | 4 | 258476 | 5600 | 2020-04-30 | 2020-05-21
DELTONA EAST - W0130 |  | 1 | 64619 | 1400 | 2020-05-12 | 2020-05-12
DELTONA EAST - W0130 |  | 1 | 64619 | 1400 | 2020-06-02 | 2020-06-02
DELTONA EAST - W0130 |  | 1 | 64619 | 1400 | 2020-06-04 | 2020-06-04
DELTONA EAST - W0130 |  | 1 | 64619 | 1400 | 2020-06-09 | 2020-06-09
DELTONA EAST - W0130 |  | 1 | 64619 | 1400 | 2020-06-11 | 2020-06-11
DELTONA EAST - W0130 Total | 1910 | 5 | 323095 | 7000 | 2020-05-12 | 2020-06-11
TURNER PLANT - W0762 |  | 1 | 64619 | 1400 | 2020-05-26 | 2020-05-26
TURNER PLANT - W0762 |  | 1 | 64619 | 1400 | 2020-05-28 | 2020-05-28
TURNER PLANT - W0762 Total | 1414 | 2 | 129238 | 2800 | 2020-05-26 | 2020-05-28
TURNER PLANT - W0763 |  | 1 | 64619 | 1400 | 2020-05-07 | 2020-05-07
TURNER PLANT - W0763 |  | 1 | 64619 | 1400 | 2020-05-14 | 2020-05-14
TURNER PLANT - W0763 |  | 1 | 64619 | 1400 | 2020-05-19 | 2020-05-19
TURNER PLANT - W0763 Total | 1682 | 3 | 193857 | 4200 | 2020-05-07 | 2020-05-19
LAKE BRYAN - K231 |  | 1 | 40000 | 814 | 2020-05-07 | 2020-05-13
LAKE BRYAN - K231 |  | 1 | 40000 | 814 | 2020-05-14 | 2020-05-20
LAKE BRYAN - K231 Total | 852 | 2 | 80000 | 1628 | 2020-05-07 | 2020-05-20
LAKE BRYAN - K238 |  | 1 | 40000 | 814 | 2020-06-05 | 2020-06-11
LAKE BRYAN - K238 |  | 1 | 40000 | 814 | 11-Nov-19 A | 2020-04-13
LAKE BRYAN - K238 Total | 693 | 2 | 80000 | 1628 | 11-Nov-19 A | 2020-04-13
ISLESWORTH - K781 |  | 1 | 64619 | 1400 | 17-Dec-19 A | 2020-04-13
ISLESWORTH - K781 |  | 1 | 40000 | 814 | 11-Nov-19 A | 2020-04-20
ISLESWORTH - K781 Total | 3202 | 2 | 104619 | 2214 | 11-Nov-19 A | 2020-04-20
ISLESWORTH - K782 |  | 1 | 40000 | 814 | 04-Nov-19 A | 2020-04-06
ISLESWORTH - K782 |  | 1 | 40000 | 814 | 11-Nov-19 A | 2020-04-27
ISLESWORTH - K782 |  | 1 | 40000 | 814 | 28-Apr-20* | 2020-05-04
ISLESWORTH - K782 |  | 1 | 40000 | 814 | 21-May-20* | 2020-05-28
ISLESWORTH - K782 Total | 870 | 4 | 160000 | 3256 | 04-Nov-19 A | 2020-05-28
VINELAND - K901 |  | 1 | 64619 | 1400 | 14-Apr-20* | 2020-04-20
VINELAND - K901 Total | 406 | 1 | 64619 | 1400 | 14-Apr-20* | 2020-04-20
VINELAND - K912 |  | 1 | 40000 | 814 | 30-Apr-20* | 2020-05-06
VINELAND - K912 |  | 1 | 40000 | 814 | 2020-05-29 | 2020-06-04
VINELAND - K912 Total | 2697 | 2 | 80000 | 1628 | 30-Apr-20* | 2020-06-04
VINELAND - K915 |  | 1 | 40000 | 814 | 14-Nov-19 A | 2020-04-17
VINELAND - K915 |  | 1 | 40000 | 814 | 23-Apr-20* | 2020-04-29
VINELAND - K915 Total | 366 | 2 | 80000 | 1628 | 14-Nov-19 A | 2020-04-29
VINELAND - K917 |  | 1 | 40000 | 814 | 20-Apr-20* | 2020-04-24
VINELAND - K917 Total | 2755 | 1 | 40000 | 814 | 20-Apr-20* | 2020-04-24
OVIEDO - W0171 |  | 1 | 64619 | 1400 | 2020-06-03 | 2020-06-03
OVIEDO - W0171 |  | 1 | 64619 | 1400 | 2020-07-01 | 2020-07-01
OVIEDO - W0171 |  | 1 | 40000 | 814 | 2020-07-31 | 2020-08-06
OVIEDO - W0171 Total | 1561 | 3 | 169238 | 3614 | 2020-06-03 | 2020-08-06
OVIEDO - W0172 |  | 1 | 64619 | 1400 | 12-Mar-20 A | 12-Mar-20 A
OVIEDO - W0172 |  | 1 | 64619 | 1400 | 19-Mar-20 A | 19-Mar-20 A
OVIEDO - W0172 |  | 1 | 64619 | 1400 | 2020-04-29 | 2020-04-29
OVIEDO - W0172 |  | 1 | 40000 | 814 | 2020-06-25 | 2020-07-01
OVIEDO - W0172 |  | 1 | 40000 | 814 | 2020-08-07 | 2020-08-13
OVIEDO - W0172 Total | 1398 | 5 | 273857 | 5828 | 12-Mar-20 A | 2020-08-13
OVIEDO - W0174 |  | 1 | 64619 | 1400 | 05-Mar-20 A | 05-Mar-20 A
OVIEDO - W0174 |  | 1 | 64619 | 1400 | 11-Mar-20 A | 11-Mar-20 A
OVIEDO - W0174 |  | 1 | 64619 | 1400 | 2020-04-22 | 2020-04-22
OVIEDO - W0174 |  | 1 | 64619 | 1400 | 2020-05-06 | 2020-05-06
OVIEDO - W0174 |  | 1 | 64619 | 1400 | 2020-05-06 | 2020-05-06
OVIEDO - W0174 |  | 1 | 64619 | 1400 | 2020-06-24 | 2020-06-24
OVIEDO - W0174 Total | 1768 | 6 | 387714 | 8400 | 05-Mar-20 A | 2020-06-24
WINTER SPRINGS - W0193 |  | 1 | 64619 | 1400 | 2020-05-06 | 2020-05-06
WINTER SPRINGS - W0193 Total | 1610 | 1 | 64619 | 1400 | 2020-05-06 | 2020-05-06
WINTER SPRINGS - W0194 |  | 1 | 64619 | 1400 | 2020-04-08 | 2020-04-08
WINTER SPRINGS - W0194 |  | 1 | 64619 | 1400 | 2020-04-15 | 2020-04-15
WINTER SPRINGS - W0194 |  | 1 | 64619 | 1400 | 2020-04-22 | 2020-04-22
WINTER SPRINGS - W0194 |  | 1 | 64619 | 1400 | 2020-06-24 | 2020-06-24
WINTER SPRINGS - W0194 |  | 1 | 40000 | 814 | 2020-06-18 | 2020-06-24
WINTER SPRINGS - W0194 Total | 1205 | 5 | 298476 | 6414 | 2020-04-08 | 2020-06-24
WINTER SPRINGS - W0195 |  | 1 | 64619 | 1400 | 2020-05-06 | 2020-05-06
WINTER SPRINGS - W0195 |  | 1 | 64619 | 1400 | 2020-06-10 | 2020-06-10
WINTER SPRINGS - W0195 |  | 1 | 40000 | 814 | 2020-07-17 | 2020-07-23
WINTER SPRINGS - W0195 |  | 1 | 40000 | 814 | 2020-07-24 | 2020-07-30
WINTER SPRINGS - W0195 |  | 1 | 40000 | 814 | 2020-08-21 | 2020-09-03
WINTER SPRINGS - W0195 Total | 2686 | 5 | 249238 | 5242 | 2020-05-06 | 2020-09-03
LOCKWOOD - W0480 |  | 1 | 64619 | 1400 | 2020-04-29 | 2020-04-29
LOCKWOOD - W0480 |  | 1 | 64619 | 1400 | 13-May-20* | 2020-05-13
LOCKWOOD - W0480 |  | 1 | 40000 | 814 | 2020-07-02 | 2020-07-09
LOCKWOOD - W0480 |  | 1 | 40000 | 814 | 2020-07-10 | 2020-07-16
LOCKWOOD - W0480 |  | 1 | 40000 | 814 | 2020-08-14 | 2020-08-20
LOCKWOOD - W0480 Total | 1680 | 5 | 249238 | 5242 | 2020-04-29 | 2020-08-20
LOCKWOOD - W0481 |  | 1 | 64619 | 1400 | 17-Mar-20 A | 17-Mar-20 A
LOCKWOOD - W0481 |  | 1 | 64619 | 1400 | 2020-05-13 | 2020-05-13
LOCKWOOD - W0481 |  | 1 | 64619 | 1400 | 2020-05-20 | 2020-05-20
LOCKWOOD - W0481 |  | 1 | 64619 | 1400 | 2020-05-27 | 2020-05-27
LOCKWOOD - W0481 Total | 1430 | 4 | 258476 | 5600 | 17-Mar-20 A | 2020-05-27
LOCKWOOD - W0483 |  | 1 | 64619 | 1400 | 2020-05-13 | 2020-05-13
LOCKWOOD - W0483 Total | 1310 | 1 | 64619 | 1400 | 2020-05-13 | 2020-05-13
LAKE MARION - K1286 |  | 1 | 64619 | 1400 | 2020-06-17 | 2020-06-17
LAKE MARION - K1286 |  | 1 | 64619 | 1400 | 2020-07-15 | 2020-07-15
LAKE MARION - K1286 Total | 2586 | 2 | 129238 | 2800 | 2020-06-17 | 2020-07-15
LAKE MARION - K1287 |  | 1 | 64619 | 1400 | 2020-08-05 | 2020-08-05
LAKE MARION - K1287 |  | 1 | 64619 | 1400 | 2020-06-24 | 2020-06-24
LAKE MARION - K1287 |  | 1 | 64619 | 1400 | 2020-07-01 | 2020-07-01
LAKE MARION - K1287 |  | 1 | 64619 | 1400 | 2020-07-08 | 2020-07-08
LAKE MARION - K1287 |  | 1 | 64619 | 1400 | 2020-07-22 | 2020-07-22
LAKE MARION - K1287 |  | 1 | 64619 | 1400 | 2020-07-29 | 2020-07-29
LAKE MARION - K1287 Total | 2751 | 6 | 387714 | 8400 | 2020-06-24 | 2020-08-05
HEMPLE - K2255 |  | 1 | 40000 | 814 | 19-Nov-19 A | 2020-04-13
HEMPLE - K2255 |  | 1 | 40000 | 814 | 03-Dec-19 A | 2020-04-27
HEMPLE - K2255 |  | 1 | 40000 | 814 | 04-Dec-19 A | 2020-04-24
HEMPLE - K2255 |  | 1 | 40000 | 814 | 06-Jan-20 A | 2020-04-30
HEMPLE - K2255 Total | 2076 | 4 | 160000 | 3256 | 19-Nov-19 A | 2020-04-30
WINTER GARDEN - K3285 |  | 1 | 40000 | 814 | 11-Nov-19 A | 2020-04-03
WINTER GARDEN - K3285 |  | 1 | 40000 | 814 | 14-Nov-19 A | 2020-04-28
WINTER GARDEN - K3285 |  | 1 | 40000 | 814 | 14-Nov-19 A | 2020-04-28
WINTER GARDEN - K3285 Total | 1124 | 3 | 120000 | 2442 | 11-Nov-19 A | 2020-04-28
LAKE MARION - K1288 |  | 1 | 64619 | 1400 | 23-Mar-20 A | 24-Mar-20 A
LAKE MARION - K1288 |  | 1 | 64619 | 1400 | 2020-04-15 | 2020-04-15
LAKE MARION - K1288 Total | 1585 | 2 | 129238 | 2800 | 23-Mar-20 A | 2020-04-15
DUNDEE - K3244 |  | 1 | 64619 | 1400 | 03-Mar-20 A | 03-Mar-20 A
DUNDEE - K3244 |  | 1 | 64619 | 1400 | 01-Apr-20* | 2020-04-01
DUNDEE - K3244 |  | 1 | 64619 | 1400 | 2020-04-08 | 2020-04-08
DUNDEE - K3244 Total | 2218 | 3 | 193857 | 4200 | 03-Mar-20 A | 2020-04-08
DELAND EAST - W1107 |  | 1 | 64619 | 1400 | 30-Dec-19 A | 06-Jan-20 A
DELAND EAST - W1107 Total | 331 | 1 | 64619 | 1400 | 30-Dec-19 A | 06-Jan-20 A
RIO PINAR - W0972 |  | 1 | 64619 | 1400 | 2020-07-22 | 2020-07-22
RIO PINAR - W0972 Total | 1732 | 1 | 64619 | 1400 | 2020-07-22 | 2020-07-22
NARCOOSSEE - W0214 |  | 1 | 64619 | 1400 | 2020-07-08 | 2020-07-08
NARCOOSSEE - W0214 |  | 1 | 64619 | 1400 | 2020-07-15 | 2020-07-15
NARCOOSSEE - W0214 |  | 1 | 64619 | 1400 | 2020-08-12 | 2020-08-12
NARCOOSSEE - W0214 |  | 1 | 64619 | 1400 | 2020-08-19 | 2020-08-19
NARCOOSSEE - W0214 Total | 1525 | 4 | 258476 | 5600 | 2020-07-08 | 2020-08-19
NARCOOSSEE - W0217 |  | 1 | 64619 | 1400 | 2020-07-29 | 2020-07-29
NARCOOSSEE - W0217 |  | 1 | 64619 | 1400 | 2020-08-05 | 2020-08-05
NARCOOSSEE - W0217 |  | 1 | 64619 | 1400 | 2020-08-12 | 2020-08-12
NARCOOSSEE - W0217 |  | 1 | 64619 | 1400 | 2020-09-02 | 2020-09-02
NARCOOSSEE - W0217 |  | 1 | 64619 | 1400 | 2020-09-09 | 2020-09-09
NARCOOSSEE - W0217 Total | 2533 | 5 | 323095 | 7000 | 2020-07-29 | 2020-09-09
NARCOOSSEE - W0220 |  | 1 | 64619 | 1400 | 2020-07-22 | 2020-07-22
NARCOOSSEE - W0220 |  | 1 | 64619 | 1400 | 2020-07-29 | 2020-07-29
NARCOOSSEE - W0220 |  | 1 | 64619 | 1400 | 2020-08-05 | 2020-08-05
NARCOOSSEE - W0220 |  | 1 | 64619 | 1400 | 2020-08-19 | 2020-08-19
NARCOOSSEE - W0220 Total | 1537 | 4 | 258476 | 5600 | 2020-07-22 | 2020-08-19
RIO PINAR - W0972 |  | 1 | 64619 | 1400 | 2020-05-27 | 2020-05-27
RIO PINAR - W0972 |  | 1 | 64619 | 1400 | 2020-06-03 | 2020-06-03
RIO PINAR - W0972 |  | 1 | 64619 | 1400 | 2020-06-10 | 2020-06-10
RIO PINAR - W0972 |  | 1 | 64619 | 1400 | 2020-06-10 | 2020-06-10
RIO PINAR - W0972 |  | 1 | 64619 | 1400 | 2020-06-17 | 2020-06-17
RIO PINAR - W0972 Total | 1732 | 5 | 323095 | 7000 | 2020-05-27 | 2020-06-17
RIO PINAR - W0973 |  | 1 | 64619 | 1400 | 2020-06-24 | 2020-06-24
RIO PINAR - W0973 |  | 1 | 64619 | 1400 | 2020-07-01 | 2020-07-01
RIO PINAR - W0973 |  | 1 | 64619 | 1400 | 2020-07-15 | 2020-07-15
RIO PINAR - W0973 |  | 1 | 64619 | 1400 | 2020-09-16 | 2020-09-16
RIO PINAR - W0973 Total | 1532 | 4 | 258476 | 5600 | 2020-06-24 | 2020-09-16
RIO PINAR - W0975 |  | 1 | 64619 | 1400 | 2020-06-17 | 2020-06-17
RIO PINAR - W0975 |  | 1 | 64619 | 1400 | 2020-06-24 | 2020-06-24
RIO PINAR - W0975 |  | 1 | 64619 | 1400 | 2020-07-01 | 2020-07-01
RIO PINAR - W0975 |  | 1 | 64619 | 1400 | 2020-07-08 | 2020-07-08
RIO PINAR - W0975 |  | 1 | 64619 | 1400 | 2020-08-24 | 2020-08-24
RIO PINAR - W0975 Total | 2306 | 5 | 323095 | 7000 | 2020-06-17 | 2020-08-24
BARNUM CITY - K1503 |  | 1 | 40000 | 814 | 04-Nov-19 A | 2020-05-01
BARNUM CITY - K1503 |  | 1 | 40000 | 814 | 06-Apr-20* | 2020-04-13
BARNUM CITY - K1503 Total | 2063 | 2 | 80000 | 1628 | 04-Nov-19 A | 2020-04-13
CHAMPIONS GATE - K1762 |  | 1 | 64619 | 1400 | 27-Dec-19 A | 08-Jan-20 A
CHAMPIONS GATE - K1762 Total | 2346 | 1 | 64619 | 1400 | 27-Dec-19 A | 08-Jan-20 A
BARNUM CITY - K1763 |  | 1 | 40000 | 814 | 11-Nov-19 A | 2020-03-27
BARNUM CITY - K1763 |  | 1 | 40000 | 814 | 11-Nov-19 A | 2020-03-30
BARNUM CITY - K1763 |  | 1 | 40000 | 814 | 20-Apr-20* | 2020-04-24
BARNUM CITY - K1763 Total | 1677 | 3 | 120000 | 2442 | 11-Nov-19 A | 2020-04-24
BARNUM CITY - K3360 |  | 1 | 64619 | 1400 | 02-Dec-19 A | 2020-04-13
BARNUM CITY - K3360 Total | 2465 | 1 | 64619 | 1400 | 02-Dec-19 A | 2020-04-13
BARNUM CITY - K3362 |  | 1 | 40000 | 814 | 13-Apr-20* | 2020-04-17
BARNUM CITY - K3362 |  | 1 | 40000 | 814 | 20-Apr-20* | 2020-04-24
BARNUM CITY - K3362 |  | 1 | 40000 | 814 | 04-May-20* | 2020-05-08
BARNUM CITY - K3362 |  | 1 | 40000 | 814 | 2020-05-11 | 2020-05-15
BARNUM CITY - K3362 Total | 2338 | 4 | 160000 | 3256 | 13-Apr-20* | 2020-05-15
INTERCESSION CITY - K967 |  | 1 | 64619 | 1400 | 30-Dec-19 A | 2020-04-09
INTERCESSION CITY - K967 Total | 1398 | 1 | 64619 | 1400 | 30-Dec-19 A | 2020-04-09
ZELLWOOD - M33 |  | 1 | 64619 | 1400 | 2020-06-09 | 2020-06-09
ZELLWOOD - M33 |  | 1 | 64619 | 1400 | 2020-06-11 | 2020-06-11
ZELLWOOD - M33 |  | 1 | 64619 | 1400 | 2020-06-16 | 2020-06-16
ZELLWOOD - M33 |  | 1 | 64619 | 1400 | 2020-06-18 | 2020-06-18
ZELLWOOD - M33 |  | 1 | 64619 | 1400 | 2020-06-23 | 2020-06-23
ZELLWOOD - M33 Total | 1226 | 5 | 323095 | 7000 | 2020-06-09 | 2020-06-23
KELLY PARK - M34 |  | 1 | 64619 | 1400 | 2020-06-25 | 2020-06-25
KELLY PARK - M34 |  | 1 | 64619 | 1400 | 2020-07-02 | 2020-07-02
KELLY PARK - M34 |  | 1 | 40000 | 814 | 2020-07-15 | 2020-07-21
KELLY PARK - M34 Total | 1567 | 3 | 169238 | 3614 | 2020-06-25 | 2020-07-21
KELLY PARK - M821 |  | 1 | 64619 | 1400 | 2020-06-30 | 2020-06-30
KELLY PARK - M821 |  | 1 | 40000 | 814 | 2020-07-07 | 2020-07-07
KELLY PARK - M821 |  | 1 | 40000 | 814 | 2020-07-08 | 2020-07-14
KELLY PARK - M821 Total | 1338 | 3 | 144619 | 3028 | 2020-06-30 | 2020-07-14
LAKE PLACID - K1066 |  | 1 | 64619 | 1400 | 2020-05-19 | 2020-05-19
LAKE PLACID - K1066 |  | 1 | 64619 | 1400 | 2020-05-21 | 2020-05-21
LAKE PLACID - K1066 |  | 1 | 64619 | 1400 | 2020-05-28 | 2020-05-28
LAKE PLACID - K1066 |  | 1 | 64619 | 1400 | 2020-06-02 | 2020-06-02
LAKE PLACID - K1066 |  | 1 | 64619 | 1400 | 2020-06-04 | 2020-06-04
LAKE PLACID - K1066 Total | 1411 | 5 | 323095 | 7000 | 2020-05-19 | 2020-06-04
LAKE PLACID - K1320 |  | 1 | 64619 | 1400 | 2020-05-05 | 2020-05-05
LAKE PLACID - K1320 |  | 1 | 64619 | 1400 | 2020-05-12 | 2020-05-12
LAKE PLACID - K1320 |  | 1 | 64619 | 1400 | 2020-06-30 | 2020-06-30
LAKE PLACID - K1320 |  | 1 | 64619 | 1400 | 16-Jul-20* | 2020-07-16
LAKE PLACID - K1320 Total | 2243 | 4 | 258476 | 5600 | 2020-05-05 | 2020-07-16
FISHEATING CREEK - K1560 |  | 1 | 64619 | 1400 | 2020-05-01 | 2020-05-01
FISHEATING CREEK - K1560 |  | 1 | 64619 | 1400 | 2020-06-11 | 2020-06-11
FISHEATING CREEK - K1560 |  | 1 | 64619 | 1400 | 2020-06-18 | 2020-06-18
FISHEATING CREEK - K1560 |  | 1 | 64619 | 1400 | 2020-06-23 | 2020-06-23
FISHEATING CREEK - K1560 |  | 1 | 64619 | 1400 | 2020-06-25 | 2020-06-25
FISHEATING CREEK - K1560 |  | 1 | 64619 | 1400 | 2020-07-09 | 2020-07-09
FISHEATING CREEK - K1560 |  | 1 | 64619 | 1400 | 2020-07-14 | 2020-07-14
FISHEATING CREEK - K1560 |  | 1 | 64619 | 1400 | 2020-07-21 | 2020-07-21
FISHEATING CREEK - K1560 Total | 2473 | 8 | 516952 | 11200 | 2020-05-01 | 2020-07-21
LAKE PLACID NORTH - K27 |  | 1 | 64619 | 1400 | 2020-04-30 | 2020-04-30
LAKE PLACID NORTH - K27 |  | 1 | 64619 | 1400 | 2020-05-14 | 2020-05-14
LAKE PLACID NORTH - K27 |  | 1 | 64619 | 1400 | 2020-05-26 | 2020-05-26
LAKE PLACID NORTH - K27 |  | 1 | 64619 | 1400 | 2020-07-02 | 2020-07-02
LAKE PLACID NORTH - K27 Total | 563 | 4 | 258476 | 5600 | 2020-04-30 | 2020-07-02
LAKE PLACID - K757 |  | 1 | 64619 | 1400 | 2020-04-16 | 2020-04-16
LAKE PLACID - K757 |  | 1 | 64619 | 1400 | 2020-04-21 | 2020-04-21
LAKE PLACID - K757 |  | 1 | 64619 | 1400 | 2020-04-23 | 2020-04-23
LAKE PLACID - K757 |  | 1 | 64619 | 1400 | 2020-04-28 | 2020-04-28
LAKE PLACID - K757 |  | 1 | 64619 | 1400 | 2020-05-07 | 2020-05-07
LAKE PLACID - K757 Total | 920 | 5 | 323095 | 7000 | 2020-04-16 | 2020-05-07
LAKE PLACID - K758 |  | 1 | 64619 | 1400 | 2020-06-09 | 2020-06-09
LAKE PLACID - K758 |  | 1 | 64619 | 1400 | 2020-06-16 | 2020-06-16
LAKE PLACID - K758 |  | 1 | 64619 | 1400 | 2020-07-07 | 2020-07-07
LAKE PLACID - K758 Total | 1362 | 3 | 193857 | 4200 | 2020-06-09 | 2020-07-07
SUNFLOWER - W0470 |  | 1 | 64619 | 1400 | 2020-10-01 | 2020-10-01
SUNFLOWER - W0470 |  | 1 | 40000 | 814 | 2020-10-12 | 2020-10-16
SUNFLOWER - W0470 |  | 1 | 40000 | 814 | 2020-10-15 | 2020-10-21
SUNFLOWER - W0470 |  | 1 | 40000 | 814 | 15-Oct-20* | 2020-10-21
SUNFLOWER - W0470 |  | 1 | 40000 | 814 | 2020-10-19 | 2020-10-23
SUNFLOWER - W0470 |  | 1 | 40000 | 814 | 2020-10-22 | 2020-11-04
SUNFLOWER - W0470 Total | 2096 | 6 | 264619 | 5470 | 2020-10-01 | 2020-11-04
SUNFLOWER - W0473 |  | 1 | 40000 | 814 | 2020-10-22 | 2020-11-04
SUNFLOWER - W0473 |  | 1 | 40000 | 814 | 2020-11-02 | 2020-11-06
SUNFLOWER - W0473 |  | 1 | 40000 | 814 | 2020-11-05 | 2020-11-11
SUNFLOWER - W0473 |  | 1 | 40000 | 814 | 2020-11-05 | 2020-11-11
SUNFLOWER - W0473 |  | 1 | 40000 | 814 | 2020-11-09 | 2020-11-13
SUNFLOWER - W0473 Total | 1653 | 5 | 200000 | 4070 | 2020-10-22 | 2020-11-13
SUNFLOWER - W0474 |  | 1 | 64619 | 1400 | 2020-10-06 | 2020-10-06
SUNFLOWER - W0474 |  | 1 | 40000 | 814 | 2020-11-12 | 2020-11-18
SUNFLOWER - W0474 |  | 1 | 40000 | 814 | 2020-11-12 | 2020-11-18
SUNFLOWER - W0474 |  | 1 | 40000 | 814 | 2020-11-16 | 2020-11-20
SUNFLOWER - W0474 |  | 1 | 40000 | 814 | 2020-11-19 | 2020-12-02
SUNFLOWER - W0474 |  | 1 | 40000 | 814 | 2020-11-19 | 2020-12-02
SUNFLOWER - W0474 Total | 2126 | 6 | 264619 | 5470 | 2020-10-06 | 2020-12-02
BITHLO - W0953 |  | 1 | 64619 | 1400 | 2020-10-08 | 2020-10-08
BITHLO - W0953 |  | 1 | 64619 | 1400 | 2020-10-13 | 2020-10-13
BITHLO - W0953 |  | 1 | 64619 | 1400 | 2020-10-15 | 2020-10-15
BITHLO - W0953 |  | 1 | 64619 | 1400 | 2020-10-20 | 2020-10-20
BITHLO - W0953 |  | 1 | 40000 | 814 | 2020-12-03 | 2020-12-09
BITHLO - W0953 |  | 1 | 40000 | 814 | 2020-12-03 | 2020-12-09
BITHLO - W0953 Total | 2354 | 6 | 338476 | 7228 | 2020-10-08 | 2020-12-09
BITHLO - W0954 |  | 1 | 64619 | 1400 | 2020-10-22 | 2020-10-22
BITHLO - W0954 |  | 1 | 40000 | 814 | 2020-11-30 | 2020-12-04
BITHLO - W0954 |  | 1 | 40000 | 814 | 2020-12-07 | 2020-12-11
BITHLO - W0954 |  | 1 | 40000 | 814 | 2020-12-10 | 2020-12-16
BITHLO - W0954 |  | 1 | 40000 | 814 | 2020-12-14 | 2020-12-18
BITHLO - W0954 Total | 1805 | 5 | 224619 | 4656 | 2020-10-22 | 2020-12-18
ALAFAYA - W0298 |  | 1 | 64619 | 1400 | 2020-10-08 | 2020-10-14
ALAFAYA - W0298 Total | 1667 | 1 | 64619 | 1400 | 2020-10-08 | 2020-10-14
EAST ORANGE - W0250 |  | 1 | 64619 | 1400 | 13-Apr-20* | 2020-04-17
EAST ORANGE - W0250 Total | 1886 | 1 | 64619 | 1400 | 13-Apr-20* | 2020-04-17
EAST ORANGE - W0255 |  | 1 | 64619 | 1400 | 06-Apr-20* | 2020-04-06
EAST ORANGE - W0255 |  | 1 | 40000 | 814 | 11-Nov-19 A | 13-Mar-20 A
EAST ORANGE - W0255 Total | 974 | 2 | 104619 | 2214 | 11-Nov-19 A | 2020-04-06
MEADOW WOODS SOUTH - K1775 |  | 1 | 64619 | 1400 | 2020-07-02 | 2020-07-02
MEADOW WOODS SOUTH - K1775 |  | 1 | 64619 | 1400 | 2020-07-07 | 2020-07-07
MEADOW WOODS SOUTH - K1775 |  | 1 | 64619 | 1400 | 2020-07-16 | 2020-07-16
MEADOW WOODS SOUTH - K1775 |  | 1 | 64619 | 1400 | 2020-07-21 | 2020-07-21
MEADOW WOODS SOUTH - K1775 Total | 1325 | 4 | 258476 | 5600 | 2020-07-02 | 2020-07-21
MEADOW WOODS SOUTH - K1789 |  | 1 | 40000 | 814 | 2020-07-23 | 2020-07-29
MEADOW WOODS SOUTH - K1789 Total | 336 | 1 | 40000 | 814 | 2020-07-23 | 2020-07-29
HUNTERS CREEK - K42 |  | 1 | 64619 | 1400 | 2020-06-11 | 2020-06-11
HUNTERS CREEK - K42 |  | 1 | 64619 | 1400 | 2020-06-30 | 2020-06-30
HUNTERS CREEK - K42 |  | 1 | 64619 | 1400 | 2020-07-09 | 2020-07-09
HUNTERS CREEK - K42 |  | 1 | 64619 | 1400 | 2020-07-23 | 2020-07-23
HUNTERS CREEK - K42 |  | 1 | 64619 | 1400 | 2020-07-28 | 2020-07-28
HUNTERS CREEK - K42 |  | 1 | 64619 | 1400 | 2020-07-30 | 2020-07-30
HUNTERS CREEK - K42 |  | 1 | 40000 | 814 | 2020-07-13 | 2020-07-17
HUNTERS CREEK - K42 |  | 1 | 40000 | 814 | 2020-08-20 | 2020-09-02
HUNTERS CREEK - K42 Total | 2131 | 8 | 467714 | 10028 | 2020-06-11 | 2020-09-02
HUNTERS CREEK - K45 |  | 1 | 40000 | 814 | 2020-07-09 | 2020-07-15
HUNTERS CREEK - K45 |  | 1 | 40000 | 814 | 2020-07-16 | 2020-07-22
HUNTERS CREEK - K45 |  | 1 | 40000 | 814 | 2020-07-30 | 2020-08-05
HUNTERS CREEK - K45 |  | 1 | 40000 | 814 | 2020-08-06 | 2020-08-12
HUNTERS CREEK - K45 |  | 1 | 40000 | 814 | 2020-08-13 | 2020-08-19
HUNTERS CREEK - K45 |  | 1 | 40000 | 814 | 2020-09-11 | 2020-09-17
HUNTERS CREEK - K45 |  | 1 | 40000 | 814 | 2020-10-02 | 2020-10-08
HUNTERS CREEK - K45 |  | 1 | 40000 | 814 | 2020-10-09 | 2020-10-15
HUNTERS CREEK - K45 Total | 2501 | 8 | 320000 | 6512 | 2020-07-09 | 2020-10-15
HUNTERS CREEK - K51 |  | 1 | 64619 | 1400 | 2020-07-14 | 2020-07-14
HUNTERS CREEK - K51 |  | 1 | 40000 | 814 | 2020-07-06 | 2020-07-10
HUNTERS CREEK - K51 |  | 1 | 40000 | 814 | 2020-08-20 | 2020-09-02
HUNTERS CREEK - K51 |  | 1 | 40000 | 814 | 2020-09-03 | 2020-09-10
HUNTERS CREEK - K51 |  | 1 | 40000 | 814 | 2020-09-18 | 2020-10-01
HUNTERS CREEK - K51 Total | 2035 | 5 | 224619 | 4656 | 2020-07-06 | 2020-10-01
SHINGLE CREEK - K861 |  | 1 | 64619 | 1400 | 2020-06-25 | 2020-06-25
SHINGLE CREEK - K861 |  | 1 | 64619 | 1400 | 2020-08-04 | 2020-08-04
SHINGLE CREEK - K861 |  | 1 | 64619 | 1400 | 2020-08-06 | 2020-08-06
SHINGLE CREEK - K861 |  | 1 | 40000 | 814 | 2020-07-09 | 2020-07-15
SHINGLE CREEK - K861 Total | 1383 | 4 | 233857 | 5014 | 2020-06-25 | 2020-08-06
WINDERMERE - K302 |  | 1 | 64619 | 1400 | 2020-06-18 | 2020-06-18
WINDERMERE - K302 Total | 1187 | 1 | 64619 | 1400 | 2020-06-18 | 2020-06-18
WINDERMERE - K303 |  | 1 | 64619 | 1400 | 2020-06-23 | 2020-06-23
WINDERMERE - K303 |  | 1 | 64619 | 1400 | 2020-06-25 | 2020-06-25
WINDERMERE - K303 |  | 1 | 64619 | 1400 | 2020-07-09 | 2020-07-09
WINDERMERE - K303 |  | 1 | 64619 | 1400 | 2020-07-14 | 2020-07-14
WINDERMERE - K303 |  | 1 | 64619 | 1400 | 2020-07-28 | 2020-07-28
WINDERMERE - K303 |  | 1 | 64619 | 1400 | 2020-07-30 | 2020-07-30
WINDERMERE - K303 Total | 1938 | 6 | 387714 | 8400 | 2020-06-23 | 2020-07-30
BAY HILL - K68 |  | 1 | 64619 | 1400 | 2020-06-02 | 2020-06-02
BAY HILL - K68 |  | 1 | 64619 | 1400 | 2020-06-04 | 2020-06-04
BAY HILL - K68 |  | 1 | 64619 | 1400 | 2020-06-09 | 2020-06-09
BAY HILL - K68 |  | 1 | 64619 | 1400 | 2020-06-11 | 2020-06-11
BAY HILL - K68 |  | 1 | 64619 | 1400 | 2020-06-16 | 2020-06-16
BAY HILL - K68 |  | 1 | 64619 | 1400 | 2020-07-16 | 2020-07-16
BAY HILL - K68 |  | 1 | 64619 | 1400 | 2020-07-21 | 2020-07-21
BAY HILL - K68 |  | 1 | 64619 | 1400 | 2020-07-23 | 2020-07-23
BAY HILL - K68 Total | 1826 | 8 | 516952 | 11200 | 2020-06-02 | 2020-07-23
OCOEE - M1090 |  | 1 | 64619 | 1400 | 2020-05-26 | 2020-05-26
OCOEE - M1090 |  | 1 | 64619 | 1400 | 2020-06-30 | 2020-06-30
OCOEE - M1090 |  | 1 | 64619 | 1400 | 2020-07-02 | 2020-07-02
OCOEE - M1090 |  | 1 | 64619 | 1400 | 2020-07-07 | 2020-07-07
OCOEE - M1090 |  | 1 | 64619 | 1400 | 2020-08-11 | 2020-08-11
OCOEE - M1090 Total | 2276 | 5 | 323095 | 7000 | 2020-05-26 | 2020-08-11
WOODSMERE - M255 |  | 1 | 64619 | 1400 | 2020-05-28 | 2020-05-28
WOODSMERE - M255 |  | 1 | 64619 | 1400 | 2020-08-04 | 2020-08-04
WOODSMERE - M255 |  | 1 | 64619 | 1400 | 2020-08-06 | 2020-08-06
WOODSMERE - M255 |  | 1 | 64619 | 1400 | 2020-08-13 | 2020-08-13
WOODSMERE - M255 Total | 1147 | 4 | 258476 | 5600 | 2020-05-28 | 2020-08-13
OKAHUMPKA - K285 |  | 1 | 64619 | 1400 | 25-Mar-20* | 2020-03-25
OKAHUMPKA - K285 |  | 1 | 64619 | 1400 | 2020-05-06 | 2020-05-06
OKAHUMPKA - K285 |  | 1 | 64619 | 1400 | 2020-05-06 | 2020-05-06
OKAHUMPKA - K285 |  | 1 | 64619 | 1400 | 2020-05-13 | 2020-05-13
OKAHUMPKA - K285 Total | 1686 | 4 | 258476 | 5600 | 25-Mar-20* | 2020-05-13
OKAHUMPKA - K565 |  | 1 | 64619 | 1400 | 04-Mar-20 A | 04-Mar-20 A
OKAHUMPKA - K565 |  | 1 | 64619 | 1400 | 2020-04-08 | 2020-04-08
OKAHUMPKA - K565 Total | 1300 | 2 | 129238 | 2800 | 04-Mar-20 A | 2020-04-08
Frostproof - K101 |  | 1 | 64619 | 1400 | 2020-09-16 | 2020-09-16
Frostproof - K101 Total | 2647 | 1 | 64619 | 1400 | 2020-09-16 | 2020-09-16
FROSTPROOF - K102 |  | 1 | 64619 | 1400 | 2020-08-05 | 2020-08-05
FROSTPROOF - K102 |  | 1 | 64619 | 1400 | 2020-08-12 | 2020-08-12
FROSTPROOF - K102 |  | 1 | 64619 | 1400 | 2020-08-19 | 2020-08-19
FROSTPROOF - K102 |  | 1 | 64619 | 1400 | 2020-08-24 | 2020-08-24
FROSTPROOF - K102 |  | 1 | 64619 | 1400 | 2020-09-02 | 2020-09-02
FROSTPROOF - K102 |  | 1 | 64619 | 1400 | 2020-09-09 | 2020-09-09
FROSTPROOF - K102 Total | 1966 | 6 | 387714 | 8400 | 2020-08-05 | 2020-09-09
FROSTPROOF - K104 |  | 1 | 64619 | 1400 | 2020-07-22 | 2020-07-22
FROSTPROOF - K104 |  | 1 | 64619 | 1400 | 2020-07-29 | 2020-07-29
FROSTPROOF - K104 Total | 1440 | 2 | 129238 | 2800 | 2020-07-22 | 2020-07-29
TAUNTON ROAD - K1081 |  | 1 | 64619 | 1400 | 2020-06-03 | 2020-06-03
TAUNTON ROAD - K1081 |  | 1 | 64619 | 1400 | 2020-06-10 | 2020-06-10
TAUNTON ROAD - K1081 Total | 1395 | 2 | 129238 | 2800 | 2020-06-03 | 2020-06-10
AVON PARK NORTH - K891 |  | 1 | 64619 | 1400 | 2020-06-17 | 2020-06-17
AVON PARK NORTH - K891 |  | 1 | 64619 | 1400 | 2020-07-01 | 2020-07-01
AVON PARK NORTH - K891 |  | 1 | 64619 | 1400 | 2020-07-08 | 2020-07-08
AVON PARK NORTH - K891 |  | 1 | 64619 | 1400 | 2020-07-15 | 2020-07-15
AVON PARK NORTH - K891 Total | 1921 | 4 | 258476 | 5600 | 2020-06-17 | 2020-07-15
AVON PARK NORTH - K892 |  | 1 | 64619 | 1400 | 2020-06-24 | 2020-06-24
AVON PARK NORTH - K892 Total | 356 | 1 | 64619 | 1400 | 2020-06-24 | 2020-06-24
ORANGEWOOD - K226 |  | 1 | 64619 | 1400 | 2020-10-07 | 2020-10-07
ORANGEWOOD - K226 |  | 1 | 64619 | 1400 | 2020-10-14 | 2020-10-14
ORANGEWOOD - K226 |  | 1 | 64619 | 1400 | 2020-11-04 | 2020-11-04
ORANGEWOOD - K226 |  | 1 | 64619 | 1400 | 2020-11-11 | 2020-11-11
ORANGEWOOD - K226 |  | 1 | 64619 | 1400 | 2020-12-02 | 2020-12-02
ORANGEWOOD - K226 Total | 1922 | 5 | 323095 | 7000 | 2020-10-07 | 2020-12-02
SHINGLE CREEK - K858 |  | 1 | 64619 | 1400 | 2020-10-21 | 2020-10-21
SHINGLE CREEK - K858 |  | 1 | 64619 | 1400 | 2020-11-18 | 2020-11-18
SHINGLE CREEK - K858 |  | 1 | 64619 | 1400 | 2020-11-30 | 2020-11-30
SHINGLE CREEK - K858 |  | 1 | 64619 | 1400 | 2020-12-09 | 2020-12-09
SHINGLE CREEK - K858 |  | 1 | 40000 | 814 | 2020-12-10 | 2020-12-16
SHINGLE CREEK - K858 Total | 1809 | 5 | 298476 | 6414 | 2020-12-10 | 2020-12-16
SOPCHOPPY - N327 |  | 1 | 64619 | 1400 | 2020-07-07 | 2020-07-07
SOPCHOPPY - N327 Total | 1463 | 1 | 64619 | 1400 | 2020-07-07 | 2020-07-07
CRYSTAL RIVER SOUTH - A158 |  | 1 | 64619 | 1400 | 01-Jan-20 A | 16-Jan-20 A
CRYSTAL RIVER SOUTH - A158 Total | 1401 | 1 | 64619 | 1400 | 01-Jan-20 A | 16-Jan-20 A
TROPIC TERRACE - A207 |  | 1 | 64619 | 1400 | 14-Apr-20* | 2020-04-14
TROPIC TERRACE - A207 Total | 1414 | 1 | 64619 | 1400 | 14-Apr-20* | 2020-04-14
HOMOSASSA - A272 |  | 1 | 64619 | 1400 | 16-Jan-20 A | 16-Jan-20 A
HOMOSASSA - A272 |  | 1 | 64619 | 1400 | 16-Jan-20 A | 22-Jan-20 A
HOMOSASSA - A272 Total | 1545 | 2 | 129238 | 2800 | 16-Jan-20 A | 22-Jan-20 A
CRAWFORDVILLE - N35 |  | 1 | 64619 | 1400 | 2020-06-15 | 2020-06-15
CRAWFORDVILLE - N35 |  | 1 | 64619 | 1400 | 2020-06-24 | 2020-06-24
CRAWFORDVILLE - N35 |  | 1 | 64619 | 1400 | 2020-06-26 | 2020-06-26
CRAWFORDVILLE - N35 |  | 1 | 64619 | 1400 | 2020-06-29 | 2020-06-29
CRAWFORDVILLE - N35 |  | 1 | 64619 | 1400 | 2020-07-01 | 2020-07-01
CRAWFORDVILLE - N35 |  | 1 | 64619 | 1400 | 2020-07-02 | 2020-07-02
CRAWFORDVILLE - N35 Total | 1190 | 6 | 387714 | 8400 | 2020-06-15 | 2020-07-02
CRAWFORDVILLE - N36 |  | 1 | 64619 | 1400 | 2020-06-17 | 2020-06-17
CRAWFORDVILLE - N36 |  | 1 | 64619 | 1400 | 2020-06-19 | 2020-06-19
CRAWFORDVILLE - N36 |  | 1 | 64619 | 1400 | 2020-06-22 | 2020-06-22
CRAWFORDVILLE - N36 Total | 1182 | 3 | 193857 | 4200 | 2020-06-17 | 2020-06-22
REDDICK - A35 |  | 1 | 64619 | 1400 | 09-Apr-20* | 2020-04-09
REDDICK - A35 |  | 1 | 64619 | 1400 | 2020-04-16 | 2020-04-16
REDDICK - A35 |  | 1 | 64619 | 1400 | 2020-04-21 | 2020-04-21
REDDICK - A35 |  | 1 | 64619 | 1400 | 2020-05-12 | 2020-05-12
REDDICK - A35 Total | 569 | 4 | 258476 | 5600 | 09-Apr-20* | 2020-05-12
REDDICK - A36 |  | 1 | 64619 | 1400 | 2020-04-14 | 2020-04-14
REDDICK - A36 |  | 1 | 64619 | 1400 | 2020-05-01 | 2020-05-01
REDDICK - A36 |  | 1 | 64619 | 1400 | 2020-05-07 | 2020-05-07
REDDICK - A36 Total | 1166 | 3 | 193857 | 4200 | 2020-04-14 | 2020-05-07
MCINTOSH - A50 |  | 1 | 64619 | 1400 | 2020-04-23 | 2020-04-23
MCINTOSH - A50 |  | 1 | 64619 | 1400 | 2020-05-05 | 2020-05-05
MCINTOSH - A50 Total | 836 | 2 | 129238 | 2800 | 2020-04-23 | 2020-05-05
MCINTOSH - A51 |  | 1 | 64619 | 1400 | 2020-04-28 | 2020-04-28
MCINTOSH - A51 |  | 1 | 64619 | 1400 | 2020-04-30 | 2020-04-30
MCINTOSH - A51 |  | 1 | 64619 | 1400 | 2020-05-14 | 2020-05-14
MCINTOSH - A51 Total | 1315 | 3 | 193857 | 4200 | 2020-04-28 | 2020-05-14
PORT RICHEY WEST - C208 |  | 1 | 64619 | 1400 | 2020-10-08 | 2020-10-08
PORT RICHEY WEST - C208 |  | 1 | 64619 | 1400 | 2020-10-13 | 2020-10-13
PORT RICHEY WEST - C208 |  | 1 | 64619 | 1400 | 2020-10-15 | 2020-10-15
PORT RICHEY WEST - C208 |  | 1 | 64619 | 1400 | 2020-10-20 | 2020-10-20
PORT RICHEY WEST - C208 |  | 1 | 64619 | 1400 | 2020-10-22 | 2020-10-22
PORT RICHEY WEST - C208 |  | 1 | 64619 | 1400 | 2020-11-03 | 2020-11-03
PORT RICHEY WEST - C208 Total | 2163 | 6 | 387714 | 8400 | 2020-10-08 | 2020-11-03
PORT RICHEY WEST - C210 |  | 1 | 64619 | 1400 | 2020-08-20 | 2020-08-20
PORT RICHEY WEST - C210 |  | 1 | 64619 | 1400 | 2020-11-17 | 2020-11-17
PORT RICHEY WEST - C210 |  | 1 | 64619 | 1400 | 2020-11-19 | 2020-11-19
PORT RICHEY WEST - C210 |  | 1 | 64619 | 1400 | 2020-12-03 | 2020-12-03
PORT RICHEY WEST - C210 |  | 1 | 64619 | 1400 | 2020-12-08 | 2020-12-08
PORT RICHEY WEST - C210 Total | 2355 | 5 | 323095 | 7000 | 2020-08-20 | 2020-12-08
FLORA MAR - C4001 |  | 1 | 64619 | 1400 | 2020-08-18 | 2020-08-18
FLORA MAR - C4001 |  | 1 | 64619 | 1400 | 2020-09-15 | 2020-09-15
FLORA MAR - C4001 |  | 1 | 64619 | 1400 | 2020-11-30 | 2020-11-30
FLORA MAR - C4001 |  | 1 | 64619 | 1400 | 2020-12-01 | 2020-12-01
FLORA MAR - C4001 |  | 1 | 64619 | 1400 | 2020-12-10 | 2020-12-10
FLORA MAR - C4001 |  | 1 | 64619 | 1400 | 2020-12-15 | 2020-12-15
FLORA MAR - C4001 |  | 1 | 64619 | 1400 | 2020-12-17 | 2020-12-17
FLORA MAR - C4001 |  | 1 | 64619 | 1400 | 2020-12-17 | 2020-12-17
FLORA MAR - C4001 Total | 2268 | 8 | 516952 | 11200 | 2020-08-18 | 2020-12-17
FLORA MAR - C4002 |  | 1 | 64619 | 1400 | 2020-09-08 | 2020-09-08
FLORA MAR - C4002 |  | 1 | 64619 | 1400 | 2020-09-10 | 2020-09-10
FLORA MAR - C4002 |  | 1 | 64619 | 1400 | 2020-09-22 | 2020-09-22
FLORA MAR - C4002 |  | 1 | 64619 | 1400 | 2020-09-03 | 2020-09-03
FLORA MAR - C4002 |  | 1 | 64619 | 1400 | 2020-11-10 | 2020-11-10
FLORA MAR - C4002 |  | 1 | 64619 | 1400 | 2020-11-12 | 2020-11-12
FLORA MAR - C4002 Total | 2310 | 6 | 387714 | 8400 | 2020-09-08 | 2020-11-12
FLORA MAR - C4003 |  | 1 | 64619 | 1400 | 2020-09-01 | 2020-09-01
FLORA MAR - C4003 |  | 1 | 64619 | 1400 | 2020-09-01 | 2020-09-01
FLORA MAR - C4003 |  | 1 | 64619 | 1400 | 2020-09-15 | 2020-09-15
FLORA MAR - C4003 |  | 1 | 64619 | 1400 | 2020-11-05 | 2020-11-05
FLORA MAR - C4003 |  | 1 | 64619 | 1400 | 2020-09-17 | 2020-09-17
FLORA MAR - C4003 |  | 1 | 64619 | 1400 | 2020-10-01 | 2020-10-01
FLORA MAR - C4003 Total | 2380 | 6 | 387714 | 8400 | 2020-09-01 | 2020-10-01
FLORA MAR - C4006 |  | 1 | 64619 | 1400 | 2020-08-13 | 2020-08-13
FLORA MAR - C4006 |  | 1 | 64619 | 1400 | 2020-09-03 | 2020-09-03
FLORA MAR - C4006 |  | 1 | 64619 | 1400 | 2020-09-08 | 2020-09-08
FLORA MAR - C4006 |  | 1 | 64619 | 1400 | 2020-09-10 | 2020-09-10
FLORA MAR - C4006 |  | 1 | 64619 | 1400 | 2020-09-10 | 2020-09-10
FLORA MAR - C4006 Total | 2932 | 5 | 323095 | 7000 | 2020-08-13 | 2020-09-10
ELFERS - C952 |  | 1 | 64619 | 1400 | 2020-08-24 | 2020-08-24
ELFERS - C952 |  | 1 | 64619 | 1400 | 2020-10-06 | 2020-10-06
ELFERS - C952 Total | 2187 | 2 | 129238 | 2800 | 2020-08-24 | 2020-10-06
BAYBORO - X16 |  | 1 | 64619 | 1400 | 2020-04-07 | 2020-04-07
BAYBORO - X16 |  | 1 | 64619 | 1400 | 2020-04-14 | 2020-04-14
BAYBORO - X16 |  | 1 | 64619 | 1400 | 22-Apr-20* | 2020-04-22
BAYBORO - X16 |  | 1 | 64619 | 1400 | 2020-05-01 | 2020-05-01
BAYBORO - X16 |  | 1 | 64619 | 1400 | 2020-05-05 | 2020-05-05
BAYBORO - X16 |  | 1 | 64619 | 1400 | 2020-05-06 | 2020-05-06
BAYBORO - X16 Total | 2782 | 6 | 387714 | 8400 | 2020-04-07 | 2020-05-06
BAYBORO - X21 |  | 1 | 64619 | 1400 | 03-Mar-20 A | 03-Mar-20 A
BAYBORO - X21 |  | 1 | 64619 | 1400 | 2020-04-09 | 2020-04-09
BAYBORO - X21 |  | 1 | 64619 | 1400 | 2020-04-09 | 2020-04-09
BAYBORO - X21 |  | 1 | 64619 | 1400 | 15-Apr-20* | 2020-04-15
BAYBORO - X21 |  | 1 | 64619 | 1400 | 2020-04-16 | 2020-04-16
BAYBORO - X21 |  | 1 | 64619 | 1400 | 2020-04-21 | 2020-04-21
BAYBORO - X21 |  | 1 | 64619 | 1400 | 2020-04-28 | 2020-04-28
BAYBORO - X21 |  | 1 | 64619 | 1400 | 2020-04-29 | 2020-04-29
BAYBORO - X21 Total | 2565 | 8 | 516952 | 11200 | 03-Mar-20 A | 2020-04-29
SIXTEENTH STREET - X43 |  | 1 | 64619 | 1400 | 20-Feb-20 A | 20-Feb-20 A
SIXTEENTH STREET - X43 |  | 1 | 64619 | 1400 | 06-Mar-20 A | 06-Mar-20 A
SIXTEENTH STREET - X43 |  | 1 | 64619 | 1400 | 07-Apr-20* | 2020-04-07
SIXTEENTH STREET - X43 Total | 1253 | 3 | 193857 | 4200 | 20-Feb-20 A | 2020-04-07
SIXTEENTH STREET - X46 |  | 1 | 64619 | 1400 | 10-Mar-20 A | 10-Mar-20 A
SIXTEENTH STREET - X46 |  | 1 | 64619 | 1400 | 2020-04-14 | 2020-04-14
SIXTEENTH STREET - X46 |  | 1 | 64619 | 1400 | 2020-04-30 | 2020-04-30
SIXTEENTH STREET - X46 Total | 2389 | 3 | 193857 | 4200 | 10-Mar-20 A | 2020-04-30
BAYBORO - X9 |  | 1 | 64619 | 1400 | 2020-04-02 | 2020-04-02
BAYBORO - X9 |  | 1 | 64619 | 1400 | 2020-04-09 | 2020-04-09
BAYBORO - X9 |  | 1 | 64619 | 1400 | 2020-04-14 | 2020-04-14
BAYBORO - X9 |  | 1 | 64619 | 1400 | 2020-04-16 | 2020-04-16
BAYBORO - X9 |  | 1 | 64619 | 1400 | 2020-04-23 | 2020-04-23
BAYBORO - X9 Total | 2257 | 5 | 323095 | 7000 | 2020-04-02 | 2020-04-23
DUNEDIN - C103 |  | 1 | 64619 | 1400 | 30-Jan-20 A | 2020-05-26
DUNEDIN - C103 |  | 1 | 64619 | 1400 | 2020-06-02 | 2020-06-02
DUNEDIN - C103 |  | 1 | 64619 | 1400 | 2020-06-04 | 2020-06-04
DUNEDIN - C103 |  | 1 | 64619 | 1400 | 2020-06-11 | 2020-06-11
DUNEDIN - C103 Total | 3052 | 4 | 258476 | 5600 | 30-Jan-20 A | 2020-06-11
DUNEDIN - C104 |  | 1 | 64619 | 1400 | 29-Jan-20 A | 2020-05-26
DUNEDIN - C104 |  | 1 | 64619 | 1400 | 2020-05-27 | 2020-05-27
DUNEDIN - C104 |  | 1 | 64619 | 1400 | 2020-06-02 | 2020-06-02
DUNEDIN - C104 |  | 1 | 64619 | 1400 | 2020-06-18 | 2020-06-18
DUNEDIN - C104 |  | 1 | 64619 | 1400 | 2020-07-16 | 2020-07-16
DUNEDIN - C104 Total | 2127 | 5 | 323095 | 7000 | 29-Jan-20 A | 2020-07-16
DUNEDIN - C108 |  | 1 | 64619 | 1400 | 22-Jan-20 A | 2020-06-11
DUNEDIN - C108 |  | 1 | 64619 | 1400 | 30-Jan-20 A | 2020-05-28
DUNEDIN - C108 |  | 1 | 64619 | 1400 | 2020-05-27 | 2020-05-27
DUNEDIN - C108 |  | 1 | 64619 | 1400 | 2020-06-09 | 2020-06-09
DUNEDIN - C108 Total | 2279 | 4 | 258476 | 5600 | 22-Jan-20 A | 2020-06-09
CURLEW (HD) - C4988 |  | 1 | 64619 | 1400 | 29-Jan-20 A | 2020-06-04
CURLEW (HD) - C4988 |  | 1 | 64619 | 1400 | 2020-06-04 | 2020-06-04
CURLEW (HD) - C4988 |  | 1 | 64619 | 1400 | 2020-06-09 | 2020-06-09
CURLEW (HD) - C4988 |  | 1 | 64619 | 1400 | 2020-06-16 | 2020-06-16
CURLEW (HD) - C4988 Total | 1708 | 4 | 258476 | 5600 | 29-Jan-20 A | 2020-06-16
PALM HARBOR - C753 |  | 1 | 64619 | 1400 | 2020-06-04 | 2020-06-04
PALM HARBOR - C753 |  | 1 | 64619 | 1400 | 2020-06-11 | 2020-06-11
PALM HARBOR - C753 |  | 1 | 64619 | 1400 | 2020-06-16 | 2020-06-16
PALM HARBOR - C753 |  | 1 | 64619 | 1400 | 2020-06-18 | 2020-06-18
PALM HARBOR - C753 |  | 1 | 64619 | 1400 | 2020-06-30 | 2020-06-30
PALM HARBOR - C753 Total | 2129 | 5 | 323095 | 7000 | 2020-06-04 | 2020-06-30
PALM HARBOR - C755 |  | 1 | 64619 | 1400 | 2020-06-09 | 2020-06-09
PALM HARBOR - C755 |  | 1 | 64619 | 1400 | 2020-06-09 | 2020-06-09
PALM HARBOR - C755 |  | 1 | 64619 | 1400 | 2020-06-23 | 2020-06-23
PALM HARBOR - C755 |  | 1 | 64619 | 1400 | 2020-06-25 | 2020-06-25
PALM HARBOR - C755 |  | 1 | 64619 | 1400 | 2020-07-02 | 2020-07-02
PALM HARBOR - C755 |  | 1 | 64619 | 1400 | 2020-07-07 | 2020-07-07
PALM HARBOR - C755 |  | 1 | 64619 | 1400 | 2020-07-14 | 2020-07-14
PALM HARBOR - C755 Total | 2597 | 7 | 452333 | 9800 | 2020-06-09 | 2020-07-14
EAST CLEARWATER - C907 |  | 1 | 64619 | 1400 | 2020-06-04 | 2020-06-04
EAST CLEARWATER - C907 |  | 1 | 64619 | 1400 | 2020-06-09 | 2020-06-09
EAST CLEARWATER - C907 |  | 1 | 64619 | 1400 | 2020-06-11 | 2020-06-11
EAST CLEARWATER - C907 |  | 1 | 64619 | 1400 | 2020-07-09 | 2020-07-09
EAST CLEARWATER - C907 Total | 2824 | 4 | 258476 | 5600 | 2020-06-04 | 2020-07-09
HIGHLANDS - C2802 |  | 1 | 64619 | 1400 | 2020-05-12 | 2020-05-12
HIGHLANDS - C2802 |  | 1 | 64619 | 1400 | 2020-07-09 | 2020-07-09
HIGHLANDS - C2802 |  | 1 | 64619 | 1400 | 2020-07-30 | 2020-07-30
HIGHLANDS - C2802 Total | 2209 | 3 | 193857 | 4200 | 2020-05-12 | 2020-07-30
HIGHLANDS - C2803 |  | 1 | 64619 | 1400 | 2020-06-04 | 2020-06-04
HIGHLANDS - C2803 |  | 1 | 64619 | 1400 | 2020-06-25 | 2020-06-25
HIGHLANDS - C2803 |  | 1 | 64619 | 1400 | 2020-07-14 | 2020-07-14
HIGHLANDS - C2803 |  | 1 | 64619 | 1400 | 2020-07-23 | 2020-07-23
HIGHLANDS - C2803 Total | 2595 | 4 | 258476 | 5600 | 2020-06-04 | 2020-07-23
HIGHLANDS - C2804 |  | 1 | 64619 | 1400 | 2020-05-05 | 2020-05-05
HIGHLANDS - C2804 |  | 1 | 64619 | 1400 | 2020-05-19 | 2020-05-19
HIGHLANDS - C2804 |  | 1 | 64619 | 1400 | 2020-05-21 | 2020-05-21
HIGHLANDS - C2804 |  | 1 | 64619 | 1400 | 2020-05-28 | 2020-05-28
HIGHLANDS - C2804 Total | 2011 | 4 | 258476 | 5600 | 2020-05-05 | 2020-05-28
HIGHLANDS - C2805 |  | 1 | 64619 | 1400 | 2020-06-09 | 2020-06-09
HIGHLANDS - C2805 |  | 1 | 64619 | 1400 | 2020-06-16 | 2020-06-16
HIGHLANDS - C2805 |  | 1 | 64619 | 1400 | 2020-06-18 | 2020-06-18
HIGHLANDS - C2805 |  | 1 | 64619 | 1400 | 2020-06-30 | 2020-06-30
HIGHLANDS - C2805 |  | 1 | 64619 | 1400 | 2020-07-28 | 2020-07-28
HIGHLANDS - C2805 Total | 2835 | 5 | 323095 | 7000 | 2020-06-09 | 2020-07-28
HIGHLANDS - C2807 |  | 1 | 64619 | 1400 | 2020-05-07 | 2020-05-07
HIGHLANDS - C2807 |  | 1 | 64619 | 1400 | 2020-05-26 | 2020-05-26
HIGHLANDS - C2807 |  | 1 | 64619 | 1400 | 2020-06-11 | 2020-06-11
HIGHLANDS - C2807 |  | 1 | 64619 | 1400 | 2020-07-02 | 2020-07-02
HIGHLANDS - C2807 Total | 1953 | 4 | 258476 | 5600 | 2020-05-07 | 2020-07-02
HIGHLANDS - C2808 |  | 1 | 64619 | 1400 | 2020-05-14 | 2020-05-14
HIGHLANDS - C2808 Total | 549 | 1 | 64619 | 1400 | 2020-05-14 | 2020-05-14
EAST CLEARWATER - C908 |  | 1 | 64619 | 1400 | 2020-06-02 | 2020-06-02
EAST CLEARWATER - C908 |  | 1 | 64619 | 1400 | 2020-06-23 | 2020-06-23
EAST CLEARWATER - C908 |  | 1 | 64619 | 1400 | 2020-07-07 | 2020-07-07
EAST CLEARWATER - C908 |  | 1 | 64619 | 1400 | 2020-07-16 | 2020-07-16
EAST CLEARWATER - C908 |  | 1 | 64619 | 1400 | 2020-07-21 | 2020-07-21
EAST CLEARWATER - C908 |  | 1 | 64619 | 1400 | 2020-08-04 | 2020-08-04
EAST CLEARWATER - C908 Total | 2984 | 6 | 387714 | 8400 | 2020-06-02 | 2020-08-04
FLORA MAR - C4000 |  | 1 | 64619 | 1400 | 2020-05-20 | 2020-05-20
FLORA MAR - C4000 |  | 1 | 64619 | 1400 | 2020-06-30 | 2020-06-30
FLORA MAR - C4000 |  | 1 | 64619 | 1400 | 2020-07-23 | 2020-07-23
FLORA MAR - C4000 |  | 1 | 64619 | 1400 | 2020-08-11 | 2020-08-11
FLORA MAR - C4000 |  | 1 | 64619 | 1400 | 2020-08-20 | 2020-08-20
FLORA MAR - C4000 Total | 2095 | 5 | 323095 | 7000 | 2020-05-20 | 2020-08-20
FLORA MAR - C4007 |  | 1 | 64619 | 1400 | 2020-05-13 | 2020-05-13
FLORA MAR - C4007 |  | 1 | 64619 | 1400 | 2020-05-19 | 2020-05-19
FLORA MAR - C4007 |  | 1 | 64619 | 1400 | 2020-07-28 | 2020-07-28
FLORA MAR - C4007 Total | 1886 | 3 | 193857 | 4200 | 2020-05-13 | 2020-07-28
FLORA MAR - C4009 |  | 1 | 64619 | 1400 | 2020-05-18 | 2020-05-18
FLORA MAR - C4009 |  | 1 | 64619 | 1400 | 2020-05-26 | 2020-05-26
FLORA MAR - C4009 |  | 1 | 64619 | 1400 | 2020-07-14 | 2020-07-14
FLORA MAR - C4009 |  | 1 | 64619 | 1400 | 2020-07-21 | 2020-07-21
FLORA MAR - C4009 Total | 1913 | 4 | 258476 | 5600 | 2020-05-18 | 2020-07-21
SEVEN SPRINGS - C4501 |  | 1 | 64619 | 1400 | 2020-05-19 | 2020-05-19
SEVEN SPRINGS - C4501 |  | 1 | 64619 | 1400 | 2020-07-02 | 2020-07-02
SEVEN SPRINGS - C4501 |  | 1 | 64619 | 1400 | 2020-07-07 | 2020-07-07
SEVEN SPRINGS - C4501 |  | 1 | 64619 | 1400 | 2020-07-09 | 2020-07-09
SEVEN SPRINGS - C4501 |  | 1 | 64619 | 1400 | 2020-08-13 | 2020-08-13
SEVEN SPRINGS - C4501 Total | 2402 | 5 | 323095 | 7000 | 2020-05-19 | 2020-08-13
SEVEN SPRINGS - C4508 |  | 1 | 64619 | 1400 | 2020-07-16 | 2020-07-16
SEVEN SPRINGS - C4508 |  | 1 | 64619 | 1400 | 2020-07-30 | 2020-07-30
SEVEN SPRINGS - C4508 |  | 1 | 64619 | 1400 | 2020-08-04 | 2020-08-04
SEVEN SPRINGS - C4508 |  | 1 | 64619 | 1400 | 2020-08-06 | 2020-08-06
SEVEN SPRINGS - C4508 |  | 1 | 64619 | 1400 | 2020-08-18 | 2020-08-18
SEVEN SPRINGS - C4508 Total | 3479 | 5 | 323095 | 7000 | 2020-07-16 | 2020-08-18
ELFERS - C950 |  | 1 | 64619 | 1400 | 2020-05-15 | 2020-05-15
ELFERS - C950 |  | 1 | 64619 | 1400 | 2020-05-21 | 2020-05-21
ELFERS - C950 Total | 1961 | 2 | 129238 | 2800 | 2020-05-15 | 2020-05-21
PASADENA - X211 |  | 1 | 64619 | 1400 | 2020-09-03 | 2020-09-03
PASADENA - X211 |  | 1 | 64619 | 1400 | 2020-09-04 | 2020-09-04
PASADENA - X211 |  | 1 | 64619 | 1400 | 2020-09-08 | 2020-09-08
PASADENA - X211 |  | 1 | 64619 | 1400 | 2020-09-10 | 2020-09-10
PASADENA - X211 |  | 1 | 64619 | 1400 | 2020-09-22 | 2020-09-22
PASADENA - X211 |  | 1 | 64619 | 1400 | 2020-10-01 | 2020-10-01
PASADENA - X211 |  | 1 | 64619 | 1400 | 2020-10-06 | 2020-10-06
PASADENA - X211 |  | 1 | 64619 | 1400 | 2020-11-11 | 2020-11-11
PASADENA - X211 |  | 1 | 40000 | 814 | 2020-09-18 | 2020-10-01
PASADENA - X211 Total | 3359 | 9 | 556952 | 12014 | 2020-09-03 | 2020-10-01
PASADENA - X213 |  | 1 | 64619 | 1400 | 2020-07-09 | 2020-07-09
PASADENA - X213 |  | 1 | 64619 | 1400 | 2020-07-14 | 2020-07-14
PASADENA - X213 |  | 1 | 64619 | 1400 | 2020-09-15 | 2020-09-15
PASADENA - X213 |  | 1 | 64619 | 1400 | 2020-06-23 | 2020-06-23
PASADENA - X213 |  | 1 | 40000 | 814 | 2020-10-02 | 2020-10-08
PASADENA - X213 Total | 1926 | 5 | 298476 | 6414 | 2020-07-09 | 2020-10-08
Pasadena - X214 |  | 1 | 64619 | 1400 | 2020-07-21 | 2020-07-21
Pasadena - X214 |  | 1 | 64619 | 1400 | 2020-08-24 | 2020-08-24
Pasadena - X214 |  | 1 | 64619 | 1400 | 2020-09-17 | 2020-09-17
Pasadena - X214 |  | 1 | 64619 | 1400 | 2020-06-25 | 2020-06-25
Pasadena - X214 |  | 1 | 64619 | 1400 | 2020-10-08 | 2020-10-08
Pasadena - X214 |  | 1 | 64619 | 1400 | 2020-11-03 | 2020-11-03
Pasadena - X214 |  | 1 | 40000 | 814 | 2020-09-03 | 2020-09-10
Pasadena - X214 |  | 1 | 40000 | 814 | 2020-09-11 | 2020-09-17
Pasadena - X214 Total | 2987 | 8 | 467714 | 10028 | 2020-07-21 | 2020-09-17
Pasadena - X217 |  | 1 | 64619 | 1400 | 2020-10-13 | 2020-10-13
Pasadena - X217 |  | 1 | 64619 | 1400 | 2020-10-15 | 2020-10-15
Pasadena - X217 |  | 1 | 64619 | 1400 | 2020-10-20 | 2020-10-20
Pasadena - X217 |  | 1 | 64619 | 1400 | 2020-11-10 | 2020-11-10
Pasadena - X217 Total | 891 | 4 | 258476 | 5600 | 2020-10-13 | 2020-11-10
PASADENA - X219 |  | 1 | 64619 | 1400 | 2020-07-16 | 2020-07-16
PASADENA - X219 |  | 1 | 64619 | 1400 | 2020-06-23 | 2020-06-23
PASADENA - X219 |  | 1 | 64619 | 1400 | 2020-08-20 | 2020-08-20
PASADENA - X219 |  | 1 | 64619 | 1400 | 2020-09-01 | 2020-09-01
PASADENA - X219 Total | 2104 | 4 | 258476 | 5600 | 2020-07-16 | 2020-09-01
Pasadena - X220 |  | 1 | 64619 | 1400 | 2020-10-22 | 2020-10-22
Pasadena - X220 |  | 1 | 64619 | 1400 | 2020-11-05 | 2020-11-05
Pasadena - X220 Total | 2146 | 2 | 129238 | 2800 | 2020-10-22 | 2020-11-05
THIRTY SECOND STREET - X30 |  | 1 | 64619 | 1400 | 12-May-20* | 2020-05-18
THIRTY SECOND STREET - X30 Total | 3019 | 1 | 64619 | 1400 | 12-May-20* | 2020-05-18
BELLVIEW - A12 |  | 1 | 64619 | 1400 | 2020-07-09 | 2020-07-09
BELLVIEW - A12 Total | 579 | 1 | 64619 | 1400 | 2020-07-09 | 2020-07-09
ORANGE BLOSSOM - A392 |  | 1 | 64619 | 1400 | 07-Oct-19 A | 29-Jan-20 A
ORANGE BLOSSOM - A392 Total | 1668 | 1 | 64619 | 1400 | 07-Oct-19 A | 29-Jan-20 A
EAGLES NEST - A224 |  | 1 | 64619 | 1400 | 2020-04-14 | 2020-04-14
EAGLES NEST - A224 |  | 1 | 64619 | 1400 | 2020-05-12 | 2020-05-12
EAGLES NEST - A224 |  | 1 | 64619 | 1400 | 2020-04-16 | 2020-04-16
EAGLES NEST - A224 |  | 1 | 64619 | 1400 | 2020-05-07 | 2020-05-07
EAGLES NEST - A224 Total | 1589 | 4 | 258476 | 5600 | 2020-04-14 | 2020-05-07
LADY LAKE - A244 |  | 1 | 64619 | 1400 | 2020-04-21 | 2020-04-21
LADY LAKE - A244 |  | 1 | 64619 | 1400 | 2020-05-05 | 2020-05-05
LADY LAKE - A244 |  | 1 | 64619 | 1400 | 2020-05-14 | 2020-05-14
LADY LAKE - A244 |  | 1 | 64619 | 1400 | 2020-05-19 | 2020-05-19
LADY LAKE - A244 |  | 1 | 64619 | 1400 | 2020-05-21 | 2020-05-21
LADY LAKE - A244 Total | 2466 | 5 | 323095 | 7000 | 2020-04-21 | 2020-05-21
CURRY FORD - W0596 |  | 1 | 64619 | 1400 | 2020-10-20 | 2020-10-20
CURRY FORD - W0596 |  | 1 | 64619 | 1400 | 2020-11-05 | 2020-11-05
CURRY FORD - W0596 |  | 1 | 64619 | 1400 | 2020-11-10 | 2020-11-10
CURRY FORD - W0596 |  | 1 | 40000 | 814 | 2020-12-09 | 2020-12-15
CURRY FORD - W0596 |  | 1 | 64619 | 1400 | 2020-10-08 | 2020-10-08
CURRY FORD - W0596 Total | 1605 | 5 | 298476 | 6414 | 2020-10-08 | 2020-12-15
RIO PINAR - W0974 |  | 1 | 64619 | 1400 | 2020-10-13 | 2020-10-13
RIO PINAR - W0974 |  | 1 | 64619 | 1400 | 2020-10-15 | 2020-10-15
RIO PINAR - W0974 |  | 1 | 64619 | 1400 | 2020-10-22 | 2020-10-22
RIO PINAR - W0974 |  | 1 | 64619 | 1400 | 2020-11-03 | 2020-11-03
RIO PINAR - W0974 |  | 1 | 40000 | 814 | 2020-11-11 | 2020-11-17
RIO PINAR - W0974 |  | 1 | 40000 | 814 | 2020-11-18 | 2020-12-01
RIO PINAR - W0974 |  | 1 | 40000 | 814 | 2020-12-02 | 2020-12-08
RIO PINAR - W0974 Total | 2504 | 7 | 378476 | 8042 | 2020-10-13 | 2020-12-08
ARBUCKLE CREEK - K1361 |  | 1 | 64619 | 1400 | 2020-11-05 | 2020-11-05
ARBUCKLE CREEK - K1361 |  | 1 | 64619 | 1400 | 2020-11-17 | 2020-11-17
ARBUCKLE CREEK - K1361 Total | 1161 | 2 | 129238 | 2800 | 2020-11-05 | 2020-11-17
DESOTO CITY - K3220 |  | 1 | 64619 | 1400 | 2020-10-01 | 2020-10-01
DESOTO CITY - K3220 |  | 1 | 64619 | 1400 | 2020-10-08 | 2020-10-08
DESOTO CITY - K3220 |  | 1 | 64619 | 1400 | 2020-11-05 | 2020-11-05
DESOTO CITY - K3220 |  | 1 | 64619 | 1400 | 2020-11-10 | 2020-11-10
DESOTO CITY - K3220 |  | 1 | 64619 | 1400 | 2020-11-19 | 2020-11-19
DESOTO CITY - K3220 Total | 1370 | 5 | 323095 | 7000 | 2020-10-01 | 2020-11-19
DESOTO CITY - K3222 |  | 1 | 64619 | 1400 | 2020-10-06 | 2020-10-06
DESOTO CITY - K3222 Total | 482 | 1 | 64619 | 1400 | 2020-10-06 | 2020-10-06
SEBRING EAST - K541 |  | 1 | 64619 | 1400 | 2020-10-13 | 2020-10-13
SEBRING EAST - K541 |  | 1 | 64619 | 1400 | 2020-10-15 | 2020-10-15
SEBRING EAST - K541 |  | 1 | 64619 | 1400 | 2020-10-22 | 2020-10-22
SEBRING EAST - K541 |  | 1 | 64619 | 1400 | 2020-11-10 | 2020-11-10
SEBRING EAST - K541 |  | 1 | 64619 | 1400 | 2020-11-12 | 2020-11-12
SEBRING EAST - K541 Total | 589 | 5 | 323095 | 7000 | 2020-10-13 | 2020-11-12
SEBRING EAST - K542 |  | 1 | 64619 | 1400 | 2020-10-20 | 2020-10-20
SEBRING EAST - K542 |  | 1 | 64619 | 1400 | 2020-11-03 | 2020-11-03
SEBRING EAST - K542 |  | 1 | 64619 | 1400 | 2020-11-12 | 2020-11-12
SEBRING EAST - K542 Total | 104 | 3 | 193857 | 4200 | 2020-10-20 | 2020-11-12
BOGGY MARSH - K958 |  | 1 | 64619 | 1400 | 2020-09-15 | 2020-09-15
BOGGY MARSH - K958 |  | 1 | 64619 | 1400 | 2020-09-17 | 2020-09-17
BOGGY MARSH - K958 |  | 1 | 64619 | 1400 | 2020-10-01 | 2020-10-01
BOGGY MARSH - K958 |  | 1 | 40000 | 814 | 2020-10-13 | 2020-10-13
BOGGY MARSH - K958 |  | 1 | 40000 | 814 | 2020-10-15 | 2020-10-15
BOGGY MARSH - K958 |  | 1 | 40000 | 814 | 2020-10-20 | 2020-10-20
BOGGY MARSH - K958 Total | 2799 | 6 | 313857 | 6642 | 2020-09-15 | 2020-10-20
BOGGY MARSH - K961 |  | 1 | 64619 | 1400 | 2020-09-22 | 2020-09-22
BOGGY MARSH - K961 |  | 1 | 64619 | 1400 | 2020-10-06 | 2020-10-06
BOGGY MARSH - K961 |  | 1 | 64619 | 1400 | 2020-10-08 | 2020-10-08
BOGGY MARSH - K961 |  | 1 | 40000 | 814 | 2020-09-15 | 2020-10-06
BOGGY MARSH - K961 |  | 1 | 40000 | 814 | 2020-10-08 | 2020-10-22
BOGGY MARSH - K961 |  | 1 | 40000 | 814 | 2020-10-22 | 2020-10-22
BOGGY MARSH - K961 Total | 1994 | 6 | 313857 | 6642 | 2020-09-22 | 2020-10-22
UCF NORTH - W0994 |  | 1 | 64619 | 1400 | 2020-10-15 | 2020-10-15
UCF NORTH - W0994 |  | 1 | 64619 | 1400 | 2020-11-02 | 2020-11-02
UCF NORTH - W0994 |  | 1 | 64619 | 1400 | 2020-11-04 | 2020-11-04
UCF NORTH - W0994 Total | 1368 | 3 | 193857 | 4200 | 2020-10-15 | 2020-11-04
ALAFAYA - W0289 |  | 1 | 64619 | 1400 | 2020-10-22 | 2020-10-22
ALAFAYA - W0289 |  | 1 | 40000 | 814 | 2020-10-01 | 2020-10-01
ALAFAYA - W0289 |  | 1 | 40000 | 814 | 2020-10-08 | 2020-10-08
ALAFAYA - W0289 Total | 1898 | 3 | 144619 | 3028 | 2020-10-22 | 2020-10-08
ALAFAYA - W0298 |  | 1 | 55488 | 2379 | 2020-11-05 | 2020-11-05
ALAFAYA - W0298 |  | 1 | 40000 | 814 | 2020-11-11 | 2020-11-11
ALAFAYA - W0298 |  | 1 | 40000 | 814 | 2020-11-11 | 2020-11-11
ALAFAYA - W0298 |  | 1 | 40000 | 814 | 2020-11-18 | 2020-11-18
ALAFAYA - W0298 |  | 1 | 40000 | 814 | 2020-11-18 | 2020-11-18
ALAFAYA - W0298 |  | 1 | 40000 | 814 | 2020-12-02 | 2020-12-02
ALAFAYA - W0298 Total | 1667 | 6 | 255488 | 6449 | 2020-11-05 | 2020-12-02
Grand Total | 282629 | 580 | 34860275 | 750863

## Submersible UG-2020
Submersible UG - Project Level Costs
Project Name | Location | Customer Count | Unit Count | Project Cost - Capital | Project Cost - O&M | Start Date | Finish Date
Dixie Shore Subdivision, Crystal River | Tropic Terrace - A207 | 183 | 24 | 265000 | 0 | 2020-02-01 | 2020-03-31

## Poles Replacement - 2020
Pole Replacement - Project Level Costs
| Year | Location | Unit Count | Customer Count by Op Center | Project Cost - Capital | Project Cost - O&M | Start Date | Finish Date
REPLACEMENT (NON-INSP BASED) |  | Apopka | 5 | 105668 | 40677.95 | 2847.4565 | 2020-01-01 | 2020-05-31
|  | Deland | 15 | 85601 | 122033.85 | 8542.3695 | 2020-01-01 | 2020-12-31
|  | Jamestown | 14 | 138613 | 113898.26 | 7972.8782 | 2020-01-01 | 2020-12-31
|  | Longwood | 25 | 92030 | 203389.75 | 14237.2825 | 2020-01-01 | 2020-12-31
|  | Inverness | 85 | 79397 | 691525.15 | 48406.7605 | 2020-01-01 | 2020-12-31
|  | Monticello | 7 | 58417 | 56949.13 | 3986.4391 | 2020-01-01 | 2020-07-31
|  | Ocala | 40 | 80509 | 325423.6 | 22779.652 | 2020-01-01 | 2020-12-31
|  | Clearwater | 122 | 161275 | 992541.98 | 69477.9386 | 2020-01-01 | 2020-12-31
|  | Seven Springs | 74 | 187524 | 602033.66 | 42142.3562 | 2020-01-01 | 2020-12-31
|  | St Pete | 98 | 176058 | 797287.82 | 55810.1474 | 2020-01-01 | 2020-12-31
|  | Walsingham | 86 | 156443 | 699660.74 | 48976.2518 | 2020-01-01 | 2020-12-31
|  | Zephyrhills | 12 | 27764 | 97627.08 | 6833.8956 | 2020-01-01 | 2020-12-31
|  | Buena Vista | 11 | 135224 | 89491.49 | 6264.4043 | 2020-01-01 | 2020-11-30
|  | Clermont | 9 | 37129 | 73220.31 | 5125.4217 | 2020-01-01 | 2020-09-30
|  | Highlands | 19 | 57450 | 154576.21 | 10820.3347 | 2020-01-01 | 2020-12-31
|  | Lake Wales | 30 | 114912 | 244067.7 | 17084.739 | 2020-01-01 | 2020-12-31
|  | SE Orlando | 71 | 94574 | 577626.89 | 40433.8823 | 2020-01-01 | 2020-12-31
|  | Winter Garden | 44 | 85734 | 357965.96 | 25057.6172 | 2020-01-01 | 2020-12-31
REPLACEMENT (INSP BASED) |  | Apopka | 4 | 105668 | 33315.08 | 2332.0556 | 2020-01-01 | 2020-12-31
|  | Deland | 219 | 85601 | 1824000.63 | 127680.0441 | 2020-01-01 | 2020-12-31
|  | Jamestown | 161 | 138613 | 1340931.97 | 93865.2379 | 2020-01-01 | 2020-12-31
|  | Longwood | 105 | 92030 | 874520.85 | 61216.4595 | 2020-01-01 | 2020-12-31
|  | Inverness | 194 | 79397 | 1615781.38 | 113104.6966 | 2020-01-01 | 2020-12-31
|  | Monticello | 38 | 58417 | 316493.26 | 22154.5282 | 2020-01-01 | 2020-12-31
|  | Ocala | 98 | 80509 | 816219.46 | 57135.3622 | 2020-01-01 | 2020-12-31
|  | Clearwater | 104 | 161275 | 866192.08 | 60633.4456 | 2020-01-01 | 2020-12-31
|  | Seven Springs | 87 | 187524 | 724602.99 | 50722.2093 | 2020-01-01 | 2020-12-31
|  | St Pete | 384 | 176058 | 3198247.68 | 223877.3376 | 2020-01-01 | 2020-12-31
|  | Walsingham | 91 | 156443 | 757918.07 | 53054.2649 | 2020-01-01 | 2020-12-31
|  | Zephyrhills | 0 | 27764 | 0 | 0 | 2020-01-01 | 2020-12-31
|  | Buena Vista | 33 | 135224 | 274849.41 | 19239.4587 | 2020-01-01 | 2020-12-31
|  | Clermont | 11 | 37129 | 91616.47 | 6413.1529 | 2020-01-01 | 2020-12-31
|  | Highlands | 60 | 57450 | 499726.2 | 34980.834 | 2020-01-01 | 2020-12-31
|  | Lake Wales | 124 | 114912 | 1032767.48 | 72293.7236 | 2020-01-01 | 2020-12-31
|  | SE Orlando | 141 | 94574 | 1174356.57 | 82204.9599 | 2020-01-01 | 2020-12-31
|  | Winter Garden | 47 | 85734 | 391452.19 | 27401.6533 | 2020-01-01 | 2020-12-31
|  | Grand Total | 2668 |  | 22072989.3 | 1545109.251

## Pole Inspection - 2020
Pole Inspection - Project Level Costs
| Year | Location | Unit Count | Customer Count | Project Cost - Capital | Project Cost - O&M | Start Date | Finish Date
INSPECTIONS |  | Apopka |  | 105668
|  | Deland |  | 85601
|  | Jamestown | 29224 | 138613 |  | 1139736 | 2020-02-10 | 2020-12-31
|  | Longwood | 13100 | 92030 |  | 510900 | 2020-02-10 | 2020-12-31
|  | Inverness | 15116 | 79397 |  | 589524 | 2020-02-10 | 2020-12-31
|  | Monticello |  | 58417
|  | Ocala | 504 | 80509 |  | 19656 | 2020-02-10 | 2020-12-31
|  | Clearwater | 8062 | 161275 |  | 314418 | 2020-02-10 | 2020-12-31
|  | Seven Springs | 15116 | 187524 |  | 589524 | 2020-02-10 | 2020-12-31
|  | St Pete |  | 176058
|  | Walsingham |  | 156443
|  | Zephyrhills |  | 27764
|  | Buena Vista |  | 135224
|  | Clermont |  | 37129
|  | Highlands |  | 57450
|  | Lake Wales |  | 114912
|  | SE Orlando | 19650 | 94574 |  | 766350 | 2020-02-10 | 2020-12-31
|  | Winter Garden |  | 85734
Summarized
|  | Location | Unit Count |  | Customer Count | Capital Cost | O&M | Start Date | Finish Date
|  | Jamestown | 29224 |  | 138613 | 0 | 4000000 | 2020-02-10 | 2020-12-31
|  | Longwood | 13100 |  | 92030 |  |  | 2020-02-10 | 2020-12-31
|  | Inverness | 15116 |  | 79397 |  |  | 2020-02-10 | 2020-12-31
|  | Ocala | 504 |  | 80509 |  |  | 2020-02-10 | 2020-12-31
|  | Clearwater | 8062 |  | 161275 |  |  | 2020-02-10 | 2020-12-31
|  | Seven Springs | 15116 |  | 187524 |  |  | 2020-02-10 | 2020-12-31
|  | SE Orlando | 19650 |  | 94574 |  |  | 2020-02-10 | 2020-12-31
*Note - cost applies to entire inspection program
|  | Grand Total | 100772 |  | 833922 |  | 4000000