## New Columns
Utilities, Inc. of Florida
Docket No. 2020139
Test Year Ended December 31, 2019
PCF-47, Flynn Rebuttal Testimony as of October 1, 2020
Proforma Project Roster
CP# | Project Name | System | Exhibit# | W, S or Both | Project Start | PIS Date (Closed) | Projected PIS Date | Projected IDC | Projected Captime | Projected Cost | Projected Total | IDC to Date | Captime to Date | Cost to Date | Total to Date | # of Bids | Primary Contractor | Additional Contractors | Ret's? | Comment
2020098 | CL I&I Investigation | Cypress Lakes | 1 | S | 2020-05-01 | 2020-12-31 |  | 28.32 | 0 | 51000 | 51028.32 | 0 | 0 | 42500 | 42500 | 1 | Specialized Plumbing Tech. |  | N
2020129 | ER LS 3 & 8 Remediation | Eagle Ridge | 2 | S | 2020-06-15 | 2020-09-30 |  | 49.34 | 35 | 82191.61 | 82275.95 | 49.34 | 2219.52 | 77890.36 | 80159.22 | 3 | Innovative Contractors |  | Y
2019024 | ER/CC SCADA & RTUs | Eagle Ridge | 3 | S | 2019-03-01 | 2020-08-31 |  | 16966.2627 | 1591 | 210602.14 | 229159.4027 | 16966.2627 | 1801.16 | 210601.14 | 229368.5627 | 3 | Sanders Company | Bailey Engineering/Ellis Automated | N | 210534
2019125 | Eng ER Site Improvements | Eagle Ridge | 4 | S | 2018-10-01 | 2020-07-01 |  | 10485.25 | 1880 | 151118 | 163483.25 | 10485.25 | 2669.4 | 151129.27 | 164283.92 | 2 | Kimley-Horn & Assoc. |  | N | 26940
2019175 | ER Site Improvements | Eagle Ridge | 5 | S | 2019-11-29 | 2020-08-31 |  | 34562.93 | 10610.7 | 658624.13 | 703797.76 | 34562.93 | 11085.62 | 667174.13 | 712822.68 | 6 | Wholesale Vinyl Fence | Sunny Grove/C&C Tree Service/Davey Tree Service | Y | 499717.68 | $608,908 documented; need $20,175 documented
2020156 | LB WWTP Master Plan | Labrador | 6 | S | 2019-08-01 |  | 2021-01-31 | 0 | 0 | 44736.06 | 44736.06 | 0 | 0 | 44736.06 | 44736.06 | 1 | Kimley-Horn & Assoc. |  | N
2019078 | Longwood LS RTUs | Longwood | 7 | S | 2019-04-08 | 2020-01-31 |  | 3487.5871 | 135.54 | 122023.54 | 125646.6671 | 3487.5871 | 135.54 | 122023.54 | 125646.6671 | 1 | Sanders Company | Bailey Engineering | N
2020028 | Eng - Crescent Bay Raw WM | LUSI | 8 | W | 2020-02-03 |  | 2021-04-30 | 3741.7114 | 1500 | 70000 | 75241.7114 | 3203.6739 | 452.48 | 65000 | 68656.1539 | 1 | Kimley-Horn & Assoc. |  | N
2020152 | LUSI Crescent Bay Raw WM | LUSI | 9 | W | 2020-06-30 |  | 2021-04-30 | 9330.9184 | 7186.4 | 486514 | 503031.3184 | 0 | 1031.72 | 0 | 1031.72 | 3 | Tri-Sure Corp |  | N
2020029 | LG Sulfuric Acid Equipment Replace | LUSI | 10 | W | 2020-02-03 | 2020-04-01 |  | 5.92 | 787.34 | 54302.5 | 55095.76 | 414.551 | 787.34 | 54302.5 | 55504.391 | 1 | Odyssey Manufacturing |  | Y
None | LG Hydrochloric Acid Storage Tank | LUSI | 11 | W | 2020-02-22 | 2020-03-31 |  | 0 | 0 | 29991.6 | 29991.6 | 0 | 0 | 29991.6 | 29991.6 | 2 | Odyssey Manufacturing |  | N
None | LG RAS Pumps | LUSI | 12 | S | 2020-08-25 |  | 2020-12-31 | 0 | 0 | 42557.68 | 42557.68 | 0 | 0 | 32798 | 32798 | 1 | Danus Utilities | Xylem Pumps | Y
2020106 | Barrington WWTP Improvements | LUSI | 13 | S | 2020-05-25 |  | 2021-05-31 | 9121.6235 | 3824.4 | 380000 | 392946.0235 | 1921.1216 |  | 40900 | 42821.1216 | 2 | Danus Utilities | Kimley-Horn & Assoc. | N
2019145 | MC Master Lift Station | Mid-County | 14 | S | 2020-05-15 |  | 2021-06-30 | 73696.3296 | 38865.915 | 2103578 | 2216140.2446 | 19615.48 | 6199.76 | 256202.46 | 282017.7 | 3 | Kamminga & Roodvoets | Kimley-Horn & Assoc. | Y
2019154 | MC LS 4 & LS 7 Generators | Mid-County | 15 | S | 2019-10-14 |  | 2020-12-31 | 1581.6726 | 4422.07 | 130159 | 136162.7426 | 568.95 | 4436 | 119699 | 124703.95 | 6 | Paramount Power | Kimley-Horn & Assoc. | N
2020127 | MC Curlew Creek I&I Remediation | Mid-County | 16 | S | 2020-07-01 |  | 2021-01-31 | 7772.0402 | 11250 | 700027 | 719049.0402 | 2419.6808 | 1814.88 | 230671 | 234905.5608 | 4 | Insituform Technologies | TLC Diversified/Kimley-Horn/SPT/T-N-T/UGF | N
2020080 | MC Headworks | Mid-County | 17 | S | 2020-03-20 |  | 2021-11-30 | 104026.491 | 53875.25 | 2424782 | 2582683.741 | 3295.58 | 3644.2 | 151493.8 | 158433.58 | 2 | TLC Diversified | Kimley-Horn & Assoc. | N
2020128 | MC Eng LS 10 FM Relocation | Mid-County | 18 | S | 2020-07-01 |  | 2021-12-31 | 1281.3193 | 420 | 55750 | 57451.3193 | 858.64 | 105 | 31640 | 32603.64 | 1 | Kimley-Horn & Assoc. |  | Y
None | PB Diffuser Replacement | Pennbrooke | 19 | S | 2020-03-15 | 2020-04-01 |  | 0 | 0 | 34000 | 34000 | 0 | 0 | 34000 | 34000 | 2 | ECO-2000 | Evoqua | Y
2020091 | SH SCADA RTUs | Sandalhaven | 20 | S | 2020-06-01 |  | 2021-03-31 | 3456.2428 | 1950 | 130000 | 135406.2428 | 0 | 0 | 0 | 0 | 1 | Barney's Pumps |  | N
None | SH I&I Investigation | Sandalhaven | 21 | S | 2021-01-30 |  | 2021-04-30 | 861.7934 | 1755 | 56500 | 59116.7934 | 0 | 0 | 0 | 0 | 2 | Specialized Plumbing Tech. |  | N
2018109 | Eng-Wekiva WWTP Improvements | Sanlando | 22 | S | 2018-08-06 | 2020-10-01 |  | 36603.8332 | 4988.54 | 278820 | 320412.3732 | 36603.8332 | 4988.54 | 278820 | 320412.3732 | 2 | Kimley-Horn & Assoc. |  | Y | Eng services and construction costs booked to separate projects #'s.
2019109 | Wekiva WWTP improvements | Sanlando | 22 | S | 2019-07-08 |  | 2020-12-31 | 317136.1583 | 86172.395 | 6205827 | 6609135.5533 | 269830.89 | 55886.17 | 5028790 | 5354507.06 | 2 | Florida Env. Construction |  | Y | CO1, $101K; CO2 $88,065
2020182 | Sanlando Wekiva Headworks | Sanlando | 23 | S | 2020-02-01 |  | 2021-09-30 | 106864.6588 | 11250 | 2580912 | 2699026.6588 | 0 | 0 | 0 | 0 | 3 | Florida Env. Construction |  | N
2020031 | Sanlando Wekiva Headworks Eng | Sanlando | 23 | S | 2020-02-01 |  | 2021-09-30 | 18048.3087 | 4876.41 | 186715 | 209639.7187 | 8211.89 | 4876.41 | 175372.3 | 188460.6 | 1 | Kimley-Horn & Assoc. |  | Y
2020111 | Sanlando Well Panel Replace | Sanlando | 24 | W | 2020-05-29 |  | 2020-12-31 | 1724.64 | 2312 | 74500 | 78536.64 | 1724.64 | 2312 | 74500 | 78536.64 | 1 | North Lake Electric |  | Y
2018098 | SUC 16" FM & WM Replacement | Sanlando | 25 | W | 2018-08-01 |  | 2021-05-31 | 68815.2067 | 13381.336 | 1791990.0728 | 1874186.6156 | 14903.25 | 6173.7245 | 793706 | 814782.9745 | 3 | Tri-Sure Corp | Kimley-Horn & Assoc. | Y | Project includes both W&S assets | 48.54%
2018098 | SUC 16" FM & WM Replacement | Sanlando | 25 | S | 2018-08-01 |  | 2021-05-31 | 72940.302 | 14183.474 | 1899410.0772 | 1986533.8531 | 15511.5 | 6543.8055 | 826103 | 848158.3055 | 3 | Tri-Sure Corp | Kimley-Horn & Assoc. | Y | Project includes both W&S assets | 51.46%
2020113 | SUC Eng F5/C1/L2 FM Replace | Sanlando | 26 | S | 2020-04-30 |  | 2021-12-31 | 17058.8735 | 407.48 | 185500 | 202966.3535 | 1036 | 407.48 | 137640 | 139083.48 | 3 | Kimley-Horn & Assoc. |  | Y
2020107 | Sanlando I&I Remediation Ph. 4 | Sanlando | 27 | S | 2020-06-01 |  | 2021-03-31 | 74463.861 | 30000 | 2223560 | 2328023.861 | 14608.76 | 1954.6 | 1314817.3 | 1331380.66 | 6 | Atlantic Pipe Services |  | N
2020136 | EE Williamson Utility Relocates | Sanlando | 28 | W | 2020-06-30 |  | 2021-12-31 | 2962.1192 | 1665.0975 | 111006.5 | 115633.7167 | 0 | 109.75 | 0 | 109.75 | 3 | Central Florida Tapping | Kimley-Horn & Assoc. | Y | Project includes both W&S assets | 25%
2020136 | EE Williamson Utility Relocates | Sanlando | 28 | S | 2020-06-30 |  | 2021-12-31 | 8886.3577 | 4995.2925 | 333019.5 | 346901.1502 | 0 | 329.25 | 0 | 329.25 | 3 | Central Florida Tapping | Kimley-Horn & Assoc. | Y | Project includes both W&S assets | 75%
2020137 | Sanlando LS Mechanical Rehabs | Sanlando | 29 | S | 2020-07-06 |  | 2020-01-31 | 6380.9027 | 6856.04 | 530040 | 543276.9427 | 2920.4 | 6856.04 | 304209 | 313985.44 | 3 | Central Florida Lift Stations |  | Y
2019088 | SUC CIP Analysis & FM Modeling | Sanlando | 30 | W | 2019-05-24 | 2020-06-30 |  | 1118 | 1195 | 18113.7566 | 20426.7566 | 1118 | 1195 | 18113.7566 | 20426.7566 | 2 | Kimley-Horn & Assoc. |  | N | Project includes both W&S assets | 21.69%
2019088 | SUC CIP Analysis & FM Modeling | Sanlando | 30 | S | 2019-05-24 | 2020-06-30 |  | 4035 | 4271 | 65386.2434 | 73692.2434 | 4035 | 4271 | 65386.2434 | 73692.2434 | 2 | Kimley-Horn & Assoc. |  | N | Project includes both W&S assets | 78.31%
2020030 | Sanlando GST deficiencies | Sanlando | 31 | W | 2020-02-24 |  | 2021-03-31 | 8743.8691 | 4259.47 | 181000 | 194003.3391 | 4757.948 | 1342.45 | 77496 | 83596.398 | 2 | Precon Corp. |  | Y
2018116 | TV I&I Redzone Inspection | Tierra Verde | 32 | S | 2018-08-31 |  | 2020-12-31 | 4394.4634 | 13511.9 | 201654 | 219560.3634 | 5885.67 | 11428.3 | 173612.41 | 190926.38 | 3 | Redzone | Insituform/T-N-T | N | Need invoices of $17,522.20
2019087 | TV LS 4 FM & GSM Relocations | Tierra Verde | 33 | S | 2019-06-01 |  | 2021-02-28 | 33652.0667 | 8449.876 | 551266.55 | 593368.4927 | 21792.95 | 8256.5 | 499766.55 | 529816 | 1 | McKenzie Contracting | Left Coast Utilities/Ellis Automated/K-H & Assoc | Y
2019173 | TV LS 4 Replacement | Tierra Verde | 34 | S | 2019-11-30 |  | 2021-09-30 | 30052.4513 | 12526.6 | 828922 | 871501.0513 | 2007.81 | 310 | 99035.94 | 101353.75 | 2 | TLC Diversified | Kimley-Horn & Assoc. | Y
2020041 | BV W2 Pump & W3 Hydro tank | Orangewood | 35 | W | 2020-01-01 |  | 2020-11-30 | 2535.3468 | 474.92 | 77223 | 80233.2668 | 1950.67 | 474.92 | 72245.57 | 74671.16 | 2 | EESI |  | Y
2020004 | OW W1 tank and generator | Orangewood | 36 | W | 2019-11-01 | 2020-09-30 |  | 4444.41 | 2477 | 177750.62 | 184672.03 | 4444.41 | 2476.52 | 177750.62 | 184671.55 | 5 | Green Well Drilling | Paramount Power | Y
2019076 | UIF Seminole RTUs | UIF-Seminole Cty' | 37 | S | 2019-04-08 | 2020-01-31 |  | 2687.7179 | 100 | 93875.8 | 96663.5179 | 2687.7179 | 100 | 93875.8 | 96663.5179 | 1 | Sanders Company | Bailey Engineering | N
2019174 | ST Chlorine Dioxide Pilot Study | Summertree | 38 | W | 2020-01-31 |  | 2021-03-31 | 4624.9533 | 1411.44 | 92000 | 98036.3933 | 2002.3066 | 1411.44 | 75712.9 | 79126.6466 | 2 | Kimley-Horn & Assoc. |  | N
2020190 | Summertree I&I Investigation Pointe West | Summertree | 39 | S | 2020-07-01 |  | 2021-03-31 | 6247.5878 | 7500 | 364479.05 | 378226.6378 | 206.7949 | 0 | 202 | 408.7949 | 3 | Insituform Technologies | Specialized Plumbing Tech. | N
2020112 | Golden Hills GIP Replacement | Golden Hills | 40 | W | 2020-04-20 |  | 2020-11-30 | 451.3 | 4392.8 | 75160 | 80004.1 | 451.3 | 4392.8 | 75160 | 80004.1 | 1 | ECO-2000 |  | Y
2019146 | GH WM Relocation | Golden Hills | 41 | W | 2019-09-18 | 2020-01-31 |  | 3128.1689 | 12918.17 | 154763.73 | 170810.0689 | 3128.1689 | 12918.17 | 154763.73 | 170810.0689 | 1 | Traverse Group |  | Y
2019110 | Little Wekiva WTP generator | Little Wekiva | 42 | W | 2019-07-01 | 2020-06-30 |  | 2605.0379 | 2616.4 | 95397 | 100618.4379 | 2605.0379 | 2616.4 | 95397 | 100618.4379 | 3 | North Lake Electric |  | N
2019111 | Park Ridge WTP generator | Park Ridge | 43 | W | 2019-07-15 | 2020-06-30 |  | 2861 | 1490.94 | 99137 | 103488.94 | 2861 | 1490.94 | 99137 | 103488.94 | 3 | North Lake Electric |  | N
2020135 | Ravenna Park I&I Remediation | Ravenna Park | 44 | S | 2020-06-01 |  | 2020-12-31 | 12263.3517 | 11348 | 853310 | 876921.3516 | 5862.09 | 4857.12 | 774157.57 | 784876.78 | 7 | Traverse Group | Atlantic Pipe Services | N | CO req'd for additional work
2020103 | Northwestern Bridge utility relocation | Weathersfield | 45 | W | 2018-02-14 |  | 2021-08-30 | 5712.5371 | 1140 | 140201 | 147053.5371 | 322.89 | 487.44 | 6005.25 | 6815.58 | 1 | Traverse Group | Kimley-Horn & Assoc. | Y
| TOTAL | [6 empty] | 1141898.2356 | 411260.196 | 28489397.16 | 30042555.5916 | 529319.9746 | 184849.39 | 13854528.8 | 14568698.1646
[11 empty] | Total, closed projects as of 10/1/2020 | 123449.0887 | 48755.15 | 2372856.69 | 2545060.9287
[9 empty] | 1.369% |  |  |  | 1.916%