## 2016
Actual Report
Note:
2016 Florida CAPEX Budget Data is not available.

## 2017
[7 empty] | 24409110.77 | 23697795.56
|  |  | 6956015.1925 | 9108365.1925 | 5344365.1925 | 3000365.1925 | 2017 BUDGET | 2017 Actual
Capital Plan | Company | Project # | Q1-17 | Q2-17 | Q3-17 | Q4-17 | 2017 Total | 2017 Actual Total
Tierra Verde - Lift Station #4 Forcemain |  | 1 |  |  |  |  | 0 | 0
Tierra Verde - Captime | Tierra Verde | Captime | 475 | 475 | 475 | 475 | 1900 | 3377.17
Tierra Verde - G/L Spending | Tierra Verde | G/L Spending | 7500 | 7500 | 7500 | 7500 | 30000 | 24961.71
Tierra Verde - IDC | Tierra Verde | IDC | 0 | 0 | 0 | 0 | 0 | 0
Lake Placid - Captime | Lake Placid | Captime | 237.5 | 237.5 | 237.5 | 237.5 | 950 | 2926.82
Lake Placid - G/L Spending | Lake Placid | G/L Spending | 2500 | 2500 | 2500 | 2500 | 10000 | 74823.54
Longwood - Longwood I/I Repairs | Longwood | 2017026 | 100000 | 300000 | 0 | 0 | 400000 | 141727.93
Longwood - Church Avenue FM Relocations | Longwood | 2016088 |  |  |  |  | 0 | 58433.15
Longwood - Captime | Longwood | Captime | 1770.6442 | 1770.6442 | 1770.6442 | 1770.6442 | 7082.5767 | 1504.21
Longwood - G/L Spending | Longwood | G/L Spending | 14000 | 14000 | 14000 | 14000 | 56000 | -31913.3
Longwood - IDC | Longwood | IDC |  |  |  |  | 0 | 12560.61
Cypress Lakes - Replace Hydro Tank #1 | Cypress Lakes | 1 |  |  |  |  | 0 | 0
Cypress Lakes - Smoke Testing/I&I Investigation |  | 1 |  |  |  |  | 0 | 0
Cypress Lakes - Filter Replacement |  | 1 |  |  |  |  | 0 | 0
Cypress Lakes - Disinfection Upgrade |  | 1 |  |  |  |  | 0 | 0
Cypress Lakes - Captime | Cypress Lakes | Captime | 2500 | 2500 | 2500 | 2500 | 10000 | 10496.65
Cypress Lakes - G/L Spending | Cypress Lakes | G/L Spending | 15000 | 15000 | 15000 | 15000 | 60000 | 168567.67
Eagle Ridge - EQ Tank & Field Office | Eagle Ridge | 2017025 | 450000 | 0 | 0 | 0 | 450000 | 470812.7
Eagle Ridge - Replace Reject Pond Liner |  | 1 |  |  |  |  | 0 | 0
Eagle Ridge - Captime | Eagle Ridge | Captime | 3500 | 3500 | 3500 | 3500 | 14000 | 37169.82
Eagle Ridge - G/L Spending | Eagle Ridge | G/L Spending | 25000 | 25000 | 25000 | 25000 | 100000 | 17595.15
Eagle Ridge - IDC | Eagle Ridge | IDC |  |  |  |  | 0 | 18033.54
Mid-County - I&I Remediation | Mid-County | 2017051 | 50000 | 500000 | 0 | 0 | 550000 | 107277.95
Mid-County - South Plant - Blower Replacement | Mid-County | 1 | 0 | 0 | 0 | 0 | 0 | 0
Mid-County - Collection System Evaluation | Mid-County | 2015134 | 0 | 0 | 0 | 0 | 0 | 2037.92
Mid-County - US 19 Utility Relocations | Mid-County | 2016032 | 0 | 0 | 0 | 0 | 0 | 6978.1
Mid-County - Replace Generator & Upgrade Electrical | Mid-County | 2016085 | 400000 | 400000 | 0 | 0 | 800000 | 1095811.84
Mid-County - Methanol Pumps and Instrumentation | Mid-County | 2016089 |  |  |  |  | 0 | 6341
Mid-County - Captime | Mid-County | Captime | 4908.2208 | 4908.2208 | 4908.2208 | 4908.2208 | 19632.8833 | 5274.3
Mid-County - G/L Spending | Mid-County | G/L Spending | 25000 | 25000 | 25000 | 25000 | 100000 | 204479.44
Mid-County - IDC | Mid-County | IDC |  |  |  |  | 0 | 51151.96
LUSI - Eng - 2nd Lower Floridan Well | LUSI | 1 | 0 | 0 | 0 | 0 | 0 | 0
LUSI - Feasibility Study & Land Purchase for NE WTP | LUSI | 1 | 0 | 0 | 0 | 0 | 0 | 0
LUSI - LUSI South TTHM HAA5 Remediation - Co | LUSI | 1 |  |  |  | 500000 | 500000 | 0
LUSI - Eng - 561 WTP Wellsite & Land |  | 1 |  |  |  |  | 0 | 0
LUSI - 561 WTP Well Construction |  | 1 |  |  |  |  | 0 | 0
LUSI - Barrington WWTP Cap Improvements |  | 1 |  |  |  |  | 0 | 0
LUSI - Master Plan |  | 1 |  |  |  |  | 0 | 0
LUSI - Eng - LG WTP Improvement | LUSI | 2016133 | 200000 | 200000 |  |  | 400000 | 429123.07
LUSI - NE Regional WTP & Lower Floridan Well | LUSI | 1 | 0 | 0 | 0 | 0 | 0 | 0
LUSI - Wellness Way off-site SFM & WM-Constr | LUSI | 1 |  |  |  |  | 0 | 0
LUSI - Wellness Way off-site SFM & WM-Engin | LUSI | 1 |  |  | 0 | 0 | 0 | 0
LUSI - Construction/Installation-LUSI SCADA System | LUSI | 2014072 | 0 | 0 | 0 | 0 | 0 | 0
LUSI - LG-Solar Organite | LUSI | 2015018 |  |  |  |  | 0 | 11267.71
LUSI - Eng - US 27 Main relocations - Phase 3 | LUSI | 2015083 | 0 | 0 | 0 | 0 | 0 | 0
LUSI - Lake Groves WWTP Splitter Box Replacement | LUSI | 2015155 |  |  |  |  | 0 | 0
LUSI - LUSI TTHM HAA5 Study | LUSI | 2015175 |  |  |  |  | 0 | 0
LUSI - Const-US 27 Main relocations - Phase 3 | LUSI | 2016009 | 30000 | 33000 | 0 | 0 | 63000 | 762.57
LUSI - Oswalt Road WM Relocations | LUSI | 2016103 |  |  |  |  | 0 | 658.72
LUSI - Captime | LUSI | Captime | 40000 | 40000 | 40000 | 40000 | 160000 | 159932.99
LUSI - G/L Spending | LUSI | G/L Spending | 150000 | 150000 | 150000 | 150000 | 600000 | 789274.94
LUSI - IDC | LUSI | IDC |  |  |  |  | 0 | 166049.9
UIF - Lake Tarpon AC & galv. WM - Phase 1 | UIF | 1 |  |  |  |  | 0 | 0
UIF - Summertree Well Abandonment | UIF | 2017006 | 200000 |  |  |  | 200000 | 173659
UIF - Timing Adjustments | UIF | 1 | -750000 | -750000 | -750000 | -750000 | -3000000 | 0
UIF - Timing Adjustments |  | 1 |  |  |  |  | 0 | 0
UIF - AMP Implementation | UIF | 1 |  |  |  |  | 0 | 0
UIF - Eng-Crystal Lake / Ravenna Park Interconnect | UIF | 2014071 | 0 | 0 | 0 | 0 | 0 | 0
UIF - Crystal Lake / Ravenna Park Interconnect | UIF | 2015080 | 0 | 0 | 0 | 0 | 0 | 0
UIF - Eng-UIF Jansen/Little Wekiva/Elec Imp & RTUs | UIF | 2015081 |  |  |  |  | 0 | 2960
UIF - UIF WM Replacements Eng | UIF | 2015082 |  |  |  |  | 0 | 0
UIF - GIS/Mapping - Conversion/Implementation | UIF | 2016025 | 60000 |  |  |  | 60000 | 100011.39
UIF - Const- UIF Elec Imp & RTUs | UIF | 2016068 | 39000 | 0 | 0 | 0 | 39000 | 68749.85
UIF - Lake Tarpon AC WM Replacement - Phase 3 | UIF | 2016091 | 250000 |  |  |  | 250000 | 1168231.19
UIF - Bear Lake Galv. & AC Main Replacement | UIF | 2016093 | 100000 | 600000 | 796000 | 0 | 1496000 | 598201.08
UIF - Crescent Hgts Galv. & AC Main Replacement | UIF | 2016094 | 500000 | 700000 | 506000 | 0 | 1706000 | 465773.64
UIF - Crystal Lake- AC Water Main Replacement - Phase 3 | UIF | 2016095 |  | 400000 | 1000000 | 186000 | 1586000 | 459565.41
UIF - Little Wekiva AC Main Replacement | UIF | 2016096 | 200000 |  | 0 | 0 | 200000 | 283809.94
UIF - Oakland Shores Galv. WM and Valve Replacement | UIF | 2016097 | 700000 | 772000 | 0 | 0 | 1472000 | 1033109.69
UIF - Phillips- AC Water Main Replacement | UIF | 2016098 | 0 | 200000 | 600000 | 389000 | 1189000 | 42.09
UIF - Ravenna Park Galv. & AC Main Replacement | UIF | 2016099 | 1000000 | 661000 | 0 | 0 | 1661000 | 1739289.23
UIF - OW/Buena Vista- AC WM Replacement | UIF | 2016102 | 615650 | 600000 | 0 | 0 | 1215650 | 1663865.95
UIF - Weathersfield Northwestern FM Relocation | UIF | 2017004 |  |  |  |  | 0 | 677223.2
UIF - Jansen WTP Gen Replacement |  | 2017168 |  |  |  |  | 0 | 63.14
UIF - Jansen AC Main Replacement |  | 1 |  |  |  |  | 0 | 0
UIF - Trailwoods Meter Relocations |  | 1 |  |  |  |  | 0 | 0
UIF - Weathersfield AC Main Replacement Ph 1 |  | 1 |  |  |  |  | 0 | 0
UIF - Weathersfield AC Main Replacement Ph 2 |  | 1 |  |  |  |  | 0 | 0
UIF - ST - Smoke Testing/I&I Investigation |  | 1 |  |  |  |  | 0 | 0
UIF - Captime | UIF | Captime | 24884.495 | 24884.495 | 24884.495 | 24884.495 | 99537.98 | 111521.72
UIF - G/L Spending | UIF | G/L Spending | 75000 | 75000 | 75000 | 75000 | 300000 | 457050.55
UIF - IDC | UIF | IDC |  |  |  |  | 0 | 513217.75
ACME - Captime | ACME | Captime | 1859.35 | 1859.35 | 1859.35 | 1859.35 | 7437.4 | 1798.74
ACME - G/L Spending | ACME | G/L Spending | 7500 | 7500 | 7500 | 7500 | 30000 | 39548.59
Sanlando - Const. Shadow Hills Diversion to Wekiva | Sanlando | 2017011 | 902000 | 2466000 | 2466000 | 1949000 | 7783000 | 5418513.48
Sanlando - Eng Const Well 2A & LS A-1 Gen | Sanlando | 2015084 |  | 0 | 0 | 0 | 0 | 1082.09
Sanlando - Eng Shadow Hills Diversion to Wekiva | Sanlando | 2016056 |  | 0 |  |  | 0 | 42550.07
Sanlando - Myrtle Lake Hills Main Extension - (with CIAC) | Sanlando | 2016057 |  |  |  |  | 0 | 1000
Sanlando - Wekiva WWTP Rehab | Sanlando | 2016058 | 600000 | 550000 | 0 | 0 | 1150000 | 1270196.63
Sanlando - Const DP W2A & LS A-1 Genset | Sanlando | 2016067 | 258000 |  |  |  | 258000 | 230072.63
Sanlando - Correct I&I deficiencies Sanlando - Phase 2 | Sanlando | 2016074 |  | 0 |  |  | 0 | 167257.17
Sanlando - Autumn Drive WM Replacement | Sanlando | 2016087 | 0 | 0 | 0 | 0 | 0 | 33925.85
Sanlando - Lift Station RTU Installations | Sanlando | 2017001 |  |  |  |  | 0 | 447388.49
Sanlando - Wekiva-Blower Replacement | Sanlando | 1 | 0 | 600000 | 0 | 0 | 600000 | 0
Sanlando - I&I Corrections Ph 3 |  | 1 |  |  |  |  | 0 | 0
Sanlando - Forcemain Replacement Ph 1 |  | 1 |  |  |  |  | 0 | 0
Sanlando - Powerline FM Replacement |  | 1 |  |  |  |  | 0 | 0
Sanlando - Springs WM Replacement |  | 1 |  |  |  |  | 0 | 0
Sanlando - Captime | Sanlando | Captime | 40084.4983 | 40084.4983 | 40084.4983 | 40084.4983 | 160337.9933 | 187528.26
Sanlando - G/L Spending | Sanlando | G/L Spending | 150000 | 150000 | 150000 | 150000 | 600000 | 799850.93
Sanlando - IDC | Sanlando | IDC |  |  |  |  | 0 | 297582.64
Sandalhaven - EWD Bulk Sewer Capacity Payment | Sandalhaven | 1 | 0 | 0 | 0 | 0 | 0 | 0
Sandalhaven - Smoke Testing/I&I Investigation |  | 1 |  |  |  |  | 0 | 0
Sandalhaven - Constr. CR 775 Widening Relocation Project - Ph 2 | Sandalhaven | 2017010 | 125000 | 50000 | 0 | 0 | 175000 | 326291.52
Sandalhaven - Eng CR 775 Widening Relocation Project - Phase 1 | Sandalhaven | 2011047 | 0 | 0 | 0 | 0 | 0 | 546
Sandalhaven - Captime | Sandalhaven | Captime | 1900 | 1900 | 1900 | 1900 | 7600 | 1515.24
Sandalhaven - G/L Spending | Sandalhaven | G/L Spending | 9000 | 9000 | 9000 | 9000 | 36000 | 29793.48
Sandalhaven - IDC | Sandalhaven | IDC |  |  |  |  | 0 | 12816.67
Labrador - Sediment Removal | Labrador | 2016076 |  |  |  |  | 0 | 0
Labrador - Captime | Labrador | Captime | 4500 | 4500 | 4500 | 4500 | 18000 | 14938.6
Labrador - G/L Spending | Labrador | G/L Spending | 7500 | 7500 | 7500 | 7500 | 30000 | 65914.36
Labrador - IDC | Labrador | IDC |  |  |  |  | 0 | 0
Pennbrooke - Pennbrooke WTP Electrical Upgrades | Pennebrooke | 2017005 | 200000 | 100000 | 0 | 0 | 300000 | 263417.3
Pennbrooke - WTP Upgrade |  | 1 |  |  |  |  | 0 | 0
Pennbrooke - Captime | Pennebrooke | Captime | 6745.4842 | 6745.4842 | 6745.4842 | 6745.4842 | 26981.9367 | 15115.17
Pennbrooke - G/L Spending | Pennebrooke | G/L Spending | 15000 | 15000 | 15000 | 15000 | 60000 | 78747.41
Pennbrooke - IDC | Pennebrooke | IDC |  |  |  |  | 0 | 6867.45
FL Cost Center - Captime | Cost Center | Captime | 0 | 0 | 0 | 0 | 0 | 378.81
FL Cost Center - G/L Spending | Cost Center | G/L Spending | 2500 | 2500 | 2500 | 2500 | 10000 | 60250.48
FL Cost Center - Valve Exerciser Machine |  | 1 |  |  |  |  | 0 | 0
FL Cost Center - Fleet Replacements | Cost Center | Transportation | 87500 | 87500 | 87500 | 87500 | 350000 | 303062.9
FL Cost Center - Transportation (UIF) - C4500 Kodiak Service Truck Upgrades | Cost Center | Transportation2 |  |  |  |  | 0 | 16000

## 2018
[5 empty] | 3304121.9717 | 1993456.9717 | 4043456.9717 | 4304456.9717 | 13675392.8867 | 2072359.66 | 2695294.63 | 2161333.25 | 2039414.42 | 1816860.44 | 1289464.57 | 1289835.35 | 1034164.69 | 1301142.34 | 1488189.48 | 581971.56 | 709189.59 | 18479219.98
[9 empty] | 2018 BUDGET | Actual | Actual | Actual | Actual | Actual | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Forecast | 2018 Actual
Capital Plan | Company | Project # | Status | Column1 | Q1-17 | Q2-17 | Q3-17 | Q4-17 | 2018 Total | January | February | March | April | May | June | July | Aug | Sep | Oct | Nov | Dec | 2018 Actual Total
Tierra Verde - Lift Station #4 Forcemain | Tierra Verde | 1 | 2018 |  |  |  |  | 250000 | 250000 | [12 empty] | 0
Tierra Verde - Redzone I&I Investigation |  | 2018116 | 2018/2019 | [5 empty] | 0 | Dec: 200 | 200
Tierra Verde - Captime | Tierra Verde | Captime |  |  | 475 | 475 | 475 | 475 | 1900 | 462.99 | 42.09 | 505.08 |  | 173.12 | 281.32 |  | 2683.36 |  | 0 | 529.84 |  | 4677.8
Tierra Verde - G/L Spending | Tierra Verde | G/L Spending |  |  | 7500 | 7500 | 7500 | 7500 | 30000 | January: 2525.21; February: 7262.92; March: 10903.82; June: 1667.73; Nov: 5848.71; Dec: 22342.32 | 50550.71
Tierra Verde - IDC | Tierra Verde | IDC |  |  | 0 | 0 | 0 | 0 | 0 | Dec: 1.51 | 1.51
Lake Placid - Captime | Lake Placid | Captime |  |  | 237.5 | 237.5 | 237.5 | 237.5 | 950 | January: 168.36 | 168.36
Lake Placid - G/L Spending | Lake Placid | G/L Spending |  |  | 2500 | 2500 | 2500 | 2500 | 10000 | January: 4920.06; June: 1243.56; July: 6080.97; Sep: 1050.75; Dec: 509.52 | 13804.86
Longwood - Longwood I/I Repairs | Longwood | Closed | Closed |  | 0 | 0 | 0 | 0 | 0 | January: 84.18; February: 183573.72; Dec: 0.1 | 183658
Longwood - Church Avenue FM Relocations | Longwood | 2016088 | Closed | [5 empty] | 0 | January: 12725.16; February: 13687.78; March: 2050.86; May: 14926.43; Dec: -0.43 | 43389.8
Longwood - L/S RTUs |  | 1 | 2019 | [5 empty] | 0 | [12 empty] | 0
Longwood - Shadow Hills WWTF Demolition |  | 2019002 | 2019 | [5 empty] | 0 | Dec: 55386.79 | 55386.79
Longwood - Captime | Longwood | Captime |  |  | 1770.6442 | 1770.6442 | 1770.6442 | 1770.6442 | 7082.5767 | 147.32 |  |  | 84.18 | 389.52 | 86.56 | 43.28 | 173.12 |  | 151 | 151.48 | 100 | 1326.46
Longwood - G/L Spending | Longwood | G/L Spending |  |  | 6000 | 6000 | 6000 | 6000 | 24000 | 7420.45 | 356 | 11095.34 | 7042.65 | 33878.38 | 3044.4 | 20604.6 | 31.02 | 16272.02 | 7634.45 |  | -37913.59 | 69465.72
Longwood - IDC | Longwood | IDC | [6 empty] | 0 | January: 1067.13; May: 2343.55; Dec: 287.73 | 3698.41
Cypress Lakes - Replace Hydro Tank #1 | Cypress Lakes | 1 | Closed | [5 empty] | 0 | Dec: 0 | 0
Cypress Lakes - Smoke Testing/I&I Investigation | Cypress Lakes | 1 | 2019 |  |  |  |  | 50000 | 50000 | [12 empty] | 0
Cypress Lakes - Filter Replacement | Cypress Lakes | 1 | 2019 |  |  |  |  | 50000 | 50000 | [12 empty] | 0
Cypress Lakes - Rehab L/S 1 |  | 1 | 2019 | [5 empty] | 0 | [12 empty] | 0
Cypress Lakes - Disinfection Upgrade | Cypress Lakes | 1 | 2019 | [5 empty] | 0 | [12 empty] | 0
Cypress Lakes - Captime | Cypress Lakes | Captime |  |  | 2500 | 2500 | 2500 | 2500 | 10000 | 147.32 | 1662.57 | 1420.57 | 894.43 | 913.45 | 476.08 | 670.84 | 476.08 | 887.24 | 551.82 | 378.7 | 692.48 | 9171.58
Cypress Lakes - G/L Spending | Cypress Lakes | G/L Spending |  |  | 15000 | 15000 | 15000 | 15000 | 60000 | 2446.3 | 1072.65 | 16947.6 | 14474.79 | 17335.69 | 3497.73 | 4012.71 | 2497.84 | 828.55 | 14235.86 | 6708.33 | 12640.47 | 96698.52
Eagle Ridge - EQ Tank & Field Office | Eagle Ridge | 2017025 | Closed |  | 0 | 0 | 0 | 0 | 0 | 4596.31 | 211415.38 | 3349.41 | 274700.4 | 9583 | 7298.29 | 39334.38 | 3565.25 | 446.24 | 9176.74 |  | 0 | 563465.4
Eagle Ridge - Lift Station RTU Improvements |  | 1 | 2018/2019 | [5 empty] | 0 | [12 empty] | 0 | bar: Nov
Eagle Ridge - Plant Site Improvements |  | 1 | 2018 | [5 empty] | 0 | [12 empty] | 0
Eagle Ridge - Replace Reject Pond Liner | Eagle Ridge | 1 | 2019 |  |  |  |  | 200000 | 200000 | [12 empty] | 0
Eagle Ridge - I&I Investigation |  | 1 | 2019 | [5 empty] | 0 | [12 empty] | 0
Eagle Ridge - CC LS Modification |  | 2018105 | [6 empty] | 0 | Aug: 546.24; Sep: 203913.72; Oct: 874.23; Nov: 200 | 205534.19
Eagle Ridge - Captime | Eagle Ridge | Captime |  |  | 3500 | 3500 | 3500 | 3500 | 14000 | 4315.03 | 3830.19 | 1725.69 | 1767.78 | 2500.72 | 3029.6 | 4874.24 | 5020.48 | 5150.32 | 3029.6 | 2683.36 | 3775.84 | 41702.85
Eagle Ridge - G/L Spending | Eagle Ridge | G/L Spending |  |  | 25000 | 25000 | 25000 | 25000 | 100000 | 9388.66 | 15233.09 | 19924.61 | 28557.33 | 27847.43 | 15430.94 | 81623.92 | 18327.3 | 9720.3 | 14392.47 | 38762.28 | 35219.65 | 314427.98
Eagle Ridge - IDC | Eagle Ridge | IDC | [6 empty] | 0 | 3582.52 | 5173.42 | 5195.99 | 7265.75 | 7337.86 | 7392.78 | 7688.77 | 7719.71 | 9257.52 | 1545.14 | 1546.64 |  | 63706.1
Mid-County - I&I Remediation | Mid-County | 2017051 | Closed |  | 0 | 0 | 0 | 0 | 0 | January: 1136.43; Dec: 0 | 1136.43
Mid-County - South Plant - Blower Replacement | Mid-County | 1 | 2019 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
Mid-County - I&I Improvements |  | 1 | 2018 | [5 empty] | 0 | [12 empty] | 0
Mid-County - Spanish Acres I&I |  | 1 | 2018 | [5 empty] | 0 | [12 empty] | 0
Mid-County - Collection System Evaluation | Mid-County | 2015134 | Closed |  | 0 | 0 | 0 | 0 | 0 | Dec: 0 | 0
Mid-County - US 19 Utility Relocations | Mid-County | 2016032 | Closed |  | 0 | 0 | 0 | 0 | 0 | Dec: 0 | 0
Mid-County - Replace Generator & Upgrade Electrical | Mid-County | 2016085 | Closed |  | 0 | 0 | 0 | 0 | 0 | 1692.42 | 118968.09 | 719.95 | 1346.88 | 59913.01 |  | 605.92 | 33.21 |  |  |  | 0 | 183279.48
Mid-County - Methanol Pumps and Instrumentation | Mid-County | 2016089 | Closed | [5 empty] | 0 | Dec: 0 | 0
Mid-County - Captime | Mid-County | Captime |  |  | 5000 | 5000 | 5000 | 5000 | 20000 | 2693.77 | 589.26 | 8288.34 | 7015.11 | 5959.56 | 5680.5 | 8003.5 | 5107.04 | 2934.84 | 2466.96 | 2991.56 | 2604.32 | 54334.76
Mid-County - G/L Spending | Mid-County | G/L Spending |  |  | 25000 | 25000 | 25000 | 25000 | 100000 | 69160 | 15929 | 17741.41 | 49070.64 | 44148.38 | 74307.76 | 38835.77 | 18137.21 | 17887.64 | 19401.82 | 13125.25 | 57673.57 | 435418.45
Mid-County - IDC | Mid-County | IDC | [6 empty] | 0 | January: 8389.09; February: 9284.32; March: 9289.74; July: 9757.89; Aug: 9758.14 | 46479.18
LUSI - Eng - 2nd Lower Floridan Well | LUSI | 1 | 2019 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
LUSI - Feasibility Study & Land Purchase for NE WTP | LUSI | 1 | 2019 |  | 25000 | 25000 | 25000 | 25000 | 100000 | [12 empty] | 0
LUSI - LUSI North TTHM HAA5 Remediation |  | 1 | 2019 | [5 empty] | 0 | [12 empty] | 0
LUSI - LG WTP Improvements Construction | LUSI | 2018153 | 2018/2019 |  | 0 | 0 | 1000000 | 1000000 | 2000000 | Nov: 102029.84; Dec: 87792.08 | 189821.92
LUSI - Eng - 561 WTP Wellsite & Land | LUSI | 1 | 2019 |  |  |  |  | 100000 | 100000 | [12 empty] | 0
LUSI - 561 WTP Well Construction | LUSI | 1 | 2020 | [5 empty] | 0 | [12 empty] | 0
LUSI - PLC Replacements |  | 2018097 | 2018 | [5 empty] | 0 | Aug: 143.28; Nov: 43.28 | 186.56
LUSI - Barrington WWTP Cap Improvements | LUSI | 1 | 2019 |  |  | 150000 | 150000 |  | 300000 | [12 empty] | 0
LUSI - Master Plan | LUSI | 2018072 | 2018 |  |  |  |  | 100000 | 100000 |  |  |  | 249.14 | 20000 | 13250.2 | 17000 | 10000 | 10100 | 10108.2 | 10810.92 | 10000 | 101518.46
LUSI - Sewer Jetter Trailer |  | 1 | 2019 | [5 empty] | 0 | [12 empty] | 0
LUSI - LUS RTU Modem 4G Upgrade |  | 2018118 | 2018 | [5 empty] | 0 | Aug: 201.51; Oct: 735.76; Nov: 57794.72 | 58731.99
LUSI - Eng - LG WTP Improvement | LUSI | 2016133 | Closed | [5 empty] | 0 | 42534 | 7895.54 | 378.81 | 17289.72 | 8314.8 | 4591.68 | 7408.88 | 11000 | 86.56 |  |  | 0 | 99499.99
LUSI - LG Centrifuge |  | 1 | 2019 | [5 empty] | 0 | [12 empty] | 0
LUSI - NE Regional WTP & Lower Floridan Well | LUSI | 1 | NA |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
LUSI - Wellness Way off-site SFM & WM-Constr | LUSI | 1 | NA | [5 empty] | 0 | [12 empty] | 0
LUSI - Wellness Way off-site SFM & WM-Engin | LUSI | 1 | NA |  |  |  | 0 | 0 | 0 | [12 empty] | 0
LUSI - Construction/Installation-LUSI SCADA System | LUSI | 2014072 | Closed |  | 0 | 0 | 0 | 0 | 0 | Dec: 0 | 0
LUSI - LG-Solar Organite | LUSI | 2015018 | Closed | [5 empty] | 0 | Dec: 0 | 0
LUSI - Eng - US 27 Main relocations - Phase 3 | LUSI | 2015083 | Closed |  | 0 | 0 | 0 | 0 | 0 | Dec: 0 | 0
LUSI - Lake Groves WWTP Splitter Box Replacement | LUSI | 2015155 | Closed | [5 empty] | 0 | Dec: 0 | 0
LUSI - LUSI TTHM HAA5 Study | LUSI | 2015175 | Closed | [5 empty] | 0 | Dec: 0 | 0
LUSI - Const-US 27 Main relocations - Phase 3 | LUSI | 2016009 | Closed |  | 0 | 0 | 0 | 0 | 0 | Sep: 62550; Dec: 0 | 62550
LUSI - Oswalt Road WM Relocations | LUSI | 2016103 | Closed | [5 empty] | 0 | Dec: 0 | 0
LUSI - Captime | LUSI | Captime |  |  | 40000 | 40000 | 40000 | 40000 | 160000 | 25978.24 | 19330.12 | 16264.39 | 16958.73 | 18016.83 | 13470.22 | 16816.56 | 19135 | 16308.36 | 13222.04 | 14433.88 | 13286.96 | 203221.33
LUSI - G/L Spending | LUSI | G/L Spending |  |  | 150000 | 150000 | 150000 | 150000 | 600000 | 76570.76 | 57305.84 | 52906.34 | 86213.14 | 143756.51 | 42581.82 | 23346.33 | 73819.47 | 91765.98 | 61578.44 | -28867.87 | 23193.1 | 704169.86
LUSI - IDC | LUSI | IDC | [6 empty] | 0 | 3553.01 | 3612.42 | 3615.27 | 3747.25 | 3960.32 | 3842.5 | 4276.37 | 4435.48 | 4513.65 | 606.52 | 1455.96 | 810.58 | 38429.33
UIF - Lake Tarpon AC & galv. WM - Phase 1 | UIF | 1 | Closed | [5 empty] | 0 | Dec: 0 | 0
UIF - Summertree Well Abandonment | UIF | 2017006 | Closed | [5 empty] | 0 | Dec: 0 | 0
UIF - Timing Adjustments | UIF | 1 |  |  | 1211665 | 750000 | 750000 | 261000 | 2972665 | [12 empty] | 0
UIF - Timing Adjustments | UIF | 1 |  |  | -750000 | -750000 | -750000 | -750000 | -3000000 | [12 empty] | 0
UIF - AMP Implementation | UIF | 1 | 2019 | [5 empty] | 0 | [12 empty] | 0
UIF - Eng-Crystal Lake / Ravenna Park Interconnect | UIF | 2014071 | Closed |  | 0 | 0 | 0 | 0 | 0 | Dec: 0 | 0
UIF - Crystal Lake / Ravenna Park Interconnect | UIF | 2015080 | Closed |  | 0 | 0 | 0 | 0 | 0 | Dec: 0 | 0
UIF - Eng-UIF Jansen/Little Wekiva/Elec Imp & RTUs | UIF | 2015081 | Closed | [5 empty] | 0 | Dec: 0 | 0
UIF - Trailwoods HC Manholes | UIF | 2018057 | Closed | [5 empty] | 0 | March: 75751; Dec: 0 | 75751
UIF - GIS/Mapping - Conversion/Implementation | UIF | 2016025 | Closed | [5 empty] | 0 | Dec: 0 | 0
UIF - Const- UIF Elec Imp & RTUs | UIF | 2016068 | Closed |  |  |  |  | 0 | 0 | June: 1458; Sep: 100; Oct: 26187; Dec: 0 | 27745
UIF - Lake Tarpon AC WM Replacement - Phase 3 | UIF | 2016091 | Closed | [5 empty] | 0 | February: 51578.66; Dec: 0.34 | 51579
UIF - Bear Lake Galv. & AC Main Replacement | UIF | 2016093 | Closed |  |  |  |  | 0 | 0 | 277959.81 | 171144.09 | 172224.97 | 105.23 | 55287.2 | 145393.67 | 63246.8 |  |  |  |  | 0.23 | 885362
UIF - Crescent Hgts Galv. & AC Main Replacement | UIF | 2016094 | Closed |  | 500000 | 0 | 0 | 0 | 500000 | 192844.83 | 186648.61 | 180879.02 | 172176.19 | 129129.62 | 110011.63 | 191800.46 | 75078.88 | 498.44 | 323365.36 |  | 0 | 1562433.04
UIF - Crystal Lake- AC Water Main Replacement - Phase 3 | UIF | 2016095 | Closed |  | 0 | 0 | 0 | 0 | 0 | 147.32 | 317397.52 | 92364.09 | 32611.26 | 45302.96 | 45664.48 | 55608.55 | 48127.56 | 237809.68 | 197639.03 |  | 0 | 1072672.45
UIF - Little Wekiva AC Main Replacement | UIF | Closed | Closed |  | 0 | 0 | 0 | 0 | 0 | February: 9481.5; Dec: 0 | 9481.5
UIF - Oakland Shores Galv. WM and Valve Replacement | UIF | Closed | Closed |  | 0 | 0 | 0 | 0 | 0 | January: 142253.82; February: 100577.73; March: 173082.1; Dec: 0 | 415913.65
UIF - Phillips- AC Water Main Replacement | UIF | 2016098 | Closed |  | 989000 | 0 | 0 | 0 | 989000 | 274155.95 | 50342.73 | 93270.45 | 55034.37 | 68062.5 | 45173.12 | 55155.18 | 45173.12 | 180905.2 | 285066.22 |  | 0 | 1152338.84
UIF - Ravenna Park Galv. & AC Main Replacement | UIF | Closed | Closed |  |  |  | 0 | 0 | 0 | January: 126.27; February: 279831.11; March: 84.18; April: 63.14; Dec: 0 | 280104.7
UIF - OW/Buena Vista- AC WM Replacement | UIF | 2016102 | Closed |  |  |  | 0 | 0 | 0 | 142402.62 | 1475.16 | 238194.49 | 222349.68 | 7173.84 | 99683.36 | 2640.08 | 137666.02 |  |  |  | 0 | 851585.25
UIF - Weathersfield Northwestern FM Relocation | UIF | 2017004 | Closed | [5 empty] | 0 | Dec: 0 | 0
UIF - Jansen WTP Gen Replacement | UIF | 2017168 | 2017 | [5 empty] | 0 | March: 1400; June: 68177.78; Sep: 100; Oct: 400; Nov: 164.92; Dec: 18707.52 | 88950.22
UIF - Jansen AC Main Replacement | UIF | 1 | 2020 | [5 empty] | 0 | [12 empty] | 0
UIF - Little Wekiva Generator |  | 1 | 2019 | [5 empty] | 0 | [12 empty] | 0 | bar: Nov
UIF - Park Ridge Generator |  | 1 | 2019 | [5 empty] | 0 | [12 empty] | 0
UIF - NW Bridge Interconnect |  | 1 | 2018/2019 | [5 empty] | 0 | [12 empty] | 0
UIF - Trailwoods Meter Relocations | UIF | 2018071 | Closed |  | 100000 |  |  |  | 129900 | April: 249.14; July: 107221.5; Aug: 32634.91; Sep: 4013.73; Dec: 0 | 144119.28
UIF - Weathersfield AC Main Replacement Ph 1 | UIF | 1 | 2021 | [5 empty] | 0 | [12 empty] | 0
UIF - Weathersfield AC Main Replacement Ph 2 | UIF | 1 | 2022 | [5 empty] | 0 | [12 empty] | 0
UIF - Seminole L/S RTUs |  | 1 | 2019 | [5 empty] | 0 | [12 empty] | 0
UIF - ST - Smoke Testing/I&I Investigation | UIF | 1 | 2018 |  |  |  |  | 50000 | 50000 | [12 empty] | 0
UIF - Captime | UIF | Captime |  |  | 24884.495 | 24884.495 | 24884.495 | 24884.495 | 99537.98 | 8249.65 | 5219.17 | 4145.87 | 4938.11 | 3072.88 | 1687.92 | 1558.08 | 1558.08 | 3830.28 | 1752.84 | 4319.14 | 1320.04 | 41652.06
UIF - G/L Spending | UIF | G/L Spending |  |  | 75000 | 75000 | 75000 | 75000 | 300000 | 55658.85 | 27237.55 | 33575.58 | 37162.71 | 38372.6 | 2951.22 | 15061.73 | 56711.68 | 7148.14 | 28323.17 | 34343.12 | 16852.86 | 353399.21
UIF - IDC | UIF | IDC | [6 empty] | 0 | 60190.45 | 68590.05 | 76319.49 | 47031.51 | 49988.4 | 53866.71 | 46219.34 | 47713.62 | 31774.27 | 569.2 | 571.58 | 712.35 | 483546.97
ACME - Captime | ACME | Captime |  |  | 1859.35 | 1859.35 | 1859.35 | 1859.35 | 7437.4 | May: 86.56; June: 324.6; Aug: 432.8; Oct: 259.68 | 1103.64
ACME - G/L Spending | ACME | G/L Spending |  |  | 7500 | 7500 | 7500 | 7500 | 30000 | February: 8538.96; March: 1563.92; April: 718.25; May: -4.12; Aug: 4220; Oct: 7808; Nov: 1600 | 24445.01
Sanlando - Const. Shadow Hills Diversion to Wekiva | Sanlando | 2017011 | 2018 | [5 empty] | 0 | 259494.5 | 471738.69 | 412065.9 | 390261.24 | 259517.07 | 204703.58 | 155298.48 | 124155.22 | 129993.56 | 22889.15 | 20937.8 | -15164.71 | 2435890.48
Sanlando - Hibocs Addition |  | 1 | 2018/2019 | [5 empty] | 0 | Dec: 143.28 | 143.28
Sanlando - Eng Const Well 2A & LS A-1 Gen | Sanlando | 2015084 | Closed |  | 0 | 0 | 0 | 0 | 0 | Dec: 0 | 0
Sanlando - Eng Shadow Hills Diversion to Wekiva | Sanlando | 2016056 | Closed |  | 0 | 0 | 0 | 0 | 0 | February: 3387; Dec: 0 | 3387
Sanlando - Myrtle Lake Hills Main Extension - (with CIAC) | Sanlando | 2016057 | Closed | [5 empty] | 0 | Dec: 0 | 0
Sanlando - Wekiva WWTP Rehab | Sanlando | 2016058 | Closed |  | 0 | 0 | 0 | 0 | 0 | 24711.75 | 23760.03 | 51310.59 | 64248.58 | 451725.58 | 20349.21 | 27507.04 |  |  |  |  | -0.04 | 663612.74
Sanlando - Const DP W2A & LS A-1 Genset | Sanlando | 2016067 | Closed | [5 empty] | 0 | March: 11223; Dec: 0 | 11223
Sanlando - Correct I&I deficiencies Sanlando - Phase 2 | Sanlando | 2016074 | Closed | [5 empty] | 0 | Dec: 0 | 0
Sanlando - Autumn Drive WM Replacement | Sanlando | 2016087 | Closed |  | 0 | 0 | 0 | 0 | 0 | Dec: 0 | 0
Sanlando - Lift Station RTU Installations | Sanlando | 2017001 | Closed | [5 empty] | 0 | 59250 | 43492.09 | 39647.32 | 56196.33 | 13920.96 | 9400.68 | 4014.92 |  | 980 |  |  | 0 | 226902.3
Sanlando - Wekiva-Blower Replacement | Sanlando | 1 | 2018 |  | 200000 | 1000000 | 0 | 0 | 1200000 | [12 empty] | 0
Sanlando - Wekiva WWTF Imp Eng |  | 2018109 | 2018/2019 | [5 empty] | 0 | Aug: 65289.28; Sep: 29698.56; Oct: 71070.4; Nov: 45260.24; Dec: 45608.2 | 256926.68
Sanlando - Lift Station & Filter Replacement |  | 1 | 2019 | [5 empty] | 0 | [12 empty] | 0
Sanlando - I&I Corrections Ph 3 |  | 2018150 | 2018 | [5 empty] | 0 | Nov: 194.76; Dec: 227268.1 | 227462.86
Sanlando - I&I Corrections Ph 4 | Sanlando | 2018117 | 2019 |  |  | 100000 | 450000 | 450000 | 1000000 | Aug: 329.84; Sep: 28080.79; Oct: 94951.87; Nov: 22774.02; Dec: 12788.1 | 158924.62
Sanlando - I&I Corrections Ph 5 |  | 1 | 2020 | [5 empty] | 0 | [12 empty] | 0
Sanlando - ENG Powerline 14" FM Replacement | Sanlando | 2018098 | 2018 | [5 empty] | 0 | Aug: 4100; Sep: 14050; Oct: 8700; Nov: 4350; Dec: 2175 | 33375
Sanlando - GST Rehabs - DM PROJECT $150K |  | 1 | 2018/2019 | [5 empty] | 0 | [12 empty] | 0
Sanlando - Powerline 14" FM Replacement | Sanlando | 1 | 2019 |  |  | 0 | 500000 | 500000 | 1000000 | [12 empty] | 0
Sanlando - Wekiva Springs Rd FM Replacement |  | 1 | 2020 | [5 empty] | 0 | [12 empty] | 0
Sanlando - L/S F1 Forcemain Replacement |  | 1 | 2020 | [5 empty] | 0 | [12 empty] | 0
Sanlando - Powerline WM Replacement |  | 1 | 2019 | [5 empty] | 0 | [12 empty] | 0
Sanlando - Springs WM Replacement | Sanlando | 1 | NA |  |  |  | 0 | 0 | 0 | [12 empty] | 0
Sanlando - Captime | Sanlando | Captime |  |  | 40084.4983 | 40084.4983 | 40084.4983 | 40084.4983 | 160337.9933 | 15846.9 | 13089.91 | 13402.15 | 9762.2 | 16644.46 | 12202 | 14620.44 | 12551.2 | 13243.68 | 17550.04 | 14130.92 | 12729.56 | 165773.46
Sanlando - G/L Spending | Sanlando | G/L Spending |  |  | 150000 | 150000 | 150000 | 150000 | 600000 | 45096.75 | 73728.16 | 64828.83 | 39567.52 | 96819.49 | 88544.07 | 136466.17 | 98742.65 | 93053.57 | 82923.82 | 82532.15 | 54810.34 | 957113.52
Sanlando - IDC | Sanlando | IDC | [6 empty] | 0 | 63670.59 | 67840.46 | 71717.69 | 74722.96 | 78674.06 | 82781.88 | 66918.66 | 58437.99 | 59956.71 | 61443.74 | 62147.45 | 3273.86 | 751586.05
Sandalhaven - EWD Bulk Sewer Capacity Payment | Sandalhaven | 1 | NA |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
Sandalhaven - L/S RTU Installation |  | 1 | 2019 | [5 empty] | 0 | [12 empty] | 0
Sandalhaven - Smoke Testing/I&I Investigation | Sandalhaven | 1 | 2019 |  |  |  |  | 50000 | 50000 | [12 empty] | 0
Sandalhaven - Constr. CR 775 Widening Relocation Project - Ph 2 | Sandalhaven | 2017010 | Closed | [5 empty] | 0 | January: 73665.7; March: 55.29; Dec: 0 | 73720.99
Sandalhaven - Eng CR 775 Widening Relocation Project - Phase 1 | Sandalhaven | 2011047 | Closed |  | 0 | 0 | 0 | 0 | 0 | Dec: 0 | 0
Sandalhaven - Captime | Sandalhaven | Captime |  |  | 1900 | 1900 | 1900 | 1900 | 7600 | January: -905.74; June: 692.48; Aug: 1038.72; Oct: 2769.92 | 3595.38
Sandalhaven - G/L Spending | Sandalhaven | G/L Spending |  |  | 9000 | 9000 | 9000 | 9000 | 36000 |  | 2800 |  | 15816.11 | 12222.31 | 33623.09 | 31827.37 | 1613.03 |  | 8792.11 | 6669 |  | 113363.02
Sandalhaven - IDC | Sandalhaven | IDC | [6 empty] | 0 | [12 empty] | 0
Labrador - Sediment Removal | Labrador | 2016076 | Closed | [5 empty] | 0 | Dec: 0 | 0
Labrador - Engineering WWTP Master Plan |  | 1 | 2018 | [5 empty] | 0 | [12 empty] | 0
Labrador - Construction WWTP Master Plan |  | 1 | 2019/2020 | [5 empty] | 0 | [12 empty] | 0
Labrador - Captime | Labrador | Captime |  |  | 4500 | 4500 | 4500 | 4500 | 18000 | 1052.25 | 1178.52 |  | 2967.36 | 991.28 | 692.48 | 1363.32 | 2531.88 | 822.32 | 1038.72 | 389.52 | 346.24 | 13373.89
Labrador - G/L Spending | Labrador | G/L Spending |  |  | 7500 | 7500 | 7500 | 7500 | 30000 | 2858.53 | 4735.62 | 4784.42 | 4658.1 | 825.01 | 510.12 | 2556.61 | 3467.85 | 460.33 | 876.07 | 5042.68 | 10034.56 | 40809.9
Labrador - IDC | Labrador | IDC | [6 empty] | 0 | [12 empty] | 0
Pennbrooke - Pennbrooke WTP Electrical Upgrades | Pennebrooke | 2017005 | Closed |  |  |  | 0 | 0 | 0 | January: 71124.67; February: 28831.33; March: 14160.14; April: 63947.16; Dec: -0.3 | 178063
Pennbrooke - WTP Upgrade | Pennebrooke | 1 | NA |  | 50000 |  | 1200000 | 1250000 | 2500000 | [12 empty] | 0
Pennbrooke - L/S RTU Installation |  | 1 | 2019 | [5 empty] | 0 | [12 empty] | 0
Pennbrooke - Captime | Pennebrooke | Captime |  |  | 6745.4842 | 6745.4842 | 6745.4842 | 6745.4842 | 26981.9367 | 1283.75 | 589.26 | 989.12 | 484.04 | 735.76 |  | 1990.88 | 779.04 |  | 1493.16 | 389.52 | 2077.44 | 10811.97
Pennbrooke - G/L Spending | Pennebrooke | G/L Spending |  |  | 15000 | 15000 | 15000 | 15000 | 60000 | 12780.66 | 3100.04 | 15795.51 | 3397.69 | 3132.03 | 28718.46 | 3325.19 | 12142.24 | 779.76 | 3315 | 23597.65 | 1512.53 | 111596.76
Pennbrooke - IDC | Pennebrooke | IDC | [6 empty] | 0 | January: 1991.4; February: 2736.28; March: 2842.84 | 7570.52
FL Cost Center - Captime | Cost Center | Captime |  |  | 0 | 0 | 0 | 0 | 0 | Nov: 346.24; Dec: 346.24 | 692.48
FL Cost Center - G/L Spending | Cost Center | G/L Spending |  |  | 2500 | 2500 | 2500 | 2500 | 10000 | 743.66 |  | 1394.4 | 269 | 772.13 | 31680.36 | 11821.88 |  | 10169.63 | 20677.71 | 19720.51 | 25135 | 122384.28
FL Cost Center - Valve Exerciser Machine | Cost Center | 2018060 | Closed |  | 60000 |  |  |  | 60000 | March: 281.1; April: 86.91; May: 65877.97; Dec: 0 | 66245.98
FL Cost Center - 15KW Generator Fleet |  | 2018151 | 2019 | [5 empty] | 0 | Nov: 151.48 | 151.48
FL Cost Center - Fleet Replacements | Cost Center | Transportation | 2019 |  | 287500 | 87500 | 87500 | 87500 | 550000 |  |  | 131656.57 | 223911.71 | -2768.67 |  | 2627.74 | 6858.34 |  | 58616.22 | 1711.98 | -90.15 | 422523.74
FL Cost Center - Transportation (UIF) - C4500 Kodiak Service Truck Upgrades | Cost Center | Transportation2 | [6 empty] | 0 | [12 empty] | 0

## 2019
Florida Capital File - 2019 | [8 empty] | 15575181.669 | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual
| 1384300 |  |  |  | INPUT | Do not type in these columns | Entire Forecast |  | 15575181.669 | 567448.8274 | 606420.84 | 1305611.22 | 841905.14 | 469388.94 | 731945.87 | 792954.77 | 1259263.34 | 431082.21 | 699225.21 | 795695.94 | 1005350.76 | 9506293.0674
Project | Project # | Type | Status | Spending | Prior Yr Spend | 2019+ Forecast | Total 6 Yr | JDE Budget | 2019 Budget | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2019 Total
Tierra Verde - ENG Lift Station #4 Forcemain | 2019086 | Capital Spending | Open | 117692 |  | 117692 | 117692 | 80542 | 80000 | 22690 | 17710 | 3800 | 5535 | 6765 | 33442 |  | 9000 |  | 10500 | 8250 |  | 117692
Tierra Verde - ENG Lift Station #4 Forcemain - Captime | 2019086 | Project Captime | Open | 811.44 |  | 811.44 | 811.44 |  |  | May: 361.44; Jul: 250; Nov: 200 | 811.44
Tierra Verde - ENG Lift Station #4 Forcemain - IDC | 2019086 | IDC | Open | 4013.6822 |  | 4013.6822 | 4013.6822 |  | 10158.75 | 170.7422 |  |  |  | 2.72 | 2.72 | 681.41 | 749.14 | 749.14 | 828.15 | 829.66 |  | 4013.6822
Tierra Verde - FM / GSM Relocation | 2019087 | Capital Spending | Open | 441193.74 |  | 551224.74 | 551224.74 | 451225 | 295000 | Jul: 187633.58; Aug: 102224.85; Sep: 29.17; Oct: 41874.34; Nov: 109431.8 | 441193.74
Tierra Verde - FM / GSM Relocation - Captime | 2019087 | Project Captime | Open | 5271.02 |  | 6921.485 | 6921.485 |  |  | Jun: 461.44; Jul: 1137.34; Aug: 1419.86; Sep: 587.34; Oct: 300; Nov: 822.88; Dec: 542.16 | 5271.02
Tierra Verde - FM / GSM Relocation - IDC | 2019087 | IDC | Open | 11708.77 |  | 23468.518 | 23468.518 |  |  | Jun: 3.47; Jul: 1423.97; Aug: 2201.52; Sep: 2205.14; Oct: 2522.5; Nov: 3352.17 | 11708.77
Tierra Verde - Liftstation #4 Replacement | 2019173 | Capital Spending | Open | 0 |  | 828440 | 828440 | 828440 | [13 empty] | 0
Tierra Verde - Liftstation #4 Replacement - Captime | 2019173 | Project Captime | Open | 100 |  | 12526.6 | 12526.6 |  |  | Dec: 100 | 100
Tierra Verde - Liftstation #4 Replacement - IDC | 2019173 | IDC | Open | 0 |  | 22293.7338 | 22293.7338 | [14 empty] | 0
Tierra Verde - Redzone I&I Investigation | 2018116 | Capital Spending | Open | 82642.2 |  | 82642.2 | 82642.2 | 95300 | 250000 | Feb: 3730; Mar: 72071.2; Apr: 4320; Nov: 2521 | 82642.2
Tierra Verde - Redzone I&I Investigation - Captime | 2018116 | Project Captime | Open | 11170.8 | 200 | 10970.8 | 11170.8 |  |  | Jan: 6908.4; Feb: 3246; Mar: 300; Apr: 216.4; Oct: 200; Dec: 100 | 10970.8
Tierra Verde - Redzone I&I Investigation - IDC | 2018116 | IDC | Open | 2129.87 | 1.51 | 2128.36 | 2129.87 |  | 6584.375 | Jan: 36.88; Feb: 74.72; Mar: 650.58; Apr: 683.09; May: 683.09 | 2128.36
Tierra Verde - G/L Spending |  | GL Spending |  | 14859.66 |  | 182204.74 | 182204.74 |  | 30000 | 2575 | 3531.28 | 17260.7 | 4505 | 600 | -17967.67 |  |  |  |  | 0 | 4355.35 | 14859.66
Tierra Verde - Captime |  | GL Captime |  |  |  | 17973.0026 | 17973.0026 |  | 3167.5212 | 519.36 | 749.2 | 173.12 | 819.36 | 948 |  | 993.96 | 1106.91 |  | 993.96 | 135.54 | 271.08 | 6710.49
Tierra Verde - Cap Suspense |  | Cap Suspense | [7 empty] | Sep: 9000 | 9000
Lake Placid - G/L Spending |  | GL Spending |  | 14387.13 |  | 77141.535 | 77141.535 |  | 15000 |  | 650 |  | 6245.92 |  | 637.5 | 1695.28 | -27.51 | 435.05 | 2940.89 |  | 1810 | 14387.13
Lake Placid - Captime |  | GL Captime |  |  |  | 7991.5963 | 7991.5963 |  | 1583.7606 | Mar: 432.8; Apr: 346.24; Jun: 271.08; Jul: 1084.32; Oct: 135.54; Nov: 90.36 | 2360.34
Lake Placid - Cap Suspense |  | Cap Suspense
Longwood - Shadow Hills WWTF Demolition | 2019002 | Capital Spending | Closed | 88986.79 | 55386.79 | 33600 | 88986.79 | 88987 |  | Jan: 17600; Mar: 16000 | 33600
Longwood - Shadow Hills WWTF Demolition - Captime | 2019002 | Project Captime | Closed | 1506.6 |  | 1506.6 | 1506.6 |  |  | Jan: 898.4; Feb: 500; Mar: 108.2 | 1506.6
Longwood - Shadow Hills WWTF Demolition - IDC | 2019002 | IDC | Closed | 843.72 | 287.73 | 555.99 | 843.72 |  |  | Jan: 555.99 | 555.99
Longwood - L/S RTUs | 2019078 | Capital Spending | Open | 68207.95 |  | 129999.95 | 129999.95 | 122818 | 130000 | Aug: 68207.95 | 68207.95
Longwood - L/S RTUs - Captime | 2019078 | Project Captime | Open | 90.36 |  | 1017.24 | 1017.24 |  |  | Oct: 90.36 | 90.36
Longwood - L/S RTUs - IDC | 2019078 | IDC | Open | 2054.4 |  | 4540.1535 | 4540.1535 |  | 1956.5 | Jan: 0; Aug: 513.26; Sep: 513.26; Oct: 513.94; Nov: 513.94 | 2054.4
Longwood - FM Phase 1 | 1 | Capital Spending | 2022 | 0 |  | 1194108 | 1194108 | [14 empty] | 0
Longwood - FM Phase 1 - Captime | 1 | Project Captime | 2022 | 0 |  | 17911.62 | 17911.62 | [14 empty] | 0
Longwood - FM Phase 1 - IDC | 1 | IDC | 2022 | 0 |  | 68403.3573 | 68403.3573 |  |  | Jan: 0 | 0
Longwood - G/L Spending |  | GL Spending |  | 44543.52 |  | 358315.545 | 358315.545 |  | 44000 | 5677.42 | 8943.63 | -47.02 | 1987.5 | 200 | 450 |  |  | 27011.99 | 320 |  |  | 44543.52
Longwood - Captime |  | GL Captime |  |  |  | 44326.7522 | 44326.7522 |  | 11807.48 | 43.28 |  | 402.96 |  | 338.85 | 180.72 |  | 700.29 | 135.54 | 225.9 | 180.72 | 135.54 | 2343.8
Longwood - Cap Suspense |  | Cap Suspense | [19 empty] | 0
Cypress Lakes - Smoke Testing/I&I Investigation | 1 | Capital Spending | 2020 | 0 |  | 50000 | 50000 |  | 50000 | [12 empty] | 0
Cypress Lakes - Smoke Testing/I&I Investigation - Captime | 1 | Project Captime | 2020 | 0 |  | 750 | 750 | [14 empty] | 0
Cypress Lakes - Smoke Testing/I&I Investigation - IDC | 1 | IDC | 2020 | 0 |  | 763.7875 | 763.7875 |  | 752.5 | Jan: 0 | 0
Cypress Lakes - Filter Replacement | 1 | Capital Spending | 2022 | 0 |  | 300000 | 300000 |  | 50000 | [12 empty] | 0
Cypress Lakes - Filter Replacement - Captime | 1 | Project Captime | 2022 | 0 |  | 4500 | 4500 | [14 empty] | 0
Cypress Lakes - Filter Replacement - IDC | 1 | IDC | 2022 | 0 |  | 10311.1312 | 10311.1312 |  | 752.5 | Jan: 0 | 0
Cypress Lakes - Rehab L/S 1 | 2019084 | Capital Spending | Open | 77490 |  | 85000 | 85000 | 76500 | 85000 | Oct: 1000; Nov: 44; Dec: 76446 | 77490
Cypress Lakes - Rehab L/S 1 - Captime | 2019084 | Project Captime | Open | 3001.16 |  | 3113.81 | 3113.81 |  |  | Oct: 1826.48; Nov: 1174.68 | 3001.16
Cypress Lakes - Rehab L/S 1 - IDC | 2019084 | IDC | Open | 51.71 |  | 1983.5188 | 1983.5188 |  | 1279.25 | Jan: 0; Oct: 21.27; Nov: 30.44 | 51.71
Cypress Lakes - Disinfection Upgrade | 1 | Capital Spending | 2020 | 0 |  | 125000 | 125000 |  | 25000 | [12 empty] | 0
Cypress Lakes - Disinfection Upgrade - Captime | 1 | Project Captime | 2020 | 0 |  | 1875 | 1875 | [14 empty] | 0
Cypress Lakes - Disinfection Upgrade - IDC | 1 | IDC | 2020 | 0 |  | 4200.8312 | 4200.8312 |  |  | Jan: 0 | 0
Cypress Lakes - | 1 | Capital Spending | N/A | 0 |  | 0 | 0 | [14 empty] | 0
Cypress Lakes - - Captime | 1 | Project Captime | N/A | 0 |  | 0 | 0 | [14 empty] | 0
Cypress Lakes - - IDC | 1 | IDC | N/A | 0 |  | 0 | 0 |  |  | Jan: 0 | 0
Cypress Lakes - G/L Spending |  | GL Spending |  | 100399.51 |  | 518762.21 | 518762.21 |  | 75000 | 0.79 | 12059.93 | 31671 | 11517.51 | 2240.43 | 961.72 | 12791.95 | 1708.05 | 2081.62 | 23783.04 |  | 1583.47 | 100399.51
Cypress Lakes - Captime |  | GL Captime |  |  |  | 75244.5422 | 75244.5422 |  | 16671.1644 | 86.56 |  | 1082 | 2015.14 | 1344.28 | 2326.77 | 1965.33 | 1365.04 | 45.18 |  | 4405.05 | 1332.81 | 15968.16
Cypress Lakes - Cap Suspense |  | Cap Suspense | [19 empty] | 0
Eagle Ridge - Lift Station RTU Improvements | 2019024 | Capital Spending | Open | 163797.14 |  | 221332.14 | 221332.14 | 229000 | 200000 | Mar: 29860; Apr: 18055.16; Jul: 68.11; Sep: 115813.87 | 163797.14
Eagle Ridge - Lift Station RTU Improvements - Captime | 2019024 | Project Captime | Open | 1146.24 |  | 2009.265 | 2009.265 |  |  | Apr: 700; Jul: 100; Sep: 346.24 | 1146.24
Eagle Ridge - Lift Station RTU Improvements - IDC | 2019024 | IDC | Open | 5777.36 |  | 10379.8471 | 10379.8471 |  | 3010 | 0 |  | 224.7 | 365.83 | 365.83 | 365.83 | 367.09 | 367.09 | 1238.59 | 1241.2 | 1241.2 |  | 5777.36
Eagle Ridge - ER North and South Plant Rehab | 2019050 | Capital Spending | Closed | 218995.29 |  | 218995.29 | 218995.29 | 200000 |  | Apr: 80930.55; May: 16896.78; Aug: 31386.88; Sep: 27.13; Oct: 81127.96; Nov: 8625.99 | 218995.29
Eagle Ridge - ER North and South Plant Rehab - Captime | 2019050 | Project Captime | Open | 3745.26 |  | 3745.26 | 3745.26 | [5 empty] | 100 | 846.24 | 100 | 250 | 200 | 548.44 | 1519.86 | 180.72 |  | 3745.26
Eagle Ridge - ER North and South Plant Rehab - IDC | 2019050 | IDC | Open | 6424.32 |  | 6424.32 | 6424.32 |  |  | 0 |  |  | 609.75 | 743.27 | 744.02 | 745.9 | 983.6 | 987.93 | 1609.85 |  |  | 6424.32
Eagle Ridge - | 1 | Capital Spending | N/A | 0 |  | 0 | 0 | [14 empty] | 0
Eagle Ridge - - Captime | 1 | Project Captime | N/A | 0 |  | 0 | 0 | [14 empty] | 0
Eagle Ridge - - IDC | 1 | IDC | N/A | 0 |  | 0 | 0 |  |  | Jan: 0 | 0
Eagle Ridge - ENG WWTP Variance & LDO | 2019125 | Capital Spending | Open | 104638.23 |  | 162000.23 | 162000.23 | 94600 | 125000 | Sep: 98433.9; Oct: 554.3; Nov: 3514.28; Dec: 2135.75 | 104638.23
Eagle Ridge - ENG WWTP Variance & LDO - Captime | 2019125 | Project Captime | Open | 1879.48 |  | 2739.91 | 2739.91 |  |  | Sep: 979.48; Oct: 600; Nov: 200; Dec: 100 | 1879.48
Eagle Ridge - ENG WWTP Variance & LDO - IDC | 2019125 | IDC | Open | 1543.73 |  | 4824.6149 | 4824.6149 |  | 752.5 | Jan: 0; Sep: 2.24; Oct: 756.77; Nov: 784.72 | 1543.73
Eagle Ridge - WWTP Tree Removal / Fencing | 2019175 | Capital Spending | Open | 116876 |  | 637000 | 637000 | 637000 |  | Dec: 116876 | 116876
Eagle Ridge - WWTP Tree Removal / Fencing - Captime | 2019175 | Project Captime | Open | 361.44 |  | 8163.3 | 8163.3 |  |  | Dec: 361.44 | 361.44
Eagle Ridge - WWTP Tree Removal / Fencing - IDC | 2019175 | IDC | Open | 0 |  | 10591.9194 | 10591.9194 |  |  | Jan: 0 | 0
Eagle Ridge - Replace Reject Pond Liner | 2019122 | Capital Spending | Open | 257795.93 |  | 257795.93 | 257795.93 | 235460 | 200000 | Nov: 152034.33; Dec: 105761.6 | 257795.93
Eagle Ridge - Replace Reject Pond Liner - Captime | 2019122 | Project Captime | Open | 5242.1 |  | 5242.1 | 5242.1 |  |  | Oct: 1855.4; Nov: 3286.7; Dec: 100 | 5242.1
Eagle Ridge - Replace Reject Pond Liner - IDC | 2019122 | IDC | Open | 1196.71 |  | 1196.71 | 1196.71 |  | 3010 | Jan: 0; Oct: 13.96; Nov: 1182.75 | 1196.71
Eagle Ridge - I&I Investigation | 1 | Capital Spending | 2020 | 0 |  | 50000 | 50000 |  | 50000 | [12 empty] | 0
Eagle Ridge - I&I Investigation - Captime | 1 | Project Captime | 2020 | 0 |  | 750 | 750 | [14 empty] | 0
Eagle Ridge - I&I Investigation - IDC | 1 | IDC | 2020 | 0 |  | 763.7875 | 763.7875 |  | 752.5 | Jan: 0 | 0
Eagle Ridge - L/S ER 3 | 1 | Capital Spending | 2020 | 0 |  | 100000 | 100000 | [14 empty] | 0
Eagle Ridge - L/S ER 3 - Captime | 1 | Project Captime | 2020 | 0 |  | 1500 | 1500 | [14 empty] | 0
Eagle Ridge - L/S ER 3 - IDC | 1 | IDC | 2020 | 0 |  | 2673.2562 | 2673.2562 |  |  | Jan: 0 | 0
Eagle Ridge - G/L Spending |  | GL Spending |  | 305648.42 |  | 724011.12 | 724011.12 |  | 100000 | 4051.19 | 2651.25 | 23578.85 | 9437.21 | 4128.58 | 47991.06 | 96113.87 | 44855.3 | 4212.34 | 13357.19 | 28417.29 | 26854.29 | 305648.42
Eagle Ridge - Captime |  | GL Captime |  |  |  | 130553.4751 | 130553.4751 |  | 23339.6301 | 8160.56 | 5839.84 | 10697.68 | 1861.04 | 1709.52 | 2123.46 | 4204.76 | 3572.24 | 2439.72 | 2665.62 | 1536.12 | 2755.98 | 47566.54
Eagle Ridge - Cap Suspense |  | Cap Suspense |  |  | 68337.84 | -68337.68 | 0.16 |  |  | 5482.28 | 7486.08 | -20639 | 1496.08 | 13945.83 | 7578.27 | 1644.06 | 4091.56 | -89422.84 |  |  |  | -68337.68
Mid-County - WWTP Improvements - Engineering | 2019145 | Capital Spending | Open | 115030.7 |  | 633179.7 | 633179.7 | 175000 |  | Sep: 65210.7; Oct: 35020; Dec: 14800 | 115030.7
Mid-County - WWTP Improvements - Engineering - Captime | 2019145 | Project Captime | Open | 3213.24 |  | 10985.475 | 10985.475 |  |  | Sep: 2161.44; Oct: 651.8; Nov: 300; Dec: 100 | 3213.24
Mid-County - WWTP Improvements - Engineering - IDC | 2019145 | IDC | Open | 1566.62 |  | 16198.6801 | 16198.6801 |  |  | Jan: 0; Sep: 13.55; Oct: 775.41; Nov: 777.66 | 1566.62
Mid-County - WWTP Improvements -Construction | 1 | Capital Spending | 2020 | 0 |  | 9100000 | 9100000 | [14 empty] | 0
Mid-County - WWTP Improvements -Construction - Captime | 1 | Project Captime | 2020 | 0 |  | 136500 | 136500 | [14 empty] | 0
Mid-County - WWTP Improvements -Construction - IDC | 1 | IDC | 2020 | 0 |  | 624102.4851 | 624102.4851 |  |  | Jan: 0 | 0
Mid-County - I&I Improvements | 1 | Capital Spending | 2020 | 0 |  | 4000000 | 4000000 | [14 empty] | 0
Mid-County - I&I Improvements - Captime | 1 | Project Captime | 2020 | 0 |  | 60000 | 60000 | [14 empty] | 0
Mid-County - I&I Improvements - IDC | 1 | IDC | 2020 | 0 |  | 202765.9439 | 202765.9439 |  |  | Jan: 0 | 0
Mid-County - Spanish Acres GSM Rehab | 2019001 | Capital Spending | Closed | 95020.56 |  | 95020.56 | 95020.56 | 117035 |  | Mar: 95009.92; Nov: 10.64 | 95020.56
Mid-County - Spanish Acres GSM Rehab - Captime | 2019001 | Project Captime | Closed | 1262.64 |  | 1262.64 | 1262.64 |  |  | Jan: 400; Feb: 662.64; Jun: 200 | 1262.64
Mid-County - Spanish Acres GSM Rehab - IDC | 2019001 | IDC | Closed | 5802.19 |  | 5802.19 | 5802.19 |  |  | 3.01 | 8 | 722.95 | 722.95 | 722.95 | 724.45 | 724.45 | 724.45 | 724.45 | 724.53 |  |  | 5802.19
Mid-County - LS #4 / #7 Gensets | 2019154 | Capital Spending | Open | 71458.55 |  | 122780.55 | 122780.55 | 116530 |  | Oct: 8750; Nov: 57708.55; Dec: 5000 | 71458.55
Mid-County - LS #4 / #7 Gensets - Captime | 2019154 | Project Captime | Open | 500 |  | 1269.83 | 1269.83 |  |  | Nov: 400; Dec: 100 | 500
Mid-County - LS #4 / #7 Gensets - IDC | 2019154 | IDC | Open | 568.95 |  | 2977.3963 | 2977.3963 |  |  | Jan: 0; Oct: 65.84; Nov: 503.11 | 568.95
Mid-County - LS RTU | 1 | Capital Spending | 2021 | 0 |  | 200000 | 200000 | [14 empty] | 0 | bar: Oct
Mid-County - LS RTU - Captime | 1 | Project Captime | 2021 | 0 |  | 3000 | 3000 | [14 empty] | 0
Mid-County - LS RTU - IDC | 1 | IDC | 2021 | 0 |  | 5380.9975 | 5380.9975 |  |  | Jan: 0 | 0
Mid-County - G/L Spending |  | GL Spending |  | 304650.92 |  | 932194.97 | 932194.97 |  | 200000 | 12935.2 | 5861.85 | 6324.94 | 10058.25 | 17249.34 | 17062.4 | 17319.51 | 15081.64 | 1396.66 | 69593 | 12001.61 | 119766.52 | 304650.92
Mid-County - Captime |  | GL Captime |  |  |  | 167562.7044 | 167562.7044 |  | 33342.3287 | 1125.28 | 4519.12 | 5366.72 | 7268.08 | 4623.46 | 3580.52 | 4179.15 | 3346.34 | 1987.92 | 4979.44 | 3438.5 | 4595.41 | 49009.94
Mid-County - Cap Suspense |  | Cap Suspense |  |  | 42985.64 | 15276.8 | 58262.44 |  |  | Jan: 11457.6; Feb: 44777.2; Mar: 11436; Jul: 5718; Aug: 6718; Sep: -64830 | 15276.8
LUSI - Eng - 2nd Lower Floridan Well | 1 | Capital Spending | 2020 | 0 |  | 150000 | 150000 | [14 empty] | 0
LUSI - Eng - 2nd Lower Floridan Well - Captime | 1 | Project Captime | 2020 | 0 |  | 2250 | 2250 | [14 empty] | 0
LUSI - Eng - 2nd Lower Floridan Well - IDC | 1 | IDC | 2020 | 0 |  | 7446.9281 | 7446.9281 |  |  | Jan: 0 | 0
LUSI - Construction 2nd Lower Floridan Well | 1 | Capital Spending | N/A | 0 |  | 0 | 0 | [14 empty] | 0
LUSI - Construction 2nd Lower Floridan Well - Captime | 1 | Project Captime | N/A | 0 |  | 0 | 0 | [14 empty] | 0
LUSI - Construction 2nd Lower Floridan Well - IDC | 1 | IDC | N/A | 0 |  | 0 | 0 |  |  | Jan: 0 | 0
LUSI - Feasibility Study & Land Purchase for NE WTP | 1 | Capital Spending | 2020 | 0 |  | 100000 | 100000 | [14 empty] | 0
LUSI - Feasibility Study & Land Purchase for NE WTP - Captime | 1 | Project Captime | 2020 | 0 |  | 1500 | 1500 | [14 empty] | 0
LUSI - Feasibility Study & Land Purchase for NE WTP - IDC | 1 | IDC | 2020 | 0 |  | 2673.2562 | 2673.2562 |  |  | Jan: 0 | 0
LUSI - Anderson Hill WM Relocation | 2019018 | Capital Spending | Closed | 71913.73 |  | 71913.73 | 71913.73 | 71914 |  | Feb: 45770.09; Jul: 26143.64 | 71913.73
LUSI - Anderson Hill WM Relocation - Captime | 2019018 | Project Captime | Closed | 1963.36 |  | 1963.36 | 1963.36 |  |  | Feb: 476.08; Mar: 302.96; Apr: 100; Jun: 90.36; Jul: 993.96 | 1963.36
LUSI - Anderson Hill WM Relocation - IDC | 2019018 | IDC | Closed | 1752.05 |  | 1752.05 | 1752.05 |  |  | Jan: 0; Feb: 348; Mar: 350.28; Apr: 351.03; May: 351.03; Jun: 351.71 | 1752.05
LUSI - LUSI North TTHM HAA5 Remediation | 1 | Capital Spending | 2021 | 0 |  | 300000 | 300000 |  | 300000 | [12 empty] | 0
LUSI - LUSI North TTHM HAA5 Remediation - Captime | 1 | Project Captime | 2021 | 0 |  | 4500 | 4500 | [14 empty] | 0
LUSI - LUSI North TTHM HAA5 Remediation - IDC | 1 | IDC | 2021 | 0 |  | 4582.725 | 4582.725 |  | 4515 | Jan: 0 | 0
LUSI - LG WTP Improvements Construction | 2018153 | Capital Spending | Closed | 1450214.17 | 186370 | 1263844.17 | 1450214.17 | 1280000 | 1065000 | Feb: 122055; Mar: 428977.8; Apr: 280650; Jun: 293997.17; Aug: 138164.2 | 1263844.17
LUSI - LG WTP Improvements Construction - Captime | 2018153 | Project Captime | Closed | 48838.04 | 3451.92 | 45386.12 | 48838.04 |  |  | 3081.42 | 4675.6 | 7097.92 | 5701.24 | 7671.52 | 9763.7 | 5210.16 | 2184.56 |  |  |  |  | 45386.12
LUSI - LG WTP Improvements Construction - IDC | 2018153 | IDC | Closed | 46982.1676 | 1576.95 | 45405.2176 | 46982.1676 |  | 29987.125 | Jan: 1451.5976; Feb: 2405.25; Mar: 5686.72; Apr: 7841.51; May: 7899.24; Jun: 9896.66; Jul: 10224.24 | 45405.2176
LUSI - Eng - 561 WTP Wellsite & Land | 1 | Capital Spending | 2020 | 0 |  | 100000 | 100000 |  | 100000 | [12 empty] | 0
LUSI - Eng - 561 WTP Wellsite & Land - Captime | 1 | Project Captime | 2020 | 0 |  | 1500 | 1500 | [14 empty] | 0
LUSI - Eng - 561 WTP Wellsite & Land - IDC | 1 | IDC | 2020 | 0 |  | 1527.575 | 1527.575 |  | 1505 | Jan: 0 | 0
LUSI - Crescent Bay Raw WM | 1 | Capital Spending | 2021 | 0 |  | 500000 | 500000 | [14 empty] | 0
LUSI - Crescent Bay Raw WM - Captime | 1 | Project Captime | 2020 | 0 |  | 7500 | 7500 | [14 empty] | 0
LUSI - Crescent Bay Raw WM - IDC | 1 | IDC | 2020 | 0 |  | 7637.875 | 7637.875 |  |  | Jan: 0 | 0
LUSI - PLC Replacements | 2018097 | Capital Spending | Closed | 37764.8 |  | 37764.8 | 37764.8 | 57584 |  | Apr: 37764.8 | 37764.8
LUSI - PLC Replacements - Captime | 2018097 | Project Captime | Closed | 1852.84 | 186.56 | 1666.28 | 1852.84 |  |  | Feb: 43.28; Mar: 1623 | 1666.28
LUSI - PLC Replacements - IDC | 2018097 | IDC | Closed | 321.2339 | 6.04 | 315.1939 | 321.2339 |  |  | Jan: 1.4039; Feb: 1.73; Mar: 13.94; Apr: 298.12 | 315.1939
LUSI - Barrington WWTP Cap Improvements | 1 | Capital Spending | 2020 | 0 |  | 250000 | 250000 |  | 225000 | [12 empty] | 0 | bar: Dec
LUSI - Barrington WWTP Cap Improvements - Captime | 1 | Project Captime | 2020 | 0 |  | 3750 | 3750 | [14 empty] | 0 | bar: Dec
LUSI - Barrington WWTP Cap Improvements - IDC | 1 | IDC | 2020 | 0 |  | 8974.5031 | 8974.5031 |  | 5079.375 | Jan: 0 | 0
LUSI - Sewer Jetter Trailer | 1 | Capital Spending | 2019 | 0 |  | 50000 | 50000 |  | 50000 | [12 empty] | 0
LUSI - Sewer Jetter Trailer - Captime | 1 | Project Captime | 2019 | 0 |  | 750 | 750 | [14 empty] | 0
LUSI - Sewer Jetter Trailer - IDC | 1 | IDC | 2019 | 0 |  | 763.7875 | 763.7875 |  | 752.5 | Jan: 0 | 0
LUSI - LG Centrifuge | 1 | Capital Spending | N/A | 0 |  | 0 | 0 | [14 empty] | 0
LUSI - LG Centrifuge - Captime | 1 | Project Captime | N/A | 0 |  | 0 | 0 | [14 empty] | 0
LUSI - LG Centrifuge - IDC | 1 | IDC | N/A | 0 |  | 0 | 0 |  | 13168.75 | Jan: 0 | 0
LUSI - LG Sulfuric Acid Tank & Pipe Replacement | 1 | Capital Spending | 2020 | 0 |  | 55000 | 55000 | [14 empty] | 0
LUSI - LG Sulfuric Acid Tank & Pipe Replacement - Captime | 1 | Project Captime | 2020 | 0 |  | 825 | 825 | [14 empty] | 0
LUSI - LG Sulfuric Acid Tank & Pipe Replacement - IDC | 1 | IDC | 2020 | 0 |  | 840.1662 | 840.1662 |  |  | Jan: 0 | 0
LUSI - G/L Spending |  | GL Spending |  | 865824.85 |  | 3794363.75 | 3794363.75 |  | 700000 | 28323.39 | 62229.6 | 48033.58 | 48039.85 | 111024.89 | 58900.63 | 96398.62 | 111889.35 | 57349.12 | 78153.13 | 62522.7 | 102959.99 | 865824.85
LUSI - Captime |  | GL Captime |  |  |  | 1189890.4355 | 1189890.4355 |  | 266738.6299 | 19432.72 | 16181.14 | 18667.12 | 18236.94 | 20696.21 | 15109.45 | 24826.43 | 23900.23 | 19845.33 | 26951.28 | 18800.95 | 18820.52 | 241468.32
LUSI - Cap Suspense |  | Cap Suspense | [7 empty] | Sep: 5000; Oct: 5000; Nov: 8450 | 18450
UIF - Timing Adjustments |  | Timing Plug |  |  |  | 0 | 0 |  | -1000000 | [12 empty] | 0
UIF - Timing Adjustments - IDC |  | IDC
UIF - AMP Implementation | 1 | Capital Spending | 2020 | 0 |  | 0 | 0 | [14 empty] | 0
UIF - AMP Implementation - Captime | 1 | Project Captime | 2020 | 0 |  | 0 | 0 | [14 empty] | 0
UIF - AMP Implementation - IDC | 1 | IDC | 2020 | 0 |  | 0 | 0 |  |  | Jan: 0 | 0
UIF - Jansen WTP Gen Replacement | 2017168 | Capital Spending | Closed | 107819 | 93677.1 | 14141.9 | 107819 | 99686 |  | Mar: 14141.9 | 14141.9
UIF - Jansen WTP Gen Replacement - Captime | 2017168 | Project Captime | Closed | 2047.42 | 1036.26 | 1011.16 | 2047.42 |  |  | Jan: 781.32; Feb: 43.28; Mar: 186.56 | 1011.16
UIF - Jansen WTP Gen Replacement - IDC | 2017168 | IDC | Closed | 6655.89 | 4396.14 | 2259.75 | 6655.89 |  |  | Jan: 717.09; Feb: 717.42; Mar: 825.24 | 2259.75
UIF - Jansen AC Main Replacement | 1 | Capital Spending | 2021 | 0 |  | 500000 | 500000 | [14 empty] | 0
UIF - Jansen AC Main Replacement - Captime | 1 | Project Captime | 2021 | 0 |  | 7500 | 7500 | [14 empty] | 0
UIF - Jansen AC Main Replacement - IDC | 1 | IDC | 2021 | 0 |  | 13452.4938 | 13452.4938 |  |  | Jan: 0 | 0
UIF - Little Wekiva Generator | 2019110 | Capital Spending | Open | 6400 |  | 100000 | 100000 | 94437 | 100000 | Jul: 4600; Oct: 900; Dec: 900 | 6400
UIF - Little Wekiva Generator - Captime | 2019110 | Project Captime | Open | 158.13 |  | 1562.13 | 1562.13 |  |  | Sep: 112.95; Oct: 45.18 | 158.13
UIF - Little Wekiva Generator - IDC | 2019110 | IDC | Open | 189.86 |  | 1767.72 | 1767.72 |  | 1505 | Jan: 0; Jul: 34.62; Aug: 34.62; Sep: 35.46; Oct: 42.58; Nov: 42.58 | 189.86
UIF - Park Ridge Generator | 2019111 | Capital Spending | Open | 6400 |  | 100000 | 100000 | 99137 | 100000 | Jul: 4140; Nov: 1360; Dec: 900 | 6400
UIF - Park Ridge Generator - Captime | 2019111 | Project Captime | Open | 67.77 |  | 1471.77 | 1471.77 |  |  | Jul: 67.77 | 67.77
UIF - Park Ridge Generator - IDC | 2019111 | IDC | Open | 168.54 |  | 1744.3601 | 1744.3601 |  | 1505 | Jan: 0; Jul: 31.66; Aug: 31.66; Sep: 31.66; Oct: 31.66; Nov: 41.9 | 168.54
UIF - NW Bridge Interconnect | 1 | Capital Spending | 2020 | 0 |  | 82000 | 82000 | [14 empty] | 0
UIF - NW Bridge Interconnect - Captime | 1 | Project Captime | 2020 | 0 |  | 1230 | 1230 | [14 empty] | 0
UIF - NW Bridge Interconnect - IDC | 1 | IDC | 2020 | 0 |  | 1252.6115 | 1252.6115 |  |  | Jan: 0 | 0
UIF - Seminole L/S RTUs | 2019076 | Capital Spending | Open | 52479.19 |  | 100000.19 | 100000.19 | 94476 | 100000 | Aug: 52479.19 | 52479.19
UIF - Seminole L/S RTUs - Captime | 2019076 | Project Captime | Open | 100 |  | 812.815 | 812.815 |  |  | May: 100 | 100
UIF - Seminole L/S RTUs - IDC | 2019076 | IDC | Open | 1584.89 |  | 3497.7841 | 3497.7841 |  | 1505 | 0 |  |  |  | 0.75 | 0.75 | 0.75 | 395.66 | 395.66 | 395.66 | 395.66 |  | 1584.89
UIF - ST - Smoke Testing/I&I Investigation | 1 | Capital Spending | 2019 | 0 |  | 50000 | 50000 |  | 50000 | [12 empty] | 0
UIF - ST - Smoke Testing/I&I Investigation - Captime | 1 | Project Captime | 2019 | 0 |  | 750 | 750 | [14 empty] | 0
UIF - ST - Smoke Testing/I&I Investigation - IDC | 1 | IDC | 2019 | 0 |  | 763.7875 | 763.7875 |  |  | Jan: 0 | 0
UIF - ENG - ST Chlorine Dioxide Pilot Study | 2019174 | Capital Spending | Open | 0 |  | 52000 | 52000 | 52000 | [13 empty] | 0
UIF - ENG - ST Chlorine Dioxide Pilot Study - Captime | 2019174 | Project Captime | Open | 0 |  | 780 | 780 | [14 empty] | 0
UIF - ENG - ST Chlorine Dioxide Pilot Study - IDC | 2019174 | IDC | Open | 0 |  | 2214.9838 | 2214.9838 |  |  | Jan: 0 | 0
UIF - Weathersfield WM Replacement | 1 | Capital Spending | 2020 | 0 |  | 0 | 0 | [14 empty] | 0
UIF - Weathersfield WM Replacement - Captime | 1 | Project Captime | 2020 | 0 |  | 0 | 0 | [14 empty] | 0
UIF - Weathersfield WM Replacement - IDC | 1 | IDC | 2020 | 0 |  | 0 | 0 |  |  | Jan: 0 | 0
UIF - Golden Hills WM Relocation NW 78th Ave | 2019146 | Capital Spending | Open | 113634.86 |  | 153999.86 | 153999.86 | 143914 |  | Sep: 2000; Nov: 111634.86 | 113634.86
UIF - Golden Hills WM Relocation NW 78th Ave - Captime | 2019146 | Project Captime | Open | 9845.93 |  | 10451.405 | 10451.405 |  |  | Sep: 190.36; Oct: 3659.58; Nov: 1897.56; Dec: 4098.43 | 9845.93
UIF - Golden Hills WM Relocation NW 78th Ave - IDC | 2019146 | IDC | Open | 943.8 |  | 4347.9845 | 4347.9845 |  |  | Jan: 0; Sep: 1.43; Oct: 44.02; Nov: 898.35 | 943.8
UIF - | 1 | Capital Spending | N/A | 0 |  | 0 | 0 | [14 empty] | 0
UIF - - Captime | 1 | Project Captime | N/A | 0 |  | 0 | 0 | [14 empty] | 0
UIF - - IDC | 1 | IDC | N/A | 0 |  | 0 | 0 |  |  | Jan: 0 | 0
UIF - G/L Spending |  | GL Spending |  | 401543.62 |  | 1656631.72 | 1656631.72 |  | 300000 | 39724.3 | 36194.7 | 46652.79 | 28958.63 | 13886.05 | 38515.52 | 37911.66 | 16644.93 | 62399.19 | 41053.5 | 26191.12 | 13411.23 | 401543.62
UIF - Captime |  | GL Captime |  | 63283.01 |  | 653308.1448 | 653308.1448 |  | 165941.4026 | 3116.16 | 1168.56 | 5307.04 | 8214.68 | 7902.28 | 5820.09 | 9171.54 | 3336.7 | 5952.47 | 2773.46 | 6014.98 | 4505.05 | 63283.01
UIF - Cap Suspense |  | Cap Suspense |  |  | 13977.75 | 9000 | 22977.75 |  |  | Nov: 4500; Dec: 4500 | 9000
ACME - G/L Spending |  | GL Spending |  | 13401.89 |  | 138910.7 | 138910.7 |  | 58000 | Feb: 11909.06; Mar: 2486.63; Apr: -1809.92; Oct: 816.12 | 13401.89
ACME - Captime |  | GL Captime |  |  |  | 46591.5765 | 46591.5765 |  | 12399.0118 | Feb: 346.24; Apr: 1731.2; Sep: 90.36; Nov: 337.56 | 2505.36
Sanlando - Hibocs Addition | 2018177 | Capital Spending | Closed | 55500 |  | 55500 | 55500 | 55500 |  | Apr: 55500 | 55500
Sanlando - Hibocs Addition - Captime | 2018177 | Project Captime | Closed | 697.72 | 143.28 | 554.44 | 697.72 |  |  | Jan: 100; Mar: 173.12; Apr: 281.32 | 554.44
Sanlando - Hibocs Addition - IDC | 2018177 | IDC | Closed | 430.7607 | 1.08 | 429.6807 | 430.7607 |  |  | Jan: 1.8307; Feb: 1.83; Mar: 3.13; Apr: 422.89 | 429.6807
Sanlando - Wekiva WWTF Imp Eng | 2018109 | Capital Spending | Open | 278820 | 255244 | 23576 | 278820 | 278820 | 44019 | Feb: 2512; May: 3250; Jul: 5250; Sep: 7376; Dec: 5188 | 23576
Sanlando - Wekiva WWTF Imp Eng - Captime | 2018109 | Project Captime | Open | 4886.54 | 1682.68 | 3203.86 | 4886.54 |  |  | Jan: 1184.04; Feb: 100; Mar: 43.28; Apr: 225.28; May: 577.31; Jun: 886.95; Aug: 187 | 3203.86
Sanlando - Wekiva WWTF Imp Eng - IDC | 2018109 | IDC | Open | 28064.2732 | 5930.3 | 22133.9732 | 28064.2732 |  | 662.486 | 1942.2832 | 1961.94 | 1962.26 | 1963.96 | 1992.76 | 1999.43 | 2038.94 | 2040.35 | 2040.35 | 2095.85 | 2095.85 |  | 22133.9732
Sanlando - Wekiva WWTF Improvements | 2019109 | Capital Spending | Open | 484780 |  | 6010201 | 6010201 | 6010201 | 3010000 | Jul: 29380; Aug: 180000; Nov: 50400; Dec: 225000 | 484780
Sanlando - Wekiva WWTF Improvements - Captime | 2019109 | Project Captime | Open | 1777.55 |  | 84658.865 | 84658.865 |  |  | Jul: 787.34; Aug: 390.31; Oct: 374; Nov: 225.9 | 1777.55
Sanlando - Wekiva WWTF Improvements - IDC | 2019109 | IDC | Open | 6951.39 |  | 368159.6018 | 368159.6018 |  | 44209.375 | Jan: 0; Jul: 227.01; Aug: 1584.45; Sep: 1584.45; Oct: 1587.26; Nov: 1968.22 | 6951.39
Sanlando - I&I Investigations Ph 4 | 2018117 | Capital Spending | Closed | 192485.39 | 157318.02 | 35167.37 | 192485.39 | 214150 |  | Jan: 10597.02; Feb: 16648.12; Mar: 6432.72; Apr: 1489.51 | 35167.37
Sanlando - I&I Investigations Ph 4 - Captime | 2018117 | Project Captime | Closed | 2883.36 | 1606.6 | 1276.76 | 2883.36 |  |  | Jan: 346.24; Feb: 64.92; Mar: 735.76; Apr: 129.84 | 1276.76
Sanlando - I&I Investigations Ph 4 - IDC | 2018117 | IDC | Closed | 9008.1758 | 3397.79 | 5610.3858 | 9008.1758 |  | 61674.9 | Jan: 1278.2558; Feb: 1404.02; Mar: 1457.96; Apr: 1470.15 | 5610.3858
Sanlando - I&I Corrections Ph 4 | 1 | Capital Spending | 2020 | 0 |  | 2000000 | 2000000 |  | 2000000 | [12 empty] | 0
Sanlando - I&I Corrections Ph 4 - Captime | 1 | Project Captime | 2020 | 0 |  | 30000 | 30000 | [14 empty] | 0
Sanlando - I&I Corrections Ph 4 - IDC | 1 | IDC | 2020 | 0 |  | 53465.125 | 53465.125 |  |  | Jan: 0 | 0
Sanlando - I&I Corrections Future | 1 | Capital Spending | 2020 | 0 |  | 3000000 | 3000000 | [14 empty] | 0
Sanlando - I&I Corrections Future - Captime | 1 | Project Captime | 2020 | 0 |  | 45000 | 45000 | [14 empty] | 0
Sanlando - I&I Corrections Future - IDC | 1 | IDC | 2020 | 0 |  | 116658.7219 | 116658.7219 |  |  | Jan: 0 | 0
Sanlando - ENG Powerline 14" FM Replacement | 2018098 | Capital Spending | Open | 47091.15 | 33275 | 39725.15 | 73000.15 | 73000 |  | Feb: 4350; Mar: 8525; Jul: 500; Nov: 441.15 | 13816.15
Sanlando - ENG Powerline 14" FM Replacement - Captime | 2018098 | Project Captime | Open | 1410.67 | 100 | 1699.305 | 1799.305 |  |  | 425.28 | 43.28 |  |  | 135.54 | 322.54 |  |  | 135.54 | 45.18 | 90.36 | 112.95 | 1310.67
Sanlando - ENG Powerline 14" FM Replacement - IDC | 2018098 | IDC | Open | 4593.0871 | 839.04 | 5244.7551 | 6083.7951 |  |  | 254.3471 | 287.41 | 351.56 | 351.56 | 352.58 | 355 | 358.77 | 358.77 | 359.79 | 360.13 | 364.13 |  | 3754.0471
Sanlando - Powerline 14" FM Replacement | 1 | Capital Spending | 2020 | 0 |  | 1500000 | 1500000 |  | 1000000 | [12 empty] | 0
Sanlando - Powerline 14" FM Replacement - Captime | 1 | Project Captime | 2020 | 0 |  | 22500 | 22500 | [14 empty] | 0
Sanlando - Powerline 14" FM Replacement - IDC | 1 | IDC | 2020 | 0 |  | 57284.0625 | 57284.0625 |  | 26337.5 | Jan: 0 | 0
Sanlando - UIF CIP Analysis/Modeling | 2019088 | Capital Spending | Open | 76100 | 32550 | 50950 | 83500 | 98280 |  | Jan: 13950; Jul: 7400; Aug: 3700; Sep: 3700; Nov: 7400; Dec: 7400 | 43550
Sanlando - UIF CIP Analysis/Modeling - Captime | 2019088 | Project Captime | Open | 5466.39 |  | 5577.39 | 5577.39 |  |  | Aug: 3720.68; Sep: 1287.63; Oct: 277.36; Nov: 180.72 | 5466.39
Sanlando - UIF CIP Analysis/Modeling - IDC | 2019088 | IDC | Open | 675.61 |  | 2630.0118 | 2630.0118 |  |  | Jul: 55.69; Aug: 111.53; Sep: 149.06; Oct: 151.14; Nov: 208.19 | 675.61
Sanlando - Essex Drive GSM Repair | 2019077 | Capital Spending | Closed | 69121.7 |  | 69121.7 | 69121.7 | 69122 |  | Mar: 69121.7 | 69121.7
Sanlando - Essex Drive GSM Repair - Captime | 2019077 | Project Captime | Closed | 0 |  | 0 | 0 | [14 empty] | 0
Sanlando - Essex Drive GSM Repair - IDC | 2019077 | IDC | Closed | 0 |  | 0 | 0 |  |  | Jan: 0 | 0
Sanlando - Markham Woods WM Repair | 2019075 | Capital Spending | Closed | 108459.13 |  | 108459.13 | 108459.13 | 70010 |  | Mar: 70009.13; Jul: 38450 | 108459.13
Sanlando - Markham Woods WM Repair - Captime | 2019075 | Project Captime | Closed | 0 |  | 0 | 0 | [14 empty] | 0
Sanlando - Markham Woods WM Repair - IDC | 2019075 | IDC | Closed | 0 |  | 0 | 0 |  |  | Jan: 0 | 0
Sanlando - ENG F5/C1/L2 FM | 1 | Capital Spending | 2020 | 0 |  | 260000 | 260000 | [14 empty] | 0
Sanlando - ENG F5/C1/L2 FM - Captime | 1 | Project Captime | 2020 | 0 |  | 3900 | 3900 | [14 empty] | 0
Sanlando - ENG F5/C1/L2 FM - IDC | 1 | IDC | 2020 | 0 |  | 12908.0087 | 12908.0087 |  |  | Jan: 0 | 0
Sanlando - F5 FM | 1 | Capital Spending | 2021 | 0 |  | 1284000 | 1284000 | [14 empty] | 0
Sanlando - F5 FM - Captime | 1 | Project Captime | 2021 | 0 |  | 19260 | 19260 | [14 empty] | 0
Sanlando - F5 FM - IDC | 1 | IDC | 2021 | 0 |  | 34546.004 | 34546.004 |  |  | Jan: 0 | 0
Sanlando - C1 FM | 1 | Capital Spending | 2021 | 0 |  | 1941800 | 1941800 | [14 empty] | 0
Sanlando - C1 FM - Captime | 1 | Project Captime | 2021 | 0 |  | 29127 | 29127 | [14 empty] | 0
Sanlando - C1 FM - IDC | 1 | IDC | 2021 | 0 |  | 52244.1048 | 52244.1048 |  | 42230.3 | Jan: 0 | 0
Sanlando - Powerline WM Replacement | 1 | Capital Spending | 2020 | 0 |  | 1100000 | 1100000 |  | 2140000 | [12 empty] | 0
Sanlando - Powerline WM Replacement - Captime | 1 | Project Captime | 2020 | 0 |  | 16500 | 16500 | [14 empty] | 0
Sanlando - Powerline WM Replacement - IDC | 1 | IDC | 2020 | 0 |  | 29405.8187 | 29405.8187 |  | 62505.2386 | Jan: 0 | 0
Sanlando - Springs WM Replacement | 1 | Capital Spending | N/A | 0 |  | 0 | 0 | [14 empty] | 0
Sanlando - Springs WM Replacement - Captime | 1 | Project Captime | N/A | 0 |  | 0 | 0 | [14 empty] | 0
Sanlando - Springs WM Replacement - IDC | 1 | IDC | N/A | 0 |  | 0 | 0 |  |  | Jan: 0 | 0
Sanlando - L2 FM | 1 | Capital Spending | 2021 | 0 |  | 561496 | 561496 | [14 empty] | 0
Sanlando - L2 FM - Captime | 1 | Project Captime | 2021 | 0 |  | 8422.44 | 8422.44 | [14 empty] | 0
Sanlando - L2 FM - IDC | 1 | IDC | 2021 | 0 |  | 28463.0666 | 28463.0666 |  |  | Jan: 0 | 0
Sanlando - ENG F1/L6/M10 FM | 1 | Capital Spending | 2021 | 0 |  | 238000 | 238000 | [14 empty] | 0
Sanlando - ENG F1/L6/M10 FM - Captime | 1 | Project Captime | 2021 | 0 |  | 3570 | 3570 | [14 empty] | 0
Sanlando - ENG F1/L6/M10 FM - IDC | 1 | IDC | 2021 | 0 |  | 12064.5737 | 12064.5737 |  |  | Jan: 0 | 0
Sanlando - F1 FM | 1 | Capital Spending | 2022 | 0 |  | 513000 | 513000 | [14 empty] | 0
Sanlando - F1 FM - Captime | 1 | Project Captime | 2022 | 0 |  | 7695 | 7695 | [14 empty] | 0
Sanlando - F1 FM - IDC | 1 | IDC | 2022 | 0 |  | 29386.7241 | 29386.7241 |  |  | Jan: 0 | 0
Sanlando - L6 FM | 1 | Capital Spending | 2022 | 0 |  | 630000 | 630000 | [14 empty] | 0
Sanlando - L6 FM - Captime | 1 | Project Captime | 2022 | 0 |  | 9450 | 9450 | [14 empty] | 0
Sanlando - L6 FM - IDC | 1 | IDC | 2022 | 0 |  | 36088.9594 | 36088.9594 |  |  | Jan: 0 | 0
Sanlando - M10 FM | 1 | Capital Spending | 2022 | 0 |  | 1944000 | 1944000 | [14 empty] | 0
Sanlando - M10 FM - Captime | 1 | Project Captime | 2022 | 0 |  | 29160 | 29160 | [14 empty] | 0
Sanlando - M10 FM - IDC | 1 | IDC | 2022 | 0 |  | 111360.2175 | 111360.2175 |  |  | Jan: 0 | 0
Sanlando - ENG L3/L7/M6 FM | 1 | Capital Spending | 2022 | 0 |  | 203000 | 203000 | [14 empty] | 0
Sanlando - ENG L3/L7/M6 FM - Captime | 1 | Project Captime | 2022 | 0 |  | 3045 | 3045 | [14 empty] | 0
Sanlando - ENG L3/L7/M6 FM - IDC | 1 | IDC | 2022 | 0 |  | 11628.6647 | 11628.6647 |  |  | Jan: 0 | 0
Sanlando - L3 FM | 1 | Capital Spending | 2023 | 0 |  | 595800 | 595800 | [14 empty] | 0
Sanlando - L3 FM - Captime | 1 | Project Captime | 2023 | 0 |  | 8937 | 8937 | [14 empty] | 0
Sanlando - L3 FM - IDC | 1 | IDC | 2023 | 0 |  | 34129.8444 | 34129.8444 |  |  | Jan: 0 | 0
Sanlando - L7 FM | 1 | Capital Spending | 2023 | 0 |  | 631200 | 631200 | [14 empty] | 0
Sanlando - L7 FM - Captime | 1 | Project Captime | 2023 | 0 |  | 9468 | 9468 | [14 empty] | 0
Sanlando - L7 FM - IDC | 1 | IDC | 2023 | 0 |  | 36157.7002 | 36157.7002 |  |  | Jan: 0 | 0
Sanlando - M6 FM | 1 | Capital Spending | 2023 | 0 |  | 1246800 | 1246800 | [14 empty] | 0
Sanlando - M6 FM - Captime | 1 | Project Captime | 2023 | 0 |  | 18702 | 18702 | [14 empty] | 0
Sanlando - M6 FM - IDC | 1 | IDC | 2023 | 0 |  | 71421.7691 | 71421.7691 |  |  | Jan: 0 | 0
Sanlando - ENG H2/H1/H3 FM | 1 | Capital Spending | 2023 | 0 |  | 210000 | 210000 | [14 empty] | 0
Sanlando - ENG H2/H1/H3 FM - Captime | 1 | Project Captime | 2023 | 0 |  | 3150 | 3150 | [14 empty] | 0
Sanlando - ENG H2/H1/H3 FM - IDC | 1 | IDC | 2023 | 0 |  | 12029.6531 | 12029.6531 |  |  | Jan: 0 | 0
Sanlando - H2 FM | 1 | Capital Spending | 2024 | 0 |  | 0 | 0 | [14 empty] | 0
Sanlando - H2 FM - Captime | 1 | Project Captime | 2024 | 0 |  | 0 | 0 | [14 empty] | 0
Sanlando - H2 FM - IDC | 1 | IDC | 2024 | 0 |  | 0 | 0 |  |  | Jan: 0 | 0
Sanlando - H1 FM | 1 | Capital Spending | 2024 | 0 |  | 0 | 0 | [14 empty] | 0
Sanlando - H1 FM - Captime | 1 | Project Captime | 2024 | 0 |  | 0 | 0 | [14 empty] | 0
Sanlando - H1 FM - IDC | 1 | IDC | 2024 | 0 |  | 0 | 0 |  |  | Jan: 0 | 0
Sanlando - H3 FM | 1 | Capital Spending | 2024 | 0 |  | 0 | 0 | [14 empty] | 0
Sanlando - H3 FM - Captime | 1 | Project Captime | 2024 | 0 |  | 0 | 0 | [14 empty] | 0
Sanlando - H3 FM - IDC | 1 | IDC | 2024 | 0 |  | 0 | 0 |  |  | Jan: 0 | 0
Sanlando - ENG H4/C8/M1 FM | 1 | Capital Spending | 2024 | 0 |  | 0 | 0 | [14 empty] | 0
Sanlando - ENG H4/C8/M1 FM - Captime | 1 | Project Captime | 2024 | 0 |  | 0 | 0 | [14 empty] | 0
Sanlando - ENG H4/C8/M1 FM - IDC | 1 | IDC | 2024 | 0 |  | 0 | 0 |  |  | Jan: 0 | 0
Sanlando - WM & Service Line Replacement | 1 | Capital Spending | 2020 | 0 |  | 4000000 | 4000000 | [14 empty] | 0
Sanlando - WM & Service Line Replacement - Captime | 1 | Project Captime | 2020 | 0 |  | 60000 | 60000 | [14 empty] | 0
Sanlando - WM & Service Line Replacement - IDC | 1 | IDC | 2020 | 0 |  | 202765.9439 | 202765.9439 |  |  | Jan: 0 | 0
Sanlando - Well Panel Replacements | 1 | Capital Spending | 2020 | 0 |  | 175000 | 175000 | [14 empty] | 0
Sanlando - Well Panel Replacements - Captime | 1 | Project Captime | 2020 | 0 |  | 2625 | 2625 | [14 empty] | 0
Sanlando - Well Panel Replacements - IDC | 1 | IDC | 2020 | 0 |  | 4678.1984 | 4678.1984 |  |  | Jan: 0 | 0
Sanlando - E.E. Williamson Utility Relocations | 1 | Capital Spending | 2020 | 0 |  | 200000 | 200000 | [14 empty] | 0
Sanlando - E.E. Williamson Utility Relocations - Captime | 1 | Project Captime | 2020 | 0 |  | 3000 | 3000 | [14 empty] | 0
Sanlando - E.E. Williamson Utility Relocations - IDC | 1 | IDC | 2020 | 0 |  | 3055.15 | 3055.15 |  |  | Jan: 0 | 0
Sanlando - GST Deficiency Corrections | 1 | Capital Spending | 2020 | 0 |  | 100000 | 100000 | [14 empty] | 0
Sanlando - GST Deficiency Corrections - Captime | 1 | Project Captime | 2020 | 0 |  | 1500 | 1500 | [14 empty] | 0
Sanlando - GST Deficiency Corrections - IDC | 1 | IDC | 2020 | 0 |  | 1527.575 | 1527.575 |  |  | Jan: 0 | 0
Sanlando - Lift Station Mechanical Rehab | 1 | Capital Spending | 2020 | 0 |  | 340000 | 340000 | [14 empty] | 0
Sanlando - Lift Station Mechanical Rehab - Captime | 1 | Project Captime | 2020 | 0 |  | 5100 | 5100 | [14 empty] | 0
Sanlando - Lift Station Mechanical Rehab - IDC | 1 | IDC | 2020 | 0 |  | 9089.0713 | 9089.0713 |  |  | Jan: 0 | 0
Sanlando - | 1 | Capital Spending | N/A | 0 |  | 0 | 0 | [14 empty] | 0
Sanlando - - Captime | 1 | Project Captime | N/A | 0 |  | 0 | 0 | [14 empty] | 0
Sanlando - - IDC | 1 | IDC | N/A | 0 |  | 0 | 0 |  |  | Jan: 0 | 0
Sanlando - G/L Spending |  | GL Spending |  | 982223.02 |  | 5124013.75 | 5124013.75 |  | 790000 | 85059.43 | 120353.81 | 92634.8 | 56999.2 | 130800.88 | 110526.27 | 21000.45 | 117537.13 | -13851.64 | 157149.3 | 28787.22 | 75226.17 | 982223.02
Sanlando - Captime |  | GL Captime |  |  |  | 660545.1753 | 660545.1753 |  | 267302.1042 | 13633.2 | 14187.64 | 12731.84 | 12664.64 | 11937.97 | 6647.79 | 23538.78 | 15632.28 | 7929.09 | 12108.24 | 14073.57 | 10470.45 | 155555.49
Sanlando - Cap Suspense |  | Cap Suspense | [19 empty] | 0
Sandalhaven - EWD Bulk Sewer Capacity Payment | 1 | Capital Spending | N/A | 0 |  | 0 | 0 | [14 empty] | 0
Sandalhaven - EWD Bulk Sewer Capacity Payment - Captime | 1 | Project Captime | N/A | 0 |  | 0 | 0 | [14 empty] | 0
Sandalhaven - EWD Bulk Sewer Capacity Payment - IDC | 1 | IDC | N/A | 0 |  | 0 | 0 |  |  | Jan: 0 | 0
Sandalhaven - L/S RTU Installation | 1 | Capital Spending | 2020 | 0 |  | 130000 | 130000 |  | 130000 | [12 empty] | 0
Sandalhaven - L/S RTU Installation - Captime | 1 | Project Captime | 2020 | 0 |  | 1950 | 1950 | [14 empty] | 0
Sandalhaven - L/S RTU Installation - IDC | 1 | IDC | 2020 | 0 |  | 1985.8475 | 1985.8475 |  | 1956.5 | Jan: 0 | 0
Sandalhaven - Smoke Testing/I&I Investigation | 1 | Capital Spending | 2020 | 0 |  | 60000 | 60000 |  | 150000 | [12 empty] | 0
Sandalhaven - Smoke Testing/I&I Investigation - Captime | 1 | Project Captime | 2020 | 0 |  | 900 | 900 | [14 empty] | 0
Sandalhaven - Smoke Testing/I&I Investigation - IDC | 1 | IDC | 2020 | 0 |  | 916.545 | 916.545 |  | 1505 | Jan: 0 | 0
Sandalhaven - Leverocks L/S 3 | 2019081 | Capital Spending | Closed | 91249 |  | 91249 | 91249 | 88000 | 0 | Jul: 91141; Oct: 108 | 91249
Sandalhaven - Leverocks L/S 3 - Captime | 2019081 | Project Captime | Closed | 722.88 |  | 722.88 | 722.88 |  |  | Jun: 722.88 | 722.88
Sandalhaven - Leverocks L/S 3 - IDC | 2019081 | IDC | Closed | 1388 |  | 1388 | 1388 |  |  | Jan: 0; Jun: 5.44; Jul: 691.28; Aug: 691.28 | 1388
Sandalhaven - G/L Spending |  | GL Spending |  | 67221.61 |  | 318239.23 | 318239.23 |  | 36000 |  | 575.1 | 36770.21 | 2597.43 | 12515.09 | 1258.49 | 1438.53 | 5603.67 | 3120.05 |  | 1655.7 | 1687.34 | 67221.61
Sandalhaven - Captime |  | GL Captime |  |  |  | 48888.4505 | 48888.4505 |  | 12670.0849 |  | 346.24 | 935.76 | 649.2 | 371.08 |  |  | 542.16 | 361.44 |  | 180.72 | 451.8 | 3838.4
Sandalhaven - Cap Suspense |  | Cap Suspense
Labrador - Engineering WWTP Master Plan | 1 | Capital Spending | 2020 | 0 |  | 45000 | 45000 | [14 empty] | 0
Labrador - Engineering WWTP Master Plan - Captime | 1 | Project Captime | 2020 | 0 |  | 675 | 675 | [14 empty] | 0
Labrador - Engineering WWTP Master Plan - IDC | 1 | IDC | 2020 | 0 |  | 687.4087 | 687.4087 |  |  | Jan: 0 | 0
Labrador - Construction WWTP Master Plan | 1 | Capital Spending | 2020 | 0 |  | 0 | 0 | [14 empty] | 0
Labrador - Construction WWTP Master Plan - Captime | 1 | Project Captime | 2020 | 0 |  | 0 | 0 | [14 empty] | 0
Labrador - Construction WWTP Master Plan - IDC | 1 | IDC | 2020 | 0 |  | 0 | 0 |  |  | Jan: 0 | 0
Labrador - FM | 1 | Capital Spending | 2023 | 0 |  | 447476 | 447476 | [14 empty] | 0
Labrador - FM - Captime | 1 | Project Captime | 2023 | 0 |  | 6712.14 | 6712.14 | [14 empty] | 0
Labrador - FM - IDC | 1 | IDC | 2023 | 0 |  | 25633.2432 | 25633.2432 |  |  | Jan: 0 | 0
Labrador - G/L Spending |  | GL Spending |  | 68249.01 |  | 277430.36 | 277430.36 |  | 35000 | 2964.17 | 2666.4 | 1884.95 | 8521.75 | 0.94 | 4040.24 | 1288.64 | 6483.58 | 6916.65 | 10359.66 | 22348.8 | 773.23 | 68249.01
Labrador - Captime |  | GL Captime |  |  |  | 124420.618 | 124420.618 |  | 30008.0959 | 129.84 | 779.04 | 1203.64 | 2918.44 | 621.12 | 2074.97 | 1084.32 | 813.24 | 1807.2 | 4382.46 | 1298.93 | 609.93 | 17723.13
Labrador - Cap Suspense |  | Cap Suspense |  |  | 1236.06 | 39400 | 40636.06 |  |  | Apr: 10250; May: 10250; Aug: 10250; Nov: 8650 | 39400
Pennbrooke - WTP Upgrade | 1 | Capital Spending | N/A | 0 |  | 0 | 0 | [14 empty] | 0
Pennbrooke - WTP Upgrade - Captime | 1 | Project Captime | N/A | 0 |  | 0 | 0 | [14 empty] | 0
Pennbrooke - WTP Upgrade - IDC | 1 | IDC | N/A | 0 |  | 0 | 0 |  |  | Jan: 0 | 0
Pennbrooke - L/S RTU Installation | 2019079 | Capital Spending | Closed | 56344.48 |  | 56344.48 | 56344.48 | 56686 | 70000 | Aug: 31507.51; Oct: 24836.97 | 56344.48
Pennbrooke - L/S RTU Installation - Captime | 2019079 | Project Captime | Closed | 0 |  | 0 | 0 | [14 empty] | 0 | bar: Nov to Dec
Pennbrooke - L/S RTU Installation - IDC | 2019079 | IDC | Closed | 474.18 |  | 474.18 | 474.18 |  | 1053.5 | Jan: 0; Aug: 237.09; Sep: 237.09 | 474.18
Pennbrooke - G/L Spending |  | GL Spending |  | 113282.87 |  | 489809.3 | 489809.3 |  | 75000 | 1662.29 | 10001.84 | 20529.29 | 12297.37 | 13030.29 | 11956.91 | 1368.62 | 6591.79 | 3745 | 5427.6 | 373.1 | 26298.77 | 113282.87
Pennbrooke - Captime |  | GL Captime |  |  |  | 183628.1191 | 183628.1191 |  | 44982.0301 | 1146.92 | 952.16 | 2250.56 | 4091.06 | 993.96 | 3354.62 | 3117.42 | 3264.26 | 180.72 | 993.96 | 564.75 | 2778.57 | 23688.96
Pennbrooke - Cap Suspense |  | Cap Suspense | [19 empty] | 0
FL Cost Center - 15KW Generator Fleet | 2018151 | Capital Spending | Closed | 230092.57 |  | 230092.57 | 230092.57 | 240400 | 92000 | Jan: 42352; Mar: 27624.8; Apr: 9866; May: 36534.62; Jun: 51283.26; Sep: 62431.89 | 230092.57
FL Cost Center - 15KW Generator Fleet - Captime | 2018151 | Project Captime | Open | 6669.16 | 151.48 | 6517.68 | 6669.16 |  |  | 143.28 | 320.92 | 200 | 143.28 | 847.02 | 371.08 | 1762.02 | 2504.18 | 225.9 |  |  |  | 6517.68
FL Cost Center - 15KW Generator Fleet - IDC | 2018151 | IDC | Open | 7833.9869 | 2.28 | 7831.7069 | 7833.9869 |  | 752.5 | 320.9169 |  | 530.3 | 605.62 | 886.92 | 1275.61 | 1288.87 | 1307.72 | 1615.75 |  |  |  | 7831.7069
FL Cost Center - AMI Meters | 1 | Capital Spending | 2020 | 0 |  | 7000000 | 7000000 | [14 empty] | 0
FL Cost Center - AMI Meters - Captime | 1 | Project Captime | 2020 | 0 |  | 105000 | 105000 | [14 empty] | 0
FL Cost Center - AMI Meters - IDC | 1 | IDC | 2020 | 0 |  | 353795.1033 | 353795.1033 | [14 empty] | 0
FL Cost Center - Regional Office Modifications | 1 | Capital Spending | 2020 | 0 |  | 0 | 0 | [14 empty] | 0
FL Cost Center - Regional Office Modifications - Captime | 1 | Project Captime | 2020 | 0 |  | 0 | 0 | [14 empty] | 0
FL Cost Center - Regional Office Modifications - IDC | 1 | IDC | 2020 | 0 |  | 0 | 0 |  | 42290.5 | Jan: 0 | 0
FL Cost Center - Fleet Replacements | 1 | Capital Spending | 2019 |  |  | 1888892.71 | 1888892.71 |  | 537500 | 178000.14 |  | 61796.26 | 40317.82 | 43.28 | -165.67 | -60 | 206788.36 |  | 2477.52 | -305 |  | 488892.71
FL Cost Center - G/L Spending |  | GL Spending |  | 42034.65 |  | 251216 | 251216 |  | 50000 |  |  | 818.13 | 12015 |  | 982.82 |  | 7497 | 1281.86 | 2685.91 | 3479 | 13274.93 | 42034.65
FL Cost Center - Captime |  | GL Captime |  |  |  | 1565.37 | 1565.37 |  |  | Feb: 605.92; Mar: 43.28; Apr: 259.68; Sep: 656.49 | 1565.37
FL Cost Center - Cap Suspense |  | Cap Suspense |  |  | 33242.48 | 14688.08 | 47930.56 |  |  | Jan: 13950; Feb: 692.48; Jun: 361.44; Aug: 361.44; Sep: -677.28 | 14688.08

## 2019 Var
BUDGET vs FORECAST | [6 empty] | BUDGET |  |  |  |  | FORECAST | 0
|  |  | 3787800.9425 | 4736709.4245 | 3809438.0152 | 3077000.01 | 15575181.669 | 2479480.8874 | 2043239.95 | 2483300.32 | 2500271.91 | 9506293.0674 | 6068888.6016
Project | Project # | Type | Q1 | Q2 | Q3 | Q4 | 2019 BUDGET | Q1 | Q2 | Q3 | Q4 | 2019 FORECAST | Variance
Tierra Verde - ENG Lift Station #4 Forcemain | 2019086 | Capital Spending | 220000 | 175000 | 0 | 0 | 375000 | 44200 | 45742 | 9000 | 18750 | 117692 | 257308
Tierra Verde - ENG Lift Station #4 Forcemain - Captime | 2019086 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 361.44 | 250 | 200 | 811.44 | -811.44
Tierra Verde - ENG Lift Station #4 Forcemain - IDC | 2019086 | IDC | 3842.94 | 10158.75 | 5797.1628 | 0 | 10158.75 | 170.7422 | 5.44 | 2179.69 | 1657.81 | 4013.6822 | 6145.0678
Tierra Verde - FM / GSM Relocation | 2019087 | Capital Spending | [5 empty] | 0 | 0 | 289887.6 | 151306.14 | 441193.74 | -441193.74
Tierra Verde - FM / GSM Relocation - Captime | 2019087 | Project Captime | [5 empty] | 0 | 461.44 | 3144.54 | 1665.04 | 5271.02 | -5271.02
Tierra Verde - FM / GSM Relocation - IDC | 2019087 | IDC | [5 empty] | 0 | 3.47 | 5830.63 | 5874.67 | 11708.77 | -11708.77
Tierra Verde - Liftstation #4 Replacement | 1 | Capital Spending | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Tierra Verde - Liftstation #4 Replacement - Captime | 1 | Project Captime | [5 empty] | 0 | 0 | 0 | 100 | 100 | -100
Tierra Verde - Liftstation #4 Replacement - IDC | 1 | IDC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Tierra Verde - Redzone I&I Investigation | 2018116 | Capital Spending | 110300 | 125000 | 125000 |  | 250000 | 75801.2 | 4320 | 0 | 2521 | 82642.2 | 167357.8
Tierra Verde - Redzone I&I Investigation - Captime | 2018116 | Project Captime | 0 | 0 | 0 | 0 |  | 10454.4 | 216.4 | 0 | 300 | 10970.8 | -10970.8
Tierra Verde - Redzone I&I Investigation - IDC | 2018116 | IDC | 1366.18 | 6584.375 | 3689.2379 | 0 | 6584.375 | 762.18 | 1366.18 | 0 | 0 | 2128.36 | 4456.015
Tierra Verde - G/L Spending |  | GL Spending | 7500 | 7500 | 7500 | 7500 | 30000 | 23366.98 | -12862.67 | 0 | 4355.35 | 14859.66 | 15140.34
Tierra Verde - Captime |  | GL Captime | 0 | 0 | 0 | 0 | 3167.5212 | 1441.68 | 1767.36 | 2100.87 | 1400.58 | 6710.49 | -3542.9688
Tierra Verde - Cap Suspense |  | Cap Suspense | [5 empty] | 0 | 0 | 9000 | 0 | 9000 | -9000
Lake Placid - G/L Spending |  | GL Spending | 3750 | 3750 | 3750 | 3750 | 15000 | 650 | 6883.42 | 2102.82 | 4750.89 | 14387.13 | 612.87
Lake Placid - Captime |  | GL Captime | 0 | 0 | 0 | 0 | 1583.7606 | 432.8 | 617.32 | 1084.32 | 225.9 | 2360.34 | -776.5794
Lake Placid - Cap Suspense |  | Cap Suspense | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Longwood - Shadow Hills WWTF Demolition | 2019002 | Capital Spending | 32000 |  |  |  |  | 33600 | 0 | 0 | 0 | 33600 | -33600
Longwood - Shadow Hills WWTF Demolition - Captime | 2019002 | Project Captime | 0 | 0 | 0 | 0 |  | 1506.6 | 0 | 0 | 0 | 1506.6 | -1506.6
Longwood - Shadow Hills WWTF Demolition - IDC | 2019002 | IDC | 0 | 0 | 555.99 | 0 |  | 555.99 | 0 | 0 | 0 | 555.99 | -555.99
Longwood - L/S RTUs | 1 | Capital Spending |  |  | 130000 |  | 130000 | 0 | 0 | 68207.95 | 0 | 68207.95 | 61792.05
Longwood - L/S RTUs - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 90.36 | 90.36 | -90.36
Longwood - L/S RTUs - IDC | 1 | IDC | 2054.4 | 1956.5 | 4012.8734 | 0 | 1956.5 | 0 | 0 | 1026.52 | 1027.88 | 2054.4 | -97.9
Longwood - G/L Spending |  | GL Spending | 11000 | 11000 | 11000 | 11000 | 44000 | 14574.03 | 2637.5 | 27011.99 | 320 | 44543.52 | -543.52
Longwood - Captime |  | GL Captime | 0 | 0 | 0 | 0 | 11807.48 | 446.24 | 519.57 | 835.83 | 542.16 | 2343.8 | 9463.68
Longwood - Cap Suspense |  | Cap Suspense | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Cypress Lakes - Smoke Testing/I&I Investigation | 1 | Capital Spending | 0 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
Cypress Lakes - Smoke Testing/I&I Investigation - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Cypress Lakes - Smoke Testing/I&I Investigation - IDC | 1 | IDC | 0 | 752.5 | 0 | 0 | 752.5 | 0 | 0 | 0 | 0 | 0 | 752.5
Cypress Lakes - Filter Replacement | 1 | Capital Spending |  |  | 50000 | 0.01 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
Cypress Lakes - Filter Replacement - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Cypress Lakes - Filter Replacement - IDC | 1 | IDC | 0 | 752.5 | 0 | 0 | 752.5 | 0 | 0 | 0 | 0 | 0 | 752.5
Cypress Lakes - Rehab L/S 1 | 1 | Capital Spending | 85000 | 0 | 0 | 0 | 85000 | 0 | 0 | 0 | 77490 | 77490 | 7510
Cypress Lakes - Rehab L/S 1 - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 3001.16 | 3001.16 | -3001.16
Cypress Lakes - Rehab L/S 1 - IDC | 1 | IDC | 51.71 | 1279.25 | 112.5945 | 0 | 1279.25 | 0 | 0 | 0 | 51.71 | 51.71 | 1227.54
Cypress Lakes - Disinfection Upgrade | 1 | Capital Spending |  |  |  | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
Cypress Lakes - Disinfection Upgrade - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Cypress Lakes - Disinfection Upgrade - IDC | 1 | IDC | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Cypress Lakes - G/L Spending |  | GL Spending | 18750 | 18750 | 18750 | 18750 | 75000 | 43731.72 | 14719.66 | 16581.62 | 25366.51 | 100399.51 | -25399.51
Cypress Lakes - Captime |  | GL Captime | 0 | 0 | 0 | 0 | 16671.1644 | 1168.56 | 5686.19 | 3375.55 | 5737.86 | 15968.16 | 703.0044
Cypress Lakes - Cap Suspense |  | Cap Suspense | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Eagle Ridge - Lift Station RTU Improvements | 1 | Capital Spending | 223000 |  |  |  | 200000 | 29860 | 18055.16 | 115881.98 | 0 | 163797.14 | 36202.86
Eagle Ridge - Lift Station RTU Improvements - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 700 | 446.24 | 0 | 1146.24 | -1146.24
Eagle Ridge - Lift Station RTU Improvements - IDC | 1 | IDC | 5552.66 | 3010 | 8279.1831 | 0 | 3010 | 224.7 | 1097.49 | 1972.77 | 2482.4 | 5777.36 | -2767.36
Eagle Ridge - ER North and South Plant Rehab | 1 | Capital Spending | [5 empty] | 0 | 97827.33 | 31414.01 | 89753.95 | 218995.29 | -218995.29
Eagle Ridge - ER North and South Plant Rehab - Captime | 1 | Project Captime | [5 empty] | 0 | 1046.24 | 998.44 | 1700.58 | 3745.26 | -3745.26
Eagle Ridge - ER North and South Plant Rehab - IDC | 1 | IDC | [5 empty] | 0 | 2097.04 | 2717.43 | 1609.85 | 6424.32 | -6424.32
Eagle Ridge - ENG WWTP Variance & LDO | 1 | Capital Spending | 75000 | 50000 |  |  | 125000 | 0 | 0 | 98433.9 | 6204.33 | 104638.23 | 20361.77
Eagle Ridge - ENG WWTP Variance & LDO - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 979.48 | 900 | 1879.48 | -1879.48
Eagle Ridge - ENG WWTP Variance & LDO - IDC | 1 | IDC | 1543.73 | 752.5 | 3271.1613 | 0 | 752.5 | 0 | 0 | 2.24 | 1541.49 | 1543.73 | -791.23
Eagle Ridge - WWTP Tree Removal / Fencing | 2019175 | Capital Spending | [5 empty] | 0 | 0 | 0 | 116876 | 116876 | -116876
Eagle Ridge - WWTP Tree Removal / Fencing - Captime | 2019175 | Project Captime | [5 empty] | 0 | 0 | 0 | 361.44 | 361.44 | -361.44
Eagle Ridge - WWTP Tree Removal / Fencing - IDC | 2019175 | IDC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Eagle Ridge - Replace Reject Pond Liner | 1 | Capital Spending |  | 200000 |  |  | 200000 | 0 | 0 | 0 | 257795.93 | 257795.93 | -57795.93
Eagle Ridge - Replace Reject Pond Liner - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5242.1 | 5242.1 | -5242.1
Eagle Ridge - Replace Reject Pond Liner - IDC | 1 | IDC | 1196.71 | 3010 | 3863.2165 | 0 | 3010 | 0 | 0 | 0 | 1196.71 | 1196.71 | 1813.29
Eagle Ridge - I&I Investigation | 1 | Capital Spending |  |  | 50000 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
Eagle Ridge - I&I Investigation - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Eagle Ridge - I&I Investigation - IDC | 1 | IDC | 0 | 752.5 | 0 | 0 | 752.5 | 0 | 0 | 0 | 0 | 0 | 752.5
Eagle Ridge - L/S ER 3 | 1 | Capital Spending | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Eagle Ridge - L/S ER 3 - Captime | 1 | Project Captime | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Eagle Ridge - L/S ER 3 - IDC | 1 | IDC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Eagle Ridge - G/L Spending |  | GL Spending | 25000 | 25000 | 25000 | 25000 | 100000 | 30281.29 | 61556.85 | 145181.51 | 68628.77 | 305648.42 | -205648.42
Eagle Ridge - Captime |  | GL Captime | 0 | 0 | 0 | 0 | 23339.6301 | 24698.08 | 5694.02 | 10216.72 | 6957.72 | 47566.54 | -24226.9099
Eagle Ridge - Cap Suspense |  | Cap Suspense | [5 empty] | -7670.64 | 23020.18 | -83687.22 | 0 | -68337.68 | 68337.68
Mid-County - WWTP Improvements - Engineering | 1 | Capital Spending | [5 empty] | 0 | 0 | 65210.7 | 49820 | 115030.7 | -115030.7
Mid-County - WWTP Improvements - Engineering - Captime | 1 | Project Captime | [5 empty] | 0 | 0 | 2161.44 | 1051.8 | 3213.24 | -3213.24
Mid-County - WWTP Improvements - Engineering - IDC | 1 | IDC | [5 empty] | 0 | 0 | 13.55 | 1553.07 | 1566.62 | -1566.62
Mid-County - WWTP Improvements -Construction | 1 | Capital Spending |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Mid-County - WWTP Improvements -Construction - Captime | 1 | Project Captime |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Mid-County - WWTP Improvements -Construction - IDC | 1 | IDC |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Mid-County - I&I Improvements | 1 | Capital Spending | 75000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Mid-County - I&I Improvements - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Mid-County - I&I Improvements - IDC | 1 | IDC | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Mid-County - Spanish Acres GSM Rehab | 2019001 | Capital Spending | 34000 |  |  |  |  | 95009.92 | 0 | 0 | 10.64 | 95020.56 | -95020.56
Mid-County - Spanish Acres GSM Rehab - Captime | 2019001 | Project Captime | 0 | 0 | 0 | 0 |  | 1062.64 | 200 | 0 | 0 | 1262.64 | -1262.64
Mid-County - Spanish Acres GSM Rehab - IDC | 2019001 | IDC | 5068.23 | 0 | 5802.19 | 0 |  | 733.96 | 2170.35 | 2173.35 | 724.53 | 5802.19 | -5802.19
Mid-County - LS #4 / #7 Gensets | [7 empty] | 0 | 0 | 0 | 71458.55 | 71458.55 | -71458.55
Mid-County - LS #4 / #7 Gensets - Captime | [7 empty] | 0 | 0 | 0 | 500 | 500 | -500
Mid-County - LS #4 / #7 Gensets - IDC | [7 empty] | 0 | 0 | 0 | 568.95 | 568.95 | -568.95
Mid-County - LS RTU | 1 | Capital Spending | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Mid-County - LS RTU - Captime | 1 | Project Captime | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Mid-County - LS RTU - IDC | 1 | IDC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Mid-County - G/L Spending |  | GL Spending | 50000 | 50000 | 50000 | 50000 | 200000 | 25121.99 | 44369.99 | 33797.81 | 201361.13 | 304650.92 | -104650.92
Mid-County - Captime |  | GL Captime | 0 | 0 | 0 | 0 | 33342.3287 | 11011.12 | 15472.06 | 9513.41 | 13013.35 | 49009.94 | -15667.6113
Mid-County - Cap Suspense |  | Cap Suspense | [5 empty] | 67670.8 | 0 | -52394 | 0 | 15276.8 | -15276.8
LUSI - Eng - 2nd Lower Floridan Well | 1 | Capital Spending | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
LUSI - Eng - 2nd Lower Floridan Well - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
LUSI - Eng - 2nd Lower Floridan Well - IDC | 1 | IDC | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
LUSI - Feasibility Study & Land Purchase for NE WTP | 1 | Capital Spending | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
LUSI - Feasibility Study & Land Purchase for NE WTP - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
LUSI - Feasibility Study & Land Purchase for NE WTP - IDC | 1 | IDC | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
LUSI - Anderson Hill WM Relocation | 2019018 | Capital Spending | [5 empty] | 45770.09 | 0 | 26143.64 | 0 | 71913.73 | -71913.73
LUSI - Anderson Hill WM Relocation - Captime | 2019018 | Project Captime | [5 empty] | 779.04 | 190.36 | 993.96 | 0 | 1963.36 | -1963.36
LUSI - Anderson Hill WM Relocation - IDC | 2019018 | IDC | [5 empty] | 698.28 | 1053.77 | 0 | 0 | 1752.05 | -1752.05
LUSI - LUSI North TTHM HAA5 Remediation | 1 | Capital Spending |  |  |  | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000
LUSI - LUSI North TTHM HAA5 Remediation - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
LUSI - LUSI North TTHM HAA5 Remediation - IDC | 1 | IDC | 0 | 4515 | 0 | 0 | 4515 | 0 | 0 | 0 | 0 | 0 | 4515
LUSI - LG WTP Improvements Construction | 2018153 | Capital Spending | 427970.16 | 700000 |  |  | 1065000 | 551032.8 | 574647.17 | 138164.2 | 0 | 1263844.17 | -198844.17
LUSI - LG WTP Improvements Construction - Captime | 2018153 | Project Captime | 0 | 0 | 0 | 0 |  | 14854.94 | 23136.46 | 7394.72 | 0 | 45386.12 | -45386.12
LUSI - LG WTP Improvements Construction - IDC | 2018153 | IDC | 35861.65 | 29987.125 | 45405.2176 | 0 | 29987.125 | 9543.5676 | 25637.41 | 10224.24 | 0 | 45405.2176 | -15418.0926
LUSI - Eng - 561 WTP Wellsite & Land | 1 | Capital Spending |  |  |  | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
LUSI - Eng - 561 WTP Wellsite & Land - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
LUSI - Eng - 561 WTP Wellsite & Land - IDC | 1 | IDC | 0 | 1505 | 0 | 0 | 1505 | 0 | 0 | 0 | 0 | 0 | 1505
LUSI - Crescent Bay Raw WM | 1 | Capital Spending | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
LUSI - Crescent Bay Raw WM - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
LUSI - Crescent Bay Raw WM - IDC | 1 | IDC | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
LUSI - PLC Replacements | 1 | Capital Spending | 34956.72 |  |  |  |  | 0 | 37764.8 | 0 | 0 | 37764.8 | -37764.8
LUSI - PLC Replacements - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 1666.28 | 0 | 0 | 0 | 1666.28 | -1666.28
LUSI - PLC Replacements - IDC | 1 | IDC | 298.12 | 0 | 315.1939 | 0 |  | 17.0739 | 298.12 | 0 | 0 | 315.1939 | -315.1939
LUSI - Barrington WWTP Cap Improvements | 1 | Capital Spending |  | 75000 | 150000 |  | 225000 | 0 | 0 | 0 | 0 | 0 | 225000
LUSI - Barrington WWTP Cap Improvements - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
LUSI - Barrington WWTP Cap Improvements - IDC | 1 | IDC | 0 | 5079.375 | 0 | 0 | 5079.375 | 0 | 0 | 0 | 0 | 0 | 5079.375
LUSI - Sewer Jetter Trailer | 1 | Capital Spending |  | 50000 |  |  | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
LUSI - Sewer Jetter Trailer - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
LUSI - Sewer Jetter Trailer - IDC | 1 | IDC | 0 | 752.5 | 0 | 0 | 752.5 | 0 | 0 | 0 | 0 | 0 | 752.5
LUSI - LG Centrifuge | 1 | Capital Spending | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
LUSI - LG Centrifuge - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
LUSI - LG Centrifuge - IDC | 1 | IDC | 0 | 13168.75 | 0 | 0 | 13168.75 | 0 | 0 | 0 | 0 | 0 | 13168.75
LUSI - G/L Spending |  | GL Spending | 175000 | 175000 | 175000 | 175000 | 700000 | 138586.57 | 217965.37 | 265637.09 | 243635.82 | 865824.85 | -165824.85
LUSI - Captime |  | GL Captime | 0 | 0 | 0 | 0 | 266738.6299 | 54280.98 | 54042.6 | 68571.99 | 64572.75 | 241468.32 | 25270.3099
LUSI - Cap Suspense |  | Cap Suspense | [5 empty] | 0 | 0 | 5000 | 13450 | 18450 | -18450
UIF - Timing Adjustments |  | Timing Adjustment |  | -250000 | -500000 | -500000 | -1000000 | 0 | 0 | 0 | 0 | 0 | -1000000
UIF - Timing Adjustments - IDC |  | IDC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
UIF - AMP Implementation | 1 | Capital Spending | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
UIF - AMP Implementation - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
UIF - AMP Implementation - IDC | 1 | IDC | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
UIF - Jansen WTP Gen Replacement | 2017168 | Capital Spending | 24735.08 |  |  |  |  | 14141.9 | 0 | 0 | 0 | 14141.9 | -14141.9
UIF - Jansen WTP Gen Replacement - Captime | 2017168 | Project Captime | 0 | 0 | 0 | 0 |  | 1011.16 | 0 | 0 | 0 | 1011.16 | -1011.16
UIF - Jansen WTP Gen Replacement - IDC | 2017168 | IDC | 0 | 0 | 2259.75 | 0 |  | 2259.75 | 0 | 0 | 0 | 2259.75 | -2259.75
UIF - Jansen AC Main Replacement | 1 | Capital Spending | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
UIF - Jansen AC Main Replacement - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
UIF - Jansen AC Main Replacement - IDC | 1 | IDC | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
UIF - Little Wekiva Generator | 1 | Capital Spending |  | 100000 |  |  | 100000 | 0 | 0 | 4600 | 1800 | 6400 | 93600
UIF - Little Wekiva Generator - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 112.95 | 45.18 | 158.13 | -158.13
UIF - Little Wekiva Generator - IDC | 1 | IDC | 189.86 | 1505 | 275.0204 | 0 | 1505 | 0 | 0 | 104.7 | 85.16 | 189.86 | 1315.14
UIF - Park Ridge Generator | 1 | Capital Spending |  | 100000 |  |  | 100000 | 0 | 0 | 4140 | 2260 | 6400 | 93600
UIF - Park Ridge Generator - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 67.77 | 0 | 67.77 | -67.77
UIF - Park Ridge Generator - IDC | 1 | IDC | 168.54 | 1505 | 252.6469 | 0 | 1505 | 0 | 0 | 94.98 | 73.56 | 168.54 | 1336.46
UIF - NW Bridge Interconnect | 1 | Capital Spending | 82000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
UIF - NW Bridge Interconnect - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
UIF - NW Bridge Interconnect - IDC | 1 | IDC | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
UIF - Seminole L/S RTUs | 1 | Capital Spending |  | 100000 |  |  | 100000 | 0 | 0 | 52479.19 | 0 | 52479.19 | 47520.81
UIF - Seminole L/S RTUs - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 100 | 0 | 0 | 100 | -100
UIF - Seminole L/S RTUs - IDC | 1 | IDC | 1584.89 | 1505 | 3075.4753 | 0 | 1505 | 0 | 1.5 | 792.07 | 791.32 | 1584.89 | -79.89
UIF - ST - Smoke Testing/I&I Investigation | 1 | Capital Spending | 50000 |  |  |  | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
UIF - ST - Smoke Testing/I&I Investigation - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
UIF - ST - Smoke Testing/I&I Investigation - IDC | 1 | IDC | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
UIF - ENG - ST Chlorine Dioxide Pilot Study | 2019174 | Capital Spending | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
UIF - ENG - ST Chlorine Dioxide Pilot Study - Captime | 2019174 | Project Captime | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
UIF - ENG - ST Chlorine Dioxide Pilot Study - IDC | 2019174 | IDC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
UIF - Golden Hills WM Relocation NW 78th Ave | 1 | Capital Spending | 2019 |  |  |  |  | 0 | 0 | 2000 | 111634.86 | 113634.86 | -113634.86
UIF - Golden Hills WM Relocation NW 78th Ave - Captime | 1 | Project Captime | 2019 |  |  |  |  | 0 | 0 | 190.36 | 9655.57 | 9845.93 | -9845.93
UIF - Golden Hills WM Relocation NW 78th Ave - IDC | 1 | IDC | 2019 |  |  |  |  | 0 | 0 | 1.43 | 942.37 | 943.8 | -943.8
UIF - G/L Spending |  | GL Spending | 75000 | 75000 | 75000 | 75000 | 300000 | 122571.79 | 81360.2 | 116955.78 | 80655.85 | 401543.62 | -101543.62
UIF - Captime |  | GL Captime | 0 | 0 | 0 | 0 | 165941.4026 | 9591.76 | 21937.05 | 18460.71 | 13293.49 | 63283.01 | 102658.3926
UIF - Cap Suspense |  | Cap Suspense | [5 empty] | 0 | 0 | 0 | 9000 | 9000 | -9000
ACME - G/L Spending |  | GL Spending | 14500 | 14500 | 14500 | 14500 | 58000 | 14395.69 | -1809.92 | 0 | 816.12 | 13401.89 | 44598.11
ACME - Captime |  | GL Captime | 0 | 0 | 0 | 0 | 12399.0118 | 346.24 | 1731.2 | 90.36 | 337.56 | 2505.36 | 9893.6518
Sanlando - Hibocs Addition | 2018177 | Capital Spending | 55000 |  |  |  |  | 0 | 55500 | 0 | 0 | 55500 | -55500
Sanlando - Hibocs Addition - Captime | 2018177 | Project Captime | 0 | 0 | 0 | 0 |  | 273.12 | 281.32 | 0 | 0 | 554.44 | -554.44
Sanlando - Hibocs Addition - IDC | 2018177 | IDC | 422.89 | 0 | 429.6807 | 0 |  | 6.7907 | 422.89 | 0 | 0 | 429.6807 | -429.6807
Sanlando - Wekiva-Blower Replacement | 1 | Capital Spending |  | 200000 | 500000 | 760000 | 1460000 | [5 empty] | 1460000
Sanlando - Wekiva-Blower Replacement - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 | [6 empty] | 0
Sanlando - Wekiva-Blower Replacement - IDC | 1 | IDC | 0 | 42290.5 | 0 | 0 | 42290.5 | [5 empty] | 42290.5
Sanlando - Wekiva WWTF Imp Eng | 2018109 | Capital Spending | 77762.0425 |  |  |  | 44019 | 2512 | 3250 | 12626 | 5188 | 23576 | 20443
Sanlando - Wekiva WWTF Imp Eng - Captime | 2018109 | Project Captime | 0 | 0 | 0 | 0 |  | 1327.32 | 1689.54 | 187 | 0 | 3203.86 | -3203.86
Sanlando - Wekiva WWTF Imp Eng - IDC | 2018109 | IDC | 16267.49 | 662.4859 | 22133.9732 | 0 | 662.486 | 5866.4832 | 5956.15 | 6119.64 | 4191.7 | 22133.9732 | -21471.4872
Sanlando - Wekiva WWTF Improvements | 1 | Capital Spending |  | 100000 | 725000 | 725000 | 1550000 | 0 | 0 | 209380 | 275400 | 484780 | 1065220
Sanlando - Wekiva WWTF Improvements - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 1177.65 | 599.9 | 1777.55 | -1777.55
Sanlando - Wekiva WWTF Improvements - IDC | 1 | IDC | 6951.39 | 44209.375 | 14365.0202 | 0 | 44209.375 | 0 | 0 | 3395.91 | 3555.48 | 6951.39 | 37257.985
Sanlando - I&I Investigations Ph 4 | 2018117 | Capital Spending | [5 empty] | 33677.86 | 1489.51 | 0 | 0 | 35167.37 | -35167.37
Sanlando - I&I Investigations Ph 4 - Captime | 2018117 | Project Captime | 0 | 0 | 0 | 0 |  | 1146.92 | 129.84 | 0 | 0 | 1276.76 | -1276.76
Sanlando - I&I Investigations Ph 4 - IDC | 2018117 | IDC | 1470.15 | 0 | 5610.3858 | 0 |  | 4140.2358 | 1470.15 | 0 | 0 | 5610.3858 | -5610.3858
Sanlando - I&I Corrections Ph 4 | 1 | Capital Spending | 1048013 | 1000000 |  |  | 2000000 | 0 | 0 | 0 | 0 | 0 | 2000000
Sanlando - I&I Corrections Ph 4 - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - I&I Corrections Ph 4 - IDC | 1 | IDC | 0 | 61674.9 | 0 | 0 | 61674.9 | 0 | 0 | 0 | 0 | 0 | 61674.9
Sanlando - I&I Corrections Future | 1 | Capital Spending | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - I&I Corrections Future - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - I&I Corrections Future - IDC | 1 | IDC | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - ENG Powerline 14" FM Replacement | 2018098 | Capital Spending | 31800 |  |  |  |  | 12875 | 0 | 500 | 441.15 | 13816.15 | -13816.15
Sanlando - ENG Powerline 14" FM Replacement - Captime | 2018098 | Project Captime | 0 | 0 | 0 | 0 |  | 468.56 | 458.08 | 135.54 | 248.49 | 1310.67 | -1310.67
Sanlando - ENG Powerline 14" FM Replacement - IDC | 2018098 | IDC | 2860.73 | 0 | 4626.1549 | 0 |  | 893.3171 | 1059.14 | 1077.33 | 724.26 | 3754.0471 | -3754.0471
Sanlando - Powerline 14" FM Replacement | 1 | Capital Spending |  | 500000 | 500000 |  | 1000000 | 0 | 0 | 0 | 0 | 0 | 1000000
Sanlando - Powerline 14" FM Replacement - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - Powerline 14" FM Replacement - IDC | 1 | IDC | 0 | 26337.5 | 0 | 0 | 26337.5 | 0 | 0 | 0 | 0 | 0 | 26337.5
Sanlando - UIF CIP Analysis/Modeling | 1 | Capital Spending | [5 empty] | 13950 | 0 | 14800 | 14800 | 43550 | -43550
Sanlando - UIF CIP Analysis/Modeling - Captime | 1 | Project Captime | [5 empty] | 0 | 0 | 5008.31 | 458.08 | 5466.39 | -5466.39
Sanlando - UIF CIP Analysis/Modeling - IDC | 1 | IDC | [5 empty] | 0 | 0 | 316.28 | 359.33 | 675.61 | -675.61
Sanlando - Essex Drive GSM Repair | 1 | Capital Spending | [5 empty] | 69121.7 | 0 | 0 | 0 | 69121.7 | -69121.7
Sanlando - Essex Drive GSM Repair - Captime | 1 | Project Captime | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - Essex Drive GSM Repair - IDC | 1 | IDC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - Markham Woods WM Repair | 1 | Capital Spending | [5 empty] | 70009.13 | 0 | 38450 | 0 | 108459.13 | -108459.13
Sanlando - Markham Woods WM Repair - Captime | 1 | Project Captime | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - Markham Woods WM Repair - IDC | 1 | IDC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - F5 FM | 1 | Capital Spending | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - F5 FM - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - F5 FM - IDC | 1 | IDC | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - C1 FM | 1 | Capital Spending | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - C1 FM - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - C1 FM - IDC | 1 | IDC | 0 | 42230.3 | 0 | 0 | 42230.3 | 0 | 0 | 0 | 0 | 0 | 42230.3
Sanlando - Powerline WM Replacement | 1 | Capital Spending |  |  | 1100000 | 1040000 | 2140000 | 0 | 0 | 0 | 0 | 0 | 2140000
Sanlando - Powerline WM Replacement - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - Powerline WM Replacement - IDC | 1 | IDC | 0 | 62505.2386 | 0 | 0 | 62505.2386 | 0 | 0 | 0 | 0 | 0 | 62505.2386
Sanlando - Springs WM Replacement | 1 | Capital Spending | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - Springs WM Replacement - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - Springs WM Replacement - IDC | 1 | IDC | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - G/L Spending |  | GL Spending | 197500 | 197500 | 197500 | 197500 | 790000 | 298048.04 | 298326.35 | 124685.94 | 261162.69 | 982223.02 | -192223.02
Sanlando - Captime |  | GL Captime | 0 | 0 | 0 | 0 | 267302.1042 | 40552.68 | 31250.4 | 47100.15 | 36652.26 | 155555.49 | 111746.6142
Sanlando - Cap Suspense |  | Cap Suspense | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Sandalhaven - EWD Bulk Sewer Capacity Payment | 1 | Capital Spending | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Sandalhaven - EWD Bulk Sewer Capacity Payment - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Sandalhaven - EWD Bulk Sewer Capacity Payment - IDC | 1 | IDC | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Sandalhaven - L/S RTU Installation | 1 | Capital Spending |  |  | 130000 |  | 130000 | 0 | 0 | 0 | 0 | 0 | 130000
Sandalhaven - L/S RTU Installation - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Sandalhaven - L/S RTU Installation - IDC | 1 | IDC | 0 | 1956.5 | 0 | 0 | 1956.5 | 0 | 0 | 0 | 0 | 0 | 1956.5
Sandalhaven - Smoke Testing/I&I Investigation | 1 | Capital Spending | 50000 | 100000 |  |  | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
Sandalhaven - Smoke Testing/I&I Investigation - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Sandalhaven - Smoke Testing/I&I Investigation - IDC | 1 | IDC | 0 | 1505 | 0 | 0 | 1505 | 0 | 0 | 0 | 0 | 0 | 1505
Sandalhaven - Leverocks L/S 3 | 1 | Capital Spending | [5 empty] | 0 | 0 | 91141 | 108 | 91249 | -91249
Sandalhaven - Leverocks L/S 3 - Captime | 1 | Project Captime | [5 empty] | 0 | 722.88 | 0 | 0 | 722.88 | -722.88
Sandalhaven - Leverocks L/S 3 - IDC | 1 | IDC | [5 empty] | 0 | 5.44 | 1382.56 | 0 | 1388 | -1388
Sandalhaven - G/L Spending |  | GL Spending | 9000 | 9000 | 9000 | 9000 | 36000 | 37345.31 | 16371.01 | 10162.25 | 3343.04 | 67221.61 | -31221.61
Sandalhaven - Captime |  | GL Captime | 0 | 0 | 0 | 0 | 12670.0849 | 1282 | 1020.28 | 903.6 | 632.52 | 3838.4 | 8831.6849
Sandalhaven - Cap Suspense |  | Cap Suspense | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Labrador - Engineering WWTP Master Plan | 1 | Capital Spending |  | 45000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Labrador - Engineering WWTP Master Plan - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Labrador - Engineering WWTP Master Plan - IDC | 1 | IDC | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Labrador - Construction WWTP Master Plan | 1 | Capital Spending | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Labrador - Construction WWTP Master Plan - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Labrador - Construction WWTP Master Plan - IDC | 1 | IDC | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Labrador - G/L Spending |  | GL Spending | 8750 | 8750 | 8750 | 8750 | 35000 | 7515.52 | 12562.93 | 14688.87 | 33481.69 | 68249.01 | -33249.01
Labrador - Captime |  | GL Captime | 0 | 0 | 0 | 0 | 30008.0959 | 2112.52 | 5614.53 | 3704.76 | 6291.32 | 17723.13 | 12284.9659
Labrador - Cap Suspense |  | Cap Suspense | [5 empty] | 0 | 20500 | 10250 | 8650 | 39400 | -39400
Pennbrooke - WTP Upgrade | 1 | Capital Spending | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Pennbrooke - WTP Upgrade - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Pennbrooke - WTP Upgrade - IDC | 1 | IDC | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Pennbrooke - L/S RTU Installation | 1 | Capital Spending |  | 70000 |  |  | 70000 | 0 | 0 | 31507.51 | 24836.97 | 56344.48 | 13655.52
Pennbrooke - L/S RTU Installation - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Pennbrooke - L/S RTU Installation - IDC | 1 | IDC | 474.18 | 1053.5 | 474.18 | 0 | 1053.5 | 0 | 0 | 474.18 | 0 | 474.18 | 579.32
Pennbrooke - G/L Spending |  | GL Spending | 18750 | 18750 | 18750 | 18750 | 75000 | 32193.42 | 37284.57 | 11705.41 | 32099.47 | 113282.87 | -38282.87
Pennbrooke - Captime |  | GL Captime | 0 | 0 | 0 | 0 | 44982.0301 | 4349.64 | 8439.64 | 6562.4 | 4337.28 | 23688.96 | 21293.0701
Pennbrooke - Cap Suspense |  | Cap Suspense | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
FL Cost Center - 15KW Generator Fleet | 2018151 | Capital Spending | 146000 | 96000 |  |  | 92000 | 69976.8 | 97683.88 | 62431.89 | 0 | 230092.57 | -138092.57
FL Cost Center - 15KW Generator Fleet - Captime | 2018151 | Project Captime | 0 | 0 | 0 | 0 |  | 664.2 | 1361.38 | 4492.1 | 0 | 6517.68 | -6517.68
FL Cost Center - 15KW Generator Fleet - IDC | 2018151 | IDC | 6980.49 | 752.5 | 7831.7069 | 0 | 752.5 | 851.2169 | 2768.15 | 4212.34 | 0 | 7831.7069 | -7079.2069
FL Cost Center - Fleet Replacements | 1 | Capital Spending | 178000 | 200000 | 30000 | 0 | 537500 | 239796.4 | 40195.43 | 206728.36 | 2172.52 | 488892.71 | 48607.29
FL Cost Center - G/L Spending |  | GL Spending | 12500 | 12500 | 12500 | 12500 | 50000 | 818.13 | 12997.82 | 8778.86 | 19439.84 | 42034.65 | 7965.35
FL Cost Center - Captime |  | GL Captime | 0 | 0 | 0 | 0 |  | 649.2 | 259.68 | 656.49 | 0 | 1565.37 | -1565.37
FL Cost Center - Cap Suspense |  | Cap Suspense | [5 empty] | 14642.48 | 361.44 | -315.84 | 0 | 14688.08 | -14688.08

## 2020 YTD
BUDGET vs FORECAST | [6 empty] | BUDGET |  |  |  |  | FORECAST
|  |  | 4845006.4047 | 5684332.7117 | 3242899.4286 | 4241300.0127 | 18013538.5578 | 2846701.22 | 3683376.1089 | 7417773.0061 | 6387073.9154 | 20334924.2504 | -2321385.6926
Project | Project # | Type | Q1 | Q2 | Q3 | Q4 | 2020 BUDGET | Q1 | Q2 | Q3 | Q4 | 2020 FORECAST | Variance
Tierra Verde - ENG Lift Station #4 Forcemain | 2019086 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 9000 | -9000
Tierra Verde - ENG Lift Station #4 Forcemain - Captime | 2019086 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tierra Verde - ENG Lift Station #4 Forcemain - IDC | 2019086 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tierra Verde - FM / GSM Relocation | 2019087 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 57072.81 | 0 | 20000 | 33000 | 110072.81 | -110072.81
Tierra Verde - FM / GSM Relocation - Captime | 2019087 | Project Captime | 0 | 0 | 0 | 0 | 0 | 1957.4 | 585 | 0 | 246.865 | 2789.265 | -2789.265
Tierra Verde - FM / GSM Relocation - IDC | 2019087 | IDC | 0 | 0 | 0 | 0 | 0 | 6276.13 | 3804.852 | 11715.5559 | 12366.4213 | 34162.9592 | -34162.9592
Tierra Verde - Liftstation #4 Replacement | 2019173 | Capital Spending | 500000 | 500000 | 0 | 0 | 1000000 | 482 | 0 | 0 | 0 | 482 | 999518
Tierra Verde - Liftstation #4 Replacement - Captime | 2019173 | Project Captime | 7500 | 7500 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
Tierra Verde - Liftstation #4 Replacement - IDC | 2019173 | IDC | 7637.875 | 19267.1125 | 0 | 0 | 26904.9875 | 5.88 | 8.76 | 0 | 0 | 14.64 | 26890.3475
Tierra Verde - Redzone I&I Investigation | 2018116 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | -165000
Tierra Verde - Redzone I&I Investigation - Captime | 2018116 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2557.5 | 2557.5 | -2557.5
Tierra Verde - Redzone I&I Investigation - IDC | 2018116 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4634.6836 | 4634.6836 | -4634.6836
Tierra Verde - G/L Spending |  | GL Spending | 10000 | 10000 | 10000 | 10000 | 40000 | 2660 | 5700 | 10000 | 10000 | 28360 | 11640
Tierra Verde - Captime |  | GL Captime | 622.8199 | 622.8199 | 622.8199 | 622.8199 | 2491.2796 | 813.24 | 591.2265 | 591.2265 | 591.2265 | 2586.9194 | -95.6398
Tierra Verde - Cap Suspense |  | Cap Suspense | 0 | 0 | 0 | 0 | 0 | -9000 | 0 | 0 | 0 | -9000 | 9000
Lake Placid - G/L Spending |  | GL Spending | 3750 | 3750 | 3750 | 3750 | 15000 | 0 | 1250 | 3750 | 3750 | 8750 | 6250
Lake Placid - Captime |  | GL Captime | 311.4099 | 311.4099 | 311.4099 | 311.4099 | 1245.6398 | 2213.82 | 295.6132 | 295.6132 | 295.6132 | 3100.6597 | -1855.0199
Lake Placid - Cap Suspense |  | Cap Suspense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Longwood - L/S RTUs | 2019078 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 53815.59 | 0 | 0 | 0 | 53815.59 | -53815.59
Longwood - L/S RTUs - Captime | 2019078 | Project Captime | 0 | 0 | 0 | 0 | 0 | 45.18 | 0 | 0 | 0 | 45.18 | -45.18
Longwood - L/S RTUs - IDC | 2019078 | IDC | 0 | 0 | 0 | 0 | 0 | 919.25 | 0 | 0 | 0 | 919.25 | -919.25
Longwood - G/L Spending |  | GL Spending | 18750 | 18750 | 18750 | 18750 | 75000 | 42721.28 | 5750 | 18750 | 18750 | 85971.28 | -10971.28
Longwood - Captime |  | GL Captime | 2321.6682 | 2321.6682 | 2321.6682 | 2321.6682 | 9286.6729 | 779.7 | 2203.8983 | 2203.8983 | 2203.8983 | 7391.3949 | 1895.278
Longwood - Cap Suspense |  | Cap Suspense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cypress Lakes - Smoke Testing/I&I Investigation | 1 | Capital Spending | 50000 | 0 | 0 | 0 | 50000 | 0 | 42500 | 7500 | 0 | 50000 | 0
Cypress Lakes - Smoke Testing/I&I Investigation - Captime | 1 | Project Captime | 750 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 750
Cypress Lakes - Smoke Testing/I&I Investigation - IDC | 1 | IDC | 763.7875 | 0 | 0 | 0 | 763.7875 | 0 | 0 | 0 | 0 | 0 | 763.7875
Cypress Lakes - I&I Project | 1 | Capital Spending |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cypress Lakes - I&I Project - Captime | 1 | Project Captime |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cypress Lakes - I&I Project - IDC | 1 | IDC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cypress Lakes - Rehab L/S 1 | 2019084 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cypress Lakes - Rehab L/S 1 - Captime | 2019084 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cypress Lakes - Rehab L/S 1 - IDC | 2019084 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cypress Lakes - Chlorine Dioxide Pilot Study | 1 | Capital Spending | 0 | 25000 | 50000 | 50000 | 125000 | 0 | 0 | 0 | 0 | 0 | 125000
Cypress Lakes - Chlorine Dioxide Pilot Study - Captime | 1 | Project Captime | 0 | 375 | 750 | 750 | 1875 | 0 | 0 | 0 | 0 | 0 | 1875
Cypress Lakes - Chlorine Dioxide Pilot Study - IDC | 1 | IDC | 0 | 381.8937 | 1336.6281 | 2482.3094 | 4200.8312 | 0 | 0 | 0 | 0 | 0 | 4200.8312
Cypress Lakes - G/L Spending |  | GL Spending | 25000 | 25000 | 25000 | 25000 | 100000 | 22223.99 | 4960 | 15000 | 15000 | 57183.99 | 42816.01
Cypress Lakes - Captime |  | GL Captime | 3277.9994 | 3277.9994 | 3277.9994 | 3277.9994 | 13111.9977 | 7680.6 | 3111.7182 | 3111.7182 | 3111.7182 | 17015.7547 | -3903.757
Cypress Lakes - Cap Suspense |  | Cap Suspense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Eagle Ridge - Lift Station RTU Improvements | 2019024 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65203 | 0 | 65203 | -65203
Eagle Ridge - Lift Station RTU Improvements - Captime | 2019024 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 863.025 | 0 | 0 | 863.025 | -863.025
Eagle Ridge - Lift Station RTU Improvements - IDC | 2019024 | IDC | 0 | 0 | 0 | 0 | 0 | 3723.6 | 3733.4432 | 4724.3847 | 0 | 12181.4279 | -12181.4279
Eagle Ridge - ER North and South Plant Rehab - Captime | 2019050 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Eagle Ridge - ER North and South Plant Rehab - IDC | 2019050 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Eagle Ridge - ENG WWTP Variance & LDO | 2019125 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 22125.8 | 6000 | 0 | 0 | 28125.8 | -28125.8
Eagle Ridge - ENG WWTP Variance & LDO - Captime | 2019125 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Eagle Ridge - ENG WWTP Variance & LDO - IDC | 2019125 | IDC | 0 | 0 | 0 | 0 | 0 | 2817.59 | 3009.4224 | 0 | 0 | 5827.0124 | -5827.0124
Eagle Ridge - WWTP Tree Removal / Fencing | 2019175 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 276664.41 | 116729.59 | 17000 | 0 | 410394 | -410394
Eagle Ridge - WWTP Tree Removal / Fencing - Captime | 2019175 | Project Captime | 0 | 0 | 0 | 0 | 0 | 7328.58 | 2926.02 | 0 | 0 | 10254.6 | -10254.6
Eagle Ridge - WWTP Tree Removal / Fencing - IDC | 2019175 | IDC | 0 | 0 | 0 | 0 | 0 | 9417.81 | 14467.6826 | 14947.4577 | 0 | 38832.9503 | -38832.9503
Eagle Ridge - Replace Reject Pond Liner | 2019122 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 87.24 | 2139.35 | 0 | 0 | 2226.59 | -2226.59
Eagle Ridge - Replace Reject Pond Liner - Captime | 2019122 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Eagle Ridge - Replace Reject Pond Liner - IDC | 2019122 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Eagle Ridge - I&I Investigation | 1 | Capital Spending | 50000 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
Eagle Ridge - I&I Investigation - Captime | 1 | Project Captime | 750 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 750
Eagle Ridge - I&I Investigation - IDC | 1 | IDC | 763.7875 | 0 | 0 | 0 | 763.7875 | 0 | 0 | 0 | 0 | 0 | 763.7875
Eagle Ridge - L/S ER 3 & 8 Rehab | 1 | Capital Spending | 0 | 50000 | 50000 | 0 | 100000 | 0 | 0 | 81890 | 0 | 81890 | 18110
Eagle Ridge - L/S ER 3 & 8 Rehab - Captime | 1 | Project Captime | 0 | 750 | 750 | 0 | 1500 | 0 | 0 | 1269.295 | 0 | 1269.295 | 230.705
Eagle Ridge - L/S ER 3 & 8 Rehab - IDC | 1 | IDC | 0 | 763.7875 | 1909.4687 | 0 | 2673.2562 | 0 | 0 | 1251.5474 | 0 | 1251.5474 | 1421.7089
Eagle Ridge - G/L Spending |  | GL Spending | 25000 | 25000 | 25000 | 25000 | 100000 | 14174.83 | 25000 | 25000 | 25000 | 89174.83 | 10825.17
Eagle Ridge - Captime |  | GL Captime | 4589.1992 | 4589.1992 | 4589.1992 | 4589.1992 | 18356.7967 | 5240.88 | 4557.4055 | 4356.4055 | 4356.4055 | 18511.0965 | -154.2998
Eagle Ridge - Cap Suspense |  | Cap Suspense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mid-County - PDR & Master L/S Replacement | 2019145 | Capital Spending | 30000 | 0 | 0 | 0 | 30000 | 46100 | 15100 | 298949 | 450000 | 810149 | -780149
Mid-County - PDR & Master L/S Replacement - Captime | 2019145 | Project Captime | 450 | 0 | 0 | 0 | 450 | 384.72 | 7591.515 | 0 | 15000 | 22976.235 | -22526.235
Mid-County - PDR & Master L/S Replacement - IDC | 2019145 | IDC | 3762.7906 | 0 | 0 | 0 | 3762.7906 | 3894.52 | 4556.4468 | 9217.8129 | 18465.6541 | 36134.4338 | -32371.6432
Mid-County - WWTP Improvements - Construction | 1 | Capital Spending | 0 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 80000 | 80000 | 160000 | 1840000
Mid-County - WWTP Improvements - Construction - Captime | 1 | Project Captime | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000
Mid-County - WWTP Improvements - Construction - IDC | 1 | IDC | 0 | 0 | 0 | 30551.5 | 30551.5 | 0 | 0 | 1204 | 3010 | 4214 | 26337.5
Mid County - Headworks | 1 | Capital Spending | [5 empty] | 0 | 85500 | 100000 | 460000 | 645500 | -645500
Mid County - Headworks - Captime | 1 | Project Captime | [5 empty] | 0 | 1325.25 | 1550 | 15000 | 17875.25 | -17875.25
Mid County - Headworks - IDC | 1 | IDC | [5 empty] | 0 | 1174.49 | 3488.4075 | 11401.3213 | 16064.2188 | -16064.2188
Mid-County - | 1 | Capital Spending | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Mid-County - | 1 | Project Captime | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Mid-County - | 1 | IDC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Mid-County - Curlew Creek I&I Improvements | 1 | Capital Spending | 250000 | 250000 | 250000 | 250000 | 1000000 | 0 | 100000 | 250000 | 285000 | 635000 | 365000
Mid-County - Curlew Creek I&I Improvements - Captime | 1 | Project Captime | 3750 | 3750 | 3750 | 3750 | 15000 | 0 | 3750 | 3750 | 3750 | 11250 | 3750
Mid-County - Curlew Creek I&I Improvements - IDC | 1 | IDC | 3818.9375 | 9633.5563 | 15579.44 | 21659.5522 | 50691.486 | 0 | 780.7188 | 6161.0937 | 12416.25 | 19358.0625 | 31333.4235
Mid-County - LS #4 / #7 Gensets | 2019154 | Capital Spending | 115000 | 0 | 0 | 0 | 115000 | 0 | 34822 | 39000 | 0 | 73822 | 41178
Mid-County - LS #4 / #7 Gensets - Captime | 2019154 | Project Captime | 1725 | 0 | 0 | 0 | 1725 | 2024.88 | 769.83 | 0 | 0 | 2794.71 | -1069.71
Mid-County - LS #4 / #7 Gensets - IDC | 2019154 | IDC | 2558.6881 | 0 | 0 | 0 | 2558.6881 | 0 | 824.5538 | 3060.6115 | 0 | 3885.1653 | -1326.4772
Mid-County - Eng Relocate LS 10 FM | 1 | Capital Spending |  |  |  |  | 0 | 0 | 28000 | 0 | 0 | 28000 | -28000
Mid-County - Eng Relocate LS 10 FM - Captime | 1 | Project Captime |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mid-County - Eng Relocate LS 10 FM - IDC | 1 | IDC |  |  |  |  | 0 | 0 | 210.7 | 0 | 0 | 210.7 | -210.7
Mid-County - LS RTU | 1 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mid-County - LS RTU - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mid-County - LS RTU - IDC | 1 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mid-County - G/L Spending |  | GL Spending | 37500 | 37500 | 37500 | 37500 | 150000 | 79936.93 | 23420 | 37500 | 37500 | 178356.93 | -28356.93
Mid-County - Captime |  | GL Captime | 6555.9988 | 6555.9988 | 6555.9988 | 6555.9988 | 26223.9953 | 19824.09 | 10528.4364 | 6223.4364 | 6223.4364 | 42799.3993 | -16575.404
Mid-County - Cap Suspense |  | Cap Suspense | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 4500 | -4500
LUSI - Eng - 2nd Lower Floridan Well | 1 | Capital Spending | 37500 | 37500 | 37500 | 37500 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
LUSI - Eng - 2nd Lower Floridan Well - Captime | 1 | Project Captime | 562.5 | 562.5 | 562.5 | 562.5 | 2250 | 0 | 0 | 0 | 0 | 0 | 2250
LUSI - Eng - 2nd Lower Floridan Well - IDC | 1 | IDC | 572.8406 | 1432.1016 | 2291.3625 | 3150.6234 | 7446.9281 | 0 | 0 | 0 | 0 | 0 | 7446.9281
LUSI - Feasibility Study & Land Purchase for NE WTP | 1 | Capital Spending | 0 | 0 | 50000 | 50000 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000
LUSI - Feasibility Study & Land Purchase for NE WTP - Captime | 1 | Project Captime | 0 | 0 | 750 | 750 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500
LUSI - Feasibility Study & Land Purchase for NE WTP - IDC | 1 | IDC | 0 | 0 | 763.7875 | 1909.4687 | 2673.2562 | 0 | 0 | 0 | 0 | 0 | 2673.2562
LUSI - LUSI North TTHM HAA5 Remediation | 1 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LUSI - LUSI North TTHM HAA5 Remediation - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LUSI - LUSI North TTHM HAA5 Remediation - IDC | 1 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LUSI - LG WTP Improvements Construction | 2018153 | Capital Spending |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
LUSI - LG WTP Improvements Construction - Captime | 2018153 | Project Captime |  |  |  |  | 0 | 1265.04 | 0 | 0 | 0 | 1265.04 | -1265.04
LUSI - LG WTP Improvements Construction - IDC | 2018153 | IDC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
LUSI - Eng - Crescent Bay Raw WM | 1 | Capital Spending | 100000 | 0 | 0 | 0 | 100000 | 4000 | 40000 | 11000 | 15000 | 70000 | 30000
LUSI - Eng - Crescent Bay Raw WM - Captime | 1 | Project Captime | 1500 | 0 | 0 | 0 | 1500 | 100 | 1400 | 0 | 0 | 1500 | 0
LUSI - Eng - Crescent Bay Raw WM - IDC | 1 | IDC | 1527.575 | 0 | 0 | 0 | 1527.575 | 31.6 | 790.5175 | 1192.7125 | 1501.2375 | 3516.0675 | -1988.4925
LUSI - Const - Crescent Bay Raw WM | 2020028 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243257 | 243257 | 486514 | -486514
LUSI - Const - Crescent Bay Raw WM - Captime | 2020028 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LUSI - Const - Crescent Bay Raw WM - IDC | 2020028 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3661.0178 | 9152.5446 | 12813.5625 | -12813.5625
LUSI - Barrington WWTP Cap Improvements | 1 | Capital Spending | 125000 | 0 | 0 | 0 | 125000 | 0 | 34300 | 180700 | 165000 | 380000 | -255000
LUSI - Barrington WWTP Cap Improvements - Captime | 1 | Project Captime | 1875 | 0 | 0 | 0 | 1875 | 0 | 375 | 0 | 0 | 375 | 1500
LUSI - Barrington WWTP Cap Improvements - IDC | 1 | IDC | 4200.8312 | 0 | 0 | 0 | 4200.8312 | 0 | 519.0394 | 3502.3231 | 7345.3406 | 11366.7031 | -7165.8719
LUSI - Sewer Jetter Trailer | 1 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LUSI - Sewer Jetter Trailer - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LUSI - Sewer Jetter Trailer - IDC | 1 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LUSI - LG Sulfuric Acid Tank & Pipe Replacement | 2020029 | Capital Spending | 55000 | 0 | 0 | 0 | 55000 | 0 | 54303 | 0 | 0 | 54303 | 697
LUSI - LG Sulfuric Acid Tank & Pipe Replacement - Captime | 2020029 | Project Captime | 825 | 0 | 0 | 0 | 825 | 687.34 | 825 | 0 | 0 | 1512.34 | -687.34
LUSI - LG Sulfuric Acid Tank & Pipe Replacement - IDC | 2020029 | IDC | 840.1662 | 0 | 0 | 0 | 840.1662 | 5.92 | 420.0104 | 0 | 0 | 425.9304 | 414.2358
LUSI - LG RAS Pump Replacement | 1 | Capital Spending | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
LUSI - LG RAS Pump Replacement - Captime | 1 | Project Captime | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
LUSI - LG RAS Pump Replacement - IDC | 1 | IDC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
LUSI - LG HCl Acid Storage Tank Relocate | 1 | Capital Spending | [5 empty] | 29991.6 | 0 | 0 | 0 | 29991.6 | -29991.6
LUSI - LG HCl Acid Storage Tank Relocate - Captime | 1 | Project Captime | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
LUSI - LG HCl Acid Storage Tank Relocate - IDC | 1 | IDC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
LUSI - G/L Spending |  | GL Spending | 175000 | 175000 | 175000 | 175000 | 700000 | 254380.64 | 176086 | 175000 | 175000 | 780466.64 | -80466.64
LUSI - Captime |  | GL Captime | 52447.9906 | 52447.9906 | 52447.9906 | 52447.9906 | 209791.9625 | 50377.84 | 49787.4916 | 49787.4916 | 49787.4916 | 199740.3147 | 10051.6479
LUSI - Cap Suspense |  | Cap Suspense | 0 | 0 | 0 | 0 | 0 | 15850 | -34300 | 0 | 0 | -18450 | 18450
UIF - Timing Adjustments |  | Timing Plug | -1000000 | -1000000 | -1000000 | -500000 | -3500000 | 0 | 0 | -2000000 | -2000000 | -4000000 | 500000
UIF - Timing Adjustments - IDC |  | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UIF - AMP Implementation | 1 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UIF - AMP Implementation - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UIF - AMP Implementation - IDC | 1 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UIF - Jansen AC Main Replacement | 1 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UIF - Jansen AC Main Replacement - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UIF - Jansen AC Main Replacement - IDC | 1 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UIF - Little Wekiva Generator | 2019110 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 64460 | 24537 | 0 | 0 | 88997 | -88997
UIF - Little Wekiva Generator - Captime | 2019110 | Project Captime | 0 | 0 | 0 | 0 | 0 | 1377.99 | 410 | 0 | 0 | 1787.99 | -1787.99
UIF - Little Wekiva Generator - IDC | 2019110 | IDC | 0 | 0 | 0 | 0 | 0 | 1129.65 | 2011.157 | 0 | 0 | 3140.807 | -3140.807
UIF - Park Ridge Generator | 2019111 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 65200 | 27537 | 0 | 0 | 92737 | -92737
UIF - Park Ridge Generator - Captime | 2019111 | Project Captime | 0 | 0 | 0 | 0 | 0 | 837.83 | 587 | 0 | 0 | 1424.83 | -1424.83
UIF - Park Ridge Generator - IDC | 2019111 | IDC | 0 | 0 | 0 | 0 | 0 | 1138.16 | 2262.6677 | 0 | 0 | 3400.8277 | -3400.8277
UIF - NW Bridge Interconnect | 1 | Capital Spending | 82000 | 0 | 0 | 0 | 82000 | 0 | 6005.25 | 0 | 0 | 6005.25 | 75994.75
UIF - NW Bridge Interconnect - Captime | 1 | Project Captime | 1230 | 0 | 0 | 0 | 1230 | 0 | 0 | 0 | 0 | 0 | 1230
UIF - NW Bridge Interconnect - IDC | 1 | IDC | 1252.6115 | 0 | 0 | 0 | 1252.6115 | 0 | 90.3795 | 0 | 0 | 90.3795 | 1162.232
UIF - Seminole L/S RTUs | 2019076 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 41396.61 | 0 | 0 | 0 | 41396.61 | -41396.61
UIF - Seminole L/S RTUs - Captime | 2019076 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UIF - Seminole L/S RTUs - IDC | 2019076 | IDC | 0 | 0 | 0 | 0 | 0 | 707.17 | 0 | 0 | 0 | 707.17 | -707.17
UIF - ST PW - Smoke Testing/I&I Investigation | 1 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 27481.05 | 0 | 0 | 0 | 27481.05 | -27481.05
UIF - ST PW - Smoke Testing/I&I Investigation - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UIF - ST PW - Smoke Testing/I&I Investigation - IDC | 1 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UIF - ST - I&I Corrections | 1 | Capital Spending |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
UIF - ST - I&I Corrections - Captime | 1 | Project Captime |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
UIF - ST - I&I Corrections - IDC | 1 | IDC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
UIF - ENG - ST Chlorine Dioxide Pilot Study | 2019174 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 32000 | 0 | 52000 | -52000
UIF - ENG - ST Chlorine Dioxide Pilot Study - Captime | 2019174 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 570 | 210 | 0 | 780 | -780
UIF - ENG - ST Chlorine Dioxide Pilot Study - IDC | 2019174 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 385.9692 | 949.1282 | 0 | 1335.0975 | -1335.0975
UIF - Weathersfield WM Replacement | 1 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UIF - Weathersfield WM Replacement - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UIF - Weathersfield WM Replacement - IDC | 1 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UIF - Ravenna Park I&I Corrections | 1 | Capital Spending |  |  |  |  | 0 | 0 | 0 | 325784.5 | 325784.5 | 651569 | -651569
UIF - Ravenna Park I&I Corrections - Captime | 1 | Project Captime |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
UIF - Ravenna Park I&I Corrections - IDC | 1 | IDC |  |  |  |  | 0 | 0 | 0 | 4903.0567 | 12257.6418 | 17160.6985 | -17160.6985
UIF - Golden Hills WM Relocation NW 78th Ave | 2019146 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 41128.87 | 0 | 0 | 0 | 41128.87 | -41128.87
UIF - Golden Hills WM Relocation NW 78th Ave - Captime | 2019146 | Project Captime | 0 | 0 | 0 | 0 | 0 | 2665.62 | 0 | 0 | 0 | 2665.62 | -2665.62
UIF - Golden Hills WM Relocation NW 78th Ave - IDC | 2019146 | IDC | 0 | 0 | 0 | 0 | 0 | 1251.61 | 0 | 0 | 0 | 1251.61 | -1251.61
UIF - OW Well 1 Hydrotank Genset | 2020004 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 87675 | 67505 | 9391 | 0 | 164571 | -164571
UIF - OW Well 1 Hydrotank Genset - Captime | 2020004 | Project Captime | 0 | 0 | 0 | 0 | 0 | 463.44 | 1433.24 | 0 | 0 | 1896.68 | -1896.68
UIF - OW Well 1 Hydrotank Genset - IDC | 2020004 | IDC | 0 | 0 | 0 | 0 | 0 | 1010.12 | 2549.932 | 3687.3406 | 0 | 7247.3926 | -7247.3926
UIF - BV Well Improvements | 2020041 | Capital Spending | [5 empty] | 20595 | 16745 | 57228 | 0 | 94568 | -94568
UIF - BV Well Improvements - Captime | 2020041 | Project Captime | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
UIF - BV Well Improvements - IDC | 2020041 | IDC | [5 empty] | 0 | 406.9935 | 1704.2319 | 0 | 2111.2254 | -2111.2254
UIF - GH Galvanized WM Replacement | 1 | Capital Spending | [5 empty] | 0 | 0 | 75160 | 0 | 75160 | -75160
UIF - GH Galvanized WM Replacement - Captime | 1 | Project Captime | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
UIF - GH Galvanized WM Replacement - IDC | 1 | IDC | [5 empty] | 0 | 0 | 1131.158 | 0 | 1131.158 | -1131.158
UIF - G/L Spending |  | GL Spending | 75000 | 75000 | 75000 | 75000 | 300000 | 17975.28 | 75000 | 75000 | 75000 | 242975.28 | 57024.72
UIF - Captime |  | GL Captime | 32628.544 | 32628.544 | 32628.544 | 32628.544 | 130514.1761 | 23154.75 | 30973.4146 | 30973.4146 | 30973.4146 | 116074.9939 | 14439.1822
UIF - Cap Suspense |  | Cap Suspense | 0 | 0 | 0 | 0 | 0 | -9000 | 28260.9 | 0 | 0 | 19260.9 | -19260.9
ACME - G/L Spending |  | GL Spending | 7500 | 7500 | 7500 | 7500 | 30000 | 8948.8 | 7000 | 17500 | 7500 | 40948.8 | -10948.8
ACME - Captime |  | GL Captime | 2437.9793 | 2437.9793 | 2437.9793 | 2437.9793 | 9751.9171 | 135.54 | 2314.3093 | 2314.3093 | 2314.3093 | 7078.4679 | 2673.4492
Sanlando - Wekiva WWTF Imp Eng | 2018109 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - Wekiva WWTF Imp Eng - Captime | 2018109 | Project Captime | 0 | 0 | 0 | 0 | 0 | 102 | 0 | 0 | 0 | 102 | -102
Sanlando - Wekiva WWTF Imp Eng - IDC | 2018109 | IDC | 0 | 0 | 0 | 0 | 0 | 6404.67 | 0 | 0 | 0 | 6404.67 | -6404.67
Sanlando - Wekiva WWTF Improvements | 2019109 | Capital Spending | 1500000 | 2000000 | 1000000 | 311000 | 4811000 | 1031068.8 | 1668931.2 | 2514421 | 413000 | 5627421 | -816421
Sanlando - Wekiva WWTF Improvements - Captime | 2019109 | Project Captime | 22500 | 30000 | 15000 | 4665 | 72165 | 11269.1 | 42357.445 | 26103.3 | 4665 | 84394.845 | -12229.845
Sanlando - Wekiva WWTF Improvements - IDC | 2019109 | IDC | 50440.6612 | 92448.9737 | 123000.4737 | 135389.1069 | 401279.2155 | 20153.36 | 54430.6353 | 111382.0467 | 136785.3503 | 322751.3922 | 78527.8233
Sanlando - I&I Corrections Ph 4 | 1 | Capital Spending | 1000000 | 1000000 | 0 | 0 | 2000000 | 0 | 74406 | 922594 | 1000000 | 1997000 | 3000
Sanlando - I&I Corrections Ph 4 - Captime | 1 | Project Captime | 15000 | 15000 | 0 | 0 | 30000 | 0 | 5000 | 25000 | 0 | 30000 | 0
Sanlando - I&I Corrections Ph 4 - IDC | 1 | IDC | 15275.75 | 38189.375 | 0 | 0 | 53465.125 | 0 | 1157.4401 | 16053.8802 | 38234.525 | 55445.8453 | -1980.7203
Sanlando - I&I Corrections Future | 1 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - I&I Corrections Future - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - I&I Corrections Future - IDC | 1 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - ENG Powerline 16" FM & WM | 2018098 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 40550 | 12850 | 43090 | 43090 | 139580 | -139580
Sanlando - ENG Powerline 16" FM & WM - Captime | 2018098 | Project Captime | 0 | 0 | 0 | 0 | 0 | 1134.52 | 939.175 | 0 | 0 | 2073.695 | -2073.695
Sanlando - ENG Powerline 16" FM & WM - IDC | 2018098 | IDC | 0 | 0 | 0 | 0 | 0 | 1634.16 | 2268.1858 | 2995.7518 | 3968.5085 | 10866.606 | -10866.606
Sanlando - Const - Powerline 16" FM & WM | 1 | Capital Spending | 0 | 1050000 | 1050000 | 500000 | 2600000 | 0 | 0 | 1550000 | 2026000 | 3576000 | -976000
Sanlando - Const - Powerline 16" FM & WM - Captime | 1 | Project Captime | 0 | 15750 | 15750 | 7500 | 39000 | 0 | 7500 | 7500 | 7500 | 22500 | 16500
Sanlando - Const - Powerline 16" FM & WM - IDC | 1 | IDC | 0 | 16039.5375 | 40098.8438 | 30551.5 | 86689.8813 | 0 | 56.4375 | 23609.6875 | 65934.05 | 89600.175 | -2910.2937
Sanlando - UIF CIP Analysis/Modeling | 2019088 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 7400 | 0 | 0 | 0 | 7400 | -7400
Sanlando - UIF CIP Analysis/Modeling - Captime | 2019088 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - UIF CIP Analysis/Modeling - IDC | 2019088 | IDC | 0 | 0 | 0 | 0 | 0 | 1897.05 | 1338.94 | 0 | 0 | 3235.99 | -3235.99
Sanlando - ENG F5/C1/L2 FM | 1 | Capital Spending | 65000 | 65000 | 65000 | 65000 | 260000 | 0 | 0 | 97250 | 97250 | 194500 | 65500
Sanlando - ENG F5/C1/L2 FM - Captime | 1 | Project Captime | 975 | 975 | 975 | 975 | 3900 | 0 | 0 | 0 | 0 | 0 | 3900
Sanlando - ENG F5/C1/L2 FM - IDC | 1 | IDC | 992.9237 | 2482.3094 | 3971.695 | 5461.0806 | 12908.0087 | 0 | 0 | 1463.6125 | 3659.0312 | 5122.6438 | 7785.365
Sanlando - F5 FM | 1 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - F5 FM - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - F5 FM - IDC | 1 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - C1 FM | 1 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - C1 FM - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - C1 FM - IDC | 1 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - ENG - Wekiva WWTF Headworks | 2020031 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 7630.5 | 92369.5 | 43715 | 43000 | 186715 | -186715
Sanlando - ENG - Wekiva WWTF Headworks - Captime | 2020031 | Project Captime | 0 | 0 | 0 | 0 | 0 | 868.06 | 1081 | 0 | 0 | 1949.06 | -1949.06
Sanlando - ENG - Wekiva WWTF Headworks - IDC | 2020031 | IDC | 0 | 0 | 0 | 0 | 0 | 70.14 | 1724.0567 | 2959.4108 | 3935.5162 | 8689.1236 | -8689.1236
Sanlando - Const - Wekiva WWTF Headworks | 1 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 2000000 | -2000000
Sanlando - Const - Wekiva WWTF Headworks - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - Const - Wekiva WWTF Headworks - IDC | 1 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15050 | 37625 | 52675 | -52675
Sanlando - L2 FM | 1 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - L2 FM - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - L2 FM - IDC | 1 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - ENG F1/L6/M10 FM | 1 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - ENG F1/L6/M10 FM - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - ENG F1/L6/M10 FM - IDC | 1 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - WM & Service Line Replacement | 1 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - WM & Service Line Replacement - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - WM & Service Line Replacement - IDC | 1 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanlando - Well Panel Replacements | 1 | Capital Spending | 0 | 87500 | 87500 | 0 | 175000 | 0 | 0 | 74500 | 0 | 74500 | 100500
Sanlando - Well Panel Replacements - Captime | 1 | Project Captime | 0 | 1312.5 | 1312.5 | 0 | 2625 | 0 | 0 | 1312.5 | 0 | 1312.5 | 1312.5
Sanlando - Well Panel Replacements - IDC | 1 | IDC | 0 | 1336.6281 | 3341.5703 | 0 | 4678.1984 | 0 | 0 | 1140.9781 | 0 | 1140.9781 | 3537.2203
Sanlando - E.E. Williamson Utility Relocations | 1 | Capital Spending | 200000 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000
Sanlando - E.E. Williamson Utility Relocations - Captime | 1 | Project Captime | 3000 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000
Sanlando - E.E. Williamson Utility Relocations - IDC | 1 | IDC | 3055.15 | 0 | 0 | 0 | 3055.15 | 0 | 0 | 0 | 0 | 0 | 3055.15
Sanlando - GST Deficiency Corrections | 2020030 | Capital Spending | 100000 | 0 | 0 | 0 | 100000 | 0 | 77496 | 0 | 0 | 77496 | 22504
Sanlando - GST Deficiency Corrections - Captime | 2020030 | Project Captime | 1500 | 0 | 0 | 0 | 1500 | 1206.91 | 1500 | 0 | 0 | 2706.91 | -1206.91
Sanlando - GST Deficiency Corrections - IDC | 2020030 | IDC | 1527.575 | 0 | 0 | 0 | 1527.575 | 11.87 | 1790.0469 | 0 | 0 | 1801.9169 | -274.3419
Sanlando - Lift Station Mechanical Rehab | 1 | Capital Spending | 0 | 170000 | 170000 | 0 | 340000 | 0 | 0 | 170000 | 370000 | 540000 | -200000
Sanlando - Lift Station Mechanical Rehab - Captime | 1 | Project Captime | 0 | 2550 | 2550 | 0 | 5100 | 0 | 0 | 2550 | 2550 | 5100 | 0
Sanlando - Lift Station Mechanical Rehab - IDC | 1 | IDC | 0 | 2596.8775 | 6492.1938 | 0 | 9089.0713 | 0 | 0 | 2596.8775 | 9502.1937 | 12099.0712 | -3010
Sanlando - G/L Spending |  | GL Spending | 247500 | 247500 | 247500 | 247500 | 990000 | 101068.89 | 160000 | 175000 | 175000 | 611068.89 | 378931.11
Sanlando - Captime |  | GL Captime | 25508.25 | 25508.25 | 25508.25 | 25508.25 | 102033 | 35140.73 | 25508.25 | 25508.25 | 25508.25 | 111665.48 | -9632.48
Sanlando - Cap Suspense |  | Cap Suspense | 0 | 0 | 0 | 0 | 0 | 74406.23 | -74406.23 | 0 | 0 | 0 | 0
Sandalhaven - L/S RTU Installation | 1 | Capital Spending | 130000 | 0 | 0 | 0 | 130000 | 0 | 0 | 0 | 0 | 0 | 130000
Sandalhaven - L/S RTU Installation - Captime | 1 | Project Captime | 1950 | 0 | 0 | 0 | 1950 | 0 | 0 | 0 | 0 | 0 | 1950
Sandalhaven - L/S RTU Installation - IDC | 1 | IDC | 1985.8475 | 0 | 0 | 0 | 1985.8475 | 0 | 0 | 0 | 0 | 0 | 1985.8475
Sandalhaven - Smoke Testing/I&I Investigation | 1 | Capital Spending | 60000 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 60000
Sandalhaven - Smoke Testing/I&I Investigation - Captime | 1 | Project Captime | 900 | 0 | 0 | 0 | 900 | 0 | 0 | 900 | 0 | 900 | 0
Sandalhaven - Smoke Testing/I&I Investigation - IDC | 1 | IDC | 916.545 | 0 | 0 | 0 | 916.545 | 0 | 0 | 13.545 | 0 | 13.545 | 903
Sandalhaven - G/L Spending |  | GL Spending | 15000 | 15000 | 15000 | 15000 | 60000 | 2241.2 | 5000 | 55000 | 10000 | 72241.2 | -12241.2
Sandalhaven - Captime |  | GL Captime | 2491.2796 | 2491.2796 | 2491.2796 | 2491.2796 | 9965.1182 | 451.8 | 2364.9058 | 2364.9058 | 2364.9058 | 7546.5175 | 2418.6007
Sandalhaven - Cap Suspense |  | Cap Suspense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Labrador - Engineering WWTP Master Plan | 1 | Capital Spending | 45000 | 0 | 0 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 45000
Labrador - Engineering WWTP Master Plan - Captime | 1 | Project Captime | 675 | 0 | 0 | 0 | 675 | 0 | 0 | 0 | 0 | 0 | 675
Labrador - Engineering WWTP Master Plan - IDC | 1 | IDC | 687.4087 | 0 | 0 | 0 | 687.4087 | 0 | 0 | 0 | 0 | 0 | 687.4087
Labrador - Construction WWTP Master Plan | 1 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Labrador - Construction WWTP Master Plan - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Labrador - Construction WWTP Master Plan - IDC | 1 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Labrador - G/L Spending |  | GL Spending | 12500 | 12500 | 12500 | 12500 | 50000 | 7773.45 | 19500 | 12500 | 12500 | 52273.45 | -2273.45
Labrador - Captime |  | GL Captime | 5900.3989 | 5900.3989 | 5900.3989 | 5900.3989 | 23601.5958 | 2823.75 | 5601.0928 | 5601.0928 | 5601.0928 | 19627.0284 | 3974.5674
Labrador - Cap Suspense |  | Cap Suspense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pennbrooke - WWTP Diffuser Replacement | 1 | Capital Spending | [5 empty] | 0 | 34000 | 0 | 0 | 34000 | -34000
Pennbrooke - WWTP Diffuser Replacement - Captime | 1 | Project Captime | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Pennbrooke - WWTP Diffuser Replacement - IDC | 1 | IDC | [5 empty] | 0 | 255.85 | 0 | 0 | 255.85 | -255.85
Pennbrooke - G/L Spending |  | GL Spending | 22500 | 22500 | 22500 | 22500 | 90000 | 51645.98 | 8089 | 22500 | 22500 | 104734.98 | -14734.98
Pennbrooke - Captime |  | GL Captime | 8844.6773 | 8844.6773 | 8844.6773 | 8844.6773 | 35378.709 | 3207.79 | 8396.0184 | 8396.0184 | 8396.0184 | 28395.8452 | 6982.8638
Pennbrooke - Cap Suspense |  | Cap Suspense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FL Cost Center - 15KW Generator Fleet - Captime | 2018151 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FL Cost Center - 15KW Generator Fleet - IDC | 2018151 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FL Cost Center - AMI Meters | 1 | Capital Spending | 250000 | 250000 | 250000 | 250000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 1000000
FL Cost Center - AMI Meters - Captime | 1 | Project Captime | 3750 | 3750 | 3750 | 3750 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
FL Cost Center - AMI Meters - IDC | 1 | IDC | 3818.9375 | 9547.3438 | 15275.75 | 21004.1562 | 49646.1875 | 0 | 0 | 0 | 0 | 0 | 49646.1875
FL Cost Center - Regional Office Modifications | 1 | Capital Spending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FL Cost Center - Regional Office Modifications - Captime | 1 | Project Captime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FL Cost Center - Regional Office Modifications - IDC | 1 | IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FL Cost Center - Fleet Replacements | 1 | Capital Spending | 87500 | 87500 | 87500 | 87500 | 350000 | 759.28 | 214025.52 | 0 | 0 | 214784.8 | 135215.2
FL Cost Center - Dump Truck |  | Project Captime | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
FL Cost Center - Dump Truck - Captime |  | IDC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
FL Cost Center - Dump Truck - IDC |  | Capital Spending | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
FL Cost Center - G/L Spending |  | GL Spending | 12500 | 12500 | 12500 | 12500 | 50000 | 0 | 17490.52 | 0 | 0 | 17490.52 | 32509.48
FL Cost Center - Captime |  | GL Captime | 0 | 0 | 0 | 0 | 0 | -18554.24 | 497 | 0 | 0 | -18057.24 | 18057.24
FL Cost Center - Cap Suspense |  | Cap Suspense | 0 | 0 | 0 | 0 | 0 | 0 | 225.9 | 0 | 0 | 225.9 | -225.9