## Proforma Project Roster
Utilities, Inc. of Florida
Docket No. 2020139
Test Year Ended December 31, 2019
Proforma Project Roster
CP# | Project Name | System | Exhibit# | W, S or Both | Project Start | Projected PIS Date | Projected Cost | Cost to Date | Primary Contractor | Additional Contractors | Ret's? | Comment
2020098 | CL I&I Investigation | CL | 1 | S | 2020-05-01 | 2020-09-30 | 50000 | 42500 | Specialized Plumbing Tech. |  | N
2020129 | ER LS 3 & 8 Remediation | ER | 2 | S | 2020-06-15 | 2020-09-30 | 81890 | 0 | Innovative Contractors |  | Y
2019024 | ER/CC SCADA & RTUs | ER | 3 | S | 2019-03-01 | 2020-07-01 | 229000 | 180072.33 | Sanders Company | Bailey Engineering/Ellis Automated | N
2019125 | Eng ER Site Improvements | ER | 4 | S | 2018-10-01 | 2020-07-01 | 162000 | 161958.07 | Kimley-Horn & Assoc. |  | N
2019175 | ER Site Improvements | ER | 5 | S | 2019-11-29 | 2020-06-30 | 657175 | 657175 | Wholesale Vinyl Fence | Sunny Grove/C&C Tree Service/Davey Tree Service | Y
None | LB WWTP Master Plan | LB | 6 | S | 2019-08-01 | 2020-08-31 | 43500 | 43500 | Kimley-Horn & Assoc. |  | N
2019078 | Longwood LS RTUs | LW | 7 | S | 2019-04-08 | 2020-01-31 | 122024 | 122024 | Sanders Company | Bailey Engineering | N
2020028 | Eng - Crescent Bay Raw WM | LUSI | 8 | W | 2020-02-03 | 2020-10-31 | 70000 | 61440.68 | Kimley-Horn & Assoc. |  | N
2020133 | LUSI Crescent Bay Raw WM | LUSI | 9 | W | 2020-06-30 | 2020-10-31 | 486514 | 0 | Tri-Sure Corp |  | N
2020029 | LG Sulfuric Acid Equipment Replace | LUSI | 10 | W | 2020-02-03 | 2020-04-01 | 54303 | 54303 | Odyssey Mftg |  | Y
None | LG Hydrochloric Acid Storage Tank | LUSI | 11 | W | 2020-02-22 | 2020-03-31 | 29992 | 29992 | Odyssey Mftg |  | N
None | LG RAS Pumps | LUSI | 12 | S | 2021-01-01 | 2021-03-31 | 43000 | 0 | Danus Utilities | Xylem Pumps | Y
2020106 | Barrington WWTP Improvements | LUSI | 13 | S | 2020-05-25 | 2021-03-30 | 380000 | 34300 | Danus Utilities | Kimley-Horn & Assoc. | N
2019145 | MC Master Lift Station | MC | 14 | S | 2020-05-15 | 2021-03-31 | 2103578 | 229736.94 | Kamminga & Roodvoets | Kimley-Horn & Assoc. | Y
2019154 | MC LS 4 & LS 7 Generators | MC | 15 | S | 2019-10-14 | 2020-09-30 | 116530 | 109035 | Paramount Power | Kimley-Horn & Assoc. | N
2020127 | MC Curlew Creek I&I Remediation | MC | 16 | S | 2020-06-29 | 2020-10-31 | 700027 | 7735 | Insituform Technologies | TLC Diversified/Kimley-Horn/SPT/T-N-T/UGF LLC | N
2019145 | MC Headworks | MC | 17 | S | 2020-03-20 | 2021-06-30 | 2424782 | 229736.94 | TLC Diversified | Kimley-Horn & Assoc. | N
2020128 | MC Eng LS 10 FM Relocation | MC | 18 | S | 2020-05-29 | 2021-12-31 | 55750 | 35744 | Kimley-Horn & Assoc. |  | Y
None | PB Diffuser Replacement | PB | 19 | S | 2020-03-15 | 2020-04-01 | 34000 | 34000 | ECO-2000 | Evoqua | Y
2020091 | SH SCADA RTUs | SH | 20 | S | 2020-06-01 | 2021-03-31 | 128000 | 0 | Sanders Company |  | N
None | SH I&I Investigation | SH | 21 | S | 2021-01-30 | 2021-04-30 | 56500 | 0 | Specialized Plumbing Tech. |  | N
2018109 | Eng-Wekiva WWTP Improvements | SUC | 22 | S | 2018-08-06 | 2020-12-31 | 278820 | 278820 | Kimley-Horn & Assoc. |  | Y | Eng services and construction costs booked to separate projects #'s.
2019109 | Wekiva WWTP improvements | SUC | 22 | S | 2019-07-08 | 2020-12-31 | 6004626 | 4199326.91 | Florida Env. Construction |  | Y
2020031 | Sanlando Wekiva Headworks | SUC | 23 | S | 2020-02-01 | 2021-06-30 | 2750000 | 144548.06 | Florida Env. Construction | Kimley-Horn & Assoc. | Y
2020111 | Sanlando Well Panel Replace | SUC | 24 | W | 2020-05-29 | 2020-09-30 | 74500 | 0 | North Lake Electric |  | Y
2018098 | SUC 16" FM & WM Replacement | SUC | 25 | W | 2018-08-01 | 2020-12-31 | 1826379 | 108273.81 | Tri-Sure Corp | Kimley-Horn & Assoc. | Y | Project includes both W&S assets
2018098 | SUC 16" FM & WM Replacement | SUC | 25 | S | 2018-08-01 | 2020-12-31 | 1935871 |  | Tri-Sure Corp | Kimley-Horn & Assoc. | Y | Project includes both W&S assets
2020113 | SUC Eng F5/C1/L2 FM Replace | SUC | 26 | S | 2020-04-30 | 2021-12-31 | 194500 | 0 | Kimley-Horn & Assoc. |  | Y
2020107 | Sanlando I&I Remediation Ph. 4 | SUC | 27 | S | 2020-06-01 | 2020-10-30 | 1996092 | 74406 | Atlantic Pipe Services |  | N
2020136 | EE Williamson Utility Relocates | SUC | 28 | W | 2020-06-30 | 2021-12-31 | 105837 | 5169 | Central Florida Tapping | Kimley-Horn & Assoc. | Y | Project includes both W&S assets
2020136 | EE Williamson Utility Relocates | SUC | 28 | S | 2020-06-30 | 2021-12-31 | 317514 | 15506 | Central Florida Tapping | Kimley-Horn & Assoc. | Y | Project includes both W&S assets
2020137 | Sanlando LS Mechanical Rehabs | SUC | 29 | S | 2020-07-06 | 2020-11-30 | 510040 | 0 | Central Florida Lift Stations |  | Y
2019088 | SUC CIP Analysis & FM Modeling | SUC | 30 | W | 2019-05-24 | 2020-02-01 | 21320 | 98280 | Kimley-Horn & Assoc. |  | N | Project includes both W&S assets
2019088 | SUC CIP Analysis & FM Modeling | SUC | 30 | S | 2019-05-24 | 2020-02-01 | 76960 |  | Kimley-Horn & Assoc. |  | N | Project includes both W&S assets
2020030 | Sanlando GST deficiencies | SUC | 31 | W | 2020-02-24 | 2020-10-30 | 145919 | 77496 | Precon Corp. |  | Y
2018116 | TV I&I Redzone Inspection | TV | 32 | S | 2018-08-31 | 2020-11-30 | 270364 | 95300 | Redzone | Insituform/T-N-T | N
2019087 | TV LS 4/FM/GSM Relocations | TV | 33 | S | 2019-06-01 | 2021-12-31 | 556767 | 551267 | McKenzie Contracting | Left Coast Utilities/Ellis Automated/K-H & Assoc | Y
2019173 | TV LS 4 Replacement | TV | 34 | S | 2019-11-30 | 2021-12-31 | 908982 | 15601.77 | TLC Diversified | Kimley-Horn & Assoc. | Y
2020041 | BV W2 Pump & W3 Hydro tank | UIF | 35 | W | 2020-01-01 | 2020-08-31 | 95000 | 37340 | EESI |  | Y
2020004 | OW W1 tank and generator | UIF | 36 | W | 2019-11-01 | 2020-07-31 | 165000 | 155180 | Green Well Drilling | Paramount Power | Y
2019076 | UIF Seminole RTUs | UIF | 37 | S | 2019-04-08 | 2020-01-31 | 93876 | 93876 | Sanders Company | Bailey Engineering | N
2019174 | ST Chlorine Dioxide Pilot Study | UIF | 38 | W | 2020-01-31 | 2020-12-30 | 52000 | 27919.01 | Kimley-Horn & Assoc. |  | N
| Summertree I&I Investigation Pointe West | UIF | 39 | S | 2020-07-01 | 2020-11-30 | 500000 | 56500 | Specialized Plumbing Tech. |  | N
2020112 | Golden Hills GIP Replacement | UIF | 40 | W | 2020-04-20 | 2020-08-01 | 75160 | 75160 | ECO-2000 |  | Y
2019146 | GH WM Relocation | UIF | 41 | W | 2019-09-18 | 2020-01-31 | 154764 | 154764 | Traverse Group |  | Y
2019110 | Little Wekiva WTP generator | UIF | 42 | W | 2019-07-01 | 2020-06-30 | 95397 | 95397 | North Lake Electric |  | N
2019111 | Park Ridge WTP generator | UIF | 43 | W | 2019-07-15 | 2020-06-30 | 99137 | 99137 | North Lake Electric |  | N
2020135 | Ravenna Park I&I Remediation | UIF | 44 | S | 2020-06-01 | 2020-10-30 | 651568 | 0 | Traverse Group | Atlantic Pipe Services | N
2020103 | Northwestern Bridge utility relocation | UIF | 45 | W | 2018-02-14 | 2021-08-31 | 76000 | 6005 | Traverse Group | Kimley-Horn & Assoc. | Y
| TOTAL | [5 empty] | 28060958 | 8498525.52