## Sheet1
FPL 067704
20210015-EI
|  |  |  | Cost Performance |  |  |  | Schedule Performance |  |  | Calc Support
$MM
Project | # of MWs | # of Projects | Region | Approved | Actual / Forecast | Fav / | % Variance | Approved | Actual / Forecast | Days |  | # Proj on/ahead of Sched | # Days ahead of Sched
|  |  |  | Plan |  | (Unfav) |  | Plan |  | Fav /
(Unfav)
FOSSIL PROJECTS
Martin Unit 8 | 787 |  | FL | 439 | 391.2 | 47.8 | 10.89% | 2005-06-30 | 2005-06-30 | 0 |  |  | 0
Manatee Unit 3 | 1107 |  | FL | 551 | 476.8 | 74.2 | 13.47% | 2005-06-30 | 2005-06-30 | 0 |  |  | 0
2005 - Total | 1894 | 2 |  | 990 | 868 | 122 | 12.32% |  |  | 0 |  | 2
Turkey Point Unit 5 | 1144 |  | FL | 580.3 | 552.4 | 27.9 | 4.808% | 2007-06-01 | 2007-05-01 | 31 |  |  | 31
2007 - Total | 1144 | 1 |  | 580.3 | 552.4 | 27.9 | 4.808% |  |  | 31 |  | 1
West County 1 (1) | 1219 |  | FL | 688.6 | 742 | -53.4 | -7.755% | 2009-06-01 | 2009-08-27 | -87 | Late |  | 0
West County 2 (2) | 1219 |  | FL | 632.4 | 578.8 | 53.6 | 8.476% | 2009-12-31 | 2009-11-03 | 58 |  |  | 58
2009 - Total | 2438 | 2 |  | 1321 | 1320.8 | 0.2 | 0.01514% |  |  | -29 |  | 1
West County 3 | 1219 |  | FL | 864.7 | 842.4 | 22.3 | 2.579% | 2011-06-01 | 2011-05-23 | 9 |  |  | 9
2011 - Total | 1219 | 1 |  | 864.7 | 842.4 | 22.3 | 2.579% |  |  | 9 |  | 1
Cape Canaveral | 1210 |  | FL | 1115 | 962.8 | 152.2 | 13.65% | 2013-06-01 | 2013-04-24 | 38 |  |  | 38
Manatee Units 1&2 ESP Project | 0 |  | FL | 153.9 | 108 | 45.9 | 29.82% | 2013-08-12 | 2013-07-26 | 17 |  |  | 17
2013 - Total | 1210 | 2 |  | 1268.9 | 1070.8 | 198.1 | 15.61% |  |  | 55 |  | 2
Riviera Beach | 1212 |  | FL | 1276 | 1272 | 4 | 0.3135% | 2014-06-01 | 2014-04-01 | 61 |  |  | 61
2014 - Total | 1212 | 1 |  | 1276 | 1272 | 4 | 0.3135% |  |  | 61 |  | 1
Martin Units 1&2 ESP Project | 0 |  | FL | 148.9 | 107 | 41.9 | 28.14% | 2014-05-21 | 2014-04-16 | 35 |  |  | 35
2015 - Total | 0 | 1 |  | 148.9 | 107 | 41.9 | 28.14% |  |  | 35 |  | 1
Port Everglades Energy Center | 1237 |  | FL | 1185 | 1139.5 | 45.5 | 3.84% | 2016-06-01 | 2016-04-01 | 61 |  |  | 61
2015 - Total | 1237 | 1 |  | 1185 | 1139.5 | 45.5 | 3.84% |  |  | 61 |  | 1
Okeechobee Clean Energy Cntr | 1778 |  | FL | 1231.7 | 1223.3 | 8.4 | 0.682% | 2019-06-01 | 2019-03-31 | 62 |  |  | 62
2019 - Total | 1778 | 1 |  | 1231.7 | 1223.3 | 8.4 | 0.682% |  |  | 62 |  | 1
Dania Beach Energy Center | 1163 |  | FL | 888 | 888 | 0 | 0%
2022 - Total | 1163 | 1 |  | 888 | 888 | 0 | 0%
Total Fossil Projects | 13295 | 13 |  | 9754.5 | 9284.2 | 470.3 | 4.821% |  |  | 285 |  | 11 | 372