## SPP LUG Change Log
Change ID # | FID | Ckt No | Substation | Original Start Year | New Start Year | Original Cons Yr | New Cons Yr | Original ISD | Revised ISD | Service Area | Contractor Name | Null / Previous Project Name | Null / Previous WO | Designated Survivor / New Project Name | Designated Survivor / New WO | Change ID # | Null / Existing OH WR | Null / Existing UG WR | Designated Survivor / New OH WR | Designated Survivor / New UG WR | Date Change Made | Date Change Provided to Contractor | Comments | JE Required | JE Action | JE Entered | JE Posted
LUG C001 | 90568909 | 13605 | MACDILL | 2021 | 2020 | 2021 | 2021 | 2021-11-15 | 2021-10-15 | WSA | Enercon | LUG WSA 13605.90568909 | LUG - TBD496 | LUG WSA 13605.91052996 | PRE-09361.71 | LUG C001 | N/A | N/A | 2273278 | 2273280 | 2020-10-01 | 2020-10-01 | financial tracking updated 10/27 | No | Null
LUG C001 | 91052996 | 13605 | MACDILL | 2020 | 2020 | 2021 | 2021 | 2021-10-15 | 2021-10-15 | WSA | Enercon | LUG WSA 13605.91052996 | PRE-09361.71 | LUG WSA 13605.91052996 | PRE-09361.71 | LUG C001 | 2273278 | 2273280 | 2273278 | 2273280 | 2020-10-01 | 2020-10-01 | financial tracking updated 10/27 | No | Null
LUG C001 | 90427351 | 13605 | MACDILL | 2021 | 2020 | 2021 | 2021 | 2021-10-15 | 2021-10-15 | WSA | Enercon | LUG WSA 13605.90427351 | LUG - TBD526 | LUG WSA 13605.91052996 | PRE-09361.71 | LUG C001 | N/A | N/A | 2273278 | 2273280 | 2020-10-01 | 2020-10-01 | financial tracking updated 10/27 | No | Null
LUG C002 | 10913196 | 13174 | MADISON | 2020 | 2020 | 2021 | 2021 | 2021-03-15 | 2021-03-15 | ESA | Leidos | LUG ESA 13174.10913196 | PRE-09361.17 | LUG ESA 13174.10913196 | PRE-09361.17 | LUG C002 | 2277381 | 2277382 | 2277381 | 2277382 | 2020-11-03 | 2020-11-13 | financial tracking updated 11/12 | No | Null
LUG C002 | 93310101 | 13174 | MADISON | 2021 | 2020 | 2022 | 2021 | 2021-10-15 | 2021-03-15 | ESA | Leidos | LUG ESA 13174.93310101 | LUG - TBD373 | LUG ESA 13174.10913196 | PRE-09361.17 | LUG C002 | N/A | N/A | 2277381 | 2277382 | 2020-11-03 | 2020-11-13 | financial tracking updated 11/12 | No | Null
LUG C003 | 10913197 | 13174 | MADISON | 2021 | 2020 | 2022 | 2022 | 2021-10-15 | 2020-12-15 | ESA | Leidos | LUG ESA 13174.10913197 | LUG - TBD382 | LUG ESA 13174.60451701 | PRE-09361.13 | LUG C003 | N/A | N/A | 2277343 | 2277348 | 2020-11-03 | 2020-11-13 | financial records updated 11/13/20 | No | Null
LUG C003 | 60451701 | 13174 | MADISON | 2020 | 2020 | 2020 | 2020 | 2020-12-15 | 2020-12-15 | ESA | Leidos | LUG ESA 13174.60451701 | PRE-09361.13 | LUG ESA 13174.60451701 | PRE-09361.13 | LUG C003 | 2277343 | 2277348 | 2277343 | 2277348 | 2020-11-03 | 2020-11-13 | financial records updated 11/13/20 | No | Null
LUG C004 | 10868138 | 13231 | BRANDON | 2020 | 2020 | 2021 | 2021 | 2021-04-15 | 2021-04-15 | ESA | Leidos | LUG ESA 13231.10868138 | PRE-09361.20 | LUG ESA 13231.10868138 | PRE-09361.20 | LUG C004 | 2290199 | 2290200 | 2290199 | 2290200 | 2020-11-03 | 2020-11-13 | financial docs updated 11/13/20 | No | Null
LUG C004 | 10868120 | 13231 | BRANDON | 2021 | 2020 | 2022 | 2021 | 2021-10-15 | 2021-04-15 | ESA | Leidos | LUG ESA 13231.10868120 | LUG - TBD381 | LUG ESA 13231.10868138 | PRE-09361.20 | LUG C004 | N/A | N/A | 2290199 | 2290200 | 2020-11-03 | 2020-11-13 | financial docs updated 11/13/20 | No | Null
LUG C005 | 60140423 | 13454 | LAKEWOOD | 2020 | 2020 | 2021 | 2021 | 2021-04-15 | 2021-04-15 | ESA | Leidos | LUG ESA 13454.60140423 | PRE-09361.104 | LUG ESA 13454.90429155 | PRE-09361.128 | LUG C005 | 2290450 | 2290459 | 2277417 | 2277418 | 2020-11-03 | 2020-11-13 | financial docs updated 11/13/20 | Yes | s/b 0
LUG C005 | 10472634 | 13454 | LAKEWOOD | 2020 | 2020 | 2021 | 2021 | 2021-12-15 | 2021-04-15 | ESA | Leidos | LUG ESA 13454.10472634 | PRE-09361.130 | LUG ESA 13454.90429155 | PRE-09361.128 | LUG C005 | 2277422 | 2277423 | 2277417 | 2277418 | 2020-11-03 | 2020-11-13 | financial docs updated 11/13/20 | Yes | s/b 0
LUG C005 | 90429155 | 13454 | LAKEWOOD | 2020 | 2020 | 2021 | 2021 | 2021-12-15 | 2021-04-15 | ESA | Leidos | LUG ESA 13454.90429155 | PRE-09361.128 | LUG ESA 13454.90429155 | PRE-09361.128 | LUG C005 | 2277417 | 2277418 | 2277417 | 2277418 | 2020-11-03 | 2020-11-13 | financial docs updated 11/13/20 | Yes | DS
LUG C006 | 90598389 | 13171 | MADISON | 2020 | 2020 | 2021 | 2021 | 2021-03-15 | 2021-03-15 | ESA | Leidos | LUG ESA 13171.90598389 | PRE-09361.18 | LUG ESA 13171.90598389 | PRE-09361.18 | LUG C006 | 2277383 | 2277385 | 2277383 | 2277385 | 2020-11-03 | 2020-11-13 | financial docs updated 11/13/20 | Yes | DS
LUG C006 | 90374558 | 13171 | MADISON | 2020 | 2020 | 2021 | 2021 | 2021-08-15 | 2021-03-15 | ESA | Leidos | LUG ESA 13171.90374558 | PRE-09361.118 | LUG ESA 13171.90598389 | PRE-09361.18 | LUG C006 | 2290542 | 2290543 | 2277383 | 2277385 | 2020-11-03 | 2020-11-13 | financial docs updated 11/13/20 | Yes | s/b 0
LUG C006 | 10455414 | 13171 | MADISON | 2021 | 2020 | 2022 | 2021 | 2021-10-15 | 2021-03-15 | ESA | Leidos | LUG ESA 13171.10455414 | LUG - TBD376 | LUG ESA 13171.90598389 | PRE-09361.18 | LUG C006 | N/A | N/A | 2277383 | 2277385 | 2020-11-03 | 2020-11-13 | financial docs updated 11/13/20 | No | Null
LUG C007 | 92884623 | 13796 | SAINT CLOUD | 2020 | 2020 | 2021 | 2021 | 2021-12-15 | 2021-12-15 | ESA | Leidos | LUG ESA 13796.92884623 | PRE-09361.119 | LUG ESA 13796.92884623 | PRE-09361.119 | LUG C007 | 2277391 | 2277392 | 2277391 | 2277392 | 2020-11-04 | 2020-11-13 | financial docs updated 11/13/20 | No | Null
LUG C007 | 92884644 | 13796 | SAINT CLOUD | 2021 | 2020 | 2022 | 2021 | 2022-06-15 | 2021-12-15 | ESA | Leidos | LUG ESA 13796.92884644 | LUG - TBD440 | LUG ESA 13796.92884623 | PRE-09361.119 | LUG C007 | N/A | N/A | 2277391 | 2277392 | 2020-11-04 | 2020-11-13 | financial docs updated 11/13/20 | No | Null
LUG C008 | 90882614 | 13099 | SUNSET LANE | 2020 | 2020 | 2021 | 2021 | 2021-03-15 | 2021-03-15 | CSA | Pike | LUG CSA 13099.90882614 | PRE-09361.78 | LUG CSA 13099.90882614 | PRE-09361.78 | LUG C008 | 2275116 | 2275117 | 2275116 | 2275117 | 2020-12-11 | 2020-12-11 | financial docs updated 12/11/2020 | No | Null
LUG C008 | 60563698 | 13099 | SUNSET LANE | 2021 | 2020 | 2021 | 2021 | 2021-07-15 | 2021-03-15 | CSA | Pike | LUG CSA 13099.60563698 | LUG - TBD172 | LUG CSA 13099.90882614 | PRE-09361.78 | LUG C008 | N/A | N/A | 2275116 | 2275117 | 2020-12-11 | 2020-12-11 | financial docs updated 12/11/2020 | No | Null
LUG C009 | 91004837 | 13093 | PLYMOUTH STREET | 2020 | 2020 | 2020 | 2021 |  |  | CSA | Pike | LUG CSA 13093.91004837 | PRE-09361.79 | LUG CSA 13093.91004837 | PRE-09361.79 | LUG C009 | 2275118 | 2275120 | 2275118 | 2275120 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | Yes | DS
LUG C009 | 91004843 | 13093 | PLYMOUTH STREET | 2020 | 2020 | 2020 | 2021 |  |  | CSA | Pike | LUG CSA 13093.91004843 | PRE-09361.83 | LUG CSA 13093.91004837 | PRE-09361.79 | LUG C009 | 2275131 | 2275132 | 2275118 | 2275120 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | Yes | s/b 0
LUG C009 | 60029740 | 13093 | PLYMOUTH STREET | 2020 | 2020 | 2022 | 2021 |  |  | CSA | Pike | LUG CSA 13093.60029740 | LUG - TBD245 | LUG CSA 13093.91004837 | PRE-09361.79 | LUG C009 | N/A | N/A | 2275118 | 2275120 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | No | Null
LUG C010 | 60059346 | 13205 | TEMPLE TERRACE | [6 empty] | CSA | Pike | LUG CSA 13205.60059346 | PRE-09361.29 | LUG CSA 13205.90998414 | PRE-09361.81 | LUG C010 | 2274986 | 2274989 | 2275124 | 2275125 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | Yes | s/b 0
LUG C010 | 90998414 | 13205 | TEMPLE TERRACE | [6 empty] | CSA | Pike | LUG CSA 13205.90998414 | PRE-09361.81 | LUG CSA 13205.90998414 | PRE-09361.81 | LUG C010 | 2275124 | 2275125 | 2275124 | 2275125 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | Yes | DS
LUG C011 | 92407065 | 13815 | BLANTON | [6 empty] | DCA | Pike | LUG DCA 13815.92407065 | PRE-09361.25 | LUG DCA 13815.93026469 | PRE-09361.27 | LUG C011 | 2274969 | 2274971 | 2274978 | 2274982 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | Yes | s/b 0
LUG C011 | 90288627 | 13815 | BLANTON | [6 empty] | DCA | Pike | LUG DCA 13815.90288627 | PRE-09361.26 | LUG DCA 13815.93026469 | PRE-09361.27 | LUG C011 | 2274973 | 2274976 | 2274978 | 2274982 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | Yes | s/b 0
LUG C011 | 93026469 | 13815 | BLANTON | [6 empty] | DCA | Pike | LUG DCA 13815.93026469 | PRE-09361.27 | LUG DCA 13815.93026469 | PRE-09361.27 | LUG C011 | 2274978 | 2274982 | 2274978 | 2274982 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | Yes | DS
LUG C012 | 10786374 | 14040 | HARNEY ROAD | [6 empty] | CSA | Pike | LUG CSA 14040.10786374 | PRE-09361.23 | LUG CSA 14040.10786374 | PRE-09361.23 | LUG C012 | 2271630 | 2271645 | 2271630 | 2271645 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | No | Null
LUG C012 | 90485522 | 14040 | HARNEY ROAD | [6 empty] | CSA | Pike | LUG CSA 14040.90485522 | LUG - TBD226 | LUG CSA 14040.10786374 | PRE-09361.23 | LUG C012 | N/A | N/A | 2271630 | 2271645 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | No | Null
LUG C013 | 91377944 | 13836 | FLORIDA AVENUE | [6 empty] | CSA | Pike | LUG CSA 13836.91377944 | PRE-09361.84 | LUG CSA 13836.91377944 | PRE-09361.84 | LUG C013 | 2275133 | 2275134 | 2275133 | 2275134 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | Yes | DS
LUG C013 | 91406672 | 13836 | FLORIDA AVENUE | [6 empty] | CSA | Pike | LUG CSA 13836.91406672 | PRE-09361.24 | LUG CSA 13836.91377944 | PRE-09361.84 | LUG C013 | 2274929 | 2274966 | 2275133 | 2275134 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | Yes | s/b 0
LUG C013 | 60133704 | 13836 | FLORIDA AVENUE | [6 empty] | CSA | Pike | LUG CSA 13836.60133704 | LUG - TBD216 | LUG CSA 13836.91377944 | PRE-09361.84 | LUG C013 | N/A | N/A | 2275133 | 2275134 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | No | Null
LUG C013 | 93321406 | 13836 | FLORIDA AVENUE | [6 empty] | CSA | Pike | LUG CSA 13836.93321406 | LUG - TBD211 | LUG CSA 13836.91377944 | PRE-09361.84 | LUG C013 | N/A | N/A | 2275133 | 2275134 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | No | Null
LUG C013 | 60133698 | 13836 | FLORIDA AVENUE | [6 empty] | CSA | Pike | LUG CSA 13836.60133698 | LUG - TBD224 | LUG CSA 13836.91377944 | PRE-09361.84 | LUG C013 | N/A | N/A | 2275133 | 2275134 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | No | Null
LUG C014 | 60123654 | 13102 | YUKON | [6 empty] | CSA | Pike | LUG CSA 13102.60123654 | PRE-09361.85 | LUG CSA 13102.60123654 | PRE-09361.85 | LUG C014 | 2275137 | 2275138 | 2275137 | 2275138 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | No | Null
LUG C014 | 60123656 | 13102 | YUKON | [6 empty] | CSA | Pike | LUG CSA 13102.60123656 | LUG - TBD246 | LUG CSA 13102.60123654 | PRE-09361.85 | LUG C014 | N/A | N/A | 2275137 | 2275138 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | No | Null
U - LUG C015 | 10375134 | 13176 | ELEVENTH AVENUE | [6 empty] | CSA | Pike | LUG CSA 13176.10375134 | PRE-09361.87 | LUG CSA 13176.10375134 | PRE-09361.87 | U - LUG C015 | 2275144 | 2275145 | 2275144 | 2275145 | 12/18/20 & 1/29/21 | 12/18/20 & 1/29/21 | financial docs updated 12/18/2020 for combination; re-updated 1/29/2021 for un-combining | No | Null |  | NO LONGER COMBINED | NO LONGER COMBINED
U - LUG C015 | 10375136 | 13176 | ELEVENTH AVENUE | [6 empty] | CSA | Pike | LUG CSA 13176.10375136 | LUG - TBD251 | LUG CSA 13176.10375136 | PRE-09361.482 | U - LUG C015 | N/A | N/A | N/A | N/A | 12/18/20 & 1/29/21 | 12/18/20 & 1/29/21 | financial docs updated 12/18/2020 for combination; re-updated 1/29/2021 for un-combining | No | Null |  | NO LONGER COMBINED | NO LONGER COMBINED
LUG C016 | 91340554 | 13100 | YUKON | [6 empty] | CSA | Pike | LUG CSA 13100.91340554 | PRE-09361.92 | LUG CSA 13100.91340554 | PRE-09361.92 | LUG C016 | 2275159 | 2275160 | 2275159 | 2275160 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | No | Null
LUG C016 | 10371703 | 13100 | YUKON | [6 empty] | CSA | Pike | LUG CSA 13100.10371703 | LUG - TBD188 | LUG CSA 13100.91340554 | PRE-09361.92 | LUG C016 | N/A | N/A | 2275159 | 2275160 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | No | Null
LUG C017 | 92357188 | 13418 | JUNEAU | [6 empty] | CSA | Pike | LUG CSA 13418.92357188 | PRE-09361.90 | LUG CSA 13418.92357188 | PRE-09361.90 | LUG C017 | 2275151 | 2275152 | 2275151 | 2275152 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | No | Null
LUG C017 | 92292295 | 13418 | JUNEAU | [6 empty] | CSA | Pike | LUG CSA 13418.92292295 | LUG - TBD190 | LUG CSA 13418.92357188 | PRE-09361.90 | LUG C017 | N/A | N/A | 2275151 | 2275152 | 2020-12-18 | 2020-12-18 | financial docs updated 12/18/2020 | No | Null
LUG C018 | 91432110 | 13071 | KEYSTONE | [6 empty] | WSA | Enercon | LUG WSA 13071.91432110 | PRE-09361.38 | LUG WSA 13071.91432109 | PRE-09361.39 | LUG C018 | 2272931 | 2272933 | 2272936 | 2272937 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | Yes | s/b 0
LUG C018 | 91432109 | 13071 | KEYSTONE | [6 empty] | WSA | Enercon | LUG WSA 13071.91432109 | PRE-09361.39 | LUG WSA 13071.91432109 | PRE-09361.39 | LUG C018 | 2272936 | 2272937 | 2272936 | 2272937 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | Yes | DS
LUG C019 | 90641822 | 13109 | MANHATTAN | [6 empty] | WSA | Enercon | LUG WSA 13109.90641822 | PRE-09361.55 | LUG WSA 13109.90641822 | PRE-09361.55 | LUG C019 | 2273297 | 2273300 | 2273297 | 2273300 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C019 | 10846390 | 13109 | MANHATTAN | [6 empty] | WSA | Enercon | LUG WSA 13109.10846390 | PRE-09361.254 | LUG WSA 13109.90641822 | PRE-09361.55 | LUG C019 | N/A | N/A | 2273297 | 2273300 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C020 | 92183966 | 13198 | GRAY STREET | [6 empty] | WSA | Enercon | LUG WSA 13198.92183966 | PRE-09361.48 | LUG WSA 13198.92183966 | PRE-09361.48 | LUG C020 | 2273238 | 2273240 | 2273238 | 2273240 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C020 | 10051852 | 13198 | GRAY STREET | [6 empty] | WSA | Enercon | LUG WSA 13198.10051852 | PRE-09361.262 | LUG WSA 13198.92183966 | PRE-09361.48 | LUG C020 | N/A | N/A | 2273238 | 2273240 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C020 | 92585443 | 13198 | GRAY STREET | [6 empty] | WSA | Enercon | LUG WSA 13198.92585443 | PRE-09361.278 | LUG WSA 13198.92183966 | PRE-09361.48 | LUG C020 | N/A | N/A | 2273238 | 2273240 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C021 | 90796385 | 13113 | MANHATTAN | [6 empty] | WSA | Enercon | LUG WSA 13113.90796385 | PRE-09361.67 | LUG WSA 13113.90796385 | PRE-09361.67 | LUG C021 | 2273299 | 2273301 | 2273299 | 2273301 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C021 | 60340774 | 13113 | MANHATTAN | [6 empty] | WSA | Enercon | LUG WSA 13113.60340774 | PRE-09361.171 | LUG WSA 13113.90796385 | PRE-09361.67 | LUG C021 | N/A | N/A | 2273299 | 2273301 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C022 | 60170422 | 13071 | KEYSTONE | [6 empty] | WSA | Enercon | LUG WSA 13071.60170422 | PRE-09361.72 | LUG WSA 13071.60170422 | PRE-09361.72 | LUG C022 | 2273270 | 2273272 | 2273270 | 2273272 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C022 | 93035682 | 13071 | KEYSTONE | [6 empty] | WSA | Enercon | LUG WSA 13071.93035682 | PRE-09361.244 | LUG WSA 13071.60170422 | PRE-09361.72 | LUG C022 | N/A | N/A | 2273270 | 2273272 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C023 | 10501133 | 13509 | STATE RD 574 | [6 empty] | ESA | Leidos | LUG ESA 13509.10501133 | LUG - TBD446 | LUG ESA 13509.10501150 | PRE-09361.127 | LUG C023 | N/A | N/A | 2277415 | 2277416 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C023 | 10501150 | 13509 | STATE RD 574 | [6 empty] | ESA | Leidos | LUG ESA 13509.10501150 | PRE-09361.127 | LUG ESA 13509.10501150 | PRE-09361.127 | LUG C023 | 2277415 | 2277416 | 2277415 | 2277416 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C024 | 60139973 | 13225 | BRANDON | [6 empty] | ESA | Leidos | LUG ESA 13225.60139973 | PRE-09361.121 | LUG ESA 13225.60139973 | PRE-09361.121 | LUG C024 | 2277396 | 2277398 | 2277396 | 2277398 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C024 | 92750192 | 13225 | BRANDON | [6 empty] | ESA | Leidos | LUG ESA 13225.92750192 | LUG - TBD383 | LUG ESA 13225.60139973 | PRE-09361.121 | LUG C024 | N/A | N/A | 2277396 | 2277398 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C025 | 10457704 | 13229 | BRANDON | [6 empty] | ESA | Leidos | LUG ESA 13229.10457704 | LUG - TBD404 | LUG ESA 13229.92525393 | LUG - TBD407 | LUG C025 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C025 | 92525393 | 13229 | BRANDON | [6 empty] | ESA | Leidos | LUG ESA 13229.92525393 | LUG - TBD407 | LUG ESA 13229.92525393 | LUG - TBD407 | LUG C025 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C026 | 10836901 | 13127 | SOUTH SEFFNER | [6 empty] | ESA | Leidos | LUG ESA 13127.10836901 | LUG - TBD414 | LUG ESA 13127.92663180 | LUG - TBD427 | LUG C026 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C026 | 92663180 | 13127 | SOUTH SEFFNER | [6 empty] | ESA | Leidos | LUG ESA 13127.92663180 | LUG - TBD427 | LUG ESA 13127.92663180 | LUG - TBD427 | LUG C026 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C027 | 90130568 | 13911 | PEACH AVENUE | [6 empty] | ESA | Leidos | LUG ESA 13911.90130568 | LUG - TBD423 | LUG ESA 13911.90130568 | LUG - TBD423 | LUG C027 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C027 | 10554588 | 13911 | PEACH AVENUE | [6 empty] | ESA | Leidos | LUG ESA 13911.10554588 | LUG - TBD433 | LUG ESA 13911.90130568 | LUG - TBD423 | LUG C027 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C028 | 91276385 | 13911 | PEACH AVENUE | [6 empty] | ESA | Leidos | LUG ESA 13911.91276385 | LUG - TBD424 | LUG ESA 13911.60157737 | LUG - TBD416 | LUG C028 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C028 | 60157737 | 13911 | PEACH AVENUE | [6 empty] | ESA | Leidos | LUG ESA 13911.60157737 | LUG - TBD416 | LUG ESA 13911.60157737 | LUG - TBD416 | LUG C028 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C028 | 91556649 | 13911 | PEACH AVENUE | [6 empty] | ESA | Leidos | LUG ESA 13911.91556649 | LUG - TBD435 | LUG ESA 13911.60157737 | LUG - TBD416 | LUG C028 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C028 | 91665193 | 13911 | PEACH AVENUE | [6 empty] | ESA | Leidos | LUG ESA 13911.91665193 | LUG - TBD449 | LUG ESA 13911.60157737 | LUG - TBD416 | LUG C028 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C029 | 90291488 | 13457 | LAKEWOOD | [6 empty] | ESA | Leidos | LUG ESA 13457.90291488 | LUG - TBD428 | LUG ESA 13457.90176591 | LUG - TBD432 | LUG C029 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C029 | 90176591 | 13457 | LAKEWOOD | [6 empty] | ESA | Leidos | LUG ESA 13457.90176591 | LUG - TBD432 | LUG ESA 13457.90176591 | LUG - TBD432 | LUG C029 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C030 | 10544635 | 13911 | PEACH AVENUE | Peach Avenue | [5 empty] | ESA | Leidos | LUG ESA 13911.10544635 | LUG - TBD429 | LUG ESA 13911.91995336 | LUG - TBD438 | LUG C030 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C030 | 10544633 | 13911 | PEACH AVENUE | Peach Avenue | [5 empty] | ESA | Leidos | LUG ESA 13911.10544633 | LUG - TBD430 | LUG ESA 13911.91995336 | LUG - TBD438 | LUG C030 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C030 | 91995336 | 13911 | PEACH AVENUE | Peach Avenue | [5 empty] | ESA | Leidos | LUG ESA 13911.91995336 | LUG - TBD438 | LUG ESA 13911.91995336 | LUG - TBD438 | LUG C030 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C030 | 92018843 | 13911 | PEACH AVENUE | Peach Avenue | [5 empty] | ESA | Leidos | LUG ESA 13911.92018843 | LUG - TBD431 | LUG ESA 13911.91995336 | LUG - TBD438 | LUG C030 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C031 | 10895225 | 13003 | RUSKIN | [6 empty] | ESA | Leidos | LUG SHA 13003.10895225 | LUG - TBD450 | LUG SHA 13003.10895211 | LUG - TBD457 | LUG C031 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C031 | 10895211 | 13003 | RUSKIN | [6 empty] | ESA | Leidos | LUG SHA 13003.10895211 | LUG - TBD457 | LUG SHA 13003.10895211 | LUG - TBD457 | LUG C031 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C032 | 93346473 | 13001 | RUSKIN | [6 empty] | ESA | Leidos | LUG SHA 13001.93346473 | LUG - TBD388 | LUG SHA 13001.93346473 | LUG - TBD388 | LUG C032 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C032 | 90251758 | 13001 | RUSKIN | [6 empty] | ESA | Leidos | LUG SHA 13001.90251758 | LUG - TBD402 | LUG SHA 13001.93346473 | LUG - TBD388 | LUG C032 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C033 | 10663246 | 13001 | RUSKIN | [6 empty] | ESA | Leidos | LUG SHA 13001.60179144 | LUG - TBD390 | LUG SHA 13001.60179144 | LUG - TBD390 | LUG C033 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C033 | 60179144 | 13001 | RUSKIN | [6 empty] | ESA | Leidos | LUG SHA 13001.10663246 | LUG - TBD391 | LUG SHA 13001.60179144 | LUG - TBD390 | LUG C033 | N/A | N/A | N/A | N/A | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C034 | 93159006 | 14121 | FISHHAWK | [6 empty] | PCA | Fishel | LUG PCA 14121.93159006 | PRE-09361.42 | LUG PCA 13785.92466250 | PRE-09361.47 | LUG C034 | 2274175 | 2274176 | 2274189 | 2274190 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | Yes | s/b 0
LUG C034 | 92466250 | 13785 | PINECREST | [6 empty] | PCA | Fishel | LUG PCA 13785.92466250 | PRE-09361.47 | LUG PCA 13785.92466250 | PRE-09361.47 | LUG C034 | 2274189 | 2274190 | 2274189 | 2274190 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | Yes | DS
LUG C034 | 10676209 | 13785 | PINECREST | [6 empty] | PCA | Fishel | LUG PCA 13785.10676209 | PRE-09361.10 | LUG PCA 13785.92466250 | PRE-09361.47 | LUG C034 | 2274167 | 2274169 | 2274189 | 2274190 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | Yes | s/b 0
LUG C034 | 90239166 | 13785 | PINECREST | [6 empty] | PCA | Fishel | LUG PCA 13785.90239166 | LUG - TBD18 | LUG PCA 13785.92466250 | PRE-09361.47 | LUG C034 | N/A | N/A | 2274189 | 2274190 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | No | Null
LUG C035 | 92599119 | 13390 | KIRKLAND RD | [6 empty] | PCA | Fishel | LUG PCA 13390.92599119 | PRE-09361.1 | LUG PCA 13390.92599119 | PRE-09361.1 | LUG C035 | 2271216 | 2271217 | 2271216 | 2271217 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | Yes | DS
LUG C035 | 10643541 | 13390 | KIRKLAND RD | [6 empty] | PCA | Fishel | LUG PCA 13390.10643541 | PRE-09361.45 | LUG PCA 13390.92599119 | PRE-09361.1 | LUG C035 | 2274185 | 2274186 | 2271216 | 2271217 | 2020-12-21 | 2020-12-21 | financial docs updated 12/21/2020 | Yes | s/b 0
LUG C036 | 10145625 | 13138 | HABANA AVENUE | [6 empty] | WSA | Enercon | LUG WSA 13138.10145625 | PRE-09361.65 | LUG WSA 13138.10145625 | PRE-09361.65 | LUG C036 | 2273309 | 2273313 | 2273309 | 2273313 | 2021-01-04 | 2021-01-06 | financial docs updated 1/6/2021 | No | Null
LUG C036 | 10145602 | 13138 | HABANA AVENUE | [6 empty] | WSA | Enercon | LUG WSA 13138.10145602 | PRE-09361.226 | LUG WSA 13138.10145625 | PRE-09361.65 | LUG C036 | 2304838 | 2304840 | 2273309 | 2273313 | 2021-01-04 | 2021-01-06 | financial docs updated 1/6/2021 | No | Null
LUG C037 | 10362869 | 13104 | MCFARLAND | [6 empty] | CSA | Pike | LUG CSA 13104.10362869 | LUG - TBD175 | LUG CSA 13104.10362869 | LUG - TBD175 | LUG C037 | N/A | N/A | N/A | N/A | 2021-01-15 |  | financial docs updated 1/15/2021 | No | Null
LUG C037 | 10362882 | 13104 | MCFARLAND | [6 empty] | CSA | Pike | LUG CSA 13104.10362882 | LUG - TBD193 | LUG CSA 13104.10362869 | LUG - TBD175 | LUG C037 | N/A | N/A | N/A | N/A | 2021-01-15 |  | financial docs updated 1/15/2021 | No | Null
LUG C038 | 90816343 | 13158 | THIRTIETH STREET | [6 empty] | CSA | Pike | LUG CSA 13158.90816343 | LUG - TBD179 | LUG CSA 13158.90816343 | LUG - TBD179 | LUG C038 | N/A | N/A | N/A | N/A | 2021-01-15 |  | financial docs updated 1/15/2021 | No | Null
LUG C038 | 93317809 | 13158 | THIRTIETH STREET | [6 empty] | CSA | Pike | LUG CSA 13158.93317809 | LUG - TBD181 | LUG CSA 13158.90816343 | LUG - TBD179 | LUG C038 | N/A | N/A | N/A | N/A | 2021-01-15 |  | financial docs updated 1/15/2021 | No | Null
LUG C039 | 91795934 | 13106 | MCFARLAND | [6 empty] | CSA | Pike | LUG CSA 13106.91795934 | LUG - TBD183 | LUG CSA 13106.10361901 | LUG - TBD239 | LUG C039 | N/A | N/A | N/A | N/A | 2021-01-15 |  | financial docs updated 1/15/2021 | No | Null
LUG C039 | 10361901 | 13106 | MCFARLAND | [6 empty] | CSA | Pike | LUG CSA 13106.10361901 | LUG - TBD239 | LUG CSA 13106.10361901 | LUG - TBD239 | LUG C039 | N/A | N/A | N/A | N/A | 2021-01-15 |  | financial docs updated 1/15/2021 | No | Null
LUG C040 | 60123660 | 13102 | YUKON | [6 empty] | CSA | Pike | LUG CSA 13102.60123660 | LUG - TBD196 | LUG CSA 13102.90748252 | LUG - TBD244 | LUG C040 | N/A | N/A | N/A | N/A | 2021-01-15 |  | financial docs updated 1/15/2021 | No | Null
LUG C040 | 90748252 | 13102 | YUKON | [6 empty] | CSA | Pike | LUG CSA 13102.90748252 | LUG - TBD244 | LUG CSA 13102.90748252 | LUG - TBD244 | LUG C040 | N/A | N/A | N/A | N/A | 2021-01-15 |  | financial docs updated 1/15/2021 | No | Null
LUG C041 | 60011810 | 13158 | THIRTIETH STREET | [6 empty] | CSA | Pike | LUG CSA 13158.60011810 | LUG - TBD202 | LUG CSA 13158.60011810 | LUG - TBD202 | LUG C041 | N/A | N/A | N/A | N/A | 2021-01-15 |  | financial docs updated 1/15/2021 | No | Null
LUG C041 | 92290015 | 13158 | THIRTIETH STREET | [6 empty] | CSA | Pike | LUG CSA 13158.92290015 | LUG - TBD209 | LUG CSA 13158.60011810 | LUG - TBD202 | LUG C041 | N/A | N/A | N/A | N/A | 2021-01-15 |  | financial docs updated 1/15/2021 | No | Null
LUG C042 | 90633859 | 13633 | PINE LAKE | [6 empty] | CSA | Pike | LUG CSA 13633.90633859 | LUG - TBD214 | LUG CSA 13633.90564142 | LUG - TBD228 | LUG C042 | N/A | N/A | N/A | N/A | 2021-01-15 |  | financial docs updated 1/15/2021 | No | Null
LUG C042 | 90564142 | 13633 | PINE LAKE | [6 empty] | CSA | Pike | LUG CSA 13633.90564142 | LUG - TBD228 | LUG CSA 13633.90564142 | LUG - TBD228 | LUG C042 | N/A | N/A | N/A | N/A | 2021-01-15 |  | financial docs updated 1/15/2021 | No | Null
LUG C043 | 90312305 | 13612 | EL PRADO | [6 empty] | WSA | Enercon | LUG WSA 13612.90312305 | PRE-09361.219 | LUG WSA 13612.90312305 | PRE-09361.219 | LUG C043 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C043 | 90312570 | 13612 | EL PRADO | [6 empty] | WSA | Enercon | LUG WSA 13612.90312570 | PRE-09361.280 | LUG WSA 13612.90312305 | PRE-09361.219 | LUG C043 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C044 | 90932106 | 13192 | DOUBLE BRANCH | [6 empty] | WSA | Enercon | LUG WSA 13192.90932106 | PRE-09361.143 | LUG WSA 13192.90932106 | PRE-09361.143 | LUG C044 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C044 | 90932283 | 13192 | DOUBLE BRANCH | [6 empty] | WSA | Enercon | LUG WSA 13192.90932283 | PRE-09361.157 | LUG WSA 13192.90932106 | PRE-09361.143 | LUG C044 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C045 | 60131389 | 14030 | PAGLEN ROAD | [6 empty] | WSA | Enercon | LUG WSA 14030.60131389 | PRE-09361.183 | LUG WSA 14030.60125643 | PRE-09361.256 | LUG C045 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C045 | 60125643 | 14030 | PAGLEN ROAD | [6 empty] | WSA | Enercon | LUG WSA 14030.60125643 | PRE-09361.256 | LUG WSA 14030.60125643 | PRE-09361.256 | LUG C045 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C046 | 60154843 | 13162 | MATANZAS | [6 empty] | WSA | Enercon | LUG WSA 13162.60154843 | PRE-09361.203 | LUG WSA 13162.90435139 | PRE-09361.263 | LUG C046 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C046 | 90435139 | 13162 | MATANZAS | [6 empty] | WSA | Enercon | LUG WSA 13162.90435139 | PRE-09361.263 | LUG WSA 13162.90435139 | PRE-09361.263 | LUG C046 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C047 | 92767537 | 13208 | LOIS AVENUE | [6 empty] | WSA | Enercon | LUG WSA 13208.92767537 | PRE-09361.210 | LUG WSA 13208.92767537 | PRE-09361.210 | LUG C047 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C047 | 90449608 | 13208 | LOIS AVENUE | [6 empty] | WSA | Enercon | LUG WSA 13208.90449608 | PRE-09361.233 | LUG WSA 13208.92767537 | PRE-09361.210 | LUG C047 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C048 | 92774744 | 13669 | MEADOW PARK | [6 empty] | WSA | Enercon | LUG WSA 13669.92774744 | PRE-09361.215 | LUG WSA 13669.92770538 | PRE-09361.232 | LUG C048 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C048 | 92770538 | 13669 | MEADOW PARK | [6 empty] | WSA | Enercon | LUG WSA 13669.92770538 | PRE-09361.232 | LUG WSA 13669.92770538 | PRE-09361.232 | LUG C048 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C049 | 92959083 | 13535 | CARROLLWOOD VILLAGE | [6 empty] | WSA | Enercon | LUG WSA 13535.92959083 | PRE-09361.214 | LUG WSA 13535.91618829 | PRE-09361.231 | LUG C049 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C049 | 91618829 | 13535 | CARROLLWOOD VILLAGE | [6 empty] | WSA | Enercon | LUG WSA 13535.91618829 | PRE-09361.231 | LUG WSA 13535.91618829 | PRE-09361.231 | LUG C049 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C049 | 92969194 | 13535 | CARROLLWOOD VILLAGE | [6 empty] | WSA | Enercon | LUG WSA 13535.92969194 | PRE-09361.252 | LUG WSA 13535.91618829 | PRE-09361.231 | LUG C049 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C050 | 60311122 | 13873 | HENDERSON ROAD | [6 empty] | WSA | Enercon | LUG WSA 13873.60311122 | PRE-09361.207 | LUG WSA 13873.60311122 | PRE-09361.207 | LUG C050 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C050 | 10820612 | 13873 | HENDERSON ROAD | [6 empty] | WSA | Enercon | LUG WSA 13873.10820612 | PRE-09361.264 | LUG WSA 13873.60311122 | PRE-09361.207 | LUG C050 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C051 | 92442286 | 13586 | DALE MABRY | [6 empty] | WSA | Enercon | LUG WSA 13586.92442286 | PRE-09361.155 | LUG WSA 13586.92442286 | PRE-09361.155 | LUG C051 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C051 | 10255361 | 13586 | DALE MABRY | [6 empty] | WSA | Enercon | LUG WSA 13586.10255361 | PRE-09361.175 | LUG WSA 13586.92442286 | PRE-09361.155 | LUG C051 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C052 | 92669942 | 14030 | PAGLEN ROAD | [6 empty] | WSA | Enercon | LUG WSA 14030.92669942 | PRE-09361.241 | LUG WSA 14030.92669942 | PRE-09361.241 | LUG C052 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C052 | 92669914 | 14030 | PAGLEN ROAD | [6 empty] | WSA | Enercon | LUG WSA 14030.92669914 | PRE-09361.279 | LUG WSA 14030.92669942 | PRE-09361.241 | LUG C052 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C052 | 92669923 | 14030 | PAGLEN ROAD | [6 empty] | WSA | Enercon | LUG WSA 14030.92669923 | PRE-09361.282 | LUG WSA 14030.92669942 | PRE-09361.241 | LUG C052 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C053 | 90242104 | 14030 | PAGLEN ROAD | [6 empty] | WSA | Enercon | LUG WSA 14030.90242104 | PRE-09361.206 | LUG WSA 14030.90886759 | PRE-09361.190 | LUG C053 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C053 | 92669080 | 14030 | PAGLEN ROAD | [6 empty] | WSA | Enercon | LUG WSA 14030.92669080 | PRE-09361.257 | LUG WSA 14030.90886759 | PRE-09361.190 | LUG C053 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C053 | 90886759 | 14030 | PAGLEN ROAD | [6 empty] | WSA | Enercon | LUG WSA 14030.90886759 | PRE-09361.190 | LUG WSA 14030.90886759 | PRE-09361.190 | LUG C053 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C054 | 90613782 | 13207 | LOIS AVENUE | [6 empty] | WSA | Enercon | LUG WSA 13207.90613782 | PRE-09361.208 | LUG WSA 13207.90613782 | PRE-09361.208 | LUG C054 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C054 | 90216846 | 13207 | LOIS AVENUE | [6 empty] | WSA | Enercon | LUG WSA 13207.90216846 | PRE-09361.192 | LUG WSA 13207.90613782 | PRE-09361.208 | LUG C054 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C055 | 90266817 | 13612 | EL PRADO | [6 empty] | WSA | Enercon | LUG WSA 13612.90266817 | PRE-09361.209 | LUG WSA 13612.90291123 | PRE-09361.274 | LUG C055 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C055 | 90291123 | 13612 | EL PRADO | [6 empty] | WSA | Enercon | LUG WSA 13612.90291123 | PRE-09361.274 | LUG WSA 13612.90291123 | PRE-09361.274 | LUG C055 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C056 | 60393455 | 13483 | WOODLANDS | [6 empty] | WSA | Enercon | LUG WSA 13483.60393455 | PRE-09361.216 | LUG WSA 13483.60393455 | PRE-09361.216 | LUG C056 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C056 | 10173513 | 13483 | WOODLANDS | [6 empty] | WSA | Enercon | LUG WSA 13483.10173513 | PRE-09361.242 | LUG WSA 13483.60393455 | PRE-09361.216 | LUG C056 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C056 | 60079455 | 13483 | WOODLANDS | [6 empty] | WSA | Enercon | LUG WSA 13483.60079455 | PRE-09361.260 | LUG WSA 13483.60393455 | PRE-09361.216 | LUG C056 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C057 | 92956326 | 13612 | EL PRADO | [6 empty] | WSA | Enercon | LUG WSA 13612.92956326 | PRE-09361.238 | LUG WSA 13612.92956326 | PRE-09361.238 | LUG C057 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C057 | 90440184 | 13612 | EL PRADO | [6 empty] | WSA | Enercon | LUG WSA 13612.90440184 | PRE-09361.181 | LUG WSA 13612.92956326 | PRE-09361.238 | LUG C057 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C058 | 91934653 | 13522 | ROME AVENUE | [6 empty] | WSA | Enercon | LUG WSA 13522.91934653 | PRE-09361.187 | LUG WSA 13522.10392882 | PRE-09361.247 | LUG C058 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C058 | 10392882 | 13522 | ROME AVENUE | [6 empty] | WSA | Enercon | LUG WSA 13522.10392882 | PRE-09361.247 | LUG WSA 13522.10392882 | PRE-09361.247 | LUG C058 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C058 | 60305728 | 13522 | ROME AVENUE | [6 empty] | WSA | Enercon | LUG WSA 13522.60305728 | PRE-09361.283 | LUG WSA 13522.10392882 | PRE-09361.247 | LUG C058 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C059/062 | 10145629 | 13138 | HABANA AVENUE | [6 empty] | WSA | Enercon | LUG WSA 13138.10145629 | PRE-09361.267 | LUG WSA 13138.10145628 | PRE-09361.68 | LUG C059/062 | N/A | N/A | N/A | N/A | 1/15/2021 & 3/5/2021 | 1/15/2021 & 3/5/2021 | originally part of CO59, but missing PRE-09361.68 (FID 10145628) financial docs updated 1/15/2021 & 3/15/2021 | No | Null
LUG C059/062 | 10145606 | 13138 | HABANA AVENUE | [6 empty] | WSA | Enercon | LUG WSA 13138.10145606 | PRE-09361.281 | LUG WSA 13138.10145628 | PRE-09361.68 | LUG C059/062 | N/A | N/A | N/A | N/A | 1/15/2021 & 3/5/2021 | 1/15/2021 & 3/5/2021 | originally part of CO59, but missing PRE-09361.68 (FID 10145628) financial docs updated 1/15/2021 & 3/15/2021 | No | Null
LUG C060 | 60302601 | 13059 | HIMES | [6 empty] | WSA | Enercon | LUG WSA 13059.60302601 | PRE-09361.193 | LUG WSA 13059.60302601 | PRE-09361.193 | LUG C060 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C060 | 93006225 | 13059 | HIMES | [6 empty] | WSA | Enercon | LUG WSA 13059.93006225 | PRE-09361.195 | LUG WSA 13059.60302601 | PRE-09361.193 | LUG C060 | N/A | N/A | N/A | N/A | 2021-01-15 | 2021-01-15 | financial docs updated 1/15/2021 | No | Null
LUG C061/72 | 93279980 | 13230 | BRANDON | [6 empty] | ESA | Leidos | LUG ESA 13230.93279980 | PRE-09361.117 | LUG ESA 13230.92180224 | PRE-09361.134 | LUG C061/72 | 2290539 | 2290540 | 2277432 | 2277435 | 2021-02-12 | 2021-02-12 | financial docs updated 2/15/2021 | Yes | s/b 0
LUG C061/72 | 92180224 | 13230 | BRANDON | [6 empty] | ESA | Leidos | LUG ESA 13230.92180224 | PRE-09361.134 | LUG ESA 13230.92180224 | PRE-09361.134 | LUG C061/72 | 2277432 | 2277435 | 2277432 | 2277435 | 2021-02-12 | 2021-02-12 | financial docs updated 2/15/2021 | Yes | DS
LUG C063 | 60059524 | 13026 | Temple Terrace | [6 empty] | CSA | Pike | LUG CSA 13026.60059524 | PRE-09361.343 | LUG CSA 13026.60059524 | PRE-09361.343 | LUG C063 | 2308256 | 2308264 | 2308256 | 2308264 | 2021-02-16 | 2021-02-18 | financial docs updated 2/18/2021 | No | Null
LUG C063 | 91490707 | 13026 | Temple Terrace | [6 empty] | CSA | Pike | LUG CSA 13026.91490707 | PRE-09361.404 | LUG CSA 13026.60059524 | PRE-09361.343 | LUG C063 | 2310348 | 2310349 | 2308256 | 2308264 | 2021-02-16 | 2021-02-18 | financial docs updated 2/18/2021 | No | Null
LUG C016 | 10371697 | 13100 | YUKON | [6 empty] | CSA | Pike | LUG CSA 13100.10371697 | LUG - TBD217 | LUG CSA 13100.91340554 | PRE-09361.92 | LUG C016 | N/A | N/A | 2275159 | 2275160 | 2021-03-03 | 2021-03-03 | identified during master project list review | No | Null
LUG C059/062 | 10145628 | 13138 | HABANA AVENUE | [6 empty] | WSA | Enercon | LUG WSA 13138.10145628 | PRE-09361.68 | LUG WSA 13138.10145628 | PRE-09361.68 | LUG C059/062 | N/A | N/A | N/A | N/A | 1/15/2021 & 3/5/2021 | 1/15/2021 & 3/5/2021 | originally left out of CO59 with PRE-09361.267 (10145629) and PRE-09361.281 (FID 10145606); financial docs updated 1/15/2021 & 3/5/2021 | No | Null
Delayed LUG C013 | 91406642 | 13836 | FLORIDA AVENUE | [6 empty] | CSA | Pike | LUG CSA 13836.91406642 | PRE-09361.376 | LUG CSA 13836.91406642 | PRE-09361.376 | Delayed LUG C013 | 2308333 | 2308341 | 2308333 | 2308341 | 2021-04-22 | 2021-04-22 | financial docs updated 4/22/2021; delayed work scope that requires it stay with it's own financials | No | Null
LUG C064 | 10791853 | 13243 | Wilson | [6 empty] | PCA | Fishel | LUG PCA 13243.10791853 | PRE-09361.330 | LUG PCA 13243.91351288 | PRE-09361.332 | LUG C064 | 2310471 | 2310475 | 2310479 | 2310480 | 2021-04-22 | 2021-04-22 | financial docs updated 4/22/2021 | Yes | s/b 0
LUG C064 | 91351288 | 13243 | Wilson | [6 empty] | PCA | Fishel | LUG PCA 13243.91351288 | PRE-09361.332 | LUG PCA 13243.91351288 | PRE-09361.332 | LUG C064 | 2310479 | 2310480 | 2310479 | 2310480 | 2021-04-22 | 2021-04-22 | financial docs updated 4/22/2021 | Yes | DS
LUG C065 | 92659353 | 13118 | LAKE ALFRED | [6 empty] | WHA | Fishel | LUG WHA 13118.92659353 | PRE-09361.310 | LUG WHA 13118.10535999 | PRE-09361.319 | LUG C065 | 2310464 | 2310467 | 2310443 | 2310452 | 2021-04-22 | 2021-04-22 | financial docs updated 4/22/2021 | Yes | s/b 0
LUG C065 | 10535999 | 13118 | LAKE ALFRED | [6 empty] | WHA | Fishel | LUG WHA 13118.10535999 | PRE-09361.319 | LUG WHA 13118.10535999 | PRE-09361.319 | LUG C065 | 2310443 | 2310452 | 2310443 | 2310452 | 2021-04-22 | 2021-04-22 | financial docs updated 4/22/2021 | Yes | DS
LUG C066/2/3 | 10913196 | 13174 | MADISON | [6 empty] | ESA | Leidos | LUG ESA 13174.10913196 | PRE-09361.17 | LUG ESA 13174.10913196 | PRE-09361.17 | LUG C066/2/3 | 2277381 | 2277382 | 2277381 | 2277382 | 2021-04-22 | 2021-04-22 | financial docs updated 4/22/2021 | Yes | DS
LUG C066/2/3 | 60451701 | 13174 | MADISON | [6 empty] | ESA | Leidos | LUG ESA 13174.60451701 | PRE-09361.13 | LUG ESA 13174.10913196 | PRE-09361.17 | LUG C066/2/3 | 2277343 | 2277348 | 2277381 | 2277382 | 2021-04-22 | 2021-04-22 | financial docs updated 4/22/2021 | Yes | s/b 0
LUG CO67 | 60287236 | 13509 | STATE ROAD 574 | [6 empty] | ESA | Leidos | LUG ESA 13509.60287236 | PRE-09361.15 | LUG ESA 13509.60287236 | PRE-09361.15 | LUG CO67 | 2277364 | 2277368 | 2277364 | 2277368 | 2021-05-05 | 2021-05-05 | financial docs updated 5/28/2021 | Yes | DS
LUG CO67 | 92577310 | 13502 | STATE ROAD 574 | [6 empty] | ESA | Leidos | LUG ESA 13502.92577310 | PRE-09361.120 | LUG ESA 13509.60287236 | PRE-09361.15 | LUG CO67 | 2277393 | 2277394 | 2277364 | 2277368 | 2021-05-05 | 2021-05-05 | financial docs updated 5/28/2021 | Yes | s/b 0
LUG CO68 | 91773975 | 13835 | FLORIDA AVENUE | [6 empty] | CSA | Pike | LUG CSA 13835.91773975 | PRE-09361.366 | LUG CSA 13835.10429505 | PRE-09361.394 | LUG CO68 | 2318798 | 2318804 | 2310287 | 2310291 | 2021-06-15 | 2021-06-15 | financial docs updated 6/18/2021 | No | Null
LUG CO68 | 10429505 | 13835 | FLORIDA AVENUE | [6 empty] | CSA | Pike | LUG CSA 13835.10429505 | PRE-09361.394 | LUG CSA 13835.10429505 | PRE-09361.394 | LUG CO68 | 2310287 | 2310291 | 2310287 | 2310291 | 2021-06-15 | 2021-06-15 | financial docs updated 6/18/2021 | No | Null
LUG CO69 | 60568375 | 13313 | EAST WINTER HAVEN | [6 empty] | WHA | Fishel | LUG WHA 13313.60568375 | PRE-09361.300 | LUG WHA 13313.90084626 | PRE-09361.296 | LUG CO69 | 2310701 | 2310702 | 2310490 | 2310491 | 2021-06-15 | 2021-06-15 | financial docs updated 6/18/2021 | Yes | s/b 0
LUG CO69 | 93103371 | 13313 | EAST WINTER HAVEN | [6 empty] | WHA | Fishel | LUG WHA 13313.93103371 | PRE-09361.313 | LUG WHA 13313.90084626 | PRE-09361.296 | LUG CO69 | 2310733 | 2310735 | 2310490 | 2310491 | 2021-06-15 | 2021-06-15 | financial docs updated 6/18/2021 | No | Null
LUG CO69 | 90084626 | 13313 | EAST WINTER HAVEN | [6 empty] | WHA | Fishel | LUG WHA 13313.90084626 | PRE-09361.296 | LUG WHA 13313.90084626 | PRE-09361.296 | LUG CO69 | 2310490 | 2310491 | 2310490 | 2310491 | 2021-06-15 | 2021-06-15 | financial docs updated 6/18/2021 | Yes | DS
LUG CO70 | 10696417 | 13961 | TERRACE | [6 empty] | PCA | Fishel | LUG PCA 13961.10696417 | PRE-09361.291 | LUG PCA 13961.92834683 | PRE-09361.287 | LUG CO70 | 2310672 | 2310673 | 2310667 | 2310668 | 2021-07-02 | 2021-07-02 | financial docs updated 7/2/2021 | Yes | s/b 0
LUG CO70 | 92834683 | 13961 | TERRACE | [6 empty] | PCA | Fishel | LUG PCA 13961.92834683 | PRE-09361.287 | LUG PCA 13961.92834683 | PRE-09361.287 | LUG CO70 | 2310667 | 2310668 | 2310667 | 2310668 | 2021-07-02 | 2021-07-02 | financial docs updated 7/2/2021 | Yes | DS
LUG CO71 | 60279838 | 13863 | PATTERSON ROAD | [6 empty] | WSA | Enercon | LUG WSA 13863.60279838 | PRE-09361.145 | LUG WSA 13863.60279838 | PRE-09361.145 | LUG CO71 | 2304611 | 2304613 | 2304611 | 2304613 | 2021-07-13 | 2021-07-13 | financial docs updated 8/4/2021 | Yes | DS
LUG CO71 | 10310468 | 13864 | PATTERSON ROAD | [6 empty] | WSA | Enercon | LUG WSA 13864.10310468 | PRE-09361.153 | LUG WSA 13863.60279838 | PRE-09361.145 | LUG CO71 | 2304909 | 2304912 | 2304611 | 2304613 | 2021-07-13 | 2021-07-13 | financial docs updated 8/4/2021 | Yes | s/b 0
LUG C061/72 | 92208546 | 13230 | BRANDON | [6 empty] | ESA | Leidos | LUG ESA 13230.92208546 | PRE-09361.107 | LUG ESA 13230.92180224 | PRE-09361.134 | LUG C061/72 | 2290489 | 2290490 | 2277432 | 2277435 | 2021-07-22 | 2021-07-22 | financial docs updated 8/4/2021; originally left out of LUG CO61 & incorporated as of 7/22/2021 | Yes | s/b 0
LUG CO73 | 10562356 | 13296 | Jan Phyl | [6 empty] | WHA | Fishel | LUG WHA 13296.10562356 | PRE-09361.304 | LUG WHA 13296.10562361 | PRE-09361.323 | LUG CO73 | 2310706 | 2310709 | 2310767 | 2310770 | 2021-07-26 | 2021-08-04 | financial docs updated 8/4/2021 | Yes | s/b 0
LUG CO73 | 10562361 | 13296 | Jan Phyl | [6 empty] | WHA | Fishel | LUG WHA 13296.10562361 | PRE-09361.323 | LUG WHA 13296.10562361 | PRE-09361.323 | LUG CO73 | 2310767 | 2310770 | 2310767 | 2310770 | 2021-07-26 | 2021-08-04 | financial docs updated 8/4/2021 | Yes | DS
LUG CO74 | 10560425 | 13297 | Jan Phyl | [6 empty] | WHA | Fishel | LUG WHA 13297.10560425 | PRE-09361.306 | LUG WHA 13297.10560425 | PRE-09361.306 | LUG CO74 | 2310711 | 2310714 | 2310711 | 2310714 | 2021-08-03 | 2021-08-04 | financial docs updated 8/4/2021 | Yes | DS
LUG CO74 | 10560430 | 13297 | Jan Phyl | [6 empty] | WHA | Fishel | LUG WHA 13297.10560430 | PRE-09361.293 | LUG WHA 13297.10560425 | PRE-09361.306 | LUG CO74 | 2310678 | 2310679 | 2310711 | 2310714 | 2021-08-03 | 2021-08-04 | financial docs updated 8/4/2021 | Yes | s/b 0
LUG CO75 | 10560425 | 13297 | Jan Phyl | [6 empty] | PCA | Fishel | LUG PCA 13243.90586047 | PRE-09361.339 | LUG PCA 13243.90684154 | PRE-09361.334 | LUG CO75 | 2310831 | 2310832 | 2310810 | 2310812 | 2021-08-20 | 2021-09-03 | financial docs updated 9/3/2021 | Yes - Later | s/b 0
LUG CO75 | 10560430 | 13297 | Jan Phyl | [6 empty] | PCA | Fishel | LUG PCA 13243.90684154 | PRE-09361.334 | LUG PCA 13243.90684154 | PRE-09361.334 | LUG CO75 | 2310810 | 2310812 | 2310810 | 2310812 | 2021-08-20 | 2021-09-03 | financial docs updated 9/3/2021 | Yes - Later | DS
LUG C076 | 10671319 | 13724 | Gallagher Road | [6 empty] | PCA | Fishel | LUG PCA 13724.10671319 | PRE-09361.329 | LUG PCA 13724.10671319 | PRE-09361.329 | LUG C076 | 2310790 | 2310795 | 2310790 | 2310795 | 2021-09-03 | 2021-10-01 | financial docs updated 10/5/2021 | Yes | DS
LUG C076 | 10671283 | 13724 | Gallagher Road | [6 empty] | PCA | Fishel | LUG PCA 13724.10671283 | PRE-09361.326 | LUG PCA 13724.10671319 | PRE-09361.329 | LUG C076 | 2310778 | 2310782 | 2310790 | 2310795 | 2021-09-03 | 2021-10-01 | financial docs updated 10/5/2021 | Yes | s/b 0
LUG CO77 | 91049435 | 13724 | Gallagher Road | [6 empty] | PCA | Fishel | LUG PCA 13724.91049435 | PRE-09361.340 | LUG PCA 13724.91049435 | PRE-09361.340 | LUG CO77 | 2310833 | 2310834 | 2310833 | 2310834 | 2021-09-03 | 2021-10-01 | financial docs updated 10/5/2021 | Yes - Later | DS
LUG CO77 | 93103251 | 13724 | Gallagher Road | [6 empty] | PCA | Fishel | LUG PCA 13724.93103251 | PRE-09361.338 | LUG PCA 13724.91049435 | PRE-09361.340 | LUG CO77 | 2310827 | 2310829 | 2310833 | 2310834 | 2021-09-03 | 2021-10-01 | financial docs updated 10/5/2021 | Yes - Later | s/b 0
LUG CO78 | 10158909 | 13164 | MATANZAS | [6 empty] | WSA | Enercon | LUG WSA 13164.10158909 | PRE-09361.69 | LUG WSA 13164.10158909 | PRE-09361.69 | LUG CO78 | 2273288 | 2273291 | 2273288 | 2273291 | 2021-09-07 | 2021-10-05 | financial docs updated 10/5/2021 | No | Null
LUG CO78 | 90252716 | 13164 | MATANZAS | [6 empty] | WSA | Enercon | LUG WSA 13164.90252716 | PRE-09361.165 | LUG WSA 13164.10158909 | PRE-09361.69 | LUG CO78 | 2304926 | 2304927 | 2273288 | 2273291 | 2021-09-07 | 2021-10-05 | financial docs updated 10/5/2021 | No | Null
LUG CO79 | 10158909 | 13522 | ROME AVENUE | [6 empty] | WSA | Enercon | LUG WSA 13522.10392902 | PRE-09361.223 | LUG WSA 13522.10392902 | PRE-09361.223 | LUG CO79 | 2304845 | 2304846 | 2304845 | 2304846 | 2021-10-07 | 2021-10-08 | financial docs updated 11/1/2021 | Yes - Later | DS
LUG CO79 | 90252716 | 13522 | ROME AVENUE | [6 empty] | WSA | Enercon | LUG WSA 13522.10392864 | PRE-09361.272 | LUG WSA 13522.10392902 | PRE-09361.223 | LUG CO79 | 2304574 | 2304575 | 2304845 | 2304846 | 2021-10-07 | 2021-10-08 | financial docs updated 11/1/2021 | Yes - Later | s/b 0