Change control Process

- The following document consolidates input from CLECs and BellSouth.  It is a working document for discussion purposes only.

BellSouth Telecommunications reserves the right to revise this document for any reason, with concurrence of the CLEC/BellSouth Review Board, including but not limited to, conformity with standards promulgated by various government or regulatory agencies, utilization of advance in the state of the technical arts, or the reflection of changes in the design of any equipment, techniques, or procedures described or referred to herein.  LIABILITY TO ANYONE ARISING OUT OF USE OR RELIANCE UPON ANY INFORMATION SET FORTH HEREIN IS EXPRESSLY DISCLAIMED, AND NO REPRESENTATIONS OR WARRANTIES, EXPRESSED OR IMPLIED, ARE MADE WITH RESPECT TO THE ACCURACY OR UTILITY OF ANY INFORMATION SET FORTH HEREIN.

This document is not to be construed as a suggestion to any manufacturer to modify or change any of its products, nor does this document represent any commitment by BellSouth Telecommunications to purchase any product whether or not it provides the described characteristics.

This document is not to be construed as a contract.  It does not create an obligation on the part of BellSouth Telecommunications or the Competitive Local Exchange Carriers to perform any modification, change or enhancement of any product or service.

Nothing contained herein shall be construed as conferring by implication, estoppel or otherwise, any license or right under any patent, whether or not the use of any information herein necessarily employs an invention of any existing or later issued patent.

- VERSION CHANGE HISTORY

This section list changes made to the baseline Electronic Interface Change Control Process document since the last issue.  New versions of this document may be obtained via BellSouth’s Web site.

| Version | Issue Date | Section Revised | Reason for Revision |
| --- | --- | --- | --- |
| 1.0 | 04/14/98 |  | Initial issue. |
| 1.2 | 2/28/00 | All | The EICCP Documentation has been modified to incorporate: - Multiple Change Request Types (CLEC Initiated, BST Initiated, Industry Standards, Regulatory and System Outages) - Incorporated manual process - Defined cycle times for process intervals and notifications - Defect Notification process - Escalation Process - Modified Change Control forms to support process changes - Changed EICCP to CCP |
| - 1.3 | - 3/14/00 | - All | - The CCP Documentation has been modified to incorporate: - Type 6 Change Request, CLEC Impacting Defect - Increased number of participants at Change Review meetings - Changed cycle time for Types 2-5 Step 3 from 20 days to 15 days - Defined Step 4 of the Defect Notification process to include communicating the workaround to the CLEC community - Web Site address for Change Control Process - Notification regarding the Retirement and Introduction of new interfaces - New status codes for Defect Change Requests - New status codes: ‘S’ for Scheduled Change Requests and ‘I’ for Implemented Change Requests (types 2-5 Change Requests) - Removed reference to EDI Helpdesk. Electronic Communications Support (ECS) will be the first point of contact for Type 1 System Outages. - Word changes to provide clarification throughout the document. |
| - 1.4 | - 4/12/00 | - All | - The CCP Documentation has been modified to incorporate: - Type 1 and 6 Notifications will be communicated to CLECs via e-mail and web posting - Step 3 Cycle Time (Types 2-5) changed from 15 business days to 20 business days - Verbiage to Step 10 (Types 2-5) regarding BellSouth presenting baseline requirements - Introduction and Retirement of New Interfaces Section - Dispute Resolution Process - Testing Environment Section - Word changes to provide clarification throughout the document - Monthly Status Meeting Agenda Template - RF1870 Change Request Form changes |

- TABLE OF CONTENTS

1.0	INTRODUCTION	6

2.0	Change Control Organization	8

3.0	cHANGE cONTROL dECISION pROCESS	9

4.0	CHANGE CONTROL PROCESS FLOW	12

Part 1 - Type 1 Process Flow	13

Part 2 – Types 2-5 Process Flow	18

5.0	 Defect Notification Process	24

6.0	 CHANGE REVIEW	27

Part 1 – Change Review Meeting	27

Part 2 – Change Review Package	27

Part 3 – Prioritizing Change Requests	27

7.0	Introduction and Retirement of interfaces	30

8.0	ESCALATION PROCESS	31

Dispute Resolution Process	34

9.0	Changes to this ProceSS	35

10.0	TESTING ENVIRONMENT	Error! Bookmark not defined.

11.0	TERMS and Definitions	37

APPENDIX A – CHANGE CONTROL FORMS	43

See Attached Forms	43

APPENDIX B – RELEASE MANAGEMENT	44

See Attached Forms	44

APPENDIX C –Additional Documents	45

See Attached Documents	45

- THIS PAGE INTENTIONALLY LEFT BLANK

# 1.0	INTRODUCTION

- This document establishes the process by which BellSouth Telecommunications (BST) and Competitive Local Exchange Carriers (CLECs) will manage requested changes to the BellSouth Local Interfaces, the introduction of new interfaces, and provide for the identification and resolution of issues related to Change Requests.  This process will cover Change Requests that affect external users of BellSouth’s Electronic Interface Applications, associated manual process improvements, performance or ability to provide service including defect notification.  This process shall be referred to as the Change Control Process.

- All parties should recognize that deviations from this process might be warranted where unanticipated circumstances arise such that strict application of these guidelines may not result in their intended purpose.  Furthermore, deviations may be required due to specific regulatory and business requirements.  Parties shall provide appropriate web notification to the CLEC/BST Change Control Team participants prior to deviating from the processes established within this document.  All parties will comply with all legal and regulatory requirements.

- The Change Control Process will cover change requests for the following interfaces and associated manual processes that have the potential to impact the interfaces connected to BellSouth:

- Local Exchange Navigation System (LENS)

- Electronic Data Interchange (EDI)

- Telecommunications Access Gateway (TAG)

- Trouble Administration Facilitation Interface (TAFI)

- Electronic Communications Trouble Administration (EC-TA) Local

- CLEC Service Order Tracking System (CSOTS)

- The types of changes that will be handled by this process are as follows:

- Software

- Hardware

- Industry Standards

- Product and Services (i.e., new services available via the in-scope interfaces)

- New or Revised Edits

- Process (i.e., electronic interfaces and manual processes relative to order, pre-order, maintenance)

- Regulatory

- Documentation (i.e., business rules for electronic and manual processes relative to order, pre-order, maintenance)

- Defects

- Testing

- The scope of the Change Control Process does not include the following:

- BonaFide Requests (BFR)

- Production Support (i.e. adding new users to existing interfaces, existing users requesting first time use of existing BST functionality)

- Contractual Agreements

- Collocation

- Change Requests of this nature will be handled through existing BellSouth processes.

- OBJECTIVES OF THE CHANGE CONTROL PROCESS:

- Support the Industry guidelines that impact Electronic Interfaces and manual processes relative to order, pre-order, maintenance, and billing as appropriate

- Ensure continuity of business processes and systems operations

- Establish process for communicating and managing changes

- Allow for mutual impact assessment and resource planning to manage and schedule changes

- Capability to prioritize requested changes

- The minimum requirements for participation in the Change Control Process electronically are:

- Word 6.0 or greater

- Excel 5.0 or greater

- Internet E-mail address

- Web access

The web site address for the Change Control Process is as follows:

http://www.interconnection.bellsouth.com/markets/lec/ccp/ccp.html

# 2.0	Change Control Organization

The Change Control organizational structure supports the Change Control Process.  Each position within the organization has defined roles and responsibilities as outlined in the Change Control Process Flow - Section 4 of this document.  Identified positions, along with associated roles and responsibilities are as follows:

Change Review Participants.  Representatives from Competitive Local Exchange Carriers (CLECs) and BellSouth.  This team meets to review, prioritize, and make recommendations for Candidate Change Requests.  The Candidate Change Requests are used as input to the Internal Change Management Processes (refer to process step 7).

CLECs and BellSouth will define points of contact in each of their companies for communicating and coordinating change notification.  All change requests are made in writing.  Notifications will be posted to the BellSouth web site.

Each company may bring the number of participants necessary to represent their position.  If the number of participants grows to be unmanageable, CLECs and BellSouth will revisit the issue of representation to apply some restrictions.

BellSouth Change Control Manager (BCCM).  The BCCM is responsible for managing the Change Control Process and is the main point of contact for Types 2 – 6 changes.  This individual maintains the integrity of the Change Requests, prepares for and facilitates the Change Review Meetings, presents the Pending Change Requests to the BST Internal Change Management Process, and ensures that all Notifications are communicated to the appropriate parties.

CLEC Change Control Manager (CCCM).   The CCCM is the CLEC point of contact for Change Requests.  This individual is responsible for presenting and prioritizing Change Requests at the Change Review Meetings.

Release Management Project Team.   A team of CLEC and BellSouth Project Managers who manage the implementation of scheduled changes and releases.

# 3.0	cHANGE cONTROL dECISION pROCESS

Change requests will be classified by Type.  There are six Types:

Type 1 – System Outage

A Type 1 change is a BellSouth System Outage.  A System Outage is where the system is totally unusable or there is degradation in an existing feature or functionality within the interface.  If the System Outage is not resolved within 20 minutes, a notification will be provided via e-mail and posted to the web within one hour.  Either BellSouth or a CLEC may initiate the change request.  Type 1 system outages will be processed on an expedited basis.  All Type 1 System Outages will be reported to the Electronic Communications Support (ECS) Help Desk.  A Type 1 System Outage is a condition where the CLEC Pre-Orders/Orders/Queries/Maintenance Requests cannot be submitted or will not be accepted by BellSouth.

Type 2 – Regulatory Change.

Any non-Type 1 change to the interfaces between the CLEC’s and BellSouth’s operational support systems mandated by regulatory or legal entities, such as the Federal Communications Commission (FCC), a state commission/authority, or state and federal courts are Type 2 changes.  Regulatory changes are not voluntary but are requisite to comply with newly passed legislation, regulatory requirements, or court rulings.  While timely compliance is required, the systems requirements and methodology to achieve compliance are usually discretionary and within the scope of change management.  Either BellSouth or a CLEC may initiate the change request.

Type 3 – Industry Standard Change.

Any non-Type 1 change to the interfaces between the CLEC’s and BellSouth’s operational support systems required to bring these interfaces in line with newly agreed upon telecommunications industry guidelines are Type 3 changes.  Either BellSouth or a CLEC may initiate the change request.

Type 4 – BellSouth Initiated Change.

Any non-Type 1 change affecting the interfaces between the CLEC’s and BellSouth’s operational support systems which BellSouth desires to implement on its own accord. These changes might involve system enhancements, manual and/or business processes.  These type changes might also include issues for Pre-Orders, Orders, Queries, and Maintenance Requests that can be submitted and accepted, but may require clarification. This classification does not include changes imposed upon these interfaces by third parties such as regulatory bodies (which are Type 2 Changes) or standards organizations (which are Type 3 Changes).

Type 5 – CLEC Initiated Change.

Any non-Type 1 change affecting interfaces between the CLEC’s and BellSouth’s operational support systems which the CLEC requests BellSouth to implement is a Type 5 change.  These changes might involve system enhancements, manual and/or business processes.  These type changes might also include issues for Pre-Orders, Orders, Queries, and Maintenance Requests that can be submitted and accepted, but may require clarification.  This classification does not include changes imposed upon these interfaces by third parties such as regulatory bodies (which are Type 2 Changes) or standards organizations (which are Type 3 Changes).

Type 6- CLEC Impacting Defects and Emergency Changes.

Any non-Type 1 change where a CLEC Impacting defect, interface or business rule discrepancy is found in a production and is impacting a CLECs ability to exchange transactions with BellSouth.  The CLEC and/or BellSouth may initiate these types of changes affecting interfaces between the CLEC’s and BellSouth’s operational support systems.  These type changes might also include issues for Pre-Orders, Orders, Queries, and Maintenance Requests that can be submitted and accepted, but may require workarounds or clarification.

Type 6 Changes should be categorized in the following manner:

Severity 1:  Interface Unusable – Interface discrepancy results in totally unusable interface.  CLEC Pre-Orders / Orders / Queries / Maintenance Requests cannot be submitted or will not be accepted by BellSouth.  Manual workarounds are not feasible.  Change is considered essential to continued operation.  BellSouth and the CLECs will work to resolve the discrepancy as quickly as possible.

Severity 2:  Interface Affecting – Pre-Orders / Orders / Queries / Maintenance Requests require workarounds on the part of BellSouth or the CLECs.  Change is considered critical to efficient operations.  BellSouth and the CLECs will work to resolve the discrepancy in a timely manner.

Severity 3:  Process Impacting – Pre-Orders / Orders / Queries / Maintenance Requests can be submitted and will be accepted through normal process/interfaces.  Clarification is considered critical to ongoing operations.  BellSouth will work to provide appropriate documentation on an expedited basis.

Figure 3-1 shows the top-level process that will be used to evaluate Change Requests.  The BellSouth Account Team(s) will handle BFR requests and production support issues.  Enhancements and defects will be handled through the Change Control Process.

Figure 3-1.  Change Control Decision Process

Agreement

BFR

# 4.0	CHANGE CONTROL PROCESS FLOW

The following two sub-sections describe the process flows for typical Type 1 through Type 5 changes.  Each sub-section will describe the cycle times for an activity and document accountability, sub-process activities, inputs and outputs for each step in the process.  Section 5 of this document describes the process flow for Type 6 changes.  Based on the categorization of the request, the following diagram will help guide a CLEC or BellSouth representative to the appropriate process flow based on Change Control Request Type:

- Figure 4-1.  Change Control Process Flow

## Part 1 - Type 1 Process Flow

Figure 4-2 provides the process flow for resolving a typical Type 1 - System Outage. The Electronic Communications Support (ECS) Group will work with the CLEC community to resolve and communicate information about system outages in a timely manner - actual cycle times are documented in table 4-1 and the sub-process steps.  The ECS Helpdesk number is 888-462-8030.

- Figure: 4-2. Type 1 Process Flow

Table 4-1 describes the cycle times for each process step that is outlined in the Type 1 - System Outage Process Flow.  These cycle times represent typical timeframes for completing the documented step and producing the desired output for the step.  In sub-process step 2 “Initial Notification” timeframe for completing this step does not begin until after the outage has been reported.  The sub-process steps 3 “Status Notification" and 4 "Resolution Notification" are iterative steps. Iterative steps will be performed one or more times until the exit criteria for that process are met.  If resolution is not reached within 20 minutes, BellSouth will provide the initial notification to the CLEC community via e-mail and post outage information on the web.

- Table 4-1.  Type 1 Cycle Times

| Process Description | 1 Identify Issue | 2 Initial Notification | 3 Status Notification | 4 Resolution Notification | 5 Final Resolution Notification | 6 Escalation |
| --- | --- | --- | --- | --- | --- | --- |
| Cycle Time | N/A | 1 hour E-mail & BST Website will be posted if outage exceeds 20 minutes | 2 - 4 hours (Iterative) | 24 hours (Iterative) | < 3 days | > 3 days System Outage Escalation Process |

Note:  The Escalation Process may be used at any time within Steps 3-6 if cycle times are not met and/or responses are not acceptable.

The table below details the steps, accountable individuals, tasks, the inputs/outputs and the cycle time of each sub-process in the Type 1 Process Flow.  This process will be used to capture and communicate system outage information, status notification(s), resolution and notification(s), and final resolution to the CLEC community.  Steps shown in the table are sequential unless otherwise indicated.

- Table 4-2.  Type 1 Detail Process Flow

| Step | Accountability | Sub-processes Activities | Inputs and Outputs | Cycle Time |
| --- | --- | --- | --- | --- |
| 1 | CCCM ECS | Identify Issue: - Internally determine if outage exists with BellSouth Electronic Interface. (The CLEC should perform internal outage resolution activities to determine if the potential problem involves the BellSouth Electronic Interface). - Call the BST Electronic Communications Support (ECS) help desk at 888-462-8030. - ECS and individual CLEC will determine if the problem is likely to have no impact on the industry. If there is no impact, the outage will be worked on a bilateral basis. - ECS will record and track the outage. | INPUTS: - Issue Characteristics - Call to ECS Helpdesk - OUTPUTS: - Recorded Outage | N/A |
| 2 | ECS | iNITIAL nOTIFICATION: - ECS will post to the Web an Initial Industry Notification that a BellSouth Electronic Interface outage has been identified. An e-mail to the CLECs participating in Change Control will also be distributed. - The CLEC initiating the Type 1 System Outage will need to be available for communications on an as needed basis. - ECS will continue to work towards the resolution of the problem - If outage is resolved, this notice is the first and final notification. The process for the item has ended. Outage Information will be reported in the monthly status meeting by the BCCM. | INPUTS: - Recorded Outage - OUTPUTS: - Industry Notification posted on Web - E-mail to CLECs participating in Change Control | 1 Hour If System Outage is not resolved within 20 minutes, a notification will be sent to CLECs via e-mail and posted to the web. |
| 3 | ECS | Status Notification: (Iterative) - If the outage is not resolved, ECS will continue to work towards the resolution on the problem. - ECS may communicate with the industry / affected parties. The following information may be discussed: - Clarification of outage - Current status of resolution - Agreement of resolution - If a resolution has not been identified continue giving status notifications to the industry and continue repeating Step 3 "Status Notification" via the web. - Proceed to Step 4 "Resolution Notification" when a resolution has been identified. | INPUTS: - Industry Notification posted on Web - OUTPUTS: - Status Notification posted on Web - Resolution information | 2-4 hour intervals |
| 4 | ECS CCCM | rESOLUTION Notification: (iTERATIVE) - The resolution notification is posted to the Web. - If the item is determined to be a defect, the CLEC that initiated the call will submit a "Change Request Form" checking the defect box. - If the resolution is not the final resolution the process will loop back to Step 3 "Status Notification". BellSouth will continue to work towards the final resolution. - When the final resolution has been created, proceed to Step 5 "Final Resolution Notification". | INPUTS: - Status Notification posted on Web - Resolution information - OUTPUTS: - Resolution Information posted on Web - Final Resolution Information | 24 hours after reporting outage |
| 5 | ECS | fINAL rESOLUTION Notification: - The final resolution notification is posted on the Web. | INPUTS: - Final Resolution Information - OUTPUTS: - Final Resolution Notification | < 3 days |
| 6 | CCCM ECS | eSCALATION - Escalation is appropriate anytime the interval exceeds the recommended guidelines for notification. - Refer to the Type 1 - Escalation Process documented in Section 7. | INPUTS: - Information or concern relating to a Type 1 - Systems Outage - OUTPUTS: - Documented Escalation - Escalation Response | - 3 days (The Escalation Process may be used at any time within Steps 3-6 if cycle times are not met and/or responses are not acceptable.) |

## Part 2 – Types 2-5 Process Flow

Figure 4-3 provides the process flow for reviewing, scheduling and implementing a typical Type 2-5 Change Request.  The process diagram applies to Change Requests submitted via the Change Control Process.  Change Requests should be submitted to the BellSouth Change Control Manager using the standard Change Request form template.  This template can be acquired on the Change Control web page.

- Figure 4-3.  Change Control Process Flow

Based on the process flow outlined above:

- Software Release Notifications will be provided 30 days or more in advance of the implementation date.

- Requirements for software releases or systems modifications will be provided to CLECs 90 days or more in advance of the implementation date.

- Documentation changes will be provided 30 days or more in advance of implementation date.

- CLEC notification of documentation updates (non-system changes) will be posted 5 (five) business days in advance of documentation posting date.

The table below details the steps, accountable individuals, tasks, inputs/outputs and cycle times of each sub-process in the Change Control process. This process will be used to develop Candidate Change Requests that will be used as input to the Internal Change Management Process.    Steps shown in the table are sequential unless otherwise indicated.

- Table 4-3.  Types 2-5 Detail Process Flow

| Step | Accountability | Sub-processes Activities | Inputs and Outputs | Cycle Time |
| --- | --- | --- | --- | --- |
| 1 | CCCM BCCM | identify need - Internally determine need for change request. These change requests might involve system enhancements, manual and/or business process changes. - Originator and CCCM or BCCM should complete the standardized Change Request Form according to Checklist. - Attach related requirements and specification documents. (See Attachment A-1A, Item 22) - Appropriate CCCM/BCCM submits Change Request Form and related information via e-mail to BellSouth. | INPUTS: - Change Request Form (Attachment A-1) - Change Request Form Checklist (Attachment A-1A) - OUTPUTS: - Completed Change Request Form with related documentation | - N/A |
| - 2 | - BCCM | - open Change Request/VALIDATE CHANGE REQUEST FOR COMPLETENESS - 1. Log Request in Change Request Log. - 2. Send Acknowledgement Notification (Attachment A-3) via e-mail to originator. - 3. Establish request status (‘N’ for New Request) - 4. Review change request for mandatory fields using the Change Request Form Checklist. - 5. Verify Change Request specifications and related information exists. - 6. Send Clarification Notification via email to the originator (Attachment A-4) if needed. - 7. Update Change Request Status to “PC” for Pending Clarification if clarification is needed. - CLEC or BellSouth Originator - If clarification is needed, make necessary corrections per Clarification Notification and submit Change Request Clarification Response (Attachment A-2). | - INPUTS: - Completed Change Request Form with related documentation - Change Request Form Checklist - Change Request Clarification Response - OUTPUTS: - New Change Request - Acknowledgment Notification - Validated Change Request - Clarification Notification - Industry Notification posted on web | 2-3 Bus Days Clarification times would be in addition to cycle time. |
| 3 | BCCM | Review change request for Acceptance - Review Change Request and related information for content. - Determine status of request: - If change already forward Cancellation Notification (Attachment A-3) to CCCM or BCCM and update status to ‘C’ for Request Canceled or ‘CT’ for Training. If Training issue, refer to CSM or Account Team. - If Change Request Clarification Notification not received, validate with CLEC that change request is no longer needed. - If request is accepted, update Change Request status to “P” for Pending in Change Request Log. NOTE: See Section 9.0 Terms and Definitions – Change Request Status for valid status codes and descriptions. - Change Request reviewed for impacted areas (i.e., system, manual process, documentation) and adverse impacts. | INPUTS: - New Change Request - Validated Change Request - Clarification Notification (if required) - OUTPUTS: - Pending Change Request - Clarification Notification (if required) - Cancellation Notification (if required) - CR status updated on web | 10 Bus Days |
| 4 | BCCM CCCM | Prepare foR CHANGE Review meeting NOTE: These activities take place to prepare for Change review meetings when prioritizations take place. BCCM - Prepare an agenda. - Make meeting preparations. - Update Change Request Log with current status for new and existing Change Requests. - Prepare and post Change Request Log to web. CCCM - Analyze Pending Change Requests. - Determine priorities for change requests and establish “Desired/Want” dates. - Create draft Priority List to prepare for Change Review meeting. | INPUTS: - Pending Change Request Notifications - Project Release Status - (Step 10) - Change Request Log - OUTPUTS: - Change Request Log - CLEC Draft Priority List | 5-7 Bus Days |
| 5 | BCCM CCCM | Conduct CHANGE Review Meeting Monthly Status Meetings - Communicate regulatory mandates. - Review status of pending/approved Change Requests (including defects) at monthly status meeting. - Review current Release Management statuses. Prioritization Meetings (held as needed based on published release schedule) - Follow Steps 1-3 from Monthly Status Meetings. - Initiators present Change Requests. - Discuss Impacts. - Prioritize Change Requests. - Develop final Candidate Requests list of Pending Change Requests by interface, ‘Need by Dates’ and prioritized Change Requests. - Update Change Request Log to ‘CRC’ for Change Review Complete, ‘RC’ for Candidate Request List, as appropriate. - Review issues and action items and assign owners. | INPUTS: - Change Request Log - CLEC Draft Priority List - Desired/Want Dates - Impact analysis - OUTPUTS: - Meeting minutes - Updated Change Request Log - Candidate Change Request List - Issues and Actions Items (if required) | - 1 Bus Day (or as needed based on volume) - Meeting Day |
| - 6 | - BCCM | - Document chANGE Review Meeting results - 1. Prepare and distribute outputs from Step 5. | - INPUTS: - Change Request Log - Final Candidate Request List - OUTPUTS: - Updated Change Request Log - Web posting of meeting output | 2 Bus Days |
| 7 | BCCM CCCM | Internal Change Management Process - Both BellSouth and CLECs will perform analysis, impact, sizing and estimating activities only to the Candidate Change Requests that meet the criteria established by the Internal Change Management Process. This ensures that participating parties are reviewing capacity and impacts to schedules before assigning resources to activities. | INPUTS: - Candidate Change Request List with agreed upon ‘Need by Dates’ - Change Request Log - OUTPUTS: - BellSouth’s Proposed Release Package | 25 Bus Days |
| 8 | BCCM CCCM | Conduct Release Package Meeting - Prepare agenda. - Make meeting preparations. - Evaluate proposed release schedule. - Non-scheduled Change Requests returned to Step 4 as Input for the “Prepare for Change Review Meeting” process. - Based on BST/CLEC consensus create Approved Release Package. - Identify Release Management Project Manager, if possible. - Establish date for initial Release Management Project Meeting. - All Change Requests that are in the approved scheduled release will be changed to “S” status for “Scheduled”. | INPUTS: - BellSouth’s Proposed Release Package - BellSouth’s Release Schedule - Change Request Log - OUTPUTS: - Approved Release Package - Updated Change Request Log - Meeting Minutes - Scheduled Change Requests - Non-Scheduled Change Requests (Return to Step 4) - Date for initial Release Management Project Meeting | 1 Bus Day |
| 9 | BCCM | CREATE RELEASE PACKAGE NOTIFICATION - Develop and distribute Release Notification Package via web. | INPUTS: - Approved Release Package - OUTPUTS: - Release Package Notification | - 2 Bus Days after Release Package Mtg. |
| - 10 | - BCCM - (Project Managers from each participating company) | - RELEASE MANAGEMENT AND IMPLEMENTATION - 1. Provide Project Management and Implementation of Release (See Release Management @ Appendix B). - Lead Project Manager communicates Release Management Project status to BCCM for inclusion in Monthly Status Meetings. - BellSouth Business Requirements will be presented to CLECs. If needed, changes will be incorporated and requirements re-baselined. - Once a Change Request is - implemented in a release, the status will be changed to “I” for Change Implemented. | - INPUTS: - Approved Release Package Notification - OUTPUTS: - Project Release Status - Implementation Date - Project Plan, Work Breakdown Schedule, Risk Assessment, Executive Summary, etc - Implemented Change Request | - Ongoing |

# 5.0	 Defect Notification OR EMERGENCY CHANGE Process

- CLEC or BellSouth identified defect or emergency change will enter this process through the Change Management Team.  If the defect is validated internally, it will route through this process, and notification provided to the CLEC community via e-mail and web posting.  CLEC Notification of documentation updates (non-system changes) will be posted 5 (five) business days in advance of documentation posting date.

The table below details the steps, accountable individuals, tasks, inputs/outputs and cycle times of each sub-process in the Type 6 Process Flow.  This process will be used to validate defects, provide defect and status notification(s), workarounds and final resolution to the CLEC community.  Steps shown in the table are sequential unless otherwise indicated.

Table 5-1.  Type 6 Detail Process Flow

| Step | Accountability | Sub-processes Activities | Inputs and Outputs | Cycle Time |
| --- | --- | --- | --- | --- |
| 1 | CCCM BCCM | identify need - Identify Defect. 2. Originator and CCCM or BCCM should complete the standardized Change Request Form indicating that it is a defect. - Attach related requirements and specification documents. These attachments should include the following, if available: - PON - OCN - Specific Scenario - Interface(s) affected - Error message (if applicable) - Release or API version (if applicable) 4. Appropriate CCCM/BCCM submits Change Request Form and related information via e-mail to BellSouth Change Management Team. | INPUTS:  Change Request with defect indicated OUTPUTS:  Completed Change Request Form (with related documentation if necessary) | - N/A |
| 2 | BCCM | Open & VALIDATE DEFECT form for completeness 1. Log Defect in Change Request Log. - Send Acknowledgment Notification via email to initiating CLEC. - Establish Defect status (‘N’ for New Defect). - BCCM reviews change request for mandatory fields using the Change Request Form Checklist. - Verify Defect specifications and related information exists. - Send Clarification Notification via email to the originator if needed. - Update Defect Status to‘ PC’ for Pending Clarification if clarification is needed. If clarification is needed, CLEC or BST originator makes necessary corrections per Clarification Notification and submits via email Defect Clarification Response. | INPUTS: - Completed Change Request Form (with related documentation if necessary) - OUTPUTS: - New Defect - Acknowledgment Notification - Clarification Notification (if required) | - 4 hrs for Severity 1 & 2 - 1 Bus Day for Severity 3 |
| 3 | BCCM | internal validation - Validate that it is a defect. - Perform internal defect analysis. - Determine status of request: - If change already exists or training issue forward Cancellation Notification to CCCM or BCCM and update status to ‘C’ for Request Cancelled or ‘CT’ for Training. If Training issue, refer to CSM or Account Team. - Send Clarification Notification via email if needed and update status to ‘PC’ for Pending Clarification. - If Change Request Clarification Notification not received, validate with CLEC that change request is no longer needed. - If request is valid, update Change Request status to ‘V’ for Validated Defect. NOTE: See Section 9.0 Terms and Definitions – Defect Status for valid status codes and descriptions. Defect notification will be provided to CLEC community via e-mail and web posting. | INPUTS: - New Defect - OUTPUTS: - Validated Defect - Defect notification to CLEC community via e-mail and web posting - Clarification Notification (if required) - Cancellation Notification (if required) | - 1 bus day for Severity 1 & 2 - 3 Bus Days for Severity 3 |
| 4 | BCCM | develop workaround (If applicable) - Defect workaround identified. - Change Request status changed to “W” for workaround identified. - Workaround is communicated via e-mail to originating CLEC. - If appropriate, communication to the CLEC community regarding workaround will be discussed via conference call. Defect workaround notification will be provided to CLEC community via e-mail and web posting. If necessary, a conference call will be established with CLECs to discuss the workaround. If it is determined that additional time is needed to develop workaround due to the complexity of the defect, notification will be provided to CLEC community via e-mail and web posting. This will only apply to Severity 3 defects. In this instance, BellSouth will continue to process orders until a workaround is identified | INPUTS: - Validated Defect - Clarification Notification (if required) OUTPUTS: - Workaround (if applicable) - Clarification Notification (if required) - Cancellation Notification (if required) - E-mail and web posting of workaround | - 1 bus day for Severity 1 & 2 - 5 Bus Days for Severity 3 |
| 5 | BCCM | Monthly status meeting - Provide status of Defect. - Solicit CLEC/ BST input. - Update Defect information as needed. | INPUTS: - Defects Received - Change Request Log - Defect Analysis - Workaround (if applicable) OUTPUTS: - Updated status - Updated Change Request Log - Meeting minutes | - Monthly or when status changes, whichever occurs first |
| 6 | BCCM | internal resolution process - Schedule and evaluate Defects based on capacity and business impacts to the CLECs. - Update status of scheduled Defects to ‘S’ for Scheduled. - Provide status and Defect Release Schedule at next Monthly Status Meeting. 4. Update status of Implemented Defects to ‘I’ for Implemented. | INPUTS: - CLEC/ BST input OUTPUTS: - Defect Release Schedule - Scheduled Defects - Implemented Defects | - Monthly |

# 6.0	 CHANGE REVIEW

## Part 1 – Change Review Meeting

- The Change Review meeting provides the forum for reviewing and prioritizing Pending Change Requests, generating Candidate Change Requests, submitting Candidate Change Requests for sizing, and reviewing the status of all release projects underway.  Status update meetings will be held monthly and are open to all CLEC’s.  Meetings will be structured according to category (pre-order, order, and maintenance, etc.).  Prioritization meetings will be scheduled to coincide with the published release schedules.  For non-system impacting changes, there will be a 5 (five)-business day notice for documentation updates.  The prioritization meeting dates will be communicated when the release schedule is published.

- During the Change Review Meeting each originator of a Change Request will be allowed 5 (five) minutes to present their Change Request.  A question and answer session not to exceed 15 minutes will follow this presentation.  After all presentations for a particular interface are complete, the prioritization process will begin.

- The Change Request Log will be distributed 5 - 7 (five to seven) business days prior to the Change Review meeting. A valid and complete Change Request must be received 33 business days prior to the Change Review Meeting to be placed on the agenda for the next scheduled meeting.

- Note:  Status Meetings will occur monthly.  Prioritization meetings will be scheduled to coincide with the published release schedules and will include the monthly status meeting agenda items.

## Part 2 – Change Review Package

- The Change Review Package will be distributed to all participants 5 – 7 (five to seven) business days prior to the Change Review meeting.  The package will include the following:

- Meeting Notice

- Agenda

- Change Request Log (List of Change Requests to be reviewed)

- Reference to Change Control Process on the BST website (for CLECs not familiar with the process, new CLECs or CLECs that choose to participate after the initial rollout)

- Status Reports from each of the active Release Management Project Teams

## Part 3 – Prioritizing Change Requests

- Prior to the Change Review Meeting, each participating CLEC should determine priorities for change requests and establish “desired/want” dates.  The CLEC should use the Preliminary Priority List form as provided via the web.

- Final prioritization will be determined at the Change Review meeting after presentation of the Change Requests for each category.

- Prioritization Voting Rules

- Voting on an interface not used by the CLEC is prohibited

- One vote per CLEC, per interface

- No proxy voting

- Each company may bring the number of participants necessary to represent their position.  If the number of participants grow to be unmanageable, CLECs and BellSouth will revisit the issue of representation to apply some restrictions.

- Forced Ranking (1 to N, with N being the highest) will be used

- Votes will be tallied to determine order of ranking

- Changes will be ranked by category, by interface

- Manual processes and documentation will be prioritized separately; however they will need to be synchronized with the electronic interface changes

- Sizing and sequencing of prioritized change requests will begin with the top priority items and continue down through the list until the capacity constraints have been reached

- In case of a tie, the affected Changes will be re-ranked and prioritized based on the re-ranking

Example:	The top 2 Changes from high to low are E5 and E2, with E1 and E4 tied for 3rd.  E1 and E4 would be re-ranked and prioritized according to the re-ranking.

| - Pre-Order LENS | - CLEC 1 | - CLEC 2 | - CLEC 3 | - Total |
| --- | --- | --- | --- | --- |
| - E1 | - 3 | - 6 | - 1 | - 10 |
| - E2 | - 4 | - 2 | - 6 | - 12 |
| - E3 | - 6 | - 1 | - 2 | - 9 |
| - E4 | - 2 | - 4 | - 4 | - 10 |
| - E5 | - 5 | - 5 | - 3 | - 13 |
| - E6 | - 1 | - 3 | - 5 | - 9 |

# Introduction and Retirement of interfaces

Introduction of New Interfaces

BellSouth will introduce new interfaces to the CLEC Community as part of the Change Control Process. BellSouth will seek to conform to the notification process for Type 4 (BellSouth Originated) changes as described in this document. In the event that BellSouth is forced to deviate from the Type 4 (BellSouth Originated) process for new non-impacting interface functionality, BellSouth will notify all CLECs of the deviation as promptly as BellSouth will provide specifications on the interface being developed to the CLEC CommunityAs new interfaces are deployed, they will be added to the scope of this document as appropriate, based on the use by the CLEC community and requested changes will be managed by this process.

Retirement of Interfaces

The retirement of interfaces will not be part of the Change Control Process.  As active interfaces are retired, BellSouth will post a CLEC Notification Letter to the web six (6) months prior to the retirement of the interface.  BellSouth will have the discretion to give provide shorter notifications (30-60 days) on interfaces that are not actively used and/or have low volumes.

# 8.0	ESCALATION PROCESS

- Guidelines

- The ability to escalate is left to the discretion of the CLEC based on the severity of the missed or unaccepted response/resolution.

- Escalations can involve issues related to the Change Control process itself.

- For change requests, the expectation is that escalation should occur only after normal Change Control procedures (e.g. communication timelines) have occurred per the Change Control agreement.

- Three levels of escalation will be used.

- For Type 1 issues, the escalation process is agreed to allow BellSouth a one day turnaround for each cycle of escalation.

- For Types 2-5 issues, the escalation process is agreed to allow BellSouth a five day turnaround for each cycle of escalation.

- Each level will go through the same Cycle, which is described below.

- All escalation communications will be distributed by Change Control to the industry unless there is a proprietary issue.

- Contact List for Escalation - ECS Group - Type I Changes

- If the originator does not receive a call back from the EC Support Group according to the times specified in this document, they may escalate according to the following list:

| - Escalation Level | - Name and Title | - Office Number | - Pager Number | - Email Address |
| --- | --- | --- | --- | --- |
| - 1st Level | - Susan Hart - Manager - EC Support Group - Interconnection Operations | - 205-733-5393 | - 1-800-946-4646 PIN 1436470 | - Susan.K.Hart@bridge.bellsouth.com |
| - 2nd Level | - Bruce Smith - Operations Director - EC Support Group - Interconnection Operations | - 205-988-7211 | - 1-800-542-3260 | - Bruce.Smith@bridge.bellsouth.com |
| - 3rd Level | - Bill Reid - Operations Assistant Vice President - Interconnection Operations | - 205-988-1447 | - 1-800-946-4646 PIN 1179523 | - Bill.C.Reid@bridge.bellsouth.com |

- NOTE: If a call is escalated without first attempting to contact the ECS Helpdesk, the caller will be referred back to the ECS Helpdesk.

- Escalation Cycle for Types 2-6 Change Requests

- Item must be formally escalated as an e-mail sent to the appropriate escalation level within BellSouth with a copy to the industry and BellSouth Change Control e-mail.

- Subject of e-mail must be CLEC (CLEC Name) ESCALATION-CR#, if applicable, Level of Escalation, unless it is proprietary.

- Content of e-mail must include:

- Definition and escalation of item.

- History of item.

- Reason for escalation.

- Desired outcome of CLEC

- Impact to CLEC of not meeting the desired outcome or item remaining on current course of action as previously discussed at the Change Control Meeting for enhancements.

- Contact information for appropriate Level including Name, Title, Phone Number, and E-mail ID.

- For escalation Level 2, forward original e-mail and include any additional information including the reason that the matter could not be resolved at Level 1.

- For escalation Level 3, forward original e-mail and include any additional information including the reason that the matter could not be resolved at Levels 1 and 2.

- BellSouth will reply to escalation request with acknowledgement of receipt within 4 hrs and begin the escalation process through Level of escalation.

- The escalating CLEC should respond to BellSouth within 5 days as to whether escalation will continue or the BellSouth response has been accepted as closure to the item.

- If the BellSouth position suggests a change in the current disposition of the item (i.e., what has already been communicated to the industry), a conference call will be held within 1 business day of the BellSouth decision in order to provide industry notification with the appropriate executives.

- BellSouth will publish the outcome of the conference call to the industry via web.

- If unsatisfied with an outcome, either party can seek appropriate relief.

- Contact List for Escalation - Type 2 - 6 Changes

- ESCALATIONS SHOULD BE WITHIN INFORMATION TECHNOLOGY.

- Within 5 business days of receipt (4 from acknowledgement), BellSouth Change Control appropriate executives will reply through BellSouth Change Control with BellSouth’s position and explanation for that position. Escalations should be made according to the following list.

| - Escalation Level | - Name and Title | - Office Number | - Email Address |
| --- | --- | --- | --- |
| - 1st Level | - Valerie Cottingham - Director - Change Control Process | - 205-321-2168 | - Valerie.cottingham@bridge.bellsouth.com |
| - 2nd Level | - Terrie Hudson - AVP Sales | - 770-936-3740 | - Terrie.Hudson@bridge.bellsouth.com |
| - 3rd Level | - TBD - VP Sales |  |  |

## Dispute Resolution Process

In the event that an issue is not resolved through the Escalation Process as described herein, BellSouth and the impacted CLEC(s) may follow this Dispute Resolution Process.  BellSouth and the CLEC shall assemble a Joint Investigative Team, within one week, comprised of subject matter experts.  The party prompting the dispute should initiate the formation of the team.  The team should be co-chaired by representatives of BellSouth and the CLEC respectively.  The investigative team will conduct a root-cause analysis to determine the source of the problem, if one exists, and then develop a plan for remedying it.  The parties to the dispute must escalate the issue within each company to the person who has ultimate authority for State operations in an effort to achieve a resolution.

If the dispute cannot be resolved between the companies after these steps are taken, then either Party to the dispute may utilize the dispute resolution process identified in Section 16 of the General Terms and Conditions of this Agreement, incorporated herein by reference.

# 9.0	Changes to this ProceSS

- The current, approved version of this process document will be stored under the component name “Ccp.doc”.  The BellSouth Change Control Manager BCCM (and alternate) will be the only persons authorized to update the document version.

- Requests for changes to the Change Control Process may be submitted to the BellSouth Change Control Manager (BCCM) using the Change Request form located in the Appendix A.  Cosmetic changes may be made and published by the BCCM (or alternate) without further review.   Other changes will be reviewed at the monthly Change Review status meetings.  All changes will be submitted as a change request and reviewed.

# 10.0	TESTING

Requests related to testing of processes and interfaces will be included in the Change Control Process.  Changes to BellSouth’s testing environments and supporting processes will be submitted through the Change Control Process as a Type 5 request.  The requests will follow the guidelines and intervals set forth in the Type 5 process flow.

# 11.0	TERMS and Definitions

- A

- Accountability.  Individual(s) having responsibility for completing and producing the outputs of each sub-process as defined in the Detailed Process Flow.

- Acknowledgement Notification.  Notification returned to originator by BCCM indicating receipt of Change Request.

- Approved Release Package.  Calendar of Candidate Change Requests with consensus target implementation dates as determined at the Release Package Meeting.

- B

- BellSouth Change Control Manager (BCCM).  BellSouth Point of Contact for processing Change Requests and defects.

- BFR (Bonafide Request).  Process used for providing custom products and/or services.  Bonafide Requests are outside the scope of the Change Control Process and should be referred to the appropriate BellSouth Account Team.

- Business Day.  A business day is considered any Monday-Friday workday that does not fall on an official BellSouth holiday.

- Business Rules.	The logical business requirements associated with the Interfaces referenced in this document.  Business rules determine the when and the how to populate data for an Interface. Examples of data defined by Business Rules are:

- The five primary transactions sets: 850, 855, 860, 865, and 997

- Data Element Abbreviation and Definition

- Activity Types at the appropriate level (account, line, feature) and the associated Usage Type (optional, conditional, required, not applicable, prohibited)

- Conditions/rules associated with each Activity and Usage Type

- Dependencies relative to other data elements

- Conditions which will be edited within BellSouth’s OSSs

- Valid Value Set

- Data Characteristics

- C

- Cancellation Notification.  Notification returned to originator by the BCCM indicating a Change Request has been canceled for one of the following reasons: BST cancellation, duplicate request, training issue, or failure to respond to clarification.

- Candidate Request List.  List of prioritized Change Requests with associated “Need by Dates” as determined at an Change Review Meeting.  These requests will be submitted for sizing and sequencing.

- Candidate Change Request.  Change Requests that have been prioritized at an Change Review Meeting and are eligible for independent sizing and sequencing by BellSouth and each CLEC.

- Change Request.  A formal request submitted on a Change Request Form, to add new functions, defects or Enhancements to existing Interfaces (as identified in the scope) in a production environment.

- Type 1 – BellSouth System Outage.  A System Outage is where the system is totally unusable or there is degradation in an existing feature or functionality within the interface.

- Type 2 – Regulatory Change. Any non-Type 1 changes to the interfaces between the CLEC’s and BellSouth’s operational support systems mandated by regulatory or legal entities, such as the Federal Communications Commission (FCC), a state commission/authority or state and federal courts.

- Type 3 – Industry Standard Change. Any non-Type 1 changes to the interfaces between the CLEC’s and BellSouth’s operational support systems required to bring these interfaces in line with newly agreed upon telecommunications industry guidelines.

- Type 4 – BellSouth Initiated Change.  Any non-Type 1 changes affecting the interfaces between the CLEC’s and BellSouth’s operational support systems which BellSouth desires to implement on its own accord.

- Type 5 – CLEC Initiated Change.  Any non-Type 1 changes affecting the interfaces between the CLEC’s and BellSouth’s operational support systems, which the CLEC requests BellSouth to implement.

- Type 6 – CLEC Impacting Defect.  Any non-Type 1 change where a CLEC Impacting Defect is found in a production environment when the system is not operating as specified in baseline business requirements.

- Change Request Status.  The status of a Change Request as it flows through the Change Control process as described in the Detailed Process Flow.

- A = Appeal.  Indicates a cancelled Change Request is being appealed by the originator (Step 3).

- C = Request Cancelled.  Indicates a Change Request has been canceled due to one of the following reasons (Step 3):

- CB = Cancellation by BellSouth.  BST may reject the change request based on the following reasons: cost/benefit, resource commitments, industry direction or BellSouth direction.

- CC = Clarification.  Requested clarification not received in allotted time (7 days).

- CD = Duplicate Request.  A request for this change already exists.

- CT = Training.  Requested change already exists, additional training may be required.

- CRC = Change Review Complete.  Indicates a Change Request has been reviewed at an Change Review Meeting, but did not reach the Candidate Request List (Step 10).

- D = Request Purge.  Indicates the cancellation of a Change Request that has been pending for 12 months and has failed to reach the Candidate Request List  (Step 3).

- I = Change Implemented.  Indicates a Change Request has been implemented in a release (Step 10).

- N = New Change Request. Indicates a Change Request has been received by the BCCM, but has not been validated (Step 2).

- P = Pending. Indicates a Change Request has been accepted by the BCCM and scheduled for Change Review (Step 3 moving to Step 4).

- PC = Pending Clarification. Indicates a Clarification Notification has been sent to the originator, BCCM awaiting response (Step 2 or 3).

- PN = Pending N times.  Indicates a Change Request reached the Candidate Request List, was sized but not scheduled for a release and has cycled through the process N number of times.  Example: P1 = 2nd time through process, P2 = 3rd time through process, etc (Step 8).

- RC = Candidate Request.  Indicates a Change Request has completed the Change Review process and been assigned to the Candidate Request List for sizing and sequencing (Step 5).

- S – Request Scheduled.  Indicates a Change Request has been scheduled for a release (Step 8).

- Change Review Meeting.  Meeting held by the Change Review participants to review and prioritize pending Change Request, generate Candidate Change Request, and submit Candidate Change Request for sizing and sequencing.

- Change Review Package.  Package distributed by the BCCM 5 – 7 business days prior to the Change Review Meeting.  The package includes the Meeting Notice, Agenda, Approved Release Package, Change Request Log, etc.

- Clarification Notification.  Notification returned to the originator by the BCCM indicating required information has been omitted from the Change Request and must be provided prior to acceptance of the Change Request.  The Change Request will be cancelled if clarification is not received by the date indicated on the Clarification Notification.

- CLEC Affecting Change.  Any change that requires the CLEC to modify the way they operate or to rewrite system code.

- CLEC Change Control Manager (CCCM).  CLEC Point of Contact for processing Change Requests.

- CSM.  Customer Support Manager which supports resale and facility based CLECs.

- Cycle Time.  The time allotted to complete each step in the Change Control Process prior to moving to the next step in the process.

- D

- Defect (Documentation).  A condition where the documentation does not agree or accurately reflect the business environment.

- Defect (Electronic Interfaces).  A defect found in a production environment when the system is not operating as specified in a baseline business requirement's document.

- Defect Status.  The status of a CLEC Impacting Defect Change Request as it flows through the Change Control process as described in the Detailed Process Flow.

- A = Appeal.  Indicates a cancelled Change Request is being appealed by the originator (Step 3).

- C = Cancelled.  Indicates a Change Request has been canceled due to one of the following reasons (Step 3):

- CC = Clarification.  Requested clarification not received in allotted time (7 days).

- CD = Duplicate Request.  A request for this change already exists.

- CT = Training.  Requested change already exists, additional training may be required.

- DC = Defect Cancelled.  Process is operating as specified in the baseline requirements.

- I = Implemented.  Indicates a Defect Change Request has been implemented in a release (Step 6).

- N = New Defect Change Request.  Indicates a Defect Change Request has been received by the BCCM and the change request form validated for completeness (Step 2).

- PC = Pending Clarification.  Indicates a Clarification Notification has been sent to the originator, BCCM awaiting response (Step 2 or 3).

- S = Scheduled for Release.  Indicates a Defect Change Request has been scheduled for a release (Step 6).

- V = Validated Defect.  Indicates internal analysis has been conducted and it is determined that it is a validated defect (Step 3).

- W = Workaround Identified.  Indicates a workaround has been developed and communicated to impacted CLEC community (Step 4).

- E

- Enhancement.  Functions which have never been introduced into the system; improving or expanding existing functions; required functional changes to system interfaces (user and other systems), data, or business rules (processing algorithms – how a process must be performed); any change in the User Requirements in a production system.

- I

- Internal Change Management Process.  Internal process unique to BellSouth and each participating CLEC for managing and controlling Change Requests.

- N

- Need-by-Date.  Date used to determine implementation of a Change Request. This date is derived at the Change Review Meeting through team consensus. Example: 1Q99 or Release XX.

- P

- Points of Contact (POC).   An individual that functions as the unique entry point for change requests on this process.

- Priority.  The level of urgency assigned for resource allocation to implement a change.  Priority may be initially entered by the originator of the Change Request, but may be changed by the BCCM with concurrence from the originator or the Review Meeting participants.  In addition, level of priority is not an indication of the timeframe in which the Change Request will be worked.  It is the originator’s label to determine the priority of the request submitted.

- One of four priorities may be assigned:

- 1-Urgent.  Should be implemented as soon as possible.  Resources may be pulled from scheduled release efforts to expedite this item.  A need-by date will be established during the Change Review Meeting.  A special release may be required if the next scheduled release does not meet the agreed upon need-by date.

- 2-High.  Implement in the next possible scheduled major release, as determined during the Release Package Meeting.

- 3-Medium.  Implement in a future scheduled major release.  A scheduled release will be established during the Release Package Meeting.

- 4-Low.  Implement in a future scheduled major release only after all other priorities. A scheduled release will be established during the Release Package Meeting.

- Project Plan. Document which defines the strategy for Release Management and Implementation, including Scope Statement, Communication Plan, Work Breakdown Structure, etc.  See Release Management Project Plan template, Attachment B-1.

- Proposed Release Package: Proposed set of change requests slated for a release that the BCCM presents to the CLEC community during the Release Package Meeting

- R

- Release – Major.   Implementation of scheduled Change(s) which may or may not impact all CLECs; may or may not require CLECs to make changes to their interface and may or may not prohibit the use of an interface upon implementation of the Change(s).  Application-to-Application and Machine-to-Human.

- Release – Minor.   Implementation of scheduled Change(s) which do not require coordination with the entire CLEC industry, do not require CLECs to make changes to their interface or do not prohibit the use of an interface upon implementation of the Change(s).  Machine-to-Human.

- Release Package.  Package distributed by the BCCM listing the Candidate Change Requests that have been targeted for a scheduled release.

- Release Package Notification.  Package distributed by the BCCM and used to conduct an initial Release Management and Implementation meeting. The package includes the list of participants, meeting date, time, Approved Release Package, Maintenance/Defect Notification, etc.

- Release Schedule: Schedule that contains the intended dates for implementation of software enhancements.  This release schedule is created annually.

- S

- Specifications.  Detailed, exact document(s) describing enhancement and/or defects, business processes and documentation changes requested and included with the Change Request as additional information.

- System Outage.  A System Outage is where the system is totally unusable or there is degradation in an existing feature or functionality within the interface.

- V

- Version (Document).  Indicates variation of an earlier Change Control process document. Users can identify the latest version by the version control number.

# APPENDIX A – CHANGE CONTROL FORMS

## See Attached Forms

- This section identifies the forms to be used during the initial phases of the Change Control process accompanied by a brief explanation of their use.  Attachments A1 – A-4A contains sample Change Control forms and line by line Checklists.

- Change Request Form.  Used when submitting a request for a change (Attachment A-1).

- Change Request Form Checklist.  Provides line-by-line instructions for completing the Change Request form (Attachment A-1A).

- Change Request Clarification Response.  Used when responding to request for clarification or Clarification Notification (Attachment A-2).

- Change Request Clarification Checklist.  Provides line-by-line instructions for completing the Change Request Clarification Response (Attachment A-2A).

- Acknowledgement Notification.  Advises originator of receipt of Change Request by BCCM (Attachment A-3).

- Acknowledgement Notification Checklist.  Provides line-by-lines instructions for completing the Acknowledgement Notification.  (Attachment A-3A).

- Cancellation Notification.  Advises the originator of cancellation of a Change Request (Attachment A-3).

- Cancellation Notification Checklist.  Provides line-by-line instructions for completing the Cancellation Notification.  (Attachment A-3B).

- Clarification Notification. Advises originator that a Change Request is being held pending receipt of additional information (Attachment A-4).

- Clarification Notification Checklist.   Provides line-by-line instructions for completing the Clarification Notification.  (Attachment A-4A).

# APPENDIX B – RELEASE MANAGEMENT

## See Attached Forms

- Release Management and Project Implementation is described in Step 10 of the Change Control Process.  Project Managers are responsible for confirming the release date, developing project plans and requirements, providing the WBS, Gantt chart and Executive Summary to the BCCM for input to the Change Review Package and ensuring the successful implementation of the release.

- The BST Change Control Manager (BCCM) will distribute the Release Notification Information via web.  The Notification should contain the following information:

- List of participants (Project Managers from each stakeholder)

- Date(s) for the next Project Manage Release meeting(s)

- Times

- Logistics

- Meeting facilitator and minutes originator (rotated between stakeholders)

- Current Approved Release Package (email attachment)

- Current Maintenance/Defect Notification Information (web posting)

- Draft Release Project Plan - WBS (email attachment created by the Lead Project Manager (s) assigned in step 8 of the Change Control Process)

- Lead Project Manager (s) assigned to the Release with reach numbers (s)

Attachments B1 – B12 contain templates designed to assist the Project Manager(s) in conducting project management responsibilities as needed for Release Management and Implementation.

# APPENDIX C –Additional Documents

## See Attached Documents