BEFORE THE FLORIDA PUBLIC SERVICE COMMISSION

DIRECT TESTIMONY OF

PATRICIA Q. WEST

ON BEHALF OF

PROGRESS ENERGY FLORIDA

DOCKET NO. 040007-EI

AUGUST 4, 2004

Q.	Please state your name and business address.

A.	My name is Patricia Q. West.  My business address is 100 Central Avenue, St. Petersburg, Florida, 33701.

Q.	By whom are you employed and in what capacity?

A.	I am employed by Progress Energy Florida, Inc. (“Progress Energy” or “Company”) as Manager of Environmental Projects and Strategy.  In that position, I have responsibility for the development of compliance strategies pertaining to new regulatory requirements for energy supply facilities in Florida, North Carolina, South Carolina and Georgia.

Q.	Have you previously filed testimony before this Commission in connection with Progress Energy Florida’s Environmental Cost Recovery Clause?

A.	Yes, I have.

- Q.	Have your duties and responsibilities remained the same since you last filed testimony in this proceeding?

A.	Yes.

Q.	What is the purpose of your testimony?

A. 	The purpose of my testimony is to explain material variances between the Estimated/Actual project expenditures and the original cost projections for environmental compliance costs associated with PEF’s Pipeline Integrity Management (“PIM”) Program for the period January 2004 through December 2004.

I will also explain the projected expenditures associated with PEF’s Section 316(b) Cooling Water Intake Program for the remainder of 2004.  PEF petitioned the Commission for approval of cost recovery for the Section 316(b) Cooling Water Intake Program on May 18, 2004. See Docket No. 040472.

Q.	Please explain the projected variance in O&M costs associated with the Pipeline Integrity Management (“PIM”) Program (Project #3a).

A.	O&M costs for the PIM Program are projected to be $745,000 higher than originally projected.  This variance is attributable to four factors.  First, PEF originally projected a total of $215,000 in O&M costs for the PIM program.  This included $150,000 for performing the baseline integrity assessment on the Bartow/Anclote pipeline segment, $50,000 for initiating the baseline assessment of the Bartow above-ground piping segment, and $15,000 for reviewing and evaluating the results.  Based on costs incurred to date and contractor bids for the remaining work, PEF now projects the costs of these activities for 2004 to be $290,000, resulting in a projected year-end variance of $75,000.

Second, PEF originally projected $20,000 in 2004 O&M costs to support the leak detection system.  Because the work is being performed as part of a capital project, PEF has reclassified these expenses as capital costs, resulting in a negative variance of ($20,000) in O&M costs.

Third, due to increased workload associated with the PIM program, PEF created a new position solely devoted to oversight of the PIM program, resulting in a variance of approximately $140,000 in O&M costs.

Finally, in accordance with the PIM Plan, PEF’s risk assessments have identified unanticipated O&M projects that need to be undertaken to reduce risks to pipeline integrity and security.  For the remainder of 2004, PEF expects to incur $250,000 in O&M costs for various remedial, preventative, and mitigative actions along the pipeline.  In addition, PEF projects $300,000 in O&M costs to lower a segment of the Bartow-Anclote pipeline below Alligator Creek to ensure adequate coverage where water flow and meandering have exposed the pipeline.  The county regularly cleans vegetation from the creek with large equipment to maintain flow, creating a high probability for damage to the pipeline unless the pipeline is lowered.  This measure is necessary to comply with the PIM regulations (49 CFR Part 195) and PEF’s PIM Plan, which  require the company to evaluate potential threats to pipeline integrity, like third party damage, and to take preventative measures to provide enhanced protection.

Q.	Please explain the projected variance in capital costs for the Pipeline Integrity Management (“PIM”) Program (Project #3b).

A.	Capital costs for the PIM Program are projected to be $692,706 higher than originally projected.  This variance is attributable to several factors.  First, PEF originally projected that work on the leak detection system for the Bartow/Anclote pipeline would be completed in 2003.  However, the project was not completed on schedule.  Year-to-date, PEF had a reclass of costs from the prior period (discussed in Mr. Portuondo’s testimony) and has incurred $131,060 in capital costs for the project and we anticipate incurring an additional $20,000 by year’s end (as discussed above this expense was originally classified as O&M).   Thus, we project a variance of $151,060 in capital costs for the leak detection system.

Second, PEF projects $60,000 in previously unanticipated capital costs to construct a protection system around a section of the pipeline at Alderman Road in order to reduce risks to pipeline integrity.  This section of the pipeline is routed along a sand embankment that is used by four wheel drive vehicles for recreational purposes.  This activity has left the pipeline exposed and vulnerable to further damage unless measures are taken to preclude public access.  This is necessary to comply with the PIM regulations (49 CFR Part 195) and PEF’s PIM Plan which, as discussed above, require the company to take preventative measures to provide protection against potential threats to pipeline integrity, including third party damage.

Q.	What costs do you expect to incur in 2004 in connection with Section 316(b) Cooling Water Intake Program?

A.	On May 18, 2004, PEF petitioned the Commission for approval of cost recovery for a new environmental program required to comply with new regulations adopted by the U.S. Environmental Protection Agency under Section 316(b) of the Clean Water Act.  For the remainder of 2004, we estimate total O&M expenditures of $50,000 to $100,000 for the development of a Proposal for Information Collection required by the new regulations.   However,  those projected costs do not exceed the $287,500 in environmental study costs that PEF included in the MFRs filed in Docket No. 000824-EI.  Thus, consistent with Commission’s offsetting policy discussed in PEF’s petition, PEF does not project any recoverable costs for this program in 2004.

Q.	Does this conclude your testimony?

A.	Yes it does.