# Appendix H. Progress Energy Florida’s RFP for Power Supply Solicitation Package

Progress Energy Florida

Request For Proposals

for

Power Supply Resources

Solicitation Document

- October 7, 2003

Revised November 12, 2003

RFP Document

Table of Contents

I.	INTRODUCTION	1

A.	Overview of Request For Proposals (RFP)	1

B.	Objectives of the RFP	1

C. 	PEF’s “Next Planned Generating Unit”	2

D.	Schedule	2

E.	Official Contact	3

II.	DEFINITIONS	1

III.	INSTRUCTIONS TO BIDDERS	1

A.	General Instructions	1

B.	Submission of Proposals	1

C.	Proposal Fees/ Proposal Variations	2

D.	Proposal Size, In-Service Date, and Term	2

E.	Contract Flexibility Provisions	3

F.	Security Requirements	3

G.	Permitting Responsibility	3

H.	Regulatory Provisions	3

I.	Reservation of Rights	4

IV.	SOLICITATION PROCESS	1

A.	Description of the Process	1

B.	Pre-Bid Submission Activities	1

C.	Evaluation Process	2

D.	Contract Negotiations	14

E.	Regulatory Filings	14

V.	PROGRESS ENERGY FLORIDA’S “NEXT PLANNED GENERATING UNIT”	1

VI.	PROGRESS ENERGY FLORIDA’S SYSTEM SPECIFIC CONDITIONS	1

- Attachment A – Key Terms and Conditions	A-1

- Attachment B – Ten-Year Site Plan	B-1

- I.	INTRODUCTION

- A.	Overview of Request For Proposals (RFP)

Progress Energy Florida (PEF) is seeking proposals from eligible Bidders for electric generating capacity and associated energy as described herein. In this RFP, Progress Energy Florida is soliciting proposals for alternatives to the Company’s “next planned generating unit,” which is approximately 500 MW of capacity available for commercial delivery by December 1, 2007.

Progress Energy Florida invites proposals from all potential suppliers who are capable of meeting the conditions of the RFP, including other electric utilities, marketers, exempt wholesale generators, independent power producers, and qualifying facilities. Demand-side proposals are not eligible to participate in the RFP. Progress Energy Florida’s most recent Ten-Year Site Plan has identified an expected requirement for base or intermediate load resources. However, the Company will consider other resource types and evaluate all bids using the same criteria. The proposals received will be compared to PEF’s self-build alternative.

The RFP is presented in two documents. The first is this RFP Solicitation Document, which outlines Progress Energy Florida’s requirements for submission of bids and describes the criteria that will be used to compare and evaluate proposals. The second document is the Response Package, which includes the information required from all Bidders and the schedules that Bidders are required to provide.

- B.	Objectives of the RFP

The purpose of the RFP is to solicit and screen, for potential subsequent contract negotiations, competitive proposals for supply-side alternatives to PEF’s next planned generating unit. Progress Energy Florida’s objective is to select resources that offer the maximum value, based on cost and non-cost attributes, to the Company and its customers. Progress Energy Florida intends to realize this objective by opening the RFP to all supply-side resource alternatives, including those that offer enhanced fuel diversity.

During its normal course of business, Progress Energy Florida continuously evaluates alternatives as resources to fulfill its need for generating plants identified in its Ten-Year Site Plan (TYSP) (see Attachment B). Alternatives that are identified and evaluated are not always the same type (i.e. peaking, intermediate, or baseload) as indicated in the TYSP. Depending on the type of alternative being evaluated, it is possible that its inclusion in the Company’s resource mix will impact the timing or need for other resources identified in the TYSP, including Hines 4. For this, and other possible reasons, PEF reserves the right to cancel, modify or withdraw the RFP, to reject any and all responses, and to terminate negotiations at any time during the RFP process.

- C. 	PEF’s “Next Planned Generating Unit”

Rule 25-22.082 of the Florida Administrative Code requires investor-owned utilities to provide a description of the “next planned generating unit” on which the RFP is based. Progress Energy Florida’s Ten-Year Site Plan (see Attachment B), which was filed with the Florida Public Service Commission on April 1, 2003, shows the “next planned generating unit” that is subject to Rule 25-22.082 to be the Hines Energy Complex Unit 4, located in Polk County, Florida. This natural gas-fired combined cycle unit of approximately 565 MW (net winter rating) would be placed in commercial operation by December 1, 2007. A detailed technical description, as well as the financial assumptions and parameters associated with the unit, are provided in Section V of this RFP.

- D.	Schedule

The solicitation schedule will be approximately a 13-month process, comprising four phases: (1) Pre-Submission; (2) Evaluation Process; (3) Contract Negotiations; and (4) Regulatory Filings. The schedule is presented below.

- Pre-Submission (9/10/03 – 12/16/03)

Notice of RFP					9/10/03

Pre-Issuance Conference			9/23/03

Issuance of RFP				10/7/03

Notices of Intent to Bid Due			10/14/03

Bidders Conference				10/21/03

Submission of Bids				12/16/03

- Evaluation Process (12/16/03 – 4/27/04)

Determination of Short List			3/5/04

Determination of Final List			4/27/04

- Contract Negotiations (4/28/04 – 7/27/04)

Initiate Contract Negotiations			4/28/04

Award Announcement			7/27/04

- Regulatory Filings (7/27/04 – 9/27/04)

File contract(s) for certification		9/27/04

Progress Energy Florida reserves the right to revise the schedule. Depending on the number of proposals received, PEF may shorten the Evaluation Process schedule and advance the dates associated with the Short List and Final List announcements and the beginning of Contract Negotiations and Regulatory Filings. In the event the PEF self-build alternative is clearly superior to the short-listed proposals, the Final List announcement and Contract Negotiations steps of the process will not take place.

- E.	Official Contact

All inquiries or contact about the RFP, including questions of clarification, requests for additional information, and submission of proposals, must be directed in writing to PEF’s Official Contact listed below:

Daniel J. Roeder

Project Leader

System Planning & Operations Department

Progress Energy Building - 7A

P.O. Box 1551

410 S. Wilmington Street

Raleigh, NC 27601

Telephone number:  (919) 546-7966

Fax number:  (919) 546-7558

E-mail address:  PEF_2007_RFP@pgnmail.com

Unsolicited contact with other PEF personnel or employees of PEF affiliated companies concerning the RFP is not allowed and will constitute grounds for disqualification. Progress Energy Florida reserves the right to provide written responses to all Bidders on the RFP web site (www.progress-energy.com/rfp) if it is deemed necessary to ensure that all Bidders have equal access to the same information.

- II.	DEFINITIONS

Presented below are the definitions of critical terms used in this RFP and solicitation process. Other definitions are included in the Key Terms & Conditions (see Attachment A).

Automatic Generation Control (AGC): AGC is the automated regulation, within predetermined limits, of the power output of electric generators within a prescribed geographic area in response to changes in system frequency, tie-line loading, or the relation of these to each other, so as to maintain the scheduled system frequency and/or the established interchange with other geographic areas. This regulation will be accomplished through communication links between PEF’s Energy Control Center dispatch computer and each generator equipped with such control.

Availability Adjustment Factor (AAF):  A Facility’s or Bidder’s ability to provide capacity in the amount requested by PEF. The Availability Adjustment Factor is defined in Section 2 of the Key Terms and Conditions (Attachment A).

Bidder:  Any entity that submits a proposal to PEF in response to this RFP.

Equivalent Availability Factor (EAF): Sum of the Equivalent Unplanned Derated Hours (EUDH) and Equivalent Planned Derated Hours (EPDH) subtracted from Available Hours (AH) and divided by Period Hours (PH). The method for calculating the Equivalent Availability Factor is defined in the discussion of Section II.H of the Response Package.

Equivalent Forced Outage Rate (EFOR): Sum of Forced Outage Hours (FOH) and Equivalent Forced Derated Hours (EFDH) divided by the sum of Forced Outage Hours (FOH) and Service Hours (SH). The method for calculating the Equivalent Forced Outage Rate is defined in the discussion of Section II.H of the Response Package.

Existing Unit Proposal:  A bid to provide capacity and energy from a specific commercial operating unit identified by the Bidder.

Facility:  All of the equipment, property, buildings, and generation and transmission facilities necessary to allow the Bidder to fulfill its proposal to provide capacity and energy to PEF pursuant to this RFP.

Forced Outage:  An unplanned component failure (immediate, delayed, postponed, or start failure) or other condition that requires the unit be removed from service immediately, within six hours, or before the end of the next weekend.

Frequency Control:  The capability of a generator to automatically respond to frequency deviations by increasing or decreasing its gross real power output as a result of governor action.

For generation located inside the PEF control area or dynamically telemetered into the PEF control area:

The Bidder’s generator(s) shall be equipped with fully functional governors with droop adjustable from 2% to 6% and nominally set at 4%. The governors will be fully responsive to frequency deviations exceeding 0.036 Hertz (Hz).

For generation located outside the PEF control area:

The Bidder shall comply with the frequency response requirements of the host control area.

Fully Dispatchable:  A generator is Fully Dispatchable when PEF makes the sole decision to operate the unit with exceptions granted for maintenance and testing, and the generator is controlled through an AGC link with PEF’s Energy Control Center. The generating facility must be available for PEF’s dispatch in accordance with the following operating parameters, as specified by the Bidder in its proposal: minimum load, ramp rates, start time, maximum starts per year, annual operating hour limit, and minimum run time.

Fully Schedulable:  A project is Fully Schedulable when the project’s output is determined by a schedule specified by PEF. PEF will provide the Bidder with a tentative schedule by 4:00 p.m. for deliveries on the following day. PEF will revise this schedule as necessary to respond to unanticipated operating requirements subject to normal utility practice.

Minimum Evaluation Requirements:  The minimum requirements that all proposals are required to meet and with which a Bidder’s compliance will be assessed in Step 4 of the evaluation process (see Section IV.C).

New Unit Proposal:  A bid to provide capacity and energy from a new unit or block of units which is not currently in commercial operation.

Official Contact:  The PEF representative, or designee, identified in Section I.E of this RFP to whom all contact regarding this solicitation process must be made.

Power System: Physically connected generation and transmission facilities operated as an integrated unit under one central management or operating supervision.

Response Package:  The second section of this RFP that identifies the information and schedules that Bidders are required to provide in their proposals to PEF.

RFP Project Team:  A group of individuals with backgrounds in a number of disciplines necessary to conduct a thorough evaluation of each proposal. The individuals may be Progress Energy employees or consultants.

Seasonal Contract Capacity (SCC): The Summer Contract Capacity and the Winter Contract Capacity, as applicable, with the summer and winter seasons as defined in Section II.F of the Response Package. For New and Existing Unit Proposals, the capacities are the values specified by the Bidder in Schedule 4 of the Response Package in the table labeled “Dispatchable Generation Capacity,” in the row labeled “Seasonal Contract Capacity.” For System Proposals, the capacities are the values specified by the Bidder in Schedule 2 Sheet A of the Response Package.

Summer Contract Capacity:  The maximum capacity (MW) the Facility can sustain during the Summer period, less the capacity utilized for station service or auxiliaries, and adjusted for losses to the delivery point to the PEF control area.

System Power Proposal:  A bid to provide capacity and energy from a Power System.

Strike Date:  The date on or before which PEF may exercise a specific option.

Threshold Requirements:  The minimum requirements that all proposals are required to meet and with which a Bidder’s compliance will be assessed in Step 1 of the evaluation process (see Section IV.A).

Voltage Control:  The ability to modify generator terminal voltage by varying the current in the generator’s field winding either automatically by appropriate control mechanisms or manually by the operator.

Winter Contract Capacity:  The maximum capacity (MW) the Facility can sustain during the Winter period, less the capacity utilized for station service or auxiliaries, and adjusted for losses to the delivery point to the PEF control area.

- III.	INSTRUCTIONS TO BIDDERS

- A.	General Instructions

Bidders are required to meet all the terms and conditions of the RFP to be eligible to compete in the solicitation process. Bidders are required to follow all instructions contained in the RFP. Bidders must respond to all questions contained in the Response Package, use the provided Microsoft Excel schedules, organize their proposals according to the structure specified in the Response Package (i.e., organized by chapter and section in the order specified by PEF), and provide supporting documentation in the format requested. Bidders should include the Project Name, chapter and section numbers, and page number on each attachment. If a question is not applicable to the type of proposal submitted, Bidders should so indicate and specify why the requested information is not applicable. It is the Bidder’s responsibility to advise PEF’s Official Contact of any conflicting requirements, omissions of information, or the need for clarification before bids are due. Bidders should clearly organize and identify all information submitted in their proposals to facilitate review and evaluation. Failure to provide all the information requested in this solicitation process or failure to demonstrate that the proposal satisfies all of the Threshold Requirements and Minimum Evaluation Requirements identified in Section IV will be grounds for disqualification.

The Bidders should mark all confidential and proprietary information contained in its proposals as “Confidential.” While PEF will use its best efforts to protect the confidentiality of such information and only release such information to the members of the RFP Project Team, management, agents and contractors, and, as necessary and consistent with applicable laws and regulations, to its affiliates and regulatory commissions, in no event shall PEF be liable to a Bidder for any damages of whatsoever kind resulting from PEF’s failure to protect the confidentiality of Bidder’s information. By submitting a proposal, the Bidder agrees to allow PEF to use all information provided and the results of the evaluation as evidence in any proceeding before the Florida Public Service Commission (FPSC). To the extent PEF wishes to use information that a Bidder considers confidential, PEF will petition the Commission to treat such information as confidential and to limit its dissemination, but PEF makes no assurance of the outcome of any such petition.

All correspondence between the Bidder and PEF must be through the Official Contact. All questions must be submitted in writing. PEF will attempt to respond within a reasonable length of time to Bidders’ requests. PEF will maintain complete documentation of all questions received from Bidders and its responses, and provide written responses via the RFP web site to all Bidders when deemed necessary to ensure an equitable level of competition.

- B.	Submission of Proposals

All proposals must be received by PEF by 1:00 PM EST on December 16, 2003. Proposals must be submitted to the PEF Official Contact. Proposals should be submitted in a sealed package and be marked with the Bidder’s name and a label indicating that the package contains a proposal in response to Progress Energy Florida’s 2007 RFP for Power Supply Resources. The package should also note the confidentiality status of information contained in the document. For each proposal, Bidders must submit three (3) bound copies and one (1) electronic version (on diskette or CD-ROM) with all text portions of the responses in Microsoft Word or Adobe Acrobat and schedules in Microsoft Excel. Each proposal is to be bound separately. Bidders must submit two (2) extra unbound copies of any document that is larger than 8 ½” x 11”. Bidders must ensure that the proposals are delivered on time. Delivery by services which cannot guarantee delivery by the time required are discouraged. Failure to submit a proposal by the deadline will be grounds for disqualification.

Bidders should carefully read all sections of this RFP Solicitation Document and the Response Package. The Response Package contains directions regarding the type and form of information Bidders are required to provide.

- C.	Proposal Fees/ Proposal Variations

Bidders may submit as many proposals as they desire. To help defray the cost of performing the proposal evaluations, Bidders are required to submit with each proposal a non-refundable proposal submittal fee of $10,000. The fee should be in the form of a check payable to “Progress Energy Florida.”

A proposal is defined according to the site, technology, fuel, and infrastructure identified by the Bidder. Thus, a proposal which contains a different site, technology, fuel (excluding secondary fuel), or infrastructure will be classified as a separate proposal and requires a separate proposal submittal fee. Bidders are allowed to propose up to a total of two variations in project term and/or pricing at no additional cost. Variations in excess of two must be accompanied by a $1,000 per variation fee to be considered for evaluation. Bidders must submit a complete electronic version of the Response Package for each variation. (The hard copy version of the primary Bid should contain a section discussing any variations and identifying the name(s) of the file(s) in which they are contained.)

- D.	Proposal Size, In-Service Date, and Term

As discussed above, PEF is seeking proposals for power supply resources to be in-service by December 1, 2007. However, PEF will accept proposals with start dates as early as December 1, 2006. Since the Company’s “next planned generating unit” is approximately 500 MW in size, the maximum size of the proposals should be approximately 500 MW. The earliest contract end date for the delivery of capacity and energy to PEF is December 31, 2008 for proposals supported by assets that do not require a need determination. The earliest contract end date for proposals requiring a need determination is December 31, 2017. The latest contract end date is December 31, 2032.

Progress Energy Florida will accept proposals that supply one amount of capacity beginning on December 1, 2007 and then increment to a greater amount of capacity beginning on December 1, 2008. The total amount of capacity must be less than approximately 500 MW and must be supplied from the same site, technology, fuel (excluding secondary fuel), and infrastructure.

- E.	Contract Flexibility Provisions

Bidders are encouraged to offer flexibility provisions. Possible provisions include, but are not limited to, fuel tolling arrangements, contract term extension options in which bidders propose an initial contract term and provide PEF the option to extend the contract at predefined prices, options to terminate or buy out the contract, or options to shorten or terminate the contract in the event of any amendments to the Florida Power Plant Siting Act or the deregulation of the electric utility industry in Florida.

- F.	Security Requirements

The Key Terms and Conditions contain security provisions which require the Bidder to provide financial security to ensure the project is completed on schedule (development security) and is operated effectively and reliably (operational security). Bidders will be required to post security consistent with the schedule provided in the Key Terms and Conditions (see Attachment A).

Security in the form of cash or U.S. government bonds held in escrow is preferred. However, PEF will accept other forms of security that may be less costly to the Bidder, including a letter of credit with a bank or financial institution. Security must be guaranteed by entities that are considered investment grade.

- G.	Permitting Responsibility

The Bidder(s) whose proposal is (are) selected will be responsible for acquiring all necessary licenses, permits, certifications, and approvals required by federal, state and local government laws, regulations and policies for the design, construction, and operation of the project. In addition, the Bidder shall fully support all of PEF’s regulatory requirements associated with this potential power supply arrangement. The Bidder is also completely and solely responsible for securing financing for its project. PEF shall have no responsibility in identifying or securing any licenses, permits, or regulatory approvals (other than being a co-applicant in a Determination of Need filing and a co-applicant in the Certificate of Need proceeding under the Florida Electric Power Plant Siting Act) or in securing any financing required for the construction or operation of the project.

- H.	Regulatory Provisions

Any negotiated contract for the purchase of power between PEF and the Bidder will be conditioned upon approval or acceptance without substantial change by any and all regulatory authorities that have, or claim to have, jurisdiction over any or all of the subject matter of this solicitation, including, without limitation, the Florida Public Service Commission and the Federal Energy Regulatory Commission. The negotiated contract will be further conditioned upon favorable regulatory action without substantial condition or qualification (including but not limited to temporal or other conditions or limitations on cost recovery) by any and all regulatory authorities from which regulatory approval may be required for the contract or for the development or effectuation of the power supply project and related activities (including but not limited to a Determination of Need by the Florida Public Service Commission).

In accordance with Rule 25-22.082 of the Florida Administrative Code, each participant [Bidder] is required

… to publish a notice in a newspaper of general circulation in each county in which the participant proposes to build an electrical power plant. The notice shall be at least one-quarter of a page and shall be published no later than 10 days after the date that the proposals are due. The notice shall state that the participant has submitted a proposal to build an electric power plant, and shall include the name and address of the participant submitting the proposal, the name and address of the public utility that solicited proposals, and a general description of each proposed power plant and its location.

Bidders are required to forward copies of these actual published notices to the Official Contact within seven (7) days of the notice appearing in the paper. The copy of this notice shall clearly indicate the name of the newspaper and the date on which the notice was published.

- I.	Reservation of Rights

Progress Energy Florida reserves the right to reject any, all, or portions of the proposals received for failure to meet any criteria set forth in this RFP. The Company also reserves the right in its sole discretion to decline to enter into a power purchase arrangement with any Bidder, or to abandon the project in its entirety. PEF reserves the right to revise the capacity needs forecast at any point during the RFP process or during negotiations; any such change may reduce, eliminate, or increase the amount of power sought.

Respondents should be aware that the following, without limitation, will be classified as non-responsive and may not be considered or evaluated if submitted:

- proposals offering non-firm capacity or energy;

- demand-side proposals;

- incomplete, inaccurate, conditional, deceptive, misleading, ambiguous, exaggerated, or non-specific offers; or

- proposals that are not in conformance with the requirements and instructions contained herein.

Those who submit proposals do so without recourse against PEF or Progress Energy Corporation or any of Progress Energy Corporation’s subsidiary companies for either rejection of their proposal(s) or for failure to execute a power purchase agreement for any reason.

- IV.	SOLICITATION PROCESS

- A.	Description of the Process

The solicitation process is a multi-phase process consisting of four general phases, as noted in Section I.D, and several sub-phases, or steps. This section of the RFP will describe the process in detail and outline Bidder requirements and alternatives at each phase and step of the process.

This section of the RFP is organized chronologically according to the solicitation process to be conducted by PEF. Specifically, the areas to be discussed are the (1) pre-bid submission activities, (2) evaluation process, (3) contract negotiations, and (4) regulatory filings. Discussed as part of the evaluation process are the minimum requirements that all proposals must meet as well as the evaluation criteria that will be used to identify the most attractive proposals.

- B.	Pre-Bid Submission Activities

The pre-bid submission activities phase of the process includes the period from issuance of the RFP to submission of bids.

- 1.	Notice of Intent to Bid

The first major activity for Bidders is submission of the Notice of Intent to Bid Form. Bidders are encouraged to submit the Notice of Intent to Bid Form by October 14, 2003. Submitting a Notice of Intent to Bid does not commit a prospective Bidder to submitting a proposal to PEF. Submission of this form ensures that the Bidder will receive all information pertaining to the RFP. While Bidders who do not submit a Notice of Intent to Bid Form will be eligible to submit a proposal, PEF cannot guarantee that these Bidders will receive all information about the solicitation process. Progress Energy Florida will accept Notices of Intent to Bid from Bidders after the October 14, 2003 due date and will provide any such Bidders with all materials provided to Bidders after the issuance of the RFP. The Notice of Intent to Bid Form is the only worksheet in the Microsoft Excel file named “Bid Notice.” A completed form should be e-mailed to the Official Contact. If desired, Bidders may submit a printed version of the form using other delivery methods such as fax, U.S. Mail, or overnight delivery.

- 2.	Bidders Conference

Progress Energy Florida will conduct a bidders conference for interested Bidders on October 21, 2003 at 1:00 PM at the Tampa Airport Marriott. If this time or location changes, PEF will notify Bidders who have submitted a Notice of Intent to Bid Form. The purpose of the bidders conference is to allow interested Bidders the opportunity to ask questions and seek additional information or clarification about the solicitation process. To make the meeting as productive and informative as possible, Bidders are encouraged to submit a written list of questions to the Official Contact prior to October 17, 2003. Each Bidder should identify on the Notice of Intent to Bid Form if one or more representatives of its company plan to attend the bidders conference.

- 3.	Progress Energy Florida Approval of Alternative Indices

While PEF prefers that Bidders use the cost escalation indices identified in Section III of the Response Package when completing the pricing schedules, Bidders are provided the opportunity to identify alternative indices to be used for evaluation and billing purposes if the Bidder prefers indices different from those proposed by PEF. To receive approval from PEF for a different index, the Bidder must demonstrate that the proposed index is more reflective of the underlying project cost element, accurately reflects the market which it would represent, is readily available from public sources, and is available in a timely manner. Bidders must be willing to submit all materials on which they rely to show the soundness of the proposed alternative index. To request to use a new index, Bidders should contact PEF’s Official Contact in writing no later than November 15, 2003. Progress Energy Florida reserves the right to update its forecasts for these indices during the evaluation period if they are no longer reflective of PEF’s current expectations of the future escalation rates of these indices.

- 4.	Submission of Bids

The last step during this phase of the process is the submission of bids. As noted, all proposals must be received by 1:00 PM EST on December 16, 2003. Proposals must remain valid until PEF either accepts the proposal or negotiates different terms during the Contract Negotiation phase. Failure to submit the proposal by the specified time will be grounds for disqualification.

- C.	Evaluation Process

PEF will use a seven-step evaluation process to review proposals and to select the best alternative. Figure IV-1 illustrates the evaluation process from the receipt of proposals to contract negotiations. The evaluation process that will be employed by PEF is reviewed below.

- 1.	Step 1:  Screening for Threshold Requirements

Subsequent to the receipt of the bids, the Company will thoroughly review and assess each proposal to ensure that it meets the Threshold Requirements listed in the RFP. Threshold Requirements represent the minimum requirements that all proposals are required to meet and with which a Bidder’s compliance can be easily assessed. PEF may, at its discretion, seek clarification and/or remedy of a Bidder’s proposal at this stage of the evaluation process. Each Bidder should maintain a contact person available to PEF throughout the Evaluation Process.

Progress Energy Florida views Threshold Requirements to be an important aspect of the evaluation process. The Bidder should ensure that its proposal satisfies the Threshold Requirements listed in Table IV-1 to be eligible for further consideration. Bidders should also review the Key Terms and Conditions set forth in Attachment A, because they are the terms and conditions that will be used to ensure the Bidder’s conformance with certain Threshold Requirements. The information Bidders are required to provide to demonstrate their compliance with the Threshold Requirements is specified in greater detail in the Response Package.

Figure IV-1

- Evaluation Process

Receipt of Proposals

Step 1

Screening for Threshold Requirements

Step 2

Segregation of Bids

Step 3

Economic Evaluation

Contract Negotiations

Step 6

Detailed Evaluation

Step 7

Selection of Final List

Step 5

Selection of Short List

Step 4

Technical Evaluation

(Minimum Evaluation Requirements and Technical Criteria)

Table IV-1

Threshold Requirements

A.	General Requirements

- The proposal is received on time.

- The offer is reasonable and bona fide.

- Complete and credible answers are provided to all questions.

- The proposal submittal fee is included.

- The pricing schedules are properly specified.

- The proper price indices are used.

- Power must be available for delivery under the contract by December 1, 2007.

- The proposed term is for a minimum of one (1) year if the project does not require a Need Determination and 10 years if a Need Determination is required. The proposed term is less than the maximum of 25 years.

- For New Unit Proposals located in Florida, the output of the unit(s) is sufficiently committed to Progress Energy Florida (or other utilities serving retail customers).

B.	Operating Performance Thresholds

- If the project is located in PEF’s control area, the Bidder will be required:

- to operate the project to conform with PEF’s Voltage Control requirements.

- to operate the project to conform with PEF’s Frequency Control requirements.

- New and Existing Unit Proposals must be Fully Dispatchable and install Automatic Generator Control that is tied into PEF’s Energy Control Center.

- The Bidder must be willing to coordinate the project’s maintenance scheduling with PEF.

- Proposals should have a project size less than or equal to approximately 500 MW.

- System Power Proposals must be Fully Schedulable (i.e., operate according to a day-ahead schedule but with schedule changes subject to normal utility practices).

C.	Contractual Thresholds

- Bidders must agree to each of the Key Terms and Conditions identified in Attachment A.

- OR -

- If Bidder has any objections to the Key Terms and Conditions, the Bidder must:

- Identify the language which is objectionable;

- Provide revised language.

D.	Site Control Thresholds [New and Existing Unit Proposals]

- Identification of the site location on a USGS map.

- At a minimum, a Letter of Intent to negotiate a lease for the full contract term or term necessary for financing (whichever is greater), or to purchase the site [New Unit Proposals]. A copy of the title and legal description of the property is required for Existing Unit Proposals.

E.	Transmission Threshold

- If the project is located outside of PEF’s control area, the Bidder must provide a transmission plan for wheeling services from those utilities which would be required to wheel the project’s power to PEF and provide evidence that the host utility is willing to grant PEF the right to dispatch the output of New and Existing Unit Proposals or the right to schedule power from System Power Proposals.

- If the project is located inside of PEF’s control area, the Bidder must complete a Network Resource System Impact Study data request (Schedule 7 of the Response Package).

Bidders must ensure that their proposals contain sufficient documentation to demonstrate that they meet all Threshold Requirements. Failure to conform to the Threshold Requirements will be grounds for disqualification. Proposals that are disqualified will not be evaluated further.

- 2.	Step 2:  Segregation of Bids

After the completion of the initial screening, PEF may, at its discretion, classify proposals into various categories distinguished by type of bid (New Unit, Existing Unit, or System Power Proposal), and term (number of years for which power is offered).  Depending on the proposals received, other categories may be developed to further segregate the bids (e.g., combustion turbine vs. combined cycle proposals). The purpose of this process is to categorize “like type” proposals to ensure a consistent and fair evaluation and to allow PEF to identify the best proposals in each category.

- 3.	Step 3:  Economic Evaluation

The next phase of the evaluation process is the economic evaluation of proposals. Each proposal that satisfies the Threshold Requirements evaluation performed in Step 1 will be subjected to economic screening analyses. This initial economic evaluation will be used to further screen proposals and identify those proposals that will be subjected to a technical evaluation in Step 4.

In the economic evaluation, PEF will evaluate each bid based on its price proposal. Progress Energy Florida plans to use a combination of spreadsheets and the Strategist optimization model to compare the costs of the bids to each other and to assess the impacts of each bid on system costs over PEF’s planning horizon. In any spreadsheet analyses performed, the total costs of each proposal will be compared to the other proposals at an appropriate capacity factor (e.g., 10% for combustion turbines, 50% for combined cycles, 80% for coal units). In the optimization analyses, PEF will develop an optimal resource plan around each proposal to determine the cumulative present value of revenue requirements (CPVRR) of the plan. Generic combustion turbine, combined cycle, and coal plants will be available technologies from which the optimization model can select. Depending on the proposals received, PEF will also examine combinations of proposals in the development of optimal resource plans. Progress Energy Florida reserves the right to eliminate proposals with high costs (relative to other proposals) from further consideration.

Progress Energy Florida’s pricing parameters for New and Existing Unit Proposals are identified and described in Table IV-2 and are specified in greater detail in the Response Package. The requirements for pricing bids for System Power Proposals are specified in the Response Package.

| Table IV-2 New and Existing Unit Proposal Pricing Parameters |  |  |
| --- | --- | --- |
| Fixed Payment |  | - The monthly fixed payment to Bidders will be based on the product of the Seasonal Contract Capacity, one-twelfth (1/12) of the Bidder-specified annual charges, and adjustments based on operating performance (see Key Terms and Conditions). - If Bidders desire, they may propose alternative methods of distributing annual payments on a monthly basis. - Bidders must complete the applicable Pricing Schedules in the Response Package. |
|  | Generation Capital | - Bidders must specify a generation capital charge for each year of the proposal. |
|  | Transmission | - Bidders must specify a transmission charge for each year of the proposal. - This charge must include all interconnection and, if applicable, wheeling costs. System upgrade costs will be estimated by PEF during the Detailed Evaluation of proposals (Step 6). |
|  | Fixed O&M | - Bidders must specify annual fixed O&M charges for each year of the proposal. |
|  | Fixed Pipeline Demand / Reservation | - Bidders must specify a fixed pipeline demand/reservation charge (if appropriate to the technology being proposed). Bidders must specify a charge for each year of the proposal. - Bidders may propose a fuel transportation tariff as the price. - PEF reserves the right to negotiate fuel transportation provisions with the Bidder if benefits can be derived for PEF and its customers. |
| Variable Payment |  |  |
|  | Fuel Price | - Bidders must specify the commodity price and a variable transportation price as an initial price and indicate the proposed index or fixed escalation rate that will be used to escalate those prices. Bidder’s may specify variable transportation as a function of the commodity price rather than an initial price and escalation index. The formula must be specified in Bidder’s Exhibit 2.1 - Progress Energy Florida will not allow Bidders to merely state that fuel is a passthrough. Progress Energy Florida may allow a passthrough as a result of the negotiation process and, as a condition for this, would reserve the right to participate in the management of the project’s fuel supply, but reserves the right to accept the base price and index or fixed escalation rate specified by the Bidder. - Bidders must specify the months in which the primary and secondary fuels will be expected to be used and be prepared to be evaluated and paid on that basis. |
|  | Variable O&M | - Bidders should specify in Schedule 1annual variable O&M prices for each year of the proposal. Variable O&M may be stated in $/MWh, $/hour, or both. |
| Start Payment |  | - Bidders should specify annual start prices for each year of the proposal. Start payments will be paid only for those starts required by PEF. The cost to start the facility for test starts, following a forced outage, or after unplanned maintenance will not be included in PEF’s payments to the Bidder. |

- 4. 	Step 4:  Technical Evaluation

In Step 4 of the evaluation process, the proposals that remain in the process after the economic screening performed in Step 3 will be evaluated on a technical basis to assess the feasibility and viability of each bid. As part of this technical evaluation, proposals will be reviewed to ensure that they conform to the Minimum Evaluation Requirements (Table IV-3) and will also be evaluated on the basis of the Technical Criteria (Table IV-4) described below.

- a.	Minimum Evaluation Requirements

Progress Energy Florida will apply Minimum Evaluation Requirements as a step in the technical evaluation process. These Minimum Evaluation Requirements, identified in Table IV-3, are the technical “must have” elements of a proposal. The information Bidders are required to provide to demonstrate their compliance with these Minimum Evaluation Requirements is specified in greater detail in the Response Package. Each Minimum Evaluation Requirement will be evaluated on a “Pass/Fail” or “Go/No Go” basis. Bidders must ensure that their proposals contain sufficient documentation to demonstrate that they meet all the Minimum Evaluation Requirements. Failure to demonstrate conformance to these Minimum Evaluation Requirements will be grounds for disqualification.

Table IV-3

Minimum Evaluation Requirements

A. 	Environmental

- Preliminary environmental analysis performed and submitted to PEF [New Unit Proposals].

- Reasonable schedule for securing permits presented and evidence provided that permits are likely to be secured [New Unit Proposals].

B. 	Engineering and Design

- The project technology will be able to achieve the operating targets specified by the Bidder [New Unit and Existing Unit Proposals].

- Operation and Maintenance Plan provided which indicates that the project will be operated and maintained in a manner adequate to allow the project to satisfy its contractual commitments [New Unit and Existing Unit Proposals].

C. 	Fuel Supply and Transportation Plan

- Preliminary fuel supply plan provided which describes the Bidder’s plan for securing fuel supply and transportation for delivery to the project. The plan shall provide a description of the fuel delivery system to the site, the terms and conditions of any existing or proposed fuel supply and transportation arrangements, and the status of such arrangements [New Unit and Existing Unit Proposals].

D. 	Project Financial Viability

- For New Unit Proposals, evidence provided that demonstrates the project is financially viable [New Unit Proposals].

- Demonstration that the Bidder has sufficient credit standing and financial resources to satisfy its contractual commitments [All Proposals].

E. 	Project Management Plan

- For a New Unit Proposal, critical path diagram and schedule for the project provided which specify the items on the critical path and demonstrate the project would achieve commercial operation by December 1, 2007 [New Unit Proposals].

- b.	Technical Criteria

Technical Criteria are characteristics (non-price attributes) PEF desires that will make the proposals more attractive to the Company. Progress Energy Florida will use three major attributes to evaluate proposals’ Technical Criteria: (1) operational quality; (2) development feasibility; and (3) project value. Each of the evaluation criteria that are contained within these evaluation attributes are identified in Table IV-4 and discussed below. Proposals will be ranked relative to each other for each of the Technical Criteria. Inability of a Bidder to substantiate the basis for any representation will be grounds for a downward revision of its proposal’s ranking or, in the event of misrepresentation, disqualification from this bidding process.

Table IV-4

Technical Criteria

| Operational Quality | Development Feasibility | Project Value |
| --- | --- | --- |
| - Minimum Load (N, E) | - Permitting Certainty (N) | - Acceptance of Key Terms and Conditions (N,E,S) |
| - Start Time (N, E) | - Financial Viability (N,E,S) | - Fuel Supply and Transportation Reliability (N,E) |
| - Ramp Rate (N, E) | - Commercial Operation Date Certainty (N) | - Reliability Impact (N,E,S) |
| - Maximum Starts/Year (N, E) | - Bidder Experience (N,E,S) | - Flexibility Provisions (N,E,S) |
| - Minimum Run-Time Constraint (N, E) |  |  |
| - Minimum Down-Time Constraint (N, E) |  |  |
| - Annual Operating Hour Limit (N, E) |  |  |

N = New Unit Proposals, E = Existing Unit Proposals, S = System Power Proposals

- Operational Quality

There are seven evaluation criteria that are considered as part of the operational quality attribute: (1) minimum load; (2) start time; (3) ramp rate; (4) maximum starts per year; (5) minimum run-time constraint; (6) minimum down-time constraint, and (7) annual operating hour limit. For New and Existing Unit Proposals, PEF will require that tests be conducted to ensure that the Bidder’s project conforms to the start time and ramp rate operating parameters claimed in its proposal. Failure to conform to these operating parameters will subject Bidders to performance penalties under any power purchase agreement.

The minimum load is the lowest capacity level at which the project may be operated. Progress Energy Florida prefers projects that show flexibility by allowing operation at less than full load. Start time assesses the amount of notice required to bring the unit, under normal operations, from a cold start to minimum synchronized load. Progress Energy Florida prefers proposals that have short start times. Ramp rate assesses the megawatt (MW) increase per minute that can be provided by the project once the unit is at or above the minimum loading level. Progress Energy Florida prefers proposals that offer a high ramp rate. Maximum starts per year assesses the maximum number of times that PEF will be allowed to start the Bidder’s project. Test starts, starts after a forced outage, and starts after unplanned maintenance will not be included when determining the number of starts requested by PEF. Progress Energy Florida prefers proposals in which there is no limit on the number of times that PEF can start a project. Minimum run-time constraint assesses the number of hours that the project is required to be operated at or above its minimum operating level once it has been dispatched on line. Progress Energy Florida prefers proposals that have no minimum run-time constraints. The minimum down-time constraint assess the number of hours that the project is required to remain out of service once it has been taken off-line for economic dispatch, maintenance outage, or forced outage. Progress Energy Florida prefers proposals that have no minimum down time constraints. The annual operating hour limit assesses the number of hours during a year that PEF would be allowed to operate the Facility. Progress Energy Florida prefers proposals that have no operating hour limits.

- Development Feasibility

There are four evaluation criteria that are considered as part of the development feasibility attribute: (1) permitting certainty; (2) financial viability; (3) commercial operation date certainty; and (4) Bidder experience. All four of the evaluation criteria that represent this evaluation attribute will be considered for New Unit Proposals. Existing Unit and System Power Proposals will be evaluated in terms of the Bidder’s financial viability and Bidder experience.

The permitting certainty evaluation criterion assesses the degree to which the Bidder is able to demonstrate that it will be able to identify and secure all of the required major permits, approvals, certificates, and licenses within the period indicated on the project’s critical path schedule. Proposals that provide well-conceived plans for securing all required permits, approvals, etc., demonstrate a thorough understanding of the permitting process, and have realistic permitting and approval schedules will receive a higher ranking than those which do not. Finally, Bidders who have made greater progress in securing permits and approvals are preferred.

The financial viability evaluation criterion assesses the financial viability of the Bidder’s proposal and the financial capability and credit of the Bidder. If the Bidder is proposing to obtain project financing for its proposal, the evaluation will focus on the financial viability of the proposal through the evaluation of project pro-forma financials based on the assumptions and capital structure in the proposal. To show financial viability, the Bidder needs to demonstrate that the project is, or becomes, free cash flow positive (not every year must show positive free cash flows but, in general, the project should be positive more than it is negative). There is no specific cash flow hurdle. If the Bidder indicates that it will be providing equity to the project or will self-finance the project, PEF will also assess the Bidder’s ability to provide the required equity or financing through the credit review. For New Unit Proposals, PEF prefers proposals for which the Bidder is able to demonstrate that there is a high likelihood of the project securing financing. For System Power and Existing Unit Proposals, PEF’s evaluation will focus on the financial resources of the Bidder. For all types of proposals, PEF will also evaluate the Bidder’s ability to financially guarantee its contractual commitments. For the demonstration of creditworthiness, credit reviews will be performed based on bond ratings from two nationally recognized bond rating agencies and PEF’s internal credit scoring model. In-house analysis is performed to determine a credit score and subsequent Progress equivalent rating on companies with the following characteristics:

- Not rated by S&P or Moody’s or

- S&P or Moody’s rated with no outstanding unsecured debt

Utilizing financial statements - the in-house analysis process, depicted below, utilizes nine leading indicators and corresponding weightings to determine a company’s aggregate credit score.

|  |  | - Credit Score |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Measure | Weighting | 0 | 1 | 2 | 3 | 4 | 5 |
| - Debt/Capital | .15 | >75% | 70-75% | 65-70% | 60-65% | 55-60% | <55% |
| Current Ratio | .10 | <.60 | .60-.69 | .70-.79 | .80-.89 | .90-.99 | >1.0 |
| EBITDA/Interest Expense | .15 | <1.25 | 1.25-1.99 | 2.00-2.49 | 2.50-2.99 | 3.00-3.99 | >4.00 |
| Fixed Assets/Total Assets | .10 | <10% | 10.00-19.99% | 20.00-29.99% | 30.00-39.99% | 40.00-49.99% | >50% |
| Fixed Assets/Equity | .10 | <1 | 1.00-1.49 | 1.50-1.99 | 2.00-2.49 | 2.50-2.99 | >3 |
| Net Worth | .20 | <$10MM | $11-49MM | $50-199MM | $200-499MM | $500-999MM | >$1B |
| Financial Statements | .05 | Qualified or Outdated | Unaudited | Compiled | Statutory Filing | Unqualified (not Big 4) | Unqualified (Big 4) |
| 3 Year Income Trend | .10 | Downward | - | - | Mixed | - | Upward |
| Years in Business | .05 | <2 | 2-3 | 3-4 | 5-6 | 7-8 | >8 |

Each measure’s score is calculated according to the formula provided below:

(Credit Score / Total Available Points) * Weighting * 100

Aggregate credit scores are calculated according to the formula provided below.  The maximum points available are 100.

(Credit Score / Total Available Points) * Weighting * 100

Company rating and credit score results are converted into Progress equivalent ratings according to the table listed below.

| Rated Companies |  | Unrated Companies |  |
| --- | --- | --- | --- |
| Lesser of |  |  | Progress |
| S&P Rating | Moody’s Rating | Credit Score | Equivalent |
| AAA to AA- | Aaa to Aa3 | 100 - 91 | PGN 1 |
| A+ to A- | A1 to A3 | 90 - 81 | PGN 2 |
| BBB+ to BBB | Baa1 to Baa2 | 80 - 71 | PGN 3 |
| BBB- | Baa3 | 70 - 61 | PGN 4 |
| BB+ to BB- | Ba1 to Ba3 | 60 - 51 | PGN 5 |
| B+ to B- | B1 to B3 | 50 - 41 | PGN 6 |

If a company is rated by both S&P and Moody’s, the lesser of the two ratings is used to determine a Progress equivalent rating.

Commercial operation date certainty assesses the degree to which the Bidder is able to demonstrate that it will be able to bring the project to commercial operation by December 1, 2007. For New Unit Proposals, PEF will evaluate the reasonableness of the following aspects of the Bidder’s proposed schedule: permitting and approvals, fuel supply and transportation arrangements, engineering design, project financing, equipment procurement, project construction, and start-up and testing. PEF’s evaluation will consider the evidence presented by the Bidder that the proposed schedule for each of these project elements is achievable. PEF prefers proposals for which the Bidder is able to demonstrate that there is little or no risk that the project will not be able to achieve the commercial operation date requirement. For Existing Unit and System Power Proposals, PEF will evaluate the Bidder’s ability to demonstrate that it will be able to provide the power being offered to PEF.

Bidder experience assesses the relative experience of the Bidder in developing and operating projects that are of an equivalent size and technology as that being proposed in response to this RFP. For a New Unit Proposal, PEF will evaluate the Bidder’s relevant experience in six areas: permitting and approvals, engineering, financing, fuel procurement, project construction, and operations and maintenance, including environmental compliance. Progress Energy Florida prefers Bidders that have a history of successfully developing comparable projects. For proposals that rely on project teams composed of more than one firm to develop the projects, PEF prefers project teams that have a history of working together to successfully complete projects. For a Bidder that proposes to supply PEF’s capacity requirements from existing capacity, PEF will only evaluate the Bidder’s fuel procurement and operations and maintenance experience. PEF will also examine the litigation history of all Bidders.

- Project Value

The project value attribute considers the following four evaluation criteria: (1) the Bidder’s acceptance of the Key Terms and Conditions; (2) the reliability of the Bidder’s fuel supply and transportation plan; (3) impact on generation system reliability; and (4) any flexibility provisions proposed by the Bidder.

Progress Energy Florida will evaluate Bidder’s acceptance of the Key Terms and Conditions by assessing the degree to which exceptions identified by the Bidder shift risk from the Bidder to PEF or its customers. Progress Energy Florida prefers Bidders which request no changes to the terms and conditions or which request only minor changes that have no material effect on the allocation of risk within any contract ultimately executed.

Progress Energy Florida will evaluate the reliability of the Bidder’s fuel supply and transportation plans by assessing the status of its fuel supply and transportation arrangements, the strength of the proposed fuel supplier, and the relative risk of the Bidder’s proposed fuel supply and transportation arrangements. Progress Energy Florida prefers proposals that have well developed fuel supply and transportation arrangements, rely on a major fuel supplier that offers a diverse mix of potential fuel supplies and access to a number of different transportation alternatives, and have minimal fuel supply and transportation risks.

Progress Energy Florida will evaluate the impact on generation system reliability of the project proposed by Bidders, primarily through an examination of outage rate information provided by the Bidder. Depending on the proposals received, additional analyses may be required.

Progress Energy Florida reserves the right to consider any unique flexibility provisions offered by a Bidder that are not considered elsewhere, such as the economic evaluation. Progress Energy Florida favors bids which provide flexibility for meeting its projected requirements.

- 5.	Step 5:  Selection of Short List

Progress Energy Florida’s objective is to select a short list which includes a mix of proposal types. Those bids which are inferior to other proposals, based on cost and technical merits, will be eliminated from further consideration. Progress Energy Florida anticipates selecting more than one proposal for the short list in order to create more opportunities for comparison. Progress Energy Florida will notify all short-listed Bidders that they have been included on the short list.

- 6.	Step 6:  Detailed Evaluation

Proposals that are included on the short list will be subjected to a more detailed assessment and will be compared to PEF’s self-build alternative. In the detailed evaluation phase, PEF will incorporate the transmission cost impacts based on system impact studies. These studies include load flow, stability, and short circuit analyses and are necessary to determine the impacts on the transmission system of building the proposed power plants at the proposed sites. In the analyses to be performed by PEF, each proposed plant will be placed into the transmission system (Hines 4 will not be part of the system configuration) and the performance of the system with and without the proposed plant will be compared. If overload situations are encountered in the simulations, determinations will be made as to what corrective actions would be required to integrate the proposed plant into the PEF transmission system. The cost of these corrective actions will be included in the economic analysis of each proposal.

Progress Energy Florida plans to use spreadsheet and the Prosym production costing models to compare the short-listed proposals to PEF’s self-build alternative. Using the optimal plans for the short-listed proposals developed in the economic analysis performed in Step 3, the detailed evaluation will assess the impact of each alternative on the CPVRR over the planning horizon compared to a Base Case plan. In order to treat all alternatives the same in the economic analysis, all cases will be compared to a Base Case optimal plan, which will consist of existing, committed, and generic future units. The results of the Prosym production costing analyses will be incorporated into the detailed financial analysis of each alternative. In addition to the direct costs associated with each alternative (that is, the energy charges of the proposals and the operating costs of the self-build alternative), the change in system production costs as a result of the alternative, relative to the Base Case, will also be a part of the financial analysis. The fixed costs associated with each alternative (the fixed charges of the proposals and the construction costs and fixed O&M of the self-build alternative) will be included in the analysis. The cost impacts of the changes in the resource plan will be reflected in the financial analysis by way of an economic carrying charge, which is the same concept as the Value of Deferral. Each alternative will receive a credit for fixed cost savings equal to the economic carrying charge of a generic combined cycle unit (the unit in the Base Case being deferred) through the term of the proposal being considered.

Progress Energy Florida will apply the cost of imputed debt to Bidder’s proposals to assure that the total costs of proposals include the marginal impact of the fixed future commitment on PEF’s capital structure. The annual additional equity cost of imputed debt on a revenue requirements basis is calculated as:

Annual Additional Equity Cost =

Risk Factor * Present Value of Future Fixed Payments

* (Cost of Equity Rate – After Tax Cost of Debt Rate)

* Equity Ratio / (1 – Tax Rate)

where the Risk Factor and Present Value of Future Fixed Payments are calculated using S&P Standard Methodology (discount rate equals 10 percent and the risk factor equals 30 percent).

This additional cost is the direct result of incurring fixed future payment obligations. Rating agencies make these adjustments to a utility’s balance sheet to reflect the existence of debt-like commitments. The Risk Factor is the percentage of the future fixed payments to be added to balance sheet debt and depends on a number of factors, including the conditions of a purchased power proposal, regulatory cost recovery risk, if the power proposal is economic compared to other alternatives. The biggest factor in selecting a risk factor is the likelihood of payment by the utility. According to Standard & Poors, “For utilities in supportive regulatory jurisdictions with a precedent for timely and full cost recovery of fuel and purchased-power costs, a risk factor as low as 30% could be used.”

Consistent with Florida PSC rules, PEF encourages participants to formulate creative responses to the RFP. Without knowing the details of the proposals that may be submitted, PEF is not able to identify or describe all the analyses that may be needed to determine which alternative is the most cost-effective alternative. Based on the Company’s review of the proposals submitted, the Company may deem it appropriate to perform scenario analyses (e.g., to examine flexibility options proposed by a bidder) and conduct sensitivity analyses of key cost and performance characteristics (such as, but not limited to, heat rate, outage rate, construction cost, O&M costs, and energy costs).

Progress Energy Florida may elect to schedule meetings or conference calls with each short-listed Bidder to review and clarify its proposal. Progress Energy Florida reserves the right to seek clarification or additional information from each Bidder regarding its proposal.

- 7.	Step 7:  Selection of Final List

Progress Energy Florida will develop a Final List based on the detailed evaluation of the short-listed proposals. This Final List will not necessarily be composed of the lowest cost alternatives. The price and non-price attributes described in this RFP solicitation document will be considered in their totality for each project. Progress Energy Florida will exercise sound professional judgment in performing the analyses and in making the final selection of the RFP process. Progress Energy Florida’s objective is to select resources that offer the maximum value, based on cost and non-cost attributes, to the Company and its customers. The final-listed Bidders will be those Bidders with which PEF will begin contract negotiations. Progress Energy Florida will not necessarily award contracts to any of the Bidders on the Final List. In the event  PEF’s self-build alternative is clearly superior to the short-listed proposals, a Final List will not be selected and an appropriate announcement will be made.

- D.	Contract Negotiations

The next phase in the solicitation process is contract negotiations. As previously noted, PEF has included Key Terms and Conditions in the RFP to allow Bidders to identify their exceptions; thereby, expediting contract negotiations and allowing PEF to assess the significance of the changes requested by Bidders. Inclusion of a proposal in the Final List does not indicate PEF’s acceptance of the exceptions identified by the Bidder. Progress Energy Florida reserves the right to negotiate any terms and conditions which provide value to PEF and its customers. Also, if in PEF’s view contract negotiations are not proceeding on a reasonable schedule to ensure achievement of the in-service date requirement, PEF has the right to terminate contract negotiations with that Bidder.

- Regulatory Filings

Determination of Need and/or Cost Recovery Filings with the Florida Public Service Commission may be required of selected proposals. Proposals that require an application for certification by the Florida Siting Board under the Florida Electrical Power Plant Siting Act will require a Determination of Need by the Florida Public Service Commission. In that event, Progress Energy Florida will be the applicant, and the Bidder will be the co-applicant in proceedings before the Florida Public Service Commission (which will determine the need for the project), the Florida Department of Environmental Protection (which will make a recommendation to the Florida Siting Board concerning site certification), and the Florida Siting Board. Cost Recovery Filings are annual filings associated with the fuel and purchased power clauses and are made after the execution of the purchased power agreement (PPA) and will be required for all selected proposals. In the case of a proposal that does not require a need determination, pre-approval of the PPA, as determined by PEF, may be required. The regulatory filing date of September 27, 2004 in the RFP schedule presented on page I-2 is for the Determination of Need Filing, if required, or the PPA pre-approval filing, if desired. Progress Energy Florida will also require that an application for site certification be filed on or before September 27, 2004 for any project that will require site certification by the Florida Siting Board.

- PROGRESS ENERGY FLORIDA’S “NEXT PLANNED GENERATING UNIT”

The following data represent preliminary cost and performance estimates for Progress Energy Florida’s next planned generating unit and are provided for information purposes only. These planning estimates have not been refined by detailed engineering or vendor quotes. The final actual cost of the project could be greater or smaller than that shown. Parties responding to this RFP should rely on their own independent evaluations and estimates of project costs in formulating their proposals.

- A combined cycle generating unit to be located on PEF’s existing Hines Energy Complex site in Polk County, Florida.

- Planned Size 565 MW (winter), 494 MW (summer).

- Commercial Operation of the facility is proposed to be December 1, 2007.

- The primary fuel is natural gas. Distillate fuel oil will be used as a backup fuel source.

- The estimated total direct cost is $249.9 million, including escalation, but excluding AFUDC. This estimate does not include transmission interconnection or required system upgrade costs.

- The estimated annual levelized revenue requirement is $38.0 million over 25 years (2008$).

- The estimated annual value of deferral of this unit is $55.05/kW-yr (2008$), which includes generation construction costs and fixed O&M.

- The estimated annual fixed O&M is $0.96/kW-yr (2007$). The estimated variable O&M is $0.26/MWh (2007$). The estimated major maintenance costs are $2.72/MWh (2007$).

- The estimated delivered fuel cost is $4.03/mmBtu (2007$), plus fixed transportation at $0.55/mmBtu.

- The following are estimates for:

Planned outage rate	5.8%

Forced outage rate    	3%

Minimum load         	147 MW (winter)

Ramp Rate              	45 MW/minute from min. to full load

Minimum run time	4 hours

Minimum down time	6 hours

Capacity factor	50% (annual average from TYSP)

Annual starts		50-100

Capacity States and heat rates (based on HHV of fuel)

| Seasonal Capacity States and Net Heat Rates |  |  |  |
| --- | --- | --- | --- |
| Capacity State (MW) |  | Primary Fuel (Btu/kWh) |  |
| Winter | Summer | Winter | Summer |
| 147 | 123 | 7731 | 8344 |
| 565 | 494 | 6720 | 6775 |

All values based on “new and clean” conditions

- The estimated transmission interconnection costs for this unit are $3.1 million, excluding AFUDC. The estimated transmission system integration costs for this unit are $26.9 million, excluding AFUDC.

- Supplemental site certification as well as amendment to related environmental permits will be required for this unit. It is PEF’s plan to comply with all environmental standards of Local, Regional, State and Federal governments.

- The major financial assumptions in the development of these numbers were:

Construction escalation:	2.5% per year

O&M escalation:		2.5 % per year

Fuel escalation:			Varies by year

Capital structure:		48% debt @ 5.5%

52% equity @ 12%

Discount rate:			7.92%

- PROGRESS ENERGY FLORIDA’S SYSTEM SPECIFIC CONDITIONS

FPC, doing business as Progress Energy Florida, Inc., is providing the following list of favorable generation location sites.

FPC has identified sites on the FPC Transmission System for the interconnection of new generation. Sites are based upon FPC's current knowledge of and experience with the FPC Transmission System.

Generation located at these sites appears to be less likely to cause severe system impacts and necessitate extensive transmission network upgrades. There may be other sites (which are not listed) that may offer similar capabilities. It must be emphasized that the full extent of the impact of a particular generation facility on the system and any needed transmission system improvements cannot be determined absent a specific study associated with the generation facility as provided for in FPC's Generator Interconnection Procedures, which can be found through the FPC and Interconnection Docs links on the FPC OASIS (http://floasis.seimens-asp.com). The ultimate disposition of transmission service associated with a generator also impacts needed transmission system improvements.

Persons interested in interconnecting generation should independently evaluate these sites as they would evaluate any potential generation site. To facilitate such studies, customers can obtain transmission cases upon request from the Florida Reliability Coordinating Council. Potential generators assume all risks should they decide to interconnect generation at one or more of these sites. Moreover, this list of sites reflects only a transmission perspective and does not consider other issues that may be relevant, such as fuel supply, water supply or environmental concerns.

FPC does not make, and expressly disclaims, any representation regarding the suitability of the sites for locating new generation. By posting this list of sites, FPC is not offering to purchase the output of any generation that may be constructed at such sites, nor does FPC warrant or otherwise guarantee the availability of transmission service from these sites.

It should be emphasized that interconnection and transmission service requests change frequently and can affect results at a particular site. Accordingly, reference should be made to the FPC OASIS (http://floasis.siemens-asp.com) for information relating to existing requests including generator interconnection requests at or near to a particular site.

General for siting

- 230 kV stations or lines are more favorable than 115 kV or 500 kV.

- Areas in proximity of nuclear generation may be more sensitive to stability issues.

- 230 k V lines are typically rated between 400 MVA to 1000 MVA.

- 115 kV lines are typically rated between 70 MVA and 200 MVA.

- Stations are more favorable than lines.

Favorable Generation Sites

Listed by County

| County | Potential Area of Interconnection | Interconnection Voltage |
| --- | --- | --- |
| Lake | Sorrento Sub | 230 kV |
| Seminole | Piedmont Sub | 230 kV |
| Orange | Woodsmere Sub | 230 kV |
| Marion | Silver Springs Sub | 230 kV |
| North Pinellas | Lake Tarpon Sub | 230 kV |
| South Pinellas | Ulmerton Sub | 230 kV |

- ATTACHMENT A

KEY TERMS & CONDITIONS

- DEFINITIONS

“Agreement” means the Power Purchase Agreement entered into between Progress Energy Florida (PEF) and the “Seller.”

“Commencement Date" means the date power is first accepted under this Agreement, and could be as early as December 1, 2006 but no later than December 1, 2007.

“Commercial Operation” means operation of the Facility commencing on the Commercial Operation Date and continuing until termination or expiration of the Agreement.

“Commercial Operation Date” means the later of (a) first day of the month following the date that the Facility has been satisfactorily completed and tested by Seller, or (b) the Commencement Date.

“Delivery Point” means the point at which deliveries of capacity and energy under the Agreement are required to be made and shall be measured which, for any Facility located within PEF’s control area, shall be the Point of Interconnection; and, for any Facility located outside PEF’s control area, shall be the physical point at which connection is made between PEF’s system and the system of the Wheeling utility adjacent to PEF’s control area which will deliver the capacity and energy to such point from the Facility or from other Wheeling utilities, as the case may be.

“Effective Date” means the date set forth in the preamble to the Agreement.

“Equivalent Availability Factor” or “EAF” shall have the meaning given in Section II.H of the Response Package.

“Equivalent Forced Outage Rate” or “EFOR” shall have the meaning given in Section II.H of the Response Package.

“Facility” or “Project”  means the equipment, spare parts inventory, lands, property, buildings, generators, step-up transformers, boilers, output breakers, transmission lines and facilities used to connect to the Delivery Point or to the Facility's point of interconnection with the Wheeling utility, protective and associated equipment, improvements, and other tangible and intangible assets, property rights and contract rights reasonably necessary for the construction, operation and maintenance of the Facility.

“Good Utility Practice”  means the practices, methods and acts (including but not limited to the practices, methods and acts engaged in or approved by a significant portion of the electric utility industry) that, at a particular time, in the exercise of reasonable judgement in light of the facts known or that should reasonably have been known at the time a decision was made, would have been expected to accomplish the desired result in a manner consistent with law, regulation, codes, standards, equipment manufacturer's recommendations, reliability, safety, environmental protection, economy and expedition.  With respect to the Facility, Good Utility Practice(s) include, but are not limited to, taking reasonable steps to ensure that:

1.	adequate equipment, materials, resources and supplies, including Primary Fuel and Secondary Fuel (with minimum inventory levels) are available to meet the needs of the Facility;

2.	sufficient management and operating personnel are available at all times and are adequately experienced and trained and licensed as necessary to operate the Facility properly, efficiently and in coordination with the transmission system control area operator and are capable of responding to reasonably foreseeable emergency conditions whether caused by events on or off the site of the Facility;

- preventive, routine, and non-routine maintenance and repairs are performed on a basis that ensures reliable long term and safe operation, and are performed by knowledgeable, trained and experienced personnel utilizing proper equipment and tools;

4.	appropriate monitoring and testing is done to ensure equipment in functioning as designed;

5.	equipment is not operated in a negligent or reckless manner, or in a manner unsafe to workers, the general public or the transmission system control area operator or contrary to environmental laws or regulations or without regard to defined limitations such as steam pressure, temperature and moisture content, chemical content of make-up water, safety inspection requirements, operating voltage, current, volt-ampere reactive (VAR) loading, frequency, rotational speed, polarity, synchronization and/or control system limits; and

6.	the equipment will function properly under both normal and emergency conditions at the Facility and/or the transmission system.

“Interconnection Facilities”  means all land, easements, materials, equipment and facilities installed for the purpose of interconnecting the Facility to the Delivery Point to facilitate the transfer of electric energy in either direction, including but not limited to connection, transformation, switching, metering, relaying, communications equipment, safety equipment, and any necessary additions and reinforcements to the control area operator’s transmission system required for safety or system security as a result of the interconnection between the Facility and the control area operator’s transmission system.

“Milestone Date” means the date by which the Seller is required to complete a specified task in accordance with the Milestone Schedule.

“Milestone Schedule” means the Milestone Schedule set forth in the Agreement, as such Milestone Schedule may be revised in accordance with the terms and conditions of the Agreement.

“MW” means megawatt or megawatts.

“Net Dependable Capacity” or “NDC” means the maximum net sustainable output of the Facility in MW that can be delivered to the Delivery Point (after deducting plant auxiliary loads and other losses), based on a performance test.

“Net Electrical Output”  means all of the Facility’s electric generating output after deducting plant auxiliary loads and any transmission losses between the Facility and the Delivery Point, as measured by metering devices owned by PEF.

“Point of Interconnection” shall mean the point where the Seller’s Interconnection Facilities connect to the Company’s transmission system.

“Project Lender” means the lender or lenders providing the initial construction and/or permanent debt financing for the Facility, and any fiscal agents, trustees, or other nominees acting on their behalf.

“Ramp Rate” means the minimum rate change in Net Electrical Output per minute over the period beginning at the time when the Seller is instructed to change the Facility’s Net Electrical Output, and ending at the time that such Net Electrical Output is achieved, based on performance testing.

“Scheduled Commercial Operation Date” means the Milestone Date by which Seller is required to achieve Commercial Operation.

“Seasonal Contract Capacity(ies)” shall have the meaning given in Section II of the RFP document.

“Seasonal NDC” means the Summer NDC and/or the Winter NDC, as applicable.

“Security Funds” means the Development Security Fund and the Operational Security Fund as defined in Section 3.2.

“Start Time” means the maximum time required to synchronize the Facility to the control area operator’s transmission system and achieve minimum load beginning when PEF instructs the Seller to start the Facility from a cold shut-down condition.

“Summer Contract Capacity” shall have the meaning given in Section II of the RFP document.

“Summer NDC” means the NDC for the Summer Period, corrected to the ambient conditions.

“Summer Period” shall be the months specified in Section II.F of the Response Package.

“System” means Power System as defined in the Solicitation Document (see page II-2).

“Wheeling” means the transmission of electric power from the electrical system of one utility to the electrical system of another utility, either directly or through the system of one or more other utilities.

“Winter Contract Capacity” shall have the meaning given in Section II of the RFP document.

“Winter NDC” means the NDC for the Winter Period, corrected to the ambient conditions.

“Winter Period” shall be the months specified in Section II.F of the Response Package.

- SECTION 1.  RIGHT OF FIRST REFUSAL

Progress Energy Florida (PEF) shall have the Right of First Refusal to purchase the Facility or to purchase any capacity expansions during the term of the Agreement, upon substantially the same terms and purchase price as that offered to any third party, which option shall be held open for a period of ninety (90) days after Seller’s presentation of the terms of such offer to PEF. Notwithstanding the foregoing, any transfer of the Facility or any expansion thereof to any third party shall be permitted only with the prior written approval of PEF, and only upon agreement by a third party to assume all of Seller’s obligations under the Agreement. This Right of First Refusal is not applicable to System sales.

- SECTION 2.  ADJUSTMENTS TO FIXED PAYMENTS

Subsequent to the Commercial Operation Date of the Facility and subject to the Seller’s meeting all other obligations under the Agreement (including availability requirements), PEF shall accept, purchase and pay for the Seasonal NDC (as applicable) to be delivered under the Agreement based on the Contract Capacity, subject to the following:

a.	If the tested Seasonal NDC is greater than or equal to the Seasonal Contract Capacity, PEF will pay Seller for capacity delivered based on the Seasonal Contract Capacity.

b.	If tested Seasonal NDC is lower than the Seasonal Contract Capacity, PEF will pay Seller based on the Seasonal Contract Capacity, after subtracting the daily liquidated damages as specified in Section 3.5, until a re-test of the Facility shows a Seasonal NDC at least equal to the applicable Seasonal Contract Capacity.

c.	If Seller fails to achieve an eighty-five percent (85%) EAF on a 12-month rolling average, starting in the second contract year, then the proposed Fixed Payments (Generation Capital, Transmission, Fixed O&M, and Fixed Pipeline Demand/Reservation as specified in Schedule 1 of the Response Package) will be reduced on a sliding-scale basis.

d.	No Fixed Payments will be made for those months in which the 12-month rolling average EAF is less than 60%.

- In any month, if the actual EFOR is greater than the EFOR guarantee, the proposed Fixed Payment will also be reduced by the Availability Adjustment Factor (AAF), where

AAF = (1 - EFORactual) / (1 - EFORguarantee).

The AAF shall not be greater than 1.0.

- The monthly fixed payment shall thus be

Actual Fixed Payment (AFP) = proposed Fixed Payment * EAF adjustment * AAF.

Fixed Payment Adjustments are not applicable to System sales.

- SECTION 3.  DEFAULT AND SECURITY

3.1	Operation by PEF Following Event of Default by Seller

a.	If during the term of the Agreement PEF becomes entitled to terminate the Agreement due to an Event of Default and if operation of the Facility is not assumed by Project Lender or its permitted assignee, then, in lieu of terminating the Agreement, PEF may, but is not obligated to, assume operational responsibility for the Facility to complete construction, continue operation, complete any necessary repairs, or take such other steps as are appropriate in the circumstances, or may designate a third party or parties to do the same, so as to assure uninterrupted availability of capacity and deliverability of electric energy from the Facility.  Seller agrees to fully cooperate with PEF in providing access to the Facility, and permitting PEF to operate the Facility as provided herein.  Any payments to Seller shall be made only after any and all costs and expenses (including liquidated damages) of PEF in exercising its rights hereunder are deducted.

b.	PEF’s exercise of its rights hereunder to operate the Facility and Seller’s Interconnection Facilities shall not be deemed an assumption by PEF of any liability of Seller.

c.	PEF may continue to operate the Facility until:

(1)	Seller demonstrates to PEF’s satisfaction that it is financially and technically qualified to operate the Facility in accordance with the Agreement and resumes operations;

(2)	the Project Lender or its permitted assignee assumes operation of the Facility; or

- PEF terminates the Agreement for an Event of Default.

d.	Operation by PEF Following Event of Default by Seller is not applicable to System sales.

3.2	Establishment of Security Funds

a.	Seller agrees to establish, fund, and maintain the Security Funds specified below, which shall be available at PEF’s discretion to pay any amount due to PEF under the Agreement:

(1)	A “Development Security Fund” which shall be established and funded as provided in Section 3.2f within thirty (30) days after the Effective Date, and shall be maintained until such time as (a) the Facility achieves Commercial Operation; (b) all amounts payable from the Development Security Fund have been paid; and (c) the Operational Security Fund has been satisfactorily established and funded. A Development Security Fund is not applicable to a sale from either an existing generator or a System.

(2)	An “Operational Security Fund”  which shall be established and funded as provided in Section 3.2g within thirty (30) days after the Commercial Operation Date, and shall be maintained until (a) the end of the term of the Agreement, or until termination of the Agreement; and (b) all amounts payable from the Operational Security Fund have been paid.

b.	The Security Funds shall be maintained at Seller’s expense, shall be originated by or deposited in a financial institution or company (“Issuer”) acceptable to PEF, and shall be in the form of either of the following, or combination of both:

(1)	an irrevocable standby letter of credit drawn on an Issuer acceptable to PEF; or

(2)	cash in U. S. Dollars or U. S. Government Bonds deposited with an Issuer acceptable to PEF.

c.	If a Security Fund in the form of an irrevocable letter of credit is utilized by the Seller to fund the above, such security must be issued for a minimum term of two (2) years.  Additionally, the form and substance of such letter of credit must meet PEF’s requirements to ensure that claims or draw-downs can be made in accordance with the terms of the Agreement.  Furthermore, at the end of each year the security must be renewed for another one (1) year term such that the minimum remaining term of any such security shall not be less than twelve (12) months.  If there is failure to comply with this provision, PEF shall have the right to draw immediately upon the security and to place the amounts so drawn in an account in accordance with the provisions of Section 3.2b.  At such time as Seller’s obligation to provide security expires, PEF shall, within a reasonable period of time, cooperate with Seller in canceling the letter of credit and/or returning such amounts.

d.	With respect to any escrow account opened as security for Seller’s obligations hereunder, PEF shall establish at Seller’s cost and with Seller’s funds an account in the name of PEF.  If cash is to be deposited, the account shall be an interest bearing account.  The documents for such escrow account and the institution holding such escrow account shall be acceptable to PEF in its sole discretion.  At such time as Seller’s obligation to provide security hereunder expires, PEF shall, within a reasonable period of time, return the cash or bonds in such escrow account to Seller.  At such times as the cash balance in such escrow account exceeds the amount of Seller’s obligation to provide security hereunder, PEF shall remit to Seller, at Seller’s request, any excess in the escrow account above Seller’s obligations.  Seller may obtain the return of such escrow account at any time by providing to PEF an irrevocable letter of credit in the same amount as the escrow account and meeting the appropriate criteria specified in the Agreement.

- PEF may reevaluate the value of all non-cash securities put into escrow as provided above at any time.  Should the value of the non-cash securities fail to be in excess of the requirements set forth above, PEF may in its sole discretion require Seller to post additional security of an acceptable nature and level.

- Development Security is security required from Seller during the development phase of the project.  It must be posted according to the schedule found below and is based on the average Seasonal Contract Capacity of the Facility.  All remaining Development Security will be returned to the Seller when the conditions of Section 3.2 are accomplished.

DEVELOPMENT SECURITY SCHEDULE

($50/kW Total)

Amount		         Cumulative

Timing				(Cash Equivalent Value)	(Cash Equivalent Value)

30 days after				$20/kW			$20/kW

contract signing

18 months before Scheduled		$20/kW			$40/kW

Commercial Operation Date

12 months before Scheduled		$10/kW			$50/kW

Commercial Operation Date

- Operational Security is required from Seller during the operational phase (i.e., commercial operations date to contract end) of the project.  It must be posted according to the schedule below and is based on the average Seasonal Contract Capacity of the Facility.  All remaining Operational Security will be returned to the Seller when the conditions of Section 3.2 are accomplished.

OPERATIONAL SECURITY SCHEDULE

($30/kW Total)

Amount		         Cumulative

Timing				(Cash Equivalent Value)	(Cash Equivalent Value)

Within 30 days after			$10/kW			$10/kW

Commercial Operation Date

5 Years After				$10/kW			$20/kW

Commercial Operation Date

10 Years After				$10/kW			$30/kW

Commercial Operation Date

3.3	Liquidated Damages for Seller’s Failure to Meet Milestone Dates Before Commercial Operation

a.	If Seller fails to achieve Commercial Operation by the Scheduled Commercial Operation Date or fails to meet any Milestone Date, Seller shall pay liquidated damages to PEF as specified below:

| Event |  | Liquidated Damages |  |
| --- | --- | --- | --- |
| i. Failure to meet each Milestone Date under Section 3.5 above (other than Commercial Operation) |  | AFP/60* |  |
| - Failure to attain Commercial Operation by the Scheduled Commercial Operation Date * Based on the Seasonal Contract Capacity |  | AFP/30* |  |

Liquidated damages shall be paid for each calendar day of delay until the event is achieved or until twelve (12) months shall pass, as liquidated damages and not as a penalty.  Liquidated damages shall begin accruing the day after failure to meet the scheduled Milestone.  Such amounts shall be cumulative for each Milestone which is not achieved.  Liquidated damages shall be payable monthly within ten (10) days of Seller’s receipt from PEF of a bill covering the applicable period and shall continue until the specific Milestone is achieved or twelve (12) months have passed.  If Seller fails to make such payment within such ten (10) days, PEF may draw on the Development Security to cover such payment. In the event that Seller fails to achieve a Milestone event within twelve (12) months of the Milestone Date for such event, PEF shall have the right to terminate the Agreement.  If PEF exercises its right to terminate the Agreement, the entire amount of the Development Security plus any accrued interest shall be retained by PEF as liquidated damages.  PEF shall also have any and all remedies specified in the Agreement, or as provided by law.

b.	If Seller fails to achieve Commercial Operation by the Scheduled Commercial Operation Date, Seller shall be liable for damages to PEF for the costs of replacing the capacity and energy over and above what PEF would have paid Seller for the capacity and energy under the Agreement, and the transactional costs of obtaining the replacement capacity and energy, in addition to any liquidated damages payable under Section 3.3a.

- If Seller provides written notice to PEF or it is otherwise determined by PEF at any time after the Effective Date that Seller will not be able to complete the Facility to a state of Commercial Operation, PEF may terminate the Agreement, and Seller shall pay liquidated damages as specified by the following formula, in addition to any liquidated damages payable under Section 3.3a through the date of termination:

|  | ($20/kW X Contract Capacity) + |  |
| --- | --- | --- |
|  | ($40/kW X Contract Capacity) X (No. of days from contract execution to date of notice) |  |
|  | (No. of days from contract execution to Scheduled Com. Oper. Date) |  |

Upon such notice given by PEF, the Agreement shall terminate and Seller waives any rights it may have under the Agreement.

3.4	Damages for Event of Default After Commercial Operation

If a termination of the Agreement occurs as a result of an Event of Default of Seller after attaining Commercial Operation, Seller, for three (3) years subsequent to the date of default, shall be liable for PEF’s damages, including, but not limited to, damages to PEF for the costs of replacing the capacity and energy over and above what PEF would have paid Seller for the capacity and energy under the Agreement, and the transactional costs of obtaining the replacement capacity and energy.

3.5	Penalties for Seasonal Contract Capacity Deficiencies

Seller shall pay to PEF an amount to be negotiated for the difference between the Seasonal Contract Capacity and the tested Seasonal NDC as determined through Facility testing, for each day that the Seasonal NDC remains below the Seasonal Contract Capacity. Assessed penalties shall be paid monthly. Penalties for Seasonal Contract Capacity Deficiencies are not applicable to System sales.

3.6	Penalties for Start Time Deficiencies

If Seller fails to meet the agreed upon Start Time requirements when tested in accordance with agreed upon provisions at any time during the term of the Agreement, then for each failure Seller shall pay PEF an amount to be negotiated, based on the applicable Seasonal Contract Capacity for the Facility, until the deficiency is corrected and satisfactorily re-tested. Assessed penalties shall be paid monthly.

3.7	Penalties for Ramp Rate Deficiencies

If Seller fails to meet the agreed upon Ramp Rate requirements when tested in accordance with agreed upon provisions at any time during the term of the Agreement, then for each failure Seller shall pay PEF an amount to be negotiated, based on the applicable Seasonal Contract Capacity for the Facility, until the deficiency is corrected and satisfactorily re-tested. Assessed penalties shall be paid monthly.

3.8	Payments from Security Funds

In addition to any other remedy available to it, PEF may draw appropriate amounts from the Security Funds to recover the damages owing to it under the Agreement, including but not limited to the recovery of liquidated damages payable under this Section 3.  At the end of the term of the Agreement, the remaining balance of the Security Funds and accumulated interest shall be returned to Seller within a reasonable period of time if any funds are remaining in the Security Funds and if no funds are owed to PEF under the Agreement.

- SECTION 4.  OPERATION OF THE FACILITY

4.1	General

Seller shall operate, maintain, and repair the Facility in a safe, prudent, reliable, and efficient manner in accordance with Good Utility Practice.

4.2	Establishment of Operating Procedures

Seller and PEF shall each appoint an Operating Representative who shall be the primary point of contact between the parties for purposes of this Section within thirty (30) days after the Effective Date.  Seller and PEF shall mutually develop written operating procedures no later than ninety (90) days prior to the Scheduled Commercial Operation Date.  The operating procedures will be established by mutual agreement based on the design of the Facility and the design of the Interconnection Facilities.  The operating procedures will be intended as a guide on how to integrate the Facility into the control area operator’s transmission system.  Topics covered shall include, but be not limited to, method of day-to-day communications; key personnel list for applicable PEF and Seller operating centers; clearances and switching practices; outage scheduling; daily capacity and energy reports; unit operations log; and reactive power support.  In no event shall the operating procedures to be established hereunder be considered as a modification, amendment or waiver of any of the terms and conditions of the Agreement.

4.3	Certification of Maintenance

a.	Seller shall obtain at its sole expense an independent engineering review of the entire Facility (including the Interconnection Facilities), its operation and maintenance to assist PEF in monitoring compliance with Good Utility Practice.  This review shall also include a review of the environmental compliance of the Facility and its operation and maintenance plan.  The independent review will be conducted by an engineering firm other than the firm chosen by Seller to design, construct, operate or maintain the Facility, and furthermore, selection of this engineering firm is subject to PEF’s approval.  The independent review will be conducted according to the following schedule:

(1)	Once every other year for the first ten (10) years following the Commercial Operation Date.

(2)	For the remainder of the term of the Agreement, once every calendar year.

b.	Seller shall cause the independent engineer to issue a written report to PEF before June 1 of every year in which the independent review has been conducted assessing Facility operation and maintenance and compliance with all applicable environmental licenses, approvals, and permits and stipulating any related remedial or other actions consistent with Good Utility Practice.  Such report shall be made available to PEF as soon as it is available to Seller.  Seller shall cause these recommendations to be implemented as soon as practical unless Seller and PEF agree otherwise.  Seller shall provide written certification of implementation of these recommendations to PEF as soon as they are completed.

c.	PEF or its designated agent shall have the right to verify such recommendations by reviewing all pertinent Facility records and by inspecting the Facility, provided that such review and inspection shall not unreasonably interfere with Seller’s operations at the Facility.

d.	Seller and PEF shall use all reasonable efforts to resolve any disputes between them as to whether any maintenance deficiency exists and/or whether a particular remedy is reasonably necessary to correct a purported deficiency.

e.	Seller agrees to undertake promptly and complete any undisputed deficiencies in maintenance and any disputed deficiencies in maintenance as ultimately agreed by Seller and PEF.

4.4	PEF Inspections

Seller shall allow PEF, at any time and with reasonable prior notice, to visit the Facility, including the control room and Interconnection Facilities, to inspect the Facility, review Seller’s operating practices, and examine the operating logs.  These visits may be made during weekends and nights as well as normal business hours.  In exercising such rights, PEF shall not unreasonably interfere with or disrupt the operation of the Facility and PEF shall comply with all of Seller’s reasonable safety regulations at the Facility.

- SECTION 5.   COMPLIANCE WITH LAWS

5.1	General

Seller agrees that it will at all times comply with all federal, state, and local statutes, laws, regulations and public ordinances of any nature relating in any way to the construction, modification, ownership, maintenance and operation of the Facility, and shall procure all necessary governmental permits, licenses, and inspections, and shall pay all fees and charges in connection therewith.  Seller shall indemnify and defend PEF from and against any liability, fines, damages, costs, or expenses arising from Seller’s failure to comply with the requirements of this Section.

5.2	Safety and Health

Seller shall comply with all federal, state and local laws and regulations pertaining to health, safety, sanitary facilities and waste disposal.  Seller shall meet all requirements of the Occupational Safety and Health Act of 1970 (OSHA), including all amendments.  Seller shall also comply with any standards, rules, regulations and orders promulgated under OSHA and particularly with the agreement for state development and enforcement of occupational health and safety standards as authorized by Section 18 of the Act.

5.3	Equal Employment Opportunity

Unless the rules, regulations or orders of the United States Secretary of Labor exempt the Agreement from the provisions of Section 202 of Executive Order No. 11246, dated September 24, 1965, relating to equal employment opportunity, those provisions are, to the extent applicable, made a part of the Agreement.

- SECTION 6.   ASSIGNMENT

Seller shall not sell or transfer the Facility or any part thereof, and shall not sell, transfer or assign the Agreement or any rights or obligations thereunder, without the prior written consent of PEF.  A request to sell or transfer the Facility, or to sell, transfer or assign the Agreement must contain the name and location of individuals or firms to whom it is to be assigned, and a detailed description of the proposed transaction.  Consent by PEF to sell or transfer the Facility, or to sell, transfer or assign the Agreement shall not relieve the Seller of responsibility for the performance of all obligations under the Agreement.  Any sale or transfer of the Facility, and any transfer or assignment of the Agreement shall not jeopardize any of the security given by Seller as provided in Section 6.  For purposes of this Section, a transfer or assignment shall include but not be limited to a sale of all or a majority interest in the stock of Seller.

- SECTION 7.  ENVIRONMENTAL REPORTING AND INDEMNITY

7.1	Environmental Compliance

Seller shall construct, maintain and operate the Facility in accordance with all state, federal and local environmental laws, regulations, ordinances, and permits.  Seller shall disclose to PEF, as soon as and to the extent known to Seller, any actual or alleged violation of any environmental laws or regulations arising out of or in connection with the construction, operation or maintenance of the Facility, or the alleged presence of environmental contamination at or in connection with the Facility, or the existence of any past or present enforcement, legal or regulatory action or proceeding relating to such alleged violation or alleged presence of environmental contamination.  Environmental contamination means the presence of hazardous wastes, hazardous substances, hazardous materials, toxic substances, hazardous air or other hazardous pollutants, and toxic pollutants, as those terms are used in the Resource Conservation and Recovery Act; the Comprehensive Environmental Response, Compensation and Liability act; the Hazardous Materials Act; the Toxic Substances Control Act; the Clean Air Act; the Safe Drinking Water Act; the Oil Pollution and Hazardous Substances Control Act; and any and all other applicable federal, state, and local laws and regulations as amended, at such levels or quantities or location, or of such form or character, to be in violation of said federal, state, and local laws and regulations.

7.2	Environmental Indemnity

Seller shall indemnify, defend and hold PEF harmless against any and all claims, demands, losses, liabilities, expenses, fines and penalties, including interest and attorney fees, resulting from any alleged violation of applicable federal, state or local environmental laws or regulations arising out of Seller’s construction, operation, maintenance or ownership of the Facility or the Facility site, or the presence of any environmental contamination at or in connection with the Facility.

- SECTION 8.  REGULATORY OUT

Notwithstanding anything to the contrary in the Agreement, if PEF, at any time during the term of the Agreement, fails to obtain or is denied the authorization of the Florida Public Service Commission (“FPSC”), or the authorization of any other legislative, administrative, judicial or regulatory body which now has, or in the future may have, jurisdiction over PEF’s rates and charges, to recover from its customers all of the payments required to be made to the Seller under the terms of the Agreement or any subsequent amendment hereto, PEF may, at its sole option, adjust the payments made under the Agreement to the amount(s) which PEF is authorized to recover from its customers. In the event that PEF so adjusts the payments to which the Seller is entitled under the Agreement, then, without limiting or otherwise affecting any other remedies which the Seller may have hereunder or by law, the Seller may, at its sole option, terminate the Agreement upon (180) days written notice to PEF. If such determination of disallowance is ultimately reversed and such payments previously disallowed are found to be recoverable, PEF shall pay all withheld payments, with interest as set for refunds under the Federal Power Act pursuant to 18 C.F.R. §35.19a.. Seller acknowledges that any amounts initially received by PEF from its ratepayers, but for which recovery is subsequently disallowed and charged back to PEF, may be offset or credited, with interest as set for refunds under the Federal Power Act pursuant to 18 C.F.R. §35.19a, against subsequent payments to be made by PEF to the Seller under the Agreement.

If, at any time, PEF receives notice that the FPSC or any other legislative, administrative, judicial or regulatory body seeks or will seek to prevent full recovery by PEF from its customers of all payments required to be made under the terms of the Agreement or any subsequent amendments to the Agreement, then PEF shall, within five business days of such action, give written notice thereof to the Seller. PEF shall use its best efforts to defend and uphold the validity of the Agreement and its right to recover from its customers all payments required to be made by PEF hereunder, and will cooperate in any effort by the Seller to intervene in any proceeding challenging, or to otherwise be allowed to defend, the validity of the Agreement and the right of PEF to recover from its customers all payments to be made by it hereunder.

The Parties do not intend this Section 8 to grant any rights or remedies to any third party(ies) or to any legislative, administrative, judicial or regulatory body; and this Section 8 shall not operate to release any person from any claim or cause of action which the Seller may have relating to, or to preclude the Seller from asserting, the validity or enforceability of any obligation undertaken by PEF under the Agreement.

- ATTACHMENT B

Progress Energy Florida

2003 Ten-Year Site Plan

(PEF 2003 TYSP Not Included in Hines 4 Need Study)

# Appendix I. Progress Energy Florida’s RFP Response Package

- Progress Energy Florida

- Request For Proposals

- for

- Power Supply Resources

- Response Package

October 7, 2003

Response Package

Table of Contents

I.	General Instructions	1

II.	Organization and Contents of Bidders’ Proposals	1

A.	Overview	1

B.	Proposal Outline	1

C.	Proposal Executive Summary	2

D.	Chapter 1: Project Summary	3

E.	Chapter 2: Proposal Pricing	3

F.	Chapter 3: Operating Performance	8

G.	Chapter 4: Permitting Plans [New Unit Proposal]	9

H.	Chapter 5: Engineering and Design Plans	12

I.	Chapter 6: Site Control [New Unit Proposal, Existing Unit Proposal]	14

J.	Chapter 7: Transmission Plan	14

K.	Chapter 8: Fuel Supply and Transportation Plan	15

L.	Chapter 9: Project Financing Plan	17

M.	Chapter 10: Commercial Operation Date Certainty	18

N.	Chapter 11: Bidder Experience	19

O.	Chapter 12: Acceptance of the Key Terms and Conditions [New Unit Proposals, Existing Unit Proposals]	20

III. 	Progress Energy Florida Approved Price Indices	21

Response Package Schedules

Notice of Intent to Bid

Schedule A – Project Summary

Schedule 1  (Sheets A, B, and C) – Pricing Schedule for New and Existing Unit Proposals

Schedule 2  (Sheets A and B) – Pricing Schedule for System Power Proposals

Schedule 3 – Project Capacity Rating and Heat Rate Schedule

Schedule 4 – Operating Performance Schedule

Schedule 5 – Environmental and Regulatory Permit Status Schedule

Schedule 6 – Air Emissions Schedule

Schedule 7 (Sections I and II) – Network Resource – System Impact Study Data Request

Schedule 8 – Project Pro Formas Schedule

Schedule 9 – Project Milestone Schedule

- I.	General Instructions

This Response Package contains the information required of Bidders and reviews the required organizational structure and contents of the proposals submitted in response to Progress Energy Florida’s RFP for Power Supply Resources. Prior to developing their proposals, Bidders are requested to carefully read Progress Energy Florida’s RFP and the instructions in this Response Package.

Proposals in response to this RFP must consist of three bound copies and an electronic version (on diskette or CD-ROM) with all text portions of the responses in Microsoft Word or Adobe Acrobat and schedules in Microsoft Excel. Each proposal is to be bound separately. Bidders must submit two (2) extra unbound copies of any document that is larger than 8 ½” x 11”. Bidders must ensure that the proposals are delivered on time. Preprinted materials such as maps, annual reports, etc. do not have to be submitted in electronic format.

Bidders are required to use the schedules provided. The schedules (as well as the format of the entire Response Package) have been designed to facilitate the evaluation of the proposals in an expedient manner. Failure to use the schedules will be grounds for disqualification.

- II.	Organization and Contents of Bidders’ Proposals

- A.	Overview

Bidders’ proposals must be organized according to the structure specified below. If a particular chapter or section is not relevant to a Bidder’s proposal, then the Bidder should include the chapter or section and indicate why it is not relevant. Where Progress Energy Florida (PEF) has included a schedule that is to be completed by the Bidder, the schedules must be completed or the Bidder must indicate why the schedule is not relevant.

- B.	Proposal Outline

The outline that Bidders must use to organize their proposals is presented below. Also specified in each section of this Response Package is the chapter number and section number that should be used for all proposals. The specific information that is to be included in each chapter is described below. However, because the information requested may not be relevant to all types of proposals, PEF has indicated in bold the type of proposal to which each question applies. Where no specific type of proposal is indicated, the Bidder should assume that the information is required for all types of proposals.

- Proposal Executive Summary

- Chapter 1:	Project Summary

- Chapter 2:	Proposal Pricing

- Chapter 3:	Operating Performance

- Chapter 4:	Permitting Plans

- Chapter 5:	Engineering and Design Plans

- Chapter 6:	Site Control

- Chapter 7:	Transmission Plan

- Chapter 8:	Fuel Supply and Transportation Plan

- Chapter 9:	Project Financing Plan

- Chapter 10: Commercial Operation Date Certainty

- Chapter 11: Bidder Experience

- Chapter 12: Acceptance of the Key Terms and Conditions

This Response Package is organized around a series of schedules. The matrix presented below indicates which schedules apply to different types of proposals. These schedules are provided in an Excel workbook included as part of this Response Package. If a schedule applies to the type of proposal that the Bidder is submitting, the Bidder is required to provide both hard and electronic copies of the schedule. Inconsistencies between the electronic and hard copies will be grounds for disqualification.

Schedules To Be Completed By Bidder

| Schedule No. and Name | New Unit | Existing Unit | System Power |
| --- | --- | --- | --- |
| Schedule A: Project Summary | X | X | X |
| Schedule 1: Pricing Schedule for New and Existing Unit Proposals | X | X |  |
| Schedule 2: Pricing Schedule for System Power Proposals |  |  | X |
| Schedule 3: Project Capacity and Heat Rate Schedule | X | X |  |
| Schedule 4: Operating Performance Schedule | X | X | X |
| Schedule 5: Environmental and Regulatory Permit Status Schedule | X |  |  |
| Schedule 6: Air Emissions Schedule | X |  |  |
| Schedule 7: Network Resource System Impact Study data request | X | X |  |
| Schedule 8: Project Pro Formas Schedule | X |  |  |
| Schedule 9: Project Milestone Schedule | X |  |  |

- C.	Proposal Executive Summary

The Bidder is required to provide a brief summary of its proposal (no more than two pages). The summary should include at a minimum a brief overview of the technology and equipment proposed, amount of capacity offered, project location and point of delivery, proposed project pricing, power delivery period, proposed fuel supply arrangements, experience with key project elements, financing plan/arrangements, permitting schedule, and conformance with Key Terms and Conditions provisions (see Attachment A to the RFP).

- D.	Chapter 1:	Project Summary

Chapter 1 of the Bidder’s proposal must consist of a completed Project Summary (Schedule A). Bidders should complete Schedule A after they have completed all other schedules; data must be consistent with the detailed schedules. In addition to submitting the Excel spreadsheet version of this schedule, the Bidder must include a hard copy of this schedule in Chapter 1 of its proposal. The information in this form will be treated as non-confidential and non-proprietary and may be released to the public.

- E.	Chapter 2:	Proposal Pricing

- 1.	Introduction

Bidders are required to complete all the applicable pricing schedules referenced in this chapter of the Response Package and to provide a complete description of the components of the charges. Progress Energy Florida has included price schedules for New and Existing Unit Proposals and System Power Proposals as part of this package. Bidders should only complete those schedules that are pertinent to the type of bid submitted (see Table on Page 2). Bidders should note that contract year one is a partial year. Therefore, a “10-year” contract will cover one partial year and nine full years, for example, December 1, 2007 through December 31, 2016.

- 2.	Price Schedule for New and Existing Unit Proposals

Bidders offering New or Existing Unit Proposals must complete all relevant sections of Schedule 1 as described in this section of the Response Package. Bidders should ensure that the pricing components of their proposals conform to the requirements described in Table IV-2 of the RFP. All costs to be paid by PEF must be reflected in the proposed pricing. PEF will not accept any charges other than those identified in Schedule 1.

Bidders must specify the pricing for their proposals in terms of the following components and units, to the degree that each component is relevant to the particular bid:

Fixed Payment

Generation Capital Charge ($/kW-Yr)

Transmission Charge ($/kW-Yr)

Fixed Operation and Maintenance (O&M) Charge ($/kW-Yr)

Pipeline Reservation Charge ($/mmBtu-day)

Variable Payment

Fuel Commodity ($/mmBtu)

Variable Transportation ($/mmBtu)

Variable O&M Price ($/MWh, $/hour, or both)

Start Payment

Start Price Per Facility ($/start/facility).

Schedule 1 consists of three Excel sheets. The sheets named “Schedule 1 Sheet A” and “Schedule 1 Sheet B” contain cells in which Bidders must enter the proposed term for their bid and the associated pricing data. The workbook is programmed to automatically calculate the yearly pricing projections over the proposed term, using the pricing data entered by the Bidder in the sheets. These calculated projections may be viewed in “Schedule 1 Sheet C,” but the Bidder is not allowed to make any entries in this sheet.

In addition to completing the schedules, Bidders should include back-up sheets (that are to be labeled by the Bidder as Exhibit 2.1) which clearly describe their pricing proposals in terms of the pricing components, the indices proposed to adjust the prices, and the frequency of change in the indices for payment purposes.

- a.	Initial Prices

In the Initial Data section of “Schedule 1 Sheet A,” the Bidder must provide initial prices for each of the pricing components. Bidders’ prices must reflect a January 1, 2003 base period. In addition to providing the initial prices, the Bidder must specify its primary and secondary fuels in this section of the schedule. The primary fuel is the fuel that the Bidder expects to use for the majority of the months in the year, and the secondary fuel is the fuel that the Bidder expects to use for the remaining months. If desired, the Bidder may propose to use only one fuel for all months throughout the year and not specify a secondary fuel. The Bidder should identify in the Initial Data Section the months in which the primary and secondary fuels will be expected to be used by entering a “P” for primary or an “S” for secondary next to each month. These entries will be used for both evaluation and payment purposes. For example, if a Bidder states that natural gas will be used eleven months of the year and oil for only one month (e.g., January), the Bidder must be willing to accept this commitment for both payment and evaluation purposes.

The final entries in the Initial Data Section are the Term of the Proposal, which represents the number of years under which capacity and energy will be provided to PEF by the Bidder, the Contract Start Month, and the Contract Start Year. Based on these entries in Sheet A, the beginning and ending dates for the corresponding contract years will automatically be displayed in Sheets B and C.

- b.	Price Escalation

In addition to providing initial prices for each of the fuel pricing components, the Bidder must specify the escalation indices to be used for each component for evaluation and payment purposes. This information must be provided in the Escalation Indices Section of “Schedule 1 Sheet A.”  Beside each pricing component, the Bidder can select a predefined index, or the Bidder can specify an alternative fixed escalation rate.

The value of the index on January 1, 2003 will be used in conjunction with the value of the index at the time of payment to determine the escalation rate to be applied to the Initial Price. For example, the primary commodity price used for payment in any month (m) is:

Primary Commodity Pricem = Initial Price x     Primary Commodity Indexm___

Primary Commodity Index1/1/2003

As a numerical example, assume the Initial Primary Commodity Price, is $5.00/mmBtu. Also assume the index selected for the Primary Commodity was 4.80 on January 1, 2003. In 2010, if the index turns out to be 6.00, the Primary Commodity Price that will be used to determine payments to the Bidder in 2010 will be:

Primary Commodity Price = 5.00 x  6.00 / 4.80 = $6.25/mmBtu.

This reflects the hypothetical 25% increase in the index from 2003 to 2010 and increases the Primary Commodity Price by 25% also.

The predefined indices from which the Bidder may choose are listed in Section III of this document, along with their current standard escalation assumptions at the time Section III was prepared. These assumptions are based on recent forecasts for the indices; however, PEF reserves the right to update these forecasts during the evaluation period if they no longer reflect PEF’s current expectations for the indices. Excel will automatically compute and display, in the right-most column of this section, the standard escalation for a particular pricing component based on the Bidder’s entries and the standard assumptions shown in Section III.

The standard escalation value will be used to evaluate the proposal; however, Bidders will be paid based on the actual values of the indices at the time of payment. The index selected for each pricing component should be consistent with market-based indices that are appropriate for that component. For example, if a Bidder proposes to use natural gas as its primary fuel, a gas commodity index is appropriate to choose. If a Bidder proposes to use a secondary fuel, the Bidder should select an appropriate index for that fuel. The Bidder must identify the pricing point for the index selected, if appropriate

To choose from the predefined indices, the Bidder selects the abbreviated code for the selected index, as given in Section III, in the first cell beside the pricing component. Selecting the cell will reveal a drop-down menu from which the index is to be selected.

Alternatively, the Bidder may choose to specify a fixed escalation rate by leaving all predefined index cells blank and entering the annual fixed escalation rate as a percent. Bidders should not specify both predefined and fixed escalators for any one pricing component. If a Bidder incorrectly completes the schedule by specifying both types of escalators, the fixed escalator will be used for evaluation and payment purposes.

Next, the Bidder must specify the Frequency of Change for the selected indices for payment purposes. For evaluation purposes, all values will escalate on a contract year basis. To specify the Frequency of Change, the Bidder may select Monthly, Quarterly, Annual, or Never (i.e., the initial price remains constant throughout the term) from the drop-down menus contained in the cells under the “Frequency of Change” heading.

- c.	Annual Charges

Bidders must enter generation capital charges in “Schedule 1 Sheet B” for every year of the term of the proposal. The generation capital charges must be based on the Seasonal Contract Capacities. Therefore, Bidders must take into account the difference in Summer and Winter Contract Capacities and enter annualized $/kW values for every year, including the start year when the proposal does not include all 12 months of the calendar year. Since the Summer and Winter Periods each contain six (6) months, this can easily be achieved by using the average Summer and Winter Contract Capacities when developing $/kW values. Bidders will be paid monthly based on the product of the Bidder-specified seasonal capacity and one-twelfth (1/12) of the Bidder-specified annual charges, and will be subject to adjustments based on actual operating performance (the adjustments for operating performance are described in the Key Terms and Conditions).

A transmission charge must be specified by the Bidder in Schedule 1 Sheet B for each year of the proposal. These charges should represent the Bidders Interconnection Facilities and wheeling (if applicable) costs to PEF’s Delivery Point and must be based on the Seasonal Contract Capacities. The transmission charges specified are to be consistent with the transmission equipment costs specified in Section 9.0 of the Bidder’s proposal. Costs for any necessary upgrades to integrate the project into the PEF transmission system will be estimated by PEF during the Detailed Evaluation of proposals and the costs for the upgrades will be included in the evaluation of the proposal. If the proposed project is not located in the PEF control area, any costs related to an upgrade of other transmission systems must be included in the price proposal by the Bidder. Progress Energy Florida will not estimate any upgrade costs for other control areas.

Bidders must specify a fixed pipeline demand/reservation charge (if appropriate to the technology being proposed). Bidders must specify a charge for each year of the proposal in $/mmBtu-day and must specify the amount of transportation proposed to be reserved (in Chapter 8 of the proposal). Bidders may specify a fixed pipeline demand/ reservation tariff as the price. Progress Energy Florida reserves the right to negotiate fuel transportation provisions with the Bidder if benefits can be derived for PEF and its customers.

The Bidder must enter annual prices for fixed and variable O&M. Although the Bidder may specify two fuels (Primary and Secondary) to be used during a year, the Bidder should enter only one annual price for each of the O&M components. These prices should reflect the weighted average annual O&M, based on the proposed fuels. The Bidder must specify an annualized price, even though the start year for the proposal may not include all twelve months of the calendar year.

The Bidder is also required to enter annual start prices. The start price component is designed to compensate the Bidder for the cost of starting the Facility. Payment will only be made for starts required by PEF. The Company will not reimburse the Bidder for test starts or starts arising from a forced outage or from an unplanned maintenance outage. The Company will estimate the number of starts for evaluation purposes but pay the Bidder based on the actual number of successful starts.

- 3.	Price Schedule For System Power Proposals

Bidders who are proposing System Power Proposals are required to complete “Schedule 2 Sheet A.” In the Initial Data Section of the Excel sheet, the Bidder must provide initial prices for the Fuel Energy components in $/MWh. Bidders’ prices must reflect a January 1, 2003 base period. Also in this section, Bidders must specify the Contract Start Year, the Term of the Proposal, which represents the number of years under which capacity and energy would be provided to PEF by the Bidder, the Winter Contract Capacity, and the Summer Contract Capacity. Based on these entries in Sheet A, the beginning and ending dates for the corresponding contract years will automatically be displayed in the schedule.

In addition to providing an initial prices for the Fuel Energy pricing component, the Bidder must specify the escalation index to be used for evaluation and payment purposes. This information must be provided in the Escalation Indices Section of the Excel sheet. The Bidder can select a predefined index, or the Bidder can specify an alternative fixed escalation rate. The predefined indices which the Bidder may choose are listed in Section III, along with their current standard escalation assumptions at the time Section III was prepared. These assumptions are based on recent forecasts for the indices; however, PEF reserves the right to update these forecasts during the evaluation period if they no longer reflect PEF’s current expectations for the indices. Excel will automatically compute and display, in the right-most column of this section, the standard escalation for a particular pricing component based on the Bidder’s entries and the standard assumptions shown in Section III. The standard escalation value will be used to evaluate the proposal. Bidders will be paid based on the actual values of the index at the time of payment. Once the initial price and escalator has been specified, the annual fuel energy charges will be calculated by Excel and may be viewed by the Bidder in “Schedule 2 Sheet B.”  The Bidder is not allowed to make any entries in this sheet.

To choose from the predefined indices, the Bidder selects the abbreviated code for the selected index, as given in Section III, in the first cell beside the pricing component. Selecting the cell will reveal a drop-down menu from which the index is to be selected.

Next, the Bidder must specify the Frequency of Change for the selected indices for payment purposes. For evaluation purposes, all values will escalate on a contract year basis. To specify the Frequency of Change, the Bidder may select Monthly, Quarterly, Annual, or Never (i.e., the initial price remains constant throughout the term) from the drop-down menus contained in the cells under the “Frequency of Change” heading.

Bidders must enter capacity and transmission charges and non-fuel energy prices in “Schedule 2 Sheet A” for every year of the term of the proposal. For the transmission charge, the Bidder should enter the total price of transmission, accounting for all transmission costs  to PEF’s Delivery Point. Should the PEF transmission system require upgrades as a result of the proposed power flow, these additional costs will be estimated by PEF during the Detailed Evaluation of proposals and included in the evaluation of the proposal. The capacity and transmission charges must be based on the Seasonal Contract Capacities and must be entered as annualized values for every year, including the start year when the proposal does not include all twelve months of the calendar year. Bidders will be paid monthly based on the product of the Seasonal Contract Capacity and one-twelfth (1/12) of the Bidder-specified annual capacity and transmission charges, and will be subject to adjustments based on the actual availability of capacity under the contract.

Bidders of System Power Proposals must guarantee 100% availability for the capacity and energy offered to PEF. In addition to receiving reduced capacity and wheeling payments, Bidders that fail to achieve 100% availability will be charged the cost of replacement capacity and energy. PEF prefers proposals that, when curtailments are necessary, curtail delivery only on a pro-rata basis simultaneously and proportionately along with the Bidder’s other firm sales, including primary public service obligations.

All costs to be paid by PEF must be reflected in the proposed pricing. PEF will not accept any charges other than those identified in Schedule 2A.

Finally, Bidders should include back-up sheets (labeled by the Bidder as Exhibit 2.1) which clearly describe their pricing proposals in terms of the pricing components and the index proposed to adjust the prices.

- 4.	Other Contract Flexibility Provisions

Also pursuant to Section III.E of the Solicitation Document, PEF is encouraging Bidders to offer other contract flexibility provisions. For example, Bidders may propose an initial contract term and provide PEF options to extend the term at predefined prices. If Bidders would like to provide such options, the pricing schedules should be used to convey the prices. The initial term should be entered as the Contract Term, and the extension provisions should be explained in a Bidder-provided Exhibit 2.2. Other flexibility provisions should be also be proposed in a Bidder-provided Exhibit 2.2.

As an alternative to proposing fuel prices, Bidders may propose a fuel tolling arrangement with Progress Energy Florida (see Section K for more information).

- F.	Chapter 3:	Operating Performance

In this chapter of its proposal, each Bidder must demonstrate how its proposal complies with all of the operating performance thresholds and the degree to which it is  consistent with PEF’s preferences for the operational quality evaluation criteria outlined in Section IV.C.4.b of the RFP. In Section II of the Solicitation Document, PEF has provided definitions for several of these operating performance thresholds which will be used to ensure that the Bidder’s generating resource provides PEF with its required level of operating performance. Bidders are required to answer the questions presented in Schedules 3 and 4 and to provide all necessary data to support the assertions made.

In Schedule 3, each Bidder is required to specify the proposed project’s capacity that is being offered to PEF based on the criteria identified below. In addition, the Bidder should specify the elevation at which the unit will be sited.

CAPACITY SPECIFICATION CRITERIA - Summer: 90ºF, 60% R.H. - Winter: 45ºF, 60% R.H.

Capacity must be specified at net generation levels at the Delivery Point. Bidders must complete the Dispatchable Generation Capacity Table shown in Schedule 3 for each season as defined in the table below. In this portion of Schedule 3, values for Contract Year Ending 12/31/2006 are required only if the Bidder is proposing a contract start date prior to January 1, 2007. Bidders should enter values in the last column of the table only if the proposed capacity increases after 12/31/2007.

| SEASONAL DEFINITIONS |  |
| --- | --- |
| Summer | Winter |
| May through October | November through April |

Each Bidder must specify in Schedule 3 the proposed project’s heat rate information for the proposed primary fuel and secondary fuel. The heat rate data must be provided by specifying seasonal capacity states and heat rates for each fuel. The heat rate data provided will be used for both evaluation and contract purposes. Heat rates must be expressed in terms of the higher heating value of the fuel. Heat rates must incorporate any margin for degradation during the term of the contract.

In Schedule 4, the Bidder must provide responses to all items that apply to the type of proposal being offered. Answer yes or no for each Operating Performance threshold by entering an “X” in the appropriate box for each item in the first part of Schedule 4. In the second part of Schedule 4, Bidders must provide operating performance evaluation criteria responses and outage information.

- G.	Chapter 4:	Permitting Plans [New Unit Proposal]

In this chapter of its proposal, each Bidder should demonstrate how its proposal complies with all of the permitting and siting thresholds and minimum evaluation requirements and the degree to which it is consistent with PEF’s preferences for a high level of certainty that the proposed project will receive its required permits within the time indicated on the project’s critical path schedule. Each Bidder is required to answer the questions presented below in the appropriate sections of its proposal and provide all necessary data to support these assertions. For sections that require responses to several bullet items, the Bidder must always precede its response with the bullet item, verbatim, as shown below.

Section

4.0	In Schedule 5, the Environmental and Regulatory Permit Status Schedule, identify which items would be required for the project to be constructed and operated by placing an “X” in the “Not Required” or “Required” column by each item. Provide a critical path schedule for each of the required items. If a permit has been applied for, indicate the date that the permit was applied for in the column marked “Applied For” and the date that the permit is likely to be issued in the column labeled “Expected Receipt.”  Some of the required items are pre-printed in Schedule 5. However, if additional permits would be required, add them to the schedule in the blank cells provided.

In a separate attachment labeled Exhibit 4.0, the Bidder should indicate why the project is likely to receive each required permit, license, or approval.

4.1	Provide specific information for the project site as identified below. Label all attachments for this section of the proposal as Exhibit 4.1.

- List any new rights-of-way required for the project for fuel pipelines, rail spurs, roadways, or electric transmission lines.

- Identify the total acreage of wetlands on the proposed site or rights-of-way before and after construction and the acreage disturbed, lost, or converted during construction.

- Provide a copy of a map showing any portions of the proposed site or rights-of-way that are in a local or state designated Coastal Zone Management Area (CZMA).

- Provide evidence that the existing zoning for the site is compatible with the proposed use and, if not, provide a plan for changing the zoning.

- Provide evidence that a Phase I Environmental Assessment has been completed and that the proposed site or rights-of-way are not contaminated. If the proposed site or rights-of-way are contaminated, indicate the clean-up measures planned, their estimated costs, schedules for completion, and status of reviews by appropriate federal or state agencies.

- Identify any environmentally sensitive areas (i.e., wetlands, water use caution areas, state lands (including submerged), CZMA, wildlife refuge, public parks, critical habitats for endangered species) within a one-mile radius of the proposed plant location and any mitigation measures for these areas.

- Identify any sites of historical or archaeological significance within a one-mile radius of the proposed plant location and any mitigation measures for these areas.

4.2	Describe the current and recent past land use and development of the site and adjacent lands, discussing the compatibility of the project with adjacent and nearby land uses.

4.3	Provide a waste disposal plan for the proposed project which identifies the solid or hazardous wastes that would be generated by the project and identifies how they would be disposed.

4.4	Indicate the quantity and source of cooling, injection, steam make-up, and general use water that would be needed for the project. This information should include the characteristics of the water to be used, necessary treatment processes, and a discussion of competing uses for the water.

4.5	Provide the following information concerning the wastewater generated by the project:

- The sources, composition, and expected quantity of wastewater to be generated by the project, the disposal method to be employed, including any waste treatment methods, and the water composition after treatment.

- The classification of any surface waters or groundwaters to which wastewater effluent is discharged and the name of the surface water.

4.6	Please describe any hydrologic alterations, (e.g., dredging, filling, diking, outfall structure, or impoundment) of any surface waters that would be required by the project, identifying the affected resource, the significance of the alteration, and the mitigation measures proposed.

4.7	Provide the following information regarding the impact of the project on the air quality of the surrounding area:

- Identify the air quality management area where the project would be located and indicate the attainment status of this area for each of the criteria pollutants.

- Identify whether there are any Class 1 areas within 100 kilometers of the proposed project site. If so, indicate whether any visibility modeling has been performed and the visibility impacts on the Class 1 areas projected by the model.

- Indicate the removal efficiency of any pollution control equipment that would be employed for NOx, SO2, PM, CO, Hg, or other hazardous air pollutants (HAPs).

- Complete Schedule 6, the Air Emissions Schedule, for both the primary and secondary fuel.

- If BACT or LAER would apply to the project, indicate how the Bidder proposes to comply with these requirements.

- Describe plans for obtaining any required offsets and allowances for the project.

- Address levels of NH3 (ammonia) emissions and requirements for handling/storage, if used.

  - Indicate the expected incremental ambient noise level during the daytime and nighttime hours that would result from the operation of the project at the nearest property boundary and any planned mitigation measures. Also, indicate the distance of the nearest residence from the project and define the expected daytime and nighttime ambient noise levels at the nearest residence.

- H.	Chapter 5:	Engineering and Design Plans

In this chapter of the proposal, the Bidder should demonstrate how its proposal complies with all of the engineering and design thresholds. The Bidder is required to provide the information requested below and all data necessary to support the assertions made.

Section

5.0	Provide an operations and maintenance plan (O&M Plan) which demonstrates that the project will be operated and maintained in a manner to allow the project to satisfy its contractual commitments. This O&M Plan should indicate proposed project staffing levels, the schedule for major maintenance activities, plans for inspecting and testing of major equipment, entities responsible for operating and maintaining the project, and status and schedule for securing a maintenance agreement. [New Unit Proposal, Existing Unit Proposal]

5.1	Provide a preliminary engineering design plan that identifies the following: [New Unit Proposal, Existing Unit Proposal]

- generation technology, including the make/model/supplier’s name

- emission control equipment, including the make/model/supplier’s name

- major equipment to be employed, including the make/model/supplier’s name

- major equipment vendors

- whether new or refurbished equipment will be used

- commercial in-service date [Existing Unit Proposal only]

  - Provide historic operating performance data (heat rate, EFOR, summer and winter MDC, number of starts) for the project that demonstrate the proposed project will be able to achieve the operating targets specified. [Existing Unit Proposal]

Provide historic operating performance data (heat rate, EFOR, summer and winter MDC, number of starts) for projects of similar technology that demonstrate that the proposed technology will be able to achieve the operating targets specified. [New Unit Proposal]

5.3	Provide a heat and material balance diagram. [New Unit Proposal]

5.4	Provide a plot plan showing the layout of the proposed project. [New Unit Proposal]

  - Specify any limitations the proposed project will have regarding the start-up fuel system. If the project has or will have a secondary fuel, please specify whether the project will be able to start on either fuel independent of other fuel systems being completely out of service. Please specify whether the project will be able to switch “on the fly.” [New Unit Proposal, Existing Unit Proposal]

5.6	Provide the following projected unit performance information: [New Unit Proposal, Existing Unit Proposal]

- Equivalent Forced Outage Rate (EFOR)

EFOR		=	[(FOH + EFDH)/(FOH + SH)]

Where:

FOH		=	Forced Outage Hours: The sum of all hours experienced during forced outages.

EFDH		=	Equivalent Forced Derated Hours: The summation of the products of the Forced Derated Hours (FDH) and size (MW) of reduction for each event, divided by the Seasonal Contract Capacity (SCC).

FDH		=	Forced Derated Hours: The number of hours experienced during a forced derated event.

SH		=	Service Hours: The total number of hours a unit was electrically connected to the transmission system.

- Equivalent Availability Factor (EAF)

EAF  =  [(AH - (EUDH + EPDH)) / PH]

Where:

AH		=	Available Hours: Period Hours (PH) less Planned Outage Hours (POH), Forced Outage Hours (FOH) and Maintenance Outage Hours (MOH).

PH		=	Period Hours: Number of hours in the period (month).

POH		=	Planned Outage Hours: The sum of all hours experienced during planned outages and planned outage extensions.

FOH		=	Forced Outage Hours: The sum of all hours experienced during forced outages.

MOH		=	Maintenance Outage Hours: The sum of all hours experienced during maintenance outages and maintenance outage extensions.

EUDH		=	Equivalent Unplanned Derated Hours: The summation of the products of Unplanned Derated Hours (UDH) and size (MW) of reduction for each event, divided by Seasonal Contract Capacity (SCC).

UDH		=	Unplanned Derated Hours: The number of hours experienced during a forced derated event, a maintenance derated event, or scheduled derated extension of a maintenance derated event.

EPDH		=	Equivalent Planned Derated Hours: The summation of the products of the Planned Derated Hours (PDH) and size (MW) of reduction for each event, divided by the Seasonal Contract Capacity (SCC).

PDH		=	Planned Derated Hours: The number of hours experienced during planned derated event or scheduled derated extension of a planned derated event.

- I.	Chapter 6:	Site Control [New Unit Proposal, Existing Unit Proposal]

In this chapter of the proposal, the Bidder should demonstrate how its proposal complies with the site control thresholds. Bidders are required to provide the information requested below and all necessary data to support the assertions made.

Section

6.0	Provide a USGS map (7.5 minute scale) that indicates the project site location, identifies all generation, substation, and other equipment, and all new rights-of-way that would be required for the project, including critical dimensions. Show proximity to and identify the nearest PEF substation and/or transmission line.

6.1	Demonstrate site control either in the form of an agreement demonstrating ownership of the site, lease of the site for the term of the proposal, or at a minimum, an executed letter of intent to negotiate a lease for the site for the full contract term or term necessary for financing (whichever is greater) or to purchase the site. Provide a copy of a letter of intent or contract that demonstrates that the Bidder’s proposal satisfies PEF’s site control threshold. If the property is fee owned, a copy of the Title and Legal Description of the property is required.

6.2	If off-site rights-of-way are required for gas, electrical, or rail service, demonstrate site control either in the form of an executed letter of intent to negotiate a lease for the rights-of-way for the full contract term or term necessary for financing (whichever is greater) or to purchase the rights-of-way.

- J.	Chapter 7:	Transmission Plan

In this chapter of the proposal, the Bidder should demonstrate how its proposal complies with the transmission threshold. Bidders are required to provide the information requested below and all necessary data to support the assertions made.

Section

7.0	If the proposed project or power source is located outside of PEF’s control area, provide a transmission plan that identifies the project’s proposed transmission path, including delivery point. Also provide evidence that the host utility and all wheeling utilities are willing to grant PEF the right to schedule the output of the unit. Identify the PEF interface utility that would be used to deliver the power to PEF.

7.1	For projects located within PEF's control area, Bidders are required to complete the Network Resource System Impact Study Data Request Form (Schedule 7, Sections I and II) and provide all the information identified in that form. For Bidder's that submit proposals in which a Generator Interconnection Study Request has already been submitted, the following information may be submitted as an alternative to completing the Network Resource System Impact Study Data Request:

- OASIS IR Queue priority date,

- Generator capacity (MW),

- Interconnection point,

- Status of the Interconnection Request.

Note: Submitting the Network Resource System Impact Study Data Request Form does not imply Generator Interconnection queue position nor does this process imply deliverability rights.  Generators wishing to establish queue position must submit an official Interconnection Request (IR) as outlined at the floasis.siemens-asp.com web site (see the PEF FLOASIS Home Page).  Deliverability can only be obtained by making a Transmission Service request (see the PEF FLOASIS Home Page). [New Unit Proposal, Existing Unit Proposal]

- K.	Chapter 8:	Fuel Supply and Transportation Plan

In this chapter of the proposal, the Bidder should demonstrate how its proposal complies with the fuel supply and transportation plan threshold and the degree to which it is consistent with PEF’s requirements for a reliable fuel supply for the proposed project. Bidders are required to provide a preliminary fuel supply plan and all necessary data to support the assertions made regarding this plan. [New Unit Proposal, Existing Unit Proposal] Bidders interested in having PEF provide fuel tolling services should complete Section 8.1 rather than Section 8.0.

Section

8.0	The preliminary fuel supply plan for both primary and secondary fuels must specify or provide the information listed below.

- Provide a map of the fuel supply and transportation infrastructure for the proposed project and a description of supply and transportation alternatives available to the project. If natural gas is proposed as a fuel (primary or secondary), identify the proposed main pipeline source, the length of any lateral from the main pipeline to the site, and the size and pressure of the lateral. If oil is proposed as a fuel (primary or backup), provide the fuel quality requirements, proposed on-site storage capacity (total usable volume and number of tanks), the proposed transport means to the site, and the distance from the expected supply source.

- Provide copies of all fuel supply and transportation agreements in place for the proposed project. If fuel supply and transportation contracts are not in place, provide a description of the types and quality of service for fuel supply and transportation sought, the pricing and operational requirements, the contract terms and conditions required, and the status of such arrangements including the date that such arrangements will be in place. If the Bidder has received proposals from fuel and transportation providers, the Bidder should include the preferred proposal as well as a description of the experience of the Bidder in developing similar supply arrangements.

- Specify the criteria that would be used to select the ultimate fuel supplier and transportation service providers.

- If a secondary fuel is to be used, provide supporting information for the periods over which the primary and secondary fuel supply are expected to be used.

- Indicate whether transportation would be provided from existing capacity or whether new construction would be required. If new construction is required, provide an assessment of  the availability of rights-of-way.

- If natural gas is being proposed, indicate the required gas pressure for the proposed project and confirm the capability of the pipeline to deliver natural gas to the project at or above that pressure.

- If natural gas is being proposed, indicate the amount of fixed pipeline demand/reservation (in mmBtu per day) on which the pricing is based.

8.1	Progress Energy Florida is willing to consider tolling proposals. If the Bidder is interested in Progress Energy Florida providing fuel tolling services, the following information must be included in its proposal:

- Provide a map of the fuel supply and transportation infrastructure for the proposed project and a description of supply and transportation alternatives available to the project. If natural gas is proposed as a fuel (primary or secondary), identify the proposed main pipeline source, the length of any lateral from the main pipeline to the site, and the size and pressure of the lateral. If oil is proposed as a fuel (primary or backup), provide the fuel quality requirements, proposed on-site storage capacity (total usable volume and number of tanks), the proposed transport means to the site, and the distance from the expected supply source. [New Unit Proposal, Existing Unit Proposal]

- If a secondary fuel can be used, provide information for the periods over which the primary and secondary fuel supply are expected to be used. [New Unit Proposal, Existing Unit Proposal]

- [Existing Unit Proposals]

- The name of gas pipeline(s) with which the project is interconnected

- Location of the interconnection/meter

- Flow capability of each meter at the plant and the pressure requirement

- The name of the Operator Account

- Specify whether there are other units at the site that serve other customers such that a balancing agreement would need to be developed with a third party.

[New Unit Proposals]

- The name of gas pipeline(s) with which the project will be interconnected

- Location of the proposed interconnection/meter

- Specify whether the facility will serve only PEF such that the meter could be added to PEF’s Operator Account.

- L.	Chapter 9:	Project Financing Plan

The Bidder is required to provide evidence that the project is financially viable and that the project will likely be able to attract funds from investors and lenders. In this section of the proposal, the Bidder should demonstrate how its proposal complies with the project financial viability threshold and the degree to which it is consistent with PEF’s preferences for proposals for which the Bidder is able to demonstrate that there is a high likelihood of the project securing funding. Bidders are required to provide the information requested below and all necessary data to support the assertions made.

Section

9.0	The financing plan must specify or provide the following: [New Unit Proposal]

- The projected cost of  the project, broken down into the following major cost elements:

Equipment

Generation facilities

Transmission Interconnection facilities

Fuel facilities (e.g. pipeline interconnection, oil storage tanks, rail spurs)

EPC Contractor

Contingency

Licensing, permits and site certificates

Interest During Construction

Other Costs.

- How the proposed project would be financed, including likely lenders and investors, the terms under which funds would be provided, and the respective percentage of funding represented by debt and equity.

- The timing for securing financing.

- A description of the project from a legal and financial standpoint indicating the actual ownership structure, the entities that will have ownership interests and their percentage interests in the project, their responsibilities for the development of the project, and their responsibilities for funding of project development expenses.

- Provide documentation demonstrating the relevant experience of the Bidder (or partner responsible for securing financing) in obtaining financing for other power generation projects.

9.1	The Bidder is required to provide sufficient financial information to enable PEF to assess the financial strength and credit of the entity that would execute a contract with PEF. Subsidiaries or affiliates of companies that desire that the project’s viability be judged based on a parent company or affiliated company must indicate the extent to which the parent or affiliate will provide financial guarantees for the proposed project and under what circumstances it would do so. To enable PEF to make such an assessment, Bidders are required to provide the following information:

- For publicly traded companies, provide copies of annual reports and Form 10-Ks for the two most recent years. For privately held companies, provide copies of audited financial statements, including, at a minimum, income statements, balance sheets, cash flow statements, and notes to financials for the two most recent years.

- Dunn and Bradstreet identification number credit rating of the Bidder’s senior unsecured debt securities.

9.2	The Bidder is required to include a discussion of the potential for increases or decreases in PEF’s cost of capital and any competitive advantage the Bidder’s financing arrangements may give the Bidder.

  - For proposals that will be seeking to obtain project financing, Bidders are required to provide full project financial pro formas that supply, at a minimum, the information outlined in Schedule 8, Financial Pro Forma Schedule, for the proposed financing term. For purposes of completing this pro forma, Bidders should assume an appropriate project capacity factor for the technology being proposed (10% for peaking duty, 50% for intermediate duty, and 80% for baseload duty). Actual project capacity factors will vary. The assumed capacity factor is used only to review the project’s financial viability as indicated by the Bidder’s financial pro formas. Progress Energy Florida reserves the right to request project pro formas from all short-listed proposals.

- M.	Chapter 10:	Commercial Operation Date Certainty

The Bidder is required to demonstrate that its New Unit Project will be able to achieve the  December 1, 2007 commercial operation date requirement. As part of this demonstration, the Bidder is required to provide a critical path diagram and schedule for the project that conforms to the requirements specified below. Progress Energy Florida will evaluate the reasonableness of the following aspects of the Bidder’s proposed schedule: permitting, securing the project site, fuel supply and transportation arrangements, engineering design, equipment procurement, project financing, project construction, and start-up and testing. Progress Energy Florida’s evaluation will consider the evidence presented by the Bidder that the proposed schedule for each of these project elements is reasonable. For the purposes of developing this schedule only, the Bidder should assume that contract negotiations are finalized by July 26, 2004. However, specifying this date should not be construed as a commitment by PEF to finalize contract negotiations by this date.

Section

10.0	Provide a critical path diagram and schedule for the project that specifies the critical path for each of the elements of the project development cycle including but not limited to, the following: permitting, securing the project site, fuel supply and transportation arrangements, engineering design, equipment procurement, construction and permanent financing, project construction, and start-up and testing. [New Unit Proposal]

10.1	Complete Schedule 9, the Project Milestone Schedule, which will be included as part of an executed contract. [New Unit Proposal]

10.2	The Bidder should provide a summary of its current and planned electric power resources including such information as the source of supply, contract terms, and accessibility to the PEF system. For proposals that require new resources be built to maintain a reliable supply on the host system, Bidders are required to state the type of capacity to be built and provide evidence that the required construction can be completed in time to maintain a reliable supply. [System Power Proposal]

10.3	If the proposed project will be providing steam or electricity to a host customer, indicate the name of the entity to whom this service will be provided, the type and amount of energy to be provided, and the status of negotiations regarding the terms and conditions under which such service will be provided, including appropriate documentation of such contracts. [New Unit Proposal, Existing Unit Proposal]

- N.	Chapter 11:	Bidder Experience

The Bidder is required to provide evidence regarding its relevant experience in developing projects that are of an equivalent size and technology. Progress Energy Florida will evaluate each Bidder’s relevant experience in six areas: permitting, engineering, financing, fuel procurement, project construction, and operations and maintenance, including environmental compliance. For proposals that rely on a project team composed of more than one firm to develop the project, the Bidder should indicate its relevant experience in working with other team members to develop projects.

Section

- Provide for at least five comparable projects a project reference not affiliated with the Bidder. For each reference, specify a contact name, title, company, address, and phone number.

For each project, indicate the utility or company served and provide a description of the project, including project location, the size and type of project, the scheduled and actual in-service date, and the availability factor achieved. [New Unit Proposal, Existing Unit Proposal]

11.1	For each of the project participants, provide an experience statement which lists the relevant experience of the firm, including other projects of a similar type, size, and technology. Describe the experience in the following six areas: permitting, engineering, financing, fuel procurement, project construction, and operations and maintenance, including environmental compliance. [New Unit Proposal, Existing Unit Proposal]

11.2	Provide documentation regarding the contractual relationship between the Bidder and all additional project participants and vendors. If this contractual relationship has not been finalized, specify the schedule for doing so. [New Unit Proposal]

  - Indicate if the Bidder has failed to perform under any contracts or agreements for power supplies. If so, please explain.

  - Provide a summary of current litigation activity related to (1) provision of energy products and services (fuel, power, ancillary services, engineering, on-site services); (2) lease option arrangements for assets; (3) purchases of energy products and services (as above); or (4) industrial construction projects (power plants, industrial plants, cogeneration facilities, etc.).

- O.	Chapter 12:	Acceptance of the Key Terms and Conditions [New Unit Proposals, Existing Unit Proposals]

Bidders willing to accept PEF’s Key Terms and Conditions (Attachment A to RFP Solicitation Document) without exceptions should indicate this in their proposals. Bidders with exceptions to the Key Terms and Conditions should indicate all exceptions in list form. Each exception should be clearly described, the requested change clearly identified, and the associated paragraph and page number from the Key Terms and Conditions indicated. Bidders that desire to provide a red-lined version may do so using the Word version that was included in the RFP Package. Red-lined versions of the Key Terms and Conditions should be accompanied by a textual discussion which reviews the reason for the exception.

- III. 	Progress Energy Florida Approved Price Indices

INDICES	Gas:	Inside FERC’s Gas Market Report or Gas Daily Price Guide.

Oil:	Platt’s Oilgram or Oil Buyer’s Guide.

Coal:	Bidder to propose index subject to review by PEF.

| Index | Code | Standard Escalation Assumption (% per year) |
| --- | --- | --- |
| Inside FERC’s Gas Market Report | GAS1 | see Esc Assump Excel sheet in Response Package |
| Gas Daily Price Guide | GAS2 | see Esc Assump Excel sheet in Response Package |
| Platt’s Oilgram | OIL1 | see Esc Assump Excel sheet in Response Package |
| Oil Buyer’s Guide | OIL2 | see Esc Assump Excel sheet in Response Package |
| Coal Index | COAL1 | see Esc Assump Excel sheet in Response Package |