BEFORE THE FLORIDA PUBLIC SERVICE COMMISSION

SUPPLEMENTAL TESTIMONY OF PAUL HOORNAERT

ON BEHALF OF

FLORIDA MUNICIPAL POWER AGENCY

JEA
REEDY CREEK IMPROVEMENT DISTRICT

AND

CITY OF TALLAHASSEE

DOCKET NO. 060635

DECEMBER 26, 2006

Q.	Please state your name and business address.

# A.	My name is Paul Hoornaert.  My business address is 55 East Monroe Street, Chicago, IL, 60603.

# Q.	By whom are you employed and in what capacity?

- I am employed by Sargent & Lundy, LLC as a Senior Project Manager, Fossil Power Technologies.

# Q.	Have you previously submitted testimony in this proceeding?

A.	Yes.

Q.	What is the purpose of your supplemental testimony?

A.	The purpose of my testimony is to provide updated capital cost estimates for the TEC project.

Q.	Are you sponsoring an exhibit with your testimony?

A.	Yes.  I am sponsoring Exhibit No. ___ (PH-1R), which provides an update to the capital cost estimate summary included in Table A.3.5 in Section A.3.0 of the TEC Need for Power Application (Exhibit No. __ (TEC-1).

Q. 	Have you developed updated capital cost estimates for the TEC?

A. 	Yes.  In light of changing market conditions observed nationwide, we have updated the TEC capital cost estimates to account for market impacts on the costs of major equipment and labor.  We also have included cost estimates for mercury controls and certain additional items that the TEC Participants have selected since the filing of my original testimony.  We also have adjusted the initial Community Contribution to account for changes in the structure of the contribution that were agreed upon with Taylor County after my pre-filed testimony was submitted.

Q. 	How do the updated costs compare to the cost estimates presented in your pre-filed testimony?

A. 	 As shown in Table A.3-5 of the TEC Need for Power Application, Exhibit No. __ (TEC-1), the total capital costs for the TEC were originally estimated to be $1,713,399,000 in 2012 dollars.  (My pre-filed testimony included a typographical error on page 7, line 5, which states that the cost estimates were $1,743,399,000).  As shown in Exhibit No. __ (PH-1R), which presents an Updated Table A.3-5 of Exhibit No. __ (TEC-1), as a result of market impacts and scope changes discussed above, the updated cost estimate is $2,039,074,000, which reflects an increase of approximately 19.01 percent from the original estimate.

Q.	Why does your updated cost estimate include costs for mercury controls?

A.	As stated in my pre-filed testimony, mercury emissions from the TEC will be reduced through the co-benefits of selective catalytic reduction (SCR), flue gas desulfurization (FGD), and a wet electrostatic precipitator (WESP).  Because mercury controls for electric generation plants are relatively untested, however, it is possible that additional controls may be necessary to comply with the second phase of the Clean Air Mercury Rule (CAMR) discussed in pre-filed testimony of Mr. Rollins.  For that reason, the TEC Participants have agreed to install additional controls if necessary to achieve a 90% reduction in TEC mercury emissions by 2018, when CAMR’s second phase begins.  Although the TEC Participants will implement a research program to determine if SCR/FGD/WESP or other more cost-effective controls can achieve this level of reduction, we have assumed that the only currently available mercury-specific control, activated carbon injection (ACI), will be installed.  My updated capital cost estimate assumes that costs for ACI (approximately $40,000,000) will be incurred when the plant is constructed even though the TEC Participants anticipate that additional mercury controls, if any, will not be needed until the second phase of CAMR.

Q.	Does this conclude your rebuttal testimony?

A.	Yes.

| UPDATED Table A.3-5 Updated Capital Cost Estimate Summary |  |
| --- | --- |
| Description |  |
| Base Estimate | $1,704,378,000 |
| Owner’s Costs | $138,762,000 |
| Land | $19,440,000 |
| Community Contribution Lump Sum | $17,000,000 |
| Owner’s AFUDC (1) | $159,494,000 |
| Total Installed Cost – May 2012 COD | $2,039,074,000 |
| (1)AFUDC calculated based on all components of capital cost estimate, including the base estimate, owner’s costs, land, and community contribution. |  |