174

1                              BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

DOCKET NO. 090009-EI

3       In the Matter of:

4       NUCLEAR COST RECOVERY CLAUSE.

______________________________/

5

6

7

8

9                               VOLUME 2

10                        Pages 174 through 448

11              ELECTRONIC VERSIONS OF THIS TRANSCRIPT ARE

A CONVENIENCE COPY ONLY AND ARE NOT

12               THE OFFICIAL TRANSCRIPT OF THE HEARING,

THE .PDF VERSION INCLUDES PREFILED TESTIMONY.

13

14       PROCEEDINGS:        HEARING

15       COMMISSIONERS

PARTICIPATING:      CHAIRMAN MATTHEW M. CARTER, II

16                           COMMISSIONER LISA POLAK EDGAR

COMMISSIONER KATRINA J. McMURRIAN

17                           COMMISSIONER NANCY ARGENZIANO

COMMISSIONER NATHAN A. SKOP

18

DATE:               Tuesday, September 8, 2009

19

PLACE:              Betty Easley Conference Center

20                           Room 148

4075 Esplanade Way

21                           Tallahassee, Florida

22       REPORTED BY:        LINDA BOLES, RPR, CRR

Official FPSC Reporter

23                           (850) 413-6732

24       APPEARANCES:        (As heretofore noted.)

25

FLORIDA PUBLIC SERVICE COMMISSION

175

1                              I N D E X

2                              WITNESSES

3

NAME:                                           PAGE NO.

4

5       STEVEN D. SCROGGS

6       Continued Cross Examination by Mr. Moyle          178

Redirect Examination by Mr. Anderson              199

7

8       RAJIV KUNDALKAR

9       Direct Examination by Mr. Anderson                207

Prefiled Direct Testimony 3-2-09 Inserted         210

10       Errata Sheet to Prefiled Direct 3-2-09 Inserted   242

Prefiled Direct Testimony 5-1-09 Inserted         243

11

STEVEN R. SIM

12

Direct Examination by Ms. Cano                    270

13       Prefiled Direct Testimony 5-1-09 Inserted         273

14       WINNIE POWERS

15       Direct Examination by Mr. Rubin                   301

Prefiled Direct Testimony 3-2-09 Inserted         305

16       Errata Sheet to Prefiled Direct 3-2-09 Inserted   328

Prefiled Direct Testimony 5-1-09 Inserted         329

17       Errata Sheet to Prefiled Direct 5-1-09 Inserted   348

Cross Examination by Mr. Moyle                    351

18       Cross Examination by Mr. Young                    353

19       JOHN J. REED

20       Direct Examination by Ms. Cano                    355

Prefiled Direct Testimony 3-2-09                  358

21       Errata Sheet to Prefiled Direct 3-2-09 Inserted   412

Prefiled Direct Testimony 5-1-09 Inserted         413

22       Cross Examination by Mr. Davis                    438

23

24       CERTIFICATE OF REPORTER                           448

25

FLORIDA PUBLIC SERVICE COMMISSION

176

1                              EXHIBITS

2       NUMBER:                                 ID.    ADMTD.

3       4                                                 203

4       5                                                 203

5       6                                                 203

6       7                                                 203

7       8                                                 203

8       9                                                 203

9       10                                                203

10       11                                                203

11       12                                                203

12       13                                                203

13       14                                                203

14       15                                                203

15       16                                                203

16       17 RSK-1 3/09                           209       270

17       18 RSK-2 3/09                           209       270

18       19 RSK-3 3/09                           209       270

19       20 RSK-4 3/09                           209       270

20       21 RSK-5 3/09                           209       270

21       22 RSK-1 5/09                           209       270

22       23 RSK-2 5/09                           209       270

23       24 RSK-3&4 5/09                         209       270

24       25 RSK-5 5/09                           209       270

25       26 RSK-6 5/09                           209       270

FLORIDA PUBLIC SERVICE COMMISSION

177

1                              EXHIBITS

2       NUMBER:                                 ID.    ADMTD.

3       27 RSK-7 5/09                           209       270

4       28 RSK-8 5/09                           209       270

5       29 RSK-9 5/09                           209       270

6       30 SRS-1                                272       300

7       31 SRS-2                                272       300

8       32 SRS-3                                272       300

9       33 SRS-4                                272       300

10       34 SRS-5                                272       300

11       35 WP-1 3/09                            304       355

12       36 WP-2 3/09                            304       355

13       37 WP-3 3/09                            304       355

14       38 WP-1 5/09                            304       355

15       39 WP-2 5/09                            304       355

16       40 JJR-1 3/09                           357

17       41 JJR-2 3/09                           357

18       42 JJR-3 3/09                           357

19       43 JJR-1 5/09                           357

20       132                                               205

21       133                                               206

22       134                                               206

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

178

1                         P R O C E E D I N G S

2                 (Transcript follows in sequence from Volume

3       1.)

4                     CROSS EXAMINATION CONTINUED

5       BY MR. MOYLE:

6            Q.   Could these other entities, Shaw and Bechtel,

7       have provided the preliminary engineering drawings that

8       you sole sourced to Black & Veatch?

9            A.   They were qualified to do so.  Bechtel is

10       engaged in our project assisting with the combined

11       operating license, and Shaw is engaged with us in

12       concert with Westinghouse doing specific detailed

13       engineering work around the nuclear reactor and, and

14       power island.  So all three entities are being engaged

15       to some level on the project and gaining familiarity.

16            Q.   Don't you think that with respect to the

17       preliminary engineering work that you would have gotten

18       a better price if you had said to the three firms that

19       are eligible and capable of providing that and say,

20       okay, here's what we want, everybody sharpen your

21       pencil, as compared to sole sourcing it to Black &

22       Veatch?

23            A.   No.  In fact, our sole source justification

24       goes through a process where we look at the rate sheet

25       for Black & Veatch/Zachry and compare that to the rate

FLORIDA PUBLIC SERVICE COMMISSION

179

1       sheet for, I believe it's Bechtel.  And in doing so, we

2       saw that a properly weighted comparison would show Black

3       & Veatch/Zachry to be about 14.5 percent more

4       competitive on their standard rate sheet than Bechtel.

5       So in doing so, we've accomplished the critical analysis

6       that we need to to demonstrate that Black & Veatch is

7       providing market, you know, qualified services at market

8       rates.

9            Q.   Isn't it true that when, you have seen

10       historically when competitive bidding is used that there

11       are deviations from standard rate sheets that companies

12       will submit?

13            A.   That's a possibility.

14            Q.   Who, who approved the sole source of the

15       preliminary engineering?

16            A.   I believe it was approved by Martin Gettler.

17            Q.   And what position does he hold?

18            A.   He's a Vice President of New Nuclear Projects.

19            Q.   I want to ask you a couple of questions about

20       this exhibit.  It's Exhibit 131.  It's the confidential

21       exhibit.  I don't want to tread into anything that you

22       all consider confidential.

23                 CHAIRMAN CARTER:  I think that there were a

24       couple of pages that Mr. Anderson said that they were,

25       agreed they were not confidential.  Mr. Anderson, would

FLORIDA PUBLIC SERVICE COMMISSION

180

1       you, as a quick reminder?

2                 MR. ANDERSON:  Page 9 was indicated by counsel

3       for SACE as subject of interrogation.  We had no

4       objection to use of that page or even public use of that

5       one page.

6                 CHAIRMAN CARTER:  Page 9?

7                 MR. ANDERSON:  Yes, sir.

8                 CHAIRMAN CARTER:  Mr. Moyle.

9                 MR. MOYLE:  I'm -- what I would like to do,

10       Mr. Chairman, is just ask him, and I'll refer him to

11       something, and if he considers it confidential, he can

12       answer the question without revealing the content.  If

13       he considers it not confidential, then he can, you know,

14       read it into the record, if that's okay.

15       BY MR. MOYLE:

16            Q.   Page 12, which is the -- tell me, tell me when

17       you're there, if you would.

18            A.   It's in front of me.

19            Q.   Okay.  Do you see the bold language at the, at

20       the top of the sheet before the cost estimate status?

21            A.   Yes.

22            Q.   Is that confidential?

23            A.   No.

24            Q.   Okay.  So the -- before you can get capital

25       cost estimates, you must complete ongoing negotiations;

FLORIDA PUBLIC SERVICE COMMISSION

181

1       that's correct?

2            A.   That's correct.

3            Q.   Okay.  You would agree that feasibility

4       determinations are difficult, not knowing the, you know,

5       the capital cost estimates; correct?

6            A.   What we have done is through the course of

7       negotiations prepared -- or continued to compare

8       preliminary cost estimates provided during these

9       negotiations to our estimates and found those to be well

10       in line.  So while we would not revise our cost estimate

11       until completing a new contract negotiation, we're still

12       maintaining a view to verify that we haven't deviated

13       from our existing cost estimate.

14            Q.   The, on the same page, the bold at the, the

15       bottom, that's not confidential, is it?

16            A.   The third bullet, is that what you're --

17            Q.   Yes, sir.

18            A.   No, it's not.

19            Q.   Okay.  So I wanted to explore for a minute the

20       notion of fixed, firm and float with respect to your,

21       your agreements.

22                 As we sit here today, you say at the end the

23       intent is to lock down known costs, material and labor

24       quantities.  What percentage of the costs are, are fixed

25       or firm or locked down as we sit here today?

FLORIDA PUBLIC SERVICE COMMISSION

182

1            A.   That would be a subject of ongoing

2       negotiations and is not something I can speak to right

3       now.

4            Q.   You can't give me a ballpark of it?

5            A.   It's ongoing negotiations, sir.

6            Q.   So is any, is any of the cost locked down as

7       we sit here today?

8            A.   Again, that'd be the topic of ongoing

9       negotiations.

10            Q.   Let me refer you to Page 31 of this exhibit

11       and ask you if you consider this page confidential and

12       the information contained herein?

13            A.   Yes, I do.

14            Q.   That is confidential?

15            A.   Yes.

16            Q.   Okay.  The, the caption at the top, is that

17       confidential, or can we talk about that?

18            A.   We can talk about that caption.

19            Q.   Okay.  So it says, "Cost comparison of recent

20       AP 1000 project announcements is difficult due to lack

21       of detail."  You would agree with that statement?

22            A.   That's correct.

23            Q.   Where, where did you get the information that

24       is reflected on this exhibit?

25            A.   Most of the information is gleaned from

FLORIDA PUBLIC SERVICE COMMISSION

183

1       publicly -- or all the information is gleaned from

2       publicly available data with certain estimates that I've

3       made based on my knowledge of the process and my

4       estimate of trying to fill in the gaps between public

5       information that may provide us an overnight cost but

6       doesn't provide us a total project cost or costs

7       associated with transmission for a certain project.  Not

8       all media reports are apples to apples.  Many media

9       reports kind of mix and match different components of

10       costs and don't provide a complete understanding.

11            Q.   The -- and I presume the numbers are what you

12       consider confidential, not the, not the descriptions to

13       the left; is that right?

14            A.   That would be correct.

15            Q.   Okay.  So when it says "total overnight cost,"

16       the first bold line there, what does that represent?

17            A.   An overnight cost is a cost estimating tool to

18       indicate what the cost would be in certain year dollars

19       if all the components were able to be purchased at one

20       time.  So all materials, all labor and services

21       presented at one point in time and that, that's the

22       case.

23                 In reality, we experience over a long period,

24       over a period of time for design and construction

25       escalation and the accrual of interest charged on the

FLORIDA PUBLIC SERVICE COMMISSION

184

1       construction balance.

2            Q.   I want to draw your attention to the third

3       column and ask you to compare that number in the third

4       column to the number found in the first column under

5       "total overnight cost."  Do you see that?

6            A.   Yes.

7            Q.   You would agree that that's a pretty wide

8       difference in those two numbers with respect to cost,

9       would you not?

10            A.   And, again, there's a wide difference, but

11       there are three question marks in the column that leads

12       up to the sum of that third column, and that's where

13       there's insufficient information for us to provide a

14       very detailed breakdown of what's causing those charges.

15            Q.   Would, would in your mind the number shown on

16       that third column lead you to question project

17       feasibility?

18            A.   No.

19            Q.   I'm sorry?

20            A.   No.

21            Q.   Do you have an opinion about project

22       feasibility with respect to the third column?

23            A.   No.  I'm here to testify about FPL's project

24       feasibility.

25            Q.   Let me ask you, this presentation was given to

FLORIDA PUBLIC SERVICE COMMISSION

185

1       the Risk Committee.  Who sits on the Risk Committee?

2            A.   The Risk Committee is again an ad hoc group of

3       directors, senior managers in FPL.  It's generally run

4       by the finance department as the business, as the

5       coordinating business unit, and then individuals are

6       chosen as topics arise.  I would not sit on the Risk

7       Committee for a project that I managed or that I was

8       involved in.  It sets up an independent review board

9       that isn't intimately involved in an individual project.

10            Q.   You would agree that with respect to nuclear

11       projects, the disposal of the nuclear fuel is also a

12       risk that's presented; correct?

13            A.   I believe -- I would say it's a, it's a

14       challenge.  But we have approved methods for the

15       existing plants, and those approved methods would apply

16       to new plants.

17            Q.   And the methods are to store the spent fuel

18       rods onsite; is that correct?

19            A.   That's one option.  Yes, sir.

20            Q.   Are there any other, other options at this

21       point in time?

22            A.   There are a number of different options being

23       pursued by Department of Energy.

24            Q.   How about with respect to FP&L?  Is it

25       pursuing any other options other than storing the spent

FLORIDA PUBLIC SERVICE COMMISSION

186

1       nuclear fuel rods onsite?

2            A.   No.  The responsibility for that lies with the

3       Department of Energy.

4            Q.   And they have had a fuel difficulties;

5       correct?

6            A.   They've had their challenges.

7            Q.   There has not been any other construction of a

8       nuclear power plant in the United States that has

9       implemented the strategy that you are pursuing, which is

10       to separate the C from the E and P; correct?  And just

11       so the record is clear, to separate the construction

12       from the engineering and procurement.

13            A.   I believe in the Generation 2 plants, their

14       existing plants, it was not uncommon to have a separate

15       constructor from the engineering and procurement

16       provider.

17            Q.   And, but they were not done by the utility

18       signing a separate contract.  Weren't they part of the

19       overall contract that was signed between a utility and

20       an EPC contractor, and then the EPC contractor would go

21       out and sub the construction work?  Isn't that correct?

22            A.   I believe that's a generalization that I

23       couldn't attest to over the 100 projects that are

24       currently operating in the United States.

25            Q.   You talked with counsel about an offramp

FLORIDA PUBLIC SERVICE COMMISSION

187

1       strategy.  FPL has not yet made a determination as to

2       whether or not to build this nuclear power plant, Turkey

3       Point 6 and 7, has it?

4            A.   We're -- no, we have not made a definitive

5       decision to go to construction, but we have made and are

6       committed to obtaining a license, and then at the

7       appropriate time committing to construction.

8            Q.   When you sign an EPC contract, typically

9       doesn't that take care of, of most of the major

10       components that would be needed with respect to

11       constructing a nuclear power plant?

12            A.   An EPC contract could take many forms, and

13       that's one of the things that we've learned as we've

14       talked with Westinghouse/Shaw that, for example, as

15       we've used EPC contracts to build West County Energy

16       Center 1 and 2 and Turkey Point 5, those are fairly

17       well-known technologies, very competitive environments

18       for services and equipment, and we're able to use that

19       EPC contract to provide a high level of risk management.

20                 But in the nuclear world, in the market that

21       we're in right now, as you mentioned before, the terms

22       firm, fixed and float, it's really critical to

23       understand what's firm and what's not and what's

24       floating and what is not.  And what we're finding is

25       that the distinction between EPC contracts that we have

FLORIDA PUBLIC SERVICE COMMISSION

188

1       been offered and EPC contracts that we are familiar with

2       is dramatically different in nuclear, that the risk

3       mitigation offered by, historically offered by EPC

4       contracts in other forms of generation are not

5       translating to the EPC contracts that we're seeing for

6       new nuclear.

7            Q.   You don't have an EPC contract in place as we

8       sit here today; correct?

9            A.   That's correct.

10            Q.   Okay.  And I -- you've been involved in

11       developing power plants previously; correct?

12            A.   Yes, sir.

13            Q.   And even in the, what they used to call the

14       merchant world or the competitive plant, you had some

15       experience in that arena, did you not?

16            A.   Yes, sir.

17            Q.   Wouldn't you agree that as a general rule of

18       thumb that there are a lot more projects that are

19       announced than are actually built?

20            A.   Yes.

21            Q.   And counsel for SACE showed you a chart about

22       the falloff in nuclear projects following Three Mile

23       Island.  Don't you expect that there's going to be a

24       similar, maybe not as dramatic, but a falloff in nuclear

25       projects from the numbers announced as to those that

FLORIDA PUBLIC SERVICE COMMISSION

189

1       will actually be built in this wave?

2            A.   I think that's a very real possibility.  I

3       think our project approach has been designed to make

4       sure we're not one of those for a bad reason that we got

5       overexposed or for a decision that we weren't in control

6       of.

7            Q.   And given the fact that you're keeping your

8       options open, it's an offramp that projects fall out,

9       you would agree that, that paying cash, 10 million plus

10       dollars to secure a part of the nuclear power plant at

11       this point, that that probably was premature; correct?

12            A.   No.  I don't agree with that at all.  In fact

13       --

14            Q.   And just so the record is --

15            A.   -- we carefully evaluated that and it was

16       heavily scrutinized.  The reasons that we entered into a

17       reservation agreement through Westinghouse with Japan

18       Steel Works is because of their unique position as the

19       sole provider of those heavy, ultra heavy forgings, and

20       that condition has not changed.

21            Q.   So, so there's one supplier in the whole world

22       of these heavy nuclear forgings; is that right?

23            A.   That's correct.

24            Q.   And, and you had to pay $10 million to reserve

25       that, notwithstanding the fact that the expectation is

FLORIDA PUBLIC SERVICE COMMISSION

190

1       there will probably be less nuclear projects going

2       forward than currently announced?

3            A.   When we made the reservation in early 2008, we

4       looked at the best information available, made that

5       decision.  We still stand by that decision.  And in

6       order to remove the likelihood of the project schedule

7       being held up on that one singular item, we felt it wise

8       to invest the 11 million in a reservation fee.  Other

9       areas, long-lead procurement, we were able to defer

10       those costs.

11            Q.   And you were asked to pay another 30 million

12       for certain long-lead item and you elected not to do

13       that; correct?

14            A.   No, sir.  We were not asked.  We went --

15            Q.   Or you considered it?

16            A.   We worked with, we worked with

17       Westinghouse/Shaw to monitor the market and determine if

18       it was necessary.  We determined it was not necessary.

19            Q.   Just a question, I omitted to ask you this,

20       with respect to your EP strategy as compared to the EPC

21       strategy, have you quantified the amount of money that

22       you think you might be able to ultimately save by

23       enabling another engineering firm to become familiar

24       with the AP 1000?

25            A.   We have not done a quantitative analysis.  But

FLORIDA PUBLIC SERVICE COMMISSION

191

1       in competitive environments, as we talked about earlier,

2       looking at the rates between Black & Veatch/Zachry and

3       Bechtel showing a 10 percent difference in rates, if you

4       apply that to the large scale of the construction scope

5       of the contract, 10 percent could be a dramatic savings.

6            Q.   A few more, a few more questions and I think

7       we'll be close to wrapping up.  You're familiar with the

8       testimony of Mr., Mr. Sim; correct?  And you referenced

9       an exhibit that he had put together previously in

10       answering one of my questions; isn't that right?

11            A.   That's correct.

12            Q.   Okay.  In Mr. Sim's testimony, May 1, 2009,

13       he's asked, "What were the results of the 2009

14       feasibility analysis for Turkey Point 6 and 7?"  And he

15       says, "The results of the analysis are presented in

16       Exhibit SRS-5."  That was the exhibit you were referring

17       to; is that right?

18            A.   That sounds correct, subject to check.

19            Q.   Would it help if I showed you a copy of it?

20                 MR. MOYLE:  Could I approach?

21                 CHAIRMAN CARTER:  Yes, you may approach.

22       You're just going to use it for cross-examination

23       purposes; correct?

24                 MR. MOYLE:  That's right.

25                 CHAIRMAN CARTER:  You may proceed.

FLORIDA PUBLIC SERVICE COMMISSION

192

1       BY MR. MOYLE:

2            Q.   Now in reviewing the testimony, I noted that

3       Mr. Sim says this is the feasibility analysis results.

4       Is, is that the extent of the, of the detailed analysis

5       that has been done with respect to the feasibility of

6       this project on a going-forward basis, the information

7       that's reflected on the one-page document, Exhibit 5 to

8       Mr. Sim's testimony?

9            A.   Exhibit 5 is a summary of the economic

10       analysis results.  These results are done in the same

11       deliberate manner as our Ten-Year Site Planning process

12       and require a number of computer models and other

13       simulations to develop.  Yes, sir.

14            Q.   Do you, do you see how -- do you think with

15       respect to a detailed, detailed analysis of the

16       long-term feasibility that a one-pager may not be viewed

17       as significant or sufficient?

18            A.   The -- I think Mr. Sim's testimony, Witness

19       Sim's testimony is pretty complete.  It leverages an

20       analytical process that was vetted before this

21       Commission in 2008 and resulted in an affirmative need

22       determination and maintains the same annual feasibility

23       analysis we conducted last year.  I think it's quite

24       complete.

25            Q.   The -- you're aware that the rating agencies

FLORIDA PUBLIC SERVICE COMMISSION

193

1       have expressed some concerns about the development of

2       nuclear projects?

3            A.   Yes, sir.

4            Q.   Okay.  And you're also aware that one of the

5       things that they have suggested to companies pursuing

6       that is to explore strategic partnerships; isn't that

7       right?

8            A.   I understand.  Yes, sir.

9            Q.   And there are five applications currently

10       involving the technology, the 1000 technology in the

11       country pending before the NRC; is that right?

12            A.   I believe that's correct.  Yes, sir.

13            Q.   Okay.  And two of them are out of the State of

14       Florida; correct?

15            A.   Correct.

16            Q.   Given the, given the -- you've also heard the

17       rating agencies refer to this as a bet-the-farm or

18       bet-the-company proposition with respect to the

19       magnitude of a nuclear plant investment?

20            A.   I've heard the term.

21            Q.   Okay.  Wouldn't you believe that it would be

22       prudent to explore in earnest strategic partnerships to

23       joint venture a nuclear project in the State of Florida?

24            A.   Yes.  Actually I think there's a couple of

25       things there.  You know, we are currently involved in

FLORIDA PUBLIC SERVICE COMMISSION

194

1       discussions with other municipalities or municipal

2       utilities and co-ops in the state.  I personally have

3       hosted two workshops with these utilities to discuss

4       what the form of partnership would be, and more

5       importantly to discuss what value is brought to the

6       table from a partner with FPL.

7                 As you may know, our need determination

8       demonstrated that FPL's customers have the capacity and

9       need for 100 percent of the generation output.  So to

10       dilute that 100 percent output away from our customers

11       to another entity that would be a partner, we'd want to

12       make sure that we carefully and objectively evaluate

13       what the true benefit brought to the partnership by the

14       other party.

15            Q.   You're aware that the population projections

16       for the State of Florida have fallen off recently?

17            A.   Yes.

18            Q.   And if those projections continue, that they

19       could have an impact on your, your needed generation;

20       correct?

21            A.   Yes.  And that's a subject of our annual

22       feasibility review.  And our experience has indicated

23       that those can be temporary.  They're important to

24       watch, but it is not our long-term expectation.

25            Q.   You talked about exploring strategic

FLORIDA PUBLIC SERVICE COMMISSION

195

1       partnerships with some municipalities and co-ops.  Have

2       you explored any strategic partnerships with any other

3       investor-owned utilities in the state?

4            A.   I have not personally been involved in those.

5       But I understand from our management's perspective that

6       those would be entertained and everything is still on

7       the table.

8            Q.   Would, would it be -- to the extent that this

9       Commission found that there was a lack of detailed

10       information with respect to prudency, would a, would a

11       docket which examined the needs of the State of Florida

12       as a whole with respect to nuclear power plants make

13       sense in your mind?

14            A.   I believe that the -- my understanding of the

15       Ten-Year Site Planning process that the Public Service

16       Commission sponsors is one of those areas where both the

17       utilities, or all the investor-owned utilities provide

18       an annual Ten-Year Site Plan that's rolled up by Public

19       Service Commission staff to look at from a statewide

20       view, and that even some commentary from Florida

21       Reliability Coordinating Council on the appropriateness

22       of those issues are provided.  So I think that's being

23       covered.

24            Q.   From a consumer's perspective, you would agree

25       that the costs incurred -- let's say that consumers take

FLORIDA PUBLIC SERVICE COMMISSION

196

1       service from both Florida Power & Light and Progress

2       Energy.  To the extent that you have two utility

3       companies heading down the same track with respect to

4       the same technology, that there potentially could be

5       economies of scale that could be realized to the

6       consumers if a strategic partnership were to be forged;

7       correct?

8            A.   I think those are the very types of benefits

9       that we're looking to identify in our discussions with

10       potential partners.

11            Q.   Okay.  But those discussions have not taken

12       place in any serious manner at this point that you're

13       aware of?

14            A.   I'm serious about everything I do, sir.

15                 MR. MOYLE:  Okay.  Thank you, Mr. Chairman.

16       That's all I have.

17                 CHAIRMAN CARTER:  Thank you.  Commissioners,

18       I'm going to go to staff, unless you have any questions

19       right now.  Then I'll come back to the bench.

20                 Staff?

21                 MR. YOUNG:  No questions.  No questions.

22                 CHAIRMAN CARTER:  Commissioners?  Commissioner

23       Skop, you're recognized.

24                 COMMISSIONER SKOP:  Thank you, Mr. Chairman.

25                 Good morning, Mr. Scroggs.

FLORIDA PUBLIC SERVICE COMMISSION

197

1                 THE WITNESS:  Good morning, sir.

2                 COMMISSIONER SKOP:  Just a quick question on

3       Page 14 of your prefiled testimony, beginning at Line 9.

4       You discuss the internal and external audit of project

5       management controls.  And I think also in your opening

6       summary you mentioned adaptive project management.  Can

7       you briefly explain what deficiencies, if any, or best

8       practices have been implemented as a result of these

9       audits?

10                 THE WITNESS:  Yes, sir.  I'm assuming this is

11       the March 2nd filed testimony?

12                 COMMISSIONER SKOP:  Yes.  Your direct prefiled

13       testimony on, beginning on --

14                 THE WITNESS:  Let me find my place, please.

15                 COMMISSIONER SKOP:  Okay.  All right.  That's

16       fine.  And I'll just repeat the question.  It's Page 14,

17       beginning at Line 9.

18                 THE WITNESS:  Yes, sir.  It's in front of me.

19       Thank you.

20                 COMMISSIONER SKOP:  Okay.  All right.

21                 THE WITNESS:  Yes.  We have a number of

22       internal and external audits that really I see them as

23       helping management make sure that we're doing everything

24       that we need to be doing to demonstrate the prudent and

25       responsible management of the project.  Some of the

FLORIDA PUBLIC SERVICE COMMISSION

198

1       things that we have identified in these processes is

2       documentation of our decision-making process and

3       documentation of some of the more mundane things that

4       could be turned into -- like a checklist for travel, a

5       checklist for certain decisions that are made routinely

6       so that we know and can demonstrate that we're doing

7       things by the book every time instead of relying on, you

8       know, my testimony or some other individual's testimony

9       that, you know, we do it.  Some of the suggestions from

10       these audits have been to increase the documentation.

11                 COMMISSIONER SKOP:  All right.  Thank you.

12       And if I could also turn your attention to Page 17 of

13       your prefiled testimony, generally Lines 15 through 23.

14                 THE WITNESS:  Yes.

15                 COMMISSIONER SKOP:  Okay.  And you discuss the

16       improved processes for sole source procurement.  And,

17       again, I think the Commission last year during this

18       proceeding, some issues arose with respect to the amount

19       of documentation that was resultant from sole source or

20       single source selection.  Can you just briefly discuss

21       the process improvements that FPL has undertaken on a

22       year-to-year basis?

23                 THE WITNESS:  Yes, sir.  Following our reviews

24       last year, we took back and kind of debriefed, you know,

25       what can we do better?  I think one of the presumptions

FLORIDA PUBLIC SERVICE COMMISSION

199

1       that we made in the process of doing sole source

2       justifications was that it was a discussion between a

3       knowledgeable presenter and a knowledgeable receiver.

4       And that was okay for the process, but it didn't leave a

5       good trail to demonstrate all the information that go

6       into decisions like that.  So we decided that we would

7       be more extensive in our description so that a third

8       party could pick up the sole source justification,

9       understand what it meant, understand through plain

10       English the decision process and what was considered to

11       come to that decision.  So we took that on as a, as an

12       effort and an initiative.  We had training with all the

13       project management staff, the process control staff, and

14       then we implemented those changes.  As new sole source

15       or single source justifications came up, we, I think you

16       will see a marked improvement in detail for those

17       justifications this year.

18                 COMMISSIONER SKOP:  Thank you.

19                 CHAIRMAN CARTER:  Anything further from the

20       bench?

21                 Ms. Cano, redirect?  Or Mr. Anderson,

22       redirect?

23                 MR. ANDERSON:  Just a few questions, thank

24       you.

25                         REDIRECT EXAMINATION

FLORIDA PUBLIC SERVICE COMMISSION

200

1       BY MR. ANDERSON:

2            Q.   Mr. Scroggs, Mr. Davis used the word slippage

3       in reference to FPL's schedule changes for filing the

4       combined operating license application and FPL's

5       estimate of when it would enter into or not enter into

6       an EPC contract.  Do you remember those questions?

7            A.   Yes, sir, I do.

8            Q.   Focusing on the word slippage, were FPL's

9       actions an accident or the result of management

10       decisions?

11            A.   The result of specific management decision

12       vetted with senior management and determined to be of

13       benefit to our customers to revise the schedule.

14            Q.   Mr. Davis also asked you some questions about

15       NRC schedule changes.  Do you recall those?

16            A.   Yes, sir.

17            Q.   Are NRC schedule changes unexpected in the

18       context of new nuclear plant development?

19            A.   No, they're not.

20            Q.   Please describe FPL's management approach to

21       NRC's schedule changes in those considerations.

22            A.   Our management approach is to maintain a very

23       strong dialogue with the NRC to understand the issues

24       that they have.  They have resource issues from time to

25       time, as well as the technical issues and specific

FLORIDA PUBLIC SERVICE COMMISSION

201

1       issues associated with our application may require them

2       to reallocate.  So an open and detailed communication

3       with the NRC is the best opportunity we have for making

4       sure we understand as early as possible what any

5       schedule changes might be.

6            Q.   Mr. Moyle asked you some questions about the

7       selection of BVZ to perform a scope of work for Turkey

8       Point 6 and 7.  Do you recall that?

9            A.   Yes, sir.

10            Q.   Could you just give us a quick overview about

11       why FPL selected BVZ and how that selection benefited

12       customers?

13            A.   First off, FPL selected BVZ because they're a

14       qualified engineering service provider and a well

15       respected national and international engineering firm.

16       They could provide and have provided excellent value for

17       the work that they've accomplished.

18                 In addition, we look forward to trying to

19       develop the option to save the customers even more money

20       through competitive bidding on some or all of the

21       construction scope of this project.  To the extent that

22       a small amount of construction could be carved out and

23       independently contracted for away from the power plant

24       main body contract, there'd be small benefits.  To the

25       extent that that can be more extensive, they could be

FLORIDA PUBLIC SERVICE COMMISSION

202

1       much larger.

2            Q.   And following up on what Commissioner Skop

3       asked about, did you follow your improved processes and

4       procedures for single source justification for that BVZ

5       retention?

6            A.   Yes, sir, we have.

7            Q.   And did that assessment include quantitative

8       analysis as well as descriptions of qualifications and

9       all those kinds of things?

10            A.   Yes.

11            Q.   And did FPL fully comply with the single and

12       sole source procedures?

13            A.   Yes, we have.

14            Q.   Was it properly approved within the company

15       pursuant to those procedures?

16            A.   Yes, it was.

17                 MR. ANDERSON:  We have no further questions.

18       Thanks.

19                 CHAIRMAN CARTER:  Exhibits?

20                 MR. ANDERSON:  I'm just turning to that page,

21       Commissioner.

22                 CHAIRMAN CARTER:  Okay.  Start on Page 4 of

23       the Comprehensive Exhibit List.

24                 MR. ANDERSON:  Thank you.  FPL offers Exhibits

25       on staff's exhibit list 4 through 12 and 13, 16 -- 13

FLORIDA PUBLIC SERVICE COMMISSION

203

1       through 16 into evidence.

2                 CHAIRMAN CARTER:  Are there any objections?

3       Without objection, show it done.

4                 (Exhibits 4 through 16 admitted into the

5       record.)

6                 Let's go to the back pages.  Exhibit Number

7       130.

8                 MR. DAVIS:  131.

9                 MS. HELTON:  I think 130, Mr. Chairman, was

10       the exhibit that Ms. Triplett had mentioned that had

11       been somehow not listed properly.  So maybe when

12       Progress comes up, that would be the appropriate time to

13       address 130.

14                 CHAIRMAN CARTER:  Oh, okay.  We'll put a hold

15       on that.  That's --

16                 MR. YOUNG:  Yes, sir.

17                 CHAIRMAN CARTER:  That's out of sequence.

18       Okay.

19                 131, Mr. Davis.

20                 MR. DAVIS:  Yes.  SACE offers 131 into

21       evidence.

22                 CHAIRMAN CARTER:  Are there any objections?

23                 MR. ANDERSON:  FPL asks that, with counsel's

24       permission, perhaps we would put Page 9 of that exhibit

25       into evidence.  We're willing to do that on a public

FLORIDA PUBLIC SERVICE COMMISSION

204

1       basis.

2                 MR. DAVIS:  Since that's all we asked about,

3       that's fine.  And the cover sheet, too, I guess.

4                 MR. ANDERSON:  We'd be fine with that.

5                 CHAIRMAN CARTER:  Okay.  So let's do that.

6       Without objection, Exhibit 131 with the modification,

7       there's the cover page and --

8                 MR. DAVIS:  Although I believe -- I'm sorry.

9       I believe that Mr. Moyle has some questions about other

10       pages.

11                 MR. MOYLE:  Yeah.  If we could have the whole

12       exhibit go in.  I asked him questions on the

13       confidential piece.

14                 CHAIRMAN CARTER:  No.  No.  You asked him on

15       the, you asked him about some of the headings.

16                 MR. MOYLE:  No.  I asked him on Page 31 --

17                 CHAIRMAN CARTER:  On Page 12, you asked him on

18       Page 12.

19                 MR. MOYLE:  My copy says 31.

20                 MS. HELTON:  Mr. Chairman, I think Mr. Moyle

21       did also ask some questions on Page 31 of the exhibit,

22       what's in the left-hand corner of Page 31.

23                 CHAIRMAN CARTER:  I was trying to go in order.

24                 MS. HELTON:  Oh, I'm sorry.

25                 CHAIRMAN CARTER:  You did ask about Page 12;

FLORIDA PUBLIC SERVICE COMMISSION

205

1       right?

2                 MR. DAVIS:  Mr. Chair, if I could retract my

3       agreement to just carve out the two pages and suggest

4       that we do place the whole --

5                 CHAIRMAN CARTER:  I'm going to withhold

6       admission on this.  You guys get with staff during the

7       break on it.

8                 MR. ANDERSON:  Yes, sir.

9                 CHAIRMAN CARTER:  Not entered at this point in

10       time.

11                 MR. DAVIS:  And, Mr. Chair --

12                 CHAIRMAN CARTER:  132.

13                 MR. DAVIS:  -- SACE would offer 132 into

14       evidence.

15                 CHAIRMAN CARTER:  Are there any objections?

16                 MR. ANDERSON:  No.

17                 CHAIRMAN CARTER:  Without objection, show it

18       done.

19                 (Exhibit 132 admitted into the record.)

20                 133.

21                 MR. DAVIS:  SACE offers 133 into evidence.

22                 CHAIRMAN CARTER:  Any objections?

23                 MR. ANDERSON:  No.

24                 CHAIRMAN CARTER:  Without objection, show it

25       done.

FLORIDA PUBLIC SERVICE COMMISSION

206

1                 (Exhibit 133 admitted into the record.)

2                 134.

3                 MR. DAVIS:  SACE offers 134 into evidence.

4                 CHAIRMAN CARTER:  Are there any objections?

5                 MR. ANDERSON:  No.

6                 CHAIRMAN CARTER:  Without objection, show it

7       done.

8                 (Exhibit 134 admitted into the record.)

9                 Okay.  At the break I would suggest the

10       parties get together with staff on this confidential

11       Exhibit Number 131 and we'll deal with that when we come

12       back.

13                 Call your next witness.  Thank you.

14                 MR. ANDERSON:  FPL calls Mr. Rajiv Kundalkar

15       as its next witness.

16                 CHAIRMAN CARTER:  Okay.  Commissioners, for

17       planning purposes, and also to the parties, we're going

18       to get back, we'll get back on our schedule where we do

19       lunch from 1:00 to 2:15.  I was hoping that we'd have,

20       we would have done more than one witness by now.  So

21       we'll probably go tonight until at least 7:00, and we'll

22       see where we are tomorrow and we'll probably go a little

23       longer than that.  So we've only got four days and we've

24       got two cases and we're going to get it done.

25                 Mr. Anderson.

FLORIDA PUBLIC SERVICE COMMISSION

207

1                 MR. ANDERSON:  Thank you.

2                          RAJIV S. KUNDALKAR

3       was called as a witness on behalf of Florida Power &

4       Light Company and, having been duly sworn, testified as

5       follows:

6                          DIRECT EXAMINATION

7       BY MR. ANDERSON:

8            Q.   Good afternoon, Mr. Kundalkar.

9            A.   Good afternoon.

10            Q.   You've been sworn as a witness, sir?

11            A.   Yes, sir.

12            Q.   Please tell us your name and your business

13       address.

14            A.   My name is Rajiv S. Kundalkar.  I'm employed

15       with Florida Power & Light Company.  My business address

16       is 700 Universe Boulevard, Juno Beach, Florida.

17            Q.   What's your position with the company?

18            A.   I'm Vice President in the nuclear division

19       responsible for organizational (phonetic) support.

20            Q.   Have you prepared and caused to be filed 32

21       pages of prefiled direct testimony in this proceeding on

22       March 3, 2009?

23            A.   Yes, I have.

24            Q.   And 24 pages of prefiled direct testimony on

25       May 1, 2009?

FLORIDA PUBLIC SERVICE COMMISSION

208

1            A.   Yes, I have.

2            Q.   There have been some errata filed also?

3            A.   That is correct.

4            Q.   Other than the errata, do you have any other

5       changes to your testimony?

6            A.   Yes, I do have two changes.  In my March

7       testimony on Page 1, on Line 12, my new title is Vice

8       President, Organizational Support.  And on Line 15 some

9       of my responsibilities are nuclear fleet licensing,

10       nuclear fleet performance improvement and nuclear fuel

11       procurement and core design.

12            Q.   Any other changes?

13            A.   I have a similar change in my March (sic.)

14       testimony on Page 1, Line 12.  And my title is Vice

15       President, Organizational Support.  Those are the only

16       two changes --

17                 CHAIRMAN CARTER:  You mean in your May; is

18       that right?  You just did March, so you're into the May

19       testimony now; correct?

20                 THE WITNESS:  Pardon me.  The second change

21       was in the May testimony on Page 1, Line 12, Vice

22       President, Organizational Support.

23       BY MR. ANDERSON:

24            Q.   If I asked you the same questions contained in

25       your prefiled direct testimony, would your answers be

FLORIDA PUBLIC SERVICE COMMISSION

209

1       the same?

2            A.   Yes, they would be.

3                 MR. ANDERSON:  FPL asks that the prefiled

4       direct testimony be inserted into the record as though

5       read.

6                 CHAIRMAN CARTER:  The prefiled testimony of

7       the witness will be inserted into the record as though

8       read.

9       BY MR. ANDERSON:

10            Q.   You are sponsoring some exhibits?

11            A.   Yes, I am.

12            Q.   For March, this is RSK-1 to RSK-5; right?

13            A.   That is correct.

14            Q.   For May, it's RSK-1 to RSK-9; correct?

15            A.   That is correct.

16                 MR. ANDERSON:  Mr. Chairman, I would note that

17       these have been premarked as Exhibits 17 to 21 and 22 to

18       29 on staff's Comprehensive Exhibit List.

19                 CHAIRMAN CARTER:  For the record, show it

20       done.

21                 MR. ANDERSON:  Thank you.

22                 (Exhibits 17 through 29 marked for

23       identification.)

24

25

FLORIDA PUBLIC SERVICE COMMISSION

267

1       BY MR. ANDERSON:

2            Q.   You've prepared a summary?

3            A.   Yes, I have.

4            Q.   Please provide your summary to the Commission.

5            A.   Thank you.  And good afternoon, Chairman

6       Carter, Commissioners.  My testimony describes how FPL's

7       team is safely and cost-effectively implementing power

8       uprates at St. Lucie and Turkey Point power plants.

9       When completed, the uprates will provide Florida's

10       customers with more than 400 megawatts of additional

11       clean and zero emission energy without expanding the

12       footprint of these power plants.

13                 As planned, FPL's 2008 work focused on nuclear

14       engineering analyses and design supporting these uprates

15       at the nuclear units.  This work was performed in 2008

16       in order for FPL to meet its schedules for the required

17       submission (phonetic) of the Nuclear Regulatory

18       Commission, NRC, and to prepare the designs of equipment

19       upgrades for the upcoming planned outages.

20                 Much of FPL's 2008 actual costs of

21       approximately $100 million were incurred for competitive

22       procurement of goods, services and long, long-lead

23       equipment from well qualified vendors at reasonable

24       costs.  Some of the examples of these are shown in

25       pictures behind me.  They show pictures of a high

FLORIDA PUBLIC SERVICE COMMISSION

268

1       pressure turbine rotor and a moisture separator

2       reheater, some of the types of components we would be

3       changing in our power plants.  The pictures also list

4       the scope and magnitude of the equipment being changed

5       out in our power plants.

6                 All of the 2008 uprate work as well as the

7       actual and estimated costs for the '09 and

8       2010 projected costs and the planning that was performed

9       used FPL's well established and highly effective project

10       management processes.  These are made up of nuclear

11       policies and procedures that govern our day-to-day

12       business.  The effectiveness of these processes has been

13       demonstrated through successful completion of a number

14       of major projects at our, at our nuclear power plants.

15                 In short, FPL is implementing the appropriate

16       project scope in the required sequence using the right

17       resources to meet the project goals of generating

18       approximately greater than 400 megawatts of clean,

19       reliable electricity by year 2012 for the benefit of

20       Florida's customers.  And this concludes my summary,

21       Chairman Carter.

22                 CHAIRMAN CARTER:  Thank you.

23                 Mr. McGlothlin.

24                 MR. McGLOTHLIN:  I'll have some questions when

25       the witness returns for rebuttal.  I have no questions

FLORIDA PUBLIC SERVICE COMMISSION

269

1       right now.

2                 CHAIRMAN CARTER:  Okay.  Mr. Jacobs.

3                 MR. JACOBS:  Mr. Chairman, no questions from

4       SACE at this time.

5                 CHAIRMAN CARTER:  Mr. Moyle.

6                 MR. MOYLE:  No questions.

7                 CHAIRMAN CARTER:  Staff.

8                 MR. YOUNG:  No questions.

9                 CHAIRMAN CARTER:  Commissioners?  Commissioner

10       Skop, you're recognized.

11                 COMMISSIONER SKOP:  Just a quick question.

12       Even with my glasses -- my eyes must not be working too

13       well -- but what does the one exhibit on the far left

14       represent?  I can't even read that title from here.

15                 THE WITNESS:  The exhibit on the far left

16       shows the new moisture separator reheater, the two

17       bundle (phonetic) portion of the moisture separator

18       reheater.  And there will be a larger enclosure in which

19       this moisture -- the two bundle will be inserted.  This

20       is one of the components on the secondary side of the

21       plant so that the turbine cycle operates more

22       efficiently.

23                 COMMISSIONER SKOP:  Okay.  Thank you.

24                 CHAIRMAN CARTER:  Anything further from the

25       bench.  I assume there's no redirect.

FLORIDA PUBLIC SERVICE COMMISSION

270

1                 MR. ANDERSON:  That's correct.  That's

2       correct.  We'd offer the exhibits.

3                 CHAIRMAN CARTER:  Exhibits?

4                 MR. ANDERSON:  We offer 17 to 21 and 22 to 29.

5                 CHAIRMAN CARTER:  Are there any objections?

6       Without objection, show it done.

7                 (Exhibits 17 through 29 admitted into the

8       record.)

9                 Call your next witness.

10                 MS. CANO:  FPL calls Dr. Steven Sim.

11                 CHAIRMAN CARTER:  Steven Sim.

12                            STEVEN R. SIM

13       was called as a witness on behalf of Florida Power &

14       Light Company and, having been duly sworn, testified as

15       follows:

16                          DIRECT EXAMINATION

17       BY MS. CANO:

18            Q.   Good afternoon, Dr. Sim.

19            A.   Good afternoon.

20            Q.   Have you been sworn?

21            A.   Yes, I have.

22            Q.   Would you please state your name and business

23       address for the record?

24            A.   My name is Steve Sim.  I work at 9250 West

25       Flagler Street, Miami, Florida Power & Light.

FLORIDA PUBLIC SERVICE COMMISSION

271

1            Q.   By whom are you employed and in what capacity?

2            A.   By Florida Power & Light as a Senior Manager

3       in Integrated Resource Planning.

4            Q.   Did you prepare and cause to be filed on

5       May 1st 15 pages of prefiled direct testimony in this

6       proceeding?

7            A.   Yes, I did.

8            Q.   And did you also prepare and cause to be filed

9       an errata to your direct testimony?

10            A.   Yes.

11            Q.   Do you have any other changes or revisions to

12       make to your testimony?

13            A.   No, I do not.

14            Q.   With the errata, if I were to ask you the same

15       questions contained in your prefiled direct testimony

16       today, would your answers be the same?

17            A.   Yes, they would.

18                 MS. CANO:  Chairman Carter, I ask that the

19       prefiled direct testimony of Dr. Sim be inserted into

20       the record as though read.

21                 CHAIRMAN CARTER:  The prefiled testimony of

22       the witness will be inserted into the record as though

23       read.

24       BY MS. CANO:

25            Q.   Are you also sponsoring exhibits to your

FLORIDA PUBLIC SERVICE COMMISSION

272

1       testimony?

2            A.   Yes, I am.

3            Q.   And do those consist of SRS-1 to SRS-5?

4            A.   Yes.

5                 MS. CANO:  Mr. Chairman, I would note that

6       these have been premarked for identification as Numbers

7       30 to 34 on staff's Comprehensive Exhibit List.

8                 CHAIRMAN CARTER:  30 to 34.  Thank you.

9                 (Exhibits 30 to 34 marked for identification.)

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

288

1       BY MS. CANO:

2            Q.   Have you prepared a summary of your direct

3       testimony?

4            A.   Yes, I have.

5            Q.   Would you please provide that at this time?

6            A.   Yes, I will.

7                 Good afternoon, Chairman Carter and

8       Commissioners.  FPL's 2009 economic analyses for both

9       the nuclear uprates in Turkey Point 6 and 7 are based on

10       a scenario approach that includes a number of updated

11       assumptions, including but not limited to the load

12       forecast, the fuel cost forecast and environmental

13       compliance cost forecast.

14                 As is usually the case, some annual changes in

15       the assumptions will favor new nuclear capacity and

16       other assumption changes do not.  And, as in prior

17       economic analyses of these new nuclear capacity options,

18       FPL's 2009 analyses directly under (phonetic)

19       uncertainty by utilizing three fuel cost forecasts and

20       four environmental compliance cost forecasts, to examine

21       in total nine scenarios of fuel and environmental

22       compliance costs.

23                 In regard to the nuclear uprates, the 2009

24       economic analysis approach for the nuclear uprates is

25       unchanged.  We compared a resource plan with nuclear

FLORIDA PUBLIC SERVICE COMMISSION

289

1       uprates to a resource plan without the nuclear uprates.

2       The two resource plans were compared on the basis of

3       cumulative present value of revenue requirements or

4       CPVRR that identifies the resource plan with the lowest

5       cost to FPL's customers.  The resource plan with nuclear

6       uprates is projected to result in lower CPVRR costs than

7       the resource plan without nuclear uprates in all of nine

8       scenarios.

9                 In regard to Turkey Point 6 and 7, the 2009

10       economic analysis approach for Turkey Point 6 and 7 is

11       also unchanged.  This approach is to first compare a

12       resource plan with Turkey Point 6 and 7 but with no

13       capital costs for new nuclear units versus a resource

14       plan without Turkey Point 6 and 7 and with a comparable

15       amount of combined cycle capacity.  The two plans are

16       then compared on a CPVRR basis.

17                 FPL then determines the breakeven capital

18       costs for Turkey Point 6 and 7 that would allow the

19       CPVRR cost for the two resource plans to be identical

20       for each of the nine scenarios.  These breakeven capital

21       costs are then compared to FPL's nonbinding estimated

22       capital cost range of $3,108 per kW to $4,540 per kW in

23       2007 dollars.

24                 The calculated breakeven capital costs for

25       Turkey Point 6 and 7 are projected to be above this

FLORIDA PUBLIC SERVICE COMMISSION

290

1       estimated capital cost range in eight of the nine

2       scenarios, meaning that the cost of Turkey Point 6 and 7

3       could be above and, in many cases, well above this

4       nonbinding capital cost range and Turkey Point 6 and 7

5       would still be cost effective.

6                 In the ninth scenario that consists of low

7       fuel and low environmental compliance costs the

8       calculated breakeven capital costs are projected to be

9       within this estimated capital cost range and near the

10       upper end of the range.

11                 In conclusion, Commissioners, both the nuclear

12       uprates in Turkey Point 6 and 7 are still projected to

13       be solidly cost-effective resource additions for FPL's

14       customers.  Therefore, the results of the 2009 economic

15       analyses support the feasibility of continuing both

16       nuclear projects.  Thank you.

17                 MS. CANO:  We tender the witness for cross

18       examination.

19                 CHAIRMAN CARTER:  Mr. McGlothlin.

20                          CROSS EXAMINATION

21       BY MR. McGLOTHLIN:

22            Q.   Sir, during your summary you indicated that

23       the range of something like 3,100 to 4,000 plus dollars

24       was expressed in 2007 dollars; correct?

25            A.   That's correct.

FLORIDA PUBLIC SERVICE COMMISSION

291

1            Q.   Is that because the estimate was prepared in

2       2007?

3            A.   Essentially, yes.

4                 MR. McGLOTHLIN:  No further questions.

5                 CHAIRMAN CARTER:  Thank you, Mr. McGlothlin.

6                 Mr. Davis.

7                 MR. DAVIS:  Mr. Chair, we'd like to reserve

8       our cross examination for rebuttal for this witness.

9                 CHAIRMAN CARTER:  Okay.  Mr. Moyle, you're

10       recognized.

11                 MR. MOYLE:  Thank you.  I have a few

12       questions.

13                          CROSS EXAMINATION

14       BY MR. MOYLE:

15            Q.   Good afternoon.  Good to see you again.

16            A.   Good afternoon.

17            Q.   In your direct testimony you looked at a

18       number of conditions that, that are changing, and I know

19       in some testimony at some point FPL took the position

20       that we're not going to let changes and assumptions, you

21       know, drive the ultimate decision.  But you would agree

22       that they are important to review; correct?  Natural gas

23       assumptions, growth assumptions, things like that.

24            A.   Well, I think I would have to first disagree

25       with your premise that FPL has decided that assumptions

FLORIDA PUBLIC SERVICE COMMISSION

292

1       won't change our decision.  I think we continually

2       update assumptions and, in our analyses, and utilize

3       them to the fullest extent possible in trying to

4       determine the long-term feasibility analysis of both

5       nuclear projects.

6            Q.   Okay.  And I -- maybe I wasn't clear in that.

7       I thought there was testimony that said, you know, we're

8       not going to make a no-go -- no-go or go decision based

9       on, you know, an assumption that may have altered from

10       one year as compared to another.  This is a long-range

11       project, we're taking a long-range view on it.  We'll be

12       mindful of them, but it's not going to dictate a

13       decision.  Is that generally accurate?

14            A.   Again, I'm not quite sure I can agree with

15       that.  We're not at a point of whether -- where we are

16       ready to make a decision in regard to construction of

17       these units.  We are taking into account fully updated

18       assumptions for a wide variety of forecasts and other

19       assumptions that we utilize in our economic analyses.

20            Q.   Okay.  Let's talk about, for a minute about

21       some of these assumptions.  Your forecast summer peak

22       load, that is lower compared to 2008.  Your 2009

23       forecast is lower as compared to 2008; correct?

24            A.   That's correct.

25            Q.   Okay.  And that would lower the economic

FLORIDA PUBLIC SERVICE COMMISSION

293

1       benefits for additional nuclear capacity; correct?

2            A.   If that were the sole change to the

3       assumptions from 2008, then generally, yes, the

4       cost-effectiveness of the new nuclear projects would be

5       diminished to some degree.

6            Q.   Okay.  And the forecast uranium costs, those

7       have gone up from 2008 as compared to 2009; correct?

8            A.   That is correct.

9            Q.   Okay.  And that would also work against the

10       cost-effectiveness of the Turkey Point 6 and 7 projects,

11       that forecast; correct?

12            A.   To a small degree because the uranium cost is

13       relatively small to begin with and the cost increase on

14       an already small cost number is also almost negligible.

15       But, yes, the direction would be towards it being less

16       cost-effective.

17            Q.   Okay.

18            A.   Again, if it were the only assumption in

19       question, which it is not.

20            Q.   You also forecast natural gas prices, and

21       there's lower natural gas prices forecast in years 2030

22       to 2040 than was utilized in the 2008 analysis; correct?

23            A.   Yes.  They were higher in certain years, the

24       mid-term years.  They were lower in the, some of the

25       beginning years and lower in the latter years, as you've

FLORIDA PUBLIC SERVICE COMMISSION

294

1       indicated.

2            Q.   Okay.  And with respect to Turkey Point 6 and

3       7, those are going to be operational in the years 2030

4       through 2040; correct?

5            A.   Actually they will become operational

6       according to the schedule in 2018 and 2020 and will

7       therefore be operating in the years in which the nearer

8       term projection of natural gas costs are higher.  They

9       will also be operating in these latter years when the

10       projected natural gas costs are lower.

11            Q.   Okay.  And my question simply was to focus on

12       2030 to 2040 and confirm that the Turkey Point 6 and 7

13       will be operating in that time frame.  Could you confirm

14       that, please?

15            A.   Can you break the question down a bit, please?

16            Q.   Sure.  Turkey Point 6, is it going to, is it

17       projected to be operating from the years 2030 to 2040?

18            A.   Yes.

19            Q.   Okay.  Turkey Point 7, is it projected to be

20       operating in the years 2030 to 2040?

21            A.   Yes.  Both units will be operating within that

22       ten-year time frame, but they will also be operating in

23       years prior and years after that ten-year time frame.

24            Q.   We hope so, if they're, if they're built.

25                 The question I wanted to ask you is with

FLORIDA PUBLIC SERVICE COMMISSION

295

1       respect to the natural gas price forecast for those

2       years, the price forecast is for lower natural gas

3       prices in the 2030 to 2040 time range; correct?

4            A.   In regard to natural gas commodity costs, that

5       would be true.

6            Q.   Okay.

7            A.   In regard to natural gas firm transportation

8       costs, the costs will be higher than what was projected

9       in either our '07 analysis or our '08 analysis.

10            Q.   Right.  And I asked you about gas, natural gas

11       prices, not the, not the transportation component.  So

12       let's just focus on the natural gas prices at this

13       point, if we can.

14            A.   Fine.  I was trying to give a complete answer

15       for both components of natural gas prices.  You had not

16       indicated commodity or gas transportation costs.

17            Q.   Okay.  You don't contract out for firm

18       transportation 20 years out in advance, do you?

19            A.   On occasion I believe that we have.

20            Q.   Isn't it true that with respect to the

21       forecast for natural gas prices trending downward from

22       2008 to 2009 that that has an incremental admittedly but

23       an incremental negative effect on the proposed Turkey

24       Point 6 and 7 project?

25            A.   I would disagree.  The units will not be built

FLORIDA PUBLIC SERVICE COMMISSION

296

1       until, or will not go into operation until 2018 or 2020.

2       The fact that natural gas prices would have gone down

3       from '08 to '09 or whether they would have gone up from

4       '08 to '09 really is, has no direct impact on what

5       natural gas prices will be starting in 2018.

6            Q.   Part of your testimony talks about the

7       feasibility for Turkey Point 6 and 7; correct?

8            A.   That's correct.

9            Q.   Okay.  You're familiar with the Commission

10       rule that indicates by May 1st of each year a utility

11       must submit for Commission review and approval a

12       detailed analysis of the long-term feasibility of

13       completing the power plant; correct?

14            A.   I'm generally aware of it.  Yes.

15            Q.   Okay.  Can you show me in your testimony where

16       that long -- where that detailed analysis can be found?

17            A.   The summary of the results of the detailed

18       feasibility analysis are found on SRS-5.

19            Q.   And that's the document that shows nine

20       scenarios; is that correct?

21            A.   That is correct.

22            Q.   And it's your testimony and your belief that

23       this one-page document you believe is sufficient for

24       meeting the requirements of the rule to provide a

25       detailed analysis of the long-term feasibility of

FLORIDA PUBLIC SERVICE COMMISSION

297

1       completing the power plant?

2            A.   I believe that this page accurately summarizes

3       a very detailed analysis of nine different scenarios

4       covering a period from 2009 through 2060 of a resource

5       plan with the new nuclear units and a resource plan

6       without the nuclear units with competing combined cycle

7       capacity.  Yes.

8            Q.   And the capital costs used in this were not

9       current capital costs; correct?

10            A.   I disagree.  The capital costs for the

11       combined cycle unit were the most up-to-date capital

12       costs that we had for that type of capacity.  And the

13       capital cost we used for the nonbinding capital cost

14       estimate for new nuclear units was, was considered at

15       the time to be still applicable for this analysis.  We

16       had no better numbers --

17            Q.   And what year were --

18            A.   -- as Mr. Scroggs had testified a bit earlier

19       this morning.

20            Q.   And what year were your capital costs for the

21       nuclear projections?

22            A.   I believe that those costs were developed

23       around 2007.  They've been reviewed each year since in

24       our 2008 feasibility analysis.  And I personally called

25       Mr. Scroggs this year to discuss whether or not they

FLORIDA PUBLIC SERVICE COMMISSION

298

1       still remain viable and the best estimates possible, and

2       he assured me that they were.  Therefore, I consider

3       them to be the most up-to-date capital cost estimates

4       that we have for the new units.

5            Q.   You would agree that in trying to ascertain

6       market prices it's better to test a market at a point in

7       time closer to, say, providing testimony than relying on

8       data that's two years old, would you not?

9            A.   Not if the cost estimate from two years ago

10       was still suitable or adequate today for purposes of the

11       analysis.  And that's what FPL believes those numbers

12       represent, the best up-to-date estimates of the capital

13       cost to the new nuclear units.

14            Q.   You would agree that the market for nuclear

15       components, nuclear construction, EPC contracts, that

16       given the passage of time, that that market changes;

17       correct?

18            A.   I think you're running a bit out of my range

19       of experience here in regard to components, cost

20       components for nuclear units.  I believe either

21       Mr. Scroggs and perhaps Mr. Reed would be a better one

22       to address those questions to.

23                 MR. MOYLE:  Okay.  Thank you.  That's, that's

24       all I have.

25                 COMMISSIONER EDGAR:  Are there questions from

FLORIDA PUBLIC SERVICE COMMISSION

299

1       staff for this witness?

2                 MR. YOUNG:  No questions.

3                 COMMISSIONER EDGAR:  No questions.

4                 Commissioners?  No questions.

5                 Redirect.

6                 MS. CANO:  Just one redirect.  Thank you.

7                         REDIRECT EXAMINATION

8       BY MS. CANO:

9            Q.   Dr. Sim, Mr. Moyle asked you to point to where

10       the detailed analyses was in your testimony, and you

11       said that SRS-5 contained the summary of the results of

12       that analysis.  Do you remember that question?

13            A.   Yes, I do.

14            Q.   Would you please briefly describe the analyses

15       and the process that lead up to the results shown in

16       SRS-5?

17            A.   Yes, I'll be happy to.

18                 Commissioners, the actual analysis looks at a

19       very lengthy time period from 2009 through 2060 of two

20       resource plans in which we analyze the costs over all of

21       those years.  It involves a variety of computer models,

22       a variety of assumptions and forecasts, and involves

23       first a step in which we calculate the cumulative

24       present value revenue requirement cost for both of the

25       resource plans, but assuming zero capital cost for

FLORIDA PUBLIC SERVICE COMMISSION

300

1       nuclear units.  We then go into those differentials in

2       CPVRR between the two plans for each one of the nine

3       scenarios of fuel and environmental compliance costs and

4       calculate separately a breakeven capital cost so that

5       the cost of, the CPVRR cost of the two plants will be

6       identical.

7                 So what we're looking at for each one of the

8       nine scenarios is a very detailed analysis essentially

9       along the same lines as the analysis that we come before

10       you with when we are seeking a need determination for a,

11       an individual power plant.

12                 MS. CANO:  Thank you.  No further questions.

13                 COMMISSIONER EDGAR:  Okay.  Let's take up the

14       exhibits.  Can you point me to the numbers?

15                 MR. YOUNG:  Madam Chair, it would be starting

16       with Number 30 on Page 7.

17                 COMMISSIONER EDGAR:  Thank you.  So we are

18       looking for this witness at exhibits previously marked

19       30 through 34.

20                 MS. CANO:  34.  FPL moves those.  Thank you.

21                 COMMISSIONER EDGAR:  Okay.  Any objection?

22       Hearing none, Exhibits 30 through 34 are entered into

23       the record.

24                 (Exhibits 30 through 34 admitted into the

25       record.)

FLORIDA PUBLIC SERVICE COMMISSION

301

1                 Thank you very much.  You're excused for the

2       time being.

3                 THE WITNESS:  Thank you.

4                 COMMISSIONER EDGAR:  And we can move to the

5       next witness.

6                 MR. ANDERSON:  FPL calls Winnie Powers as its

7       next witness.

8                 CHAIRMAN CARTER:  You may proceed.

9                 MR. RUBIN:  Thank you, Chairman Carter.

10                            WINNIE POWERS

11       was called as a witness on behalf of Florida Power &

12       Light Company and, having been duly sworn, testified as

13       follows:

14                          DIRECT EXAMINATION

15       BY MR. RUBIN:

16            Q.   You've been sworn as a witness earlier today?

17            A.   Yes, I have.

18            Q.   Would you please state your name and business

19       address?

20            A.   My name is Winnie Powers, and my address --

21                 CHAIRMAN CARTER:  You need to pull the

22       microphone a little closer to you and please start over.

23                 THE WITNESS:  Okay.  My name is Winnie Powers.

24                 CHAIRMAN CARTER:  Chris, can you give her some

25       volume?  Please start over.

FLORIDA PUBLIC SERVICE COMMISSION

302

1                 THE WITNESS:  My name is Winnie Powers.  My

2       business --

3                 CHAIRMAN CARTER:  I'm not feeling it.  Try

4       again.

5                 THE WITNESS:  My name is Winnie Powers.  My --

6       no.

7                 CHAIRMAN CARTER:  Hang on one second.  Hang on

8       a second.

9                 COMMISSIONER ARGENZIANO:  Mr. Chair, I can't

10       hear her.

11                 CHAIRMAN CARTER:  Can you hear her,

12       Commissioner?

13                 COMMISSIONER EDGAR:  No.  It's very low.

14                 CHAIRMAN CARTER:  Chris is working on her

15       microphone now.  We're going to try to -- I was

16       wondering about that because we're having trouble

17       hearing her here.

18                 COMMISSIONER ARGENZIANO:  Okay.  Thank you.

19                 CHAIRMAN CARTER:  Okay.  Let's try it again.

20                 THE WITNESS:  Okay.  My name is Winnie Powers.

21       My business address is 9250 West Flagler Street, Miami,

22       Florida.

23                 CHAIRMAN CARTER:  Commissioner Argenziano, is

24       that better?

25                 COMMISSIONER ARGENZIANO:  Yes.  That's much

FLORIDA PUBLIC SERVICE COMMISSION

303

1       better.  Thank you.

2                 CHAIRMAN CARTER:  Okay.  You may proceed.

3                 MR. RUBIN:  Thank you, sir.

4       BY MR. RUBIN:

5            Q.   By whom are you employed and in what capacity?

6            A.   I'm employed by Florida Power & Light Company,

7       and I am the New Nuclear Accounting Project Manager.

8            Q.   Have you prepared and caused to be filed 23

9       pages of prefiled direct testimony in this proceeding on

10       March 2, 2009?

11            A.   Yes, I have.

12            Q.   And did you also cause, cause to be filed

13       errata to your March 2 testimony on August 21, 2009?

14            A.   Yes, I did.

15            Q.   Have you also prepared and caused to be filed

16       19 pages of prefiled direct testimony in this proceeding

17       on May 1, 2009?

18            A.   Yes.

19            Q.   And did you also cause to be filed errata to

20       your May 1 testimony on August 21, 2009?

21            A.   Yes.

22            Q.   Do you have any further changes or revisions

23       to your prefiled direct testimony?

24            A.   No, I do not.

25            Q.   If I asked you the same questions contained in

FLORIDA PUBLIC SERVICE COMMISSION

304

1       your prefiled direct testimony, would your answers be

2       the same?

3            A.   Yes.

4                 MR. RUBIN:  FPL asks that Ms. Powers' prefiled

5       direct testimony of March 2, 2009, and May 1, 2009, with

6       errata be inserted into the record as though read.

7                 CHAIRMAN CARTER:  Let's try it again.  The

8       prefiled testimony of the witness will be inserted into

9       the record as though read.

10       BY MR. RUBIN:

11            Q.   Are you also sponsoring any exhibits to your

12       direct testimony?

13            A.   Yes I am.

14            Q.   And do those exhibits consist of revised

15       Exhibit WP-1 along with Exhibits WP-2 and 3 to your

16       March 2, 2009, testimony, and revised Exhibits WP-1 and

17       WP-2 to your May 1, 2009, testimony, also shown as

18       Exhibits 35 through 39 on staff's exhibit list?

19            A.   Yes.

20                 MR. RUBIN:  Mr. Chairman, I would note that

21       Ms. Powers' exhibits have been premarked for

22       identification as Exhibits 35 through 39.

23                 CHAIRMAN CARTER:  35 through 39.  Thank you.

24                 (Exhibits 35 through 39 marked for

25       identification.)

FLORIDA PUBLIC SERVICE COMMISSION

349

1       BY MR. RUBIN:

2            Q.   Have you prepared a summary of your direct

3       testimony?

4            A.   Yes.

5            Q.   Would you please provide your summary to the

6       Commission?

7            A.   I will.

8                 CHAIRMAN CARTER:  Chris, give me little more

9       volume on her, please, on Ms. Powers.  This is not taken

10       against -- this is not against your time, Ms. Powers.

11                 THE WITNESS:  Okay.  Thank you.

12                 CHAIRMAN CARTER:  Okay.  Let's try it now.

13                 THE WITNESS:  Okay.  Good afternoon, Mr.

14       Chairman, Commissioners.  The purpose of my testimony is

15       to present FPL's nuclear filing requirements or NFRs

16       that quantify our request for the Commission

17       determination of the prudence and reasonableness of our

18       costs.  I provide an overview of FPL's filing and

19       demonstrate that the filing complies with the nuclear

20       power plant cost recovery rule, which I will refer to as

21       the rule, and the related statute.

22                 Additionally, I explain how carrying charges

23       are provided for under this rule.  I speak to the

24       process of excluding costs that are not separate and

25       apart from recovery under the rule, but confirm that FPL

FLORIDA PUBLIC SERVICE COMMISSION

350

1       will record AFUDC on these costs, as we do with other

2       construction work in progress.

3                 My testimony outlines the comprehensive and

4       overlapping controls that we have in place which are

5       documented, assessed, audited and tested on an ongoing

6       basis by both FPL's internal and external auditors.  Our

7       internal controls and costs have also been audited by

8       this Commission's audit staff.

9                 These comprehensive corporate and overlapping

10       business unit controls for incurring costs and recording

11       transactions, along with the testimony provided by our

12       witnesses, should give this Commission assurance that

13       our total costs are prudent and that our projected costs

14       are reasonable.

15                 FPL filed the final NFR schedules containing

16       information through 2008 for its St. Lucie and Turkey

17       Point uprates and Turkey Point 6 and 7 preconstruction

18       and site selection projects on March 2nd, 2009, and is

19       requesting the Commission determine these costs as

20       prudently incurred.

21                 On May 1st, 2009, FPL filed its actual

22       estimated and 2010 projected NFRs for the same projects,

23       and is requesting the Commission determine these costs

24       as reasonable.

25                 Based on the Commission's determinations, FPL

FLORIDA PUBLIC SERVICE COMMISSION

351

1       requests this Commission approve for recovery effective

2       January 1, 2010, FPL's total requested revenue

3       requirement of $62,789,984 on a jurisdictional basis

4       through the capacity cost recovery clause.  This amount

5       represents the true-up of actual costs incurred through

6       2008 and estimated and projected costs through 2010 for

7       FPL's uprate and Turkey Point 6 and 7 projects.  This

8       concludes my summary.

9                 CHAIRMAN CARTER:  Mr. McGlothlin.

10                 MR. McGLOTHLIN:  OPC has no questions.

11                 CHAIRMAN CARTER:  Mr. Davis.

12                 MR. DAVIS:  None from SACE.

13                 CHAIRMAN CARTER:  Mr. Moyle, you're

14       recognized.

15                 MR. MOYLE:  Thank you.

16                          CROSS EXAMINATION

17       BY MR. MOYLE:

18            Q.   You mentioned about the audits of the separate

19       and apart issue and you said that there was an internal

20       audit done and an external audit; is that correct?

21            A.   I mentioned that our costs and internal

22       controls have been audited by our internal auditors and

23       external, and the PSC auditors as well.

24            Q.   Okay.  And just so, just so we're clear, there

25       hasn't been an audit specifically done with respect to

FLORIDA PUBLIC SERVICE COMMISSION

352

1       the separate and apart issue where an outside auditing

2       firm has been contracted and said please come in and

3       review specifically whether these costs are properly

4       allocated; is that correct?

5            A.   No, it's not correct.  Witness Reed

6       reviewed -- it's not a true audit, but he did review our

7       process of determining how costs are separate and apart

8       and how we segregate them.

9            Q.   And Witness Reed, he's not a CPA, is he?

10            A.   I don't believe he is.

11            Q.   I had one other question.  On Page 3, Line 17,

12       you talk about the base rate revenue requirements of

13       70,566 related to the Gantry Crane going into the

14       plant-in-service at St. Lucie.

15            A.   Based on the errata, that amount is $83,651.

16            Q.   Okay.  Thank you.  Isn't, isn't this crane

17       part of what is needed to construct the dry cask storage

18       facility at St. Lucie?

19            A.   I'm not aware of if it is, but let me clarify

20       exactly what this amount represents.  We have a Gantry

21       Crane currently at our Port St. Lucie plant, and it's

22       functioning well for the things that we need it to

23       function for.

24                 In order to do the uprate project, we need to

25       make certain modifications to that crane, and this

FLORIDA PUBLIC SERVICE COMMISSION

353

1       amount represents the base rate revenue impact of those

2       modifications going into plant-in-service.

3            Q.   Okay.  You don't have any information as to

4       whether it's needed and necessary for the dry cask

5       project?

6            A.   I think the appropriate witness would be

7       Witness Kundalkar for that.

8                 MR. MOYLE:  Okay.  Thank you.  That's all I

9       have.

10                 CHAIRMAN CARTER:  Staff.

11                          CROSS EXAMINATION

12       BY MR. YOUNG:

13            Q.   Good afternoon, Ms. Powers.  How are you?

14            A.   Good afternoon.  I'm fine.

15            Q.   I just have a few questions.

16                 In your summary, and correct me if I'm wrong,

17       in your summary you stated that your treatment of the

18       AFUDC is appropriate; correct?

19            A.   Yes.

20            Q.   Okay.  Has the Commission issued an order

21       explicitly addressing recovery of carrying costs for

22       FPL's projects that is greater or lesser than what, than

23       what is stated in Section 366.97 of the Florida

24       Statutes?

25            A.   No.

FLORIDA PUBLIC SERVICE COMMISSION

354

1            Q.   93.  Excuse me.

2            A.   The Commission has not issued an order

3       regarding that.  However, the Commission does have a

4       rule, which is the nuclear cost recovery rule,

5       25-6.0423, which describes how you recover carrying

6       costs related to those projects.  And the Commission

7       also has an AFUDC rule, 25-6.0141, that tells you how to

8       apply AFUDC to all of your construction work in

9       progress.

10            Q.   But the nuclear rule that you mentioned just

11       now does not address the incremental or decremental

12       difference in the AFUDC; correct?

13            A.   Let me, if I may, go to the rule.

14                 Okay.  The Rule 25-6.0423 in Section 5(B),

15       carrying costs on construction cost balance, states, "A

16       utility is entitled to recover through the utility's

17       capacity cost recovery clause the carrying costs on the

18       utility's annual projected construction cost balance

19       associated with the power plant."  It goes on to say,

20       "The actual carrying costs recovered through the

21       capacity cost recovery clause shall reduce the allowance

22       for funds used during construction that would otherwise

23       have been recorded as a cost of construction eligible

24       for future recovery as plant-in-service."

25                 MR. YOUNG:  No further questions.

FLORIDA PUBLIC SERVICE COMMISSION

355

1                 CHAIRMAN CARTER:  Commissioners?

2                 Redirect?

3                 MR. RUBIN:  No, no redirect, sir.

4                 CHAIRMAN CARTER:  Exhibits?

5                 MR. RUBIN:  FPL moves Exhibits 35, 36, 37, 38

6       and 39.

7                 CHAIRMAN CARTER:  Are there any objections?

8       Without objection, show it done.

9                 (Exhibits 35 through 39 admitted into the

10       record.)

11                 Ms. Powers, you may be excused for now.

12                 THE WITNESS:  Thank you, Chairman.

13                 CHAIRMAN CARTER:  See you later at part two of

14       the party.

15                 Call your next witness.

16                 MR. ANDERSON:  FPL calls Mr. John Reed as its

17       next witness.

18                 CHAIRMAN CARTER:  Mr. John Reed.

19                             JOHN J. REED

20       was called as a witness on behalf of Florida Power &

21       Light Company and, having been duly sworn, testified as

22       follows:

23                          DIRECT EXAMINATION

24       BY MS. CANO:

25            Q.   Good afternoon, Mr. Reed.

FLORIDA PUBLIC SERVICE COMMISSION

356

1            A.   Good afternoon.

2            Q.   Have you been sworn?

3            A.   Yes, I have.

4            Q.   Would you please state your name and business

5       address for the record?

6            A.   My name is John J. Reed.  My business address

7       is 293 Boston Post Road, Marlborough, Massachusetts.

8            Q.   By whom are you employed and in what capacity?

9            A.   I am the Chairman and CEO of Concentric Energy

10       Advisors.

11            Q.   Did you prepare and cause to be filed on March

12       2nd, 2009, 54 pages of prefiled direct testimony and on

13       May 1st, 2009, 21 pages of prefiled direct testimony in

14       this proceeding?

15            A.   Yes, I did.

16            Q.   Did you also prepare and cause to be filed an

17       errata sheet to your testimony?

18            A.   Yes.

19            Q.   Do you have any other changes or revisions to

20       make to your testimony at this time?

21            A.   No, nothing further.

22            Q.   With the errata, if I were to ask you the same

23       questions contained in your prefiled direct testimony,

24       would your answers be the same?

25            A.   Yes, they would.

FLORIDA PUBLIC SERVICE COMMISSION

357

1                 MS. CANO:  Chairman Carter, I ask that the

2       prefiled direct testimony be inserted into the record as

3       though read.

4                 CHAIRMAN CARTER:  The prefiled testimony of

5       the witness will be inserted into the record as though

6       read.

7       BY MS. CANO:

8            Q.   Are you also sponsoring exhibits to your

9       testimony?

10            A.   Yes, I am.

11            Q.   Do those consist of JJR-1 to JJR-3 for your

12       March testimony and JJR-1 for your May testimony?

13            A.   That's correct.

14                 MS. CANO:  Mr. Chairman, I would note that

15       these have been premarked for identification as numbers

16       40 to 43 on staff's exhibit list.

17                 CHAIRMAN CARTER:  For the record, 40 through

18       43.

19                 (Exhibits 40 through 43 marked for

20       identification.)

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

434

1       BY MS. CANO:

2            Q.   Have you prepared a summary of your direct

3       testimony?

4            A.   Yes, I have.

5            Q.   Would you please provide that at this time?

6            A.   Certainly.  Good afternoon.  During the past

7       30 years I have provided expert testimony on a wide

8       variety of economic and financial issues related to the

9       energy and utility industry, including several nuclear

10       construction projects.

11                 My testimony here today presents my opinion as

12       to the reasonableness of FPL's policies and procedures

13       for its uprate and new nuclear programs and how these

14       policies and procedures have resulted in prudently

15       incurred costs for FPL and its customers.

16                 As part of my firm's work on this matter my

17       staff and I reviewed numerous documents and interviewed

18       several FPL staff members in order to evaluate FPL's

19       project management capabilities.  As with Concentric's

20       review in the 2008 nuclear cost recovery case, we

21       reviewed six elements for each of five processes that

22       are integral to the company's project management

23       capabilities.  These six elements included defined

24       corporate procedures, written project execution plans,

25       involvement of key internal stakeholders, reporting and

FLORIDA PUBLIC SERVICE COMMISSION

435

1       oversight mechanisms, corrective action mechanisms and

2       reliance upon a viable technology.

3                 Our review encompassed the five following

4       processes.  First, cost estimation and budgeting,

5       schedule management, contract management and

6       administration, internal oversight and external

7       oversight.

8                 Lastly, my direct testimony presents a

9       comparison of FPL's cost estimate for its new nuclear

10       project as compared to cost estimates for similar

11       projects.

12                 Let me first turn to the cost estimating and

13       budgeting process.  FPL has corporate procedures in

14       place that explicitly document the process for

15       developing a cost estimate, and Concentric has found

16       that FPL has complied with those procedures.  FPL uses a

17       partial takeoff cost estimating process which is

18       recognized within the nuclear energy industry as being

19       the most accurate means of developing a preliminary cost

20       estimate.  The FPL cost estimates have included a

21       reasonable contingency factor that is consistent with

22       industry guidelines.

23                 Finally, Concentric has found that FPL's cost

24       estimate for the new nuclear project is reasonable and

25       well within the range of similar cost estimates for

FLORIDA PUBLIC SERVICE COMMISSION

436

1       other projects.

2                 Next, within the schedule and management

3       function, FPL has specific corporate policies for

4       developing and maintaining project schedules and has

5       complied with those procedures in executing the uprate

6       projects and the new nuclear project.  These procedures

7       utilize industry standard critical path scheduling

8       methods and an often used software program to optimize

9       these schedules and to define the relationships between

10       activities.  I've also noted that FPL has a

11       well-documented process for initiating corrective action

12       mechanisms if a project falls behind schedule.

13                 Turning to the contract management function,

14       FPL has robust procedures that appear to cover all

15       facets of contract development and FPL has complied with

16       those procedures.  FPL has a preference for competitive

17       bidding where possible and when it is in the best

18       interest of the company and its customers.  For those

19       instances where the company has utilized, has decided

20       not to utilize competitive bidding, it has documented

21       its reasons for doing so.

22                 Finally, for the external and internal

23       oversight mechanisms, FPL has established appropriate

24       internal and external mechanisms to gauge project

25       performance and to institute best practices.  This

FLORIDA PUBLIC SERVICE COMMISSION

437

1       includes the development of executive reporting

2       requirements, internal audit requirements and a

3       corporate Risk Committee which are responsible for

4       reviewing both projects.

5                 In conclusion, I have found that FPL's project

6       management practices and procedures for both projects

7       are reasonable and meet or exceed industry norms.  These

8       practices and procedures include an appropriate level of

9       oversight of both the projects and include internal and

10       external project reviews to ensure compliance with the

11       company's policies.

12                 I've also concluded that all of the costs for

13       which FPL is seeking recovery in this case have been

14       prudently incurred during 2007 and 2008, and that FPL

15       has produced reasonable projections of expenditures for

16       2009 and 2010.  Thank you.  That concludes my summary.

17                 MS. CANO:  Thank you.  We tender the witness

18       for cross exam.

19                 CHAIRMAN CARTER:  Mr. McGlothlin.

20                 MR. McGLOTHLIN:  I'll have several questions

21       when he returns on rebuttal, but no questions now.

22                 CHAIRMAN CARTER:  On rebuttal?

23                 Mr. Davis.

24                 MR. DAVIS:  Mr. Chair, I have a few now and

25       more later on rebuttal.

FLORIDA PUBLIC SERVICE COMMISSION

438

1                 CHAIRMAN CARTER:  You're recognized.

2                          CROSS EXAMINATION

3       BY MR. DAVIS:

4            Q.   Mr. Reed, if you'll turn, please, to JJR-1 and

5       --

6                 CHAIRMAN CARTER:  Excuse me, Mr. Davis.  Would

7       you pull your mike a little closer to you?

8                 MR. DAVIS:  Yes, I'll be happy to.

9                 CHAIRMAN CARTER:  And what you just -- and say

10       what you just said again.

11                 MR. DAVIS:  I will.

12                 CHAIRMAN CARTER:  Because I didn't get it.

13       BY MR. DAVIS:

14            Q.   Mr. Reed, could you turn, please, to your

15       Exhibit 1?

16            A.   Yes.

17            Q.   And if you will turn to Page 3 of 36.

18            A.   You're referring to Exhibit 1 of the May

19       testimony then?

20            Q.   Yes, I am.

21                 CHAIRMAN CARTER:  What was the page again?

22                 MR. DAVIS:  It was the May testimony, and it

23       was Exhibit 1, Page 3 of 36 as the pagination is at the

24       top right hand of the page.

25                 CHAIRMAN CARTER:  Okay.  Thank you.  You may,

FLORIDA PUBLIC SERVICE COMMISSION

439

1       you may proceed.

2                 THE WITNESS:  I have that page.

3       BY MR. DAVIS:

4            Q.   Okay.  If you'll look at the -- first of all,

5       the, the second set of bullets on that page, do you see

6       those?

7            A.   Yes.

8            Q.   You developed a list of recommendations and

9       observations which are captured in those bullets; is

10       that right?

11            A.   That's correct.

12            Q.   And these were provided to FP&L when?

13            A.   With the publication of this report actually

14       just a few days slightly ahead of that.  So April of

15       2009.

16            Q.   So in April of 2009 that was, you know,

17       roughly the time when the feasibility analysis was being

18       presented to the Commission at the beginning of

19       May 2009.  These recommendations that you have here on

20       this page with these bullets had not been enacted or

21       implemented by FP&L at that time; correct?

22            A.   As I understand your question, were they

23       implemented by FPL by the time the feasibility analysis

24       was submitted in the May 1st filing?  I would say in

25       general they were.  We had provided these

FLORIDA PUBLIC SERVICE COMMISSION

440

1       recommendations to the company, as I said, several days

2       in advance of the publication of this document.  The

3       company, as I understand it, is implementing or is in

4       the process of implementing, was at that time all of the

5       recommendations.  There was no disagreement with regard

6       to their implementation.  So I would say they had been

7       adopted and they were in the process of being

8       implemented at that time.

9            Q.   But probably not reflected in the May 1st

10       filing with the Commission.

11            A.   Other than being included in this report, I

12       think that's accurate.

13            Q.   Okay.  Now look at the next paragraph, please.

14       And you state in the second sentence of the next

15       paragraph under these bullets, is -- and this is with

16       regard to both the Turkey Point 6 and 7 as well as the

17       EPU project, that it is important to note that as the

18       projects continue to move forward, the risks faced by

19       both projects will increase markedly.

20                 What were you referring to, what risks?

21            A.   The principal risk we're referring to there is

22       the risk of delay or schedule slippage.  The cost of a

23       delay is a function of the accumulated costs expended to

24       that point in time.  And obviously if you've only spent

25       $100 million, the cost of delay is just the carrying

FLORIDA PUBLIC SERVICE COMMISSION

441

1       cost on $100 million.  Once you've spent billions of

2       dollars, a slippage in the schedule, a slippage in the

3       online date adds many, many millions of dollars in terms

4       of additional carrying costs.  So the consequences of a

5       scheduled slippage, for example, become a much greater

6       risk as you have moved further into the project.

7            Q.   Now at the time that you prepared this report

8       and even at present, FPL has not entered into an EP

9       contract with Westinghouse/Shaw; correct?

10            A.   That's correct.

11            Q.   And that would be a milestone at which the

12       risk would increase substantially?

13            A.   Not necessarily.  An EP contract or an EPC

14       contract is really meant to address risk and to help

15       quantify, to help capture it and assign who is going to

16       bear that risk.  So signing a contract is a way of

17       defining those risks and quantifying them.  I don't

18       think it necessarily will increase the risks.

19            Q.   Is it fair to say, based on your experience in

20       the industry, that an EPC contractor like

21       Westinghouse/Shaw seeks to put as much risk on FP&L as

22       possible?

23            A.   No, I don't think that's fair.  In my

24       experience, the contractor, the prime contractor in that

25       example is willing to bear the risk at a price.  The

FLORIDA PUBLIC SERVICE COMMISSION

442

1       negotiations for an EPC contract decide who is best able

2       to handle that risk and who's best able to basically

3       shoulder the costs associated with that risk.  So the

4       contractor is willing to absorb risk, but it all comes

5       at a price.

6            Q.   So the more risk then that Westinghouse/Shaw

7       would be convinced to absorb, the higher the price once

8       they enter this EP contract.

9            A.   Generally, yes.

10            Q.   And you don't know at this point in time

11       whether the amount of money that FP&L is projecting for

12       2010 for the EP contract is sufficient for the amount of

13       risk that Westinghouse/Shaw is going to be willing to

14       bear.

15            A.   As Mr. Scroggs indicated, those negotiations

16       are currently ongoing, and the final terms and the

17       balance of risks are to be determined.  That will affect

18       the cost in 2010.  But, again, the benefit is waiting

19       until many of those risks are better understood, better

20       measured and better known and then negotiating the

21       contract rather than doing it in advance.

22            Q.   And as you understand this process of cost

23       recovery, if Westinghouse/Shaw is able to enact a higher

24       price for incurring certain risk than what's being

25       projected today, then FP&L will just true those up later

FLORIDA PUBLIC SERVICE COMMISSION

443

1       on.

2            A.   There will be a true-up in 2010 for the cost.

3       Again, at that time the decision to enter into an EP

4       contract or to not enter into it and the terms will be

5       subject to review.  That's when I would expect the

6       review to occur with regard to whether that allocation

7       of risks is appropriate.

8            Q.   Now if you'll turn, please, to Exhibit 4,

9       which is the last page of your JJR-1 from your May

10       testimony.  It, it's numbered 36 of 36.

11            A.   Yes, I have that.

12            Q.   This is your comparison of cost estimates for

13       AP 1000 reactors that you referred to in your summary;

14       is that correct?

15            A.   Well, specifically Exhibit JJR-3 to my April,

16       I'm sorry, to my March direct testimony is what I was

17       referring to.  I believe this is a similar document of a

18       slightly different vintage.

19            Q.   Is it a more recent vintage or a -- or not?

20            A.   I think it's about a month and a half later

21       than the version filed in March.

22            Q.   Now the statement has been made that Progress,

23       I'm sorry, that FP&L's high estimate is in the range of

24       other nuclear power projects for the AP 1000 that are

25       moving forward today.

FLORIDA PUBLIC SERVICE COMMISSION

444

1                 First of all, the dollars per kilowatt that

2       are referred to on the Florida Power & Light lines of

3       this Exhibit 4 differ between overnight and all-in

4       costs; is that right?

5            A.   That's correct.

6            Q.   A previous witness was asked about overnight

7       costs.  What do you mean by all-in costs?

8            A.   Those include escalation and AFUDC.

9            Q.   Now on the first line of this page dealing

10       with Florida Power & Light with the October 2007

11       estimate, you have $3,643 per kilowatt, and that's the

12       $8 billion project cost estimate.  Now explain how you

13       got an $8 billion project cost estimate there.

14            A.   That's from the information the company

15       published in October 2007 as the overnight costs

16       excluding inflation and AFUDC.

17            Q.   Okay.  And that, would that be a, a low,

18       medium or high cost?

19            A.   This is the midrange figure.

20            Q.   And when we look at the second line that we

21       have, again, October 2007 date of estimate, this is the

22       all-in cost and this shows a project cost of

23       $14 billion; is that correct?

24            A.   Yes.  Again, that's the midrange estimate.

25            Q.   So in -- just correct me if I'm wrong, but

FLORIDA PUBLIC SERVICE COMMISSION

445

1       between 12 billion and 18 billion, would 14 or 15 be the

2       midrange?

3            A.   Well, this was -- specifically 14.00 was the

4       number identified as the midrange estimate out of the

5       three.

6            Q.   I see.  So in both of these cases in comparing

7       project costs for FP&L to other AP 1000 reactors, you

8       were using the midrange in this table.

9            A.   For FPL, yes.

10            Q.   Okay.

11            A.   We also used the midrange for the others that

12       had a range published.

13            Q.   And what is the high range for FP&L for the

14       all-in cost?

15            A.   The high number is the number referred to with

16       Mr. Scroggs.  I believe it's 17.7 or 17.8 billion.

17            Q.   What is that per kilowatt?  Do you have that

18       on this table?

19            A.   No, I don't have it on the table.

20            Q.   Can you perform that calculation?

21            A.   I don't have a calculator with me, but it

22       would that be figure divided by 2,200 megawatts.

23            Q.   Is that approximately $8,000 per megawatt?

24            A.   Per kilowatt.  Yes.

25            Q.   Per kilowatt I mean.

FLORIDA PUBLIC SERVICE COMMISSION

446

1            A.   Yes.

2            Q.   Now you're aware, are you not, that FP&L is

3       now saying that their cost estimate is more the high

4       range than the midrange?

5            A.   I think the company has stated that they

6       expect the numbers to be between the midrange and the

7       high range, so somewhere in the upper half of its range.

8            Q.   Now these other costs that you have for other

9       reactor projects are the midrange though, you said.

10            A.   In all cases what we present here was the

11       midrange to try and keep the comparison as

12       straightforward as possible.

13            Q.   And did you take the Progress Energy cost

14       estimates for the Levy nuclear plant from the need

15       determination documents?

16            A.   No.  From their January 2009 information.

17            Q.   Now you're aware, are you not, that the

18       Tennessee Valley Authority has now backed out of its

19       AP 1000 project for the Bellefonte plant?

20            A.   It has suspended development.  I would not say

21       it's backed out of it.

22            Q.   And has there been an announcement by Duke

23       recently about its project?

24            A.   Not about this project that I'm aware of.  It

25       had an announcement about a separate project in Ohio.

FLORIDA PUBLIC SERVICE COMMISSION

447

1            Q.   Okay.  Was that an AP 1000 project?

2            A.   No.  That's an EPR project.

3            Q.   Now how did you determine if the costs were

4       comparable in comparing the FP&L project to Progress

5       Energy, for instance?

6            A.   We looked at the Progress Energy numbers with

7       and without transmission costs, and those numbers are

8       presented here between the line called Progress Energy

9       and Progress Energy Florida.  And what you see there of

10       course is that on an all-in basis, the 17 billion cost

11       estimate provided in January 2009 is consistent with the

12       upper end of the range for FPL's cost estimate.

13            Q.   So Progress's midpoint is consistent with

14       FP&L's upper end.  But do you know what Progress's upper

15       end is?

16            A.   I don't recall without going back and checking

17       the source material.

18                 CHAIRMAN CARTER:  Mr. Davis, are you about to

19       go down another line?

20                 MR. DAVIS:  No.  I think I'm actually finished

21       with this witness.

22                 CHAIRMAN CARTER:  Okay.  If you're finished,

23       that's a good time to finish because we're on lunch.

24       See you guys at 2:15.  `

25                 (Recess taken.)

FLORIDA PUBLIC SERVICE COMMISSION

448

1       STATE OF FLORIDA    )

:         CERTIFICATE OF REPORTER

2       COUNTY OF LEON      )

3

4                 I, LINDA BOLES, RPR, CRR, Official Commission

Reporter, do hereby certify that the foregoing

5       proceeding was heard at the time and place herein

stated.

6

IT IS FURTHER CERTIFIED that I

7       stenographically reported the said proceedings; that the

same has been transcribed under my direct supervision;

8       and that this transcript constitutes a true

transcription of my notes of said proceedings.

9

I FURTHER CERTIFY that I am not a relative,

10       employee, attorney or counsel of any of the parties, nor

am I a relative or employee of any of the parties'

11       attorneys or counsel connected with the action, nor am I

financially interested in the action.

12

DATED THIS _____ day of _____________________,

13       2009.

14

15                  ________________________________

LINDA BOLES, RPR, CRR

16                 FPSC Official Commission Reporter

(850) 413-6734

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION