853

1                              BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

3                                           DOCKET NO. 090009-EI

4       In the Matter of:

5       NUCLEAR COST RECOVERY CLAUSE.

______________________________/

6

7

8                               VOLUME 5

9                        Pages 853 through 1032

10              ELECTRONIC VERSIONS OF THIS TRANSCRIPT ARE

A CONVENIENCE COPY ONLY AND ARE NOT

11                THE OFFICIAL TRANSCRIPT OF THE HEARING.

THE .PDF VERSION INCLUDES PREFILED TESTIMONY.

12

13

PROCEEDINGS:           HEARING

14

15       COMMISSIONERS

PARTICIPATING:         CHAIRMAN MATTHEW M. CARTER, II

16                              COMMISSIONER LISA POLAK EDGAR

COMMISSIONER KATRINA J. McMURRIAN

17                              COMMISSIONER NANCY ARGENZIANO

COMMISSIONER NATHAN A. SKOP

18

19       DATE:                  Wednesday, September 9, 2009

20

TIME:                  Commenced at 9:30 a.m.

21

22       PLACE:                 Betty Easley Conference Center

Room 148

23                              4075 Esplanade Way

Tallahassee, Florida

24

25       REPORTED BY:           MARY ALLEN NEEL, RPR, FPR

854

1       PARTICIPATING:

2                 J. MICHAEL WALLS, ESQUIRE, and DIANNE M.

3       TRIPLETT, ESQUIRE, Carlton Fields Law Firm, Post Office

4       Box 3239, Tampa, Florida  33601-3239, representing

5       Progress Energy Florida, Inc.

6                 JOHN T. BURNETT and R. ALEXANDER GLENN,

7       Progress Energy Service Company, LLC, Post Office Box

8       14042, St. Petersburg, Florida  33733-4042, representing

9       Progress Energy Florida, Inc.

10                 EDGAR M. ROACH, JR., ESQUIRE, McGuire Woods,

11       P.O. Box 27507, Raleigh, North Carolina  37611,

12       representing Progress Energy Florida, Inc.

13                 VICKI GORDON KAUFMAN, ESQUIRE, and JON C.

14       MOYLE, JR., ESQUIRE, Keefe, Anchors, Gordon & Moyle, 118

15       North Gadsden Street, Tallahassee, Florida 32301,

16       representing Florida Industrial Power Users Group.

17                 JOHN W. MCWHIRTER, JR., ESQUIRE,

18       c/o McWhirter Law Firm, Post Office Box 3350, Tampa,

19       Florida 33601, representing Florida Industrial Power

20       Users Group.

21                 JAMES W. BREW, ESQUIRE, Brickfield, Burchette,

22       Ritts & Stone, 1025 Thomas Jefferson Street, NW, Eighth

23       Floor, West Tower, Washington, DC  20007, representing

24       White Springs Agricultural Chemicals d/b/a PCS

25       Phosphate.

855

1       PARTICIPATING (Continued):

2                 GARY A. DAVIS, ESQUIRE, Gary A. Davis &

3       Associates, Post Office Box 649, Hot Springs, North

4       Carolina  28779, representing Southern Alliance for

5       Clean Energy.

6                 CHARLES REHWINKEL, ESQUIRE, and JOSEPH

7       MCGLOTHLIN, ESQUIRE, Office of Public Counsel, c/o The

8       Florida Legislature, 111 W. Madison Street, Room 812,

9       Tallahassee, Florida  32399-1400, representing the

10       citizens of the State of Florida.

11                 KEINO YOUNG, ESQUIRE, LISA BENNETT ESQUIRE,

12       and ANNA WILLIAMS, ESQUIRE, FPSC General Counsel's

13       Office, 2540 Shumard Oak Boulevard, Tallahassee, Florida

14       32399-0850, representing the Commission Staff.

15                 MARY ANNE HELTON, ESQUIRE, and SAMANTHA

16       CIBULA, ESQUIRE, Florida Public Service Commission, 2540

17       Shumard Oak Boulevard, Tallahassee, Florida  32300-0850,

18       Advisors to the Florida Public Service Commission.

19

20

21

22

23

24

25

856

1                               I N D E X

2       OPENING STATEMENTS                                  PAGE

3            BY MR. BURNETT                                  860

BY MR. REHWINKEL                                864

4            BY MR. BREW                                     871

BY MR. DAVIS                                    878

5            BY MR. MOYLE                                    885

6

7

8                               WITNESSES

9

NAME                                                PAGE

10

WILL GARRETT

11

Prefiled Direct Testimony Inserted                   891

12

THOMAS GEOFF FOSTER

13

Direct Examination by Ms. Triplett                   912

14       Prefiled Direct Testimony Inserted                   915

Cross-Examination by Mr. Rehwinkel                   941

15       Cross-Examination by Mr. Brew                        943

Cross-Examination by Mr. Moyle                       945

16       Cross-Examination by Mr. Young                       947

17       JON FRANKE

18       Direct Examination by Ms. Triplett                   953

03/02/09 Prefiled Direct Testimony Inserted          955

19       05/01/09 Prefiled Direct Testimony Inserted          981

Cross-Examination by Mr. Rehwinkel                   999

20       Cross-Examination by Mr. Moyle                      1028

21       CERTIFICATE OF REPORTER                             1032

22

23

24

25

857

1                               EXHIBITS

2       NUMBER                                       ID.  ADMTD.

3        81       WG-1                               911     911

4        82       WG-2                               911     911

5        83 - 89  TGR-1 through TGF-7                        951

6        90       SH-1                                      1031

7       139       Updated Position to 32A            951     952

8       140       CR3 Uprate                         951     952

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

858

1                          P R O C E E D I N G S

2                 (Transcript continues in sequence from

3       Volume 4.)

4                 CHAIRMAN CARTER:  Good morning.  I would like

5       to call this hearing to order.  First of all, good

6       morning, everyone.  Everybody is looking bright-eyed and

7       bushy-tailed.  We'll probably keep the same schedule we

8       had yesterday, at least until 7:00, at least until then.

9       If we make any progress, we -- no pun intended.

10                 Before we begin, let me ask staff, any

11       preminary matters?  Ms. Helton, you're recognized.

12                 MS. HELTON:  Thank you, Mr. Chairman.  I would

13       like to enter an appearance, please, for Samantha

14       Cibula, who will be sitting in for me this morning and

15       advising you.

16                 CHAIRMAN CARTER:  Okeydokey.  Are there any

17       preliminary matters from -- I'll come back to you,

18       staff.  Let me go to the parties first.  Any preliminary

19       matters from the parties?

20                 MR. REHWINKEL:  No.

21                 CHAIRMAN CARTER:  Good morning, Mr. Rehwinkel.

22       Good to see you again.

23                 MR. REHWINKEL:  Good morning.

24                 CHAIRMAN CARTER:  Okay.  Staff, you're

25       recognized for preliminary matters.

859

1                 MR. YOUNG:  Yes, Mr. Chairman.  Item Number

2       130 on staff's -- on the Comprehensive Exhibit List, I

3       think that that item is no longer needed because it's a

4       part of staff's Comprehensive Exhibit List, excuse me,

5       and Ms. Triplett will talk about that.

6                 CHAIRMAN CARTER:  Okay.

7                 MS. TRIPLETT:  Thank you, Chairman.  My mic is

8       loud.

9                 CHAIRMAN CARTER:  We like it loud here.  We

10       like volume.

11                 MS. TRIPLETT:  I apologize.  It turns out that

12       it was marked as Exhibit 90, so we don't need Number

13       130.

14                 CHAIRMAN CARTER:  Are all the parties

15       comfortable with that?

16                 MR. REHWINKEL:  Yes.

17                 CHAIRMAN CARTER:  Okay.  So, Commissioners,

18       for the record, we will just mark an X as 130 not being

19       admitted, so we can go from there.

20                 Okay.  Staff, preliminary matters?

21                 MR. YOUNG:  Yes, sir.  At this time, we'll

22       begin the opening statement for Progress Energy Florida.

23       As indicated in the Prehearing Order, opening statements

24       shall not exceed 10 minutes per party, for PEF.

25                 CHAIRMAN CARTER:  Okay.  Is there anything

860

1       else, any other preliminary matters?  Mr. Burnett,

2       anything preliminary?

3                 MR. BURNETT:  No, sir.

4                 CHAIRMAN CARTER:  Mr. Rehwinkel, Mr. Davis?

5       Mr. Brew, good to see you.

6                 MR. BREW:  Thank you.  Good morning,

7       Mr. Chairman.  No, nothing.

8                 CHAIRMAN CARTER:  Okay.  Mr. Burnett, you're

9       recognized.

10                 MR. BURNETT:  Thank you, Mr. Chairman.  Good

11       morning, Commissioners.

12                 Commissioners, I would like to begin my

13       opening remarks by telling you what is not at issue in

14       this case this year with respect to the Levy and the

15       Crystal River 3 uprate projects.  There is no challenge

16       to the prudence of any cost or dollars spent on these

17       projects through 2008, there is no challenge to the

18       reasonableness of any cost or dollars spent on these

19       projects to date in 2009, and there is no challenge to

20       the reasonableness of any specific projected cost for

21       2010.

22                 There are three material issues that remain in

23       controversy in this case:  Number 1, was PEF prudent in

24       signing the EPC contract for the Levy projects; number

25       2, has PEF established that the Levy project remains

861

1       feasible; and number 3, has PEF been prudent in spending

2       money on the CR3 uprate project prior to obtaining a

3       license amendment from the Nuclear Regulatory

4       Commission.

5                 As to the first issue, the evidence in this

6       case will show that PEF was prudent in exercising the

7       EPC contract.  Specifically, Mr. Lyash and Mr. Miller,

8       who negotiated the EPC contract, will show that

9       executing the EPC was necessary to maintain the project

10       schedule.  They will also show that by signing the EPC,

11       PEF obtained beneficial contract terms for PEF and our

12       customers.  You will not hear any credible evidence that

13       disputes either one of these facts.

14                 As to the second issue, the Levy project

15       remains feasible, and we have presented sufficient

16       evidence to establish this fact.  You will hear both of

17       our witnesses, and you will hear OPC's witness tell you

18       that feasibility cannot be based on a CPVRR, a

19       cumulative present value revenue requirements analysis,

20       as some of the intervenor witnesses suggest.  In fact,

21       you will hear OPC's witness, Dr. Jacobs, testify that no

22       utility would evaluate a long-term base load nuclear

23       power plant on year-to-year changes in forecasts.  He

24       will also tell you that if a utility did use annual

25       forecasts to evaluate a long-term base load project, a

862

1       utility would never build a nuclear power plant or any

2       other base load project.  And again, that's not

3       Mr. Lyash or Mr. Miller.  That's OPC's witness, and we

4       couldn't agree with him more.

5                 Now, as to what feasibility does mean, the

6       evidence will establish that feasibility must be

7       analyzed on a qualitative basis that examines whether

8       the project can be physically completed, whether it can

9       be licensed, whether there are fundamental changes in

10       state or regulatory policy, and whether any significant

11       events have taken place, such as technology failures or

12       design flaws.  Our evidence will show that the Levy

13       plant remains feasible under this analysis, and you will

14       not hear any evidence to the contrary.

15                 Finally, as to the last material issue in

16       dispute, PEF's witnesses will establish that like every

17       other one of the hundreds of uprates that the NRC has

18       approved, PEF has developed and submitted a detailed NRC

19       application for the CR3 uprate that is based on a

20       substantial engineering analysis.  Just like the hundred

21       or so other applications just like this one that the NRC

22       has approved, the evidence will show that PEF has a high

23       degree of confidence that it will obtain the needed

24       approval from the NRC for the CR3 uprate project.  You

25       will not hear any witness dispute the fact that

863

1       incurring costs prior its license amendment request is

2       normal and expected, nor will you hear any challenge to

3       the detailed engineering analysis that PEF has performed

4       for its license amendment for CR3.

5                 In summary, Commissioners, the relevant issues

6       in this case are just as clear and succinct as PEF's

7       evidence, which will show that our actions and decisions

8       have been reasonable and prudent.  And we look forward

9       for addressing any questions that the Commission may

10       have.  Thank you.

11                 CHAIRMAN CARTER:  Thank you.  Before we go any

12       further, I know I did it yesterday, but I see a new

13       face, so out of abundance of caution, we'll redo the

14       taking of the appearances of the parties.  Mr. Burnett,

15       I know I did this yesterday, but let's do that again.  I

16       apologize to you.  You may begin.

17                 MR. BURNETT:  Thank you, sir.  John Burnett on

18       behalf of Progress Energy Florida.  I also have with me

19       Ms. Dianne Triplett from Carlton Fields.  Mr. Mike Walls

20       is also appearing with us.  He's defending a rate case

21       deposition.  We also have Ed Roach and Alexander Glenn

22       who is with us as well.

23                 CHAIRMAN CARTER:  Okay.  Mr. Rehwinkel.

24                 MR. REHWINKEL:  Good afternoon -- good

25       morning, Mr. Chairman.  Charles Rehwinkel and Joe

864

1       McGlothlin with the Office of Public Counsel on behalf

2       of the citizens of Florida.

3                 CHAIRMAN CARTER:  Mr. Brew.

4                 MR. BREW:  Good morning, Mr. Chairman and

5       Commissioners.  James Brew of the firm of Brickfield,

6       Burchette, Ritts & Stone for White Springs Agricultural

7       Chemicals.

8                 CHAIRMAN CARTER:  Mr. Davis.

9                 MR. DAVIS:  Yes.  Good morning, Mr. Chair and

10       members of the Commission.  Gary Davis for Southern

11       Alliance for Clean Energy.

12                 CHAIRMAN CARTER:  Okay.  Did I get -- I think

13       I got everybody yesterday, but out of an abundance of

14       caution and to have a clean record for this hearing, I

15       wanted to do that.  I hope I didn't throw anybody off by

16       doing that.

17                 Staff.

18                 MR. YOUNG:  Keino Young, Lisa Bennett, and

19       Anna R. Williams, staff.

20                 MS. CIBULA:  Samantha Cibula and Mary Anne

21       Helton, advisors to the Commission.

22                 CHAIRMAN CARTER:  Okay.  Now I feel so much

23       better.

24                 Mr. Rehwinkel, you're recognized.

25                 MR. REHWINKEL:  Thank you, Mr. Chairman.

865

1                 Commissioners, the Office of Public Counsel on

2       behalf of the 18 million citizens of Florida is here

3       today before you on a matter of singular importance both

4       to this state and its ratepayers.  We represent, as I

5       have said, the millions of customers in this state who

6       are being called upon today, and perhaps for years to

7       come, to pay for a nuclear plant that has yet to

8       generate electricity and potentially may never do so.

9       Hopefully it will.

10                 At the outset, we want to be clear that our

11       advocacy at this juncture is focused on a relatively

12       narrow issue of prudence and reasonableness of two areas

13       of the company's decision-making.  One deals with the

14       Levy nuclear project or LNP, and the other with the

15       Crystal River Unit 3 uprate project.

16                 The concerns we raise in our case, primarily

17       through the expert testimony of Dr. William R. Jacobs, a

18       nuclear engineer by undergraduate, graduate, and

19       doctoral education and extensive work experience, are

20       raised with respect for the dedication, sincerity, and

21       expertise of the employees of Progress Energy.  Our

22       purpose in this case is to raise concerns about

23       decisions that may yet prove to result in excess costs

24       to customers.

25                 We will ask you to decide, after hearing all

866

1       the evidence, to find that Progress has erred in its

2       judgment to sign the engineering, procurement and

3       construction or EPC contract on December 31, 2008.  In

4       the alternative, if you cannot reach such a decision, we

5       will ask that you hold off any decision of this aspect

6       of the LNP project until certain critical, relevant, but

7       as yet unknown information becomes known.  This could

8       either take the form of a spin-off docket or deferral of

9       this matter and a final decision in this matter until

10       the 2010 hearing cycle.

11                 With respect to the Crystal River 3 uprate,

12       our position is that the Commission, after hearing all

13       the evidence, should put the company on notice that its

14       sequence of expending hundreds of million of dollars

15       related to Phases 2 and 3 of this project before getting

16       authorization from the Nuclear Regulatory Commission may

17       not be prudent in light of the remaining licensing

18       challenges.

19                 The Public Counsel is not in a position to

20       seek disallowance of any costs at this current stage of

21       the docket relative to either project.  Our effort here

22       is to preserve under the rules and statutes governing

23       the recovery of pre-startup nuclear costs our rights to

24       challenge and the citizens' rights to challenge the

25       prudence of these costs if Progress does not obtain the

867

1       licensing it seeks.

2                 Commissioners, to step back for a moment, I

3       would like to frame the situation from the perspective

4       of customers.  For decades, and really forever, the law

5       of electric utility ratemaking in this state has been

6       that customers do not pay until a plant becomes

7       commercial, begins commercial service.  The State of

8       Florida, for good reasons, has changed this approach

9       with respect to new nuclear generation.  Customers now

10       pay for site selection, pre-construction, and certain

11       carrying costs in advance of commercial service for new

12       nuclear generation.  This abrupt policy shift even

13       requires customers to pick up the tab when a plant is

14       abandoned mid-construction or short of completion.

15                 As a check on this process, the Legislature

16       has entrusted to you the obligation to monitor costs for

17       reasonableness, prudence, and ongoing long-term

18       feasibility.  In this way, customers are protected from

19       utility decision-making that might otherwise ignore

20       unreasonable cost escalation or that might take

21       excessive risks.  In this new era that seeks to foster

22       the expansion of new nuclear generation, your vigilance

23       is the saving grace for a ratemaking model that has

24       generated significant concern from the public.  It is

25       this aspect of the new statutory framework that the

868

1       citizens invoke here today.

2                 Our case is relatively simple and

3       straightforward.  However, that simplicity belies the

4       seriousness of the matter before you.

5                 PEF seeks extraordinary recovery of

6       significant costs of the construction and licensing of a

7       $17 billion nuclear generating complex.  This is a large

8       and complex management, finance, and engineering

9       undertaking.  The fact that it is a human endeavor means

10       mistakes will be made.  That fact alone means that the

11       standard of care is essentially what was known or

12       reasonably should have been known by the management at

13       the time of making decisions that might be questioned.

14                 With regard to the LNP project, the issue

15       before you is whether PEF acted reasonably and prudently

16       when it signed a multi-billion-dollar contract with the

17       Consortium.  Dr. Jacobs provides thoroughly documented

18       expert testimony that casts serious doubt on whether the

19       signing of the contract was prudent or reasonable under

20       the circumstances that PEF knew or reasonably should

21       have known at the time of signing.

22                 Our case demonstrates that PEF either knew or

23       should have know that the NRC's effective denial of its

24       limited work authorization or LWA was such a real

25       possibility, or even probability, that they should have

869

1       delayed the signing of the EPC until at least the end of

2       January 2009, when they had a very good idea they were

3       going to get the NRC's decision on the time frame.  By

4       ignoring the NRC's patently skeptical approach to the

5       complexity of the site geology and all the information

6       within its knowledge, PEF has potentially exposed the

7       company and its customers to costs greater than would

8       have been incurred had they waited a few days to see

9       what the NRC was going to say about the review schedule.

10                 We urge you to consider all the evidence,

11       including the direct, rebuttal, and cross-examination.

12       A significant portion of this case involves geological

13       information and the regulatory process at the NRC which

14       considers that information.  As a fellow regulatory

15       body, you are well positioned to understand that

16       presumptions of correctness generally do not accompany

17       regulatory filings, nor do rules promulgated carry with

18       them a presumption of favorable action.  We ask you to

19       listen to the evidence and then decide were the actions

20       of PEF reasonable under the circumstances that PEF knew

21       or should have known regarding the likelihood of a

22       favorable LWA approval.  We believe the evidence

23       supports either a finding that they erred in prematurely

24       signing a contract or that you may find cause to spin

25       off or defer the determination for further evidence

870

1       gathering once certain cost facts have been established

2       after renegotiation.

3                 We further submit that due to the major

4       retrenchment caused by the schedule shift and the need

5       to renegotiate the EPC, PEF cannot have effectively done

6       an appropriate feasibility analysis.  We support you

7       directing that the analysis be done once costs are known

8       after the renegotiation occurs.

9                 Finally, Commissioners, the Public Counsel is

10       asking that PEF be put on notice that the costs for

11       Phases 2 and 3 of the CR3 extended power uprate that

12       have been expended while there is a reasonably

13       significant degree of uncertainty about obtaining NRC

14       approval should be subject to disallowance as being

15       imprudent.  PEF has taken a significant gamble with

16       ratepayer funds on an unprecedented, first-of-its-kind

17       uprate.  While we laud the initiative and engineering

18       expertise, the nature of the novel up-front cost

19       recovery opportunity requires that PEF's actions be

20       closely scrutinized in this case.  We are not asking for

21       any disallowance here.  Dr. Jacobs has offered his

22       expert opinion that the sequence of spending and

23       licensing is incorrect and may be imprudent.

24                 Thank you very much for your patience, and we

25       look forward to putting our case on.

871

1                 CHAIRMAN CARTER:  Before I go to Mr. Brew,

2       Captain McNeill, you want to enter an appearance on this

3       matter?  I wanted to try to keep a clean record for both

4       the FPL and the Progress -- good morning.

5                 CAPTAIN McNEILL:  Good morning, sir.  I

6       actually don't represent the Navy in this case.

7                 CHAIRMAN CARTER:  On this one?

8                 CAPTAIN McNEILL:  Yes.  I don't, sir.

9                 CHAIRMAN CARTER:  Okay.  Thank you very

10       kindly.

11                 CAPTAIN McNEILL:  Thank you.

12                 CHAIRMAN CARTER:  I certainly wanted to give

13       you an opportunity.

14                 COMMISSIONER EDGAR:  Mr. Chairman, now that

15       I've had my second cup of coffee for the morning on our

16       eighth or something day straight in the hearing room, I

17       would like to put in an appearance as well.

18                 CHAIRMAN CARTER:  Good to see you.

19                 COMMISSIONER EDGAR:  Thank you.

20                 CHAIRMAN CARTER:  Good morning and welcome.

21                 Mr. Brew.

22                 MR. BREW:  Thank you.  Good morning, Chairman

23       and Commissioners.

24                 Progress Energy has not finally determined

25       whether it intends to proceed with building the Levy

872

1       units, notwithstanding the need determination last year

2       or the State's siting certificate approval.  The utility

3       is keeping its options open with an eye on key factors

4       that may ultimately influence that decision to go

5       forward.  One such factor certainly is cost.  This

6       approach is certainly necessary under any circumstances,

7       given the delays and changes evidenced, as discussed

8       yesterday, by TVA and Duke on their planned nuclear

9       programs.

10                 But these are not any circumstances.  Apart

11       from declining load and plunging fuel prices, Progress

12       has a serious problem with its planned schedule for the

13       Levy units that the Public Counsel has addressed in

14       detail.  Potential Levy partners, in Progress's own

15       words, are exercising common sense in awaiting

16       resolution of the schedule and revised TPC before making

17       any commitments.  Any reasonable management would do no

18       less at this point.  It should need to have a better

19       idea of what it is getting into, what the costs are and

20       what the risks are before making any commitment.  The

21       smart thing to do, the prudent thing to do is to soberly

22       assess the relative merits of moving forward with a

23       project that, at least in Progress's case, would already

24       triple the existing rate base of that company.

25                 Florida ratepayers do not have that option.

873

1       As Mr. Rehwinkel just noted, we are compelled to fund

2       the project up front to the tune of billions of dollars

3       for what now appears to be at least a decade before

4       we'll start seeing anything in return.

5                 Now, this is the first year that the

6       Commission has addressed the feasibility portion under

7       the new nuclear recovery rule, and a critical fact to

8       keep in mind is that the nuclear recovery rule does not

9       in the slightest change the risks, the financial risks

10       of building a nuclear power plant.  It does not speed up

11       the NRC's licensing review.  It does not move vendor

12       queues.  It does not improve the availability of nuclear

13       qualified labor.  What the rule does is, it promotes

14       nuclear development in Florida by shifting financial

15       risk to Florida consumers.  Now, how far consumer necks

16       are stuck out on this is purely a function of the

17       reviews in this docket, and particularly the feasibility

18       review.

19                 What the feasibility review is intended to do

20       is determine on an ongoing basis whether the project

21       continues to make economic sense for Florida consumers,

22       exercising the same financial costs that Progress is

23       exercising, that other utilities are exercising, that

24       Wall Street is exercising, that potential partners are

25       exercising.  That's the purpose of this review in this

874

1       docket.  To do otherwise and not regularly and seriously

2       examine the economics of moving forward in this economy,

3       with the uncertainty now associated with the Levy

4       project, would defy common sense as well as the plain

5       language of the rule.

6                 Now, PCS has introduced testimony by Peter

7       Bradford.  Mr. Bradford has sat in your place for many

8       years.  He chaired two state commissions in New York and

9       Maine at a time when the commissions needed to deal with

10       the recovery of nuclear costs.  He served as a

11       commissioner at the Nuclear Regulatory Commission during

12       the licensing of the first generation of nuclear plants.

13       You would be hard pressed to find anybody that has dealt

14       with the questions from a ratemaking perspective of

15       recovering the costs of nuclear power plants than

16       Mr. Bradford.

17                 Moving on to specifically on the feasibility

18       questions, it should certainly seem odd that Progress

19       would file updated fuel and environmental forecasts and

20       do nothing with them.  It's as though they serve no

21       purpose in this case.  Those projections, of course, go

22       exactly to the ultimate question as to whether or not

23       consumers have any reasonable expectation that the

24       extraordinary investment we're making up front in this

25       project are ever likely to benefit ratepayers in the

875

1       future.  That's why the Commission ordered them in the

2       need docket, along with updated construction data.

3                 Now, Progress does not offer the detailed

4       feasibility evaluation that's required by the rule.

5       Instead, Progress suggests simply that as long as they

6       haven't changed their mind, there's no new legislative

7       barriers, or the NRC hasn't disapproved the project,

8       that it needs to go forward.  That flies in the face of

9       what they're doing, which is hedging their bets, and

10       what needs to be done under any common sense assessment

11       of the long-term risks for the project.

12                 The company's generic reference to fuel

13       diversity, low carbon emissions, and expected low fuel

14       costs of building any nuclear unit anywhere in Florida

15       at any time at any cost is, to say the least,

16       insufficient.  The rule is in fact project-specific,

17       requiring a detailed analysis of the long-term

18       feasibility of completing the power plant.  We don't

19       have that here.  It cannot be satisfied by a simple

20       reference to the nominal virtues of nuclear power.  That

21       would render the annual feasibility review pointless.

22       It is in fact vital.

23                 Now, we understand that much has changed, in

24       fact, almost everything has changed from the need case.

25       But looking at them in short order, Progress can't say

876

1       when it expects either Levy unit to be in service.  It

2       can't say what its updated costs of the facilities are

3       likely to be.  It can't say whether it still plans to

4       build them in close parallel tracks, or if in fact it

5       plans to build two units at all.  You don't have that

6       basic information.  Without that, Progress has little

7       hope of securing a financial partner for the project, at

8       the same time, without this basic information, Progress

9       doesn't have reasonable basis for asserting that

10       continuing with the project is feasible.

11                 Now, on the external side, you've had negative

12       customer growth by Progress for the first time ever.

13       The company's last Ten-Year Site Plan reduced their

14       long-term growth forecasts.  You have natural gas prices

15       that have plunged, and most updates expect that to be,

16       if not permanent, certainly long-term in terms of the

17       forecast for fuel supply in this country.  The magnitude

18       and apparent persistence of these sea changes can't be

19       reasonably ignored.

20                 Our recommendation on this docket is that,

21       first, the Commission needs to require Progress to

22       provide detailed, updated cost and schedule information

23       for the project and that the Commission's approval for

24       estimated cost needs to be tied to that.  We need to

25       have information before we authorize cost recovery.

877

1                 Second, we need updated information that's

2       actually relevant.  Reference to stale data from the

3       need docket shouldn't be accepted.

4                 Third, there are certain permanent

5       ramifications of the schedule slip.  Progress forecasted

6       capacity need in 2016.  Well, neither Levy unit can meet

7       that now.  The company is going to have to either

8       acquire or build additional capacity to meet that

9       capacity need.  That in turn will affect the need for

10       the Levy units.  That has to be addressed.

11                 Also, Progress's strategy from the need docket

12       was to be a first mover, to be at the front of every

13       line.  Well, with the schedule slip, it's not apparent

14       that they'll be at the front of any line anymore.  In

15       fact, they may be at the end of the line for the first

16       wave of plants.  That may affect the timing and the

17       ability to get long lead time equipment and other

18       materials.  That needs to be addressed.

19                 On the prudence side, PCS agrees with OPC that

20       there are significant questions associated with the

21       limited work authorization and the execution of the Levy

22       EPC last year.  From our perspective, based on the

23       testimony and the discovery, it simply appears that the

24       NRC was doing their job and that Progress assumed

25       silence to be acquiescence was not reasonable under the

878

1       circumstances at the time.  Our suggestion is that that

2       be spun off into a separate docket where Progress has

3       the burden of proof of moving forward to demonstrate its

4       reasonableness.

5                 Finally, it's already apparent that Progress

6       consumers alone can't afford the rate impacts being

7       produced by the Levy project.  About half of the cost

8       recovery authorized for 2009 was deferred until next

9       year.  The company now proposes that the lion's share of

10       the costs that they want approved for next year be

11       deferred again.  There's only so far we can go with

12       accounting before we have to confront the rate impacts

13       for consumers.  Our suggestion is that once we have

14       updated costs and schedule, then we need to set spending

15       limits that are consistent with the rate impacts so that

16       we avoid a train wreck under the nuclear cost recovery

17       rule.

18                 Thank you very much.

19                 CHAIRMAN CARTER:  Thank you.  Mr. Davis.

20                 MR. DAVIS:  Good morning, Mr. Chair and

21       Commissioners.  I'm going to try not to repeat any of

22       the points that have been made, and also the points that

23       we made yesterday as well.

24                 But yesterday SACE did focus on the impacts to

25       ratepayers of the FP&L Turkey Point 6 and 7 proposed

879

1       cost recovery, and these impacts are much greater with

2       Progress Levy, and we want to point that out and put

3       some numbers to it.  If the cost recovery amounts were

4       done based on the normal rule, it would add up to $13

5       per month to the bills of ratepayers in its territory in

6       2010.  It would be $29 per month by 2017, when it

7       doesn't look like there will be any electricity

8       generated by the units at that time.  And just to

9       reiterate, as with FP&L, these rate increases would be

10       on top of the base rate increases that Progress is

11       proposing and I think you have coming up in another

12       hearing soon.

13                 We also are going to focus in this hearing on

14       the feasibility issue.  We believe that the other

15       intervenors will cover the imprudence of Progress

16       entering into the EPC contract prior to the approval of

17       the limited work authorization from the NRC quite

18       thoroughly.  We're going to focus on the lack of

19       long-term feasibility of the new nuclear reactors, and

20       we're going to again present the testimony of Dr. Mark

21       Cooper and Arnie Gundersen.

22                 As you heard yesterday, Mr. Gundersen has 35

23       years of experience in the nuclear industry as an

24       engineer, and you heard Dr. Cooper's experience in

25       economic analysis of energy issues.  They are going to

880

1       basically say the same thing about the circumstances

2       that have changed dramatically since the need was

3       determined for the Progress Levy facilities.  I'm not

4       going to reiterate those circumstances.  Mr. Brew just

5       went through those.

6                 I will bring you back to your rule again that

7       we're dealing with here on feasibility.  The

8       Commission's rule requires that a utility seeking cost

9       recovery for nuclear project costs shall submit for

10       Commission review and approval -- I underline that

11       again -- a detailed analysis of the long-term

12       feasibility of completing the power plant.  SACE

13       believes that this is not a hollow requirement.

14       Progress, on the other hand, asserts that feasibility

15       has nothing to do with economic feasibility, and that's

16       going to be a different issue than you heard yesterday.

17                 You know, again, I'll come back to the fact

18       that with cost recovery, when the utilities bet the farm

19       on a $17 billion project, the ratepayers suffer if the

20       bet goes bad.  And in this case, we have with the Levy

21       project Progress betting a lot more sooner, and they're

22       even raising the stakes as the odds are getting worse.

23       That's kind of the situation we're in with Progress.

24                 We have these factors that we discussed

25       yesterday and that Mr. Brew has spoken of this morning,

881

1       and any one of the factors, these dramatically changed

2       circumstances, would be enough to render a nuclear power

3       plant too risky right now.  As a matter of fact, you'll

4       hear, and you heard some testimony yesterday about the

5       fact that most of the other utilities who are in the

6       first wave with the AP-1000 reactor are hurrying to the

7       back of the line.  Everyone is trying to get out of the

8       first wave now and move to the second wave.  I guess

9       they could keep -- you know, leapfrogging backwards is

10       where we're going with this.

11                 The TVA Bellefonte plant, as you heard, is no

12       longer the reference combined operating license

13       application with the NRC, and Moody's has just given the

14       Southern Company Vogtle plant a negative advise on their

15       financing.  And SCANA, as you heard yesterday, has had a

16       downgrade from Moody's.  Duke Lee in South Carolina is

17       being delayed.

18                 And so everyone is rushing to the back of the

19       line rather than marching forward with these plants, and

20       for good reason, because these factors that we've

21       discussed at length and will continue to discuss are

22       kind of a perfect storm, coming all together as they do.

23       When they do come together like this, it's overwhelming

24       that a nuclear power plant is a risky investment at this

25       point.

882

1                 Now, one difference between the Progress

2       project and FP&L, as we discussed yesterday, is that

3       Progress has already been forced to accept the reality

4       that its aggressive schedule cannot be met.  We

5       presented a lot of information yesterday about an

6       aggressive schedule by FP&L, but Progress has already

7       been forced to accept that reality.  And we don't know

8       today how far that slippage will go, or we don't know

9       how much it's going to cost, because Progress has not

10       provided those numbers to the Commission.

11                 But ironically, though, while proposing a

12       slower schedule now, with a focus on obtaining its

13       combined operating license rather than on construction

14       activities, Progress's 2009 and 2010 costs that it seeks

15       recovery for are astronomical.  It proposes to charge

16       the ratepayers for nearly 400 million for these two

17       years, including 300 million in engineering design and

18       procurement costs.  In contrast, FP&L, which was

19       proposing essentially the same approach, was going to be

20       charging the ratepayers 58 million.

21                 And so SACE is suggesting a somewhat different

22       tack than the other intervenors, that, number one, you

23       disapprove the long-term feasibility analysis, but

24       number two, that you do not approve these 2009 and 2010

25       costs going forward without a better analysis that

883

1       demonstrates that they really are reasonable costs.

2                 We don't believe that they are.  We don't

3       believe that they should be moving forward and spending

4       this kind of money and charging it to the ratepayers,

5       and so -- we also don't want to have other dockets to

6       deal with these issues.  We believe that this is the

7       docket to deal with all the issues regarding the

8       long-term feasibility, and that the Commission can make

9       a decision in this docket, and should.  It then would be

10       up to Progress to come back if they want to and try to

11       demonstrate the long-term feasibility to rev the process

12       back up again if they choose, but there's no reason why

13       we should string this out.

14                 Now, Progress disputes the purpose behind the

15       annual feasibility analysis, and I guess that's why they

16       did not comply with the conditions that the PSC placed

17       on the need determination order in 2008.  Progress did

18       not provide the economic analysis that it was clear from

19       the order that the Commission was seeking.  The

20       Commission wasn't just seeking the updated fuel

21       forecasts and updated environmental forecasts and

22       updated capital cost estimates just to have those

23       numbers.  I mean, it was obviously seeking an updated

24       economic analysis of the feasibility of these units.

25                 Now, while Progress did provide an updated

884

1       fuel forecast and an updated environmental forecast, we

2       believe that both of these are flawed and shouldn't be

3       relied upon, for a lot of the reasons that have been

4       discussed previously.  But Progress did not provide an

5       updated project cost.  We're in the same position where

6       we're relying upon 2007 estimates.  And certainly

7       circumstances have changed, and an updated cost is

8       necessary before you can approve it.

9                 Now, again, Progress argues that feasibility

10       only means that the project is technically and legally

11       feasible, and they further ague that nuclear power

12       investments should be exempt from a demonstration of

13       economic feasibility once the need determination is

14       made.  That's not the way we read the long-term

15       feasibility requirement.  Based on the Commission's

16       requirements in the need determination, we don't believe

17       the Commission agrees with Progress's interpretation

18       either.

19                 Progress has forgotten that the cost recovery

20       provision is an extraordinary incentive that comes with

21       heightened scrutiny by the PSC of the long-term

22       feasibility of the project.  If Progress is unwilling to

23       accept that scrutiny, particularly the economic

24       scrutiny, then it can build the Levy plant without cost

25       recovery.  Of course, the company would not accept that

885

1       risk, but it's willing to place it on its ratepayers.

2                 Thank you.

3                 CHAIRMAN CARTER:  Mr. Moyle, before giving

4       your opening statement, so we can keep the record clear,

5       go ahead on and enter your appearance, as well as if

6       you've got a co-counsel with you today.  You're

7       recognized.

8                 MR. MOYLE:  Thank you, Mr. Chairman.  Jon

9       Moyle along with Vicki Kaufman and John McWhirter on

10       behalf of FIPUG.  And I apologize for my dilatory

11       appearance this morning and have just a brief opening

12       statement that I would like to make and reiterate some

13       points that have been made this morning and also that

14       were made yesterday.

15                 You know, to step back and put this in

16       perspective, this is another ask of charges that would

17       be put on consumers.  The Legislature has provided a

18       mechanism for this to be reviewed, which is what you all

19       are doing.  And I would argue, while it's different, it

20       needs to be a rigorous and robust review, not dissimilar

21       to what you're being asked to do in rate cases that are

22       before you, where you dig in, get into the details, look

23       hard at what is being asked.

24                 And the notion of long-term feasibility is one

25       that's an important criteria.  And I think it's a very

886

1       difficult question or ask of this Commission to approve

2       long-term feasibility when a fundamental question, which

3       is, "What's this going to cost?" cannot be answered.

4       You know, here you have information being provided,

5       "Well, it's 17.2 billion, but, you know, we're not

6       really certain about that number, because some things

7       have happened.  There are some delays, and we're going

8       to have to go back and renegotiate a contract."

9                 You heard Mr. Reed from the Wharton School of

10       Business yesterday talk about nuclear projects and delay

11       having a significant impact on them.  Well, this project

12       is not immune from that.  The delays are going to have a

13       significant impact.  And we would argue, before you can

14       make a judgment on long-term feasibility, you've got to

15       know what the cost is.

16                 You know, the technical aspects, that's one

17       issue.  But if you look at the rule, it doesn't modify

18       long-term feasibility in any way to limit what you look

19       at.  And surely, in making that judgment, cost is a very

20       critical component.  I mean, it's something that my

21       clients and others are enduring, having to feel today.

22       And the costs are significant, you know, $12 per

23       residence here that's being deferred, a portion of it,

24       because it's a very significant issue.  And as you

25       undertake to review this and to analyze it, we would ask

887

1       that you keep in mind that is a key component.

2                 The other piece that we touched on a little

3       bit yesterday is, you know, in this proceeding, you have

4       Florida Power & Light and Progress Energy, and it has

5       kind of been split up, probably for convenience.  But,

6       you know, again, we have five of these projects, these

7       AP-1000 projects that are pending before the NRC, and

8       Florida as a state has two of them.

9                 I'm representing a client, and you all have

10       more of a policy role to consider.  But we would urge

11       you, given all the uncertainties and the questions, to

12       ask for additional detail and to send a message that

13       these companies should seriously consider strategic

14       partnerships, which is what Wall Street is saying to

15       them.  I don't think anybody is disagreeing that

16       strategic partnerships make sense, but to send that

17       message to them.

18                 Mr. Olivera recently provided sworn testimony

19       to you where he said they look to signals from this

20       Commission as to what direction to head.  And we think

21       that this proceeding provides you an opportunity to send

22       a serious, strong signal about a strategic partnership

23       so that consumers aren't paying double.  I mean, it's

24       the Walmart effect.  My clients, both in the FPL and in

25       the Progress service territory are, in effect, going to

888

1       be paying double for this, and largely because there's

2       not a strategic partnership.  It's a lot of risk for the

3       companies, and it's a lost of risk for the State.  And

4       we think that, particularly given the downturn in demand

5       and the changed circumstances, that there ought to be a

6       serious analysis of a strategic partnership.

7                 The final point I would make is that this

8       State operated for many, many years with a 15 percent

9       reserve margin.  There was a discussion about that.  It

10       kind of through a settlement went up to 20 percent.  But

11       if you -- you know, if you make a changed assumption

12       with respect to is 17.5 the right number, I mean, that

13       potentially gives you lots of opportunities to force and

14       forge a strategic partnership.

15                 So those are two key points I wanted to

16       briefly make.  I look forward to the testimony today and

17       to continuing to explore this further.  And again, my

18       apologies for having to run a few minutes late.

19                 CHAIRMAN CARTER:  Thank you, Mr. Moyle.

20                 Are the witnesses here in the room that will

21       be testifying today?  If you will be testifying in this

22       matter, would you please stand so I can swear you in as

23       a group?  Would you please raise your right hand?

24                 (Witnesses collectively sworn.)

25                 CHAIRMAN CARTER:  Thank you.  Please be

889

1       seated.

2                 Also, just kind of a reminder to those of you

3       that saw it done yesterday and those of you that are new

4       to the process, these lights here will help you with

5       keeping your timing.  Green is always good.  The amber

6       light lets you know you've got two minutes left, and the

7       red light lets you know you have 30 seconds left in the

8       process of doing your summary of your testimony.

9                 Staff, are there any other preliminary matters

10       before we begin with the witnesses?

11                 MR. YOUNG:  Just a reminder, Mr. Chairman,

12       that witness summaries, if any, shall not exceed five

13       minutes per witness for each -- for the Progress

14       petition.  Several witnesses will testify as a panel.

15       Summaries of these witnesses shall not be more than five

16       minutes total.

17                 CHAIRMAN CARTER:  Okay.  Are all parties

18       comfortable with that?  You guys remember that?

19                 Okay.  Mr. Burnett, you're recognized.  Call

20       your first witness.

21                 MR. BURNETT:  Thank you, sir.  With your

22       permission, I'll turn it over to Ms. Triplett for the

23       first witness.

24                 CHAIRMAN CARTER:  Ms. Triplett, you're

25       recognized.

890

1                 MS. TRIPLETT:  Thank you.  PEF's first witness

2       is Will Garrett, and he was stipulated to and excused

3       from the proceeding.

4                 CHAIRMAN CARTER:  Okay.  Let's deal with

5       Mr. Garrett's -- is that correct, the parties stipulated

6       to -- okay.  Let's do this, then.  The prefiled

7       testimony of the witness will be inserted into the

8       record as though read.

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

911

1                 CHAIRMAN CARTER:  Were there any exhibits for

2       this witness?

3                 MS. TRIPLETT:  Yes, sir.  There were two, and

4       they're marked 81 and 82 in staff's composite exhibit

5       list.

6                 CHAIRMAN CARTER:  Are there any objections?

7       Without objection, show it done.  Eighty-one and 82 are

8       entered.

9                 (Exhibits Number 81 and 82 were identified and

10       admitted into the record.)

11                 MS. TRIPLETT:  Thank you, sir.

12                 CHAIRMAN CARTER:  That should conclude it for

13       witness Garrett; correct?

14                 MS. TRIPLETT:  Well, he has rebuttal

15       testimony, and I was going to move that in when we got

16       to that point, if that was okay with you.

17                 CHAIRMAN CARTER:  Okay.  That's fine.  We'll

18       do it during the course of rebuttal.  Call your next

19       witness.

20                 MS. TRIPLETT:  Thank you.  Progress Energy

21       Florida calls Geoff Foster, Thomas Geoff Foster to the

22       stand.

23                 CHAIRMAN CARTER:  Thomas Geoff Foster.

24

25

912

1       Thereupon,

2                         THOMAS GEOFF FOSTER

3       was called as a witness on behalf of Progress Energy

4       Florida and, having been first duly sworn, was examined

5       and testified as follows:

6                          DIRECT EXAMINATION

7       BY MS. TRIPLETT:

8            Q.   Will you please introduce yourself to the

9       Commission and provide your address?

10            A.   Yes.  My name is Thomas Geoffrey Foster.  My

11       business address is 299 First Avenue North,

12       St. Petersburg, Florida.

13            Q.   Who do you work for, and what is your

14       position?

15            A.   I work for Progress Energy Services Company as

16       the Supervisor of Regulatory Planning.

17            Q.   And have you filed prefiled direct testimony

18       and exhibits in this proceeding?

19            A.   Yes.

20            Q.   And do you have that prefiled testimony and

21       exhibits with you?

22            A.   I do.

23            Q.   Do you have any changes to make to your

24       prefiled testimony and exhibits?

25            A.   No changes.  However, there are two schedules

913

1       we prepared regarding my testimony that Ms. Triplett has

2       and is prepared to distribute.

3                 MS. TRIPLETT:  Chairman, with your pleasure.

4       We have already discussed these two schedules with staff

5       and the parties, and they were in agreement with them,

6       and I can distribute them to the clerk and

7       Commissioners.  I thought if it was okay, we could mark

8       them as exhibits.

9                 CHAIRMAN CARTER:  Okay.  Let's do this.  Let's

10       -- do all the parties -- let's do it this way.  Do all

11       the parties have these?

12                 MS. TRIPLETT:  I think the only party perhaps

13       who doesn't have it is Mr. Moyle.

14                 CHAIRMAN CARTER:  Okay.  Let's make sure

15       Mr. Moyle has it.  Staff, do you have it?  And a copy to

16       the Commissioners before we go any further with the

17       witness.

18                 MS. TRIPLETT:  Thank you.

19                 CHAIRMAN CARTER:  And we'll deal with -- we'll

20       deal with marking it and giving it a number after we get

21       ready to -- we can probably do it after he has his --

22       well, I want to make sure every has an opportunity to

23       look it over.  We'll deal with it as we deal with

24       exhibits.  Just bring it up, and then we'll give it a

25       number at that point in time.  Okay?

914

1                 MS. TRIPLETT:  Okay.  Yes, sir.

2       BY MS. TRIPLETT:

3            Q.   Mr. Foster, if I asked you the same questions

4       in your prefiled testimony today, would you give the

5       same answers that are in your prefiled testimony?

6            A.   Yes.

7                 MS. TRIPLETT:  We request that the prefiled

8       testimony be entered into the record as though read.

9                 CHAIRMAN CARTER:  The prefiled testimony of

10       the witness will be inserted into the record as though

11       read.

12

13

14

15

16

17

18

19

20

21

22

23

24

25

941

1       BY MS. TRIPLETT:

2            Q.   Mr. Foster, do you have a summary of your

3       prefiled testimony?

4            A.   I do.

5            Q.   Would you please summarize your prefiled

6       testimony for the Commission?

7            A.   Yes.  Good morning.  My name is Thomas

8       Geoffrey Foster.  I presented testimony regarding the

9       company's 2009 actual/estimated and 2010 projected costs

10       for the Crystal River uprate as well as the Levy nuclear

11       projects.  My testimony also presents total estimated

12       revenue requirements 2010 for purposes of setting 2010

13       rates in the capacity cost recovery clause.

14                 I'm available to answer questions regarding my

15       testimony.  Thank you.

16                 CHAIRMAN CARTER:  You get points for being

17       brief.

18                 Mr. Rehwinkel, you're recognized.

19                 MR. REHWINKEL:  Thank you, Mr. Chairman.  I

20       hope I get points for being brief too, because I have a

21       few recordkeeping questions for Mr. Foster.

22                           CROSS-EXAMINATION

23       BY MR. REHWINKEL:

24            Q.   Can you turn to TGF-2, page 3 of 3, on

25       Schedule P-8 of your May 1st testimony?

942

1                 CHAIRMAN CARTER:  Commissioner Skop.

2                 COMMISSIONER SKOP:  Thank you.  Can

3       Mr. Rehwinkel repeat that a little bit more slowly,

4       please.  Thank you.

5                 MR. REHWINKEL:  Yes.  This is behind Tab

6       Number TGF-2, and it is Schedule P-8, and page 3 of 3,

7       Levy County Nuclear Units 1 and 2.

8       BY MR. REHWINKEL:

9            Q.   Do you have that, Mr. Foster?

10            A.   Yes, sir, I'm there.

11            Q.   And good morning, by the way.

12            A.   And I don't want to cut you off, but I did not

13       sponsor this -- I sponsored this schedule, but it is

14       addressed by -- or it's attached to my testimony, but I

15       do not sponsor it.

16            Q.   Okay.

17            A.   I just wanted to make sure that's clear up

18       front.

19            Q.   I just wanted to ask you a question, and you

20       can answer it that way if you want.  And this is a

21       confidential exhibit that I'm referring to, so I do not

22       want to ask you to state any numbers or any confidential

23       information here.  But on line 15, there in column H, to

24       your knowledge, has that number changed that is in line

25       15, column H?

943

1            A.   I do not have any knowledge of that at this

2       time.  That would probably be something best addressed

3       to Mr. Miller.

4            Q.   Okay.  To your knowledge, have any of the

5       numbers related to the Levy nuclear plant changed such

6       that your schedules would need to be updated?

7            A.   No.  No, sir.

8                 MR. REHWINKEL:  Okay.  That's all the

9       questions I have.  Thank you.

10                 CHAIRMAN CARTER:  You get points,

11       Mr. Rehwinkel.  Mr. Brew.

12                 MR. BREW:  I'm going to shoot for points too.

13                           CROSS-EXAMINATION

14       BY MR. BREW:

15            Q.   Good morning, Mr. Foster.

16            A.   Good morning.

17            Q.   Could I refer you to page 18 of your direct

18       testimony?

19            A.   Just give me one second, please.

20            Q.   Sure.  Let me know when you've got it.

21            A.   Yes, sir.

22            Q.   Now, in the question and answer that begins on

23       line 11, you say that you do not provide any true-up to

24       original schedules for the Levy project; is that right?

25            A.   Yes, sir.

944

1            Q.   And the reason for that is because you don't

2       have an updated cost for the project?

3            A.   At this time -- and again, I think this is

4       probably something that's most appropriately addressed

5       by Mr. Miller, but at this time, we do not have an

6       updated total project cost due to changes in the

7       schedule shift.

8            Q.   Okay.  And in the next question and answer

9       that moves over to page 19, you say that there's not

10       actually a requirement in the nuclear cost recovery

11       statute or rule to provide such TOR schedules.  Do you

12       see that?

13            A.   That's accurate.

14            Q.   If there were such a requirement, you would

15       still have nothing to provide until you have an updated

16       project cost and schedule; is that right?

17            A.   If there was a requirement, we would put our

18       best proxy forward, which would still be based -- my

19       understanding is -- and again, I would go to Mr. Miller

20       for the numbers, but our best estimate, I believe -- and

21       again, this is his testimony -- would be the

22       17.2 billion.

23            Q.   The 17.2 is what was filed in the need case?

24            A.   That was filed in the need case.

25            Q.   Okay.  And on page 18, you say that that

945

1       estimate is going to be changed because of the project

2       slippage; is that right?

3            A.   I don't know that for a fact.  I would say

4       it's likely to change.

5            Q.   Okay.  Let me try it differently.  I'm not

6       asking you to speculate on what Mr. Miller's testimony

7       would be, only what you do.  You don't have a TOR

8       schedule to prepare because you don't have the updated

9       cost and schedule information; is that right?

10            A.   We did not provide TOR schedules because we

11       don't have an updated total project cost number.

12                 MR. BREW:  Thank you.  That's all I have.

13                 CHAIRMAN CARTER:  Great job, Mr. Brew.

14       Mr. Davis.

15                 MR. DAVIS:  I'll do even better.  No

16       questions.

17                 CHAIRMAN CARTER:  Wow.  Mr. Moyle, you're

18       batting cleanup today.

19                 MR. MOYLE:  Just a couple, if I could.

20                           CROSS-EXAMINATION

21       BY MR. MOYLE:

22            Q.   Sir, just so I'm clear, you're seeking from

23       the ratepayers $12.33, isn't that right, beginning

24       January 1, 2010, related to Levy?

25            A.   That is what the statute provides for.  That's

946

1       our quantification based on the sales estimate that was

2       used in my prefiled, yes, sir.

3            Q.   But you're not looking to collect all of that.

4       You're going to defer some of it; is that right?

5            A.   Our company has proposed an alternative;

6       that's correct, sir.

7            Q.   Okay.  And you're removing roughly $6 from

8       that 12.33 amount, is that right, give or take?

9            A.   I would say that's a good ballpark, yes, sir.

10            Q.   But the fact that it's being removed doesn't

11       mean that consumers aren't ultimately going to have to

12       pay that amount; correct?

13            A.   That's correct.

14            Q.   Because that's just going to be, in effect,

15       carried, and ultimately consumers will still have to pay

16       that with interest; correct?

17            A.   That's correct, sir.

18            Q.   The carrying costs currently on the project

19       are north $10 million per year, isn't that right, the

20       interest carrying costs?

21            A.   Is there somewhere I -- I believe that's an

22       accurate number, that they are north of $10 million,

23       yes, sir.

24            Q.   Okay.  And you expect that number to go up as

25       this project matures, correct, with the additional

947

1       expenditures?

2            A.   I expect that we go out in time and have more

3       investment in the project that the carrying costs on

4       those investments will go up, yes.

5            Q.   Okay.  And then the question about the --

6       Mr. Brew asked you a little bit, but as we sit here

7       today, can you tell this Commission what you think this

8       project is going to ultimately cost?

9            A.   Again, that's not something I am testifying

10       to.

11            Q.   That's a Mr. Miller question?

12            A.   That's a Mr. Miller question, yes, sir.

13                 MR. MOYLE:  That's all I have.  Thank you.

14                 CHAIRMAN CARTER:  Thank you, Mr. Moyle.

15                 Commissioners, I'm going to go to staff unless

16       there are any questions from the bench at this time.

17       I'll still come back to the bench.

18                 Staff, you're recognized.

19                 MR. YOUNG:  Thank you, sir.  We just have a

20       few questions.

21                           CROSS-EXAMINATION

22       BY MR. YOUNG:

23            Q.   Good morning, Mr. Foster.

24            A.   Good morning.

25            Q.   You are PEF's witness addressing the

948

1       ratemaking and policy matters in this proceeding; right?

2       You just stated that; correct?

3            A.   Yes, sir.

4            Q.   All right.  Mr. Foster, are you PEF's witness

5       addressing Issue 3, which is the AFUDC issue?

6            A.   Yes, sir.

7            Q.   My question is, what is your understanding of

8       Issue 3?  Let me first ask that.

9            A.   My understanding of Issue 3 is that it deals

10       with -- let me check, because Issue 2 and 3 I remember

11       were close.  But it's the incremental-decremental;

12       correct?

13            Q.   Yes, sir.

14            A.   Okay.  Our company's position is, this is a

15       statute issue.  It's what does the statute provide for,

16       and I think perhaps -- I forget exactly who, but

17       somebody said yesterday a legal issue.  And while I'm

18       not a lawyer, my plain reading of the statute, section

19       (2)(b), tells you that there is a fixed carrying charge

20       associated with these projects.

21                 MR. YOUNG:  Okay.  No further questions.

22                 CHAIRMAN CARTER:  Commissioners, anything from

23       the bench.  Redirect?

24                 Did you say yes?

25                 COMMISSIONER SKOP:  Yes.

949

1                 CHAIRMAN CARTER:  Commissioner Skop.

2                 COMMISSIONER SKOP:  Thank you, Mr. Chairman.

3                 Good morning, Mr. Foster.

4                 THE WITNESS:  Good morning.

5                 COMMISSIONER SKOP:  Just briefly, a lot of the

6       discussion has focused upon delays and projected costs

7       of completion and the uncertainty of those costs in

8       light of undertaking a major capital project which has

9       not been attempted in over 30 years in this country.

10       With respect to the limited work authorization that

11       Progress requested, that was recently denied by the NRC

12       for Levy 1 and 2; is that correct?

13                 THE WITNESS:  You know, Commissioner, I'm

14       really not the best expert on that.  My understanding is

15       that there are some LWA issues that have caused a shift,

16       but beyond that, I would hesitate to tender myself as

17       the expert on that.

18                 COMMISSIONER SKOP:  Who would be the

19       appropriate witness?

20                 THE WITNESS:  Mr. Miller or Mr. Lyash would be

21       the ones to talk to, sir.

22                 COMMISSIONER SKOP:  All right.  Thank you.

23                 CHAIRMAN CARTER:  Anything further from the

24       bench?  Redirect?

25                 MS. TRIPLETT:  Sir, I don't have any redirect,

950

1       but I didn't know if now was the appropriate time to

2       mark these.

3                 CHAIRMAN CARTER:  Now would be a good time.

4                 MS. TRIPLETT:  Okay.  I think the next numbers

5       I have are 139 and 140.

6                 CHAIRMAN CARTER:  Okay.  Let's do this.  Which

7       one do you want for 139?

8                 MS. TRIPLETT:  Why don't we do 139 as "Updated

9       Position to 32A."

10                 CHAIRMAN CARTER:  Okay.  That's the one with

11       the box on it, 139?

12                 MS. TRIPLETT:  Yes, sir.

13                 CHAIRMAN CARTER:  Okay.  And 140 is the other

14       page?

15                 MS. TRIPLETT:  Yes.

16                 CHAIRMAN CARTER:  How about a short title for

17       each?  139 first.

18                 MS. TRIPLETT:  139, we could use "Updated

19       Position to 32A."

20                 CHAIRMAN CARTER:  Okay.  That's short.  Okay.

21       Now 140.

22                 MS. TRIPLETT:  How about "CR3 Uprate, High

23       Level Estimate"?

24                 CHAIRMAN CARTER:  You almost had me until you

25       put that "high level estimate" on.  Why don't we go with

951

1       "CR3 Uprate"?

2                 MS. TRIPLETT:  We could do that too.

3                 CHAIRMAN CARTER:  Okay.  Let's go with "CR3

4       uprate."

5                 (Exhibits Number 139 and 140 were marked for

6       identification.)

7                 CHAIRMAN CARTER:  Okay.  Hang on one second.

8       Let me get my pages together here.  We'll come back to

9       those in a minute.  Let's flip over to page --

10       Commissioners, that will be page 12, marked for

11       identification on staff's Comprehensive Exhibit List,

12       Number 82 through -- it looks like -- let me see here.

13       Eighty-nine; is that right?

14                 MS. TRIPLETT:  I have 83 through 89.

15                 CHAIRMAN CARTER:  What did I say?  Eighty-two?

16       Eighty-three through 89.  Do you want to move those in?

17                 MS. TRIPLETT:  Yes, sir.  Can we move those

18       in?

19                 CHAIRMAN CARTER:  Are there any objections?

20       Without objection, show it done.

21                 (Exhibits Number 83 through 89 were admitted

22       into the record.)

23                 CHAIRMAN CARTER:  Now let's go to the back

24       pages, Commissioners.  Exhibit 139 and 140, any

25       objection from the parties?

952

1                 Without objection, show it done.

2                 (Exhibits Number 139 and 140 were admitted

3       into the record.)

4                 CHAIRMAN CARTER:  Okay.  Anything further for

5       this witness on direct?

6                 MS. TRIPLETT:  I'm sorry, Chairman.  Were you

7       moving in 139 and 140 together?

8                 CHAIRMAN CARTER:  Yes.

9                 MS. TRIPLETT:  Thank you.

10                 CHAIRMAN CARTER:  Yes, they're both entered.

11                 MS. TRIPLETT:  I have nothing further.

12                 CHAIRMAN CARTER:  Okay.  You may be excused.

13                 MS. TRIPLETT:  And, Chairman Carter,

14       Mr. Foster does not have any rebuttal testimony, so may

15       he be dismissed or excused from the rest of the

16       proceeding?

17                 CHAIRMAN CARTER:  Do the parties have any --

18       okay.  Staff, anything further for this witness?

19                 MR. YOUNG:  No, sir.

20                 CHAIRMAN CARTER:  You are released.

21                 MS. TRIPLETT:  Thank you.

22                 CHAIRMAN CARTER:  Thank you.  Call your next

23       witness.

24                 MS. TRIPLETT:  I call Jon Franke.

25                 Good morning.

953

1                 Mr. Chairman, I'm ready when you are.

2                 CHAIRMAN CARTER:  You may proceed.

3                 MS. TRIPLETT:  Thank you.

4       Thereupon,

5                              JON FRANKE

6       was called as a witness on behalf of Progress Energy

7       Florida and, having been first duly sworn, was examined

8       and testified as follows:

9                          DIRECT EXAMINATION

10       BY MS. TRIPLETT:

11            Q.   Will you please introduce yourself to the

12       Commission and provide your address?

13            A.   My name is Jon Franke.  My business address is

14       15760 West Power Line Street, Crystal River, Florida.

15            Q.   And who do you work for, and what is your

16       position?

17            A.   I work for Progress Energy Florida, and I am

18       the Vice President of Crystal River Nuclear Plant.

19            Q.   Have you adopted the prefiled direct testimony

20       of Steve Huntington filed March 2nd, 2009, in this

21       proceeding?

22            A.   Yes.

23            Q.   And have you also filed prefiled direct

24       testimony filed May 1st, 2009, in this proceeding?

25            A.   Yes.

954

1            Q.   And were your prefiled testimonies true and

2       accurate at the time they were filed, and are they still

3       materially accurate today?

4            A.   That is correct.

5            Q.   And if I asked you the same questions in your

6       prefiled testimony today, would you give the same

7       answers that are in your prefiled testimony?

8            A.   Yes.

9                 MS. TRIPLETT:  We request that the March 2nd

10       and May 1st prefiled testimonies be entered into the

11       record as though read.

12                 CHAIRMAN CARTER:  The prefiled testimony of

13       the witness will be inserted into the record as though

14       read.

15

16

17

18

19

20

21

22

23

24

25

998

1       BY MS. TRIPLETT:

2            Q.   Do you have a summary, Mr. Franke, of your

3       prefiled testimonies?

4            A.   I do, and I'm prepared to give it.

5            Q.   Okay.  Would you please summarize your

6       testimonies?

7            A.   I presented testimony regarding the company's

8       costs related to the Crystal River Unit 3 power uprate

9       project.  Specifically, my testimony shows that the

10       actual project costs incurred in 2008 were both

11       reasonable and prudently incurred.  My testimony also

12       supports the reasonableness of the 2009 and 2010

13       projected costs.

14                 Finally, my testimony demonstrates the

15       long-term feasibility of completing the project as

16       outlined in the integrated project plan.  This

17       integrated project plan demonstrates that the project

18       remains within the bounds of the original estimates.

19       There are no unforeseen project risks that would prevent

20       its completion.  All necessary regulatory approvals to

21       date have been approved, and those pending approval are

22       on track for timely approval.

23                 That is my summary.

24                 CHAIRMAN CARTER:  Outstanding.

25                 MS. TRIPLETT:  We tender Mr. Franke for

999

1       cross-examination.

2                 CHAIRMAN CARTER:  Thank you.  Mr. Rehwinkel,

3       good morning.

4                 MR. REHWINKEL:  Thank you.

5                           CROSS-EXAMINATION

6       BY MR. REHWINKEL:

7            Q.   Good morning, Mr. Franke.

8            A.   Good morning.

9            Q.   I would like to ask you to turn to pages --

10       well, in your Huntington testimony.

11            A.   I understand.

12            Q.   The portions of your testimony there that

13       describe the costs for the uprate for Phases 2 and 3,

14       can you show me where those are?  Let me ask you to turn

15       to page 9 of the Huntington testimony.

16            A.   Unfortunately, my copy does not have page

17       numbers.  What's the question that you have, sir?

18            Q.   I'm in section IV or Roman numeral 4.

19            A.   I understand, Roman numeral 4.  Yes.

20            Q.   Okay.  The costs that are in the Q and A at

21       the top of the page there on lines 2 through 8 appear to

22       me to total -- well, how much -- are these the costs

23       for -- that apply to all three phases or Phases 2 and

24       Phases 3 of the EPU?

25            A.   It appears that these numbers cover more than

1000

1       a single phase.

2            Q.   Okay.

3            A.   In fact, I'm certain the reference includes

4       all phases.

5            Q.   Do you know how much of these numbers refer to

6       or relate to the costs for Phases 2 and Phases 3?

7            A.   It's not broken out that way, no.  It's broken

8       out by -- it appears to be broken out by years.

9            Q.   And Phase 1 of the uprate was the MUR, M-U-R?

10            A.   That is correct, measurement uncertainty

11       recapture, MUR.

12            Q.   And do you know how much of the MUR costs

13       comprise the total cost of the uprate project?

14            A.   I don't have those figures in front of me.

15            Q.   Are they ascertainable?

16            A.   Yes.

17            Q.   So if we knew the MUR costs for 2008, we could

18       deduct those from the costs that are shown on this page;

19       is that correct?

20            A.   That is correct.

21            Q.   And the cost for 2008 is the 65,137,303.

22       That's the total of the three phases in 2008?

23            A.   That is correct.  That did include a

24       measurement uncertainty recapture cost as well.

25            Q.   Okay.  Would it be possible to get a

1001

1       late-filed exhibit that identifies the MUR cost for

2       2008?

3            A.   That is possible.

4                 MR. REHWINKEL:  Mr. Chairman -- Commissioner

5       Edgar, may I ask for a late-filed exhibit that would be

6       2008 MUR costs?

7                 COMMISSIONER EDGAR:  Well, you may ask.  Let's

8       see where it takes us.  First of all, let's turn to

9       Progress.  Is that something you can compile and submit,

10       and if so, by when?

11                 MS. TRIPLETT:  Yes, we can, and by today.

12                 COMMISSIONER EDGAR:  Mr. Moyle, I know that

13       this is a topic of great interest to you.

14                 MR. MOYLE:  It is.  And, you know, we have

15       maintained that we're at a proceeding here.  The

16       evidence should be in.  And to the extent that

17       late-filed evidence comes in, we continue to maintain a

18       concern about that.

19                 Given the fact that it is being requested by

20       the Office of Public Counsel, my hunch is that it

21       probably would help my client's position, so being a

22       pragmatist, I probably would not object.

23                 COMMISSIONER EDGAR:  I appreciate the candor,

24       as always.

25                 Let me ask this.  I'm correct, am I not, that

1002

1       this witness will be coming back on rebuttal?

2                 MR. REHWINKEL:  Yes.

3                 MS. TRIPLETT:  Yes, ma'am.

4                 COMMISSIONER EDGAR:  Is it possible to have

5       that requested information provided prior to this

6       witness's return on rebuttal?

7                 MS. TRIPLETT:  Certainly.

8                 COMMISSIONER EDGAR:  Then, Mr. Rehwinkel, and

9       to the other parties, would it being possible for us to

10       mark as a late-filed, have that submitted -- and I'll

11       look to staff to correct me if I should say this in a

12       way that will work better than what I'm explaining --

13       such that all the parties can look at it, and then it

14       would be available for questioning on rebuttal?

15                 Yes, Mr. Rehwinkel.

16                 MR. REHWINKEL:  What I could do is withdraw my

17       request for a late-filed at this time.  We've lodged the

18       request with the company.  I could reask the question

19       when he reappears on rebuttal.  Hopefully, in the

20       interim, we could have that information disseminated.

21       That way we wouldn't have to wade into these late-filed

22       exhibit waters.

23                 COMMISSIONER EDGAR:  Okay.  That, to my

24       memory, is consistent with actions that we have tried to

25       take to accommodate all concerns, and yet also

1003

1       facilitate questioning on issues that have arisen from

2       the parties.  So my direction will be that we will try

3       to do that, ask Progress to put that information

4       together.

5                 Mr. Rehwinkel, for the record, why don't you

6       just say one more time what it is you are asking for.

7                 MR. REHWINKEL:  Okay.  Thank you.  My request

8       to the witness and the company is to have the MUR costs

9       for 2008 provided.  And I would like it in a form that I

10       could deduct it from the $65 million number on page 9,

11       line 5, of Mr. Huntington's direct testimony.

12                 COMMISSIONER EDGAR:  Okay.  So we will ask

13       Progress to compile that information, distribute it to

14       our staff and all parties, with the understanding that

15       upon that review, you will have the opportunity to ask

16       questions, and if there are objections to that, they

17       should be raised at that point in time prior to the

18       responses.

19                 Ms. Cibula, does that work for you

20       procedurally?

21                 MS. CIBULA:  Yes, that works.

22                 COMMISSIONER EDGAR:  Okay.  Thank you.

23       Mr. Rehwinkel, go ahead.

24                 MR. REHWINKEL:  Thank you.

25                 MR. YOUNG:  I'm sorry, Madam Chair.  Just to

1004

1       clarify, do you want to have a placeholder for 141, or

2       do you want to just remove 141?

3                 COMMISSIONER EDGAR:  I think we'll just wait.

4       Initially I was going to say placeholder.  So thank you

5       for the clarification, but we will wait until it is

6       distributed and everybody has a chance to look at it.

7                 Thank you.

8       BY MR. REHWINKEL:

9            Q.   Mr. Franke, could I ask you to turn to your

10       May 1st testimony, page 6.  Do you have pages on that?

11            A.   Let me find that one.  My May 1st testimony?

12            Q.   Yes, in the Roman numeral 2 section.

13            A.   May 1st, I do have page numbers.  Which page?

14            Q.   Page 6.

15            A.   Page 6, yes.

16            Q.   On lines 12 through 18, you describe costs for

17       2009 related to the CR3 EPU; is that correct?

18            A.   That is correct.

19            Q.   Do any of these costs contain MUR costs?

20            A.   I do not believe there are any MUR costs in

21       2009.

22            Q.   Okay.  So from 2009 forward, the only costs

23       related to the uprate would be related to Phases 2 and

24       3; is that correct?

25            A.   That is correct.

1005

1            Q.   Okay.  By my math, it looks like there's

2       $126 million of costs related to 2009.  And I've added

3       the $16.2 million, the $40.3 million, the 4.6 million,

4       the 60.3 million, and the $4.7 million number shown in

5       that section.  Is that correct?

6            A.   Yes.  I believe in the schedules provided by

7       Mr. Foster, the total number is 126.1 million.

8            Q.   Okay.  And that's for 2009?

9            A.   That is correct.

10            Q.   For 2010, is the cost 49.9, or 50 million

11       almost?

12            A.   That sounds right.

13            Q.   Is that correct?  Okay.  So the cost on page

14       6, lines 19 through 23, continuing onto page 7, lines 1

15       and 2, is approximately $50 million?

16            A.   That is correct.

17            Q.   So the costs that are subject to recovery in

18       this hearing are -- for Phases 2 and Phases 3 of the CR3

19       uprate project are the 65 million that we discussed in

20       Mr. Huntington's testimony less the MUR costs, and the

21       125 million and the 50 million; is that correct?

22            A.   I believe we are asking for the MUR costs as

23       well for 2008, for prudency review of that as well.

24            Q.   I apologize.  My question was with respect to

25       Phases 2 and Phases 3 of the uprate.

1006

1            A.   With respect to 2 and 3, that would be

2       correct.

3            Q.   Okay.  Let's look at Mr. Huntington's

4       testimony.  On the fourth page, there's a Q and A that

5       says, "Please summarize your testimony."

6            A.   Yes.

7            Q.   Okay.  On line 14, the statement there is,

8       "The project is on schedule and on budget."  Is that

9       still an accurate statement?

10            A.   The project is -- as of today or as of filing?

11            Q.   As of today.

12            A.   As of today, there are issues we are working

13       through in one particular portion of the project that I

14       discussed in my own testimony that I filed later, and we

15       are within the budget parameters of the project.

16            Q.   Okay.  And is that the low pressure turbine

17       issue?

18            A.   Yes.  We're still working through resolving

19       that with our vendor.

20            Q.   Okay.  On page 21 of Mr. Huntington's

21       testimony, which is -- it looks like five or six pages

22       from the back.  There is a question that starts, "Were

23       any project risks identified that were deemed to have a

24       high probability of affecting the uprate project?"

25            A.   I've found that page.

1007

1            Q.   Okay.  Now, in this testimony that was filed

2       on March 2nd, 2009, the only issue that was identified

3       was this hoist crane or this turbine building crane

4       reliability issue; is that correct?

5            A.   That is one item that Mr. Huntington

6       discussed, yes.

7            Q.   Okay.  And I believe you testified in

8       deposition that that issue has been resolved?

9            A.   It has been mitigated.  We look at project

10       risk, and we need to be careful when we discuss what

11       risk means.  There's risk to the project being feasible

12       or completed.  We have no high risk items, nor I do not

13       believe have had high risk items with regard to that.

14                 The vagueness of this question requested that

15       we discuss other potential risks, like schedule risks or

16       cost risks associated with the project.  This appears to

17       have been a schedule risk that Mr. Huntington discussed,

18       and this one has been mitigated.  We've done a number of

19       measures to reduce the opportunity of a crane failure to

20       impact the outage schedule in our upcoming outage for

21       our turbine work.

22            Q.   Okay.  Now, you said the vagueness of the

23       question.  I mean, that was a question that was posed by

24       yourself or --

25            A.   I understand.  I understand.

1008

1            Q.   And you're saying that was not considered a

2       high risk issue?

3            A.   It was high risk to schedule performance, not

4       to feasibility of the power uprate project.

5            Q.   Okay.  Well, let me ask you a question about

6       schedule.  At this point in time, Phases 2 and Phases 3

7       of your uprate project are scheduled to be implemented

8       during the scheduled outages at the Crystal River

9       nuclear plant in 2009 and 2011; is that correct?

10            A.   That is correct.

11            Q.   And those are outages 16 and 17?

12            A.   Exactly.

13            Q.   With respect to the project, when you -- could

14       you define schedule risk to me?  What does that mean?

15            A.   What schedule risk means -- we are very

16       sensitive to exceeding our outage duration schedule, and

17       that's really what I'm talking about, an individual

18       outage duration.  Every day my plant is off-line, it's a

19       cost to my customers of about 1 1/2 to $2 million of

20       replacement fuel costs.  As such, we track risks against

21       our ability to execute under our business plan schedule

22       for outage duration.  This outage in refuel 16 is a

23       business plan duration of 85 days.  So when we

24       characterize a risk to the project, a schedule risk, it

25       is a risk that might extend one portion of the outage

1009

1       against that business plan.

2            Q.   And is your testimony here today that you have

3       not identified any risks that would extend the planned

4       outage beyond the intended outage duration?

5            A.   Not at this time.  We have identified some

6       risks like the turbine building crane that we've

7       mitigated, and we've continued to work -- obviously,

8       once we get into the outage, the actual duration will

9       depend on what we discover during the outage that needs

10       to be resolved that we were not aware of during the

11       pre-planning phase of the outage.

12            Q.   Okay.  Now, the low pressure turbine issue

13       that you discuss in your May 1st testimony -- is it your

14       May 1st -- I mean your rebuttal testimony.

15            A.   That is correct.

16            Q.   Okay.  I don't want to ask you about your

17       rebuttal testimony, but I want to ask you about that

18       issue.  As I understand it, Progress Energy personnel

19       went over to Germany, to Siemens, to look at or view a

20       test of the low pressure turbine.  Is that correct?

21            A.   We had personnel witness a test that we had

22       required of Siemens, that's correct, in March.

23            Q.   Okay.  And the purpose of witnessing that test

24       was because there were some low pressure turbine rotors

25       that had developed problems at one of -- at another

1010

1       nuclear plant; is that correct?

2            A.   Well, the test was one that we had required in

3       our original specification made -- I believe that

4       specification was likely written in 2008.  But the test

5       itself was changed after -- the test requirements were

6       changed after an event at DC Cook last fall.

7            Q.   Okay.  And because of the results of the test,

8       is it my understanding that -- is my understanding

9       correct that Progress Energy declined to take delivery

10       of the low pressure turbines for purposes of installing

11       them in the 2009 outage?

12            A.   I would say the best characterization is that

13       we are continuing to work with Siemens to understand the

14       acceptability of those turbines and when a correct

15       delivery, you know, an acceptable delivery of those

16       turbines can be made.  We're working in negotiations now

17       with that vendor to understand how they will address

18       some findings of that test.

19            Q.   Okay.  Is there a possibility that you will

20       take delivery of the low pressure turbines from Siemens

21       in time to install them in 2009?

22            A.   Each day it becomes less likely, but we're

23       obviously still working with Siemens to understand what

24       the final resolution will be.

25            Q.   Okay.  So is it more likely than not that they

1011

1       will not be installed in 2009?

2            A.   It's more likely than not that they will not

3       be installed in 2009.

4            Q.   Okay.  So if they are not installed in 2009,

5       that means that to successfully complete the uprate

6       project to the full extent that you want, you will have

7       to install the turbines in the 2011 outage; is that

8       correct?

9            A.   That is correct.

10            Q.   Okay.  Now, if you do that, will that extend

11       the outage in 2011?

12            A.   We don't believe it will at this time.

13            Q.   Is there a possibility that it will?

14            A.   There's always a possibility.  Right now, from

15       my best guest, it will not.  The long lead duration on

16       that outage right now is high pressure turbines.  High

17       pressure turbines take longer to install than low

18       pressure turbines.

19            Q.   Okay.  Let me ask you to turn to your direct

20       testimony from May 1st, 2009, and ask you to turn to

21       page 4, the question and answer that says, "Please

22       summarize your testimony."

23            A.   Yes.

24            Q.   Okay.  And by my count, it says three times in

25       those two -- two of the -- the first two paragraphs of

1012

1       that answer the terms "reasonable and prudent."  You're

2       not suggesting that if you say it a bunch of times, it

3       means that it's reasonable and prudent?  It's --

4            A.   I just didn't want there to be any doubt.

5            Q.   You're saying -- okay.  In here on line 17

6       through 19, it states that PEF has incurred reasonable

7       and prudent costs to complete work scheduled for the

8       remaining two phases of the project, which is currently

9       on schedule.  Is that still true?

10            A.   Yes, with the caveat that we are working with

11       Siemens on the low pressure turbines.

12            Q.   Okay.  Is there a possibility that if the low

13       pressure turbines are -- that if you don't install them

14       in 2009, that they -- is there any possibility that they

15       would not be available for 2011?

16            A.   Right now we believe they will be available.

17       You're asking me to suppose what might happen in the

18       future.  I'm dealing with a vendor who had a challenge

19       producing turbines at my specification.  We understand

20       their mistake.  They still believe that they could be

21       delivered for this outage to be genuine right now.  We

22       believe that the right action is to continue to work

23       with them.  I have no reason to believe we cannot have

24       them available for installation in 2011.

25            Q.   Okay.  Let me ask you to turn to page 7 of

1013

1       your May 1st testimony.  On line -- starting on line 4,

2       there's a Q and A that asks about what licensing work

3       was and will be done in 2009 and 2010.

4            A.   Yes.

5            Q.   Do you see that?  Is it -- you state starting

6       on line 7 that the company is working on the NRC license

7       application in 2009 and expects to receive approval from

8       the NRC by 2010.  Is that still the case?

9            A.   It's more likely now, as I addressed in my

10       rebuttal testimony, that the application will actually

11       be submitted in the first quarter of 2010, and we

12       anticipate approval approximately 12 months after

13       submittal.

14            Q.   Okay.  So does this statement here and the

15       facts that you are now relating about your expected

16       application date -- and let me -- well, let me step back

17       and ask this.  The document that you would file with the

18       NRC for approval is called a license amendment request;

19       is that correct?

20            A.   That's correct, LAR for short.

21            Q.   LAR.

22            A.   LAR for short, yes.

23            Q.   Okay.  So the LAR filing date that was

24       expected on May 1st of 2010 has now slipped into the

25       second -- or the first quarter of 2011; is that correct?

1014

1            A.   Yes, I believe we are expecting a fall

2       submission.  But I believe in order to ensure a good

3       amendment that we are moving that till -- right now the

4       schedule shows February of 2011.

5            Q.   Okay.  Well, you state down beginning on lines

6       12 through 14 that you developed the license application

7       cost estimates on a reasonable licensing and engineering

8       basis, using the best available information, consistent

9       with utility industry and PEF practice.  Do you see

10       that?

11            A.   Yes.

12            Q.   When you say on a reasonable licensing basis

13       or reasonable licensing and engineering basis, that

14       turned out not to be correct, in the sense that now the

15       schedule has slipped for several months; is that right?

16            A.   No, I wouldn't agree.  At the time, I believe

17       those estimates were reasonable based on what we

18       understood.  As with any engineering, and certainly any

19       regulatory process, as you move through the process, you

20       learn more, and as you learn more, you continue to

21       refine what is reasonable.

22            Q.   Okay.  Now, the reason for the slippage in the

23       schedule of the filing of the LAR was because of the

24       resolution of several technical issues associated with

25       the Phase 2 and Phase 3 uprates; is that correct?

1015

1            A.   No, that is not correct.

2            Q.   What's the reason?

3            A.   We're just finding that it will take our

4       primary vendor a little more time to get their

5       information in the right format and then for us to

6       perform the reviews.  Additionally, the fall outage that

7       we have in 2009 will delay some aspects of the license

8       amendment request, as the staff required to review it

9       will have to focus on that outage instead of focusing as

10       much on this license amendment request.

11            Q.   Were there not several issues that you met

12       with the NRC about, some technical problems?

13            A.   There were technical issues.  I would not

14       characterize them as problems.  They were technical

15       questions that we have met with the NRC on, myself two

16       times in 2008 and 2009, as well as discussions on the

17       phone.  That's a normal licensing process to work

18       through specific technical issues with the staff.  These

19       did not cause delay.

20            Q.   So your testimony is that the four issues that

21       you met with the NRC about in 2008 have nothing to do

22       with the timing of your LAR request?

23            A.   No, only in that some of them are part of the

24       larger development of a license amendment request.

25       There's nothing special about these technical issues

1016

1       which are creating delay.

2            Q.   On page 8 at the bottom of your testimony,

3       just so I understand, on lines 20 through 22, carrying

4       onto the next page, you state there that the project

5       management -- it says, "Through the project management

6       activities that I have identified, the company is on

7       schedule to perform the CR3 uprate project as planned."

8       That statement also needs to be modified by the issue

9       that we discussed about low pressure turbines?

10            A.   As I discussed in my rebuttal testimony, the

11       low pressure turbine issue is one that we're continuing

12       to work through.  The final delivery of the extended

13       power uprate at the completion of 2011 right now is on

14       schedule and on track.

15            Q.   Okay.  And on page 10 of your testimony, lines

16       5 through 6, you discuss the scope of the 2009 outage

17       during -- the scope of the 2009 uprate work during

18       outage 16, and you state what's included in that scope;

19       is that correct?

20            A.   That is correct.

21            Q.   Okay.  And where it says it includes two low

22       pressure turbine replacements, those are the low

23       pressure turbines that we've discussed here already

24       today?

25            A.   That is correct.

1017

1            Q.   Okay.  On page 11 of your testimony, in the Q

2       and A, you discuss $36.9 million related to resolving a

3       point of discharge issue; is that correct?

4            A.   Yes.

5            Q.   Now, are those costs included in the costs

6       that we discussed earlier?

7            A.   I believe if you look at that earlier question

8       that actually discussed these costs, these are the

9       non-power-block costs primarily that are discussed in

10       the earlier testimony.  So, yes, they are part of this

11       originally.  You can distinguish them.  They are

12       non-power-block costs, and they were separated in that

13       manner.

14            Q.   Okay.  But these are Phase 2, Phase 3 costs?

15            A.   Phase 3 costs.

16            Q.   Phase 3.  Okay.  Would the company be

17       incurring these costs if they were not doing Phase 3, or

18       Phase 2, for that matter, of the uprate project?

19            A.   No, they would not.

20            Q.   On page 12 of your testimony, you discuss

21       185.3 or $159.5 million on a jurisdictional basis of

22       assets related to Phase 2 of the project; is that

23       correct?

24            A.   That is correct.

25            Q.   Now, are these costs different in any way than

1018

1       the 2009 costs that we discussed earlier?

2            A.   Those are part of the 2009 costs, as discussed

3       earlier.

4            Q.   Okay.  Have these costs changed because of the

5       low pressure turbine replacement issue that we discussed

6       earlier?

7            A.   If we do not place the low pressure turbines

8       in service, these numbers would change.  I believe we

9       have those figures available.

10            Q.   Okay.  Let me ask you to turn to page 15 of

11       your May 1st testimony.  You state on line 7, beginning

12       on line 7, "At this time, there is no indication of any

13       risks that would affect the project's feasibility."  Do

14       you see that?

15            A.   Yes.

16            Q.   Is that still correct?

17            A.   Absolutely.

18            Q.   Okay.  What is your definition of feasibility

19       with respect to that statement?

20            A.   Feasibility is the ability of the project to

21       provide an extended power uprate for Crystal River 3 and

22       achieve an economic benefit for my customers.

23            Q.   Now, if for some reason you were not able to

24       complete the project in outage 17 in 2011, would you go

25       to outage 18?

1019

1            A.   Yes.

2            Q.   And that's the only time you would do it?

3       Anything you didn't complete that needed to be done, if

4       you didn't complete it in outage 17, you would go to

5       outage 18 to complete it?

6            A.   That is correct.

7            Q.   Okay.  Is --

8            A.   Under our current plans.

9            Q.   Okay.  And is there any possibility that that

10       might happen?

11            A.   I think that's a very low probability, very

12       low probability.  When you're -- right now the

13       schedule -- everything I know, the schedule can be

14       completed by 2011.

15            Q.   If the project -- let me ask it this way.  At

16       this point in time, you have stated that you plan to

17       file your LAR in the first quarter of 2010?

18            A.   That's correct.

19            Q.   And I believe you stated elsewhere that you

20       expect the LAR approval or action by the NRC in the

21       summer of 2010; is that right?

22            A.   The review process is 12 months from

23       acceptance of the license amendment request.  The NRC is

24       committed to having that reviewed within 30 to 60 days

25       of submittal, so we're talking 12 months from submittal,

1020

1       plus 30 to 60 days, depending on their initial

2       acceptance review by the Commission.  So by the summer,

3       we expect the amendment to have been returned to us

4       prior to the outage in 2011.

5            Q.   Okay.  And when you say by the summer, you

6       mean of 2011?

7            A.   That is correct.

8            Q.   Now, when is the date that outage 17 begins?

9            A.   I don't know the exact date.  The only date

10       that -- we would need the license amendment prior to

11       increasing power of the reactor.  That outage could be

12       executed without the license amendment, and then we

13       could increase power following the completion of the

14       outage as necessary.

15            Q.   What would be the last point in time that you

16       could receive NRC approval of your LAR and get the work

17       done during the 2011 outage?

18            A.   I believe we do not need the license amendment

19       to execute the outage.  We only need it to increase the

20       reactor power.

21            Q.   Okay.  So even if you did not have the LAR

22       action by the NRC in hand at the time of the beginning

23       or the end of the outage, you would still do the work?

24            A.   That is correct.

25            Q.   Okay.  What would you do if the NRC -- if you

1021

1       did the work and the NRC did not authorize?

2            A.   We would continue to operate at current power

3       level until we receive the license.  This is very

4       similar to our MUR project.  Obviously, the urgency to

5       get these megawatts on the grid is high.  When we

6       completed our MUR Phase 1 project, for example, we

7       installed the equipment during the 2007 outage.  That

8       outage ended in early December of 2007.  We received the

9       NRC approval for the licensed increase in December after

10       the completion of that outage, and we executed the

11       actual increase in power -- I believe it was the end of

12       January, possibly the first week of February 2008.  So

13       we would follow that same process.

14            Q.   The LAR that you will submit or plan to submit

15       in 2010 will be for authorization to increase your --

16       the electrical output of the plant 180 megawatts; is

17       that correct?

18            A.   That is -- well, it's a total of

19       180 megawatts.  The increase between -- it's a total of

20       180 including all the various phases.

21            Q.   Okay.  So the MUR was how many megawatts?

22            A.   Twelve megawatts.

23            Q.   Okay.  So what the LAR that you would request

24       in 2011 would relate to would be the balance?

25            A.   The LAR really relates to about 140 out of the

1022

1       180.  The low pressure turbine rotors, for example, do

2       not -- the benefit of those low pressure turbine rotors

3       do not require the license amendment request.  It

4       doesn't require that we increase reactor power.  It's an

5       efficiency improvement for the plant, as well as one

6       other modification that we'll install in this outage,

7       which we believe will gain us 4 megawatts thermal this

8       outage.  So the license amendment request really is tied

9       to the last 140 megawatts, roughly.

10            Q.   Okay.  And the increasing of electrical output

11       by the Crystal River plant to that degree would be a

12       first of its kind for a Babcock & Wilcox PWR reactor; is

13       that correct?

14            A.   There is currently a Babcock & Wilcox plant

15       that is within about 7 percent of that power level.  So

16       I would say the last portion is a stretch uprate for

17       B&W, but it is in the same neighborhood as one of our

18       sister plants in Ohio is running currently.

19            Q.   Is that Davis-Besse?

20            A.   It is Davis-Besse.  It operates about

21       7 percent below the power level we are seeking in our

22       license amendment request.

23            Q.   But isn't it correct that Davis-Besse was

24       licensed at that level?

25            A.   Actually, I believe -- and I would be subject

1023

1       to check.  I believe initially they were licensed at a

2       lower power level and took some measures to increase

3       that power.

4            Q.   But the measures that they received or that

5       they took to increase to the level of 7 percent below

6       where you hope to end up was a relatively small

7       percentage increase in their original license?

8            A.   That's correct.  Their original license was at

9       a higher power level than our original license.

10            Q.   Okay.  So for purposes of my question, the

11       increase in electrical output for the Crystal River 3

12       plant is unprecedented relative to the initial licensed

13       output of a Babcock & Wilcox PWR reactor; is that

14       correct?

15            A.   If you keep slicing it small enough,

16       eventually you'll be able to earn the word

17       "unprecedented."  There's a lot of nuclear plants that

18       have been uprated in excess of the amounts that we're

19       talking about.  You know, if you continue to slice it

20       down to B&W plants in Florida, yes, this is

21       unprecedented.  But the application of an extension of

22       power to nuclear power plants is a relatively understood

23       normal license amendment process for a nuclear power

24       plant in the United States.

25            Q.   Okay.  But you would agree, would you not,

1024

1       that there's a difference in the design and operation of

2       a boiling water reactor versus a pressurized water

3       reactor, would you not?

4            A.   Absolutely.

5            Q.   Okay.  And so there are different physical and

6       engineering and mechanical properties that have to be

7       managed and engineered when it comes to a PWR reactor

8       versus a boiling water reactor; is that right?

9            A.   There are some differences.  The majority of

10       the technical issues are very similar.  Each design

11       requires a different set of parameters to be evaluated

12       in a different manner, but the questions are all the

13       same.

14            Q.   But the licensing process, the NRC looks at it

15       based on the make and the type of reactor, do they not?

16            A.   They actually look at the individual design of

17       each reactor.  So the fact that one plant is a B&W R --

18       a BWR versus PWR does not change that review process.

19       Each plant, particularly the first -- you know, the

20       nuclear plants that are operating today, they're all

21       different.  They all are of a little bit different size,

22       a little bit different design, a little bit different

23       set of equipment and design parameters, so each one of

24       these extended power uprates was unique in some manner,

25       similar to the one we are applying.

1025

1            Q.   Okay.  Earlier when you were talking about my

2       slicing to get down to an unprecedented level, just to

3       be clear, my question was not as to B&W reactors in the

4       state of Florida, but B&W reactors nationwide.

5            A.   But my point is that each of the 20 extended

6       power uprates the NRC has approved was special and

7       unique in its own fashion.  You used the word

8       "unprecedented."  My point is that all extended power

9       uprates are reviewed by the NRC, so the experience of

10       those reviews are reviews of unique applications.  Mine

11       is just the next one in line.  That does not make it

12       unprecedented.

13            Q.   But this is the first B&W reactor that will be

14       increased in power to this extent; is that correct?

15            A.   That is correct.

16            Q.   And just to be clear, so I understand your

17       testimony, on page 15, lines 17 and 18, where it states

18       that PEF plans to file its license amendment request for

19       the EPU in the fall of 2009, that has been modified now

20       by your rebuttal testimony; is that correct?

21            A.   I believe in my rebuttal testimony we refer to

22       first quarter of 2010, and that is still accurate.

23            Q.   Okay.  Now, on page 16 of your testimony, the

24       Q and A there that discusses the low pressure turbines

25       with a similar design for high efficiency rotors at the

1026

1       DC Cook plant --

2            A.   That is correct.

3            Q.   That's the issue that caused you to modify

4       your test parameters that you requested of Siemens; is

5       that right?

6            A.   Yes, we did modify the test parameters.  And I

7       believe the original specification called for a test of

8       one of the two rotors, and we asked that they test both

9       individually as opposed to just one of the two.

10            Q.   And when they did that test and the results

11       came back, you were unsatisfied with them?

12            A.   They did not meet our original specifications;

13       that's correct.

14            Q.   So you were unsatisfied at least for purposes

15       of taking delivery at the time you had originally

16       wanted?

17            A.   We have not accepted delivery of those

18       turbines at this time, and we have -- that's correct.

19            Q.   Okay.  And on page 17 of your testimony,

20       there's an implication here that -- or there's an

21       allusion to the Siemens test, is that correct, on lines

22       5 through 9?

23            A.   That is correct.  I am trying to demonstrate

24       that resolution of this issue could impact the schedule

25       of the installation of the low pressure turbines, as

1027

1       well as in a small manner the final output of the plant

2       to a small degree.

3            Q.   Okay.  Now, is it correct that if you do not

4       install the low pressure turbine in 2009 that it would

5       affect your output by about 7 percent, your planned

6       increase in output?

7            A.   Not 7 percent of total reactor power, about 7

8       -- it's approximately 24 megawatts, I think is the best

9       way to say it, if we do not install them in 2009.

10            Q.   So what would happen there is that

11       24 megawatts that you would plan on getting in Phase 2,

12       you would not be able to achieve that output until

13       installation of the low pressure turbines in 2011?

14            A.   That's correct.

15                 MR. REHWINKEL:  Commissioners, I think those

16       are all the questions I have for this witness at this

17       time until rebuttal.

18                 Thank you, Mr. Franke.

19                 CHAIRMAN CARTER:  Okay.  Mr. Brew.

20                 MR. BREW:  No questions for this witness.

21                 CHAIRMAN CARTER:  Mr. Davis.

22                 MR. DAVIS:  None.

23                 CHAIRMAN CARTER:  Mr. Moyle, you're

24       recognized.

25                 MR. MOYLE:  I just have a brief line of

1028

1       questions.

2                           CROSS-EXAMINATION

3       BY MR. MOYLE:

4            Q.   Your testimony supports the uprate costs that

5       you believe are reasonable and prudent for 2008 and

6       2009; is that correct?

7            A.   Yes, sir.

8            Q.   Okay.  And with respect to that number, did

9       you go through and review the backup and the detail to

10       support that request?

11            A.   As much as possible, yes.

12            Q.   Did you look at anything and say, "You know,

13       this doesn't look like it is reasonable and prudent,"

14       and back anything out of that request as we sit here

15       today?

16            A.   You're implying that I waited until after the

17       fact.  The way we do this -- and I'm directly

18       responsible for the work that goes on at my facility.

19       As we work through each of the individual projects, we

20       challenge budget costs all the way along the line.  So

21       when I say I reviewed the project costs, I didn't wait

22       until the expenditures were expended.  And, yes, there

23       were many options and actions that the staff had

24       proposed that I personally, as well as prior to my own

25       reviews, were challenged to reduce the cost as much as

1029

1       possible.

2            Q.   I guess -- and I appreciate the answer.  I

3       wasn't really suggesting that.  But let's just say

4       hypothetically that you're in asking for a dollar or

5       $100 million with respect to uprate costs that you

6       believe are reasonable and prudent.

7            A.   Yes.

8            Q.   Using a dollar example, was there ever a point

9       in time where the number was $1.20, and you said, "You

10       know what, these 20 cents, they don't look reasonable

11       and prudent.  Let's not seek those"?  Did that analysis

12       ever take place?

13            A.   We did -- and it would be difficult to come up

14       with specific examples, but there were several options

15       on how to spend the money in different ways that we

16       challenged and were able to bring the cost down.  For

17       example, the Areva reviews, the original budgets for

18       that we did not feel were reasonable and prudent.  We

19       went back to Areva.  We challenged them.  We asked them

20       to open their books, and we drove their cost down to a

21       level we thought was the lowest we could get for our

22       customers.

23            Q.   And I guess the point with respect to a

24       mind-set is, do you view it as the Commission's role to

25       determine reasonable and prudent, and would you put

1030

1       forward costs and let them sort out what's reasonable

2       and prudent, or do you look at it and say, "You know

3       what.  It's our role.  It's somewhat of a self-audit

4       role.  We need to make sure that the costs that we're

5       asking for are only reasonable and prudent"?  Which is

6       it in those two scenarios?

7            A.   I don't pretend to define what the

8       Commission's role in this is.  My role is to keep the

9       costs as low as possible to achieve the results in the

10       most assured manner.  That's my role.

11            Q.   But as we sit here today, with that dollar

12       example, you can't tell me, you know, how much above the

13       dollar, again, using that as a rough estimate,

14       percentagewise how much above that you decided not to

15       seek; correct?

16            A.   I would just say that -- no, I don't know what

17       the actual figure is.  I do know that in many places on

18       many of these projects -- because this is a very complex

19       -- you know, there's a number of individual projects

20       that in a number of places we've cut costs for the

21       projects.  I don't know what the actual number would be.

22                 MR. MOYLE:  I would be tempted to ask for a

23       late-filed exhibit to show that actual number, but

24       against my better judgment, I won't.

25                 CHAIRMAN CARTER:  He'll be back on rebuttal.

1031

1       Maybe you can ask him then.

2                 Staff, you're recognized.

3                 MR. YOUNG:  No questions.

4                 CHAIRMAN CARTER:  Commissioners?

5                 Redirect?

6                 MS. TRIPLETT:  Good news.  No redirect.

7                 CHAIRMAN CARTER:  Outstanding.  Exhibits.

8       Number 90.

9                 MS. TRIPLETT:  Yes, sir, Number 90, we would

10       ask that to be admitted.

11                 CHAIRMAN CARTER:  Are there any objections?

12       Without objection, show it done.

13                 (Exhibit Number 90 was admitted into the

14       record.)

15                 CHAIRMAN CARTER:  Good news, everybody.  We

16       started on time this morning, and I'm going to give the

17       court reporter a break.  We'll come back at 35 after.

18                 (Recess taken.)

19                 (Transcript continues in sequence in

20       Volume 6.)

21

22

23

24

25

1032

1                        CERTIFICATE OF REPORTER

2

3       STATE OF FLORIDA:

4       COUNTY OF LEON:

5                  I, MARY ALLEN NEEL, Registered Professional

6       Reporter, do hereby certify that the foregoing

7       proceedings were taken before me at the time and place

8       therein designated; that my shorthand notes were

9       thereafter translated under my supervision; and the

10       foregoing pages numbered 853 through 1031 are a true and

11       correct record of the aforesaid proceedings.

12                 I FURTHER CERTIFY that I am not a relative,

13       employee, attorney or counsel of any of the parties, nor

14       relative or employee of such attorney or counsel, or

15       financially interested in the foregoing action.

16                 DATED THIS 10th day of September, 2009.

17

18

____________________________

19                                 MARY ALLEN NEEL, RPR, FPR

2894-A Remington Green Lane

20                                 Tallahassee, Florida  32308

(850) 878-2221

21

22

23

24

25