1033

1                              BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

DOCKET NO. 090009-EI

3       In the Matter of:

4       NUCLEAR COST RECOVERY CLAUSE.

______________________________/

5

6

7

8                               VOLUME 6

9                       Pages 1033 through 1246

10              ELECTRONIC VERSIONS OF THIS TRANSCRIPT ARE

A CONVENIENCE COPY ONLY AND ARE NOT

11               THE OFFICIAL TRANSCRIPT OF THE HEARING,

THE .PDF VERSION INCLUDES PREFILED TESTIMONY.

12

13

PROCEEDINGS:        HEARING

14

COMMISSIONERS

15       PARTICIPATING:      CHAIRMAN MATTHEW M. CARTER, II

COMMISSIONER LISA POLAK EDGAR

16                           COMMISSIONER KATRINA J. McMURRIAN

COMMISSIONER NANCY ARGENZIANO

17                           COMMISSIONER NATHAN A. SKOP

18       DATE:               Wednesday, September 9, 2009

19       PLACE:              Betty Easley Conference Center

Room 148

20                           4075 Esplanade Way

Tallahassee, Florida

21

REPORTED BY:        LINDA BOLES, RPR, CRR

22                           Official FPSC Reporter

(850) 413-6734

23

PARTICIPATING:      (As heretofore noted.)

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1034

1                              I N D E X

2                              WITNESSES

3

NAME:                                          PAGE NO.

4

5       GARY DOUGHTY

6       Direct Examination by Mr. Doughty                 1036

Prefiled Direct Testimony 3-2-09 Inserted         1039

7       Cross Examination by Mr. Brew                     1098

Cross Examination by Mr. Moyle                    1102

8

9       GARY FURMAN

10       Prefiled Direct Testimony 3-2-09 Inserted         1110

Prefiled Direct Testimony 5-1-09 Inserted         1132

11

12       GARRY MILLER

13       Direct Examination by Mr. Burnett                 1145

Prefiled Direct Testimony 3-2-09 Inserted         1147

14       Prefiled Direct Testimony 5-1-09 Inserted         1170

Cross Examination by Mr. Rehwinkel                1203

15

16

17

18       CERTIFICATE OF REPORTER                           1246

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1035

1                              EXHIBITS

2       NUMBER:                                 ID.    ADMTD.

3       91 GRD-1                                1038      1108

4       92 GRD-2                                1038      1108

5       93 GRD-3                                1038      1108

6       94 GRD-4                                1038      1108

7       95 GRD-5                                1038      1108

8       96 GRD-6                                1038      1108

9       141 Levy Unit 1 Timeline                1210

10       142 Excerpts From PEF COLA              1210

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1036

1                         P R O C E E D I N G S

2                 (Transcript follows in sequence from

3       Volume 5.)

4                 COMMISSIONER EDGAR:  Folks, we're going to get

5       started in just a moment, if you could all gather

6       together again for us.  The Chairman has asked that we

7       proceed, and he's going to watch us from above so that

8       he can stretch out his, his back.  And he has also asked

9       that I convey that he would like us to try to adhere to

10       the schedule that we have kind of been doing, which is

11       run lunch around 1:00ish to 2:15ish, depending on the

12       natural break, and that we may go to 7:00ish, not the

13       way he put it but the way I put it, to see how far we

14       can get.  And so we'll just see how things are going

15       later in the afternoon.

16                 So with that, I would like you to call your

17       next witness.

18                 MR. ROACH:  Okay.  My name is Ed Roach.  Our

19       next witness is Gary Doughty.

20                           GARY R. DOUGHTY

21       was called as a witness on behalf of Progress Energy

22       Florida and, having been duly sworn, testified as

23       follows:

24                          DIRECT EXAMINATION

25       BY MR. ROACH:

FLORIDA PUBLIC SERVICE COMMISSION

1037

1            Q.   Mr. Doughty, state your name and work address.

2            A.   Gary Robert Doughty, 412 White Columns Way,

3       Wilmington, North Carolina.

4            Q.   And by whom are you employed and in what

5       position?

6            A.   I'm employed by Janus Management Associates,

7       Incorporated, and I am president.

8            Q.   Has your direct testimony of 57 pages and

9       accompanying exhibits been prefiled on March 2nd in this

10       proceeding?

11            A.   Yes.

12            Q.   Do you have any changes or corrections to your

13       testimony?

14            A.   No.

15            Q.   If I asked you the same questions today, would

16       you give the same answers?

17            A.   Yes.

18                 MR. ROACH:  I'd like to ask that the prefiled

19       testimony of Mr. Doughty be inserted into the record as

20       if read.

21                 COMMISSIONER EDGAR:  The prefiled, the

22       prefiled testimony of the witness will be inserted into

23       the record as though read.

24                 MR. ROACH:  Okay.  I'd like to also note that

25       Mr. Doughty has six exhibits which are marked

FLORIDA PUBLIC SERVICE COMMISSION

1038

1       GRD-1 through GRD-6.

2                 COMMISSIONER EDGAR:  Thank you.

3                 MR. ROACH:  Which have been preidentified as

4       Exhibits 91 through 96.

5                 (Exhibit 91 through 96 marked for

6       identification.)

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1096

1       BY MR. ROACH:

2            Q.   Mr. Doughty, could you summarize your

3       testimony?

4            A.   Yes.

5                 COMMISSIONER EDGAR:  And, I'm sorry, did you

6       ask if he had been sworn?

7                 MR. ROACH:  He has been.  Yes, ma'am.

8                 COMMISSIONER EDGAR:  He has.

9                 THE WITNESS:  Yes, I have.

10                 COMMISSIONER EDGAR:  Okay.  I apologize.  Go

11       right ahead.

12                 THE WITNESS:  Chairman and Commissioners, the

13       purpose of my testimony is to present my expert opinion

14       that Progress Energy Florida's Levy Nuclear Plant

15       project management and project controls are reasonable

16       and prudent.  This is a result of an independent review

17       conducted earlier this year of the project in seven

18       major areas:  Project oversight, project concept and

19       contract strategy, project management, project controls,

20       risk management, policies and procedures in place and

21       project assessment.

22                 In my opinion, Progress Energy has the

23       requisite processes and organization to manage a project

24       of Levy Nuclear Plant's magnitude and complexity.

25       Progress Energy has reasonable and effective management

FLORIDA PUBLIC SERVICE COMMISSION

1097

1       practices for this project.  Senior management oversight

2       and involvement are extensive.  The project governance

3       policy provides a comprehensive guide for the project

4       with coordinated independent oversight.

5                 I also conclude that the Levy Nuclear Project

6       has a sophisticated risk management process consistent

7       with industry best practices.  There are reasonable

8       project controls in place to develop estimates, to

9       monitor schedules and to control contractors.  There is

10       reasonable reporting and performance monitoring, and

11       those processes are being improved with the signing of

12       the EPC contract.

13                 Additionally, there is an effective and

14       comprehensive set of existing project management and

15       execution policies and procedures.  And, finally, there

16       are extensive project reviews -- internal audits,

17       external audits, benchmarking, self-assessment and

18       quality control reviews -- to comply with NRC

19       requirements.  All of these demonstrate that the Levy

20       Nuclear Plant project management and project controls

21       are reasonable and prudent.  That finishes my summary.

22                 MR. ROACH:  The witness is available for

23       cross-examination.

24                 COMMISSIONER EDGAR:  Thank you.

25                 Mr. Rehwinkel.

FLORIDA PUBLIC SERVICE COMMISSION

1098

1                 MR. REHWINKEL:  No questions.

2                 COMMISSIONER EDGAR:  Mr. Brew.

3                 MR. BREW:  Thank you, Commissioner.

4                          CROSS EXAMINATION

5       BY MR. BREW:

6            Q.   Good morning, Mr. Doughty.  How are you?

7            A.   Good morning.  I am fine.

8            Q.   You said in your summary that you performed

9       the work for Progress earlier this year.  Was the work

10       that you performed for Progress exclusively for the

11       purpose of this proceeding?

12            A.   Yes.

13            Q.   Do you do any other work for Progress relating

14       to its nuclear program?

15            A.   No, not currently.

16            Q.   Did you perform any work for them in 2008?

17            A.   No.

18            Q.   Okay.  Did you attend any Progress/NRC

19       meetings or discussions?

20            A.   Any Progress meetings with the NRC?

21            Q.   NRC, yes.

22            A.   No, I did not.

23            Q.   Okay.  Your discussion in direct testimony has

24       a considerable discussion of, of prudence reviews; is

25       that right?

FLORIDA PUBLIC SERVICE COMMISSION

1099

1            A.   Yes, it does.  Could you refer me to the page

2       you're talking about?

3            Q.   Well, I'm talking generally.  But why don't we

4       just look at GRD-3 of your exhibits.

5            A.   Okay.  I'm there.

6            Q.   Okay.  Good.  And in each of the items that

7       are listed on this, on Page 1 of 1, you provided

8       testimony and recommendations regarding the

9       reasonableness or prudence of the utility's activities?

10            A.   Yes, I did.

11            Q.   Okay.  Well, let's talk --

12            A.   And this was before the commissions that are

13       stated there in the list.

14            Q.   Before the public utility commissions that are

15       listed under the heading State Commission?

16            A.   Yes.

17            Q.   Okay.  Let's talk a little bit about prudence.

18       Prudence reviews by a regulatory commission by

19       definition are retrospective, are they not?

20            A.   They generally are, although there has been a

21       move to do some real-time prudence in some state utility

22       commission venues.

23            Q.   Okay.  And all of the prudence matters that

24       are discussed on GRD, or referenced on GRD-3 were

25       retrospective reviews?

FLORIDA PUBLIC SERVICE COMMISSION

1100

1            A.   Not exactly.  Let me go back to GRD-3.  In the

2       case of the Arkansas Nuclear One Unit 2 steam

3       generators, that was a decision that was being

4       considered by the Arkansas Public Service Commission

5       with regard to Arkansas Power & Light's decision to

6       replace the steam generators before actual work

7       proceeded.

8            Q.   On whether it should be done.

9                 Okay.  But the others were retrospective

10       reviews?

11            A.   No.  The same thing would be true in the

12       Maryland case for the replacement of the Calvert Cliffs

13       1 and 2 steam generators.

14            Q.   Okay.  It was in (phonetic) advance.

15                 All right.  For a prudence review, would a

16       utility's failure to follow its own procedures

17       constitute imprudence?

18            A.   One would have to look at the totality of

19       information available to be able to make that

20       determination.  You could not just simply say prima

21       facie that the, that the utility was prudent --

22       imprudent.

23            Q.   Okay.  So if the company had written

24       established procedures and didn't follow them, that

25       wouldn't make out a case for prudence?

FLORIDA PUBLIC SERVICE COMMISSION

1101

1            A.   Say that again.

2            Q.   That would not make out a case for prudence in

3       your opinion?

4            A.   That may indicate that there is the potential

5       that there is imprudence, but it does not say that there

6       was imprudence.

7            Q.   Okay.  Can there be imprudence for failure to

8       act in the face of circumstances that dictate actions

9       required?

10            A.   Can there be?  That's possible, yes.

11            Q.   Sure.  Okay.  Let's take a look for a minute

12       at your testimony on Page 42.

13            A.   I'm there.

14            Q.   And the Q and A beginning on Line 15, which

15       discusses Progress's risk management for the Levy

16       project.  Do you see that?

17            A.   Yes.

18            Q.   And on Lines 17 through 20 you say, "The

19       project team identified risks and prepared a Risk

20       Register to track them."  Do you see that?

21            A.   Yes.

22            Q.   If a project team member identified a risk,

23       who vetted it?

24            A.   The project team met and, the team that is the

25       project team associated with the Levy Nuclear Project

FLORIDA PUBLIC SERVICE COMMISSION

1102

1       met to review the risk, added to the register so it was

2       vetted collectively.  So, for instance, if it was a

3       licensing issue, Mr. Kitchen (phonetic) or Mr. Miller

4       would have vetted it.

5            Q.   As part of the licensing team.

6            A.   Yes.

7            Q.   Okay.  Would any, anybody independent of that

8       team review it?

9            A.   How do you mean independent?  Of the Levy

10       Nuclear Project or of the licensing team?

11            Q.   Of the licensing team.

12            A.   They may have, but I don't know for sure.

13            Q.   You don't know.  You didn't look at that.

14            A.   I didn't look at external review of the Risk

15       Register in terms of somebody vetting it.  No.

16                 MR. BREW:  Okay.  That's all I have.  Thank

17       you.

18                 COMMISSIONER EDGAR:  Thank you.

19                 Mr. Davis.

20                 MR. DAVIS:  No questions.

21                 COMMISSIONER EDGAR:  No questions.

22                 Mr. Moyle.

23                          CROSS EXAMINATION

24       BY MR. MOYLE:

25            Q.   In your summary, you indicated that you looked

FLORIDA PUBLIC SERVICE COMMISSION

1103

1       at how, as I understood it, as how Progress is managing

2       this project and managing their risk with the, with the

3       Levy planned nuclear power plants; correct?

4            A.   Correct.

5            Q.   Okay.  Wouldn't, wouldn't you agree that in

6       order to make a judgment as to how risk is being

7       managed, that an important component of that would be to

8       know the, the dollar figure to which the risk -- the

9       ultimate dollar figure that people are using to manage

10       risk?

11            A.   You may not be able to know that.  That's the

12       problem with being here now and trying to anticipate

13       what costs might be in the future.  That's why you build

14       an estimate.

15            Q.   Okay.

16            A.   So you do the best possible job you can in

17       building an estimate to include contingencies to account

18       for the possibility or potential likelihood that some

19       occurrence may happen that will cause that estimate to

20       be higher.

21            Q.   You would agree that in order to determine

22       either prudence or long-term feasibility, that cost is

23       a, is a critical component of that; correct?

24            A.   I would agree that it's a, that cost is an

25       important component.  But technical feasibility is just

FLORIDA PUBLIC SERVICE COMMISSION

1104

1       as important.  Regulatory feasibility is just as

2       important.

3            Q.   The -- you would also agree in terms of

4       formulating your, your opinion and judgment that to the

5       extent that you can have more current cost data, that

6       that would better inform your opinion; correct?

7            A.   It's what naturally happens in a, in a project

8       is that you conceive the project, you estimate the cost.

9       They have a band of uncertainty associated with them.

10       As time marches on and you procure items and receive

11       bids, you now have an actual price to incorporate into

12       your estimate or budget from which to work.  So in that

13       sense, yes, that's, that's what makes sense.  There is

14       cost, more cost certainty because you've actually

15       cleared the uncertainty bound (phonetic) into certain as

16       in the case of a fixed price contract, say.

17            Q.   Yes, sir.  Hypothetically, let's say we're

18       sitting here in 2015 having this annual proceeding and

19       you're testifying about, well, I think that the, that

20       Progress has been reasonably managing cost, you wouldn't

21       anticipate relying on a cost estimate that was done in,

22       you know, in 2009 for the basis of that testimony or

23       2008 for the basis of that testimony.  You would want to

24       try to have most current information related to cost for

25       that testimony; correct?

FLORIDA PUBLIC SERVICE COMMISSION

1105

1            A.   Not necessarily.  If the estimate is holding,

2       that is the budget is holding and what you've done is

3       transferred dollars from contingency into the actual

4       expenditure for that, say, item of cost, then, then the

5       estimate that we presented or that the company presented

6       in two thousand and -- what did you say, nine --

7            Q.   Yes.

8            A.   -- is still holding, then, and they have

9       processes and procedures to incorporate that cost, what

10       you've done is I think achieved a situation in which the

11       cost uncertainty is less but it's still holding that

12       same budget.  So you would have that current

13       information, but it may still be that same original or

14       that current estimate.  The current estimate being

15       earlier than the 2015 time frame that we're talking

16       about.

17            Q.   And it just would depend on whether, whether

18       the cost numbers are tracking correctly or not.

19            A.   Correct.

20            Q.   Okay.  Now as we sit here today, what

21       understanding do you have with respect to the total cost

22       of the planned nuclear project?

23            A.   Say that again.

24            Q.   What understanding, if any, do you have with

25       respect to the total cost for the Levy project as we sit

FLORIDA PUBLIC SERVICE COMMISSION

1106

1       here today?

2            A.   I understand that the schedule shift has

3       occurred because of the change in the LWA.  That,

4       therefore, is causing Progress Energy to renegotiate --

5       not renegotiate -- to establish new contract parameters

6       within the EPC contract to adjust the schedule.  But

7       right now we know, we know that it is the current

8       estimate.  That is, that is what we know, that is the

9       current information.  And that may or may not change

10       depending on the outcome of those negotiates.

11            Q.   And is that the estimate that you used to

12       formulate your opinion, the current, the current

13       estimate?

14            A.   That was -- when I did this work was in

15       January and February of this year, so, yes.

16            Q.   And just so the record is clear, what number

17       is that that you used with respect to formulating your

18       opinion as to the total project cost?

19            A.   It was approximately $17 billion.

20                 MR. MOYLE:  Thank you.  That's all I have.

21                 COMMISSIONER EDGAR:  Other questions from

22       staff?

23                 MR. YOUNG:  No questions.

24                 COMMISSIONER EDGAR:  Commissioners?

25                 Commissioner Skop.

FLORIDA PUBLIC SERVICE COMMISSION

1107

1                 COMMISSIONER SKOP:  Thank you, Madam Chair.

2                 Just a quick question.  And if you can't

3       answer this or this is not within your scope, I'm happy

4       to reserve it for one of the other witnesses.

5                 But in your response to Mr. Moyle's question

6       you mentioned the, the limited work authorization denial

7       by the NRC on Levy 1 and 2; is that correct?

8                 THE WITNESS:  Yes, sir.

9                 COMMISSIONER SKOP:  Okay.  Now I guess based

10       upon the prior representations of the NRC regarding its

11       newly improved and streamlined license, licensing

12       process, was it reasonably foreseeable that the NRC

13       would substantially depart from this process by denying

14       the AW -- the LWA in your opinion?

15                 THE WITNESS:  I'm not familiar enough with the

16       workings of the NRC in the current time frame, and I

17       believe Mr. Thompson may be able to better answer that.

18                 COMMISSIONER SKOP:  Okay.  All right.  Thank

19       you.

20                 COMMISSIONER EDGAR:  Redirect?

21                 MR. ROACH:  No redirect.

22                 COMMISSIONER EDGAR:  No redirect.  Okay.

23                 Exhibits.

24                 MR. ROACH:  Exhibits, I'd ask that Exhibits

25       91 through 96 be received into evidence.

FLORIDA PUBLIC SERVICE COMMISSION

1108

1                 COMMISSIONER EDGAR:  Okay.  Why am I not

2       seeing them?  91, is that what you said?

3                 MR. ROACH:  Yes, ma'am.  91 through 96.

4                 COMMISSIONER EDGAR:  Okay.  Staff, help me out

5       here.

6                 MS. CIBULA:  Page 14.

7                 COMMISSIONER EDGAR:  What page?

8                 MS. CIBULA:  Page 14.

9                 MR. ROACH:  Page 14.

10                 COMMISSIONER EDGAR:  Page 14.

11                 COMMISSIONER ARGENZIANO:  I'm sorry.  Madam

12       Chair, was it Page 14?

13                 COMMISSIONER EDGAR:  That's what we are -- ah,

14       yes.  Okay.  There you go.  Thank you very much.  So

15       Page 14, 91 to 98.

16                 MR. ROACH:  96, 91 through 96.

17                 COMMISSIONER ARGENZIANO:  Thank you.

18                 COMMISSIONER EDGAR:  91 to 96.  91 to 96 are

19       entered into the record at this time.  Thank you all for

20       getting me to the right page.

21                 (Exhibits 91 through 96 admitted into the

22       record.)

23                 And the witness is excused.  Thank you very

24       much.

25                 And you may call your next witness.

FLORIDA PUBLIC SERVICE COMMISSION

1109

1                 MS. TRIPLETT:  Thank you, Madam Chairman.  Our

2       next witness is Gary Furman.  And I believe he has also

3       been stipulated and excused from appearing at the

4       hearing.

5                 COMMISSIONER EDGAR:  Ah, I see that.  Yes.  So

6       for Witness Furman and his exhibits that I understand

7       have been stipulated, that remains the agreement of all

8       parties; is that correct?  I'm seeing nods.  Okay.  Then

9       the prefiled testimony of Witness Furman will be entered

10       into the record as though read.

11                 Exhibits?

12                 MS. TRIPLETT:  There are no exhibits.  And I

13       just wanted to make sure that there were two sets of

14       testimonies, there's a March 2nd and a May 1, and no

15       exhibits.

16                 COMMISSIONER EDGAR:  And both the March 2nd

17       and the May 1 prefiled testimony are entered into the

18       record at this time.

19                 MS. TRIPLETT:  Thank you.

20                 COMMISSIONER EDGAR:  Thank you.

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1145

1                 COMMISSIONER EDGAR:  Which brings us to

2       Witness Miller?

3                 MR. BURNETT:  Yes, ma'am.

4                 May I proceed, Madam Chair?

5                 COMMISSIONER EDGAR:  Yes, sir.

6                 MR. BURNETT:  Thank you.

7                             GARRY MILLER

8       was called as a witness on behalf of Progress Energy

9       Florida and, having been duly sworn, testified as

10       follows:

11                          DIRECT EXAMINATION

12       BY MR. BURNETT:

13            Q.   Sir, would you please introduce yourself to

14       the Commission and provide your business address?

15            A.   Yes.  My name is Garry Miller.  My business

16       address is 100 East Davie Street, Raleigh, North

17       Carolina.

18            Q.   And you've been sworn today; correct, sir?

19            A.   I have.

20            Q.   Who do you work for and what is your position?

21            A.   I work for Progress Energy Carolinas and my

22       position is General Manager, Nuclear Plant Development.

23            Q.   Have you filed two sets of prefiled direct

24       testimony dated March 2nd and May 1, 2009, in this

25       proceeding?

FLORIDA PUBLIC SERVICE COMMISSION

1146

1            A.   Yes, I have.

2            Q.   And do you have any changes to make to your

3       prefiled testimonies?

4            A.   No, I do not.

5            Q.   If I asked you the same questions in your

6       prefiled testimonies today, would you give the same

7       answers that are in the prefiled testimony?

8            A.   Yes, I would.

9                 MR. BURNETT:  Madam Chair, we request that

10       both sets of the prefiled testimony be entered into the

11       record as if they were read today.

12                 COMMISSIONER EDGAR:  Both sets of the prefiled

13       testimony of this witness will be entered into the

14       record as though read.

15                 MR. BURNETT:  Thank you.

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1201

1       BY MR. BURNETT:

2            Q.   Mr. Miller, do you have a summary of your

3       prefiled testimony?

4            A.   I do.

5            Q.   Will you please give it?

6            A.   Yes.  My name is Garry Miller.  My direct

7       testimony supports the prudence of the company's costs

8       incurred in furtherance of the Levy Nuclear Project in

9       2006, 2007 and 2008.  These costs were necessary to

10       advance the Levy Nuclear Project and they are prudent.

11       Indeed, I understand that no Intervenor has challenged

12       the prudence of any specific actual cost incurred by the

13       company from 2006 through 2008 for the Levy Nuclear

14       Project.

15                 I also explain in my direct testimony that the

16       company's estimated 2009 and 2010 costs for the Levy

17       Nuclear Project are reasonable.  These estimated costs

18       reflect a lower level of spending that accounts for the

19       unexpected schedule shift for the Levy Nuclear Project

20       due to the NRC's determination that it cannot timely

21       review and therefore issue the limited work

22       authorization, LWA, requested by the company.

23                 These estimated costs primarily involve

24       scheduled long-lead item payments and the necessary cost

25       to obtain a combined operating license from the NRC for

FLORIDA PUBLIC SERVICE COMMISSION

1202

1       the nuclear project and other federal and state

2       regulatory approvals.  These costs would have been

3       incurred in 2009 and 2010 regardless of the NRC's

4       decision with respect to the LWA.  As I understand too,

5       no Intervenor has challenged the reasonableness of any

6       specific estimated cost for 2009 and 2010 for the Levy

7       Nuclear Project.

8                 Finally, my testimony supports the long-term

9       feasibility of the LNP.  The LNP continues to be

10       feasible for a number of reasons including, number one,

11       the Westinghouse AP 1000 reactor design remains a viable

12       nuclear technology for the deployment at the Levy site,

13       with, among other factors, AP 1000 construction is

14       proceeding at two sites in China.

15                 Number two, the Levy, the LNP remains feasible

16       from a project milestone perspective as evidenced by the

17       fact that PEF has achieved every major milestone as

18       planned with the exception of the LWA, which is now part

19       of the COL issuance.

20                 And, third, the essential reasons for the LNP

21       have not fundamentally changed.  Therefore, the

22       long-term completion of the Levy nuclear power plants is

23       feasible.  Thank you.

24                 MR. BURNETT:  Madam Chair, before tendering

25       Mr. Miller I would just like to note for Mr. Miller and

FLORIDA PUBLIC SERVICE COMMISSION

1203

1       the parties that he has quite a bit of confidential

2       information in his testimony.  So I'd just ask for Mr.

3       Miller to be cognizant of that in giving his responses,

4       but we tender him for cross.

5                 COMMISSIONER EDGAR:  Okay.  Thank you for the

6       point.  We ask everyone, of course, to be sensitive to

7       that and we'll work our way through it together, if need

8       be.

9                 Mr. Rehwinkel, do you have cross.

10                 MR. REHWINKEL:  Yes I do, Madam Chairman.  And

11       along the lines of Mr. Burnett's comments, I have fairly

12       lengthy cross-examination for this witness, and a good

13       bit of it deals with confidential information.  So I am

14       going to endeavor to be very cautious about that.  I

15       would beg the Commission's indulgence with respect to

16       the pace of cross-examination because I want to be very

17       cautious and make sure that any answer I elicit is given

18       consideration by the witness as to the nature of the

19       information, and the need to point to information and

20       ask people to read it versus stating it out loud.  So

21       I'd just ask for your indulgence on that.

22                 COMMISSIONER EDGAR:  I understand.  And,

23       again, we appreciate your sensitivity.

24                 MR. REHWINKEL:  Thank you.

25                          CROSS EXAMINATION

FLORIDA PUBLIC SERVICE COMMISSION

1204

1       BY MR. REHWINKEL:

2            Q.   Good afternoon, Mr. Miller.

3            A.   Good afternoon.

4            Q.   My name is Charles Rehwinkel.  We've met

5       before.  It's good to see you again.

6            A.   You too.

7            Q.   You are the person or the individual in the

8       most direct, most directly, in management most directly

9       responsible for the building of the LNP project; is that

10       correct?

11            A.   That is correct.

12            Q.   In your testimony that you've given in this

13       matter so far, including your deposition, you have

14       described a series of events culminating in a schedule

15       shift of between 20 to 36 months; is that correct?

16            A.   That is correct.

17            Q.   And by schedule shift, I mean in the schedule

18       of the licensing, construction and completion of the LNP

19       project.

20            A.   That is correct.  It is a schedule shift in

21       the in-service date of the LNP project.

22            Q.   Okay.  And is that still a good estimate?

23            A.   The 20 to 36 month is still a good estimate.

24       Yes.

25            Q.   Okay.  And do you still have -- do you have

FLORIDA PUBLIC SERVICE COMMISSION

1205

1       any idea when you might decide whether it's 20 or 36 or

2       some other number?

3            A.   Yes.  The, the, the decision-making is ongoing

4       in our company with regard to the final decision of what

5       that schedule shift would be, incorporating information

6       that we're getting from Westinghouse and Shaw and

7       considering other relevant information.  And so we would

8       anticipate we would make that decision here maybe in the

9       next two months.

10            Q.   Okay.  But here today you cannot say what that

11       schedule shift number actually will be; is that right?

12            A.   It is correct to say that our company has not

13       made a decision as of today on the schedule shift.

14            Q.   Okay.  Do you have with you, just so I can

15       take care of this before I move on, do you have with you

16       the testimony of Thomas Foster or Geoff Foster?

17            A.   I do not, but I have the exhibits that I

18       sponsored.

19            Q.   Okay.  Do you have the exhibit I asked

20       Mr. Foster about, which is P8 TGF-2, Page 3 of 3?

21            A.   I have TGF-2.  Let me go to the specific page

22       you're talking about.  Schedule P8?

23            Q.   Yes.

24            A.   At the bottom it says Page 20 of 46?  At the

25       bottom of the document.

FLORIDA PUBLIC SERVICE COMMISSION

1206

1            Q.   I don't have that.

2            A.   I believe it's, I believe I know which page

3       you're talking about, so let's proceed.

4            Q.   Okay.  What I'm asking you about is Line 15,

5       Column H.  And it is a confidential number; is that

6       correct?

7            A.   That is correct.

8            Q.   Okay.  Can you tell me, without telling me

9       what the number is, can you state publicly what this

10       number represents, represented at the time it was put on

11       the schedule?

12            A.   It represented the overnight contract price

13       for the EPC.

14            Q.   Okay.  And that's the EPC to construct Levy

15       Nuclear Units 1 and 2?

16            A.   That is correct.

17            Q.   Can you tell me whether the number on Line 15,

18       Column H has changed?

19            A.   Yes, it has changed.

20            Q.   Do you know what it has changed to?

21            A.   I cannot give you the specific number, but I

22       do know why it changed and sort of the magnitude of the

23       change.

24            Q.   Okay.  Can you state publicly what the

25       magnitude of the change is?

FLORIDA PUBLIC SERVICE COMMISSION

1207

1            A.   No, because it's a change order, which is a

2       confidential document.

3            Q.   Okay.  Is it possible that you could provide

4       that, that number that represents change to the parties

5       who have executed nondisclosure agreements in this

6       docket?

7            A.   I would have to consult with the legal team of

8       how to do that.

9            Q.   Okay.  Is it possible that that number could

10       be provided before you get on the stand for rebuttal?

11            A.   Yes, assuming that we work through the legal

12       mechanism to do that.

13                 MR. REHWINKEL:  Okay.  Madam Chairman, what I

14       would like to do, similar to the request I had of

15       Mr. Franke, is ask for the incremental change in the

16       figure, Line 15, Column H, to be provided informally to

17       parties who have a, have executed the appropriate legal

18       documents to view it, if any.

19                 COMMISSIONER EDGAR:  Mr. Burnett.

20                 MR. BURNETT:  No objection.

21                 COMMISSIONER EDGAR:  Okay.

22                 MR. REHWINKEL:  And that we be shown this

23       information between culmination of his direct testimony

24       and his reappearance for rebuttal.

25                 COMMISSIONER EDGAR:  Okay.  If it's possible

FLORIDA PUBLIC SERVICE COMMISSION

1208

1       to do that on the lunch break to get it started, please

2       do so.  If not, just as soon as reasonably able.

3                 MR. REHWINKEL:  Okay.

4                 MR. BURNETT:  Yes, ma'am.

5                 MR. REHWINKEL:  Thank you.  And I will not ask

6       as a late-filed exhibit.  We'll deal with that, if

7       necessary, at that time.

8                 COMMISSIONER EDGAR:  Okay.

9       BY MR. REHWINKEL:

10            Q.   Okay.  Do you know if, Mr. Miller, if any

11       other numbers on this TGF-2 schedule have changed

12       because of the schedule shift?

13            A.   I have not reviewed these lines on this

14       particular, on P8 in that regard.  As you can imagine,

15       there are contracts on here related to the overall

16       project execution.  And so while you picked the one that

17       was related to the EPC, there are others such as related

18       to transmission, and all of that schedule is being

19       shipped accordingly.  So there are some other contracts

20       on here that could possibly change.

21            Q.   Okay.  Do you know with any degree of

22       certainty -- or let me ask it this way.  Do you know

23       with the same degree of certainty that you know about

24       the number we just discussed, the incremental change to

25       the EPC number, those other numbers?

FLORIDA PUBLIC SERVICE COMMISSION

1209

1            A.   No, because the activities to reflow that work

2       is still in progress.  So, no.

3            Q.   Okay.  I'm done with this schedule then for

4       now.  Thank you.

5                 Now in your testimony, isn't it correct that

6       the cause, according to you, for -- well, let me, let me

7       strike that question.

8                 And, Commissioner, I would like to ask for an

9       exhibit, two exhibits to be passed out at this time for

10       cross-examination.  And these are not confidential.

11                 COMMISSIONER EDGAR:  Okay.

12                 MR. REHWINKEL:  And while Ms. Vandiver passes

13       those out, while Ms. Vandiver passes those exhibits out

14       --

15                 COMMISSIONER EDGAR:  So I am on 141, I

16       believe.

17                 MR. REHWINKEL:  Okay.  Item 141 would be a

18       one-page exhibit called Levy Unit 1 Timeline.

19                 COMMISSIONER EDGAR:  Yes, please.

20                 MR. REHWINKEL:  And the second exhibit is

21       Excerpts from PEF COLA, C-O-L-A.  That's a four- page

22       exhibit.

23                 COMMISSIONER EDGAR:  Okay.  Exhibit marked

24       141, Levy Unit 1 Timeline.  142, Excerpts from PEF COLA.

25                 MR. REHWINKEL:  Actually it's a seven-page

FLORIDA PUBLIC SERVICE COMMISSION

1210

1       exhibit.  I misstated it.

2                 COMMISSIONER EDGAR:  This says Page 4 -- Pages

3       4 at the top.

4                 MR. REHWINKEL:  Yes.  So what says four needs

5       to be changed to seven.

6                 COMMISSIONER EDGAR:  So noted.  Thank you.

7                 MR. REHWINKEL:  Thank you.

8                 (Exhibits 141 and 142 marked for

9       identification.)

10       BY MR. REHWINKEL:

11            Q.   Mr. Miller, do you have the exhibits that have

12       been marked 141 and 142 --

13            A.   I do.

14            Q.   -- in front of you?

15                 Exhibit 141 is the Levy estimated timeline of

16       the first unit.  Do you see that?

17            A.   I do.

18            Q.   Are you familiar with this document or this, a

19       document similar to this?

20            A.   Yes.

21            Q.   Okay.  And I'll represent to you this came

22       from a September 2008 slide presentation that included

23       confidential information, so I've excerpted just this

24       document.

25            A.   Okay.

FLORIDA PUBLIC SERVICE COMMISSION

1211

1            Q.   Is it fair to say that this document here

2       represented, represents what your intent was with

3       respect to the timeline from filing of -- well, from the

4       preparation of your combined license application through

5       to commercial operation date for the Levy Unit 1?

6            A.   I would characterize this as a graphic

7       illustration of how the schedule flows sort of in a

8       graphical form.

9            Q.   Okay.

10            A.   That's what this document is.

11            Q.   So at a very high level, this is, this is the

12       major time milestone points for your project for Number

13       1.

14            A.   At the time this document was produced, that

15       is correct.

16            Q.   Okay.  And the green box here with the arrow

17       pointing from the words LWA, that is the time frame that

18       the company intended to do the, essentially the

19       dewatering and excavation work that was the essence of

20       the LWA request; is that correct?

21            A.   Well, based on the timeline of this, depending

22       on when it was exactly in September, this LWA scope

23       could have been from excavation forward, meaning

24       engineered (phonetic) backfill, mud mat, those kind of

25       things, forms, drilled shafts into some of the other

FLORIDA PUBLIC SERVICE COMMISSION

1212

1       buildings.  So depending on when it was this actual

2       document was produced, as with respect to the

3       September 12th letter where we modified the LWA scope,

4       subject to that clarification, it's describing where we

5       need LWA to come in to complete certain preconstruction

6       work prior to the work governed by the COL.

7            Q.   Okay.  And it is correct, is it not, that

8       performing the excavation and dewatering work as well as

9       the other work that was described in your LWA request to

10       the, to the NRC that was filed on September 12th, that

11       was crucial to meeting the September, I mean the 2016

12       COD; is that correct?

13            A.   Yes.  It is correct that the LWA as requested,

14       to complete that work in advance of early 2012, that was

15       necessary to achieve the mid 2016 date.

16            Q.   Okay.  Could you turn to Exhibit 142, which

17       are, as I represent to you, excerpts from the various

18       sections of your COLA that was on the Nuclear, the NRC's

19       website.  Are you generally familiar with, with these

20       documents?

21            A.   I am.

22            Q.   Okay.  And just the page, the first page there

23       is just a graphic representation of the way the two

24       units would look on the, superimposed on a photograph of

25       the site; is that right?

FLORIDA PUBLIC SERVICE COMMISSION

1213

1            A.   That is correct.

2            Q.   Okay.  And then the next page just shows the

3       location of the, the, the site with a star representing

4       the location of the units; is that correct?

5            A.   Correct.  That broken line which represents

6       the property boundary, which is defined as the site, and

7       the star is the general location of the power blocks

8       within that site.

9            Q.   Okay.  And the location of the star within the

10       dotted line is, is not an accident.  That was something

11       that was, although it's probably an approximation of the

12       unit site, there is a reason for it being in that

13       location; is that right?

14            A.   There is a reason.  Nuclear plants require an

15       exclusionary area boundary, if you will, a buffer around

16       the plant where you control all the property for

17       emergency purposes.  And so it, it's ideal to be able to

18       place the facilities in the center of the property and

19       take advantage of the property boundaries to the maximum

20       extent.

21            Q.   Okay.  And on the next page, this is the same

22       outline that's shown on the, with the dotted line, but

23       this shows where wetlands exist on the property site and

24       in the, in the surrounding land; is that correct?

25            A.   That is correct.  It shows an outline of the

FLORIDA PUBLIC SERVICE COMMISSION

1214

1       power blocks and then it shows a wetland delineation.

2            Q.   Okay.  And those, those locations also played

3       a role in where you designated the exact location of the

4       units; is that correct?

5            A.   Well, it's correct in a sense.  When I go back

6       and remind you that the goal would be to place the units

7       in the center of the property to maximize the boundaries

8       to all the site boundaries, it turned out the way that

9       property was laid out that there were upland areas in

10       the center of the site that did not require a permit to

11       get into the wetlands.  And so it was, it just happened

12       that we were able to start the work in the very center

13       of the site.

14            Q.   Okay.  And then on the next page there's a

15       representation of where a 100-year flood zone is

16       relative to the site; is that correct?

17            A.   It is a representation of the 100-year flood

18       zone with respect to the current grade of the site.

19            Q.   Okay.  Did that play any role in the location

20       of the units within the property boundaries?

21            A.   No.  But the reason is is because the current

22       grade of the site is approximately 42 feet above sea

23       level.  And as part of the preparation of the site, we

24       will remove some of the soil overburden that has roots

25       and vegetative matter and then raise that level to

FLORIDA PUBLIC SERVICE COMMISSION

1215

1       approximately 50 feet at the power blocks.

2            Q.   Okay.  Thank you.  The next page is sort of a

3       chart representation of the strata, the various strata

4       of soils and rocks in the area, the hydrology and kind

5       of the classification of, of the strata and geological

6       terms; is that correct?

7            A.   Yes.  This is a representation graphically of

8       the layers of the geosubstrate.

9            Q.   And I, I am just taking you through this to

10       get some context for some of the questions that I'm

11       going to ask you.

12                 The next page shows kind of the geology of the

13       area, the surface rock and the sediment types within ten

14       feet of the, of the land surface relative to the

15       location of the plant; is that right?

16            A.   One moment.  Let me review this document.

17            Q.   Sure.

18            A.   So this is a representation of what's in the

19       top ten feet of the soil overburden, if you will.

20            Q.   Okay.  And so where the star is shows that --

21                 COMMISSIONER EDGAR:  Mr. Rehwinkel, could you

22       pause for a moment?

23                 MR. REHWINKEL:  Yes.

24                 COMMISSIONER EDGAR:  I think Commissioner Skop

25       would like to ask a question.

FLORIDA PUBLIC SERVICE COMMISSION

1216

1                 COMMISSIONER SKOP:  Yes.  I just want to make

2       sure I'm understanding, because we're flipping through

3       the pages.  You're looking at the cross section of the,

4       the soil top layers; is that correct?  Okay.  A

5       different one.  Never mind.  I'll reserve my question.

6                 COMMISSIONER EDGAR:  Thank you.

7                 Mr. Rehwinkel.

8                 MR. REHWINKEL:  Okay.  Thank you.  Yes.

9       BY MR. REHWINKEL:

10            Q.   The star shows that the site is, is on what

11       would be kind of medium/fine sand and silt; is that

12       right?

13            A.   Just for clarification, let me verify you're

14       on Figure 2.3-17?

15            Q.   I apologize.  Yes, that's correct.

16            A.   All right.  What this document shows is what

17       is present within ten feet of the land surface.  So at

18       the star location it would be the top ten feet surface

19       is medium/fine sand and silt.

20            Q.   So if you, if you go back to the prior page

21       and you look under the column that's headed Geology and

22       Lithology, the sand is at the top.

23            A.   I would characterize it as sandy soil.

24            Q.   Okay.  And as you go down vertically, you

25       encounter under the blocks that are under sand, sand and

FLORIDA PUBLIC SERVICE COMMISSION

1217

1       clay, phosphate, sand limestone and dolostone, limestone

2       and dolostone, limestone and dolostone, et cetera.  And

3       to, to the left under Stratigraphic Unit shows the

4       classification of those strata under the geological

5       classification system; is that right?

6            A.   That's correct.

7            Q.   Okay.  Now the Levy site and the issues that

8       are part of the geotechnical presentation you made to

9       the NRC as part of your LWA and your COLA relate

10       primarily to the Avon Park foundation -- Formation; is

11       that right?

12            A.   That is correct.

13            Q.   Okay.  So the Avon Park Formation is the, the

14       formation that would be most impacted by the

15       geotechnical analysis that the NRC staff would be making

16       of your filing; is that right?

17            A.   That is correct.

18            Q.   Okay.  And right above the Avon Park

19       foundation (sic.) is Ocala Limestone; is that right?

20            A.   That is correct.

21            Q.   As it shows here.  Now --

22            A.   If it's present.

23            Q.   Yes.  Let's turn to the last page of the

24       exhibit, and this is Figure 2.3-18, and it shows the

25       regional aquifer system analysis; is that correct?

FLORIDA PUBLIC SERVICE COMMISSION

1218

1            A.   Yes.  I see this as Figure 2.3-18, regional

2       aquifer system analysis.

3            Q.   Okay.  And just for the record, the yellow

4       highlighting on here is mine, not, not what, part of

5       what you filed.

6                 But is it correct that the, on the right-hand

7       side --

8                 COMMISSIONER EDGAR:  Mr. Rehwinkel, I'm sorry,

9       one more time.  Commissioner Skop -- and maybe a time

10       after that, too.  Commissioner Skop.

11                 COMMISSIONER SKOP:  Thank you, Madam Chair.

12                 Just to Mr. Rehwinkel and to the witness, I

13       just want to make sure I'm understanding this particular

14       figure, and I was a page ahead of you as I was trying to

15       form my question.  But the yellow line that you drew,

16       Mr. Rehwinkel, is the section view from D to D prime.

17       And that, is that the cross section that is illustrated

18       in the top left-hand corner?

19                 MR. REHWINKEL:  That was my next question.

20       Yes.

21                 COMMISSIONER SKOP:  All right.  Thank you.

22       BY MR. REHWINKEL:

23            Q.   Is that, is that correct, Mr. Miller?

24            A.   I'm not familiar enough with this graphic to

25       make that, make that determination.  However, I do know

FLORIDA PUBLIC SERVICE COMMISSION

1219

1       that there, the limestone has slope in that area.  And

2       in the case of the Levy nuclear site, it's Avon Park

3       which comes closest to the surface.  As a matter of

4       fact, that's represented up in the inset figure where it

5       says Levy Nuclear Plant location, and you can see, if

6       you follow the shaded crosshatched area, it's

7       predominantly the Avon Park Limestone.

8            Q.   Okay.  So where you see at the bottom of that

9       inset the word "Cedar Key Limestone," and line that goes

10       up from that points to a little, tiny piece of Ocala

11       Limestone; is that correct?

12            A.   I see that.  Yes.

13            Q.   Okay.  But surrounding that is, everything

14       that touches the surface in the crosshatching is in the

15       Ocala Limestone and Lake City Limestone undifferentiated

16       strata; is that right?

17            A.   Again, I'm trying to interpret the graphic

18       because I've not seen this in quite a while.  And as I

19       looked at it again, I do agree that the D to D prime is

20       the, what you characterize as that yellow line that

21       you've marked on the larger figure.  It's a cross

22       section.

23                 I cannot discern because the granularity of

24       this image is not so great in the Levy Nuclear Plant

25       area location, but I see either Avon, Avon Park

FLORIDA PUBLIC SERVICE COMMISSION

1220

1       Limestone at the surface or Ocala Limestone at the

2       surface, and in some places farther on up you get

3       Suwannee Limestone and others.  But at the Levy Nuclear

4       Plant location it's dominated by the Avon Park.

5            Q.   Okay.  So it looks like on this that the line

6       that comes from Levy Nuclear Plant location touches what

7       is Avon Park Limestone as it comes to the surface; is

8       that correct?

9            A.   That's what this graphic appears to show.

10            Q.   Okay.  And that's what you filed with the NRC.

11            A.   That's my understanding from my general

12       understanding of the geology of the site.

13            Q.   Okay.  And I ask you these questions because

14       isn't it true that the geology of the site was very

15       crucial with respect to the evaluation and consideration

16       by the NRC of your LWA?

17            A.   I would answer your question as it's certainly

18       relevant.  As the NRC makes a deliberation on the LWA,

19       they need to understand the geology and how the

20       foundation design is going to progress to be able to

21       make that determination.

22            Q.   And you recognize when you -- well, let me ask

23       it to you this way.  Isn't it true that selecting the

24       site for your nuclear plant is a crucial part of the

25       planning of your, of the construction of a nuclear

FLORIDA PUBLIC SERVICE COMMISSION

1221

1       plant?

2            A.   The site selection is probably the most

3       critical first step you take.

4            Q.   Okay.  And one of the major considerations

5       that you undertook was a site that would support various

6       needs for location to transmission, et cetera, but, but

7       significantly geology.

8            A.   Yes.  And I was involved and led the siting

9       study for the Levy site, and we considered, as you said,

10       geology or geotechnical features, we considered

11       availability of water, the ability to deliver the

12       transmission capacity from that site, other parameters

13       such as nearby land uses, all of those were considered,

14       but certainly geology and geotechnical is an area that's

15       very significant to that decision-making.

16            Q.   Okay.  And is it fair to say that from a time

17       constraint standpoint you were fairly challenged to get

18       a site selected such that you could meet a date that you

19       identified in your need analysis?

20            A.   I would not characterize it that way, sir.

21       Because as when we started the siting process in late

22       2005, we had not established the 2016 in-service date at

23       that time.  Our goal was to identify a site and start

24       the process, and then build a schedule that would then,

25       you know, yield the in-service date we desired.

FLORIDA PUBLIC SERVICE COMMISSION

1222

1                 I would characterize it more as bookends.  You

2       have a, you'll have a need that'll establish the end

3       date, the in-service date, but you cannot start until

4       your site is selected because you must have that to

5       begin to do the analysis on that particular site.  But

6       the siting would drive the overall schedule.  It cannot

7       start before that --

8            Q.   Okay.

9            A.   -- until the site is selected.

10            Q.   So was it -- is it fair to say that by the

11       time you selected a site, you were approaching a very

12       critical stage to meet a 2016 in-service or COD date?

13            A.   It would be correct to say that as we selected

14       the site and announced it in December of 2006, we had

15       approximately 18 months to be able to complete an

16       application and submit it in July of 2008 that would

17       yield an overall schedule of 2016.

18            Q.   Okay.  So that was your window of opportunity

19       to develop a COLA, the 18 months?

20            A.   For a 2016 in-service date.

21            Q.   Okay.  Yes.  And sometime between the

22       December 2006 announcement of the site and the first

23       part of 2007 you realized, did you not, that you would

24       need an LWA in order to meet the 2016 COD?

25            A.   During 2007, yes, we did identify the fact

FLORIDA PUBLIC SERVICE COMMISSION

1223

1       that an LWA would be necessary for the Levy site to

2       achieve a 2016 in-service date.

3            Q.   And would it be fair to say that the LWA that

4       you envision would be somewhat of a linchpin in meeting

5       that schedule?

6            A.   It was -- yes, it was an important element.  I

7       don't know if the term "linchpin" is the correct phrase.

8       But it was certainly an important element of the overall

9       schedule to achieve the mid 2016 date.

10            Q.   Did you realize at the time you decided you

11       needed an LWA that without an LWA and the ability to

12       do -- or the ability to do the dewatering and excavation

13       before the issuance of a COL, that you would not be able

14       to meet the 2016 COD?

15            A.   Yes.  Yes.  As the schedule was built and as

16       the schedule was presented in our need determination

17       last year, it actually incorporated LWA as an integral

18       part of that schedule that was necessary to achieve a

19       mid 2016 in-service date.

20            Q.   Okay.  Now having established the need for an

21       LWA and the time frame for an LWA, that, that played a

22       significant role in the negotiation of the EPC, did it

23       not?

24            A.   The -- I wouldn't say -- it's not a

25       significant role.  It is a parameter that affects the

FLORIDA PUBLIC SERVICE COMMISSION

1224

1       execution of the EPC that had to be considered in the

2       timing of how the EPC would flow from a work

3       perspective.

4            Q.   Well, did the LWA influence the cash flows

5       that you negotiated within the EPC?

6            A.   No, and let me explain why.  Because the LWA

7       scope of work which currently -- which would have been

8       diaphragm wall installation, permeation grouting,

9       excavation dewatering then engineered backfill, mud mat,

10       and that sequence all through that, that scope of work

11       has to be done regardless of whether it's authorized

12       through an LWA or authorized through a COL.  Because it

13       is necessary to do that to be able to establish the

14       conditions for the first pour of safety-related

15       concrete.  So that scope of work and the cost of that

16       scope of work is in the EPC irrespective of what

17       regulatory approval authorizes it.

18            Q.   Okay.  I think your question was directly

19       responsive to the question that I asked, but I don't

20       think I asked the question I intended.

21            A.   Okay.

22            Q.   So my question is this, the, the ability to do

23       the work that was subsumed ultimately in the LWA

24       directly affected the schedule that influenced the cash

25       flows in the EPC; is that correct?

FLORIDA PUBLIC SERVICE COMMISSION

1225

1            A.   Yes.

2            Q.   Okay.

3            A.   The milestones that are in the EPC, such as

4       first concrete pour, they assume certain regulatory

5       approvals in advance of that.  And so those milestones

6       do flow assuming that an LWA was authorized in the

7       current version of the EPC.

8            Q.   Okay.  And without the LWA or the ability to

9       do the work that was subsumed in the LWA, the EPC that

10       you negotiated would not meet the reality of meeting a

11       COD of 2016; is that right?

12            A.   State your question again.  It was --

13            Q.   Okay.  Without doing the work that was in the

14       LWA prior to 2012, the, the milestones and the cash

15       flows that you negotiated in the EPC would be

16       meaningless; is that correct?

17            A.   The phrase "meaningless" is not an accurate

18       representation.  I would say to you that without meeting

19       the regulatory, getting the regulatory approval that the

20       schedule was based on, that means that the

21       preconstruction work in advance of the COL that is

22       governed by the LWA, that scope of work, that work would

23       then necessarily have to move in time.  And so the

24       schedules which were in the EPC and the associated cash

25       flow that goes with them would be changed.  They

FLORIDA PUBLIC SERVICE COMMISSION

1226

1       wouldn't be meaningless because a lot of that work would

2       be -- you can use that same information to move it in

3       time.

4            Q.   So my question -- and I understand.  That's a

5       fair answer to my question.  But with respect to meeting

6       a 2016 date, not achievable if you had to do the LWA

7       work inside of the COL; is that correct?

8            A.   It is correct to say that without an LWA

9       approval in advance of the COL, the schedule that's in

10       the current EPC could not be executed as it exists.

11            Q.   Okay.  And there is no way that you would

12       proceed under an EPC with -- let me strike that

13       question.

14                 So having determined that -- well, we've

15       established that the LWA was critical to meeting the

16       schedule that you negotiated in your EPC; is that

17       correct?

18            A.   That's correct.

19            Q.   Okay.  That in turn affected your

20       negotiations -- well, let me say this.  That in turn

21       affected your ability to lock down joint owner

22       commitments; is that correct?

23            A.   No.  I don't see the connection you're making.

24       I don't understand your question.

25            Q.   Okay.  Negotiating towards certain milestones

FLORIDA PUBLIC SERVICE COMMISSION

1227

1       within the EPC drove your ability to get commitments

2       from joint owners; is that correct?

3            A.   I believe I understand your question is is

4       the, was the timing and the ultimate execution of the

5       EPC related to the timing and execution of joint owner

6       agreements?

7            Q.   Yes.

8            A.   Is that your question?

9            Q.   That's my question.

10            A.   The answer is those are linked together, and

11       we would expect that the EPC would be executed and then

12       you would follow that with the joint owners' agreements.

13       And so they are linked in that perspective.

14            Q.   Okay.  Is it fair to say that there's kind of

15       a domino analogy?  Is it the LWA being done at the time

16       you assumed is linked to the assumptions about when,

17       about how you structure your EPC that you're going to

18       agree to, which is also then linked to what you can

19       negotiate with joint owners?

20            A.   I don't agree with the term "domino."  But it

21       is accurate to say that the EPC considered the LWA as

22       part of the regulatory approval, and so the schedules in

23       the EPC reflected the ability to, to complete certain

24       work in advance of first concrete as authorized by the

25       NRC under an LWA.  And then following through with that,

FLORIDA PUBLIC SERVICE COMMISSION

1228

1       then obviously the final execution of the EPC, as I said

2       earlier, that is linked to the joint owner agreements.

3            Q.   Okay.  Well, if you -- your testimony has been

4       that absent execution of an EPC, you could not get legal

5       commitments from joint owners for the LNP project.

6            A.   My testimony is, just to be accurate, is that

7       we, it was our intention to execute the EPC.  And in

8       advance of that, we would have negotiations with joint

9       owners.  And then once the EPC was executed, that would

10       then afford the ability to close the joint owner

11       negotiations.

12            Q.   Okay.  Were any joint owners willing to sign a

13       binding commitment to the project without knowing what

14       the EPC agreement would look like and execute it --

15       without seeing an executed EPC?

16            A.   I was not involved directly in those

17       negotiations, so I cannot answer your question.

18            Q.   Okay.

19            A.   I cannot answer that.

20            Q.   So that might be better asked to Mr. Lyash?

21            A.   That would be correct.

22            Q.   Okay.  So is it -- it's true, is it not, that

23       your testimony before this Commission is that the NRC's

24       determination on an LWA is the sole cause for the delay

25       in LNP schedule?

FLORIDA PUBLIC SERVICE COMMISSION

1229

1            A.   It is my, it is my testimony that the LWA

2       determination by the NRC necessarily drives a schedule

3       shift in the Levy project.

4            Q.   And when you -- I asked NRC's determination.

5       I think in your testimony you characterize it as the NRC

6       staff's determination.  Is there a difference?

7            A.   In this case I would not characterize it.

8       When I refer to NRC or NRC staff, I'm talking about the

9       collective NRC organization.

10            Q.   Okay.  And do the Commissioners at the NRC

11       make, have any role in deciding whether or not they're

12       going to -- or the schedule of the LWA?

13            A.   In this particular case, no, the Commissioners

14       were not involved in this determination of whether an

15       LWA would be granted in advance of the COL.  That's done

16       at the staff level.

17            Q.   Okay.  That's something that's delegated to

18       them?

19            A.   It's their responsibility.  It's not

20       necessarily a delegation.

21            Q.   Okay.  And you also assert or testify that you

22       did not know that the NRC staff would decide that it

23       would review the LWA concurrently with a COL; is that

24       correct?

25            A.   It is correct.  We absolutely had no previous

FLORIDA PUBLIC SERVICE COMMISSION

1230

1       insight or knowledge that the NRC would not grant an LWA

2       in advance of the COL prior to January 23rd, 2009.

3            Q.   Okay.  And specifically your testimony is that

4       your first indication that the NRC staff would do so,

5       which is place the review of the LWA inside of the COL

6       review, was on January 23rd, 2009, and not a, not a

7       minute sooner?

8            A.   That is correct.

9            Q.   Okay.  And by saying this, are you also

10       testifying that you could not reasonably have known that

11       this would be the outcome, this meaning the decision you

12       got from the NRC staff on January 23rd?

13            A.   Yes.  I am testifying that I would not

14       reasonably have known that outcome based on the ongoing

15       interactions we had with the NRC and the actions that

16       they were taking as late as December 4th of 2009 (sic.)

17       where our project manager, his name was Brian Anderson,

18       made public statements about the length it takes for the

19       entire review process for an LWA.

20            Q.   Okay.  Now I'm trying to limit my questioning

21       to --

22                 COMMISSIONER EDGAR:  Mr. Rehwinkel, just a

23       moment.

24                 MR. REHWINKEL:  Okay.

25                 COMMISSIONER EDGAR:  Commissioner.

FLORIDA PUBLIC SERVICE COMMISSION

1231

1                 COMMISSIONER SKOP:  Just potentially on the

2       record, I believe the date you said was December 2009.

3       I don't think we've got there yet.  I thought that you

4       might have --

5                 THE WITNESS:  Thank you, Commissioner.

6       December 4th, 2008.

7       BY MR. REHWINKEL:

8            Q.   Now just to be clear, and I'm limiting my

9       cross-examination to your direct testimony --

10            A.   I understand.

11            Q.   -- and I'm not asking you to not, to act like

12       you don't know certain things.  But what you just

13       mentioned, December 4th, 2008, that appears nowhere in

14       your direct testimony; is that correct?

15            A.   That is correct.

16            Q.   Okay.  And you did not mention that date in

17       your deposition that I took on December -- on July 2nd,

18       2008, did you?

19            A.   That is correct.

20            Q.   Okay.  And that deposition lasted about eight

21       hours; correct?

22            A.   About nine.

23            Q.   Nine?  Okay.  That is not a precursor to how

24       long this is going to take, hopefully.

25                 (Laughter.)

FLORIDA PUBLIC SERVICE COMMISSION

1232

1                 You also contend in your testimony here that

2       you reasonably believed that the NRC staff could review

3       the application for the LWA because you put it together

4       in 18 months, and that they should be able to look at it

5       and make a determination before -- in what time period?

6            A.   The time period would be approximately 30

7       months.  And let me amplify what you just said.

8                 What we thought was based on the announcement

9       of the site in December 2006 through the period that we

10       submitted our application in July 2008, about 18 months,

11       we investigated the site, we drilled over 108 borings

12       and selected soil samples and core samples.  We did

13       geotechnical analysis of that site, foundation design,

14       we completed all that work in 18 months and handed over

15       that analysis to the NRC staff as part of our submittal.

16       So we reasonably expected for the NRC to be able to

17       complete their LWA review in the, in the time frame we

18       requested in the letter that we submitted July of 2008.

19            Q.   Okay.  And when you say you did the analysis

20       over that 18-month period, it's not your testimony that

21       you handed over every bit of analysis that you did for

22       site characterization, et cetera, to the NRC staff; is

23       that right?

24            A.   No, that's not what I meant.  As you know, the

25       application itself is a summary of analysis.  And so

FLORIDA PUBLIC SERVICE COMMISSION

1233

1       what we do is we make available through requests for

2       additional informations, or RAIs, analysis that they

3       request on demand, the basis for some summary statement

4       or some analysis summary that shows up in the

5       application itself.

6            Q.   Okay.

7            A.   But the point is that work was done and

8       available to support that application going in July

9       2008.

10            Q.   I understand.  Thank you.

11                 You've also testified that you believed that

12       the fact that dewatering and excavation measures have

13       been done elsewhere in Florida on a similar scale under

14       similar conditions supported your view that the timeline

15       you just described, a 30-month review, could be

16       accomplished; is that correct?

17            A.   That was pertinent, yes.  That is correct.

18       That is pertinent information to this decision-making

19       because there are lots of examples of this being done.

20       And as you'll see in the rebuttal testimony, I have an

21       exhibit that lists some of those for convenience.

22            Q.   Now just for the record, none of those sites

23       involved nuclear facilities or where there was public

24       safety issues being reviewed in a nuclear power plant

25       environment; is that correct?

FLORIDA PUBLIC SERVICE COMMISSION

1234

1            A.   Your statement is not correct because public

2       safety is not a nuclear issue.  So, for example, the

3       work done at the Capitol building when they did the

4       expansion for the visitor center, which used dewatering

5       techniques of diaphragm walls, that's certainly public

6       safety.  But in the context of a nuclear application and

7       protection of the public health and safety by nuclear

8       reasons, I'm not aware of a site that had a dewatering

9       while grouting configuration like this.

10            Q.   Thank you.  Is it also your testimony or can I

11       glean from your testimony that the perception of the

12       ability of the NRC staff to meet this 30-month time

13       frame was PEF's management's collective belief as well?

14            A.   Ask your question again.

15            Q.   Okay.  Yeah.  Let me ask it, let me ask it a

16       little bit different way.

17                 All of the things that we've reviewed that

18       influence your belief that the NRC staff could meet this

19       30-month time frame, was that the unanimous collective

20       belief of PEF's management?

21            A.   I don't know if the right phrase is

22       "unanimous."

23                 The way this process works is we, my

24       organization is involved in industry groups and

25       licensing interactions with the NRC.  And we provide

FLORIDA PUBLIC SERVICE COMMISSION

1235

1       recommendations and information to our senior

2       management, and they depend on us for that information.

3       So to say it's unanimous is not the right

4       characterization of how this works.  It's an informed

5       process where we make recommendations.

6            Q.   It is true, is it not, that no one in

7       management challenged the assessment that the 30-month

8       schedule could be met?

9            A.   I'm not sure that the word "challenged" is the

10       correct word.  We discussed it, we had questions and

11       back and forth dialogue.  And based on the

12       reasonableness of what we had heard from industry

13       interactions and NRC statements, we believed that was

14       representative of what would actually happen with an LWA

15       execution.

16            Q.   When you say we had back and forth dialogue,

17       are you talking about within your organization or above

18       with the people that you reported to?

19            A.   When, when I talk about back and forth

20       dialogue, I'm talking about as I interfaced with my

21       senior management and the leadership of our company.  As

22       we talk about subjects, there's a dialogue back and

23       forth on various things and we discuss those.

24            Q.   Do you have with you, and I'm not going to ask

25       you about your rebuttal testimony, but do you have with

FLORIDA PUBLIC SERVICE COMMISSION

1236

1       you your rebuttal testimony and Exhibit GM-7?

2            A.   I do.

3            Q.   Do I have it?  I just had it.

4                 Can I ask you to turn -- well, first of all,

5       are you familiar with what GM-7 is?

6            A.   Yes, I am.

7            Q.   Is this a document that you were involved in

8       the preparation of?

9            A.   Yes, it is.

10            Q.   Okay.  Can I ask you to turn to Page 4 of 6?

11            A.   I'm there.

12            Q.   Okay.  Now this is, this is an interrogatory

13       that, that purports, the answer purports to describe all

14       discussions that the company had with the NRC prior to

15       and following the submission of the LWA.

16            A.   That is correct.

17            Q.   Okay.  Now were you present at, at any of

18       these, any meetings that are described here?

19            A.   Yes.  I was present at some of those meetings,

20       but not all of them.  And I was present on some of the

21       calls that are in here.

22            Q.   Can you tell me which ones?

23            A.   So, for an example, I would have been at the

24       September 12th call, I believe I was there.  Certainly

25       the January 23rd call I was on.  There was management

FLORIDA PUBLIC SERVICE COMMISSION

1237

1       meetings in here that I was involved in.  So different

2       ones.  For example, I was at the February 20th meeting

3       as an example.  So not all, but some of those meetings I

4       was present at.  And certainly the one that was the most

5       significant was the January 23rd, 2009.  I was there.

6            Q.   You mean you were on the phone?

7            A.   I was on the phone.  Correct.

8            Q.   Okay.  But you filed your LWA on

9       September 12th; is that correct?  You're -- let me, let

10       me step back.

11                 You supplemented your LWA on September 12th,

12       2008; is that correct?

13            A.   Correct.  We filed as part of our COLA

14       application an LWA request in July 2008, and we then

15       updated that request in a September 12th submittal.  And

16       we had a call September 5th with the NRC prior to that

17       submittal.

18            Q.   The September 12th supplement included in the

19       LWA the dewatering and permeation grouting aspects of

20       what became your LWA request; is that correct?

21            A.   The -- it is correct to say that those two

22       were added as part of the LWA scope, and then there was

23       scope that was removed from the original LWA request

24       also.

25            Q.   The dewatering, the, the installation of the

FLORIDA PUBLIC SERVICE COMMISSION

1238

1       wall and the, the permeation grouting to prepare a

2       bottom for the excavated pit were the crucial parts of

3       the LWA; is that correct?

4            A.   It's not correct the way you phrased it.  The

5       dewatering is not an NRC LWA activity.  The installation

6       of the diaphragm wall and the installation of the

7       permeation grouting were added per the NRC's request and

8       were part of the scope.  However, dewatering and

9       excavation is not part of the scope of LWA.

10            Q.   Okay.  So what I should have asked you is were

11       the diaphragm wall and the permeation grouting aspects

12       of the LWA the crucial aspects of the LWA in order to

13       meet your, your 2016 COD?

14            A.   They were important, but I wouldn't use the

15       word "crucial" because what we did when this decision

16       was made to revise and update the September 12th, 2008,

17       letter to the NRC reducing scope of the LWA and adding

18       scope to it, we then went back to our preconstruction

19       logic schedule and worked on how we could take the time

20       back out associated with this change and we were able to

21       overlap certain activities and still achieve an

22       in-service date of mid 2016 by overlapping some of the

23       work for the dewatering wall installation and the grout

24       installation.

25            Q.   Okay.  But once the permeation, permeation

FLORIDA PUBLIC SERVICE COMMISSION

1239

1       grouting and the diaphragm wall were added to the LWA,

2       you could not do those activities without authorization

3       in the, in the LWA; is that correct?

4            A.   That is correct.  Without the LWA being

5       subsequently changed to remove those, we were not

6       allowed to install those two items without prior LWA

7       issuance.

8            Q.   Okay.  So once those items were put inside of

9       the LWA and dependent upon NRC authorization to proceed,

10       they became crucial to achieve in an LWA in order to

11       meet your 2016 COD; is that correct?

12            A.   Again, your word "crucial," it is -- I

13       wouldn't characterize it as any more crucial than the

14       placement of the engineered backfill, which is part of

15       that same scope of the LWA.  It became an important

16       component of the LWA scope that had to be considered in

17       the schedule development.

18            Q.   In the meetings that are described in GM-7

19       after September 12, 2008, that would be the

20       October 1 call; is that correct?

21            A.   Yes.

22            Q.   October 6th is just a letter -- not just, but

23       it is a letter.  It's not a meeting.

24            A.   It's not a meeting.

25            Q.   Are those the only two meetings post

FLORIDA PUBLIC SERVICE COMMISSION

1240

1       September 12th, 2008, that deal with communications

2       about the LWA schedule?

3            A.   From our --

4            Q.   Between the company and the NRC?

5            A.   Right.  From our recollection, as we created

6       this interrogatory response, we have an ongoing dialogue

7       with the NRC routinely, but these are the dates that we

8       remember discussions concerning LWA and that's why these

9       were added on to this schedule.  But there were

10       discussions in between these or unrelated topics on

11       these same dates that could have occurred because we

12       have a project manager who we interface with routinely.

13            Q.   Okay.  Can you tell me the dates of those

14       additional --

15            A.   I cannot, sir, because they're so frequent

16       that it's -- there are calls routinely made, so I cannot

17       tell, tell you those.

18            Q.   Okay.  And you mentioned a December 4th

19       statement by the NRC.  You didn't include this on this,

20       this interrogatory response for what reason?

21            A.   We did not include it because we had not

22       identified that in his transcript at the time we created

23       this response.  We certainly would have otherwise.  And

24       I would tell you the reason that's the case is we had

25       many interactions with the NRC all throughout 2008.  And

FLORIDA PUBLIC SERVICE COMMISSION

1241

1       when the NRC project manager made that statement that

2       the entire LWA review process could be completed in a

3       ballpark 24 months, we didn't consider it a remarkable

4       statement.  It's what we would expect him to say, so we

5       didn't remember him saying it in this public forum in

6       response to a public question.  So as we created this

7       interrogatory response, it did not, you know, we didn't

8       remember that as a key event, and it was discovered as

9       part of our preparation of our rebuttal testimony in a

10       transcript.

11            Q.   Is it, is it true that Mr. Thompson told you

12       about it?

13            A.   It is true that Mr. Thompson found it in the

14       transcript --

15            Q.   Okay.

16            A.   -- of the public meeting.

17            Q.   Mr. Thompson was not advising you at any point

18       in time about the filing of the LWA, was he?

19            A.   No.

20            Q.   Okay.  Isn't it true that after you filed the

21       LWA or nearing time of the filing of the LWA

22       supplemental on September 12th that company officials

23       met with senior NRC officials and told them that they

24       were asking for an aggressive schedule for the COL

25       including the LWA, the environmental impact statement

FLORIDA PUBLIC SERVICE COMMISSION

1242

1       and the safety report?

2            A.   Yes.  It is correct to say that senior, that

3       senior management in our company met with NRC senior

4       officials in the September time frame.

5            Q.   Is it also correct that they said that the,

6       that the schedule was aggressive?

7            A.   At the time -- I was present at that meeting.

8       I don't remember the exact language, but I think they

9       probably did acknowledge that we were asking for an

10       aggressive schedule and they were reviewing it.

11            Q.   And by aggressive, I mean it was aggressive

12       with respect to the typical milestones that you would

13       expect to be approved by the NRC in their review of a,

14       of a COLA and LWA?

15            A.   No.  Specifically I would consider it to be

16       aggressive with respect to the EIS schedule.  The LWA

17       approval requires an EIS or a partial EIS.  And in our

18       company's decision-making, we chose to have a full EIS

19       available in support of the LWA decision.  So we knew

20       that the EIS constrained the LWA, so the aggressive date

21       we were particularly asking for related to an EIS.  That

22       would typically take approximately 24 months, and we

23       were asking for something less than that so the EIS

24       would be available to support an LWA decision.

25            Q.   Would you agree that the company -- wouldn't

FLORIDA PUBLIC SERVICE COMMISSION

1243

1       you agree that the company recognized that they were

2       requesting an aggressive schedule not for just one of

3       the milestones but generally for the review schedule?

4            A.   No, I would not agree with that.

5            Q.   You wouldn't agree with that?

6            A.   No.

7            Q.   You wouldn't agree that you were asking for

8       delivery of each of the LWA, the environmental impact

9       statement and the COLA at aggressive time points in what

10       you thought would be a typical consideration timeline?

11            A.   No, and let me explain why.  Again, we

12       announced our site December 2006.  We developed a full

13       application and submitted it July 2008, in about 18

14       months.  And so the overall time frame for the COL we

15       requested and for those timeframes for the LWA and EIS

16       we thought were reasonable considering the amount of

17       time it took us to conclude our activities and deliver

18       that analysis, a summary analysis to them.

19            Q.   Okay.  Did the NRC staff think your schedule

20       was aggressive?

21            A.   Are you asking me did they say that?

22            Q.   Yes.

23            A.   I don't recall if they said those specific

24       words.  I think they probably did with regard to the EIS

25       because it's typically 24 months.

FLORIDA PUBLIC SERVICE COMMISSION

1244

1            Q.   So would you agree with the statement that the

2       ultimate COLA issue that you were asking for was a, was

3       a relatively aggressive set of milestones?

4            A.   No, I wouldn't agree.  With the overall COL

5       date?

6            Q.   Yes.

7            A.   No, I would not agree with that.  Again, put

8       in perspective, we developed our application fully in 18

9       months.  And from the period of July of 2008 through

10       what we were asking for, which was, what, December of

11       2011 or January of 2012, that's almost 42 months.  And

12       so we did not think that was unreasonable.

13                 MR. REHWINKEL:  Okay.  Commissioner, Madam

14       Chairman, I have a line of questioning that I am about

15       to go into that involves use of cross-examination

16       exhibits.  And it's almost 1:00.  Would this be a good

17       time?

18                 COMMISSIONER EDGAR:  Yes, sir.  I think that

19       you and I are thinking along the same line.  I was just

20       going to ask you if this might be an appropriate

21       breaking spot.

22                 MR. REHWINKEL:  Yes.

23                 COMMISSIONER EDGAR:  So if -- you know, it may

24       be helpful on the lunch break to go ahead and pass out

25       documents so that we have them all before us and we can

FLORIDA PUBLIC SERVICE COMMISSION

1245

1       go through and mark them at the beginning.  But it is

2       your pleasure, your, your cross.

3                 MR. REHWINKEL:  I think what I would like to

4       do, since they are, 90 percent of them are red,

5       confidential --

6                 COMMISSIONER EDGAR:  Oh, I did not, I did not

7       realize that.  Okay.

8                 MR. REHWINKEL:  I will, I will do that though

9       right before we, when we get the one-minute warning or

10       whatever, we can do it then so we can make sure that

11       everything is safeguarded correctly.

12                 COMMISSIONER EDGAR:  Okay.  Thank you.  We

13       will, again, of course, work with you and all the

14       parties to do that.

15                 All right.  We are going on lunch break until

16       2:15.  We are on recess.

17                 (Recess taken.)

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1246

1       STATE OF FLORIDA    )

:         CERTIFICATE OF REPORTER

2       COUNTY OF LEON      )

3

4                 I, LINDA BOLES, RPR, CRR, Official Commission

Reporter, do hereby certify that the foregoing

5       proceeding was heard at the time and place herein

stated.

6

IT IS FURTHER CERTIFIED that I

7       stenographically reported the said proceedings; that the

same has been transcribed under my direct supervision;

8       and that this transcript constitutes a true

transcription of my notes of said proceedings.

9

I FURTHER CERTIFY that I am not a relative,

10       employee, attorney or counsel of any of the parties, nor

am I a relative or employee of any of the parties'

11       attorneys or counsel connected with the action, nor am I

financially interested in the action.

12

DATED THIS _____ day of _____________________,

13       2009.

14

15                  ________________________________

LINDA BOLES, RPR, CRR

16                 FPSC Official Commission Reporter

(850) 413-6734

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION