1966

1                             BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

DOCKET NO. 090009-EI

3

4       In the Matter of:

5       NUCLEAR COST RECOVERY CLAUSE.

______________________________/

6

7

8                              VOLUME 12

9                       Pages 1966 through 2110

10              ELECTRONIC VERSIONS OF THIS TRANSCRIPT ARE

A CONVENIENCE COPY ONLY AND ARE NOT

11               THE OFFICIAL TRANSCRIPT OF THE HEARING.

THE .PDF VERSION INCLUDES PREFILED TESTIMONY.

12

PROCEEDINGS:          HEARING

13

COMMISSIONERS

14       PARTICIPATING:        CHAIRMAN MATTHEW M. CARTER, II

COMMISSIONER LISA POLAK EDGAR

15                             COMMISSIONER KATRINA J. McMURRIAN

COMMISSIONER NANCY ARGENZIANO

16                             COMMISSIONER NATHAN A. SKOP

17

18       DATE:                 Thursday, September 10, 2009

19       TIME:                 Commenced at 5:00 p.m.

Concluded at 7:00 p.m.

20

PLACE:                Betty Easley Conference Center

21                             Room 148

4075 Esplanade Way

22                             Tallahassee, Florida

23       REPORTED BY:          CLARA C. ROTRUCK

Court Reporter

24                             (850) 224-0722

25       PARTICIPATING:    (As heretofore noted.)

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1967

1                              I N D E X

2

3                              WITNESSES

NAME:                                       PAGE NO.

4

HUGH L. THOMPSON, JR.

5

Cross Examination by Mr. Rehwinkel         1969

6          Cross Examination by Mr. Brew              1989

Redirect Examination by Mr. Roach          1995

7

GARY DOUGHTY

8

Direct Examination by Mr. Roach            1999

9          Prefiled Rebuttal Testimony inserted       2001

Cross Examination by Mr. Rehwinkel         2017

10          Cross Examination by Mr. Moyle             2031

11       JEFFREY J. LYASH

12          Direct Examination by Mr. Walls            2033

Prefiled Rebuttal Testimony inserted       2035

13          Cross Examination by Mr. Brew              2078

Cross Examination by Mr. Davis             2106

14

15

16

17

18

19

20

21

22

23

24

25

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1968

1                              EXHIBITS

2       NUMBER:                                    ID.    ADMTD.

3       124 through 127                                    1998

155  EPA Analysis of HR 2454, June 2009   2096

4

5

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1969

1                         P R O C E E D I N G S

2                 (Transcript follows in sequence from

3       Volume 11.)

4                          CROSS EXAMINATION

5       BY MR. REHWINKEL:

6            Q    Mr. Thompson, can you show me in these two

7       documents where the rule is that you're referring to?

8            A    Where the rule is that I'm referring to?

9            Q    Or the rule -- the parts of the rule that

10       you've read related to the LWA.

11            A    The first parts I read dealt with the

12       background, which is --

13            Q    What is the citation?

14            A    My citation is 57416, Federal Register Notice,

15       Volume 17, on the background document.

16            Q    So do you know the CFR section?

17            A    That was the regulation portions I looked at.

18                 CHAIRMAN CARTER:  I think we're two ships

19       passing in the night.  Would you ask your question

20       again, Mr. Rehwinkel?

21                 MR. REHWINKEL:  I'm asking if he can give me a

22       CFR citation to the parts of the rule that he read.

23                 THE WITNESS:  10 CFR Part 52.

24       BY MR. REHWINKEL:

25            Q    Okay.  The whole thing?

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1970

1            A    Well, I read those portions of it sufficient

2       to understand the key elements that were identified for

3       the LWA activities that would be permitted and those

4       activities -- what would be required for a licensee to

5       be able to do, and then with the changes that resulted

6       between the rulemaking activities that they originally

7       started out with an LWA and what they came out with

8       eventually.

9            Q    So is it your testimony that you can't tell me

10       where in 10 CFR Part 52, which provisions within there

11       that you reviewed?

12            A    You mean these three key provisions that I

13       identified in my testimony?

14            Q    Yes, sir.

15            A    At this moment, I can't define -- there's

16       about 40 pages in there, I would have to review those in

17       detail, but there's a number of comment sections in the

18       Federal Register Notice.

19                 MR. ROACH:  Mr. Chairman, this is a pretty

20       thick stack of papers.  Do you want to give him a few

21       minutes to take a look at it?

22                 MR. REHWINKEL:  I'm in no hurry.  I don't mean

23       that in a flippant way, Mr. Chairman.  I want him to be

24       able to answer the question.  If he can't give me a

25       citation to the rule, that could be his answer, I don't

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1971

1       know.  I think it's a fair question.  He said he

2       reviewed the portions of the rule that he needed to

3       provide this part of his testimony, and I think I'm

4       entitled to cross-examine him on that.

5                 CHAIRMAN CARTER:  Mr. Thompson, do you need a

6       moment?

7                 THE WITNESS:  Yes, I need a moment.

8                 CHAIRMAN CARTER:  You got it.

9                 MR. ROACH:  If counsel has a specific section

10       he wants to ask about, it might be helpful for the

11       process to point him to it and he can say whether he

12       read it or not.

13                 MR. REHWINKEL:  I can't do that, because I

14       don't know what provisions he's read.

15                 CHAIRMAN CARTER:  Okay, hold on.  Mr. Thompson

16       is going to review the document and he's going to answer

17       the question, based upon what he looked at.  So let's

18       don't get frisky.

19                 THE WITNESS:  What I did, I read the rule in

20       some sense, but what I went through was the Commission

21       papers and the background associated with those to find

22       out what the LWA allowed and what it didn't allow.  I

23       did not have to go through and read every detailed

24       section in the comments and the public comments on the

25       rule.  So that's what my position was based on

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1972

1       primarily, not trying to re-read the regulation, but

2       reading the Commission statements and what they had in

3       place with respect to what an LWA process was supposed

4       to permit a licensee to have and what was required.

5                 For example, an environmental impact statement

6       was required, and they had to -- would not be required

7       to have an LWA -- you know, evacuation -- you know, for

8       evacuating the -- not evacuating, but excavating the

9       site activities.  So it differentiated what the two

10       things were related from.

11                 CHAIRMAN CARTER:  Okay, you may proceed.  Go

12       ahead, Mr. Rehwinkel.

13                 MR. REHWINKEL:  Thank you.  We may come back

14       to this, but let me move on.

15                 CHAIRMAN CARTER:  I think he answered your

16       question, he said he looked at all of the comments and

17       all, so he won't be able to point to it, so let's move

18       on.

19                 MR. REHWINKEL:  Yes, exactly.

20       BY MR. REHWINKEL:

21            Q    Can I ask you to turn, Mr. Thompson, to page

22       20, the bottom of page 20 and the top of page 21?

23            A    Okay.

24            Q    Okay.  You state at the top -- there is a

25       question at the bottom of page 20 and an answer at the

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1973

1       top of page 21.  The answer says, "Yes, the NRC has

2       raised the acceptance review standard in 2007 at the

3       Commission's direction."  Do you see that?

4            A    Right.

5            Q    Is that written down somewhere?

6            A    That's new reg -- NRO Reg. 100, "Acceptance

7       Review Process for Design Certification and Combined

8       License Applications," dated September 26, 2007.

9            Q    So that's what you cite on the next page, page

10       22, the NRO Reg. 100?

11            A    Correct.

12            Q    Okay.  And on page 22, line 7, you ask the

13       question, "What was the intent behind the NRC's change

14       in the acceptance review standard?"

15            A    Correct.

16            Q    And you testify as to an intent, and where is

17       that intent written down?  Or is that based on an

18       analysis that you have done?

19            A    Well, that intent is written down.  Also, I

20       was present with the NRC EDO, Luis Reyes and Bill

21       Borchardt, in their office.  I was working with

22       Mitsubishi Heavy Industries, and we were discussing with

23       them what the plans would be for getting a DCD review,

24       and that's when they basically told me what the

25       Commission was doing.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1974

1                 There is a -- let me see if I have a reference

2       here on it.

3                 There is a staff requirements memo, I hate to

4       give you all this gobbledy-gook, but it's going to come

5       out, it's an SRM COM DEK 07-0001/COM JSM 07-001, "Report

6       of the Combined License Review Task Force," June 22,

7       2007.

8                 Let me explain what that document -- that

9       document was -- the chairman -- Chairman Klein and

10       Commissioner Merrifield had put together a task force to

11       look at how to improve the NRC staff licensing of the

12       new applications that were coming in, and lots of them

13       were coming in, so what they decided that they needed to

14       do was to increase the technical review that's done

15       before docketing, such that the docketing not only has a

16       completeness, but it meets the technical requirements

17       associated for having confidence that the application

18       meets NRC requirements.

19                 Originally the project managers themselves

20       just did the completeness review, and the project

21       manager is not the subject matter expert.  The new

22       review process they put in place and put it in and gave

23       the staff the 60 days rather than the 30 days, said that

24       they would also give pieces of -- well, the entire

25       application would be reviewed by the technical staff who

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1975

1       would have to do the technical reviews later on.  That

2       process was put in place informally in the early 2007s,

3       and then formally I think it was put in place in the

4       first part of 2008.  But it was in place during this

5       period.

6            Q    So my question was, is the intent that you

7       describe here written down?  You're saying it's written

8       down in the document that you gave a citation to?

9            A    That's correct.

10            Q    Is that an official NRC document?

11            A    That it is.

12            Q    I ask you to turn to page 25 of your

13       testimony.

14            A    Okay.

15            Q    You testify here about the December 4, 2008 --

16            A    Correct.

17            Q    -- meeting and the statement by Brian

18       Anderson, is that correct?

19            A    That's correct.

20            Q    Okay.  Now, were you at that meeting?

21            A    No, I was not.

22            Q    Were you advising or working for Progress

23       Energy during 2008?

24            A    No, I was not.

25            Q    Not?  Okay.  Are you the one that discovered

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1976

1       this transcript and advised all the witnesses here today

2       that have included it in their testimony on rebuttal?

3            A    Patty Laramore, who was my licensing

4       assistant, found this in my request for her to review

5       for publicly available documents.  What I was wanting to

6       do was look at what the document available for the

7       managers who were making decisions up until the December

8       time frame, what did they know and what would they

9       reasonably know.  This was one of the documents that

10       was -- we identified.

11            Q    Have you included the transcript as an exhibit

12       to your testimony?

13            A    Yes, I did.  I included portions of the

14       transcript, it's not the whole transcript.  I do have it

15       if you want to read the whole transcript.

16            Q    Okay.  Can you tell me who asked the question

17       that you say that Mr. Anderson answered?

18            A    Just a moment.  What was it, hold it?

19            Q    I think Mr. Miller said stand down.

20            A    Oh, stand down?  Stand by.

21                 The individual who asked the question is

22       Robert Fetrow, F-e-t-r-o-w, who lives in Inglis,

23       Florida.

24            Q    Does he work for Progress Energy?

25            A    I don't believe so.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1977

1            Q    Based on your experience with NRC staff, why

2       would they have answered his question and not Progress

3       Energy's question about the time frame?

4            A    It was an NRC meeting, and NRC meetings are

5       intended to explain to the public what their

6       responsibilities are.  They are requesting public input

7       as to what areas of the environmental review they would

8       like to do, and they are also wanting to be able to

9       establish a presence that they are going to do their job

10       right.

11                 NRC has a health and safety job, and they owe

12       it to the citizens of Florida, they owe it to the

13       citizens of any part of the country that has a license

14       application to not only explain the process, but give

15       the individuals there who are concerned citizens answers

16       and an opportunity to raise questions.  And part of this

17       was to establish the scoping meeting for the

18       environmental impact statement.  But in addition to

19       that, they wanted to explain the NRC process and they

20       also explained the opportunities to participate in a

21       hearing and what the hearing process was that NRC was

22       going to have.  So if they really wanted to know the

23       full framework of opportunities to participate in the

24       NRC licensing process, this was the meeting that put

25       that in place.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1978

1            Q    On page 26 of your rebuttal testimony, can you

2       look at lines 12 through 14?

3            A    Yes.

4            Q    Do you see that statement there?  It says

5       there, "My experience with the NRC is that it strives to

6       be open and to provide applicants and the public with

7       honest answers to questions."  Do you see that?

8            A    Yes.

9            Q    Are you stating there that Mr. Anderson gave a

10       dishonest answer?

11            A    No.  No, just the opposite, he gave an honest

12       one.  I'm saying that NRC has responsibilities for

13       openness, integrity, they have opened it for clarity,

14       for reliability, but one of -- and independence, and all

15       I was saying, one of the things a project manager wants

16       to do is not lose credibility.  So his activities -- and

17       he is responsible for interfacing with the public, he is

18       responsible for interfacing with the technical reviewers

19       and the NRC staff and he is responsible for interfacing

20       with the licensee.  So all of these three broad areas

21       are his responsibilities, and he needs to be not only

22       independent, but he needs to be forthright and frank and

23       honest with all of them.  And in this case, I'm saying

24       he was.

25            Q    Was this an accurate answer?

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1979

1            A    Yes.

2            Q    How was it accurate?

3            A    It gave his opinion.  It gave his opinion at

4       the time, as he stated.

5            Q    How do you know it was his opinion at the

6       time?  Did you ask him?

7            A    It was a transcribed meeting.  It was a formal

8       meeting that NRC has part of their process.  This was

9       not some back-door comment when somebody secretly made a

10       tape-recording of somebody's comment.  This was a formal

11       part of NRC's meeting.  I have no question of the

12       integrity of Mr. Anderson.

13            Q    My question was, did you ask him if this was

14       accurate?

15            A    Well, I gave you my broader answer.

16            Q    I think you're obligated to say yes or no.

17            A    Would you ask the question one more time?

18            Q    Did you ask Mr. Anderson --

19            A    No.

20            Q    Okay.  So he said two years on December 4,

21       2008, and what was the review schedule for the LWA a

22       little over a month later?

23            A    They didn't have a review schedule for the

24       LWA.  They made it the same part as the COLA review

25       schedule.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1980

1            Q    So are they going to review the LWA?

2            A    I'm sorry?

3            Q    Did they decide to review the LWA on -- did

4       they announce a decision about reviewing the LWA on

5       January 23, 2009?

6            A    Yeah, my reading of the information, and I was

7       not part of that phone call on January 23rd, though.

8       The notes that I've read from the briefing material was

9       that they made a decision at that time.  They did not

10       have adequate resources to conduct the LWA review at an

11       earlier time frame than the COLA review.  I found that

12       very surprising, but -- that they put those reviews

13       together.

14            Q    You found it surprising to read about it?

15            A    No, I found it surprising they made the

16       decision to do it separate and combined.

17            Q    When were you hired by Progress Energy to work

18       on this case?

19            A    The early part of August.

20            Q    So that's when you were surprised?

21            A    That's when I surprised.  I didn't -- I had

22       not been working for them.

23            Q    So Mr. Anderson gave an answer that it would

24       take -- they were going to look at -- according to your

25       reading of his transcript, that it was going to take --

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1981

1       the NRC was going to take two years to do their entire

2       review process through the limited work authorization?

3            A    Correct.

4            Q    Did that turn out to be the NRC's decision?

5            A    Not for the -- not for the Levy.  It was

6       consistent with what they did on Vogtle, but not for the

7       Levy one.

8            Q    But they weren't talking about Vogtle down

9       there in Crystal River on December 4, 2008, were they?

10            A    No, but he was talking about a ballpark, and

11       the ballpark was what they were planning.  The planning

12       that they were talking about primarily is the

13       environmental review schedule, and that's about 24

14       months and that's consistent with published NRC guidance

15       and public documents.

16            Q    Can you show me in this transcript where an

17       environmental impact statement is mentioned?

18            A    In the transcript?

19            Q    That you cite in your testimony.

20            A    I didn't cite that in my testimony, but if you

21       want me to go back and go through the transcript, I'm

22       glad --

23            Q    I'm just asking you about this portion that

24       you quote here, that you're offering as testimony to the

25       Public Service Commission.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1982

1            A    No, I was giving you my experience and

2       knowledge of what NRC normally does on a -- talking

3       about the environmental impact statement.

4            Q    But Mr. Anderson's quote that you included in

5       your testimony specifically references the limited work

6       authorization, does it not?

7            A    No, it doesn't.  It includes the entire

8       process, and the entire process includes the

9       environmental impact statement associated with it.

10       That's what the LWA rule requires.

11            Q    Let me ask you to look on page 26, and that

12       first sentence on line 1.  Can you show me where in that

13       sentence it references the environmental impact

14       statement?

15            A    It doesn't have that in the first sentence.

16       In the second sentence, it has "our entire review

17       process."  I highlighted "entire," emphasis added.

18            Q    I only see, on lines 1 through 4, one

19       sentence.  Am I mistaken?

20            A    I don't know.  What I have, it says -- my

21       quote is, "Just to give you a ballpark time frame, we

22       expect that somewhere on the order of two years will be

23       required to complete our entire" -- I have emphasis

24       added -- "review process for the limited work

25       authorization."

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1983

1            Q    Okay.  That's one sentence, right?

2            A    Correct.

3            Q    That refers to the limited work authorization,

4       doesn't it?

5            A    No, it says, "our entire review process."

6            Q    "For the limited work authorization," correct?

7            A    Correct.  The NEPA process requires, if you're

8       making a major decision, you have to have an

9       environmental impact statement associated with it.

10       That's what the LWA rule, as I articulated earlier,

11       requires.

12            Q    How many LWAs had the NRC reviewed at the time

13       Mr. Anderson made this statement under the new rule?

14            A    I don't believe they had completed a review of

15       any.

16            Q    So on page 26, lines 14 through 18, you state,

17       "If they had known of any serious LWA review delays, it

18       is my opinion that they would have simply said that

19       there are some issues with this site that will take

20       longer than our usual schedule, and we cannot provide

21       any ballpark estimate at this time."  Do you see that?

22            A    Yes.

23            Q    Now, my question I asked about -- I emphasized

24       the word "usual."  Did you hear that in my tone?

25            A    No.  Do it for me one more time.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1984

1            Q    Never mind.

2                 Where was this usual schedule, where did that

3       come from, if this rule had really not been used before?

4            A    I'm really sorry, I'm a little hard of

5       hearing.

6            Q    I apologize.

7            A    But if you will point me to what you have

8       questions about in my testimony, I will hopefully be

9       able to respond to you.

10            Q    Okay.  On line 17, you reference a usual

11       schedule.  Do you see that?

12            A    Yes.

13            Q    Okay.  Now, where did this usual schedule come

14       from, this being the first LWA associated with a COLA?

15            A    No, it's the usual environmental impact

16       statement review schedule.

17            Q    On the next page, page 27 of your testimony --

18            A    Yes.

19            Q    -- on lines 4 through 7, you reference

20       information available to PEF when it signed the EPC

21       contract.  How do you know what information was

22       available to PEF at the time they signed the EPC

23       contract?

24            A    This was the information that was publicly

25       available that I found.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1985

1            Q    Okay.  Not stuff that they told you?

2            A    I'm sorry?

3            Q    Not information that they told you about?

4            A    No, no, no.  This was information -- there was

5       one, I can't remember whether we found it separately or

6       not, was the notes of the telephone call of -- of the

7       January 23rd NRC phone call, but what I was looking at

8       was the information that was publicly available, readily

9       available at the time that the EPC contract was signed

10       that I was able to identify.

11            Q    Now, did you see any evidence that Progress

12       Energy Florida had considered this December 4th

13       statement by Mr. Anderson in any of its decision-making

14       related to the EPC contract?

15            A    I didn't look at any of their decision-making

16       process.  I looked at what was publicly available and

17       what they knew or should have known, so that was the

18       standard I used when looking at it, and certainly they

19       were present at the meeting.

20            Q    So you don't have any knowledge about whether

21       they relied on the statements made by Mr. Anderson on

22       December 4, 2008, with respect to their decision-making,

23       do you?

24            A    No, I don't, I just know it was information

25       that they knew or should have known.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1986

1            Q    So it's really a matter of what they could

2       have known rather than what they should have known?

3            A    I think it's what they knew.

4            Q    But you don't know whether they knew it, do

5       you?

6            A    Well, they were there at the meeting.  I mean,

7       I --

8            Q    You don't know whether they relied on it, do

9       you?

10            A    It's information that was available for them

11       to rely on if they wanted to.  I don't know.

12            Q    On page 33 of your testimony --

13            A    Okay, 33?

14            Q    Yes, lines 6 through 15.

15            A    Okay.

16            Q    Within that Q&A, you reference on lines 10 and

17       11 discussions with NRC power uprate project managers,

18       do you see that?

19            A    Yes.

20            Q    Can you tell me who those people were that you

21       talked to?

22            A    John Stang and Tom Alexson.

23            Q    Okay.  On lines 14 and 15, you say, "There

24       have been no cases where a power level approved by the

25       NRC was smaller than that requested by the licensee."

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1987

1       Do you see that?

2            A    Yes.

3            Q    Have any Babcock & Wilcox plants been the

4       subject of an LAR for an uprate to the magnitude that

5       CR-3 is being uprated to?

6            A    No.

7            Q    So is there any precedent for a Babcock &

8       Wilcox PWR reactor being subject to an LAR request for

9       this magnitude?

10            A    Is there any precedent?

11            Q    Yes.

12            A    The NRC has established a very detailed

13       guidance for what needs to be put in an extended power

14       uprate application.  They did that in 2003.  They

15       divided it into two parts, one part dealing with boiling

16       water reactors and one part dealing with pressurized

17       water reactors.  To the extent that there are a number

18       of pressurized water reactors that have power uprates,

19       those portions would be precedence for the Crystal River

20       uprate.  There are no specific B&W designs that I'm

21       aware of that have made such a request.

22            Q    Is it correct that the uprate for the Crystal

23       River 3 reactor is about 20 percent of the current

24       licensed output of the plant?

25            A    That sounds about right.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1988

1            Q    Okay.  Is it your testimony that the magnitude

2       of the uprate request is really not a relevant

3       consideration, that an uprate is an uprate?

4            A    My testimony is that the existing framework

5       for granting an uprate has been established in detail by

6       the Commission.  It's been -- they've exercised it over

7       20 times for extended power uprate, and this is a

8       program the NRC has touted as being one of their premier

9       regulatory programs that they have high -- give high

10       priority to, established clear time frames for

11       conducting licensing reviews, and is one where I believe

12       that they have established what the basis and the

13       guidelines that a licensee would need to provide in

14       order to have confidence that their licensed amendment

15       would be approved.

16                 The NRC has also established additional

17       guidance, I think it was in May -- May or March of this

18       year -- of last year -- no, this year, which

19       established, again, the higher level of review such that

20       the interactions between the licensees and the NRC staff

21       before they submit a licensing amendment are done so

22       that the issues are identified well in advance of the

23       license amendment being submitted.  The results of those

24       activities, there should be a high level of confidence

25       that a license amendment would actually be approved once

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1989

1       it's submitted.

2            Q    So you're testifying on page 33, lines 14 and

3       15, that there is no precedent for approval of an LAR

4       for less than the amount of uprate requested by the

5       licensee, correct?

6            A    I think that's correct.  I'm saying that there

7       are no cases where a license application has been

8       submitted and the NRC said, you asked for 20 megawatts,

9       you're going to get 18.

10            Q    There's no case where a Babcock & Wilcox PWR

11       reactor has asked for an uprate of 180 megawatts,

12       correct?

13            A    Correct.

14                 MR. REHWINKEL:  That's all the questions I

15       have.  Thank you.

16                 CHAIRMAN CARTER:  Mr. Brew?

17                 MR. BREW:  Thank you, Mr. Chairman.

18                          CROSS EXAMINATION

19       BY MR. BREW:

20            Q    Good evening, Mr. Thompson.  In your 25 years

21       at the AEC and the NRC, you served in various positions

22       that you mentioned, is that right, in your testimony?

23            A    Yes, that's correct.

24            Q    And was one of those other positions a

25       technical assistant to Commissioner Peter Bradford?

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1990

1            A    Yes, it was.

2            Q    In the context of your review of the materials

3       for your testimony here, did you ever talk to Brian

4       Anderson?

5            A    No, I did not.

6            Q    And if I can refer you to your testimony on

7       page 20 -- 19 and 20, where you reference the October 6,

8       2008, docketing letter from the NRC, do you see that?

9            A    Just a moment.  On 19 and 20?

10            Q    19 and 20.

11            A    Yes, the October 6 in the middle of the page,

12       yes.

13            Q    What I want to ask you about is the sentence

14       that begins on the last line of 19 and moves over to 20,

15       which says, "The letter also stated that the NRC would

16       'require additional information from PEF about the

17       complex geotechnical characteristics of the Levy site'

18       before it could develop an integrated review schedule."

19       Do you see that?

20            A    Correct.

21            Q    Actually, it says -- the actual quote from the

22       letter says, "develop a complete and integrated review

23       schedule."  Would you accept that?

24            A    That's okay.  Was I misquoted, you're saying?

25            Q    I think so.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1991

1                 MR. ROACH:  That part is not in quotes, I

2       don't think, is it?  The quotes stop at the end of the

3       word "site."

4       BY MR. BREW:

5            Q    It is not quoted, but would you accept that

6       the actual quote is for a complete and integrated

7       schedule?

8            A    That's fine.

9            Q    Okay.  Based on your experience of years at

10       the NRC and letters such as this, would you expect that

11       the staff would be saying exactly what they mean, no

12       more, no less?

13            A    Yes, absolutely.

14            Q    And so when they say that before coming up

15       with a complete and integrated schedule, they need

16       answers to certain questions?

17            A    Correct.

18            Q    And said -- and no reasonable inference can be

19       drawn other than that staff needs more information?

20            A    I think the reasonable information in this

21       particular case was they had a number of areas that they

22       could commence their review.  It had sufficient level of

23       information that they would -- we would be willing to

24       establish their -- start their reviews on other

25       sections.  I believe in the particular areas with the

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1992

1       geotechnical ones, they said they didn't have enough

2       information to start their review.

3            Q    And that they would not develop a complete and

4       integrated schedule until they got that information?

5            A    That's correct.

6            Q    Okay.  And then they got that information in a

7       response on November 20, 2008, is that right?

8            A    Correct.

9            Q    And on pages 25 and 26 of your testimony,

10       which you were just discussing with Mr. Rehwinkel, you

11       discussed the Thursday, December 4, 2008, public scoping

12       meeting --

13            A    Right.

14            Q    -- do you recall that?

15                 So the -- Progress supplied the responses to

16       the request for additional information on the

17       geotechnical on November 20th, which was the Thursday

18       before Thanksgiving?

19            A    Right.

20            Q    The scoping meeting was held the Thursday

21       after Thanksgiving?

22            A    Correct.

23            Q    Do you have any basis to assume that Mr.

24       Anderson was at all referring to the schedule for review

25       of the LWA based on any review of the responses at that

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1993

1       point in time?

2            A    I wouldn't think he had any specific feedback

3       from the geotechnical people at that time.

4            Q    Were you here throughout the day today?

5            A    Yes, I was.

6            Q    Did you hear the discussion with Mr. Miller

7       about the fact that because of the holidays, certain

8       people that were required for that review had limited

9       availability?

10            A    Yes, I heard that.

11            Q    And you have no reason to dispute that?

12            A    I used to work at NRC, so I sure don't have a

13       reason to --

14            Q    After December 15th, it's hard to find

15       anybody.

16            A    Except me, when I was there, and Peter was

17       always there.

18            Q    Peter was there?

19            A    Peter was always there.

20            Q    Wouldn't it be a reasonable inference, then,

21       that the reference to a 24-month review that Mr.

22       Anderson made at the scoping meeting was a general

23       statement of the NRC process and not intended as a

24       specific comment on the Levy review?

25            A    No.  It was -- I agree, it established what

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1994

1       the NRC expectation would normally be.

2            Q    And so if I can refer you to the transcript

3       that's appended to your testimony?

4            A    Correct.

5            Q    At the bottom of page -- this is HT-3.

6            A    Okay.

7            Q    At the bottom of page 28 of 29, which reads,

8       "The detailed review schedule activities will be made

9       publicly available once we have completed the

10       development of our schedule.  That would more accurately

11       reflect where staff actually was at the time," they'll

12       will set a schedule once they have been through that

13       information?

14            A    Correct.

15            Q    Okay.  Is it a fair statement from the review

16       of the materials you looked at that throughout 2008, the

17       NRC staff were well aware of Progress's interest in the

18       limited work authorization and its importance to the

19       proposed schedule?

20            A    Yes.

21            Q    And would it also be reasonable to assume that

22       the NRC made clear to Progress what their needs were to

23       establish a schedule?

24            A    Yes.

25                 MR. BREW:  That's all I have.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1995

1                 CHAIRMAN CARTER:  Thank you, Mr. Brew.

2                 Mr. Jacobs?

3                 MR. JACOBS:  Mr. Chairman, SACE has no

4       questions.

5                 CHAIRMAN CARTER:  Mr. Moyle?

6                 MR. MOYLE:  No questions.

7                 CHAIRMAN CARTER:  Staff?

8                 MR. YOUNG:  No questions.

9                 CHAIRMAN CARTER:  Commissioners, anything from

10       the bench?

11                 COMMISSIONER EDGAR:  No, sir.

12                 CHAIRMAN CARTER:  Redirect?

13                 MR. ROACH:  Yes, sir.

14                         REDIRECT EXAMINATION

15       BY MR. ROACH:

16            Q    Mr. Thompson, you were given these two

17       exhibits, or potential exhibits, with 10 CFR Part 50 and

18       10 CFR Part 52.  Let me direct your attention, if I

19       could, to 10 CFR Part 50.10.  It is on page 14 of 10 CFR

20       Part 50.

21            A    Okay.

22            Q    Do you want to take a minute to look at it, or

23       are you familiar with this?

24                 COMMISSIONER EDGAR:  Excuse me, did you say

25       the page number?

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1996

1                 MR. ROACH:  It's page 14 of the book, it's

2       entitled, 10 CFR Part 50.

3                 COMMISSIONER EDGAR:  Thank you.

4       BY MR. ROACH:

5            Q    You were asked for references to the

6       information that's on page 15 of your testimony.  Does

7       this appear to be the section you were referencing?

8            A    That's correct.

9            Q    And in your testimony, you say there are three

10       things that changed.  There's the change to the

11       definition of construction, and I'm just paraphrasing,

12       but the third thing is they require the preparation of

13       an environmental impact statement, do you see that?

14            A    Correct.

15            Q    When you were asked questions about the

16       December 4th meeting, you were talking back and forth

17       with the question-and-answer about the limited work

18       authorization and where it said anything about an

19       environmental impact statement, do you recall those

20       questions?

21            A    Correct.

22            Q    Is an environmental impact statement part of

23       the limited work authorization application?

24            A    It's required to be part of the limited work

25       authorization, or, in the case of Levy, they made it,

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1997

1       the environmental impact statement cover the entire

2       activities.

3            Q    So you say the entire process for the limited

4       work authorization, that would also include an

5       environmental impact statement?

6            A    And it also included the limited work

7       authorization.

8            Q    Let me, if I could, refer you to page 30 of

9       your testimony, the January 23rd phone call.

10            A    Okay.

11            Q    And this is when the NRC finally said that

12       they weren't going to -- you asked about what the

13       schedule was set on January 23rd on this conference

14       call, is that correct?

15            A    Correct.

16            Q    And why did the NRC say that they weren't

17       going to be able to do the schedule in the 24 months?

18            A    They said they didn't have adequate staff

19       resources.

20                 MR. ROACH:  No further questions.

21                 CHAIRMAN CARTER:  ExhibitS?

22                 MR. ROACH:  I would like to move the admission

23       of ExhibitS 124 to 127.

24                 CHAIRMAN CARTER:  Are there any objections?

25                 Without objection, show it done.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1998

1                 (Exhibit Nos. 124 through 127 admitted into

2       the record.)

3                 CHAIRMAN CARTER:  Anything further for this

4       witness?

5                 MR. REHWINKEL:  Mr. Chairman, I assume that

6       the Commission will take official notice --

7                 CHAIRMAN CARTER:  Absolutely, absolutely, for

8       the record.  For the record, we'll just take official

9       notice of 10 CFR Part 50 and 10 CFR Part 52.

10                 MR. REHWINKEL:  Thank you.

11                 CHAIRMAN CARTER:  Okay, you may be excused.

12                 Call your next witness.

13                 MR. ROACH:  I would like to call Gary Doughty.

14                 COMMISSIONER EDGAR:  I'm sorry, I apologize

15       for interrupting you, I was trying to beat you.  I know

16       that we're all anxious to keep moving, but could we take

17       five minutes?

18                 MR. ROACH:  I second that request.

19                 COMMISSIONER EDGAR:  Or seven, but just a few.

20                 CHAIRMAN CARTER:  We are taking five.

21                 (Brief recess.)

22                 CHAIRMAN CARTER:  We're back on the record,

23       and when we last left, you were calling your next

24       witness.

25                 MR. ROACH:  Yes, sir, call Gary Doughty.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

1999

1       Whereupon,

2                             GARY DOUGHTY

3       was called as a witness on behalf of Progress Energy

4       Florida, Inc., and, having been previously duly sworn,

5       was examined and testified as follows:

6                          DIRECT EXAMINATION

7       BY MR. ROACH:

8            Q    State your name and your work address.

9            A    Gary Robert Doughty, 412 White Columns Way,

10       Wilmington, North Carolina.

11            Q    And you have been sworn previously?

12            A    Yes, sir, I have.

13            Q    By whom are you employed, and in what

14       position?

15            A    I am employed by Janus Management Associates,

16       Incorporated, and I am president.

17            Q    And has your rebuttal testimony of 15 pages

18       been pre-filed on August 10th in this proceeding?

19            A    Yes.

20            Q    Do you have any corrections or changes to your

21       testimony?

22            A    No.

23            Q    If I ask you the same questions today, would

24       you give the same answers?

25            A    Yes.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2000

1                 MR. ROACH:  I would like to ask that the

2       prefiled testimony be inserted into the record as if

3       read.

4                 CHAIRMAN CARTER:  The prefiled testimony of

5       the witness will be inserted into the record as though

6       read.

7                 MR. ROACH:  Mr. Chairman, there are no

8       exhibits to this testimony.

9                 CHAIRMAN CARTER:  Good.

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2016

1       BY MR. ROACH:

2            Q    Please summarize your testimony.

3            A    Mr. Chairman and Commissioners, in my opinion,

4       Dr. Jacobs has relied on hindsight to evaluate the

5       prudence of Progress Energy Florida's decisions, and he

6       has speculated rather than using facts in making some of

7       those opinions.

8                 For instance, Dr. Jacobs inaccurately

9       describes the position of the Nuclear Regulatory

10       Commission likelihood of approving a limited work

11       authorization for the Levy nuclear project at the time

12       it sent its letter on October 6, 2008.

13                 Second, Dr. Jacobs implies there was a

14       connection between the NRC's decision with respect to

15       the LWA and the stop-work order Progress Energy issued

16       to a contractor in 2007 on the Harris plant for quality

17       control deficiencies identified by Progress Energy.

18       There is no such documented linkage.

19                 Third, Dr. Jacobs presumes Progress Energy

20       placed itself in a very weak position to renegotiate the

21       engineer procured construction contract.  This

22       characterization is speculation, and actually, Progress

23       Energy may have been in a stronger position to make a

24       change order rather than what Dr. Jacobs presumes.

25                 And fourth, Dr. Jacobs states Progress Energy

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2017

1       should have had joint owners in place prior to the

2       signing of the EPC contract.  What he doesn't consider

3       is that the prospective joint owners may have wanted a

4       project that had the EPC contract in place because of

5       the greater cost certainty to them and to the project.

6       In my opinion, Progress Energy acted prudently when it

7       entered into the EPC contract on December 31, 2008, and

8       what it knew and could have known at the time, and that

9       summarizes my testimony.

10                 MR. ROACH:  The witness is available for

11       cross-examination.

12                 CHAIRMAN CARTER:  Mr. Rehwinkel?

13                 MR. REHWINKEL:  Thank you, Mr. Chairman.

14                          CROSS EXAMINATION

15       BY MR. REHWINKEL:

16            Q    Good afternoon, Mr. Doughty.

17                 On page 6 of your rebuttal testimony, could

18       you turn to there?

19            A    Yes, I'm there.

20            Q    On line 10 through 12, you start off, "PEF

21       interpreted this as an indication" -- well, let me start

22       over again and ask you this way:  You relate a series of

23       events here of a filing of the RAI's responses on

24       November 20, 2008, do you see that?

25            A    Are you talking about the page before, or that

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2018

1       6 --

2            Q    I'm on page 6.

3            A    Yes.

4            Q    Okay.  And you state that PEF offered to meet

5       with NRC technical representatives at the time of the

6       geotechnical RAI submittal, but the NRC declined to

7       meet, do you see that?

8            A    Yes.

9            Q    And that is based on something that PEF

10       employees told you?

11            A    Yes.

12            Q    And then you state further that this was

13       interpreted by PEF as an indication that there was

14       nothing further needed at that time from the NRC to

15       process the LWA request, is that correct?

16            A    Yes.

17            Q    And how do you know that, they interpreted it

18       that way?

19            A    We conducted an interview with Mr. Miller.

20            Q    And the only reason -- the only reasonable

21       interpretation of the declining to meet was that

22       everything was good?

23            A    There was no further indication of additional

24       RAIs and there was no indication that they requested

25       additional information.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2019

1            Q    Did you ask the NRC staff why they declined to

2       meet?

3            A    No.

4            Q    So you don't know why they declined to meet,

5       do you?

6            A    Other than that they didn't require any

7       additional information, no.

8            Q    That is the only reason, the only logical

9       reason that they would decline to meet?

10            A    That's what I interpreted.

11            Q    But you don't know whether there was any

12       holidays that interfered with them making an appointment

13       to meet with Progress?

14            A    Well, we didn't say that -- they didn't meet

15       on Thanksgiving weekend, no.

16            Q    There is no documentation as to the reason the

17       NRC declined to meet, is there?

18            A    No.

19            Q    You state, continuing on line 12, "Based on

20       industry experience, PEF reasonably expected that

21       providing responses to the NRC RAIs would lead to an LWA

22       review schedule."  Do you see that?

23            A    Yes.

24            Q    What is this industry experience that you are

25       talking about?

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2020

1            A    The experience in terms of their previous

2       experience with respect to interactions with the NRC.

3       They were keeping the NRC up to date.  They had

4       submitted the RAIs and turned them around in detailed

5       fashion, that is, they were comprehensive responses to

6       the RAIs, and, in my view, they were -- it was

7       reasonable to expect that they would get a schedule.

8            Q    You evaluated the RAIs for their technical

9       sufficiency?

10            A    I'm not an expert in geotechnical information,

11       but I did review the RAIs.

12            Q    Did you review them for technical sufficiency?

13            A    No.

14            Q    And the industry experience that you refer to

15       here, is that based on all the other LWA review

16       schedules that had been established by the NRC?

17            A    No, because none had been established.

18            Q    Now, were you with the Progress Energy folks

19       in January of 2009 when the LWA notification was

20       received by teleconference?

21            A    I was not in the meeting, but I was at

22       Progress Energy Carolina headquarters.

23            Q    So you were there -- you were part of -- you

24       were surprised on that day?

25            A    Say that again.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2021

1            Q    You were surprised on that day?

2            A    I didn't know it on January 23rd, but it

3       would be after that.

4            Q    Okay.  So is the statement that it was a

5       complete surprise to PEF based on something Mr. Miller

6       told you?

7            A    Mr. Miller, Mr. Kitchen, and there may have

8       been one or other two people whom we interviewed.

9            Q    Who in the industry told you they were

10       surprised?

11            A    That was what was related to me in terms of

12       Progress Energy people getting calls from people in the

13       industry in the similar situations who were surprised

14       that the LWA was not -- was -- schedule was not separate

15       from the COL when done earlier.

16            Q    What similar situations do you mean?  I mean,

17       there was no other LWA pending --

18            A    No, other people were applying for COLAs and

19       contacted PEF and expressed surprise.

20            Q    Okay, but there was nobody else that had a

21       COLA and an LWA pending at the time, right?

22            A    Correct.

23            Q    Okay.  On page 7, you, like everyone else it

24       seems, quotes this November 8th statement by Mr.

25       Anderson here, is that correct, up on line -- starting

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2022

1       on line 3 --

2            A    Yes.

3            Q    -- December 4, 2008?

4            A    I'm sorry, I interrupted your question.  Could

5       you say it again?

6            Q    I guess you're one of all of the rebuttal

7       witnesses to Dr. Jacobs that quotes the December 4,

8       2008, statement by Mr. Anderson here, correct?

9            A    I do quote it here, yes.

10            Q    Okay.  Now, you have chosen to highlight the

11       portions of the statement by Mr. Anderson that excludes

12       the phrase "a ballpark time frame" twice, correct?  You

13       have chosen not to highlight those two phrases, right?

14            A    Those two phrases.  There is one phrase that

15       reads "just to give you a ballpark time frame."

16            Q    And you don't highlight that, do you?

17            A    No.

18            Q    And then, "and that is a ballpark time frame,"

19       you don't highlight that, either, right?

20            A    No, I didn't.

21            Q    Okay.  Is that because you consider that to be

22       extraneous and unimportant information in this

23       statement?

24            A    I included the entire statement, but the most

25       important part was what I highlighted.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2023

1            Q    And you know that is important because of all

2       the other LWAs that the NRC has given time frames on?

3            A    No.  As we have already discussed, there are

4       no other LWAs.  This is specific to this plant.

5            Q    Okay.  On line 4, you state that, "this

6       response reinforced PEF's assumptions regarding the NRC

7       review of the LWA."  How do you know that that

8       reinforced their assumptions?

9            A    This was consistent with the -- this is my

10       opinion -- consistent with -- they were at the meeting,

11       "they" being Progress Energy personnel, and it was

12       another indication of the expected time for an LWA and

13       that an LWA would be forthcoming.

14            Q    You were not at the meeting, were you?

15            A    No, sir.

16            Q    So how do you know this reinforced their

17       assumptions?

18            A    I said that's my opinion.

19            Q    Okay.  But what was that opinion based on?

20            A    This and the other information that they were

21       working with with respect to their application and

22       interaction with the NRC.

23            Q    Wouldn't you, to know -- to form this opinion,

24       wouldn't you need to know that they relied on this

25       information with respect to their opinions about the LWA

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2024

1       and NRC review of it?

2            A    I don't know that they didn't rely on it.  It

3       is consistent with -- as Mr. Miller explained, it was

4       not news in terms of a change in what the NRC was

5       saying, so it was part of that overall communication

6       process.

7            Q    But you don't know whether they relied on it

8       or not, do you?

9            A    I don't know for certain that they relied on

10       this specific statement, but that it was part of the

11       overall environment that they were dealing with with

12       respect to their LWA application.

13            Q    So you can't say with any certainty that it

14       reinforced any assumptions they might have held

15       regarding the NRC's review of the LWA, can you?

16            A    I did say it, and I stand by that.

17            Q    You can say with certainty that it did?

18            A    No, not with certainty.

19            Q    Okay.  All right.

20                 You've criticized, it seems to me, on line

21       6 and 7, Dr. Jacobs for not including this information

22       in his testimony, do you not, "this information" meaning

23       the December 4, 2008, statement by Mr. Anderson?

24            A    Can you point me to a place?

25            Q    Well, it says, "This information was not

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2025

1       included in Jacobs' testimony."

2            A    Correct.

3            Q    Is that a criticism of Dr. Jacobs' testimony?

4            A    It's a fact.

5            Q    Okay.  How many Progress Energy witnesses on

6       direct included this information?

7            A    On direct, none.

8            Q    None.  Is that another fact?

9            A    Yes.

10            Q    Okay, thank you.

11            A    But it also has been explained by Mr. Miller

12       as to why, and I explained it in my previous answer.

13            Q    Well, did you review the discovery responses

14       that the company gave about meetings that they had with

15       NRC staff?

16            A    I did review some, yes.

17            Q    Did you review any that contained December 4,

18       2008?

19            A    Say that again.

20            Q    Did you review any that disclosed this

21       December 4, 2008, communication with NRC staff about the

22       LWA?

23            A    This is -- are we talking about this same

24       meeting?

25            Q    Yes.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2026

1            A    This meeting was a noticed meeting for the

2       public, so I don't know that it constituted a separate

3       communication, formal communication, with the NRC by the

4       Progress Energy folks.  It was a public meeting.

5            Q    Did you review discovery that listed other

6       public meetings, publicly noticed meetings, with NRC

7       staff?

8            A    Well, publicly noticed -- yes, NRC publicly

9       noticed meetings with Progress Energy personnel, not for

10       the purposes of public dissemination of information.

11            Q    Okay.  I thought Mr. Miller said they just

12       forgot about it.  Wasn't that his explanation why it

13       wasn't in the direct?

14                 MR. ROACH:  I object.  I don't think that does

15       justice to Mr. Miller's answer.

16                 CHAIRMAN CARTER:  To the objection, Mr.

17       Rehwinkel?

18                 MR. REHWINKEL:  Mr. Doughty said that Mr.

19       Miller explained why it wasn't in the direct testimony,

20       so I'm asking him to explain further his testimony here

21       today.

22                 THE WITNESS:  It was my recollection of his

23       testimony earlier today or -- yes, earlier today.

24       BY MR. REHWINKEL:

25            Q    Is that because he forgot?

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2027

1            A    I don't recall.

2            Q    Okay, let's turn to page 10 of your rebuttal

3       testimony.

4            A    I'm at page 10.

5            Q    Okay, on -- the Q&A that starts on line 6 and

6       continues on down for the next page and a half relates

7       to the CH2M Hill quality assurance issues, is that

8       correct?

9            A    Yes.

10            Q    Now, you state that Dr. Jacobs' pointing to QA

11       issues with CH2M Hill is wrong, first because it rose

12       out of work performed by CH2M Hill at the Harris nuclear

13       plant and not at LNP, is that correct?

14            A    The question I answer is is he accurate, and

15       the answer is no, and then I point out that he has

16       pointed to certain QA issues with CH2M Hill at the

17       Harris plant.

18            Q    So is it your testimony that the issues, the

19       QA issues that related to CH2M Hill in North Carolina,

20       had nothing to do with the work they were doing at LNP?

21            A    No.  The stop-work order applied to both --

22       any work that CH2M Hill was doing.

23            Q    On lines 17 through 19, you say, "Based on

24       Progress Energy's assessment of completed corrective

25       actions, this stop-work order was lifted on May 1,

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2028

1       2007," do you see that?

2            A    I see that.

3            Q    Is there an implication in your testimony

4       there that once the stop-work order was lifted relative

5       to CH2M Hill's work, that Progress Energy had determined

6       they had completed corrective actions?

7            A    This is a statement of fact, and as Mr. Miller

8       explains and in the review of the documents that I did,

9       Progress Energy closely monitored all the work that CH2M

10       Hill did, including increasing the audit frequency.

11            Q    But on May 1, 2007, CH2M Hill had not

12       corrected all of the deficiencies noted in both their

13       internal audit as well as Progress Energy's audit,

14       correct?

15            A    Correct.  There was a -- compensatory measures

16       taken, which Mr. Miller explained, and there were action

17       items that had to be completed by CH2M Hill.

18            Q    On page 11 of your rebuttal testimony -- no,

19       let me move on to page 12.

20                 You have not negotiated an EPC contract, have

21       you?

22            A    Yes.

23            Q    You have?

24            A    Yes.

25            Q    For who?

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2029

1            A    For Northeast Utilities.

2            Q    Have you negotiated an EPC contract for a

3       nuclear power generating station?

4            A    Not that are similar to the contract in this

5       case, but large contracts I have reviewed that are

6       similar.

7            Q    Did you advise Progress Energy Florida about

8       negotiation of their EPC contract before December 31,

9       2008?

10            A    No, I did not.

11            Q    Aren't you speculating about the relative

12       bargaining position of PEF and the consortium with

13       respect to renegotiating any aspect of the EPC contract?

14            A    I'm stating the alternative view based on my

15       knowledge of what Progress Energy knew at the time and

16       what was in the EPC contract and the description of the

17       negotiation process and the benefits of the contract

18       situation.

19            Q    So the answer is yes, you're speculating, to

20       some degree?

21            A    I'm making a judgment, yes.

22            Q    Okay.  And on page 13, lines 10 through 13,

23       the non-confidential parts of that, do you see that?

24            A    Yes.

25            Q    You are stating an opinion about PEF being in

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2030

1       a stronger position to renegotiate the contract than if

2       those terms were not previously secured, do you see

3       that?

4            A    Yes.

5            Q    That's really based on information that you

6       were told by Mr. Miller and others?

7            A    No.  I reviewed the EPC contract in either

8       late January or early February in two different

9       sessions, in addition to being introduced to the

10       concepts that Progress Energy was seeking by Mr. Miller

11       prior to doing my review.  After reviewing the contract

12       and seeing where the benefits accrue, I'm making that

13       judgment myself, because there is a change order process

14       that is in place, and my knowledge of contracting and so

15       forth, and contract administration, this is a stronger

16       position for them, in my judgment, than it would be if

17       they had to re- -- to start negotiations over again.

18            Q    But it remains to be seen how those contract

19       renegotiations turn out, does it not?

20            A    It does.

21            Q    Thank you.

22                 MR. REHWINKEL:  No further questions.  Thank

23       you.

24                 CHAIRMAN CARTER:  Mr. Brew?

25                 MR. BREW:  No questions for this witness.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2031

1                 CHAIRMAN CARTER:  Mr. Davis?

2                 MR. DAVIS:  None, thanks.

3                 CHAIRMAN CARTER:  Mr. Moyle, you're

4       recognized.

5                 MR. MOYLE:  I have just a couple of questions.

6                          CROSS EXAMINATION

7       BY MR. MOYLE:

8            Q    We spent a lot of time in the last couple of

9       days talking about a couple of statements made by

10       officials; for example, the October 6 letter from the

11       NRC.  You are familiar with that letter, right?

12            A    Yes, sir.

13            Q    And then there is a December 4th statement by

14       an NRC official at a public meeting, you're familiar

15       with that statement --

16            A    Yes.

17            Q    -- you've included it in your testimony?

18                 Wouldn't you agree, sir, that those statements

19       speak for themselves?

20            A    Yes.

21            Q    And wouldn't you also agree that this

22       Commission can look at those statements just like you or

23       any other witness and make a judgment as to what is

24       being said in those statements?

25            A    If they have other information, but the

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2032

1       statements, as you just said and as I agreed, speak for

2       themselves, so they can draw conclusions from those

3       statements, if that's what you mean.

4            Q    I understand, but as we sit here today, you

5       don't have any kind of special expertise that allows you

6       to get into the mind of somebody writing a letter and

7       go, well, here's what they were really thinking?  I

8       mean, the fact is the letters speak for themselves,

9       correct?

10            A    Correct.

11                 MR. MOYLE:  That's all I have.

12                 CHAIRMAN CARTER:  Thank you.

13                 Staff?

14                 MR. YOUNG:  No questions.

15                 CHAIRMAN CARTER:  Commissioners?  Redirect?

16                 MR. ROACH:  No, sir.

17                 CHAIRMAN CARTER:  And there are no exhibits?

18                 MR. ROACH:  No exhibits.

19                 CHAIRMAN CARTER:  Anything further for this

20       witness?

21                 Thank you, sir.  You may be excused.

22                 Call your next witness.

23                 MR. WALLS:  Progress Energy calls Jeff Lyash.

24                 MR. REHWINKEL:  Mr. Chairman, while Mr. Lyash

25       is coming to the stand, I have talked to the other

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2033

1       parties, including Progress Energy, and with your --

2                 (Brief pause.)

3                 CHAIRMAN CARTER:  Now, what were you saying,

4       Mr. Rehwinkel?

5                 MR. REHWINKEL:  Yes, Mr. Chairman, I have

6       talked to the other parties, including Progress.  If it

7       would be okay with you, we would like to change the

8       order slightly where Mr. Brew, Mr. Davis and Mr. Moyle

9       would go, and then I would go last and ask questions if

10       I had any.

11                 CHAIRMAN CARTER:  Okay, that will be fine.

12                 MR. REHWINKEL:  I think it may save some time.

13                 CHAIRMAN CARTER:  No problem.  Mr. Brew --

14       wait a minute.  Let's do this, how about Mr. Walls,

15       you're recognized.

16                 MR. WALLS:  Thank you.

17       Whereupon,

18                           JEFFREY J. LYASH

19       was called as a witness on behalf of Progress Energy

20       Florida, Inc., and, having been previously duly sworn,

21       was examined and testified as follows:

22                          DIRECT EXAMINATION

23       BY MR. WALLS:

24            Q    Mr. Lyash, will you please introduce yourself

25       to the Commission and provide your business address?

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2034

1            A    Yes.  My name is Jeffrey J. Lyash, and my

2       business address is 410 South Wilmington Street,

3       Raleigh, North Carolina.

4            Q    Have you already been sworn in as a witness?

5            A    I have.

6            Q    Who do you work for and what is your position?

7            A    I work for Progress Energy, and my position is

8       Executive Vice-President of Corporate Development.

9            Q    Have you filed prefiled rebuttal testimony

10       with exhibits in this proceeding?

11            A    I have.

12            Q    And do you have that with you?

13            A    I do.

14            Q    Do you have any changes to make to this

15       prefiled rebuttal testimony or exhibits?

16            A    I do not.

17            Q    If I asked you the same questions asked in

18       your prefiled rebuttal testimony today, would you give

19       the same answers?

20            A    I would.

21                 MR. WALLS:  We request that the prefiled

22       rebuttal testimony be moved into evidence.

23                 CHAIRMAN CARTER:  The prefiled testimony of

24       the witness will be inserted into the record as though

25       read.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2076

1       BY MR. WALLS:

2            Q    Do you have a summary of your rebuttal

3       testimony?

4            A    I do.

5            Q    Will you provide it to the Commission, please?

6            A    Yes.

7                 Good evening, Commissioners.  I'm providing

8       rebuttal testimony to the Intervenors' contentions that

9       the company's decision to execute the EPC contract in

10       December of 2008 was neither reasonable nor prudent, and

11       to the contention that the feasibility analysis provided

12       by Gary Miller in this docket was somehow deficient or

13       inadequate.

14                 PEF's decision to execute the EPC contract in

15       December of 2008 was reasonable and prudent.  Contrary

16       to Intervenors' contentions, we never expected potential

17       joint owners to sign up before the execution of the EPC

18       contract.  The potential joint owners reasonably wanted

19       to know what the final signed EPC agreement provided

20       before they signed the joint ownership participation

21       agreement.

22                 In addition, in December 2008, the company did

23       not know and should not have known that the NRC would

24       not approve the LWA before issuing the combined license.

25       PEF reasonably and prudently acted on this information

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2077

1       that was available at the time, and by so doing was able

2       to preserve the contractual benefits that had been

3       secured through two years of intense negotiations.  All

4       risks associated with the Levy project were identified,

5       analyzed and appropriately managed by the company

6       through the adoption of risk mitigation plans consistent

7       with the company's risk mitigation policies.

8                 Finally, the feasibility analysis provided by

9       Mr. Miller is adequate and consistent with the purpose

10       of the nuclear cost recovery statute and rule.  PEF's

11       analysis is proper for assessing the feasibility for

12       long-term projects such as LNP.

13                 The analysis offered by Intervenors, on the

14       contrary, would present an unworkable framework whereby

15       long-term feasibility is constantly reevaluated based on

16       year-to-year fluctuations in projections.  If the

17       company based its decision on stopping and restarting

18       the project each year on these annual fluctuations, the

19       company could never build the nuclear power plant.  Such

20       an approach would lead to a decrease in regulatory

21       certainty, lead to an increase in costs and ultimately

22       result in no nuclear generation being built in the

23       state.

24                 Further, the Intervenors' proposition that the

25       Commission should make no decisions now regarding the

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2078

1       prudence and feasibility of the Levy project would also

2       do away with regulatory certainty, and would, I believe,

3       result in no nuclear generation being built.  This is

4       surely not the purpose of the nuclear cost recovery

5       statute and rule, which are both intended to encourage

6       utility investment in nuclear power plants.  Indeed, if

7       feasibility is viewed as strictly a cost-effective

8       analysis, as the Intervenors suggest, PEF would never

9       have initiated the LNP project.

10                 That concludes my statement.  Thank you.

11                 MR. WALLS:  We tender Mr. Lyash for cross.

12                 CHAIRMAN CARTER:  Mr. Brew?

13                          CROSS EXAMINATION

14       BY MR. BREW:

15            Q    Good evening, Mr. Lyash.  I want to follow up

16       first on a question I asked Mr. Miller, since you both

17       sponsored testimony on feasibility.  Has Progress Energy

18       made a final decision on whether to proceed with the

19       Levy project?

20            A    Progress Energy has initiated -- the answer is

21       no, but let me explain.

22                 Progress Energy has entered into this Levy

23       project with the full intent of taking the project to

24       completion and in the best interests of the

25       shareholders, but with any project of this size, we

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2079

1       constantly evaluate and reevaluate that decision at each

2       milestone and reaffirm the decision to proceed.  That's

3       what we have done and we will continue to do.  So we

4       have no indication presently that this project cannot

5       and will not be completed, but we will constantly assess

6       that.

7            Q    So would you agree, then, that that decision

8       to go forward is not a static, one-time one, but is one

9       that you continually and sequentially review?

10            A    That's correct, as we would do with any

11       project of this magnitude, and frankly, any project that

12       we would implement.

13            Q    Okay.  You made a statement in your summary

14       that's similar to a statement that appears on page 6 of

15       your rebuttal that appears on line 10 through 12, which

16       says, "PEF's feasibility analysis represents the

17       necessary analysis to determine if long-term basal

18       nuclear generation projects like Levy Units 1 and 2 can

19       be completed."  Do you see that?

20            A    Yes, I do.

21            Q    Does the nuclear cost recovery rule apply --

22       feasibility analysis apply to projects like Levy, or

23       Levy?

24            A    I'm sorry, can you ask that last part again?

25            Q    I will try it a different way.  Is the

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2080

1       feasibility analysis required under the rule project-

2       specific?

3            A    I think the rule is generic in nature, but the

4       project in front of us is Levy, and so feasibility

5       determination in this instance would apply to Levy.

6            Q    So when the rule says -- requires a detailed

7       analysis of the long-term feasibility of completing the

8       power plant, it means Levy in this context?

9            A    Yes, I would agree.

10            Q    So Progress is required to file an annual

11       feasibility analysis that pertains to Levy?

12            A    Yes, the feasibility analysis at issue today

13       is with respect to the Levy nuclear project.

14            Q    Not any nuclear plant in Florida?

15            A    Yes, I believe that's correct.

16            Q    Okay.  Now, you mentioned in your summary, you

17       mention on page 6, you mention later in your testimony

18       your concern about feasibility analysis that relies on

19       year-to-year variability in various items, is that

20       right?

21            A    Yes.

22            Q    Okay.  Is the schedule shift that's been

23       announced a year-to-year variation or is it a permanent

24       one?

25            A    I would think that the schedule shift here is

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2081

1       permanent in nature.  It's particularly the 20-month

2       extension in the in-service, or in the commencement of

3       safety-related concrete pour, yes.

4            Q    So that's not something you expect to vary

5       year to year, this is a shift in the schedule that's

6       going to be permanent?

7            A    Well, I would expect year to year that we

8       would see shifts in the schedule, forward and backward,

9       for many variety of reasons, and that those schedule

10       shifts would be evaluated and considered within the

11       context of the overall project.  So while this year,

12       because of the issue with the LWA that has been

13       discussed in detail, we see a permanent shift that

14       impacts the project, I'm not sure that this will be

15       unique in the overall life of the project.

16            Q    Would you consider a schedule delay of 20 to

17       36 months to be a significant delay?

18            A    Yes, I would consider that significant in

19       terms of the established project schedule.  In terms of

20       project feasibility, however, given that this is a 60-

21       to 80-year asset and the scale of the benefits that

22       accrues, I'm not sure a 20-month shift in terms of that

23       broader context is significant.

24            Q    In terms of year-to-year variations, when was

25       the last time Progress Energy Florida experienced a

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2082

1       negative customer growth?

2            A    Likely some 20 to 30 years ago.

3            Q    Okay, so the drop in the customer -- in

4       Progress's sales that they've recently experienced you

5       would consider to be a significant development?

6            A    Well, I think the economic recession -- the

7       answer is yes in the short term.  I think the economic

8       recession we're seeing today is certainly significant

9       and, in a lot of senses, unprecedented.  However, our

10       customer growth projections in the future continue to be

11       positive, and, in fact, just within the last 18 months

12       we've set some record peaks on our generation system.

13       So I think it is certainly significant in the short

14       term; however, once again, I don't consider that to be

15       significant in terms of the long-term viability or

16       benefits of the Levy project.

17            Q    Between 2008 and 2009, your ten-year site

18       plan, Progress has lowered its long-term low growth

19       forecast, hasn't it?

20            A    That's correct.  We reflected our view of the

21       current economic recession and the shift in customer

22       growth into our ten-year site plan filing.

23            Q    So -- I'm sorry, are you finished?

24            A    Yes.

25            Q    Okay.  So Progress expects the ramifications

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2083

1       of the recession to have a lasting impact?

2            A    Yes, I think the ramifications of any

3       recession have a lasting impact, and we have reflected

4       what we think the extent of that impact is into our ten-

5       year site plan.  However, in terms of the need or the

6       benefit from the Levy project, they do not impact that

7       conclusion.

8            Q    They don't impact, what was that?

9            A    I said in terms of the need for the Levy

10       station and in terms of the long-term benefits to the

11       customers, those lasting impacts of the recession which

12       are reflected in our ten-year site plan don't impact our

13       conclusion.

14            Q    But the schedule shift takes the Levy units

15       out of your ten-year site plan, doesn't it?

16            A    Potentially.  We have not settled on a date

17       yet.  We're considering a 20- to 36-month window, which

18       would place the Levy units either within or just at the

19       horizon of the ten-year site plan.

20            Q    And so if you need base load capacity within

21       that ten-year horizon, you'll need to get it from

22       another source, is that right?

23            A    Yes, we'll need to meet our resource needs

24       during that ten-year window by some method.  It does not

25       make the Levy decision irrelevant to the ten-year site

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2084

1       plan, because we might bridge that need with different

2       methods with or without the Levy units.

3            Q    But if you built new capacity, that would

4       affect your need for additional capacity that would be

5       represented by Levy, wouldn't it?

6            A    We have not made a decision to build

7       additional capacity.  We currently have a combined -- we

8       currently have a combustion turbine in the ten-year site

9       plan.  It might perhaps impact the size or the nature of

10       that project.  It could perhaps be covered with purchase

11       power agreements or other variables in the plan.

12            Q    My question was, if you built additional

13       capacity, that would affect the need for the capacity

14       when you would need the capacity for the Levy units,

15       wouldn't it?

16            A    Yes, it might, but that would be very

17       scenario-specific.  It would depend on the nature of the

18       decision that we made and a number of other factors that

19       would bear on that.

20            Q    And you haven't made those judgments yet?

21            A    Well, we're in the process -- no, we're in the

22       process, as I said, now of evaluating where to place the

23       Levy schedule, what is the optimum schedule to flex to

24       here, and that decision will in significant part inform

25       those short-term generation decisions.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2085

1                 However, I must say that regardless of what

2       short-term decision is made with respect to the Levy

3       project -- generation other than Levy in the site plan,

4       the nature of a large base load unit like Levy that

5       accrues the benefits that come with it in terms of fuel

6       diversity, fuel costs, environmental impact and the

7       long-term benefit produced, that need for the Levy units

8       in our plan really -- over that long-term period really

9       is unaffected by short-term decisions we may make about

10       other generation necessary to fill the gap.

11            Q    The generic benefits you were just talking

12       about are -- you've kind of mentioned on page 28 of your

13       testimony.

14            A    Did you say 28?

15            Q    28, yes.

16            A    Thank you.

17            Q    Are those the kind of benefits that you're

18       referring to, fuel portfolio diversity, lessened

19       reliance on fossil fuels and carbon-free energy

20       generation?

21            A    Yes, those as well as the long-term cost

22       benefits to the customers accrued by the low and stable

23       fuel price related to nuclear power.

24            Q    Okay, so whether there are actually cost

25       benefits to consumers is a function of how much the unit

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2086

1       actually costs, is it not?

2            A    Yes, the unit cost is certainly one of the

3       factors in the benefits that accrue to customers.

4            Q    So it's not a -- you don't get these benefits

5       regardless of cost, right?

6            A    You do get these benefits -- many of these

7       benefits regardless of cost, although I'm not suggesting

8       that cost is irrelevant.  So, for example, the value of

9       a diverse fuel portfolio, reduction in reliance on

10       fossil fuels, the reduction in carbon emissions

11       associated with the generating stack, these are benefits

12       that really accrue to the customer regardless of the

13       particular capital construction cost.  So they remain in

14       any case.  Now --

15            Q    Could I --

16            A    Just one last, and then I'll stop.  But I

17       don't mean to suggest that cost is not a relevant

18       factor, it's just not the only factor.

19            Q    Okay.  Can you get all of those same benefits

20       from biomass?

21            A    No, not at this scale or for this period of

22       time.

23            Q    Could you get it a lot more economical?

24            A    Pardon me?

25            Q    Could you get it much more economical?

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2087

1            A    No.  I believe to accumulate these benefits

2       the Levy nuclear project is the most economical way to

3       do that.  That was, I think, vetted fairly extensively

4       in the need case.

5            Q    In the need case, okay.

6                 Let's talk about in the latter part of your

7       testimony you discuss an updated cumulative present

8       worth revenue requirement analysis that you performed in

9       response to a staff information request, is that right?

10            A    That's correct.

11            Q    And among other things, you say that this is

12       not the type of analysis that you would normally

13       perform, but you're doing it for the purposes of this

14       proceeding?

15            A    That's correct.

16            Q    Okay.  Would you agree that for purposes of

17       the feasibility analysis under the rule, the Commission

18       needs some kind of analysis showing that the project is

19       likely to provide net benefits to consumers over time?

20            A    Well, let me, if I may, let me tell you my

21       view of feasibility.  I think feasibility, certainly as

22       Mr. Gary Miller --

23            Q    Let me stop you.  Again, just if you can

24       answer my question and then explain.  Don't answer your

25       own question.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2088

1            A    I'm sorry, can you restate the question?

2            Q    Whether or not the Commission in this

3       proceeding needs in its economic and feasibility

4       analysis some analysis of whether there are likely to be

5       net economic benefits to consumers over the life of the

6       plan?

7            A    Yes, I think a qualitative analysis of that

8       needs to be part of the discussion, and I think that's

9       what has been provided in Mr. Miller's testimony.

10                 You know, this -- I think feasibility goes to,

11       as Mr. Miller said, can the plant be built technically,

12       is there a fatal flaw in the design, can it be

13       constructed, can it be operated, will it deliver the

14       benefits, and cost, which you implied in a previous

15       question is a part of that, is certainly an issue and

16       should not be ignored.  However, that total cost for the

17       project I think needs to be viewed in the long term,

18       not -- my point was not based on a cumulative net

19       present value revenue requirement that fluctuates month

20       to month or year to year.

21            Q    But under the rule, customers are paying for

22       the cost currently, even though they won't actually see

23       any of those benefits for another decade?

24            A    Yes, under the legislation, customers are

25       paying for a portion of the plant cost and carrying cost

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2089

1       in anticipation of substantial long-term benefit, that's

2       correct.

3            Q    And that's expected in this case to amount to

4       several billions of dollars before the units go into

5       service, is that right?

6            A    That's correct.

7            Q    Okay.  So a part of that same rule requires

8       this feasibility analysis to be performed, is that

9       right?

10            A    It does.

11            Q    And so part of that analysis needs to make

12       sure that the dollars ratepayers are spending up front

13       is being well spent, is that right?

14            A    I think that's the purpose of a prudence

15       determination as to whether those costs are being

16       prudently incurred.

17            Q    No, there are two purposes here.  One is

18       prudence, the other is feasibility.

19            A    Correct.

20            Q    Do you equate the two?

21            A    No, I don't.

22            Q    So I'm talking feasibility.  So would you

23       agree that the, part of the purpose of the feasibility

24       in the requirement is to make sure that the dollars that

25       consumers are going to be spending continue to be

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2090

1       well-spent?

2            A    Now, I can only read the rule as it's stated,

3       and that is that the legislation requires that a

4       determination of feasibility be performed.  And as I

5       said previously, I think that that is technical,

6       regulatory, operational feasibility to complete the

7       plant, and as a part of that qualitatively, I think

8       total cost needs to be considered, keeping in mind that

9       the benefits to this plant are large and very long-term.

10            Q    Can the project be considered to be feasible

11       if it's not expected to be cost-effective for consumers?

12            A    Yes, it can, but it depends on what cost-

13       effectiveness standard you're comparing it to.

14                 I think, for example, if, as has been

15       presented in a number of the Intervenors' testimony, the

16       test is as we provided in response to the interrogatory;

17       in other words, a point-in-time cumulative present value

18       revenue requirement.  I could conceive that the plant

19       would, with respect to that one test, prove to be not

20       the most cost-effective solution at a given point in

21       time, and I could conceive that a year later the plant

22       would, per that test once again, prove to be cost-

23       effective.

24                 So I'm trying to answer your question

25       straightforwardly.  Yes, I think there are circumstances

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2091

1       where you could craft a feasibility test based on cost

2       that would not show a positive net present value.

3            Q    What I'm trying to get to is I'm trying to

4       find out does Progress object to the cumulative present

5       value revenue requirement analysis, or does it object to

6       providing any quantitative analysis of cost benefits for

7       consumers?

8            A    Well, we certainly object to the notion that

9       that cumulative present value revenue requirement

10       outside the need test is a valid test, and we provided

11       it because the Commission asked, and if the Commission

12       asks, we will continue to provide it.  In this

13       particular case, that showed better benefits than we

14       showed in the need, but I don't consider it relevant to

15       this decision.  I think the Commission should certainly

16       consider, for example, whether the total project cost

17       has changed in a magnitude or in a way that would make

18       the project not feasible.

19                 So we don't object to cost being incorporated

20       into the discussion of feasibility and being considered

21       as part of it, but I think by the nature of the length

22       of this project and the scale, it's going to be a

23       qualitative discussion, as opposed to a very

24       quantitative point-in-time analysis.

25            Q    So you object to demonstrating to the

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2092

1       Commission that consumers are likely to see net benefits

2       from the project over time?

3            A    No, I object to the notion that we should use

4       a cost-based net present value test on an annual basis

5       to make that decision.

6            Q    Do you have a different test in mind?

7            A    I think it's the one that we proposed, or the

8       one that we included in the testimony, and that is, to

9       provide the Commission with an assessment of whether the

10       project continues to be feasible from a technology,

11       execution, regulatory and licensing point of view, to

12       update, as the Commission requested in the need order,

13       our fuel forecast and our environmental cost

14       projections, and at the point in time to provide our

15       best estimate total project cost, all of which we have

16       done.  I think that, given that information, it puts the

17       Commission in an adequate position to assess whether the

18       project remains feasible.

19            Q    So you want to provide a qualitative

20       assessment and not actually try to demonstrate that it's

21       cost beneficial to consumers, is that right?

22            A    Yes.  However, as I said, what I'm objecting

23       to is the notion that the cost beneficial test is the

24       specific cumulative present revenue requirement test

25       that was asked for in the interrogatories.  I'm not

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2093

1       objecting to an overall feasibility assessment that

2       incorporates total cost.

3            Q    Total cost and net benefits to consumers, net

4       economic benefits to consumers?

5            A    Well, I think that this assessment -- I'm

6       sorry, could you rephrase the question?  I want to

7       answer yes or no, but that one --

8            Q    Your answer said you didn't object to

9       providing information on total cost.

10            A    Correct.

11            Q    What I asked is, do you object to providing an

12       analysis that shows a net economic benefit to consumers,

13       whether they exist or not?

14            A    No, and I think we have done that.  However,

15       if you're suggesting that we provide a quantitative

16       analysis --

17            Q    Yes.

18            A    -- for example, of the value of fuel

19       diversity, of the value of reducing reliance on fossil

20       fuel, of the value of long-term reduction of CO, those

21       are things that are difficult, if not impossible, to

22       quantify with a point estimate.

23            Q    Would Progress undertake this project if you

24       couldn't show to senior management that it was likely to

25       provide net benefits to Progress, economic benefits?

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2094

1            A    No, in this particular case, although there

2       are projects that we undertake on our system year in and

3       year out that provide no net benefit to Progress Energy.

4       As example, the significant expansion of energy

5       efficiency programs that's currently underway, they

6       really have no net economic benefit to the company;

7       however, we propose and implement those because we view

8       them as having net benefits to the customers in the long

9       term and an important part of the mix.

10            Q    Are there any capital investments in

11       generation that the company would make if the company

12       didn't expect it would see a net economic benefit?

13            A    No, that would be unlikely, and primarily

14       because you need to raise capital in order to implement

15       these projects, so unless we can show that we can

16       provide a return to the investors for the capital raised

17       and invested, it's unlikely we would have the capital to

18       execute the project.

19            Q    Let's talk a little bit about the analysis you

20       did provide that shows up in your Exhibit JL-2.  When

21       you're ready?

22            A    Yes.

23            Q    I would like to refer you to page 13 of that

24       exhibit.

25            A    I'm sorry, I have pages 1 through 10, 10 being

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2095

1       the Table 5, and then pages 1 through 13 in the

2       appendix.

3            Q    This would be -- it's labeled 13 of 23 at the

4       upper right-hand corner, but it's 3 of 13 at the bottom

5       of the page in your appendix.

6            A    13 of 23 in the upper right-hand corner?

7            Q    Right, yes, part of the appendix.  Do you have

8       that?

9            A    Yes, I do.

10            Q    And that is the Levy Nuclear June '09 Review

11       Emission Cost Estimates?

12            A    Yes.

13            Q    And am I correct that for the columns that

14       label CO costs per ton that the numbers shown in those

15       four columns are the same numbers that the company

16       supplied in its need case last year?

17            A    Yes, I believe that's correct.  We updated

18       emission costs, in other words, our resource planning

19       group executed a review, and where there were changes in

20       the numbers over the course of the year, for example,

21       NOx, Ox or mercury had moved, those numbers were

22       updated.  Where there was no indicated change in the

23       number, those numbers would have been reported at the

24       same level they were last year.  And as you rightfully

25       point out, the CO numbers, although we reviewed and

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2096

1       updated them, are unchanged, because nothing with

2       respect to that of significance has changed.

3            Q    Now, Mr. Miller in his exhibit noted the

4       existence of the Waxman-Markey Bill.  Are you familiar

5       with that bill?

6            A    Generally.

7            Q    Generally?

8                 MR. BREW:  Mr. Chairman, I would like at this

9       time to mark for identification the document that I've

10       circulated.

11                 CHAIRMAN CARTER:  The number would be 155.

12                 (Exhibit No. 155 marked for identification.)

13                 MR. BREW:  And your short title, if I may,

14       would be EPA Analysis of HR 2454, June 2009.

15                 MR. WALLS:  If I could just clarify that this

16       is an excerpt of a larger document?

17                 MR. BREW:  That's correct.

18                 MR. WALLS:  Do you happen to know what the

19       total pages are of the larger document?

20                 MR. BREW:  I can get the entire document for

21       you.  It's around 30 pages.  I was trying to save trees.

22                 MR. WALLS:  Understood.

23                 CHAIRMAN CARTER:  You may proceed.

24                 THE WITNESS:  Am I looking at the correct

25       document here?

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2097

1       BY MR. BREW:

2            Q    That's it, yes.

3                 Now, Mr. Lyash, are you aware that the U.S.

4       House of Representative approved -- passed the American

5       Clean Energy and Security Act of 2009 in June of this

6       year?

7            A    Yes, I am, they did pass that by one vote.

8            Q    Yes, indeed.

9            A    Remarkable.

10            Q    And that's HR 54.  So that's currently the

11       Bill that's passed the House of Representatives, is that

12       right?

13            A    That's correct.

14            Q    And the document that I have handed to you is

15       a summary of the -- an analysis of that bill that was

16       performed by the Environmental Protection Agency, do you

17       see that?

18            A    Yes, I do.

19            Q    And if I can refer you to what is I think the

20       third page of this document that's labeled 25 in the

21       lower right-hand corner?

22            A    Yes.

23            Q    And the title of that sheet is labeled Offset

24       and Allowance Prices, do you see that?

25            A    Yes.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2098

1            Q    Since I've circulated this in color, it shows

2       scene 2, which is Allowance Price, in green on the

3       chart?

4            A    Uh-huh.

5            Q    And if you look at that, would you agree with

6       me that through the year 2030, allowance prices are not

7       expected to exceed $30 a ton in 2005 dollars?

8            A    Yes, that's what this graph depicts.

9            Q    So that would be the EPA's assessment of the

10       bill as passed, is that right?

11            A    I'll take you at your word.  I'm unfamiliar

12       with the document.

13            Q    So for the emission allowances that you

14       employed on page 13 of 23, at 2030 under the column

15       Lieberman-Warner, you show a cost of $158 a ton, is that

16       right?

17            A    That's correct.

18            Q    And under the MIT CO version, it was $117 a

19       ton?

20            A    Yes.

21            Q    And then the EPA old version from last year

22       was $63 a ton?

23            A    Yes.

24            Q    And then the EBS study was $42 a ton?

25            A    Correct.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2099

1            Q    Okay.  Is there a bill called Lieberman-Warner

2       that's currently pending in front of the U.S. Congress?

3            A    No, I don't believe there is.

4            Q    Okay, so a current update of what Congress is

5       intending on climate change and the cost of carbon

6       trading is more accurately reflected in the EPA analysis

7       than in the values that you've used from last year's

8       need case, would you agree with me?

9            A    No, I wouldn't.

10            Q    Because?

11            A    Well, first I'd like to say that I'm not at

12       all convinced, and neither are most folks watching the

13       process, that the Waxman-Markey bill at the end of the

14       day will be the one that passes.  It passed the House of

15       Representatives by one vote.  There are significant

16       issues that all parties engaged have with the bill.

17       There is nothing at the present time moving in the

18       Senate in support of it.  So although I think you could

19       get a wide range of views on this, I'm not convinced

20       that Waxman-Markey in fact represents the long-term

21       carbon policy.

22                 The second is that even with the Waxman-Markey

23       bill, while EPA has their estimate of what carbon

24       pricing would do, this is one estimate of that behavior.

25       There are a multitude of other investments.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2100

1                 The third point that I'd make is that if the

2       country's objective as stated is to, in fact, reduce

3       carbon emissions over time, I think the general

4       consensus, and certainly as an example what came out of

5       the EPRI MERGE analysis, would say that carbon pricing

6       would likely have to be driven much higher than this to

7       positively impact carbon.

8                 So while I would agree with you that

9       Waxman-Markey and that EPA's assessment of Waxman-Markey

10       indicate lower carbon prices than we have here, I

11       wouldn't be able to conclude from that that this in fact

12       is more representative of the likely outcome than a

13       range of other alternatives.

14            Q    Okay.  Let's start from the premise that it is

15       the House bill and that there are changes to come as

16       this debate unfolds.  Would you agree with me that in

17       the Waxman-Markey bill, 35 percent of allowances are

18       initially allocated for free to the electric industry to

19       mitigate the rate impacts on consumers of implementing

20       the cap and trade program?

21            A    Yes, that is in the bill, I agree.

22            Q    And so to the extent that allowances are

23       allocated to utilities to mitigate the rate impacts on

24       consumers, that would affect the cost-benefit analysis

25       for this plant?

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2101

1            A    Yes, certainly the split between allocation

2       and auction is an important piece of this legislation.

3            Q    And another important piece would be whether

4       or not to allow offsets as a way of complying with the

5       statute, is that right?

6            A    That's a piece of it, and, in fact, that's a

7       very controversial piece, that, my opinion, is unlikely

8       to be preserved, but that's my opinion.

9            Q    But you would agree that the inclusion of

10       offsets in Waxman-Markey was another piece of that bill

11       designed to keep the cost of compliance down while

12       actually achieving lower emissions?

13            A    Yes, I would agree that it's the intent.  I'm

14       not sure that it will be implemented, or that in the end

15       it will be cost-effective.

16            Q    But would you agree with me that both of these

17       features were included in the Waxman-Markey bill for the

18       express purpose of mitigating the cost of compliance on

19       the U.S. economy?

20            A    I would agree that that's part of the reason.

21       I don't think that's probably the entire reason.

22            Q    Okay.  In your exhibit, moving back to page 16

23       of 23, you provide -- you have a series of pages

24       providing your updated long-term fuel forecast, and 16

25       of 23 is the mid-reference fuel table?

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2102

1            A    I'm sorry, let me get to where you are first.

2            Q    Okay.  Take your time.

3            A    16 of 23, this is a mid-reference fuel

4       table --

5            Q    The mid-reference fuel table, that's right.

6       Hold that page, but back on page 33 of your rebuttal

7       testimony, line 17, you say the company used its updated

8       fuel forecast?

9            A    What page?

10            Q    I'm sorry for jumping.  It's page 33, line 17.

11       It says, "The company used its updated fuel forecast."

12       Do you see that?

13            A    Yes.

14            Q    In reference to the mid-reference fuel

15       forecast, is that a Progress long-range fuel forecast?

16            A    Yes.  We have -- as a matter of process and

17       routine, we update our fuel forecast.  In developing

18       that updated fuel forecast, we use a wide range of

19       industry projections to develop that that have proved to

20       be fairly reliable for us over the long term, and

21       incorporate those against our system.  So this is a

22       specific Progress Energy fuel forecast, but based on a

23       fairly well-established and accepted industry approach

24       to doing such estimates.

25            Q    So this is not a Nimax forecast or an Energy

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2103

1       Information forecast, this is a Progress Energy

2       forecast?

3            A    This is -- as required, this must be a

4       Progress Energy-specific fuel forecast, because it

5       applies to the availability of these fuels in Florida.

6       We don't really have indigenous fuel supplies, so we've

7       got to get them on the market and get transportation to

8       get them here.  But it's based on independent, industry

9       accepted, forward fuel pricing, multiple inputs, in

10       order to develop that.  It's not something we develop

11       entirely on our own.

12            Q    But if I compare the numbers that you

13       developed in this forecast on your exhibit with what Mr.

14       Miller filed in his direct, would you agree with me that

15       through the year 2022, the gas prices in your forecast

16       are consistently lower than what Mr. Miller filed back

17       in May?

18            A    Well, I don't have Mr. Miller's in front of

19       me.  I can say that what Mr. Miller filed in May was

20       based on our then-fuel forecast, and when requested in

21       the interrogatory to provide this information, we did

22       not do a special fuel forecast for this.  We updated

23       this to reflect the fuel forecast that we had produced

24       as a matter of course in the interim.

25            Q    I'm focusing on what you got to, not how you

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2104

1       got there.  Would you agree that the forecasts shown on

2       your mid-reference forecast don't consistently exceed

3       the fuel table for Mr. Miller's exhibit until the year

4       2030 and beyond?

5            A    I don't have Mr. Miller's exhibit in front of

6       me.

7            Q    Okay.  But if you were to compare the two, it

8       would show that basically you show lower fuel prices for

9       the first 12 years and higher fuel prices from year 2030

10       and on out?

11            A    I don't have Mr. Miller's forecast, so I can't

12       confirm or deny your assertion.

13                 (Brief pause.)

14       BY MR. BREW:

15            Q    Do you have Mr. Miller's exhibit now?

16            A    Yes, I have this exhibit.

17            Q    That would be his Exhibit GM-1, and I was

18       showing you the gas portion of that, which is page 2 of

19       2.

20            A    Uh-huh.

21            Q    So would you agree with me that from 2009 to

22       2021, the prices shown on your forecast are lower in all

23       those years than in Mr. Miller's forecast in May?

24            A    Excuse me, I'm just taking a minute to look at

25       it.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2105

1            Q    Sure.

2            A    Yes, and again, I'm not quite as familiar with

3       Mr. Miller's GM-1 and exactly what this table represents

4       with respect to notions of fuel price, but I would say

5       that this mid-reference fuel table that's in the

6       interrogatory response generally shows lower fuel prices

7       in the early years for gas and higher for distillate.

8            Q    And higher for what?

9            A    In some cases, a little higher for distillate.

10            Q    And just sticking to the gas cost, it shows

11       higher -- your exhibit shows higher gas prices in years

12       2030 and beyond?

13            A    The two forecasts appear to converge as you go

14       out in time, but slightly higher in the mid-reference

15       fuel case in response to the interrogatory.

16            Q    Okay, thanks.

17            A    I might add that, just having reflected on

18       it --

19            Q    Wait a second.  I would rather that you waited

20       for a question rather than just sort of adding.

21                 Thank you, Mr. Lyash, that's all I have.

22                 CHAIRMAN CARTER:  Mr. Davis?

23                 MR. DAVIS:  Yes, Mr. Chair, I'll try to be

24       brief because Mr. Brew covered some of the questions I

25       was going to ask.

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2106

1                          CROSS EXAMINATION

2       BY MR. DAVIS:

3            Q    Good evening, Mr. Lyash.

4            A    Good evening.

5            Q    And I will try not to keep you too long.

6                 First of all, you're not a lawyer, right?

7            A    That's correct.

8            Q    And I'm not saying that as if it's a big deal

9       to be a lawyer, but --

10            A    No offense taken.

11            Q    Actually, my parents didn't want me to be a

12       lawyer, so there you go, but I play one on TV.

13                 The reason I asked you that question is you

14       have made certain recommendations or certain statements

15       in your testimony to the Commission about how they

16       should interpret their rule on determining long-term

17       feasibility of the Levy 1 and 2 project, right?

18            A    I have made statements about how we interpret

19       the requirement for long-term feasibility and how we

20       view that.  The Commission is certainly in a position to

21       make a decision as they see fit.

22            Q    So you're not suggesting that you have the

23       correct legal interpretation of that term, long-term

24       feasibility?

25            A    I would never presume to do the Commission's

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2107

1       business for them.  I would respectfully try to put

2       forward the information I think is relevant in their

3       decision.

4            Q    Okay.  And you were testifying about your

5       interpretation of long-term feasibility from the

6       standpoint of a corporate executive of Progress Energy,

7       correct?

8            A    Yes, and to the extent that our own legal

9       staff has reviewed the requirement and discussed with me

10       how our legal department's view of that requirement

11       stands.

12            Q    And that was my next question, I appreciate

13       that.  So you were assisted by legal counsel in writing

14       your testimony on that point, correct?

15            A    Well, this -- now, this is my testimony, so

16       this represents my personal views and the views of the

17       company.

18            Q    After consulting with your legal counsel about

19       that?

20            A    I consult with my legal counsel daily as we go

21       through the course of business on this and every other

22       issue, so yes.

23            Q    So in other words, this is legal argument from

24       your legal counsel?

25            A    No, this is my testimony, and it represents my

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2108

1       views and the views of the company.

2            Q    Okay.  Well, let me just ask first of all with

3       regard to Levy 1 and 2, Progress wouldn't build those

4       units without the cost recovery provision in Florida

5       law, right?

6            A    Well, that's a hypothetical.  However, I would

7       tell you that without the legislation that was passed

8       and the rules that were implemented on alternative cost

9       recovery, I think constructing this plant would be

10       certainly more difficult and perhaps not possible.  I

11       personally couldn't recommend that we would proceed with

12       a project like this without that regulatory certainty

13       and financial support.

14            Q    As a matter of fact, on page 27 of your

15       testimony, line 14, you state, "Without such alternative

16       cost recovery mechanisms, the company would not have

17       embarked upon the development of nuclear power plants in

18       Florida"?

19            A    Correct.

20                 CHAIRMAN CARTER:  Get a little closer to the

21       mike, Mr. Davis.

22                 MR. DAVIS:  I apologize.  Usually my voice

23       carries without it.

24       BY MR. DAVIS:

25            Q    So you have provided an opinion that -- let me

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2109

1       make sure I'm not misinterpreting your opinion -- that

2       as a corporate manager, you don't believe that

3       feasibility includes an economic analysis?

4            A    No, what I said was I don't believe

5       feasibility includes the type of point estimate analysis

6       that's represented in this interrogatory.

7                 And I'm not saying that we wouldn't provide

8       this or that it isn't informative, but my position is

9       that that sort of an economic analysis on a recurring

10       basis annually is not something that we do for any major

11       capital investment, nuclear or non-nuclear, and it

12       should not be the test in this case, because it's

13       untenable, it's unimplementable.  What I did not say is

14       that total project cost and the impact of that on the

15       feasibility of the project should not be a

16       consideration.  I think it should.

17                 (Brief pause at 6:58 p.m.)

18                 (The transcript continues in sequence with

19       Volume 13.)

20

21

22

23

24

25

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491

2110

1                       CERTIFICATE OF REPORTER

2       STATE OF FLORIDA )

3       COUNTY OF LEON   )

4             I, CLARA C. ROTRUCK, do hereby certify that I was

5       authorized to and did stenographically report the

6       foregoing proceedings at the time and place herein

7       stated.

8             IT IS FURTHER CERTIFIED that the foregoing

9       transcript is a true record of my stenographic notes.

10             I FURTHER CERTIFY that I'm not a relative,

11       employee, attorney, or counsel of any of the parties,

12       nor am I a relative or employee of any of the parties'

13       attorney or counsel connected with the action, nor am I

14       financially interested in the action.

15             DATED this 11th day of September, 2009, at

16       Tallahassee, Leon County, Florida.

17

18

19

20

21               _______________________________________

22                          CLARA C. ROTRUCK

23

24

25

FOR THE RECORD TALLAHASSEE FLORIDA 850.222.5491