2111

1                              BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

3       In the Matter of:                DOCKET NO. 090009-EI

4       NUCLEAR COST RECOVERY CLAUSE.

______________________________/

5

6

7

8

9                              VOLUME 13

10                       Pages 2111 through 2178

11              ELECTRONIC VERSIONS OF THIS TRANSCRIPT ARE

A CONVENIENCE COPY ONLY AND ARE NOT

12               THE OFFICIAL TRANSCRIPT OF THE HEARING,

THE .PDF VERSION INCLUDES PREFILED TESTIMONY.

13

14       PROCEEDINGS:        HEARING

15       COMMISSIONERS

PARTICIPATING:      CHAIRMAN MATTHEW M. CARTER, II

16                           COMMISSIONER LISA POLAK EDGAR

COMMISSIONER KATRINA J. McMURRIAN

17                           COMMISSIONER NANCY ARGENZIANO

COMMISSIONER NATHAN A. SKOP

18

DATE:               Thursday, September 10, 2009

19

TIME:               Commenced at 9:30 a.m.

20                           Concluded at 8:26 p.m.

21       PLACE:              Betty Easley Conference Center

Room 148

22                           4075 Esplanade Way

Tallahassee, Florida

23

REPORTED BY:        JANE FAUROT, RPR

24                           Official FPSC Reporter

(850) 413-6732

25

PARTICIPATING:      (As heretofore noted.)

FLORIDA PUBLIC SERVICE COMMISSION

2112

1                              I N D E X

2                              WITNESSES

3

NAME:                                        PAGE NO.

4

JEFFREY LYASH

5

Cross Examination by Mr. Davis            2114

6              (Continued)

Cross Examination by Mr. Moyle            2135

7            Cross Examination by Mr. Rehwinkel        2156

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

2113

1                              EXHIBITS

2       NUMBER:                                   ID.   ADMTD.

3       156       Need Determination Study        2121   2174

4       128-129                                          2173

5       155

6       157       Levy Update                     2174   2174

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

2114

1                         P R O C E E D I N G S

2                 (Transcript follows in sequence from

3       Volume 12.)

4                     CONTINUED CROSS EXAMINATION

5       BY MR. DAVIS:

6            Q.   And I'm not going to go through the same

7       dialogue you had with Mr. Brew on that issue.  The

8       record will reflect that.  But you do agree that a point

9       analysis is a major decision point which is your need

10       assessment that is provided to the Commission and used

11       in the determination of need where you do the CPVRR

12       analysis for need.

13            A.   I'm sorry, I didn't get the question out of

14       that.

15            Q.   Maybe I didn't phrase it well enough.  Let me

16       try again.  That the need for Levy 1 and 2 was

17       determined at least in part based upon a one-time

18       cost-effectiveness analysis?

19            A.   Yes, there was a cumulative present value

20       revenue requirement analysis done in support of the need

21       case.  So, with respect to that I think your statement

22       is correct.  Although, again, it was a part of a broader

23       need case that I think the Commission considered in

24       granting that need.

25            Q.   But, it is certainly an economic analysis that

FLORIDA PUBLIC SERVICE COMMISSION

2115

1       the Commission relies upon in making a decision as to

2       need and that you as a company rely upon in going

3       forward with the project?

4            A.   Yes, it was an analysis that the Commission

5       relied in part on at the determination of need, and I

6       have no objection to incorporation of that analysis as a

7       significant part of a plant need determination.  My

8       objection is that to cycle that analysis based on

9       volatile -- and at the time the need was granted it was

10       with consideration of the long-term benefits, the

11       $92 billion worth of avoided fuel costs associated with

12       this plant over its lifetime.  And so I think that is

13       appropriate.

14                 My objection is that to use that as a test

15       year in and year out when we know that gas prices,

16       carbon prices, environmental costs, the economy as it

17       ebbs and flows will change.  If that is used as a

18       substantial part of the decision in a way that it bears

19       directly and significantly on feasibility, it will be

20       untenable.  It will place the Commission in a position

21       where I'm not sure how they will make a decision when

22       they see one set of numbers this month and six months

23       from now another set of numbers changes, and six months

24       later --

25            Q.   Well, your need determination is made as a

FLORIDA PUBLIC SERVICE COMMISSION

2116

1       snapshot, as well.  I mean, there is no difference

2       between a CPVRR analysis for your need determination

3       than one could be used for the feasibility

4       determination.

5            A.   Well, I don't agree with you.  I think there

6       is quite a difference.  This is what --

7            Q.   Let me stop you.

8                 MR. WALLS:  Objection.

9                 CHAIRMAN CARTER:  Let him finish.  Let him

10       finish, Mr. Davis.

11                 MR. DAVIS:  Okay.

12                 THE WITNESS:  The process for a need case I

13       think is clear and that is a required part of it.  I

14       don't think that implies that that necessarily means it

15       is a required piece of making a feasibility

16       determination, number one.

17                 Number two, the need determination is done at

18       a point where the project hasn't been substantially

19       embarked upon and there isn't substantial monetary

20       expenditures, engineering work, procurement.  And so I

21       think it is more appropriate to use that information to

22       decide whether to undertake a project, but not on an

23       annual basis to decide to continue a project that is

24       already underway progressing that has accumulated a

25       substantial set of effort and expense.

FLORIDA PUBLIC SERVICE COMMISSION

2117

1       BY MR. DAVIS:

2            Q.   Now, if you had wanted to, after the need

3       determination on Levy 1 and 2, you could have chosen,

4       meaning Progress could have chosen to proceed without

5       cost-recovery and there would have been no requirement

6       of demonstrating annual long-term feasibility.

7            A.   I can't answer your question.  I haven't

8       thought about it and gone back and read the legislation

9       and the need case to determine how it would apply in

10       that instance.

11            Q.   Well, if you will accept that I might know a

12       little bit about the law --

13            A.   We have established you are the lawyer and I

14       am not.

15            Q.   -- but I think the rule is pretty clear that

16       it only applies if you are seeking cost-recovery.  And

17       so, if you didn't want to demonstrate an annual

18       feasibility, you could forego the cost-recovery,

19       correct?

20            A.   I guess, yes, theoretically that is possible.

21       However, as we have already discussed, the cost-recovery

22       and prudence determination processes here are a critical

23       piece of actually executing the project.  So, as you

24       noted rightfully in my testimony, I don't believe we

25       could build this plant without them.  So that is not in

FLORIDA PUBLIC SERVICE COMMISSION

2118

1       effect an option.

2            Q.   But the decision with the cost-effectiveness

3       requirement is not whether or not you, Progress, would

4       build a plant, it is whether or not the Commission

5       determines that the ratepayers of Progress Energy are

6       being protected in terms of the long-term feasibility of

7       the project.

8            A.   I apologize, but I didn't get the subtlety of

9       the point or the question.

10            Q.   You keep answering the question from the

11       standpoint of a corporate decision-maker as to whether

12       or not to build the plant.  That is not the question

13       that the Commission is asking with long-term

14       feasibility.  It is a question of whether the ratepayers

15       are being protected by a decision to allow Progress to

16       continue to recover costs.

17                 MR. WALLS:  Objection, I didn't hear a

18       question in there.  It seems like he is testifying to

19       me.

20                 CHAIRMAN CARTER:  Tighten it up.  Tighten it

21       up, Mr. Davis.

22                 MR. DAVIS:  My question is isn't that correct?

23                 CHAIRMAN CARTER:  That's tight.

24       BY MR. DAVIS:

25            Q.   You do see the difference there, don't you?

FLORIDA PUBLIC SERVICE COMMISSION

2119

1            A.   I understand what you are saying, I am just

2       not sure how you would like me to respond here or what

3       the question is.

4            Q.   A yes or a no would be a way to --

5            A.   Well, no, I don't agree with you.

6            Q.   Okay.  Let's turn for a minute to your

7       exhibit, your JL-2.  And if you will turn to Page 6,

8       which is Table 1.

9            A.   I'm there.

10            Q.   If you look at the low fuel reference, you see

11       that under three scenarios, that the -- I'm sorry, this

12       is from the need determination docket, correct?  I meant

13       to turn to Table 2, which is Page 7.

14            A.   Table 1 is a summary of what was presented in

15       the need determination.

16            Q.   I understand that.

17            A.   Table 2 is the 20-month shift in the

18       in-service date.

19            Q.   Correct.  And if you look at the first column

20       at the top of Table 2, under low fuel reference, do you

21       see that?

22            A.   Yes.

23            Q.   Again, you say you are not relying upon the

24       CPVRR analysis for your feasibility filing here, but

25       there has been a lot of statements about the results in

FLORIDA PUBLIC SERVICE COMMISSION

2120

1       this table.  You see under the low fuel reference that

2       the Levy 1 and 2 project is not cost-effective for the

3       no CO2 scenario, the Bingaman-Specter, the EPA no CCS,

4       and MIT mid CO2, correct?

5            A.   Yes, I see that.  That is also the case in

6       the -- generically in the need case that was presented.

7       And as I recall from the need case, the conclusions of

8       those discussions was that really the low fuel and no

9       carbon case were not viewed in the long-term to be

10       credible or likely, and so the focus of the discussions,

11       at least in the need determination, was on the mid and

12       high fuel reference cases and on the range of scenarios

13       that regulated carbon.

14            Q.   But things have changed a little bit since

15       2008 with regard to natural gas prices, correct?

16            A.   Yes.  And I think things are likely to change

17       again by 2009, as is consistent with the history of

18       natural gas prices in the U.S.

19            Q.   While we are talking about natural gas, I do

20       have an exhibit I would like to ask you about because of

21       some statements that were made in your testimony.

22                 CHAIRMAN CARTER:  Do you need a number, Mr.

23       Davis?

24                 MR. DAVIS:  Yes, Mr. Chair.

25                 CHAIRMAN CARTER:  The number will be 156,

FLORIDA PUBLIC SERVICE COMMISSION

2121

1       Commissioners.  156.  A short title?

2                 MR. DAVIS:  A short title is need

3       determination.  I think that is what it is called.

4                 CHAIRMAN CARTER:  Need determination study?

5                 MR. DAVIS:  Yes, need determination study.

6       Thank you.

7                 (Exhibit Number 156 marked for

8       identification.)

9                 CHAIRMAN CARTER:  Thank you.  One second.

10       BY MR. DAVIS:

11            Q.   Mr. Lyash, what I presented to you as

12       Exhibit 156 is an excerpt from the Progress Energy

13       Florida petition for need for Levy 1 and 2, the need

14       determination study.  Do you recognize this?

15            A.   Not specifically, but I'm sure that is the

16       source.

17            Q.   And you testified in that proceeding?

18            A.   I did, correct.

19            Q.   And if you look at the page excerpted as Page

20       52 and 53 at the bottom, you have testified in your

21       rebuttal testimony that intervenors should not have

22       relied upon the NYMEX futures gas price as an analysis

23       of future natural gas prices.  Do you recall that

24       testimony?

25            A.   Yes.  I think I testified that they should not

FLORIDA PUBLIC SERVICE COMMISSION

2122

1       rely solely or principally on the NYMEX futures market

2       prices.

3            Q.   And you described -- and, I'm sorry, but the

4       person who authored this need determination study for

5       and on behalf of Progress describes at the bottom of

6       Page 52 and the top of Page 53 the process that Progress

7       uses to project natural gas prices, correct?

8            A.   Yes.

9            Q.   And if you look at the top of Page 53, there

10       is a statement that the way that Progress does this is

11       to compare with other electric utility industry and fuel

12       market information that might include NYMEX futures

13       market prices, correct?

14            A.   It might -- yes, it might as a portion of that

15       assessment.

16            Q.   So, it is not out of the ordinary for a

17       natural gas analyst to compare their projections to the

18       NYMEX futures market prices, correct?

19            A.   No, it is not out of the ordinary for our fuel

20       forecasters to potentially include NYMEX future prices.

21       However, if you read this entire description, what we

22       are saying here is that we take fuel forecasts provided

23       by PIRA, Global Insight.  We also look at other electric

24       utility industry information, fuel market information

25       that might include NYMEX, current contracts, current

FLORIDA PUBLIC SERVICE COMMISSION

2123

1       market data, and we use our long-term professional

2       judgment, and we have a full-time group of folks who

3       produce these forecasts to make sure what we are

4       producing is accurate and balanced.

5                 So, I would agree with you that me might use

6       NYMEX futures in that assessment, by I would also tell

7       you we wouldn't rely principally or solely on NYMEX

8       futures to make that decision.

9            Q.   And did you review Doctor Cooper's testimony

10       and his exhibit about the future gas prices?

11            A.   Yes, I did in a cursory manner.

12            Q.   And he compared NYMEX futures to other sources

13       of future projections for gas prices and concluded NYMEX

14       was a good predictor.

15            A.   I don't agree with his conclusion and neither

16       do our fuel forecasters.

17            Q.   But they do compare their forecasts to NYMEX

18       futures, correct?

19            A.   They did and have in producing our gas

20       forecasts.

21                 MR. DAVIS:  I have got another exhibit and

22       this one is a confidential one.  It shouldn't take too

23       long to do this, I don't think.

24                 CHAIRMAN CARTER:  Hang on a sec.  Are we going

25       to be trying to enter this or what is the plan?  Just

FLORIDA PUBLIC SERVICE COMMISSION

2124

1       for examination purposes?

2                 MR. DAVIS:  It is, and it will be very short.

3                 CHAIRMAN CARTER:  All right.  Let's let

4       everyone get a keep first.

5                 MR. DAVIS:  This is the one I intended to

6       start with.

7                 CHAIRMAN CARTER:  Mr. Davis, on this, are you

8       going to use it for examination?

9                 MR. DAVIS:  Yes, I am.  Just very, very quick.

10                 CHAIRMAN CARTER:  Just for cross-examination,

11       so we don't need a number, right?

12                 MR. DAVIS:  Only cross-examination.

13                 CHAIRMAN CARTER:  You're recognized.

14                 MR. DAVIS:  And this would be Exhibit 157 for

15       cross purposes.  You are saying that we are not entering

16       it.

17                 CHAIRMAN CARTER:  If you are going to use it

18       just for cross-examination, I won't give you a number.

19                 MR. DAVIS:  I appreciate that, Mr. Chair.

20       That is what I wanted to do.

21                 CHAIRMAN CARTER:  Okay.  You may proceed.

22       BY MR. DAVIS:

23            Q.   Mr. Lyash, I have consulted with your

24       attorneys about how to protect any confidential

25       information.  You should be looking at the one-pager

FLORIDA PUBLIC SERVICE COMMISSION

2125

1       there.

2            A.   Uh-huh.

3            Q.   And I will just represent to you that this was

4       a response to a production request from PCS and the

5       request -- and I will state it precisely.  The request

6       was please provide copies of all fuel price studies,

7       forecasts, surveys, and related documents that PEF

8       reviewed or relied upon in preparing the updated fuel

9       forecast shown on Miller Exhibit GM-1.  And this is one

10       of those documents produced in response to that request.

11                 Without reviewing any confidential

12       information, isn't it true that this document mentions

13       that Progress does rely upon NYMEX prices for its future

14       projections of natural gas prices?

15            A.   No, I wouldn't characterize it that way.  It

16       certainly indicates that we considered NYMEX as an

17       element of producing a natural gas forecast, which I

18       think is consistent with what I said.  I don't see

19       anything here that tells me rely on that as our proxy.

20            Q.   Okay.  And I would represent to you that this

21       is the only document produced in response to Request

22       Number 18 referring to natural gas prices.  So is there

23       anything in this document that tells you that other --

24       and without revealing any confidential information --

25       that other numbers or future projections other than

FLORIDA PUBLIC SERVICE COMMISSION

2126

1       NYMEX were relied upon?

2            A.   No, but I don't think that implies that we

3       rely on NYMEX.  We have a process for estimating forward

4       fuel prices, which I think the Commission is quite

5       familiar with and I believe historically the staff has

6       evaluated.  I think that comes into play in the fuel

7       docket on an annual basis.  So, I think it is apparent

8       at least -- let me preface that by saying I don't run

9       the fuels department.  I am familiar with the fuels

10       because it is a significant cost and we try to manage it

11       prudently, but I would agree with you that the only item

12       mentioned here is NYMEX, but I wouldn't agree with the

13       implication that, therefore, NYMEX is what we use as our

14       proxy.

15            Q.   And I'm not trying to establish that.  I am

16       just trying to establish you do rely upon it.  Now, if

17       you will turn, please, to the next exhibit that we

18       provided.  This one has also been stamped confidential,

19       and I'm not going to ask you to reveal any confidential

20       information here.

21                 MR. BURNETT:  Mr. Chair, I'm sorry, if I may

22       just to help Mr. Davis.  I reviewed the next one that is

23       titled Levy update for June 17th, 2009 SMC.  The

24       portions that he is included can be now publicly spoken

25       about, so there is no reason to maintain confidentiality

FLORIDA PUBLIC SERVICE COMMISSION

2127

1       of those excerpts.

2                 MR. DAVIS:  Okay.  I appreciate that.  Thank

3       you.

4       BY MR. DAVIS:

5            Q.   Mr. Lyash, if you will turn to -- well, first

6       of all, the cover page says Levy update for SMC meeting

7       on June 17th, 2009.  What is the SMC meeting, do you

8       know?

9            A.   SMC stands for Senior Management Committee.

10       The Senior Management Committee meets at least weekly

11       and oftentimes more frequently.  It is comprised of the

12       senior officers of the company where we discuss on an

13       ongoing basis the full range of company operations.

14            Q.   And were you at this particular meeting on

15       June 17th?

16            A.   I can't recall specifically.  Normally, I

17       would be.  I would have to see if I can determine

18       whether I was at this particular one.

19            Q.   On the third page of this document, it has

20       economic views and --

21            A.   I'm sorry, are you talking about Page 6?  I

22       have got a lot of missing pages here.  Page 6 is the

23       one you are referring to?

24            Q.   This is an excerpt, and the third page is

25       numbered as Page 6.

FLORIDA PUBLIC SERVICE COMMISSION

2128

1            A.   Uh-huh.

2            Q.   And just so we have the context, this is a

3       discussion of whether to proceed with Levy or how to

4       proceed with Levy, is that correct?

5            A.   No, not necessarily.  In SMC, we do periodic

6       updates on a range of projects and contemporary issues.

7       So this may or may not have involved a decision related

8       to Levy.  It may have just been an informational

9       session.

10            Q.   Is it about Levy, however, right?  Levy update

11       is the name of it.

12            A.   Oh, yes.  This portion of the presentation is

13       an update on Levy.  Your question was did it -- was it

14       related to a decision that SMC was making regarding

15       Levy, and my response was no, not necessarily.

16            Q.   Okay.  Well, the third page I referred to is

17       entitled economic views.  And the first number over,

18       entire life, CPVRR methodology.

19            A.   Yes.  That is what the document says.

20            Q.   That is something that you were considering

21       from an economic standpoint for your own

22       decision-making, correct?

23            A.   No.  I would read this as a set of topics that

24       we are going to review.  And on the next page, if I read

25       this correctly is the CPVRR that was used during the

FLORIDA PUBLIC SERVICE COMMISSION

2129

1       need proceeding.  And so, I would -- without recalling

2       this meeting specifically, I would say that this is just

3       refreshing the SMC on elements of the need case and what

4       was reflected in it.  Not that we would be redoing this

5       or using it on an ongoing basis.

6            Q.   Well, why would you be doing that a year after

7       the need determination?

8            A.   Why would we be doing a year after the need

9       determination.  Well, this is an important project to

10       the company, and this is a -- as you have already

11       pointed out, an element of the need determination, and

12       we are proceeding through the phases of the project,

13       including this activity that we are engaged in today.

14       So I'm not sure that a reminder of these things, which

15       is what was the CPVRR in the need case, what -- how does

16       the nuclear cost-recovery clause behave based on that;

17       how are our retail prices in comparison statewide,

18       locally; what are the full economic impacts that flowed

19       from that.  That is a range of topics.  I think it would

20       be appropriate to reground periodically the senior

21       management team in where we started as part of the

22       discussion of where we are going.

23            Q.   And that is what the Commission is being asked

24       to do in this case.

25            A.   The Commission has access to this same CPVRR.

FLORIDA PUBLIC SERVICE COMMISSION

2130

1       It is unchanged.

2            Q.   And you can update that periodically, though,

3       fairly easily, can you not?

4            A.   We don't update as a matter of course -- yes,

5       we can.  No, we don't.  As I have stated, we don't do it

6       as a matter of course.  But, in fact, we did it in

7       response to the interrogatory that the staff asks, and

8       so that demonstrates that we certainly can.

9            Q.   Now, going back to your updated CPVRR

10       analysis.  Do you know what population increase

11       projections you used in that?

12            A.   No, I don't specifically, and I am -- let me

13       clarify your term population increase.  In producing our

14       fuels forecast, and in updating our site plans, we

15       review economic data which reflects Florida population

16       and translate that into projected trends in our service

17       territory.  We use that along with a number of other

18       factors to project load growth, both energy and peak.

19       And so, those information are incorporated into the

20       forecasts and site plans that we file with the

21       Commission.

22            Q.   Well, if you look back at Exhibit 156, which

23       we have provided you previously, the need determination

24       study, on Page 44 it has the long-term economic and

25       demographic summary of information used in your need

FLORIDA PUBLIC SERVICE COMMISSION

2131

1       determination study, correct?

2            A.   Yes.  These on Page 44 are some of the inputs

3       that go into that study.

4            Q.   And the input with regard to the PEF service

5       area population in this case was a 1.6 percent annual

6       growth rate, correct?

7            A.   Yes, and that is translated into considering

8       the other factors here.  For example, personal income is

9       a significant factor in determining statistically what

10       customer behavior will look like that impacts energy

11       consumption and peak load growth.

12            Q.   And you also have real GDP annual growth,

13       employment annual growth, and you mentioned personal

14       income.  You would expect that those numbers would have

15       changed considerably since the 2008 need determination,

16       correct?

17            A.   Yes, they did change and are incorporated into

18       the forecast that we currently have.  By the way, this

19       discussion really sort of emphasizes why I think this

20       CPVRR approach is untenable, because these numbers have

21       changed in a year and a year from now as we sit here

22       they will have changed again as they likely will six

23       months from now.

24            Q.   Well, you are familiar, are you not, that some

25       economists think that this is a long-term slow down in

FLORIDA PUBLIC SERVICE COMMISSION

2132

1       the economy?

2            A.   Yes, and I am familiar with some who don't.

3            Q.   Well, and, you know, give me a one-handed

4       economist is the same.  And you rely upon the Bureau of

5       Economic and Business Research from the University of

6       Florida for your population growth data, do you not?

7            A.   Yes.  We rely on USF and a number of other

8       sources for economic data, population growth and others.

9            Q.   And are you familiar that BEBR, as they are

10       called, published a study in March of 2009, which is

11       probably more up-to-date than the one you used in your

12       projections?

13            A.   I'm not -- I can't say whether the one we used

14       reflects that or not.  But I will say that these

15       forecasts are updated routinely, and they incorporate

16       the latest economic data, and the latest forecast that

17       we did, which I think was in May, but that is subject to

18       check, in the May time frame was built into our forecast

19       and still supports the long-term need for Levy.

20            Q.   Well, not if you consider the low fuel cost

21       scenarios, right?  We don't need to go through that

22       again, because you verified that already.

23            A.   Yes, I think it is still supported even with

24       the low fuel cost scenarios.  And I think it is

25       supported, because as I said, these are long-term

FLORIDA PUBLIC SERVICE COMMISSION

2133

1       decisions that accumulate substantial benefits for the

2       customer in fuel costs, volatile in nature and rising

3       over time, but also accumulates substantial other

4       benefits.

5            Q.   Can you explain why FPL is showing a reduction

6       in summer peak in 2017 of 10 percent and Progress is

7       only showing a reduction of 2.6 percent?

8            A.   No, because I don't do FPL's fuel forecasts

9       and I'm not responsible -- or load forecasting.  I'm not

10       responsible for that.  I can say that our forecasts are

11       what they are, they are based on methods that we have

12       employed for decades, and retrospectively they are

13       fairly accurate.

14            Q.   Now, if you will turn to your testimony,

15       please.  And this is my next to last question.  Page 39,

16       Line 14.  And, actually I want to ask you about the

17       sentence starting on Line 17.  Rather, the company

18       monitors these additional factors and others for

19       fundamental changes in them that would require the

20       company to reconsider its decision that completion of

21       the Levy nuclear power plants is feeble.  And with

22       regard to how you do that analysis, and how you monitor

23       these factors, you have mentioned previously that Mr.

24       Miller's testimony is basically your analysis in a

25       qualitative fashion, is that right?

FLORIDA PUBLIC SERVICE COMMISSION

2134

1            A.   Yes.

2            Q.   And, then you state in this sentence that a

3       fundamental change is what you are looking for.  How do

4       you define fundamental?

5            A.   I don't think fundamental can be defined in

6       static terms.  I think you have got to monitor the

7       political, the regulatory, the technical landscape, as

8       well as societal issues.  And when a change takes place

9       that is clearly significant and lasting that would call

10       into question the long-term benefits of the project,

11       then that is the sort of change that is recognizable at

12       that point in time.

13                 I think it is impossible to set a definition

14       of that at the front end, because the economy and issues

15       are not static and there is just many, many moving parts

16       to this.  So, the point of my testimony here is that to

17       rely on these sort of short-term gas price fluctuations,

18       three dollars today, $14 a couple of years ago, three

19       dollars today, $14 next year, that is not a fundamental

20       change.  And, so, to use that as a test is not a tenable

21       approach.  However, at the same time if there is a shift

22       in cost that is so great and so impactful as to clearly

23       be a fundamental change, then we ought -- and challenge

24       the feasibility, then we ought to undertake that.

25            Q.   Is there such thing as a detailed qualitative

FLORIDA PUBLIC SERVICE COMMISSION

2135

1       analysis?

2            A.   Detailed qualitative -- is there such a thing.

3       I don't know.

4                 MR. DAVIS:  Thank you.

5                 CHAIRMAN CARTER:  That completes it, Mr.

6       Davis?

7                 MR. DAVIS:  Yes, sir.

8                 CHAIRMAN CARTER:  Mr. Moyle, you are

9       recognized.

10                 MR. MOYLE:  Thank you, Mr. Chairman.

11                          CROSS EXAMINATION

12       BY MR. MOYLE:

13            Q.   Mr. Lyash, good evening.  John Moyle on behalf

14       of FIPUG.  To stick with the baseball analogy, I have

15       changed from being clean up hitter to now I am the setup

16       man for Mr. Rehwinkel.  So, I am going to --

17            A.   I'm a Rays supporter.  We could use a good

18       setup man right now.

19            Q.   I am going to try to make a few points and ask

20       a few questions and take into consideration the lateness

21       of the hour.

22                 You were asked some questions about the

23       nuclear cost-recovery rule and you provided some

24       testimony on that.  You are familiar with that rule, you

25       have read it, correct?

FLORIDA PUBLIC SERVICE COMMISSION

2136

1            A.   Yes.

2            Q.   I told your counsel I was going to ask you a

3       couple of questions about it, and I think they were

4       going to give you a copy.

5            A.   Thank you.

6            Q.   And you clarified that you weren't suggesting

7       to the Commission necessarily how they should interpret

8       their rule, but you were sort of given some insights as

9       to how you currently interpret it, correct?

10            A.   Yes, that is all we can do.

11            Q.   Okay.  And you had said that you determine

12       long-term feasibility based on technological,

13       regulatory, and execution aspects of a project, isn't

14       that correct?

15            A.   Yes.

16            Q.   And I looked at the rule.  I couldn't find

17       regulatory and execution in there at all, and the only

18       reference on technological was a section up in the

19       definitions.  2H talks about cost associated with site

20       and technology selection.  I mean, the rule says what it

21       says, but you would agree with me that cost is more the

22       focus of this rule than things like technology,

23       regulatory, or execution, correct?

24            A.   No, I wouldn't agree with that.  I think the

25       notion of feasibility has to be considered in the

FLORIDA PUBLIC SERVICE COMMISSION

2137

1       overall context of the rule, and I think the overall

2       focus of the rule is to establish a framework to

3       encourage investment in technologies such as nuclear

4       power that have the type of long-term benefits that we

5       discussed.  So, while cost is certainly a part of it, I

6       wouldn't agree that that is the focus or the intent of

7       the rule.

8            Q.   Okay.  The title of the rule has cost in it,

9       correct?

10            A.   Cost recovery, yes.

11            Q.   Okay.  And in the definition section there is

12       a whole bunch of sections in there that define cost,

13       correct?

14            A.   Yes.

15            Q.   And this probably isn't fair, but have you

16       ever heard of a term in para materia?  Do you know what

17       that means?

18            A.   No.  It sounds like a legal term.

19            Q.   It's one of those Latin --

20            A.   I would prefer that we discuss engineering

21       terms.

22            Q.   -- and I think it means that you have got to

23       read things kind of in the overall context.  And I guess

24       it is still -- you would agree with me, given the fact

25       that you have been on staff at the NRC and have been in

FLORIDA PUBLIC SERVICE COMMISSION

2138

1       regulated environments, that rules when they are

2       interpreted and applied, that words should be given

3       their plain meaning, correct?

4            A.   Yes, within the overall intent of the

5       legislation or rule.

6            Q.   Okay.  And to the extent that a rule is clear

7       on its face, you really don't need to look for intent,

8       you would agree with that as well, correct?

9            A.   No, I think intent is always an important part

10       of understanding and applying any rule.

11            Q.   With respect to the long-term feasibility

12       section of the rule, the long-term feasibility section

13       of the Rule 5C5, it doesn't talk about technological,

14       regulatory, or execution aspects, does it?

15            A.   Which page are you on, just so I make sure I

16       get that?

17            Q.   Well, this is -- on my copy it is Page 2, but

18       the correct section of the rule is C5, 5C5.

19            A.   Okay.

20            Q.   Do you see that, by May 1 of each year?

21            A.   I do.

22            Q.   It doesn't use the words, technological,

23       regulatory, or execution in that portion of the Rule

24       5C5, does it?

25            A.   No.  It also doesn't use the term cost.  It

FLORIDA PUBLIC SERVICE COMMISSION

2139

1       sort of purposely, I think, uses the word long-term

2       feasibility.  So while it doesn't include technical, or

3       regulatory, or legal, or project management, or cost,

4       and I would view that as giving the fact that the cost

5       is not there as important a weight as if it had been

6       there.

7            Q.   You understand that the purpose of this

8       proceeding is for you to present evidence and convince

9       this Commission to permit you to recover costs from my

10       clients and others, correct?

11            A.   Yes, I do.

12            Q.   And I think you also indicated in response to

13       a previous question that you do agree that total project

14       costs are an important part of determining long-term

15       feasibility, correct?

16            A.   Yes.  Total project cost is certainly

17       important in that context.

18            Q.   All right.  Now, you spent ten-plus years at

19       the NRC, is that right?

20            A.   Nine.

21            Q.   And you have been with us most of the day

22       today, correct?

23            A.   Yes.

24            Q.   I found it interesting, Mr. John Frank, you

25       were here when he testified, correct?

FLORIDA PUBLIC SERVICE COMMISSION

2140

1            A.   Yes, I was.

2            Q.   And he spoke about the uprate project and the

3       need to stay close to the NRC, to go meet with them, to

4       find out what they are thinking.  The way he described

5       it he kind of had reasonable assurance that he was going

6       to get a thumbs up on his application even though it had

7       not been submitted.  You recall that, correct?

8            A.   Yes, I do.

9            Q.   Do you agree with his approach as he outlined

10       it in terms of saying it is prudent and reasonable to

11       stay close to the NRC and to try to understand what they

12       are thinking?

13            A.   Yes.  I not only agree with it, I believe very

14       strongly.  It was applied in the case of the Levy COL

15       and continues to be applied in that manner today.

16            Q.   And that would include having discussions and

17       conversations about key items in your project, correct?

18            A.   Yes.

19            Q.   Given his testimony and your answers, I am

20       puzzled by something that I wanted to draw to your

21       attention.  And before I do, there has been a lot of

22       conversation about the LWA and the EPC and the

23       interrelation between those two.  You would agree with

24       that, correct?

25            A.   I would certainly agree that this qualifies as

FLORIDA PUBLIC SERVICE COMMISSION

2141

1       a lot.

2            Q.   And would you also agree, and I think there

3       was some discussion about it, that the LWA was a key

4       component.  That it triggered certain actions to be

5       taken pursuant to the EPC?

6            A.   Yes.  I think the LWA is a critical milestone.

7       But it is no more or less critical than, for example,

8       the final environmental impact statement, or the final

9       safety evaluation report, or the license issuance, or

10       the site certification.  So, yes, I agree it is

11       significant, but I don't agree that it is more

12       significant than many others.

13            Q.   Okay.  The thing I want to draw your attention

14       to is found on Page 13, Line 6.  Would you just read

15       into the record for us, please, out loud the two

16       sentences that start on Line 6, I traveled?

17            A.   "I traveled to Washington to meet with the NRC

18       to explain that the company was prepared to execute the

19       EPC agreement for the LNP and to generally discuss the

20       company's COLA.  We did not specifically discuss the

21       LWA, but at no time in this meeting or in any of the

22       prior meetings with the NRC did the NRC ever inform us

23       that the NRC was not going to issue an LWA for the LNP

24       as the company requested."

25            Q.   And given your experience at the NRC, and in

FLORIDA PUBLIC SERVICE COMMISSION

2142

1       government, and in the regulatory world, you would agree

2       that given the previous testimony of your other witness,

3       that that was probably a topic that you should have

4       brought up when you traveled to Washington just before

5       the execution of the EPC contract to specifically say,

6       hey, this LWA is important.  Where are we on this, how

7       is it going, and try to get some information, you would

8       agree with that, would you not?

9            A.   Yes.  And as a matter of fact, I would tell

10       you that we had extensive discussions with the staff on

11       these things.  Let me point out that as I said --

12            Q.   Well, wait a minute.  Hold on.

13            A.   Can I answer the question?

14                 CHAIRMAN CARTER:  Let him finish.  You may

15       finish.

16                 THE WITNESS:  Yes.  The NRC typically when

17       they have an issue that is going to be impactful is very

18       plain about it.  That has been my experience with the

19       Commission and it is my experience today.  I think Mr.

20       Miller pointed out that where the NRC had concerns with

21       the notion of a partial EIS and supported the LWA, they

22       very clearly let us know that it was their view to

23       support that effort.  A full EIS would be required and

24       we ought to consider changing our plan, and we did.

25                 I viewed the LWA as important, but, frankly,

FLORIDA PUBLIC SERVICE COMMISSION

2143

1       no more important than the FEIS or the FSER or the COLA.

2       On many occasions I and the staff visited with technical

3       staff and senior management of the Commission to review

4       the status of the project, our expectations about the

5       schedule to make sure they were clear on what our plan

6       was, including prior to issuance of the COLA.  In my

7       drop in visits, I clearly talked to them about what our

8       schedule was and what reliance we placed on each of

9       these milestones, including the LWA.

10                 I had no particular reason to call out the LWA

11       specifically or separately from the rest of the schedule

12       because I had no reason to believe that there was an

13       issue particularly affecting that.  And at no time did

14       they voice a concern to me about their ability to

15       meet -- generally meet our schedule, but certainly not

16       specifically related to a -- when I heard it, it was a

17       shocking decision about LWA taking the same timeline as

18       the license.

19            Q.   Who did you go to Washington with for this

20       trip?

21            A.   For this particular trip?

22            Q.   Yes, sir, the one that is referenced on --

23            A.   I believe that involved Jim Scarola, our chief

24       nuclear officer, and Bill Johnson, the president of our

25       holding company.  But I also had other interactions

FLORIDA PUBLIC SERVICE COMMISSION

2144

1       beyond this with the staff over the months leading up to

2       it.

3            Q.   Yes, sir.  And what I want to do is talk about

4       the trip that you reference in your testimony just

5       before the execution of the EPC.  I appreciate you

6       telling me about the other trips.  The one I want to

7       spend a minute focusing on is the one that you and Mr.

8       Johnson and Mr. Scarola went to.  All three of you all

9       are senior management with the company, correct?

10            A.   Correct.

11            Q.   And is it your testimony that going up there

12       meeting with Commissioners and staff during the course

13       of those meetings you did not bring up once the status

14       of the LWA?

15            A.   No, I wouldn't agree with that

16       characterization.  We brought up the overall status of

17       the project, what our expectation was for milestone

18       reviews, meaning FEIS, LWA, FSER, COLA issuance.  As

19       well as other issues related to completion of the LSAB

20       hearings, schedules for admission of contentions,

21       contested hearings that might flow from that, as well as

22       generic industry events, design certification document

23       Rev 17 review, our COLA, et cetera.  So we talked about

24       that full range of issues to make sure that we

25       understood that the Commission understood that the

FLORIDA PUBLIC SERVICE COMMISSION

2145

1       actions we were taking and the decisions we were making.

2       And that if they had concerns with those, we would have

3       expected them to put those concerns forward.

4                 And, in fact, we did talk about some concerns.

5       Concerns related to the DCD process, concerns related to

6       the progress on the reference COLA.  And there was not a

7       particular boring in on the LWA in isolation because it

8       did not stand out for us above any one of a number of

9       other milestones that would have to be met to keep the

10       project on this schedule.

11            Q.   So, you just told me you talked about a lot of

12       things in that meeting when you, and Mr. Johnson, and

13       Mr. Scarola went up there, but isn't it true that one of

14       the things you did not specifically discuss was the LWA?

15       If you can answer yes or no, I would appreciate it.

16            A.   No, that is not true.

17            Q.   So how do I read your statement on Line 8, "We

18       did not specifically discuss the LWA."  Is that

19       incorrect?

20            A.   Well, let me explain my answer.  We discussed

21       the LWA in the context of the overall licensing

22       activity, but if your question is did you specifically

23       bore in on whether an LWA would be issued by a

24       particular date and put that question in that succinct

25       form to the Commission, no, we did not.

FLORIDA PUBLIC SERVICE COMMISSION

2146

1            Q.   Wouldn't you agree that generally in

2       interacting with regulatory entities, whether it be the

3       Florida Public Service Commission, or DEP, or another

4       entity, that typically the applicant or the petition

5       seeking relief from the governmental agency puts issues

6       on the table that they would like to discuss?

7            A.   Yes, and I think this is a two-way street.  I

8       would expect in my experiences that state agencies like

9       the DEP, the PSC, and federal agencies like the NRC

10       would do the same.

11            Q.   Let me direct your attention to Page 5,

12       Line 22.  And specifically you state on Line 22, "The

13       company never expected potential joint owners to sign a

14       joint ownership participation agreement before the EPC

15       agreement was executed."  Was that part of the reason

16       why you executed the EPC to increase your chances of

17       getting joint ownership?

18            A.   No, I wouldn't link those two in that manner.

19       They are certainly linked in that we didn't expect joint

20       owners to commit and sign a joint owners agreement, an

21       O&M agreement and make their capital contributions

22       without an EPC, but we would not move to sign an EPC

23       that we didn't think was ready and right just to

24       facilitate joint ownership discussions.

25            Q.   This contract amendment that needs to be

FLORIDA PUBLIC SERVICE COMMISSION

2147

1       negotiated as a result of the withdrawal of the LWA, you

2       would agree that that is a significant or material

3       portion of the EPC that needs to be renegotiated,

4       correct?

5            A.   Yes.  I think the contract change order and

6       amendment is certainly significant, but I want to make

7       sure everybody understands that the EPC contract is not

8       being renegotiated.  That is a fully executed contract

9       that sets terms and conditions.  There is a provision in

10       the contract to negotiate a change order and amendment,

11       and what we are doing currently is negotiating just that

12       change order and amendment, and in that context, yes, it

13       is significant.

14            Q.   And given the fact that that has not yet been

15       done, you wouldn't have any objection, would you, to

16       bringing that matter back before the Commission when you

17       nail down that amendment so that they could then

18       understand fully and more appropriately the cost, the

19       overall total cost of the project?

20            A.   No, I would expect during next year's

21       proceeding of this nature that we would address that

22       with the Commission.  And if that negotiation has some

23       item that arises that is impactful to the feasibility of

24       the project perhaps before.

25            Q.   But, in the meantime, you are saying put it

FLORIDA PUBLIC SERVICE COMMISSION

2148

1       off till next year, this year you are asking for $12

2       plus recovery from residents on 1,000 kilowatt hours,

3       correct?

4            A.   Yes, because I think the feasibility of this

5       plant still remains intact.  And not only that, but in

6       the response to the interrogatory with respect to the

7       outcome of this, we did a plus or minus up to 25 percent

8       on capital construction cost, which I think shows

9       clearly that the plant still -- even under that test

10       which I don't agree with -- economically feasible.

11            Q.   And that 25 percent worst-case scenario that

12       would add 4 billion-plus to it potentially?

13            A.   Not necessarily.  That particular case in the

14       analysis, yes.

15            Q.   Okay.  And just so we are clear on that, that

16       that is just a mathematical calculation, 25 percent of

17       17.2 billion, correct?

18            A.   That is correct.

19            Q.   Back on the joint owner point, you would

20       similarly agree that it is probably not likely for a

21       joint owner to sign on now while you have this material

22       significant outstanding issue related to the EPC yet to

23       be negotiated, correct?

24            A.   Yes, I think it is likely the joint owners

25       would want to wait until this change order is executed

FLORIDA PUBLIC SERVICE COMMISSION

2149

1       in order to execute the EPC agreement.

2            Q.   Do you agree that it makes sense to explore

3       strategic partnerships?

4            A.   Yes, I do.

5            Q.   Have you done that?

6            A.   Yes, we have.

7            Q.   But as we sit here today, you don't have any

8       letters of intent or agreements in that respect?

9            A.   No, we have no final commitment to the

10       project.  But, as we have said from the beginning, joint

11       ownership has significant advantages not only for our

12       company, but for our customers and the state.

13                 We have engaged in those discussions very

14       meaningfully with a range of partners, municipals,

15       co-ops, potential financial partners, and IOUs.  Those

16       discussions have progressed far and substantially, and

17       we have reached agreement with joint owners on a number

18       of aspects of the project, but we have not yet got to

19       final commitment from them.

20            Q.   You have had meaningful discussions with other

21       Florida based IOUs?

22            A.   We have reached out to the Florida IOUs to

23       determine whether they are interested in the project.

24            Q.   Have you had meaningful discussions or is it

25       preliminary?

FLORIDA PUBLIC SERVICE COMMISSION

2150

1            A.   I would prefer not to characterize the

2       particular state of any discussions because they are

3       confidential.

4            Q.   Okay.  You would agree that to the extent that

5       there could be a strategic partnership forged that that

6       may be a good thing for ratepayers to the extent that

7       economies of scale could be realized, correct?

8            A.   Yes.  I think the nature of these strategic

9       partnerships is to spread the risk, easing customer

10       price impact, and to engage a broader set of resources

11       in the project.  Those are the benefits, I think, that

12       accrue as a result of if we were to strike such an

13       alliance.

14                 MR. MOYLE:  Mr. Chairman, if you would just

15       give me a minute.

16                 CHAIRMAN CARTER:  Absolutely.

17       BY MR. MOYLE:

18            Q.   A couple of final lines, hopefully.  You were

19       here when Mr. Reed testified, an expert for FPL?

20            A.   No, I wasn't.

21            Q.   You were not?  Mr. Reed indicated he thought a

22       go slow approach and a decision not to execute an EPC

23       made more business sense.  I take it you would not agree

24       with that assessment?

25            A.   No, I wouldn't, but I'm not familiar with the

FLORIDA PUBLIC SERVICE COMMISSION

2151

1       basis for Mr. Reed's conclusion.  Perhaps it is the best

2       thing for FPL, I can only comment on what is best for

3       Progress Energy.  And in this case, we have a need for

4       the base load generation, and so moving at the pace that

5       we have and continue to move we think is the best

6       decision for us and our customers.

7            Q.   A couple of other final points.  Page 9,

8       Line 10.  You state that partially in response to this

9       question about negotiations and the need to sign the EPC

10       contract that the company had no reasonable ground to

11       stall the signing of the EPC agreement now that those

12       negotiations were complete.  Is it your testimony that

13       you do not believe uncertainty related to the LWA was a

14       valid reason to maybe put off the execution of the EPC

15       for a period of time?

16            A.   I'm not sure whether my answer is yes or no

17       here because I can't think of the structure of the

18       question.  But, I think it certainly would have been

19       something that might have been an issue for us, although

20       we had no reason to delay executing the EPC, but it was

21       not an issue that the consortium would have taken into

22       consideration.

23                 We have been negotiating with these folks for

24       two years consistently and constantly.  Those

25       negotiations had moved to the point where all of the

FLORIDA PUBLIC SERVICE COMMISSION

2152

1       issues had been resolved with respect to the EPC and we

2       had captured significant value for our shareholders and

3       our customers in that contract.  And so there really was

4       no more negotiations to be done on the contract.

5            Q.   Sir, in response to a question from Mr. Brew,

6       I thought you had said that you had not yet made a

7       decision to move forward with Levy, is that correct?

8            A.   No, I didn't it in exactly that context.  What

9       I said was that we have committed to the project and our

10       intention is to build the project.  And we have made

11       decisions all the way along the way to take the next

12       step and execute the next milestone, but that we would,

13       as we have done consistently evaluate whether

14       continuation of the project and commitment to the next

15       step is warranted.  And so we have done that all the way

16       along the way and we did that after careful

17       consideration with respect to executing the EPC

18       contract.

19            Q.   Maybe I wrote it down wrong.  If a decision

20       has not been made to move forward with the project, you

21       would agree it probably wouldn't make sense to execute

22       an EPC contract, correct?  I mean, that is a big

23       significant contract where you commit a lot and off you

24       go, correct?

25            A.   Yes, it is certainly a big decision and it is

FLORIDA PUBLIC SERVICE COMMISSION

2153

1       a significant step and it is a decision not to be taken

2       lightly.  I think maybe this is a matter of semantics.

3       I don't believe you are suggesting that we should make a

4       decision at a point in time to build the plant and then

5       not constantly reevaluate that and make a sequence of

6       decisions to continue the project.  That would not be

7       the way any reasonable manager would manage such an

8       undertaking.

9            Q.   And I think given our conversation we are in

10       agreement that with respect to making an evaluation that

11       your company has to make an evaluation that costs are an

12       important component of that, just like this Commission

13       has to make an evaluation and costs are an important

14       component of that, correct?

15            A.   Yes.

16            Q.   And, finally, a little bit on the contract

17       negotiations.  Did you negotiate, were you at the table

18       on any of these discussions?

19            A.   Yes.

20            Q.   Okay.  And is it fair to ask you who -- you

21       know, a lot of times in negotiations one party has kind

22       of a higher ground or more leverage in the negotiations.

23       Who had the higher ground or the leverage in the

24       negotiations with Westinghouse?

25            A.   I don't know that you can characterize this as

FLORIDA PUBLIC SERVICE COMMISSION

2154

1       one party having higher ground than the other.  I was

2       involved in these negotiations for the entire duration

3       of the negotiations up to and including execution of the

4       EPC contract, which has my signature on it.

5                 Neither party would I consider to have higher

6       ground or more leverage.  We come from different places

7       and we negotiate the terms and conditions of the

8       contract from different perspectives, but at the end of

9       the day, I think what we got here is an EPC contract

10       that captures significant value for our customers.

11            Q.   So my impression that you all have 17 billion

12       allocated for a nuclear project, have money to spend,

13       that led me to believe that you all had probably a

14       better negotiating position as compared to a vendor who

15       had a product that the vendor wished to sell, is that

16       correct?

17                 MR. WALLS:  Objection, asked and answered.

18                 CHAIRMAN CARTER:  To the objection.

19                 MR. MOYLE:  I think it is following up on his

20       answer on a clarifying point.

21                 CHAIRMAN CARTER:  Ms. Helton.

22                 MS. HELTON:  I'm having a hard time

23       distinguishing how Mr. Moyle's question that he just

24       asked is different from the leverage question that he

25       asked before which the witness answered.

FLORIDA PUBLIC SERVICE COMMISSION

2155

1                 CHAIRMAN CARTER:  Okay.  Sustained.  Move on.

2       BY MR. MOYLE:

3            Q.   Let me refer you to your testimony on Page 9,

4       again.  These are on the contract discussions, and this

5       is in a confidential section, so I am going to try to

6       tread lightly.

7                 Do you see on Line 17 where it talks about the

8       consortium's decision?

9            A.   Yes.

10            Q.   And then there is an infinitive after that, do

11       you see that?

12            A.   Uh-huh.

13            Q.   That is overstated, is it not?  I mean, that

14       word used in there, that wasn't something that you all

15       had to do?

16            A.   Which word are you referring to?  Perhaps I'm

17       not sure of the word.

18            Q.   To require?

19                 CHAIRMAN CARTER:  I think on the confidential,

20       Mr. Moyle, it is okay to talk about what number a word

21       in the sentence it is, because it is confidential.  So

22       let's stay focused.

23       BY MR. MOYLE:

24            Q.   Do you see that?

25            A.   No, I don't think it is overstated when taken

FLORIDA PUBLIC SERVICE COMMISSION

2156

1       in the context of the last six words in the sentence.

2                 MR. MOYLE:  Thank you for your time.

3                 CHAIRMAN CARTER:  Mr. Rehwinkel.

4                 MR. REHWINKEL:  Thank you, Mr. Chairman.

5                          CROSS EXAMINATION

6       BY MR. REHWINKEL:

7            Q.   Good evening, Mr. Lyash.

8            A.   Good evening.

9            Q.   Hopefully good night shortly.  I heard a hear

10       hear back there.

11                 Well, I know you have heard enough about

12       feasibility and you are eager to talk about prudence in

13       the LWA, so I will ask a few questions about that.  I

14       actually would like to follow up on the question that

15       Mr. Moyle asked you about the meeting in Washington that

16       you attended with Mr. Scarola and Mr. Johnson.  Do you

17       recall those questions?

18            A.   Yes.

19            Q.   And I think your testimony is, and this is on

20       Page 13, starting on Line 6, that this was immediately

21       prior to the execution of the EPC agreement?

22            A.   Yes.

23            Q.   So what does that mean, is it sometime in late

24       December, or sometime in December?

25            A.   Yes.  This would have -- I'm sorry, I can't

FLORIDA PUBLIC SERVICE COMMISSION

2157

1       precisely put a date on it, but this would have been in

2       the November or early December time frame.

3            Q.   Okay.  And your testimony was that you did not

4       separate the LWA from the rest of the COLA, and there

5       were questions or the inquiries you made to the NRC

6       staff regarding their decisions or their inclination

7       about your schedule, is that correct?

8            A.   That is correct.

9            Q.   Isn't it true that from the date of filing of

10       the COLA in July of 2008, that the NRC staff had placed

11       extra focus on the LWA aspects of your filing?

12            A.   No, I wouldn't characterize it in that manner.

13            Q.   Okay.  There was a September 5th meeting with

14       the NRC staff where they communicated to you that they

15       wanted certain activities included in the LWA, is that

16       correct?

17            A.   Yes, it is.

18            Q.   And it was specifically about the LWA, was it

19       not, that meeting?

20            A.   I believe there were other topics covered at

21       the meeting --

22            Q.   Primarily.

23            A.   -- in addition to just the LWA.  As Mr. Miller

24       pointed out, the geotechnical questions and the RAIs

25       that go back and forth are applicable to more than the

FLORIDA PUBLIC SERVICE COMMISSION

2158

1       LWA.  They are generically applicable to the docketing

2       of the COLA and the COLA review itself.  So, any

3       geotechnical question or dialogue on those would have

4       been not necessarily attributed to the LWA, but just

5       attributed to the docketing process for the COLA.  They

6       did make the specific request that you cite, which is

7       particularly the LWA, to expand that scope.

8            Q.   And that was primarily the focus of the

9       September 5th meeting, was it not?

10            A.   As I said, I believe there were other issues,

11       geotechnical issues discussed at the meeting.  One of

12       the issues was certainly this LWA issue.

13            Q.   And on September 12th you made a filing, a

14       supplemental filing related to the LWA, isn't that

15       correct?

16            A.   Yes, it is.

17            Q.   And that really wasn't a supplemental filing

18       on any other aspect of your COLA, was it?

19            A.   No, I don't believe it was.  It was responsive

20       to the staff's request that we incorporate the diaphragm

21       wall and the permeation grouting into the LWA request to

22       support the docketing of the application.

23            Q.   And on October 6th you got your docketing

24       letter accompanied by additional RAIs that focused on

25       aspects of the LWA, isn't that correct?

FLORIDA PUBLIC SERVICE COMMISSION

2159

1            A.   No.  We got the docketing letter that included

2       RAIs on geotechnical issues, which as both I and Mr.

3       Miller have said are applicable to the license

4       application broadly, not specifically related to the

5       LWA.

6            Q.   And isn't it true that the October 6th letter

7       made three separate references in three separate

8       paragraphs to the geotechnical aspects of your filing?

9            A.   Yes.

10            Q.   So in that context, your assertion or your

11       testimony to the Florida Public Service Commission that

12       you expect them to accept is that you did not -- you

13       nevertheless gave no additional credence to the LWA as a

14       specific scheduling challenge?

15            A.   Yes, that is correct, and let me explain my

16       basis for that.  I will tell you that in my experience

17       both working for the Commission and working with the

18       Commission on the licensee side of the table over 25

19       years, where there are issues that the Commission has of

20       this magnitude and nature, they are not reticent to put

21       them in front of the licensee, and they did no such

22       thing related to this LWA, first.

23                 Second, while these geotechnical questions and

24       RAIs certainly relate to the LWA, they relate more

25       directly to the COLA, and are typical of the NRC method

FLORIDA PUBLIC SERVICE COMMISSION

2160

1       of doing business.  They may ask questions because there

2       is an unresolved issue, or as the PSC does, they may

3       just ask questions to create a record of the question

4       and the answer to establish the basis for their COLA

5       docketing and their docketing review.  So, neither I nor

6       anybody else in the company, while these interactions

7       are significant, saw them at all as unusual with respect

8       to how the NRC behaves on these licensing issues.

9            Q.   How many pending applications for COLA were

10       there at the time that you made your -- let's say on

11       December 1st, 2008?

12            A.   Your question is how many --

13            Q.   Let me strike that and ask this question.  At

14       the time you, Mr. Scarola, and Mr. Johnson went to

15       Washington, how many pending COLAs were there before the

16       NRC?

17            A.   I'm sorry, I can't give you a specific number,

18       I think there were somewhere between ten and 20 pending

19       COLAs and early site permits, but at various stages --

20       announced, but at various pages of the process.  I can't

21       give you a number on how many had been docketed.

22            Q.   Was it over ten?

23            A.   I can't say.

24            Q.   Well, that's fine.  And so my question to you

25       following that is that at the time you went to

FLORIDA PUBLIC SERVICE COMMISSION

2161

1       Washington and met with NRC staff immediately preceding

2       the signing of your EPC, your COLA was the only one that

3       had an LWA as a part of it, isn't that correct?

4            A.   Yes.  I think as Mr. Miller established,

5       Southern Company had an LWA associated with their ESP.

6            Q.   Right.  But I asked about COLAs, and that is

7       the only one, right?

8            A.   Yes.

9            Q.   And yours was the first LWA as a part of a new

10       rule that went into effect in 2007 relating to LWAs,

11       correct, that was part of a COLA?

12            A.   That was part of a COLA, yes.  I'm not clear

13       whether there were other work authorizations associated

14       with other facilities not associated with a COLA which

15       the LWA rule was applicable.

16            Q.   So on top of the question I asked you earlier

17       about the attention that the staff had given to your

18       LWA, you also were the only one as a part of a COLA at

19       this time you met with the NRC staff, right?

20            A.   Yes.

21            Q.   Okay.  Now, all of these other pending

22       applications, regardless of the number of them, and

23       there was more than a handful, would you agree with

24       that?

25            A.   Yes.

FLORIDA PUBLIC SERVICE COMMISSION

2162

1            Q.   They all had FSERs, they had environmental

2       impact statement milestone requests pending, is that

3       correct?

4            A.   I'm sorry, are you asking about a specific

5       application?

6            Q.   All of them.  All of the applications would

7       have had an environmental impact statement aspect to

8       them, would they not?

9            A.   They would have, yes.

10            Q.   Okay.  And all of them would have had the

11       safety report, was it FSER aspect, as well?

12            A.   Yes.

13            Q.   Okay.  But yours is the only one that had an

14       LWA, right?

15            A.   I think we have established that, yes.

16            Q.   Yet you gave no -- you paid no specific

17       attention to that in your conversations with the NRC

18       staff immediately before the signing of the EPC.  That

19       is your testimony, correct?

20                 MR. WALLS:  Objection, asked and answered many

21       times.

22                 CHAIRMAN CARTER:  To the objection, Mr.

23       Rehwinkel.

24                 MR. REHWINKEL:  My question was the first time

25       it was asked and answered after establishing certain

FLORIDA PUBLIC SERVICE COMMISSION

2163

1       other facts.

2                 CHAIRMAN CARTER:  Ms. Helton.

3                 MR. REHWINKEL:  I can withdraw the question.

4       I know it is getting late.

5                 CHAIRMAN CARTER:  Okay.  We will be here -- we

6       will just be without air conditioning, but we will be

7       here.  You may proceed.

8                 MR. REHWINKEL:  Thank you.

9       BY MR. REHWINKEL:

10            Q.   On Page 10 of your rebuttal testimony, Mr.

11       Lyash, starting on Lines 14 through 18, you state the

12       sole purpose of the LWA rule is to expedite the NRC's

13       review of certain construction activities to allow them

14       to begin before the COL is issued.  Do you see that?

15            A.   Yes.

16            Q.   And you are talking about the current rule,

17       the LWA rule?

18            A.   Yes, although this is also true of the prior

19       LWA rule.

20            Q.   Okay.  So, when you state expedite the NRC's

21       review, you are not stating that as part of expediting

22       the NRC's review that there is any lessening of the

23       standard for review?

24            A.   No.  I think there are -- no, I'm not.  There

25       are specific standards established for how to review

FLORIDA PUBLIC SERVICE COMMISSION

2164

1       this LWA, and I don't think they are any less or

2       different than the standards that are generically

3       applied to technical material review.  The purpose of

4       this rule is to extract the scope of work that would be

5       covered by an LWA, and to review it separately in

6       advance and independently from the rest of the broader

7       set of activities so as to permit the licensee to begin

8       those activities before the license is issued.

9            Q.   And you would agree there is no presumption in

10       the rule that because an LWA is filed that it will be

11       granted, is that correct?

12            A.   That is correct in this case and in all

13       regulatory cases of this nature, I would think.

14            Q.   And there is no presumption in the rule that

15       an LWA will be considered on a specific time frame

16       regardless of the complexity of the issues that are

17       presented in the LWA, is that correct?

18            A.   Yes, that is correct.  I think there is a

19       general expectation and discussion that the Commission

20       has had in numerous forums about what they saw as the

21       time frame for LWA and environment impact statement

22       issuance, but that does not warrant that that is

23       necessarily what they will deliver, as we have seen in

24       this case.

25            Q.   And there has been a lot of testimony today,

FLORIDA PUBLIC SERVICE COMMISSION

2165

1       and I think even in your testimony about a December 4th

2       statement by Bryan Anderson.  Are you familiar with that

3       statement?

4            A.   I am.  You didn't say that is in my testimony,

5       did you?

6            Q.   I really don't know.  It seems like it has

7       been in everybody's, but --

8            A.   No, it is not in my testimony, but I am

9       certainly familiar with it.

10            Q.   Okay.  Now, were you present when he made that

11       statement?

12            A.   No, I wasn't present.

13            Q.   Did you receive a report from any of your

14       subordinates that told you about the statement?

15            A.   No.  I received a report on the hearing and

16       the content of it, but it didn't specifically call out

17       this statement.  As we have said, it is not a remarkable

18       statement, and I think what it indicates is that Mr.

19       Anderson in his project management activities felt

20       comfortable making that statement given the knowledge he

21       had of our COLA and LWA process at the time.

22            Q.   But you don't know that for sure, that is just

23       speculation on your part?

24            A.   No, I don't know that for sure, but it is more

25       than speculation.  I worked with this agency for nine

FLORIDA PUBLIC SERVICE COMMISSION

2166

1       years, so I know that what their standards are, and I

2       think is unlikely, although I can't guarantee it, that a

3       project manager at a public meeting being transcribed if

4       he knew that there was a significant deviation in what

5       the utility expected and they were planning to issue,

6       would make a statement of that nature.  He would avoid

7       that statement.  So, that is the context I put it in.

8            Q.   You didn't report this statement to the board

9       of directors in any meeting that they held regarding

10       decisions to sign the EPC, did you?

11            A.   No, I did not.

12            Q.   Were you here when Mr. Miller was asked a

13       question about feasibility, and he stated, "I think if

14       the cost of the project doubled that he would consider

15       it not to be feasible"?

16            A.   I was here when he made statements of that

17       nature, yes.

18            Q.   Okay.  I mean, did I mischaracterize what he

19       said?  I was doing it in a very broadbrush way.

20            A.   I think you did it broadly enough.

21            Q.   So, if that -- we know that that -- do you

22       agree with that?

23            A.   Do I agree with --

24            Q.   With what he said regarding that if the cost

25       double you would consider it to be not feasible?

FLORIDA PUBLIC SERVICE COMMISSION

2167

1            A.   All other things being static --

2            Q.   Yes.

3            A.   -- if the cost of the project doubled, then I

4       think you could very well conclude that it is not

5       feasible.

6            Q.   Okay.  Is there a number between doubling and

7       the current price that you would consider to be the

8       break-even point about feasibility?

9            A.   No.

10            Q.   There is not a number?

11            A.   No, there is not a number.  And the reason

12       there is not a number is, as we have said many times,

13       the capital cost purely is not the sole determinant of

14       the feasibility of this project.  For example, if the

15       cost of steel doubled, and that were the reason for the

16       project escalation increase, that doubling of steel

17       might effect a broad range of other alternatives and

18       escalate them right with it.  So, there are enough

19       moving parts to this that I think you cannot establish a

20       number.

21            Q.   Well, my question was along the lines of your

22       clarification, all other things being kept equal.

23                 MR. REHWINKEL:  But, I will withdraw that.

24       Mr. Chairman, that is all the questions I have.  Thank

25       you.

FLORIDA PUBLIC SERVICE COMMISSION

2168

1                 CHAIRMAN CARTER:  Thank you.  Staff.

2                 MR. YOUNG:  No questions.

3                 CHAIRMAN CARTER:  Commissioners.  Commissioner

4       McMurrian, you're recognized.

5                 COMMISSIONER McMURRIAN:  Thank you.  Good late

6       evening, Mr. Lyash.

7                 THE WITNESS:  Good evening, Commissioner.

8                 COMMISSIONER McMURRIAN:  I was listening to

9       the questions from Mr. Moyle about the joint ownership,

10       but I couldn't recall, did you tell us already that you

11       had discussed or your company had discussed with other

12       Florida IOUs joint ownership of the nuclear plants?

13                 THE WITNESS:  Yes, Commissioner.  We have

14       reached out to other Florida IOUs to discuss their

15       interest in joint ownership in our facility and the

16       potential that there might be reciprocal joint

17       ownerships if and when any of them were to undertake

18       such a project.  So we have done that.

19                 COMMISSIONER McMURRIAN:  Okay.  And I have two

20       or three, I think, Mr. Chairman.

21                 CHAIRMAN CARTER:  You're recognized.

22                 COMMISSIONER McMURRIAN:  If you were to come

23       to an agreement with a Florida IOU for joint ownership

24       of Levy 1 and 2, can you tell me whether your company

25       has an opinion on whether such a Florida IOU would be

FLORIDA PUBLIC SERVICE COMMISSION

2169

1       able to seek advanced recovery of their share of the

2       preconstruction costs from their customers?

3                 THE WITNESS:  I haven't personally and I don't

4       believe our company has come to a conclusion on that.

5       Although I would say, you know, just based on my

6       exposure to this point, I would think that would be

7       consistent, in my reading that would be consistent with

8       the intent of the legislation.

9                 COMMISSIONER McMURRIAN:  Okay.  And I guess

10       one other question.  If you believe that new policies or

11       regulations would be helpful to encourage joint

12       ownership of nuclear plants in particular, you would

13       suggest that to the appropriate policymakers or

14       regulators, wouldn't you?

15                 THE WITNESS:  We would.  If such an

16       opportunity were desired and we were asked to comment on

17       that we would certainly give our input on it.

18                 COMMISSIONER McMURRIAN:  Okay.  Thank you.

19       That's all I have, Mr. Chairman.

20                 CHAIRMAN CARTER:  Commissioner Skop, you're

21       recognized.

22                 COMMISSIONER SKOP:  Thank you, Mr. Chairman.

23       I will try and make this brief.  Good evening, Mr.

24       Lyash.

25                 THE WITNESS:  Good evening.

FLORIDA PUBLIC SERVICE COMMISSION

2170

1                 COMMISSIONER SKOP:  If I could turn your

2       attention to Page 33 of your testimony, please.

3                 COMMISSIONER ARGENZIANO:  Excuse me,

4       Commissioner Skop, what page did you indicate?

5                 COMMISSIONER SKOP:  33 of the rebuttal

6       testimony.

7                 COMMISSIONER ARGENZIANO:  Okay, thank you.

8                 THE WITNESS:  Yes, sir.

9                 COMMISSIONER SKOP:  And in response to a

10       question that was presented on Line 4, can you briefly

11       explain on Lines 6 through 8 the significance of the

12       response to that question?

13                 THE WITNESS:  I'm sorry, Commissioner, I am on

14       Page 33.

15                 COMMISSIONER SKOP:  Yes, Page 33.

16                 THE WITNESS:  And just to make sure I have the

17       right line, what you are asking about is the statement

18       that says the company's updated cumulative present value

19       revenue requirement analysis demonstrates that LNP is

20       still cost-effective?

21                 COMMISSIONER SKOP:  Yes.

22                 THE WITNESS:  And your question, I'm sorry?

23                 COMMISSIONER SKOP:  Okay.  On Page 4 you are

24       presented with the question and your response beginning

25       on Line 5 basically through Line 8, in response to the

FLORIDA PUBLIC SERVICE COMMISSION

2171

1       updated analysis, what did the company's projections

2       show?

3                 THE WITNESS:  Yes.  The company's response to

4       the interrogatory was that analysis that is exhibit, I

5       think JL-2.  And what it showed was that the Levy plant

6       remains cost-effective, and for the mid-fuel reference

7       case and the carbon center is slightly more

8       cost-effective than was presented in the need case.

9                 It also goes on to assess capital sensitivity

10       to the project, and shows that in this range of minus 15

11       to 25 percent that the Levy project even with somewhat

12       escalated capital cost, the escalations that we would

13       anticipate to take place as a result of the passage of

14       time is still cost-effective.

15                 COMMISSIONER SKOP:  In furtherance of that,

16       would it also be correct to understand that based upon

17       the company's updated analysis, that it is slightly more

18       cost-effective even at this time even with the schedule

19       shift as a result of the LWA denial?

20                 THE WITNESS:  That is correct.

21                 COMMISSIONER SKOP:  Okay.  All right.  Moving

22       to Page 34 of your rebuttal testimony, Lines 20 through

23       23 on that page.

24                 THE WITNESS:  Yes, sir.

25                 COMMISSIONER SKOP:  The question arose about

FLORIDA PUBLIC SERVICE COMMISSION

2172

1       joint ownership, and can you basically explain the

2       significance of those lines of testimony as they pertain

3       to joint ownership and what the opportunity costs might

4       be?

5                 THE WITNESS:  Yes.  If I understand your

6       question, the testimony says that joint ownership

7       scenarios, because the plant is cost-effective and

8       produces a clear net benefit for the customers, at less

9       than 100 percent ownership you would expect a reduction

10       in the total of the benefit to the customers.  And so in

11       a case where you were taking less than 100 percent

12       ownership, you are necessarily transferring not only the

13       cost but the attendant benefit to the co-owner, and that

14       is really what that is reflecting.

15                 COMMISSIONER SKOP:  Okay.  So, although joint

16       ownership may or may not be a good thing, that comes

17       with the trade-off to the extent that you -- if you sell

18       part of the generating asset, you also give up part of

19       the expected fuel savings costs that you would bring to

20       your customers, is that correct?

21                 THE WITNESS:  Yes, that is correct.  And the

22       presumption here, though, is that we would -- if we were

23       to take on partners we would be transferring not only

24       the costs, but that benefit, hopefully to other citizens

25       of Florida.

FLORIDA PUBLIC SERVICE COMMISSION

2173

1                 COMMISSIONER SKOP:  Okay.  Thank you.

2                 CHAIRMAN CARTER:  Commissioners, anything

3       further from the bench?  Redirect.

4                 MR. WALLS:  No, sir.

5                 CHAIRMAN CARTER:  Exhibits 128 and 129, is

6       that right?

7                 MR. WALLS:  Yes, that is correct.

8                 CHAIRMAN CARTER:  Are there any objections?

9                 MR. BREW:  No objections.

10                 CHAIRMAN CARTER:  Okay.  We have got to go --

11       128 and 129 entered.

12                 (Exhibit Numbers 128 and 129 admitted into the

13       record.)

14                 CHAIRMAN CARTER:  Now let's go to the back

15       pages.  You have got 155?

16                 MR. BREW:  Yes.

17                 CHAIRMAN CARTER:  Are there any objections?

18                 MR. WALLS:  No.

19                 CHAIRMAN CARTER:  Without objection, show it

20       done.

21                 (Exhibit Number 155 admitted into the record.)

22                 CHAIRMAN CARTER:  Mr. Davis, you have got 156?

23                 MR. DAVIS:  Chair, I had 156, and I would also

24       since the Progress counsel said that the Levy update

25       document that I presented is not confidential, go ahead

FLORIDA PUBLIC SERVICE COMMISSION

2174

1       and mark that as Exhibit 157 and have that entered,

2       please.

3                 CHAIRMAN CARTER:  Okay, let's do this.  Are

4       there any objections to 156?

5                 MR. WALLS:  No.

6                 CHAIRMAN CARTER:  Without objection, show it

7       done.

8                 (Exhibit Number 156 admitted into the record.)

9                 CHAIRMAN CARTER:  Mr. Burnett, you said in

10       reference to this Levy update document that was marked

11       confidential that you waived the confidentiality on it,

12       is that correct?

13                 MR. BURNETT:  No, sir, not waive it.  It is

14       just that those particular pages at this time are no

15       longer confidential.  Just a slight clarification.

16                 CHAIRMAN CARTER:  Semantics.

17                 MR. BURNETT:  Yes, sir.

18                 CHAIRMAN CARTER:  157, any objections, Mr.

19       Burnett?

20                 MR. BURNETT:  No, sir.

21                 CHAIRMAN CARTER:  Okay.  So we will call that

22       short title, Levy Update.  Without objection, show it

23       entered.

24                 (Exhibit Number 157 marked for identification

25       and admitted into the record.)

FLORIDA PUBLIC SERVICE COMMISSION

2175

1                 CHAIRMAN CARTER:  Anything further for this

2       witness from any of the parties?  Mr. Lyash, you may be

3       excused.

4                 THE WITNESS:  Thank you, Mr. Chairman.

5                 CHAIRMAN CARTER:  I need all the lawyers to

6       pay attention.  Did we do 155?  Yes, we did.  And 156,

7       that was by Mr. Davis -- 156 and 157 by Mr. Davis.  155

8       by Mr. Brew entered.  Okay.

9                 I need all the lawyers to pay attention.  Mr.

10       Anderson, is that you back there?

11                 MR. ANDERSON:  Yes, sir.

12                 CHAIRMAN CARTER:  Okay.  Staff, you're

13       recognized for concluding matters and additional

14       procedures.

15                 MR. YOUNG:  Yes, sir.  The critical dates.

16       Hearing transcripts are due --

17                 CHAIRMAN CARTER:  Hang on.  Let Mr. Anderson

18       get here so he can take notes.  Mr. Wright.  You may

19       proceed.

20                 MR. YOUNG:  Yes.  Hearing transcripts, daily

21       transcripts.  Briefs are due September 18th, 2009.

22       Staff's recommendation will be filed on October 7th,

23       2009.  And it will be to you at agenda conference, which

24       is October 16th, 2009.

25                 CHAIRMAN CARTER:  Before I ask Commissioners,

FLORIDA PUBLIC SERVICE COMMISSION

2176

1       let me ask any of the parties -- are there any further

2       matters from any of the parties?  Mr. Moyle.

3                 MR. MOYLE:  I have not participated in this

4       proceeding before this year, so I guess the only

5       question I have is that is there some reason why this

6       has to be done on this time frame in that, you know,

7       next week we have the two days of Power and Light and

8       then we have PEF.  I mean, if there is a statutory time

9       frame or something --

10                 CHAIRMAN CARTER:  Are you trying to say you

11       are not having fun?  That's what it sounds like to me.

12                 MR. MOYLE:  I'm just saying I think the

13       quality of my brief might be improved if there was

14       additional time.

15                 COMMISSIONER EDGAR:  It's a marathon, Mr.

16       Moyle.  It's a marathon.

17                 CHAIRMAN CARTER:  Ms. Helton, you're

18       recognized.

19                 MS. HELTON:  Mr. Young may be able to address

20       this more specifically, but it is my understanding that

21       this time frame is imposed on all of us by our rule, and

22       so that we can ensure that we have a decision in time to

23       roll it into the fuel hearing in November.

24                 CHAIRMAN CARTER:  Okay.  There is your answer.

25       Anything from any of the rest of the parties before I go

FLORIDA PUBLIC SERVICE COMMISSION

2177

1       back to staff?  Commissioners, anything further?  Staff,

2       anything further?

3                 COMMISSIONER ARGENZIANO:  What time do we meet

4       tomorrow, Mr. Chairman?

5                 CHAIRMAN CARTER:  I beg your pardon,

6       Commissioner Argenziano?

7                 COMMISSIONER ARGENZIANO:  I'm only kidding.  I

8       said 9:00 o'clock tomorrow?

9                 CHAIRMAN CARTER:  Would be 9:00 p.m. tomorrow.

10       With that, we are adjourned.

11                 (The hearing concluded at 8:26 p.m.)

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

2178

1       STATE OF FLORIDA    )

2                           :    CERTIFICATE OF REPORTER

3       COUNTY OF LEON      )

4

I, JANE FAUROT, RPR, Chief, Hearing Reporter

5       Services Section, FPSC Division of Commission Clerk, do

hereby certify that the foregoing proceeding was heard

6       at the time and place herein stated.

7                 IT IS FURTHER CERTIFIED that I

stenographically reported the said proceedings; that the

8       same has been transcribed under my direct supervision;

and that this transcript constitutes a true

9       transcription of my notes of said proceedings.

10                 I FURTHER CERTIFY that I am not a relative,

employee, attorney or counsel of any of the parties, nor

11       am I a relative or employee of any of the parties'

attorney or counsel connected with the action, nor am I

12       financially interested in the action.

13                 DATED THIS 11th day of September, 2009.

14

15             ___________________________________________

JANE FAUROT, RPR

16                   Official FPSC Hearings Reporter

(850) 413-6732

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION