1

1                             BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

3                                          DOCKET NO. 100009-EI

4       In the Matter of:

5       NUCLEAR COST RECOVERY CLAUSE.

______________________________/

6

7                               VOLUME 1

8                         Pages 1 through 168

9              ELECTRONIC VERSIONS OF THIS TRANSCRIPT ARE

A CONVENIENCE COPY ONLY AND ARE NOT

10               THE OFFICIAL TRANSCRIPT OF THE HEARING,

THE .PDF VERSION INCLUDES PREFILED TESTIMONY.

11

12

13       PROCEEDINGS:        HEARING

14       COMMISSIONERS

PARTICIPATING:      CHAIRMAN NANCY ARGENZIANO

15                           COMMISSIONER LISA POLAK EDGAR

COMMISSIONER NATHAN A. SKOP

16                           COMMISSIONER ART GRAHAM

COMMISSIONER RONALD A. BRISÉ

17

DATE:               Tuesday, August 24, 2010

18

TIME:               Commenced at 9:30 a.m.

19

PLACE:              Betty Easley Conference Center

20                           Room 148

4075 Esplanade Way

21                           Tallahassee, Florida

22       REPORTED BY:        LINDA BOLES, RPR, CRR

Official FPSC Reporter

23                           (850) 413-6734

24

25

FLORIDA PUBLIC SERVICE COMMISSION

2

1       APPEARANCES:

2                 JOHN T. BURNETT, ESQUIRE, and R. ALEXANDER

3       GLENN, ESQUIRE, Progress Energy Service Company, LLC,

4       299 First Avenue, N. PEF-151, St. Petersburg, Florida

5       33701, and J. MICHAEL WALLS, ESQUIRE, and BLAISE N.

6       HUHTA, ESQUIRE, Carlton Fields P.A., Post Office Box

7       3239, Tampa, Florida 33601-3239, appearing on behalf of

8       Progress Energy Florida, Inc.

9                 BRYAN S. ANDERSON, ESQUIRE, MITCHELL S. ROSS,

10       ESQUIRE, and JESSICA A. CANO, ESQUIRE, Florida Power &

11       Light Company, 700 Universe Boulevard, Juno Beach,

12       Florida 33408-0420, appearing on behalf of Florida Power

13       & Light Company.

14                 J. R. KELLY, PUBLIC COUNSEL, CHARLES J.

15       REHWINKEL, ESQUIRE, and JOSEPH A. MCGLOTHLIN, ESQUIRE,

16       Office of Public Counsel, c/o The Florida Legislature,

17       111 West Madison Street, Room 812, Tallahassee, FL

18       32399-1400, appearing on behalf of the Office of Public

19       Counsel.

20                  JAMES W. BREW, ESQUIRE, and F. ALVIN TAYLOR,

21       ESQUIRE, Brickfield, Burchette, Ritts & Stone, P.C.,

22       1025 Thomas Jefferson Street, NW, Eighth Floor, West

23       Tower, Washington, DC 20007, appearing on behalf of

24       White Springs Agricultural Chemicals, Inc.

25

FLORIDA PUBLIC SERVICE COMMISSION

3

1       APPEARANCES (Continued):

2                 VICKI GORDON KAUFMAN, ESQUIRE, and

3       JON C. MOYLE, JR., ESQUIRE, Keefe, Anchors, Gordon &

4       Moyle, P.A., 118 North Gadsden Street, Tallahassee,

5       Florida 32312, appearing on behalf of the Florida

6       Industrial Power Users Group.

7                 GARY A. DAVIS, ESQUIRE, and JAMES S. WHITLOCK,

8       ESQUIRE, Gary A. Davis & Associates, 61 North Andrews

9       Avenue, Post Office Box 649, Hot Springs, North Carolina

10       28743, and E. LEON JACOBS, JR., ESQUIRE, Williams &

11       Jacobs, LLC, 1720 S. Gadsden Street MS 14, Suite 201,

12       Tallahassee, FL  32301, appearing on behalf of Southern

13       Alliance for Clean Energy.

14                 CAPTAIN SHAYLA L. MCNEILL, AFCESA, Federal

15       Executive Agencies, c/o AFLSA/JACL-ULT, 139 Barnes

16       Avenue, Suite 1, Tyndall AFB, Florida 32403-5319,

17       appearing on behalf of Federal Executive Agencies.

18                 KEINO YOUNG, ESQUIRE, LISA BENNETT, ESQUIRE,

19       and ANNA R. WILLIAMS, ESQUIRE, FPSC General Counsel's

20       Office, 2540 Shumard Oak Boulevard, Tallahassee, Florida

21       32399-0850, appearing on behalf of the Florida Public

22       Service Commission Staff.

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

4

1       APPEARANCES (Continued):

2                 CURT KISER, GENERAL COUNSEL, and MARY ANNE

3       HELTON, DEPUTY GENERAL COUNSEL, FPSC General Counsel's

4       Office, 2540 Shumard Oak Boulevard, Tallahassee, Florida

5       32399-0850, appearing as advisor to the Commission.

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

5

1                              I N D E X

2                              WITNESSES

3

OPENING STATEMENTS:                            PAGE NO.:

4

5       MR. GLENN                                       13

MR. REHWINKEL                                   20

6       MR. BREW                                        28

MS. KAUFMAN                                     35

7       MR. DAVIS                                       42

8       NAME:                                          PAGE NO.:

9       WILL GARRETT

10       Prefiled Direct Testimony Inserted              53

11

12       THOMAS G. FOSTER

13       Direct Examination by Ms. Huhta                 71

Prefiled Direct Testimony Inserted              73

14       Cross Examination by Mr. Rehwinkel             100

Cross Examination by Mr. Brew                  136

15       Cross Examination by Ms. Kaufman               150

Cross Examination by Mr. Davis                 163

16

17

18

19

20

21

22       CERTIFICATE OF REPORTER                        168

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

6

1                              EXHIBITS

NUMBER:                                      ID.  ADMTD.

2       1    Comprehensive Exhibit List              10       50

3       2    WG-1                                    52       52

4       3    WG-2                                    52       52

5       61   Staff's Exhibit 61                      51       51

62   Staff's Exhibit 62                      51       51

6       63   Staff's Exhibit 63                      51       51

64   Staff's Exhibit 64                      51       51

7       65   Staff's Exhibit 65                      51       51

66   Staff's Exhibit 66                      51       51

8       67   Staff's Exhibit 67                      51       51

68   Staff's Exhibit 68                      51       51

9       69   Staff's Exhibit 69                      51       51

70   Staff's Exhibit 70                      51       51

10       71   Staff's Exhibit 71                      51       51

72   Staff's Exhibit 72                      51       51

11       73   Staff's Exhibit 73                      51       51

74   Staff's Exhibit 74                      51       51

12       75   Staff's Exhibit 75                      51       51

76   Staff's Exhibit 76                      51       51

13

188 PEF Response to OPC 3rd ROG 47          101

14

189 (Confidential) PEF Response to Staff    102

15            ROG 29

16       190 Excerpts from PEF 2008 Need             110

Determination

17

191 (Confidential) PEF Response to OPC      116

18            ROGS 90 through 93

19       192  PEF's Response to Staff Data           124

`    Request 1

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

7

1                         P R O C E E D I N G S

2                 CHAIRMAN ARGENZIANO:  Good morning.  Just

3       gather my things here and we will start our hearing.  We

4       will convene our hearing this morning, and we'll have

5       staff read the notice.

6                 MR. YOUNG:  Good morning.  By notice duly

7       given on August 10th, 2010, this time and place has been

8       set for a hearing in Docket Number 10009-EI (sic.),

9       Nuclear Cost Recovery Clause.  The purpose of this

10       hearing is set out in the notice.

11                 CHAIRMAN ARGENZIANO:  We'll take appearances.

12                 MR. ANDERSON:  Good morning, Chairman

13       Argenziano.

14                 CHAIRMAN ARGENZIANO:  Good morning.

15                 MR. ANDERSON:  Good morning, Commissioners.

16       My name is Bryan Anderson.  I'm here today with my

17       colleague Mitchell Ross and with Jessica Cano.  We are

18       attorneys for Florida Power & Light Company.

19                 CHAIRMAN ARGENZIANO:  Good morning.

20                 MR. WALLS:  Good morning, Commissioners.  My

21       name is Mike Walls with Carlton Fields on behalf of

22       Progress Energy Florida.  Behind me is Mr. Glenn, Alex

23       Glenn and John Burnett, also appearing on behalf of

24       Progress Energy Florida.

25                 CHAIRMAN ARGENZIANO:  Good morning.

FLORIDA PUBLIC SERVICE COMMISSION

8

1                 MS. HUHTA:  Good morning, Commissioners.

2       Blaise Huhta with Carlton Fields, also on behalf of

3       Progress Energy Florida.

4                 CHAIRMAN ARGENZIANO:  Good morning.

5                 MR. JACOBS:  Good morning, Commissioners.

6       Leon Jacobs here.  With me is Gary Davis, and he'll be

7       carrying on most of the case, and we represent Southern

8       Alliance For Clean Energy.

9                 CHAIRMAN ARGENZIANO:  Good morning.

10                 MS. KAUFMAN:  Good morning, Chairman and

11       Commissioners.  I'm Vicki Gordon Kaufman.  I am with the

12       law firm of Keefe, Anchors, Gordon & Moyle here in

13       Tallahassee.  We're appearing on behalf of the Florida

14       Industrial Power Users Group.  And I'd like to enter an

15       appearance for Jon Moyle as well.

16                 MR. BREW:  Good morning.

17                 CHAIRMAN ARGENZIANO:  Good morning.

18                 MR. BREW:  My name is James Brew.  I'm with

19       the law firm of Brickfield, Burchette, Ritts & Stone.

20       I'm representing White Springs Agricultural Chemicals -

21       PCS Phosphate in this proceeding, and I'd also like to

22       make an appearance for F. Alvin Taylor.

23                 MR. REHWINKEL:  Good morning.  My name is

24       Charles Rehwinkel, Florida Office of Public Counsel.

25       Here with me today also making an appearance is Joe

FLORIDA PUBLIC SERVICE COMMISSION

9

1       McGlothlin and J.R. Kelly.

2                 CHAIRMAN ARGENZIANO:  Good morning.

3                 CAPTAIN McNEILL:  Good morning, Madam Chair,

4       Commissioners.  Captain Shayla McNeill on behalf of the

5       Federal Executive Agencies.

6                 CHAIRMAN ARGENZIANO:  Good morning, Captain.

7                 Okay.  Let's move into our technical hearing.

8       I'm sorry.

9                 MR. YOUNG:  Madam Chair.

10                 CHAIRMAN ARGENZIANO:  Sorry.  Go ahead.

11                 MR. YOUNG:  Keino Young, Anna R. Williams.

12                 CHAIRMAN ARGENZIANO:  I'm sorry.

13                 MR. YOUNG:  Keino Young, Anna R. Williams and

14       Lisa Bennett on behalf of the staff.

15                 MS. HELTON:  And, Madam Chairman, Mary Anne

16       Helton, Advisor to the Commission.  And also here today

17       to advise the Commission is our General Counsel, Curt

18       Kiser.

19                 CHAIRMAN ARGENZIANO:  We're done.  Anybody

20       else?  Okay.  Let's move into our technical hearing and

21       start with preliminary matters.  Yes.

22                 MR. YOUNG:  Madam Chairman, staff has prepared

23       a Comprehensive Exhibit List.  The list itself is marked

24       as Exhibit Number 1.  If there are no objections to the

25       Comprehensive Exhibit List, staff will ask that the

FLORIDA PUBLIC SERVICE COMMISSION

10

1       Comprehensive Exhibit List be entered into the record

2       as, be entered into the record after opening statements

3       or at the Chairman's pleasure.

4                 CHAIRMAN ARGENZIANO:  Any comments?  Fine.

5                 (Exhibit 1 marked for identification.)

6                 MR. YOUNG:  Also, Madam Chairman, staff will

7       ask that the staff's stipulated exhibits that is

8       included throughout the Comprehensive Exhibit List be

9       entered into the record after opening statements of each

10       case or at the Chairman's pleasure.

11                 CHAIRMAN ARGENZIANO:  So be it.  Thank you.

12                 MR. YOUNG:  Staff will also, staff will also

13       request, Madam Chairman, that, that marked -- staff

14       would also request marking the listed exhibits as

15       numbered in the Comprehensive Exhibit List and suggest

16       that any other exhibits proffered during the hearing be

17       numbered sequentially following those listed in the

18       Comprehensive Exhibit List.

19                 CHAIRMAN ARGENZIANO:  Very good.

20                 MR. YOUNG:  The stipulated prefiled testimony

21       exhibits can be taken up in turn as the witnesses are

22       called at the hearing.  At that time, staff will

23       recommend that the testimony of the stipulated witnesses

24       be inserted into the record as though read, and staff

25       will request that the stipulated exhibits be moved into

FLORIDA PUBLIC SERVICE COMMISSION

11

1       the record.

2                 CHAIRMAN ARGENZIANO:  Very good.  And we have

3       excused witnesses?

4                 MR. YOUNG:  Yes, ma'am.  The following

5       witnesses have been excused:  Cooper, Gunderson, Karp,

6       Garrett, Galloway, and Galloway.

7                 CHAIRMAN ARGENZIANO:  Okay.  Why don't we --

8       okay.  We're on the proposed stipulations.  Do I see

9       somebody?  Okay.  Do we want to take up Progress first?

10                 COMMISSIONER SKOP:  Madam Chair.

11                 CHAIRMAN ARGENZIANO:  Commissioner Skop.

12                 COMMISSIONER SKOP:  I'd be prepared to take up

13       Progress first, if it's the will of the Commission.

14                 CHAIRMAN ARGENZIANO:  And then move back,

15       since staff has noted that they requested any

16       stipulations concerning FPL be taken up after an

17       opportunity to cross-examine the three witnesses, FPL

18       witnesses.

19                 COMMISSIONER SKOP:  Madam Chair.

20                 CHAIRMAN ARGENZIANO:  Commissioner Skop.

21                 COMMISSIONER SKOP:  I also have problems with

22       that.  At the time when we get to the motion, I would

23       like to speak to the proposed motion for stipulation.  I

24       have substantial issues with considering the proposed

25       stipulations prior to hearing all of the FPL witness

FLORIDA PUBLIC SERVICE COMMISSION

12

1       testimony in this docket for reasons that I will get

2       into.

3                 CHAIRMAN ARGENZIANO:  Okay.  Anyone else?

4       Then why don't we do -- why don't we go to Progress and

5       move on with our agenda, and then we'll come back to the

6       stipulation.

7                 Staff.

8                 MS. KAUFMAN:  Chairman Argenziano?

9                 CHAIRMAN ARGENZIANO:  Yes.

10                 MS. KAUFMAN:  I'm sorry.  And respectfully,

11       Commissioner Skop, I just wanted to ask the Commission

12       if it might be possible to take up the Florida Power &

13       Light stipulation before we begin the witness testimony

14       just for purposes of planning and maybe to avoid some

15       late nights and so the witnesses would know.

16                 COMMISSIONER SKOP:  Thank you, Madam --

17                 MS. KAUFMAN:  Just for, you know, ease of

18       administration.

19                 COMMISSIONER SKOP:  Thank you, Madam Chairman.

20       And, Ms. Kaufman, again, I think that, you know, in

21       fairness to Progress, I mean, we could have lengthy

22       debate as to whether to accept the motion or approve the

23       motion for the proposed stipulations, but I don't

24       believe that would be fair to Progress.  I mean, they're

25       here, they're prepared to put on their case in chief.

FLORIDA PUBLIC SERVICE COMMISSION

13

1       The Order Establishing Procedure indicated that Progress

2       would go first.  The motion was filed, you know, a few

3       days ago, to say the least.  I have problems.  I don't

4       have a problem in discussing the motion prior to the FPL

5       case in chief.  However, I will have problems

6       considering accepting the proposed stipulations for

7       reasons that I will get into that should be astutely

8       obvious to all of the intervening parties that agreed to

9       this proposed stipulation.  I'll get into that at the

10       appropriate time.  But it's probably going to be a

11       lengthy discussion and, you know, I'm -- from my

12       perspective, I'm willing to consider the stipulations

13       after hearing the witness testimony.  But I will get

14       into that at the appropriate time.  Thank you.

15                 CHAIRMAN ARGENZIANO:  Let's proceed with

16       Progress's case.  Thank you.

17                 MR. YOUNG:  Madam Chairman?

18                 CHAIRMAN ARGENZIANO:  Yes, please.

19                 MR. YOUNG:  Opening statements, if any, staff

20       recommends shall not exceed ten minutes as ruled upon by

21       the Prehearing Officer for PEF's petition.

22                 CHAIRMAN ARGENZIANO:  Okay.  Opening

23       statements.

24                 MR. GLENN:  Thank you, Madam Chairman,

25       Commissioners.  Alex Glenn on behalf of Progress Energy

FLORIDA PUBLIC SERVICE COMMISSION

14

1       Florida.

2                 My company has two projects before this

3       Commission today:  Our Levy nuclear plant project and

4       our Crystal River Unit 3, CR3, power uprate project.

5                 With respect to our Levy nuclear project, the

6       real question today is this:  Should our company

7       continue to build these plants and have new nuclear

8       generation in Florida?  That's really it.  We say yes.

9       We intend to build these plants because it's the right

10       thing to do for our customers and for the State of

11       Florida.  This decision really is about the future

12       60-plus years that these nuclear power plants are going

13       to produce electricity and provide billions of dollars

14       of benefits for our customers.  These plants are going

15       to enhance fuel diversity, reduce reliance on fossil

16       fuels and provide carbon free baseload energy.  These

17       plants will also provide our customers billions of

18       dollars of fuel savings over the plants' lives.

19                 Now these long-term nuclear benefits are the

20       reasons that the Legislature decided to encourage

21       investment in new nuclear generation, the reasons we

22       decided to build these plants and the reasons that this

23       Commission decided to approve our need determination and

24       build these plants.  The reasons to build these plants

25       still exist today.

FLORIDA PUBLIC SERVICE COMMISSION

15

1                 Now Intervenors will tell you that there's

2       greater uncertainty, that the costs have increased, that

3       the risks have increased, that the plants are expensive,

4       that they will be delayed several years, that they could

5       increase the price $5 billion.  Some will tell you that

6       the project should be canceled, some will tell you that

7       the project should not be canceled, but that projected

8       costs should be placed at risk if the project is

9       canceled at some future time.

10                 Let's be clear, there is greater uncertainty,

11       there is greater risk since the need determination,

12       potential risks and uncertainties, I would note, that we

13       raised in our need determination, that we raised in our

14       2008 nuclear cost recovery docket, our 2009 filing, and

15       in our prefiled direct testimony today.  So we don't

16       entirely disagree with the Intervenors that the overall

17       risk profile of the Levy project has changed since the

18       project began.  Where we depart completely from the

19       Intervenors is on the notion that the increased

20       uncertainties make project cancellation the optimal

21       choice.

22                 Under the circumstances facing us, we agree

23       that project cancellation is an alternative that must be

24       considered.  We considered it.  We studied it and

25       analyzed it in great detail.  Had my company not been

FLORIDA PUBLIC SERVICE COMMISSION

16

1       able to mitigate some of the risks and uncertainties

2       through an amendment to our engineering, procurement and

3       construction contract, our EPC agreement, we would have

4       canceled the project.  But we were able to amend the EPC

5       agreement in a prudent manner that will allow us to

6       continue with the project in a deliberate and prudent

7       way.

8                 The path we've chosen, we believe, properly

9       balances the risks and the benefits of the Levy project

10       and is the optimal decision for our customers and for

11       the state.  It recognizes the long-term substantial

12       benefits of these plants to our customers, while

13       mitigating the short-term uncertainty and risk by

14       reducing the capital investment and the costs to our

15       customers in the near term until we obtain the operating

16       license from the U.S. Nuclear Regulatory Commission, the

17       NRC.

18                 Now after months of review of our evaluation

19       and our decision, the Commission staff audit agreed.  In

20       their audit report, the staff states, and I quote, given

21       the uncertainties facing the company, audit staff

22       recognizes that keeping the project progressing without

23       further substantial investment and cost is a reasonable

24       approach at this point in time.

25                 Now some of the Intervenors may contend that

FLORIDA PUBLIC SERVICE COMMISSION

17

1       our decision was not reasonable, but listen carefully to

2       what they're saying.  What they're really saying is that

3       they think a different decision should be made.  That

4       decision, project cancellation, will virtually end the

5       development of nuclear generation in Florida.  That

6       decision, we contend, is not the optimal decision given

7       the substantial long-term benefits of new nuclear

8       generation.  That decision, abandoning new nuclear at

9       this stage and foregoing the opportunity to realize

10       billions of dollars over the long-term, in our view

11       would be shortsighted.  And we believe after you hear

12       all the evidence, after you listen, you listen to

13       Mr. Lyash and Mr. Elnitsky, that you'll agree with us.

14                 Now turning to our CR3 uprate project, this

15       project involves modifications to our existing nuclear

16       power plant, the CR3 plant, to increase the power output

17       by 180 megawatts when the project is finished.  Now we

18       separated this project into three phases of work over

19       the planned refueling outages when the unit is already

20       offline.  We completed the Phase 1 work in the 2007

21       refueling outage.  We completed, just completed the

22       Phase 2 work in our recent 2009 refueling outage.  And

23       we're on track to complete the Phase 3 work, what we

24       call the extended power uprate or EPU, you'll hear the

25       witnesses talk about, is on schedule for the next

FLORIDA PUBLIC SERVICE COMMISSION

18

1       planned CR3 refueling outage.

2                 Now the EPU requires us to file a license

3       amendment request or LAR, you'll hear the witnesses say

4       L-A-R or LAR, which must be approved by the Nuclear

5       Regulatory Commission prior to the full power uprate.

6       Now the Commission's staff auditors raised questions

7       regarding the $1.8 million that we paid to AREVA to

8       provide an initial draft of the LAR because we needed to

9       do rework on that initial draft.

10                 The initial draft LAR was not the quality

11       product it should have been, period.  We recognized that

12       at the time and we corrected it at no additional cost to

13       our customers.  Let me say that again.  Any work to fix

14       the initial draft rework on the initial draft of the LAR

15       was done at no additional cost to customers.  It was

16       done on AREVA's dime, and you'll hear Mr. Franke talk

17       about that.

18                 Now we continue to work with the NRC on the

19       LAR submittal and we remain confident that we will

20       obtain that approval.  No one really contends otherwise

21       here today.  In fact, OPC's witness, Dr. Jacobs, agrees

22       that we could obtain approval of the LAR.  Dr. Jacobs,

23       however, recommends that we demonstrate the project is

24       feasible and that our project schedule is prudent next

25       year.  In next year's docket, not today, not this week

FLORIDA PUBLIC SERVICE COMMISSION

19

1       during the hearings, but next year based on the NRC's

2       future review of our license amendment request.

3                 Just as he unsuccessfully argued last year,

4       Dr. Jacobs simply disagrees with a project schedule

5       where a substantial portion of the project costs are

6       incurred before we actually obtain approval by the NRC.

7                 Now as this Commission heard and agreed last

8       year, this is the way every other nuclear power uprate

9       project has been licensed and managed by every other

10       utility across the country, and that the NRC has

11       approved every single uprate of the 104 since 2001.  So,

12       again, this was Dr. Jacobs' same argument last year

13       which was not accepted when the Commission approved all

14       of our reasonable and prudent uprate costs, and it

15       should not be accepted this year as well.

16                 So why are we here?  We ask this Commission to

17       find that Progress Energy prudently incurred costs on

18       our Levy project and our CR3 power uprate project in

19       2009, that our 2010 and projected 2011 costs are

20       reasonable, that we be allowed to recover those prudent

21       and reasonable costs and really, most important, that

22       moving forward with new nuclear in Florida remains the

23       right course of action for customers and for the state.

24       Thank you.

25                 CHAIRMAN ARGENZIANO:  Thank you.  Who's up?

FLORIDA PUBLIC SERVICE COMMISSION

20

1                 MR. REHWINKEL:  I think --

2                 CHAIRMAN ARGENZIANO:  Sorry.

3                 MR. REHWINKEL:  Yeah.  Madam Chairman, Charles

4       Rehwinkel with the Office of Public Counsel.  I assume

5       that we're going to go in the order that we've agreed

6       among ourselves to cross.

7                 CHAIRMAN ARGENZIANO:  Yes.  That will be fine.

8       Thank you.

9                 MR. REHWINKEL:  Madam Chairman, Commissioners,

10       my name is Charles Rehwinkel with the Office of Public

11       Counsel.

12                 Today you embark on a historical hearing for

13       the people of Florida.  You have heard Progress's

14       opening, and it is the opening I would expect from a

15       worthy and honorable opponent in a hearing like this.

16       Count how many times you heard the word "optimal" in the

17       opening statement.  We understand that Progress would

18       like you to make or endorse the optimal decision that

19       they have made, but we're asking you to make what's the

20       best decision for the people of Florida.

21                 From our perspective, there are at least two

22       major issues for you to decide in this docket this week.

23       One relates to the overall status of the Levy nuclear

24       project and whether customers, Florida customers should

25       be forced to pony up 100 percent of the stakes to place

FLORIDA PUBLIC SERVICE COMMISSION

21

1       a 400 plus million dollar bet in a high stakes gamble

2       where the odds have decreased lately for any chance of a

3       payoff.

4                 The second major issue is whether Progress

5       made a prudent decision back in 2006 or 2007 about the

6       sequencing of the licensing and procurement activities

7       for the Crystal River Unit 3 extended power uprate

8       project.  While both issues are significant, it is the

9       LNP decision that we believe deserves your most careful

10       consideration in this year's proceeding.

11                 The ramifications of your ultimate decision

12       are profound and will certainly impact Florida

13       customers' bills either positively or negatively for the

14       next ten to 15 years and beyond.  The evidence will be

15       fairly undisputed that the LNP project that you

16       authorized barely two years ago, two years ago this

17       month, has encountered a series of setbacks since those

18       euphoric days of the summers of 2008.  Literally days

19       after your August 8th issuance of your need order,

20       housing and financial crises plunged financial and

21       credit markets into turmoil, triggering a recession that

22       has been the worst since the Great Depression.  Recovery

23       has been slow, a domino effect on customer demand,

24       natural gas prices, and the appetite for any form of

25       carbon tax have materially undercut the very foundation

FLORIDA PUBLIC SERVICE COMMISSION

22

1       upon which the Levy need case was decided.

2                 Against this backdrop, the critical early work

3       authorization that was essential to meeting the then

4       fast track of the LNP project was denied by the NRC in

5       early 2009.  Together you will hear testimony these

6       events have put the LNP project into a tailspin.

7       Initially in May 2009 the company announced then just a

8       20-month delay in the in-service date of the LNP.

9       However, as 2009 progressed, that relatively significant

10       delay grew to a 24-month and then a 36-month delay in

11       those discussions in the North Carolina offices and

12       board room of the parent corporation.  Scenarios were

13       analyzed you will hear about, numbers were crunched.

14       The parent company's senior executives and the Progress

15       Energy parent board debated and decided that the

16       financials of the corporation would not support even

17       that significant three-year delay.

18                 Instead, it was back to the drawing board.

19       Look at 60 months, five years.  This was done.  The

20       senior management of the parent corporation and the

21       board settled upon what effectively is a minimum

22       five-year delay in any possible in-service date of the

23       plant.  This even took the option for nuclear generation

24       outside the window of the need determination that you

25       had just determined in 2008.  But importantly to

FLORIDA PUBLIC SERVICE COMMISSION

23

1       Progress Energy's shareholders, it provided a safe haven

2       for billions of dollars of the corporation's precious

3       capital.

4                 Sounds like a good deal; correct?  Well,

5       there's one tiny hitch.  The proposed scenario approved

6       by the board that they're asking for your endorsement of

7       comes at a steep price to Florida customers; not to

8       Progress, but to Florida customers.  They keep their

9       powder dry, they buy time to improve their financial

10       outlook.  The price instead is proposed -- the price for

11       continuing at this juncture of the project is proposed

12       to be paid by PEF's customers here in Florida.

13                 Let's look at the price tag for delay.  We

14       believe the evidence you will hear will show that if it

15       is even built, the overall project costs go from above

16       the original $17.2 billion number that you endorsed two

17       years ago to well above $20 billion, with the chance

18       that it could significantly increase another 10 percent

19       or more by PEF's own estimate.  Customers' bills in the

20       years before it goes into service, if it's ever built,

21       would be increased well above the, more than 50 percent

22       above the amount you were told in the 2008 hearing.

23       Base rates, base rates for Progress Energy's customers

24       in Florida would more than double by the time the two

25       LNP units would go into service in 2022.

FLORIDA PUBLIC SERVICE COMMISSION

24

1                 From 2010 to 2012 and during the minimum time

2       that construction of the project would be on hold, PEF's

3       customers will be asked to pay what amounts to a

4       retainer or option fee of more than $400 million just so

5       PEF can wait and see if conditions might get better so

6       they can consider taking the steps to restart the

7       stalled project.

8                 All of this real story is masked by the legal

9       speak of the testimony that follows, the statutory

10       formula that ensures that the company gets their money

11       upfront and what they really hope will be a rather

12       routine cost recovery docket.  What was once a robust,

13       fast-tracked construction project has been whittled down

14       to essentially the management of what remains of a

15       $7.6 billion contract that PEF rushed headlong to sign

16       in those heady days of 2008 when they really were taking

17       a vigorous and unambiguous step to build this nuclear

18       plant.  Back then they could look you in the eye and

19       tell you that they unequivocally were building a nuclear

20       power plant.

21                 Commissioners, we strongly urge and we plead

22       with you to read between the lines of what you hear

23       today in the evidence.  Listen to the subtle wording and

24       the shading in the wordings, the subtext.  Accept the

25       company's invitation that you've heard hear today to

FLORIDA PUBLIC SERVICE COMMISSION

25

1       critically evaluate the status of this project.  You

2       must glean from both the words and actions embodied in

3       the evidence enough information to make your own

4       decision and judgment about this project.

5                 You will hear live testimony in this hearing

6       from four outstanding nuclear engineers, three of them

7       testifying on the Levy project:  Our witness, Dr.

8       William Jacobs, and Jeff Lyash and John Elnitsky from

9       Progress Energy.  They all have impeccable credentials.

10                 Dr. Jacobs has extensive involvement in the

11       construction and startup of nuclear plants.  He is the

12       Georgia Public Service Commission's independent

13       construction monitor for the only nuclear plant project

14       that has actual safety-related construction underway.

15       And while it may be uncommon to hear an attorney from

16       the other side compliment the witnesses for another

17       side, I must state my admiration and respect for all

18       three of Progress Energy's excellent nuclear engineering

19       witnesses.  Jon Franke is a nuclear engineer you will

20       hear from in the CR3 portion of the document.

21                 In the Levy part of the case, however, you

22       cannot help but be impressed with the credentials,

23       experience, knowledge, passion, earnestness and

24       sincerity of these professionals.  If you're going to

25       contract for, procure and build a nuclear plant, these

FLORIDA PUBLIC SERVICE COMMISSION

26

1       are the people that you want to have working for you.

2       They're passionate about this project, they believe they

3       can build it.  They will tell you they know they can

4       build it.  They will tell you they want to build it.

5       They will even tell you they intend to build it.  But

6       they will not testify and they cannot testify that they

7       will build it.  They cannot say this and they will not

8       say this because they don't know for certain if

9       conditions will ever improve so that they can take the

10       steps to restart this project and build the plant.

11                 This case though is not about their

12       personalities.  You will hear a lot of testimony about

13       enterprise risks.  These are risks outside of their

14       control.  These are risks that are so great that they

15       have effectively caused the project to be on indefinite

16       hold until and only if these risks become such that the

17       Progress Energy Corporation board of directors take the

18       steps to authorize them to tell the contractor to

19       restart the project and proceed sometime maybe in 2013

20       or 2014 at the earliest based on what is basically a

21       guestimate.

22                 We believe you will see that at best this once

23       vibrant, robust LNP project is now very tenuous.  It's

24       effectively on life support, and someone has to decide

25       who will pay to continue to keep the patient alive.

FLORIDA PUBLIC SERVICE COMMISSION

27

1                 Progress has a proposal for you today, but you

2       have the last word on who pays.  Progress is willing to

3       keep its option alive and they describe it as an option

4       in their testimony, so long as the Florida customers pay

5       all of the 400 million plus hospital bill.  Otherwise,

6       management in North Carolina is unwilling to put any of

7       the shareholders' money on the line.

8                 In prefiled testimony, they appear to want to

9       give -- want you to give the unqualified blessing of

10       this Commission to submitting the bill to those

11       customers, all the while they concede that the project

12       may never be built.

13                 Dr. Jacobs testifies that PEF gave little or

14       no consideration to a scenario that PEF would spend over

15       $400 million of the customers' money, get a license to

16       build the plant and still cancel it.  The company has

17       now said that they were aware of this potential outcome

18       and implicitly considered it.  They will testify that

19       $400 million is but a small price to pay and that it is,

20       quote, clearly insignificant, close quote.  This

21       analysis is insensitive at best and inadequate at worst.

22       The customers deserve better.  They deserve your active

23       supervision and oversight.  They need for you to step in

24       and say, Progress, you must share in this gamble.  If

25       you want to ask your customers to support this project

FLORIDA PUBLIC SERVICE COMMISSION

28

1       in its current state, you must share in it equally at

2       least.  Public Counsel takes this position --

3                 CHAIRMAN ARGENZIANO:  Mr. Rehwinkel, you're at

4       your ten-minute mark.

5                 MR. REHWINKEL:  Okay.  This is the position of

6       the Office of Public Counsel, and I appreciate your

7       consideration.  Thank you.

8                 CHAIRMAN ARGENZIANO:  Thank you.

9                 MR. BREW:  Good morning, Madam Chairman,

10       Commissioners.

11                 CHAIRMAN ARGENZIANO:  Good morning.

12                 MR. BREW:  My name is James Brew.  I'm counsel

13       for PCS Phosphate in this proceeding.  PCS Phosphate

14       operates mining and fertilizer manufacturing facilities

15       over about 100,000 acres in Hamilton County.  The

16       operation is very energy intensive.  To put things in

17       perspective, PCS is about a 70-megawatt load that uses

18       as much electricity as a city of roughly 100,000 people.

19       We are one of the largest interruptible loads on the

20       Progress system, and Progress does cut us off in order

21       to preserve firm and reliable service to their firm

22       service customers.

23                 The PCS operation is also a source of

24       renewable energy in that we recapture waste heat from

25       manufacture of sulfuric acid to generate substantial

FLORIDA PUBLIC SERVICE COMMISSION

29

1       amounts of electricity with no incremental carbon

2       emissions.

3                 Now most important for the purposes of this

4       proceeding, PCS operates in a globally competitive

5       marketplace, and the cost of electric power is a big

6       component of our overall operating cost.  The decisions

7       you make in this docket very definitely affects our

8       economic competitiveness.

9                 It's also important, I think, to appreciate

10       that PCS does not have any particular interest for or

11       against nuclear power in general.  We do not bring any

12       preconceived agenda to these proceedings other than a

13       need for reliable and economically competitive power.

14                 Now I want to talk briefly about the Levy

15       project.  There are, as you know, three basic purposes

16       to these nuclear cost recovery proceedings:  To audit

17       the actual and estimated costs of the project, to

18       determine the prudence of costs that might be recovered,

19       and to assess the long-term feasibility of completing

20       the project.

21                 There is, as we know, a fourth essential

22       function of these proceedings, and that is how to

23       address the rate impacts of the project.  In 2008, the

24       Commission approved $418 million for recovery for the

25       project and deferred $198 million for later recovery.

FLORIDA PUBLIC SERVICE COMMISSION

30

1       Last year, the Commission approved $444 million for

2       recovery and agreed to spread the $273 million of those

3       costs over five years.  And so $60 million of the

4       amounts requested for recovery this year relate to the

5       amortization of last year's costs.

6                 Putting our position in the briefest terms,

7       Progress consumers can't afford Levy alone.  In this

8       docket we must come to grips with a monumental change in

9       the project.  It is now five years behind schedule, an

10       additional $5 billion over cost, over the original

11       estimate.  That brings the going in before construction

12       estimated installed cost of the two units up to

13       $22.5 billion.

14                 Now there are two major issues that a, that

15       accompany this cost and schedule increase.  First -- and

16       Progress offers at least three witnesses to talk about

17       enterprise risks.  Interestingly, none of those

18       enterprise risks include project management,

19       engineering, procurement, construction or all of the

20       other facets of construction where you normally expect

21       delays and cost increases to occur.  The point in all of

22       this is that Progress is trying to make it very clear

23       that they are not understating the going-forward risks

24       of this project and that those risks are, in fact,

25       increasing.

FLORIDA PUBLIC SERVICE COMMISSION

31

1                 Second, unlike last year, unlike in the need

2       case, Progress no longer claims that finalizing joint

3       ownership agreements is a top priority and just around

4       the corner.  The company concedes that for the

5       foreseeable future, and one would guess at least through

6       the receipt of a construction license but probably

7       beyond that, Progress and its ratepayers are on their

8       own.  Folks may talk about having a potential interest

9       in the future about investing in the Levy project, but

10       there is no one at this point that's been willing to

11       commit their capital to the project.

12                 So after we finish talking about the omitted

13       EPC contract, enterprise risks and Progress's three Levy

14       scenarios, we return to the core concern, which is the

15       level of customer rate impacts.  And the unaltered fact

16       that is not disputed is that these impacts are

17       thoroughly unacceptable even in a best-case scenario.

18       Also, waiting three or four years while the licensing

19       process follows its course will not lessen the project

20       cost or impacts but will throw another $450 million of

21       ratepayer money at the project.

22                 Given this outlook, which pretty much is not

23       in dispute between Progress and the Intervenors that

24       filed testimony, PCS urges the Commission to bring an

25       element of common sense to this process.  We believe

FLORIDA PUBLIC SERVICE COMMISSION

32

1       that the fundamental issue is that Levy is not viable

2       without significant joint ownership even in a best-case

3       scenario because the rate impacts will be too severe

4       long before the units approach in-service, and

5       especially because the best-case scenario is not a

6       particularly likely one.

7                 We also believe that the impact of the

8       schedule delay on Progress's inability to secure joint

9       ownership participation must be addressed before

10       Progress ratepayers are placed more at risk.

11                 Now let's briefly talk about the rate impacts

12       for a minute based on the information in this case.

13                 Based on what Progress has supplied, they now

14       estimate that the project costs at $22.5 billion, about

15       $8 billion of that would be recovered through the NCRC,

16       still leaving about $14 billion to go into base rates.

17       Now you take a 10 percent return on $14 billion taxes,

18       property taxes and depreciation, and we're looking at

19       $2 billion base rate increases when the units go into

20       service.

21                 What we do have from Progress is an estimate

22       that once the units go into service, the average cost to

23       your average residential customer is going to go up

24       about 700 bucks a year.  And in 2014 as part of the NCRC

25       recovery your average residential customer is going to

FLORIDA PUBLIC SERVICE COMMISSION

33

1       see increases of about 300 bucks a year.

2                 In the past two years, the Commission has

3       found ways to spread some of the rate impacts over time.

4       As the project spins up on its own, with Progress alone,

5       there's not going to be a way to spread those costs over

6       time.  We're going to have to confront them squarely,

7       and we think this is an issue that we have to deal with

8       now.

9                 With respect to joint ownership, Progress has

10       maintained that it has actively negotiated to find other

11       participants in this project.  And remember that since

12       the costs of the project aren't likely to really go

13       down, they're only likely to go up, the essential way

14       for mitigating rate impacts is to find others to share

15       in the costs and risks.  And Progress has maintained

16       that it's been actively discussing this with various

17       parties in Florida, but that it's needed greater

18       clarity.  Well, now they have a need determination, they

19       have Cabinet approval for the site, they filed their

20       application with the NRC, they negotiated an EPC

21       contract, they negotiated an amendment to the EPC

22       contract.  And instead of joint ownership being right

23       around the corner, now it's basically back burner, which

24       means that for the foreseeable future, Progress

25       ratepayers are on their own, and that's something that

FLORIDA PUBLIC SERVICE COMMISSION

34

1       has to be dealt with.

2                 Next, and ironically or perhaps most

3       importantly, the basic definition of prudence concerns

4       what a reasonable utility manager would do under the

5       same or similar circumstance.  Now in your average

6       prudence case that's usually clouded by the fact that

7       parties argue you can't apply hindsight information to

8       that determination.  Well, here we have spot on

9       comparisons.  Other Florida utility systems managers

10       that need to address their resource needs under the same

11       circumstances in Florida, including Florida's interest

12       in developing clean energy sources, have determined that

13       the known costs of Levy are too high, the risks are too

14       uncertain, and they are unwilling at this point to

15       commit their capital to the project.  So as opposed

16       to -- it's not so much that reasonable people can differ

17       on which option is optimal or best, but that other

18       Florida utility system managers have all actually

19       decided against project participation at this time.

20                 To sum up, it's our view that it's now

21       apparent that Levy is not viable with Progress as the

22       sole owner for the simple reason that the rate impacts

23       for Progress customers are too severe.  We do not see

24       any winners in a dynamic in which Progress shareholders

25       and consumers are effectively all in every year in these

FLORIDA PUBLIC SERVICE COMMISSION

35

1       proceedings over the cost of the project and the rate

2       impacts.  We do not see any ratepayer benefit in

3       spending another $450 million to arrive at exactly the

4       same point in three years.

5                 What we're recommending is that the

6       recommendations of the Public Counsel to look at other

7       options should be adopted.  And more importantly, that

8       absent executed agreements for joint ownership amounting

9       to at least 50 percent of the capacity of both units,

10       which is what PCS argued in the need case was required

11       since there was never a need for the second unit in the

12       first place, the Commission should not approve cost

13       recovery for anything besides licensing and that those

14       issues need to be addressed here.  Thank you.

15                 CHAIRMAN ARGENZIANO:  Thank you.

16                 Ms. Kaufman.

17                 MS. KAUFMAN:  Thank you, Madam Chairman,

18       Commissioners.

19                 I'm Vicki Gordon Kaufman, and I am here on

20       behalf of the Florida Industrial Power Users Group, and

21       you'll hear them referred to throughout the proceeding

22       by the acronym FIPUG.  I just wanted to take a moment

23       before I turn to Progress's request to tell you all a

24       little bit about FIPUG and who they are.

25                 FIPUG is a group of large industrial customers

FLORIDA PUBLIC SERVICE COMMISSION

36

1       throughout the state, and our members are engaged in

2       various and diverse endeavors such as phosphate mining

3       and production; air separation for use in hospitals;

4       grocery chains, which, as you can imagine, have very

5       large electrical loads; hospitals; cement companies; all

6       of whom are large, large consumers of electricity.

7                 These companies have several things in common.

8       One thing that they have in common is that they employ

9       people in the areas in which they are located, and FIPUG

10       members take service both in Progress and in Florida

11       Power & Light's territory, they contribute to the local

12       tax base of their communities for support of schools and

13       other services, they create jobs, and they support and

14       are trying to expand economic development in Florida,

15       which I think we all know is a big and important issue

16       in these economic times.

17                 The FIPUG members also have something else in

18       common, and that is that one of their largest variable

19       costs, and for many of them the largest variable cost

20       that they have when they try to plan their budgets and

21       plan for the future is the price of electricity.  And

22       when I talk about electricity, I'm not only talking

23       about base rates but about all the pass-through clauses

24       that appear on every customer's bill every month,

25       including the nuclear pass-through clause that you're

FLORIDA PUBLIC SERVICE COMMISSION

37

1       considering here.  And we know that those clauses are

2       now accounting for over half of customers' bills.

3                 So you'll see FIPUG here in this proceeding

4       and you will see them in other proceedings where you

5       consider issues related to whether the utilities are

6       appropriately pursuing the best course to ensure that

7       they deliver reliable and cost-effective power to the

8       ratepayers, and how their projects, including the ones

9       you're going to hear about today, what impact those

10       projects have on the rates that FIPUG members and all

11       consumers in Florida pay.

12                 I want to talk about the Levy project first,

13       and I'll try not to repeat what my colleagues have said

14       about it, which FIPUG agrees with their positions.  I

15       will tell you that FIPUG has very grave concerns

16       regarding this project and the amount of money that has

17       been spent and will be spent on it, including whether it

18       will ever be built and whether it will ever provide any

19       energy to ratepayers.

20                 Since your approval of the project in the

21       determination of need, the project has experienced delay

22       after delay, increase after increase, while the company

23       continues to receive complete recovery for every dollar

24       and while ratepayers pay the bill, retail ratepayers

25       only.

FLORIDA PUBLIC SERVICE COMMISSION

38

1                 The delays include the fact that the NRC

2       refused to issue Progress a limited work authorization

3       for certain activities, and this denial led to an entire

4       restructuring of the schedule for the project.

5       Currently, and I believe this is subject to many more

6       delays given the risks that Progress itself describes

7       through many of its witnesses, you have a project that's

8       five years behind schedule, $5 billion over budget, and

9       the first slab of cement has not been poured.

10                 At this point in time, as others have

11       mentioned and as you'll hear I think the Progress

12       witnesses talk about in some detail, the project faces

13       numerous risks and uncertainties, including licensing

14       and permitting issues, uncertainty in state and federal

15       energy policy, world and state economic conditions, and

16       these are only some of the risks.

17                 And as Mr. Rehwinkel has already described to

18       you, essentially Progress has this project on hold at

19       the ratepayers' expense until they -- as they continue

20       to see what their future may hold.  On top of this, as

21       Mr. Brew has alluded to, there is no joint ownership in

22       this project.  This joint ownership, were Progress able

23       to secure it, would certainly take some of the onus off

24       the retail ratepayers who now are bearing the entire

25       burden of the project.

FLORIDA PUBLIC SERVICE COMMISSION

39

1                 Now Mr. Lyash in his testimony describes the

2       status or maybe it's more correct to say the lack

3       thereof of the joint ownership situation, and he

4       basically says that the prospective joint owners need

5       greater certainty about the project.  And as I read his

6       testimony, he doesn't hold out any hope for joint

7       ownership any time in the near future.  Just as

8       prospective joint owners are evaluating the risks and

9       uncertainty, that's what's facing Florida's ratepayers

10       as well.  Potential joint owners see the risk and

11       they're unwilling to commit to it, essentially leaving

12       the retail ratepayers holding the bag here.

13                 Mr. Brew talked to you about rate impact, and

14       I have a feeling that that's something that we're going

15       to hear a lot about as we start the hearing.  The rate

16       impact of this project is significant, and I think you

17       need to look at the rate impact and balance it against

18       the grave uncertainty as to whether this project will

19       ever come to fruition and ever provide any benefits to

20       retail ratepayers.

21                 Now to summarize the difficulties that the

22       project has faced, but, as I said, Progress wants the

23       ratepayers to continue to pay every single dollar while

24       they have no -- someone said in this case, they have no

25       skin in the game.  The costs are simply passed through

FLORIDA PUBLIC SERVICE COMMISSION

40

1       to the retail ratepayers, and we think it's unfair to

2       continue to ask the ratepayers to bear the financial

3       burden of a project that may never materialize and has

4       faced one delay and one increase after another.

5                 So we would join in the recommendations that

6       my colleagues have given to you, and we would ask you to

7       do two things after you hear the testimony.  We would

8       ask you to continue, I mean, to consider deferring the

9       cost recovery of any future costs for this project until

10       we have a handle as to whether this project is ever

11       going to happen.  And then we also think you should take

12       a hard look at some kind of risk sharing mechanism so

13       that the ratepayers are not what I call the payer of

14       last resort in this situation.

15                 As you know, ratepayers, including FIPUG

16       members and all consumers, they don't have an option as

17       to where they can get their electric service and they

18       don't have an option as to what, what appears on their

19       bill.  That's your job to take a look at this and be

20       sure that the costs that are sought and that ultimately

21       the ratepayers pay are reasonable.  We believe you have

22       the authority to adopt a risk sharing mechanism, and I

23       know that's an issue that we're going to brief after the

24       hearing is over.

25                 As, briefly as to the uprate project, we have

FLORIDA PUBLIC SERVICE COMMISSION

41

1       a lot of concerns about this project as well.  We agree

2       with Mr. Rehwinkel, the costs pale in comparison to the

3       Levy project, but it's still important.  As I understand

4       it as we sit here today, Progress has not even submitted

5       its license amendment request or LAR to the NRC, which

6       it needs to proceed with the project.  So we would ask

7       you to thoroughly review Progress's activities in regard

8       to the management of this project and see whether there

9       are duplicate costs that may have been incurred in

10       regard to the work that Mr. Glenn mentioned that AREVA

11       has done on the, on the LAR and the revision of the LAR,

12       which I understand to still be in progress.

13                 Commissioners, this is an important docket,

14       its issues are vitally important to the ratepayers of

15       Florida, and FIPUG appreciates the opportunity to

16       present its views to you, and we know that you will

17       carefully consider them.  Thank you.

18                 CHAIRMAN ARGENZIANO:  Thank you.

19                 Mr. Jacobs or -- I'm sorry.

20                 MR. JACOBS:  Madam Chairman, Mr. Davis will

21       offer the -- one brief point.  I omitted entering an

22       appearance for Mr. James Whitlock as well on behalf of

23       the Southern Alliance for Clean Energy.

24                 CHAIRMAN ARGENZIANO:  Wonderful.

25                 MR. DAVIS:  Good morning, Madam Chair and

FLORIDA PUBLIC SERVICE COMMISSION

42

1       members of the Commission.

2                 CHAIRMAN ARGENZIANO:  Good morning.

3                 MR. DAVIS:  My name is Gary Davis, and I'm

4       here representing the Southern Alliance for Clean Energy

5       today.  Those of you who may not be familiar with SACE,

6       we have made a big investment in working with this

7       Commission in a number of documents.  SACE does this

8       throughout the southeast.  I'm honored to be on the

9       board of SACE as -- and serve with Mr. Jacobs in

10       addition to representing SACE here today.  We work with

11       Commissions throughout the southeast to promote

12       responsible energy choices, and that's why we're here in

13       this docket today.

14                 As you may know, we appeared last year as

15       well.  And the -- we're participating again to focus the

16       Commission on the basic point that, of the lack of

17       long-term feasibility of the Levy nuclear project.

18       We're not taking a position other than supporting the

19       position of OPC on the uprate project, but we're focused

20       entirely on Levy in this docket.

21                 Last year Progress was forced to acknowledge a

22       scheduled delay of 20 months and as compared to the

23       schedule that was the basis for the need determination

24       in 2008.  In the space of one year that schedule delay

25       has tripled, now we're talking 60 months or five years,

FLORIDA PUBLIC SERVICE COMMISSION

43

1       and the projected non-firm cost has grown from

2       $17.2 billion to $22.5 billion for the project.  That's

3       an over $5 billion increase, 31 percent, in one year.

4       So remember those two numbers, five and five, five

5       years, $5 billion in the space of one year.  So under

6       the current schedule, the Levy project would not be in

7       service until 2021, 2022.  That's beyond the ten-year

8       plan horizon of the utility.

9                 As I will discuss in a minute, SACE predicted

10       this would happen last year, but Progress refused to

11       acknowledge the possibility.  And now Progress has

12       acknowledged that the economics of nuclear construction

13       are highly uncertain even with the cost recovery from

14       the ratepayers, and they are asking for $148 million

15       just to preserve a place in line or, as Progress says,

16       preserve the nuclear option.

17                 Reserving a place in line has little value for

18       the Progress ratepayers because the line is leading

19       nowhere.  I call it the line to nowhere.  Progress has

20       presented you with a false choice today.  It's not a

21       choice where you are going to cancel the Levy project.

22       That's not your role.  It is entirely up to Progress to

23       decide whether to cancel.  Your role is to determine the

24       long-term feasibility of the project and to decide

25       whether the ratepayers of Progress are going to be on

FLORIDA PUBLIC SERVICE COMMISSION

44

1       the hook for more costs if the project proceeds.

2                 These costs are not reasonable or prudent and

3       that's another decision you have to make.  But if

4       Progress believes that the costs are reasonable from a

5       corporate perspective, then you have the choice of

6       saying to Progress in this docket, go ahead and take

7       that risk yourselves.  You're not canceling a nuclear

8       project if you determine that the Levy project is not

9       feasible in the long-term and if you determine that the

10       recovery of costs in the future are not reasonable.

11       That's again not your role.

12                 Now for the new Commissioners on the

13       Commission, I'm sure you're familiar with the cost

14       recovery rule at this point.  But just harking back to

15       the mission statement, your mission is to facilitate the

16       efficient provision of safe and reliable utility

17       services at fair prices.  So your job is not to make

18       sure that Progress's board decisions are validated.

19       It's really up to you to protect the consumers and the

20       ratepayers of Florida.  You swore to perform your duties

21       in an independent and objective manner.  This means that

22       you have the courage to form your own opinions, and that

23       no matter what the staff recommends, you will be

24       independent.  So -- and that includes going against

25       staff's recommendation if staff recommends that you

FLORIDA PUBLIC SERVICE COMMISSION

45

1       approve the long-term feasibility of the Levy nuclear

2       plant.

3                 The cost recovery clause and the long-term

4       feasibility requirement is not a hollow requirement.  I

5       want to emphasize how important it is, because the

6       nuclear cost recovery provision is an unprecedented,

7       extraordinary financial incentive for a utility like

8       Progress.

9                 As you know, generally construction costs

10       cannot go into the rate base until the plant starts

11       generating electricity.  But in this case with cost

12       recovery, the ratepayers pay upfront long before any

13       electricity is generated, and they pay whether or not

14       the unit is ever completed.  So this transfers the risk

15       from the utility to the ratepayers.  In return for this

16       extraordinary incentive, you have every year the

17       responsibility to determine whether the project is still

18       in the interest of Florida ratepayers, and you have to

19       determine whether a nuclear project is still feasible so

20       that it is reasonable to recover the costs from the

21       ratepayers.

22                 Again, the Commission doesn't decide to cancel

23       a reactor.  If Progress is unwilling to accept that

24       yearly scrutiny, then the utility can build the Levy

25       project without cost recovery.  I mean, that's the

FLORIDA PUBLIC SERVICE COMMISSION

46

1       choice.  And so, again, it's a quid pro quo; in exchange

2       for the cost recovery, you have the scrutiny that you

3       apply in this nuclear cost recovery docket each year.

4       Now the company has indicated that it would not place

5       that risk on its shareholders without cost recovery.

6       But, I mean, again, that's the company's choice, not

7       yours.

8                 You will hear a lot of testimony from Progress

9       about how it has weighed and will continue to weigh

10       enterprise risks to determine whether it should move

11       ahead with the reactors.  The company does this for its

12       own business purposes and it has its own business-based

13       equation in doing that.  You have your own equation that

14       you have to follow in this docket for the protection of

15       the Florida ratepayers.

16                 Keep in mind that Progress has a very strong

17       incentive to continue with this project because the Levy

18       project will more than double the company's rate base,

19       and that is the rate base upon which, as Mr. Brew

20       pointed out, the return on equity is based and the

21       consumers actually will ultimately get billed.  Let me

22       say that one more time.  This project would double, more

23       than double the Progress rate base.  It would also boost

24       rates to Progress ratepayers by $40, more than $40 per

25       1,000 kilowatt hours per month in 2020 before one

FLORIDA PUBLIC SERVICE COMMISSION

47

1       kilowatt hour of electricity is ever generated by the

2       unit.

3                 So, again, the Commission has its own risk

4       equation.  It's not bound by the one Progress has used

5       to evaluate its enterprise risks.  Enterprise by

6       definition is Progress's business.  The burden in this

7       proceeding is on Progress though to convince you that

8       the project is feasible in the long-term and that it's

9       reasonable to keep those risks on the ratepayers.  It's

10       not up to OPC, it's not up to FIPUG, it's not up to SACE

11       to make that demonstration otherwise.  It's up to

12       Progress to demonstrate to you that the project is

13       long-term, feasible and that the costs should be put on

14       the ratepayers.

15                 We have presented in this docket two expert

16       witnesses, their testimony has been prefiled, and these

17       are two witnesses who testified last year:  Dr. Mark

18       Cooper, who testifies primarily about the economic risks

19       and the other risks such as the regulatory risks as we

20       proceed forward, and we also have Mr. Arnold Gunderson,

21       who is a nuclear engineer who was part of the nuclear

22       boom and bust of the 1970s and actually licensed plants

23       and managed construction projects like these in the

24       '70s, and he tells, as he did last year, a cautionary

25       tale about any nuclear engineer who's going to come into

FLORIDA PUBLIC SERVICE COMMISSION

48

1       a proceeding like this and predict with certainty the

2       future is rosy for this plant or any other plant.

3                 If you read Mr. Gunderson's testimony from

4       last year and Dr. Cooper's testimony from last year as I

5       do, I have to say we told you so as far as where we are

6       this year.  Progress has attacked their credibility in

7       the rebuttal testimony you'll hear, but their

8       credibility is firmly established by the fact that they

9       predicted the situation we're in a year later last year.

10                 And they predicted extended delays, they

11       predicted these risks that Progress has discussed in

12       detail.  As a matter of fact, if you read Progress's

13       testimony from this year, particularly the petition

14       itself, it reads like SACE's testimony last year except

15       that the conclusion is different.  So I submit to you

16       that the credibility of these witnesses is in the truth

17       of what they said last year.  And if you'll please pay

18       close attention to their testimony this year -- they

19       won't be here for cross-examination, so I encourage you

20       to read what they said and to look at their exhibits.

21                 I won't go through a summary of their

22       testimony, but suffice it to say that they both

23       recommend again not that the Commission cancel the Levy

24       nuclear project, but that the Commission find that it's

25       not long-term feasible and deny any future costs for

FLORIDA PUBLIC SERVICE COMMISSION

49

1       cost recovery for the project as not reasonable.

2                 It -- Dr. Cooper does recommend that the

3       nuclear option be evaluated in the future but not

4       through licensing.  Both of them talk about the proposal

5       by Progress, which is to spend money to obtain a license

6       for the nuclear plant as either line sitting or site

7       banking, but it's basically, as they call it, preserving

8       an option.  And both of our experts talk about how that

9       option is not worth the cost that it will cost the

10       ratepayers to preserve.

11                 And just let me close on why that is.  If

12       Progress goes through the licensing process and spends

13       the 400 million or whatever it will cost to get through

14       that process and then cancels the project, the option

15       has no value.  If Progress cancels the project at some

16       point in the future, the option has no value.  So what

17       does that option cost as compared to canceling the

18       project now?  Well, the testimony will show that it

19       costs at least one and a half times more to preserve

20       that option through the licensing process than it does

21       to cancel the project now.  So you'll see that that is a

22       false promise and is of little value to the ratepayers

23       of the State of Florida if the project is ultimately

24       canceled.

25                 CHAIRMAN ARGENZIANO:  And you are at your

FLORIDA PUBLIC SERVICE COMMISSION

50

1       ten-minute mark.

2                 MR. DAVIS:  I'm going to close.  Thank you

3       very much.

4                 CHAIRMAN ARGENZIANO:  Okay.

5                 MR. DAVIS:  Just we again request that the

6       Commission exercise your oversight role in this case and

7       put an end to this waste of the ratepayers' hard-earned

8       money.  Thank you.

9                 CHAIRMAN ARGENZIANO:  Thank you.

10                 Okay.  I guess we're -- Keino.

11                 MR. YOUNG:  Yes, Madam Chairman, two things.

12       FEA is present at the hearing and has informed me that

13       they wish not to make an opening statement but request

14       to be excused from the hearing.

15                 CHAIRMAN ARGENZIANO:  Okay.  I'll allow that.

16                 Are we ready for our witnesses?

17                 MR. YOUNG:  Second thing, Madam Chairman,

18       before we get to the witnesses, staff would request that

19       at this time we move in the Comprehensive Exhibit List,

20       which is identified as Exhibit Number 1.

21                 CHAIRMAN ARGENZIANO:  Show that moved.

22                 (Exhibit 1 admitted into the record.)

23                 MR. YOUNG:  Also, staff would request that

24       staff's stipulated exhibits, which is identified as

25       61 through 76 and it begins on page, page 8 of the

FLORIDA PUBLIC SERVICE COMMISSION

51

1       Comprehensive Exhibit List, be entered into the record

2       at this time.

3                 CHAIRMAN ARGENZIANO:  Show that entered.

4       61 to 76, did you say, Keino?

5                 MR. YOUNG:  76, yes, ma'am.

6                 (Exhibits 61 through 76 marked for

7       identification and admitted into the record.)

8                 CHAIRMAN ARGENZIANO:  Anything else?  Keino,

9       is that it?

10                 MR. YOUNG:  At this time, Madam Chairman,

11       staff would request that you rule on whether FEA can be

12       excused from the hearing at this time.

13                 CHAIRMAN ARGENZIANO:  Yes.  Let's show that

14       they can leave.  Thank you.

15                 I think we're ready for our witnesses.  And if

16       we can go, if we can get our -- we're going to have our

17       little color-coded five-minute timer on.  And for the

18       witnesses, we're going to need to swear you in, but we

19       will, when you see the red, please sum up your

20       discussion.  We need all witnesses to stand.  We need to

21       swear in your oath.

22                 (Witnesses collectively sworn.)

23                 Thank you.  If any new witnesses come, please

24       let us know if they have not been sworn in.  And let's

25       move on to our first witness.  I guess Mr. Garrett has

FLORIDA PUBLIC SERVICE COMMISSION

52

1       been excused, so it's Mr. Foster.

2                 MR. YOUNG:  Madam Chairman, just a reminder to

3       the parties, as per the Prehearing Officer's ruling,

4       opening statements shall not exceed five minutes.

5                 CHAIRMAN ARGENZIANO:  Yes.  And we have the

6       little light there to show you.  Thank you.

7                 COMMISSIONER EDGAR:  Madam Chair, do we need

8       to enter Mr. Garrett's testimony?

9                 CHAIRMAN ARGENZIANO:  Yes, we do.

10                 MS. HUHTA:  Madam Chairman, if I may be

11       recognized.

12                 CHAIRMAN ARGENZIANO:  Where are we?  Oh, I'm

13       sorry.

14                 MS. HUHTA:  Madam Chairman, Ms. Blaise Huhta

15       from Progress.  We would just move that Mr. Garrett's

16       testimony of March 1st, 2010, would be entered into the

17       record as though read.  He has been excused by

18       stipulation of the parties.  Mr. Garrett also had

19       Exhibits WG-1 and WG-2, staff's comprehensive Exhibits

20       2 and 3 on the Comprehensive Exhibit List.  We would ask

21       that those also be moved into evidence.

22                 CHAIRMAN ARGENZIANO:  Show those moved.  Thank

23       you.

24                 (Exhibits 2 and 3 marked for identification

25       and admitted into the record.)

FLORIDA PUBLIC SERVICE COMMISSION

71

1                 MS. HUHTA:  Progress's next witness is

2       Mr. Foster.

3                 CHAIRMAN ARGENZIANO:  Good morning.

4                 THE WITNESS:  Good morning.

5                 MS. HUHTA:  May I proceed?

6                 CHAIRMAN ARGENZIANO:  Yes, please.

7                 MR. HUHTA:  Thank you.

8                           THOMAS G. FOSTER

9       was called as a witness on behalf of Progress Energy

10       Florida and, having been duly sworn, testified as

11       follows:

12                          DIRECT EXAMINATION

13       BY MS. HUHTA:

14            Q.   Mr. Foster, will you please introduce yourself

15       to the Commission and provide your address.

16            A.   My name is Thomas Geoffrey Foster.

17       My business address is 299 First Avenue North,

18       St. Petersburg, Florida.

19            Q.   And you have already been sworn in as a

20       witness; correct?

21            A.   Yes.

22            Q.   Who do you work for and what is your position?

23            A.   I work for Progress Energy Services Company as

24       the Supervisor of Regulatory Planning.

25                 CHAIRMAN ARGENZIANO:  Excuse me.  Someone, can

FLORIDA PUBLIC SERVICE COMMISSION

72

1       you turn off your cell phone?  Thank you.

2                 THE WITNESS:  Do you need me to repeat, or --

3                 CHAIRMAN ARGENZIANO:  If you would, please.

4                 THE WITNESS:  Okay.  I work for Progress

5       Energy Service Company as the Supervisor of Regulatory

6       Planning.

7       BY MS. HUHTA:

8            Q.   And, Mr. Foster, have you filed prefiled

9       direct testimony and exhibits in this proceeding?

10            A.   Yes.

11            Q.   And do you have a copy of that March or

12       April 30th, 2010, testimony and exhibits with you?

13            A.   Yes.

14            Q.   And do you have any changes to make to your

15       prefiled testimony and exhibits today?

16            A.   No.

17            Q.   And if I asked you the same questions in your

18       prefiled testimony today, would you give the same

19       answers that are in your prefiled testimony?

20            A.   Yes.

21                 MS. HUHTA:  We request, Madam Chair, that the

22       prefiled testimony of Mr. Foster be moved into evidence

23       as if it was read in the record today.

24                 Thank you.

25

FLORIDA PUBLIC SERVICE COMMISSION

99

1       BY MS. HUHTA:

2            Q.   Mr. Foster, do you have a summary of your

3       prefiled testimony?

4            A.   Yes.

5            Q.   And will you please provide that summary to

6       the Commission?

7            A.   Yes.

8                 Good morning.  My name is Thomas Geoffrey

9       Foster.  My direct testimony presents PEF's estimated

10       actual costs for the Levy nuclear project and Crystal

11       River 3 uprate for the periods of January 2010 through

12       December 2010.  I also present projected costs for these

13       projects for the period January 2011 through

14       December 2011, as well as the total estimated revenue

15       requirements for these projects for the purpose of

16       setting the 2011 rates in the capacity cost recovery

17       clause.  I'm available to answer any questions related

18       to my testimony.  Thank you.

19                 MS. HUHTA:  We would tender Mr. Foster for

20       cross.

21                 MR. YOUNG:  Madam Chairman, just two

22       clarifications, one on the Garrett testimony --

23       exhibits.  Just to clarify, you did move those into

24       evidence.

25                 CHAIRMAN ARGENZIANO:  They were moved, yes.

FLORIDA PUBLIC SERVICE COMMISSION

100

1       They were moved into evidence.

2                 And Mr. Rehwinkel.

3                 MR. REHWINKEL:  Yes.  Madam Chairman, Charles

4       Rehwinkel with the Office of Public Counsel.

5                 Before I undertake to cross-examine

6       Mr. Foster, I would like to note for the record that,

7       that as part of the agreement to not cross-examine

8       Mr. Garrett, we asked that the company make Mr. Foster

9       available to answer certain questions that we would have

10       asked of Mr. Garrett.  So I may have some questions that

11       are outside of his direct testimony per agreement with

12       the company.  So if you'll bear with me, I'd appreciate

13       it.

14                          CROSS EXAMINATION

15       BY MR. REHWINKEL:

16            Q.   Good -- still morning.  Good morning,

17       Mr. Foster.

18            A.   Good morning.

19            Q.   First of all, is it your testimony that the

20       information that you have testified to today is, is

21       up-to-date and accurate to the best of your knowledge?

22            A.   It's up -- it's a projection.  So since the

23       projection, there have been actuals that come in, but I

24       don't know of anything that would materially change.

25            Q.   Okay.  Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

101

1                 MR. REHWINKEL:  Madam Chairman, I would like

2       to start off and pass out two exhibits for

3       cross-examination purposes.  One is not confidential and

4       the other is.

5                 The first exhibit is the company's response to

6       Public Counsel's third set of interrogatories,

7       Interrogatory Number 47, and the second is PEF's

8       response to staff Interrogatory Number 29.  That has

9       been identified as Exhibit 76 of the staff's stipulated

10       exhibit list.  What I am not sure about is whether the

11       staff's document is confidential or not or if it's the

12       redacted version.

13                 MR. YOUNG:  It's the redacted version.

14                 MR. REHWINKEL:  Okay.  So what I've asked to

15       be identified is the confidential version of 76, of

16       interrogatory -- the company's response to Interrogatory

17       29.  So I guess what I need first is a number.

18                 CHAIRMAN ARGENZIANO:  And you said the number

19       was --

20                 MR. REHWINKEL:  For the exhibit.

21                 MR. YOUNG:  It will be 188.

22                 CHAIRMAN ARGENZIANO:  188.  Thank you.

23                 (Exhibit 188 marked for identification.)

24                 MR. YOUNG:  Starting at 188 on page 21.

25                 MR. REHWINKEL:  So the non -- the

FLORIDA PUBLIC SERVICE COMMISSION

102

1       Interrogatory 47 would be 188, and Interrogatory 29,

2       staff's 29, would be 189?

3                 CHAIRMAN ARGENZIANO:  189.

4                 (Exhibit 189 marked for identification.)

5                 MR. YOUNG:  Point of clarification, Madam

6       Chairman.  Does Mr. Rehwinkel want a new identification

7       number, exhibit identification number for the red

8       confidential exhibit?  Because it is a part of staff

9       Exhibit Number 76, although it's the redacted version.

10                 MR. REHWINKEL:  Because it is the, because it

11       is the unredacted version, I think we would need a new

12       number.

13                 CHAIRMAN ARGENZIANO:  New number.

14                 MR. REHWINKEL:  And it is possible, if we

15       don't inquire about any information that is

16       confidential, then I would not move this document into

17       evidence, which would be my preference if we can avoid

18       it.

19       BY MR. REHWINKEL:

20            Q.   Okay.  After the logistics, Mr. Foster, do you

21       have the two documents, Exhibit 188 and 189, in front of

22       you?

23            A.   Yes, I have the two documents.

24            Q.   Now, Exhibit 188, are you familiar with this

25       document?

FLORIDA PUBLIC SERVICE COMMISSION

103

1            A.   Let me just make sure, because they -- forgive

2       me.  I'm not as good at listening to exhibit numbers.

3       But are you referring to the staff or, I'm sorry,

4       Citizens' Interrogatory Number 47?

5            Q.   Yes, sir.

6            A.   Yes, sir, I am.

7            Q.   Okay.  This is an interrogatory response that

8       was prepared by you or under your direction?

9            A.   That is correct, sir.

10            Q.   Okay.  My question to you is Exhibit 188

11       shows -- well, let me ask your interpretation of what

12       this shows from the standpoint of a customer's bill in

13       year 2021.

14            A.   Year 2021.  It estimates that the NCRC impact

15       will be approximately 25.69, that there will be a base

16       rate component of about 28.70, and that when compared to

17       a gas, an all gas type scenario, there will be estimated

18       fuel savings of about 7.45 in that, that year.

19            Q.   You say 7.45.  You mean $7.45?

20            A.   Yes, sir.  Sorry.

21            Q.   Okay.  That's okay.  Now, the -- and so the

22       estimated rate impact of Levy capital additions line,

23       $54.39, that's the, that is just the base rate and the

24       NCRC impacts added together?

25            A.   That's correct, sir.

FLORIDA PUBLIC SERVICE COMMISSION

104

1            Q.   Okay.  And then for the years 2022 and 2023,

2       well, for, for 2022, that would be a full year of Levy

3       Unit 1 and a partial year of Levy Unit 2?

4            A.   Yes, sir.

5            Q.   Okay.  And then for the year 2023, a full

6       year, actually most of the units in service, most of the

7       full impact of the units in service would be $68.65?

8            A.   I think, I think the ongoing impact in base

9       rates is the 67.71.

10            Q.   Okay.

11            A.   And then there was in that year shown a

12       94-cent NCRC rate impact.  And you'll have to forgive

13       me.  There's a lot of numbers in here and I'm trying to

14       remember exactly why that was, but off the top of my

15       head I'm --

16            Q.   Okay.  So the year 2024 has no NCRC impact,

17       and is the clean base rate impact, if you will, of the

18       two units?

19            A.   That is an estimate of the clean additive base

20       rate impacts.  And I say that because in this, as I

21       recall, there was not an assumption of perfect

22       ratemaking or anything where if something went in back

23       in 15, it's been depreciated and all that good stuff.

24       It's kind of a, just an additive, so.

25            Q.   Okay.  So your fuel savings impact of $26.85,

FLORIDA PUBLIC SERVICE COMMISSION

105

1       can you tell me what the basis for that is?  And I'm

2       looking in the year 2024.

3            A.   Yes, sir.  Well, my understanding, and I

4       didn't conduct these analyses, Mr. Lyash may be a better

5       witness on some of how they compare those things, but my

6       understanding is you do a run against the two scenarios,

7       you've got one with Levy and one without where you have

8       to have additional gas.  And it estimates, using a lot

9       of assumptions, what the fuel costs will be out in

10       future years.

11            Q.   And do you have Exhibit 189 with you, the

12       confidential?

13            A.   And that's 29?

14            Q.   Number 29, yes.

15            A.   Interrogatory Number 29?  Yes, sir, I do.

16            Q.   Yes.  Now, for -- what is the difference in

17       your opinion -- are you familiar with Exhibit 189?

18            A.   Yes, sir, I am.

19            Q.   Okay.  Did you assist in the preparation of

20       this response to the staff interrogatory?

21            A.   Yes, sir, I did.

22            Q.   What is the difference in your opinion between

23       the results that are shown between Exhibit 188 and

24       Exhibit 189 with respect to the results?

25            A.   And, again, as it gets into -- because some of

FLORIDA PUBLIC SERVICE COMMISSION

106

1       these are based off of runs that were used in

2       feasibility and whatnot.  And as it gets to that, I

3       defer to Mr. Lyash.  He's really our witness on that.

4                 But my understanding of, if you're thinking

5       about deltas in rate impacts, Interrogatory, let me make

6       sure I get this right, Number 29, is more of a full view

7       of what you expect the system to be doing in those

8       years.

9                 And whereas Interrogatory Number 47 was just a

10       simple, hey, give us the base rate impacts of having

11       Levy, it was not necessarily specifically a comparison

12       of two scenarios.  Whereas, I believe 40, I'm sorry, 29,

13       was specifically asked to be a comparison of two

14       scenarios and so included things like projected future

15       environmental costs.

16                 And I'm certainly not the expert on how you

17       derive future environmental costs, but we have a

18       process, and I'm sure Mr. Lyash would be happy to go

19       into detail on that, if needed.

20            Q.   Okay.  So if I looked on page -- well, if

21       you'd look at Exhibit 189, which is staff's 29, at the

22       very bottom right-hand corner of the page there's some

23       numbering that says FPSC ROG 8-29-4.  Do you see that?

24            A.   Yes, sir, I do.

25            Q.   And is this the page you'd go to to see kind

FLORIDA PUBLIC SERVICE COMMISSION

107

1       of the bottom line results of the analysis that was

2       requested by the staff?

3            A.   Yeah.  This is kind of a good summary of the

4       impacts of the two scenarios over time, I would say.

5            Q.   Okay.  And for the years '21 and '22, you see

6       for, in the last column, column five, $29 and $25.12 for

7       the 2021 and 2022 respectively; is that correct?

8            A.   Yes, sir.

9            Q.   Okay.  And those would be what you would

10       compare, those two year results on Exhibit 188, to get

11       the difference between what you consider the full

12       ratemaking impact versus just the incremental impact of

13       Levy Units 1 and 2 in base rates?

14            A.   I'd say it's a good proxy.  I mean, I'll tell

15       you, in the 189 -- I'm getting it, I've almost got them

16       figured out here -- there's small differences.  Again, I

17       told you on question 47 we did not assume perfect

18       ratemaking, but for the purposes of this we did.  We

19       went ahead and depreciated it.  And, you know, when

20       you're going out many years, you kind of have to make

21       that assumption.  So, but generally comparable, you

22       know, maybe some little differences for things like

23       that.  Does that make sense?

24            Q.   Yes.  And when you said this, you meant 189,

25       or --

FLORIDA PUBLIC SERVICE COMMISSION

108

1            A.   I apologize.  189 assumes perfect ratemaking.

2       Yes, sir.

3            Q.   Okay.  When you say perfect ratemaking, you

4       mean running the, the revenue requirements associated

5       with the Levy plant in, into a calculation that also

6       includes other system offsets like plant retirements or

7       plant additions?

8            A.   There's some of that.  What I really mean with

9       perfect ratemaking is on Exhibit 188, again, let's say,

10       you know, in 2015 you had a base rate impact of 314.

11       Well, in 2022, it's just left in there as 314.  We just

12       kind of added up the years.  Versus in reality, I sure

13       hope sales have gone up by the time you get to, out to

14       2022, or I would expect if we get back to some kind of a

15       normal economic situation, you'll have had some

16       depreciation on those assets so their basis will be

17       lower.  But we just didn't try to make assumptions for

18       when different rate cases might occur.  In these types

19       of analysis, you do that kind of for everything, so --

20            Q.   Meaning, meaning 189?

21            A.   189.  I apologize.  I'll get the hang of it, I

22       promise.  But you kind of have to because you're going

23       out 50 years, and it will just -- it wouldn't be, it

24       just wouldn't make sense otherwise, so.

25            Q.   Now do you know if this, this type of

FLORIDA PUBLIC SERVICE COMMISSION

109

1       analysis, meaning what you did for, to respond to staff

2       29 in Exhibit 189, was performed in the need

3       determination?  Do you have any knowledge about that?

4            A.   I don't remember.  I don't remember

5       specifically on that.  It's been a couple of years.

6            Q.   Okay.

7            A.   I know, I know -- what I know is these outputs

8       are links to the same type of analysis done on the

9       feasibility, so I'm just not sure if they converted it

10       to this specific table.

11            Q.   Okay.

12            A.   Does that make sense?

13            Q.   Yes.  And so I would ask you, do you know

14       whether the analysis that was presented to the

15       Commission was more akin to what is in 188 versus what

16       is in 189 with respect to ratepayer billing?

17            A.   Just a second.  I believe it was more akin to

18       188 than 189, yes, sir.

19            Q.   Okay.

20            A.   But if there's a specific document you want me

21       to look at and refresh, I'm happy to do that.

22            Q.   Yes.

23                 MR. REHWINKEL:  Madam Chairman, I'd like to

24       ask for an exhibit to be marked for identification.  And

25       this is, it has a red cover on it and it says it's

FLORIDA PUBLIC SERVICE COMMISSION

110

1       confidential but it is not.  These are excerpts from the

2       2008 need determination.

3                 CHAIRMAN ARGENZIANO:  Okay.  So that is not

4       confidential, and it would be marked as --

5                 MR. REHWINKEL:  Yeah.  So everybody who has a

6       copy of it can put "non" above the word "confidential"

7       and ignore the red.  And so could I get a number for

8       this?

9                 CHAIRMAN ARGENZIANO:  190.

10                 MR. REHWINKEL:  1-9-0?

11                 CHAIRMAN ARGENZIANO:  Thank you.

12                 (Exhibit 190 marked for identification.)

13                 MR. REHWINKEL:  And I apologize, Madam

14       Chairman.  I did not number this exhibit and I should

15       have.  I thought that I had taken care of that, but I

16       did not.  The short title of this would be Excerpts from

17       PEF 2008 Need Determination for this exhibit.  And what

18       I would like to direct Mr. Foster to once the exhibits

19       have been handed out is the very beginning of the

20       exhibit is testimony filed on March 11, 2008, by Javier

21       Portuondo on behalf of Progress Energy.

22       BY MR. REHWINKEL:

23            Q.   Are you familiar with this testimony,

24       Mr. Foster?

25            A.   I'm somewhat familiar.

FLORIDA PUBLIC SERVICE COMMISSION

111

1            Q.   Okay.

2            A.   I mean, I wouldn't -- it's not my testimony,

3       but I'm somewhat familiar with it, yes, sir.

4            Q.   Okay.  And it is 12 pages of testimony

5       followed by a blank page and then an Exhibit JP-1, and

6       then followed by JP-2 and 3.

7            A.   I'm there.

8            Q.   Would you, would you have participated in the

9       preparation of these exhibits?

10            A.   I did participate in this, yes, sir.

11            Q.   Okay.  So on JP-1 we see, for Levy Units 1, 2,

12       and Transmission, for various years residential rate

13       impacts in the, in three boxes.  Do you see that?

14            A.   Yeah.  And I think I maybe can answer your

15       question now.

16            Q.   Yes.

17            A.   If you want me to go ahead.  So if you're to

18       look at 188, it's consistent with looking at the

19       addition of Levy 1, 2, and Transmission.

20            Q.   Okay.

21            A.   And as you can see, there's not an adjustment.

22       Say, you know, the 2015 assumption around Transmission,

23       there's not an adjustment to say, oh, in 2016 it would

24       have been depreciated, a lower basis, and therefore a

25       lower return.

FLORIDA PUBLIC SERVICE COMMISSION

112

1                 So, so to answer your question, these are on a

2       consistent basis.  Yes, sir.

3            Q.   Okay.  So if I looked at -- if I went past

4       Exhibits JP-1, 2 and 3, there is an interrogatory,

5       actually it is a late-filed deposition exhibit for

6       Mr. Portuondo for that docket, and then the late-filed

7       deposition exhibit, late-filed deposition Exhibit Number

8       5, we see the three numbers that you see on JP-1 and

9       spread on 2015, 2016 and 2017; is that right?

10            A.   That is accurate.

11            Q.   Okay.  So this presentation on JP -- well, on

12       Mr. Portuondo's late-filed Exhibit 5 that was in the

13       2008 need determination would be an apples to apples

14       comparison to the number in 188.  Is that fair?

15            A.   Let me just think about it for a second.

16            Q.   Sure.

17            A.   I, let me, I guess, clarify.  It's on a

18       consistent basis as what we presented in 188.  However,

19       I would note that, that there are two sections to

20       late-filed Exhibit Number 5.  The top section is the

21       capacity cost recovery clause, or NCRC really, rate

22       impacts.  And that gets, that's a total estimated

23       residential rate impact.  And then the bottom part is

24       base rate impacts, and it's talking about specific

25       annual increases versus the total impact.

FLORIDA PUBLIC SERVICE COMMISSION

113

1                 So, I guess, to get to the 67.71, I just want

2       to make sure it's clear, you have to add up the 7, 26

3       and 18.  Does that make sense, sir?

4            Q.   Yes.  Yes.  Okay.

5            A.   A little bit of a presentation difference, but

6       at its heart they're the same representation.

7            Q.   But these are roughly equivalent or comparable

8       numbers, if you add those three on JP-5 --

9            A.   To the 67.71 on Exhibit 188?

10            Q.   Yes.

11            A.   I would agree with that, yes, sir.

12            Q.   Okay.  Now let me ask you to go back into

13       Mr. Portuondo's testimony, on page 8 of that testimony.

14            A.   Give me a second, please.

15            Q.   Actually pages 7 and 8.

16            A.   I'm on 7.

17            Q.   Okay.  There is a question there.  It says,

18       "What is your current estimate of the impact on an

19       average retail customer bill while the plants are under

20       construction?"

21                 And then the answer on page 8 says, "The

22       estimated impact on an average retail customer bill is

23       expected to range from $6.43 in 2009 to $24.75 in 2015

24       per 1,000 kWh."  Do you see that?

25            A.   I do see that, yes, sir.

FLORIDA PUBLIC SERVICE COMMISSION

114

1            Q.   Okay.  And are those numbers shown on the

2       late-filed deposition Exhibit 5 that's included in

3       Exhibit 190?

4            A.   Yes, sir, they are.  Oh, I'm sorry.  Forgive

5       me.  I got -- I think I misheard you.  Could you restate

6       your question?

7            Q.   Yeah.  My question is are the $6.43 that are

8       in Mr. Portuondo's testimony that we just looked at on

9       pages 7 and 8, are they shown on the late-filed Exhibit

10       5 that is included in 190?

11            A.   Okay.  Okay.  Got you.  Oh, okay.  Okay.  Got

12       you.  Sorry.  And, again, I'm still getting used to it.

13       I was thinking that this 47 was the late-filed.

14            Q.   We'll get to 47.  I'm not talking about that

15       right now.

16            A.   But, no.  Yes.  Yes, they are, sir.

17            Q.   Okay.  And what this shows in 2015, the

18       $24.75 is, is the, the NCRC impact, the year before the

19       projected, the then projected 2016 in-service date of

20       Unit 1.  Is that fair?

21            A.   Yes, that's fair.

22            Q.   Okay.  Now let's turn to 189, which is the

23       response to staff's 29.  Do you have that?

24            A.   189.  Yes, I do, sir.

25            Q.   Yeah.  Okay.  Now this shows on page, on the

FLORIDA PUBLIC SERVICE COMMISSION

115

1       page 29-4, the one, the page that has the results --

2            A.   Yes, sir, I'm there.

3            Q.   -- for the years 2019 and 2020, those are the

4       two years before the projected in-service date of

5       2021 under the revised scenario for the Levy project; is

6       that correct?

7            A.   Yes, sir.

8            Q.   Okay.  So for 2020, which is the year before

9       the unit goes into service, you see $38.48.

10            A.   For which year?  I'm sorry.

11            Q.   For 2020.

12            A.   Yes, I do, sir.

13            Q.   Okay.  Now that's -- what is the difference

14       between that 38.48 as the year before the in-service

15       date in 2020, 2020 versus the 24.75 that is the year

16       before the then in-service date under the original Levy

17       nuclear plant schedule?  Do you understand my question?

18            A.   I think I understand your question.  Yes, sir.

19            Q.   Okay.

20            A.   And I'll tell you, fundamentally what's the

21       difference?  The project costs or the investment in the

22       project is higher in 2020 than it would have been in our

23       estimates in the need in 2015.  As far as what goes into

24       that, that's something you should speak to Mr. Lyash

25       about, but, that's, you know, at its heart.

FLORIDA PUBLIC SERVICE COMMISSION

116

1            Q.   Okay.  Thank you.

2                 MR. REHWINKEL:  I'm going to tackle an easy

3       issue before I get into a more difficult one.  I would

4       like to, Madam Chairman, pass out another exhibit for

5       cross-examination purposes.

6                 THE WITNESS:  Can I put these to the side

7       or --

8                 MR. REHWINKEL:  Yes.

9                 CHAIRMAN ARGENZIANO:  Do we need a number?

10                 MR. REHWINKEL:  Yes, Madam Chairman.

11                 CHAIRMAN ARGENZIANO:  191.  And the title?

12                 MR. REHWINKEL:  This will be PEF Response to

13       OPC Interrogatories 90 through 93.  And this would be

14       191?

15                 CHAIRMAN ARGENZIANO:  That's correct.

16                 (Exhibit 191 marked for identification.)

17                 MR. REHWINKEL:  Thank you.

18                 CHAIRMAN ARGENZIANO:  Mr. Rehwinkel, is this

19       confidential or not?

20                 MR. REHWINKEL:  Yes, Madam Chairman.  There is

21       confidential information in it.

22                 CHAIRMAN ARGENZIANO:  Okay.

23                 MS. HELTON:  Madam Chairman, if I could just

24       interrupt for one minute, because I want to make sure I

25       understand, and I especially want to make sure that the

FLORIDA PUBLIC SERVICE COMMISSION

117

1       new Commissioners understand.  Typically when we have

2       confidential information that's provided in a hearing,

3       the confidential information is highlighted yellow.  And

4       when I look through here, I don't see anything that's

5       highlighted yellow, which would trigger us to know what

6       we can say on the record and what we have to kind of

7       dance around on the record.  So if Mr. Rehwinkel could

8       speak to that, that would be greatly appreciated.

9                 CHAIRMAN ARGENZIANO:  Good point.

10                 MR. REHWINKEL:  Yes.  Mr. Foster, the company

11       could probably confirm this, but if -- it's the

12       information on 93, anything that has a dollar amount

13       should be assumed to be confidential.  Actually there

14       are dollar amounts that are not, but the safest thing to

15       do would be to assume that the dollar amounts are

16       confidential.

17                 MS. HELTON:  And just for clarification

18       purposes then, it's only Interrogatory Number 93 and the

19       dollar amounts mentioned there that have the potential

20       to be confidential?

21                 MR. REHWINKEL:  Yes.  The -- well, on 93, in

22       the, on the page 6 of Interrogatory 93, in the second

23       paragraph there's a 16.2 million, 20 million, and

24       $3.8 million number to which, as I'm saying them, of

25       course are not confidential.  But all the other dollar

FLORIDA PUBLIC SERVICE COMMISSION

118

1       numbers, all the other dollar numbers are confidential.

2                 MS. HELTON:  If the company is comfortable

3       with that, I'm comfortable with that.

4                 MS. HUHTA:  That is a correct statement

5       regarding this document.  I believe that the copies were

6       just not made in color and that's where the highlighting

7       went.

8                 MR. REHWINKEL:  Yeah.  I apologize.

9       BY MR. REHWINKEL:

10            Q.   Mr. Foster, are you familiar with the response

11       to Interrogatory 90 that is included in Exhibit 191?

12            A.   I would say I'm aware of the response,

13       however, and I may just, I may just help you out here,

14       because I know, as it relates to this specific topic,

15       Ms. Hardison is really kind of the expert on these

16       dollars.

17            Q.   Okay.

18            A.   So I hope that doesn't shortcut you too much,

19       but I didn't want to --

20            Q.   I understand.  I had a question for you that

21       would be -- Mr. Garrett is shown as the respondent to

22       this interrogatory.

23            A.   Yes, sir.

24            Q.   And my question on this one is the Public

25       Counsel had propounded an interrogatory asking if any of

FLORIDA PUBLIC SERVICE COMMISSION

119

1       the transmission costs that would persist or continue on

2       if hypothetically the Levy nuclear project was not

3       continued or if it was delayed, were they taken out of

4       the request for NCRC recovery?  Are you familiar --

5            A.   As I said, I've read this discovery response

6       and answer.  But as far as -- I guess I'm not sure

7       exactly --

8            Q.   Well, my question is, is for 2009 and 2010 and

9       projected 2011, are any costs included in the schedules

10       that you sponsor that relate to transmission that is,

11       that will occur even if the Levy project does not go

12       forward?

13            A.   My understanding is no, sir, so.

14            Q.   Okay.  And the, what is that understanding

15       based on?

16            A.   Just, and, you know, we have a process

17       whereby -- I don't necessarily prepare all the budgets

18       and stuff.  I'm more of kind of the translator from the

19       business units and their organizations who look at all

20       these costs and, you know, go line item by line item,

21       they look at their contracts.  Again, I'm not the expert

22       on that.  And of course we have discussions about it.

23                 But as far as do I do the detailed, you know,

24       look at different contracts, do I go out and verify

25       transmission projects?  I don't do that, that's not my

FLORIDA PUBLIC SERVICE COMMISSION

120

1       role with the company.  I'm more of making sure we

2       translate the dollars that they have looked at and made

3       sure do that into what the statute and rule provide for

4       as far as revenue requirements.  Does that, does that

5       make sense?

6            Q.   Well, I guess my question is, is if -- who

7       would be the person to ask that, the question I just

8       asked you?

9            A.   Absolutely.  And that is -- I guess a shorter

10       answer to your question is because our processes and our

11       organization, the folks who are responsible for that

12       have asserted that to me.  And the person you should

13       ask, or the most appropriate person here today would be

14       Ms. Hardison.

15            Q.   Okay.  Fair enough.

16            A.   Sorry I took so long getting there.

17            Q.   That's okay.  I would ask you then to turn to

18       93, which has been noted as confidential.  And I would

19       ask that you of course not relate any of the

20       confidential information, if you can even answer

21       questions about that.  Are you familiar with the

22       response in 93?

23            A.   I'm generally familiar.  And, again, I just

24       want to make it clear, if you're getting into details

25       about specific handling of maybe contracts and costs

FLORIDA PUBLIC SERVICE COMMISSION

121

1       around that, I know Mr. Franke has those details and is

2       prepared to address them.

3            Q.   Okay.  So you can't tell me on the stand here

4       today whether any, whether you did any work to determine

5       whether costs related to the AREVA contract or any

6       rewriting of the LAR were included or excluded from cost

7       recovery?

8            A.   I guess I would say that our company included

9       all the costs that we feel are reasonable and prudent.

10       And so, again, when it comes to specific costs related

11       to an individual contract, you'll have to talk to

12       Mr. Franke.  But my expectation and my belief is we

13       included those costs because we believe and are prepared

14       to defend them as reasonable and prudent.

15            Q.   Okay.  Did you review any of the schedules

16       that Mr. Franke attached to his rebuttal testimony

17       relating to the AREVA contracts?

18            A.   I do not believe so.

19            Q.   All right.  So -- and would you be familiar in

20       any way with those contracts as they relate to costs

21       that the company is requesting for recovery in this

22       docket?

23            A.   Could you say that one more time?  I just want

24       to make sure I got it right.

25            Q.   Yes.  That's okay.  Would you be familiar with

FLORIDA PUBLIC SERVICE COMMISSION

122

1       those contracts as they relate to, those contracts

2       meaning the AREVA contracts that are attached to

3       Mr. Franke's rebuttal testimony, as they relate to costs

4       that the company is requesting recovery for in this

5       docket?

6            A.   Again, I don't believe I reviewed those

7       schedules, so I'm having a little trouble speaking to

8       whether I'm familiar with them.  I don't know if it

9       makes sense to put that schedule in front of me just so

10       I can see whether I've seen it before.

11            Q.   Well, I wasn't asking so much with respect to

12       a schedule, but with respect to costs that the company

13       is seeking recovery for in, for 2009, 2010 and 2011, are

14       there any --

15            A.   Maybe I, maybe I -- okay, I think I got you.

16       As it relates to, I believe, the AREVA contract, my

17       understanding is we have not pulled any costs out of our

18       projections, because we believe we prudently and

19       reasonably incurred them.  But, again, that's, I won't

20       say my colleague, because he's got a couple of pay

21       grades on me, but that would be Mr. Franke's AOR there.

22            Q.   Okay.  So is your testimony there was no

23       adjustments made with respect to costs related to the

24       LAR rewrite as it relates to cost recovery requests for

25       the 2009, 2010 and 2011?

FLORIDA PUBLIC SERVICE COMMISSION

123

1            A.   And let me make sure I answer that a little

2       carefully.  I can't say that in, for instance, in 2009

3       there may not have been accrual true-ups or similar

4       things, but to my knowledge I think the heart of your

5       question is did we pull money out that we spent on that

6       contract?  To my knowledge, no.

7            Q.   And would you have any knowledge from an

8       accounting or preparation of, of your testimony

9       standpoint as to whether there was any company costs,

10       payroll costs or any other company costs, meaning the

11       Progress Energy company, corporation, that were adjusted

12       to, for, for any of the rewrite costs related to the

13       LAR?

14            A.   Any company costs adjusted.  Forgive me.  I'm

15       just making sure I understand.  To my knowledge, there

16       were not, no.

17            Q.   Okay.

18            A.   But, again, that's something probably best

19       asked of Mr. Franke.

20            Q.   Okay.  I just wanted to make sure that,

21       whether you had any knowledge about whether there were

22       any adjustments made.  And your statement, your

23       testimony is that there were none; is that correct?

24            A.   To my knowledge there were none.

25                 MR. REHWINKEL:  Okay.  Madam Chairman, I would

FLORIDA PUBLIC SERVICE COMMISSION

124

1       like to ask for another exhibit to be, to be passed out.

2       And this is, this is PEF's response to staff data

3       request Number 1.

4                 COMMISSIONER SKOP:  This could be Exhibit 192

5       marked for identification.

6                 MR. REHWINKEL:  I apologize, Mr. Chairman.  I

7       wasn't looking at the change.

8                 (Exhibit 192 marked for identification.)

9                 COMMISSIONER SKOP:  That's fine.

10                 Mr. Rehwinkel, on what's been marked for

11       identification as Exhibit 192, is that information in

12       its entirety confidential, or do we need to address

13       that?

14                 MR. REHWINKEL:  Mr. Chairman, the information

15       that is confidential to my knowledge is, is on page,

16       Bates stamp page 0000, that's five zeroes and a 36,

17       which appears to be the response to question 25.

18                 COMMISSIONER SKOP:  All right.  Very well.

19                 MS. KAUFMAN:  Mr. Chairman?

20                 COMMISSIONER SKOP:  Yes, Ms. Kaufman.

21                 MS. KAUFMAN:  Could I just ask, is it just the

22       numbers again or everything?

23                 MR. REHWINKEL:  I --

24                 MS. HELTON:  When you look at the response, it

25       says "confidential" at the top.  So an easy assumption

FLORIDA PUBLIC SERVICE COMMISSION

125

1       is that the whole thing was meant to be confidential.

2                 MR. REHWINKEL:  I apologize.  There is gray

3       that you can't see very well that is the dollar amounts.

4       In hindsight, I should have -- but it is all the dollar

5       amounts that are, that are in the response part of that

6       page.

7                 COMMISSIONER SKOP:  And that's what's been

8       Bate stamp marked as 0000036?

9                 MR. REHWINKEL:  Yes, sir.

10                 COMMISSIONER SKOP:  Okay.  All right.  Thank

11       you.

12                 MR. REHWINKEL:  It is the response to question

13       25.

14                 MS. HELTON:  Mr. Chairman, can we ask the

15       company if they agree that it's just the numbers?

16                 COMMISSIONER SKOP:  Mr. -- I'm sorry.  Ms.

17       Huhta.

18                 MS. HUHTA:  Ms. Huhta.  Yes.  The numbers in

19       response to question 25 as well as the percentage on the

20       second to the last line on that page, and that's Bates,

21       the last are 0000036.

22                 COMMISSIONER SKOP:  Thank you.

23       BY MR. REHWINKEL:

24            Q.   Mr. Foster, are you familiar with this data

25       response that was provided to the staff auditors?

FLORIDA PUBLIC SERVICE COMMISSION

126

1            A.   I have seen this data response.  Yes, sir.

2            Q.   Okay.  Are you familiar with the response to

3       question number 18?

4            A.   Give me a second, please.

5            Q.   Which is on 27.

6            A.   Okay.  I'm there.

7            Q.   Okay.  Are you familiar with this response?

8            A.   I'm familiar with the response.

9            Q.   Okay.  Is this a response that you would have

10       prepared or would have been prepared under your

11       direction?

12            A.   This is not one that would have been prepared

13       under my direction.  No, sir.

14            Q.   Okay.  Are you familiar on the -- and your

15       testimony in this docket deals with the, with the

16       May 1st projection and estimates for 2010 and 2011;

17       correct?

18            A.   The -- we filed April 30th, but, yes, sir.

19            Q.   Yes.  You also provided testimony in 2009

20       related to the projections and estimates; is that right?

21            A.   Yes, sir.

22            Q.   There is a question by the staff about, that

23       asks for, I guess, a reconciliation of the, to get from

24       $426.6 million on the third line of that table to

25       $479.1 million on the last line of that table.  Do you

FLORIDA PUBLIC SERVICE COMMISSION

127

1       see that?

2            A.   I do, sir.  Yes.

3            Q.   Okay.  There's a column that says total

4       adjustments, $52.5 million.  Do you see that?

5            A.   Yes, sir.

6            Q.   Okay.  Are you familiar with what comprises

7       that $52.5 million?

8            A.   I -- no, that wouldn't be something I'd

9       testify to.  That would be something that Mr. Franke

10       would speak to.

11            Q.   Okay.  Do you know whether the $52.5 million

12       was included in cost recovery for last year?

13            A.   Oh, boy.  Now you're testing my memory here,

14       because -- when did this -- I'm trying to remember when

15       that came about.  I think it was late last year, so I

16       wouldn't expect that it was.

17            Q.   So --

18            A.   Now that's, I'm just going off, you know, kind

19       of a subject to check, but my recollection would be

20       probably we didn't know about this.

21            Q.   Okay.  So would these dollars then, the

22       $52.5 million, would they be included in this year's

23       cost recovery request for, for recovery for true-up for

24       2009 and any impacts in 2010 and 2011?

25            A.   Yes.  We would have made our estimates off our

FLORIDA PUBLIC SERVICE COMMISSION

128

1       most up-to-date numbers.

2            Q.   Is the $52.5 million, is that an adjustment to

3       the budget for the EPU project in 2009?

4            A.   Let me think about how, how, how you said

5       that.  Because there's -- one of the things with these

6       projects that makes it a little tough is the point at

7       which we prepare our filings is often different than the

8       point at which the budget is prepared for a given year,

9       and so there's a lot of -- it can be hard to compare

10       numbers on a one-to-one basis.

11                 So I guess I believe this 52.5 was, there was

12       an IPP where they itemized this, and this exact list I

13       think you see in front of you was in there.  And my

14       recollection, it was late '09, so, that that came about.

15       So my expectation is from the budget prepared for '09 to

16       towards the end of '09, that this would be an adjustment

17       made to that budget or a variance to that budget.  Does

18       that, does that help?

19            Q.   So when you said IPP, you mean integrated

20       project plan.

21            A.   Yes, sir.  Sorry.

22            Q.   That's okay.  And that is the company's

23       official document where any changes, material changes to

24       the budget for the project budget are approved; is that

25       right?

FLORIDA PUBLIC SERVICE COMMISSION

129

1            A.   I don't know that I'd say it that absolutely.

2       It's one of, I think, the company's control processes.

3            Q.   Okay.

4            A.   But there's a lot of stuff that goes into

5       monitoring your costs and, and keeping up to speed with

6       where we are, where we expect to be.  So I would agree

7       that that's one, one process we use to monitor for cost

8       changes and then make sure our management is apprised.

9            Q.   Well, but --

10            A.   Go ahead, sir.

11            Q.   No.  Go ahead.  You can finish your answer.

12            A.   No, no, no.  I'm done.

13            Q.   If I look on page 26 of this response and in

14       the response the second full paragraph, the last, the

15       next to the last line says, "The current cost estimate

16       for the uprate is 479.1 million."  Do you see that?

17            A.   I do, sir.  Yes.

18            Q.   And that 479.1 million is what is on page 36.

19       And so that would have been changed by the

20       $52.5 million; is that right?

21            A.   I'm sorry.  You said page 36?

22            Q.   I'm sorry.  Page 27.  I apologize.

23            A.   Okay.  So -- and then could you just say it

24       one more time?

25            Q.   Yes.

FLORIDA PUBLIC SERVICE COMMISSION

130

1            A.   The 426.

2            Q.   The 426 was the, was the budget -- would that

3       have been the budget before AFUDC in 2009?

4            A.   That's where you get into difficulty.  I can't

5       say for sure that it was.  That would be my expectation.

6       But without going back and looking at time lines, I'd

7       have a hard time.

8            Q.   Well, your budget is presented on what they

9       call a direct view and a financial view; correct?

10            A.   That's accurate, sir.

11            Q.   And the direct view is those costs that the

12       project managers control, i.e., the capital

13       expenditures; is that right?

14            A.   Yeah.  I'd agree with that statement.

15            Q.   And the financial view has the financing costs

16       or the AFUDC component added into it; is that right?

17            A.   Yes.  There's a --

18            Q.   Okay.  So if a direct view of $426.6 million

19       was increased by $52.5 million, you would get

20       47.9 million; correct?

21            A.   Say it one more time.

22            Q.   If a direct view of 426.6 million is increased

23       by 52.5 million --

24            A.   Yes.

25            Q.   -- then the --

FLORIDA PUBLIC SERVICE COMMISSION

131

1            A.   The 479?

2            Q.   Yes.

3            A.   I agree with that.

4            Q.   And you can see there it says, "Adjusted EPU

5       expenditures excluding AFUDC and JO."  That's joint

6       owners.

7            A.   Correct.  So we haven't removed the costs that

8       we'll get reimbursed from them.

9            Q.   Correct.

10            A.   But -- and let me -- I'm not trying to be

11       difficult.  It's just when you refer to budget, it has a

12       specific context in the company and it -- you know,

13       there's different timings, and I just want to make sure

14       I don't answer you inaccurately.

15            Q.   Okay.  So where I'm getting at is, is this

16       document where you told the staff that the, the estimate

17       for the EPU project increased in 2009 by $52.5 million;

18       is that right?  And you showed them how the line items

19       got you there.  Is that correct?

20            A.   This shows that the cost estimate increased by

21       $52.5 million and has an itemized list.  I'd agree with

22       that.

23            Q.   Now in your testimony that you filed in this

24       proceeding in 2010, do, is there any description or

25       breakdown of this $52.5 million?

FLORIDA PUBLIC SERVICE COMMISSION

132

1            A.   Well, I can say with regard to my testimony, I

2       don't have anything in there.

3            Q.   Okay.

4            A.   You know, there's a lot of testimony

5       following, so I can't necessarily speak to every other

6       witness.

7            Q.   Okay.  Do you know if -- well, first of all,

8       are you familiar with any issues related to the

9       disposition of long-lead materials as it relates to cost

10       recovery in this docket?

11            A.   Disposition of long-lead materials.  I, I know

12       anecdotally that our group, our, the project group for

13       Levy has been in some negotiations, but I don't know the

14       specifics around that.  Mr. Elnitsky is really probably

15       the right guy to ask.

16            Q.   All right.  I can ask him about that.  Yeah.

17       I think I'll wait.

18                 Mr. Foster, those are all the questions I have

19       for you.  Thank you.

20            A.   Thank you.

21                 CHAIRMAN ARGENZIANO:  I think -- thank you.

22       This may be a good time to take a ten-minute break and

23       give our court reporter a chance to rest her fingers.

24                 MS. HELTON:  Madam Chairman, before we break,

25       it's my understanding that Mr. Rehwinkel has quite a few

FLORIDA PUBLIC SERVICE COMMISSION

133

1       confidential exhibits that he will be using through the

2       course of the proceeding, and it's my understanding that

3       the company has offered to help him highlight those

4       parts that are actually confidential, which might

5       expedite matters through the day.

6                 MR. REHWINKEL:  Yeah.  I will -- what I was

7       hoping to do, I provided my confidential exhibits to the

8       company yesterday, and we've had discussions that we

9       will sit down and not only look at what might be

10       winnowed down with respect to what is actually

11       confidential.  And let me say this, is that Progress has

12       been very good to work with with respect to getting us

13       the documents and information we've requested.

14                 There have been claims of confidentiality that

15       as they've worked through the process with the

16       Prehearing Officer and the parties, that they have

17       narrowed their request.  We do not look at it like they

18       over requested.  They facilitated the information to us.

19       And so we have tried to work with them on that and we've

20       also tried to make sure that we're able to put on our

21       case without being overly burdened by, you know, getting

22       lost in the confidential aspects of the case.

23                 So we appreciate Ms. Helton bringing this to

24       our attention, because it is a serious matter.  We do

25       not want the company to be subject to liability.  This

FLORIDA PUBLIC SERVICE COMMISSION

134

1       is an unusual case, I just need to state this for the

2       record, because they're in active negotiations on major

3       contract issues right now.  And we appreciate that and

4       we want to work with them on that.

5                 So I, in an abundance of caution, have labeled

6       these as confidential.  We will work with them on that

7       for the benefit of the Commission and the public.

8                 CHAIRMAN ARGENZIANO:  That would be great.

9       Most helpful.

10                 Commissioner Skop.

11                 COMMISSIONER SKOP:  Thank you, Madam Chair.

12       And just to Mr. Rehwinkel's point, again, Progress

13       voluntarily agreed to disclose previously redacted

14       information, went above and beyond what was required to

15       address the Commission staff's concerns and Public

16       Counsel's.

17                 And just generally speaking, the majority of

18       the information that remains confidential are those

19       items directly related to existing contracts, numbers,

20       percentages that have competitive interests.  So, again,

21       it was very fortunate that Progress proactively took the

22       steps to disclose that information, and that reflects

23       positively on Progress.  And, Mr. Glenn, I'd like to

24       thank your company for the cooperation, because it

25       facilitates the hearing process.  Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

135

1                 MR. YOUNG:  Madam Chairman, it's my

2       understanding that the company is going to request that

3       we collect Exhibit, what is identified as Exhibit Number

4       191 and 192, and we'll collect it and replace those

5       exhibits with the highlighted copies, with highlighted

6       copies.

7                 CHAIRMAN ARGENZIANO:  Members, if you'd gather

8       191 and 192.  Correct?

9                 MR. YOUNG:  Yes, ma'am.

10                 CHAIRMAN ARGENZIANO:  Okay.  Commissioner

11       Skop.

12                 COMMISSIONER SKOP:  Just one additional point.

13       In most instances where there were differences of

14       opinion, it has been resolved in favor of transparency,

15       with the exception of those contractual issues.  So,

16       again, that should make things go a lot smoother.

17                 CHAIRMAN ARGENZIANO:  Okay.  Let's come back

18       at five of, give everybody a break.

19                 (Recess taken.)

20                 Okay.  And I think, Mr. Rehwinkel, you were

21       done with the witness?

22                 MR. REHWINKEL:  Yes.  Yes, Madam Chairman.

23                 CHAIRMAN ARGENZIANO:  Okay.  Then we'll just

24       move on.

25                 MR. BREW:  Thank you, Madam Chairman.

FLORIDA PUBLIC SERVICE COMMISSION

136

1                          CROSS EXAMINATION

2       BY MR. BREW:

3            Q.   Good morning, Mr. Foster.

4            A.   Good morning.

5            Q.   Well, this will be tedious but not long.  Can

6       I refer you to your Exhibit TGF-2, schedule P-1, that's

7       on page 4 of 44?

8            A.   Give me a second, please.

9            Q.   Sure.

10            A.   TGF-2.

11            Q.   Schedule P-1.

12            A.   P-1.  Got you.

13            Q.   Page 4.

14            A.   Yes, sir, I'm there.

15            Q.   Okay.  If I look at the bottom line number on

16       page 9, the 147 million, that's the company's requested

17       revenue requirements for 2011; is that right?

18            A.   For the Levy project, that's accurate.

19            Q.   For the Levy project, yes.  And above that on

20       line 7, the 60 million amount?

21            A.   Yes, sir.

22            Q.   That is, that is the amount that was, one of

23       the amounts for the rate management plan for the amounts

24       approved for recovery last year; is that right?

25            A.   Yes, sir.  That was part of the deferral

FLORIDA PUBLIC SERVICE COMMISSION

137

1       approved for recovery in future periods last year.

2            Q.   Okay.  So 60 million of the 147 is for the

3       costs approved last year?

4            A.   I might say it slightly differently, but I

5       think in spirit we're saying the same thing.

6            Q.   Okay.

7            A.   It's part of the deferral from last year that

8       we're collecting in accordance with the plan that we

9       filed and was approved last year as part of these

10       proceedings.

11            Q.   Okay.  Close enough.  Can I ask you to go to

12       TGF-3, schedule TOR-3?

13            A.   Yes.  Give me a second, please.

14            Q.   Yeah.  And I'm on page 5 and 6 of 17.

15            A.   Okay.  I'm there, sir.

16            Q.   Okay.  Now am I correct that these pages show

17       the projected spending amounts for Levy Units 1 and 2

18       for, from 2006 through the duration of the project,

19       meaning their in-service dates?

20            A.   Let me just think about that for a second

21       because there's a couple of different things represented

22       in these schedules.  Could you, could you state your

23       question one more time to make sure I'm --

24            Q.   Yeah.  The easiest way would be line 6 is

25       entitled Total Final Period Amount.  Do you see that?

FLORIDA PUBLIC SERVICE COMMISSION

138

1            A.   Yes, sir.

2            Q.   Okay.  And let's just make it simple.  Let's

3       look at projected 2014, the amount of 688 million.

4            A.   Yes, sir.

5            Q.   Okay.  What does that represent?

6            A.   That represents the expected period, and I'm

7       just doing some math to make sure, the expected period

8       revenue requirements for, for that year.

9            Q.   For that year.  Okay.

10            A.   Yes, sir.

11            Q.   Now if I could take you back to Exhibit Number

12       188.

13            A.   I do still have that one.

14            Q.   Don't let it go far.

15            A.   Yes, sir.

16            Q.   And I look at the estimated residential rates

17       per 1,000 kilowatt hours for 2014, the $23.78.  Do you

18       see that?

19            A.   Yes, sir.

20            Q.   Is that 23.78 based on that $688 million?

21            A.   I'm just recalling, making sure I recall

22       properly.  But, yes, sir, I believe it is.

23            Q.   Okay.  What else does the 23.78 include in

24       addition to the $688 million?

25            A.   I'm just looking to make sure.  I've got to

FLORIDA PUBLIC SERVICE COMMISSION

139

1       think about the recovery of the deferral and whether it

2       was done in, by that year yet.

3            Q.   You still have another 57 million in the

4       deferral for 2014.

5            A.   Okay.  So then we would reflect recovering

6       that.  And I'm sorry, I just had walked through the

7       years again.  A lot of schedules here.

8            Q.   Well, that's what I'm trying to get to is does

9       the 23.78 include that remaining deferral of the

10       57 million?

11            A.   That would not.  I'm sorry.  Thank you for

12       asking so I can clarify.  Again, if you look at line 6,

13       it's specific to say total final period amount.

14            Q.   Uh-huh.

15            A.   And as you can see, if you look at 2011, it's

16       less than what we've requested; right?  It's 75 million,

17       and that's a period amount.  But to the extent there are

18       any prior period amounts to be recovered, that would be

19       in addition.

20                 Now the only prior period we would expect in

21       2014 right now would be that deferral because, well, we

22       don't know if we're going to have any other over or

23       under recoveries, but --

24            Q.   Right.

25            A.   Does that answer your question, or --

FLORIDA PUBLIC SERVICE COMMISSION

140

1            Q.   Well, we're getting there.

2            A.   Okay.

3            Q.   So on, on TGF-2, page 44, you show the

4       amortization schedule for the rate management plan, and

5       that shows for 2014, 57,271,000 to be amortized in 2014.

6       Correct?

7            A.   That's correct, sir.

8            Q.   Okay.  So we know that the, the 688 million

9       projected amount, revenue requirement for that same year

10       does not include the 57 million.  My question is whether

11       the $23.78 on Exhibit 188 for that year does.

12            A.   So, and let me, let me be specific.  I think

13       earlier you asked a question -- first, yes, I believe it

14       does.  Earlier you asked a question, is that 23.78 based

15       on the 688, and I would still say yes, it is.  However,

16       there are some other items in there.  And it does, as I

17       think we note there, note 3, it reflects the revenue

18       requirements in the NCRC rate.  I'll just read it so I

19       don't paraphrase.  "Rate presented above reflect the

20       rate management plan as proposed in Docket 100009."

21            Q.   Okay.  So the 23.78 would then include that

22       amount?

23            A.   Yes, sir.  And sorry if I wasn't clear

24       earlier.

25            Q.   Okay.  Staying in TGF-3 but moving to schedule

FLORIDA PUBLIC SERVICE COMMISSION

141

1       TOR-2, which is page 4 of 17.

2            A.   Yes, sir.

3            Q.   And in column F, under the column Current

4       Estimated In-Service Amount.

5            A.   Yes, sir.

6            Q.   You told, show on line 6 total final period

7       amount of 22.056 billion.  Do you see that?

8            A.   I see that amount.  Yes, sir.

9            Q.   Okay.  Does that include the fuel?

10            A.   Let me think about that.

11            Q.   Let me save some time.  Note 2 says that the

12       numbers are not inclusive of nuclear fuel.  Do you see

13       that?

14            A.   That make it easier for me, yes.  I'm sorry.

15       I was just trying to remember if it did or not.  And,

16       no, they are not inclusive of the fuel.

17            Q.   Okay.  So if the fuel load is approximately

18       $500 million, the all in, the costs, AFUDC, transmission

19       and fuel is like $22.5 billion?

20            A.   If you add in about a half a billion to this

21       number, you get to about $22.5 billion.  I'd note that

22       the description in service may, may not be the best

23       description as I sit here today and think about it.  It

24       was the description kind of agreed to for this schedule

25       I think among the parties.  But when you, when you

FLORIDA PUBLIC SERVICE COMMISSION

142

1       typically think about in service, you think about what

2       you set as what's the value of whatever asset goes in

3       when you place something in service.

4                 So this is kind of an accounting, you know,

5       maybe a little bit geeky distinction.  But, you know, I

6       wouldn't expect it to be $22 billion that is kind of

7       that in-service amount, because we would have collected

8       the preconstruction costs and also along the way the

9       carrying costs.  So it's more a view of maybe capital

10       costs incurred plus collections through NCRC up to that

11       date.  Does that make sense?  A lot of gobbledygook, I

12       know.

13            Q.   Well, let's back up and make sure we're clear.

14       On page 6 of 17, also of schedule TOR-3, under the

15       column S, Projected Total.

16            A.   Say again.  S, Projected Total.  I see that

17       column.

18            Q.   Right.  And you have a final, total final

19       period amount of $8.2 billion?

20            A.   Yes, sir.

21            Q.   Does that represent the amount that would be

22       collected over that period through the NCRC?

23            A.   That's an estimated amount for what we think

24       will be collected under the statute and rule.

25            Q.   Okay.  And any remaining amounts would then be

FLORIDA PUBLIC SERVICE COMMISSION

143

1       reflected in base rates?

2            A.   Basically, yeah.  That's pretty good,

3       straightforward, yeah.

4            Q.   All right.  So, if, if the total in-service

5       amount is 22.5 billion and you've collected to that

6       point 8.2 billion, you'd have about 14 billion left to

7       go into base rates?

8            A.   Yeah.  That sounds right, sir.

9            Q.   Okay.

10            A.   You know, not to the penny there, but --

11            Q.   Let's talk a little bit about the Exhibit 188

12       again.

13            A.   188?

14            Q.   Yes, please.

15            A.   Yes, sir.

16            Q.   And just to keep it simple, let's stick with

17       year 2014 again.  Well, when you're ready.

18            A.   Oh, yes, sir.  I'm there.  I'm sorry.

19            Q.   To get to the estimated residential rate

20       calculation of $23.78, you took the estimated revenue

21       requirement for that year and the 57 million of the

22       remaining deferral and then applied it over the

23       company's sales forecast for that period?

24            A.   That would be, yeah, at its most basic.  Yes,

25       sir.

FLORIDA PUBLIC SERVICE COMMISSION

144

1            Q.   And that would be the same sales forecast that

2       Mr. Lyash shows on his Exhibit JL-3?

3            A.   I'm not 100 percent sure if it's the exact

4       same forecast.  We do, we do a lot of sales forecasts

5       over the year.  I would expect the number to be very

6       close, if not the same.

7            Q.   Okay.  I'm just trying -- thank you.  I'm just

8       trying to figure out if the sales forecast shown on that

9       other exhibit is the same one that you used here or

10       whether we need a different information base.  So --

11            A.   I believe the other exhibit you're mentioning

12       --

13            Q.   Yes.

14            A.   -- I believe these are based, the division, if

15       you will, is based off the same sales forecast.

16            Q.   Okay.  Thanks.

17            A.   That's -- I'm sure that's something we could

18       confirm if you need us to check that real quick.

19                 And in fact I wish I had the other in front of

20       me because I think note 4 here says what sales forecast

21       we used.  And I think we have a similar note, and I

22       think they're the same sales forecast.  I just, as you

23       know, we produced a lot of documents in this docket,

24       and --

25                 MR. BREW:  May I approach, Madam Chairman?

FLORIDA PUBLIC SERVICE COMMISSION

145

1       BY MR. BREW:

2            Q.   Mr. Foster, I showed you Exhibit JL-3 to

3       Mr. Lyash's exhibit, and one of the appendices shows the

4       projected sales.

5            A.   Just give me a second.

6            Q.   Yes.

7            A.   I'm looking to see if they have an assumption

8       listed here for what, what sales forecast was used.

9                 MR. BREW:  Madam Chairman, this is on page 18

10       of 21 of Exhibit JL-3.

11                 CHAIRMAN ARGENZIANO:  18 of 21?

12                 MR. BREW:  Yes.

13                 THE WITNESS:  Yeah, I'm sorry.  In his

14       exhibits I can't find a specific reference.  I'd say

15       that's something we could confirm pretty fast if

16       there's -- you know, I don't know if a late-filed or

17       something along those lines.  I would expect them to be

18       very close, if not the exact same.

19       BY MR. BREW:

20            Q.   The column, again -- focusing on Exhibit 188.

21            A.   Yes, sir.

22            Q.   The column that's, or the line that's labeled

23       Estimated Base Rate; do you see that?

24            A.   Yes, sir.

25            Q.   Could you explain for me the simplifying

FLORIDA PUBLIC SERVICE COMMISSION

146

1       assumptions beyond note 1 in terms of what type of costs

2       are included in that estimated cost recovery?  Would it

3       include a return on the investment?

4            A.   It would.  Yes, sir.

5            Q.   Gross up for taxes?

6            A.   Yes, sir.

7            Q.   Depreciation?

8            A.   Yes, sir.

9            Q.   Property taxes?

10            A.   Yes, sir.  Basically if you think about what

11       we've put in our request for the uprate and how those,

12       that math is done, it would be basically that same type

13       of math.  And you're right, you have to make, for

14       instance, an ROE assumption.  And -- well, I'll just

15       leave it at that.

16            Q.   My question is, are the numbers that are

17       reflected here, would they have reflected that basic

18       calculation of an assumed return on investment and

19       depreciation and taxes?

20            A.   Oh, absolutely.

21            Q.   Okay.  And the base rate impacts for 2021 and

22       2022 reflect the projected in-service dates of those

23       units; is that right?

24            A.   Yes, sir.

25            Q.   And so the split in the cost recovery between

FLORIDA PUBLIC SERVICE COMMISSION

147

1       base rates and what's recovered through the NCRC would

2       be tied to those in-service dates; is that right?

3            A.   Let me think about that for a second.  So --

4       and forgive me.  I am just trying to make sure I think

5       about this.  I think that's one of those things that

6       would depend.  My, you know, typically as we go through

7       we haven't really had this situation, but my, my

8       expectation is when you set your NCRC revenue

9       requirements, you set them for an annual period, and so

10       it might be reflective of, and I know I'm probably going

11       too detailed again, getting a little geeky on the

12       accounting side.

13                 But, for instance, you'd bank (phonetic) in

14       half a year maybe of Unit 1 into your total revenue

15       requirement in the NCRC, but it would tend to get spread

16       out over an entire year's sales forecast.  Do you follow

17       me?  And so it would be kind of a -- does that, does

18       that make sense?  Like, I wouldn't envision, and I think

19       our assumption is that we don't go and have a step first

20       half of the year while we've still got Unit 1 in CWIP,

21       and then the second half we have a step down in NCRC and

22       a step up in --

23            Q.   Actually I'm trying to get to that more

24       specifically.  Let's take the year 2021.  You've got

25       estimated NCRC rate of $25.69.  Do you see that?

FLORIDA PUBLIC SERVICE COMMISSION

148

1            A.   I do see that.  Yes.

2            Q.   Okay.  Now would that be reflected of the NCR

3       costs through the entire year or would it assume an

4       in-service date in the middle of 2021 for Unit 1?

5            A.   So I'm going to answer this in a clear as mud

6       fashion, but it assumes an in-service date of the middle

7       of 2021.

8            Q.   Uh-huh.

9            A.   However, a simplifying assumption was made, I

10       believe -- oh, actually, let me look at this, look at my

11       notes I guess.  Let me think about that.

12                 I think what it has is it, I think it

13       represents, and, again, this is something I could

14       confirm.  These are estimates out in 2021.

15                 But I believe what we assume, to kind of

16       simplify it there, was that when the bulk of Unit 1 goes

17       in service in July, it kind of remains in the NCRC until

18       the end of the year, and then in the end of the year

19       picks up, or in the next year picks up.

20            Q.   In the next year the NCRC goes down to $18.47,

21       because that assumes that Unit 1 is in service, in base

22       rates for the entire year?

23            A.   Yes, sir.  That --

24            Q.   Okay.  So the next line, the estimated rate

25       impact of Levy capital additions is the sum of the NCRC

FLORIDA PUBLIC SERVICE COMMISSION

149

1       and the base rate recovery?

2            A.   For a given year.

3            Q.   For any given year?

4            A.   For, yeah.  And, again, I would just say --

5       well, yes, that's what it illustrates.  Yes.

6            Q.   Okay.  So 2021, that estimated impact is

7       $54.39?

8            A.   I agree.  Yes.

9            Q.   Okay.  And so that would be about, a little

10       over $600 a year for a customer using 1,000 kilowatt

11       hours a month?

12            A.   I'm doing the math in my head here.  I think

13       that's accurate.  Yeah.

14            Q.   Okay.  Close enough.  At least 50 times 12

15       would be 600 bucks; right?

16            A.   Yeah.

17            Q.   Okay.  Let's go down to the bottom line where

18       the estimated fuel savings.  The -- taking that

19       estimated fuel savings of $7.45 again for 2021; do you

20       see that?

21            A.   I do, sir.

22            Q.   Now is that estimated fuel savings based on

23       the, the mid reference fuel case that the company

24       provided in Mr. Lyash's exhibits?

25            A.   My understanding is it's the mid reference

FLORIDA PUBLIC SERVICE COMMISSION

150

1       fuel case.  Yes, sir.

2            Q.   Okay.  So to the extent that the mid reference

3       fuel case is, is accurate, that's what you'd be

4       projecting?

5            A.   Yes, sir.

6            Q.   Okay.  Mr. Foster, are you familiar with or

7       responsible for fuel price forecasting at all?

8            A.   I am not responsible for fuel price

9       forecasting.

10                 MR. BREW:  Okay.  Thank you.  That's all I

11       have.

12                 THE WITNESS:  Thank you.

13                 CHAIRMAN ARGENZIANO:  Did you have any

14       exhibits to be entered?  There were none, were there?

15                 MR. BREW:  Pardon?

16                 CHAIRMAN ARGENZIANO:  Did you have any

17       exhibits?

18                 MR. BREW:  I did not have any exhibits

19       additionally to mark.

20                 CHAIRMAN ARGENZIANO:  Mr. Young, did you have

21       --

22                 MR. YOUNG:  No, ma'am.  You were right.

23                 CHAIRMAN ARGENZIANO:  Ms. Kaufman?

24                 MS. KAUFMAN:  Thank you, Madam Chairman.

25                          CROSS EXAMINATION

FLORIDA PUBLIC SERVICE COMMISSION

151

1       BY MS. KAUFMAN:

2            Q.   Mr. Foster.

3            A.   Good morning.

4            Q.   Good afternoon.

5            A.   Oh, yeah.

6                 CHAIRMAN ARGENZIANO:  Before, before you

7       begin, I'm just going to say, around 12:30 I think we're

8       going to break for lunch for an hour, so we're going to

9       try -- I don't want to split up your questioning, so if

10       we have to come back, there's no problem, but around

11       that time, even a quarter of if we have to go a little

12       further.  But that's my intention.

13                 MS. KAUFMAN:  Thank you, Madam Chair.  That

14       will probably be more than sufficient.  Thank you.

15                 CHAIRMAN ARGENZIANO:  Okay.  Great.

16                 MR. YOUNG:  Madam Chairman, what is being

17       passed out is the -- staff alerted you of the --

18                 CHAIRMAN ARGENZIANO:  The highlighted already?

19                 MR. YOUNG:  The highlighted copies of Exhibits

20       Number 191 and 192.

21                 CHAIRMAN ARGENZIANO:  Great.  Thank you.

22       BY MS. KAUFMAN:

23            Q.   Mr. Foster, we've got all our paper together.

24       I'm Vicki Kaufman.  I'm here on behalf of the Florida

25       Industrial Power Users Group.  And I want to -- I just

FLORIDA PUBLIC SERVICE COMMISSION

152

1       have a few questions for you, and I want to turn to the

2       ever-popular Exhibit 188.  Do you still have that?

3            A.   I'm there.  Thank you.

4            Q.   Okay.  And the chart that appears at the

5       bottom of Exhibit 188 is the company's best estimate as

6       we sit here today of the rate impacts of the Levy

7       project.  Is that right?

8            A.   Yes, with the accounting caveat that it does

9       not assume any rate cases and that kind of stuff.  So I

10       would say that it could be lower if there's a rate case

11       in between where you adjust what's already in service.

12       Does that --

13            Q.   But --

14            A.   Does that answer your question?

15            Q.   Yes.  I just want to be clear that what we're

16       supposed to take away from this exhibit is, on a high

17       level, this is what customers and the Commissioners can

18       expect, or it's the company's estimate of what they can

19       expect as we sit here today in terms of the rate impact

20       of this project.

21            A.   This is -- okay.  So, yes, this is an estimate

22       of what, kind of just the natural fallout of our

23       projected spend is over, you know, through the, through

24       the project in service.  So I would agree with that,

25       yes.  However, I would say that when you say rate impact

FLORIDA PUBLIC SERVICE COMMISSION

153

1       and you don't compare it to anything else, that may be a

2       little -- this is the nuclear associated with Levy rate

3       impacts; however, does not, does not consider the fact

4       that if you don't build, there may be other costs you

5       incur.  I think that when Mr. Rehwinkel was asking me

6       his string of questions between, I don't know if it was

7       191 or what, but, and this 188 kind of talked a little

8       bit about that.

9                 Does that make sense?  Does that answer your

10       question?

11            Q.   Well, I guess you might be making it a little

12       more complicated than my question was, but all I'm just

13       trying to establish is that staff asks you to calculate

14       the ratepayer impact after 2012 of completing the

15       project on a 100 percent ownership basis, using the

16       option that Progress has proffered in this case.  And

17       what you have prepared in response is a chart on Exhibit

18       188.

19            A.   Yes.

20            Q.   Okay.  Now the chart on 188, the impact shown

21       there is based on dollars per 1,000 kW; correct?

22            A.   Yes.  That's what it says, 1,000 kWh.

23            Q.   KWh.  Thank you.  So this may be obvious, but

24       to the extent you have a residential customer that uses

25       more than 1,000 kWh, the impact is going to be greater;

FLORIDA PUBLIC SERVICE COMMISSION

154

1       correct?

2            A.   I would agree that that is how the math works,

3       yes.

4            Q.   And this is, this is per month; I think we've

5       established that, correct, with Mr. Brew?

6            A.   I think this is per 1,000 kWh.

7            Q.   Okay.  When Mr. Brew was talking to you about

8       the $600 impact, that's an annual impact; correct?

9            A.   Based on assumption, on an assumption that

10       Mr. Brew presented, that would be a rough approximation

11       of an annual impact.

12            Q.   Okay.  Were you here when I did my opening

13       remarks to the Commission this morning?

14            A.   I was.

15            Q.   And so you would agree with me that for my

16       clients, the industrial consumers, the rate impact would

17       be much greater than shown on this chart; correct?

18            A.   No, I would not.

19            Q.   Well, they utilize more electricity, and so

20       therefore wouldn't their NCRC be greater than, for

21       example, in 2014, 23.78?

22            A.   Per 1,000 kWh, I don't believe it would.

23            Q.   But, again, we might be talking past each

24       other.  To the extent they use more than 1,000 kWh.

25            A.   So I guess what I would say is this is a rate,

FLORIDA PUBLIC SERVICE COMMISSION

155

1       a dollars per kW, a thousand kWh, and your usage will

2       get multiplied by that rate, the kWhs will cancel out.

3       And then if you use more than a thousand, yes.  This is

4       a -- so I wouldn't agree that your customers will pay

5       more.  They will pay what the rate is times their usage,

6       just like everybody else.

7            Q.   Exactly.  But at the end of the day they'll

8       see a higher charge than what you've reflected for the

9       1,000 kWh residential rate; right?

10            A.   And I would -- and this is something I'm sure

11       Mr. Lyash will speak to greatly.  They will see a

12       greater benefit in years when we have significant fuel

13       savings, or -- so.

14            Q.   Understood.  But, again, my question is, they

15       will pay more than, for example, in 2014 $23.78?

16            A.   If --

17            Q.   If they use more than 1,000 kWh.

18            A.   That's the rate they will pay per 1,000 kWh.

19       I don't know -- if you tell me how much they're going to

20       use in 2014, I can probably calculate it for you.

21            Q.   Well, let's just say if they use more, they're

22       going to pay more than the 23.78; correct?

23            A.   They're going to -- if they use more than

24       1,000 kWh, their bill will be higher than 23.78.  But

25       they will never pay -- well, this is an estimate, and I

FLORIDA PUBLIC SERVICE COMMISSION

156

1       haven't made it specific to an industrial customer.  But

2       with that caveat, they will pay that rate, and that's

3       exactly what they'll pay, just multiplied by their

4       usage.  I don't know how to make it --

5            Q.   I think I understand.

6            A.   Okay.

7            Q.   Have we, have you done any analysis of the

8       impact on any class other than a residential customer

9       using 1,000 kWh?

10            A.   I haven't specifically done any analysis on a

11       different rate class, no.

12            Q.   Okay.  I want to take a look at Exhibit 189

13       and 190 that I think you discussed with Mr. Rehwinkel.

14            A.   Can I get an updated copy of those?  I know

15       mine were grabbed.

16            Q.   You don't have those any longer?

17            A.   I have 191 and 192 back, but I didn't get 189

18       and 190, so.

19                 MS. KAUFMAN:  I would ask if staff --

20                 CHAIRMAN ARGENZIANO:  If we can get him a

21       copy?  Do we have a copy that we can --

22                 MS. KAUFMAN:  If I can approach, I'll just

23       give him Mr. Davis's.

24                 CHAIRMAN ARGENZIANO:  Please do.  That would

25       be the easiest.

FLORIDA PUBLIC SERVICE COMMISSION

157

1                 MR. YOUNG:  I think also Progress should have

2       a copy.

3                 THE WITNESS:  Thank you, Charles.

4                 MS. KAUFMAN:  Thank you, Mr. Rehwinkel.

5       BY MS. KAUFMAN:

6            Q.   Okay.  Mr. Foster, so you've got 189 and 190

7       in front of you; correct?

8            A.   Yes, ma'am.

9            Q.   Okay.  If you would turn in 189 to the page

10       Mr. Rehwinkel asked you about, which is 29-4.

11            A.   189 -- I think I, actually I think, I think

12       this is 188.  I think I still need 189.  I'm sorry.

13            Q.   Which one do you need?  I'm sorry.

14            A.   189.  I apologize.  Thank you so much.

15            Q.   Okay.  So 189, page 29-4.

16            A.   I'm there.

17            Q.   Okay.  And then on 190, it's kind of in the

18       middle, 2176.  Mr. Rehwinkel asked you about these

19       schedules.

20            A.   Where is it?  What's the title or something?

21            Q.   It's called Progress Energy Late-Filed Exhibit

22       Number 5.  I think it was Mr. Portuondo's exhibit.

23            A.   All right.  I'm there, ma'am.

24            Q.   Okay.  Now if I -- I just want to understand

25       the relationship between these two exhibits that

FLORIDA PUBLIC SERVICE COMMISSION

158

1       Mr. Rehwinkel asked you about.  And on Exhibit Number

2       189, okay, on 2020, I want you to look at the $38.48.

3            A.   Yes.

4            Q.   Are you there?

5            A.   I see that.

6            Q.   Okay.  And did I understand that that is

7       comparable to the $24.75 on page 2176 from your

8       determination of need?

9            A.   And which number?  I'm sorry.

10            Q.   The 24.75 on line 1.

11            A.   Twenty-four -- I'm sorry.  You're looking at

12       Late-Filed Exhibit 5?

13            Q.   Yes, sir.

14            A.   I'm sorry. I'm not seeing --

15                 CHAIRMAN ARGENZIANO:  Under 2015.

16                 THE WITNESS:  Under 2015.

17                 MS. KAUFMAN:  Sorry.  Yes.  Thank you, Madam

18       Chairman.

19                 THE WITNESS:  Oh, I see it.  I apologize.

20                 I would not -- no, I would not say that it is

21       -- so I guess in theory the math behind numbers are very

22       similar.  One's a comparison between a scenario with

23       nuclear and without where you have costs in such as

24       other units, you have the cost of fuel completely

25       factored in.  Late-Filed Exhibit 5 was not that.  That's

FLORIDA PUBLIC SERVICE COMMISSION

159

1       specifically the NCRC.  It says CCR, but kind of the

2       same thing in this, in this establishment.  So, no, I

3       would say that those are not comparable.  No, ma'am.

4       BY MS. KAUFMAN:

5            Q.   Okay.  If you look at Late-Filed Exhibit

6       Number 5 and you see the $24.75 in 2015, I think that

7       you testified earlier that that number reflects the

8       charge before the in-service date of the first unit?

9            A.   I think I reflected that that represents the

10       charge in NCRC before the first unit is in service.

11            Q.   Right.  Okay.  And on Exhibit 189, what does

12       the 38.48 represent?

13            A.   Well, it represents the difference in revenue

14       requirements between a scenario with Levy versus one

15       with an all gas type portfolio as presented in our

16       feasibility analysis.

17            Q.   Does the 38.48 include the NCRC and any base

18       rate impact?

19            A.   Yes.

20            Q.   Okay.  And the one on late-filed 5 is the NCRC

21       only; correct?

22            A.   Yeah.  I just want to make it clear that these

23       aren't comparable numbers.

24            Q.   I understand your position.

25            A.   Okay.  I just want to make that clear.  You're

FLORIDA PUBLIC SERVICE COMMISSION

160

1       comparing them and it's not a comparable number to

2       compare.

3            Q.   I just want to try to understand the

4       difference.

5            A.   Go ahead.  I'm sorry.

6            Q.   That's okay.  And so the 38.48, as I said, is

7       the, the base rate and the NCRC number on --

8            A.   It would be inclusive of those.  I agree with

9       that statement.

10            Q.   Okay.  And the Late-Filed Exhibit 5 is the

11       NCRC only for --

12            A.   I would disagree with that.

13            Q.   Okay.  Tell me why.

14            A.   Because it has a base rate impact listed on it

15       under 2015 of $7.64.  But there are many other

16       differences between these.

17            Q.   Okay.  I see what you're saying.  So you're

18       looking at the total at the bottom of Late-Filed Exhibit

19       Number 5 for the 3660.  You're adding in the base rate

20       impact and the transmission.  Okay.  I see that.

21                 Would you agree with me that since your

22       estimates were presented to the Commission in the

23       determination of need, that the rate impact that the

24       Levy project will have on ratepayers has increased?

25            A.   The rate impact.  In -- well, that's an

FLORIDA PUBLIC SERVICE COMMISSION

161

1       interesting question.

2            Q.   I thought it was pretty easy.  Sorry.

3            A.   I would agree that costs and in service have

4       increased, and there are definitely years where the rate

5       impact is higher.  So I would agree with that.  I

6       wouldn't necessarily agree that the rate impact is

7       always higher in all cases, because then you have to

8       look at more of a global analysis, like I think

9       Mr. Lyash testified to around feasibility.  And I just

10       haven't done that.

11                 But what I can tell you is I think if you look

12       at Late-Filed Exhibit Number 5, it's got a

13       2011 estimated rate impact there, and it's $16.77.  And

14       that was, that was provided in our need case.  And as we

15       stand here before you, I believe what I can confirm,

16       we're more at like a 499.  So it depends specifically

17       what time period you're asking about, and I'm sure there

18       are years where you're absolutely right.  And then as

19       you consider the benefits down the line, I don't know

20       how that all factors out.

21                 But I would definitely agree, and I think

22       we've been very frank and open about, yes, our estimate

23       of the total project costs have gone up.

24            Q.   And since your estimate of the total project

25       costs have gone up, you would agree, would you not, that

FLORIDA PUBLIC SERVICE COMMISSION

162

1       what you expect the ratepayers to pay for this project

2       has gone up as well?

3            A.   I don't know how the -- and, again, this is

4       something that I would look to Mr. Lyash to speak to in

5       more depth.  So if you're just looking at the cost side

6       of this project, I think you're being accurate, fairly

7       characterizing it.  There's also a benefit side.  And

8       these things are going to change, I mean, obviously.

9       Fuel forecasts change, environmental forecasts will

10       change.  I'm not the expert on them, but I know enough

11       to know they change just by what happens in fuel

12       hearings every year.

13                 So if you look exclusively at the cost side, I

14       think I agree with you.  But I think if you take a step

15       back and take a global view, I can't answer that because

16       I don't know what's happened on the benefits side.

17                 Does that, does that answer your question?

18            Q.   I understand.  And I'm just maybe a little bit

19       more simplistic than what you're trying to explain.  I

20       just want to confirm that the costs that your, that the

21       company is asking the ratepayers to bear as a result of

22       this project have increased since the project was first

23       described to the Commission in the determination of need

24       proceeding.

25            A.   The cost to build the plant, I would agree our

FLORIDA PUBLIC SERVICE COMMISSION

163

1       estimate is higher than it was when we presented it in

2       the need, absolutely.

3                 MS. KAUFMAN:  Thank you, Commissioners.

4                 And thank you, Mr. Foster.

5                 THE WITNESS:  And I'm sorry for splitting

6       hairs there.  I just want to make sure I was clear on

7       that.  And thank you.

8                 CHAIRMAN ARGENZIANO:  I don't think you need

9       to apologize.  I think you've done a good job.

10                 THE WITNESS:  Oh, thank you.

11                 CHAIRMAN ARGENZIANO:  You're just trying to be

12       complete, I think.  Thank you.

13                 THE WITNESS:  Thank you.

14                 CHAIRMAN ARGENZIANO:  You're recognized.

15                 And there were no exhibits to be entered; am I

16       correct?

17                 MS. KAUFMAN:  No, ma'am.  Thank you.

18                 CHAIRMAN ARGENZIANO:  Okay.

19                          CROSS EXAMINATION

20       BY MR. DAVIS:

21            Q.   Just one question.  Mr. Foster, my name is

22       Gary Davis.  I represent Southern Alliance for Clean

23       Energy, and I just want to ask one question.  If you go

24       back to, as you say, the ever-popular Exhibit 188.

25            A.   Which one was it?  I'm sorry.

FLORIDA PUBLIC SERVICE COMMISSION

164

1            Q.   188, please.

2            A.   Oh, okay.  Sorry.  I'm --

3            Q.   And you've been focused by other questioners

4       on different years.  I want to focus on again this page

5       number 1 and the year, and the table 2020.

6            A.   I see it, yes, sir.

7            Q.   You would agree that in 2020 you're not

8       expecting to generate any electricity from the Levy

9       nuclear plant; right?

10            A.   I believe that's accurate, yes, sir.

11            Q.   Okay.  You're not looking at in-service dates

12       until 2021, 2022; right?

13            A.   That's my understanding.  Yes, sir.

14            Q.   So here in 2020, what is the total increase in

15       the consumer residential rate per 1,000 kilowatt hours

16       based on the recovery of costs in nuclear cost recovery

17       hearings, assuming they're all granted for the consumer?

18       Is that $43.42?

19            A.   Could you just state that one more time?  I'm

20       sorry.  There was a lot in there and I want to make sure

21       I --

22            Q.   Yeah.  And I probably tripped over myself a

23       couple of times.  But let me ask it.  Look at line 1 of

24       this table, Estimated NCRC Rate.

25            A.   Okay.  I see it, sir.

FLORIDA PUBLIC SERVICE COMMISSION

165

1            Q.   So the consumer would be paying essentially

2       $43.42 for the NCRC charges for the Levy nuclear plant

3       before one kilowatt hour of electricity is generated

4       from it in 2020; right?

5            A.   This represents the residential rate.  So if

6       you're just looking at a generic retail rate level, it

7       would be a little bit different, but that's, you know, a

8       pretty close proxy there.  So the rate that we would

9       just, based on the outfall of the projected cash flows

10       and converting it to the recovery, as per the rule and

11       statute, brought us to a number of 43.42.  I think I'd

12       agree with that.

13            Q.   Okay.  Now --

14            A.   And that, yes, I don't expect any generation

15       in 2020.

16            Q.   Okay.  Now, and going on down to the estimated

17       rate impact of Levy capital additions, this would

18       include what you've already added to the base rate by

19       2020, is that correct, the $5.87?

20            A.   I agree.  And let me just make sure I'm clear

21       again, that this is, this schedule does not necessarily

22       compare -- it's just a what are the costs.

23            Q.   Well, you're anticipating questions that I

24       didn't even ask, but --

25            A.   I want to make sure it's clear what this

FLORIDA PUBLIC SERVICE COMMISSION

166

1       represents since we're referring to this document.

2            Q.   Okay.

3            A.   I just want to make sure it doesn't represent

4       a comparison to what costs would be in a different

5       scenario where you're not building something and that's

6       not in your generation resource plan.

7            Q.   I understand.  That's in Exhibit 189, I

8       believe.  But I'm not going to refer you to that.

9            A.   Okay.

10            Q.   Just looking at the bottom line estimated rate

11       impact of Levy capital additions, which includes the

12       base rate, that would be almost $50 per 1,000 kilowatt

13       hours in 2020; correct?

14            A.   I agree it's $49.29.

15            Q.   And again, before one kilowatt hour of

16       electricity is generated by Levy?

17            A.   That's my understanding.  Yes, sir.

18            Q.   And if you were to happen to cancel the

19       project in that year for some reason, that would be

20       charged to the consumer or the residential consumer who

21       would never see a kilowatt hour from Levy; correct?

22            A.   I don't, I don't know that I'd speculate on

23       what the rate would be if we canceled ten years from

24       now.

25            Q.   Actually it would probably be more because

FLORIDA PUBLIC SERVICE COMMISSION

167

1       you'd get to recover some additional costs.

2            A.   I'm not aware of that.  If it's in the record

3       somewhere in my testimony.

4            Q.   Okay.  Well, do you know that, that --

5            A.   I don't know that.  No, I don't, sir.

6            Q.   All right.  Well, that's fair enough.  But,

7       again, $49 with no electricity generated from Levy in

8       2020; correct?

9            A.   I agree that's what it says, yes, sir.

10       That's --

11            Q.   Thank you.  That's all I have.  Thank you.

12                 CHAIRMAN ARGENZIANO:  Okay.  Let's just, let's

13       just break for lunch now and come back in an hour.  And

14       if staff could secure the confidential information

15       before we leave.  And we'll see you in an hour.

16                 That would be 89, 91 and 92.

17                 (Recess taken.)

18                 (Transcript continues in sequence with

19       Volume 2.)

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION