169

1                              BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

3                        DOCKET NO. 100009-EI

In the Matter of:

4

NUCLEAR COST RECOVERY CLAUSE.

5       ______________________________/

6

7

8                               VOLUME 2

9                        Pages 169 through 486

10              ELECTRONIC VERSIONS OF THIS TRANSCRIPT ARE

A CONVENIENCE COPY ONLY AND ARE NOT

11               THE OFFICIAL TRANSCRIPT OF THE HEARING,

THE .PDF VERSION INCLUDES PREFILED TESTIMONY.

12

13       PROCEEDINGS:             HEARING

14       COMMISSIONERS

PARTICIPATING:           CHAIRMAN NANCY ARGENZIANO

15                                COMMISSIONER LISA POLAK EDGAR

COMMISSIONER NATHAN A. SKOP

16                                COMMISSIONER ART GRAHAM

COMMISSIONER RONALD A. BRISÉ

17

18       DATE:                    Tuesday, August 24, 2010

19       TIME:                    Commenced at 9:30 a.m.

Concluded at 5:50 p.m.

20

PLACE:                   Betty Easley Conference Center

21                                Room 148

4075 Esplanade Way

22                                Tallahassee, Florida

23       REPORTED BY:             JANE FAUROT, RPR

Official FPSC Reporter

24                                (850) 413-6732

25       APPEARANCES:             (As heretofore noted.)

FLORIDA PUBLIC SERVICE COMMISSION

170

1                              I N D E X

2                              WITNESSES

3

NAME:                                        PAGE NO.

4

GARY ROBERT DOUGHTY

5

Direct Examination by Mr. Walls           176

6            Prefiled Testimony Inserted               179

Cross Examination by Mr. Rehwinkel      229

7            Cross Examination by Mr. Brew           248

8       PATRICIA GALLOWAY

9            Prefiled Examination Inserted           260

10       JON FRANKE

11            Direct Examination by Mr. Walls         309

Prefiled Direct Testimony Inserted

12              March 2, 2010                         312

Prefiled Direct Testimony Inserted

13              April 30, 2010                        337

Cross Examination by Mr. Rehwinkel      371

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

171

1                              EXHIBITS

2       NUMBER:                                 ID.   ADMTD.

3       4, 5, 6, 7, 8 and 9                            175

4       188, 189, 190 and 192                          175

5       10, 11, 12 and 13                              257

6       14, 15, 16, 17 and 18                          259

7       193       CR-3 EPU LAR Events Outline   398

8       194       6/17/08 CR-3 EPU Management   418

Presentation

9

195       License Amendment Request     430

10

196       CR-3 EPU Expert Panel         450

11

197       Adverse Condition

12                 Investigation                 450

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

172

1                        P R O C E E D I N G S

2                 (Transcript follows in sequence from

3       Volume 1.)

4                 MR. YOUNG:  Staff has no questions.

5                 CHAIRMAN ARGENZIANO:  Okay.  Is everybody here

6       who needs to be here?  Okay, we're on, then.

7                 Commissioner Skop.

8                 COMMISSIONER SKOP:  Yes, Madam Chair, thank

9       you.  Let me find my document.

10                 Mr. Foster, just a quick question in relation

11       to what has been marked for identification as Exhibit

12       188.

13                 THE WITNESS:  Yes, sir.

14                 COMMISSIONER SKOP:  Okay.  And on the graph at

15       the bottom of that page, it shows the estimated rate

16       impact of the Levy capital additions from 2013 through

17       2024, is that correct?

18                 THE WITNESS:  The capital impact, yes, I would

19       agree with that, sir.

20                 COMMISSIONER SKOP:  Okay.  And then the bottom

21       column -- excuse me, the bottom row is the estimated

22       fuel impact savings, is that correct?

23                 THE WITNESS:  Yes, sir.

24                 COMMISSIONER SKOP:  Okay.  So just following

25       the numbers, taking 2024, for example, the actual

FLORIDA PUBLIC SERVICE COMMISSION

173

1       residential impact per a thousand kilowatt hours would

2       be the sum of the capital addition plus the fuel

3       savings.  So would that be t he net impact in the bill

4       as a whole, not necessarily the bill components, but the

5       bill as a whole would that be the worst-case, it would

6       be approximately $40?

7                 THE WITNESS:  Well, I hesitate to say in the

8       worst-case.  But I would say -- I would agree that based

9       on our projections right now is that if you assume that

10       in the interim we don't have to build any other plants,

11       if we don't build a nuclear plant, so there are no other

12       capital additions, which I don't believe is a very good

13       assumption, but if that were the assumption, I think to

14       get to your kind of worst-case, and that there are no

15       carbon costs that come into play, I think, yes, I think

16       you've characterized it fairly, sir.

17                 COMMISSIONER SKOP:  All right.  Let me reframe

18       my question.

19                 THE WITNESS:  Sure.  Sure.  I'm sorry if I'm

20       being picky.

21                 COMMISSIONER SKOP:  Under the current

22       projections that would be based on the information that

23       we have before us, the Delta difference would be that

24       number, approximately $40 per thousand kilowatts under

25       today's projections?

FLORIDA PUBLIC SERVICE COMMISSION

174

1                 THE WITNESS:  Yes.

2                 COMMISSIONER SKOP:  But.

3                 THE WITNESS:  Yes, but.  But I think there are

4       other costs, comparison type costs that are not embedded

5       in that, if you will.

6                 COMMISSIONER SKOP:  And this chart merely

7       illustrates the potential residential rates that would

8       occur for the time frame in question, but the basis for

9       those rates are 100 percent ownership, and so,

10       therefore, the data on this page, if -- and correct me

11       if I'm wrong, does not include any co-ownership interest

12       that may occur with respect to the two proposed nuclear

13       units, is that correct?

14                 THE WITNESS:  You're absolutely right, sir.

15                 COMMISSIONER SKOP:  Okay.  So I guess with

16       respect to the amounts and this data in relation to

17       co-ownership, you are probably not the appropriate

18       witness to ask in terms of what the probability of

19       co-ownership might be.

20                 THE WITNESS:  Certainly not probability of

21       co-ownership, no, sir.

22                 COMMISSIONER SKOP:  All right.

23                 Thank you, Madam Chair.

24                 CHAIRMAN ARGENZIANO:  Thank you.

25                 Commissioners, any other questions?

FLORIDA PUBLIC SERVICE COMMISSION

175

1                 Redirect?

2                 MS. HUHTA:  No redirect.

3                 CHAIRMAN ARGENZIANO:  Okay.  Then we will move

4       exhibits.

5                 MS. HUHTA:  Progress would move in Thomas G.

6       Foster's Exhibits TGF-1, 2, 3, 4, 5, and 6 as exhibits.

7       On Staff's Comprehensive List, 4, 5, 6, 7, 8, 9.

8                 CHAIRMAN ARGENZIANO:  Any objections?  Hearing

9       none, so moved.

10                 MS. HUHTA:  Thank you.

11                 (Exhibits 4, 5, 6, 7, 8, and 9 admitted into

12       the record.)

13                 CHAIRMAN ARGENZIANO:  And now --

14                 MR. REHWINKEL:  Madam Chairman, Public

15       Counsel.

16                 CHAIRMAN ARGENZIANO:  I'm sorry.  There you

17       go.

18                 MR. REHWINKEL:  I would move 188, 189, 190,

19       and 192 at this time.  I will wait until Mr. Franke gets

20       up to do 191 so we can see about confidential

21       information.

22                 CHAIRMAN ARGENZIANO:  Okay.  Any objections?

23       Hearing none, so moved.

24                 (Exhibits 188, 189, 190, and 192 admitted into

25       the record.)

FLORIDA PUBLIC SERVICE COMMISSION

176

1                 CHAIRMAN ARGENZIANO:  Go ahead.  We're okay?

2                 Ms. Kaufman, you didn't have any exhibits.

3                 Okay.  The witness is excused.  Thank you.

4                 THE WITNESS:  Thank you so much.

5                 MS. HUHTA:  Madam Chair, Mr. Foster does not

6       have any rebuttal testimony.  We would ask that he be

7       excused from the remainder of the proceeding.

8                 CHAIRMAN ARGENZIANO:  Any problems,

9       Commissioners?  Okay.

10                 MS. HUHTA:  Thank you.

11                 CHAIRMAN ARGENZIANO:  Thank you.  You're

12       excused.  He's like thank you; let me out the door.

13       (Laughter.)

14                 Okay.  Our next witness, Gary -- is it

15       Doughty?

16                 MR. WALLS:  Gary Doughty.

17                 CHAIRMAN ARGENZIANO:  Doughty.  I had a friend

18       with the same last name in high school and it was

19       Doughty.  Welcome.

20                 THE WITNESS:  Thank you.

21                         GARY ROBERT DOUGHTY

22       was called as a witness on behalf of Progress Energy

23       Florida, Inc., and having been duly sworn, testified as

24       follows:

25                          DIRECT EXAMINATION

FLORIDA PUBLIC SERVICE COMMISSION

177

1       BY MR. WALLS:

2            Q.   Mr. Doughty, will you please introduce

3       yourself to the Commission and provide your business

4       address?

5            A.   My name is Gary Robert Doughty, and my address

6       is 412 White Columns Way, Wilmington, North Carolina.

7            Q.   And have you already been sworn in as a

8       witness today?

9            A.   Yes, I have.

10            Q.   Who do you work for and what is your position?

11            A.   I am with Janus Management Associates,

12       Incorporated, and I am president.

13            Q.   Have you filed Prefiled Direct Testimony and

14       exhibits on March 1, 2010, in this proceeding?

15            A.   Yes, I have.

16            Q.   Do you have a copy with you?

17            A.   Yes, I do.

18            Q.   Do you have any changes to make to your

19       prefiled testimony and exhibits?

20            A.   Yes, one.  At Page 39, Line 22, the second

21       two, T-W-O, should read ten, T-E-N.  So the phrase

22       should read, "Two of these ten invoices."

23            Q.   And, Mr. Doughty, if I asked you the same

24       questions in your prefiled testimony today, would you

25       give the same answers that are in your prefiled

FLORIDA PUBLIC SERVICE COMMISSION

178

1       testimony?

2            A.   Yes, I would.

3                 MR. WALLS:  We request that the prefiled

4       testimony of Mr. Doughty be entered in the record as

5       read.

6                 CHAIRMAN ARGENZIANO:  Show that entered into

7       the record as read.  Thank you.

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

228

1       BY MR. WALLS:

2            Q.   Do you have a summary of your prefiled

3       testimony, Mr. Doughty?

4            A.   Yes, I do.

5            Q.   Will you please summarize your testimony for

6       the Commission?

7            A.   Yes.

8                 Good afternoon, Commissioners.  I have over

9       30 years of experience in the nuclear industry, starting

10       with the United States Navy when I was a naval officer

11       in the Nuclear Submarine Force.  In my Direct Testimony,

12       I present my expert opinion with respect to the

13       reasonableness and prudence of Progress Energy Florida's

14       project management, contracting, and oversight controls

15       for the Levy Nuclear Project, and we often phrase that

16       as LNP, in 2009.

17                 After my review and analysis of Progress

18       Energy Florida's project management policies,

19       procedures, processes, and controls, it is my opinion

20       that Progress Energy, their project management,

21       contracting, and oversight controls for LNP in 2009 were

22       reasonable and prudent.  And I'm now available to answer

23       questions related to my testimony.

24                 MR. WALLS:  We tender Mr. Doughty for cross.

25                 CHAIRMAN ARGENZIANO:  Mr. Rehwinkel.

FLORIDA PUBLIC SERVICE COMMISSION

229

1                 MR. REHWINKEL:  Yes, thank you.

2                          CROSS EXAMINATION

3       BY MR. REHWINKEL:

4            Q.   Good afternoon, Mr. Doughty.

5            A.   Good afternoon.

6            Q.   I didn't mean to slight you in listing the

7       engineers, nuclear engineers.  I was talking about the

8       company witnesses.

9            A.   Thank you.

10            Q.   I would ask you what is your understanding of

11       the term reasonable and prudent as you use it in your

12       testimony?

13            A.   Exactly what I say when I talk about prudence

14       with respect to Page 9, beginning about the middle of

15       the page, where it's that standard of care which a

16       reasonable utility manager would be expected to exercise

17       under the same circumstances encountered by utility

18       management at the time decisions had to be made.

19                 And then what I do is enumerate some tenets

20       with respect to when you evaluate prudence, for

21       instance, that hindsight is prohibited, that there is an

22       assumption or presumption of prudence, and evidence has

23       to be identified and clarified and found to indicate

24       imprudence.  And that you can't substitute your judgment

25       for that of the utility manager.  There could be an

FLORIDA PUBLIC SERVICE COMMISSION

230

1       honest difference of opinions in terms of whether or not

2       one course of action is prudent or another.  You can

3       have an honest difference of opinion, and there can be

4       many alternatives that could be prudent.

5            Q.   Let me ask you about that alternative.  You

6       would agree, would you not, that a utility manager when

7       making a decision that might be subject to review under

8       a reasonable and prudent standard might have a range of

9       decisions that she could make, each of which would be

10       reasonable and prudent, is that correct?

11            A.   Yes.

12            Q.   And in your testimony -- actually in the work

13       you did to support your testimony, did you find that to

14       be the case with respect to what you reviewed for 2009?

15       That meaning that there were ranges of options that the

16       utility managers that you reviewed with Progress Energy

17       chose from?

18            A.   Yes, in the sense that when I looked at

19       project management and project controls, I identified

20       certain standards which are contained in my testimony,

21       and then followed those through with respect to that

22       evaluation.  So, frequently, for instance, in the terms

23       of procedures, in reviewing the procedures and having

24       knowledge of nuclear industry procedures, large project

25       procedures, evaluated the characteristics of the

FLORIDA PUBLIC SERVICE COMMISSION

231

1       procedures that are being employed on the Levy nuclear

2       project with reference to what my team collectively had

3       in mind in terms of procedures for a project of this

4       complexity and magnitude.

5            Q.   Now, it's true, is it not, that your testimony

6       only addresses -- well, let me step back and ask it this

7       way.  The scope of work that resulted in your testimony

8       only included Progress Energy's Levy nuclear plant?

9            A.   That's correct.

10            Q.   And you did not, therefore, look at the

11       project related to the CR-3 extended power uprate, is

12       that correct?

13            A.   That is correct.

14            Q.   Was there a reason for that?

15            A.   That was -- the focus was specifically

16       requested by Progress Energy Florida to look at the Levy

17       Nuclear Project.

18            Q.   Okay.  In your testimony do you make any

19       reference to customers?

20            A.   I don't recall any specific reference to

21       customers, no.

22            Q.   Okay.  If a utility manager has a range of

23       options that are being evaluated for reasonableness and

24       prudence, and one of the options is more beneficial --

25       let me strike that and ask it this way.

FLORIDA PUBLIC SERVICE COMMISSION

232

1                 If a utility manager has a range of options in

2       his decision-making, each of which would meet the

3       reasonableness and prudence standard in your testimony,

4       and one of those options is more beneficial to the

5       customers, does that utility manager have any obligation

6       to choose that decision over the other decisions?

7            A.   I'm not sure I can answer your hypothetical

8       because I don't think there is enough facts.  You have

9       to look at the entirety of the information, the totality

10       of the information.  And how does one determine what --

11       whether that is a greater benefit or not?  I have to

12       deal with a specific.

13            Q.   Okay.  Well, the purpose of your testimony is

14       to validate the decision-making of Progress Energy such

15       that its decisions qualify for cost-recovery under the

16       reasonableness and prudence standards of the statute,

17       isn't that correct?

18            A.   Yes, for 2009.

19            Q.   Okay.  Now, are you -- I noticed in your body

20       of work that you have done quite a lot of work on behalf

21       of public service commissions around the country, is

22       that correct?

23            A.   Both.  Actually, our team, my team, has done

24       quite a large number of major nuclear projects when the

25       first wave of later nuclear projects were coming on

FLORIDA PUBLIC SERVICE COMMISSION

233

1       line.  I was involved both on the company side and on

2       the Commission side.

3            Q.   Okay.  So you understand the purpose of --

4       well, let me ask it this way.  Isn't it true that the

5       advanced cost-recovery provisions of the statute that

6       governs this proceeding are relatively new with respect

7       to utility ratemaking?

8            A.   Yes.  Can I clarify my response to the

9       previous question?

10            Q.   Sure.

11            A.   One of the things I do understand with respect

12       to being an expert witness is I'm not on somebody's

13       side.  I am on, in essence, the Commission's side to

14       identify the true facts and give my expert opinion.  So

15       it's not in terms of choosing sides, but rather

16       independence.  So could you repeat your question?

17            Q.   Well, sure.  I mean, what you just told me is

18       much like what Dr. Jacobs does for the Georgia Public

19       Service Commission.  He's an independent monitor of the

20       construction project, isn't that fair?

21            A.   Right, and I have served that role.

22            Q.   Okay.  So in serving that role, you do

23       understand that the public service commissions that you

24       would work for are charged with looking out, in part,

25       for the interests of the customers of the utilities they

FLORIDA PUBLIC SERVICE COMMISSION

234

1       regulate, isn't that true?

2            A.   Yes, that true.

3            Q.   Okay.  So the question I asked that you said

4       yes to, but you may -- you wanted to talk about the

5       prior question, so I want to ask it again.  Is the

6       advanced recovery provisions of the nuclear

7       cost-recovery rule and statute that govern this

8       proceeding are relatively new in terms of utility

9       ratemaking, isn't that correct?

10            A.   Yes, to a certain extent.  Certainly in the

11       new nuclear power field, but in many instances utility

12       commissions are reviewing decisions at the time the

13       utility raises it as a potential capital investment.  So

14       it's more prospective or even current prudence review

15       rather than what the first wave of nuclear plants had

16       and coal plants, too, and hydro facilities, which was a

17       retrospective, after the project had already been

18       completed and was ready to be placed in service, and,

19       therefore, in rates.

20            Q.   And until the advanced recovery statutes were

21       authorized in a handful of states, isn't it true that

22       virtually every state only allowed cost-recovery for

23       major rate base additions only after those additions

24       contributed to the generation of electricity?

25            A.   To the extent of my knowledge, and I'm not --

FLORIDA PUBLIC SERVICE COMMISSION

235

1       I don't know if this is a universal -- capable of being

2       a universal response, but to the best of my knowledge

3       that was the case, certainly as I was describing in the

4       1970s and '80s.

5            Q.   Okay.  So what's new about the statute that

6       governs this proceeding is that cost-recovery is allowed

7       in advance, many years in advance of the proposed units

8       generating any electricity, correct?

9            A.   As I understand the statute, and the Nuclear

10       Cost-Recovery Clause, that is what's happening, because

11       you have established in the state of Florida this

12       statute by law to permit recovery of those type of

13       expenditures that are covered by the law.

14            Q.   And the Florida Public Service Commission is

15       charged under the law with, among other things, making

16       determinations about the reasonableness and prudence of

17       the utility's decision-making as these advanced -- as

18       these expenditures occur well in advance of the

19       generation of any electricity, isn't that correct?

20                 MR. WALLS:  I'm going to object to this line

21       of questioning.  Mr. Doughty I'm not sure is an expert

22       on the Florida statute and rule.  He had a particular

23       job to do and came in and testified to the project

24       management controls and oversight controls, and it seems

25       like he is being asked to opine about the statute and

FLORIDA PUBLIC SERVICE COMMISSION

236

1       rule.

2                 CHAIRMAN ARGENZIANO:  Mr. Rehwinkel.

3                 MR. REHWINKEL:  Madam Chairman, my questions

4       go to the nature and the quality of the reasonableness

5       and prudence opinion that he's rendering here.  And I

6       have a line of questions that is about to get to an

7       ultimate point, and actually I touched on it earlier,

8       which is the Public Service Commission is charged with

9       looking after the customers.  And part of this

10       decision-making that he is evaluating, I want to find

11       out whether qualitatively there is any view with respect

12       to the customers' interests.  So I'm trying to test the

13       nature of his opinions that he's offering, specifically

14       on reasonableness and prudence.

15                 CHAIRMAN ARGENZIANO:  Can you rephrase without

16       asking him his opinion of the statute or his knowledge

17       of the statute?

18                 MR. REHWINKEL:  Well, I think he already

19       acknowledged that his reasonableness and prudence

20       opinions are given to meet the standards that are in

21       this statute.

22                 CHAIRMAN ARGENZIANO:  Ms. Helton.

23                 MR. REHWINKEL:  I'm definitely not looking for

24       his legal opinion about the statute.

25                 CHAIRMAN ARGENZIANO:  Okay.

FLORIDA PUBLIC SERVICE COMMISSION

237

1                 MS. HELTON:  As I understand the witness'

2       testimony, and please correct me, Mr. Walls, if I'm not

3       hearing this correctly, he is here to give an opinion

4       with respect to prudence as prudence is contemplated in

5       Chapter 366, is that correct?

6                 MR. WALLS:  But on project management controls

7       and oversight.

8                 MS. HELTON:  With one specific, I guess,

9       narrow type of expenses that could be deemed prudent

10       under the statute, is that what your point is?

11                 MR. WALLS:  My point is that the Commission

12       has established an issue in this proceeding each year,

13       which is whether the company's project management

14       controls and oversight on the project are reasonable and

15       prudent, and that's what Mr. Doughty is coming in as an

16       independent expert to review the project management

17       policies and procedures and implementation of those, and

18       say whether those are reasonable and prudent.

19                 He is not looking at the costs that are being

20       requested and recovered, and he's not opining on any of

21       the costs.  He is specifically looking at did the

22       company have prudent project management policies and

23       procedures in place, and did they follow those in 2009,

24       and that's what he is opining on.

25                 MS. HELTON:  Madam Chairman, I'm sorry, I'm

FLORIDA PUBLIC SERVICE COMMISSION

238

1       going to have to have Mr. Rehwinkel repeat the question.

2                 CHAIRMAN ARGENZIANO:  Let's do that.

3                 MR. REHWINKEL:  Why don't I do this; why don't

4       I ask a different question?

5                 MS. HELTON:  Okay.

6                 CHAIRMAN ARGENZIANO:  We can do that, too.

7       BY MR. REHWINKEL:

8            Q.   Mr. Doughty, let me ask you again about the

9       range of reasonable decisions that you might, or the

10       range of decisions that might be subject to an

11       evaluation for reasonableness and prudence.  And is it

12       your testimony that the customers' interests should not

13       be given any greater weight in evaluating which of a

14       range of possible options that the company might have

15       should be chosen as long as all of the options would fit

16       the reasonableness and prudence standard that is in your

17       testimony on Page 9?

18            A.   But my testimony is with regard to the project

19       management and project controls that were in place for

20       the project.  So it's a narrow focus, I agree, but it is

21       the focus.  I haven't looked at any other types of

22       decisions other than those that apply to did the company

23       reasonably have in place organizational processes,

24       procedures, policies, and not only implement them, but

25       carry through on them and have a feedback loop to check

FLORIDA PUBLIC SERVICE COMMISSION

239

1       them, as an example.

2            Q.   So is it your testimony that the customers

3       interests have -- the customers have no interest in

4       those project controls and management practices?

5            A.   The customers would have an interest in the

6       sense of if they were reasonable and prudent policies,

7       procedures, project management decisions and activities

8       would yield, you know, a reasonable implementation of

9       the project.

10            Q.   Is it fair to say that as long as a utility

11       manager makes a reasonable or prudent decision within

12       the range of options that he has, that whether one

13       decision favors the customers' interests more than the

14       other, it does not matter for purposes of the Public

15       Service Commission's determination?

16            A.   I don't think I understand your question,

17       because I haven't looked at that.  I looked at project

18       management and project controls on the Levy Nuclear

19       Project.

20            Q.   Okay.  Now, you did not evaluate the decision

21       by the company in 2009 with respect to -- the

22       decision-making by the company with respect to which of

23       the options they might choose with respect to the

24       in-service date of the project, is that correct?

25            A.   If you are talking about the decision that

FLORIDA PUBLIC SERVICE COMMISSION

240

1       they made in March/April of 2010, that's correct.  I did

2       not look at that.  What I looked at was the collection

3       of information and the actions that were taken during

4       2009 with respect to project management and project

5       controls.

6            Q.   Did any of that cover the decision-making that

7       led up to the 2010 decision to select the option that

8       they are proposing in this case?

9            A.   In the sense that I looked at and reported on

10       the fact that they had requested information from both

11       Westinghouse Electric Corporation and Shaw, Stone and

12       Webster with regard to providing them information for a

13       schedule shift of greater than the 20 months that was

14       indicated, yes, and I spoke with various personnel with

15       respect to that effort that was going on then, which was

16       the data collection and the beginning of the analysis.

17            Q.   On that point --

18                 MR. REHWINKEL:  And, Madam Chairman, I have

19       some questions based -- with some documents, but the

20       company is reviewing those documents to try to winnow

21       down confidentiality, or at least to identify it in the

22       documents.  And if I could work with the company on

23       this, I don't need to ask Mr. Doughty questions about

24       the documents, I just need to authenticate the documents

25       with him.  So what I would like to do is to try to ask

FLORIDA PUBLIC SERVICE COMMISSION

241

1       him about these documents, and if we need to produce the

2       documents we will.  Otherwise, I will take them up with

3       the other witnesses I intended them with.

4                 CHAIRMAN ARGENZIANO:  Okay.

5       BY MR. REHWINKEL:

6            Q.   Mr. Doughty, you mentioned interviews, and is

7       it correct that you interviewed John Elnitsky and Sue

8       Hardison as part of your work?

9            A.   Yes, it is.

10                 CHAIRMAN ARGENZIANO:  Mr. Rehwinkel, hang on

11       one second.

12                 MR. WALLS:  We are not imposing any objections

13       on authenticity or grounds, so.

14                 CHAIRMAN ARGENZIANO:  Okay.

15                 MR. REHWINKEL:  I understand.  I just need to

16       go through this.

17       BY MR. REHWINKEL:

18            Q.   And you would have generated notes from those

19       interviews, is that correct?

20            A.   That is correct.  They were notes as taken,

21       essentially.

22            Q.   Now, did you take these or did members of your

23       team do these?

24            A.   All of the above; that is, that there were --

25       all of us took notes and accumulated them into the

FLORIDA PUBLIC SERVICE COMMISSION

242

1       single set of notes.

2            Q.   Were they recorded or just these are

3       handwritten notes that you typed up?

4            A.   Handwritten, typed up.

5            Q.   Okay.  All right.  Now, when you took these

6       notes and generated the documents that the company

7       provided to the staff and to the Public Counsel, were

8       the subjects of the interviews, did they make any

9       corrections or provide any further input to the draft

10       that you produced?

11            A.   Which draft?  Or what draft are you talking

12       about?

13            Q.   I'm looking at a draft of Sue Hardison's

14       interview on February 9, 2010?

15            A.   No, they did not.

16            Q.   Okay.  Were they offered that opportunity?

17            A.   No.

18                 CHAIRMAN ARGENZIANO:  Excuse me, Mr.

19       Rehwinkel.

20                 Commissioner Skop.

21                 COMMISSIONER SKOP:  Thank you, Madam Chair.

22                 To Mr. Rehwinkel, with respect to the

23       documents in question, I think that you indicated you

24       did not have any questions regarding the documents, but

25       it appears that you are laying a predicate or a

FLORIDA PUBLIC SERVICE COMMISSION

243

1       foundation for authenticating the documents, is that

2       correct?  Because I think I heard Progress -- and the

3       reason I ask, I thought I heard Progress say that they

4       are not contesting to the authenticity of the documents,

5       so I'm wondering if it is necessary to lay that

6       foundation.

7                 MR. REHWINKEL:  Well, it is not as to the

8       documents itself, but if I ask a subsequent witness did

9       you say that, I want to make sure that there is not a

10       dispute about that.

11                 COMMISSIONER SKOP:  Very well.  Thank you.

12       BY MR. REHWINKEL:

13            Q.   And what about with Mr. Elnitsky, would he

14       have been offered the opportunity to review the notes?

15            A.   No.

16            Q.   Okay.  Is there any doubt in your mind about

17       the accuracy of the statements that are contained in the

18       notes for Mr. Elnitsky and Ms. Hardison?

19            A.   As labeled on the top, they are for discussion

20       purposes only, because they are not a recordation of the

21       actual questions and answers.  So there may be some

22       items that were not necessarily part of the focus, but

23       were broader in terms and we may not have gotten exactly

24       right.

25            Q.   On Page 24 of your testimony, could you turn

FLORIDA PUBLIC SERVICE COMMISSION

244

1       to that?

2            A.   Page 24?

3            Q.   Yes, sir.

4            A.   I'm there.

5            Q.   Okay.  Actually, this starts on Page 23 at the

6       bottom.  You offered testimony about the implementation

7       of the LNP schedule shift, and you testified that the

8       company reduced planned 2009 work on both the nuclear

9       plant and the base load transmission project to address

10       the schedule shift, do you see that?

11            A.   Yes.

12            Q.   And you continue on to the top of Page 24, all

13       the way down to Line 6.  You say, "This included

14       deferral of procurement activities for those long lead

15       items that could reasonably and economically be

16       deferred, limited planned staffing additions for the

17       NPD, and reducing the amount of work planned for the

18       base load transmission project."  Do you see that?

19            A.   Yes.

20            Q.   Did you review a program within the company in

21       2009 called operational readiness project?

22            A.   Not that I recall.

23            Q.   Okay.  Do you recall reviewing any projects of

24       the company that caused them to -- whereby they intended

25       to hire and train engineers and other operating

FLORIDA PUBLIC SERVICE COMMISSION

245

1       personnel for the projected Levy plant?

2            A.   I was aware of the staffing plans that were

3       anticipated for the Levy Nuclear Project, but I did not

4       read anything beyond that.  It was primarily in

5       discussion with Mr. Miller when we were doing the 2008

6       review in early 2009.

7            Q.   Okay.  Did you review the staff audit report

8       that was produced in this docket?

9            A.   I've reviewed staff audit reports, I think

10       three of them.  I don't know the exact dates.  One would

11       have been for 2008.  I think one came out in the middle

12       of 2009, and the third one may have just recently come

13       out or came out as a draft.

14            Q.   I'm asking about the one that's attached to

15       the testimony of the staff witnesses in this case.  Did

16       you review that document?

17            A.   Not while I was doing this review, no.

18            Q.   Did you review it after that?

19            A.   If it's the one that came out in 2010 --

20            Q.   Yes.

21            A.   -- I have recently reviewed that.

22            Q.   Okay.  Do you recall the section in there

23       about an operational readiness group?

24            A.   No.

25            Q.   Okay.  So if there was -- I guess by

FLORIDA PUBLIC SERVICE COMMISSION

246

1       definition, you did not review that effort by the

2       company with respect to whether they limited planned

3       staffing additions relative to that project, is that

4       correct?

5            A.   Are you reading from my testimony on a

6       particular line?

7            Q.   Yes.  Again, Line 6 through 9 on Page 24.

8            A.   The planned staffing additions had to do with

9       the project team.  The organization that existed prior

10       to the signing of the engineer procured construct

11       contract was adjusted, and there were plans to add

12       significant numbers of staff in the early part of 2009

13       because of the anticipated start up of work both by the

14       consortium -- well, by the consortium and the other work

15       that was going on by other contractors.  So that's what

16       I'm talking about is the project management staff, the

17       project control staff that was anticipated to be added

18       to and then was not.

19            Q.   Okay.  You didn't find anything in your work

20       where the company did anything wrong or that wasn't

21       prudent, isn't that correct?

22            A.   I did not find any imprudent or wrong activity

23       by the company that would have led me to change my

24       opinion of the reasonableness of the project management

25       and project controls in place.

FLORIDA PUBLIC SERVICE COMMISSION

247

1            Q.   Okay.  And the project management activities

2       that you evaluated, would the company's actions with

3       respect to those activities have any influence or affect

4       on the enterprise risks that would impact the Levy

5       Nuclear Project?

6            A.   Would you restate your question or --

7            Q.   Yes.  The project management activities that

8       you evaluated for prudence, none of those activities

9       would have any impact or influence upon enterprise risks

10       that might impact the Levy Nuclear Project, isn't that

11       correct?

12            A.   No.  In reviewing project management and

13       project risk, a reasonably run project will reduce risk

14       unless it's totally external.  For instance, we were

15       talking earlier with another witness with regard to

16       carbon taxes or cap and trade legislation which is

17       beyond the control of the company, so an externality, if

18       you will.

19            Q.   Well, my question was as to enterprise risks

20       which are external, aren't they?

21            A.   Not necessarily.  But for the most part, the

22       ones that people talk about are external.

23            Q.   Okay.  But would you agree with the definition

24       that enterprise risks are those that are outside the

25       control of the company?

FLORIDA PUBLIC SERVICE COMMISSION

248

1            A.   Not necessarily.  But for the most part, many

2       enterprise risks are outside the ability of the company

3       to control.

4                 MR. REHWINKEL:  Okay.  Thank you, Mr. Doughty;

5       that is all the questions I have.

6                 Thank you.

7                 CHAIRMAN ARGENZIANO:  Thank you.

8                 Commissioners, any questions?

9                 COMMISSIONER SKOP:  I have a few.

10                 CHAIRMAN ARGENZIANO:  Commissioner Skop.

11                 COMMISSIONER SKOP:  Do you want to take the

12       other intervenors who have any questions before?

13                 CHAIRMAN ARGENZIANO:  Well, did you want to

14       ask your question now?

15                 COMMISSIONER SKOP:  I can wait until the

16       intervenors.

17                 CHAIRMAN ARGENZIANO:  Okay.  Well, then let's

18       proceed.

19                 MR. BREW:  Thanks.

20                          CROSS EXAMINATION

21       BY MR. BREW:

22            Q.   Good rod afternoon, Mr. Doughty.

23            A.   Good afternoon.

24            Q.   Mr. Doughty, were you asked to evaluate the

25       enterprise risks facing the company?

FLORIDA PUBLIC SERVICE COMMISSION

249

1            A.   No.

2            Q.   Okay.  Were you asked to evaluate the

3       company's evaluation of its going forward options with

4       respect to Levy that it announced in its April 30th

5       testimony?

6            A.   I'm sorry, I didn't hear the last part of your

7       question.

8            Q.   The going-forward options that the company

9       described in its April 30 testimony, were you asked to

10       evaluate those options?

11            A.   No, sir.

12                 MR. BREW:  That's all I have.  Thanks.

13                 CHAIRMAN ARGENZIANO:  Ms. Kaufman.

14                 MS. KAUFMAN:  Thank you, Chairman.

15                          CROSS EXAMINATION

16       BY MS. KAUFMAN:

17            Q.   Good afternoon, Mr. Doughty.  I just really

18       have one area that I want to talk to you about, and you

19       addressed this with Mr. Rehwinkel.

20                 On Page 9 of your testimony, you talk about

21       the standard of reasonableness --

22            A.   Just a second.

23            Q.   I'm sorry.

24            A.   Okay.  Page 9.

25            Q.   Okay.  Toward the bottom you talked about the

FLORIDA PUBLIC SERVICE COMMISSION

250

1       standard of reasonableness and prudence that you used in

2       your assessment.

3            A.   Yes.

4            Q.   And one of the tenets, I guess, of your

5       assessment is the one that appears on Line 23, that

6       there is a presumption of management prudence?

7            A.   Yes.

8            Q.   Would you agree with me that in a proceeding

9       like this where the company is asking to collect money

10       or change rates to the ratepayers that the burden of

11       proof always lies with the utility?

12            A.   No, I would not agree.

13            Q.   Okay.  Have you review -- I know that you are

14       not an attorney, but in the course of your review here

15       and your work, have you taken a look at any Public

16       Service Commission orders in regard to how the

17       Commission looks at presumptions and burdens of proof?

18            A.   Are we talking about the Florida Commission?

19            Q.   Yes, sir, the Florida Commission.

20            A.   No, I haven't.  But in my experience in

21       dealing with prudence since 1984, it's pretty well

22       established within other jurisdictions that there is a

23       presumption of prudence, and in terms of many articles

24       that I have read.  And the fundamental tenets that I

25       identify here are a collection.  The first and foremost

FLORIDA PUBLIC SERVICE COMMISSION

251

1       is the National Regulatory Research Institute, which

2       issued a significant paper back in about the 1985 to '88

3       time frame from Ohio State University, which identified

4       some of these tenets, and then subsequent to that

5       significant either public service commission decisions,

6       or if they were elevated to the court to where those

7       were recorded, the outcome of that court, those court

8       decisions.

9            Q.   You are not referring to Florida decisions,

10       though?

11            A.   No, ma'am.

12                 MS. KAUFMAN:  Madam Chairman, I have an

13       exhibit.  It's actually an order, but I will pass it out

14       so everybody will have reference to it.

15                 CHAIRMAN ARGENZIANO:  It should be numbered

16       193.

17                 MS. HELTON:  Madam Chairman, my recommendation

18       would be that we just take official notice of the order.

19       I don't think it's necessary to mark it as an exhibit.

20                 CHAIRMAN ARGENZIANO:  Okay.  Very good.

21                 MS. KAUFMAN:  That's fine.

22                 For the record, it is Order Number

23       PSC-09-0024.

24                 CHAIRMAN ARGENZIANO:  Thank you.

25       BY MS. KAUFMAN:

FLORIDA PUBLIC SERVICE COMMISSION

252

1            Q.   Mr. Doughty, you have Order Number 09-0024 in

2       front of you, correct?

3            A.   Yes, I do.

4            Q.   Okay.  And I'll represent to you, and I think

5       your counsel will agree, that this is an order from the

6       annual fuel adjustment proceedings in which the

7       Commission sets the fuel adjustment factor, and they set

8       that annually.

9                 If you take a look at Page 12, which I've got

10       tabbed for you, and I'm going to be looking at the top

11       paragraph there.  And, again, I represent to you that in

12       this case the Commission was looking at making a

13       prudence determination about some activities of Florida

14       Power and Light.  Would you mind reading that

15       highlighted sentence?

16            A.   The highlighted sentence that's in yellow

17       that's in about the middle of the first paragraph?

18            Q.   Yes, sir.

19            A.   It has been well-established both by us and

20       the state's courts that the burden of proof lies with

21       the utility who is seeking a rate change.

22            Q.   So would you agree with me that this is the

23       standard that the Commission typically applies to a

24       utility seeking a rate change in Florida?

25            A.   I don't know if I can agree with you.  I don't

FLORIDA PUBLIC SERVICE COMMISSION

253

1       have enough knowledge to be able to agree or disagree,

2       but I do understand what I read there.

3                 MS. KAUFMAN:  Thank you.  That's all the

4       questions I have.

5                 CHAIRMAN ARGENZIANO:  Thank you.

6                 MR. DAVIS:  None from SACE.  Thank you.

7                 CHAIRMAN ARGENZIANO:  Okay.  Commissioner

8       Skop.

9                 COMMISSIONER SKOP:  Thank you, Madam Chair.

10                 Just a few questions, Mr. Doughty.  On Page 3

11       of your prefiled testimony -- or, excuse me, Page 7 of

12       your prefiled testimony.

13                 THE WITNESS:  Page 7?

14                 COMMISSIONER SKOP:  Yes, sir.

15                 THE WITNESS:  Yes.

16                 COMMISSIONER SKOP:  On Lines 1 through 6 you

17       identify that you've performed 16 independent reviews

18       regarding the prudency of utility management with

19       respect to nuclear power plants and submitted testimony

20       regarding the reviews to nine public utility

21       commissions.  With respect to the exhibit that's marked

22       in your prefiled testimony as GRD-3, and I'll give you a

23       second to turn to that.

24                 THE WITNESS:  Okay.

25                 COMMISSIONER SKOP:  With respect to each of

FLORIDA PUBLIC SERVICE COMMISSION

254

1       those management prudence reviews that you conducted for

2       those commissions listed there, were there any instances

3       where you found management to be imprudent or actions to

4       be imprudent?

5                 THE WITNESS:  Yes, Commissioner.  In items

6       under Maryland, Item Number 1, and for Massachusetts,

7       the Pilgrim outage, we found imprudence in management of

8       a long outage which went longer than was reasonable, in

9       our opinion.  And I can't quantify dollars, but it was

10       in terms of days in several instances in the Pilgrim

11       case, and in at least two instances in the Calvert

12       Cliffs case.

13                 COMMISSIONER SKOP:  Okay.  And you have had,

14       based on your biographical information, substantial

15       nuclear experience working at Millstone units up in

16       Connecticut and various other things, as well as your

17       nuclear submarine experience, is that correct?

18                 THE WITNESS:  Yes, sir.

19                 COMMISSIONER SKOP:  Okay.  In relation to the

20       information that you were asked to review in this

21       proceeding, it's my understanding from your testimony

22       that it was strictly limited to the Levy 1 and 2 nuclear

23       units and not the CR-3 EPU LAR, is that correct?

24                 THE WITNESS:  That's correct.

25                 COMMISSIONER SKOP:  Okay.  On Page 11 of your

FLORIDA PUBLIC SERVICE COMMISSION

255

1       prefiled testimony, you indicated that in your

2       professional opinion that Progress had reasonable and

3       prudent LNP, or -- yes, LNP project management -- I mean

4       project management and project controls in place in

5       2009, and that was because basically they had taken

6       appropriate steps and had appropriate controls in place

7       to identify not only risk management, but risk

8       mitigation on contractual issues and other things that

9       you identified on Page 12, is that correct?

10                 THE WITNESS:  Yes, sir.  And that they had in

11       place policies and procedures to guide personnel who

12       were participants in the project.  Cost controls,

13       contract controls on the vendors that were involved in

14       the project.

15                 COMMISSIONER SKOP:  Okay.  And then, finally,

16       on Page 23 of your prefiled testimony, you discuss the

17       circumstances regarding the fact that the NRC denied the

18       LWA and indicated they would not issue it prior to the

19       COL, is that correct?

20                 THE WITNESS:  Yes, sir.

21                 COMMISSIONER SKOP:  Okay.  And in this case is

22       it correct to understand, based on the data that you

23       have reviewed, that Progress reasonably thought at the

24       time that the original schedule was created that

25       pursuant to the NRC's streamlined licensing process of a

FLORIDA PUBLIC SERVICE COMMISSION

256

1       new that the LAW would be granted to allow limited work

2       authorization prior to the issuance of COL?

3                 THE WITNESS:  Yes, sir.

4                 COMMISSIONER SKOP:  And when that changed, you

5       know, that was not reasonably foreseeable by Progress,

6       is that correct, because Progress doesn't control what

7       the NRC does?

8                 THE WITNESS:  That is correct.  And, in fact,

9       in December of 2008, there was an indication here in

10       Florida by an NRC representative that there was an

11       expectation of receiving the LWA on the schedule that

12       they were anticipating.

13                 COMMISSIONER SKOP:  Okay.  So on Page 23 of

14       your prefiled testimony, Lines 18 through 20, you

15       indicated without the ability to accomplish the LWA

16       scope requested that PEF had to readjust its schedule,

17       and that's primarily what drove that schedule shift for

18       the LWA to the extent that they had anticipated on being

19       able to do work in advance of the COL that the NRC

20       subsequently told them they could not perform, is that

21       correct?

22                 THE WITNESS:  Yes, sir.

23                 COMMISSIONER SKOP:  All right.  Thank you,

24       Madam Chair.

25                 Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

257

1                 CHAIRMAN ARGENZIANO:  Staff.

2                 MR. YOUNG:  Staff has no questions.

3                 CHAIRMAN ARGENZIANO:  Progress, redirect?

4                 MR. WALLS:  No redirect.

5                 CHAIRMAN ARGENZIANO:  Okay.  Let's move

6       exhibits.

7                 MR. WALLS:  Yes.  We would move Exhibits

8       GRD-1, 2, 3, and 4, which are identified in the Staff

9       Comprehensive Exhibit as Exhibits 10, 11, 12, and 13.

10                 CHAIRMAN ARGENZIANO:  Any objections?  Hearing

11       none, so moved.

12                 (Exhibits 10, 11, 12, and 13 admitted into the

13       record.)

14                 CHAIRMAN ARGENZIANO:  Mr. Rehwinkel?

15                 Any other questions, Commissioners?

16                 You're excused.  Thank you.

17                 THE WITNESS:  Thank you.

18                 MR. REHWINKEL:  Madam Chairman, before

19       Mr. Franke takes the stand, would it be possible to take

20       a brief break to discuss confidentiality with the

21       company?

22                 CHAIRMAN ARGENZIANO:  Certainly.  We'll take

23       about a five-minute break.

24                 MR. YOUNG:  Madam Chairman, before we do that,

25       I think Mr. Walls is going to ask for Mr. Doughty to be

FLORIDA PUBLIC SERVICE COMMISSION

258

1       excused.  He doesn't have rebuttal.

2                 MR. WALLS:  Yes.  Mr. Doughty does not have

3       rebuttal testimony, so we would ask he be excused from

4       the hearing.

5                 CHAIRMAN ARGENZIANO:  He's excused.  Let the

6       poor guy go.

7                 MR. WALLS:  Thank you.

8                 CHAIRMAN ARGENZIANO:  Thank you.  Let's take a

9       five-minute break.

10                 (Recess.)

11                 CHAIRMAN ARGENZIANO:  Where were we now?  Did

12       you get everything -- you got everything you needed,

13       Mr. Rehwinkel?

14                 MR. REHWINKEL:  Yes, ma'am.  The company has

15       been very helpful in taking exhibits that I planned to

16       use and reviewing them for confidentiality, not only for

17       purposes of the Commissioners and parties in

18       understanding what is confidential, but to eliminate or

19       narrow down confidentiality within the documents.  I

20       appreciate it.

21                 CHAIRMAN ARGENZIANO:  Okay.  Absolutely.  Then

22       we're square.  Keino -- Mr. Young.

23                 MR. YOUNG:  Mr. Chairman, at this time I think

24       Mr. Walls is going to make a request that Ms.

25       Galloway's -- Dr. Galloway's Prefiled Testimony and

FLORIDA PUBLIC SERVICE COMMISSION

259

1       Exhibits be entered into the record.

2                 CHAIRMAN ARGENZIANO:  Be entered into the

3       record?

4                 MR. WALLS:  That's correct.  The parties have

5       agreed to waive cross examination and stipulate to the

6       testimony of Dr. Patricia Galloway's Prefiled Testimony

7       on April 30th, 2010, into the record as though read and

8       to the entry of her exhibits into the record.  So we

9       would move that her testimony be entered into the

10       record.

11                 CHAIRMAN ARGENZIANO:  Hearing no objection,

12       show that Dr. Galloway's testimony be entered into the

13       record as though read.

14                 MR. WALLS:  And we have four exhibits,

15       Exhibits PDG-1, 2, 3, 4, and 5, which are identified on

16       staff's exhibit list as Numbers 14, 15, 16, 17, and 18,

17       and we would move those into evidence at this time.

18                 CHAIRMAN ARGENZIANO:  Hearing no objection,

19       those are moved into the record.

20                 (Exhibits 14, 15, 16, 17, and 18 admitted into

21       the record.)

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

308

1                 CHAIRMAN ARGENZIANO:  Anything else?  Okay.  I

2       guess we are ready for our next witness, Mr. Jon Franke.

3                 THE WITNESS:  Yes, ma'am.

4                 CHAIRMAN ARGENZIANO:  Hi.  Welcome.

5                 MR. WALLS:  Mr. Franke, would you --

6       Mr. Franke was not previously sworn.

7                 CHAIRMAN ARGENZIANO:  He was not?

8                 MR. WALLS:  No, he was not.

9                 CHAIRMAN ARGENZIANO:  Okay.  Would you stand,

10       please, and raise your right hand.  And you do not have

11       to repeat after me.

12                 I'm sorry, I started out the wrong way.  I was

13       put you -- get you onto a board.  I used to do that a

14       lot as a legislator, and I'd go around to different

15       counties and put people on different boards, and I was

16       going to give you a whole different thing to say.  So

17       let's not do that.

18                 (Witness sworn.)

19                 CHAIRMAN ARGENZIANO:  Thank you.  Proceed,

20       please.

21                              JON FRANKE

22       was called as a witness on behalf of Progress Energy

23       Florida, Inc., and having been duly sworn, testified as

24       follows:

25                          DIRECT EXAMINATION

FLORIDA PUBLIC SERVICE COMMISSION

309

1       BY MR. WALLS:

2            Q.   Mr. Franke, would you please introduce

3       yourself and provide your business address?

4            A.   Yes.  My name is Jon Franke.  I am the Vice

5       President for the Crystal River Nuclear Plant.  My

6       address is 15760 West Power Line Drive, Crystal River,

7       Florida 34428.

8            Q.   And have you filed Prefiled Direct Testimony

9       and Exhibits on March 1, 2010, and April 30, 2010, in

10       this proceeding?

11            A.   I have.

12            Q.   Do you have copies with you?

13            A.   Yes, I do.

14            Q.   Do you have any changes to make to your

15       prefiled testimony?

16            A.   Yes, I have one correction made to a schedule.

17       This is Schedule P-7 of my testimony.  Actually, it's

18       attached to Jeff Foster's testimony for which I sponsor.

19       If you refer to Line 4 of that schedule, Column Gulf or

20       G.

21                 Mr. Rehwinkel, would you like for me to wait

22       for you to get that?  And this is a confidential number,

23       but there should be a -- currently if you look at --

24       Mr. Rehwinkel, I will wait for you to find it -- it is

25       Schedule P-7.

FLORIDA PUBLIC SERVICE COMMISSION

310

1                 And, yes, we did discuss this in deposition,

2       Column G.  There is a number there that is zero in the

3       current schedule.  I have a corrected number.  This was

4       an error in the schedule.  There is a total in Column

5       Hotel which does reflect this number being in the

6       column, so it does not change.

7                 Now, this change is essentially an omission,

8       but does not change any of the conclusions of the

9       schedule.  The number is later totalled in Hotel, so it

10       does not effect any requirements or recovery or any

11       changes in my testimony.  It's just a detail that we

12       identified during deposition.  There should be a number.

13       I have that number.  It is confidential, and we can make

14       it available to the parties afterwards.

15                 Additionally, in my direct testimonies of

16       March and April there are changes that have occurred

17       subsequent.  All answers at that time were accurate at

18       the time of those deposition -- of that testimony.  It's

19       specifically two places they have changed.  This has

20       been updated in my rebuttal and in deposition.  They

21       refer to, one, the end of my current outage, which at

22       different times, depending on when you asked me, based

23       on our schedule at the time, we had different estimates

24       of when the plant would return to service.  It currently

25       is expected to return to service in the fall of 2010.

FLORIDA PUBLIC SERVICE COMMISSION

311

1                 And that leads to a change in our refueling

2       outage 17, which will be fall of 2012 now.  And,

3       additionally, there were times where the license

4       amendment request was projected to be submitted, and

5       that has changed now.  We are working with the NRC to

6       develop the appropriate time to submit that license

7       amendment request.  And those dates I projected in

8       earlier testimony are no longer accurate.

9            Q.   With those changes, if I asked you the

10       questions today would you give the same answers?

11            A.   Yes, I would, with those changes.

12                 MR. WALLS:  We request that the prefiled

13       testimony be moved in evidence as if it was read in the

14       record today.

15                 CHAIRMAN ARGENZIANO:  So moved.

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

369

1       BY MR. WALLS:

2            Q.   Do you have a summary, Mr. Franke?

3            A.   Yes, I do.  There was one other change we made

4       in deposition, but it is worth mentioning here, as well.

5       I apologize.  In my March 1 testimony on Page 2, I

6       indicated on Line 16 that I had been promoted to my

7       current position two years ago.  And as Mr. Rehwinkel

8       pointed out, it was actually only one year ago.  So that

9       two on Line 16, Page 2, should be a one.  And I do have

10       a summary I prepared.

11            Q.   Will you provide the summary, please.

12            A.   My name is Jon Franke, the Vice President for

13       the Crystal River Nuclear Plant.  My March 1, 2010,

14       Direct Testimony explains the prudence of costs incurred

15       in 2009 for the Crystal River 3 extended power uprate

16       project.  My April 30th, 2010, direct testimony explains

17       the reasonableness of the company's actual and estimated

18       2010 costs and projected 2011 costs for the project.  I

19       also provide testimony regarding Progress Energy

20       Florida's project management, contracting, and oversight

21       controls for the uprate project in 2009, and explain why

22       they are reasonable and prudent.

23                 The Crystal River 3 uprate project divides up

24       the work necessary to generate an additional estimated

25       180 net megawatts of electricity of nuclear power in

FLORIDA PUBLIC SERVICE COMMISSION

370

1       three separate planned outages when the unit is already

2       off line in conjunction with refueling operations.  The

3       company successfully completed the first phase during

4       the 2007 refueling outage, and the second phrase of work

5       during the 2009 refueling outage.  That equipment

6       installed in 2009 will be tested upon return to service

7       of the plant following the current outage.

8                 Progress Energy Florida incurred reasonable

9       and prudent costs in 2009 to plan for and carry out the

10       second phase of project work.  Progress Energy Florida

11       also incurred costs in support of the third and final

12       phase of the project in 2009, and will continue to incur

13       costs for this work in 2010 and 2011.  This work is

14       scheduled for the next Crystal River 3 refueling outage

15       after the current extended outage ends.

16                 There are no increased costs in this

17       proceeding due to the extended outage of the unit at

18       this time.  The uprate project costs in 2010 and '11 are

19       necessary to complete the final phase of work and,

20       therefore, are reasonable.  I'm available to answer

21       questions related to my testimony.

22                 CHAIRMAN ARGENZIANO:  Thank you.

23                 MR. WALLS:  We tender Mr. Franke for cross.

24                 CHAIRMAN ARGENZIANO:  Mr. Rehwinkel.

25                 MR. REHWINKEL:  Thank you, Madam Chairman.

FLORIDA PUBLIC SERVICE COMMISSION

371

1                           CROSS EXAMINATION

2       BY MR. REHWINKEL:

3            Q.   Good afternoon, Mr. Franke.

4            A.   Good afternoon, Mr. Rehwinkel.

5            Q.   I'm going to ask you some questions directed

6       to your direct testimony.  Some of these questions may

7       delve into areas that morph into your rebuttal

8       testimony, and I'm indifferent as to whether you want to

9       answer them in this round or in rebuttal, but I would

10       prefer that as long as there is continuity of the

11       questioning that we can ask questions now, but I leave

12       that to you.

13            A.   And I will be receptive.  I have a copy of my

14       rebuttal, as well.  It is our intention for me to come

15       back later again for rebuttal testimony.

16            Q.   Okay.  I don't intend to refer to your

17       rebuttal, but if we get into a subject matter there,

18       we'll just see where it goes.  Thank you.

19            A.   Yes, sir.

20            Q.   Turning to your March 1, 2010, Direct

21       Testimony on Page 14.

22            A.   Yes.

23            Q.   You testify there that for 2009, the license

24       application capital expenditures were $20,016,839, is

25       that correct?

FLORIDA PUBLIC SERVICE COMMISSION

372

1            A.   That is correct.

2            Q.   And you also testify on Line 17 that your

3       project management capital expenditures were

4       $21,154,156, is that correct?

5            A.   That is correct.  And realize that those are

6       large general titles of scope of work.  So, for example,

7       the licensing application expenditures include other

8       engineering work which overlaps with that licensed

9       application.  They're broad categories.

10            Q.   Now, would you agree -- wouldn't you agree

11       that these two dollar amounts that we have addressed for

12       2009 are the most relevant to the issue of the LAR and

13       the engineering work related to the CR-3 uprate project?

14            A.   Yes, they speak to those two areas primarily.

15       Although, there is some power block engineering listed

16       on Page 15, Line 16, that relate to engineering work

17       associated with the power uprate, as well.

18            Q.   Okay.  Isn't it true that the CR-3 uprate was

19       a project that was initiated in late 2006 by the

20       company?

21            A.   Excuse me.  I'm sorry, I did not understand

22       your question.

23            Q.   Isn't it true that the CR-3 -- well, let's

24       step back.  The uprate that we are talking about is

25       planned for three phases, correct?

FLORIDA PUBLIC SERVICE COMMISSION

373

1            A.   Yes, sir.

2            Q.   The measurement uncertainty recapture, which

3       has already occurred and went into -- I guess, you had

4       power ascension for that project in early 2009?

5            A.   That is not correct.  The equipment was

6       installed in the fall of 2007.  The license amendment

7       was achieved after that outage, and we actually

8       increased the power, I believe it was late January or

9       early February of 2008.

10            Q.   I see.

11            A.   So we actually achieved the power in 2008.

12            Q.   I meant 2008.

13            A.   Yes, sir.

14            Q.   Okay.  And then Phase II was the balance of

15       plant phase that was originally intended to achieve --

16       was it 28 megawatts?

17            A.   The original scope -- and there's a little

18       misnomer.  The subsequent two outages included work

19       which would be characterized as balance of plant.  The

20       work in 2009 was exclusive to the balance of plant.

21       There is some balance of plant work in my next outage.

22       However, there were original designs early in the

23       project to achieve a four megawatt increase due to

24       thermal efficiencies associated with -- it's a technical

25       piece of equipment.  It's a moisture separator reheater,

FLORIDA PUBLIC SERVICE COMMISSION

374

1       drain reheaters.  That was installed in 2009.

2       Additionally, we were at -- much prior to our last

3       outage, we had planned to install low pressure turbines

4       which were projected to get about another 24 megawatts

5       of thermal efficiencies out of the steam plant.

6            Q.   Okay.  So, essentially, the intent was for

7       Phase I and Phase II to yield an additional 40 megawatts

8       with Phase III to yield 140 megawatts for a total of

9       180, is that correct?

10            A.   That was the original plan, yes, sir.

11            Q.   Okay.  And that entire plan was approved by

12       management in late 2006, is that correct?

13            A.   Yes, that sounds about right.  I don't

14       remember the exact date, but I'm confident it was 2006,

15       and I believe the need was approved around that same

16       time frame.

17            Q.   Okay.  Now, isn't it true that the original

18       budget for the entire plan was on a direct view basis

19       $427 million?

20            A.   Let me refer to --

21            Q.   Okay.

22            A.   The best place in the testimony to look at

23       that would probably be TOR-7.

24            Q.   Okay.

25            A.   Yes, I believe the -- hold on.  Yes, I believe

FLORIDA PUBLIC SERVICE COMMISSION

375

1       the correct number originally, once burdened, you know,

2       there was direct, and then there is direct plus overhead

3       costs, essentially, was 439.3.  That would be

4       apples-for-apples for comparison of the needs case.  I

5       believe the actual number in the needs case was

6       15 percent below that because of the burdens, as we have

7       explained in subsequent years of true-up was not

8       included in that original estimate.

9            Q.   Okay.  So looking at Schedule TOR-7.

10            A.   Yes, sir.

11            Q.   We see the $439.3 million number that you

12       referenced, and part of that, $102.4 million of that

13       says transmission facilities, is that correct?

14            A.   Yes, sir.  Absolutely; yes, sir.

15            Q.   Now, isn't it true that not long after that

16       $439 million number was developed and the project

17       authorized that you realized that you didn't need the

18       transmission facilities after all, correct?

19            A.   I would say that this project has had a

20       number, a large number of increases and decreases in

21       scope.  This particular schedule does detail the

22       transmission decreases that did occur.  There are also a

23       large number of, as we moved through a more clearer and

24       finalized understanding of what would be required, there

25       were additional components that were taken out of scope,

FLORIDA PUBLIC SERVICE COMMISSION

376

1       additional components that were added to scope, systems

2       added to scope that were not part of this original

3       feasibility.

4                 So, yes, it did include the transmission

5       costs.  It also included other components that are now

6       out of scope, and a large number of components and

7       system changes required once we worked through the

8       engineering that are not on this original estimate.

9            Q.   Okay.  But the direct answer to my question --

10       and you are a very responsive witness.  I know you

11       understand the yes or no, and then the explanation.

12            A.   Yes, sir.

13            Q.   Is that very soon after this estimate was

14       developed that you realized that you did not need the

15       transmission facilities, correct?

16            A.   That is correct.  One of the first changes in

17       the project was a better understanding of the

18       transmission needs, and these transmission changes were

19       not required.

20            Q.   Okay.  And isn't it also true that the

21       transmission system is -- I hope this word is

22       accurate -- agnostic to how the kilowatts are generated?

23            A.   No, I can't say that, unfortunately.  There is

24       a lot of special needs to the transmission system for a

25       nuclear plant, and I'll give you a couple of examples.

FLORIDA PUBLIC SERVICE COMMISSION

377

1       The safety features of Crystal River 3 requires a

2       certain voltage support and a certain ability to

3       withstand a trip of the unit so that it doesn't cause a

4       subsequent loss to the grid in the vicinity of the

5       nuclear plant.  So there are very specific needs from a

6       nuclear safety standpoint.

7                 Additionally, and it will become important in

8       this, it is important to this particular project, we

9       also have rules associated with the transmission's

10       ability to withstand the loss of the unit, so that the

11       loss of a single unit does not cascade to a larger loss

12       of other units and large sections of the grid.

13                 As we complete this uprate, I believe Crystal

14       River 3 will be the largest generator on the grid, and

15       that subsequently changes transmission need.  So, no,

16       there are very clear ties between transmission needs and

17       the nuclear plant in both directions.  The

18       transmission's ability to support the plant and the

19       transmission system's ability to withstand the loss of

20       the plant to the grid.

21            Q.   But there was nothing about the engineering of

22       the plant or the rescoping of the uprate project that

23       made the transmission needs go away, was there?

24            A.   It was a better understanding of those

25       interplays I just discussed.  Early on there was a

FLORIDA PUBLIC SERVICE COMMISSION

378

1       belief -- this is one of those conditions where when

2       you're studying the feasibility of a project this large,

3       you make assumptions based on a feasibility level of

4       understanding of the engineering work required to

5       complete the activity.

6                 In this case, the feasibility study pointed to

7       a weakness in the transmission system that would have to

8       be upgraded.  Once the need was approved and the budget

9       was approved to go forward with those engineering

10       studies -- obviously, you can't spend a lot of money

11       until the money is budgeted and approved.  We discovered

12       that there were ways to work around not having to expend

13       those resources, and we constantly do that.  We look for

14       ways to provide the needs of the uprate in conjunction

15       with the needs of the plant at a lower cost.  And in

16       this case we were able to find a way to install the

17       uprate without these transmission costs.  And we are

18       going to continue to do that.

19            Q.   Okay.  But I guess my question is isn't it

20       true that the way you engineered the uprate did not

21       affect the need for the transmission facilities, isn't

22       that correct?

23            A.   Well, I'm not sure how to draw the line,

24       Charles.  I mean, I guess, we clearly had to do

25       engineering analysis, sir, to understand relative to

FLORIDA PUBLIC SERVICE COMMISSION

379

1       this uprate what its impact on the transmission.  So in

2       some cases engineering work identifies a need to install

3       new equipment or change existing equipment.  In other

4       cases that engineering work provides the basis for not

5       doing those upgrades or those changes.

6                 In this case, that engineering work had a

7       conclusion that this work was not required.  So it was

8       part of the project, but it did not require significant

9       changes to the plant once that engineering work was

10       completed.

11            Q.   Let me ask it this way.  Maybe this will get

12       to the heart of the question that I have.  A significant

13       aspect of the engineering work that is related to this

14       uprate project is designed to allow you to increase the

15       thermal output of the reactor and the plant, correct?

16            A.   That is correct.  There is a portion that is

17       improving the efficiency of the existing reactor output.

18       In other words, get more electricity for the same

19       reactor power.  And then there is a second piece that is

20       an actual increase in the reactor power, and then you

21       have to install additional equipment or larger, more

22       higher capable equipment to be able to accommodate that

23       higher reactor power and turn that into electricity.

24            Q.   And you have to do all of that within the

25       rules and regulations that the NRC oversees and get

FLORIDA PUBLIC SERVICE COMMISSION

380

1       their approval, correct?

2            A.   For that second piece, yes.  The thermal

3       efficiencies typically can be -- they're still under the

4       NRC rules, but they do not require, and I think your

5       question is they do not require prior approval by the

6       NRC.  There are still rules that apply to the

7       installation of modifications, however, those rules

8       allow the installation without prior NRC approval.

9            Q.   Okay.  So the vast majority of the engineering

10       costs that have been incurred and you expect to incur in

11       this project will be related to the increase in the

12       thermal capabilities of the reactor as well as the

13       efficiencies of the plant based on those increased

14       thermal capabilities, correct?

15            A.   That's correct, those two pieces.

16            Q.   So those aspects of the engineering, the

17       increase in the thermal output of the reactor and the

18       increase in the efficiency of the plant based on that

19       increased thermal capability had no bearing on the need

20       for the transmission facilities, correct?

21            A.   That's not true.  The transmission needs are

22       reflective of how much output the plant achieves, so it

23       is independent of the reactor power.  So let me see if I

24       can explain this.  If you follow the original plan as

25       you stated earlier, the original plan was to increase

FLORIDA PUBLIC SERVICE COMMISSION

381

1       the reactor output about 40 megawatts prior to receiving

2       the change in our license which allows us to increase

3       the thermal output of the reactor.  So those 40 extra

4       megawatts electric would have to be reviewed against

5       those transmission needs, and the needs of the plant

6       with regard to the transmission system at the site.  So

7       even just those first 40 megawatts electrically are

8       important to the plant from a safety standpoint.  We

9       would have to perform engineering to verify that they

10       were okay for the plant to be able to generate.

11            Q.   Okay.  But you did not perform any material

12       engineering tasks related to increasing the thermal

13       efficient output of the plant or the efficiency of the

14       plant once you increased that thermal output that caused

15       the need for the transmission facilities to go away, did

16       you?

17            A.   We made no physical modification to the plant

18       which accommodated the relief from any need to perform

19       transmission work.  That was engineering analysis alone.

20       So, essentially, we sat down with pencils and

21       calculators, updated the electrical grid model that we

22       used, and we were able to find a way to not have to make

23       significant modifications to the transmission system.

24                 Those studies aren't cheap.  They take a

25       little bit of time and some money.  So we worked through

FLORIDA PUBLIC SERVICE COMMISSION

382

1       those and determined that it was not required.

2            Q.   Okay.  Now, on this same Schedule TOR-7, which

3       is Page 9 of 9 of Mr. Foster's TGF-6.

4            A.   Yes, sir.

5            Q.   In the middle of the page under initial

6       milestones there is an item that says point of

7       discharge, $49.5 million.  Do you see that?

8            A.   Yes, sir.

9            Q.   And that is a cooling tower project to allow

10       you to increase the thermal output of the plant and stay

11       within environmental regulations, is that correct?

12            A.   That's correct.  Various changes that we are

13       making in a minor way the thermal efficiencies, but in a

14       major way the increase in reactor power will drive more

15       heat into our circulating water system which heats up

16       our discharge canal.  And as such, we have to still

17       accommodate our environmental permit with the state

18       which limits the temperature on the outfall of the

19       plant, and this is a cooling tower to accommodate that.

20                 Currently we have cooling towers which cool

21       this discharge canal, and so this is a modification to

22       increase the capacity of that cooling capability on the

23       discharge canal to accommodate the higher level of heat

24       primarily for summer months.

25            Q.   Okay.  Now, have there been any changes in the

FLORIDA PUBLIC SERVICE COMMISSION

383

1       company's plans with respect to the need to install

2       point of discharge facilities?

3            A.   Right now it is in our plan and in our

4       schedule to install this design.  We have, over the last

5       year, and I think I talk about it in our testimony and

6       it is reflected in the schedules, we have deferred some

7       of the costs associated with that due to the extended

8       nature of the current outage.

9                 Since my current extended outage has carried

10       me through the summer of 2010, I will not expect to

11       achieve the higher power level until I return to service

12       in the fall of 2012.  That means that this cooling tower

13       need, once again it's for an environmental permit, would

14       not need to be in service and cooling the canal until,

15       you know, prior to the heat of the summer months in

16       2013.  So we have changed the schedule, but our current

17       plan is to still install this cooling tower.

18            Q.   Okay.  So you don't anticipate the need for

19       the cooling tower to go away, is that correct?

20            A.   As I explained with the transmission earlier,

21       we will continue to monitor for places where we could

22       decrease the costs of this project.  We are continuing

23       to monitor the environmental regulations that may impact

24       this, any changes to our position with regard to meeting

25       those, and if there is a way to reduce this scope we

FLORIDA PUBLIC SERVICE COMMISSION

384

1       can, but for right now our plan is to install these

2       cooling towers.

3            Q.   Okay.  When we discussed this issue in your

4       deposition, my impression was that the entire need for

5       the POD, or the point of discharge facilities might go

6       away.  Was that a mistaken impression on my part?

7            A.   No, just the complete answer is we are going

8       to continue to monitor the need for this part of the

9       project, and it may change.  But as of right now the

10       current decision is that this is part of the project and

11       will continue forward.

12            Q.   Okay.  So, now, if the costs related to the

13       POD facilities are deferred until 2013 --

14            A.   Yes, sir.

15            Q.   -- that would be outside of the currently

16       planned refueling outage, R-17, which you testified

17       would be the fall of 2012, correct?

18            A.   That's correct.

19            Q.   Would these costs still be submitted for

20       cost-recovery?

21            A.   If they are required to achieve the uprate,

22       yes, they would.

23            Q.   Okay.  Now, are any costs associated with

24       point of discharge in any estimate for the years 2010 or

25       2011?

FLORIDA PUBLIC SERVICE COMMISSION

385

1            A.   I believe they are included as we deferred

2       them.  The deferred costs are still in those 2010 and

3       '11 estimates, yes.

4            Q.   Okay.  By the way, when you mention the fall

5       of 2010 for returning to service for your unit --

6            A.   From the current outage, yes, sir.

7            Q.   Yes.  My thinking of fall is that it goes

8       through, I guess, the middle of December.  Winter starts

9       in the middle of December around --

10            A.   In Florida it's probably a little wider than

11       most states, but I think the most accurate description

12       is we expect to return in the fourth quarter of 2010.

13            Q.   Okay.  And when you say your LAR, did you say

14       that you thought you had filed that with the NRC in the

15       fall of this year, as well?

16            A.   Yes, and we talked about this in deposition.

17       I think the best answer is we are working through an

18       issue we discussed in deposition with the NRC.  They

19       continue to, you know, change their regulatory position

20       with regard to a number of items.  We monitor that very

21       closely as we always have.  The same testimony I

22       provided last year.  We are going to sit back, and we

23       want to submit the license application at the right

24       time.  There is no correct time.  In sitting back and

25       taking advantage of this delay in need for the license

FLORIDA PUBLIC SERVICE COMMISSION

386

1       application during this year, we have identified a new

2       element of the license application based on very recent

3       licensing action the NRC has taken, and we are currently

4       in the process of making a decision for how to change

5       our license application.  We have identified a need to

6       change it.

7                 And once we are through our project control

8       process where that change goes through management for

9       approval, and actually in conjunction with that, we will

10       continue to work with the NRC as to when the appropriate

11       time to submit that license extension is.  It could be

12       as early as this fall.  It might be as late as next

13       spring.

14                 I need to work through that process to

15       finalize when that date is.  It would be imprudent for

16       me right now to submit it under the current new

17       regulatory environment.  We are going to submit it at

18       the right time so that it will be accepted by the NRC.

19            Q.   Okay.  So today is the first time you have

20       testified that it could be sometime in 2011?

21            A.   That's correct.

22            Q.   Okay.  You're aware, I take it, that Florida

23       Power and Light recently withdrew, very recently

24       withdrew their license amendment request from the NRC?

25            A.   I'm aware of that; yes, sir.

FLORIDA PUBLIC SERVICE COMMISSION

387

1            Q.   Do you have any opinion about the impact of

2       that on this project?

3            A.   Actually, we have been monitoring the

4       St. Lucie application, as well as the other on-going

5       applications with the NRC, and we have applied the

6       lessons of those submittals to our application as we

7       have gone.  And my staff informs me that any lessons

8       learned have already been applied to the current status

9       of my license application that would be learned from the

10       St. Lucie application.

11            Q.   So it's your testimony today that you believe

12       the withdrawal by Florida Power and Light will have no

13       impact on the way you present your, or you prepare and

14       present your LAR to the NRC?

15            A.   I would say it already had some impact, but

16       that I don't foresee any future impacts due to the

17       St. Lucie withdrawal.  And we have looked at this.

18            Q.   Okay.  And since your deposition there is no

19       change in your assessment of the digital instrumentation

20       issue with respect to your license amendment

21       preparation?

22            A.   Yes.  I believe it's still the same status as

23       the deposition.  That was only a week and a half ago.

24            Q.   Yes.

25            A.   We are continuing to define the correct

FLORIDA PUBLIC SERVICE COMMISSION

388

1       solution.  We know there are solutions to dealing with

2       the digital modification and its acceptance in licensing

3       space, so now we are currently in the process of

4       choosing what that solution will be, making a

5       recommendation to management, developing any schedule

6       and cost impacts that might have on the total project.

7                 I am very confident that the potential changes

8       in both schedule and cost would still bound that this is

9       a feasible project.  It's just a matter of which

10       solution do we choose and how it affects cost and

11       schedule.

12            Q.   Have your staff prepared any estimates of what

13       cost might be for any engineering change that are

14       associated with this?

15            A.   I have seen no cost estimates yet.

16            Q.   Okay.  Do you have any rough idea of what they

17       might be?

18            A.   I know that I am confident -- the best answer

19       to that is I am confident that there is no way they can

20       get to the point where they would affect the feasibility

21       of this project based on how cost-effective this project

22       is to our customers in net present value.  It's

23       impossible for it to get that high to where it would

24       ever become a material question.

25            Q.   Okay.  You did not have a direct role in the

FLORIDA PUBLIC SERVICE COMMISSION

389

1       preparation or the decision-making in 2006 with respect

2       to this license amendment -- I mean, this EPU for CR-3,

3       did you?

4            A.   I would say no direct role.  I was the plant

5       manager at the time working with the team.  I was part

6       of the management team which was presented the project,

7       but at that time the project reported through a

8       different chain.

9            Q.   Okay.  So you didn't have any direct

10       decision-making role with respect to how to proceed with

11       this project, is that correct?

12            A.   No, sir, but I am here to represent the

13       company's decisions with regard to the project all the

14       way back to those dates.

15            Q.   Okay.  And it's true that the original plan

16       was to have the full 180 megawatts from the extended

17       power uprate implemented and power ascension by the end

18       of 2011, correct?

19            A.   Yes, sir.

20            Q.   Can you -- I'm asking it to you in an

21       open-ended way.  Can you state for the record, if it's

22       not confidential, what the current budget for the

23       overall project is?

24            A.   I don't think the overall number is

25       necessarily confidential.  And you have to be careful

FLORIDA PUBLIC SERVICE COMMISSION

390

1       because the schedules that we provide relate to NCRC

2       costs.  There are portions of this project which are

3       being covered under the environmental cost-recovery

4       clause, so sometimes we get wrapped around what that

5       total number is, but I believe the -- and as we

6       discussed earlier, it gets complicated when you talk

7       gross joint owner or independent joint owner, but the

8       total project, I believe, is 481.5 million.

9            Q.   Is that net of joint owners?

10            A.   That is net of joint owners, and it looks

11       like --

12            Q.   But it includes AFUDC, correct?

13            A.   Yes, I believe it does.  It's hard to get

14       that.

15            Q.   Okay.

16            A.   The financial view total net of joint owners

17       before AFUDC looks like it's 479.4.

18            Q.   Okay.  And isn't it true that the budget

19       for -- the approved cost estimate for the EPU project

20       increased $52.8 million in the third quarter of 2009?

21            A.   Yes.  We went through a budget process where

22       prior to this the costs had come down because of scope

23       changes like the transmission project, and then as we

24       were finalizing the engineering work required for the

25       next phases, we recognized additional work which would

FLORIDA PUBLIC SERVICE COMMISSION

391

1       be required to be performed, and that added costs back

2       into the project to the tune of 52.5 million.

3            Q.   Okay.  Now, the original -- if I look on Page

4       9 of 9 of this TOR-7, without transmission facilities, I

5       see $287.5 million, is that correct, in the initial

6       milestones column?

7            A.   Yes, that's correct.

8            Q.   Okay.  Now, if you ignore transmission

9       facilities, that number is directly comparable to the

10       $481 million number you just mentioned, isn't it?

11            A.   No.

12            Q.   Why not?

13            A.   Well, if you are going to take transmission

14       costs out, you have got to add up the other things that

15       we learned since the time the transmission was removed.

16       I mean, to pick a particular portion of the project and

17       cut it out and say, well, you know, I'm going to take

18       advantage of saying your costs should be reduced because

19       that one had to be done once you learned more is not an

20       apples-for-apples comparison if you are going to, you

21       know, blind your eyes to the case where that same

22       engineering work or other engineering work in support of

23       the project identified additional cost requirements of

24       the project.

25                 So, you know, if you want to choose a single

FLORIDA PUBLIC SERVICE COMMISSION

392

1       project that ended up with a cost decrease and not

2       reflected by that engineering work, I don't think it's a

3       fair comparison to then compare that number to other

4       engineering work which identified additional scope

5       requirements.

6            Q.   But in this TOR-7 schedule, it's true, is it

7       not, that below the line of total, there is a separate

8       and distinct line that says transmission facilities,

9       correct?

10            A.   It does.  And I could have rewritten this

11       TOR-7 to have sliced and diced this project into the 40

12       or 50 different subprojects required at the time, and

13       you would see a large number of projects that were on

14       one line and not on the other.  In some cases those line

15       items might be in the future number.  In other cases

16       they might be in that previous number.  So I guess what

17       I'm saying is to the detail that this schedule defines

18       what is in that, the number you referred to, which is

19       the 287.5, I believe you could -- you know, I could take

20       that 287.5 and add another four or five sublines to it,

21       and so it's just the matter of detail provided in the

22       schedule, Mr. Rehwinkel.

23            Q.   But you agree that the transmission costs, the

24       $102.4 million that are here were not part of the

25       integral engineering solutions related to the increase

FLORIDA PUBLIC SERVICE COMMISSION

393

1       of either thermal output of the reactor or electrical

2       efficiencies of the plant itself?

3            A.   I apologize, I must not have been clear when

4       you asked that question before, Mr. Rehwinkel.  No, it

5       was.  You can't increase the reactor power without

6       addressing the transmission needs.  So it was part of

7       the project to increase reactor power, absolutely

8       required scope to understand the transmission needs of

9       the higher power level of the plant.  And some money was

10       spent with regard to that.  It was only engineering

11       money; it was not physical changes.

12                 And just as we had to evaluate those

13       transmission needs, we had to evaluate the feed water

14       heater needs, for example.  A year ago we thought we had

15       to replace two feedwater heaters.  Now we believe we

16       have to replace four.  We thought that there was a need

17       to change our SERC water intake pumps.  We decided that

18       was not required.

19                 I have got a list of probably 20 or

20       30 decisions like that where scope was brought in or

21       taken out.  Our original scope, for example, was 287.5

22       million, and did not include a safety-related cross tie

23       in our low pressure injection system.  We now know that

24       is required, and the cost associated with that item, had

25       I broken it out before, is about $16.2 million

FLORIDA PUBLIC SERVICE COMMISSION

394

1       currently.  So there would have been no money for that

2       in the 287.5, but there would be in this current 360.1.

3            Q.   But you would agree, would you not, that there

4       were no R-16 or R-17 scope changes that even came close

5       to $102.4 million in any discrete engineering solution?

6            A.   No one solution, but you add up all those

7       changes, additions and minuses, yes, it didn't quite

8       come to the 102.4, because you'll notice that the 439.3

9       is still above the original number, apples-for-apples,

10       between the need and the current budget when you go

11       apples-for-apples is still -- what is that, not quite

12       $21 million below that original needs.

13                 So we have taken 102 out.  We have added a

14       number of projects.  The total numbers float around, but

15       when you get to the end of the day we are still in the

16       same ballpark, which is pretty good for a project this

17       size.

18            Q.   Isn't it true that within the company there is

19       an emphasis on meeting the budget that's established in

20       the IPP?

21            A.   You know, the purpose of the IPP is to create

22       a budget, and then changes as the project goes forward

23       are reviewed through our management chain and through

24       our project controls process so that those changes are

25       appropriate and adequately managed.  It is never the

FLORIDA PUBLIC SERVICE COMMISSION

395

1       expectation of a project manager on a project like this

2       to assume that a feasibility budget is what he should be

3       held accountable to four years later.

4                 It's difficult to hold any project manager

5       accountable or project that the scope is not finalized

6       on.  And at the point of a feasibility study you know

7       what you know.  Your intention is to spend the

8       appropriate amount of time to get a strong sense of what

9       the total cost will be.  You always know there will be

10       scope increases and decreases, and we hold them

11       accountable, and you should be happy I hold them

12       accountable to what the best lowest cost and successful

13       conclusion to meet the project goals.

14                 So in this case, if you look at TOR-7, if I

15       merely was holding accountable to that original budget,

16       he would have an extra $20-something million in his

17       pocket to spend, and we're going to be holding him

18       accountable to the 418.6.  If that scope changes, we

19       will hold him accountable based on what we think is the

20       prudent cost for that new scope.

21            Q.   And that would be true if the transmission

22       facility item of $102.4 million was truly a need for the

23       uprate project, correct?

24            A.   Yes.  But if I'm going to take the 102 away,

25       I've got to give him the money back for the other

FLORIDA PUBLIC SERVICE COMMISSION

396

1       increases in scope, just as I took money away for

2       decreases in scope.

3            Q.   The company has an internal audit function

4       called the audit services division, is that correct?

5            A.   Yes, sir.

6            Q.   ASD.  And ASD conducts periodic audits of

7       projects like the uprate project, correct?

8            A.   That's correct.

9            Q.   And one of the functions they look at is cost

10       management and adherence to the budget, correct?

11            A.   Yes.  I would not characterize it necessarily

12       as adherence to the budget.  I would call it adherence

13       to the project management guidelines.  Should they see

14       that a budget is being exceeded or running under budget,

15       they would refer back to our project controls procedures

16       and ensure that the adequate approvals for those budget

17       changes were occurring.  So I would say they are more

18       holding them accountable to the project controls

19       function than necessarily to budget numbers.

20            Q.   Okay.  And on Page 23 of your Direct

21       Testimony, if I could direct you to Line 16 on down, you

22       do cite for the Commission's consideration the prudence

23       of the costs that you are seeking the customers to pay

24       for that you have an internal audit program that

25       facilitates your management and oversight controls,

FLORIDA PUBLIC SERVICE COMMISSION

397

1       isn't that correct?

2            A.   Yes, sir.

3            Q.   And the costs of those projects are rolled up,

4       to some degree, in the costs that you seek recovery for

5       here, correct?

6            A.   I'm not sure -- I kind of lost your question

7       there.

8            Q.   I'll withdraw the question.

9                 But you do offer this function for the

10       Commission to support your cost-recovery here?

11            A.   Yes.  Part of our project controls function is

12       inclusion of our audit program as part of the oversight

13       of the project, yes, sir.

14                 MR. REHWINKEL:  Madam Chairman, at this time I

15       would like to offer an exhibit for cross-examination

16       purposes.  And if you will give me one second.

17                 CHAIRMAN ARGENZIANO:  Sure.

18                 MR. REHWINKEL:  Madam Chairman, this is a

19       document with a short title that says CR-3 EPU LAR

20       Events Outline.

21                 CHAIRMAN ARGENZIANO:  Very short.  Can we

22       shorten it?  And you need a number on this exhibit.

23       Were we at 193?

24                 MR. REHWINKEL:  193.

25                 CHAIRMAN ARGENZIANO:  193.  Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

398

1                 (Exhibit 193 marked for identification.)

2                 CHAIRMAN ARGENZIANO:  And, again, this is

3       confidential where highlighted.

4                 MR. REHWINKEL:  Yes.  This is a document that

5       the company has taken the effort to highlight, and I

6       think the only confidential information is shown on

7       Pages 2, 3, and 4.  Actually, 2, 3, 4, and --

8                 CHAIRMAN ARGENZIANO:  Uh-huh.  That's all I

9       have.

10                 MR. REHWINKEL:  Yeah.  It says confidential at

11       the top of Page 5, but there is no highlightings there.

12       So you will see dollar amounts, only dollar amounts and

13       one percentage amount that are confidential.

14                 CHAIRMAN ARGENZIANO:  Okay.

15       BY MR. REHWINKEL:

16            Q.   Mr. Franke, are you familiar with this

17       document?

18            A.   No, I'm not, but I'm trying to get familiar as

19       I sit here.

20            Q.   Okay.

21            A.   I'm familiar with most of the items listed in

22       it.

23            Q.   Okay.  Well, this is a document, as you can

24       see from the bottom -- you recognize this numbering

25       10PMA-DR4 CR-3.  This is Data Request Number 4 related

FLORIDA PUBLIC SERVICE COMMISSION

399

1       to CR-3 that was submitted in this docket by the staff

2       auditors.  Do you see that?

3            A.   (Indicating affirmatively.)

4            Q.   I'm looking at the numbering at the bottom.

5            A.   Yes.

6            Q.   Okay.  All right.  Now, there is -- it says,

7       G-I-N-N-A, that is Ginna, right?

8            A.   That's correct.  That's a correct

9       pronunciation.

10            Q.   Okay.  Ginna is a reactor, a plant that you

11       modeled your initial LAR development efforts after at

12       the suggestion of the NRC, correct?

13            A.   That is correct.

14            Q.   Okay.  And this shows that the Ginna LAR was

15       approved in July of 2006, correct?

16            A.   Yes, that is correct.

17            Q.   And shortly thereafter, Progress -- it says

18       Progress Energy CEO in December 11, 2006, authorized the

19       CR-3 EPU project, is that correct?

20            A.   That's correct.

21            Q.   Was that Mr. Lyash in late 2006?

22            A.   No, that was not.  I believe actually this

23       would have -- I'm not sure exactly when our CEOs

24       changed.  It was probably -- it was either Bill Johnson

25       or his predecessor.

FLORIDA PUBLIC SERVICE COMMISSION

400

1            Q.   Okay.

2            A.   This is Progress Energy CEO, not Progress

3       Energy Florida.

4            Q.   Oh, I'm sorry.  This is not -- okay.

5            A.   Well, I believe Mr. Lyash's name was on that

6       form, as well.

7            Q.   Okay.  Now, Ginna, what type of reactor was at

8       Ginna?

9            A.   Ginna is a Westinghouse, an early Westinghouse

10       design reactor.

11            Q.   Okay.  It's not the same kind as Crystal

12       River?

13            A.   No.  It's a pressurized water reactor.  We got

14       into this last year.  There is no such thing as an exact

15       replica reactor to CR-3 or any reactor in the United

16       States.  Ginna is a pressurized water reactor, so -- in

17       general, there are two types of light water reactors in

18       the United States, pressurized water reactors and

19       boiling water reactors.  Ginna was one of the early

20       pressurized water reactors to seek an extended power

21       uprate.

22            Q.   Okay.  Now, at the time you conceived the EPU

23       project, your anticipated filing of the LAR with the NRC

24       would have been in June of 2009, correct?

25            A.   I can't remember if it was June or August, but

FLORIDA PUBLIC SERVICE COMMISSION

401

1       in the summer of 2009.

2            Q.   Okay.  And at some point after that, you

3       changed that date to September of 2009, correct?

4            A.   Yes.

5            Q.   Okay.  And then after September of 2009, the

6       LAR submittal date became February of 2010, correct?

7            A.   Yes.  The date of the LAR continued to move as

8       we monitored the success and failure of other licensees

9       with regard to our submittals and looked for feedback

10       from the NRC on those license submittals so that we

11       could incorporate the latest lessons.

12                 Remembering that there is not a specific date

13       that you want to submit the LAR.  Early is not good.

14       You want to submit your license application at the point

15       where, one, you would, in a best case, receive approval

16       prior to the equipment being installed that you could

17       take advantage of it; and, two, late enough so that you

18       can incorporate the most amount of lessons learned so

19       that the application has the best chance of being

20       received and accepted for review by the NRC.

21            Q.   Well, what you don't want to do is to spend

22       all the money to engineer the solution to operate the

23       plant and then not be able to send power because you

24       don't have a LAR, correct?

25            A.   Well, it's impossible to do what you just

FLORIDA PUBLIC SERVICE COMMISSION

402

1       described.  The premise of what you just said is

2       impossible.  You have to expend a tremendous amount of

3       engineering, the vast majority of the engineering to

4       support the LAR application.  If you look carefully at

5       those units which have had their license amendment

6       applications rejected for review, including the peer

7       utilities, the reason was that there was insufficient

8       engineering review performed prior to that submittal.

9                 So, you can't have both.  You have got to do

10       the engineering to submit the LAR, and the LAR can't

11       exist without the engineering.  So in a perfect world I

12       wouldn't have to spend any money.  I could just submit

13       the LAR and they would approve it.  But you have got to

14       spend the money to get the LAR.

15            Q.   I think -- I didn't mean to ask the question

16       that you answered, I apologize.  My question was you

17       would not, as far as the timing of your LAR --

18            A.   Yes, sir.

19            Q.   I mean your -- or your license amendment,

20       actually, is what you are looking for.  The LAR is the

21       request, and the amendment is what you get from the NRC

22       if you are successful, correct?

23            A.   Yes.  The LAR is -- the long word for LAR is

24       license amendment request.  So this is an amendment to

25       your license from the NRC.  It's like a driver's

FLORIDA PUBLIC SERVICE COMMISSION

403

1       license.  It's a little more exhaustive to pass the

2       test, but it is a license to operate the reactor.  This

3       is an amendment to that license.

4            Q.   Okay.  So what I meant was you wouldn't want

5       to spend all the money to engineer the solutions to make

6       your plant capable of increasing thermal and electrical

7       output, but not have the license amendment in hand so

8       you could ascend the power to where you wanted it,

9       correct?

10            A.   The nature of your question -- you are asking

11       an impossible wish.  You know, it's like telling me I

12       would like to eat my steak and not pay for it.  Okay.  I

13       can't get my license without spending that money to do

14       that engineering work.  What you are asking me is

15       wouldn't it be nice if you didn't have to do the

16       engineering work to get your license.  But the answer --

17       the only fair answer is I can't get my license without

18       doing that engineering work, so I have to pay for it.

19            Q.   Okay.  My question is you would want to have

20       an amendment in hand at the time you've completed all

21       the engineering and your last outage so that you can get

22       the additional megawatts out of the plant, right?

23            A.   Well, maybe I'm -- we are getting crossed in

24       words.  The objective would be when you -- when you are

25       ready to increase power, you would like to increase

FLORIDA PUBLIC SERVICE COMMISSION

404

1       power as early as you can.  Now, there are two trails

2       you would have to walk down to get to that increase in

3       power on an uprate like we are talking about here.  One

4       trail is a licensing trail, which says I've got to walk

5       through the engineering work and the licensing work to

6       submit the license application from the NRC, work

7       through their review process and get approval of the

8       LAR.

9                 The other trail you have to walk is all the

10       modifications and installation activities so that the

11       plant, once that license application is received, is

12       capable of generating that electrical power.  Many

13       plants have gotten to the end point of both of those

14       walking paths at different times.  I know of examples

15       where plants have installed the equipment and not yet

16       received the LAR, and then they got the LAR and they

17       increased power subsequent to the receipt of the

18       paperwork, but that engineering and that installation of

19       equipment had already occurred.  That happened to me at

20       Brunswick when I was at the Brunswick Nuclear Plant.

21       It's happened at a number of other utilities.  Or you

22       receive the license application prior to that last

23       outage which installs those last components, maybe a

24       month ahead of time, maybe six months ahead of time.

25       But in any case you have got to walk both of those

FLORIDA PUBLIC SERVICE COMMISSION

405

1       paths, both requirements have to be met to achieve the

2       power increase.

3            Q.   I noticed that you pulled out a copy of the

4       CR-3 IPP to look at a budget number earlier?

5            A.   Yes, I did.

6            Q.   And you would agree with me that in each of

7       the last three IPPs you have a chart that has milestones

8       on it, correct?

9            A.   Yes.

10            Q.   And every single one of those milestones shows

11       the company receiving the license amendment prior to the

12       completion of all the uprate work, correct?

13            A.   That is correct.

14            Q.   And that's what you want to happen; that's the

15       most efficient way to do it, correct?

16            A.   It's really not a matter of efficiency.  Okay.

17       Let me make sure I'm clear here.  You don't want to

18       delay the power increase.  So our position all along has

19       been conduct the modifications, because most of the cost

20       of the modification work is required to submit the

21       license application anyway, and it provides a higher

22       level of assurance that the license application will be

23       received.  Continue with your licensing activities, so

24       at the end you've completed both.

25                 Now, the timing is driven in two ways, I would

FLORIDA PUBLIC SERVICE COMMISSION

406

1       say.  Primarily, it's driven by refueling outages, when

2       your outages will be.  So, for example, we knew that it

3       would take two outages to install all the equipment

4       associated with Phases II and III of the uprate.  You

5       would like to complete at the end of that second outage

6       the actual power increase to the new power level, so it

7       would be nice to have that license application ahead of

8       time.

9                 However, there's a whole second set of

10       standards that have to be achieved on that licensing

11       side.  And the timing of approval of that licensing

12       depends on everything from ongoing regulatory

13       environment, how much information you know when with

14       regard to the engineering and design work associated

15       with those modifications.  So it's really both timelines

16       you have to look at.  You would like to be able to do it

17       as soon as possible for both cases.

18            Q.   Okay.  And originally when you conceived this

19       plan in December of 2006, the target date for receiving

20       your license amendment would have been June, correct --

21       for submitting, it would have been June 2009, correct?

22            A.   Yes, sir.

23            Q.   And your expectation would have been 12 to 14

24       months for the NRC to act on your amendment request?

25            A.   Yes.  The Commission is unofficially committed

FLORIDA PUBLIC SERVICE COMMISSION

407

1       to a 12-month review, and they can take traditionally

2       about two months for a good application to review it for

3       acceptance review.  That can be extended to four in

4       cases where the license application has a lot of

5       questions, so you are talking about 14 months, in

6       general, from sending it to the NRC.  For a good

7       application, they should be able to accept it within two

8       months.  If they've accepted it within two months, their

9       general rule is that they will have it approved in a

10       year.

11            Q.   Okay.  And that would have put you in --

12       sometime in late 2010, is that correct?

13            A.   That's correct.

14            Q.   And that was the plan?

15            A.   That was the original schedule.

16            Q.   Okay.  Now, the scenario is that due to a

17       certain set of circumstances, some of which are outlined

18       in this document that we are discussing, you could

19       possibly submit your LAR as late as the spring of 2011,

20       correct?

21            A.   That's correct.

22            Q.   And perform your remaining work in Phase III,

23       including what was left from Phase II, in the fall of

24       2012?

25            A.   That's correct.

FLORIDA PUBLIC SERVICE COMMISSION

408

1            Q.   And you could conceivably be without a license

2       amendment at the time that work was complete for Phase

3       III, correct?

4            A.   Well, I want to be totally transparent with

5       regard to this issue.  Okay.  It is a little more

6       complicated than you've described.

7                 If I submit it in the spring of 2011, I would

8       expect that license prior to the start of my 2012

9       outage.  Fourteen months from the spring of 2011 is the

10       summer of 2012.  So it still would be prior to that 2012

11       outage.

12                 Now, in complete transparency, this digital

13       modification piece has changed the game somewhat.  The

14       NRC, as reflected in a license that was approved earlier

15       this year, has taken a position with regard to Interim

16       Staff Guidance 6, which is guidance documents on how to

17       review and approve digital instruments.  Okay.  This

18       interim staff guidance has an allowance for review for

19       digital equipment of any nature in an NRC application to

20       take not 12 months, but longer than that.  So in this

21       case we are kind of in a new box.  And even with regard

22       to Interim Staff Guidance 6, we'll be applying for a

23       license under a program the NRC has called a topical.

24                 In this case there is a topical report on the

25       equipment we may choose.  We have not finalized that

FLORIDA PUBLIC SERVICE COMMISSION

409

1       decision.  So we have got to work through what that

2       actual schedule with the NRC may be.  This is a little

3       new ground for the NRC.  They have got the guidance out

4       there.  They have applied it to one licensee.  There is

5       another licensee that they are in the works with right

6       now, but each of these cases will be special.

7                 I think looking at the specifics of our

8       application and the needs of the digital licensing, I

9       think we probably have the simplest application and the

10       least complex due to what we are trying to license and

11       how it applies to the plant.  I would rather not go into

12       a lot of detail there, but I do believe ours is one of

13       the least complex ones they will have to review.  But an

14       actual schedule is going to have to be something we work

15       through with the NRC and understand what that schedule

16       is.

17            Q.   Okay.  Thank you.  We have already -- I think

18       you've already indicated that the license amendment

19       related to the measurement uncertainty recapture was not

20       received prior to your ability to ascend power, is that

21       correct?

22            A.   Prior to the physical plant being modified to

23       accommodate the change, yes.  We had completed the

24       physical plant modifications, and I believe it was a

25       couple of weeks later we received the license

FLORIDA PUBLIC SERVICE COMMISSION

410

1       application, the license amendment itself.

2            Q.   Isn't it true that at the time -- that in

3       December of 2006, that the Progress Energy CEO formally

4       authorized this CR-3 EPU, that the company knew that

5       this would be the first extended power uprate for

6       Progress Energy Florida?

7            A.   There is only one nuclear plant in Progress

8       Energy Florida.  This is the first extended power uprate

9       for Progress Energy Florida, certainly not the first for

10       Progress Energy, Incorporated.

11            Q.   Okay.  And isn't it also true that at that

12       time, in December of 2006, that you knew that your only

13       possible contractor for this job, AREVA, had never done

14       an extended power uprate for this type of reactor?

15            A.   Yes.  To be specific, AREVA owns the

16       proprietary knowledge required for submittal of a power

17       uprate to the NRC for a large portion of the extended

18       power uprate work.  And so, yes, this was the first time

19       AREVA had preformed an uprate on their B&W units.

20            Q.   Okay.  And management was aware of that?

21            A.   Yes, sir.

22            Q.   Okay.  And at that time, December of 2006, you

23       were also aware that this would be the largest extended

24       power uprate at a B&W reactor, a Babcock and Wilcox

25       reactor, correct?

FLORIDA PUBLIC SERVICE COMMISSION

411

1            A.   We were aware of that, yes.  It takes us about

2       7 percent above the largest output for a similarly

3       designed plant.

4            Q.   You were also aware that this would be the

5       largest percentage uprate of any pressurized water

6       reactor, correct?

7            A.   I can't say I was aware of that.  I don't know

8       that that's true.

9            Q.   Was management aware that this would be the

10       first Babcock and Wilcox reactor taken above

11       3,000 megawatts?

12            A.   That sounds right.  Davis Bessey is a very

13       similar plant to us.  They operate about 7 percent

14       below, and were originally licensed at that level, I

15       believe, about 7 percent below where we are shooting for

16       with this license application.  I don't have their

17       thermal megawatt number memorized.

18            Q.   The NRC made note of that after your April

19       2008 meeting, correct?

20            A.   I'll have to take your word for it.

21            Q.   Okay.

22                 CHAIRMAN ARGENZIANO:  Mr. Rehwinkel, I hate to

23       do this, but I have a request for just a short break.

24                 MR. REHWINKEL:  Sure.

25                 CHAIRMAN ARGENZIANO:  Is that okay?  We will

FLORIDA PUBLIC SERVICE COMMISSION

412

1       take a five-minute.

2                 (Recess.)

3                 CHAIRMAN ARGENZIANO:  Okay.  Mr. Rehwinkel.

4                 MR. REHWINKEL:  Thank you, Madam Chairman.

5       BY MR. REHWINKEL:

6            Q.   Mr. Franke, I would like to take a quick run

7       through this document, which is 193, Exhibit 193.  Do

8       you still have that in front of you?

9            A.   The 193?

10            Q.   Yes.

11            A.   I know you were working on that with

12       Mr. Foster.

13            Q.   I'm sorry.  This is the LAR Events Outline,

14       the one that we are --

15            A.   Okay.  The same one that we were looking at

16       before?

17            Q.   Yes.

18            A.   Yes, sir.

19            Q.   And mindful when we get to the Pages 2 through

20       5 that there is confidential information highlighted.

21            A.   Yes.

22            Q.   This document shows a projection, in the May

23       2009 item, a projection of a spend for EPU project

24       costs, is that correct, related to LAR activities?

25            A.   Yes, it does.

FLORIDA PUBLIC SERVICE COMMISSION

413

1            Q.   Okay.  And on the next item down there, June

2       29, 2009, you reference a Point Beach LAR submittal and

3       some relation to an FPL supplement.  Do you see that?

4            A.   What was the date?

5            Q.   I'm sorry.  It's just below that of June --

6       I'm still on Page 2, June 29, 2009?

7            A.   Yes, I do understand that.

8            Q.   Okay.  Now, the FPL supplement, is this an

9       issue that was related to FPL's withdrawal of their LAR?

10            A.   Recognize that this -- this is talking about

11       Point Beach.

12            Q.   Yes.

13            A.   I believe the withdrawal you were referring to

14       earlier was St. Lucie.

15            Q.   Okay.  There was just a reference to FPL in

16       this paragraph here, and I didn't know if there was --

17       if Point Beach was referencing a supplement that FPL

18       filed?  If you don't know, it's fine, I don't --

19            A.   I'm not certain.  I believe Point Beach is an

20       FPL plant, also.  It's just not under the purview of

21       this Commission.

22            Q.   Okay.

23            A.   And as such, this is referring to Point

24       Beach's FPL application.

25            Q.   Okay.  Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

414

1            A.   There are similarities between this and St.

2       Lucie.

3            Q.   Okay.  On the next page, on Page 3, there is a

4       reference to the EPU project management team, and that

5       is Crystal River EPU project management team, correct?

6            A.   Yes, sir.

7            Q.   It says, "Assembled an expert panel to review

8       the current status of the LAR presentation activities,

9       and to provide feedback to EPU management on the

10       increasing industry standards associated with the NRC

11       licensing activities."  Is that correct?

12            A.   Yes, sir.  The timeline with regard to that,

13       that's when the team assembled.  The plan to do that

14       expert panel was well ahead of that date.

15            Q.   Okay.  Is there a document that you have been

16       able to identify or locate that demonstrates that this

17       expert panel was something that was always planned?

18            A.   I haven't looked, to be honest.  We can go

19       look for that if you'd like.  I do know that we had

20       discussions about the need for an expert panel and the

21       need to self-assess and review our application.

22       Remember, this expert panel was an internal assessment

23       planned by Progress Energy because of a lot of the

24       issues you described earlier concerning the fact that

25       this was the first AREVA extended power uprate, and one

FLORIDA PUBLIC SERVICE COMMISSION

415

1       of the early PWR extended power uprates, and that it

2       was -- this is not a simple license application you're

3       doing.  So for anything this large, you are going to

4       want to set up a self-assessment program that makes sure

5       that you take advantage of company internal resources

6       and industry experts.  That's just the way we do

7       business.

8            Q.   Well, if your expert panel was something that

9       was long planned --

10            A.   Yes, sir.

11            Q.   -- why would you long plan for them to provide

12       feedback on increasing industry standards associated

13       with NRC licensing activities?  You wouldn't have known

14       that when you planned it, would you?

15            A.   That's not the sole purpose of that expert

16       panel.  I mean, they certainly were given the task in

17       July to make sure that our license application in light

18       of what our own licensing team was beginning to see was

19       taking advantage of those earlier applications of the

20       other utilities.  So that particular scope I don't think

21       was identified months ahead of time.  But, you know,

22       this is the way we do business.  We are constantly

23       looking for ways to improve, where we can improve our

24       performance, and a function of that is to step back and

25       say, okay, when are you doing something special, new;

FLORIDA PUBLIC SERVICE COMMISSION

416

1       incorporate into that plan the need to self-assess and

2       bring to bear experts that you have and maybe in the

3       industry to make sure you are doing it in the best

4       manner possible.  That is what our expert panel was.

5                 It was designed to be as we were receiving the

6       inputs from AREVA and our own staff, to go back and sit

7       down.  This is a case where you are taking inputs from a

8       large number of people, and you want a core team of

9       experts to sit down and go through it and provide

10       feedback as to how you're doing.  That is just the way

11       we do business.  This self-assessment kind of program is

12       something that is engrained in everything we do.

13            Q.   Well, isn't it true that you had already in

14       your timelines for the EPU project already had planned a

15       site review that was different from the expert panel

16       review?

17            A.   Absolutely.  And the reason for that is the

18       licensed application itself is not from AREVA.  It is

19       from Progress Energy.  We are the ones who acting as

20       Florida Power Corp under the license own the license to

21       operate Crystal River 3.  As such, any work performed by

22       AREVA would have to be reviewed by my own staff prior to

23       my signature for submittal to the NRC.  So that's part

24       of the engineering process.  What I'm talking about with

25       regard to the expert panel is part of our assessment

FLORIDA PUBLIC SERVICE COMMISSION

417

1       process, our oversight of that engineering process.

2            Q.   Isn't it true that the document that the

3       expert panel produced in a management debrief dated

4       July 14, 2009, did not mention AREVA's work product

5       relative to increasing industry standards associated

6       with NRC licensing activities?

7            A.   I would have to refer to that.  I was present

8       at that debrief.  I don't remember what was mentioned in

9       every slide.  I know it is part of the docket.  It has

10       been added as part of this docket.

11            Q.   Okay.  But isn't it true that an internal

12       review was conducted as a result of the results of the

13       expert panel presentation?

14            A.   Let me talk through this event.  We had an

15       expert panel review.  Its design was to go into the

16       license application and review it for its acceptance to

17       NRC standards.  I would have expected, and we did ask

18       for that team to look at does this license application

19       meet the standards for acceptance by the NRC, and are we

20       on track for submitting a high quality license amendment

21       request.  That expert panel found some real problems,

22       real issues with this license application that needed

23       resolution.

24                 Fundamentally what it found was that we had

25       not been putting enough company resources and enough

FLORIDA PUBLIC SERVICE COMMISSION

418

1       outside resources on the project to ensure success.  We

2       hadn't been spending enough money on it.  And, quite

3       frankly, we should have been ahead of some of these

4       issues and identified them a little built earlier.  And

5       that is what that expert panel review concluded.

6                 As such, we followed our corrective action

7       program, which is when we find a problem, we generate a

8       nuclear condition report.  And then that requires an

9       investigation to determine what lessons to learn from

10       that expert panel review.

11                 So first we identified some real issues.  That

12       is what that self-assessment program is designed to do,

13       issues that we should have been able to prevent.  We

14       went into our corrective action program to understand

15       and learn every lesson we could from that so that going

16       forward we could correct the mistakes and get the

17       license application in the right format prior to

18       submittal.

19                 MR. REHWINKEL:  Thank you.

20                 Madam Chairman, I'd like to offer an exhibit

21       for cross-examination purposes, and it's the June 17,

22       2008, CR-3 EPU Management Presentation.  I believe I

23       need a number for that.

24                 CHAIRMAN ARGENZIANO:  194.

25                 (Exhibit 194 marked for identification.)

FLORIDA PUBLIC SERVICE COMMISSION

419

1                 MR. REHWINKEL:  This document does contain

2       confidential information.

3                 CHAIRMAN ARGENZIANO:  Thank you.

4       BY MR. REHWINKEL:

5            Q.   Mr. Franke, while it is being passed out, are

6       you familiar with this document?

7            A.   I looked at it last night, but prior to that I

8       had not seen it.

9            Q.   Okay.  Well, I hope I can ask you questions

10       about it that you will be able to answer.

11                 This document would -- it looks like it is a

12       presentation to Progress Energy management related to

13       the EPU project made by Danny Roderick (phonetic).

14            A.   Yes.  The management review meeting program at

15       this point in time would have been a presentation by

16       Danny Roderick's organization to his boss.  It is

17       possible that my boss at the time, Dale Young, who was

18       the Vice President at the time may have been present,

19       and usually other senior managers from the nuclear group

20       would have been present for this review.

21            Q.   Okay.  On Page 34.

22            A.   Yes, sir.

23            Q.   This document shows the budget for the project

24       in 2008, is that correct, at $461 million?

25            A.   I'm looking at Page 34, and I don't see that.

FLORIDA PUBLIC SERVICE COMMISSION

420

1       IPP update March 2008, yes, 461 million.  I'm not sure

2       what EAC means.

3            Q.   Okay.  And it shows initial authorization

4       November, 2006, 493 million up at the top of that page.

5       Do you see that?

6            A.   Yes, sir.

7            Q.   Okay.  So in 2008, 461 million would have been

8       kind of the controlling budget amount for this project,

9       right?

10            A.   Yes.  The only thing that's not detailed

11       here -- I think what this shows is the trend, you know.

12       I think I mentioned earlier that the costs were

13       decreased at first from the original authorizations

14       where the need was based at a higher number and then

15       came down initially, and then as we learned more we

16       added money back in.  That is what this is showing.

17                 What I would be careful in characterizing

18       these numbers is there's a lot of factors here.  First

19       of all, this point of discharge mitigation that is

20       listed on the slide is that portion of the total budget

21       which is not covered by the nuclear cost-recovery.  So

22       these numbers don't necessarily reflect directly to this

23       hearing, because there's a good portion -- in fact, I

24       believe two-thirds of that particular modification is

25       recovered under a different clause.  It is recovered

FLORIDA PUBLIC SERVICE COMMISSION

421

1       under the environmental clause.

2                 And what I don't know is are these numbers

3       inclusive or exclusive of joint-owner costs and whether

4       or not they are -- well, financial view means it's

5       burdened, so it is not direct costs.  So I know that at

6       least the number in 2006 is burdened, and I don't know

7       how AFUDC is treated in these numbers.  So, you know, I

8       can say that this is showing a trend.  I can't say that

9       461 relates to any specific number in this hearing.

10            Q.   Okay.  But you would agree, would you not, and

11       your testimony to the Commission would be such that you

12       don't manage a project with any greater or less scrutiny

13       or oversight based on which clause or which

14       cost-recovery mechanism you bring to the Commission for

15       approval with, do you?

16            A.   No.  You were just asking me about the number,

17       and I'm trying to make sure that I carefully quantify

18       what that number means to me.

19            Q.   Okay.  On Page 36 of this presentation, this

20       is at the time would have been the planned schedule for

21       this project, correct, or a graphic representation of

22       that schedule?

23            A.   It's a Level I schedule, which means that it

24       is a very high level overview.

25            Q.   Okay.  But midway down the page there is -- on

FLORIDA PUBLIC SERVICE COMMISSION

422

1       the left-hand side it says, EPU R-17, correct?

2            A.   Yes, sir.

3            Q.   And that is the third phase of the EPU,

4       correct?

5            A.   Yes, although there are -- I'm just trying to

6       make sure.  It is the third, the third phase -- R-17 was

7       the third outage of the implementation and the third

8       phase.

9            Q.   At this time?

10            A.   Yes.

11            Q.   Okay.  And there is a line here that's -- I

12       apologize, it's kind of difficult to read, but the line

13       that's right under EPU R-17 says engineering review of

14       NSS.  That's the nuclear safety --

15            A.   Nuclear steam supply system.  It's the reactor

16       side of the plant.

17            Q.   Okay.  Chapter 14, Analysis and LAR

18       Preparation.  Do you see that?

19            A.   Yes.

20            Q.   Now, I have a better copy of this, but it

21       looks -- but I represent to you that the break in the

22       line says site review of LAR and submit to NRC.  And it

23       shows a beginning point of March 31, 2009, and an ending

24       point of June 30th, 2009.  Will you accept that?

25            A.   Yes, I can.

FLORIDA PUBLIC SERVICE COMMISSION

423

1            Q.   Okay.  And the site review that's referenced

2       here is an engineering review by Progress personnel,

3       isn't that correct?

4            A.   Primarily.  It would also include other

5       personnel that are affected, but principally an

6       engineering review.  There would be other groups that

7       did reviews.

8            Q.   Okay.  But this does not reference or refer to

9       an expert panel, does it?

10            A.   This is a Level I schedule.  It's not going to

11       have that detail in it.

12            Q.   Okay.  And in the next page, 37, there are

13       some confidential numbers on this page.

14            A.   I just might note, just to that point, this

15       project has probably had easily a dozen different

16       assessments performed by outside experts, inside

17       experts, audit services, including the audit service

18       department issue you mentioned earlier.  None of those

19       are on this schedule.  You wouldn't have those kind of

20       assessments on the schedule.

21            Q.   Okay.  Well, on that point, this schedule

22       does -- it contemplates a three-month review of the

23       draft that you would receive from AREVA, and then

24       submittal to the NRC, correct?

25            A.   Yes, it did.

FLORIDA PUBLIC SERVICE COMMISSION

424

1            Q.   I mean, there is no contemplation here that

2       there would be any kind of extended review of AREVA's

3       work product, right, beyond the three-month review

4       internally?

5            A.   Yes.  This schedule shows a three-month

6       review.  Recognize it was written before we had the

7       lessons learned of Point Beach and the other submittals

8       that were on-going with the NRC.

9            Q.   Okay.  And I could ask you to do this and look

10       at each page of this document, but there was no

11       presentation to management here that references the

12       expert panel, is there?

13            A.   There is no -- I can go through it.  Give me

14       just a few seconds.

15                 A couple of things I note when reviewing this.

16       First of all, yes, on Page 48 it talks about extensively

17       using industry experience.  That may have referred to

18       the use of outside industry experts with regard to their

19       view of the LAR.  Additionally, if you look at Page 68

20       under EPU concerns, it talks about EC quality

21       improvement actions and oversight of nonstationed

22       personnel strategy and implementation.  It is possible

23       when those bullets were discussed, they discussed

24       oversight plans for AREVA work which may or may not have

25       included the expert panel.  That's two points.

FLORIDA PUBLIC SERVICE COMMISSION

425

1                 And the third point is I'm very aware at this

2       point of the project that the oversight and assessment

3       activities for the extended power uprate, which this was

4       a much -- this presentation was not just for the LAR; it

5       was for the entire project, that in the plans for the

6       project were a large number of different assessments.

7       It may be audits of accounting, it might be looking at

8       project controls, it might be implementation steps.

9       None of those assessments are mentioned in this

10       presentation.  It doesn't mean they weren't planned for.

11       This presentation just didn't cover the self-assessment

12       activities when they discussed it with management.  But

13       I am aware, and it's an easy record to find, any number

14       of different assessments that are very similar in nature

15       to the expert panel.

16            Q.   And speaking of Page 48 here, this references

17       the May 19th, 2008, meeting with NRC.

18            A.   Yes.

19            Q.   And that's a meeting that we have had

20       extensive conversations --

21            A.   Yes, and a meeting I was at.

22            Q.   And you were there.  And the slide that has

23       the schedule on it, that was shown, that was part of the

24       presentation to the NRC, wasn't it?

25            A.   Which one?

FLORIDA PUBLIC SERVICE COMMISSION

426

1            Q.   Well, the one that we talked about earlier

2       that --

3            A.   It may very well have been.  They may have

4       re-used that slide on --

5            Q.   And you did not tell the NRC that you were

6       going to have an expert panel review?

7            A.   I don't believe we did.

8            Q.   Okay.  This presentation also shows management

9       the licensing strategy that you intended to -- at some

10       point prior to this time frame, you intended to pursue

11       with respect to your LAR, does it not?

12            A.   It does talk through a number of the issues we

13       discussed last year and some specific licensing

14       activities.  And let me see if I can remind you of what

15       we're talking about here.  For example, in Pages 51 and

16       52, I see that it's talking about some very specific

17       choke points with regards to the plant's ability to

18       mitigate transients after the increase in power has been

19       achieved.

20                 These issues have to be addressed in the

21       licensing application, and what the company was doing

22       back in May was looking for any opportunities where we

23       might need to submit licensing actions that would have

24       to be -- the specific purpose of that meeting was to

25       search out with the NRC to explore the options we were

FLORIDA PUBLIC SERVICE COMMISSION

427

1       considering to determine if there were any, what you

2       would call a link submittal, which is some portion of

3       the license that might accept a method of doing an

4       analysis or a specific action scenario.  It would have

5       to be approved prior to the NRC accepting the EPU

6       submittal itself.

7                 In other words, they want to approve this one

8       piece of the license that you're going to use as a basis

9       for your extended power uprate license.  The NRC has

10       gotten a new policy -- it was a relatively new policy at

11       this time that those approvals would have to be achieved

12       before the actual extended power uprate license would be

13       accepted for review.  And so these are cases where we

14       were exploring what the right strategy to deal with

15       these issues were with regard to this particular aspect

16       of the way the NRC was licensing.

17            Q.   But in this presentation there were several

18       issues that you thought that you would be submitting,

19       for lack of a better term, smaller LARs?

20            A.   I would say that there were three or four

21       items that we had identified that might require it,

22       depending on which choice or method we chose to pursue.

23       And we used this meeting to flesh out what the right

24       option would be, how receptive they were to those link

25       submittals, or if they needed to be link submittals, or

FLORIDA PUBLIC SERVICE COMMISSION

428

1       if we thought we could use a different process.

2                 And I have slept a couple of times since we

3       had this meeting, but if my memory serves me correct, in

4       some cases we took a different approach.  One example

5       would be boron precipitation.  It's a phenomenon that

6       has to be addressed post accident, and rather than

7       applying for the use of a manual action going forward

8       under extended power uprate that we already had a

9       license for, we chose to modify the plant so that that

10       manual action was no longer required.

11                 In other cases we identified where those

12       licensing activities would not be required because they

13       could be performed under another process like the 50.59

14       process.  And we discussed those with the NRC, and we

15       came to agreement.

16            Q.   Okay.  At the time you -- at the time you met

17       with the NRC, and apparently even in June of 2008, your

18       strategy was still to pursue license amendment requests

19       for several of the solutions, and only analyze one of

20       the solutions under CFR 50.59, isn't that true?

21            A.   Actually, I believe we only identified a

22       single submittal that would be required in addition to

23       the EPU submittal.  At that point that was the rod

24       ejection, and we did apply for and have received that

25       license application.  So it wasn't several; it was only

FLORIDA PUBLIC SERVICE COMMISSION

429

1       one.

2            Q.   Okay.  But in this deck or these slides you

3       reference, basically, a contingent LAR that you would

4       submit, correct?

5            A.   Yes.  And in this case the discussion would

6       have been around, for this presentation, would have been

7       around, you know, should we come to the conclusion,

8       working with the NRC, that that link submittal would be

9       required and that would be when it would be submitted.

10       So we were still in the process of making those

11       evaluations and determinations.

12            Q.   Okay.  Fair enough.

13            A.   But you are asking me what happened, and what

14       happened is we only had to submit one.

15            Q.   Right.  But at the time your strategy was to

16       submit several?

17            A.   I'm lost in the timeline.  We started with --

18       we started with not knowing how many we would have to

19       submit going to the NRC and finding out.  Working

20       through and identifying which strategies would require a

21       license amendment request in addition to the extended

22       power uprate one and which ones did not, and then as we

23       distilled down, we went from three to one.  I don't know

24       when we went from three to one.  And we ended up with

25       only one.  So I'm not sure of the time line on top of

FLORIDA PUBLIC SERVICE COMMISSION

430

1       each other with regard to when this presentation was

2       made.

3                 MR. REHWINKEL:  Madam Chairman, I would like

4       to ask for another exhibit to be identified for

5       cross-examination.  It would be 195.

6                 CHAIRMAN ARGENZIANO:  That's correct.

7                 MR. REHWINKEL:  And this is license request --

8       it actually should say License Amendment Request,

9       Appendix E.

10                 CHAIRMAN ARGENZIANO:  Did you say Appendix B?

11                 MR. REHWINKEL:  E, as in Edward.  And this

12       entire document is confidential.

13                 CHAIRMAN ARGENZIANO:  Okay.

14                 (Exhibit 195 marked for identification.)

15                 THE WITNESS:  It's probably worth noting that

16       this document we were just looking at was only a month

17       after we met with the NRC.  So we were in the process of

18       determining how we were going to deal with that

19       feedback.

20       BY MR. REHWINKEL:

21            Q.   That's fair enough.  I understand that.

22                 The purpose of my question was to identify

23       essentially that you were -- your strategy was somewhat

24       in flux in the sense that it was evolving based on your

25       discussions with the NRC, is that fair?

FLORIDA PUBLIC SERVICE COMMISSION

431

1            A.   That is very fair.

2            Q.   Okay.  Now, what I have passed out is a

3       document I believe you are familiar with, is that

4       correct?  This is a draft of a summary of the LAR, at

5       least as you had contemplated it before June 7th, 2010?

6            A.   Yes.  And I'm not sure of the exact date of

7       this draft, because this is a draft document, and we

8       need to understand that it is a draft document.  In

9       fact, I believe it has comments, word processing

10       comments in the margins where a reviewer has added

11       comments sometime after March and prior to, I'd say,

12       July of this year, based on the information that is in

13       it.  So it's a draft document that was in existence or a

14       status of a section of the LAR in that time frame.

15            Q.   But it's fair to say that this document,

16       absent the digital instrumentation -- is that a good

17       terminology to use?

18            A.   That's a good terminology.  The application of

19       the new regulation with regard to our digital instrument

20       requirements.

21            Q.   Okay.  Aside from that, this document fairly

22       represents the licensing strategy that Progress would

23       pursue absent the digital instrumentation issue that has

24       recently arisen, is that fair?

25            A.   That's fair.

FLORIDA PUBLIC SERVICE COMMISSION

432

1            Q.   Okay.  And with the addition -- and what this

2       document shows is that putting aside the rod ejection

3       analysis, which you had already submitted a LAR for, and

4       you have now received your license amendment related to

5       that analysis?

6            A.   That's correct.

7            Q.   This document shows that you would pursue your

8       LAR based on doing internally, within Progress, 50.59

9       analyses for all of the engineering solutions that would

10       allow you to get to the thermal output that would

11       support your amended license output, is that fair?

12            A.   Well, let me -- I think I know your question,

13       let me see if I can answer it correctly.  Our strategy,

14       and it is indicated in this summary in a number of

15       places, is to be able to install the equipment under

16       50.59.  Now, that what means is -- it's 50.59, or 10 CFR

17       50.59.  That section of the regulation describes how a

18       licensee may modify the plant without prior approval of

19       the NRC.  It provides the guardrails, so to speak.  So

20       long as we are inside those guardrails, we're allowed to

21       make changes to the plant.

22                 It's the process if we have got a new valve

23       because they don't make the old valve, it's how we

24       analyze installing that new valve is okay without prior

25       NRC approval.  So, in this case, a lot of the

FLORIDA PUBLIC SERVICE COMMISSION

433

1       modifications required can be installed without prior

2       NRC approval.  That's our strategy.  It's not the

3       strategy everyone takes, but most have taken that

4       strategy.  And so, in effect, if I want to install a

5       pump that has a higher capacity than the old pump, the

6       NRC doesn't have a problem with that, and doesn't expect

7       me to ask their permission ahead of time.

8                 If later I want to take advantage of that new

9       higher capacity to increase reactor power, then the NRC

10       says, well, wait a minute, you're going to increase

11       reactor power now.  In order to do that, you need a

12       license amendment.  So our strategy has been to install

13       the equipment required to support the basis for the

14       NRC's approval without -- so that equipment can be

15       installed without their approval.  But it provides the

16       function which gives the NRC the basis for approval of

17       our increased reactor power.

18            Q.   And, basically, the NRC expects that your

19       50.59 analysis would support that you can operate at the

20       increased level safely?

21            A.   No, and that's the fine point.  The NRC would

22       expect that my 50.59 analysis would say I could operate

23       at the existing power level with that equipment

24       installed.  Okay.  So the example I gave you is a good

25       one.  Well, we can actually use an example from the

FLORIDA PUBLIC SERVICE COMMISSION

434

1       document.

2                 In one case it says we intend to install a

3       cross-tie system on our low pressure injection system.

4       It's how we will mitigate a need for power uprate.  The

5       NRC is more than happy for me to install that system now

6       at existing power levels, because it only supports the

7       current licensed condition.  Okay.  So there's no

8       problem with me installing it now, but I can't increase

9       reactor power yet.  That additional equipment adds

10       additional margin that the NRC had not perceived as a

11       need at the existing power level.  So I can install it

12       and operate the plant at existing power level without

13       their prior approval.

14                 Prior to increasing power, however, I would

15       have to get their permission to take advantage of that

16       equipment and analysis space.  They would be required to

17       review that analysis in order for them to say, okay, now

18       that you have installed it, I can increase reactor

19       power.  In fact, it speaks to a great deal to your

20       questions earlier about how much engineering work is

21       required to submit the license application.  This is a

22       great example.  They are going to want to see that you

23       have designed and you are on the track to install

24       equipment that has that true capability.  They will

25       review that capability, and once they see you have it,

FLORIDA PUBLIC SERVICE COMMISSION

435

1       they will say, okay, now you can increase reactor power.

2       That is just one element, but that is kind of a slice of

3       how this works.

4            Q.   And your license amendment request will

5       explain to their satisfaction, if they approve it, that

6       you can operate that reactor at the higher level with

7       the engineering solutions that you have installed?

8            A.   That's correct.  The best way to describe

9       it -- I'll give you an example.  It is very complicated,

10       because it is more than change in the plant required.

11       But let's say that there was only one change.  This one

12       LPI cross-tie was the only change required in order for

13       the NRC to say, okay, now you have changed the plant so

14       that it can operate at a higher power level.

15                 What we would do, and our strategy has been

16       all along, to design that modification in a manner and

17       license it in a manner such that it could be installed

18       under the existing license without amendment.  And once

19       it is -- and as it is being installed, go to the NRC and

20       say we are going to install a system which meets, in

21       this case, a LPI cross-tie.  It has a very specific

22       specification, ability to respond to a transient, and as

23       such, once that is installed, I should be able to

24       increase reactor power, and I'm going to ask you

25       permission, NEC, to increase reactor power.

FLORIDA PUBLIC SERVICE COMMISSION

436

1                 So that's what is going on.  Now, it's not

2       just that one system; it's a number of different changes

3       that were required, but that would be one example.

4            Q.   So if I was looking at this document, which

5       is -- what did we call this, 195, the third page of this

6       is E-3.  And since this entire document is confidential,

7       I'm not going to read this, but I would leave it to you

8       to read it if you feel like you can publicly state it.

9       At the very top of that page there is a sentence.  The

10       first -- actually, the first two sentences.  This in a

11       nutshell is your strategy --

12            A.   Yes.

13            Q.   -- for supporting the license amendment

14       request, ignoring for the sake of argument the digital

15       instrumentation issue, is that correct?

16            A.   Yes.  I believe the sentence you're referring

17       to starts, "CR-3 intends"?

18            Q.   Well, actually, the one before that.

19            A.   Yes.  "These modifications improve plant

20       margins at existing power levels."  This particular

21       sentence I would not characterize as confidential.

22            Q.   But the next one.

23            A.   "CR-3 intends to implement these modifications

24       under 10 CFR 50.59, thus the installation of these

25       modifications does not require prior NRC approval via

FLORIDA PUBLIC SERVICE COMMISSION

437

1       this license amendment request."

2            Q.   Okay.  Now I think you said earlier in

3       response to a question a couple of questions ago that

4       some have pursued this particular approach to supporting

5       a license amendment request, but some have not, is that

6       correct?

7            A.   I'm only aware of one plant that has not.  I

8       would say that that one plant's initial submission of a

9       license amendment request was rejected by the NRC.

10            Q.   And who was that?

11            A.   I would rather not say.

12            Q.   Okay.

13            A.   I do know who it was.  It's Point Beach.

14            Q.   Okay.  And is it your testimony that this

15       approach is the -- would not find any -- let me ask it

16       this way.

17                 Is it your testimony that the approach that is

18       embodied on this Appendix E3 would not cause any concern

19       by the NRC with respect to your LAR under the

20       circumstances of the type of uprate that you are

21       planning at Crystal River 3?

22            A.   No.  And my basis for that is that by looking

23       at virtually every power uprate that has been installed

24       in the United States, virtually every one was -- the

25       components were installed at least, or some of the

FLORIDA PUBLIC SERVICE COMMISSION

438

1       components were installed under 50.59, and then the

2       power increase was achieved after the license was in

3       place.

4            Q.   So you would agree, would you not, that the

5       relative power increase that you propose under the LAR

6       that you intend to submit is significant relative to

7       other extended power uprate submissions that the NRC has

8       received, would you not?

9            A.   I'm sorry, I didn't really understand your

10       question.  I got turned around there.

11            Q.   Would you agree that the CR-3 extended power

12       uprate is a relatively large percentage increase?

13            A.   It's a good uprate.  It's not unusual.  Just

14       looking at the list of other uprates, there have been a

15       large number between 15 and 20 percent, maybe 10 or 12

16       that have been approved.

17            Q.   Now, what was Ginna, were they about

18       17 percent?

19            A.   Ginna was 16.8 percent.

20            Q.   But Ginna had also undergone in the '80s an

21       uprate in the 18 percent range, had they not?

22            A.   Give me one moment.  I am only aware of one

23       Ginna.  There may have been two.  I'm only aware of one.

24            Q.   Would you agree -- I think Dr. Jacobs -- do

25       you have Dr. Jacobs' testimony with you?

FLORIDA PUBLIC SERVICE COMMISSION

439

1            A.   No, but I'll be happy to refer to it.

2            Q.   Well, he has an exhibit that lists the

3       uprates.  Would you agree with that?

4            A.   Yes, he does, and I'm familiar with the

5       exhibit.  To be honest, I'm surprised I don't see Ginna

6       on one of my lists here.

7            Q.   Okay.  Well, if I could ask you to look at

8       Page 4 of 4 of Dr. Jacobs' Exhibit 3.

9            A.   Certainly.

10            Q.   There is a footnote under the schedule.

11            A.   Yes.  This is why I do not list it in my list.

12       Give me just a second.  I feel better now.

13                 What this is a note to, this is a -- this

14       exhibit from Dr. Jacobs' testimony is actually a

15       printout of a page from the NRC, and it lists all the

16       increases in power of nuclear facilities in the United

17       States.  What it's referring to is capacity recapture

18       power uprates are not included in this table, and then

19       it lists Ginna of an uprate of 17 percent in '84, which

20       I believe is the 16.8.  Let me look at the date here.

21       No, this is -- they did an additional 16.8 percent in

22       2006.  So what happened in '84 at Ginna makes -- this

23       makes a lot of sense to me.

24                 Capacity recapture power uprates are a little

25       different.  I believe what this is referring to and why

FLORIDA PUBLIC SERVICE COMMISSION

440

1       it's not in the table is that this -- I would like to

2       verify, but I believe what we are seeing here is this

3       was an increase in power that did not require a license

4       amendment because the original license accommodated the

5       higher power level, yet for some other reason Ginna

6       chose not to operate at that higher power level.

7                 And it may have been when they originally

8       built the plant they got a power level to operate at a

9       higher power level than they were able to achieve with

10       the equipment they had installed.  But as far as the NRC

11       was concerned they could operate at the higher power

12       level, and that is typically what this is referring to.

13            Q.   Okay.

14                 COMMISSIONER SKOP:  Mr. Rehwinkel?

15                 MR. REHWINKEL:  Yes.

16                 COMMISSIONER SKOP:  Just for planning

17       purposes, do you know how long you have on your cross

18       remaining?

19                 MR. REHWINKEL:  I have probably another hour

20       at least.

21                 COMMISSIONER SKOP:  Okay.  Please feel free to

22       continue.

23                 MR. REHWINKEL:  Okay.  Is it the Commission's

24       intention to go to a certain point tonight?

25                 COMMISSIONER SKOP:  I believe the Chairman

FLORIDA PUBLIC SERVICE COMMISSION

441

1       indicated her preference was to adjourn at 5:30 this

2       evening.

3                 MR. REHWINKEL:  Okay.

4                 COMMISSIONER SKOP:  So that's -- feel free to

5       continue.  What I'm most impressed with, though, is your

6       ability to get opposing counsel to mark up your

7       documents for you.

8                 MR. REHWINKEL:  Well, I do appreciate the fact

9       that they have done this, because it accommodates the

10       Commission, as well.  I appreciate it.

11                 COMMISSIONER SKOP:  Just wait until you get

12       the bill for billable hours.  (Laughter.)

13       BY MR. REHWINKEL:

14            Q.   Mr. Franke, we talked a little bit about the

15       expert panel debrief.

16            A.   Yes, sir.

17            Q.   But before we get to that, isn't it true that

18       in 2006 when Progress Energy set out to implement the

19       extended power uprate that you thought that the process

20       would be cheaper and less complex than it has turned out

21       to be?

22            A.   The licensing application process?

23            Q.   Yes.

24            A.   I believe that's true, yes.  I believe when we

25       started in 2006, we believed that the Ginna model would

FLORIDA PUBLIC SERVICE COMMISSION

442

1       be sufficient and that the depth of information required

2       by the NRC would be a lot less rigorous than subsequent

3       NRC licensing activities proved to be.  And as a result,

4       we had to add time, we had to add cost, and I would also

5       say that we changed our philosophy with regard to when

6       the appropriate time to submit the license application

7       was.  We wanted to make sure that we took advantage of

8       the lessons learned of previous license applications in

9       ours, so that when we submitted we had the highest

10       chance of receipt successfully by the NRC.

11            Q.   You would agree that you thought the overall

12       project would be easier in a relative sense, correct?

13            A.   I think we believed that the license

14       application would require less rigor.  Easy is not a

15       term I would apply or try to compare, you know, whether

16       something was easier or not easier.  It's just a matter

17       of work.  It's all work.  It's good work to be in.

18            Q.   But you thought that it would be cheaper,

19       correct?

20            A.   We thought that the licensing application

21       piece would be cheaper.  We thought the overall project,

22       as we talked earlier when we referred to TOR-7, that the

23       entire project would be more expensive.  So the project

24       has gotten a little bit cheaper overall, and the

25       licensing piece of it has gotten a little more

FLORIDA PUBLIC SERVICE COMMISSION

443

1       complicated.

2            Q.   Absent the transmission piece of it, you

3       thought it would be much cheaper, correct?

4            A.   Well, if I want to take that one point out,

5       yes, you are correct.  We thought that the plant piece

6       would be cheaper, we thought the transmission piece

7       would be more expensive, and we were a little wrong on

8       both accounts.  But when you sum it all up at the end,

9       it's about the same price.

10            Q.   Okay.  And over the time of the project the

11       NRC's expectations have evolved, isn't that correct?

12            A.   Absolutely.

13            Q.   With respect to what they want to see in a

14       license amendment request?

15            A.   Yes.  They continue to revise their process.

16       A great example is this digital licensing.  You know,

17       the NRC -- ironically, we had just licensed the digital

18       instrument we were intending to use, relicensed it for a

19       related -- an unrelated application back in 2003.  And

20       now when we looked back in 2009 at the standards that

21       have evolved there, those standards have moved, and we

22       no longer could use that same basis that they had

23       approved in 2003 for 2009.

24            Q.   In your testimony, you attached a copy of a

25       contract with AREVA, and that is attached as Exhibit

FLORIDA PUBLIC SERVICE COMMISSION

444

1       JF-7, is that correct?

2            A.   This is rebuttal.  Yes, sir.  I do have that.

3            Q.   And that contract represents your expectation

4       that AREVA would deliver to you, at the time, at the

5       milestone that was assumed in the contract a draft LAR

6       of sufficient quality to be accepted by the NRC, isn't

7       that true?

8            A.   In this case, what this was a contract to

9       perform was to generate a license application as defined

10       at the time that the contract was written.  It did not

11       accommodate any changes in scope that might be required

12       to meet a moving standard.

13            Q.   Okay.  But your expectation from AREVA was

14       that they deliver a draft; at the time they delivered it

15       that would meet your expectations of acceptance by the

16       NRC, correct?

17            A.   No.  I would say that our contract with AREVA

18       was to deliver a draft in accordance with the scope and

19       format that we had communicated to them that it was

20       expected.

21            Q.   Okay.  Well, you didn't enter into this

22       contract with the dollar amounts that are assumed in the

23       contract with the expectation that they would give you a

24       product that you would not be able to submit to the NRC,

25       were you?  Did you?

FLORIDA PUBLIC SERVICE COMMISSION

445

1            A.   The intention of this contract -- I would love

2       to able to get a vendor to sign a contract that says I

3       want you to meet whatever future standard might be

4       placed on the requirements of this work.  That is not

5       the way it works.

6                 This was a contract written with AREVA to a

7       specific scope and expectation.  That's how these

8       contracts are written.  I can't get a contract from

9       AREVA that says I want you to meet the requirements the

10       NRC may have in three years.

11            Q.   And you expected AREVA to provide this work

12       product on the time frame that you expected or you

13       contracted for it, correct?

14            A.   That's correct.

15            Q.   And that time frame was in the spring of 2009,

16       correct?

17            A.   I'd have to review the contract, but I know

18       our intention was to have this original scope and format

19       license amendment request draft provided to us by the

20       summer of 2009.

21            Q.   And you also expected AREVA to have the

22       requisite expertise to produce the work product that you

23       contracted for, correct?

24            A.   That's a difficult question to answer, Mr.

25       Rehwinkel.  AREVA didn't have a staff full of engineers

FLORIDA PUBLIC SERVICE COMMISSION

446

1       that had ever produced an extended power uprate license

2       before.  However, they were the only staff that had the

3       proprietary knowledge required to generate that

4       information.  So I would say that I would expect them to

5       use their engineering staff they had to produce a

6       document that met a format and a scope that we had

7       defined.

8                 It would have been unreasonable for me to

9       expect and impossible for me -- or for AREVA to produce

10       a staff that was experienced at delivering an extended

11       power uprate license because they don't exist on the

12       planet.  They didn't at that time, anyway.

13            Q.   Okay.  December 11, 2006, when management

14       approved or formally authorized the CR-3 EPU, is it your

15       testimony then that you were aware that AREVA had some

16       lack of expertise or experience with respect to

17       producing an acceptable draft LAR?

18            A.   I would say that we knew that the engineers

19       that would be producing this document may not have had

20       extensive EPU experience.  Here is the issue.  There are

21       two kinds of experiences that are required to produce

22       this document and one set of proprietary information.

23       So when you go to contract with whomever you are going

24       to contract, first you have to get the people that are

25       technically qualified on the equipment and the basic

FLORIDA PUBLIC SERVICE COMMISSION

447

1       design of the reactor plant.  Okay.  Then it would be

2       nice to have some people that not only had that

3       knowledge, also had done this kind of licensing design

4       reviews previously.  The analysis itself isn't that

5       much -- isn't that special, it is similar to analysis

6       that had originally been performed when the plants were

7       originally licensed, as well as in subsequent

8       engineering work that AREVA had performed for other

9       similar licensing activities.

10                 But, you know, in a perfect world there would

11       be that group of folks that have that all wrapped up

12       into one.  It just doesn't exist.  It will -- when we

13       are finally done with this project, AREVA will have a

14       staff that has done it.

15                 It is probably worthwhile to note in this

16       contract, if you look at Page -- the page numbers using

17       the docketed page numbers, 6 of 91, the contract

18       accounts for time and material billing as part of the

19       scope, part of the rules under which this contract would

20       be enforced.

21            Q.   But you would agree that on December 11, 2006,

22       there was some awareness on Progress' part that AREVA

23       might need some extra supervision and contract

24       management by Progress, correct?

25            A.   That's correct.  In fact, that was one of the

FLORIDA PUBLIC SERVICE COMMISSION

448

1       reasons we chose to, and subsequently as we worked

2       through this process, we laid out a plan to have that

3       expert panel review as a self-assessment process.

4            Q.   You didn't communicate that to AREVA, though,

5       did you?

6            A.   I have no idea if we did or not.  I know that

7       they knew we would be using a self-evaluation process.

8       Whether they knew it would be these particular people

9       looking at it, I don't know.

10            Q.   And isn't it true that Progress had what you

11       consider the requisite engineering skills to oversee

12       AREVA and their performance of what you contracted for?

13            A.   I think Progress in conjunction with some

14       outside expertise, we had the ability to go back and

15       look at whether they were producing a quality product or

16       not.

17            Q.   Now, isn't it true that when you got the work

18       product from AREVA and you saw the results, you,

19       Progress' management, saw the results that the expert

20       panel identified, that you were disappointed in the work

21       product that you received from AREVA?

22            A.   Yes, we were very disappointed.  Absolutely.

23       The expert panel review, as we were receiving the first

24       big cache of the sections of the license amendment,

25       demonstrated that AREVA had done a very poor job, and

FLORIDA PUBLIC SERVICE COMMISSION

449

1       that some of the submittals from AREVA -- and, in fact,

2       some from my own inexperienced staff had not provided

3       the details required, nor met the original scope of the

4       original contract.  As such, we went back with AREVA.

5       We sat down.  You know, we were very disappointed in our

6       oversight to date.  Very happy we had the expert panel.

7       We used that expert panel to define where those

8       deficiencies were, do a good job of understanding it,

9       use our nuclear condition report system to do an

10       investigation of what caused the problems, and put in

11       place corrective action so it would not happen again.

12       And I can assure you I didn't pay AREVA an extra dime to

13       meet that extra scope.

14                 MR. REHWINKEL:  Madam Chairman, I would like

15       to ask for two exhibits to be identified for the record

16       for cross-examination.

17                 THE WITNESS:  And I just misspoke.  I didn't

18       pay an extra dime for the original scope.

19                 CHAIRMAN ARGENZIANO:  They will be 196 and

20       197, and if you can give a brief description.

21                 MR. REHWINKEL:  Okay.  196 would be CR-3, EPU

22       Expert Panel.

23                 CHAIRMAN ARGENZIANO:  At the mike so that our

24       court reporter can hear you, can properly hear you.

25                 MR. REHWINKEL:  196, that would be Expert

FLORIDA PUBLIC SERVICE COMMISSION

450

1       Panel would be a good short title.

2                 CHAIRMAN ARGENZIANO:  Okay.

3                 MR. REHWINKEL:  And 197 would be Adverse

4       Condition Investigation.

5                 CHAIRMAN ARGENZIANO:  Thank you.

6                 (Exhibits 196 and 197 marked for

7       identification.)

8                 MR. REHWINKEL:  And I should say that 196 is a

9       document entitled CR-3 EPU Expert Panel Management

10       Debrief, July 14, 2009.  While 197 has a cover sheet

11       with an action request, and then an Attachment 3, which

12       is the adverse condition investigation form.  There are

13       some documents in between that are just -- I can provide

14       them, but I think they are mostly kind of recordkeeping,

15       housekeeping documents.

16                 THE WITNESS:  They are.

17       BY MR. REHWINKEL:

18            Q.   You are familiar with both of these documents,

19       are you not?

20            A.   Yes, sir, I am.

21            Q.   Okay.

22                 MR. REHWINKEL:  And, Madam Chairman, I did not

23       have a chance to provide these to the company for

24       confidentiality determinations.  I don't know if we

25       could huddle for just a couple of minutes with the

FLORIDA PUBLIC SERVICE COMMISSION

451

1       company to talk about them.

2                 CHAIRMAN ARGENZIANO:  Okay.  Let's do that and

3       take a few minutes.

4                 (Off the record.)

5                 CHAIRMAN ARGENZIANO:  While we have a few

6       minutes, if everybody listens up, just when you have

7       confidential information, you might want to have them

8       highlighted so that we don't have to do this.  And

9       not -- no real big problem, just for the future

10       reference so that we can keep moving smoothly in case

11       there is other information.  We plan to close today

12       at -- you know, recess today at 5:30.  Tomorrow we'll

13       probably stay later.

14                 (Off the record.)

15                 MR. BURNETT:  Madam Chairman, may I be

16       recognized?

17                 CHAIRMAN ARGENZIANO:  Where are you?  Yes.

18       Please, go right ahead.

19                 MR. BURNETT:  Good evening.  Madam Chairman,

20       I'm not quite sure how these documents got classified as

21       confidential, no yellow highlighting, and they seem to

22       have them on top, but these can be spoken about freely

23       in the public.  Neither one of these documents are

24       confidential.

25                 CHAIRMAN ARGENZIANO:  So both are not

FLORIDA PUBLIC SERVICE COMMISSION

452

1       confidential?

2                 MR. BURNETT:  Yes, ma'am.  Any content can

3       spoken of freely.

4                 CHAIRMAN ARGENZIANO:  Okay.  Thank you.

5                 MR. BURNETT:  Thank you for the time to

6       review.

7                 CHAIRMAN ARGENZIANO:  Appreciate that.  Thank

8       you.

9                 MR. BURNETT:  Thank you.

10                 MR. REHWINKEL:  Thank you.

11       BY MR. REHWINKEL:

12            Q.   Mr. Franke, are you familiar with Exhibits 196

13       and 197?  I may have already asked you that.

14            A.   Yes, I am.

15            Q.   Now, 196 is a slide presentation that I assume

16       was given by the expert panel to management on

17       July 14th, 2009, is that correct?

18            A.   That's correct.

19            Q.   Okay.  And the first page after the title

20       page, Page 2 just lists the team members of the panel,

21       correct?

22            A.   That's correct.

23            Q.   And the first two, Bryan Miller and Mark

24       Turkal, T-U-R-K-A-L, they are Progress employees,

25       correct?

FLORIDA PUBLIC SERVICE COMMISSION

453

1            A.   They are Progress employees, yes, sir.

2            Q.   Okay.  And they were employees that had the

3       requisite experience to be able to evaluate critically

4       the submittal by AREVA, correct?

5            A.   Yes, in conjunction with the team.  They have

6       some experience with extended power uprates.  They work

7       for Progress Energy Carolinas.  But, yes, they work for

8       Progress Energy.

9            Q.   Okay.  Now, the third page of this document

10       gives -- tells the scope of the review, and isn't it

11       true that what the panel looked at was a single draft

12       copy of the AREVA work product?

13            A.   Yes, as well as some of the work that was

14       performed by my own people.  It's probably worth noting,

15       by the way, as you talk about the team members

16       experience, Bryan Miller and Mark Turkal were

17       experienced with previous EPUs.  So their experience was

18       more historical in nature.

19                 Greg Ellis, however, is a gentleman that's

20       very active in ongoing licensing activities, and as such

21       was probably the one member that brought forward the

22       more recent experiences with extended power uprates.

23       Bryan and Mark had not worked on power uprates for many

24       years.  If you look at the dates of the Waterford and

25       Brunswick extended power uprates, they were years

FLORIDA PUBLIC SERVICE COMMISSION

454

1       before.

2            Q.   Okay.  Now, the third page.  Okay.  It shows

3       the scope, and then the purpose was to assess the LAR,

4       that's the draft licensing report, correct?

5            A.   That's correct.

6            Q.   To see whether it would meet NRC acceptance

7       review and provide sufficient detail for the NRC to

8       independently conclude acceptability of the project for

9       purposes of a license amendment, is that right?

10            A.   That is correct.

11            Q.   And the document also lists the review

12       standards, the RS-001, compare it to the Ginna EPU

13       submittal, and the Ginna responses to the RAI, the

14       Request for Additional Information, as well as the NRC's

15       safety evaluation for the Ginna EPU and the Point Beach

16       EPU submittal?

17            A.   That's correct.

18            Q.   Okay.  Now, what the fourth page shows are the

19       specific deficiencies that the panel found.  They note

20       that there was a cut and paste job in the Ginna

21       submittal that even included, I guess, Ginna specifics

22       that had no applicability to CR-3?

23            A.   Yes.  What the panel review identified is that

24       some of the work by AREVA had essentially been

25       electronic clip and paste.  They had taken the Ginna

FLORIDA PUBLIC SERVICE COMMISSION

455

1       submittal, and for those more generic sections, not the

2       facility-specific sections that required AREVA

3       engineering, but some of the more -- a lot of the LAR is

4       technical in nature, a lot of it is just a lot of

5       language, and in those sections that might have been

6       just kind of generic language, which encompasses the

7       purpose of an extended power uprate and that sort of

8       thing, that we actually found the word Ginna still in

9       the sections.

10            Q.   In the third bullet point there it says that

11       it appears that the RAIs and the NRC safety evaluation

12       for the Ginna EPU -- I said safety, it says SE, but

13       that's what that means, right?

14            A.   Yes.  SE is Safety Evaluation.  That is when

15       you submit a license application request, the NRC's

16       technical detailed response is called a Safety

17       Evaluation or a Safety Evaluation Report.

18            Q.   Okay.  It says that they were not considered

19       or addressed in this draft license report, is that

20       correct?

21            A.   Absolutely.  And we can go through the whole

22       presentation if you'd like.  The point you are making is

23       very valid, and it was a disappointment by us.  It was

24       clear AREVA had not done the job we had contracted them

25       for.

FLORIDA PUBLIC SERVICE COMMISSION

456

1            Q.   Well, didn't the NRC -- didn't your discussion

2       on May 19th, 2008, almost, I guess, a year earlier, the

3       NRC specifically told Progress to pattern the LAR after

4       the most recent PWR efforts, Ginna, including

5       consideration of RAIs?

6            A.   Absolutely.

7            Q.   Okay.  So was that communicated to AREVA?

8            A.   Yes, it was.

9            Q.   Okay.

10            A.   So what happened here is we found using the

11       expert panel they had made mistakes.  We did a thorough

12       scrub.  We were embarrassed by the results.  We went

13       back to AREVA, sat them down, had a lot of strong

14       conversations.  Disappointment is probably a weak

15       description of my personal opinion of what we were at,

16       and we went back and explained to them that they were

17       going to go fix it and fix it on their dime, and that's

18       what they did.

19            Q.   Exhibit 196.  Well, first of all, after this

20       debrief occurred, I expect that you very quickly -- if

21       we look on Exhibit 196, near the top of the page, it

22       looks like this action request was originated the very

23       next day.

24            A.   Yes, sir.

25            Q.   Okay.  And there's a summary of the

FLORIDA PUBLIC SERVICE COMMISSION

457

1       independent review that I assume the Progress team did

2       once they received this debrief, is that correct?  Is

3       that what this summary shows on the first page of

4       Exhibit 197?

5            A.   If you are talking about -- it says -- at the

6       top it says Action Request 00345243.

7            Q.   Yes.

8            A.   And then it's in the table format where it

9       says description.

10            Q.   Yes.

11            A.   That's a description of the problem.  That's

12       kind of a problem statement that is written at the time

13       the nuclear condition report is initiated.

14            Q.   Okay.  The next page, which is -- it says

15       Attachment 3, Sheet 1 of 2, adverse condition

16       investigation form.  This is the guts of what the

17       Progress -- well, actually, tell me who did this adverse

18       condition investigation form?

19            A.   We actually used a team.  The specific

20       investigator was a gentleman named Bryan McCabe

21       (phonetic).  His name is on the top of the second page

22       in the handout, but it is the first page of the

23       investigation report form.

24            Q.   Now, who does he work for?

25            A.   He works for our corporate -- he works in our

FLORIDA PUBLIC SERVICE COMMISSION

458

1       corporate office.  Bryan is a -- he's a senior

2       regulatory affairs specialist.  He has a couple of

3       licensing engineers working for him.  He's -- he's one

4       of our licensing experts in the company.

5            Q.   Okay.  So he has the expertise to do this

6       review that is in this -- that's attached to Exhibit

7       197?

8            A.   Yes.

9            Q.   Okay.  And you agree with the findings, the

10       investigation summary as well as the apparent cause that

11       is shown on Attachment 3, is that true?

12            A.   I agree, yes, absolutely.

13            Q.   Okay.  Now, we could go through all of this,

14       but it's fairly self-explanatory.  The investigation

15       summary essentially shows that the work product of AREVA

16       was of poor quality, correct?

17            A.   Yes.  The work product of AREVA was of poor

18       quality.

19            Q.   Okay.

20            A.   For the reasons identified in this

21       investigation.

22            Q.   Now, this document -- neither this document

23       nor the presentation that is contained in Exhibit

24       196 make any reference to evolving NRC -- increasing

25       industry standards associated with NRC licensing

FLORIDA PUBLIC SERVICE COMMISSION

459

1       activities, do they?

2            A.   I'm not sure if it does.  This was

3       investigating the overall poor quality, and it was

4       looking at, including those things like the Ginna clip

5       and paste errors and that, essentially, it did not meet

6       the original scope and content of the investigation.  So

7       I would say that this investigation was looking more at

8       why the contract did not meet its initial scope and

9       sequence.

10            Q.   This investigation, meaning what is in 197?

11            A.   That is correct.

12            Q.   Okay.  But, again, the report of the expert

13       panel makes no mention of increasing industry standards

14       associated with NRC licensing activities, does it?  In

15       fact, doesn't the expert panel reference the guidance

16       the NRC gave you about the RAIs for Ginna a year ago?

17            A.   I think you's mixing some apples and oranges

18       here.  This was not a root cause of why AREVA did not

19       meet their contractual requirements, okay.  This was a

20       root cause as to why we were not in a position to have

21       the licensing application approved.

22                 There is a misconception here.  The problem

23       was we weren't ready to submit the license application.

24       Okay.  And this investigation did not look at things

25       like contractual -- meeting the contract or costs

FLORIDA PUBLIC SERVICE COMMISSION

460

1       associated with what would be required to meet the

2       contract.  It was answering the question why aren't you

3       able to submit your license application, or why isn't it

4       further enough developed right now in order to submit

5       your license application.  What you are trying to apply

6       it to is why didn't AREVA meet their contract.  That is

7       two completely different things.  So this isn't --

8       nowhere in that problem statement does it say why didn't

9       AREVA meet its contract.

10            Q.   Which problem statement is that?

11            A.   The problem statement that was on that first

12       page you just referred to.

13            Q.   But the root cause analysis is that this

14       was -- that AREVA did a sloppy job?

15            A.   No, it isn't.  It doesn't say AREVA anywhere

16       in here.  Well, it say AREVA and NGG activities.  But

17       the adverse condition is not why didn't AREVA meet its

18       contract.  You have got to be very careful when you ask

19       a specific question to one of these guys that's trained

20       on root cause, they are going to answer that question.

21       And the question here was why there was not a high

22       quality EPU LAR with sufficient content and quality to

23       pass the NRC acceptance review.  I'm quoting from the

24       first page of the investigation report form.

25                 So it is answering the question why aren't you

FLORIDA PUBLIC SERVICE COMMISSION

461

1       ready to submit your license application.  It isn't

2       answering the question why didn't AREVA do its job.

3       That was a conversation I had with AREVA management.

4            Q.   Okay.  But under the apparent cause LAR

5       quality issues heading at the bottom of the first page

6       of the adverse condition investigation form, F3A, I

7       assume that's a category?

8            A.   Yes, that is a code we use to -- we do a

9       hundred of these a year, maybe not to this level, but we

10       do a large number of investigations.  We try to

11       categorize them into categories as to the reasons why we

12       made a mistake at the plant.

13            Q.   Okay.  And it says management follow-up or

14       monitoring activities did not identify problems.  Do you

15       agree with that?  Not only that it says it, but that is

16       what happened?

17            A.   Yes.

18            Q.   Okay.  Now, do you remember when we started

19       off cross-examination awhile back, I asked you about the

20       dollars that were included in your Direct Testimony

21       related to project management.  Do you remember that,

22       and licensing activities, correct?

23            A.   Yes, sir.

24            Q.   Those dollars would be covering activities

25       that would oversee this contract as well as the Progress

FLORIDA PUBLIC SERVICE COMMISSION

462

1       Energy employees that were associated with this draft

2       LAR activity, correct?

3            A.   I think what this investigation identified and

4       what the expert panel identified is that the level of

5       engagement -- and you can read that a lot of ways.  How

6       I read that is we were not spending sufficient time or

7       sufficient resources to oversee the AREVA work early

8       enough.  So when we start turning it into dollars, and

9       some of this is semantics, and I want to be careful

10       here.  I'm aware that this particular document was

11       subject to audit by staff.

12                 When you send an accountant to go review

13       something and he sees that there is improper financial

14       management, they will write a sentence that says, you

15       know, management monitoring was not sufficient.  This

16       root cause was saying why wasn't the licensing work done

17       correctly, and what it's identifying is very clear to

18       me, that we were not spending sufficient resources on

19       this licensing application and we needed to spend more

20       money on it, not less in oversight.

21            Q.   Well, the intention of Progress was not to get

22       this type of work product or get it in a way that

23       delayed -- well, first of all, it was not your intention

24       to get the work product that the debrief -- the expert

25       panel --

FLORIDA PUBLIC SERVICE COMMISSION

463

1            A.   No, we expected it to be at a higher quality

2       at that stage.

3            Q.   And you didn't expect the six-month delay that

4       the rewrite caused in the preparation of the draft LAR,

5       correct?

6            A.   We did not expect the six-month delay.  But I

7       will tell you today that one of the -- and it is not in

8       this investigation because it wasn't part of the

9       problem.  But one of the fallouts of this expert panel

10       review was a better understanding of what the NRC -- of

11       the right way to continue to engage with the NRC.

12                 And let me make sure that this is clear.

13       Prior to this expert panel review, I think we were still

14       kind of stuck on the idea that the Ginna submittal was

15       the right model, okay.  Greg Ellis and the others that

16       came forward in this expert panel, they took a step back

17       and looked at other licensing activities.  They said

18       wait a minute, this standard from Ginna is no longer the

19       right standard, and the NRC expectations are moving.

20                 One of the lessons of this expert panel was

21       while it did delay the licensing application, when we

22       took a step back and looked at our strategy going

23       forward, we recognized that early submittal is not

24       necessarily good, because early might mean you don't

25       have the lesson of a license application that is on

FLORIDA PUBLIC SERVICE COMMISSION

464

1       going.  So, yes, it did cause a six-month delay, but I

2       will tell you since then I have made conscious decisions

3       not to submit earlier because I might not be supplying a

4       license application that is up to the latest standards

5       and it might get rejected.  Other utilities have made

6       that mistake.  It's not my intention to make that

7       mistake.

8            Q.   You would agree, though, that had the expert

9       panel said that this was a good draft LAR you would have

10       submitted it, wouldn't you?

11            A.   I may have submitted it, and from what I now

12       understand of the changing NRC standards, it likely

13       would have been rejected.

14            Q.   You didn't know that at the time?

15            A.   The expert panel explained that to me.

16            Q.   They explained that to you in this document?

17            A.   Yes, they did.

18            Q.   Is there a mention in here that had the --

19            A.   Yes.

20            Q.   -- quality of this been right that it would

21       have still failed?

22            A.   Well, let's be careful.  I'm going back.  I'm

23       doing the same thing I accused you of earlier.  I am

24       mixing the contract with the changing standards.  If you

25       look at the expert panel, and I don't know the number of

FLORIDA PUBLIC SERVICE COMMISSION

465

1       the exhibit, the exhibit numbers --

2            Q.   This is 196.

3            A.   196 is absent from my copy.  But the

4       presentation by the expert panel, it talks about the

5       license report quality on one page.  And that speaks to

6       a large degree, and there is no page numbers here,

7       but --

8            Q.   Lower left.

9            A.   Lower left.  That speaks more to the contract,

10       of meeting the original contract.  But if you look at

11       the next page, Page 5, okay, most of this detail talks

12       about scope beyond what that original visionary scope of

13       2006/2007 was when the contract was signed with AREVA.

14       That the NRC has now gone further, and Ginna standards

15       that they discuss as not meeting on Page 4 is no longer

16       the standard required by the NRC, and that you are going

17       to have to go farther and longer.  Okay.  You are going

18       to have to look at Point Beach, you are going to have

19       look at the other submittals that were ongoing.  Why

20       Monticello was rejected, okay, and you are going to have

21       to incorporate those lessons learned.  So this is really

22       more a reflection of scope increase beyond that original

23       contract scope.

24                 This isn't an assessment of the contract.

25       It's an assessment of the activity.  That contract, what

FLORIDA PUBLIC SERVICE COMMISSION

466

1       we found out from the expert panel was not everything

2       required in order to achieve the application we needed,

3       and so we had to go beyond that original contract scope.

4            Q.   Well, doesn't on Page 5, the item that reads

5       based on the LAR review, aren't they -- it says the

6       technical work has not progressed far enough to support

7       the submittal.  Absent this information, the LAR cannot

8       be submitted to the NRC.

9            A.   And that is exactly what I'm talking about.

10       Here is where the expert panel is telling me that the

11       detail requirements of the licensed application, the

12       rigor that is explained and demonstrated in that

13       application is a higher standard than what we are

14       providing.  And that's the lessons of those license

15       applications that I just talked about, Point Beach,

16       Monticello, and other applications that have occurred.

17            Q.   But it says that the work has not progressed.

18       It doesn't say what they did falls short of what the NRC

19       requires, does it?

20            A.   That's the next page.

21            Q.   But the items --

22            A.   Look on Page 6, at the top Page 6.  Reading,

23       it says the current EPU LAR will not pass NRC acceptance

24       review.

25            Q.   But that's because of the quality of it, isn't

FLORIDA PUBLIC SERVICE COMMISSION

467

1       it?

2            A.   Read the next word.  The next sentence is

3       extensive technical work is necessary to complete the

4       large submittal.  This is talking about that technical

5       rigor and depth and detail that we were talking about.

6            Q.   But on Page 5 it says based on the LAR review,

7       technical work has not progressed far enough to support

8       the submittal.  If you go back to Page 2 of the

9       document, the panel notes that -- doesn't the panel

10       discuss that the draft wasn't even complete?

11            A.   Yes.

12            Q.   Okay.  So what the panel was saying is that

13       they didn't get the work done on time?

14            A.   That's correct.

15            Q.   Okay.  And Page 5 says that based on the LAR

16       review, technical work has not progressed.  That is part

17       of that problem that they didn't fulfill the milestone

18       that the contract expected, which is to give you a

19       complete draft, right?

20            A.   Let me detail it out for you here.  AREVA did

21       not meet our schedule.  They did not meet the original

22       scope and content of their original contract.  We held

23       them to task with that regard, and we had them rewrite

24       and meet that original contract at their expense.

25                 Additionally, the expert panel recognized that

FLORIDA PUBLIC SERVICE COMMISSION

468

1       the contract was not sufficient.  Now, they didn't go in

2       and review the contract.  That wasn't their purview.

3       Their purview was to say is this application going to

4       meet the newest standards.  And what that they

5       identified was, wait a minute, you know -- and this was

6       really something subsequent to the expert panel, because

7       they weren't asked to look at the contract.  It was that

8       the depth of detail, and that is what is being talked

9       about in Page 5, that the scope of work identified in

10       that original contract would never meet today's

11       standards for the NRC, despite the fact that they had

12       indicated to us back in -- was it 2007, May of 2007,

13       that the Ginna submittal was the right model.  Well, in

14       2009 the expert panel told us that is not the right

15       model anymore.  You have got to go well beyond what

16       Ginna submitted if you are going to be successful today.

17            Q.   The items that are listed on Page 5 --

18                 CHAIRMAN ARGENZIANO:  I'm sorry, did you have

19       a question?

20                 COMMISSIONER SKOP:  Just before we conclude

21       today I have a brief question, not for the witness.

22                 CHAIRMAN ARGENZIANO:  Mr. Rehwinkel, on your

23       line of questioning continue, and then when you -- when

24       we take a break from that point that you are trying to

25       get to --

FLORIDA PUBLIC SERVICE COMMISSION

469

1                 MR. REHWINKEL:  Okay.  I will just ask one

2       more question, and then --

3                 CHAIRMAN ARGENZIANO:  Fine.

4                 MR. REHWINKEL:  Okay.

5       BY MR. REHWINKEL:

6            Q.   The items on Page 5 that start with EC

7       development for advanced ADV, Atmospheric Dump Valves,

8       right?

9            A.   Yes.

10            Q.   Okay.  Those items there, they represent

11       incomplete analysis in the draft, not changes in the

12       NRC's regulations, correct?

13            A.   Let me try to use this example to try to drive

14       the point home, okay.  The Ginna submittal, for example,

15       might have said that we are going to use atmospheric

16       dump valves -- and this is an example, Ginna didn't use

17       this strategy.  But let me see if I can relate it in

18       simple terms so that it's clear.  I'm doing a bad job,

19       clearly.

20                 For example, with regard to this bullet, the

21       level of detail explained by the Ginna submittal may say

22       we're going to use atmospheric dump valves in order to

23       depressurize the reactor to meet this small break LOCA,

24       okay.  And it might go into some cursory analysis that

25       says that that should be sufficient, okay.  What this

FLORIDA PUBLIC SERVICE COMMISSION

470

1       bullet is saying is that you actually -- the EC

2       development, EC is actually the Engineering Change

3       package, and this goes back to what we have been talking

4       about for a year now.  What this expert panel is telling

5       me is that not only do you have to tell the NRC that you

6       are going to use ADVs, you have got to perform the

7       engineering change.  You have got to go into the details

8       of which valve you are going to use; what size it's

9       going to be, what is the blowdown that this valve can

10       accomplish, in other words what pressure it can

11       accomplish in what time frame; how does that line up

12       against the timeline of a small break LOCA.  Show me

13       your reactor model that demonstrates that that blowdown

14       will be sufficient to depressurize the reactor, and your

15       high pressure injection pumps can provide enough flow

16       into the reactor so that the design is adequate.  That's

17       what I am talking about.

18                 In Ginna they might have said ADS valves.  EDC

19       development -- EC development means you need that

20       engineering change written and designed and developed.

21       And that's what I'm talking about here.  The Ginna depth

22       of detail got -- the depth of detail required for this

23       specific example was now much larger than it had been

24       before with the Ginna.

25                 Now, they weren't comparing to Ginna.  What

FLORIDA PUBLIC SERVICE COMMISSION

471

1       they were comparing to is what is the new requirements,

2       what is the present requirement.

3            Q.   I guess my question still is what's the

4       meaning of the phrase has not progressed far enough?

5       That connotes that there was a target that the AREVA

6       folks should have known about and just did not get the

7       work done.

8            A.   I'm still not communicating well.  This expert

9       panel never looked at the contract.  So to imply that

10       they made a conclusion relative to a contractual

11       requirement is impossible.  They were comparing the

12       license application to the NRC standards.  They didn't

13       know what was in the contract.  So this expert panel was

14       not saying that AREVA didn't meet a contractual

15       requirement?  They never read the contract.  They were

16       reading with what's today's standard for the licensed

17       application, and they said you're not meeting it.

18            Q.   My question wasn't as to the contract, it was

19       to the -- that AREVA, from what the expert panel is

20       saying in this document here, is AREVA had some

21       expectations about the completeness of their work that

22       they did not meet.

23            A.   I don't think AREVA had that expectation.

24       That is where the root cause comes in.  I don't think

25       AREVA had the expertise to know the depth of detail

FLORIDA PUBLIC SERVICE COMMISSION

472

1       required.  The expert panel came in and said to the

2       point of that apparent cause where we talked about

3       inexperienced engineers, is that they did not have, as

4       we discussed before, they had never submitted one, and,

5       oh, by the way, they hadn't submitted one lately.  And

6       with the lack of that knowledge, they didn't know where

7       the bar was.  The contract was written to a lower bar

8       than what is required today, so here is what we did.  We

9       took a step back.  We said you are going to meet the

10       contract requirements and you're going to meet it on

11       your dime.

12                 Now, we are both recognize that that scope is

13       much higher, that bar requires a much more extensive

14       technical review.  In fact, now it includes the EC

15       development for some of these modifications, and now we

16       are going to have to go forth and develop those ECs,

17       develop that technical rigor prior to submittal.  All of

18       this led to the conclusion that I'm not going to submit

19       this EPU LAR too early.  I want to make sure I

20       understand the standards at the time that I submit it,

21       and I'm going to have the depth of detail so that it

22       isn't kicked back like the other licensees had to face.

23                 MR. REHWINKEL:  Well, I can stop at this

24       point.  I have some other questions about this adverse

25       condition.

FLORIDA PUBLIC SERVICE COMMISSION

473

1                 CHAIRMAN ARGENZIANO:  Okay.  Why don't we do

2       this.  Commissioner Skop had a question, and then I

3       think we are going to go into recess until tomorrow

4       morning.

5                 Commissioner Skop.

6                 COMMISSIONER SKOP:  Thank you, Madam Chair.

7                 My question is not to the witness, it's for

8       planning purposes, so if this is the appropriate time.

9                 CHAIRMAN ARGENZIANO:  Okay.  Then let's do

10       this.  I think Commissioner Graham had a question to the

11       witness or to Mr. Rehwinkel.

12                 Commissioner Graham.

13                 COMMISSIONER GRAHAM:  Thank you through the

14       Chair.  Actually, I think I'm just trying to understand.

15                 THE WITNESS:  Yes, sir.

16                 COMMISSIONER GRAHAM:  The shortfall here was

17       the contract you initially had with AREVA didn't hold

18       them -- you said it was to a lower standard.  So had you

19       sat down with the expert panel prior to the writing of

20       the contract with AREVA, maybe you would have known

21       where that standard should have been and then drafted a

22       contract off of that.

23                 THE WITNESS:  In a perfect world, yes.

24       Unfortunately, those lessons were actually learned -- in

25       fact, Mr. Rehwinkel didn't point it out; I could have.

FLORIDA PUBLIC SERVICE COMMISSION

474

1       On an earlier document we talked about Point Beach.

2       Point Beach is where we learned a lot of this, and that

3       was an application that was received in 2009.  So,

4       unfortunately, at the time this contract was written,

5       Ginna was the right standard, but while the work was

6       progressing that standard moved.

7                 COMMISSIONER GRAHAM:  But with AREVA, when

8       they first came back to you, they didn't hit the

9       standard that you originally contracted with, which

10       was --

11                 THE WITNESS:  No, they did not.

12                 COMMISSIONER GRAHAM:  -- already a low

13       standard, but they didn't hit that standard that you

14       contracted.  You held their feet to the fire.  They

15       brought the work up to the standard that you had

16       contracted, and then the expert panel told you you still

17       don't want to go forward, but that it's because you

18       didn't go far enough.

19                 THE WITNESS:  Yes, that's correct.  They said

20       that that -- once again, they didn't review the

21       contract.  We wrote the contract based on the scope of

22       work of Ginna.  As they were working through that

23       contract, as I explained, the standard moved.

24                 COMMISSIONER GRAHAM:  Yes.

25                 THE WITNESS:  And it moved fast and far.

FLORIDA PUBLIC SERVICE COMMISSION

475

1       There is a number of EPU LAR submittals that had to be

2       withdrawn in this time frame because the NRC standards

3       were moving fast.  So when they delivered the product,

4       you're right, I wasn't happy.  And we were disappointed

5       both in AREVA and our own performance to allow them to

6       deliver something that didn't meet the contract.  We

7       held their feet to the fire.  They performed the work

8       back under their dime, and they were able to meet that

9       original standard.

10                 Now, since we learned, mind you, in that time

11       frame from the expert panel, and we started looking even

12       better, even more closely with the ongoing licensing

13       activities, we said, okay, we're going to have to add

14       some money to this contract, add some expenses

15       associated with the LAR, because this standard is higher

16       than that original contract recognized.  And that's what

17       we have been doing since.

18                 COMMISSIONER GRAHAM:  So there is no fault

19       here, it's just a moving target.

20                 THE WITNESS:  I don't want to dissuade.  I was

21       not happy that they didn't meet that contract.  So there

22       was fault there.

23                 COMMISSIONER GRAHAM:  I mean, but they fixed

24       that.

25                 THE WITNESS:  They fixed that, and they fixed

FLORIDA PUBLIC SERVICE COMMISSION

476

1       it on their dime.  I was a little disappointed my team

2       didn't notice it earlier.  We had the expert panel in

3       place to be able to catch this kind of mistake, but I

4       was disappointed, quite frankly, that it got to that

5       point.  But from a cost standpoint, it didn't cause any

6       increased cost.  It was just a matter of being a little

7       upset at my vendor and upset at my own staff for

8       allowing that to happen.

9                 COMMISSIONER GRAHAM:  Okay.  I just wanted to

10       make sure I understood it.

11                 THE WITNESS:  Yes, sir.

12                 CHAIRMAN ARGENZIANO:  Thank you.

13                 Commissioner Skop.

14                 COMMISSIONER SKOP:  Thank you, Madam Chair.

15       And, again, this is just related to planning purposes,

16       so if it is the appropriate time.

17                 CHAIRMAN ARGENZIANO:  It's the appropriate

18       time.

19                 COMMISSIONER SKOP:  Okay.  And relating to

20       planning purposes related to the FPL case, which, again,

21       we are going to take up at some future point in time

22       when Progress' case in chief is over, I'd like to have

23       the opportunity, based on further reflection, to ask

24       Mr. Olivera some constructive questions on behalf of his

25       company.  And I know Mr. Olivera is not listed on the

FLORIDA PUBLIC SERVICE COMMISSION

477

1       order of witnesses, and I don't expect that he would

2       sponsor testimony.  However, in light of recent events,

3       I do have some questions that I think it would be

4       constructive on behalf of the Commission for me to ask.

5                 And I would perhaps ask our staff to inquire

6       with FPL's counsel, I don't know if they are still here,

7       whether Mr. Olivera would perhaps make himself

8       available.  And if not, we do have subpoena power under

9       Florida Statutes if we need to go there.  But I just

10       would look to our staff to address that concern.

11                 MS. HELTON:  I see Ms. Cano is in the

12       audience.  If I were Ms. Cano, I probably would not want

13       to address this question right now without consulting

14       with her management.  So why don't we approach it this

15       way, Madam Chairman, if it is okay with you and

16       Commissioner Skop.  Why don't we talk to Power and Light

17       and see what their response is and then go from there.

18       I would rather not say anything further than that right

19       now.

20                 CHAIRMAN ARGENZIANO:  Thank you.

21                 Commissioner Skop.

22                 COMMISSIONER SKOP:  And thank you, Madam

23       Chair.  And, again, I think that, again, staff is able

24       to have conversations that I can't have directly, but if

25       he is available, I do have a few questions that I would

FLORIDA PUBLIC SERVICE COMMISSION

478

1       like to have the opportunity to ask if that would be

2       amenable.  And if not, I guess we can look at it from a

3       different perspective.  But I think that addresses my

4       concerns.  And, again, I do have some follow-up

5       questions for Mr. Franke tomorrow when the intervenors

6       are done.

7                 CHAIRMAN ARGENZIANO:  Okay.  We can do that.

8       Let's do this, let's make sure that staff secures all

9       the confidential --

10                 COMMISSIONER EDGAR:  Can I ask a question?

11                 CHAIRMAN ARGENZIANO:  Sure.

12                 COMMISSIONER EDGAR:  I just want to make sure

13       I understand.  Commissioner Skop, are you telling us

14       that you have questions during the FPL portion of this

15       proceeding, not the Progress portion, that none of the

16       witnesses that are on the list to appear before us would

17       be able to address?

18                 COMMISSIONER SKOP:  Based on the list of

19       witnesses, it's my belief that they would not be able to

20       answer the questions on behalf of the company in the

21       manner in which I would expect to get answers.

22                 COMMISSIONER EDGAR:  And I am just trying,

23       again, for planning purposes trying to think through the

24       next few days, and it is --

25                 COMMISSIONER SKOP:  Well, I think, just to be

FLORIDA PUBLIC SERVICE COMMISSION

479

1       clear, again, the length of today's proceeding and the

2       number of witnesses, it's going to be fluid.  What my

3       intent was is to provide as much advance notice as

4       possible, given recent events have made things, you

5       know, kind of fluid.  But, again, if our staff could

6       pursue that, you know, certainly I'd like the

7       opportunity to ask those questions.  And, you know, as

8       far that goes I think that is my perspective to ask

9       them.  Again, he has not sponsored testimony nor do I

10       expect him to sponsor testimony.  But on behalf of his

11       company, I do have some questions that I'd like to hear

12       from the -- from him.

13                 COMMISSIONER EDGAR:  And I'm not sure what you

14       mean by recent events, but I will leave it at that.  I

15       don't know what that means, but that's okay.

16                 COMMISSIONER SKOP:  At this point I don't

17       think I need to explain it to you.  I think that at the

18       appropriate time, if he appears, I'll ask my questions

19       and it will be self-evident.

20                 COMMISSIONER EDGAR:  I wasn't finished with my

21       question.  But my question was are we still -- we are

22       still looking at this week for that request, and just

23       again for --

24                 COMMISSIONER SKOP:  I don't know when Progress

25       will finish its case in chief.  Again, Mr. Rehwinkel

FLORIDA PUBLIC SERVICE COMMISSION

480

1       indicated he still probably has probably about 30 more

2       minutes of cross-examination on this witness.  We have

3       other intervenors and we have other witnesses.  But just

4       for planning purposes, if our staff could inquire.  And,

5       again, staff may want to look at some additional hearing

6       dates, given the way that this is moving along.

7                 You know, we had four days scheduled.

8       Hopefully, we will get into the FPL portion before the

9       end of those four days, but I can't predict the future.

10       But, you know, this is contingency planning.  I think it

11       is important that we start looking at additional days.

12       I know we have September 1, 2, and 3 open, and the 8th

13       and 9th.  So we might want to take a look at that.

14                 CHAIRMAN ARGENZIANO:  Okay.  Questions?

15                 MS. HELTON:  Madam Chairman.

16                 COMMISSIONER EDGAR:  Actually, I would have,

17       actually, liked to have not been interrupted while I was

18       trying to pose a question, but I do think I got the

19       answer that I was looking for.  So, thank you.

20                 CHAIRMAN ARGENZIANO:  Okay.

21                 Ms. Helton.

22                 MS. HELTON:  Thank you.

23                 On reflection, it may help in our discussions

24       with Florida Power and Light if we had some idea of what

25       the subject matter was for the questions from

FLORIDA PUBLIC SERVICE COMMISSION

481

1       Commissioner Skop.

2                 CHAIRMAN ARGENZIANO:  I don't know.  I

3       can't --

4                 Commissioner Skop.

5                 MS. HELTON:  And maybe I can add a little bit

6       more to that that might help Commissioner Skop, too.

7                 COMMISSIONER SKOP:  Very well.  Please feel

8       free to do so.

9                 MS. HELTON:  As I understand our ability to

10       call witnesses, Power and Light may have the opportunity

11       to suggest someone who they think might be more

12       appropriate to answer the questions or who might be at a

13       different level who could still answer the questions.

14       And so I think it would help, with respect to our

15       conversations with them, to have an understanding of

16       what the questions are, the scope of the questions, or

17       the subject matter of the questions, so that they feel

18       like there's a valid reason to have the president of the

19       company come to the hearing when he had not planned to

20       do so.

21                 CHAIRMAN ARGENZIANO:  Commissioner Skop.

22                 COMMISSIONER SKOP:  Again, having given it

23       sufficient thought and looking at the list of witnesses,

24       again, I think it is a fair question to ask.  And I'm

25       not so sure that I like the manner in which it has been

FLORIDA PUBLIC SERVICE COMMISSION

482

1       styled, but I think it suffices to say I have asked for

2       Mr. Olivera for a very specific reason.  He is President

3       and Chief Executive Officer of Florida Power and Light.

4       And, again, I think that when we get to their case there

5       is some constructive things that the company has done;

6       there are also some things that they need to answer for,

7       and my constructive questions posed to Mr. Olivera would

8       be concerning the accuracy and the timeliness of

9       information that his company provides to this

10       Commission.

11                 CHAIRMAN ARGENZIANO:  I think it has been

12       stated what the Commissioner would like to do, and we

13       will take it from there.  I guess staff can -- I guess

14       we will find out tomorrow morning.

15                 MS. HELTON:  Yes, ma'am.  Thank you very much.

16                 CHAIRMAN ARGENZIANO:  Thank you.

17                 And what I would like to do is make sure that

18       we secure the confidential packets that we have.  I

19       think that 197 and 196 were not confidential, so we

20       don't have to worry about those two.

21                 And with that we will recess until

22       9:30 tomorrow morning, and be prepared to probably stay

23       late tomorrow.  Later.

24                 Commissioner Graham, I'm sorry.

25                 COMMISSIONER GRAHAM:  Madam Chair, I guess

FLORIDA PUBLIC SERVICE COMMISSION

483

1       since we are on the conversation of Florida Power and

2       Light, are we going to start off with the questions that

3       staff had and then go from there?  Because we may find

4       out that there is enough answers after the questions

5       that staff had to handle most of the things -- other

6       questions that people may have.  So I think that's a

7       great starting point.  If not all the questions are --

8       if not all of the questions are satisfied at that point,

9       we can move forward.  But I think that may be a good

10       place to start.

11                 CHAIRMAN ARGENZIANO:  Commissioner Skop.

12                 COMMISSIONER SKOP:  Thank you.  And thank you,

13       Commissioner Graham.

14                 Again, staff has their questions.  Again, I

15       have some of my own.  Again, FPL has sponsored

16       witnesses, I have technical questions related to the

17       testimony.  I have questions related to issues, live

18       issues before the Commission.

19                 CHAIRMAN ARGENZIANO:  Commissioner Skop, may

20       I?

21                 COMMISSIONER SKOP:  Yes, ma'am.

22                 CHAIRMAN ARGENZIANO:  Go ahead, finish up.  I

23       didn't mean to cut you off.

24                 COMMISSIONER SKOP:  No.  And, again, I just

25       want to be free to ask the questions.  Again, what

FLORIDA PUBLIC SERVICE COMMISSION

484

1       Public Counsel and some of the intervenors have

2       requested is nothing more than tantamount to being a

3       blanket deferral of all issues until a future point in

4       time, and I'll get into that specifically when we

5       discuss the motion that comes before the Commission.

6                 It is not going to be a pleasant discussion.

7       I mean, I have sufficient reasons as to why I should be

8       able to ask my questions and why the Commission has its

9       obligation to conduct a thorough review.  I think

10       Mr. Rehwinkel made that case for me this morning or this

11       afternoon when he specifically stated the provisions

12       that require the Commission to conduct a proceeding and

13       to look at the prudency and project management controls

14       on an annual basis.

15                 So, again, I'm saving that discussion until

16       the appropriate time.  I didn't want to get bogged down

17       in that to the detriment of Progress this morning, but I

18       do have questions.  And I hope I'll have the

19       opportunity --

20                 CHAIRMAN ARGENZIANO:  Well, I think we will

21       wait and see what happens tomorrow.  And if there are

22       further questions, everyone should be entitled to have

23       answers to their questions.

24                 And with that, let's recess until 9:30

25       tomorrow morning.  Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

485

1                 (The hearing adjourned at 5:50 p.m.)

2

3

4

5

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION