1384

1                              BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

DOCKET NO. 100009-EI

3

In the Matter of:

4

NUCLEAR COST RECOVERY CLAUSE.

5       ______________________________/

6

7

8

VOLUME 6

9

Pages 1384 through 1489

10

11              ELECTRONIC VERSIONS OF THIS TRANSCRIPT ARE

A CONVENIENCE COPY ONLY AND ARE NOT

12               THE OFFICIAL TRANSCRIPT OF THE HEARING,

THE .PDF VERSION INCLUDES PREFILED TESTIMONY.

13

PROCEEDINGS:             HEARING

14

COMMISSIONERS

15       PARTICIPATING:           CHAIRMAN NANCY ARGENZIANO

COMMISSIONER LISA POLAK EDGAR

16                                COMMISSIONER NATHAN A. SKOP

COMMISSIONER ART GRAHAM

17                                COMMISSIONER RONALD A. BRISÉ

18       DATE:                    Thursday, August 26, 2010

19       TIME:                    Commenced at 9:30 a.m.

Concluded at 6:09 p.m.

20

PLACE:                   Betty Easley Conference Center

21                                 Room 148

4075 Esplanade Way

22                                Tallahassee, Florida

23       REPORTED BY:             JANE FAUROT, RPR

Official FPSC Reporter

24                                (850) 413-6732

25       APPEARANCES:             (As heretofore noted.)

FLORIDA PUBLIC SERVICE COMMISSION

1385

1

I N D E X

2

3                              WITNESSES

4

NAME:                                        PAGE NO.

5

TERRY O. JONES

6

Questions by Commissioners               1387

7            Cross Examination by Mr. McGlothlin      1421

Cross Examination by Mr. Moyle           1428

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1386

1

EXHIBITS

2

NUMBER:                                     ID.  ADMTD.

3

242       FPL's Responses to               1412

4                 Staff's Fourth PODs

5

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1387

1                         P R O C E E D I N G S

2                 (Transcript follows in sequence from

3       Volume 5.)

4                 CHAIRMAN ARGENZIANO:  Commissioner Skop,

5       you're recognized.

6                 COMMISSIONER SKOP:  Thank you, Madam Chair.

7                 And I just want to pick up where we left off

8       before lunch.  Just one point in passing, and I hate to

9       belabor the point, but I think it will become important

10       because I'm sure it will come up on redirect.

11                 Mr. Jones, the letter that Mr. Anderson signed

12       dated August 23rd, that informed the Commission after

13       the NRC response letter had been posted in the

14       Commission's docket, the FPL letter that was provided to

15       the Commission subsequent to that on the 23rd, did you

16       review that letter before it was sent to the Commission

17       or did Mr. Anderson ask you to review that letter?

18                 THE WITNESS:  Yes, I did.

19                 COMMISSIONER SKOP:  Okay.  And do you have a

20       copy of that letter in front of you?

21                 THE WITNESS:  No, I do not.

22                 COMMISSIONER SKOP:  Okay.  Subject to check,

23       would you concur that that's basically a one paragraph

24       letter?

25                 THE WITNESS:  Yes.  As I recall it's about one

FLORIDA PUBLIC SERVICE COMMISSION

1388

1       paragraph.

2                 COMMISSIONER SKOP:  Is there is any reason why

3       it would take ten days to prepare a one-paragraph letter

4       to notify the Commission of this information?

5                 THE WITNESS:  No, it doesn't take ten days to

6       write a one-paragraph letter.

7                 COMMISSIONER SKOP:  Thank you.  And I won't

8       belabor that point, but I had just anticipated that

9       something might arise, so I thought I would address it

10       before it came up.

11                 I want to turn your attention real quick to

12       the staff audit report and cover a technical issue with

13       you.  And if you could please turn your attention to

14       Page 34 of the staff audit report.

15                 THE WITNESS:  Do I have that report?

16                 CHAIRMAN ARGENZIANO:  Make sure he has a copy.

17                 COMMISSIONER SKOP:  Okay.  Are you with me?

18                 THE WITNESS:  I have the report.

19                 COMMISSIONER SKOP:  If I could ask you to turn

20       to Page 34 of the report where it discusses pressure

21       discrepancies.

22                 MS. HELTON:  Excuse me, Madam Chairman, and

23       Commissioner Skop, if I could just say for purposes of a

24       clear record that that has already been marked as

25       Exhibit Number 77.

FLORIDA PUBLIC SERVICE COMMISSION

1389

1                 CHAIRMAN ARGENZIANO:  Thank you.  Did you

2       ask --

3                 MR. YOUNG:  I'm sorry, Ms. Helton.  I gave

4       Ms. Helton the wrong information.  If you flip the

5       page --

6                 CHAIRMAN ARGENZIANO:  It's not 77.

7                 MR. YOUNG:  No, ma'am.  It's Number 178.

8                 CHAIRMAN ARGENZIANO:  Quite a bit of

9       difference.  Okay, 178.  Thank you.

10                 Commissioner Skop.

11                 COMMISSIONER SKOP:  Thank you, Madam Chair.

12                 Mr. Jones, do you see the passage entitled

13       Pressure Discrepancies on Page 34 of the staff audit

14       report?

15                 THE WITNESS:  Yes, I do.

16                 COMMISSIONER SKOP:  Okay.  And can I ask you

17       to read the first sentence with the exception of the

18       confidential number at the end of that sentence, please?

19                 THE WITNESS:  You want me to read that out

20       loud?

21                 COMMISSIONER SKOP:  Yes, please, with the

22       exception of the confidential.

23                 THE WITNESS:  Okay.  FPL has found

24       discrepancies between the design pressure used for the

25       Siemens turbine upgrade contract and actual plant

FLORIDA PUBLIC SERVICE COMMISSION

1390

1       parameters and estimates a cost to resolve this issue

2       will reach -- and that part is redacted.

3                 COMMISSIONER SKOP:  Okay.  All right.  Would

4       it be correct to understand that what this pertains to

5       is that the steam header pressure or the existing steam

6       header pressure and the turbine inlet pressure, there's

7       a mismatch between the design specification that was

8       specified for the inlet pressure to the turbine?

9                 THE WITNESS:  Yes, Commissioner Skop, if I

10       could explain that.  As you are very much aware,

11       whatever heat is produced from the reactor is

12       transferred through the steam generator and you expect a

13       certain steam generator pressure.  And then from the

14       steam generator you have a number of components between

15       the steam generator and the turbine, and so there is

16       some pressure loss through those components.  And what

17       this is -- and so this is to that issue in that as a

18       part of the early specification for the turbine there

19       are heat rates that are run by Shaw Engineering, basic

20       modeled heat rates that look at the desired reactor

21       output, and then it looks at -- it takes the design

22       basis documents, the original vendor information for the

23       several components to which those vendors have

24       performance specs which would, through engineering

25       analysis, tell you what the pressure loss in that line

FLORIDA PUBLIC SERVICE COMMISSION

1391

1       would be.

2                 So if you picture, you know, a garden hose run

3       really far out into the yard or the street, by the time

4       you get to the end of that there is very little water

5       pressure so to speak.  And so early on in the project,

6       through engineering analysis and through the vendor

7       information for each of those components, there was a

8       pressure drop calculated.  And so based on that, you

9       communicate that early information to Siemens.

10                 The overall project plan is do the engineering

11       analysis on what the performance should be, then go do

12       field testing to verify actual performance.  Following

13       that actual field testing to validate performance, then

14       you go back and finalize your design specification with

15       your turbine supplier, in this case which is Siemens.

16                 In this case, the existing instrumentation and

17       test points at Turkey Point -- Turkey Point is a real,

18       I'm not going to say old, it's an old plant.  And the

19       test points that were needed weren't there, and so there

20       was a modification to add the test points during a

21       refueling outage and then there was testing that was

22       performed throughout the year to verify the actual plant

23       conditions, compared that to the heat rate, which was

24       part of the project plan, and we had about 40 pounds per

25       square inch less than what we had desired.  Which then

FLORIDA PUBLIC SERVICE COMMISSION

1392

1       would cause us to take one of several paths.  We could

2       revise the turbine spec, because the turbine isn't

3       designed yet.  Siemens is waiting for that input.  And

4       so this is a perfect example in a project where there

5       are logic ties.  You must do this before you do that,

6       and you must do this before you do that.  And so Siemens

7       is not allowed to proceed until we've done the in-field

8       verifications, fed that back to Shaw, who did the

9       original heat rate to get that final specification for

10       that turbine.

11                 So with the pressure drop greater, which is an

12       existing plant condition from the original design, we

13       either needed to change the turbine design to

14       accommodate that lower pressure, which would have meant

15       fewer megawatts than what we wanted, or evaluate other

16       alternatives, such as removing those 1960 vintage

17       components and upgrading those components so there would

18       be less line loss and so more of the energy from the

19       reactor could get to the turbine, or increase the

20       average temperature of the reactor coolant system, which

21       would have the same effect as replacing the obsolete

22       components.

23                 So we went through a decision-making process

24       and ultimately -- and we did an economic analysis by our

25       resource planning people, and it was very cost-effective

FLORIDA PUBLIC SERVICE COMMISSION

1393

1       to just replace the obsolete components rather than

2       sacrifice the megawatts.

3                 COMMISSIONER SKOP:  Okay.  With respect to

4       that in terms of the design point or design

5       specification discrepancy, has there been any root cause

6       analysis done to determine who was responsible for

7       specifying the steam inlet pressure versus what the

8       actual header pressure would have been?

9                 THE WITNESS:  No, there was no root cause.  As

10       I said, Commissioner Skop, the project plan starts with

11       the unit heat rate, and that analysis is performed by

12       Shaw.  Shaw doesn't have any in-plant data because the

13       test points don't exist.  So they have to use the vendor

14       specifications for the components.

15                 The vendor specifications for the components

16       that were installed back in the late '60s, and, you

17       know, the plant went on line in '72, those numbers from

18       those original manufacturers would have indicated less

19       of a pressure drop than real conditions.

20                 COMMISSIONER SKOP:  Okay.  And that's my

21       question.  To the extent that the plant is relatively

22       old, and design specifications would have been what they

23       were with the existing equipment, and that equipment may

24       foul or degrade over time causing, you know, additional

25       pressure drop over design specification at the time, was

FLORIDA PUBLIC SERVICE COMMISSION

1394

1       there no cross-check done to actual plant parameters of

2       the steam header pressure?

3                 THE WITNESS:  Oh.  Yes, I understand your

4       question.  The components actually hadn't degraded.

5                 COMMISSIONER SKOP:  Okay.

6                 THE WITNESS:  It's that like for main steam

7       isolation valve, the engineering factors without getting

8       into a lot of detail would assume, say, for sake of

9       argument, a five-pound pressure drop.  Actual measured

10       condition when we install a pressure tap during the

11       outage between that valve and another valve, the

12       measured differential pressure was higher.  So Shaw used

13       the correct design input parameters, but we didn't have

14       a way to field verify that particular point without

15       installing the test taps.

16                 COMMISSIONER SKOP:  Okay.  Well, I think the

17       test tabs would have determined the differential

18       pressure, or at least the pressure drop across any piece

19       of either a valve or fitting, if you would.  And you

20       might have to do that in sequence across the steam

21       header for the main steam valve, the main shutoff

22       valves, or whatever is in there.  I don't want to get

23       into too much technical mumbo-jumbo detail.

24                 THE WITNESS:  Sure.

25                 COMMISSIONER SKOP:  But it seems to me that

FLORIDA PUBLIC SERVICE COMMISSION

1395

1       you know what your steam inlet pressure would be, or

2       steam chest pressure would be, and you know what actual

3       plant parameters currently deliver to the existing

4       turbine.  And it seems to me that that would be the

5       basis for -- notwithstanding the design specification

6       and what FPL would seek to achieve, but you would think

7       somebody would cross reference the design specification

8       data against the actual data which isn't looking at the

9       pressure drop, it's a summation of all those pressure

10       drops at the steam inlet to the turbine -- existing

11       turbine.  Does that kind of make sense?

12                 THE WITNESS:  It definitely makes sense to me.

13       Those are the same questions that I asked is was there

14       any way that we could have got a rough order of

15       magnitude by looking at other plant installed

16       instrumentation.  The critical pressure, as you say, is

17       the inlet pressure to the turbine.  Unfortunately,

18       the -- and so I do know what the steam chest pressure

19       is, it's before the steam gets to the first moving set

20       of blades in the turbine.

21                 If you picture a turbine, it's just a big

22       fancy fan, and you are going to blow steam through the

23       blades and make it spin.  So we are interested in what

24       the pressure of the steam is right before the blades on

25       this turbine.  And that is certainly a parameter that

FLORIDA PUBLIC SERVICE COMMISSION

1396

1       you can walk into the control room and see what that is.

2                 The turbine upgrade and design, however, is

3       changing the turbine control valves.  The turbine

4       control valves at Turkey Point are sequentialed and

5       throttled, and so, therefore, there is a pressure drop

6       across those.  So that current steam chest pressure to

7       me is meaningless at this point.  I can't make a

8       comparison.

9                 However, to your point, though, you know,

10       upstream of that is a steam header pressure to the

11       turbine that is not a calibrated gauge and so it could

12       be off, you know, 20 maybe 30 pounds.  And so it would

13       give you some information.  However, it is not a

14       calibrated gauge.  But to that point, but to that point,

15       the team was on the project timeline to do -- to install

16       the test points and get actual field conditions.

17                 Could they have known earlier?  They could

18       have had an indication earlier that the pressure could

19       have been off by some amount.  They still would have had

20       to install the test ports, and they still would have had

21       to collect all the in field data to validate, which was

22       done toward the end of the year.

23                 COMMISSIONER SKOP:  Okay.  And, again, what I

24       was interested in, and maybe I got a little bit more

25       detail to the steam chest pressure and the throttle

FLORIDA PUBLIC SERVICE COMMISSION

1397

1       valve.  What I was more concerned with is the header

2       pressure right before you go into the turbine controls

3       that would give you some -- at least a critical check

4       and balance on does the design specification match up

5       with actual plant parameters within a range of

6       uncertainty that one could, you know, estimate to check

7       and see.

8                 Because, again, looking at the confidential

9       numbers and the summation of the two numbers that are

10       remaining to be confidential, and without disclosing

11       those numbers, those numbers are not insignificant.

12       There may be some, you know, benefit to replacing aged

13       equipment, but there is still a cost impact as a result

14       of the pressure discrepancies, and somebody -- the

15       ratepayers are going to have to ultimately pay for that

16       unless it's found to be imprudent.

17                 So that's where, I think trying get to the

18       bottom of this new development is at issue.  Sometimes

19       things happen, but it's important, I think, to get a

20       better understanding because the two dollar amounts

21       there are almost as much as it has been requested for

22       the EPU for the 2011 projected cost.  I mean, that is

23       not giving anything away, it is just order of magnitude.

24       So I think that addresses the technical question I had.

25       And I want to go back now to some remaining questions.

FLORIDA PUBLIC SERVICE COMMISSION

1398

1                 THE WITNESS:  Commissioner Skop, could I

2       clarify?

3                 COMMISSIONER SKOP:  You may.

4                 THE WITNESS:  Yes.  It was always a part of

5       the project plan to do the heat rate so that Siemens

6       could start work, you know, preliminary engineering

7       design type work.  It was always part of the project

8       plan to go modify the plant, to install test points so

9       that we could get the detailed accurate information,

10       because that critical parameter needs to be within 12

11       psi.  It can accommodate about a 12-psi margin, and that

12       plant was followed.  I think that everyone was expecting

13       it to just be okay.

14                 Even if they would have discovered it six

15       months earlier, it doesn't change the output.  The

16       output is still either don't replace the components with

17       components that have less pressure drop, and we

18       certainly could do that, and the turbine would be

19       designed at that spec, but you would have lower

20       megawatts.  But the cost associated with those

21       modifications, which the last time I looked for the

22       modifications was around $34 million, is very

23       cost-effective.  It's a positive MPV of about

24       $116 million benefit to our customers to make that

25       modification.  If it would have been a negative MPV, we

FLORIDA PUBLIC SERVICE COMMISSION

1399

1       would have said, no, we are not going to replace those

2       components, those megawatts are too expensive.  Does

3       that make --

4                 COMMISSIONER SKOP:  I think it makes sense.  I

5       think what I'm trying to drive out without, you know,

6       questioning, you know, management action, is that there

7       has been a discrepancy that was identified, and there is

8       costs associated with resolving that issue and also some

9       costs to resolve the differences and change the steam

10       header line-up in terms of the steam isolation valves,

11       main steam pressure valves, whatever is in there going

12       from memory.

13                 But I think my concern would be, and certainly

14       that may have been part of the plan, but, obviously,

15       putting the pressure taps in and determining the actual

16       pressure drop between the respective valves and fittings

17       at some point could that work?  And I'm not trying to

18       armchair quarterback the decision that was made, but I'm

19       just trying to look in totality should that work have

20       been, perhaps, done prior to specifying the design

21       pressure used for the Siemens turbine, or could that

22       have been reserved, or did the turbine contract needed

23       to be, you know, executed and moved forward to preserve

24       the schedule.  But, again, there is a cost impact

25       associated with whatever happened.  And I'll leave it to

FLORIDA PUBLIC SERVICE COMMISSION

1400

1       the intervenors after I'm gone to hash that one out.

2       But I'm just trying to get some visibility into, you

3       know, how did this arise and, you know, what are the

4       costs to remedy the pressure discrepancies that have

5       been found.

6                 THE WITNESS:  Yes, I'd like to explain.

7                 COMMISSIONER SKOP:  Please do.

8                 THE WITNESS:  Okay.  To preserve the megawatt

9       guarantee that we have contractually with Siemens, there

10       are a lot of specific data points that they want

11       collected, so that's part of the driver.  So that's one

12       reason to go install a lot of test ports.  In fact, on

13       Unit 3, this fall outage we'll be installing some test

14       pressure taps inside the Unit 3 condenser.

15                 These particular test points, the plant needed

16       to be shut down, depressurized, and cooled down to

17       install these because they are in the main steam system,

18       which at power is normally 800 psi, as I know you are

19       aware.  The question could the testing have been done

20       like immediately following the outage?  It could have.

21       It wasn't scheduled that way because we didn't need that

22       final input until much further downstream.  Siemens was

23       not ready -- Siemens was not scheduled to go to

24       manufacturing until a certain point.  So the project

25       plan was laid out to this outage do the test points, and

FLORIDA PUBLIC SERVICE COMMISSION

1401

1       then you had this number of months to do the actual

2       in-field measurements, feed it back to Shaw, who did the

3       heat balance.  So I did want to be clear that Shaw

4       didn't make any error.  Their inputs were off of paper

5       and components that were installed in 1970 or whatever

6       may perform exactly as designed, may perform a little

7       different.

8                 And so, therefore, I just want to be clear

9       that it is not added cost.  I could have chose to spend

10       zero dollars, and the components that are currently

11       installed are perfectly fine, and will be there for the

12       next 20 years.  But there was an opportunity for those

13       megawatts with the net present value benefit to our

14       customers, and so it was a business decision.  Now, we

15       could have made that business decision earlier, but at

16       the end of the day it doesn't matter.

17                 COMMISSIONER SKOP:  Okay.  And the reason I

18       ask, Mr. Jones is, again, the pressure discrepancies

19       were identified in this iteration of the staff audit

20       report which is -- let me make sure I'm looking at it,

21       the one that was issued in July 2010.  This was not, I

22       don't believe and I have it in front of me, in last

23       year's report.  So, again, this seems to be an emerging

24       issue.  And I'm not suggesting that Shaw did anything

25       wrong other than rely on the existing, you know,

FLORIDA PUBLIC SERVICE COMMISSION

1402

1       as-built specification given the hardware that was

2       spec'd out for the steam header, but that would not be

3       intuitively obvious to me from reading the summary

4       contained in the staff audit report.  That part is kind

5       of left out.  So I think that is where my line of

6       questioning originates from is, okay, here is an issue,

7       is there a root cause to the issue, and then here is the

8       cost to remedy the issue.

9                 But, certainly, there does seem to be a cost,

10       and I know you said there wasn't because you did the,

11       you know, financial analysis on the net present value

12       requirement.  But the last sentence in Page 34 seems to

13       suggest there is an increase in project costs to resolve

14       the differences.

15                 So, again, I'm not sure, and I'm not sure

16       whether the Commission has been provided with that

17       additional analysis, financial analysis that has been

18       performed to ascertain whether, you know, the various

19       options there.  So, that's the question.  You know, I

20       don't want to get too much into that.  I think you have

21       addressed my concerns.  I will leave it to the

22       intervenors.  But we need to try and get some

23       transparency of what's going on there.  It seems like

24       FPL and the vendors did what they were supposed to do,

25       but relating that back to loss or gain of uprate and

FLORIDA PUBLIC SERVICE COMMISSION

1403

1       generation capability, that's something that the full

2       picture is not there for me, so that's why I asked those

3       specific questions.  And I think we can move on from

4       here on that one, unless you have anything to add on

5       that.

6                 THE WITNESS:  Yes, Commissioner, we did

7       provide to audit staff our detailed white paper that did

8       go back and look at that overall timeline.  It did look

9       at several options, and it is including a

10       decision-making white paper that we wrote and provided

11       to senior management on or about -- the date of the

12       report was March 11th, 2010, when we brought it to

13       conclusion as to whether to modify or not modify.

14                 COMMISSIONER SKOP:  Okay.  And just to follow

15       up on a couple of different lines of question, and then,

16       hopefully, we can wrap this up.  You mentioned that FPL,

17       after it removed the EPU senior management team, started

18       looking at options of self-performing work remaining on

19       the EPU, looking at other EPC contractors, and I think

20       you mentioned High Point as one of them.  And, again, I

21       have confirmed that is not confidential, at least from

22       the redacted information I'm looking at, because I saw

23       the word unredacted.  So I don't think that is a

24       problem.  But ultimately FPL decided not to shift the

25       work to a different EPC contractor, is that correct?

FLORIDA PUBLIC SERVICE COMMISSION

1404

1                 THE WITNESS:  That is correct.  We ultimately

2       decided to retain Bechtel as the EPC.  We decided to

3       take some portions of the work, such as start-up

4       testing, and do that in-house.  And we looked at some

5       specific engineering and gave that to other companies

6       that we thought could do it more efficiently.  But as

7       the overall engineering procurement contractor, we did

8       decide to stay with Bechtel because at the end of the

9       day we thought that the energy and effort to switch

10       horses, if you will, at this point, demobilized Bechtel,

11       mobilized a new EPC was -- any cost/benefit we would get

12       there would negate the cost/benefit that we were looking

13       for.

14                 COMMISSIONER SKOP:  Okay.  And that was my

15       point.  Again, I can try and look if up, but I won't

16       belabor that.  I guess the conclusion in relation to not

17       going towards a new EPC contractor, that it would be

18       cost prohibitive in doing such when you look at those

19       additional ramp-up costs, and termination costs, and all

20       the things that go into that.  So it was

21       more financially driven rather than benefit driven, is

22       that correct?

23                 THE WITNESS:  I'm not sure I understand your

24       question.

25                 COMMISSIONER SKOP:  Okay.  Somewhere in the

FLORIDA PUBLIC SERVICE COMMISSION

1405

1       voluminous record -- again, one of the reasons -- they

2       may be in the Concentric report, but I believe one of

3       the reason why they did not go with an alternate EPC

4       contractor was because it would have been cost

5       prohibitive in terms of gaining any benefit as opposed

6       to staying with the existing contractor at this point,

7       is that correct?  I mean, I can try and look for it real

8       quick, but --

9                 THE WITNESS:  Yes, Commissioner.  In effect,

10       to demobilize Bechtel there would have been costs

11       associated with that, mobilize a second EPC, there would

12       have been costs associated with that, and the disruption

13       to the project, we felt was too great a risk to take.

14                 COMMISSIONER SKOP:  All right.  That resolves

15       that question.  Let's talk real quick about -- you

16       mentioned that you assumed the position of Vice

17       President of Nuclear Power Uprate on or about

18       August 1st, 2009, and prior to that you worked for

19       NextEra, specifically on the Point Beach project, is

20       that correct?  Or one of the -- your Midwest manager

21       type of position.

22                 THE WITNESS:  To clarify if I may, I am an

23       employee of Florida Power and Light Company.  I work for

24       the nuclear fleet.  My assignment was to the affiliate

25       company to which the customers do not pay for that.  I

FLORIDA PUBLIC SERVICE COMMISSION

1406

1       was the vice-president of operations for Midwest.  As

2       far as EPU for that particular plant, that was a project

3       being done for my plant.  I did not have responsibility

4       for the actual project, just the results.

5                 COMMISSIONER SKOP:  And so to be clear, Point

6       Beach is a nuclear unit operated by the unregulated

7       entity which is now, I believe, Next Energy, NextEra

8       Energy Resources, is that correct?

9                 THE WITNESS:  Yes, sir.

10                 COMMISSIONER SKOP:  Okay.  And with respect to

11       Point Beach, do you know what the -- you mentioned in

12       your testimony your reference to LAR.  Do you know what

13       the status of the LAR is for Point Beach at this time?

14                 MR. ANDERSON:  Chairman Argenziano, I would

15       like to be heard very briefly.

16                 CHAIRMAN ARGENZIANO:  Yes.

17                 MR. ANDERSON:  This proceeding involves

18       Florida Power and Light Company's Florida plants.  It

19       does not involve in any respect our sister companies'

20       plants in other parts of the country.

21                 COMMISSIONER SKOP:  Madam Chair, to the

22       objection.

23                 CHAIRMAN ARGENZIANO:  Commissioner Skop.

24                 COMMISSIONER SKOP:  It's relevant.  I'm laying

25       a foundation for my next question.  The status of --

FLORIDA PUBLIC SERVICE COMMISSION

1407

1       merely it is inquiring about the status of the LAR, and

2       just merely ask the witness if he knew of the status of

3       the LAR.  And it's simply a yes or no.  I don't plan

4       to --

5                 MR. ANDERSON:  That's fine.

6                 CHAIRMAN ARGENZIANO:  Okay.

7                 THE WITNESS:  Yes, I know the status of the

8       extended power uprate License Amendment Request for

9       Point Beach.

10                 COMMISSIONER SKOP:  Okay.  And feel free to

11       object.  Can you tell me what that status is?

12                 THE WITNESS:  Yes.  That status is -- it is in

13       the review and approval part of it.  As I mentioned

14       earlier, the NRC's process has an acceptance review

15       which they can take up to two months.  And once they

16       have agreed to accept it, then they get into a much more

17       detailed review for that License Amendment Request, and

18       that is the process that we are in with Point Beach.

19                 COMMISSIONER SKOP:  Okay.  And just a very few

20       remaining questions.  The nuclear division is organized

21       at FPL, but it's intertwined to some degree to the

22       extent that it has the entire fleet, both unregulated

23       reactors and existing reactors under the nuclear

24       division, is that correct?

25                 THE WITNESS:  That is correct.  We operate as

FLORIDA PUBLIC SERVICE COMMISSION

1408

1       a nuclear fleet.

2                 COMMISSIONER SKOP:  Okay.  I guess the

3       question that I would ask is, is the fact that, you

4       know, you have limited resources to accomplish projects,

5       and I think you've mentioned the organizational

6       structure.  It was detailed with great specificity in

7       last year's audit report with the org chart, and we have

8       talked about the management changes.  Is that combined

9       organization -- are there sufficient resources available

10       that allow or don't impact the ability to execute the

11       EPU completion on cost and schedule as it pertains to

12       the regulated units?

13                 Let me reframe my question.  You have the

14       nuclear division which has unregulated and regulated

15       plants as a fleet, okay.  But we have specific issues

16       related to EPU and new construction in Florida, as well

17       as the unregulated entity has their own business

18       segment.  My question is, is that organizational

19       structure as a whole impacting the ability of FPL to

20       execute the EPU completion on cost and schedule?

21                 THE WITNESS:  No, Commissioner.  As far as the

22       other company is concerned, they have their extended

23       power uprate team.  St. Lucie and Turkey Point each have

24       theirs.  There are always resource challenges in any

25       business or any major activity, so we do -- we will

FLORIDA PUBLIC SERVICE COMMISSION

1409

1       supply people, you know, within the fleet to wherever

2       there is a need, and we will properly allocate those

3       costs, and then we will either backfill that position,

4       or we may have some regular employee backfill, or we may

5       use a contractor to substitute.

6                 And we don't just do that within the nuclear

7       fleet.  I have gotten people from our other business

8       units within the company to come on the project either

9       on a project bound basis, temporary basis, and so we do

10       move resources around.  But as with any -- EPU aside,

11       EPU aside, just running the day-to-day business within

12       the nuclear fleet or within our non-nuclear fleet, there

13       is always pressure on resources and challenges with

14       that, but not to the extent that I'm worried about

15       resources being a major risk for the project.

16                 COMMISSIONER SKOP:  Okay.  Thank you.  I'm

17       just -- I am going to need to have you reference a

18       confidential document at this point.  And, staff, the

19       Bates page I'm looking at, this is what has been marked

20       as POD-29.  And the Bates page specifically is 153493 of

21       NCRC-10.  And if we could pass out copies to the witness

22       and the Commissioners, perhaps.

23                 MR. ANDERSON:  Which number was that, again,

24       please?

25                 COMMISSIONER SKOP:  It's what has been marked

FLORIDA PUBLIC SERVICE COMMISSION

1410

1       for identification -- or, actually, it's not marked, but

2       it is POD-29, and the Bates page is FPL 153493 NCR-10.

3                 THE WITNESS:  I'm sorry, Commissioner, could

4       you repeat that number?

5                 COMMISSIONER SKOP:  Yes.  The number -- and,

6       like I say, it's probably going to have to get looked at

7       so everyone can follow along, but it's FPL 153493 is the

8       number I have.

9                 THE WITNESS:  153493.

10                 COMMISSIONER SKOP:  And that's at the top

11       right-hand corner.

12                 And, staff, if I can get a copy of that

13       confidential document after all, because, again, there

14       may be a mismatch between the pages I have and the one

15       you passed out.  So I just want to double-check that I'm

16       on the right page.

17                 MS. HELTON:  Madam Chairman.

18                 CHAIRMAN ARGENZIANO:  Yes.

19                 MS. HELTON:  Just so we can have a clear

20       record, staff is telling me that this has not been given

21       any kind of an exhibit number, and I'm just wondering

22       whether it should be in case it is admitted into the

23       record so that we will have a clear record.

24                 CHAIRMAN ARGENZIANO:  Commissioner Skop?

25                 COMMISSIONER SKOP:  We can mark it for

FLORIDA PUBLIC SERVICE COMMISSION

1411

1       identification.  I don't usually move exhibits, but we

2       need to do what we need to do.

3                 MS. HELTON:  I just think that might be

4       better.

5                 CHAIRMAN ARGENZIANO:  To give it a number.

6                 MS. HELTON:  I think Ms. Bennett would like to

7       do that.

8                 COMMISSIONER SKOP:  All right.  Thank you.

9                 MS. BENNETT:  It's a set of documents in its

10       entirety that we were going ask to be moved into the

11       record, and they are almost all confidential.  It is

12       Document Number 06790-10 in our case management system,

13       and that's all of FPL's responses to Staff's Fourth

14       Production of Documents.  And I believe Commissioner

15       Skop is asking questions on POD Number 29, which

16       consists of several hundred pages.

17                 COMMISSIONER SKOP:  Okay.  And, staff, like I

18       say, because this is being thrown on Commissioners, can

19       we have someone from staff help everyone on the bench

20       get to the page.  Is everyone there?

21                 CHAIRMAN ARGENZIANO:  Okay.

22                 COMMISSIONER SKOP:  Okay.

23                 CHAIRMAN ARGENZIANO:  I think so.

24                 MR. YOUNG:  And, Madam Chairman, for

25       identification purposes, that will be Exhibit Number

FLORIDA PUBLIC SERVICE COMMISSION

1412

1       242.

2                 CHAIRMAN ARGENZIANO:  242.

3                 MR. YOUNG:  Yes, ma'am.

4                 CHAIRMAN ARGENZIANO:  And what did we title

5       it, Commissioner Skop?  What did we call it?

6                 COMMISSIONER SKOP:  Ms. Bennett.  I'd call it

7       Concentric Report, but --

8                 MS. BENNETT:  The name of the document?

9                 CHAIRMAN ARGENZIANO:  Yes, please.

10                 MS. BENNETT:  Let's short title it FPL's

11       Responses to Fourth PODs, Staff's Fourth PODs.

12                 CHAIRMAN ARGENZIANO:  Thank you.

13                 (Exhibit 242 marked for identification.)

14                 CHAIRMAN ARGENZIANO:  You're recognized.

15                 COMMISSIONER SKOP:  Thank you, Madam Chair.

16                 At the beginning of that document, if we go

17       seven pages in, that should be that Bates number,

18       because the bottom of the page is numbered Page 7 of 23.

19                 CHAIRMAN ARGENZIANO:  Okay.

20                 COMMISSIONER SKOP:  Okay.  Mr. Jones, are you

21       at that page, which is Bates mark stamped FPL 153493?

22                 THE WITNESS:  Yes, I am.

23                 COMMISSIONER SKOP:  And do you see the deleted

24       comment at the top right of that page?

25                 THE WITNESS:  Yes, I do.

FLORIDA PUBLIC SERVICE COMMISSION

1413

1                 COMMISSIONER SKOP:  Okay.  With respect to

2       that comment in my prior line of questioning regarding

3       whether there was sufficient level of effort dedicated

4       to ensuring that FPL's ability to execute the FPL EPU

5       effort on cost and schedule, should that comment factor

6       in that analysis, given the extent of, for lack of a

7       better word, time that was dedicated within the scope of

8       that comment without getting into too much detail?  If

9       you read the comment, I think it should be somewhat

10       evident where I'm going with that.

11                 THE WITNESS:  Yes, I've read the comment.  I

12       don't know -- I can't speak to what portion of the team

13       was involved in the activity that's referenced here and

14       what the impact was.  In other words, it's not clear if

15       we're talking an entire group of people or some portion

16       of the team, and so I can't draw any conclusion from

17       that, that comment.

18                 COMMISSIONER SKOP:  All right.  Well, let me

19       try and help home in on the point that concerns me.  The

20       first sentence, obviously that is going to address the

21       location.  The second sentence addresses the team, the

22       time, and, I guess, perhaps the location.  And then the

23       remaining portion of that addresses what occurred

24       subsequent to that.  And I guess my -- where I'm going

25       with this in the line of my previous question is this

FLORIDA PUBLIC SERVICE COMMISSION

1414

1       occurred shortly before the July 25th type meeting and

2       probably at the same time that all this, you know, cost

3       data for the Florida based proceedings would have been

4       prepared and testimony would have been filed.  So that

5       is kind of where I'm getting to on that.

6                 THE WITNESS:  Yes, I understand.  And I

7       understand the location.  In regard to the second

8       sentence, I don't know if that's the entire team, a

9       portion of the team.  The team I do know at that time

10       was quite large, and so I cannot offer what, if any,

11       impact that had on the Florida project.  There's just

12       not enough information to know.

13                 I would tell you that it's not unusual.  In

14       fact, it's more the norm in our nuclear fleet that when

15       we have a refueling outage, say, at St. Lucie, that a

16       good portion of our staff will go and provide additional

17       oversight and monitoring at St. Lucie.  That doesn't

18       mean they stop everything they are doing, but it means

19       they do spend a portion of their day evaluating

20       performance and assisting during a refueling outage.

21       And so this statement, it doesn't go to what type of

22       effort this was.

23                 COMMISSIONER SKOP:  Thank you.  Two follow-up

24       questions and then one small line of questioning, and I

25       think we will be done.  This is a draft copy of the

FLORIDA PUBLIC SERVICE COMMISSION

1415

1       Concentric report or what ultimately became the

2       Concentric report, and enclosed as part of the

3       Concentric report was the employee letter.  The question

4       that I have is were you provided with a copy of the

5       employee letter that was sent to Mr. Hay?

6                 THE WITNESS:  I read a copy of the employee

7       concern letter.  I don't recall exactly when that was.

8       I was interviewed as a part of the Concentric

9       investigation, and I just don't specifically recall if

10       it was at that particular date or after that I saw the

11       letter.  But it is -- as you mentioned, it is an

12       attachment to the report.

13                 COMMISSIONER SKOP:  Okay.  And with respect to

14       the report which was prepared at FPL's direction by

15       Concentric in an independent report, were you asked to

16       review any drafts of this report?

17                 THE WITNESS:  Yes, I did review drafts of the

18       Concentric report, and I provided my verbal comments,

19       feedback to the Concentric report in regards to things

20       such as timeline or facts in the report.

21                 COMMISSIONER SKOP:  Okay.  And if I could ask

22       you to turn to the first page.  Actually, let me get the

23       right Bates number page, that would probably be the best

24       way to go about this.  I may have to shift documents on

25       us.

FLORIDA PUBLIC SERVICE COMMISSION

1416

1                 Ms. Bennett, if you could help me out.  I'm

2       looking at the same confidential document, POD-29, and

3       the page is Bates Page FPL 153197.  Let me see if that's

4       in the same grouping.  I think that may be actually in a

5       different document, so if you could help everyone get to

6       that.  This is -- right, that's the page we are all

7       looking for.  So if we can get the witness a copy and

8       the Commissioners.

9                 (Inaudible comment; microphone off.)

10                 Yes, 153197.  I believe it is the first page

11       of a separate document in that stack they gave you with

12       a big green comment box.  Okay.  Is everyone there?

13                 All right.  Mr. Jones, if I could ask you to

14       review what has been marked for identification as

15       Exhibit Number 242, Bates Page FPL 153197, and the

16       comment at the top right corner of this document.

17                 MR. ANDERSON:  We are still catching up with

18       you over here for a moment.

19                 CHAIRMAN ARGENZIANO:  Let's make sure

20       everybody is caught up before we move on.  If you will

21       just indicate when you are ready.

22                 MR. ANDERSON:  We're there now.  Thank you for

23       the help.

24                 COMMISSIONER SKOP:  And, Mr. Jones, have you

25       had an opportunity to review Bates Page FPL 153197,

FLORIDA PUBLIC SERVICE COMMISSION

1417

1       which is Page 1 of 20 of that document?

2                 THE WITNESS:  Yes, I have.

3                 COMMISSIONER SKOP:  Okay.  In a prior line of

4       questioning we discussed the Executive Steering

5       Committee meeting that was held on or about July 25th,

6       2009, and I asked you a question as to who may have

7       requested that meeting.

8                 THE WITNESS:  Yes.

9                 COMMISSIONER SKOP:  Does that comment give

10       some clarity to who may have requested that meeting and

11       the line-by-line review that we discussed?

12                 THE WITNESS:  That comment makes a statement

13       as to who requested the line-by-line.

14                 COMMISSIONER SKOP:  Okay.  And you stated that

15       that person, which I believe you previously testified

16       was the president and chief operating officer of FPL

17       Group attended the meeting on July 25th, 2009, is that

18       correct?

19                 THE WITNESS:  That is correct.

20                 COMMISSIONER SKOP:  Okay.  And I don't believe

21       that name is confidential based on my ruling and the

22       fact that there is no protective order or challenge to

23       the ruling on that.  This document is confidential, but,

24       however, the name of a corporate officer of FPL Group, I

25       don't believe, is confidential, so I would ask if you

FLORIDA PUBLIC SERVICE COMMISSION

1418

1       could name that individual.

2                 THE WITNESS:  The President and Chief

3       Operating Office of NextEra.

4                 COMMISSIONER SKOP:  At the time it would have

5       been FPL Group, though.

6                 THE WITNESS:  It would have been FPL Group at

7       the time.

8                 COMMISSIONER SKOP:  Okay.  So could you please

9       identify that individual, please?

10                 THE WITNESS:  That individual is James Robo.

11                 COMMISSIONER SKOP:  All right.  Thank you.

12       And just one final question that I have.  Just in

13       summary, I could ask the court reporter to read back the

14       transcript, and I would rather avoid doing that, but I'm

15       trying to also anticipate what might be an objection

16       from Mr. Anderson.  But just to be clear, on the

17       July 25th, 2009, Executive Steering Committee meeting,

18       at which point a line-by-line financial review of the

19       FPL EPUs was conducted, I believe it was your testimony

20       that Mr. Olivera attended that meeting and that Mr. Robo

21       attended that meeting from FPL Group.

22                 Actually, let me reframe that.  That Mr.

23       Olivera as President of Florida Power and Light attended

24       that meeting and that Mr. Robo as President and Chief

25       Operating Officer of FPL Group at that time attended the

FLORIDA PUBLIC SERVICE COMMISSION

1419

1       meeting on the 25th to have that line-by-line budget

2       discussion, is that correct?

3                 THE WITNESS:  Yes, among others.

4                 COMMISSIONER SKOP:  Okay.  And you also

5       attended that meeting?

6                 THE WITNESS:  Yes, I did.

7                 COMMISSIONER SKOP:  All right.  Very well.

8                 Madam Chair, at this point I don't believe I

9       have any additional questions.  Let me just double and

10       triple check here.  I don't believe I have any

11       additional questions at this point for Mr. Jones.

12       However, I would reserve my right to ask additional

13       questions if we get into an evidentiary hearing posture.

14       Thank you.

15                 CHAIRMAN ARGENZIANO:  Thank you.

16                 Commissioners, I think I have a question, and

17       stop me if it's something that shouldn't be asked.  I'm

18       sure you will.  The Concentric report, I guess it goes

19       through periods of change and edits that occur, and

20       anywhere else there is edits to either mistakes, or

21       grammar, or technical terms, or whatever.  Has it

22       changed substantially from its initial --

23                 THE WITNESS:  Madam Chairman, prior to this

24       hearing, I was shown the stacks of drafts for the

25       Concentric report.  Prior to being shown that, just

FLORIDA PUBLIC SERVICE COMMISSION

1420

1       prior to the hearing, I had no knowledge of how many

2       drafts there were.  I know that I reviewed at least two

3       and provided my verbal comments and feedback on that

4       report, but I can't speak to the number of changes and

5       whether they were all editorial, or context, or such.  I

6       would defer that to the author of the report, John Reed.

7                 CHAIRMAN ARGENZIANO:  Okay.

8                 COMMISSIONER SKOP:  May I ask a brief follow

9       up on that?

10                 CHAIRMAN ARGENZIANO:  Commissioner Skop.

11                 COMMISSIONER SKOP:  Thank you.

12                 Mr. Jones, if this was an independent effort,

13       then how can independence be maintained if FPL

14       management is offering its comments and suggestions to

15       the independent investigation report?  I don't get to --

16       as an example, I don't get to do that with our staff

17       audit report.

18                 THE WITNESS:  Well, we have a number of

19       independent or internal reports that we commission.  It

20       could be, you know, human resources and those people

21       that have a need to know or are close to the issues are

22       asked to verify the facts or time line is correct.  They

23       are asked for the feedback.  At the end of the day, it

24       is up to the investigating entity to make the final

25       decision on their report.  I do not provide any written

FLORIDA PUBLIC SERVICE COMMISSION

1421

1       comments.  I do not provide any electronic editing.  I

2       just provide my perspective on tone and perspective and

3       whether or not there was any technical errors in the

4       drafts that I reviewed.

5                 COMMISSIONER SKOP:  Thank you.

6                 CHAIRMAN ARGENZIANO:  Thank you.  And,

7       Mr. Jones, you indicated that Mr. Reed would be the

8       person to ask about maybe track changes and the

9       differences.

10                 THE WITNESS:  Yes, Madam Chair.

11                 CHAIRMAN ARGENZIANO:  Thank you.  Are we done

12       with this witness?

13                 MR. YOUNG:  No, Madam Chair, I think FIPUG

14       might have some questions.

15                 CHAIRMAN ARGENZIANO:  Oh, I'm sorry, yes.  I

16       forgot where we were.

17                 MR. McGLOTHLIN:  I just have one follow-up

18       question.

19                          CROSS EXAMINATION

20       BY MR. McGLOTHLIN:

21            Q.   Sir, you said earlier that the uprate project

22       had progressed from very little engineering to about

23       20 percent engineering at this point, is that correct?

24            A.   About 19 to 20 percent of the total number of

25       modifications that are currently identified are

FLORIDA PUBLIC SERVICE COMMISSION

1422

1       complete.  There may be additional modifications that

2       will be identified through the LAR engineering analysis

3       process, and based on the NRC's review, as well as there

4       could be additional modifications identified as a part

5       of the design engineering.  And then one other source is

6       similar to when you are doing a little remodeling in

7       your house, and you were going to do a simple thing like

8       move the stove, and you discover that the conduit is in

9       a different spot than what you expected and you're in

10       the middle of a modification.  You may have to make

11       another modification to be able to complete the original

12       intended modification.

13            Q.   Now, your Direct Testimony also states that

14       the nonbinding estimate is the term that you used, has

15       increased to something like $2.3 billion for all of the

16       uprate projects, is that correct?

17            A.   For the feasibility analysis, we used -- it is

18       2.050 to 2.3 billion.  The feasibility analysis used the

19       upper end of that range.  My forecast range for

20       everything that I had identified as modifications, the

21       Bechtel resource ramp, FPL ramp, as well as the known

22       modifications at the time were at the low end of that

23       range.

24            Q.   You have also used a term level of certainty.

25       What level of certainty do you attach to this latest

FLORIDA PUBLIC SERVICE COMMISSION

1423

1       nonbinding effort?

2            A.   P50.

3            Q.   Say again?

4            A.   P50.

5            Q.   What's that?

6            A.   P50 means that there is an equal probability

7       of it going up as there is of it going down.

8            Q.   And there are any parameters in terms of how

9       far up or how far down that attach to P50?

10            A.   I think it's important to look at the trend

11       and the rate at which you are identifying issues and the

12       magnitude of which you are identifying issues.  That

13       doesn't mean that you wouldn't have a discovery through

14       testing, as we did for the steam pressure where you

15       would need to do a business case on whether to proceed

16       or not.  But it's more important to look at the trend of

17       discovery than, you know, just a subjective, gee, it

18       could go here or go there.

19                 Dr. Sim will report in detail on the

20       feasibility.  I do know that the needs filing that the

21       present value for the customers was around 347 million.

22       And I do know that for 2010, using the upper end of the

23       2.3 billion and the 450 megawatts, that the present

24       value is now over a billion for the customers.  But, of

25       course, there are many different factors that go into

FLORIDA PUBLIC SERVICE COMMISSION

1424

1       that feasibility, and Dr. Sim is best suited to explain

2       that.

3            Q.   Well, my question is limited to capital costs,

4       the price tag of completing units.  And you have used

5       the term P50, which means equal probability of

6       increasing or decreasing, but you also said look at the

7       trend.  Now, compared to the nonbinding estimate that

8       was presented a year ago, and using the upper end of

9       $2.3 billion, that is an increase of about $500 million,

10       is it not?

11            A.   Could you restate the question?

12            Q.   Comparing the nonbinding estimate that has

13       been presented in your testimony in this case, comparing

14       that to the high end of that range to the nonbinding

15       estimate that was presented a year ago, that represents

16       an increase of approximately $500 million, does it not?

17            A.   That represents a change in forecast of

18       $500 million if you take the 2.3 and compare it to the

19       needs filing, that's correct.

20            Q.   Now, you also said the important thing is to

21       look at the trend.  Is that the trend we should be

22       concerned with if we are trying to get a handle on what

23       the ultimate price tag of the uprates is going to be?

24            A.   The trend you should be concerned with is the

25       month over month and the types of engineering discovery

FLORIDA PUBLIC SERVICE COMMISSION

1425

1       that we're having through engineering analysis and

2       whether those are significant, medium, or low.  And by

3       that I mean as a part of this project, we have a risk

4       management tool, and so anyone on the project or anyone

5       external to the project if they identify anything that

6       could impact cost, schedule, quality can raise that

7       issue, and we will assign some probability of that

8       occurring.  We'll conceptually assign some dollar amount

9       with that or schedule impact with that, and we'll

10       capture that as a part of the project costs.

11                 So when you are looking at that $2.3 billion

12       figure as the high end, about 158 million of that is

13       what we have identified as risk.  It's things that

14       haven't come to pass, and there's opportunities to

15       mitigate.  Now, you are not going to mitigate the entire

16       $158 million, clearly, and you're not going to mitigate

17       it tomorrow.  Some of those things that are on that risk

18       matrix is I've got to complete the engineering to know

19       what the answer is, or I've got to devise a strategy to

20       deal with it.  So here is a very simple example is the

21       secondary side of the nuclear power plant, which is all

22       steam and water, we refer to as the clean side of the

23       power plant.  It's not part of the primary side.

24                 Well, back in the '80s, the original steam

25       generators for Turkey Point had some very, very tiny

FLORIDA PUBLIC SERVICE COMMISSION

1426

1       leakage, but that resulted in some contamination of the

2       secondary side.  And so what was in the project was a

3       nominal amount of dollars in the event that some of that

4       secondary side components, once we removed it, that we

5       would not be able to free release it or salvage it, that

6       we would have to treat it as radioactive waste.  And so

7       it was identified as a risk and a very conceptual

8       estimate of an additional 11 -- it could be 11 or $13

9       million.  I have a lot of numbers in my head for a $2

10       billion project.

11                 But, nonetheless, that is one that got my

12       attention is we are putting $11 million, and the project

13       is taking a $11 million hit because someone raised the

14       potential that the secondary may have internal

15       contamination and it's going to be very expensive to

16       dispose of.

17                 Now, I can't mitigate that risk overnight, but

18       I have a project plan, and I have someone working on

19       that.  And I don't expect all that to come to fruition.

20       In fact, I suspect it will be a fraction of that cost.

21       But until we get to the end answer, however many months

22       it takes, that $11 million will be there.  So not that

23       entire amount is definitely hardware.  A certain portion

24       of that is allocated for scope not defined, as well as

25       risk, things that people thought this could occur.  I

FLORIDA PUBLIC SERVICE COMMISSION

1427

1       don't have an answer yet.  I may -- that engineering for

2       that is going to occur next year, and then I can give a

3       definitive number for that.

4            Q.   And at the end of that process, your estimate

5       is that the probability of the 2.3 billion being more or

6       less is P50, correct?  Is that what you said earlier?

7            A.   That's what I said earlier.  The key is cost

8       certainty -- cost certainty comes with completing the

9       design engineering.  And as I stated earlier, okay, if

10       we would have done the LAR engineering first, then all

11       the design engineering, then you would spend a year

12       estimating, and then you could provide a project

13       estimate, which is what most people are used to when

14       they get an estimate to have their house reroofed or,

15       you know, a brake job done on their car, so to speak.

16                 And if we were to take that approach, and

17       that's what the Legislature and this Commission had the

18       wisdom to do, is you wouldn't have any benefit, you

19       know, for the customers.  And so you do that in

20       overlapping phases and you sequence it with the

21       refueling outage so that you bring the megawatts sooner.

22       But with that, because the engineering isn't done, you

23       trade off a huge customer benefit for cost uncertainty

24       for the first few years of the project until the

25       engineering is done.  That's the trade-off.

FLORIDA PUBLIC SERVICE COMMISSION

1428

1                 MR. McGLOTHLIN:  That's all I have at this

2       time.

3                 CHAIRMAN ARGENZIANO:  Commissioner Skop.

4                 I'm sorry, Mr. Moyle.

5                 MR. MOYLE:  Thank you, Madam Chairman.  I have

6       just a couple of lines of questions.  One related to

7       this issue of timing and the other related to some of

8       these confidential documents.

9                          CROSS EXAMINATION

10       BY MR. MOYLE:

11            Q.   Good afternoon, sir.  Jon Moyle on behalf of

12       FIPUG.  I just want to make sure I have some timing down

13       properly with respect to the withdrawal of the licensing

14       action that you guys withdrew.  I'm correct that that

15       withdrawal letter -- you sent a letter on August 13th

16       and you got a letter back from the Nuclear Regulatory

17       Commission on August 13th, as well, is that right?

18            A.   Yes, that's correct.

19            Q.   And I think you testified earlier that on

20       August 11th you had a phone call where I assume they

21       kind of delivered the bad news to you, is that right?

22            A.   That is correct.  On August the 11th we had a

23       phone call, and the NRC informed us that there was

24       significantly more detail they were looking for in a

25       couple of areas, and that at that point they didn't

FLORIDA PUBLIC SERVICE COMMISSION

1429

1       think they could accept the License Amendment Request.

2       We provided push back on that for the basis for that and

3       started discussions with senior management.

4            Q.   And, essentially, what the NRC staff told you

5       was you really had two options.  One, you could withdraw

6       your request; or, two, you could not withdraw it and get

7       a denial notice, correct?

8            A.   The process is that if you do not withdraw

9       your License Amendment Request you will get a denial

10       request, that is correct.

11            Q.   Okay.  So, then, I guess sequencing again,

12       your senior management already had a meeting set up on

13       the 12th of August with senior NRC staff, correct?

14            A.   That's correct, and we began the escalation of

15       the issue with our management, and they began the

16       escalation with their management.

17            Q.   And your objective was to try to turn them

18       around, was it not, with respect to their decision

19       either to deny or to require you to withdraw?

20            A.   That is correct.

21            Q.   And I tried to take notes when you were going

22       through this because all of this is happening pretty

23       close to the hearing.  Do you know, wasn't the discovery

24       cutoff date in this hearing on August 12th, do you know

25       that?

FLORIDA PUBLIC SERVICE COMMISSION

1430

1            A.   No, I do not know what the cutoff is for the

2       hearing.

3            Q.   But this decision of the NRC that basically

4       resulted in you withdrawing this application, I think

5       you testified it will have additional cost to the

6       project, correct?

7            A.   That is correct.  And I further explained that

8       the engineering that was done is good engineering.  They

9       are asking for -- to go to another whole level, so that

10       is additional engineering to be done.  So there is a

11       cost associated with that.

12            Q.   And the costs, I think you had used the

13       phrase -- you had said 125 million or 150 million, that

14       you expected there to be increased cost, not of that

15       magnitude, but do you know the order of magnitude of

16       costs that will flow from this decision as we sit here

17       today or is that something that is to be decided as time

18       goes forward?

19            A.   No, I was referring to the amount that we have

20       spent on the License Amendment Request process for our

21       Florida plants is on the order of around $100 million,

22       and we forecast, you know, approximately another 20 or

23       25 million.  The additional engineering to be done here

24       to satisfy the technical reviewers could be on the order

25       of a million or a million and a half.  I would rather

FLORIDA PUBLIC SERVICE COMMISSION

1431

1       not speculate and say this is definitely the number, but

2       it will probably be on that order of magnitude for the

3       engineering analysis.  If there are additional

4       modifications required by the NRC to the spent fuel pool

5       to allow extended power uprate, then that would be

6       additional cost.

7            Q.   Right.  And with respect, I think the two

8       variables were the additional cost and the additional

9       time, correct, that resulted from this withdrawal?

10            A.   Yes, there is the additional engineering

11       analysis --

12            Q.   Right.

13            A.   -- that has not yet been performed.  The time

14       aspect of it is it takes time to do the engineering and

15       that is what you are paying for.  The time variable that

16       I was referring to is the time it will take the NRC to

17       review the resubmittal and whether or not it will have

18       an impact on the scheduled refueling outage, and that is

19       yet to be determined.  However, one of our contingencies

20       is to perform all the modifications and do the power

21       ascension on line, which we call that an

22       on-line implementation which we have done before.

23                 The other impact, again, since the rules are

24       changing, the staff interim guidance on spent fuel pool

25       criticality just came out last night, or we just got a

FLORIDA PUBLIC SERVICE COMMISSION

1432

1       copy of it last night or today, I was informed.  And

2       it's just going to be going on the public register for

3       comment.  That's going to be the standard that we are

4       going to have to live to, and that could require

5       physical modifications to the existing spent fuel pools

6       at Turkey Point and St. Lucie.  And until we complete

7       that analysis, I cannot tell you the extent of that

8       physical modification.

9            Q.   All right.  Your testimony in this case,

10       there's an Issue Number 22 that says, and I quote, what

11       system and jurisdictional amount should the Commission

12       approve as FPL's reasonable actual/estimated 2010 cost

13       and estimated true-up amounts for the extended power

14       uprate project.  Your testimony speaks to that issue,

15       correct?  Yes/no.

16            A.   Yes.

17            Q.   Okay.  And are you aware that Public Counsel's

18       position, which FIPUG agreed with, was that OPC agrees

19       with staff's proposal to conduct a more detailed

20       examination of the costs in a separate docket.  You're

21       aware that that's the position of FIPUG and OPC with

22       respect to that issue?

23            A.   No, I'm not aware of what your position is.

24            Q.   The fact that there could be additional cost

25       associated with this withdrawal, wouldn't you agree that

FLORIDA PUBLIC SERVICE COMMISSION

1433

1       allowing the parties the opportunity to dig into this

2       issue further as it develops to understand the magnitude

3       of those costs would be beneficial in determining

4       whether these costs were prudently incurred or

5       imprudently incurred?

6            A.   First, let me speak to the characterization.

7                 MR. MOYLE:  Madam Chairman --

8                 THE WITNESS:  You tied it to the withdrawal.

9                 CHAIRMAN ARGENZIANO:  Hang on one second.

10                 Mr. Moyle.

11                 MR. MOYLE:  You know, I mean, obviously, the

12       Commission rule is the yes/no, and then the explanation.

13       I'm just simply trying to ask a yes/no question --

14                 CHAIRMAN ARGENZIANO:  Okay, but would you --

15                 MR. MOYLE:  -- which is should additional

16       time -- would additional time help ascertain the cost

17       associated with the withdrawal that a future Commission

18       may decide could be prudent or could be imprudent?

19       Would additional time help ascertain those costs?

20                 THE WITNESS:  Yes, additional time would help

21       ascertain those costs.

22       BY MR. MOYLE:

23            Q.   And you were asked a few questions about the

24       Point Beach uprate project, correct?

25            A.   That's correct.

FLORIDA PUBLIC SERVICE COMMISSION

1434

1            Q.   Okay.  Did the Point Beach uprate project also

2       have a withdrawal of a requested licensing action for

3       its extended power uprate efforts?

4            A.   The License Amendment Request with the

5       extended power uprate for Point Beach has not been

6       withdrawn.

7            Q.   Okay.  Throughout the country some of these

8       extended uprate projects have gone forward, correct, and

9       have been completed?

10            A.   Yes, there are a number of extended power

11       uprate projects that have been accomplished in the

12       United States.  The boiling water reactors, there are a

13       large number of those.  As far as pressurized water

14       reactors, in the context of a true extended power

15       uprate, although if you check the NRC website you will

16       see a couple of other listed, but a true extended power

17       uprate has been Ginna.

18            Q.   The other line of questions I have, just

19       briefly.  You have all of these confidential documents

20       in front of you, do you not, that staff identified as an

21       exhibit?  I wanted to direct your attention to FPL Bates

22       stamp document 152887, which is a letter dated

23       February 19th, 2010.

24            A.   Did you say 152887?

25            Q.   Yes, 152887.

FLORIDA PUBLIC SERVICE COMMISSION

1435

1            A.   I'm not there yet.

2            Q.   And 152888.  It's a February 19th, 2010,

3       letter.  And there is actually a cover page associated

4       with it, 152886.  And just tell me when you are there.

5                 COMMISSIONER SKOP:  Mr. Moyle, if I could ask

6       what Bates number is that, because some of the documents

7       we have you have to scroll through them.  Do you have a

8       front cover Bates page and then a subsequent Bates page?

9                 MR. MOYLE:  Yes.  The Bates page on the very

10       first is 152886, and then it's 152887, and then 152888,

11       according to the information I have.

12                 COMMISSIONER SKOP:  That's what I thought it

13       was.

14                 MR. YOUNG:  It's at the bottom of the page,

15       Commissioner.  And, Madam Chairman, it's my

16       understanding that this letter is no longer confidential

17       except for the name of the employee and the position, I

18       think.

19                 MR. ANDERSON:  Yes.  All the names and titles,

20       I believe -- just to be clear, there's a public version

21       of this and there is a nonpublic.  It's just -- we want

22       to be careful how we proceed.

23                 CHAIRMAN ARGENZIANO:  You say all names are

24       confidential and positions.

25                 MR. YOUNG:  Except for the Commission's ruling

FLORIDA PUBLIC SERVICE COMMISSION

1436

1       on the one individual.

2                 COMMISSIONER SKOP:  The one individual,

3       Mr. Jim Robo, who is president and chief operating

4       officer of FPL Group at the time.  Actually, of FPL

5       Group at the time of this letter was withheld from being

6       confidential.

7                 CHAIRMAN ARGENZIANO:  Okay.

8       BY MR. MOYLE:

9            Q.   Just a couple of questions on this letter.

10       The person who signed this letter, are they still with

11       FPL, do you know?

12            A.   No, they are not.

13            Q.   And you were asked questions previously about

14       the change in management related to the EPU project.

15       You talked about succession planning, but the change in

16       management related to the EPU project didn't have

17       anything to do with succession planning, did it?

18            A.   Yes, succession planning does factor into

19       that.  It's part of my development to run a major

20       construction project.  I have been in line operations

21       most of my career.

22            Q.   So counsel for FPL has indicated this letter

23       is declassified or not confidential.  The letter

24       suggests that on the second page that there was trouble

25       with the EPU project.  And it says, quote, the trouble

FLORIDA PUBLIC SERVICE COMMISSION

1437

1       was enough to replace the entire senior project team.

2       Do you disagree with that statement?

3            A.   Yes, I do.

4            Q.   So you were involved and had knowledge of the

5       senior project team and how they were performing?

6            A.   I disagree with that statement in the context

7       that the entire senior project team was replaced, as I

8       testified to earlier.

9            Q.   With respect to any members of that project

10       team that were replaced, was the reason that they were

11       replaced was because of poor performance or trouble with

12       the EPU project?

13            A.   As I mentioned before, the very most senior

14       people associated with that project were solid

15       performers, had been solid performers for decades.  I

16       already testified to the fact that there was a

17       reorganization to take the EPU and separate the EPU from

18       the projects and fuels organization.  That required a

19       division of responsibility.  There were some

20       reassignments and so that's part of the reason was to

21       decentralize it.  Part of the reason was to align skill

22       sets and functions.  Part of the reason was to get

23       different performance and put a different area of focus

24       on the project.

25            Q.   Okay.  The bottom of the first page, 152887,

FLORIDA PUBLIC SERVICE COMMISSION

1438

1       there's a statement, finally, in July of 2009, senior

2       management decided it was time to inform executive

3       managers of the poor condition of EPU, which

4       precipitated the replacement of the entire EPU project

5       senior management team.  I take it from your previous

6       answers that you would take exception with that sentence

7       in this letter, is that right?

8            A.   I'm sorry, I lost the sentence.

9            Q.   It's the second from the last sentence at the

10       bottom of Page 1.  Finally, in July of 2009.

11            A.   I'm with you.  Yes, I do not agree with the

12       characterization that that statement makes.

13            Q.   Do you know the individual who wrote this

14       letter?

15            A.   Yes, I do.

16            Q.   As we sit here today, I take it you question

17       his veracity?

18            A.   No, I don't question his veracity.  I have a

19       difference of opinion in regard to how he characterizes

20       that.

21                 MR. MOYLE:  Okay.  Thank you.  That's all I

22       have.

23                 CHAIRMAN ARGENZIANO:  Commissioner Skop.

24                 COMMISSIONER SKOP:  Thank you, Madam Chair.  A

25       couple of follow-up questions and I will try and make

FLORIDA PUBLIC SERVICE COMMISSION

1439

1       this as brief as possible.

2                 Mr. Jones, if I could direct you back to the

3       same letter that Mr. Moyle asked you to refer to.  And I

4       don't have the Bates page in front of me, but we -- for

5       the sake of discussion, we know what letter we are

6       talking about.  This is the employee letter dated

7       February 19th, 2010, that was directed to Mr. Hay, who

8       is FPL Group Chairman and Chief Executive Officer.  Do

9       you see the first page of the letter?

10                 THE WITNESS:  Yes, I do.

11                 COMMISSIONER SKOP:  The last sentence at the

12       first page, can you please read that last sentence for

13       me?

14                 THE WITNESS:  The last sentence on the first

15       page?

16                 COMMISSIONER SKOP:  Yes, sir, beginning with

17       my.

18                 THE WITNESS:  My project controls group

19       prepared detailed reviews that were presented to, it's

20       redacted, late in July 2009 on the poor condition of

21       EPU.

22                 COMMISSIONER SKOP:  Okay.  And that redaction

23       there is Mr. Jim Robo, who is no longer confidential.

24       So could I ask you to re-read the sentence, noting that

25       that information is no longer redacted, based on my

FLORIDA PUBLIC SERVICE COMMISSION

1440

1       ruling?

2                 THE WITNESS:  My project controls group

3       prepared detailed reviews that were presented to Mr. Jim

4       Robo late in July 2009 on the poor condition of EPU.

5                 COMMISSIONER SKOP:  Okay.  And on the second

6       page of the letter, second paragraph, can you read that

7       paragraph in its entirety, please?

8                 THE WITNESS:  I am concerned about how FPL

9       will report these findings at the upcoming PSC hearings.

10       Any information from EPU other than -- other than which

11       was presented to management last summer will be a

12       manipulation of the truth.  Current reporting for PTN

13       and PSL, meaning Turkey Point and St. Lucie, does not

14       contain information showing there is serious trouble

15       with these projects.  The trouble was enough to replace

16       the entire senior project team.

17                 COMMISSIONER SKOP:  Okay.  And then can you

18       read the first sentence of the next paragraph, please?

19                 THE WITNESS:  Enclosed with this letter are

20       the presentations given to Mr. Robo last July.  If you

21       investigate -- do you want me to read the whole

22       paragraph?

23                 COMMISSIONER SKOP:  No, that's fine.  I think

24       we've covered enough on that.  Notwithstanding the

25       Concentric report, do you have any reason to doubt the

FLORIDA PUBLIC SERVICE COMMISSION

1441

1       validity of these allegations?

2                 THE WITNESS:  Yes, I do.  Going to the second

3       paragraph on Page 2, as I stated earlier, the project

4       forecast that we had and the direction that we had

5       coming out of July 2009 remained within our monthly

6       reports.  Those numbers are generated by the project

7       controls organization and continued that forecast along

8       with the progress we were making on the actions in

9       regards -- and I won't go back through those, but in

10       regards to ongoing activities continue to be reported to

11       the senior execs.

12                 Those same presentations with those forecast

13       numbers were provided to PSC audit -- audit staff as in

14       the normal course of discovery.  In fact, when I learned

15       that -- (REPORTER NOTE:  Redacted confidential words

16       removed) -- was leaving the company, I had a meeting

17       with -- I'm sorry.

18                 COMMISSIONER SKOP:  We made a boo-boo.  So how

19       do we -- can we move to strike that or what do we want

20       to do?

21                 MR. ANDERSON:  We move to strike that, please.

22       It is clearly an inadvertent error.

23                 CHAIRMAN ARGENZIANO:  So moved.

24                 THE WITNESS:  Sorry.  When I learned that this

25       employee was -- he was the -- that's a title.  When I

FLORIDA PUBLIC SERVICE COMMISSION

1442

1       learned this employee was leaving the company, I had a

2       meeting with this employee, and I showed him the

3       executive steering committee presentations that had the

4       forecast numbers in it, as well as the actions that were

5       being taken by the project team.  And then I also showed

6       him the documents that we were providing in discovery

7       that had those same forecast numbers in it.  And he

8       commented to me that, one, he was pleased that I took

9       the time to meet with him, that he was not aware of that

10       information, and that he was glad that that information

11       was being shared with the senior executives and being

12       provided to the PSC staff.

13                 COMMISSIONER SKOP:  All right.  And

14       notwithstanding your difference of opinion with the

15       Concentric report, as identified in your management

16       discussion, Concentric took a different position and

17       indicated that they found the employee -- the

18       allegations in the employer letter and the employee to

19       be credible and that most of the allegations were indeed

20       fact accurate, is that correct, based on the Concentric

21       view of their own independent analysis?

22                 THE WITNESS:  Mr. Skop, it isn't that I

23       disagree with the Concentric report, this employee is a

24       good employee.  He's credible.  He knows what he is

25       doing.  He is a good  -- (REPORTER NOTE: Redacted

FLORIDA PUBLIC SERVICE COMMISSION

1443

1       confidential words removed).  I disagreed with

2       Concentric's conclusion in regard to that number being

3       final, that number being solid, that number being well

4       vetted and ready -- and ready for reporting, no

5       different than the megawatts.  And in that regard --

6                 COMMISSIONER SKOP:  I'm sorry, we'll get to

7       that in a second.  Just to follow up on one page of a

8       question that Mr. Moyle asked with respect to removal of

9       the EPU senior management team.  If you could turn to

10       Page 24 of the staff audit report, and if staff has a

11       number that has been marked for identification yet on

12       that document.

13                 MR. YOUNG:  178.

14                 COMMISSIONER SKOP:  Okay.  So the document is

15       marked for identification as Document 178, which is the

16       staff audit report for Florida Power and Light's project

17       management internal controls for nuclear plant uprate

18       and construction projects.

19                 MR. ANDERSON:  Could I pause for a second?  I

20       noted an inadvertent reference by the witness to a -- to

21       a title.  Could we have the same treatment in relation

22       to that?

23                 CHAIRMAN ARGENZIANO:  Absolutely.

24                 MR. ANDERSON:  Thank you.

25                 CHAIRMAN ARGENZIANO:  Absolutely.

FLORIDA PUBLIC SERVICE COMMISSION

1444

1                 MR. ANDERSON:  Thank you.  And I will just ask

2       that everyone, including our witness, slow down and pay

3       careful, careful attention in relation to that.

4                 COMMISSIONER SKOP:  I certainly did not want

5       that to come out.  Again, the action of that employee

6       was -- you know, again, you want to encourage that type

7       of concern to come forward when it's appropriate to do

8       so.

9                 Mr. Jones, if I could turn your attention to

10       Page 24 of the staff audit report, Commission staff

11       audit report.

12                 THE WITNESS:  I'm there.

13                 COMMISSIONER SKOP:  Okay.  And on that page

14       under Section 3.1.2, it discusses EPU management

15       replacement and restructure.  And in response to a line

16       of questioning from Mr. Moyle, I guess you reached

17       different conclusions as to why the EPU -- or the EPU

18       senior management team was removed.  Can I ask you to

19       read the first paragraph regarding the removal of the

20       EPU senior management team on that page, please?

21                 THE WITNESS:  Excuse me, which paragraph?

22                 COMMISSIONER SKOP:  Okay.  Where it begins

23       removal of the EPU senior management team, can I ask you

24       to read that first paragraph, please?

25                 THE WITNESS:  "In July of 2009, FPL's senior

FLORIDA PUBLIC SERVICE COMMISSION

1445

1       management changed EPU project management teams.  The

2       significance of this event is that FPL's senior

3       management believed the original team was not performing

4       as expected.  Senior management believed that a change

5       in EPU management was necessary to ensure the project

6       quality and forecasted costs were not compromised.

7       FPL's senior management noted," and there is a Footnote

8       3.

9                 COMMISSIONER SKOP:  We can skip the footnote.

10                 THE WITNESS:  Okay.

11                 COMMISSIONER SKOP:  And if you could just keep

12       reading that indented paragraph and then the next

13       sentence after that indented paragraph, please.

14                 THE WITNESS:  "Both previously assigned EPU

15       level managers were no longer involved in the EPU

16       project because FPL Group's Senior Management decided

17       that changes to these leadership positions would enhance

18       FPL's ability to bring the EPU project to successful

19       completion, promote effective succession planning, and

20       talent utilization, improve the quality and timeliness

21       of forecasted project costs."

22                 COMMISSIONER SKOP:  Okay.  And then the next

23       sentence right after that, please.

24                 THE WITNESS:  The next sentence is according

25       to FPL, the original management team had not been

FLORIDA PUBLIC SERVICE COMMISSION

1446

1       aggressive in keeping cost estimates from the EPU

2       contractor under control.  FPL's senior management

3       stated that the original EPU project team was not able

4       to accomplish this.  FPL's senior management further

5       noted --

6                 COMMISSIONER SKOP:  That's fine.

7                 With respect to the indentation part that you

8       previously read, that reference is FPL -- excuse me, FPL

9       Group Senior Management decided, is that correct?

10                 THE WITNESS:  Yes.

11                 COMMISSIONER SKOP:  Okay.  So putting this

12       into perspective, the Executive Steering committee held

13       a line-by-line project review, or line-by-line review of

14       the EPU project on or about July 25th, 2009.  Subsequent

15       to that, according to this staff audit report, FPL Group

16       Senior Management decided to replace the EPU senior

17       management team.  And I guess, as we stated, Mr. Robo,

18       who is Chief Operating Officer, who, as you testified,

19       requested that line-by-line and attended that meeting, I

20       guess it's interesting that the decision to replace the

21       EPU senior management team seems to have been made at

22       the FPL Group level, not the Florida Power and Light

23       level, according to that information.

24                 And I just picked up on that myself, so I

25       thought I would ask you what your personal knowledge may

FLORIDA PUBLIC SERVICE COMMISSION

1447

1       be regarding who made that decision.  And that goes to

2       my previous question about the EPU senior management

3       team seems to be removed immediately after that July

4       25th, 2009, meeting, or somewhere shortly thereafter.

5                 MR. ANDERSON:  Commissioner Skop, I would just

6       ask that the questions more carefully characterize the

7       testimony earlier today.  There was no testimony that

8       the entire team, for example, was removed, et cetera.

9                 COMMISSIONER SKOP:  And that's fine.  It

10       states that -- you know, again, I'm reading what I have

11       before me.  I wasn't there.  I didn't do the staff

12       internal audit.  And, again, I'm not trying to be

13       inflammatory.  I'm trying to have a very constructive

14       discussion.

15                 So, Mr. Anderson, I do appreciate your

16       comment.  So we can couch it in the fact that maybe not

17       every person was removed, but certainly there was an

18       event, and that event was a line-by-line management

19       review at a meeting that was attended by Jim Robo, who

20       was Chief Operating Officer and President of FPL Group

21       at the time.

22                 According to your testimony, Mr. Olivera from

23       Florida Power and Light was there.  You attended the

24       meeting.  And then shortly thereafter, according to this

25       paragraph, FPL Group senior management decided to change

FLORIDA PUBLIC SERVICE COMMISSION

1448

1       the leadership positions that were changed.  So I think

2       that should tighten that up a little bit.

3                 So do you have any personal knowledge of why

4       FPL Group Senior Management would make that decision in

5       lieu of Florida Power and Light management?  Because

6       there seems to be a lot of people involved in this

7       meeting here on July 25th.

8                 THE WITNESS:  Commissioner Skop, as I recall

9       the reorganization was announced prior to that July 25th

10       meeting.  I know I was certainly approached before that

11       July 25th meeting.  And in regards to FPL Group's senior

12       management, I'm not privy to which of the senior

13       executives were involved in any decision-making.  I

14       would like to point out that these two paragraphs are

15       taken from a response that we provided which is -- we

16       provided several paragraphs, and so to just focus in on

17       two could characterize this improperly.

18                 COMMISSIONER SKOP:  Okay.  Very well.  And let

19       me move on on that line.  I think that, obviously, what

20       was important there is the fact that the meeting was

21       held.  It was attended by high level executives from

22       Florida Power and Light and also high level executives

23       from FPL Group, and then there was action taken after

24       that.

25                 But let me get back to my point as to your

FLORIDA PUBLIC SERVICE COMMISSION

1449

1       disagreement with the findings of the Concentric report.

2       And as you previously testified, based upon the

3       line-by-line formal review of the EPU projects that was

4       conducted on July 25th, 2009, there was clear indication

5       that the magnitude of the projected cost estimate had

6       increased substantially, is that correct?

7                 THE WITNESS:  That's correct.  The forecast

8       was significantly higher than the original needs filing.

9                 COMMISSIONER SKOP:  Okay.  And that was known,

10       based on -- that was known by both FPL and FPL Group

11       Executive Management who attended the July 25th, 2009,

12       Executive Steering Committee meeting, is that correct?

13                 THE WITNESS:  Yes, Commissioner, that is

14       correct.  And as I stated, there was clear direction

15       given and clearly opportunities identified to mitigate

16       that.

17                 COMMISSIONER SKOP:  I understand, but I'm

18       talking about the magnitude.

19                 THE WITNESS:  Okay.

20                 COMMISSIONER SKOP:  Again, the end number is

21       going to be what the end number is going to be.  But

22       what I'm trying to get at is that there seemed to be

23       warning flags or key indicators that, you know, caused

24       management to be replaced, and that the cost magnitude

25       of the projected cost estimate had increased

FLORIDA PUBLIC SERVICE COMMISSION

1450

1       substantially.  And that gets back to the point of who

2       knew what when and why was that not disclosed in the

3       testimony.  And so my next question is, since we are on

4       a roll here, if the FPL witness who gave testimony on

5       September 8th, 2009, who attended that meeting on

6       July 25th, knew or should have known that there was a

7       clear indication that the magnitude of the projected

8       cost estimate had increased substantially, and that

9       witness did not amend his prefiled testimony that was

10       given under oath to the Florida Public Service

11       Commission to reflect this material information, then

12       would it stand to reason that the FPL witness testimony

13       was inaccurate and incomplete?

14                 MR. ANDERSON:  I object to the question.  It

15       contains numerous, numerous facts and assumptions not in

16       evidence.  And this is about the third time we have been

17       through all the details in relation to this July

18       meeting.  Mr. Jones has carefully explained the context

19       of all of those numbers and figures.  I believe we have

20       been very patient in relation to the provision of

21       Mr. Jones.  But we are also crossing over into -- you

22       know, I believe the questions are not even questions.

23       We are getting paragraph long statements and

24       characterizations or what could be described as

25       testimony.  And that is not proper questioning either,

FLORIDA PUBLIC SERVICE COMMISSION

1451

1       so we object.

2                 CHAIRMAN ARGENZIANO:  Commissioner Skop, to

3       the objection and can you phrase questions to be

4       questions.

5                 COMMISSIONER SKOP:  Okay.  To the objection,

6       the question goes to the heart of the veracity and

7       accuracy of the information provided to the Florida

8       Public Service Commission by an FPL witness that gave

9       testimony to this Commission under oath.  It requires

10       laying a predicate to determine who knew what when.  And

11       based on that predicate that was the result of the

12       Concentric report, which I think I have clearly

13       established the foundation that not only Jim Robo, who

14       was President and Chief Executive Officer of FPL Group,

15       but Armando Olivera, based on witness testimony,

16       attended that meeting.  The witness before us attended

17       that meeting.  And the witness that gave testimony

18       previously to the Commission, whose name has been

19       redacted, why -- again, I accepted the argument, but I

20       disagree with it.

21                 But the bottom line is we have laid the

22       foundation of who knew what when, so the person that

23       gave the testimony to the Commission knew or should have

24       known based on this witness' testimony that there was

25       clear indication that the magnitude of the projected

FLORIDA PUBLIC SERVICE COMMISSION

1452

1       cost estimate had increased substantially.

2                 So my question, Mr. Anderson, goes to the very

3       heart in the opinion of this witness is that if the FPL

4       witness gave previous testimony, sworn testimony, and

5       knew what he knew or should have known based on that

6       July meeting, then -- and that witness did not amend his

7       prefiled testimony while under oath to reflect this

8       material information, then I ask the witness merely to

9       opine whether it would stand to reason that the FPL

10       witness testimony that was previously given on

11       September 8th, 2009, was inaccurate and incomplete.  I

12       mean it's lengthy, but you have to be lengthy to kind of

13       get there.  I mean, I'm doing this on the fly.

14                 CHAIRMAN ARGENZIANO:  Mr. Anderson.

15                 MR. ANDERSON:  The final question itself is

16       absolutely inappropriate.  It asks for a legal

17       conclusion of an engineering witness.  In addition, the

18       lengthy, lengthy, lengthy prelude and predicate are

19       argumentative and characterizing of one's position.  The

20       arguments that one associates with an advocate honestly

21       and not with a decision-maker.  I am being very careful.

22       I'm trying to --

23                 COMMISSIONER SKOP:  Let me withdraw -- let me

24       withdraw the question and proffer what the --

25                 CHAIRMAN ARGENZIANO:  Okay.  The question is

FLORIDA PUBLIC SERVICE COMMISSION

1453

1       withdrawn, and are you going to ask a question?

2                 COMMISSIONER SKOP:  The problem here is I

3       don't have the witness that gave his testimony, so I

4       can't examine that witness.  That witness, to my

5       understanding, is no longer an employee of Florida Power

6       and Light Company.  The problem is also with, you know,

7       some of the deferral thing that as time goes on and we

8       defer these items, witnesses leave, time fades, memories

9       fade, so I'm at a little bit of a strategic disadvantage

10       here.  But I would respectfully proffer that the

11       question I'm trying to ask the witness of, which he may

12       not have personal knowledge, were to establish whether

13       the testimony given under oath was accurate and complete

14       based upon what should have been known from that

15       July 25th meeting.  And I'll just move on from that

16       point.

17                 I think that is the core of the issue, given

18       the fact that the witness -- the witness before the

19       Commission has indicated and responded that, yes, it was

20       true that there was clear indication that the magnitude

21       of the projected cost estimate had increased

22       substantially and that was known by the people that

23       attended the meeting, including the prior FPL witness on

24       July 25th.  I won't belabor the point.  I will move on

25       to my question.

FLORIDA PUBLIC SERVICE COMMISSION

1454

1                 MR. ANDERSON:  And we'll note the record

2       speaks for itself as to what the witness has said for

3       more than four hours.

4                 COMMISSIONER SKOP:  And for the record, I

5       would also note that you asked the question to the

6       witness as to whether he had any changes to his prefiled

7       testimony at that point.

8                 CHAIRMAN ARGENZIANO:  Let's do this.  Let's

9       take a break and let's do ten minutes.  Thank you.

10                 (Recess.)

11                 CHAIRMAN ARGENZIANO:  Okay.  If everyone will

12       take their seats.  Wait a minute.

13                 (Pause.)

14                 CHAIRMAN ARGENZIANO:  If I go too long, just

15       yell like you did.  That was perfect.  I'm sorry that I

16       had to make you wait that long.  I just kept thinking we

17       were going to get over that hump.

18                 Okay.  I think we're back on, and I want to

19       say something first.  And I know Commissioner Graham had

20       indicated -- if you would just allow me to make a couple

21       of comments first, I would appreciate it, and I will

22       recognize you and then Commissioner Skop.

23                 To the witness, if I could ask you to please,

24       if you are asked a question to answer yes or no.  And if

25       you feel that you must elaborate, I can understand that,

FLORIDA PUBLIC SERVICE COMMISSION

1455

1       and then we'll allow that.  But I think that we will be

2       here until after Christmas if we just continue.  But I

3       understand the necessity sometimes that a yes or no

4       answer is not always the end all.  So please let me

5       know.  But if you could kind of -- if it's possible,

6       please do that.

7                 The other thing I wanted to say, and it may

8       set us on track to where we need to be.  I just wanted

9       to make a comment that I think that Commissioner Skop's

10       subject matter that he was asking is something that I am

11       very interested in also, and I think it's very

12       pertinent.  And I am going to read part of this, and

13       that's why I think it's pertinent.  I'm not going to go

14       to as to whether he is being an advocate or not.  I

15       think it's very difficult.  I didn't hear that.  I think

16       it is very difficult to get to where you want to go

17       sometimes, but I want to read part of the report, and I

18       want to make sure before I read part of that report that

19       it is not confidential except for the names.  Is that

20       correct, and any number amount?  Okay.  I want to read a

21       part of that very quickly and then make a suggestion, if

22       I may.

23                 And it is on -- let me see if I can find the

24       page.  Page 47 of 56.  I'm sorry, Page 41, 41, Page 41

25       where it begins on the bottom, next to the last

FLORIDA PUBLIC SERVICE COMMISSION

1456

1       paragraph.  The Concentric investigation also examined

2       the 2009 Nuclear Cost-Recovery Clause proceedings to

3       evaluate whether information provided to the FPSC during

4       the proceedings was accurate and consistent with the

5       standards expected for testimony before and submissions

6       made to a regulatory agency.  Concentric identified that

7       budget estimate information provided by the

8       vice-president, excuse me, uprates in his May 2009

9       testimony had changed and the change was not discussed

10       in the hearing.  Concentric stated in, I'm sorry,

11       Concentric stated in its report that while Concentric

12       agrees that the new analysis confirmed the conclusions

13       of Mr. Blank's testimony, we believe that -- picking a

14       number, and I'm not going to into that -- or percentage

15       increase in the projected cost of the EPU project should

16       have been discussed in the live testimony on

17       September 8th, 2009.

18                 In an interview with Concentric, FPSC audit

19       staff determined that FPL witnesses are prepared by

20       their attorneys for potential questions that might be

21       asked during the hearing, as most witnesses are.  During

22       the interview, Concentric agreed that Mr. Blank had

23       participated in a line-by-line budget discussion with

24       FPL's executive steering committee in July 2009, and,

25       therefore, understood that the budget information

FLORIDA PUBLIC SERVICE COMMISSION

1457

1       provided in May 2009 was indeed incorrect by the time of

2       the hearing on September 8th, 2009.  Yet when asked by

3       FPL Attorney Anderson, if I ask you the same questions

4       contained in your prefiled direct testimony, would your

5       answers be the same, Mr. Blank answered, yes, they would

6       be.

7                 FPSC audit staff and Concentric agree

8       Mr. Blank knew the budget estimate was being reviewed

9       and likely would change.  In fact, Concentric states in

10       the Martin investigation report on September 9th, 2009,

11       the ESC was presented with a newly revised forecast that

12       further increased the cost -- did you say the numbers

13       were not -- by 104 million total for both sites.  This

14       presentation stated that approximately 30 percent of the

15       total project costs have high certainty.

16                 And the reason I read that because it is

17       pertinent and it is important to find out what happened

18       there.  But can I make the suggestion that possibly this

19       is not the right witness, and perhaps the next witness

20       is the person to ask that question.

21                 COMMISSIONER SKOP:  I think that the

22       information you read, had I been able to find that,

23       would have been able to lay a foundation to ask the

24       witness the question without the objection by Mr.

25       Anderson, but I'll yield.

FLORIDA PUBLIC SERVICE COMMISSION

1458

1                 CHAIRMAN ARGENZIANO:  The question is can we

2       ask that question, would you be satisfied with asking

3       that of the next -- the next gentleman is the man who

4       wrote the report.

5                 Okay.  Then explain, please.  Give me an

6       explanation.

7                 COMMISSIONER SKOP:  I would not.  What I need

8       to do is, instead of a lengthy predicate, I need to

9       tighten it up.  It has been a long day.  But the witness

10       has already testified that there was clear indication

11       that the magnitude of the projected cost estimate had

12       increased substantially.  He answered yes to that

13       question.

14                 The Concentric report indicated, as you

15       stated, that while Concentric agrees that the new --

16       Concentric agrees that they believe that a $300 million,

17       or a 27 percent increase in the projected cost of the

18       EPU project should have been discussed during the live

19       testimony of September 8th, 2009.

20                 So my question to the witness is I know why

21       you disagree with the Concentric report, okay.  And that

22       is on what the final number is going to be.  My question

23       to you, which you have answered yes, is that at that

24       meeting on July 25th there was clear indication that the

25       magnitude of the projected cost estimate had increased

FLORIDA PUBLIC SERVICE COMMISSION

1459

1       substantially.  So based on that foundation, the

2       question I have to you is -- and let me ask one other

3       thing.  The passage that Chairman Argenziano read, is it

4       your understanding from attending that July 25th meeting

5       that that person was in attendance at that meeting, the

6       prior FPL witness?

7                 THE WITNESS:  Yes, that person was in

8       attendance at the meeting.

9                 COMMISSIONER SKOP:  Okay.  So based upon

10       attendance at that meeting and based upon your prior

11       testimony that you just gave, he also would have had a

12       clear indication that the magnitude of the projected

13       cost estimate had increased substantially based upon

14       attending that meeting, is that correct?

15                 THE WITNESS:  Yes, Commissioner, based on

16       being -- not only being in attendance for that meeting,

17       but his team had prepared those numbers and that

18       forecast.  And, also, I want to make sure it's clear

19       that reorganizing the project was announced prior to

20       this meeting.  And the prior witness -- we go through a

21       change management process for an orderly transition, and

22       as I described before, we needed to split the EPU

23       project and the other major capital projects apart, and

24       you have to have people to run both organizations.

25                 Having said that, the prior witness retained

FLORIDA PUBLIC SERVICE COMMISSION

1460

1       the responsibilities for the preparation for the hearing

2       and had access to that information.  I do need to be --

3       I do need to say again that that number was not

4       considered a valid number and there was work to be done

5       to validate that number, and that's where I disagree

6       with Concentric.

7                 And if I could say one other thing.  You asked

8       me a question much earlier in the day about the

9       September 9th presentation and had the forecast changed.

10       And I said, no, the numbers are basically the numbers.

11       And as I look at this passage here, specifically on Page

12       42, and the reference to the $104 million, I want to

13       correct my prior testimony and say the number from July

14       to that time could have changed.  They moved month over

15       month.

16                 The point I was trying to make earlier is that

17       the numbers that go in those presentations come right

18       out of the project controls.  If you could visualize a

19       notebook this thick of spreadsheets that roll up to that

20       number.  That number from July never goes away was what

21       I was trying to attest to in regards to the September

22       9th meeting.  You build on that or you subtract from

23       that.

24                 COMMISSIONER SKOP:  Let me get back to the

25       question before the Commission.  The person whose name

FLORIDA PUBLIC SERVICE COMMISSION

1461

1       is redacted that attended the July 25th, 2009, meeting

2       with you, you just testified by virtue of the fact that

3       the person attended the line-by-line review, that that

4       person would have had a clear indication that the

5       magnitude of the projected cost estimate had increased

6       substantially.  Again, I'm framing my question not into

7       what the ultimate dollar amount will be, but the

8       magnitude and the indicators that the magnitude had

9       increased substantially.  The question I have to you --

10                 MR. ANDERSON:  We object even to that

11       predicate point, because what he just said is I do need

12       to say again that the number was not a valid number.  At

13       every turn, every one of these hypothetical questions

14       which you are asking of this witness is

15       mischaracterizing that vital point.

16                 COMMISSIONER SKOP:  Okay.  Well, again, the

17       witness has testified, and we can have the court

18       reporter read it back, Madam Chair, that by virtue of

19       attending the meeting of July 25th, 2009, and by virtue

20       of the line-by-line discussion, there was a clear

21       indication that the magnitude of the projected cost

22       estimate had increased substantially.  The witness

23       answered that question yes.  I'll be happy to have the

24       court reporter read that back.

25                 The witness also testified that this was known

FLORIDA PUBLIC SERVICE COMMISSION

1462

1       by both FPL and FPL Group Executive Management who

2       attended the July 25th, 2009, Executive Steering

3       Committee meeting.  So I hate to beat this into the

4       thing, but the subtlety here is that they are talking

5       about the actual number.  I'm talking about indicators

6       to say we have got a problem and the magnitude has

7       changed.

8                 So the question I have, and, Mr. Anderson, you

9       can object to your heart's content, but the question is

10       this:  Based upon the fact that the witness has

11       testified that the magnitude of the projected cost

12       estimate had increased, this is my question.  If the FPL

13       witness, whose name is redacted, knew that the magnitude

14       of the projected cost estimate had increased

15       substantially by virtue of his attendance at the

16       July 25th, 2009, meeting, and did not amend his prefiled

17       testimony under oath to reflect this material

18       information, then would it stand to reason that his

19       testimony was inaccurate and incomplete?

20                 MR. ANDERSON:  We object, again, to the

21       formulation of the question.  You state and did not

22       amend the testimony, et cetera.  What you are doing in

23       there is you are wrapping in an entire legal opinion

24       which you are asking for this particular person to

25       respond to.

FLORIDA PUBLIC SERVICE COMMISSION

1463

1                 COMMISSIONER SKOP:  I don't have the luxury --

2       Mr. Anderson, to your objection, I don't have the luxury

3       of having the former FPL employee to question him on

4       that thing, so that is part of the problem here.  And,

5       again, I can withdraw the question.  I think we know the

6       heart of what I'm trying to get at.  I'll leave it to

7       staff if they want to go after this or one of the

8       intervenors and try and frame it --

9                 CHAIRMAN ARGENZIANO:  Do you want me to ask --

10                 COMMISSIONER SKOP:  Yes, we can ask staff if

11       they want, because I have got a few more questions after

12       that and I'm done.

13                 MR. YOUNG:  Commissioner Skop, that is one of

14       my questions for Witness Reed as relates to the

15       testimony that he -- his Concentric report that he

16       produced when he talked about it, frankly, in that

17       report as relates to whether the witness from last year

18       was truthful in his statements towards the Commission.

19                 COMMISSIONER SKOP:  Okay.  And, too,

20       Mr. Young, I think the point I'm trying to adduce from

21       the witness is that the witness testified there was

22       clear indication that the magnitude of the projected

23       cost estimate had increased substantially.  And by

24       virtue of the former FPL employee who gave testimony

25       that was at that meeting, then they would have had that

FLORIDA PUBLIC SERVICE COMMISSION

1464

1       same knowledge that the current witness has.

2                 So what I'm trying to get at, if they had the

3       same knowledge and didn't amend their testimony to

4       reflect that material information, then I'm trying to

5       get an answer as to whether their testimony was accurate

6       and complete.  And that's the problem I'm facing here.

7       And Mr. Reed, I don't know whether he -- you know, the

8       disconnect here is Mr. Reed is not an FPL employee and

9       didn't attend the July 25th meeting.

10                 CHAIRMAN ARGENZIANO:  Okay.  I want to ask

11       counsel a question.  Does a Commissioner, as I guess I

12       have seen -- excuse me, Commissioner Skop.  I have seen

13       judges ask questions of witnesses all the time, and I

14       would like to know -- I guess I'd like to know your

15       opinion on the objection.

16                 Commissioner Skop and then --

17                 COMMISSIONER SKOP:  Thank you.

18                 The point I wanted to make, too, Madam Chair,

19       and I apologize for interrupting, but it is directly on

20       point.  Again, Mr. Anderson's objection, I understand

21       his basis.  However, when it gets down to the veracity

22       of testimony given under oath to the Florida Public

23       Service Commission, you know, I was accused of being an

24       advocate or whatever.  I think it is well within my

25       prerogative as a Commissioner for this Commission to

FLORIDA PUBLIC SERVICE COMMISSION

1465

1       determine and make a substantial inquiry as to the

2       accuracy and the veracity of the testimony that was

3       given under oath.  So I think we ought to have broad

4       latitude in that regard.

5                 CHAIRMAN ARGENZIANO:  Well, that's the reason

6       for my question.

7                 MS. HELTON:  If I'm understanding

8       Mr. Anderson's objection correctly, I think it's that,

9       he thinks in his opinion that perhaps Commissioner Skop

10       is trying to draw some kind of a legal conclusion out of

11       the witness, and the witness is not an attorney.

12                 Perhaps Commissioner Skop could phrase his

13       question --

14                 CHAIRMAN ARGENZIANO:  Could it be phrased

15       different, or do you have to be an attorney to answer

16       that question?

17                 MS. HELTON:  Well, I was going to give a

18       suggestion just for Commissioner Skop, perhaps, to

19       phrase his question -- all legalities aside, in his

20       opinion, was the testimony given in the 2009 proceeding

21       accurate based on the information that was learned at

22       that meeting.

23                 CHAIRMAN ARGENZIANO:  That would get to the

24       same point.

25                 Commissioner Skop.

FLORIDA PUBLIC SERVICE COMMISSION

1466

1                 COMMISSIONER SKOP:  Thank you, Madam Chair.

2                 And, again, Mr. Jones, I'm not asking for your

3       legal conclusion, and I'm not asking for you to

4       articulate the reason why you disagree with the

5       Concentric report.  What I am asking is in relation to

6       actual knowledge that there was clear indication that

7       the magnitude of the projected cost estimate had

8       increased substantially, as you testified to, whether

9       the prior witness who knew that same information should

10       have amended his testimony and should have amended his

11       testimony to include that material information?

12                 MS. HELTON:  Madam Chairman and Commissioner

13       Skop, I think the problem is whether he should have

14       amended his testimony.  I don't think -- and I have to

15       say I agree with Mr. Anderson there, that I'm not sure

16       that this witness would have any basis upon which to

17       know whether his testimony should be amended or not.  I

18       think it is a fair question, however, to ask in his

19       opinion was --

20                 CHAIRMAN ARGENZIANO:  I would ask in his

21       opinion.

22                 COMMISSIONER SKOP:  Mr. Jones, let me ask two

23       questions as a follow-up to that.  First, if you were

24       similarly situated, based on attending that meeting on

25       July 25th, 2009, and you knew based on your testimony

FLORIDA PUBLIC SERVICE COMMISSION

1467

1       there was clear indication that the magnitude of the

2       projected cost estimate for the EPU had increased

3       substantially, as you testified to, then if you were

4       appearing to testify before this Commission, would you

5       have found it appropriate to amend your testimony to

6       include the fact that the magnitude of the projected

7       cost estimate had increased?

8                 THE WITNESS:  I don't know, because you're

9       asking me really --

10                 CHAIRMAN ARGENZIANO:  Can you answer yes or

11       no?

12                 THE WITNESS:  I do not know.

13                 CHAIRMAN ARGENZIANO:  Okay.

14                 COMMISSIONER SKOP:  All right.  On that same

15       thought, if the FPL witness that provided live testimony

16       on September 8th, 2009, who attended that meeting with

17       you, and also based on your testimony, should have had a

18       clear indication that the magnitude of the projected

19       cost estimate had increased substantially by virtue of

20       attending that meeting, in your opinion, should that

21       witness have amended his testimony to reflect that

22       material information?

23                 MR. ANDERSON:  Same objection.  Same

24       objection.  In fact, just to be -- you know, Ms. Helton

25       I think formulated an unobjectionable question.  The

FLORIDA PUBLIC SERVICE COMMISSION

1468

1       fundamental problem with these questions is they have

2       these front-end predicates, which are not right.

3                 COMMISSIONER SKOP:  Why don't I defer to our

4       legal staff to ask an unobjectionable question in that

5       same line, and then I'll continue my questions that I

6       have more thought out.

7                 MS. HELTON:  Since I am here in an advisory

8       capacity, I don't feel comfortable asking the question.

9       Perhaps Mr. Young or Ms. Bennett could remember the

10       question that I suggested to Commissioner Skop and they

11       can ask it.

12                 COMMISSIONER SKOP:  I hate to do this, but

13       that's what I intend to do.

14                 MR. YOUNG:  Madam Chairman, if Commissioner

15       Skop can repeat the question and I can go from there.

16                 CHAIRMAN ARGENZIANO:  Well, wasn't it a little

17       something like in your opinion.

18                 MR. YOUNG:  Okay.  I got it.

19                 CHAIRMAN ARGENZIANO:  Okay.  I think you have

20       it.

21                 COMMISSIONER SKOP:  It's in your opinion,

22       should the FPL witness should have amended his

23       testimony.

24                 CHAIRMAN ARGENZIANO:  Okay.  Well, then, you

25       just asked the question.

FLORIDA PUBLIC SERVICE COMMISSION

1469

1                 Mr. Jones -- he just asked the question.

2                 COMMISSIONER SKOP:  Mr. Jones, should the FPL

3       witness --

4                 CHAIRMAN ARGENZIANO:  In your opinion.

5                 COMMISSIONER SKOP:  -- in your opinion, have

6       amended his testimony, period.  Yes or no?

7                 THE WITNESS:  No.

8                 COMMISSIONER SKOP:  Why?  Based on the fact

9       that he had clear indication of the magnitude of the

10       projected cost estimate had increased substantially, as

11       you testified by attendance at that meeting?

12                 THE WITNESS:  He clearly had, as I stated

13       earlier, knowledge of the change in the forecast, as

14       well as he clearly had knowledge of all the

15       opportunities in regards to mitigating that forecast,

16       and he clearly had knowledge of all project activities

17       that were going, and he clearly had knowledge of all the

18       directions from senior management to mitigate such to

19       reduce that.  And so, therefore, I don't want to speak

20       to the state of his mind, but one could conclude that he

21       knew that that was not a valid acceptable number.  No

22       different than the increase in megawatts.

23                 The position that you put me in is when I

24       think about prudence is that I have the benefit of

25       hindsight of where the project is now.  And so,

FLORIDA PUBLIC SERVICE COMMISSION

1470

1       therefore, it is hard for me to transport myself exactly

2       back in time, other than going back and looking at the

3       facts at the time, which I just stated.

4                 CHAIRMAN ARGENZIANO:  Okay.  I have a question

5       for you, because now that brings up a question that I

6       have.  In your opinion, knowing that that individual

7       whose name is confidential understood that the budget

8       information -- and I'm going to read it right from the

9       line here -- understood that the budget information

10       provided in May 2009 was indeed incorrect by the time of

11       the hearing, do you still think -- is your opinion

12       still, no, that he shouldn't have amended, even though

13       he knew it was incorrect?

14                 MR. ANDERSON:  I think the Chairman is reading

15       from the Concentric conclusion as opposed to anything

16       the witness talked about.

17                 CHAIRMAN ARGENZIANO:  Yes, I did read from the

18       Concentric.

19                 MR. ANDERSON:  And, Mr. Jones, you know, you

20       can -- I would just ask that you specify what you are

21       reading from so that the source is clear.

22                 CHAIRMAN ARGENZIANO:  Oh, I'm sorry, if I

23       didn't say that.  I thought I said it was from the

24       report.  If I didn't, it was from the Concentric report

25       that I has just read in the entirety.

FLORIDA PUBLIC SERVICE COMMISSION

1471

1                 MR. ANDERSON:  Can you indicate the page and

2       line, if you want him to look at it?

3                 CHAIRMAN ARGENZIANO:  Certainly.  Page 42, and

4       I couldn't count the line.  You'll have the look -- the

5       first paragraph.

6                 MR. YOUNG:  Excuse me, Madam Chairman, I think

7       it's the staff audit that you are looking at.

8                 CHAIRMAN ARGENZIANO:  Yes, I'm sorry.  I'm

9       talking about the Concentric report, and, yes, it is the

10       staff audit.  I'm sorry.  And I hope that is the way I

11       identified it the first time when I read it.  If not,

12       I'll make that correction now.

13                 MR. ANDERSON:  May I just check that the

14       witness does have the page and the report in front of

15       him, because that helps.

16                 THE WITNESS:  Yes.

17                 CHAIRMAN ARGENZIANO:  The page is 42, and it

18       is the top paragraph, beginning with in an interview.

19                 MR. ANDERSON:  Thank you.  I appreciate that.

20                 CHAIRMAN ARGENZIANO:  Thank you.  I didn't

21       realize I had made that mistake.  Thank you.

22                 Where it indicates that --

23                 THE WITNESS:  Yes, I'm with you.

24                 CHAIRMAN ARGENZIANO:  Okay.  I think the fifth

25       line down.  And I am just simply asking if knowing that

FLORIDA PUBLIC SERVICE COMMISSION

1472

1       line, where it does read understood that the budget

2       information provided in May 2009 was indeed incorrect,

3       dot, dot, dot, that your opinion would still remain the

4       same that, no, he should not have amended his comments,

5       his report.

6                 THE WITNESS:  Yes, my opinion remains the

7       same.  I read this, and this is someone's opinion in

8       regards to correct or incorrect.

9                 CHAIRMAN ARGENZIANO:  Very well.  Thank you.

10                 Commissioner Skop, did you have another

11       question?

12                 COMMISSIONER SKOP:  Yes, I have a few more

13       questions.

14                 Mr. Jones, to the Chairman's prior question

15       that you disagreed with, those are the findings of

16       Concentric, which was independently -- I mean, which was

17       retained to provide an independent analysis of the facts

18       associated with the accuracy of information provided to

19       the Florida Public Service Commission, is that correct?

20                 THE WITNESS:  Yes, Commissioner, that's

21       correct.

22                 COMMISSIONER SKOP:  Okay.  And they take a

23       different conclusion based upon their own independent

24       analysis that you disagree with, correct?

25                 THE WITNESS:  Yes, that is correct.

FLORIDA PUBLIC SERVICE COMMISSION

1473

1                 COMMISSIONER SKOP:  Okay.  All right.  Just a

2       few more questions.

3                 Mr. Jones, as part of an April 2nd filing with

4       the Securities and Exchange Commission, that AK-FD

5       disclosure contained a letter dated April 2nd that was

6       directed to team.  And as an employee of Florida Power

7       and Light Company, did you receive a copy of that letter

8       that appears to be sent to employees regarding the

9       anonymous employee letters?

10                 MR. ANDERSON:  What document is this, again,

11       please?

12                 CHAIRMAN ARGENZIANO:  Can you repeat that,

13       Commissioner Skop?

14                 COMMISSIONER SKOP:  Okay.  I'm asking if

15       Mr. Jones received a copy of an April 2nd letter from

16       Mr. Hay to team related to the anonymous employee

17       letters.  And that was filed as an attachment to a

18       Securities and Exchange filing AK under Regulation FD on

19       April 2nd, 2010.

20                 CHAIRMAN ARGENZIANO:  Did you get that,

21       Mr. Anderson, or do you need a minute to get it?

22                 MR. ANDERSON:  I do, but I'm puzzled because

23       this involves in no respect the nuclear cost-recovery

24       clause or anything we've talked about.

25                 COMMISSIONER SKOP:  I believe, Madam Chair --

FLORIDA PUBLIC SERVICE COMMISSION

1474

1                 MR. ANDERSON:  There is no foundation for it;

2       there is no relation of this to any issue.

3                 COMMISSIONER SKOP:  Okay.  Let me attempt to

4       lay a foundation.  As an FPL employee, did you receive a

5       letter from Mr. Hay directed to team on April 2nd, 2010,

6       that addressed the subject of anonymous employee

7       letters?

8                 THE WITNESS:  Commissioner Skop, if I could

9       see the letter I would feel more comfortable answering

10       the question.

11                 COMMISSIONER SKOP:  I need to make a copy real

12       quick.  So if I could -- if we could hold in place.

13                 CHAIRMAN ARGENZIANO:  Okay.  Let's get a copy.

14       He needs to be able to see that letter.  Do we have an

15       extra copy that -- okay.  Do you have a different

16       question you may get to while we're doing that?

17                 COMMISSIONER SKOP:  Again, my different -- my

18       next question pertains to that.  I'm laying the

19       foundation for my final question.

20                 CHAIRMAN ARGENZIANO:  Okay.  Then we are kind

21       of on an informal recess until the copy gets made.

22       Anybody needs to -- remember, in 15 minutes if we are

23       not done, and you walk outside without somebody inside

24       to let you back in, you will be locked out.

25                 (Off the record.)

FLORIDA PUBLIC SERVICE COMMISSION

1475

1                 CHAIRMAN ARGENZIANO:  We're back on.

2                 COMMISSIONER SKOP:  Madam Chair, I'm not so

3       sure that the copies we passed out -- and, again, the

4       intent was to make copies without the highlight, so,

5       again, I'm not sure how that got highlighted.

6                 CHAIRMAN ARGENZIANO:  Does it matter?

7                 COMMISSIONER SKOP:  I don't believe it

8       matters, but it may warrant an objection that could be

9       otherwise cured by having an unhighlighted copy of the

10       document.  But for purposes --

11                 CHAIRMAN ARGENZIANO:  Okay.

12                 COMMISSIONER SKOP:  Mr. Jones, I want to give

13       you a minute to review this letter that was dated

14       April 2nd, 2010, addressed to team that was attached as

15       part of an AK filing under Regulation FD that was filed

16       with the Securities and Exchange Commission on

17       April 2nd, 2010.  Do you see that letter?

18                 THE WITNESS:  I have the letter, yes.

19                 COMMISSIONER SKOP:  Okay.  As an FPL employee,

20       did you receive a copy of that letter that was directed

21       to team?

22                 THE WITNESS:  Yes.

23                 COMMISSIONER SKOP:  Okay.  Thank you.  The

24       first highlighted section at the bottom of the page --

25                 MR. ANDERSON:  We do not have highlights,

FLORIDA PUBLIC SERVICE COMMISSION

1476

1       Commissioner Skop.

2                 COMMISSIONER SKOP:  Okay.  I don't know what

3       has been passed out and what hasn't been passed out.

4                 CHAIRMAN ARGENZIANO:  I do.

5                 MS. HELTON:  While we are kind of interrupted,

6       maybe it might be good if we could just go ahead, for

7       purpose of a clear record, give this an exhibit number

8       for identification purposes.

9                 COMMISSIONER SKOP:  Well, my preference would

10       be to enter into the record an unhighlighted copy of the

11       letter.  That was my intent, but I couldn't seem to get

12       the copies that --

13                 CHAIRMAN ARGENZIANO:  All right.  Well, can we

14       do that afterwards?

15                 COMMISSIONER SKOP:  I think we can do that

16       afterwards.

17                 CHAIRMAN ARGENZIANO:  Okay.

18                 COMMISSIONER SKOP:  So, I mean, the highlight

19       is not intended to be on the document, okay.  That was

20       my own personal highlight to attract my attention to a

21       position on the page.

22                 All right.  Mr. Jones, you testified that you

23       received a copy of this letter dated April 2nd, 2010,

24       from Mr. Hay, who is the Chairman and CEO of FPL Group.

25       And the last paragraph on the first page, can you read

FLORIDA PUBLIC SERVICE COMMISSION

1477

1       the first sentence of that paragraph, please, beginning

2       with the words, we are proud?

3                 THE WITNESS:  Yes.  "We are proud that the

4       quality of major company processes for validating the

5       accuracy of information we furnished to our external

6       stakeholders.

7                 COMMISSIONER SKOP:  Keep going.

8                 THE WITNESS:  I think I was going a little

9       fast.

10                 COMMISSIONER SKOP:  Okay.  Can you --

11                 MR. ANDERSON:  At this time I'd like to go

12       ahead and interpose an objection.  This letter does not

13       come within one hundred yards of the testimony of this

14       witness.  This witness did not write the document and

15       did not participate in the preparation of the document.

16       It relates in no way to any issue at the NCRC

17       proceeding.  And, yes, looking at this letter, we are

18       proud of the quality of our company processes for

19       validating the accuracy of information we furnish to

20       external shareholders.  Yes, that is absolutely true,

21       but it has absolutely nothing to do with this proceeding

22       or this case, and we go farther and farther afield as

23       the hours proceed.

24                 COMMISSIONER SKOP:  Madam Chair, to the

25       objection, I respectfully disagree.  I'm laying a

FLORIDA PUBLIC SERVICE COMMISSION

1478

1       foundation to ask the witness a question that the

2       witness would have direct personal knowledge of in

3       relation to an employee letter.  So, again, I'm laying

4       the foundation between the letter that Mr. Hay sent to

5       employees on April 2nd, 2010, that was part of the

6       Securities and Exchange filing which the witness has

7       testified as an FPL employee he received a copy of.

8                 That is critical to the question that I am

9       going to ask on my subsequent questions.  So I am merely

10       laying a foundation to avoid an objection.  I think I

11       should be given broad latitude because it pertains to

12       the witness' opinion and some of the veracity of

13       statements that have been made to the Florida Public

14       Service Commission.

15                 MR. ANDERSON:  I'm sorry, two things.

16       Constructively I suggest just asking that question,

17       then.  We do object to this document and we ask for a

18       ruling.

19                 CHAIRMAN ARGENZIANO:  Legal counsel to the

20       objection and to Commissioner Skop's purpose for laying

21       the foundation.  And could the question be asked without

22       the document?

23                 COMMISSIONER SKOP:  (Indicating negatively.)

24                 CHAIRMAN ARGENZIANO:  No, I didn't think so.

25       Okay.

FLORIDA PUBLIC SERVICE COMMISSION

1479

1                 MS. HELTON:  Madam Chairman, my recommendation

2       is to go a little bit further down this line and see

3       where we're going, and allow Commissioner Skop to ask

4       the next question or two.  And if we haven't reached the

5       point where it all comes together, then maybe we can

6       revisit it.

7                 CHAIRMAN ARGENZIANO:  Well, we have an

8       objection.

9                 MS. HELTON:  To do that you would have to

10       overrule the objection at this time.

11                 CHAIRMAN ARGENZIANO:  Well, at this time I

12       will overrule the objection.  And, Commissioner Skop, if

13       you can move us down the line.

14                 COMMISSIONER SKOP:  Thank you.

15                 Mr. Jones, the first paragraph on that letter

16       that you testified that you received on or about

17       April 2nd, 2010, can you read the full sentence

18       beginning with the word, we, of that last paragraph,

19       please?

20                 THE WITNESS:  We are proud that the quality of

21       major company processes for validating the accuracy of

22       information we furnish to our external stakeholders

23       continues to satisfy scrutiny.

24                 COMMISSIONER SKOP:  Thank you.  With respect

25       to the employee complaint letter that you indicated that

FLORIDA PUBLIC SERVICE COMMISSION

1480

1       you were interviewed regarding and that you had seen a

2       copy of, which the name of the person remains

3       confidential, the April 2nd letter deals with the

4       anonymous employee complaints.  The employee letter of

5       February 19th, 2010, deals with the actual redacted name

6       of an employee who made a complaint.

7                 And the question that I would like to ask on

8       the employee letter in the Concentric report that you

9       talked about there previously, and I'll want to ask you,

10       that employee letter which was in parallel with, you

11       know -- which was sent to FPL Group management prior to

12       the April 2nd being sent to the team, there was an

13       investigation conducted.  But the concerns expressed in

14       the employee letter indicated concern about how FPL

15       would report the findings of the upcoming PSC hearings,

16       and that any information from the EPU other than which

17       was presented to management last summer will be a

18       manipulation of the truth.  Okay.

19                 So my question, based upon your knowledge of

20       the employee letter and its concerns and the existence

21       of that letter and the existence of the findings of the

22       Concentric report which you may or may not agree with,

23       but --

24                 CHAIRMAN ARGENZIANO:  The question.

25                 COMMISSIONER SKOP:  The question.  I'm trying

FLORIDA PUBLIC SERVICE COMMISSION

1481

1       to look at my small notes.

2                 CHAIRMAN ARGENZIANO:  Okay.

3                 COMMISSIONER SKOP:  Okay.  My question is as

4       it pertains to the accuracy of the information provided

5       to the Florida Public Service Commission -- let me see.

6       Hold on.  Yes, I want a minute.  I'm trying to rephrase.

7                 The common element between the anonymous

8       letters and the employee letter of February 19th, 2010,

9       one common element, again, seems to be pertaining to the

10       accuracy of information provided to the Florida Public

11       Service Commission.  My question is, based upon the

12       existence of the employee letter dated February 19th,

13       2010, and the subsequent findings of the Concentric

14       report, which brought into question the veracity of

15       statements made under oath to the Florida Public Service

16       Commission, did it occur to you that the employee

17       complaint letter dated February 19th, 2010, should be

18       made public?

19                 MR. ANDERSON:  We object to that question.

20       That is a multi, multi, multi-part question.  I couldn't

21       even begin to follow it.  I think if the information is

22       desired to be elicited of the witness, ask a direct

23       question of the witness.  There is -- look at the basic

24       predicate of that.  It began with the common element

25       between anonymous letters and this letter were X.  There

FLORIDA PUBLIC SERVICE COMMISSION

1482

1       was no even discussion or foundation that the witness

2       even read the common letter.  I just suggest asking

3       plain simple questions.

4                 COMMISSIONER SKOP:  All right.  I will reframe

5       the question.

6                 CHAIRMAN ARGENZIANO:  Commissioner Skop, if

7       you can reframe the question, and then I think I'm going

8       to make a decision for the rest of the day.

9                 COMMISSIONER SKOP:  All right.  Thank you.

10                 Mr. Jones, you have read the employee

11       complaint letter dated February 19th, 2010, that was

12       directed to Mr. Hay, is that correct?

13                 THE WITNESS:  Yes, I have.

14                 COMMISSIONER SKOP:  Okay.  And the concern

15       expressed in that letter is the accuracy of information

16       and how information would be reported to the Florida

17       Public Service Commission, is that not correct, that one

18       of the allegations in that letter has that very concern

19       in it?

20                 THE WITNESS:  Yes.  It states that it is

21       concerned about how FPL will report these findings at

22       the upcoming PSC hearings.

23                 COMMISSIONER SKOP:  Okay.  And the finding of

24       the Concentric report, which you disagree with, but the

25       finding of the Concentric report which was prepared

FLORIDA PUBLIC SERVICE COMMISSION

1483

1       independently concludes that the witness should have

2       amended his testimony to address a $300 million or

3       27 percent cost escalation at the September 8th, 2009,

4       hearing, correct?

5                 MR. ANDERSON:  I suggest that -- I ask that

6       the witness be pointed to the specific portion of the

7       report rather than have it paraphrased.

8                 COMMISSIONER SKOP:  Okay.  Very well.  On

9       the -- well, let's go to the staff audit report because

10       it is quicker that way.  And what is the -- 178,

11       Mr. Young, I guess?

12                 CHAIRMAN ARGENZIANO:  I think it was 178.  Is

13       that correct, the staff audit report?

14                 MS. HELTON:  Yes, ma'am.  That's my

15       recollection, 178.

16                 CHAIRMAN ARGENZIANO:  178, okay.

17                 COMMISSIONER SKOP:  If we go to what has been

18       marked for identification as Exhibit 178, and I believe

19       it's on Page 41 of the staff audit report.

20                 CHAIRMAN ARGENZIANO:  Everybody there?  Okay.

21                 COMMISSIONER SKOP:  Okay.  Can you read the

22       last paragraph on Page 41 of the staff audit report?

23                 THE WITNESS:  The inset?

24                 COMMISSIONER SKOP:  Yes.

25                 THE WITNESS:  While Concentric agrees that the

FLORIDA PUBLIC SERVICE COMMISSION

1484

1       new analysis confirm the conclusions in Mr. Blank's

2       testimony, we believe that a $300 million, or 27 percent

3       increase in the projected cost of the EPU project should

4       have been discussed in the live testimony on

5       September 8th, 2009.

6                 COMMISSIONER SKOP:  All right.  Would you

7       agree that the Concentric finding deals with the

8       veracity of the testimony given in the Florida Public

9       Service Commission for that witness?

10                 MR. ANDERSON:  I object.  The document speaks

11       for itself, and he is asking the wrong witness.

12                 CHAIRMAN ARGENZIANO:  Perhaps it should be the

13       other witness.

14                 COMMISSIONER SKOP:  I'll try and reframe.

15                 Mr. Jones, based upon reading the Concentric

16       finding at the bottom of Page 41 of the staff audit

17       report, which has been marked for identification as

18       Exhibit 178, does that not relate to how information is

19       provided to the Florida Public Service Commission?

20                 THE WITNESS:  Yes, this paragraph is in that

21       context.

22                 COMMISSIONER SKOP:  Okay.  And that was a

23       concern in the employee letter dated February 19th,

24       2010, correct, the letter that you read?

25                 THE WITNESS:  No, Commissioner.  I believe the

FLORIDA PUBLIC SERVICE COMMISSION

1485

1       employee stated in the upcoming Florida Public Service

2       Commission hearings.

3                 COMMISSIONER SKOP:  But the general concern

4       was the accuracy of information provided to the Florida

5       Public Service Commission, is that correct?

6                 MR. ANDERSON:  I would object.  That letter

7       speaks for itself, and I believe the witness has

8       accurately characterized exactly what it does say.

9                 CHAIRMAN ARGENZIANO:  Commissioner Skop.

10                 COMMISSIONER SKOP:  I was looking to get an

11       answer from the witness, but I would take Mr. Anderson's

12       comments as an objection, is that correct, Mr. Anderson?

13                 CHAIRMAN ARGENZIANO:  He objected.

14                 COMMISSIONER SKOP:  Okay.

15                 CHAIRMAN ARGENZIANO:  Can you ask a different

16       question or rephrase?

17                 COMMISSIONER SKOP:  I will try to rephrase to

18       avoid an objection.

19                 Mr. Jones, based on the February 19th employee

20       letter, did the employee express concerns regarding how

21       information would be provided to the Florida Public

22       Service Commission?

23                 THE WITNESS:  Yes, Commissioner, he states

24       that he is concerned about how FPL will report these

25       findings at the upcoming PSC hearings.

FLORIDA PUBLIC SERVICE COMMISSION

1486

1                 COMMISSIONER SKOP:  Okay.  And you have read

2       the finding of the Concentric report as it pertains to

3       the testimony given by the name of the redacted FPL

4       witness, is that correct?

5                 THE WITNESS:  Yes, I have.

6                 COMMISSIONER SKOP:  Okay.  And that concerns

7       the accuracy of the information provided to this

8       Commission, is that correct?

9                 THE WITNESS:  Yes, it does.

10                 COMMISSIONER SKOP:  Okay.  So does not the

11       finding of the Concentric report and the employee letter

12       dated February 19th, 2010, not stand in sharp contrast

13       to the statements made in the letter sent to employees

14       on April 2nd, 2010, with respect to the accuracy of

15       information furnished to our external stakeholders that

16       continues to satisfy scrutiny?

17                 MR. ANDERSON:  That is an -- objection.  That

18       is an inappropriate question for this witness.

19                 COMMISSIONER SKOP:  All right.  It's getting

20       late in the day, and I think I have made my point, so

21       I'm going to --

22                 CHAIRMAN ARGENZIANO:  Commissioner Skop, here

23       is what I'm going to do, because it is late in the day.

24       I really hoped that we could get through this today.

25       But, unfortunately, people are tired, and I can see that

FLORIDA PUBLIC SERVICE COMMISSION

1487

1       maybe some people maybe just need to take a break away

2       from here.  And I do have several questions for Mr. Reed

3       coming up, so I don't think that any of us need to stay

4       here until 9:00 or 10:00 o'clock tonight.

5                 Unfortunately, I was hoping we could get it

6       done today, but I don't think that's going to happen.

7       So I suggest that we recess until tomorrow morning at

8       9:30.

9                 I'm sorry, did I forget to do anything?

10                 MR. ANDERSON:  Well, I'm just not clear what

11       is the status of this witness.

12                 CHAIRMAN ARGENZIANO:  Well, we didn't excuse

13       him, so he has to sit here all night.  I'm only kidding.

14       No, I think -- Commissioner Skop, were you done with

15       questions for this witness?

16                 COMMISSIONER SKOP:  I'm done unless staff or

17       redirect or anything.

18                 CHAIRMAN ARGENZIANO:  Was there any other

19       questions?  So you are -- so we will excuse Mr. Jones.

20                 Thank you.

21                 MS. HELTON:  Do you all have redirect?

22                 MR. ANDERSON:  No.

23                 COMMISSIONER SKOP:  And then staff will move

24       in the other exhibits that we marked at a later point in

25       time, is that correct?

FLORIDA PUBLIC SERVICE COMMISSION

1488

1                 CHAIRMAN ARGENZIANO:  And might I do this,

2       just a little change, because I forgot something.  Can

3       we start at 9:45 tomorrow rather than 9:30?  Is there

4       any problem with doing that?  9:45 tomorrow morning.

5       Thank you.(

6                 We're on recess.

7                 (The hearing adjourned at 6:09 p.m.)

8                 (Transcript continues in sequence with

9       Volume 7.)

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1489

1

2

3

4

5

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION