## December 2010
12
Place an X in the box when your data is verified:
|  |  | Vicki Mack |  | Allison Bryant |  |  | Sarah Seckinger
|  |  | Hal Banks |  | Carol Stevens
|  |  | Paul Pratofiorito |  | Debbie Deatherage
|  |  | Allison Beaty |  | Barbara Gambill
Business |  |  |  |  | YTD | YTD | YTD | YTD |  | YTD | Year-End | Original | Year-End | Year-End
Unit |  | PE | Walker Description | Coor. | Actual | Budget | Variance $ | Variance % | * | Explanation | Projected | Budget | Variance | Variance % | **
POWER GENERATION
ENVIRONMENTAL
|  | 1001 | ECRC-CRIST-4-5 OPACITY REPLACEMENT | VICKI | -1982.16 | 0 | -1982.16 | 100% |  |  | -1982.16 | 0 | -1982.16 | -100
|  | 1031 | ECRC AIR CRIST UNIT 7 SCR CATALYST REPLACEMENT | VICKI | 409682.77 | 0 | 409682.77 | 100% |  |  | 409682.77 |  | 409682.77 | 100
|  | 1033 | ENVIR-WASTE-CRIST FLY ASH LANDFILL STORAGE CELL CAPPING | VICKI | 266058.04 | 625000 | -358941.96 | -57.43% | * |  | 266058.04 | 625000 | -358941.96 | -57.4307
|  | 1038 | ECRC-AIR-CRIST 6 UPGR PRECIP | VICKI | 471744.19 | 1100000 | -628255.81 | -57.11% | * |  | 471744.19 | 1100000 | -628255.81 | -57.1142
|  | 1158 | ECRC-AIR-CRIST SCR U7 MISC | VICKI | 6063.46 | 150000 | -143936.54 | -95.96% | * |  | 6063.46 | 150000 | -143936.54 | -95.9577
|  | 1222 | ECRC-AIR-CRIST SCRUBBER | VICKI | 25538775.83 | 21855174 | 3683601.83 | 16.85% | * |  | 25538775.83 | 21855174 | 3683601.83 | 16.8546
|  | 1233 | ECRC - CRIST MISCELLANEOUS | VICKI | 395967.32 | 150000 | 245967.32 | 164% | * |  | 395967.32 | 150000 | 245967.32 | 163.9782
|  | 1244 | ECRC-AIR-CRIST RATA CEM TEST TRAILER | VICKI | 130518.05 | 0 | 130518.05 | 100% |  |  | 130518.05 |  | 130518.05 | 100
|  | 1247 | ECRC - CRIST 4 & 5 BY PASS STACK CEMS EQUIP | VICKI | 966312.76 | 0 | 966312.76 | 100% | * |  | 966312.76 | 0 | 966312.76 | 100
|  | 1253 | ENVIR-WASTE-CRIST FLY ASH LANDFILL STORAGE CELL DEVEL | VICKI | 270318.1 | 500000 | -229681.9 | -45.94% | * |  | 270318.1 | 500000 | -229681.9 | -45.9364
|  | 1256 | ECRC - CRIST 6 & 7 BY PASS STACK CEMS EQUIP | VICKI | 1387753.86 | 0 | 1387753.86 | 100% | * |  | 1387753.86 | 0 | 1387753.86 | 100
|  | 1276 | ENVIR-WASTE-CRIST ASH POND DISCHARGE WEIR REPLACEMENT | VICKI | 1690612.09 | 2000004 | -309391.91 | -15.47% | * |  | 1690612.09 | 2000004 | -309391.91 | -15.4696
|  | 1279 | ECRC-AIR-CRIST 6 SCR | VICKI | 50360354.92 | 31156470 | 19203884.92 | 61.64% | * |  | 50360354.92 | 31156470 | 19203884.92 | 61.6369 | **
|  | 1283 | ECRC-AIR-CRIST 4-7 CEMS SYSTEM FOR SCRUBBERS | VICKI | 307691.29 | 0 | 307691.29 | 100% | * |  | 307691.29 | 0 | 307691.29 | 100
|  | 1298 | ECRC - CRIST WATER CONSERVATION PROGRAM | VICKI | 8338973.43 | 7560752 | 778221.43 | 10.29% | * |  | 8338973.43 | 7560752 | 778221.43 | 10.2929
|  | 1299 | ECRC CRIST 4-7 ASH POND CHEMISTRY CONTROL SYSTEM | VICKI | 48158.78 | 50000 | -1841.22 | -0.036824 |  |  | 48158.78 | 50000 | -1841.22 | -3.6824
|  | 1365 | ENVIR-SCHOLZ-WATER POTABLE WATER SYSTEM | VICKI | 0 | 40000 | -40000 | -100% | * |  | 0 | 40000 | -40000 | -100
|  | 1468 | ECRC-AIR-SMITH 1 SNCR | VICKI | 1287.43 | 0 | 1287.43 | 100% |  |  | 1287.43 | 0 | 1287.43 | 100
|  | 1548 | ECRC - DANIEL UNIT 1 SCR | VICKI | [7 empty] | 0 | 0 | 0
|  | 1550 | ECRC - DANIEL UNIT 2 SCR | VICKI | [7 empty] | 0 | 0 | 0
|  | 1551 | ECRC-AIR-DANIEL 1 & 2 SCRUBBER | VICKI | 37297.5 | 8029472 | -7992174.5 | -99.54% | * |  | 37297.5 | 8029472 | -7992174.5 | -99.5355
|  | 1555 | ECRC - WASTE - DANIEL ASH STORAGE | VICKI | 43623.05 | 0 | 43623.05 | 100% | * |  | 43623.05 | 0 | 43623.05 | 100
|  | 1601 | ECRC-WATER SMITH RECLAIMED WATER PROJECT UNIT3 | VICKI | 0 | 1500000 | -1500000 | -100% | * |  | 0 | 1500000 | -1500000 | -100
|  | 1613 | ENVIR-WASTE-SMITH 1&2-CAP ASH LANDFILL CELLS | VICKI | 156344.81 | 170000 | -13655.19 | -8.032% |  |  | 156344.81 | 170000 | -13655.19 | -8.0325
|  | 1640 | ENVIROMENTAL AIR SMITH 3 CEMS REPLACEMENT | VICKI | -201208.79 | 0 | -201208.79 | 100% | * |  | -201208.79 | 0 | -201208.79 | -100
|  | 1727 | ENVIR-AIR-SCHERER SELECTIVE CATALYTIC REDUCT (SCR) | VICKI | 20092860.17 | 19161742 | 931118.17 | 4.859% | * |  | 20092860.17 | 19161742 | 931118.17 | 4.8593
|  | 1728 | ENVIR-AIR-SCHERER SCRUBBER | VICKI | 18551149.09 | 17707315 | 843834.09 | 4.765% | * |  | 18551149.09 | 17707315 | 843834.09 | 4.4037
|  | 1729 | ENVIR-AIR-SCHERER BAGHOUSE | VICKI | 626708.26 | 301852 | 324856.26 | 107.6% | * |  | 626708.26 | 301852 | 324856.26 | 107.621
|  | 1778 | ENVIR - SCHERER - ENVIRONMENTAL SITE PLAN | VICKI | 4043069.89 | 4346894 | -303824.11 | -6.989% | * |  | 4043069.89 | 4346894 | -303824.11 | -1.7158
|  | 1791 | ENVIR-SCHERER 3 RADIANT REHEAT SURFACE BOILER MODIFICATIONS | VICKI | -9060.52 | 0 | -9060.52 | 100% |  |  | -9060.52 | 0 | -9060.52 | -3.0016
|  | 1824 | ECRC-AIR-DANIEL 1 LO NOX BURNERS | VICKI | 1675552.77 | 2395110 | -719557.23 | -30.04% | * |  | 1675552.77 | 2395110 | -719557.23 | -16.5534
|  | 1826 | ECRC-AIR-DANIEL 2 LO NOX BURNERS | VICKI | -83294.4 | 0 | -83294.4 | 100% | * |  | -83294.4 | 0 | -83294.4 | -3.4777
|  | 1847 | ECRC DANIEL SCRUBBER LAND | VICKI | 6.09 | 50000 | -49993.91 | -99.99% | * |  | 6.09 | 50000 | -49993.91 | 100
| TOTAL ENVIRONMENTAL |  |  |  | 135521338.08 | 118849785 | 16671553.08 | 14.03% |  |  | 135521338.08 | 118849785 | 16671553.08 | 14.0274
FOSSIL
|  | 1010 | Crist 6 PRIMARY SUPERHEATER REPLACEMENT | VICKI | 200000 | 0 | 200000 | 100% | * |  | 200000 | 0 | 200000 | 100
|  | 1013 | CRIST 6 HRA SIDEWALLS HEADER TO HEADER | VICKI | 920027.39 | 999997 | -79969.61 | -7.997% |  |  | 920027.39 | 999997 | -79969.61 | -7.997
|  | 1024 | CRIST 7 - 7A 4160 VAC VOLT BREAKERS 1 | VICKI | -8172.74 | 0 | -8172.74 | 100% |  |  | -8172.74 | 0 | -8172.74 | -100
|  | 1028 | CRIST 7 PRIMARY/SECONDARY ASH COLLECTOR REPLACEMENT | VICKI | -3025.5 | 0 | -3025.5 | 100% |  |  | -3025.5 | 0 | -3025.5 | -100
|  | 1044 | CRIAT 4 - 2300 VOLT BREAKERS, 18 VACUUM BREAKERS | VICKI | 0 | 450000 | -450000 | -100% | * |  | 0 | 450000 | -450000 | -100
|  | 1046 | CRIST 6 PA FAN SPEEDCHANGER | VICKI | 0 | 80002 | -80002 | -100% | * |  | 0 | 80002 | -80002 | -100
|  | 1048 | CRIST 5 STEAM COOLED FRONT WALL REPLACEMENT | VICKI | 0 | 300000 | -300000 | -100% | * |  | 0 | 300000 | -300000 | -100
|  | 1052 | CRIST 6 - 6A 4160 VOLT BREAKERS | VICKI | 9675.78 | 0 | 9675.78 | 100% |  |  | 9675.78 | 0 | 9675.78 | 100
|  | 1053 | CRIST 6 - 6B 4160 VOLT BREAKERS | VICKI | 3633.67 | 0 | 3633.67 | 100% |  |  | 3633.67 | 0 | 3633.67 | 100
|  | 1090 | CRIST 7 AIRHEATER SOOT BLOWERS | VICKI | 1158.78 | 0 | 1158.78 | 100% |  |  | 1158.78 | 0 | 1158.78 | 100
|  | 1091 | CRIST 7 COLD AIR HEATER AND HOT INTERMEDIATE BASKETS | VICKI | 14651.39 | 0 | 14651.39 | 100% | * |  | 14651.39 | 0 | 14651.39 | 100
|  | 1094 | CRIST FUEL HANDLING CRANE | VICKI | 3302227.96 | 3400032 | -97804.04 | -2.877% |  |  | 3302227.96 | 3400032 | -97804.04 | -2.8766
|  | 1100 | CRIST-MINOR MISC ITEMS | VICKI | 352652.39 | 399990 | -47337.61 | -11.83% | * |  | 352652.39 | 399990 | -47337.61 | -11.8347
|  | 1105 | CRIST-#9 CONVEYOR STRUCTURAL METAL | VICKI | 10202.61 | 0 | 10202.61 | 100% | * |  | 10202.61 | 0 | 10202.61 | 100
|  | 1111 | CRIST-6 LOWER ECNONMIZER AND HEADER REPLACEMENT | VICKI | 1117111.2 | 800000 | 317111.2 | 39.64% | * |  | 1117111.2 | 800000 | 317111.2 | 39.6389
|  | 1121 | CRIST 6 REHEAT HEADER FROM REHEAT OUTLET TO IP TURBINE | VICKI | 186283.06 | 1000000 | -813716.94 | -81.37% | * |  | 186283.06 | 1000000 | -813716.94 | -81.3717
|  | 1122 | CRIST BARGE HAUL SYSTEM | VICKI | 1867063.96 | 499997 | 1367066.96 | 273.4% | * |  | 1867063.96 | 499997 | 1367066.96 | 273.415
|  | 1123 | CRIST #7 CONDENSER EXPANSION JOINTS | VICKI | 1158.78 | 0 | 1158.78 | 100% |  |  | 1158.78 | 0 | 1158.78 | 100
|  | 1125 | CRIST #7C CONDENSATE PUMP MOTOR | VICKI | 259.88 | 0 | 259.88 | 100% |  |  | 259.88 | 0 | 259.88 | 100
|  | 1128 | CRIST INTAKE SCREENS | VICKI | -11179.01 | 0 | -11179.01 | 100% | * |  | -11179.01 | 0 | -11179.01 | -100
|  | 1131 | CRIST #7 CIRCULATION WATER ISOLATION VALUES & EXPAN JOINTS | VICKI | 1815.97 | 0 | 1815.97 | 100% |  |  | 1815.97 | 0 | 1815.97 | 100
|  | 1146 | CRIST 7 BATTER BANK | VICKI | 156622.53 | 0 | 156622.53 | 100% |  |  | 156622.53 |  | 156622.53 | 100
|  | 1147 | CRIST 4&5 BATTERY BANK | VICKI | 81644.49 | 0 | 81644.49 | 100% |  |  | 81644.49 |  | 81644.49 | 100
|  | 1148 | CRIST - MISC ITEMS | VICKI | 1063670.75 | 500010 | 563660.75 | 1.1273 | * |  | 1063670.75 | 500010 | 563660.75 | 112.7299
|  | 1150 | CRIST 6 - BATTERY BANK | VICKI | 40317.07 | 0 | 40317.07 | 1 |  |  | 40317.07 |  | 40317.07 | 100
|  | 1159 | CRIST REPLACE 4160 V BREAKERS.CABLES & SWITCHES | VICKI | 216276.99 | 0 | 216276.99 | 1 | * |  | 216276.99 | 0 | 216276.99 | 100
|  | 1196 | CRIST 6 REHEAT AND SUPERHEAT DAMPERS | VICKI | 299997.38 | 300000 | -2.62 | -8.7333e-06 |  |  | 299997.38 | 300000 | -2.62 | -0.00087333
|  | 1230 | CRIST 6 REPL REHEATER | VICKI | 1502540.11 | 2000000 | -497459.89 | -0.24873 | * |  | 1502540.11 | 2000000 | -497459.89 | -24.873
|  | 1258 | CRIST 4-7 DEMINERALIZER CONTROLS REPLACEMENT | VICKI | 251898.19 | 392760 | -140861.81 | -0.35865 | * |  | 251898.19 | 392760 | -140861.81 | -35.8646
|  | 1262 | CRIST 6 - HOT REHEAT PIPE | VICKI | [7 empty] | 0 | 0 | 0
|  | 1265 | CRIST 4 - 7 AQUEOUS AMMONIA/HYDRAZINE BULK TANKS | VICKI | 0 | 363000 | -363000 | -1 | * |  | 0 | 363000 | -363000 | -100
|  | 1266 | CRIST REPLACEMENT OF 4160V BREAKERS AT FUEL HANDLING | VICKI | 16817.1 | 0 | 16817.1 | 1 | * |  | 16817.1 | 0 | 16817.1 | 100
|  | 1267 | CRIST REPLACEMENT OF 575V BREAKERS AT FUEL HANDLING | VICKI | 320566.84 | 0 | 320566.84 | 1 | * |  | 320566.84 | 0 | 320566.84 | 100
|  | 1300 | Scholz-Misc. Steam Plant Additions & Imp. | VICKI | 121565.54 | 120000 | 1565.54 | 0.013046 |  |  | 121565.54 | 120000 | 1565.54 | 1.3046
|  | 1400 | Smith - Misc. Steam Plant Additions & Imp. | VICKI | 1019584.14 | 400000 | 619584.14 | 1.549 | * |  | 1019584.14 | 400000 | 619584.14 | 154.896
|  | 1403 | SMITH 3A & 3B GAS TURBINES AIR FILTRATION SYSTEM | VICKI | 1618166.75 | 1250000 | 368166.75 | 0.29453 | * |  | 1618166.75 | 1250000 | 368166.75 | 29.4533
|  | 1405 | SMITH UNIT 1-NON ECRC COST OF REMOVAL ON SNCR UNIT 1 PROJECT | VICKI | 1177.27 | 0 | 1177.27 | 1 |  |  | 1177.27 | 0 | 1177.27 | 100
|  | 1419 | SMITH - REPLACE BELT SCALES & UNIT 2 FEEDERS | VICKI | 0 | 150000 | -150000 | -1 | * |  | 0 | 150000 | -150000 | -100
|  | 1421 | SMITH - U4 COMBUSTION CONTROLS REPLACEMENT | VICKI | 1958658.58 | 500000 | 1458658.58 | 2.9173 | * |  | 1958658.58 | 500000 | 1458658.58 | 291.7317
|  | 1438 | SMITH COMBINED CYCLE LTSA | VICKI | 34362399.46 | 23848029 | 10514370.46 | 0.44089 | * |  | 34362399.46 | 23848029 | 10514370.46 | 44.0891
|  | 1452 | SMITH UNIT 2-REPLACE HOT REHEAT PIPING | VICKI | 773611.34 | 999997 | -226385.66 | -0.22639 | * |  | 773611.34 | 999997 | -226385.66 | -22.6386
|  | 1465 | SMITH-UNIT 2 REPL DUCTWORK/EXPANSION JOINTS | VICKI | 368800.44 | 250000 | 118800.44 | 0.4752 | * |  | 368800.44 | 250000 | 118800.44 | 47.5202
|  | 1474 | SMITH UNIT 3 TURBINE BLADE | VICKI | 0 | 350000 | -350000 | -1 | * |  | 0 | 350000 | -350000 | -100
|  | 1488 | SMITH 1&2 REPLACE ASH VALVES | VICKI | 0 | 160000 | -160000 | -1 | * |  | 0 | 160000 | -160000 | -100
|  | 1500 | Daniel-Misc. Steam Plant Additions & Imp. | VICKI | 613082.25 | 499706 | 113376.25 | 0.22689 | * |  | 613082.25 | 499706 | 113376.25 | 22.6886
|  | 1503 | DANIEL 1 CWP MOTOR C05463 | VICKI | 0 | 73102 | -73102 | -1 | * |  | 0 | 73102 | -73102 | -100
|  | 1511 | DANIEL 1 ACE TWIP C05254 MS PE 2155 | VICKI | 223041.49 | 125750 | 97291.49 | 0.77369 | * |  | 223041.49 | 125750 | 97291.49 | 77.369
|  | 1515 | DANIEL 2 ACE TWIP C05348 MS PE 2185 | VICKI | -11856.74 | 0 | -11856.74 | 1 |  |  | -11856.74 | 133 | -11989.74 | -9014.8421
|  | 1531 | DANIEL 1 HP/IP TURBINE UPGRADE | VICKI | 5242781.39 | 5250496 | -7714.61 | -0.0014693 |  |  | 5242781.39 | 5250496 | -7714.61 | -0.14693
|  | 1532 | DANIEL 2 HP/IP TURBINE UPGRADE | VICKI | 26303.87 | 0 | 26303.87 | 1 | * |  | 26303.87 | 0 | 26303.87 | 100
|  | 1564 | DANIEL 2 CAPITAL VALVE REPLACEMENTS C03256 | VICKI | 399.75 | 0 | 399.75 | 1 |  |  | 399.75 |  | 399.75 | 100
|  | 1569 | DANIEL 2 HOT AIR HEATER BASKET | VICKI | 5017.97 | 0 | 5017.97 | 1 |  |  | 5017.97
|  | 1600 | SMITH 3 MISC REPLACEMENTS | VICKI | 1741564.41 | 1200000 | 541564.41 | 0.4513 | * |  | 1741564.41 | 1200000 | 541564.41 | 45.1304
|  | 1604 | SMITH TRACTOR SHED/SHOP | VICKI | 0 | 600000 | -600000 | -1 | * |  | 0 | 600000 | -600000 | -100
|  | 1607 | SMITH - INSTALL FISH EXCLUSION DEVICE | VICKI | 488316.74 | 400000 | 88316.74 | 0.22079 | * |  | 488316.74 | 400000 | 88316.74 | 22.0792
|  | 1611 | SMITH - U3 WATER LAB BUILDING REPL. | VICKI | 663788.79 | 0 | 663788.79 | 1 |  |  | 663788.79 |  | 663788.79 | 100
|  | 1651 | SMITH 1&2 BOBCAT TRACTOR REPLACEMENT | VICKI | 0 | 83000 | -83000 | -1 | * |  | 0 | 83000 | -83000 | -100
|  | 1656 | SMITH 1&2 REPLACE NO.1 AND TRIPPER BELTS | VICKI | 47063.62 | 66000 | -18936.38 | -0.28691 | * |  | 47063.62 | 66000 | -18936.38 | -28.6915
|  | 1672 | SMITH PROPERTY LINE FENCING | VICKI | 0 | 950000 | -950000 | -1 | * |  | 0 | 950000 | -950000 | -100
|  | 1679 | SMITH - U3 CORROSION PROJECT | VICKI | 239171.14 | 1000000 | -760828.86 | -0.76083 | * |  | 239171.14 | 1000000 | -760828.86 | -76.0829
|  | 1700 | Scherer-Misc. Additions & Improvements | VICKI | -824589.16 | 0 | -824589.16 | 1 | * |  | -824589.16 | 0 | -824589.16 | -100
|  | 1705 | SCHERER 3 SUPERHEATER OUTLET | VICKI | 341204.06 | 331750 | 9454.06 | 0.028498 |  |  | 341204.06 | 331750 | 9454.06 | 2.8498
|  | 1707 | SCHERER 3&4 RELOCATION OF FIRE HOUSE TRESTLE | VICKI | 67705 | 65000 | 2705 | 0.041615 |  |  | 67705 | 65000 | 2705 | 4.1615
|  | 1708 | SCHERER 3 PULVERIZER GEARBOX REPLACEMENT | VICKI | 0 | 128750 | -128750 | -1 | * |  | 0 | 128750 | -128750 | -100
|  | 1709 | SCHERER 3 HP TURBINE ROTOR | VICKI | 1372063.61 | 1134998 | 237065.61 | 0.20887 | * |  | 1372063.61 | 1134998 | 237065.61 | 20.8869
|  | 1716 | SCHERER PORTABLE EQUIPMENT | VICKI | 0 | 64974 | -64974 | -1 | * |  | 0 | 64974 | -64974 | -100
|  | 1717 | SCHERER LAND PURCHASE | VICKI | 3699.89 | 31250 | -27550.11 | -0.8816 | * |  | 3699.89 | 31250 | -27550.11 | -88.1604
|  | 1721 | SCHERER -TRACKED DOZER | VICKI | -17877.3 | 0 | -17877.3 | 1 | * |  | -17877.3 | 0 | -17877.3 | -100
|  | 1731 | SCHERER 3 VOLTAGE REGULATOR | VICKI | 0 | 74484 | -74484 | -1 | * |  | 0 | 74484 | -74484 | -100
|  | 1732 | SCHERER 3 FLYASH HOPPER | VICKI | 18396.57 | 51250 | -32853.43 | -0.64104 | * |  | 18396.57 | 51250 | -32853.43 | -64.1043
|  | 1733 | SCHERER 3 BOILER SONIC CLEANING EQUIP | VICKI | 28025.46 | 87500 | -59474.54 | -0.67971 | * |  | 28025.46 | 87500 | -59474.54 | -67.9709
|  | 1737 | SCHERER 3 REPLACE SERVICE WATER PIPING | VICKI | 1084.26 | 0 | 1084.26 | 1 |  |  | 1084.26 | 0 | 1084.26 | 100
|  | 1738 | SCHERER 3 REPLACE CONDENSER EXPANSION JOINTS | VICKI | 0 | 100000 | -100000 | -1 | * |  | 0 | 100000 | -100000 | -100
|  | 1739 | SCHERER 3 REPLACE GENERATOR 500KV BREAKER | VICKI | 411293.91 | 250000 | 161293.91 | 0.64518 | * |  | 411293.91 | 250000 | 161293.91 | 64.5176
|  | 1743 | SCHERER COMMON SERVICE WATER PIPING | VICKI | 2192.91 | 0 | 2192.91 | 1 |  |  | 2192.91 | 0 | 2192.91 | 100
|  | 1747 | SCHERER 3 BOILER WATER CIRC PUMP | VICKI | 80534.48 | 90140 | -9605.52 | -0.10656 |  |  | 80534.48 | 90140 | -9605.52 | -10.6562
|  | 1750 | SCHERER - MISC ADDITIONS AND IMPROVMENTS | VICKI | 439900.65 | 481664 | -41763.35 | -0.086706 |  |  | 439900.65 | 481664 | -41763.35 | -8.6706
|  | 1755 | SCHERER TRESTLE DUST SUPPRESSION COMMON | VICKI | 78174.77 | 0 | 78174.77 | 1 | * |  | 78174.77 |  | 78174.77 | 100
|  | 1757 | SCHERER 3 - REPLACE AIR HEATER BASKETS | VICKI | 404113.29 | 0 | 404113.29 | 1 | * |  | 404113.29 | 0 | 404113.29 | 100
|  | 1761 | SCHERER 3 CONDENSATE POLISHER | VICKI | 0 | 25016 | -25016 | -1 | * |  | 0 | 25016 | -25016 | -100
|  | 1763 | SCHERER 3 CYCLE ISOLATION VALVE | VICKI | 0 | 77500 | -77500 | -1 | * |  | 0 | 77500 | -77500 | -100
|  | 1766 | SCHERER 3 & 4 REPLACE 3D - DUSTLESS TRANSFER | VICKI | 4923.82 | 92877 | -87953.18 | -0.94699 | * |  | 4923.82 | 92877 | -87953.18 | -94.6986
|  | 1767 | SCHERER 3 & 4 INSTALL ELEVATOR AT C CRUSHER HOUSE | VICKI | 0 | 75000 | -75000 | -1 | * |  | 0 | 75000 | -75000 | -100
|  | 1769 | SCHERER 3 & 4 INSTALL SERVICE WATER LINE FOR DUST SUPPRESSIO | VICKI | 0 | 115628 | -115628 | -1 | * |  | 0 | 115628 | -115628 | -100
|  | 1770 | SCHERER COMMON INSTALL BACKUP CONTROL ROOM | VICKI | 0 | 56250 | -56250 | -1 | * |  | 0 | 56250 | -56250 | -100
|  | 1773 | SCHERER COMMON REPLACE COAL PILE RUN-OFF POND PIPING | VICKI | 86798.85 | 93751 | -6952.15 | -0.074155 |  |  | 86798.85 | 93751 | -6952.15 | -7.4155
|  | 1774 | SCHERER 3 REPLACE FRONT PENDANT REHEATER | VICKI | 73.39 | 0 | 73.39 | 1 |  |  | 73.39 |  | 73.39 | 100
|  | 1775 | SCHERER 3 REPLACE SOOTBLOWER CONTROLS | VICKI | 134623.17 | 160000 | -25376.83 | -0.15861 | * |  | 134623.17 | 160000 | -25376.83 | -15.8605
|  | 1784 | SCHERER 3 TRAVELING WATER SCREEN ON COOLING TOWER 369703 | VICKI | 44.45 | 0 | 44.45 | 1 |  |  | 44.45 |  | 44.45 | 100
|  | 1785 | SCHERER COMMON REVERSE OSMOSIS WATER TREATMENT PLANT | VICKI | 0 | 94069 | -94069 | -1 | * |  | 0 | 94069 | -94069 | -100
|  | 1786 | SCHERER 3 REPLACE COAL TRANSPORT LINES 369703 | VICKI | 5.61 | 0 | 5.61 | 1 |  |  | 5.61 |  | 5.61 | 100
|  | 1788 | SCHERER COMMON WINDBREAK DUST SUPPRESSION FENCE | VICKI | 0 | 50000 | -50000 | -1 | * |  | 0 | 50000 | -50000 | -100
|  | 1789 | SCHERER 3 REPLACE CONDENSATE MOTOR | VICKI | 64243.85 | 63000 | 1243.85 | 0.019744 |  |  | 64243.85 | 63000 | 1243.85 | 1.9744
|  | 1799 | SCHERER - INSTALL SECURITY SYSTEM | VICKI | -27.87 | 0 | -27.87 | 1 |  |  | -27.87 | 0 | -27.87 | -100
|  | 1811 | DANIEL 1 EXPANSION JOINTS C01693 | VICKI | 64477.74 | 68894 | -4416.26 | -0.064102 |  |  | 64477.74 | 68894 | -4416.26 | -6.4102
|  | 1814 | DANIEL 2 EXPANSION JOINTS C00435 & C00437 | VICKI | -8694.22 | 0 | -8694.22 | 1 |  |  | -8694.22 |  | -8694.22 | -100
|  | 1842 | DANIEL 1 GSU TRANSFORMER | VICKI | 30672.5 | 0 | 30672.5 | 1 | * |  | 30672.5 | 0 | 30672.5 | 100
|  | 1859 | DANIEL 1 LUBE OIL SKIDS ON ID FANS | VICKI | 77487.88 | 70584 | 6903.88 | 0.097811 |  |  | 77487.88 | 70584 | 6903.88 | 9.7811
|  | 1903 | CRIST AIR DRYER AND COMPRESSOR REPLACEMENT | VICKI | 17.71 | 0 | 17.71 | 1 |  |  | 17.71 | 0 | 17.71 | 100
|  | 1904 | CRIST COMMON TRAVELLING SCREENS | VICKI | 271506.87 | 0 | 271506.87 | 1 | * |  | 271506.87 | 0 | 271506.87 | 100
| TOTAL FOSSIL |  |  |  | 64550611.37 | 53696197 | 10854414.37 | 20.21% |  |  | 64550611.37 | 53696330 | 10854281.37 | 20.2142
RENEWABLES
|  | 90 | PERDIDO LANDFILL GAS TO ENERGY | VICKI | 5169600.56 | 2694900 | 2474700.56 | 91.83% | * |  | 5169600.56 | 2694900 | 2474700.56 | 91.829 |  | Budget moved from 2009
| TOTAL RENEWABLES |  |  |  | 5169600.56 | 2694900 | 2474700.56 | 91.83% |  |  | 5169600.56 | 2694900 | 2474700.56 | 91.829
TOTAL POWER GENERATION |  |  |  |  | 205241550.01 | 175240882 | 30000668.01 | 17.12% |  |  | 205241550.01 | 175241015 | 30000535.01 | 17.1196
POWER DELIVERY
NEW BUSINESS TRANSMISSION
|  | 2601 | TRANSMISSION LINE PROPERTY | SARAH | [6 empty] | 0 | 0 | 0 | 0
|  | 2603 | 2603 BUILD SHAKY JOE SWAMP TRANSMISSION SUBSTATION | SARAH | 240564.55 | 0 | 240564.55 | 100% | * |  | 240564.55 | 0 | 240564.55 | 100
| TOTAL NEW BUSINESS TRANSMISSION |  |  |  | 240564.55 | 0 | 240564.55 | 100% |  |  | 240564.55 | 0 | 240564.55 | #DIV/0!
NEW BUSINESS DISTRIBUTION
|  | 2553 | New Business Street Lights | HAL | 627761.69 | 500247 | 127514.69 | 25.49% | * |  | 627761.69 | 500247 | 127514.69 | 25.4903
|  | 2556 | Private Street & Yard Lights | HAL | 1611057.57 | 1496011 | 115046.57 | 7.69% |  |  | 1611057.57 | 1496011 | 115046.57 | 7.6902
|  | 2558 | Advanced Energy Management (AEM) | HAL | 1207224.82 | 2114294 | -907069.18 | -42.9% | * |  | 1207224.82 | 2114294 | -907069.18 | -42.9018 | Less installations than anticipated
|  | 2550 | Customer's Meters | PAUL | 1033241.97 | 500000 | 533241.97 | 106.6% | * |  | 1033241.97 | 500000 | 533241.97 | 106.6484
|  | 2551 | Line Transformers | PAUL | 6790685.03 | 6000000 | 790685.03 | 13.18% | * |  | 6790685.03 | 6000000 | 790685.03 | 13.1781
|  | 2552 | New Business Distribution | PAUL | 4152839.63 | 5126000 | -973160.37 | -18.98% | * |  | 4152839.63 | 5126000 | -973160.37 | -18.9848
|  | 2554 | NEW BUSINESS - UNDERGROUND | PAUL | 3560816.32 | 6404000 | -2843183.68 | -44.4% | * |  | 3560816.32 | 6404000 | -2843183.68 | -44.397 | **
|  | 2555 | ADVANCED METERING INFRASTRUCTURE | PAUL | 6062453.99 | 2609000 | 3453453.99 | 132.4% | * |  | 6062453.99 | 2609000 | 3453453.99 | 132.367 | **
|  | 2559 | METER TREATERS | PAUL | 186135.66 | 241000 | -54864.34 | -22.77% | * |  | 186135.66 | 241000 | -54864.34 | -22.7653
| TOTAL NEW BUSINESS DISTRIBUTION |  |  |  | 25232216.68 | 24990552 | 241664.68 | 0.967% |  |  | 25232216.68 | 24990552 | 241664.68 | 156.3252
OTHER TRANSMISSION
|  | 2801 | TRANS SUB INFRASTRUCTURE PROJECTS | SARAH | 4816524.78 | 3450000 | 1366524.78 | 39.61% | * |  | 4816524.78 | 3450000 | 1366524.78 | 39.6094 | **
|  | 2802 | TRANS LINE INFRASTRUCTURE PROJECT | SARAH | 4892605.16 | 3000000 | 1892605.16 | 63.09% | * |  | 4892605.16 | 3000000 | 1892605.16 | 63.0868 | **
|  | 2804 | Ft.Walton & Pensacola Trans Line Add. & Imp | SARAH | -26.14 | 0 | -26.14 | 100% |  |  | -26.14 | 0 | -26.14 | -100
|  | 2808 | SHOAL RIVER-SANTA ROSA 230KV NEW TL | SARAH | -694943.97 | 1806098 | -2501041.97 | -138.5% | * |  | -694943.97 | 1806098 | -2501041.97 | -138.4776
|  | 2809 | SINAI CEMETARY SUBSTATION UPGRADE | SARAH | 260.4 | 0 | 260.4 | 100% |  |  | 260.4 |  | 260.4 | 100
|  | 2810 | HIGHLAND CTY-MILLERS FERRY 115KV LINE REPL | SARAH | 727860.71 | 250000 | 477860.71 | 191.1% | * |  | 727860.71 | 250000 | 477860.71 | 191.1443
|  | 2814 | LAGUNA-SANTA ROSA 230KV CONVERSION | SARAH | 1168801.52 | 708107 | 460694.52 | 65.06% | * |  | 1168801.52 | 708107 | 460694.52 | 65.06
|  | 2821 | MILLER BAYOU 230/115 KV PWR SUPPLY | SARAH | 4.16 | 0 | 4.16 | 100% |  |  | 4.16 |  | 4.16 | 100
|  | 2822 | TRANS LINE SWITCH REPLACEMENT PROJECT 2006-2008 | SARAH | 4734.94 | 0 | 4734.94 | 100% |  |  | 4734.94 | 0 | 4734.94 | 100
|  | 2825 | SINAI CEMETERY 230 KV REACTOR | SARAH | 2287765.64 | 2000000 | 287765.64 | 14.39% | * |  | 2287765.64 | 2000000 | 287765.64 | 14.3883
|  | 2827 | LAGUNA 230 KV SUB 50MVA REACTOR | SARAH | 152864.03 | 0 | 152864.03 | 100% | * |  | 152864.03 | 0 | 152864.03 | 100
|  | 2828 | Glendale Prot & Control Sys Repl | SARAH | 24004.75 | 0 | 24004.75 | 100% | * |  | 24004.75 | 0 | 24004.75 | 100
|  | 2833 | LULLWATER LONG BEACH 115 KV RECONDUCTOR | SARAH | -4543 | 0 | -4543 | 100% |  |  | -4543 | 0 | -4543 | -100
|  | 2837 | WRIGHT RELAY MODERNIZATION 2015 | SARAH | 374339.69 | 602000 | -227660.31 | -37.82% | * |  | 374339.69 | 602000 | -227660.31 | -37.8173
|  | 2838 | WEWA PROTECTION AND CONTROL REPLACEMENT | SARAH | 519850.63 | 800000 | -280149.37 | -35.02% | * |  | 519850.63 | 800000 | -280149.37 | -35.0187
|  | 2843 | CALLAWAY 230 & 115KV PROT & CONTROL SYS REPL | SARAH | 111290.48 | 140000 | -28709.52 | -20.51% | * |  | 111290.48 | 140000 | -28709.52 | -20.5068
|  | 2845 | TRANSMISSION TOOLS & TEST EQUIPMENT (SGIG) | SARAH | 219406.67 | 0 | 219406.67 | 100% |  |  | 219406.67 |  | 219406.67 | 100
|  | 2846 | TRANSMISSION ROW CLEARING | SARAH | 630681.35 | 0 | 630681.35 | 100% | * |  | 630681.35 | 0 | 630681.35 | 100
|  | 2852 | BRENTWOOD 230/115KV AUTOBANK | SARAH | 8223491.56 | 9500000 | -1276508.44 | -13.44% | * |  | 8223491.56 | 9500000 | -1276508.44 | -13.4369
|  | 2853 | LAGUNA BEACH 230-115KV AUTOBANK | SARAH | 985175.92 | 0 | 985175.92 | 100% |  |  | 985175.92 |  | 985175.92 | 100
|  | 2854 | TRANS PILOT PROTECTIVE RELAY | SARAH | 2.56 | 0 | 2.56 | 100% |  |  | 2.56 |  | 2.56 | 100
|  | 2863 | Wright - Freedom Way 115kV Sub and Line | SARAH | 3131080.55 | 5549000 | -2417919.45 | -43.57% | * |  | 3131080.55 | 5549000 | -2417919.45 | -43.574 | **
|  | 2864 | Holmes Creek-Marianna 115KV Line Reconductor | SARAH | 0 | 50000 | -50000 | -100% | * |  | 0 | 50000 | -50000 | -100
|  | 2865 | BRENTWOOD-PINE FOREST 115KV RECONDUCTOR | SARAH | 2775674.21 | 3334000 | -558325.79 | -16.75% | * |  | 2775674.21 | 3334000 | -558325.79 | -16.7464
|  | 2867 | LAGUNA 115KV CAPACITOR BREAKER REPL | SARAH | 1558842.01 | 3616614 | -2057771.99 | -56.9% | * |  | 1558842.01 | 3616614 | -2057771.99 | -56.8977
|  | 2874 | SMITH-LAGUNA 230KV CONVERSION | SARAH | 2951818.73 | 216803 | 2735015.73 | 1262% | * |  | 2951818.73 | 216803 | 2735015.73 | 1261.5212 | **
|  | 2876 | BRENTWOOD- BAYOU CHICO 115KV RECONDUCTOR | SARAH | 335871.75 | 330000 | 5871.75 | 1.779% |  |  | 335871.75 | 330000 | 5871.75 | 1.7793
|  | 2882 | MOLINO - PINE FOREST 115KV RECONDUCTOR | SARAH | 673238.98 | 0 | 673238.98 | 100% | * |  | 673238.98 | 0 | 673238.98 | 100
|  | 2886 | RECONDUCTOR CRIST-BARRY 230KV LINE | SARAH | 328470.25 | 175000 | 153470.25 | 87.7% | * |  | 328470.25 | 175000 | 153470.25 | 87.6973
|  | 2894 | S CRESTVIEW RELAY S HOUSE REPL | SARAH | 1922.72 | 0 | 1922.72 | 100% |  |  | 1922.72 |  | 1922.72 | 100
|  | 2896 | SHOAL RVR 230/115KV RELAY S HOUSE REPL | SARAH | 1.04 | 0 | 1.04 | 1 |  |  | 1.04 |  | 1.04 | 100
| TOTAL OTHER TRANSMISSION |  |  |  | 36197072.08 | 35527622 | 669450.08 | 1.884% |  |  | 36197072.08 | 35527622 | 669450.08 | 1.8843
OTHER DISTRIBUTION
|  | 3401 | DIST SUB INFRASTRUCTURE PROJECTS | SARAH | 1332880.03 | 1000000 | 332880.03 | 33.29% | * |  | 1332880.03 | 1000000 | 332880.03 | 33.288
|  | 3402 | Misc. Distribution Improvements & Repl. | PAUL | 3927900.16 | 3388000 | 539900.16 | 15.94% | * |  | 3927900.16 | 3388000 | 539900.16 | 15.9357
|  | 3403 | Dist. Additions & Retir. Due to Hwy. Comm. | PAUL | 884307.5 | 1080000 | -195692.5 | -18.12% | * |  | 884307.5 | 1080000 | -195692.5 | -18.1197
|  | 3404 | Distribution Line Minor Projects | PAUL | 2040913.76 | 746000 | 1294913.76 | 173.6% | * |  | 2040913.76 | 746000 | 1294913.76 | 173.5809
|  | 3405 | Underground System Additions & Improve. | PAUL | 2664917.56 | 2163000 | 501917.56 | 23.2% | * |  | 2664917.56 | 2163000 | 501917.56 | 23.2047
|  | 3406 | DISTRIBUTION UNDERGROUND CONVERSIONS | PAUL | -1373140.7 | 852000 | -2225140.7 | -261.2% | * |  | -1373140.7 | 852000 | -2225140.7 | -261.1667 | **
|  | 3407 | MISC CAPITAL ACCRUALS | PAUL | -189819.44 | 0 | -189819.44 | 100% | * |  | -189819.44 | 0 | -189819.44 | -100
|  | 3408 | Distribution Improvements - Osmose | PAUL | 1484101.09 | 1300000 | 184101.09 | 14.16% | * |  | 1484101.09 | 1300000 | 184101.09 | 14.1616
|  | 3428 | JAY ROAD 115/12KV TX UPGRADE | SARAH | 261.55 | 0 | 261.55 | 100% |  |  | 261.55 | 0 | 261.55 | 100
|  | 3430 | BEACH HAVEN 115KV 30 MVAR CAP BANK | SARAH | [7 empty] | 0 | 0 | 0
|  | 3433 | NICEVILLE 115KV 30MVAR CAP BANK | SARAH | 0 | 150000 | -150000 | -100% | * |  | 0 | 150000 | -150000 | -100
|  | 3453 | DIST 12KV BREAKER REPLACEMENT PROGRAM 2006-2007 | SARAH | 5620.72 | 150000 | -144379.28 | -96.25% | * |  | 5620.72 | 150000 | -144379.28 | -96.2529
|  | 3461 | NAVARRE 115/12KV BANK #2 2007-2008 | SARAH | 63444.07 | 110000 | -46555.93 | -42.32% | * |  | 63444.07 | 110000 | -46555.93 | -42.3236
|  | 3462 | GRACEVILLE 30 MVAR CAPACITY BANK 2008-2009 | SARAH | 6139.19 | 0 | 6139.19 | 100% |  |  | 6139.19 | 0 | 6139.19 | 100
|  | 3469 | LULLWATER 115 KVCAPBANK | SARAH | 638 | 0 | 638 | 100% |  |  | 638 | 0 | 638 | 100
|  | 3475 | MOBILE TRANSFORMER | SARAH | 368970.64 | 0 | 368970.64 | 100% | * |  | 368970.64 | 0 | 368970.64 | 100
|  | 3476 | BEACH HAVEN RELAY MODERNIZATION 2008 | SARAH | 311045.78 | 490000 | -178954.22 | -36.52% | * |  | 311045.78 | 490000 | -178954.22 | -36.5213
|  | 3477 | VALPARAISO RELAY MODERNIZATION 2008 | SARAH | 1116.57 | 0 | 1116.57 | 100% |  |  | 1116.57 | 0 | 1116.57 | 100
|  | 3481 | GREENWOOD PROT & CONTROL SYS REPL | SARAH | 1076362.67 | 1540000 | -463637.33 | -30.11% | * |  | 1076362.67 | 1540000 | -463637.33 | -30.1063
|  | 3483 | GOULDING PROT & CONTROL SYS REPL | SARAH | 157227.43 | 0 | 157227.43 | 100% | * |  | 157227.43 | 0 | 157227.43 | 100
|  | 3491 | HENDERSON PARK SUB | SARAH | 49317.55 | 100000 | -50682.45 | -50.68% | * |  | 49317.55 | 100000 | -50682.45 | -50.6825
|  | 3498 | SMART GRID | PAUL | 2713239.67 | 0 | 2713239.67 | 100% | * |  | 2713239.67 | 0 | 2713239.67 | 100
|  | 3499 | NEW ELECTRIC NETWORK | PAUL | 0 | 2840000 | -2840000 | -100% | * |  | 0 | 2840000 | -2840000 | -100 | **
|  | 3500 | ASSET MANAGEMENT IMPROVEMENT PROGRAMS | PAUL | 1222901.31 | 1798000 | -575098.69 | -31.99% | * |  | 1222901.31 | 1798000 | -575098.69 | -31.9855
|  | 3501 | Misc Distribution Line Specific Feeder Improvs | PAUL | 69115.21 | 900000 | -830884.79 | -92.32% | * |  | 69115.21 | 900000 | -830884.79 | -92.3205
|  | 3502 | SHOAL RIVER OCB 9812 | PAUL | -24563.94 | 0 | -24563.94 | 100% | * |  | -24563.94 | 0 | -24563.94 | -100
|  | 3512 | BLACKWATER SUB - OCB 5612 RECONDUCTOR | PAUL | 159528.9 | 253000 | -93471.1 | -36.95% | * |  | 159528.9 | 253000 | -93471.1 | -36.9451
|  | 3517 | CRYSTAL BEACH SUB - CONSTRUCT NEW 795 FEEDER | PAUL | 432441.95 | 297000 | 135441.95 | 45.6% | * |  | 432441.95 | 297000 | 135441.95 | 45.6034
|  | 3518 | JAY ROAD 7252 RECONDUCTOR | PAUL | -153785.01 | 0 | -153785.01 | 100% | * |  | -153785.01 | 0 | -153785.01 | -100
|  | 3609 | REDWOOD SUB OCB 8702 RECONDUCTOR & WATSON BAYOU | PAUL | -37319.48 | 0 | -37319.48 | 100% | * |  | -37319.48 | 0 | -37319.48 | -100
|  | 3630 | BEACH HAVEN SUB OCB 6052 FDR IMPROVMENT | PAUL | -189695.34 | 0 | -189695.34 | 100% | * |  | -189695.34 | 0 | -189695.34 | -100
|  | 3633 | WEST PERDIDO KEY CROSSING ENHANCEMENTS | PAUL | 254211.05 | 0 | 254211.05 | 100% | * |  | 254211.05 | 0 | 254211.05 | 100
|  | 3639 | PANAMA CITY AIRPORT SUBSTATION FEEDER | PAUL | 87223.71 | 0 | 87223.71 | 100% | * |  | 87223.71 | 0 | 87223.71 | 100
|  | 3640 | SPANISH MILL SUBSTATION-ECUA FEEDERS | PAUL | -10229.05 | 0 | -10229.05 | 100% | * |  | -10229.05 | 0 | -10229.05 | -100
|  | 3642 | CHIPLEY 9202 - PHASE ADDITION | PAUL | 233428.94 | 175000 | 58428.94 | 33.39% | * |  | 233428.94 | 175000 | 58428.94 | 33.388
|  | 3650 | STORM SUPPORT - OVERHEAD | PAUL | 9733.37 | 0 | 9733.37 | 100% |  |  | 9733.37 | 0 | 9733.37 | 100
|  | 3651 | STORM SUPPORT - UNDERGROUND | PAUL | 1347.1 | 0 | 1347.1 | 100% |  |  | 1347.1 | 0 | 1347.1 | 100
|  | 3652 | STORM HARDENING - OVERHEAD | PAUL | 613253.2 | 700000 | -86746.8 | -12.39% | * |  | 613253.2 | 700000 | -86746.8 | -12.3924
|  | 3653 | STORM HARDENING - JOINT USE | PAUL | 0 | 300000 | -300000 | -100% | * |  | 0 | 300000 | -300000 | -100
|  | 3655 | BRENTWOOD SUB - OCB 6774 FEEDER IMP | PAUL | [8 empty] | 0 | 0
|  | 3691 | EAST HILL SUB CONVERT 2 - 4KV FDR 12/4KV TO 12KV | PAUL | 217720.4 | 409000 | -191279.6 | -46.77% | * |  | 217720.4 | 409000 | -191279.6 | -46.7676
|  | 3693 | DEVILLIERS SUB OCB 7414 REPLACE 20 PROTECTORS | PAUL | 328038.32 | 311000 | 17038.32 | 5.479% |  |  | 328038.32 | 311000 | 17038.32 | 5.4786
| TOTAL OTHER DISTRIBUTION |  |  |  | 18738794.44 | 21052000 | -2313205.56 | -10.99% | * |  | 18738794.44 | 21052000 | -2313205.56 | -10.9881
JOINT SUB. & DIST. LINE
|  | 3700 | System Reactive Corrective Capacity | PAUL | 548535.08 | 373000 | 175535.08 | 47.06% | * |  | 548535.08 | 373000 | 175535.08 | 47.0603 |  |  | *
|  | 3702 | CIRCUIT SWITCHER IMPR - TS (2004-2008) | SARAH | 103202.29 | 250000 | -146797.71 | -58.72% | * |  | 103202.29 | 250000 | -146797.71 | -58.7191
|  | 3713 | DUKE FIELD 115/12 KV NEW SUB AND FEEDER | SARAH | 2345.63 | 100000 | -97654.37 | -97.65% | * |  | 2345.63 | 100000 | -97654.37 | -97.6544 |  |  | *
|  | 3727 | HINSON'S CROSSROADS BANK ADDITION (NEW) | SARAH | 1989653.88 | 2000000 | -10346.12 | -0.5173% |  |  | 1989653.88 | 2000000 | -10346.12 | -0.51731
|  | 3731 | LULLWATER SUB BANK ADDITION (NEW) | SARAH | 774682.19 | 1200000 | -425317.81 | -35.44% | * |  | 774682.19 | 1200000 | -425317.81 | -35.4432
|  | 3742 | EMS TRANS SYSTEM ADD AND IMPROVMENTS | SARAH | 346202.58 | 721000 | -374797.42 | -51.98% | * |  | 346202.58 | 721000 | -374797.42 | -51.983
|  | 3745 | JAY ROAD BANK UPGRADE | SARAH | 452986.52 | 500000 | -47013.48 | -9.403% |  |  | 452986.52 | 500000 | -47013.48 | -9.4027 |  |  | *
|  | 3747 | PANAMA CITY AIRPORT SUB | SARAH | 938.25 | 50000 | -49061.75 | -98.12% | * |  | 938.25 | 50000 | -49061.75 | -98.1235
|  | 3751 | SANTA ROSA MIRAMAR 115KV LINE #2 | SARAH | 80.73 | 0 | 80.73 | 100% |  |  | 80.73 |  | 80.73 | 100
|  | 3752 | FAIRFIELD RING BUS | SARAH | 1887342.52 | 3800000 | -1912657.48 | -50.33% | * |  | 1887342.52 | 3800000 | -1912657.48 | -50.3331
|  | 3753 | HOLIDAY NEW SUB 2009 | SARAH | 314056.74 | 2735333 | -2421276.26 | -88.52% | * |  | 314056.74 | 2735333 | -2421276.26 | -88.5185
|  | 3754 | ECUA 230/12 KV NEW SUB NEW FDR | SARAH | 510204.94 | 200000 | 310204.94 | 155.1% | * |  | 510204.94 | 200000 | 310204.94 | 155.1025
|  | 3755 | JAY ROAD BANK UPGRADE (SGIG) | SARAH | -70150.18 | 0 | -70150.18 | 100% |  |  | -70150.18 |  | -70150.18 | -100
|  | 3756 | FAIRFIELD RING BUS (SGIG) | SARAH | 513474.05 | 0 | 513474.05 | 100% |  |  | 513474.05 |  | 513474.05 | 100
| TOTAL JOINT SUB. & DIST. LINE |  |  |  | 7373555.22 | 11929333 | -4555777.78 | -38.19% |  |  | 7373555.22 | 11929333 | -4555777.78 | -38.1897
TOTAL POWER DELIVERY |  |  |  |  | 87782202.97 | 93499507 | -5717304.03 | -6.115% |  |  | 87782202.97 | 93499507 | -5717304.03 | -6.1148
GENERAL PLANT
FLEET
|  | 4304 | Automobiles, Auto Trucks & Equip. | ALLISON Bryant | 1956859.66 | 1700000 | 256859.66 | 15.11% | * |  | 1956859.66 | 1700000 | 256859.66 | 15.1094
`
| TOTAL FLEET |  |  |  | 1956859.66 | 1700000 | 256859.66 | 15.11% | * |  | 1956859.66 | 1700000 | 256859.66 | 15.1094
TELECOMMUNICATIONS
|  | 4305 | WIRELESS SYSTEMS | DEBBIE | 116269.88 | 125000 | -8730.12 | -6.984% |  |  | 116269.88 | 125000 | -8730.12 | -6.9841 | 4305
|  | 4310 | VOICE & DATA CONVERGED NETWORK | DEBBIE | 724530.25 | 800000 | -75469.75 | -9.434% |  |  | 724530.25 | 800000 | -75469.75 | -9.4337 | 4310
|  | 4311 | TRANSPORT NETWORK ADD/IMPROVE | DEBBIE | 283176.16 | 216800 | 66376.16 | 30.62% | * |  | 283176.16 | 216800 | 66376.16 | 30.6163 | 4311
|  | 4385 | FIELD COMPUTERS | DEBBIE | 79057.34 | 70000 | 9057.34 | 12.94% |  |  | 79057.34 | 70000 | 9057.34 | 12.9391 | 4385
| TOTAL TELECOMMUNICATIONS |  |  |  | 1203033.63 | 1211800 | -8766.37 | -0.7234% |  |  | 1203033.63 | 1211800 | -8766.37 | -0.72342
CORPORATE SERVICES
|  | 4300 | Office Furniture & Mechanical Equip. | BARBARA | 76912.32 | 0 | 76912.32 | 100% | * |  | 76912.32 | 0 | 76912.32 | #DIV/0! |  | 30 offset by other Pes for ice machines & environ detctors. 24k budget exception for cafeteria work
|  | 4302 | Misc. Buildings, Land, and Equip. | BARBARA | 73021.13 | 71740 | 1281.13 | 1.786% |  |  | 73021.13 | 71740 | 1281.13 | 1.7858 |  | For VMC generator off set by PD 4304
|  | 4303 | Security | BARBARA | -35033.1 | -40705 | 5671.9 | -13.93% |  |  | -35033.1 | -40705 | 5671.9 | -13.9342 |  | 6k to cover security system for new vp
|  | 4306 | AV Equip/Print Services | BARBARA | 177335.02 | 0 | 177335.02 | 100% | * |  | 177335.02 | 0 | 177335.02 | 100 |  | Offset by PD PE 2552
|  | 4345 | MILTON LINE SV & WHSE ROOF | BARBARA | 139321.82 | 155860 | -16538.18 | -10.61% | * |  | 139321.82 | 155860 | -16538.18 | -10.6109 |  | Less than expected use to offset other pe's
|  | 4347 | PINE FOREST ADMIN WHS & LS ROOF | BARBARA | 7009.19 | 5400 | 1609.19 | 29.8% |  |  | 7009.19 | 5400 | 1609.19 | 29.7998
| TOTAL CORPORATE SERVICES |  |  |  | 438566.38 | 192295 | 246271.38 | 128.1% |  |  | 438566.38 | 192295 | 246271.38 | 128.0696 |  | 150k and 48K OFFSET BY POWER DELIVERY PE 43042554, 2552 & 24K BUDGET EXCEPTION
OTHER
|  | 4301 | Tools, Implements and Test Equip. 5 Yr (Depreciate) | PAUL | 669691.19 | 358000 | 311691.19 | 87.06% | * |  | 669691.19 | 358000 | 311691.19 | 87.0646
|  | 4308 | POWER DELIVERY TECHNOLOGY IMPROVEMENTS | PAUL | 629522.32 | 709000 | -79477.68 | -11.21% | * |  | 629522.32 | 709000 | -79477.68 | -11.2098
|  | 4344 | T&D WAREHOUSE EQUIPMENT REPLACEMENT | ALLISON BEATY | 171860.3 | 150000 | 21860.3 | 14.57% | * |  | 171860.3 | 150000 | 21860.3 | 14.5735
|  | 4376 | GLSCAPE AND MRO | CAROL | 2934106.21 | 2232097 | 702009.21 | 31.45% | * |  | 2934106.21 | 2232097 | 702009.21 | 31.4507
|  | 4378 | POWER CONTROL CENTER | SARAH | 246600.05 | 365000 | -118399.95 | -32.44% | * |  | 246600.05 | 365000 | -118399.95 | -32.4383
|  | 4379 | ECCR-PURCHASE THERMAL IMAGE TOOLS | HAL | 1.58 | 0 | 1.58 | 100% |  |  | 1.58 | 0 | 1.58 | 100
|  | 4400 | TRANSMISSION TOOLS & TEST EQUIPMENT | SARAH | 1258077.91 | 50000 | 1208077.91 | 2416% | * |  | 1258077.91 | 50000 | 1208077.91 | 2416.1558
|  | 4779 | Plant Transfer |  | 0 | 0 | 0 | 0% |  |  | 0 | 0 | 0 | 0
|  | 4785 | ACCRUED PAYROLL |  | 18272.29 | 0 | 18272.29 | 100% | * |  | 18272.29 | 0 | 0 | 0
|  | 4790 | UNASS OVERHEADS |  | 85025.22 | 0 | 85025.22 | 100% | * |  | 85025.22 | 0 | 18272.29 | 100
| TOTAL OTHER |  |  |  | 6013157.07 | 3864097 | 2149060.07 | 55.62% |  |  | 6013157.07 | 3864097 | 2149060.07 | 55.6161
TOTAL GENERAL PLANT |  |  |  |  | 9611616.74 | 6968192 | 2643424.74 | 37.94% |  |  | 9611616.74 | 6968192 | 2643424.74 | 37.9356
NON-UTILITY
|  | 4999 | NEW PRODUCTS AND SERVICES | HAL | 203338.78 | 264353 | -61014.22 | -23.08% | * |  | 203338.78 | 264353 | -61014.22 | -23.0806
TOTAL NON-UTILITY |  |  |  |  | 203338.78 | 264353 | -61014.22 | -23.08% |  |  | 203338.78 | 264353 | -61014.22 | -23.0806
TOTAL CAPITAL |  |  |  |  | 302838708.5 | 275972934 | 26865774.5 | 9.735% |  |  | 302838708.5 | 275973067 | 26865641.5 | 9.7349
* YTD VARIANCE EXPLANATION NEEDED EACH QUARTER IF YTD VARIANCE EXCEEDS 10% OR $250,000, WHICHEVER IS LESS. (LESS THAN $10,000 DOES NOT REQUIRE AN EXPLANATION) FOR NON-QUARTER MONTHS, EXPLAIN VARIANCES OVER $250,000 ONLY.

## Summary
Gulf Power Company
December 2010
Year-to-Date Capital Expenditures
Thousands of Dollars
| Year-to-Date | [6 empty] | Re-Estimated | Estimated
|  |  |  | Variance |  |  | Original | 2010 | Year-End
Business Unit | Actual |  | Budget | $ | % |  | Budget | Expenditures | Variance
Power Generation:
New Generation Projects | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Environmental | 135521.3381 |  | 118849.785 | 16671.5531 | 14.0274 |  | 118849.785 | 135521.3381 | 16671.5531 | 56980.612 | 68870.79 | 1000 | 68439 | -67082.3381
Production Modifications | 0 |  | 0 |  |  |  |  | 0 | 0
Fossil Steam & CT | 64550.6114 |  | 53696.197 | 10854.4144 | 20.2145 |  | 53696.33 | 64550.6114 | 10854.2814 | 19651.941 | 23677.361 |  | 24997 | -39553.6114
Renewables | 5169.6006 |  | 2694.9 | 2474.7006 | 91.829 |  | 2694.9 | 5169.6006 | 2474.7006
Hydro | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Nuclear | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Nuclear Fuel | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Total Power Generation | 205241.55 |  | 175240.882 | 30000.668 | 17.1197 |  | 175241.015 | 205241.55 | 30000.535
Power Delivery:
Transmission | 36437.6366 |  | 35527.622 | 910.0146 | 2.5614 |  | 35527.622 | 36437.6366 | 910.0146 | 8819.661 | 17494.01 |  | 9834 | -26603.6366
Distribution | 43971.0111 |  | 46042.552 | -2071.5409 | -4.4992 |  | 46042.552 | 43971.0111 | -2071.5409 | 44661.999 | 31749.943 |  | 56625 | 12653.9889
Joint Sub. & Dist. Lines | 7373.5552 |  | 11929.333 | -4555.7778 | -38.1897 |  | 11929.333 | 7373.5552 | -4555.7778 | 3213.913 | 4511 |  | 3562 | -3811.5552
Total Power Delivery | 87782.203 |  | 93499.507 | -5717.304 | -6.1148 |  | 93499.507 | 87782.203 | -5717.304
General Plant:
Fleet | 1956.8597 |  | 1700 | 256.8597 | 15.1094 |  | 1700 | 1956.8597 | 256.8597 | 2856.497 | 2929 |  | 3083 | 1126.1403
Telecommunications | 1203.0336 |  | 1211.8 | -8.7664 | -0.72342 |  | 1211.8 | 1203.0336 | -8.7664 | 688.287 | 1714.189 |  | 1794 | 590.9664
Corporate Services | 438.5664 |  | 192.295 | 246.2714 | 128.0696 |  | 192.295 | 438.5664 | 246.2714 | 911.3 | 1088.002 |  | 1091 | 652.4336
Other | 6013.1571 |  | 3864.097 | 2149.0601 | 55.6161 |  | 3864.097 | 6013.1571 | 2149.0601 | 707.834 | 1037.325 |  | 1357 | -4656.1571
Total General | 9611.6167 |  | 6968.192 | 2643.4247 | 37.9356 |  | 6968.192 | 9611.6167 | 2643.4247
Other | 203.3388 |  | 264.353 | -61.0142 | -23.0806 |  | 264.353 | 203.3388 | -61.0142 | 342.796 | 526.006 |  | 452.4 | 249.0612
Total Capital | 302838.7085 |  | 275972.934 | 26865.7745 | 9.7349 |  | 275973.067 | 302838.7085 | 26865.6415 |  |  |  |  | -126434.7079
| 0 |  | 0 | 0 |  |  | 0 | 0 | 0
176404.0006
January Year-to-date
[5 empty] | Original | Year-end
| Actual |  | Budget | Variance | Budget | Variance
Power Generation:
Environmental | 135521.3381 |  | 118849.785 | 16671.5531 | 118849.785 | 16671.5531
Fossil Steam, CT & Other | 69720.2119 |  | 56391.097 | 13329.1149 | 56391.23 | 13328.9819
Total Power Generation | 205241.55 |  | 175240.882 | 30000.668 | 175241.015 | 30000.535
Power Delivery:
Transmission | 36437.6366 |  | 35527.622 | 910.0146 | 35527.622 | 910.0146
Lighting & AEM | 3446.0441 |  | 4110.552 | -664.5079 | 4110.552 | -664.5079
AMI | 6062.454 |  | 2609 | 3453.454 | 2609 | 3453.454
Transformers | 6790.685 |  | 6000 | 790.685 | 6000 | 790.685
NB - UG | 3560.8163 |  | 6404 | -2843.1837 | 6404 | -2843.1837
NB - Other | 5372.2173 |  | 5867 | -494.7827 | 5867 | -494.7827 | NB (OH) & Meters
New Business Distribution | 25232.2167 |  | 24990.552 | 241.6647 | 24990.552 | 241.6647
Other Distribution | 18738.7944 |  | 21052 | -2313.2056 | 21052 | -2313.2056
Joint Sub. & Dist. Lines | 7373.5552 |  | 11929.333 | -4555.7778 | 11929.333 | -4555.7778
Total Power Delivery | 87782.203 |  | 93499.507 | -5717.304 | 93499.507 | -5717.304
Total General & Other | 9814.9555 |  | 7232.545 | 2582.4105 | 7232.545 | 2582.4105
Total Capital | 302838.7085 |  | 275972.934 | 26865.7745 | 275973.067 | 26865.6415
January Year-to-date
[5 empty] | Original | Year-end
| Actual |  | Budget | Variance | Budget | Variance
Other Environmental:
Crist Scrubber | 1387.7539 |  | 0 | 1387.7539 | 2000.004 | -309.3919
Crist 6 SCR | 1690.6121 |  | 2000.004 | -309.3919 | 31156.47 | 19203.8849
Crist Water Conservation | 1.2874 |  | 0 | 1.2874 | 0 | 1.2874
Scherer SCR | #REF! |  | #REF! | #REF! | #REF! | #REF!
Scherer Scrubber | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Scherer Baghouse | #REF! |  | #REF! | #REF! | #REF! | #REF!
Scherer Other Envion. | #REF! |  | #REF! | #REF! | #REF! | #REF!
Other | #REF! |  | #REF! | #REF! | #REF! | #REF!
Total Other Environmental | #REF! |  | #REF! | #REF! | #REF! | #REF!
Fossil Steam, CT & Other:
Scherer Misc Additions | #REF! |  | #REF! | #REF! | #REF! | #REF!
Smith LTSA | 67.705 |  | 65 | 2.705 | 65 | 65
Perdido Landfill | 5169.6006 |  | 2694.9 | 2474.7006 | 2694.9 | -2753.464
Other | #REF! |  | #REF! | #REF! | #REF! | #REF!
Total Fossile Steam, CT & Other | #REF! |  | #REF! | #REF! | #REF! | #REF!
January Year-to-Date
[5 empty] | Original | Year-end
| Actual |  | Budget | Variance | Budget | Variance
Transmission:
Trans. Sub Infrastructure | 9709.1299 |  | 6450 | 3259.1299 | 6450 | 3259.1299
Shoal River 115KV | 152.864 |  | 0 | 152.864 | 0 | 152.864
Devillers-Goulding 115KV | 374.3397 |  | 602 | -227.6603 | 602 | -227.6603
Lullwater LB 115KV Rec. | 2775.6742 |  | 3334 | -558.3258 | 3334 | -558.3258
Transm ROW Clearing | 328.4703 |  | 175 | 153.4702 | 175 | 153.4702
Brentwood-Bayou Chico 115KV | #REF! |  | #REF! | #REF! | #REF! | #REF!
Other | #REF! |  | #REF! | #REF! | #REF! | #REF!
Total Transmission | #REF! |  | #REF! | #REF! | #REF! | #REF!
January Year-to-Date
[5 empty] | Original | Year-end
| Actual |  | Budget | Variance | Budget | Variance
New Business Distribution:
Lighting & AEM | 3446.0441 |  | 4110.552 | -664.5079 | 4110.552 | -664.5079
AMI | 6062.454 |  | 2609 | 3453.454 | 2609 | 3453.454
Transformers | 6790.685 |  | 6000 | 790.685 | 6000 | 790.685
NB - UG | 3560.8163 |  | 6404 | -2843.1837 | 6404 | -2843.1837
NB - Other | 5372.2173 |  | 5867 | -494.7827 | 5867 | -494.7827
Total NB Distribution | 25232.2167 |  | 24990.552 | 241.6647 | 24990.552 | 241.6647
Distribution (Non-NB):
Misc Distribution Improvement | 6145.0877 |  | 5468 | 677.0877 | 5468 | 677.0877
Distribution Line Minor Proj. | 2040.9138 |  | 746 | 1294.9138 | 746 | 1294.9138
Underground System Adds. | 1291.7769 |  | 3015 | -1723.2231 | 3015 | -1723.2231
Lullwater 115KV Capbank | 0 |  | 2840 | -2840 | 2840 | -2840
West Perdido Key Enh. | #REF! |  | #REF! | #REF! | #REF! | #REF!
Storm Support - UG | #REF! |  | #REF! | #REF! | #REF! | #REF!
Storm Hardening | #REF! |  | #REF! | #REF! | #REF! | #REF!
Devillers Sub | #REF! |  | #REF! | #REF! | #REF! | #REF!
Other | #REF! |  | #REF! | #REF! | #REF! | #REF!
Total Distribution (Non-NB) | #REF! |  | #REF! | #REF! | #REF! | #REF!

## FINPLAN (hidden)
Capital Expenditures -- Gulf Power Company
(Thousands of Dollars)
Non-SWE
SWE Retail SWE Wholesale | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Current Year
1) Generation
New Regulated F/H Generation | Jan: 0 | 0
New Unregulated F/H Generation (SWE Wholesale) | Jan: 0 | 0
New Unregulated F/H Generation (SWE Retail) | Jan: 0 | 0
Total New Generation | Jan: 0 | 0
Regulated F/H Generation: Retrofits | Jan: 64550.6114 | 64550.6114
Nuclear Generation: Retrofits | Jan: 0 | 0
Total Generation: Retrofits | Jan: 64550.6114 | 64550.6114
Regulated Generation: Environmental | Jan: 135521.3381 | 135521.3381
Total Generation | 200071.9494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200071.9494
2) Nuclear Fuel
Farley | Jan: 0
Hatch | Jan: 0
Vogle | Jan: 0
Total Nuclear Fuel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3) Transmission
New Generation Connections | Jan: 0
Other | Jan: 43570.6273
Total Transmission | 43570.6273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4) Distribution
New Business | Jan: 0
Other | Jan: 43971.0111
Total Distribution | 43971.0111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5) General Plant & Miscellaneous
Buildings | Jan: 438.5664
Fleet | Jan: 1956.8597
Telecommunications | Jan: 1203.0336
Other | Jan: #REF!
Total General Plant & Miscellaneous | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unallocated Changes to Capital ** | Jan: 0
Latest Projection (Sum Above) | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200071.9494
Official Budget | Jan: 31175.061 | 277958
Difference | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -77886.0505
Total from Capital Expenditures Report | Jan: 302838.7085
Variance | Jan: #REF!
Note on C30: CTEHRANI: Add EMS with "D" disp code

## Variance Explanation
Gulf Power Company
December 2010
YTD / Proforma Capital Variance Explanation
Thousands of Dollars
Business Unit | YTD Variance Amount |  | Variance Explanation |  |  | Estimated Year-End Variance
Power Generation: |  |  | Power Generation (Environmental)
New Generation Projects | 0 |  | 0 | 1551 | ECRC-AIR-DANIEL 1 & 2 SCRUBBER - Timing Issue. Dollars going to PS&I. Certificate filed with MPSC in July. | 0
Environmental | 16671.5531 | * | 0 | 1601 | ECRC-WATER SMITH RECLAIMED WATER PROJECT UNIT3 - Underrun due to delay in project start. | 16671.5531 | 1462 | -2740000
Production Modifications | 0 |  | 1387.7539 | 1256 | ECRC - CRIST 6 & 7 BY PASS STACK CEMS EQUIP - Timing Issue | 0 | 1438 | -1338000
Fossil Steam & CT | 10854.4144 | * | 0 | 1222 | ECRC-AIR-CRIST SCRUBBER - Increased material need and increased punchlist scope. | 10854.2814 | 1634 | 700000
Renewables | 2474.7006 |  | 0 | 1279 | ECRC-AIR-CRIST 6 SCR - Scope increase - Lime injection. Majority of dollars moved from 2011. | 2474.7006
Hydro | 0 |  |  |  |  | 0 | 1644 | 150000
Nuclear | 0 |  | 1387.7539 |  |  | 0 | 1645 | 300000
Nuclear Fuel | 0 |  |  |  |  | 0 | 2899 | -4239000
Total Power Generation | 30000.668 |  | Power Generation (Fossil Steam & CT & Renewables) |  |  | 30000.535
|  |  | 2474.7006 | 90 | PERDIDO LANDFILL GAS TO ENERGY - Over budget due to 2010 budget error. Will be over budget at YE $2.7M.
Power Delivery: |  |  | 0 | 1438 | SMITH COMBINED CYCLE LTSA - Approved increase due to A & B rotor change-outs.
Transmission | 910.0146 |  |  |  |  | 910.0146
Distribution | -2071.5409 |  | 2474.7006 |  |  | -2071.5409
Joint Sub. & Dist. Lines | -4555.7778 |  |  |  |  | -4555.7778
Total Power Delivery | -5717.304 | * | Power Delivery |  |  | -5717.304
|  |  | 0 | 2863 | WRIGHT-FREEDOM WAY 115kV SUB & LINE - TL - Project delayed due to contract signing issues.
|  |  | 0 | 2867 | LAGUNA 115KV CAPACITOR BREAKER REPL - Activities are behind schedule.
|  |  | 0 | 3499 | NEW ELECTRIC NETWORK - Budgeted in wrong PE. Dollars will be charged to PE 3498 Smart Grid.
|  |  | 0 | 2554 | NEW BUSINESS - UNDERGROUND - Under due to customer growth.
|  |  | 0 | 3406 | DISTRIBUTION UNDERGROUND CONVERSIONS - CIAC and DSO Stripoff have caused this PE to be under budget.
|  |  | 0 | 2808 | SHOAL RIVER-SANTA ROSA 230KV NEW TL - Changes in project need, scope and activities under review. No additional charges in 2010.
General Plant: |  |  | 0 | 3752 | FAIRFIELD RING BUS - Dollars spent in advance in 2009, causing 2010 underage.
|  |  | 0 | 2852 | BRENTWOOD 230/115KV AUTOBANK - Timing issue.
|  |  | 0 | 3404 | Distribution Line Minor Projects - System requirements. Will offset in another PE.
Fleet | 256.8597 |  | 0 | 2551 | Line Transformers - Timing issue. | 256.8597 | 1500
Telecommunications | -8.7664 |  | 0 | 2802 | TRANS LINE INFRASTRUCTURE PROJECT - Additional work for storm hardening. | -8.7664
Corporate Services | 246.2714 |  | 2713.2397 | 3498 | SMART GRID - Dollars budgeted in PE 3499 will primarily offset by year end. | 246.2714
Other | 2149.0601 |  | 2713.2397 |  |  | 2149.0601
Total General | 2643.4247 | * |  |  |  | 2643.4247
General Plant and Other
Other | -61.0142 | * | 0 | 4376 | GLSCAPE & MRO - over run due to delay in implementation & extra costs seen until all OPCO's have implemented. | -61.0142
|  |  | 0 | 4304 | Automobiles, Auto Trucks & Equip. - Timing issue.
Total Capital | 26865.7745 |  | 0 |  |  | 26865.6415
| 0 |  |  |  |  | 0 | 1259 | 200000
[7 empty] | 1224 | 550000
[7 empty] | 1215 | 400000
-1030000
30000