A Turnkey or Lump Sum contract contains terms of payment where the Company agrees to pay the contractor a mutually agreed to, pre-determined, fixed price for the performance of the contracted scope of work.  The agreed to fixed price covers the contractor’s expenses, overhead, and profit.

In a turnkey or lump sum contract:

- The maximum risk of failure is on the contractor

- The contractor has the greater incentive to cut costs

- Both parties have a minimum administrative burden

- The contractor may or may not make a profit

- The contractor has definite specifications

- Default by the contractor is always a possibility during any phase of work

The contract administrator’s primary responsibility is to ensure that the Company gets what it is paying for – a safe project and a quality product completed, as scheduled, within the fixed contract price.

Monitoring the quality of work and schedule, along with continuous communication with the contractor is very important when administering a turnkey or lump sum contract.

The matrix below provides the contract administrator a suggested guide on duties that should be performed.  Every task in the matrix may or may not apply depending upon the contract.

| What to do… | Guidelines |
| --- | --- |
| Learn Your Contract | Write a contract summary – Summarize scope, list contractor responsibilities, list contractor contacts, list Company responsibilities, list important milestones or scheduled events, list documents needed for controls, and attach it to the front of your copy of the contract. Make sure you clearly understand the quality specifications and the schedule requirements. |
| Establish a Quality Inspection Procedure | Quality inspection requirements will be based on a variety of factors. Determine what testing or documentation will be required to ensure that the specifications are being followed. Generally, your inspection procedure should take into account the following concerns: - Inferior or substandard workmanship - Inferior equipment or materials - Cost cutting attempts by the contractor that could affect work product - Work performed by the contractor that could damage Company property or cause unnecessary change orders to the contractor’s benefit - Company materials may be wasted, stolen, or misused |

| What to do… | Guidelines |
| --- | --- |
| Maintain a Log | Maintain a daily diary or a log sheet and record: - General project progress - Inspection times and findings - Unusual happenings related to the contract - Meetings or telephone conversations with contractor personnel - Weather |
| Conduct Pre-work Meetings | Conduct a pre-work meeting. Be sure to: - Involve all appropriate parties - Discuss the contract specifications in detail - Indicate quality expectations - Indicate that quality will be monitored continuously and how it will be monitored - Discuss job site rules in detail - Review the safety requirements included in the contract and other site-specific information - Discuss meeting frequency and who should attend - Identify work locations - Establish progress report requirements - Discuss and get a detailed schedule from the contractor that identifies the critical path and major milestones - Get manpower loading schedule from the contractor - Establish claims, extra work, back charge, and non-performance procedures - Discuss Company support requirements; i.e., power, water, communications, access or interface to Southern Company information systems - Record minutes (tape recorder if possible) of meeting and distribute for comments to all that attended - Review with contractor the APCO Contractor Drug Alcohol Testing and Background Check Guidelines and verify that compliance has, or will be observed - Review contractual safety information |
| Stay Abreast of Your Project | Being visibly involved is one of the best controls for administering a contract. Daily, if not more frequently: - Meet informally with the contractor - Ensure quality controls are followed - Ensure Company responsibilities are met - Observe actual work in progress - Compare progress to schedule - Observe actual manpower - Look for efficiency gains - Observe safety practices that impact Company employees’ property and customers |

| What to do... | Guidelines |
| --- | --- |
| Conduct Scheduled Meetings | Conduct scheduled meetings if the project is high dollar, has a high level of risk, or if the project will last longer than one month. Discuss: - Schedule progress as compared to original - Current manpower comparison to loading schedule - Contractor concerns - Company concerns (safety, quality, and schedule) - Plans to address concerns |
| Conduct Unscheduled Meetings | Conduct unscheduled meetings if: - Schedule is not being met - Specifications are not being followed - Quality is not controlled - Safety concerns arise |
| Respond to Contractor Correspondence | Always respond in writing to correspondence received from the Contractor. Failure to respond in writing may waive our rights under the contract. If a dispute is involved, or if you are unsure of the appropriate response, contact the LSO. Examples of correspondence you may receive: - Meeting minutes - Requests for a contract change - Requests for extra compensation - Requests for more time/delays - Requests for information - Allegation of action/inaction by the Company impacting contractor's performance |
| When Contractor Work is Unacceptable | If you have doubts about the work of the contractor, consider: - Showing up at unexpected times to inspect the contractor’s work - Inspecting every aspect of the contractor’s work (don’t take the contractor’s word that work has been done) - Consulting with a Company technical expert if you doubt specs are being followed - Contacting the LSO for assistance |
| If the Schedule Changes | Contact affected Company personnel and the LSO immediately if there is a schedule change or when you have any information indicating a change. |
| Prepare for Close-out | A site walk down should be conducted and a punch list developed to determine if anything needs to be accomplished prior to the contractor leaving the site. Meet with the contractor at appropriate intervals and discuss: - Punch list progress - Schedule concerns - Quality concerns - Performance expectations that were or were not met - Clean up requirements for the project that haven’t been met - Resolve claims and back charges |

| What to do… | Guidelines |
| --- | --- |
| Close-out | Before the contractor leaves the site, ensure that the following items have been accomplished. Have a meeting, if necessary, and discuss: - The release of all equipment clearances - Completed punch list - Whether all Company materials have been returned properly, including drawings, diagrams, tools, materials, etc. - Whether security badges, keys, and access cards have been returned, and access to information systems have been removed - A release of all liens - Warranty documentation is in hand and delivered - All drawings are complete and delivered, including as-builts - Quality records are complete - Operating and maintenance manuals are delivered - Contract and all associated documentation (claims, extra work, letters, back charges, etc.) are complete - Proper disposition of surplus and scrap material |
| Review Invoice | Review the invoice and contract simultaneously to ensure that contractor is paid no more or less than is required by the contract. Contact the LSO immediately if a dispute arises. |
| Conduct a Post-project Critique Meeting | Conduct a post-project critique meeting. If necessary, discuss: - Schedule concerns - Quality concerns - Performance expectations that were or were not met - Clean up requirements for the project that haven’t been met - Whether all Company materials have been returned properly, including drawings, diagrams, tools, materials, etc. - Whether security badges, keys, and access cards have been returned and access to information systems have been removed |
| Close-out the Contract | - Ensure that all open Work Orders, Purchase Orders, EWAs, and GWOs are closed when the work is complete - Ensure that spare parts are received and stored properly - Ensure that all unused parts, excess materials, etc. are properly disposed of |
| Contractor Evaluation | Perform contractor evaluations after every project and/or annually utilizing the appropriate template. Refer to the standard Contractor Evaluation Form (Attachment III-9). |