## Master Project List
Contractor | Designated Survivor CWO Project List Year | Original Project List Year | Designated Survivor Funding Project | Designated Survivor Project Name | Designated Survivor Lateral Project Name | Designated Survivor WorkPro Street Name | Designated Survivor TECO OH Removal Work Request # | Designated Survivor TECO OH Removal Work Request Description | Designated Survivor TECO UG Install Work Request # | Designated Survivor TECO UG Removal Work Request Description | LUG CO # | 2020 PO # | 2021 Eng PO # | 2021 Const PO # | Original CWO Project List | Placeholder Funding Project | Original TECO Funding Project | Original Project Name | Original Lateral Project Name | Original WorkPro Street Name | Original TECO OH Removal Work Request # | Original TECO OH Removal Work Request Description | Original TECO UG Install Work Request # | Original TECO UG Removal Work Request Description | Parent No. | Substation | Service Area | Length (miles) | Count of Structures | Count of Customers | Eng Start | Construx Start | Construx End | Notes
Enercon | 2021 | 2021 | PRE-09361.135 | LUG WSA 13162.92185426 | Lateral Hardening-Fuse-92185426 | CKT: 13162 - 92185426 | 2304567 | LUG WSA 13162.92185426 OH | 2304570 | LUG WSA 13162.92185426 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD497 | PRE-09361.135 | LUG WSA 13162.92185426 | Lateral Hardening-Fuse-92185426 | CKT: 13162 - 92185426 | 2304567 | LUG WSA 13162.92185426 OH | 2304570 | LUG WSA 13162.92185426 UG | 13162 | MATANZAS | WSA | 0.36572 | 26 | 19 | 2021-01-01 | 2021-09-01 | 2021-12-01
Enercon | 2021 | 2021 | PRE-09361.136 | LUG WSA 13194.90645535 | Lateral Hardening-Fuse-90645535 | CKT: 13194 - 90645535 | 2304573 | LUG WSA 13194.90645535 OH | 2304576 | LUG WSA 13194.90645535 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD498 | PRE-09361.136 | LUG WSA 13194.90645535 | Lateral Hardening-Fuse-90645535 | CKT: 13194 - 90645535 | 2304573 | LUG WSA 13194.90645535 OH | 2304576 | LUG WSA 13194.90645535 UG | 13194 | DOUBLE BRANCH | WSA | 1.0994 | 50 | 285 | 2021-01-01 | 2021-07-01 | 2021-12-01
Enercon | 2021 | 2021 | PRE-09361.137 | LUG WSA 13079.60077624 | Lateral Hardening-Fuse-60077624 | CKT: 13079 - 60077624 | 2304579 | LUG WSA 13079.60077624 OH | 2304581 | LUG WSA 13079.60077624 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD499 | PRE-09361.137 | LUG WSA 13079.60077624 | Lateral Hardening-Fuse-60077624 | CKT: 13079 - 60077624 | 2304579 | LUG WSA 13079.60077624 OH | 2304581 | LUG WSA 13079.60077624 UG | 13079 | COOLIDGE | WSA | 0.33655 | 30 | 58 | 2021-01-01 | 2021-08-01 | 2021-12-01
Enercon | 2021 | 2021 | PRE-09361.138 | LUG WSA 13586.91748729 | Lateral Hardening-Fuse-91748729 | CKT: 13586 - 91748729 | 2304584 | LUG WSA 13586.91748729 OH | 2304586 | LUG WSA 13586.91748729 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD500 | PRE-09361.138 | LUG WSA 13586.91748729 | Lateral Hardening-Fuse-91748729 | CKT: 13586 - 91748729 | 2304584 | LUG WSA 13586.91748729 OH | 2304586 | LUG WSA 13586.91748729 UG | 13586 | DALE MABRY | WSA | 0.6714 | 42 | 45 | 2021-01-01 | 2021-08-01 | 2021-11-01
Enercon | 2021 | 2021 | PRE-09361.139 | LUG WSA 13162.10158432 | Lateral Hardening-Fuse-10158432 | CKT: 13162 - 10158432 | 2304589 | LUG WSA 13162.10158432 OH | 2304590 | LUG WSA 13162.10158432 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD501 | PRE-09361.139 | LUG WSA 13162.10158432 | Lateral Hardening-Fuse-10158432 | CKT: 13162 - 10158432 | 2304589 | LUG WSA 13162.10158432 OH | 2304590 | LUG WSA 13162.10158432 UG | 13162 | MATANZAS | WSA | 0.16439 | 10 | 61 | 2021-01-01 | 2021-10-01 | 2021-12-01
Enercon | 2021 | 2021 | PRE-09361.140 | LUG WSA 13864.10310477 | Lateral Hardening-Fuse-10310477 | CKT: 13864 - 10310477 | 2304592 | LUG WSA 13864.10310477 OH | 2304593 | LUG WSA 13864.10310477 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD502 | PRE-09361.140 | LUG WSA 13864.10310477 | Lateral Hardening-Fuse-10310477 | CKT: 13864 - 10310477 | 2304592 | LUG WSA 13864.10310477 OH | 2304593 | LUG WSA 13864.10310477 UG | 13864 | PATTERSON ROAD | WSA | 0.7108 | 57 | 18 | 2021-01-01 | TBD
Enercon | 2021 | 2021 | PRE-09361.141 | LUG WSA 13113.92909503 | Lateral Hardening-Fuse-92909503 | CKT: 13113 - 92909503 | 2304596 | LUG WSA 13113.92909503 OH | 2304599 | LUG WSA 13113.92909503 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD503 | PRE-09361.141 | LUG WSA 13113.92909503 | Lateral Hardening-Fuse-92909503 | CKT: 13113 - 92909503 | 2304596 | LUG WSA 13113.92909503 OH | 2304599 | LUG WSA 13113.92909503 UG | 13113 | MANHATTAN | WSA | 0.072538 | 9 | 215 | 2021-01-01
Enercon | 2021 | 2021 | PRE-09361.142 | LUG WSA 13516.60169592 | Lateral Hardening-Fuse-60169592 | CKT: 13516 - 60169592 | 2304601 | LUG WSA 13516.60169592 OH | 2304602 | LUG WSA 13516.60169592 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD504 | PRE-09361.142 | LUG WSA 13516.60169592 | Lateral Hardening-Fuse-60169592 | CKT: 13516 - 60169592 | 2304601 | LUG WSA 13516.60169592 OH | 2304602 | LUG WSA 13516.60169592 UG | 13516 | GEORGE ROAD | WSA | 0.26042 | 19 | 11 | 2021-01-01
Enercon | 2021 | 2021 | PRE-09361.143 | LUG WSA 13192.90932106 | Lateral Hardening-Fuse-90932106 | CKT: 13192 - 90932106 | 2308106 | LUG WSA 13192.90932106 OH | 2308108 | LUG WSA 13192.90932106 UG | LUG C044 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD505 | PRE-09361.143 | LUG WSA 13192.90932106 | Lateral Hardening-Fuse-90932106 | CKT: 13192 - 90932106 | 2308106 | LUG WSA 13192.90932106 OH | 2308108 | LUG WSA 13192.90932106 UG | 13192 | DOUBLE BRANCH | WSA | 0.19318 | 13 | 2 | 2021-01-01 |  |  | Combined with PRE-09361.157 (FID 90932283)
Enercon | 2021 | 2021 | PRE-09361.143 | LUG WSA 13192.90932106 | Lateral Hardening-Fuse-90932106 | CKT: 13192 - 90932106 | 2308106 | LUG WSA 13192.90932106 OH | 2308108 | LUG WSA 13192.90932106 UG | LUG C044 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD519 | PRE-09361.157 | DNU LUG WSA 13192.90932283 | DNU Lateral Hardening-Fuse-90932283 | N/A | N/A | N/A | N/A | N/A | 13192 | DOUBLE BRANCH | WSA | 0.15379 | 8 | 2 | 2021-01-01 |  |  | Combined with PRE-09361.143 (FID 90932106)
Enercon | 2021 | 2021 | PRE-09361.144 | LUG WSA 13333.91785740 | Lateral Hardening-Fuse-91785740 | CKT: 13333 - 91785740 | 2304604 | LUG WSA 13333.91785740 OH | 2304606 | LUG WSA 13333.91785740 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD506 | PRE-09361.144 | LUG WSA 13333.91785740 | Lateral Hardening-Fuse-91785740 | CKT: 13333 - 91785740 | 2304604 | LUG WSA 13333.91785740 OH | 2304606 | LUG WSA 13333.91785740 UG | 13333 | WATERS AVENUE | WSA | 0.23277 | 26 | 13 | 2021-01-01
Enercon | 2021 | 2021 | PRE-09361.145 | LUG WSA 13863.60279838 | Lateral Hardening-Fuse-60279838 | CKT: 13863 - 60279838 | 2304611 | LUG WSA 13863.60279838 OH | 2304613 | LUG WSA 13863.60279838 UG | LUG CO71 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD507 | PRE-09361.145 | LUG WSA 13863.60279838 | Lateral Hardening-Fuse-60279838 | CKT: 13863 - 60279838 | 2304611 | LUG WSA 13863.60279838 OH | 2304613 | LUG WSA 13863.60279838 UG | 13863 | PATTERSON ROAD | WSA | 0.46989 | 32 | 259 | 2021-01-01 |  |  | Combined with PRE-09361.153 (FID 10310468)
Enercon | 2021 | 2021 | PRE-09361.146 | LUG WSA 13109.90643551 | Lateral Hardening-Fuse-90643551 | CKT: 13109 - 90643551 | 2304615 | LUG WSA 13109.90643551 OH | 2304617 | LUG WSA 13109.90643551 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD508 | PRE-09361.146 | LUG WSA 13109.90643551 | Lateral Hardening-Fuse-90643551 | CKT: 13109 - 90643551 | 2304615 | LUG WSA 13109.90643551 OH | 2304617 | LUG WSA 13109.90643551 UG | 13109 | MANHATTAN | WSA | 0.66761 | 50 | 95 | 2021-01-01
Enercon | 2021 | 2021 | PRE-09361.147 | LUG WSA 13332.91700188 | Lateral Hardening-Fuse-91700188 | CKT: 13332 - 91700188 | 2304621 | LUG WSA 13332.91700188 OH | 2304622 | LUG WSA 13332.91700188 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD509 | PRE-09361.147 | LUG WSA 13332.91700188 | Lateral Hardening-Fuse-91700188 | CKT: 13332 - 91700188 | 2304621 | LUG WSA 13332.91700188 OH | 2304622 | LUG WSA 13332.91700188 UG | 13332 | WATERS AVENUE | WSA | 0.10833 | 10 | 60 | 2021-01-01
Enercon | 2021 | 2021 | PRE-09361.148 | LUG WSA 13756.90207831 | Lateral Hardening-Fuse-90207831 | CKT: 13756 - 90207831 | 2304624 | LUG WSA 13756.90207831 OH | 2304626 | LUG WSA 13756.90207831 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD510 | PRE-09361.148 | LUG WSA 13756.90207831 | Lateral Hardening-Fuse-90207831 | CKT: 13756 - 90207831 | 2304624 | LUG WSA 13756.90207831 OH | 2304626 | LUG WSA 13756.90207831 UG | 13756 | GRANADA | WSA | 0.37917 | 36 | 181 | 2021-01-01
Enercon | 2021 | 2021 | PRE-09361.149 | LUG WSA 13672.60106849 | Lateral Hardening-Fuse-60106849 | CKT: 13672 - 60106849 | 2304745 | LUG WSA 13672.60106849 OH | 2304747 | LUG WSA 13672.60106849 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD511 | PRE-09361.149 | LUG WSA 13672.60106849 | Lateral Hardening-Fuse-60106849 | CKT: 13672 - 60106849 | 2304745 | LUG WSA 13672.60106849 OH | 2304747 | LUG WSA 13672.60106849 UG | 13672 | MEADOW PARK | WSA | 0.2678 | 26 | 256 | 2021-01-01
Enercon | 2021 | 2021 | PRE-09361.150 | LUG WSA 13860.10307215 | Lateral Hardening-Fuse-10307215 | CKT: 13860 - 10307215 | 2304734 | LUG WSA 13860.10307215 OH | 2304736 | LUG WSA 13860.10307215 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD512 | PRE-09361.150 | LUG WSA 13860.10307215 | Lateral Hardening-Fuse-10307215 | CKT: 13860 - 10307215 | 2304734 | LUG WSA 13860.10307215 OH | 2304736 | LUG WSA 13860.10307215 UG | 13860 | PATTERSON ROAD | WSA | 0.27917 | 26 | 219 | 2021-01-01
Enercon | 2021 | 2021 | PRE-09361.151 | LUG WSA 13756.60165355 | Lateral Hardening-Fuse-60165355 | CKT: 13756 - 60165355 | 2304892 | LUG WSA 13756.60165355 OH | 2304902 | LUG WSA 13756.60165355 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD513 | PRE-09361.151 | LUG WSA 13756.60165355 | Lateral Hardening-Fuse-60165355 | CKT: 13756 - 60165355 | 2304892 | LUG WSA 13756.60165355 OH | 2304902 | LUG WSA 13756.60165355 UG | 13756 | GRANADA | WSA | 0.082955 | 12 | 55 | 2021-01-01
Enercon | 2021 | 2021 | PRE-09361.152 | LUG WSA 13672.10493801 | Lateral Hardening-Fuse-10493801 | CKT: 13672 - 10493801 | 2304907 | LUG WSA 13672.10493801 OH | 2304908 | LUG WSA 13672.10493801 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD514 | PRE-09361.152 | LUG WSA 13672.10493801 | Lateral Hardening-Fuse-10493801 | CKT: 13672 - 10493801 | 2304907 | LUG WSA 13672.10493801 OH | 2304908 | LUG WSA 13672.10493801 UG | 13672 | MEADOW PARK | WSA | 0.57973 | 43 | 368 | 2021-01-01
Enercon | 2021 | 2021 | PRE-09361.145 | LUG WSA 13863.60279838 | Lateral Hardening-Fuse-60279838 | CKT: 13863 - 60279838 | 2304611 | LUG WSA 13863.60279838 OH | 2304613 | LUG WSA 13863.60279838 UG | LUG CO71 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD515 | PRE-09361.153 | DNU LUG WSA 13864.10310468 | DNU Lateral Hardening-Fuse-10310468 | DNU CKT: 13864 - 10310468 | 2304909 | DNU LUG WSA 13864.10310468 OH | 2304912 | DNU LUG WSA 13864.10310468 UG | 13864 | PATTERSON ROAD | WSA | 0.21061 | 22 | 28 | 2021-01-01 |  |  | Combined with PRE-09361.145 (FID 60279838)
Enercon | 2021 | 2021 | PRE-09361.154 | LUG WSA 13864.10310497 | Lateral Hardening-Fuse-10310497 | CKT: 13864 - 10310497 | 2304913 | LUG WSA 13864.10310497 OH | 2304914 | LUG WSA 13864.10310497 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD516 | PRE-09361.154 | LUG WSA 13864.10310497 | Lateral Hardening-Fuse-10310497 | CKT: 13864 - 10310497 | 2304913 | LUG WSA 13864.10310497 OH | 2304914 | LUG WSA 13864.10310497 UG | 13864 | PATTERSON ROAD | WSA | 0.15 | 10 | 10 | 2021-01-01
Enercon | 2021 | 2021 | PRE-09361.155 | LUG WSA 13586.92442286 | Lateral Hardening-Fuse-92442286 | CKT: 13586 - 92442286 | 2308109 | LUG WSA 13586.92442286 OH | 2308110 | LUG WSA 13586.92442286 UG | LUG C051 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD517 | PRE-09361.155 | LUG WSA 13586.92442286 | Lateral Hardening-Fuse-92442286 | CKT: 13586 - 92442286 | 2308109 | LUG WSA 13586.92442286 OH | 2308110 | LUG WSA 13586.92442286 UG | 13586 | DALE MABRY | WSA | 0.48902 | 40 | 180 | 2021-01-01 |  |  | Combined with PRE-09361.175 (FID 10255361)
Enercon | 2021 | 2021 | PRE-09361.155 | LUG WSA 13586.92442286 | Lateral Hardening-Fuse-92442286 | CKT: 13586 - 92442286 | 2308109 | LUG WSA 13586.92442286 OH | 2308110 | LUG WSA 13586.92442286 UG | LUG C051 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD538 | PRE-09361.175 | DNU LUG WSA 13586.10255361 | DNU Lateral Hardening-Fuse-10255361 | N/A | N/A | N/A | N/A | N/A | 13586 | DALE MABRY | WSA | 0.28106 | 19 | 22 | 2021-03-01 |  |  | Combined with PRE-09361.155 (FID 92442286)
Enercon | 2021 | 2021 | PRE-09361.156 | LUG WSA 13672.91971930 | Lateral Hardening-Fuse-91971930 | CKT: 13672 - 91971930 | 2304916 | LUG WSA 13672.91971930 OH | 2304918 | LUG WSA 13672.91971930 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD518 | PRE-09361.156 | LUG WSA 13672.91971930 | Lateral Hardening-Fuse-91971930 | CKT: 13672 - 91971930 | 2304916 | LUG WSA 13672.91971930 OH | 2304918 | LUG WSA 13672.91971930 UG | 13672 | MEADOW PARK | WSA | 0.1947 | 19 | 27 | 2021-01-01
Enercon | 2021 | 2021 | PRE-09361.158 | LUG WSA 13678.10254063 | Lateral Hardening-Fuse-10254063 | CKT: 13678 - 10254063 | 2304919 | LUG WSA 13678.10254063 OH | 2304920 | LUG WSA 13678.10254063 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD520 | PRE-09361.158 | LUG WSA 13678.10254063 | Lateral Hardening-Fuse-10254063 | CKT: 13678 - 10254063 | 2304919 | LUG WSA 13678.10254063 OH | 2304920 | LUG WSA 13678.10254063 UG | 13678 | TURKEY FORD | WSA | 0.275 | 18 | 11 | 2021-01-01
Enercon | 2021 | 2021 | PRE-09361.159 | LUG WSA 13141.10147344 | Lateral Hardening-Fuse-10147344 | CKT: 13141 - 10147344 | 2304739 | LUG WSA 13141.10147344 OH | 2304742 | LUG WSA 13141.10147344 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD521 | PRE-09361.159 | LUG WSA 13141.10147344 | Lateral Hardening-Fuse-10147344 | CKT: 13141 - 10147344 | 2304739 | LUG WSA 13141.10147344 OH | 2304742 | LUG WSA 13141.10147344 UG | 13141 | HYDE PARK | WSA | 0.098485 | 7 | 12 | 2021-01-01
Enercon | 2021 | 2021 | PRE-09361.160 | LUG WSA 13756.10589587 | Lateral Hardening-Fuse-10589587 | CKT: 13756 - 10589587 | 2304921 | LUG WSA 13756.10589587 OH | 2304922 | LUG WSA 13756.10589587 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD522 | PRE-09361.160 | LUG WSA 13756.10589587 | Lateral Hardening-Fuse-10589587 | CKT: 13756 - 10589587 | 2304921 | LUG WSA 13756.10589587 OH | 2304922 | LUG WSA 13756.10589587 UG | 13756 | GRANADA | WSA | 0.14356 | 13 | 8 | 2021-01-01
Enercon | 2021 | 2021 | PRE-09361.161 | LUG WSA 13864.10310505 | Lateral Hardening-Fuse-10310505 | CKT: 13864 - 10310505 | 2304729 | LUG WSA 13864.10310505 OH | 2304731 | LUG WSA 13864.10310505 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD523 | PRE-09361.161 | LUG WSA 13864.10310505 | Lateral Hardening-Fuse-10310505 | CKT: 13864 - 10310505 | 2304729 | LUG WSA 13864.10310505 OH | 2304731 | LUG WSA 13864.10310505 UG | 13864 | PATTERSON ROAD | WSA | 0.50568 | 41 | 3 | 2021-01-01
Enercon | 2021 | 2021 | PRE-09361.162 | LUG WSA 13860.10307212 | Lateral Hardening-Fuse-10307212 | CKT: 13860 - 10307212 | 2304744 | LUG WSA 13860.10307212 OH | 2304746 | LUG WSA 13860.10307212 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD524 | PRE-09361.162 | LUG WSA 13860.10307212 | Lateral Hardening-Fuse-10307212 | CKT: 13860 - 10307212 | 2304744 | LUG WSA 13860.10307212 OH | 2304746 | LUG WSA 13860.10307212 UG | 13860 | PATTERSON ROAD | WSA | 0.25227 | 28 | 2 | 2021-01-01
Enercon | 2021 | 2021 | PRE-09361.163 | LUG WSA 13111.60072751 | Lateral Hardening-Fuse-60072751 | CKT: 13111 - 60072751 | 2304923 | LUG WSA 13111.60072751 OH | 2304925 | LUG WSA 13111.60072751 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD525 | PRE-09361.163 | LUG WSA 13111.60072751 | Lateral Hardening-Fuse-60072751 | CKT: 13111 - 60072751 | 2304923 | LUG WSA 13111.60072751 OH | 2304925 | LUG WSA 13111.60072751 UG | 13111 | MANHATTAN | WSA | 0.20379 | 17 | 18 | 2021-01-01
Enercon | 2021 | 2021 | PRE-09361.164 | LUG WSA 13333.10007588 | Lateral Hardening-Fuse-10007588 | CKT: 13333 - 10007588 | 2304749 | LUG WSA 13333.10007588 OH | 2304751 | LUG WSA 13333.10007588 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD527 | PRE-09361.164 | LUG WSA 13333.10007588 | Lateral Hardening-Fuse-10007588 | CKT: 13333 - 10007588 | 2304749 | LUG WSA 13333.10007588 OH | 2304751 | LUG WSA 13333.10007588 UG | 13333 | WATERS AVENUE | WSA | 0.16004 | 16 | 16 | 2021-02-01
Enercon | 2021 | 2021 | PRE-09361.69 | LUG WSA 13164.10158909 | Lateral Hardening-Fuse-10158909 | CKT: 13164 - 10158909 | 2273288 | LUG WSA 13164.10158909 OH | 2273291 | LUG WSA 13164.10158909 UG | LUG CO78 | 4500274705 | N/A | N/A | 2021 | LUG - TBD528 | PRE-09361.165 | DNU LUG WSA 13164.90252716 | DNU Lateral Hardening-Fuse-90252716 | DNU CKT: 13164 - 90252716 | 2304926 | DNU LUG WSA 13164.90252716 OH | 2304927 | DNU LUG WSA 13164.90252716 UG | 13164 | MATANZAS | WSA | 0.21572 | 15 | 59 | 2021-02-01 |  |  | Combined with PRE-09361.65 (FID 10158909)
Enercon | 2021 | 2021 | PRE-09361.166 | LUG WSA 13491.91827162 | Lateral Hardening-Fuse-91827162 | CKT: 13491 - 91827162 | 2304928 | LUG WSA 13491.91827162 OH | 2304930 | LUG WSA 13491.91827162 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD529 | PRE-09361.166 | LUG WSA 13491.91827162 | Lateral Hardening-Fuse-91827162 | CKT: 13491 - 91827162 | 2304928 | LUG WSA 13491.91827162 OH | 2304930 | LUG WSA 13491.91827162 UG | 13491 | JACKSON ROAD | WSA | 0.2392 | 21 | 34 | 2021-02-01
Enercon | 2021 | 2021 | PRE-09361.167 | LUG WSA 13113.90422522 | Lateral Hardening-Fuse-90422522 | CKT: 13113 - 90422522 | 2304932 | LUG WSA 13113.90422522 OH | 2304934 | LUG WSA 13113.90422522 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD530 | PRE-09361.167 | LUG WSA 13113.90422522 | Lateral Hardening-Fuse-90422522 | CKT: 13113 - 90422522 | 2304932 | LUG WSA 13113.90422522 OH | 2304934 | LUG WSA 13113.90422522 UG | 13113 | MANHATTAN | WSA | 0.10985 | 6 | 3 | 2021-02-01
Enercon | 2021 | 2021 | PRE-09361.168 | LUG WSA 13756.10589595 | Lateral Hardening-Fuse-10589595 | CKT: 13756 - 10589595 | 2304936 | LUG WSA 13756.10589595 OH | 2304937 | LUG WSA 13756.10589595 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD531 | PRE-09361.168 | LUG WSA 13756.10589595 | Lateral Hardening-Fuse-10589595 | CKT: 13756 - 10589595 | 2304936 | LUG WSA 13756.10589595 OH | 2304937 | LUG WSA 13756.10589595 UG | 13756 | GRANADA | WSA | 0.24924 | 22 | 93 | 2021-02-01
Enercon | 2021 | 2021 | PRE-09361.169 | LUG WSA 13586.10255333 | Lateral Hardening-Fuse-10255333 | CKT: 13586 - 10255333 | 2304730 | LUG WSA 13586.10255333 OH | 2304732 | LUG WSA 13586.10255333 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD532 | PRE-09361.169 | LUG WSA 13586.10255333 | Lateral Hardening-Fuse-10255333 | CKT: 13586 - 10255333 | 2304730 | LUG WSA 13586.10255333 OH | 2304732 | LUG WSA 13586.10255333 UG | 13586 | DALE MABRY | WSA | 0.12159 | 9 | 4 | 2021-02-01
Enercon | 2021 | 2021 | PRE-09361.170 | LUG WSA 13428.90423835 | Lateral Hardening-Fuse-90423835 | CKT: 13428 - 90423835 | 2304755 | LUG WSA 13428.90423835 OH | 2304757 | LUG WSA 13428.90423835 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD533 | PRE-09361.170 | LUG WSA 13428.90423835 | Lateral Hardening-Fuse-90423835 | CKT: 13428 - 90423835 | 2304755 | LUG WSA 13428.90423835 OH | 2304757 | LUG WSA 13428.90423835 UG | 13428 | ROCKY CREEK | WSA | 0.26326 | 16 | 208 | 2021-03-01
Enercon | 2021 | 2021 | PRE-09361.172 | LUG WSA 13141.91575422 | Lateral Hardening-Fuse-91575422 | CKT: 13141 - 91575422 | 2304938 | LUG WSA 13141.91575422 OH | 2304939 | LUG WSA 13141.91575422 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD535 | PRE-09361.172 | LUG WSA 13141.91575422 | Lateral Hardening-Fuse-91575422 | CKT: 13141 - 91575422 | 2304938 | LUG WSA 13141.91575422 OH | 2304939 | LUG WSA 13141.91575422 UG | 13141 | HYDE PARK | WSA | 0.095455 | 8 | 34 | 2021-03-01
Enercon | 2021 | 2021 | PRE-09361.173 | LUG WSA 13678.90514672 | Lateral Hardening-Fuse-90514672 | CKT: 13678 - 90514672 | 2304733 | LUG WSA 13678.90514672 OH | 2304735 | LUG WSA 13678.90514672 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD536 | PRE-09361.173 | LUG WSA 13678.90514672 | Lateral Hardening-Fuse-90514672 | CKT: 13678 - 90514672 | 2304733 | LUG WSA 13678.90514672 OH | 2304735 | LUG WSA 13678.90514672 UG | 13678 | TURKEY FORD | WSA | 0.5358 | 29 | 9 | 2021-03-01
Enercon | 2021 | 2021 | PRE-09361.174 | HOLD LUG WSA 13164.10158912 | Lateral Hardening-Fuse-10158912 | CKT: 13164 - 10158912 | 2304900 | HOLD LUG WSA 13164.10158912 OH | 2304903 | HOLD LUG WSA 13164.10158912 UG | HOLD | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD537 | PRE-09361.174 | LUG WSA 13164.10158912 | Lateral Hardening-Fuse-10158912 | CKT: 13164 - 10158912 | 2304900 | LUG WSA 13164.10158912 OH | 2304903 | LUG WSA 13164.10158912 UG | 13164 | MATANZAS | WSA | 0.21023 | 19 | 236 | 2021-03-01 |  |  | Placed On Hold, per Jason Blackwell, on 8/28/2021
Enercon | 2021 | 2021 | PRE-09361.176 | LUG WSA 13544.10053269 | Lateral Hardening-Fuse-10053269 | CKT: 13544 - 10053269 | 2304718 | LUG WSA 13544.10053269 OH | 2304720 | LUG WSA 13544.10053269 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD539 | PRE-09361.176 | LUG WSA 13544.10053269 | Lateral Hardening-Fuse-10053269 | CKT: 13544 - 10053269 | 2304718 | LUG WSA 13544.10053269 OH | 2304720 | LUG WSA 13544.10053269 UG | 13544 | CARROLLWOOD VILLAGE | WSA | 0.16174 | 16 | 19 | 2021-03-01
Enercon | 2021 | 2021 | PRE-09361.177 | LUG WSA 13864.60380454 | Lateral Hardening-Fuse-60380454 | CKT: 13864 - 60380454 | 2304759 | LUG WSA 13864.60380454 OH | 2304762 | LUG WSA 13864.60380454 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD540 | PRE-09361.177 | LUG WSA 13864.60380454 | Lateral Hardening-Fuse-60380454 | CKT: 13864 - 60380454 | 2304759 | LUG WSA 13864.60380454 OH | 2304762 | LUG WSA 13864.60380454 UG | 13864 | PATTERSON ROAD | WSA | 0.15795 | 13 | 1 | 2021-03-01
Enercon | 2021 | 2021 | PRE-09361.178 | LUG WSA 13141.92442350 | Lateral Hardening-Fuse-92442350 | CKT: 13141 - 92442350 | 2304898 | LUG WSA 13141.92442350 OH | 2304899 | LUG WSA 13141.92442350 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD541 | PRE-09361.178 | LUG WSA 13141.92442350 | Lateral Hardening-Fuse-92442350 | CKT: 13141 - 92442350 | 2304898 | LUG WSA 13141.92442350 OH | 2304899 | LUG WSA 13141.92442350 UG | 13141 | HYDE PARK | WSA | 0.087689 | 13 | 12 | 2021-03-01
Enercon | 2021 | 2021 | PRE-09361.179 | LUG WSA 13141.10147371 | Lateral Hardening-Fuse-10147371 | CKT: 13141 - 10147371 | 2304894 | LUG WSA 13141.10147371 OH | 2304896 | LUG WSA 13141.10147371 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD542 | PRE-09361.179 | LUG WSA 13141.10147371 | Lateral Hardening-Fuse-10147371 | CKT: 13141 - 10147371 | 2304894 | LUG WSA 13141.10147371 OH | 2304896 | LUG WSA 13141.10147371 UG | 13141 | HYDE PARK | WSA | 0.47027 | 49 | 94 | 2021-03-01
Enercon | 2021 | 2021 | PRE-09361.180 | LUG WSA 13678.10288738 | Lateral Hardening-Fuse-10288738 | CKT: 13678 - 10288738 | 2304890 | LUG WSA 13678.10288738 OH | 2304891 | LUG WSA 13678.10288738 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD543 | PRE-09361.180 | LUG WSA 13678.10288738 | Lateral Hardening-Fuse-10288738 | CKT: 13678 - 10288738 | 2304890 | LUG WSA 13678.10288738 OH | 2304891 | LUG WSA 13678.10288738 UG | 13678 | TURKEY FORD | WSA | 0.57784 | 28 | 4 | 2021-03-01
Enercon | 2021 | 2022 | PRE-09361.182 | LUG WSA 13533.91957169 | Lateral Hardening-Fuse-91957169 | CKT: 13533 - 91957169 | 2304711 | LUG WSA 13533.91957169 OH | 2304715 | LUG WSA 13533.91957169 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD545 | PRE-09361.182 | LUG WSA 13533.91957169 | Lateral Hardening-Fuse-91957169 | CKT: 13533 - 91957169 | 2304711 | LUG WSA 13533.91957169 OH | 2304715 | LUG WSA 13533.91957169 UG | 13533 | COOLIDGE | WSA | 0.24432 | 21 | 354 | 2021-03-01
Enercon | 2021 | 2022 | PRE-09361.184 | LUG WSA 13865.90531031 | Lateral Hardening-Fuse-90531031 | CKT: 13865 - 90531031 | 2304754 | LUG WSA 13865.90531031 OH | 2304756 | LUG WSA 13865.90531031 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD547 | PRE-09361.184 | LUG WSA 13865.90531031 | Lateral Hardening-Fuse-90531031 | CKT: 13865 - 90531031 | 2304754 | LUG WSA 13865.90531031 OH | 2304756 | LUG WSA 13865.90531031 UG | 13865 | PATTERSON ROAD | WSA | 0.26383 | 19 | 21 | 2021-04-01
Enercon | 2021 | 2022 | PRE-09361.185 | LUG WSA 13535.92983670 | Lateral Hardening-Fuse-92983670 | CKT: 13535 - 92983670 | 2304883 | LUG WSA 13535.92983670 OH | 2304884 | LUG WSA 13535.92983670 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD548 | PRE-09361.185 | LUG WSA 13535.92983670 | Lateral Hardening-Fuse-92983670 | CKT: 13535 - 92983670 | 2304883 | LUG WSA 13535.92983670 OH | 2304884 | LUG WSA 13535.92983670 UG | 13535 | CARROLLWOOD VILLAGE | WSA | 0.21269 | 14 | 164 | 2021-04-01
Enercon | 2021 | 2022 | PRE-09361.186 | LUG WSA 13589.93177909 | Lateral Hardening-Fuse-93177909 | CKT: 13589 - 93177909 | 2304722 | LUG WSA 13589.93177909 OH | 2304724 | LUG WSA 13589.93177909 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD549 | PRE-09361.186 | LUG WSA 13589.93177909 | Lateral Hardening-Fuse-93177909 | CKT: 13589 - 93177909 | 2304722 | LUG WSA 13589.93177909 OH | 2304724 | LUG WSA 13589.93177909 UG | 13589 | DALE MABRY | WSA | 0.11951 | 6 | 33 | 2021-04-01
Enercon | 2021 | 2022 | PRE-09361.188 | LUG WSA 13522.10392924 | Lateral Hardening-Fuse-10392924 | CKT: 13522 - 10392924 | 2304881 | LUG WSA 13522.10392924 OH | 2304882 | LUG WSA 13522.10392924 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD551 | PRE-09361.188 | LUG WSA 13522.10392924 | Lateral Hardening-Fuse-10392924 | CKT: 13522 - 10392924 | 2304881 | LUG WSA 13522.10392924 OH | 2304882 | LUG WSA 13522.10392924 UG | 13522 | ROME AVENUE | WSA | 0.11591 | 9 | 10 | 2021-04-01
Enercon | 2021 | 2022 | PRE-09361.189 | LUG WSA 13737.10297943 | Lateral Hardening-Fuse-10297943 | CKT: 13737 - 10297943 | 2304878 | LUG WSA 13737.10297943 OH | 2304879 | LUG WSA 13737.10297943 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD552 | PRE-09361.189 | LUG WSA 13737.10297943 | Lateral Hardening-Fuse-10297943 | CKT: 13737 - 10297943 | 2304878 | LUG WSA 13737.10297943 OH | 2304879 | LUG WSA 13737.10297943 UG | 13737 | CLEARVIEW | WSA | 0.20208 | 18 | 84 | 2021-04-01
Enercon | 2021 | 2022 | PRE-09361.190 | LUG WSA 14030.90886759 | Lateral Hardening-Fuse-90886759 | CKT: 14030 - 90886759 | 2308111 | LUG WSA 14030.90886759 OH | 2308112 | LUG WSA 14030.90886759 UG | LUG C053 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD553 | PRE-09361.190 | LUG WSA 14030.90886759 | Lateral Hardening-Fuse-90886759 | CKT: 14030 - 90886759 | 2308111 | LUG WSA 14030.90886759 OH | 2308112 | LUG WSA 14030.90886759 UG | 14030 | PAGLEN ROAD | WSA | 0.53788 | 49 | 161 | 2021-04-01 |  |  | Combined with PRE-09361.206 (FID 90242104) & PRE-09361.257 (FID 92669080)
Enercon | 2021 | 2022 | PRE-09361.190 | LUG WSA 14030.90886759 | Lateral Hardening-Fuse-90886759 | CKT: 14030 - 90886759 | 2308111 | LUG WSA 14030.90886759 OH | 2308112 | LUG WSA 14030.90886759 UG | LUG C053 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD569 | PRE-09361.206 | DNU LUG WSA 14030.90242104 | DNU Lateral Hardening-Fuse-90242104 | N/A | N/A | N/A | N/A | N/A | 14030 | PAGLEN ROAD | WSA | 0.079167 | 6 | 92 | 2021-05-01 |  |  | Combined with PRE-09361.190 (FID 90886759) & PRE-09361.257 (FID 92669080)
Enercon | 2021 | 2022 | PRE-09361.190 | LUG WSA 14030.90886759 | Lateral Hardening-Fuse-90886759 | CKT: 14030 - 90886759 | 2308111 | LUG WSA 14030.90886759 OH | 2308112 | LUG WSA 14030.90886759 UG | LUG C053 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD620 | PRE-09361.257 | DNU LUG WSA 14030.92669080 | DNU Lateral Hardening-Fuse-92669080 | N/A | N/A | N/A | N/A | N/A | 14030 | PAGLEN ROAD | WSA | 0.27254 | 19 | 46 | 2021-10-01 |  |  | Combined with PRE-09361.190 (FID 90886759) & PRE-09361.206 (FID 90242104)
Enercon | 2021 | 2022 | PRE-09361.191 | LUG WSA 13207.90147316 | Lateral Hardening-Fuse-90147316 | CKT: 13207 - 90147316 | 2304874 | LUG WSA 13207.90147316 OH | 2304876 | LUG WSA 13207.90147316 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD554 | PRE-09361.191 | LUG WSA 13207.90147316 | Lateral Hardening-Fuse-90147316 | CKT: 13207 - 90147316 | 2304874 | LUG WSA 13207.90147316 OH | 2304876 | LUG WSA 13207.90147316 UG | 13207 | LOIS AVENUE | WSA | 0.20473 | 17 | 23 | 2021-04-01
Enercon | 2021 | 2022 | PRE-09361.193 | LUG WSA 13059.60302601 | Lateral Hardening-Fuse-60302601 | CKT: 13059 - 60302601 | 2308113 | LUG WSA 13059.60302601 OH | 2308114 | LUG WSA 13059.60302601 UG | LUG C060 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD556 | PRE-09361.193 | LUG WSA 13059.60302601 | Lateral Hardening-Fuse-60302601 | CKT: 13059 - 60302601 | 2308113 | LUG WSA 13059.60302601 OH | 2308114 | LUG WSA 13059.60302601 UG | 13059 | HIMES | WSA | 0.50701 | 51 | 291 | 2021-04-01 |  |  | Combined with PRE-09361.195 (FID 93006225)
Enercon | 2021 | 2022 | PRE-09361.193 | LUG WSA 13059.60302601 | Lateral Hardening-Fuse-60302601 | CKT: 13059 - 60302601 | 2308113 | LUG WSA 13059.60302601 OH | 2308114 | LUG WSA 13059.60302601 UG | LUG C060 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD558 | PRE-09361.195 | DNU LUG WSA 13059.93006225 | DNU Lateral Hardening-Fuse-93006225 | N/A | N/A | N/A | N/A | N/A | 13059 | HIMES | WSA | 0.28258 | 20 | 336 | 2021-05-01 |  |  | Combined with PRE-09361.193 (FID 60302601)
Enercon | 2021 | 2022 | PRE-09361.194 | LUG WSA 13738.10298299 | Lateral Hardening-Fuse-10298299 | CKT: 13738 - 10298299 | 2304872 | LUG WSA 13738.10298299 OH | 2304873 | LUG WSA 13738.10298299 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD557 | PRE-09361.194 | LUG WSA 13738.10298299 | Lateral Hardening-Fuse-10298299 | CKT: 13738 - 10298299 | 2304872 | LUG WSA 13738.10298299 OH | 2304873 | LUG WSA 13738.10298299 UG | 13738 | CLEARVIEW | WSA | 0.31307 | 27 | 71 | 2021-04-01
Enercon | 2021 | 2022 | PRE-09361.196 | LUG WSA 13207.90146892 | Lateral Hardening-Fuse-90146892 | CKT: 13207 - 90146892 | 2304870 | LUG WSA 13207.90146892 OH | 2304871 | LUG WSA 13207.90146892 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD559 | PRE-09361.196 | LUG WSA 13207.90146892 | Lateral Hardening-Fuse-90146892 | CKT: 13207 - 90146892 | 2304870 | LUG WSA 13207.90146892 OH | 2304871 | LUG WSA 13207.90146892 UG | 13207 | LOIS AVENUE | WSA | 0.26402 | 25 | 60 | 2021-05-01
Enercon | 2021 | 2022 | PRE-09361.197 | LUG WSA 13162.10158434 | Lateral Hardening-Fuse-10158434 | CKT: 13162 - 10158434 | 2304868 | LUG WSA 13162.10158434 OH | 2304869 | LUG WSA 13162.10158434 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD560 | PRE-09361.197 | LUG WSA 13162.10158434 | Lateral Hardening-Fuse-10158434 | CKT: 13162 - 10158434 | 2304868 | LUG WSA 13162.10158434 OH | 2304869 | LUG WSA 13162.10158434 UG | 13162 | MATANZAS | WSA | 0.38182 | 30 | 47 | 2021-05-01
Enercon | 2021 | 2022 | PRE-09361.198 | LUG WSA 13079.60077605 | Lateral Hardening-Fuse-60077605 | CKT: 13079 - 60077605 | 2304706 | LUG WSA 13079.60077605 OH | 2304708 | LUG WSA 13079.60077605 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD561 | PRE-09361.198 | LUG WSA 13079.60077605 | Lateral Hardening-Fuse-60077605 | CKT: 13079 - 60077605 | 2304706 | LUG WSA 13079.60077605 OH | 2304708 | LUG WSA 13079.60077605 UG | 13079 | COOLIDGE | WSA | 0.1803 | 17 | 32 | 2021-05-01
Enercon | 2021 | 2022 | PRE-09361.199 | LUG WSA 13870.90428273 | Lateral Hardening-Fuse-90428273 | CKT: 13870 - 90428273 | 2304758 | LUG WSA 13870.90428273 OH | 2304760 | LUG WSA 13870.90428273 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD562 | PRE-09361.199 | LUG WSA 13870.90428273 | Lateral Hardening-Fuse-90428273 | CKT: 13870 - 90428273 | 2304758 | LUG WSA 13870.90428273 OH | 2304760 | LUG WSA 13870.90428273 UG | 13870 | HENDERSON ROAD | WSA | 0.4017 | 25 | 104 | 2021-05-01
Enercon | 2021 | 2022 | PRE-09361.200 | LUG WSA 13737.91960399 | Lateral Hardening-Fuse-91960399 | CKT: 13737 - 91960399 | 2304866 | LUG WSA 13737.91960399 OH | 2304867 | LUG WSA 13737.91960399 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD563 | PRE-09361.200 | LUG WSA 13737.91960399 | Lateral Hardening-Fuse-91960399 | CKT: 13737 - 91960399 | 2304866 | LUG WSA 13737.91960399 OH | 2304867 | LUG WSA 13737.91960399 UG | 13737 | CLEARVIEW | WSA | 0.43277 | 32 | 56 | 2021-05-01
Enercon | 2021 | 2022 | PRE-09361.201 | LUG WSA 13674.10277747 | Lateral Hardening-Fuse-10277747 | CKT: 13674 - 10277747 | 2304737 | LUG WSA 13674.10277747 OH | 2304738 | LUG WSA 13674.10277747 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD564 | PRE-09361.201 | LUG WSA 13674.10277747 | Lateral Hardening-Fuse-10277747 | CKT: 13674 - 10277747 | 2304737 | LUG WSA 13674.10277747 OH | 2304738 | LUG WSA 13674.10277747 UG | 13674 | MEADOW PARK | WSA | 0.56723 | 36 | 361 | 2021-05-01
Enercon | 2021 | 2022 | PRE-09361.202 | HOLD LUG WSA 13078.10127958 | Lateral Hardening-Fuse-10127958 | CKT: 13078 - 10127958 | 2304716 | HOLD LUG WSA 13078.10127958 OH | 2304717 | HOLD LUG WSA 13078.10127958 UG | HOLD | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD565 | PRE-09361.202 | LUG WSA 13078.10127958 | Lateral Hardening-Fuse-10127958 | CKT: 13078 - 10127958 | 2304716 | LUG WSA 13078.10127958 OH | 2304717 | LUG WSA 13078.10127958 UG | 13078 | COOLIDGE | WSA | 0.74545 | 35 | 554 | 2021-05-01 |  |  | Placed On Hold, per Jason Blackwell, on 5/20/2021
Enercon | 2021 | 2022 | PRE-09361.204 | LUG WSA 13510.10218990 | Lateral Hardening-Fuse-10218990 | CKT: 13510 - 10218990 | 2304864 | LUG WSA 13510.10218990 OH | 2304865 | LUG WSA 13510.10218990 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD567 | PRE-09361.204 | LUG WSA 13510.10218990 | Lateral Hardening-Fuse-10218990 | CKT: 13510 - 10218990 | 2304864 | LUG WSA 13510.10218990 OH | 2304865 | LUG WSA 13510.10218990 UG | 13510 | GEORGE ROAD | WSA | 0.35814 | 37 | 20 | 2021-05-01
Enercon | 2021 | 2022 | PRE-09361.205 | LUG WSA 13669.60107076 | Lateral Hardening-Fuse-60107076 | CKT: 13669 - 60107076 | 2304741 | LUG WSA 13669.60107076 OH | 2304743 | LUG WSA 13669.60107076 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD568 | PRE-09361.205 | LUG WSA 13669.60107076 | Lateral Hardening-Fuse-60107076 | CKT: 13669 - 60107076 | 2304741 | LUG WSA 13669.60107076 OH | 2304743 | LUG WSA 13669.60107076 UG | 13669 | MEADOW PARK | WSA | 0.12254 | 9 | 4 | 2021-05-01
Enercon | 2021 | 2022 | PRE-09361.207 | LUG WSA 13873.60311122 | Lateral Hardening-Fuse-60311122 | CKT: 13873 - 60311122 | 2308115 | LUG WSA 13873.60311122 OH | 2308116 | LUG WSA 13873.60311122 UG | LUG C050 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD570 | PRE-09361.207 | LUG WSA 13873.60311122 | Lateral Hardening-Fuse-60311122 | CKT: 13873 - 60311122 | 2308115 | LUG WSA 13873.60311122 OH | 2308116 | LUG WSA 13873.60311122 UG | 13873 | HENDERSON ROAD | WSA | 0.79261 | 61 | 235 | 2021-05-01 |  |  | Combined with PRE-09361.264 (FID 10820612)
Enercon | 2021 | 2022 | PRE-09361.207 | LUG WSA 13873.60311122 | Lateral Hardening-Fuse-60311122 | CKT: 13873 - 60311122 | 2308115 | LUG WSA 13873.60311122 OH | 2308116 | LUG WSA 13873.60311122 UG | LUG C050 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD627 | PRE-09361.264 | DNU LUG WSA 13873.10820612 | DNU Lateral Hardening-Fuse-10820612 | N/A | N/A | N/A | N/A | N/A | 13873 | HENDERSON ROAD | WSA | 0.10076 | 6 | 2 | 2021-10-01 |  |  | Combined with PRE-09361.207 (FID 60311122)
Enercon | 2021 | 2022 | PRE-09361.208 | LUG WSA 13207.90613782 | Lateral Hardening-Fuse-90613782 | CKT: 13207 - 90613782 | 2308117 | LUG WSA 13207.90613782 OH | 2308118 | LUG WSA 13207.90613782 UG | LUG C054 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD555 | PRE-09361.192 | DNU LUG WSA 13207.90216846 | DNU Lateral Hardening-Fuse-90216846 | N/A | N/A | N/A | N/A | N/A | 13207 | LOIS AVENUE | WSA | 0.27178 | 23 | 99 | 2021-04-01 |  |  | Combined with PRE-09361.208 (FID 90613782)
Enercon | 2021 | 2022 | PRE-09361.208 | LUG WSA 13207.90613782 | Lateral Hardening-Fuse-90613782 | CKT: 13207 - 90613782 | 2308117 | LUG WSA 13207.90613782 OH | 2308118 | LUG WSA 13207.90613782 UG | LUG C054 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD571 | PRE-09361.208 | LUG WSA 13207.90613782 | Lateral Hardening-Fuse-90613782 | CKT: 13207 - 90613782 | 2308117 | LUG WSA 13207.90613782 OH | 2308118 | LUG WSA 13207.90613782 UG | 13207 | LOIS AVENUE | WSA | 0.37973 | 31 | 64 | 2021-05-01 |  |  | Combined with PRE-09361.192 (FID 90216846)
Enercon | 2021 | 2022 | PRE-09361.210 | LUG WSA 13208.92767537 | Lateral Hardening-Fuse-92767537 | CKT: 13208 - 92767537 | 2308119 | LUG WSA 13208.92767537 OH | 2308120 | LUG WSA 13208.92767537 UG | LUG C047 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD573 | PRE-09361.210 | LUG WSA 13208.92767537 | Lateral Hardening-Fuse-92767537 | CKT: 13208 - 92767537 | 2308119 | LUG WSA 13208.92767537 OH | 2308120 | LUG WSA 13208.92767537 UG | 13208 | LOIS AVENUE | WSA | 0.18352 | 18 | 117 | 2021-06-01 |  |  | Combined with PRE-09361.233 (FID 90449608)
Enercon | 2021 | 2022 | PRE-09361.210 | LUG WSA 13208.92767537 | Lateral Hardening-Fuse-92767537 | CKT: 13208 - 92767537 | 2308119 | LUG WSA 13208.92767537 OH | 2308120 | LUG WSA 13208.92767537 UG | LUG C047 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD596 | PRE-09361.233 | DNU LUG WSA 13208.90449608 | DNU Lateral Hardening-Fuse-90449608 | N/A | N/A | N/A | N/A | N/A | 13208 | LOIS AVENUE | WSA | 0.22386 | 19 | 83 | 2021-08-01 |  |  | Combined with PRE-09361.210 (FID 92767537)
Enercon | 2021 | 2022 | PRE-09361.211 | LUG WSA 13737.60311396 | Lateral Hardening-Fuse-60311396 | CKT: 13737 - 60311396 | 2304769 | LUG WSA 13737.60311396 OH | 2304771 | LUG WSA 13737.60311396 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD574 | PRE-09361.211 | LUG WSA 13737.60311396 | Lateral Hardening-Fuse-60311396 | CKT: 13737 - 60311396 | 2304769 | LUG WSA 13737.60311396 OH | 2304771 | LUG WSA 13737.60311396 UG | 13737 | CLEARVIEW | WSA | 0.19205 | 8 | 16 | 2021-06-01
Enercon | 2021 | 2022 | PRE-09361.212 | LUG WSA 13198.92655424 | Lateral Hardening-Fuse-92655424 | CKT: 13198 - 92655424 | 2304772 | LUG WSA 13198.92655424 OH | 2304773 | LUG WSA 13198.92655424 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD575 | PRE-09361.212 | LUG WSA 13198.92655424 | Lateral Hardening-Fuse-92655424 | CKT: 13198 - 92655424 | 2304772 | LUG WSA 13198.92655424 OH | 2304773 | LUG WSA 13198.92655424 UG | 13198 | GRAY STREET | WSA | 0.094129 | 8 | 11 | 2021-06-01
Enercon | 2021 | 2022 | PRE-09361.213 | LUG WSA 13514.10624934 | Lateral Hardening-Fuse-10624934 | CKT: 13514 - 10624934 | 2304861 | LUG WSA 13514.10624934 OH | 2304862 | LUG WSA 13514.10624934 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD576 | PRE-09361.213 | LUG WSA 13514.10624934 | Lateral Hardening-Fuse-10624934 | CKT: 13514 - 10624934 | 2304861 | LUG WSA 13514.10624934 OH | 2304862 | LUG WSA 13514.10624934 UG | 13514 | GEORGE ROAD | WSA | 0.23523 | 20 | 18 | 2021-06-01
Enercon | 2021 | 2022 | PRE-09361.216 | LUG WSA 13483.60393455 | Lateral Hardening-Fuse-60393455 | CKT: 13483 - 60393455 | 2308121 | LUG WSA 13483.60393455 OH | 2308122 | LUG WSA 13483.60393455 UG | LUG C056 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD579 | PRE-09361.216 | LUG WSA 13483.60393455 | Lateral Hardening-Fuse-60393455 | CKT: 13483 - 60393455 | 2308121 | LUG WSA 13483.60393455 OH | 2308122 | LUG WSA 13483.60393455 UG | 13483 | WOODLANDS | WSA | 1.3216 | 100 | 526 | 2021-06-01 |  |  | Combined with PRE-09361.242 (FID 10173513) & PRE-09361.260 (FID 60079455)
Enercon | 2021 | 2022 | PRE-09361.216 | LUG WSA 13483.60393455 | Lateral Hardening-Fuse-60393455 | CKT: 13483 - 60393455 | 2308121 | LUG WSA 13483.60393455 OH | 2308122 | LUG WSA 13483.60393455 UG | LUG C056 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD605 | PRE-09361.242 | DNU LUG WSA 13483.10173513 | DNU Lateral Hardening-Fuse-10173513 | N/A | N/A | N/A | N/A | N/A | 13483 | WOODLANDS | WSA | 0.54678 | 47 | 140 | 2021-09-01 |  |  | Combined with PRE-09361.216 (FID 90393455) & PRE-09361.260 (FID 60079455)
Enercon | 2021 | 2022 | PRE-09361.216 | LUG WSA 13483.60393455 | Lateral Hardening-Fuse-60393455 | CKT: 13483 - 60393455 | 2308121 | LUG WSA 13483.60393455 OH | 2308122 | LUG WSA 13483.60393455 UG | LUG C056 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD623 | PRE-09361.260 | DNU LUG WSA 13483.60079455 | DNU Lateral Hardening-Fuse-60079455 | N/A | N/A | N/A | N/A | N/A | 13483 | WOODLANDS | WSA | 0.25606 | 19 | 65 | 2021-10-01 |  |  | Combined with PRE-09361.216 (FID 90393455) & PRE-09361.242 (FID 10173513)
Enercon | 2021 | 2022 | PRE-09361.217 | LUG WSA 13520.10242257 | Lateral Hardening-Fuse-10242257 | CKT: 13520 - 10242257 | 2304859 | LUG WSA 13520.10242257 OH | 2304860 | LUG WSA 13520.10242257 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD580 | PRE-09361.217 | LUG WSA 13520.10242257 | Lateral Hardening-Fuse-10242257 | CKT: 13520 - 10242257 | 2304859 | LUG WSA 13520.10242257 OH | 2304860 | LUG WSA 13520.10242257 UG | 13520 | STADIUM | WSA | 0.45095 | 44 | 28 | 2021-06-01
Enercon | 2021 | 2022 | PRE-09361.218 | LUG WSA 13892.10338448 | Lateral Hardening-Fuse-10338448 | CKT: 13892 - 10338448 | 2304854 | LUG WSA 13892.10338448 OH | 2304856 | LUG WSA 13892.10338448 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD581 | PRE-09361.218 | LUG WSA 13892.10338448 | Lateral Hardening-Fuse-10338448 | CKT: 13892 - 10338448 | 2304854 | LUG WSA 13892.10338448 OH | 2304856 | LUG WSA 13892.10338448 UG | 13892 | EHRLICH ROAD | WSA | 1.1121 | 71 | 256 | 2021-06-01
Enercon | 2021 | 2022 | PRE-09361.219 | LUG WSA 13612.90312305 | Lateral Hardening-Fuse-90312305 | CKT: 13612 - 90312305 | 2308123 | LUG WSA 13612.90312305 OH | 2308124 | LUG WSA 13612.90312305 UG | LUG C043 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD582 | PRE-09361.219 | LUG WSA 13612.90312305 | Lateral Hardening-Fuse-90312305 | CKT: 13612 - 90312305 | 2308123 | LUG WSA 13612.90312305 OH | 2308124 | LUG WSA 13612.90312305 UG | 13612 | EL PRADO | WSA | 0.094886 | 7 | 72 | 2021-06-01 |  |  | Combined with PRE-09361.280 (FID 90312570)
Enercon | 2021 | 2022 | PRE-09361.219 | LUG WSA 13612.90312305 | Lateral Hardening-Fuse-90312305 | CKT: 13612 - 90312305 | 2308123 | LUG WSA 13612.90312305 OH | 2308124 | LUG WSA 13612.90312305 UG | LUG C043 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD643 | PRE-09361.280 | DNU LUG WSA 13612.90312570 | DNU Lateral Hardening-Fuse-90312570 | N/A | N/A | N/A | N/A | N/A | 13612 | EL PRADO | WSA | 0.18542 | 18 | 25 | 2021-11-01 |  |  | Combined with PRE-09361.219 (FID 90312305)
Enercon | 2021 | 2022 | PRE-09361.220 | LUG WSA 13522.91947423 | Lateral Hardening-Fuse-91947423 | CKT: 13522 - 91947423 | 2304851 | LUG WSA 13522.91947423 OH | 2304852 | LUG WSA 13522.91947423 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD583 | PRE-09361.220 | LUG WSA 13522.91947423 | Lateral Hardening-Fuse-91947423 | CKT: 13522 - 91947423 | 2304851 | LUG WSA 13522.91947423 OH | 2304852 | LUG WSA 13522.91947423 UG | 13522 | ROME AVENUE | WSA | 0.52614 | 50 | 47 | 2021-06-01
Enercon | 2021 | 2022 | PRE-09361.221 | LUG WSA 13334.91645657 | Lateral Hardening-Fuse-91645657 | CKT: 13334 - 91645657 | 2304847 | LUG WSA 13334.91645657 OH | 2304849 | LUG WSA 13334.91645657 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD584 | PRE-09361.221 | LUG WSA 13334.91645657 | Lateral Hardening-Fuse-91645657 | CKT: 13334 - 91645657 | 2304847 | LUG WSA 13334.91645657 OH | 2304849 | LUG WSA 13334.91645657 UG | 13334 | WATERS AVENUE | WSA | 0.48428 | 46 | 142 | 2021-07-01
Enercon | 2021 | 2022 | PRE-09361.222 | LUG WSA 13490.92815117 | Lateral Hardening-Fuse-92815117 | CKT: 13490 - 92815117 | 2304767 | LUG WSA 13490.92815117 OH | 2304770 | LUG WSA 13490.92815117 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD585 | PRE-09361.222 | LUG WSA 13490.92815117 | Lateral Hardening-Fuse-92815117 | CKT: 13490 - 92815117 | 2304767 | LUG WSA 13490.92815117 OH | 2304770 | LUG WSA 13490.92815117 UG | 13490 | JACKSON ROAD | WSA | 0.16723 | 13 | 163 | 2021-07-01
Enercon | 2021 | 2022 | PRE-09361.223 | LUG WSA 13522.10392902 | Lateral Hardening-Fuse-10392902 | CKT: 13522 - 10392902 | 2304845 | LUG WSA 13522.10392902 OH | 2304846 | LUG WSA 13522.10392902 UG | LUG CO79 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD586 | PRE-09361.223 | LUG WSA 13522.10392902 | Lateral Hardening-Fuse-10392902 | CKT: 13522 - 10392902 | 2304845 | LUG WSA 13522.10392902 OH | 2304846 | LUG WSA 13522.10392902 UG | 13522 | ROME AVENUE | WSA | 0.66591 | 68 | 103 | 2021-07-01 |  |  | Combined with PRE-09361.272 (FID 10392864)
Enercon | 2021 | 2022 | PRE-09361.224 | LUG WSA 14030.60341032 | Lateral Hardening-Fuse-60341032 | CKT: 14030 - 60341032 | 2304841 | LUG WSA 14030.60341032 OH | 2304844 | LUG WSA 14030.60341032 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD587 | PRE-09361.224 | LUG WSA 14030.60341032 | Lateral Hardening-Fuse-60341032 | CKT: 14030 - 60341032 | 2304841 | LUG WSA 14030.60341032 OH | 2304844 | LUG WSA 14030.60341032 UG | 14030 | PAGLEN ROAD | WSA | 0.13239 | 10 | 81 | 2021-07-01
Enercon | 2021 | 2022 | PRE-09361.225 | LUG WSA 13574.10250638 | Lateral Hardening-Fuse-10250638 | CKT: 13574 - 10250638 | 2304763 | LUG WSA 13574.10250638 OH | 2304766 | LUG WSA 13574.10250638 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD588 | PRE-09361.225 | LUG WSA 13574.10250638 | Lateral Hardening-Fuse-10250638 | CKT: 13574 - 10250638 | 2304763 | LUG WSA 13574.10250638 OH | 2304766 | LUG WSA 13574.10250638 UG | 13574 | ROCKY CREEK | WSA | 0.17083 | 12 | 10 | 2021-07-01
Enercon | 2021 | 2022 | PRE-09361.227 | LUG WSA 13220.10191173 | Lateral Hardening-Fuse-10191173 | CKT: 13220 - 10191173 | 2304836 | LUG WSA 13220.10191173 OH | 2304837 | LUG WSA 13220.10191173 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD590 | PRE-09361.227 | LUG WSA 13220.10191173 | Lateral Hardening-Fuse-10191173 | CKT: 13220 - 10191173 | 2304836 | LUG WSA 13220.10191173 OH | 2304837 | LUG WSA 13220.10191173 UG | 13220 | HABANA AVENUE | WSA | 0.5178 | 45 | 66 | 2021-07-01
Enercon | 2021 | 2022 | PRE-09361.228 | LUG WSA 13612.60022877 | Lateral Hardening-Fuse-60022877 | CKT: 13612 - 60022877 | 2304776 | LUG WSA 13612.60022877 OH | 2304777 | LUG WSA 13612.60022877 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD591 | PRE-09361.228 | LUG WSA 13612.60022877 | Lateral Hardening-Fuse-60022877 | CKT: 13612 - 60022877 | 2304776 | LUG WSA 13612.60022877 OH | 2304777 | LUG WSA 13612.60022877 UG | 13612 | EL PRADO | WSA | 0.061174 | 7 | 22 | 2021-07-01
Enercon | 2021 | 2022 | PRE-09361.229 | LUG WSA 13220.90901917 | Lateral Hardening-Fuse-90901917 | CKT: 13220 - 90901917 | 2304834 | LUG WSA 13220.90901917 OH | 2304835 | LUG WSA 13220.90901917 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD592 | PRE-09361.229 | LUG WSA 13220.90901917 | Lateral Hardening-Fuse-90901917 | CKT: 13220 - 90901917 | 2304834 | LUG WSA 13220.90901917 OH | 2304835 | LUG WSA 13220.90901917 UG | 13220 | HABANA AVENUE | WSA | 0.48977 | 38 | 55 | 2021-07-01
Enercon | 2021 | 2022 | PRE-09361.230 | LUG WSA 13535.92983661 | Lateral Hardening-Fuse-92983661 | CKT: 13535 - 92983661 | 2304831 | LUG WSA 13535.92983661 OH | 2304832 | LUG WSA 13535.92983661 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD593 | PRE-09361.230 | LUG WSA 13535.92983661 | Lateral Hardening-Fuse-92983661 | CKT: 13535 - 92983661 | 2304831 | LUG WSA 13535.92983661 OH | 2304832 | LUG WSA 13535.92983661 UG | 13535 | CARROLLWOOD VILLAGE | WSA | 0.33314 | 32 | 10 | 2021-07-01
Enercon | 2021 | 2022 | PRE-09361.231 | LUG WSA 13535.91618829 | Lateral Hardening-Fuse-91618829 | CKT: 13535 - 91618829 | 2308125 | LUG WSA 13535.91618829 OH | 2308126 | LUG WSA 13535.91618829 UG | LUG C049 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD577 | PRE-09361.214 | DNU LUG WSA 13535.92959083 | DNU Lateral Hardening-Fuse-92959083 | N/A | N/A | N/A | N/A | N/A | 13535 | CARROLLWOOD VILLAGE | WSA | 0.10227 | 9 | 6 | 2021-06-01 |  |  | Combined with PRE-09361.231 (FID 91618829) & PRE-09361.252 (FID 92969194)
Enercon | 2021 | 2022 | PRE-09361.231 | LUG WSA 13535.91618829 | Lateral Hardening-Fuse-91618829 | CKT: 13535 - 91618829 | 2308125 | LUG WSA 13535.91618829 OH | 2308126 | LUG WSA 13535.91618829 UG | LUG C049 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD594 | PRE-09361.231 | LUG WSA 13535.91618829 | Lateral Hardening-Fuse-91618829 | CKT: 13535 - 91618829 | 2308125 | LUG WSA 13535.91618829 OH | 2308126 | LUG WSA 13535.91618829 UG | 13535 | CARROLLWOOD VILLAGE | WSA | 0.50265 | 34 | 70 | 2021-08-01 |  |  | Combined with PRE-09361.214 (FID 92959083) PRE-09361.252 (FID 92969194)
Enercon | 2021 | 2022 | PRE-09361.231 | LUG WSA 13535.91618829 | Lateral Hardening-Fuse-91618829 | CKT: 13535 - 91618829 | 2308125 | LUG WSA 13535.91618829 OH | 2308126 | LUG WSA 13535.91618829 UG | LUG C049 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD615 | PRE-09361.252 | DNU LUG WSA 13535.92969194 | DNU Lateral Hardening-Fuse-92969194 | N/A | N/A | N/A | N/A | N/A | 13535 | CARROLLWOOD VILLAGE | WSA | 0.073295 | 6 | 4 | 2021-09-01 |  |  | Combined with PRE-09361.214 (FID 92959083) & PRE-09361.231 (FID 91618829)
Enercon | 2021 | 2022 | PRE-09361.232 | LUG WSA 13669.92770538 | Lateral Hardening-Fuse-92770538 | CKT: 13669 - 92770538 | 2308127 | LUG WSA 13669.92770538 | 2308128 | LUG WSA 13669.92770538 UG | LUG C048 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD578 | PRE-09361.215 | DNU LUG WSA 13669.92774744 | DNU Lateral Hardening-Fuse-92774744 | N/A | N/A | N/A | N/A | N/A | 13669 | MEADOW PARK | WSA | 0.27803 | 24 | 268 | 2021-06-01 |  |  | Combined with PRE-09361.232 (FID 92770538)
Enercon | 2021 | 2022 | PRE-09361.232 | LUG WSA 13669.92770538 | Lateral Hardening-Fuse-92770538 | CKT: 13669 - 92770538 | 2308127 | LUG WSA 13669.92770538 | 2308128 | LUG WSA 13669.92770538 UG | LUG C048 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD595 | PRE-09361.232 | LUG WSA 13669.92770538 | Lateral Hardening-Fuse-92770538 | CKT: 13669 - 92770538 | 2308127 | LUG WSA 13669.92770538 | 2308128 | LUG WSA 13669.92770538 UG | 13669 | MEADOW PARK | WSA | 0.30152 | 37 | 204 | 2021-08-01 |  |  | Combined with PRE-09361.215 (FID 92774744)
Enercon | 2021 | 2022 | PRE-09361.234 | LUG WSA 13079.60104344 | Lateral Hardening-Fuse-60104344 | CKT: 13079 - 60104344 | 2304709 | LUG WSA 13079.60104344 OH | 2304710 | LUG WSA 13079.60104344 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD597 | PRE-09361.234 | LUG WSA 13079.60104344 | Lateral Hardening-Fuse-60104344 | CKT: 13079 - 60104344 | 2304709 | LUG WSA 13079.60104344 OH | 2304710 | LUG WSA 13079.60104344 UG | 13079 | COOLIDGE | WSA | 0.1411 | 21 | 25 | 2021-08-01
Enercon | 2021 | 2022 | PRE-09361.235 | LUG WSA 13575.90054924 | Lateral Hardening-Fuse-90054924 | CKT: 13575 - 90054924 | 2304750 | LUG WSA 13575.90054924 OH | 2304752 | LUG WSA 13575.90054924 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD598 | PRE-09361.235 | LUG WSA 13575.90054924 | Lateral Hardening-Fuse-90054924 | CKT: 13575 - 90054924 | 2304750 | LUG WSA 13575.90054924 OH | 2304752 | LUG WSA 13575.90054924 UG | 13575 | ROCKY CREEK | WSA | 0.1072 | 12 | 238 | 2021-08-01
Enercon | 2021 | 2022 | PRE-09361.236 | LUG WSA 13750.60110680 | Lateral Hardening-Fuse-60110680 | CKT: 13750 - 60110680 | 2304725 | LUG WSA 13750.60110680 OH | 2304727 | LUG WSA 13750.60110680 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD599 | PRE-09361.236 | LUG WSA 13750.60110680 | Lateral Hardening-Fuse-60110680 | CKT: 13750 - 60110680 | 2304725 | LUG WSA 13750.60110680 OH | 2304727 | LUG WSA 13750.60110680 UG | 13750 | CASEY ROAD | WSA | 0.18561 | 12 | 43 | 2021-08-01
Enercon | 2021 | 2022 | PRE-09361.237 | LUG WSA 13198.10051875 | Lateral Hardening-Fuse-10051875 | CKT: 13198 - 10051875 | 2304774 | LUG WSA 13198.10051875 OH | 2304775 | LUG WSA 13198.10051875 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD600 | PRE-09361.237 | LUG WSA 13198.10051875 | Lateral Hardening-Fuse-10051875 | CKT: 13198 - 10051875 | 2304774 | LUG WSA 13198.10051875 OH | 2304775 | LUG WSA 13198.10051875 UG | 13198 | GRAY STREET | WSA | 0.097348 | 8 | 20 | 2021-08-01
Enercon | 2021 | 2022 | PRE-09361.238 | LUG WSA 13612.92956326 | Lateral Hardening-Fuse-92956326 | CKT: 13612 - 92956326 | 2308129 | LUG WSA 13612.92956326 OH | 2308130 | LUG WSA 13612.92956326 UG | LUG C057 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD544 | PRE-09361.181 | DNU LUG WSA 13612.90440184 | DNU Lateral Hardening-Fuse-90440184 | N/A | N/A | N/A | N/A | N/A | 13612 | EL PRADO | WSA | 0.25208 | 16 | 170 | 2021-03-01 |  |  | Combined with PRE-09361.238 (FID 92956326)
Enercon | 2021 | 2022 | PRE-09361.238 | LUG WSA 13612.92956326 | Lateral Hardening-Fuse-92956326 | CKT: 13612 - 92956326 | 2308129 | LUG WSA 13612.92956326 OH | 2308130 | LUG WSA 13612.92956326 UG | LUG C057 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD601 | PRE-09361.238 | LUG WSA 13612.92956326 | Lateral Hardening-Fuse-92956326 | CKT: 13612 - 92956326 | 2308129 | LUG WSA 13612.92956326 OH | 2308130 | LUG WSA 13612.92956326 UG | 13612 | EL PRADO | WSA | 0.23428 | 25 | 20 | 2021-08-01 |  |  | Combined with PRE-09361.181 (FID 90440184); WR info shown incorrectly on previous list from Leidos as LUG WSA 13522.10392882
Enercon | 2021 | 2022 | PRE-09361.239 | LUG WSA 13514.91361858 | Lateral Hardening-Fuse-91361858 | CKT: 13514 - 91361858 | 2304656 | LUG WSA 13514.91361858 OH | 2304657 | LUG WSA 13514.91361858 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD602 | PRE-09361.239 | LUG WSA 13514.91361858 | Lateral Hardening-Fuse-91361858 | CKT: 13514 - 91361858 | 2304656 | LUG WSA 13514.91361858 OH | 2304657 | LUG WSA 13514.91361858 UG | 13514 | GEORGE ROAD | WSA | 0.16231 | 18 | 70 | 2021-08-01
Enercon | 2021 | 2022 | PRE-09361.240 | LUG WSA 13522.10392905 | Lateral Hardening-Fuse-10392905 | CKT: 13522 - 10392905 | 2304654 | LUG WSA 13522.10392905 OH | 2304655 | LUG WSA 13522.10392905 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD603 | PRE-09361.240 | LUG WSA 13522.10392905 | Lateral Hardening-Fuse-10392905 | CKT: 13522 - 10392905 | 2304654 | LUG WSA 13522.10392905 OH | 2304655 | LUG WSA 13522.10392905 UG | 13522 | ROME AVENUE | WSA | 0.47481 | 50 | 105 | 2021-08-01
Enercon | 2021 | 2022 | PRE-09361.241 | LUG WSA 14030.92669942 | Lateral Hardening-Fuse-92669942 | CKT: 14030 - 92669942 | 2308131 | LUG WSA 14030.92669942 OH | 2308132 | LUG WSA 14030.92669942 UG | LUG C052 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD604 | PRE-09361.241 | LUG WSA 14030.92669942 | Lateral Hardening-Fuse-92669942 | CKT: 14030 - 92669942 | 2308131 | LUG WSA 14030.92669942 OH | 2308132 | LUG WSA 14030.92669942 UG | 14030 | PAGLEN ROAD | WSA | 0.55814 | 34 | 112 | 2021-08-01 |  |  | Combined with PRE-09361.279 (FID 92669914) & PRE-09361.282 (FID 92669923)
Enercon | 2021 | 2022 | PRE-09361.241 | LUG WSA 14030.92669942 | Lateral Hardening-Fuse-92669942 | CKT: 14030 - 92669942 | 2308131 | LUG WSA 14030.92669942 OH | 2308132 | LUG WSA 14030.92669942 UG | LUG C052 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD642 | PRE-09361.279 | DNU LUG WSA 14030.92669914 | DNU Lateral Hardening-Fuse-92669914 | N/A | N/A | N/A | N/A | N/A | 14030 | PAGLEN ROAD | WSA | 0.20303 | 19 | 25 | 2021-11-01 |  |  | Combined with PRE-09361.241 (FID 92669942) PRE-09361.282 (FID 92669923)
Enercon | 2021 | 2022 | PRE-09361.241 | LUG WSA 14030.92669942 | Lateral Hardening-Fuse-92669942 | CKT: 14030 - 92669942 | 2308131 | LUG WSA 14030.92669942 OH | 2308132 | LUG WSA 14030.92669942 UG | LUG C052 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD645 | PRE-09361.282 | DNU LUG WSA 14030.92669923 | DNU Lateral Hardening-Fuse-92669923 | N/A | N/A | N/A | N/A | N/A | 14030 | PAGLEN ROAD | WSA | 0.20701 | 15 | 36 | 2021-11-01 |  |  | Combined with PRE-09361.241 (FID 92669942) & PRE-09361.279 (FID 92669914)
Enercon | 2021 | 2022 | PRE-09361.243 | LUG WSA 13612.60003135 | Lateral Hardening-Fuse-60003135 | CKT: 13612 - 60003135 | 2304652 | LUG WSA 13612.60003135 OH | 2304653 | LUG WSA 13612.60003135 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD606 | PRE-09361.243 | LUG WSA 13612.60003135 | Lateral Hardening-Fuse-60003135 | CKT: 13612 - 60003135 | 2304652 | LUG WSA 13612.60003135 OH | 2304653 | LUG WSA 13612.60003135 UG | 13612 | EL PRADO | WSA | 0.3036 | 33 | 81 | 2021-09-01
Enercon | 2021 | 2022 | PRE-09361.245 | LUG WSA 13522.92169062 | Lateral Hardening-Fuse-92169062 | CKT: 13522 - 92169062 | 2304648 | LUG WSA 13522.92169062 OH | 2304649 | LUG WSA 13522.92169062 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD608 | PRE-09361.245 | LUG WSA 13522.92169062 | Lateral Hardening-Fuse-92169062 | CKT: 13522 - 92169062 | 2304648 | LUG WSA 13522.92169062 OH | 2304649 | LUG WSA 13522.92169062 UG | 13522 | ROME AVENUE | WSA | 0.31686 | 29 | 77 | 2021-09-01
Enercon | 2021 | 2022 | PRE-09361.246 | LUG WSA 13575.90054386 | Lateral Hardening-Fuse-90054386 | CKT: 13575 - 90054386 | 2304646 | LUG WSA 13575.90054386 OH | 2304647 | LUG WSA 13575.90054386 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD609 | PRE-09361.246 | LUG WSA 13575.90054386 | Lateral Hardening-Fuse-90054386 | CKT: 13575 - 90054386 | 2304646 | LUG WSA 13575.90054386 OH | 2304647 | LUG WSA 13575.90054386 UG | 13575 | ROCKY CREEK | WSA | 0.1017 | 13 | 105 | 2021-09-01
Enercon | 2021 | 2022 | PRE-09361.247 | LUG WSA 13522.10392882 | Lateral Hardening-Fuse-10392882 | CKT: 13522 - 10392882 | 2308133 | LUG WSA 13522.10392882 OH | 2308134 | LUG WSA 13522.10392882 UG | LUG C058 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD550 | PRE-09361.187 | DNU LUG WSA 13522.91934653 | DNU Lateral Hardening-Fuse-91934653 | N/A | N/A | N/A | N/A | N/A | 13522 | ROME AVENUE | WSA | 0.47045 | 41 | 128 | 2021-04-01 |  |  | Combined with PRE-09361.247 (FID 10392882) & PRE-09361.283 (FID 60305728)
Enercon | 2021 | 2022 | PRE-09361.247 | LUG WSA 13522.10392882 | Lateral Hardening-Fuse-10392882 | CKT: 13522 - 10392882 | 2308133 | LUG WSA 13522.10392882 OH | 2308134 | LUG WSA 13522.10392882 UG | LUG C058 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD610 | PRE-09361.247 | LUG WSA 13522.10392882 | Lateral Hardening-Fuse-10392882 | CKT: 13522 - 10392882 | 2308133 | LUG WSA 13522.10392882 OH | 2308134 | LUG WSA 13522.10392882 UG | 13522 | ROME AVENUE | WSA | 0.68731 | 61 | 162 | 2021-09-01 |  |  | Combined with PRE-09361.187 (FID 91934653) & PRE-09361.283 (FID 60305728)
Enercon | 2021 | 2022 | PRE-09361.247 | LUG WSA 13522.10392882 | Lateral Hardening-Fuse-10392882 | CKT: 13522 - 10392882 | 2308133 | LUG WSA 13522.10392882 OH | 2308134 | LUG WSA 13522.10392882 UG | LUG C058 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD646 | PRE-09361.283 | DNU LUG WSA 13522.60305728 | DNU Lateral Hardening-Fuse-60305728 | N/A | N/A | N/A | N/A | N/A | 13522 | ROME AVENUE | WSA | 0.095644 | 8 | 11 | 2021-11-01 |  |  | Combined with PRE-09361.187 (FID 91934653) & PRE-09361.247 (FID 10392882)
Enercon | 2021 | 2022 | PRE-09361.248 | LUG WSA 13198.10051851 | Lateral Hardening-Fuse-10051851 | CKT: 13198 - 10051851 | 2304641 | LUG WSA 13198.10051851 OH | 2304645 | LUG WSA 13198.10051851 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD611 | PRE-09361.248 | LUG WSA 13198.10051851 | Lateral Hardening-Fuse-10051851 | CKT: 13198 - 10051851 | 2304641 | LUG WSA 13198.10051851 OH | 2304645 | LUG WSA 13198.10051851 UG | 13198 | GRAY STREET | WSA | 0.21231 | 21 | 33 | 2021-09-01
Enercon | 2021 | 2022 | PRE-09361.249 | LUG WSA 14030.92670479 | Lateral Hardening-Fuse-92670479 | CKT: 14030 - 92670479 | 2304639 | LUG WSA 14030.92670479 OH | 2304640 | LUG WSA 14030.92670479 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD612 | PRE-09361.249 | LUG WSA 14030.92670479 | Lateral Hardening-Fuse-92670479 | CKT: 14030 - 92670479 | 2304639 | LUG WSA 14030.92670479 OH | 2304640 | LUG WSA 14030.92670479 UG | 14030 | PAGLEN ROAD | WSA | 0.1089 | 6 | 3 | 2021-09-01
Enercon | 2021 | 2022 | PRE-09361.250 | LUG WSA 13522.10392874 | Lateral Hardening-Fuse-10392874 | CKT: 13522 - 10392874 | 2304637 | LUG WSA 13522.10392874 OH | 2304638 | LUG WSA 13522.10392874 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD613 | PRE-09361.250 | LUG WSA 13522.10392874 | Lateral Hardening-Fuse-10392874 | CKT: 13522 - 10392874 | 2304637 | LUG WSA 13522.10392874 OH | 2304638 | LUG WSA 13522.10392874 UG | 13522 | ROME AVENUE | WSA | 0.15758 | 12 | 4 | 2021-09-01
Enercon | 2021 | 2022 | PRE-09361.251 | LUG WSA 13162.93124277 | Lateral Hardening-Fuse-93124277 | CKT: 13162 - 93124277 | 2304632 | LUG WSA 13162.93124277 OH | 2304636 | LUG WSA 13162.93124277 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD614 | PRE-09361.251 | LUG WSA 13162.93124277 | Lateral Hardening-Fuse-93124277 | CKT: 13162 - 93124277 | 2304632 | LUG WSA 13162.93124277 OH | 2304636 | LUG WSA 13162.93124277 UG | 13162 | MATANZAS | WSA | 0.15701 | 23 | 5 | 2021-09-01
Enercon | 2021 | 2022 | PRE-09361.253 | LUG WSA 13198.10051896 | Lateral Hardening-Fuse-10051896 | CKT: 13198 - 10051896 | 2304630 | LUG WSA 13198.10051896 OH | 2304631 | LUG WSA 13198.10051896 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD616 | PRE-09361.253 | LUG WSA 13198.10051896 | Lateral Hardening-Fuse-10051896 | CKT: 13198 - 10051896 | 2304630 | LUG WSA 13198.10051896 OH | 2304631 | LUG WSA 13198.10051896 UG | 13198 | GRAY STREET | WSA | 0.13258 | 11 | 18 | 2021-10-01
Enercon | 2021 | 2022 | PRE-09361.255 | LUG WSA 13612.60002970 | Lateral Hardening-Fuse-60002970 | CKT: 13612 - 60002970 | 2304628 | LUG WSA 13612.60002970 OH | 2304629 | LUG WSA 13612.60002970 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD618 | PRE-09361.255 | LUG WSA 13612.60002970 | Lateral Hardening-Fuse-60002970 | CKT: 13612 - 60002970 | 2304628 | LUG WSA 13612.60002970 OH | 2304629 | LUG WSA 13612.60002970 UG | 13612 | EL PRADO | WSA | 0.24811 | 23 | 131 | 2021-10-01
Enercon | 2021 | 2022 | PRE-09361.256 | LUG WSA 14030.60125643 | Lateral Hardening-Fuse-60125643 | CKT: 14030 - 60125643 | 2308135 | LUG WSA 14030.60125643 OH | 2308136 | LUG WSA 14030.60125643 UG | LUG C045 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD546 | PRE-09361.183 | DNU LUG WSA 14030.60131389 | DNU Lateral Hardening-Fuse-60131389 | N/A | N/A | N/A | N/A | N/A | 14030 | PAGLEN ROAD | WSA | 0.15152 | 9 | 111 | 2021-03-01 |  |  | Combined with PRE-09361.256 (FID 60125643)
Enercon | 2021 | 2022 | PRE-09361.256 | LUG WSA 14030.60125643 | Lateral Hardening-Fuse-60125643 | CKT: 14030 - 60125643 | 2308135 | LUG WSA 14030.60125643 OH | 2308136 | LUG WSA 14030.60125643 UG | LUG C045 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD619 | PRE-09361.256 | LUG WSA 14030.60125643 | Lateral Hardening-Fuse-60125643 | CKT: 14030 - 60125643 | 2308135 | LUG WSA 14030.60125643 OH | 2308136 | LUG WSA 14030.60125643 UG | 14030 | PAGLEN ROAD | WSA | 0.089205 | 14 | 101 | 2021-10-01 |  |  | Combined with PRE-09361.183 (FID 60131389)
Enercon | 2021 | 2022 | PRE-09361.258 | LUG WSA 13071.92377934 | Lateral Hardening-Fuse-92377934 | CKT: 13071 - 92377934 | 2304623 | LUG WSA 13071.92377934 OH | 2304625 | LUG WSA 13071.92377934 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD621 | PRE-09361.258 | LUG WSA 13071.92377934 | Lateral Hardening-Fuse-92377934 | CKT: 13071 - 92377934 | 2304623 | LUG WSA 13071.92377934 OH | 2304625 | LUG WSA 13071.92377934 UG | 13071 | KEYSTONE | WSA | 0.98239 | 66 | 63 | 2021-07-01
Enercon | 2021 | 2022 | PRE-09361.259 | LUG WSA 13138.60170460 | Lateral Hardening-Fuse-60170460 | CKT: 13138 - 60170460 | 2304618 | LUG WSA 13138.60170460 OH | 2304620 | LUG WSA 13138.60170460 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD622 | PRE-09361.259 | LUG WSA 13138.60170460 | Lateral Hardening-Fuse-60170460 | CKT: 13138 - 60170460 | 2304618 | LUG WSA 13138.60170460 OH | 2304620 | LUG WSA 13138.60170460 UG | 13138 | HABANA AVENUE | WSA | 0.26458 | 23 | 170 | 2021-10-01
Enercon | 2021 | 2022 | PRE-09361.261 | LUG WSA 13535.92952190 | Lateral Hardening-Fuse-92952190 | CKT: 13535 - 92952190 | 2304614 | LUG WSA 13535.92952190 OH | 2304616 | LUG WSA 13535.92952190 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD624 | PRE-09361.261 | LUG WSA 13535.92952190 | Lateral Hardening-Fuse-92952190 | CKT: 13535 - 92952190 | 2304614 | LUG WSA 13535.92952190 OH | 2304616 | LUG WSA 13535.92952190 UG | 13535 | CARROLLWOOD VILLAGE | WSA | 0.2572 | 18 | 78 | 2021-10-01
Enercon | 2021 | 2022 | PRE-09361.263 | LUG WSA 13162.90435139 | Lateral Hardening-Fuse-90435139 | CKT: 13162 - 90435139 | 2308137 | LUG WSA 13162.90435139 OH | 2308138 | LUG WSA 13162.90435139 UG | LUG C046 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD566 | PRE-09361.203 | DNU LUG WSA 13162.60154843 | DNU Lateral Hardening-Fuse-60154843 | N/A | N/A | N/A | N/A | N/A | 13162 | MATANZAS | WSA | 0.26667 | 25 | 32 | 2021-05-01 |  |  | Combined with PRE-09361.263 (FID 90435139)
Enercon | 2021 | 2022 | PRE-09361.263 | LUG WSA 13162.90435139 | Lateral Hardening-Fuse-90435139 | CKT: 13162 - 90435139 | 2308137 | LUG WSA 13162.90435139 OH | 2308138 | LUG WSA 13162.90435139 UG | LUG C046 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD626 | PRE-09361.263 | LUG WSA 13162.90435139 | Lateral Hardening-Fuse-90435139 | CKT: 13162 - 90435139 | 2308137 | LUG WSA 13162.90435139 OH | 2308138 | LUG WSA 13162.90435139 UG | 13162 | MATANZAS | WSA | 0.29773 | 24 | 23 | 2021-10-01 |  |  | Combined with PRE-09361.203 (FID 60154843)
Enercon | 2021 | 2022 | PRE-09361.265 | LUG WSA 13138.10145618 | Lateral Hardening-Fuse-10145618 | CKT: 13138 - 10145618 | 2304610 | LUG WSA 13138.10145618 OH | 2304612 | LUG WSA 13138.10145618 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD628 | PRE-09361.265 | LUG WSA 13138.10145618 | Lateral Hardening-Fuse-10145618 | CKT: 13138 - 10145618 | 2304610 | LUG WSA 13138.10145618 OH | 2304612 | LUG WSA 13138.10145618 UG | 13138 | HABANA AVENUE | WSA | 0.071023 | 6 | 92 | 2021-10-01
Enercon | 2021 | 2022 | PRE-09361.266 | LUG WSA 13737.90740214 | Lateral Hardening-Fuse-90740214 | CKT: 13737 - 90740214 | 2304607 | LUG WSA 13737.90740214 OH | 2304609 | LUG WSA 13737.90740214 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD629 | PRE-09361.266 | LUG WSA 13737.90740214 | Lateral Hardening-Fuse-90740214 | CKT: 13737 - 90740214 | 2304607 | LUG WSA 13737.90740214 OH | 2304609 | LUG WSA 13737.90740214 UG | 13737 | CLEARVIEW | WSA | 0.10114 | 12 | 15 | 2021-10-01
Enercon | 2021 | 2022 | PRE-09361.268 | LUG WSA 13737.90740699 | Lateral Hardening-Fuse-90740699 | CKT: 13737 - 90740699 | 2304603 | LUG WSA 13737.90740699 OH | 2304605 | LUG WSA 13737.90740699 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD631 | PRE-09361.268 | LUG WSA 13737.90740699 | Lateral Hardening-Fuse-90740699 | CKT: 13737 - 90740699 | 2304603 | LUG WSA 13737.90740699 OH | 2304605 | LUG WSA 13737.90740699 UG | 13737 | CLEARVIEW | WSA | 0.16553 | 13 | 17 | 2021-10-01
Enercon | 2021 | 2022 | PRE-09361.269 | LUG WSA 13079.90517178 | Lateral Hardening-Fuse-90517178 | CKT: 13079 - 90517178 | 2304585 | LUG WSA 13079.90517178 OH | 2304588 | LUG WSA 13079.90517178 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD632 | PRE-09361.269 | LUG WSA 13079.90517178 | Lateral Hardening-Fuse-90517178 | CKT: 13079 - 90517178 | 2304585 | LUG WSA 13079.90517178 OH | 2304588 | LUG WSA 13079.90517178 UG | 13079 | COOLIDGE | WSA | 0.12973 | 16 | 56 | 2021-10-01
Enercon | 2021 | 2022 | PRE-09361.270 | LUG WSA 13078.10127955 | Lateral Hardening-Fuse-10127955 | CKT: 13078 - 10127955 | 2304582 | LUG WSA 13078.10127955 OH | 2304583 | LUG WSA 13078.10127955 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD633 | PRE-09361.270 | LUG WSA 13078.10127955 | Lateral Hardening-Fuse-10127955 | CKT: 13078 - 10127955 | 2304582 | LUG WSA 13078.10127955 OH | 2304583 | LUG WSA 13078.10127955 UG | 13078 | COOLIDGE | WSA | 0.17822 | 15 | 33 | 2021-10-01
Enercon | 2021 | 2022 | PRE-09361.271 | LUG WSA 14030.92669557 | Lateral Hardening-Fuse-92669557 | CKT: 14030 - 92669557 | 2304577 | LUG WSA 14030.92669557 OH | 2304580 | LUG WSA 14030.92669557 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD634 | PRE-09361.271 | LUG WSA 14030.92669557 | Lateral Hardening-Fuse-92669557 | CKT: 14030 - 92669557 | 2304577 | LUG WSA 14030.92669557 OH | 2304580 | LUG WSA 14030.92669557 UG | 14030 | PAGLEN ROAD | WSA | 0.0089015 | 5 | 78 | 2021-11-01
Enercon | 2021 | 2022 | PRE-09361.223 | LUG WSA 13522.10392902 | Lateral Hardening-Fuse-10392902 | CKT: 13522 - 10392864 | 2304845 | LUG WSA 13522.10392902 OH | 2304846 | LUG WSA 13522.10392902 UG | LUG CO79 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD635 | PRE-09361.272 | DNU LUG WSA 13522.10392864 | DNU Lateral Hardening-Fuse-10392864 | DNU CKT: 13522 - 10392864 | 2304574 | DNU LUG WSA 13522.10392864 OH | 2304575 | DNU LUG WSA 13522.10392864 UG | 13522 | ROME AVENUE | WSA | 0.10587 | 7 | 10 | 2021-11-01 |  |  | Combined with PRE-09361.223 (FID 10392902)
Enercon | 2021 | 2022 | PRE-09361.273 | LUG WSA 13674.90420693 | Lateral Hardening-Fuse-90420693 | CKT: 13674 - 90420693 | 2304569 | LUG WSA 13674.90420693 OH | 2304572 | LUG WSA 13674.90420693 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD636 | PRE-09361.273 | LUG WSA 13674.90420693 | Lateral Hardening-Fuse-90420693 | CKT: 13674 - 90420693 | 2304569 | LUG WSA 13674.90420693 OH | 2304572 | LUG WSA 13674.90420693 UG | 13674 | MEADOW PARK | WSA | 0.3233 | 29 | 125 | 2021-10-01
Enercon | 2021 | 2022 | PRE-09361.274 | LUG WSA 13612.90291123 | Lateral Hardening-Fuse-90291123 | CKT: 13612 - 90291123 | 2308140 | LUG WSA 13612.90291123 OH | 2308141 | LUG WSA 13612.90291123 UG | LUG C055 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD572 | PRE-09361.209 | DNU LUG WSA 13612.90266817 | DNU Lateral Hardening-Fuse-90266817 | N/A | N/A | N/A | N/A | N/A | 13612 | EL PRADO | WSA | 0.20985 | 19 | 103 | 2021-05-01 |  |  | Combined with PRE-09361.274 (FID 90291123)
Enercon | 2021 | 2022 | PRE-09361.274 | LUG WSA 13612.90291123 | Lateral Hardening-Fuse-90291123 | CKT: 13612 - 90291123 | 2308140 | LUG WSA 13612.90291123 OH | 2308141 | LUG WSA 13612.90291123 UG | LUG C055 | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD637 | PRE-09361.274 | LUG WSA 13612.90291123 | Lateral Hardening-Fuse-90291123 | CKT: 13612 - 90291123 | 2308140 | LUG WSA 13612.90291123 OH | 2308141 | LUG WSA 13612.90291123 UG | 13612 | EL PRADO | WSA | 0.13333 | 15 | 10 | 2021-11-01 |  |  | Combined with PRE-09361.209 (FID 90291123)
Enercon | 2021 | 2022 | PRE-09361.275 | LUG WSA 13109.60233901 | Lateral Hardening-Fuse-60233901 | CKT: 13109 - 60233901 | 2304565 | LUG WSA 13109.60233901 OH | 2304568 | LUG WSA 13109.60233901 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD638 | PRE-09361.275 | LUG WSA 13109.60233901 | Lateral Hardening-Fuse-60233901 | CKT: 13109 - 60233901 | 2304565 | LUG WSA 13109.60233901 OH | 2304568 | LUG WSA 13109.60233901 UG | 13109 | MANHATTAN | WSA | 0.47254 | 42 | 282 | 2021-10-01
Enercon | 2021 | 2022 | PRE-09361.276 | LUG WSA 13737.10297934 | Lateral Hardening-Fuse-10297934 | CKT: 13737 - 10297934 | 2304560 | LUG WSA 13737.10297934 OH | 2304563 | LUG WSA 13737.10297934 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD639 | PRE-09361.276 | LUG WSA 13737.10297934 | Lateral Hardening-Fuse-10297934 | CKT: 13737 - 10297934 | 2304560 | LUG WSA 13737.10297934 OH | 2304563 | LUG WSA 13737.10297934 UG | 13737 | CLEARVIEW | WSA | 0.19678 | 18 | 24 | 2021-11-01
Enercon | 2021 | 2022 | PRE-09361.277 | LUG WSA 13589.93162023 | Lateral Hardening-Fuse-93162023 | CKT: 13589 - 93162023 | 2304547 | LUG WSA 13589.93162023 OH | 2304552 | LUG WSA 13589.93162023 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD640 | PRE-09361.277 | LUG WSA 13589.93162023 | Lateral Hardening-Fuse-93162023 | CKT: 13589 - 93162023 | 2304547 | LUG WSA 13589.93162023 OH | 2304552 | LUG WSA 13589.93162023 UG | 13589 | DALE MABRY | WSA | 0.3267 | 16 | 1 | 2021-10-01
Enercon | 2020 | 2022 | PRE-09361.68 | LUG WSA 13138.10145628 | Lateral Hardening-Fuse-10145628 | CKT: 13138 - 10145628 | 2273294 | LUG WSA 13138.10145628 OH | 2273296 | LUG WSA 13138.10145628 UG | LUG C059/C062 | 4500274705 | N/A | N/A | 2021 | LUG - TBD630 | PRE-09361.267 | DNU LUG WSA 13138.10145629 | DNU Lateral Hardening-Fuse-10145629 | N/A | N/A | N/A | N/A | N/A | 13138 | HABANA AVENUE | WSA | 0.12197 | 10 | 5 | 2021-10-01 |  |  | Combined with PRE-09361.281 (FID 10145606) & PRE-09361.68 (FID 10145628)
Enercon | 2020 | 2022 | PRE-09361.68 | LUG WSA 13138.10145628 | Lateral Hardening-Fuse-10145628 | CKT: 13138 - 10145628 | 2273294 | LUG WSA 13138.10145628 OH | 2273296 | LUG WSA 13138.10145628 UG | LUG C059/C062 | 4500274705 | N/A | N/A | 2021 | LUG - TBD644 | PRE-09361.281 | LUG WSA 13138.10145606 | Lateral Hardening-Fuse-10145606 | CKT: 13138 - 10145606 | 2308143 | LUG WSA 13138.10145606 OH | 2308144 | LUG WSA 13138.10145606 UG | 13138 | HABANA AVENUE | WSA | 0.25587 | 24 | 222 | 2021-11-01 |  |  | Combined with PRE-09361.267 (FID 10145629) & PRE-09361.68 (FID 10145628)
Enercon | 2021 | 2022 | PRE-09361.284 | LUG WSA 13522.60305720 | Lateral Hardening-Fuse-60305720 | CKT: 13522 - 60305720 | 2304522 | LUG WSA 13522.60305720 OH | 2304536 | LUG WSA 13522.60305720 UG |  | N/A | 4500279866 | 4500291222 | 2021 | LUG - TBD647 | PRE-09361.284 | LUG WSA 13522.60305720 | Lateral Hardening-Fuse-60305720 | CKT: 13522 - 60305720 | 2304522 | LUG WSA 13522.60305720 OH | 2304536 | LUG WSA 13522.60305720 UG | 13522 | ROME AVENUE | WSA | 0.068371 | 6 | 10 | 2021-11-01
Enercon | 2020 | 2020 | PRE-09361.31 | LUG WSA 14032.10820614 | Lateral Hardening-Fuse-10820614 | CKT: 14032 - 10820614 | 2271231 | LUG WSA 14032.10820614 OH | 2271237 | LUG WSA 14032.10820614 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD459 | PRE-09361.31 | LUG WSA 14032.10820614 | Lateral Hardening-Fuse-10820614 | CKT: 14032 - 10820614 | 2271231 | LUG WSA 14032.10820614 OH | 2271237 | LUG WSA 14032.10820614 UG | 14032 | PAGLEN ROAD | WSA | 0.34943 | 25 | 204 | 2020-06-01 | 2021-01-01 | 2021-04-01
Enercon | 2020 | 2020 | PRE-09361.32 | LUG WSA 13071.90738378 | Lateral Hardening-Fuse-90738378 | CKT: 13071 - 90738378 | 2272328 | LUG WSA 13071.90738378 OH | 2272333 | LUG WSA 13071.90738378 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD460 | PRE-09361.32 | LUG WSA 13071.90738378 | Lateral Hardening-Fuse-90738378 | CKT: 13071 - 90738378 | 2272328 | LUG WSA 13071.90738378 OH | 2272333 | LUG WSA 13071.90738378 UG | 13071 | KEYSTONE | WSA | 0.16288 | 20 | 296 | 2020-06-01 | 2021-01-01 | 2021-03-01
Enercon | 2020 | 2020 | PRE-09361.33 | LUG WSA 14032.92634300 | Lateral Hardening-Fuse-92634300 | CKT: 14032 - 92634300 | 2272329 | LUG WSA 14032.92634300 OH | 2272334 | LUG WSA 14032.92634300 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD461 | PRE-09361.33 | LUG WSA 14032.92634300 | Lateral Hardening-Fuse-92634300 | CKT: 14032 - 92634300 | 2272329 | LUG WSA 14032.92634300 OH | 2272334 | LUG WSA 14032.92634300 UG | 14032 | PAGLEN ROAD | WSA | 0.31383 | 21 | 306 | 2020-06-01 | 2021-01-01 | 2021-04-01
Enercon | 2020 | 2020 | PRE-09361.34 | LUG WSA 13071.91245761 | Lateral Hardening-Fuse-91245761 | CKT: 13071 - 91245761 | 2272893 | LUG WSA 13071.91245761 OH | 2272895 | LUG WSA 13071.91245761 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD462 | PRE-09361.34 | LUG WSA 13071.91245761 | Lateral Hardening-Fuse-91245761 | CKT: 13071 - 91245761 | 2272893 | LUG WSA 13071.91245761 OH | 2272895 | LUG WSA 13071.91245761 UG | 13071 | KEYSTONE | WSA | 0.2892 | 17 | 6 | 2020-06-01 | 2021-01-01 | 2021-03-01
Enercon | 2020 | 2020 | PRE-09361.35 | LUG WSA 14032.91487301 | Lateral Hardening-Fuse-91487301 | CKT: 14032 - 91487301 | 2272897 | LUG WSA 14032.91487301 OH | 2272899 | LUG WSA 14032.91487301 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD463 | PRE-09361.35 | LUG WSA 14032.91487301 | Lateral Hardening-Fuse-91487301 | CKT: 14032 - 91487301 | 2272897 | LUG WSA 14032.91487301 OH | 2272899 | LUG WSA 14032.91487301 UG | 14032 | PAGLEN ROAD | WSA | 0.2786 | 25 | 199 | 2020-07-01 | 2021-01-01 | 2021-04-01
Enercon | 2020 | 2020 | PRE-09361.36 | LUG WSA 14032.10339836 | Lateral Hardening-Fuse-10339836 | CKT: 14032 - 10339836 | 2272920 | LUG WSA 14032.10339836 OH | 2272921 | LUG WSA 14032.10339836 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD464 | PRE-09361.36 | LUG WSA 14032.10339836 | Lateral Hardening-Fuse-10339836 | CKT: 14032 - 10339836 | 2272920 | LUG WSA 14032.10339836 OH | 2272921 | LUG WSA 14032.10339836 UG | 14032 | PAGLEN ROAD | WSA | 0.12841 | 11 | 2 | 2020-07-01 | 2021-01-01 | 2021-03-01
Enercon | 2020 | 2020 | PRE-09361.37 | LUG WSA 14032.92803239 | Lateral Hardening-Fuse-92803239 | CKT: 14032 - 92803239 | 2272923 | LUG WSA 14032.92803239 OH | 2272925 | LUG WSA 14032.92803239 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD465 | PRE-09361.37 | LUG WSA 14032.92803239 | Lateral Hardening-Fuse-92803239 | CKT: 14032 - 92803239 | 2272923 | LUG WSA 14032.92803239 OH | 2272925 | LUG WSA 14032.92803239 UG | 14032 | PAGLEN ROAD | WSA | 0.23977 | 8 | 5 | 2020-07-01 | 2021-01-01 | 2021-04-01
Enercon | 2020 | 2020 | PRE-09361.39 | LUG WSA 13071.91432109 | Lateral Hardening-Fuse-91432109 | CKT: 13071 - 91432109 | 2272936 | LUG WSA 13071.91432109 OH | 2272937 | LUG WSA 13071.91432109 UG | LUG C018 | 4500274705 | N/A | N/A | 2020 | LUG - TBD466 | PRE-09361.38 | DNU LUG WSA 13071.91432110 | DNU Lateral Hardening-Fuse-91432110 | DNU CKT: 13071 - 91432110 | 2272931 | DNU LUG WSA 13071.91432110 OH | 2272933 | DNU LUG WSA 13071.91432110 UG | 13071 | KEYSTONE | WSA | 0.22443 | 17 | 11 | 2020-07-01 | 2021-01-01 | 2021-02-01 | Combined with PRE-09361.39 (FID 91432109)
Enercon | 2020 | 2020 | PRE-09361.39 | LUG WSA 13071.91432109 | Lateral Hardening-Fuse-91432109 | CKT: 13071 - 91432109 | 2272936 | LUG WSA 13071.91432109 OH | 2272937 | LUG WSA 13071.91432109 UG | LUG C018 | 4500274705 | N/A | N/A | 2020 | LUG - TBD467 | PRE-09361.39 | LUG WSA 13071.91432109 | Lateral Hardening-Fuse-91432109 | CKT: 13071 - 91432109 | 2272936 | LUG WSA 13071.91432109 OH | 2272937 | LUG WSA 13071.91432109 UG | 13071 | KEYSTONE | WSA | 0.14261 | 15 | 20 | 2020-07-01 | 2021-01-01 | 2021-03-01 | Combined with PRE-09361.38 (FID 91432110)
Enercon | 2020 | 2020 | PRE-09361.40 | LUG WSA 14032.92729035 | Lateral Hardening-Fuse-92729035 | CKT: 14032 - 92729035 | 2272939 | LUG WSA 14032.92729035 OH | 2272940 | LUG WSA 14032.92729035 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD468 | PRE-09361.40 | LUG WSA 14032.92729035 | Lateral Hardening-Fuse-92729035 | CKT: 14032 - 92729035 | 2272939 | LUG WSA 14032.92729035 OH | 2272940 | LUG WSA 14032.92729035 UG | 14032 | PAGLEN ROAD | WSA | 0.36364 | 27 | 5 | 2020-07-01 | 2021-01-01 | 2021-04-01
Enercon | 2020 | 2022 | PRE-09361.48 | LUG WSA 13198.92183966 | Lateral Hardening-Fuse-92183966 | CKT: 13198 - 92183966 | 2273238 | LUG WSA 13198.92183966 OH | 2273240 | LUG WSA 13198.92183966 UG | LUG C020 | 4500274705 | N/A | N/A | 2021 | LUG - TBD625 | PRE-09361.262 | DNU LUG WSA 13198.10051852 | DNU Lateral Hardening-Fuse-10051852 | N/A | N/A | N/A | N/A | N/A | 13198 | GRAY STREET | WSA | 0.15549 | 12 | 9 | 2021-10-01 |  |  | Combined with PRE-09361.48 (FID 92183966) & PRE-09361.262 (FID 10051852)
Enercon | 2020 | 2022 | PRE-09361.48 | LUG WSA 13198.92183966 | Lateral Hardening-Fuse-92183966 | CKT: 13198 - 92183966 | 2273238 | LUG WSA 13198.92183966 OH | 2273240 | LUG WSA 13198.92183966 UG | LUG C020 | 4500274705 | N/A | N/A | 2021 | LUG - TBD641 | PRE-09361.278 | DNU LUG WSA 13198.92585443 | DNU Lateral Hardening-Fuse-92585443 | N/A | N/A | N/A | N/A | N/A | 13198 | GRAY STREET | WSA | 0.089583 | 12 | 27 | 2021-11-01 |  |  | Combined with PRE-09361.48 (FID 92183966) & PRE-09361.278 (FID 92585443)
Enercon | 2020 | 2020 | PRE-09361.48 | LUG WSA 13198.92183966 | Lateral Hardening-Fuse-92183966 | CKT: 13198 - 92183966 | 2273238 | LUG WSA 13198.92183966 OH | 2273240 | LUG WSA 13198.92183966 UG | LUG C020 | 4500274705 | N/A | N/A | 2020 | LUG - TBD469 | PRE-09361.48 | LUG WSA 13198.92183966 | Lateral Hardening-Fuse-92183966 | CKT: 13198 - 92183966 | 2273238 | LUG WSA 13198.92183966 OH | 2273240 | LUG WSA 13198.92183966 UG | 13198 | GRAY STREET | WSA | 0.16629 | 12 | 86 | 2020-07-01 | 2021-01-01 | 2021-03-01 | Combined with PRE-09361.262 (FID 10051852) & PRE-09361.278 (FID 92585443)
Enercon | 2020 | 2020 | PRE-09361.49 | LUG WSA 13678.90514649 | Lateral Hardening-Fuse-90514649 | CKT: 13678 - 90514649 | 2273257 | LUG WSA 13678.90514649 OH | 2273259 | LUG WSA 13678.90514649 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD470 | PRE-09361.49 | LUG WSA 13678.90514649 | Lateral Hardening-Fuse-90514649 | CKT: 13678 - 90514649 | 2273257 | LUG WSA 13678.90514649 OH | 2273259 | LUG WSA 13678.90514649 UG | 13678 | TURKEY FORD | WSA | 0.50966 | 13 | 42 | 2020-07-01 | 2021-01-01 | 2021-04-01
Enercon | 2020 | 2020 | PRE-09361.50 | LUG WSA 13425.10244449 | Lateral Hardening-Fuse-10244449 | CKT: 13425 - 10244449 | 2273263 | LUG WSA 13425.10244449 OH | 2273265 | LUG WSA 13425.10244449 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD471 | PRE-09361.50 | LUG WSA 13425.10244449 | Lateral Hardening-Fuse-10244449 | CKT: 13425 - 10244449 | 2273263 | LUG WSA 13425.10244449 OH | 2273265 | LUG WSA 13425.10244449 UG | 13425 | ROCKY CREEK | WSA | 0.69659 | 33 | 195 | 2020-07-01 | 2021-01-01 | 2021-05-01
Enercon | 2020 | 2020 | PRE-09361.51 | LUG WSA 13670.93124410 | Lateral Hardening-Fuse-93124410 | CKT: 13670 - 93124410 | 2273274 | LUG WSA 13670.93124410 OH | 2273276 | LUG WSA 13670.93124410 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD472 | PRE-09361.51 | LUG WSA 13670.93124410 | Lateral Hardening-Fuse-93124410 | CKT: 13670 - 93124410 | 2273274 | LUG WSA 13670.93124410 OH | 2273276 | LUG WSA 13670.93124410 UG | 13670 | MEADOW PARK | WSA | 0.71345 | 25 | 383 | 2020-07-01 | 2021-01-01 | 2021-05-01
Enercon | 2020 | 2020 | PRE-09361.52 | LUG WSA 13428.91540495 | Lateral Hardening-Fuse-91540495 | CKT: 13428 - 91540495 | 2273279 | LUG WSA 13428.91540495 OH | 2273281 | LUG WSA 13428.91540495 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD473 | PRE-09361.52 | LUG WSA 13428.91540495 | Lateral Hardening-Fuse-91540495 | CKT: 13428 - 91540495 | 2273279 | LUG WSA 13428.91540495 OH | 2273281 | LUG WSA 13428.91540495 UG | 13428 | ROCKY CREEK | WSA | 0.23314 | 30 | 402 | 2020-08-01 | 2021-01-01 | 2021-03-01
Enercon | 2020 | 2020 | PRE-09361.53 | LUG WSA 13332.91335523 | Lateral Hardening-Fuse-91335523 | CKT: 13332 - 91335523 | 2273285 | LUG WSA 13332.91335523 OH | 2273287 | LUG WSA 13332.91335523 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD474 | PRE-09361.53 | LUG WSA 13332.91335523 | Lateral Hardening-Fuse-91335523 | CKT: 13332 - 91335523 | 2273285 | LUG WSA 13332.91335523 OH | 2273287 | LUG WSA 13332.91335523 UG | 13332 | WATERS AVENUE | WSA | 0.29205 | 23 | 230 | 2020-08-01 | 2021-01-01 | 2021-03-01
Enercon | 2020 | 2020 | PRE-09361.54 | LUG WSA 13544.10053266 | Lateral Hardening-Fuse-10053266 | CKT: 13544 - 10053266 | 2273289 | LUG WSA 13544.10053266 OH | 2273292 | LUG WSA 13544.10053266 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD475 | PRE-09361.54 | LUG WSA 13544.10053266 | Lateral Hardening-Fuse-10053266 | CKT: 13544 - 10053266 | 2273289 | LUG WSA 13544.10053266 OH | 2273292 | LUG WSA 13544.10053266 UG | 13544 | CARROLLWOOD VILLAGE | WSA | 0.29072 | 20 | 161 | 2020-08-01 | 2021-04-01 | 2021-06-01
Enercon | 2020 | 2022 | PRE-09361.55 | LUG WSA 13109.90641822 | Lateral Hardening-Fuse-90641822 | CKT: 13109 - 90641822 | 2273297 | LUG WSA 13109.90641822 OH | 2273300 | LUG WSA 13109.90641822 UG | LUG C019 | 4500274705 | N/A | N/A | 2021 | LUG - TBD617 | PRE-09361.254 | DNU LUG WSA 13109.10846390 | DNU Lateral Hardening-Fuse-10846390 | N/A | N/A | N/A | N/A | N/A | 13109 | MANHATTAN | WSA | 0.2411 | 27 | 29 | 2021-10-01 |  |  | Combined with PRE-09361.55 (FID 90641822)
Enercon | 2020 | 2020 | PRE-09361.55 | LUG WSA 13109.90641822 | Lateral Hardening-Fuse-90641822 | CKT: 13109 - 90641822 | 2273297 | LUG WSA 13109.90641822 OH | 2273300 | LUG WSA 13109.90641822 UG | LUG C019 | 4500274705 | N/A | N/A | 2020 | LUG - TBD476 | PRE-09361.55 | LUG WSA 13109.90641822 | Lateral Hardening-Fuse-90641822 | CKT: 13109 - 90641822 | 2273297 | LUG WSA 13109.90641822 OH | 2273300 | LUG WSA 13109.90641822 UG | 13109 | MANHATTAN | WSA | 0.21742 | 22 | 413 | 2020-08-01 | 2021-04-01 | 2021-07-01 | Combined with PRE-09361.254 (FID 10846390/LUG-TBD617)
Enercon | 2020 | 2020 | PRE-09361.56 | LUG WSA 13747.10299739 | Lateral Hardening-Fuse-10299739 | CKT: 13747 - 10299739 | 2273306 | LUG WSA 13747.10299739 OH | 2273308 | LUG WSA 13747.10299739 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD477 | PRE-09361.56 | LUG WSA 13747.10299739 | Lateral Hardening-Fuse-10299739 | CKT: 13747 - 10299739 | 2273306 | LUG WSA 13747.10299739 OH | 2273308 | LUG WSA 13747.10299739 UG | 13747 | CASEY ROAD | WSA | 0.10038 | 5 | 128 | 2020-08-01 | 2021-04-01 | 2021-06-01
Enercon | 2020 | 2020 | PRE-09361.57 | LUG WSA 13756.60165357 | Lateral Hardening-Fuse-60165357 | CKT: 13756 - 60165357 | 2273311 | LUG WSA 13756.60165357 OH | 2273314 | LUG WSA 13756.60165357 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD478 | PRE-09361.57 | LUG WSA 13756.60165357 | Lateral Hardening-Fuse-60165357 | CKT: 13756 - 60165357 | 2273311 | LUG WSA 13756.60165357 OH | 2273314 | LUG WSA 13756.60165357 UG | 13756 | GRANADA | WSA | 0.26989 | 26 | 133 | 2020-09-01 | 2021-04-01 | 2021-07-01
Enercon | 2020 | 2020 | PRE-09361.58 | LUG WSA 13491.10230118 | Lateral Hardening-Fuse-10230118 | CKT: 13491 - 10230118 | 2273318 | LUG WSA 13491.10230118 OH | 2273320 | LUG WSA 13491.10230118 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD479 | PRE-09361.58 | LUG WSA 13491.10230118 | Lateral Hardening-Fuse-10230118 | CKT: 13491 - 10230118 | 2273318 | LUG WSA 13491.10230118 OH | 2273320 | LUG WSA 13491.10230118 UG | 13491 | JACKSON ROAD | WSA | 0.51477 | 36 | 94 | 2020-09-01 | 2021-04-01 | 2021-07-01
Enercon | 2020 | 2020 | PRE-09361.59 | LUG WSA 13141.92630916 | Lateral Hardening-Fuse-92630916 | CKT: 13141 - 92630916 | 2273323 | LUG WSA 13141.92630916 OH | 2273326 | LUG WSA 13141.92630916 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD480 | PRE-09361.59 | LUG WSA 13141.92630916 | Lateral Hardening-Fuse-92630916 | CKT: 13141 - 92630916 | 2273323 | LUG WSA 13141.92630916 OH | 2273326 | LUG WSA 13141.92630916 UG | 13141 | HYDE PARK | WSA | 0.40398 | 35 | 41 | 2020-10-01 | 2021-05-01 | 2021-08-01
Enercon | 2020 | 2020 | PRE-09361.60 | LUG WSA 13673.10277744 | Lateral Hardening-Fuse-10277744 | CKT: 13673 - 10277744 | 2273330 | LUG WSA 13673.10277744 OH | 2273332 | LUG WSA 13673.10277744 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD481 | PRE-09361.60 | LUG WSA 13673.10277744 | Lateral Hardening-Fuse-10277744 | CKT: 13673 - 10277744 | 2273330 | LUG WSA 13673.10277744 OH | 2273332 | LUG WSA 13673.10277744 UG | 13673 | MEADOW PARK | WSA | 1.0036 | 56 | 266 | 2020-09-01 | 2021-05-01 | 2021-08-01
Enercon | 2020 | 2020 | PRE-09361.61 | LUG WSA 13138.60079254 | Lateral Hardening-Fuse-60079254 | CKT: 13138 - 60079254 | 2273333 | LUG WSA 13138.60079254 OH | 2273334 | LUG WSA 13138.60079254 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD482 | PRE-09361.61 | LUG WSA 13138.60079254 | Lateral Hardening-Fuse-60079254 | CKT: 13138 - 60079254 | 2273333 | LUG WSA 13138.60079254 OH | 2273334 | LUG WSA 13138.60079254 UG | 13138 | HABANA AVENUE | WSA | 0.092045 | 13 | 152 | 2020-10-01 | 2021-05-01 | 2021-07-01
Enercon | 2020 | 2020 | PRE-09361.62 | LUG WSA 13141.92442349 | Lateral Hardening-Fuse-92442349 | CKT: 13141 - 92442349 | 2273327 | LUG WSA 13141.92442349 OH | 2273331 | LUG WSA 13141.92442349 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD483 | PRE-09361.62 | LUG WSA 13141.92442349 | Lateral Hardening-Fuse-92442349 | CKT: 13141 - 92442349 | 2273327 | LUG WSA 13141.92442349 OH | 2273331 | LUG WSA 13141.92442349 UG | 13141 | HYDE PARK | WSA | 0.40189 | 43 | 122 | 2020-10-01 | 2021-04-01 | 2021-09-01
Enercon | 2020 | 2020 | PRE-09361.63 | LUG WSA 13333.10007582 | Lateral Hardening-Fuse-10007582 | CKT: 13333 - 10007582 | 2273321 | LUG WSA 13333.10007582 OH | 2273324 | LUG WSA 13333.10007582 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD484 | PRE-09361.63 | LUG WSA 13333.10007582 | Lateral Hardening-Fuse-10007582 | CKT: 13333 - 10007582 | 2273321 | LUG WSA 13333.10007582 OH | 2273324 | LUG WSA 13333.10007582 UG | 13333 | WATERS AVENUE | WSA | 0.30455 | 27 | 24 | 2020-10-01 | 2021-05-01 | 2021-07-01
Enercon | 2020 | 2020 | PRE-09361.64 | LUG WSA 13586.92298267 | Lateral Hardening-Fuse-92298267 | CKT: 13586 - 92298267 | 2273317 | LUG WSA 13586.92298267 OH | 2273319 | LUG WSA 13586.92298267 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD485 | PRE-09361.64 | LUG WSA 13586.92298267 | Lateral Hardening-Fuse-92298267 | CKT: 13586 - 92298267 | 2273317 | LUG WSA 13586.92298267 OH | 2273319 | LUG WSA 13586.92298267 UG | 13586 | DALE MABRY | WSA | 0.44905 | 45 | 459 | 2020-10-01 | 2021-05-01 | 2021-08-01
Enercon | 2020 | 2022 | PRE-09361.65 | LUG WSA 13138.10145625 | Lateral Hardening-Fuse-10145625 | CKT: 13138 - 10145625 | 2273309 | LUG WSA 13138.10145625 OH | 2273313 | LUG WSA 13138.10145625 UG | LUG C036 | 4500274705 | N/A | N/A | 2021 | LUG - TBD589 | PRE-09361.226 | DNU LUG WSA 13138.10145602 | DNU Lateral Hardening-Fuse-10145602 | N/A | N/A | N/A | N/A | N/A | 13138 | HABANA AVENUE | WSA | 0.22027 | 23 | 257 | 2021-07-01 |  |  | Combined with PRE-09361.65 (FID 10145625)
Enercon | 2020 | 2020 | PRE-09361.65 | LUG WSA 13138.10145625 | Lateral Hardening-Fuse-10145625 | CKT: 13138 - 10145625 | 2273309 | LUG WSA 13138.10145625 OH | 2273313 | LUG WSA 13138.10145625 UG | LUG C036 | 4500274705 | N/A | N/A | 2020 | LUG - TBD486 | PRE-09361.65 | LUG WSA 13138.10145625 | Lateral Hardening-Fuse-10145625 | CKT: 13138 - 10145625 | 2273309 | LUG WSA 13138.10145625 OH | 2273313 | LUG WSA 13138.10145625 UG | 13138 | HABANA AVENUE | WSA | 0.3 | 27 | 343 | 2020-10-01 | 2021-09-01 | 2021-12-01 | Combined with PRE-09361.226 (FID 10145602)
Enercon | 2020 | 2020 | PRE-09361.66 | LUG WSA 13140.10013916 | Lateral Hardening-Fuse-10013916 | CKT: 13140 - 10013916 | 2273304 | LUG WSA 13140.10013916 OH | 2273307 | LUG WSA 13140.10013916 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD487 | PRE-09361.66 | LUG WSA 13140.10013916 | Lateral Hardening-Fuse-10013916 | CKT: 13140 - 10013916 | 2273304 | LUG WSA 13140.10013916 OH | 2273307 | LUG WSA 13140.10013916 UG | 13140 | HYDE PARK | WSA | 0.10284 | 13 | 143 | 2020-10-01 | 2021-10-01 | 2021-12-01
Enercon | 2020 | 2021 | PRE-09361.67 | LUG WSA 13113.90796385 | Lateral Hardening-Fuse-90796385 | CKT: 13113 - 90796385 | 2273299 | LUG WSA 13113.90796385 OH | 2273301 | LUG WSA 13113.90796385 UG | LUG C021 | 4500274705 | N/A | N/A | 2021 | LUG - TBD534 | PRE-09361.171 | DNU LUG WSA 13113.60340774 | DNU Lateral Hardening-Fuse-60340774 | N/A | N/A | N/A | N/A | N/A | 13113 | MANHATTAN | WSA | 0.20398 | 19 | 35 | 2021-03-01 |  |  | Combined with PRE-09361.67 (FID 90796385)
Enercon | 2020 | 2020 | PRE-09361.67 | LUG WSA 13113.90796385 | Lateral Hardening-Fuse-90796385 | CKT: 13113 - 90796385 | 2273299 | LUG WSA 13113.90796385 OH | 2273301 | LUG WSA 13113.90796385 UG | LUG C021 | 4500274705 | N/A | N/A | 2020 | LUG - TBD488 | PRE-09361.67 | LUG WSA 13113.90796385 | Lateral Hardening-Fuse-90796385 | CKT: 13113 - 90796385 | 2273299 | LUG WSA 13113.90796385 OH | 2273301 | LUG WSA 13113.90796385 UG | 13113 | MANHATTAN | WSA | 0.51326 | 34 | 233 | 2020-10-01 | 2021-09-01 | 2021-12-01 | Combined with PRE-09361.171 (FID 60340774)
Enercon | 2020 | 2020 | PRE-09361.68 | LUG WSA 13138.10145628 | Lateral Hardening-Fuse-10145628 | CKT: 13138 - 10145628 | 2273294 | LUG WSA 13138.10145628 OH | 2273296 | LUG WSA 13138.10145628 UG | LUG C059/C062 | 4500274705 | N/A | N/A | 2020 | LUG - TBD489 | PRE-09361.68 | LUG WSA 13138.10145628 | Lateral Hardening-Fuse-10145628 | CKT: 13138 - 10145628 | 2273294 | LUG WSA 13138.10145628 OH | 2273296 | LUG WSA 13138.10145628 UG | 13138 | HABANA AVENUE | WSA | 0.30379 | 18 | 352 | 2020-09-01 | 2021-09-01 | 2021-12-01 | Combined with PRE-09361.267 (FID 10145629) & PRE-09361.281 (FID 10145606)
Enercon | 2020 | 2020 | PRE-09361.69 | LUG WSA 13164.10158909 | Lateral Hardening-Fuse-10158909 | CKT: 13164 - 10158909 | 2273288 | LUG WSA 13164.10158909 OH | 2273291 | LUG WSA 13164.10158909 UG | LUG CO78 | 4500274705 | N/A | N/A | 2020 | LUG - TBD490 | PRE-09361.69 | LUG WSA 13164.10158909 | Lateral Hardening-Fuse-10158909 | CKT: 13164 - 10158909 | 2273288 | LUG WSA 13164.10158909 OH | 2273291 | LUG WSA 13164.10158909 UG | 13164 | MATANZAS | WSA | 0.79432 | 68 | 270 | 2020-09-01 | 2021-06-01 | 2021-12-01 | Combined with PRE-09361.165 (FID 90252716)
Enercon | 2020 | 2020 | PRE-09361.70 | LUG WSA 13140.91873275 | Lateral Hardening-Fuse-91873275 | CKT: 13140 - 91873275 | 2273284 | LUG WSA 13140.91873275 OH | 2273286 | LUG WSA 13140.91873275 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD491 | PRE-09361.70 | LUG WSA 13140.91873275 | Lateral Hardening-Fuse-91873275 | CKT: 13140 - 91873275 | 2273284 | LUG WSA 13140.91873275 OH | 2273286 | LUG WSA 13140.91873275 UG | 13140 | HYDE PARK | WSA | 0.5267 | 55 | 31 | 2020-10-01 | 2021-02-01 | 2021-06-01
Enercon | 2020 | 2021 | PRE-09361.71 | LUG WSA 13605.91052996 | Lateral Hardening-Fuse-91052996 | CKT: 13605 - 91052996 | 2273278 | LUG WSA 13605.91052996 OH | 2273280 | LUG WSA 13605.91052996 UG | LUG C001 | 4500274705 | N/A | N/A | 2021 | LUG - TBD496 | PRE-09361.71 | DNU LUG WSA 13605.90568909 | DNU Lateral Hardening-Fuse-90568909 | N/A | N/A | N/A | N/A | N/A | 13605 | MACDILL | WSA | [6 empty] | Combined with PRE-09361.71 (FID 91052996) & LUG-TBD526 (FID 90427351)
Enercon | 2020 | 2021 | PRE-09361.71 | LUG WSA 13605.91052996 | Lateral Hardening-Fuse-91052996 | CKT: 13605 - 91052996 | 2273278 | LUG WSA 13605.91052996 OH | 2273280 | LUG WSA 13605.91052996 UG | LUG C001 | 4500274705 | N/A | N/A | 2021 | LUG - TBD526 | PRE-09361.71 | DNU LUG WSA 13605.90427351 | DNU Lateral Hardening-Fuse-91052996 | N/A | N/A | N/A | N/A | N/A | 13605 | MACDILL | WSA | 0 | 29 | 50 | 2021-01-01 |  |  | Combined with LUG-TBD496 (FID 90568909) & PRE-09361.71 (FID 90427351)
Enercon | 2020 | 2020 | PRE-09361.71 | LUG WSA 13605.91052996 | Lateral Hardening-Fuse-91052996 | CKT: 13605 - 91052996 | 2273278 | LUG WSA 13605.91052996 OH | 2273280 | LUG WSA 13605.91052996 UG | LUG C001 | 4500274705 | N/A | N/A | 2020 | LUG - TBD492 | PRE-09361.71 | LUG WSA 13605.91052996 | Lateral Hardening-Fuse-91052996 | CKT: 13605 - 91052996 | 2273278 | LUG WSA 13605.91052996 OH | 2273280 | LUG WSA 13605.91052996 UG | 13605 | MACDILL | WSA | 0.33201 | 27 | 115 | 2020-10-01 | 2021-08-01 | 2021-10-01 | Combined with LUG-TBD496 (FID 90568909) & LUG-TBD526 (FID 90427351)
Enercon | 2020 | 2022 | PRE-09361.72 | LUG WSA 13071.60170422 | Lateral Hardening-Fuse-60170422 | CKT: 13071 - 60170422 | 2273270 | LUG WSA 13071.60170422 OH | 2273272 | LUG WSA 13071.60170422 UG | LUG C022 | 4500274705 | N/A | N/A | 2021 | LUG - TBD607 | PRE-09361.72 | DNU LUG WSA 13071.93035682 | DNU Lateral Hardening-Fuse-93035682 | N/A | N/A | N/A | N/A | N/A | 13071 | KEYSTONE | WSA | 0.63447 | 40 | 178 | 2021-09-01 |  |  | Combined with PRE-09361.72 (FID 60170422)
Enercon | 2020 | 2020 | PRE-09361.72 | LUG WSA 13071.60170422 | Lateral Hardening-Fuse-60170422 | CKT: 13071 - 60170422 | 2273270 | LUG WSA 13071.60170422 OH | 2273272 | LUG WSA 13071.60170422 UG | LUG C022 | 4500274705 | N/A | N/A | 2020 | LUG - TBD493 | PRE-09361.72 | LUG WSA 13071.60170422 | Lateral Hardening-Fuse-60170422 | CKT: 13071 - 60170422 | 2273270 | LUG WSA 13071.60170422 OH | 2273272 | LUG WSA 13071.60170422 UG | 13071 | KEYSTONE | WSA | 0.9947 | 74 | 362 | 2020-09-01 | 2021-06-01 | 2021-11-01 | Combined with PRE-09361.244 (FID 93035682)
Enercon | 2020 | 2020 | PRE-09361.73 | LUG WSA 13111.92999604 | Lateral Hardening-Fuse-92999604 | CKT: 13111 - 92999604 | 2273262 | LUG WSA 13111.92999604 OH | 2273266 | LUG WSA 13111.92999604 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD494 | PRE-09361.73 | LUG WSA 13111.92999604 | Lateral Hardening-Fuse-92999604 | CKT: 13111 - 92999604 | 2273262 | LUG WSA 13111.92999604 OH | 2273266 | LUG WSA 13111.92999604 UG | 13111 | MANHATTAN | WSA | 0.41705 | 32 | 61 | 2020-10-01 | 2021-10-01 | 2021-12-01
Enercon | 2020 | 2020 | PRE-09361.74 | LUG WSA 13586.60303627 | Lateral Hardening-Fuse-60303627 | CKT: 13586 - 60303627 | 2273255 | LUG WSA 13586.60303627 OH | 2273260 | LUG WSA 13586.60303627 UG |  | 4500274705 | N/A | N/A | 2020 | LUG - TBD495 | PRE-09361.74 | LUG WSA 13586.60303627 | Lateral Hardening-Fuse-60303627 | CKT: 13586 - 60303627 | 2273255 | LUG WSA 13586.60303627 OH | 2273260 | LUG WSA 13586.60303627 UG | 13586 | DALE MABRY | WSA | 1.0686 | 67 | 69 | 2020-09-01 | 2021-07-01 | 2021-12-01
Fishel | 2021 | 2021 | CANCELLED | LUG PCA 13961.10696419 | Lateral Hardening-Fuse-10696419 | N/A | N/A | N/A | N/A | N/A |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD20 | CANCELLED | LUG PCA 13961.10696419 | Lateral Hardening-Fuse-10696419 | N/A | N/A | N/A | N/A | N/A | 13961 | TERRACE | PCA | 0.5589 | 26 | 3 | 2021-01-01 | 2021-04-01 | 2021-06-01 | Project cancelled, as of 11/15, due to new construction project in area
Fishel | 2020 | 2020 | PRE-09361.1 | LUG PCA 13390.92599119 | Lateral Hardening-Fuse-92599119 | CKT: 13390 - 92599119 | 2271216 | LUG PCA 13390.92599119 OH | 2271217 | LUG PCA 13390.92599119 UG | LUG C035 | 4500272910 | N/A | N/A | 2020 | LUG - TBD1 | PRE-09361.1 | LUG PCA 13390.92599119 | Lateral Hardening-Fuse-92599119 | CKT: 13390 - 92599119 | 2271216 | LUG PCA 13390.92599119 OH | 2271217 | LUG PCA 13390.92599119 UG | 13390 | KIRKLAND ROAD | PCA | 0.72367 | 46 | 266 | 2020-06-01 | 2020-06-20 | 2020-12-20 | Combined with PRE-09361.45 (FID 10643541)
Fishel | 2020 | 2020 | PRE-09361.1 | LUG PCA 13390.92599119 | Lateral Hardening-Fuse-92599119 | CKT: 13390 - 92599119 | 2271216 | LUG PCA 13390.92599119 OH | 2271217 | LUG PCA 13390.92599119 UG | LUG C035 | 4500272910 | N/A | N/A | 2020 | LUG - TBD15 | PRE-09361.45 | DNU LUG PCA 13390.10643541 | DNU Lateral Hardening-Fuse-10643541 | DNU CKT: 13390 - 10643541 | 2274185 | DNU LUG PCA 13390.10643541 OH | 2274186 | DNU LUG PCA 13390.10643541 UG | 13390 | KIRKLAND ROAD | PCA | 1.1722 | 67 | 221 | 2020-09-01 | 2021-03-01 | 2021-06-01 | Combined with PRE-09361.1 (FID 92599119)
Fishel | 2020 | 2020 | PRE-09361.2 | LUG PCA 13961.92829453 | Lateral Hardening-Fuse-92829453 | CKT: 13961 - 92829453 | 2274016 | LUG PCA 13961.92829453 OH | 2274027 | LUG PCA 13961.92829453 UG |  | 4500272910 | N/A | N/A | 2020 | LUG - TBD2 | PRE-09361.2 | LUG PCA 13961.92829453 | Lateral Hardening-Fuse-92829453 | CKT: 13961 - 92829453 | 2274016 | LUG PCA 13961.92829453 OH | 2274027 | LUG PCA 13961.92829453 UG | 13961 | TERRACE | PCA | 0.33693 | 25 | 447 | 2020-06-01 | 2021-01-01 | 2021-03-01
Fishel | 2021 | 2021 | PRE-09361.285 | LUG PCA 13961.10696431 | Lateral Hardening-Fuse-10696431 | CKT: 13961 - 10696431 | 2310526 | LUG PCA 13961.10696431 OH | 2310527 | LUG PCA 13961.10696431 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD19 | PRE-09361.285 | LUG PCA 13961.10696431 | Lateral Hardening-Fuse-10696431 | CKT: 13961 - 10696431 | 2310526 | LUG PCA 13961.10696431 OH | 2310527 | LUG PCA 13961.10696431 UG | 13961 | TERRACE | PCA | 0.15795 | 8 | 4 | 2021-01-01 | 2021-04-01 | 2021-05-01
Fishel | 2021 | 2021 | PRE-09361.286 | LUG PCA 13785.92299245 | Lateral Hardening-Fuse-92299245 | CKT: 13785 - 92299245 | 2310665 | LUG PCA 13785.92299245 OH | 2310666 | LUG PCA 13785.92299245 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD21 | PRE-09361.286 | LUG PCA 13785.92299245 | Lateral Hardening-Fuse-92299245 | CKT: 13785 - 92299245 | 2310665 | LUG PCA 13785.92299245 OH | 2310666 | LUG PCA 13785.92299245 UG | 13785 | PINECREST | PCA | 1.0799 | 57 | 174 | 2021-01-01 | 2021-04-01 | 2021-06-01
Fishel | 2021 | 2021 | PRE-09361.287 | LUG PCA 13961.92834683 | Lateral Hardening-Fuse-92834683 | CKT: 13961 - 92834683 | 2310667 | LUG PCA 13961.92834683 OH | 2310668 | LUG PCA 13961.92834683 UG | LUG CO70 | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD22 | PRE-09361.287 | LUG PCA 13961.92834683 | Lateral Hardening-Fuse-92834683 | CKT: 13961 - 92834683 | 2310667 | LUG PCA 13961.92834683 OH | 2310668 | LUG PCA 13961.92834683 UG | 13961 | TERRACE | PCA | 0.72027 | 37 | 23 | 2021-01-01 | 2021-05-01 | 2021-07-01 | Combined with PRE-09361.291 (FID 10696417)
Fishel | 2021 | 2021 | PRE-09361.288 | LUG PCA 13462.91412064 | Lateral Hardening-Fuse-91412064 | CKT: 13462 - 91412064 | 2310493 | LUG PCA 13462.91412064 OH | 2310496 | LUG PCA 13462.91412064 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD23 | PRE-09361.288 | LUG PCA 13462.91412064 | Lateral Hardening-Fuse-91412064 | CKT: 13462 - 91412064 | 2310493 | LUG PCA 13462.91412064 OH | 2310496 | LUG PCA 13462.91412064 UG | 13462 | ALEXANDER ROAD | PCA | 0.050379 | 5 | 46 | 2021-01-01 | 2021-04-01 | 2021-05-01
Fishel | 2021 | 2021 | PRE-09361.289 | LUG PCA 13961.10696486 | Lateral Hardening-Fuse-10696486 | CKT: 13961 - 10696486 | 2310528 | LUG PCA 13961.10696486 OH | 2310529 | LUG PCA 13961.10696486 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD24 | PRE-09361.289 | LUG PCA 13961.10696486 | Lateral Hardening-Fuse-10696486 | CKT: 13961 - 10696486 | 2310528 | LUG PCA 13961.10696486 OH | 2310529 | LUG PCA 13961.10696486 UG | 13961 | TERRACE | PCA | 0.5447 | 32 | 38 | 2021-01-01 | 2021-05-01 | 2021-07-01
Fishel | 2021 | 2021 | PRE-09361.290 | LUG PCA 13961.91967308 | Lateral Hardening-Fuse-91967308 | CKT: 13961 - 91967308 | 2310530 | LUG PCA 13961.91967308 OH | 2310532 | LUG PCA 13961.91967308 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD25 | PRE-09361.290 | LUG PCA 13961.91967308 | Lateral Hardening-Fuse-91967308 | CKT: 13961 - 91967308 | 2310530 | LUG PCA 13961.91967308 OH | 2310532 | LUG PCA 13961.91967308 UG | 13961 | TERRACE | PCA | 0.48693 | 32 | 28 | 2021-01-01 | 2021-06-01 | 2021-08-01
Fishel | 2021 | 2021 | PRE-09361.287 | LUG PCA 13961.92834683 | Lateral Hardening-Fuse-92834683 | CKT: 13961 - 92834683 | 2310667 | LUG PCA 13961.92834683 OH | 2310668 | LUG PCA 13961.92834683 UG | LUG CO70 | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD26 | PRE-09361.291 | DNU LUG PCA 13961.10696417 | DNU Lateral Hardening-Fuse-10696417 | DNU CKT: 13961 - 10696417 | 2310672 | DNU LUG PCA 13961.10696417 OH | 2310673 | DNU LUG PCA 13961.10696417 UG | 13961 | TERRACE | PCA | 0.11345 | 7 | 3 | 2021-01-01 | 2021-07-01 | 2021-08-01 | Combined with PRE-09361.287 (FID 92834683)
Fishel | 2021 | 2021 | PRE-09361.292 | LUG WHA 13916.60279623 | Lateral Hardening-Fuse-60279623 | CKT: 13916 - 60279623 | 2310521 | LUG WHA 13916.60279623 OH | 2310523 | LUG WHA 13916.60279623 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD27 | PRE-09361.292 | LUG WHA 13916.60279623 | Lateral Hardening-Fuse-60279623 | CKT: 13916 - 60279623 | 2310521 | LUG WHA 13916.60279623 OH | 2310523 | LUG WHA 13916.60279623 UG | 13916 | LAKE RUBY | WHA | 0.18561 | 9 | 282 | 2021-01-01 | 2021-07-01 | 2021-08-01
Fishel | 2021 | 2021 | PRE-09361.306 | LUG WHA 13297.10560425 | Lateral Hardening-Fuse-10560425 | CKT: 13297 - 10560425 | 2310711 | LUG WHA 13297.10560425 OH | 2310714 | LUG WHA 13297.10560425 UG | LUG CO74 | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD28 | PRE-09361.293 | DNU LUG WHA 13297.10560430 | DNU Lateral Hardening-Fuse-10560430 | DNU CKT: 13297 - 10560430 | 2310678 | DNU LUG WHA 13297.10560430 OH | 2310679 | DNU LUG WHA 13297.10560430 UG | 13297 | JAN PHYL | WHA | 0.42064 | 27 | 333 | 2021-01-01 | 2021-07-01 | 2021-09-01 | Combined with PRE-09361.306 (FID 10560425)
Fishel | 2021 | 2021 | PRE-09361.294 | HOLD LUG WHA 13314.92426509 | Lateral Hardening-Fuse-92426509 | CKT: 13314 - 92426509 | 2310682 | HOLD LUG WHA 13314.92426509 OH | 2310684 | HOLD LUG WHA 13314.92426509 UG | HOLD | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD29 | PRE-09361.294 | LUG WHA 13314.92426509 | Lateral Hardening-Fuse-92426509 | CKT: 13314 - 92426509 | 2310682 | LUG WHA 13314.92426509 OH | 2310684 | LUG WHA 13314.92426509 UG | 13314 | EAST WINTER HAVEN | WHA | 0.40208 | 33 | 246 | 2021-03-01 | 2021-07-01 | 2021-09-01 | Placed On Hold, per Jason Blackwell, on 8/4/2021
Fishel | 2021 | 2021 | PRE-09361.295 | LUG WHA 13118.92612349 | Lateral Hardening-Fuse-92612349 | CKT: 13118 - 92612349 | 2310454 | LUG WHA 13118.92612349 OH | 2310456 | LUG WHA 13118.92612349 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD30 | PRE-09361.295 | LUG WHA 13118.92612349 | Lateral Hardening-Fuse-92612349 | CKT: 13118 - 92612349 | 2310454 | LUG WHA 13118.92612349 OH | 2310456 | LUG WHA 13118.92612349 UG | 13118 | LAKE ALFRED | WHA | 0.93693 | 39 | 220 | 2021-03-01 | 2021-07-01 | 2021-09-01
Fishel | 2021 | 2021 | PRE-09361.296 | LUG WHA 13313.90084626 | Lateral Hardening-Fuse-90084626 | CKT: 13313 - 90084626 | 2310490 | LUG WHA 13313.90084626 OH | 2310491 | LUG WHA 13313.90084626 UG | LUG C069 | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD31 | PRE-09361.296 | LUG WHA 13313.90084626 | Lateral Hardening-Fuse-90084626 | CKT: 13313 - 90084626 | 2310490 | LUG WHA 13313.90084626 OH | 2310491 | LUG WHA 13313.90084626 UG | 13313 | EAST WINTER HAVEN | WHA | 0.092045 | 9 | 35 | 2021-03-01 | 2021-07-01 | 2021-08-01 | Combined with PRE-09361.300 (FID 60568375) and PRE-09361.313 (FID 93103371)
Fishel | 2021 | 2021 | PRE-09361.297 | LUG WHA 13699.10637242 | Lateral Hardening-Fuse-10637242 | CKT: 13699 - 10637242 | 2310505 | LUG WHA 13699.10637242 OH | 2310506 | LUG WHA 13699.10637242 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD32 | PRE-09361.297 | LUG WHA 13699.10637242 | Lateral Hardening-Fuse-10637242 | CKT: 13699 - 10637242 | 2310505 | LUG WHA 13699.10637242 OH | 2310506 | LUG WHA 13699.10637242 UG | 13699 | BERKLEY ROAD | WHA | 0.62462 | 37 | 284 | 2021-03-01 | 2021-07-01 | 2021-09-01
Fishel | 2021 | 2021 | PRE-09361.298 | LUG WHA 13313.10684614 | Lateral Hardening-Fuse-10684614 | CKT: 13313 - 10684614 | 2310685 | LUG WHA 13313.10684614 OH | 2310686 | LUG WHA 13313.10684614 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD33 | PRE-09361.298 | LUG WHA 13313.10684614 | Lateral Hardening-Fuse-10684614 | CKT: 13313 - 10684614 | 2310685 | LUG WHA 13313.10684614 OH | 2310686 | LUG WHA 13313.10684614 UG | 13313 | EAST WINTER HAVEN | WHA | 0.1358 | 16 | 106 | 2021-03-01 | 2021-07-01 | 2021-09-01
Fishel | 2021 | 2021 | PRE-09361.299 | LUG WHA 13296.92376304 | Lateral Hardening-Fuse-92376304 | CKT: 13296 - 92376304 | 2310688 | LUG WHA 13296.92376304 OH | 2310689 | LUG WHA 13296.92376304 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD34 | PRE-09361.299 | LUG WHA 13296.92376304 | Lateral Hardening-Fuse-92376304 | CKT: 13296 - 92376304 | 2310688 | LUG WHA 13296.92376304 OH | 2310689 | LUG WHA 13296.92376304 UG | 13296 | JAN PHYL | WHA | 0.29015 | 20 | 200 | 2021-03-01 | 2021-07-01 | 2021-09-01
Fishel | 2020 | 2020 | PRE-09361.3 | LUG PCA 13724.90911087 | Lateral Hardening-Fuse-90911087 | CKT: 13724 - 90911087 | 2274044 | LUG PCA 13724.90911087 OH | 2274045 | LUG PCA 13724.90911087 UG |  | 4500272910 | N/A | N/A | 2020 | LUG - TBD3 | PRE-09361.3 | LUG PCA 13724.90911087 | Lateral Hardening-Fuse-90911087 | CKT: 13724 - 90911087 | 2274044 | LUG PCA 13724.90911087 OH | 2274045 | LUG PCA 13724.90911087 UG | 13724 | GALLAGHER ROAD | PCA | 0.5392 | 32 | 31 | 2020-06-01 | 2021-01-01 | 2021-03-01
Fishel | 2021 | 2021 | PRE-09361.296 | LUG WHA 13313.90084626 | Lateral Hardening-Fuse-90084626 | CKT: 13313 - 90084626 | 2310490 | LUG WHA 13313.90084626 OH | 2310491 | LUG WHA 13313.90084626 UG | LUG C069 | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD35 | PRE-09361.300 | DNU LUG WHA 13313.60568375 | DNU Lateral Hardening-Fuse-60568375 | DNU CKT: 13313 - 60568375 | 2310701 | DNU LUG WHA 13313.60568375 OH | 2310702 | DNU LUG WHA 13313.60568375 UG | 13313 | EAST WINTER HAVEN | WHA | 0.22765 | 34 | 33 | 2021-03-01 | 2021-07-01 | 2021-09-01 | Combined with PRE-09361.296 (FID 90084626) and PRE-09361.313 (FID 93103371)
Fishel | 2021 | 2021 | PRE-09361.301 | LUG WHA 13297.60269456 | Lateral Hardening-Fuse-60269456 | CKT: 13297 - 60269456 | 2310703 | LUG WHA 13297.60269456 OH | 2310705 | LUG WHA 13297.60269456 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD36 | PRE-09361.301 | LUG WHA 13297.60269456 | Lateral Hardening-Fuse-60269456 | CKT: 13297 - 60269456 | 2310703 | LUG WHA 13297.60269456 OH | 2310705 | LUG WHA 13297.60269456 UG | 13297 | JAN PHYL | WHA | 0.30625 | 30 | 59 | 2021-03-01 | 2021-08-01 | 2021-10-01
Fishel | 2021 | 2021 | PRE-09361.302 | LUG WHA 13699.10637259 | Lateral Hardening-Fuse-10637259 | CKT: 13699 - 10637259 | 2310513 | LUG WHA 13699.10637259 OH | 2310516 | LUG WHA 13699.10637259 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD37 | PRE-09361.302 | LUG WHA 13699.10637259 | Lateral Hardening-Fuse-10637259 | CKT: 13699 - 10637259 | 2310513 | LUG WHA 13699.10637259 OH | 2310516 | LUG WHA 13699.10637259 UG | 13699 | BERKLEY ROAD | WHA | 0.15587 | 13 | 26 | 2021-04-01 | 2021-08-01 | 2021-09-01
Fishel | 2021 | 2021 | PRE-09361.303 | LUG WHA 13473.60168916 | Lateral Hardening-Fuse-60168916 | CKT: 13473 - 60168916 | 2310498 | LUG WHA 13473.60168916 OH | 2310499 | LUG WHA 13473.60168916 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD38 | PRE-09361.303 | LUG WHA 13473.60168916 | Lateral Hardening-Fuse-60168916 | CKT: 13473 - 60168916 | 2310498 | LUG WHA 13473.60168916 OH | 2310499 | LUG WHA 13473.60168916 UG | 13473 | SOUTH ELOISE | WHA | 0.34356 | 24 | 419 | 2021-04-01 | 2021-08-01 | 2021-10-01
Fishel | 2021 | 2021 | PRE-09361.323 | LUG WHA 13296.10562361 | Lateral Hardening-Fuse-10562361 | CKT: 13296 - 10562361 | 2310767 | LUG WHA 13296.10562361 OH | 2310770 | LUG WHA 13296.10562361 UG | LUG CO73 | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD39 | PRE-09361.304 | LUG WHA 13296.10562356 | DNU Lateral Hardening-Fuse-10562356 | DNU CKT: 13296 - 10562356 | 2310706 | DNU LUG WHA 13296.10562356 OH | 2310709 | DNU LUG WHA 13296.10562356 UG | 13296 | JAN PHYL | WHA | 0.22064 | 17 | 29 | 2021-04-01 | 2021-08-01 | 2021-09-01 | Combined with PRE-09361.323 (FID 10562361)
Fishel | 2021 | 2021 | PRE-09361.305 | LUG WHA 13916.92509975 | Lateral Hardening-Fuse-92509975 | CKT: 13916 - 92509975 | 2310435 | LUG WHA 13916.92509975 OH | 2310437 | LUG WHA 13916.92509975 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD40 | PRE-09361.305 | LUG WHA 13916.92509975 | Lateral Hardening-Fuse-92509975 | CKT: 13916 - 92509975 | 2310435 | LUG WHA 13916.92509975 OH | 2310437 | LUG WHA 13916.92509975 UG | 13916 | LAKE RUBY | WHA | 0.45057 | 35 | 71 | 2021-04-01 | 2021-08-01 | 2021-10-01
Fishel | 2021 | 2021 | PRE-09361.306 | LUG WHA 13297.10560425 | Lateral Hardening-Fuse-10560425 | CKT: 13297 - 10560425 | 2310711 | LUG WHA 13297.10560425 OH | 2310714 | LUG WHA 13297.10560425 UG | LUG CO74 | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD41 | PRE-09361.306 | LUG WHA 13297.10560425 | Lateral Hardening-Fuse-10560425 | CKT: 13297 - 10560425 | 2310711 | LUG WHA 13297.10560425 OH | 2310714 | LUG WHA 13297.10560425 UG | 13297 | JAN PHYL | WHA | 0.3142 | 21 | 72 | 2021-04-01 | 2021-08-01 | 2021-10-01 | Combined with PRE-09361.293 (FID 10560430)
Fishel | 2021 | 2021 | PRE-09361.307 | LUG WHA 13296.60531111 | Lateral Hardening-Fuse-60531111 | CKT: 13296 - 60531111 | 2310717 | LUG WHA 13296.60531111 OH | 2310719 | LUG WHA 13296.60531111 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD42 | PRE-09361.307 | LUG WHA 13296.60531111 | Lateral Hardening-Fuse-60531111 | CKT: 13296 - 60531111 | 2310717 | LUG WHA 13296.60531111 OH | 2310719 | LUG WHA 13296.60531111 UG | 13296 | JAN PHYL | WHA | 0.95246 | 68 | 90 | 2021-04-01 | 2021-10-01 | 2021-10-01
Fishel | 2021 | 2021 | PRE-09361.308 | LUG WHA 13699.10637247 | Lateral Hardening-Fuse-10637247 | CKT: 13699 - 10637247 | 2310507 | LUG WHA 13699.10637247 OH | 2310509 | LUG WHA 13699.10637247 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD43 | PRE-09361.308 | LUG WHA 13699.10637247 | Lateral Hardening-Fuse-10637247 | CKT: 13699 - 10637247 | 2310507 | LUG WHA 13699.10637247 OH | 2310509 | LUG WHA 13699.10637247 UG | 13699 | BERKLEY ROAD | WHA | 0.18996 | 11 | 119 | 2021-05-01 | 2021-08-01 | 2021-09-01
Fishel | 2021 | 2021 | PRE-09361.309 | LUG WHA 13473.60168942 | Lateral Hardening-Fuse-60168942 | CKT: 13473 - 60168942 | 2310722 | LUG WHA 13473.60168942 OH | 2310725 | LUG WHA 13473.60168942 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD44 | PRE-09361.309 | LUG WHA 13473.60168942 | Lateral Hardening-Fuse-60168942 | CKT: 13473 - 60168942 | 2310722 | LUG WHA 13473.60168942 OH | 2310725 | LUG WHA 13473.60168942 UG | 13473 | SOUTH ELOISE | WHA | 0.34678 | 27 | 187 | 2021-05-01 | 2021-08-01 | 2021-10-01
Fishel | 2021 | 2021 | PRE-09361.319 | LUG WHA 13118.10535999 | Lateral Hardening-Fuse-10535999 | CKT: 13118 - 10535999 | 2310443 | LUG WHA 13118.10535999 OH | 2310452 | LUG WHA 13118.10535999 UG | LUG C065 | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD45 | PRE-09361.310 | DNU LUG WHA 13118.92659353 | DNU Lateral Hardening-Fuse-92659353 | DNU CKT: 13118 - 92659353 | 2310464 | DNU LUG WHA 13118.92659353 OH | 2310467 | DNU LUG WHA 13118.92659353 UG | 13118 | LAKE ALFRED | WHA | 0.40833 | 30 | 52 | 2021-05-01 | 2021-08-01 | 2021-10-01 | Combined with PRE-09361.319 (FID 10535999)
Fishel | 2021 | 2021 | PRE-09361.311 | LUG WHA 13118.10535995 | Lateral Hardening-Fuse-10535995 | CKT: 13118 - 10535995 | 2310727 | LUG WHA 13118.10535995 OH | 2310730 | LUG WHA 13118.10535995 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD46 | PRE-09361.311 | LUG WHA 13118.10535995 | Lateral Hardening-Fuse-10535995 | CKT: 13118 - 10535995 | 2310727 | LUG WHA 13118.10535995 OH | 2310730 | LUG WHA 13118.10535995 UG | 13118 | LAKE ALFRED | WHA | 0.95057 | 63 | 363 | 2021-05-01 | 2021-09-01 | 2021-11-01 | previously listed incorrectly as Fuse 10676209
Fishel | 2021 | 2021 | PRE-09361.312 | LUG WHA 13699.10637240 | Lateral Hardening-Fuse-10637240 | CKT: 13699 - 10637240 | 2310502 | LUG WHA 13699.10637240 OH | 2310503 | LUG WHA 13699.10637240 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD47 | PRE-09361.312 | LUG WHA 13699.10637240 | Lateral Hardening-Fuse-10637240 | CKT: 13699 - 10637240 | 2310502 | LUG WHA 13699.10637240 OH | 2310503 | LUG WHA 13699.10637240 UG | 13699 | BERKLEY ROAD | WHA | 1.0178 | 48 | 137 | 2021-06-01 | 2021-10-01 | 2021-12-01
Fishel | 2021 | 2021 | PRE-09361.296 | LUG WHA 13313.90084626 | Lateral Hardening-Fuse-90084626 | CKT: 13313 - 90084626 | 2310490 | LUG WHA 13313.90084626 OH | 2310491 | LUG WHA 13313.90084626 UG | LUG C069 | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD48 | PRE-09361.313 | DNU LUG WHA 13313.93103371 | DNU Lateral Hardening-Fuse-93103371 | DNU CKT: 13313 - 93103371 | 2310733 | DNU LUG WHA 13313.93103371 OH | 2310735 | DNU LUG WHA 13313.93103371 UG | 13313 | EAST WINTER HAVEN | WHA | 0.10095 | 13 | 20 | 2021-06-01 | 2021-10-01 | 2021-12-01 | Combined with PRE-09361.296 (FID 90084626) and PRE-09361.300 (FID 60568375)
Fishel | 2021 | 2021 | PRE-09361.314 | LUG WHA 13118.92204382 | Lateral Hardening-Fuse-92204382 | CKT: 13118 - 92204382 | 2310737 | LUG WHA 13118.92204382 OH | 2310738 | LUG WHA 13118.92204382 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD49 | PRE-09361.314 | LUG WHA 13118.92204382 | Lateral Hardening-Fuse-92204382 | CKT: 13118 - 92204382 | 2310737 | LUG WHA 13118.92204382 OH | 2310738 | LUG WHA 13118.92204382 UG | 13118 | LAKE ALFRED | WHA | 0.69129 | 41 | 88 | 2021-06-01 | 2021-10-01 | 2021-12-01
Fishel | 2021 | 2021 | PRE-09361.315 | LUG WHA 13118.92659172 | Lateral Hardening-Fuse-92659172 | CKT: 13118 - 92659172 | 2310458 | LUG WHA 13118.92659172 OH | 2310459 | LUG WHA 13118.92659172 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD50 | PRE-09361.315 | LUG WHA 13118.92659172 | Lateral Hardening-Fuse-92659172 | CKT: 13118 - 92659172 | 2310458 | LUG WHA 13118.92659172 OH | 2310459 | LUG WHA 13118.92659172 UG | 13118 | LAKE ALFRED | WHA | 0.275 | 26 | 18 | 2021-06-01 | 2021-10-01 | 2021-12-01
Fishel | 2021 | 2021 | PRE-09361.316 | LUG WHA 13473.92097460 | Lateral Hardening-Fuse-92097460 | CKT: 13473 - 92097460 | 2310740 | LUG WHA 13473.92097460 OH | 2310743 | LUG WHA 13473.92097460 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD51 | PRE-09361.316 | LUG WHA 13473.92097460 | Lateral Hardening-Fuse-92097460 | CKT: 13473 - 92097460 | 2310740 | LUG WHA 13473.92097460 OH | 2310743 | LUG WHA 13473.92097460 UG | 13473 | SOUTH ELOISE | WHA | 0.24015 | 19 | 152 | 2021-06-01 | 2021-10-01 | 2021-12-01
Fishel | 2021 | 2021 | PRE-09361.317 | LUG WHA 13296.90010289 | Lateral Hardening-Fuse-90010289 | CKT: 13296 - 90010289 | 2310746 | LUG WHA 13296.90010289 OH | 2310751 | LUG WHA 13296.90010289 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD52 | PRE-09361.317 | LUG WHA 13296.90010289 | Lateral Hardening-Fuse-90010289 | CKT: 13296 - 90010289 | 2310746 | LUG WHA 13296.90010289 OH | 2310751 | LUG WHA 13296.90010289 UG | 13296 | JAN PHYL | WHA | 1.3356 | 81 | 82 | 2021-06-01 | 2021-09-01 | 2021-12-01
Fishel | 2021 | 2021 | PRE-09361.318 | LUG WHA 13313.10684581 | Lateral Hardening-Fuse-10684581 | CKT: 13313 - 10684581 | 2310752 | LUG WHA 13313.10684581 OH | 2310754 | LUG WHA 13313.10684581 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD53 | PRE-09361.318 | LUG WHA 13313.10684581 | Lateral Hardening-Fuse-10684581 | CKT: 13313 - 10684581 | 2310752 | LUG WHA 13313.10684581 OH | 2310754 | LUG WHA 13313.10684581 UG | 13313 | EAST WINTER HAVEN | WHA | 0.24015 | 23 | 38 | 2021-07-01 | 2021-09-01 | 2021-12-01 | previously listed incorrectly as Fuse 92097460
Fishel | 2021 | 2021 | PRE-09361.319 | LUG WHA 13118.10535999 | Lateral Hardening-Fuse-10535999 | CKT: 13118 - 10535999 | 2310443 | LUG WHA 13118.10535999 OH | 2310452 | LUG WHA 13118.10535999 UG | LUG C065 | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD54 | PRE-09361.319 | LUG WHA 13118.10535999 | Lateral Hardening-Fuse-10535999 | CKT: 13118 - 10535999 | 2310443 | LUG WHA 13118.10535999 OH | 2310452 | LUG WHA 13118.10535999 UG | 13118 | LAKE ALFRED | WHA | 0.35492 | 26 | 101 | 2021-07-01 | 2021-10-01 | 2021-12-01 | Combined with PRE-09361.310 (FID 92659353)
Fishel | 2021 | 2021 | PRE-09361.320 | LUG WHA 13699.60165416 | Lateral Hardening-Fuse-60165416 | CKT: 13699 - 60165416 | 2310518 | LUG WHA 13699.60165416 OH | 2310519 | LUG WHA 13699.60165416 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD55 | PRE-09361.320 | LUG WHA 13699.60165416 | Lateral Hardening-Fuse-60165416 | CKT: 13699 - 60165416 | 2310518 | LUG WHA 13699.60165416 OH | 2310519 | LUG WHA 13699.60165416 UG | 13699 | BERKLEY ROAD | WHA | 0.35795 | 18 | 10 | 2021-07-01 | 2021-10-01 | 2021-12-01
Fishel | 2021 | 2021 | PRE-09361.321 | LUG WHA 13916.91386005 | Lateral Hardening-Fuse-91386005 | CKT: 13916 - 91386005 | 2310757 | LUG WHA 13916.91386005 OH | 2310762 | LUG WHA 13916.91386005 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD56 | PRE-09361.321 | LUG WHA 13916.91386005 | Lateral Hardening-Fuse-91386005 | CKT: 13916 - 91386005 | 2310757 | LUG WHA 13916.91386005 OH | 2310762 | LUG WHA 13916.91386005 UG | 13916 | LAKE RUBY | WHA | 0.52822 | 36 | 199 | 2021-07-01 | 2021-10-01 | 2021-12-01
Fishel | 2021 | 2021 | PRE-09361.322 | LUG WHA 13314.10567076 | Lateral Hardening-Fuse-10567076 | CKT: 13314 - 10567076 | 2310764 | LUG WHA 13314.10567076 OH | 2310765 | LUG WHA 13314.10567076 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD57 | PRE-09361.322 | LUG WHA 13314.10567076 | Lateral Hardening-Fuse-10567076 | CKT: 13314 - 10567076 | 2310764 | LUG WHA 13314.10567076 OH | 2310765 | LUG WHA 13314.10567076 UG | 13314 | EAST WINTER HAVEN | WHA | 0.42443 | 32 | 89 | 2021-07-01 | 2022 | 2022
Fishel | 2021 | 2021 | PRE-09361.323 | LUG WHA 13296.10562361 | Lateral Hardening-Fuse-10562361 | CKT: 13296 - 10562361 | 2310767 | LUG WHA 13296.10562361 OH | 2310770 | LUG WHA 13296.10562361 UG | LUG CO73 | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD58 | PRE-09361.323 | LUG WHA 13296.10562361 | Lateral Hardening-Fuse-10562361 | CKT: 13296 - 10562361 | 2310767 | LUG WHA 13296.10562361 OH | 2310770 | LUG WHA 13296.10562361 UG | 13296 | JAN PHYL | WHA | 0.225 | 19 | 37 | 2021-07-01 | 2022 | 2022 | Combined with PRE-09361.304 (FID 10562356)
Fishel | 2021 | 2021 | PRE-09361.324 | LUG WHA 13297.10560432 | Lateral Hardening-Fuse-10560432 | CKT: 13297 - 10560432 | 2310484 | LUG WHA 13297.10560432 OH | 2310488 | LUG WHA 13297.10560432 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD59 | PRE-09361.324 | LUG WHA 13297.10560432 | Lateral Hardening-Fuse-10560432 | CKT: 13297 - 10560432 | 2310484 | LUG WHA 13297.10560432 OH | 2310488 | LUG WHA 13297.10560432 UG | 13297 | JAN PHYL | WHA | 0.43068 | 29 | 362 | 2021-08-01 | 2022 | 2022
Fishel | 2021 | 2021 | PRE-09361.325 | LUG WHA 13972.10618037 | Lateral Hardening-Fuse-10618037 | CKT: 13972 - 10618037 | 2310771 | LUG WHA 13972.10618037 OH | 2310776 | LUG WHA 13972.10618037 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD60 | PRE-09361.325 | LUG WHA 13972.10618037 | Lateral Hardening-Fuse-10618037 | CKT: 13972 - 10618037 | 2310771 | LUG WHA 13972.10618037 OH | 2310776 | LUG WHA 13972.10618037 UG | 13972 | LUCERNE PARK | WHA | 0.2517 | 13 | 1 | 2021-08-01 | 2022 | 2022
Fishel | 2021 | 2021 | PRE-09361.329 | LUG PCA 13724.10671319 | Lateral Hardening-Fuse-10671319 | CKT: 13724 - 10671319 | 2310790 | LUG PCA 13724.10671319 OH | 2310795 | LUG PCA 13724.10671319 UG | LUG CO76 | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD61 | PRE-09361.326 | DNU LUG PCA 13724.10671283 | DNU Lateral Hardening-Fuse-10671283 | DNU CKT: 13724 - 10671283 | 2310778 | DNU LUG PCA 13724.10671283 OH | 2310782 | DNU LUG PCA 13724.10671283 UG | 13724 | GALLAGHER ROAD | PCA | 0.38011 | 13 | 77 | 2021-08-01 | 2022 | 2022 | Combined with PRE-09361.329 (FID 10671319)
Fishel | 2021 | 2021 | PRE-09361.327 | LUG PCA 13722.60360851 | Lateral Hardening-Fuse-60360851 | CKT: 13722 - 60360851 | 2310412 | LUG PCA 13722.60360851 OH | 2310417 | LUG PCA 13722.60360851 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD62 | PRE-09361.327 | LUG PCA 13722.60360851 | Lateral Hardening-Fuse-60360851 | CKT: 13722 - 60360851 | 2310412 | LUG PCA 13722.60360851 OH | 2310417 | LUG PCA 13722.60360851 UG | 13722 | GALLAGHER ROAD | PCA | 0.21288 | 17 | 124 | 2021-09-01 | 2022 | 2022
Fishel | 2021 | 2021 | PRE-09361.328 | LUG PCA 13268.91633548 | Lateral Hardening-Fuse-91633548 | CKT: 13268 - 91633548 | 2310784 | LUG PCA 13268.91633548 OH | 2310785 | LUG PCA 13268.91633548 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD63 | PRE-09361.328 | LUG PCA 13268.91633548 | Lateral Hardening-Fuse-91633548 | CKT: 13268 - 91633548 | 2310784 | LUG PCA 13268.91633548 OH | 2310785 | LUG PCA 13268.91633548 UG | 13268 | J.D. PAGE | PCA | 0.8911 | 48 | 216 | 2021-09-01 | 2022 | 2022
Fishel | 2021 | 2021 | PRE-09361.329 | LUG PCA 13724.10671319 | Lateral Hardening-Fuse-10671319 | CKT: 13724 - 10671319 | 2310790 | LUG PCA 13724.10671319 OH | 2310795 | LUG PCA 13724.10671319 UG | LUG CO76 | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD64 | PRE-09361.329 | LUG PCA 13724.10671319 | Lateral Hardening-Fuse-10671319 | CKT: 13724 - 10671319 | 2310790 | LUG PCA 13724.10671319 OH | 2310795 | LUG PCA 13724.10671319 UG | 13724 | GALLAGHER ROAD | PCA | 1.7574 | 83 | 181 | 2021-09-01 | 2022 | 2022 | Combined with PRE-09361.326 (FID 10671283)
Fishel | 2021 | 2021 | PRE-09361.332 | LUG PCA 13243.91351288 | Lateral Hardening-Fuse-91351288 | CKT: 13243 - 91351288 | 2310479 | LUG PCA 13243.91351288 OH | 2310480 | LUG PCA 13243.91351288 UG | LUG CO64 | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD65 | PRE-09361.330 | DNU LUG PCA 13243.10791853 | DNU Lateral Hardening-Fuse-10791853 | DNU CKT: 13243 - 10791853 | 2310471 | DNU LUG PCA 13243.10791853 OH | 2310475 | DNU LUG PCA 13243.10791853 UG | 13243 | WILSON | PCA | 0.42102 | 31 | 99 | 2021-09-01 | 2022 | 2022 | Combined with PRE-09361.332 (FID 91351288)
Fishel | 2021 | 2021 | PRE-09361.331 | LUG PCA 13724.10671334 | Lateral Hardening-Fuse-10671334 | CKT: 13724 - 10671334 | 2310797 | LUG PCA 13724.10671334 OH | 2310799 | LUG PCA 13724.10671334 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD66 | PRE-09361.331 | LUG PCA 13724.10671334 | Lateral Hardening-Fuse-10671334 | CKT: 13724 - 10671334 | 2310797 | LUG PCA 13724.10671334 OH | 2310799 | LUG PCA 13724.10671334 UG | 13724 | GALLAGHER ROAD | PCA | 0.57254 | 31 | 120 | 2021-09-01 | 2022 | 2022
Fishel | 2021 | 2021 | PRE-09361.332 | LUG PCA 13243.91351288 | Lateral Hardening-Fuse-91351288 | CKT: 13243 - 91351288 | 2310479 | LUG PCA 13243.91351288 OH | 2310480 | LUG PCA 13243.91351288 UG | LUG CO64 | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD67 | PRE-09361.332 | LUG PCA 13243.91351288 | Lateral Hardening-Fuse-91351288 | CKT: 13243 - 91351288 | 2310479 | LUG PCA 13243.91351288 OH | 2310480 | LUG PCA 13243.91351288 UG | 13243 | WILSON | PCA | 0.28617 | 18 | 223 | 2021-09-01 | 2022 | 2022 | Combined with PRE-09361.330 (FID 10791853)
Fishel | 2021 | 2021 | PRE-09361.333 | LUG PCA 13655.90431393 | Lateral Hardening-Fuse-90431393 | CKT: 13655 - 90431393 | 2310803 | LUG PCA 13655.90431393 OH | 2310807 | LUG PCA 13655.90431393 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD68 | PRE-09361.333 | LUG PCA 13655.90431393 | Lateral Hardening-Fuse-90431393 | CKT: 13655 - 90431393 | 2310803 | LUG PCA 13655.90431393 OH | 2310807 | LUG PCA 13655.90431393 UG | 13655 | HAMPTON | PCA | 1.2312 | 70 | 298 | 2021-09-01 | 2022 | 2022
Fishel | 2021 | 2021 | PRE-09361.334 | LUG PCA 13243.90684154 | Lateral Hardening-Fuse-90684154 | CKT: 13243 - 90684154 | 2310810 | LUG PCA 13243.90684154 OH | 2310812 | LUG PCA 13243.90684154 UG | LUG CO75 | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD69 | PRE-09361.334 | LUG PCA 13243.90684154 | Lateral Hardening-Fuse-90684154 | CKT: 13243 - 90684154 | 2310810 | LUG PCA 13243.90684154 OH | 2310812 | LUG PCA 13243.90684154 UG | 13243 | WILSON | PCA | 0.22841 | 19 | 7 | 2021-09-01 | 2022 | 2022 | Combined with PRE-09361.339 (FID 90586047)
Fishel | 2021 | 2021 | PRE-09361.335 | LUG PCA 13268.10705945 | Lateral Hardening-Fuse-10705945 | CKT: 13268 - 10705945 | 2310816 | LUG PCA 13268.10705945 OH | 2310818 | LUG PCA 13268.10705945 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD70 | PRE-09361.335 | LUG PCA 13268.10705945 | Lateral Hardening-Fuse-10705945 | CKT: 13268 - 10705945 | 2310816 | LUG PCA 13268.10705945 OH | 2310818 | LUG PCA 13268.10705945 UG | 13268 | J.D. PAGE | PCA | 1.4027 | 67 | 76 | 2021-10-01 | 2022 | 2022
Fishel | 2021 | 2021 | PRE-09361.336 | LUG PCA 13724.10671229 | Lateral Hardening-Fuse-10671229 | CKT: 13724 - 10671229 | 2310819 | LUG PCA 13724.10671229 OH | 2310822 | LUG PCA 13724.10671229 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD71 | PRE-09361.336 | LUG PCA 13724.10671229 | Lateral Hardening-Fuse-10671229 | CKT: 13724 - 10671229 | 2310819 | LUG PCA 13724.10671229 OH | 2310822 | LUG PCA 13724.10671229 UG | 13724 | GALLAGHER ROAD | PCA | 0.29678 | 16 | 9 | 2021-12-01 | 2022 | 2022
Fishel | 2021 | 2021 | PRE-09361.337 | LUG PCA 13268.92962459 | Lateral Hardening-Fuse-92962459 | CKT: 13268 - 92962459 | 2310824 | LUG PCA 13268.92962459 OH | 2310826 | LUG PCA 13268.92962459 UG |  | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD72 | PRE-09361.337 | LUG PCA 13268.92962459 | Lateral Hardening-Fuse-92962459 | CKT: 13268 - 92962459 | 2310824 | LUG PCA 13268.92962459 OH | 2310826 | LUG PCA 13268.92962459 UG | 13268 | J.D. PAGE | PCA | 0.43333 | 28 | 48 | 2021-11-01 | 2022 | 2022
Fishel | 2021 | 2021 | PRE-09361.340 | LUG PCA 13724.91049435 | Lateral Hardening-Fuse-91049435 | CKT: 13724 - 91049435 | 2310833 | LUG PCA 13724.91049435 OH | 2310834 | LUG PCA 13724.91049435 UG | LUG CO77 | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD73 | PRE-09361.338 | DNU LUG PCA 13724.93103251 | DNU Lateral Hardening-Fuse-93103251 | DNU CKT: 13724 - 93103251 | 2310827 | DNU LUG PCA 13724.93103251 OH | 2310829 | DNU LUG PCA 13724.93103251 UG | 13724 | GALLAGHER ROAD | PCA | 0.44072 | 29 | 30 | 2021-11-01 | 2022 | 2022 | Combined with PRE-09361.340 (FID 93103251)
Fishel | 2021 | 2021 | PRE-09361.334 | LUG PCA 13243.90684154 | Lateral Hardening-Fuse-90684154 | CKT: 13243 - 90684154 | 2310810 | LUG PCA 13243.90684154 OH | 2310812 | LUG PCA 13243.90684154 UG | LUG CO75 | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD74 | PRE-09361.339 | DNU LUG PCA 13243.90586047 | DNU Lateral Hardening-Fuse-90586047 | DNU CKT: 13243 - 90586047 | 2310831 | DNU LUG PCA 13243.90586047 OH | 2310832 | DNU LUG PCA 13243.90586047 UG | 13243 | WILSON | PCA | 0.27405 | 17 | 21 | 2021-12-01 | 2022 | 2022 | Combined with PRE-09361.334 (FID 90684154)
Fishel | 2021 | 2021 | PRE-09361.340 | LUG PCA 13724.91049435 | Lateral Hardening-Fuse-91049435 | CKT: 13724 - 91049435 | 2310833 | LUG PCA 13724.91049435 OH | 2310834 | LUG PCA 13724.91049435 UG | LUG CO77 | N/A | 4500282909 | 4500291224 | 2021 | LUG - TBD75 | PRE-09361.340 | LUG PCA 13724.91049435 | Lateral Hardening-Fuse-91049435 | CKT: 13724 - 91049435 | 2310833 | LUG PCA 13724.91049435 OH | 2310834 | LUG PCA 13724.91049435 UG | 13724 | GALLAGHER ROAD | PCA | 1.9932 | 103 | 97 | 2021-09-01 | 2022 | 2022 | Combined with PRE-09361.338 (FID 91049435)
Fishel | 2020 | 2020 | PRE-09361.4 | LUG PCA 13146.10629014 | Lateral Hardening-Fuse-10629014 | CKT: 13146 - 10629014 | 2274142 | LUG PCA 13146.10629014 OH | 2274147 | LUG PCA 13146.10629014 UG |  | 4500272910 | N/A | N/A | 2020 | LUG - TBD4 | PRE-09361.4 | LUG PCA 13146.10629014 | Lateral Hardening-Fuse-10629014 | CKT: 13146 - 10629014 | 2274142 | LUG PCA 13146.10629014 OH | 2274147 | LUG PCA 13146.10629014 UG | 13146 | HOPEWELL | PCA | 0.54337 | 30 | 91 | 2020-06-01 | 2021-01-01 | 2021-03-01
Fishel | 2020 | 2020 | PRE-09361.41 | LUG PCA 13462.60458175 | Lateral Hardening-Fuse-60458175 | CKT: 13462 - 60458175 | 2274170 | LUG PCA 13462.60458175 OH | 2274174 | LUG PCA 13462.60458175 UG |  | 4500272910 | N/A | N/A | 2020 | LUG - TBD11 | PRE-09361.41 | LUG PCA 13462.60458175 | Lateral Hardening-Fuse-60458175 | CKT: 13462 - 60458175 | 2274170 | LUG PCA 13462.60458175 OH | 2274174 | LUG PCA 13462.60458175 UG | 13462 | ALEXANDER ROAD | PCA | 0.66004 | 32 | 65 | 2020-09-01 | 2021-01-01 | 2021-03-01
Fishel | 2020 | 2020 | PRE-09361.43 | LUG PCA 13462.60180762 | Lateral Hardening-Fuse-60180762 | CKT: 13462 - 60180762 | 2274177 | LUG PCA 13462.60180762 OH | 2274179 | LUG PCA 13462.60180762 UG |  | 4500272910 | N/A | N/A | 2020 | LUG - TBD13 | PRE-09361.43 | LUG PCA 13462.60180762 | Lateral Hardening-Fuse-60180762 | CKT: 13462 - 60180762 | 2274177 | LUG PCA 13462.60180762 OH | 2274179 | LUG PCA 13462.60180762 UG | 13462 | ALEXANDER ROAD | PCA | 0.13371 | 14 | 88 | 2020-11-01 | 2021-02-01 | 2021-03-01
Fishel | 2020 | 2020 | PRE-09361.44 | LUG PCA 13462.91407512 | Lateral Hardening-Fuse-91407512 | CKT: 13462 - 91407512 | 2274180 | LUG PCA 13462.91407512 OH | 2274183 | LUG PCA 13462.91407512 UG |  | 4500272910 | N/A | N/A | 2020 | LUG - TBD14 | PRE-09361.44 | LUG PCA 13462.91407512 | Lateral Hardening-Fuse-91407512 | CKT: 13462 - 91407512 | 2274180 | LUG PCA 13462.91407512 OH | 2274183 | LUG PCA 13462.91407512 UG | 13462 | ALEXANDER ROAD | PCA | 0.28106 | 24 | 81 | 2020-11-01 | 2021-02-01 | 2021-03-01
Fishel | 2020 | 2020 | PRE-09361.46 | LUG PCA 13120.60015632 | Lateral Hardening-Fuse-60015632 | CKT: 13120 - 60015632 | 2274187 | LUG PCA 13120.60015632 OH | 2274188 | LUG PCA 13120.60015632 UG |  | 4500272910 | N/A | N/A | 2020 | LUG - TBD16 | PRE-09361.46 | LUG PCA 13120.60015632 | Lateral Hardening-Fuse-60015632 | CKT: 13120 - 60015632 | 2274187 | LUG PCA 13120.60015632 OH | 2274188 | LUG PCA 13120.60015632 UG | 13120 | ALEXANDER ROAD | PCA | 0.20303 | 14 | 135 | 2020-12-01 | 2021-04-01 | 2021-06-01
Fishel | 2020 | 2021 | PRE-09361.47 | LUG PCA 13785.92466250 | Lateral Hardening-Fuse-92466250 | CKT: 13785 - 92466250 | 2274189 | LUG PCA 13785.92466250 OH | 2274190 | LUG PCA 13785.92466250 UG | LUG C034 | 4500272910 | N/A | N/A | 2021 | LUG - TBD18 | PRE-09361.47 | DNU LUG PCA 13785.90239166 | DNU Lateral Hardening-Fuse-90239166 | N/A | N/A | N/A | N/A | N/A | 13785 | PINECREST | PCA | 2.5172 | 115 | 182 | 2021-01-01 | 2021-08-01 | 2021-12-01 | Combined with PRE-09361.10 (FID 10676209), PRE-09361.42 (FID 93159006) & PRE-09361.47 (FID 92466250)
Fishel | 2020 | 2020 | PRE-09361.47 | LUG PCA 13785.92466250 | Lateral Hardening-Fuse-92466250 | CKT: 13785 - 92466250 | 2274189 | LUG PCA 13785.92466250 OH | 2274190 | LUG PCA 13785.92466250 UG | LUG C034 | 4500272910 | N/A | N/A | 2020 | LUG - TBD10 | PRE-09361.10 | DNU LUG PCA 13785.10676209 | DNU Lateral Hardening-Fuse-10676209 | DNU CKT: 13785 - 10676209 | 2274167 | DNU LUG PCA 13785.10676209 OH | 2274169 | DNU LUG PCA 13785.10676209 UG | 13785 | PINECREST | PCA | 0.95057 | 54 | 266 | 2020-09-01 | 2021-01-01 | 2021-03-01 | Combined with PRE-09361.42 (FID 93159006), PRE-09361.47 (FID 92466250) & LUG TBD18 (FID 90239166)
Fishel | 2020 | 2020 | PRE-09361.47 | LUG PCA 13785.92466250 | Lateral Hardening-Fuse-92466250 | CKT: 13785 - 92466250 | 2274189 | LUG PCA 13785.92466250 OH | 2274190 | LUG PCA 13785.92466250 UG | LUG C034 | 4500272910 | N/A | N/A | 2020 | LUG - TBD12 | PRE-09361.42 | DNU LUG PCA 14121.93159006 | DNU Lateral Hardening-Fuse-93159006 | DNU CKT: 14121 - 93159006 | 2274175 | DNU LUG PCA 14121.93159006 OH | 2274176 | DNU LUG PCA 14121.93159006 UG | 14121 | FISHHAWK | PCA | 0.56951 | 31 | 74 | 2020-10-01 | 2021-01-01 | 2021-03-01 | Combined with PRE-09361.10 (FID 10676209), PRE-09361.47 (FID 92466250) & LUG TBD18 (FID 90239166)
Fishel | 2020 | 2020 | PRE-09361.47 | LUG PCA 13785.92466250 | Lateral Hardening-Fuse-92466250 | CKT: 13785 - 92466250 | 2274189 | LUG PCA 13785.92466250 OH | 2274190 | LUG PCA 13785.92466250 UG | LUG C034 | 4500272910 | N/A | N/A | 2020 | LUG - TBD17 | PRE-09361.47 | LUG PCA 13785.92466250 | Lateral Hardening-Fuse-92466250 | CKT: 13785 - 92466250 | 2274189 | LUG PCA 13785.92466250 OH | 2274190 | LUG PCA 13785.92466250 UG | 13785 | PINECREST | PCA | 0.72008 | 31 | 72 | 2020-10-01 | 2021-04-01 | 2021-06-01 | Combined with PRE-09361.10 (FID 10676209), PRE-09361.42 (FID 93159006) & LUG TBD18 (FID 90239166)
Fishel | 2020 | 2020 | PRE-09361.5 | LUG WHA 13972.92421291 | Lateral Hardening-Fuse-92421291 | CKT: 13972 - 92421291 | 2274151 | LUG WHA 13972.92421291 OH | 2274626 | LUG WHA 13972.92421291 UG |  | 4500272910 | N/A | N/A | 2020 | LUG - TBD5 | PRE-09361.5 | LUG WHA 13972.92421291 | Lateral Hardening-Fuse-92421291 | CKT: 13972 - 92421291 | 2274151 | LUG WHA 13972.92421291 OH | 2274626 | LUG WHA 13972.92421291 UG | 13972 | LUCERNE PARK | WHA | 0.43693 | 23 | 379 | 2020-07-01 | 2021-01-01 | 2021-03-01
Fishel | 2020 | 2020 | PRE-09361.6 | LUG WHA 13312.60182741 | Lateral Hardening-Fuse-60182741 | CKT: 13312 - 60182741 | 2274153 | LUG WHA 13312.60182741 OH | 2274156 | LUG WHA 13312.60182741 UG |  | 4500272910 | N/A | N/A | 2020 | LUG - TBD6 | PRE-09361.6 | LUG WHA 13312.60182741 | Lateral Hardening-Fuse-60182741 | CKT: 13312 - 60182741 | 2274153 | LUG WHA 13312.60182741 OH | 2274156 | LUG WHA 13312.60182741 UG | 13312 | EAST WINTER HAVEN | WHA | 0.1483 | 15 | 52 | 2020-07-01 | 2021-01-01 | 2021-03-01
Fishel | 2020 | 2020 | PRE-09361.7 | LUG WHA 13972.90241880 | Lateral Hardening-Fuse-90241880 | CKT: 13972 - 90241880 | 2274158 | LUG WHA 13972.90241880 OH | 2274159 | LUG WHA 13972.90241880 UG |  | 4500272910 | N/A | N/A | 2020 | LUG - TBD7 | PRE-09361.7 | LUG WHA 13972.90241880 | Lateral Hardening-Fuse-90241880 | CKT: 13972 - 90241880 | 2274158 | LUG WHA 13972.90241880 OH | 2274159 | LUG WHA 13972.90241880 UG | 13972 | LUCERNE PARK | WHA | 0.90379 | 49 | 130 | 2020-08-01 | 2021-01-01 | 2021-03-01
Fishel | 2020 | 2020 | PRE-09361.8 | LUG PCA 13961.92820848 | Lateral Hardening-Fuse-92820848 | CKT: 13961 - 92820848 | 2274161 | LUG PCA 13961.92820848 OH | 2274162 | LUG PCA 13961.92820848 UG |  | 4500272910 | N/A | N/A | 2020 | LUG - TBD8 | PRE-09361.8 | LUG PCA 13961.92820848 | Lateral Hardening-Fuse-92820848 | CKT: 13961 - 92820848 | 2274161 | LUG PCA 13961.92820848 OH | 2274162 | LUG PCA 13961.92820848 UG | 13961 | TERRACE | PCA | 0.49451 | 26 | 509 | 2020-09-01 | 2021-01-01 | 2021-03-01
Fishel | 2020 | 2020 | PRE-09361.9 | LUG PCA 13961.60193482 | Lateral Hardening-Fuse-60193482 | CKT: 13961 - 60193482 | 2274163 | LUG PCA 13961.60193482 OH | 2274166 | LUG PCA 13961.60193482 UG |  | 4500272910 | N/A | N/A | 2020 | LUG - TBD9 | PRE-09361.9 | LUG PCA 13961.60193482 | Lateral Hardening-Fuse-60193482 | CKT: 13961 - 60193482 | 2274163 | LUG PCA 13961.60193482 OH | 2274166 | LUG PCA 13961.60193482 UG | 13961 | TERRACE | PCA | 0.4822 | 35 | 118 | 2020-09-01 | 2021-01-01 | 2021-03-01
Leidos | 2020 | 2020 | PRE-09361.101 | LUG ESA 13230.10471354 | Lateral Hardening-Fuse-10471354 | CKT: 13230 - 10471354 | 2290383 | LUG ESA 13230.10471354 OH | 2290386 | LUG ESA 13230.10471354 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD336 | PRE-09361.101 | LUG ESA 13230.10471354 | Lateral Hardening-Fuse-10471354 | CKT: 13230 - 10471354 | 2290383 | LUG ESA 13230.10471354 OH | 2290386 | LUG ESA 13230.10471354 UG | 13230 | BRANDON | ESA | 0.44242 | 38 | 49 | 2020-07-01 | 2021-01-01 | 2021-04-01
Leidos | 2020 | 2020 | PRE-09361.102 | LUG ESA 13502.92679861 | Lateral Hardening-Fuse-92679861 | CKT: 13502 - 92679861 | 2290442 | LUG ESA 13502.92679861 OH | 2290446 | LUG ESA 13502.92679861 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD337 | PRE-09361.102 | LUG ESA 13502.92679861 | Lateral Hardening-Fuse-92679861 | CKT: 13502 - 92679861 | 2290442 | LUG ESA 13502.92679861 OH | 2290446 | LUG ESA 13502.92679861 UG | 13502 | STATE ROAD 574 | ESA | 0.17614 | 16 | 50 | 2020-07-01 | 2021-01-01 | 2021-03-01
Leidos | 2020 | 2020 | PRE-09361.103 | LUG ESA 13796.10842826 | Lateral Hardening-Fuse-10842826 | CKT: 13796 - 10842826 | 2290447 | LUG ESA 13796.10842826 OH | 2290448 | LUG ESA 13796.10842826 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD338 | PRE-09361.103 | LUG ESA 13796.10842826 | Lateral Hardening-Fuse-10842826 | CKT: 13796 - 10842826 | 2290447 | LUG ESA 13796.10842826 OH | 2290448 | LUG ESA 13796.10842826 UG | 13796 | SAINT CLOUD | ESA | 0.15189 | 13 | 353 | 2020-07-01 | 2021-01-01 | 2021-03-01
Leidos | 2020 | 2020 | PRE-09361.105 | LUG ESA 13509.10501132 | Lateral Hardening-Fuse-10501132 | CKT: 13509 - 10501132 | 2290461 | LUG ESA 13509.10501132 OH | 2290465 | LUG ESA 13509.10501132 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD340 | PRE-09361.105 | LUG ESA 13509.10501132 | Lateral Hardening-Fuse-10501132 | CKT: 13509 - 10501132 | 2290461 | LUG ESA 13509.10501132 OH | 2290465 | LUG ESA 13509.10501132 UG | 13509 | STATE ROAD 574 | ESA | 0.10814 | 6 | 7 | 2020-08-01 | 2021-01-01 | 2021-03-01
Leidos | 2020 | 2020 | PRE-09361.106 | LUG ESA 13433.10466911 | Lateral Hardening-Fuse-10466911 | CKT: 13433 - 10466911 | 2290485 | LUG ESA 13433.10466911 OH | 2290488 | LUG ESA 13433.10466911 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD341 | PRE-09361.106 | LUG ESA 13433.10466911 | Lateral Hardening-Fuse-10466911 | CKT: 13433 - 10466911 | 2290485 | LUG ESA 13433.10466911 OH | 2290488 | LUG ESA 13433.10466911 UG | 13433 | TWELFTH AVENUE | ESA | 0.70568 | 47 | 159 | 2020-08-01 | 2021-01-01 | 2021-05-01
Leidos | 2020 | 2020 | PRE-09361.134 | LUG ESA 13230.92180224 | Lateral Hardening-Fuse-92180224 | CKT: 13230 - 92180224 | 2277432 | LUG ESA 13230.92180224 OH | 2277435 | LUG ESA 13230.92180224 UG | LUG C061/72 | 4500271952 | N/A | N/A | 2020 | LUG - TBD342 | PRE-09361.107 | DNU LUG ESA 13230.92208546 | DNU Lateral Hardening-Fuse-92208546 | DNU CKT: 13230 - 92208546 | 2290489 | DNU LUG ESA 13230.92208546 OH | 2290490 | DNU LUG ESA 13230.92208546 UG | 13230 | BRANDON | ESA | 0.17462 | 16 | 32 | 2020-08-01 | 2021-01-01 | 2021-03-01 | Combined with PRE-09361.117 (FID 93279980) and PRE-09361.134 (FID 92180224)
Leidos | 2020 | 2020 | PRE-09361.108 | LUG ESA 13171.93104605 | Lateral Hardening-Fuse-93104605 | CKT: 13171 - 93104605 | 2290491 | LUG ESA 13171.93104605 OH | 2290493 | LUG ESA 13171.93104605 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD343 | PRE-09361.108 | LUG ESA 13171.93104605 | Lateral Hardening-Fuse-93104605 | CKT: 13171 - 93104605 | 2290491 | LUG ESA 13171.93104605 OH | 2290493 | LUG ESA 13171.93104605 UG | 13171 | MADISON | ESA | 0.36345 | 21 | 48 | 2020-08-01 | 2021-01-01 | 2021-04-01
Leidos | 2020 | 2020 | PRE-09361.109 | LUG ESA 13509.90504849 | Lateral Hardening-Fuse-90504849 | CKT: 13509 - 90504849 | 2290494 | LUG ESA 13509.90504849 OH | 2290496 | LUG ESA 13509.90504849 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD344 | PRE-09361.109 | LUG ESA 13509.90504849 | Lateral Hardening-Fuse-90504849 | CKT: 13509 - 90504849 | 2290494 | LUG ESA 13509.90504849 OH | 2290496 | LUG ESA 13509.90504849 UG | 13509 | STATE ROAD 574 | ESA | 0.95928 | 56 | 675 | 2020-08-01 | 2021-01-01 | 2021-07-01
Leidos | 2020 | 2020 | PRE-09361.11 | LUG ESA 13174.60588225 | Lateral Hardening-Fuse-60588225 | CKT: 13174 - 60588225 | 2271218 | LUG ESA 13174.60588225 OH | 2271221 | LUG ESA 13174.60588225 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD326 | PRE-09361.11 | LUG ESA 13174.60588225 | Lateral Hardening-Fuse-60588225 | CKT: 13174 - 60588225 | 2271218 | LUG ESA 13174.60588225 OH | 2271221 | LUG ESA 13174.60588225 UG | 13174 | MADISON | ESA | 0.29091 | 15 | 374 | 2020-06-01 | 2020-12-01 | 2020-12-01
Leidos | 2020 | 2020 | PRE-09361.110 | LUG ESA 13502.92573944 | Lateral Hardening-Fuse-92573944 | CKT: 13502 - 92573944 | 2290497 | LUG ESA 13502.92573944 OH | 2290498 | LUG ESA 13502.92573944 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD345 | PRE-09361.110 | LUG ESA 13502.92573944 | Lateral Hardening-Fuse-92573944 | CKT: 13502 - 92573944 | 2290497 | LUG ESA 13502.92573944 OH | 2290498 | LUG ESA 13502.92573944 UG | 13502 | STATE ROAD 574 | ESA | 0.61894 | 40 | 514 | 2020-08-01 | 2021-04-01 | 2021-08-01
Leidos | 2020 | 2020 | PRE-09361.111 | LUG ESA 13799.60395568 | Lateral Hardening-Fuse-60395568 | CKT: 13799 - 60395568 | 2290520 | LUG ESA 13799.60395568 OH | 2290524 | LUG ESA 13799.60395568 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD346 | PRE-09361.111 | LUG ESA 13799.60395568 | Lateral Hardening-Fuse-60395568 | CKT: 13799 - 60395568 | 2290520 | LUG ESA 13799.60395568 OH | 2290524 | LUG ESA 13799.60395568 UG | 13799 | SAINT CLOUD | ESA | 0.45739 | 45 | 260 | 2020-08-01 | 2021-04-01 | 2021-07-01
Leidos | 2020 | 2020 | PRE-09361.112 | LUG ESA 13226.10462583 | Lateral Hardening-Fuse-10462583 | CKT: 13226 - 10462583 | 2290525 | LUG ESA 13226.10462583 OH | 2290526 | LUG ESA 13226.10462583 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD347 | PRE-09361.112 | LUG ESA 13226.10462583 | Lateral Hardening-Fuse-10462583 | CKT: 13226 - 10462583 | 2290525 | LUG ESA 13226.10462583 OH | 2290526 | LUG ESA 13226.10462583 UG | 13226 | BRANDON | ESA | 0.12178 | 19 | 190 | 2020-08-01 | 2021-04-01 | 2021-06-01
Leidos | 2020 | 2020 | PRE-09361.113 | LUG ESA 14116.60140011 | Lateral Hardening-Fuse-60140011 | CKT: 14116 - 60140011 | 2290527 | LUG ESA 14116.60140011 OH | 2290529 | LUG ESA 14116.60140011 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD348 | PRE-09361.113 | LUG ESA 14116.60140011 | Lateral Hardening-Fuse-60140011 | CKT: 14116 - 60140011 | 2290527 | LUG ESA 14116.60140011 OH | 2290529 | LUG ESA 14116.60140011 UG | 14116 | LAKEWOOD | ESA | 0.32595 | 29 | 50 | 2020-09-01 | 2021-04-01 | 2021-06-01
Leidos | 2020 | 2020 | PRE-09361.114 | LUG ESA 13797.93188519 | Lateral Hardening-Fuse-93188519 | CKT: 13797 - 93188519 | 2290531 | LUG ESA 13797.93188519 OH | 2290532 | LUG ESA 13797.93188519 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD349 | PRE-09361.114 | LUG ESA 13797.93188519 | Lateral Hardening-Fuse-93188519 | CKT: 13797 - 93188519 | 2290531 | LUG ESA 13797.93188519 OH | 2290532 | LUG ESA 13797.93188519 UG | 13797 | SAINT CLOUD | ESA | 0.65966 | 50 | 152 | 2020-09-01 | 2021-04-01 | 2021-10-01
Leidos | 2020 | 2020 | PRE-09361.115 | LUG ESA 13226.92664597 | Lateral Hardening-Fuse-92664597 | CKT: 13226 - 92664597 | 2290534 | LUG ESA 13226.92664597 OH | 2290535 | LUG ESA 13226.92664597 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD350 | PRE-09361.115 | LUG ESA 13226.92664597 | Lateral Hardening-Fuse-92664597 | CKT: 13226 - 92664597 | 2290534 | LUG ESA 13226.92664597 OH | 2290535 | LUG ESA 13226.92664597 UG | 13226 | BRANDON | ESA | 0.30947 | 16 | 348 | 2020-09-01 | 2021-05-01 | 2021-07-01
Leidos | 2020 | 2020 | PRE-09361.116 | LUG ESA 13796.92728705 | Lateral Hardening-Fuse-92728705 | CKT: 13796 - 92728705 | 2290536 | LUG ESA 13796.92728705 OH | 2290537 | LUG ESA 13796.92728705 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD351 | PRE-09361.116 | LUG ESA 13796.92728705 | Lateral Hardening-Fuse-92728705 | CKT: 13796 - 92728705 | 2290536 | LUG ESA 13796.92728705 OH | 2290537 | LUG ESA 13796.92728705 UG | 13796 | SAINT CLOUD | ESA | 0.44981 | 34 | 318 | 2020-09-01 | 2021-05-01 | 2021-08-01
Leidos | 2020 | 2020 | PRE-09361.119 | LUG ESA 13796.92884623 | Lateral Hardening-Fuse-92884623 | CKT: 13796 - 92884623 | 2277391 | LUG ESA 13796.92884623 OH | 2277392 | LUG ESA 13796.92884623 UG | LUG C007 | 4500271952 | N/A | N/A | 2020 | LUG - TBD354 | PRE-09361.119 | LUG ESA 13796.92884623 | Lateral Hardening-Fuse-92884623 | CKT: 13796 - 92884623 | 2277391 | LUG ESA 13796.92884623 OH | 2277392 | LUG ESA 13796.92884623 UG | 13796 | SAINT CLOUD | ESA | 1.2991 | 54 | 52 | 2020-10-01 | 2021-06-01 | 2021-12-01 | Combined with LUG-TBD440 (FID 92884644)
Leidos | 2020 | 2021 | PRE-09361.119 | LUG ESA 13796.92884623 | Lateral Hardening-Fuse-92884623 | CKT: 13796 - 92884623 | 2277391 | LUG ESA 13796.92884623 OH | 2277392 | LUG ESA 13796.92884623 UG | LUG C007 | 4500271952 | N/A | N/A | 2021 | LUG - TBD440 | PRE-09361.119 | DNU LUG ESA 13796.92884644 | DNU Lateral Hardening-Fuse-92884644 | N/A | N/A | N/A | N/A | N/A | 13796 | SAINT CLOUD | ESA | 0.28542 | 16 | 16 | 2021-09-01 | 2022 | 2022 | Combined with PRE-09361.119 (FID 92884623)
Leidos | 2020 | 2020 | PRE-09361.12 | LUG ESA 13454.90755954 | Lateral Hardening-Fuse-90755954 | CKT: 13454 - 90755954 | 2277333 | LUG ESA 13454.90755954 OH | 2277335 | LUG ESA 13454.90755954 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD327 | PRE-09361.12 | LUG ESA 13454.90755954 | Lateral Hardening-Fuse-90755954 | CKT: 13454 - 90755954 | 2277333 | LUG ESA 13454.90755954 OH | 2277335 | LUG ESA 13454.90755954 UG | 13454 | LAKEWOOD | ESA | 0.29564 | 23 | 292 | 2020-06-01 | 2020-11-01 | 2020-12-01
Leidos | 2020 | 2020 | PRE-09361.15 | LUG ESA 13509.60287236 | Lateral Hardening-Fuse-60287236 | CKT: 13509 - 60287236 | 2277364 | LUG ESA 13509.60287236 OH | 2277368 | LUG ESA 13509.60287236 UG | LUG C067 | 4500271952 | N/A | N/A | 2020 | LUG - TBD355 | PRE-09361.120 | DNU LUG ESA 13502.92577310 | DNU Lateral Hardening-Fuse-92577310 | DNU CKT: 13502 - 92577310 | 2277393 | DNU LUG ESA 13502.92577310 OH | 2277394 | DNU LUG ESA 13502.92577310 UG | 13502 | STATE ROAD 574 | ESA | 0.16458 | 12 | 268 | 2020-11-01 | 2021-05-01 | 2021-07-01 | Combined with PRE-09361.15 (FID 60287236)
Leidos | 2020 | 2020 | PRE-09361.121 | LUG ESA 13225.60139973 | Lateral Hardening-Fuse-60139973 | CKT: 13225 - 60139973 | 2277396 | LUG ESA 13225.60139973 OH | 2277398 | LUG ESA 13225.60139973 UG | LUG C024 | 4500271952 | N/A | N/A | 2020 | LUG - TBD356 | PRE-09361.121 | LUG ESA 13225.60139973 | Lateral Hardening-Fuse-60139973 | CKT: 13225 - 60139973 | 2277396 | LUG ESA 13225.60139973 OH | 2277398 | LUG ESA 13225.60139973 UG | 13225 | BRANDON | ESA | 0.80549 | 54 | 41 | 2020-10-01 | 2021-05-01 | 2021-12-01 | Combined with LUG-TBD383 (FID 92750192)
Leidos | 2020 | 2021 | PRE-09361.121 | LUG ESA 13225.60139973 | Lateral Hardening-Fuse-60139973 | CKT: 13225 - 60139973 | 2277396 | LUG ESA 13225.60139973 OH | 2277398 | LUG ESA 13225.60139973 UG | LUG C024 | 4500271952 | N/A | N/A | 2021 | LUG - TBD383 | PRE-09361.121 | DNU LUG ESA 13225.92750192 | DNU Lateral Hardening-Fuse-92750192 | N/A | N/A | N/A | N/A | N/A | 13225 | BRANDON | ESA | 0.09375 | 9 | 6 | 2021-01-01 | 2022 | 2022 | Combined with PRE-09361.121 (FID 60139973)
Leidos | 2020 | 2020 | PRE-09361.122 | LUG ESA 13796.10842823 | Lateral Hardening-Fuse-10842823 | CKT: 13796 - 10842823 | 2277399 | LUG ESA 13796.10842823 OH | 2277400 | LUG ESA 13796.10842823 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD357 | PRE-09361.122 | LUG ESA 13796.10842823 | Lateral Hardening-Fuse-10842823 | CKT: 13796 - 10842823 | 2277399 | LUG ESA 13796.10842823 OH | 2277400 | LUG ESA 13796.10842823 UG | 13796 | SAINT CLOUD | ESA | 0.44811 | 34 | 21 | 2020-10-01 | 2021-09-01 | 2021-12-01
Leidos | 2020 | 2020 | PRE-09361.123 | LUG ESA 13226.92670950 | Lateral Hardening-Fuse-92670950 | CKT: 13226 - 92670950 | 2277406 | LUG ESA 13226.92670950 OH | 2277407 | LUG ESA 13226.92670950 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD358 | PRE-09361.123 | LUG ESA 13226.92670950 | Lateral Hardening-Fuse-92670950 | CKT: 13226 - 92670950 | 2277406 | LUG ESA 13226.92670950 OH | 2277407 | LUG ESA 13226.92670950 UG | 13226 | BRANDON | ESA | 0.2017 | 23 | 37 | 2020-11-01 | 2021-07-01 | 2021-09-01
Leidos | 2020 | 2020 | PRE-09361.124 | LUG ESA 13226.92665539 | Lateral Hardening-Fuse-92665539 | CKT: 13226 - 92665539 | 2277408 | LUG ESA 13226.92665539 OH | 2277409 | LUG ESA 13226.92665539 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD359 | PRE-09361.124 | LUG ESA 13226.92665539 | Lateral Hardening-Fuse-92665539 | CKT: 13226 - 92665539 | 2277408 | LUG ESA 13226.92665539 OH | 2277409 | LUG ESA 13226.92665539 UG | 13226 | BRANDON | ESA | 0.087879 | 5 | 13 | 2020-12-01 | 2021-09-01 | 2021-10-01
Leidos | 2020 | 2020 | PRE-09361.125 | LUG ESA 13883.91179506 | Lateral Hardening-Fuse-91179506 | CKT: 13883 - 91179506 | 2277410 | LUG ESA 13883.91179506 OH | 2277411 | LUG ESA 13883.91179506 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD360 | PRE-09361.125 | LUG ESA 13883.91179506 | Lateral Hardening-Fuse-91179506 | CKT: 13883 - 91179506 | 2277410 | LUG ESA 13883.91179506 OH | 2277411 | LUG ESA 13883.91179506 UG | 13883 | PROVIDENCE ROAD | ESA | 0.075 | 6 | 151 | 2020-12-01 | 2021-09-01 | 2021-10-01
Leidos | 2020 | 2020 | PRE-09361.126 | LUG ESA 13509.91772133 | Lateral Hardening-Fuse-91772133 | CKT: 13509 - 91772133 | 2277412 | LUG ESA 13509.91772133 OH | 2277413 | LUG ESA 13509.91772133 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD361 | PRE-09361.126 | LUG ESA 13509.91772133 | Lateral Hardening-Fuse-91772133 | CKT: 13509 - 91772133 | 2277412 | LUG ESA 13509.91772133 OH | 2277413 | LUG ESA 13509.91772133 UG | 13509 | STATE ROAD 574 | ESA | 0.051705 | 8 | 22 | 2020-12-01 | 2021-09-01 | 2021-10-01
Leidos | 2020 | 2020 | PRE-09361.127 | LUG ESA 13509.10501150 | Lateral Hardening-Fuse-10501150 | CKT: 13509 - 10501150 | 2277415 | LUG ESA 13509.10501150 OH | 2277416 | LUG ESA 13509.10501150 UG | LUG C023 | 4500271952 | N/A | N/A | 2020 | LUG - TBD362 | PRE-09361.127 | LUG ESA 13509.10501150 | Lateral Hardening-Fuse-10501150 | CKT: 13509 - 10501150 | 2277415 | LUG ESA 13509.10501150 OH | 2277416 | LUG ESA 13509.10501150 UG | 13509 | STATE ROAD 574 | ESA | 0.50871 | 33 | 37 | 2020-10-01 | 2021-08-01 | 2021-11-01 | Combined with LUG-TBD446 (FID 10501133)
Leidos | 2020 | 2021 | PRE-09361.127 | LUG ESA 13509.10501150 | Lateral Hardening-Fuse-10501150 | CKT: 13509 - 10501150 | 2277415 | LUG ESA 13509.10501150 OH | 2277416 | LUG ESA 13509.10501150 UG | LUG C023 | 4500271952 | N/A | N/A | 2021 | LUG - TBD446 | PRE-09361.127 | DNU LUG ESA 13509.10501133 | DNU Lateral Hardening-Fuse-10501133 | N/A | N/A | N/A | N/A | N/A | 13509 | STATE ROAD 574 | ESA | 0.27481 | 20 | 27 | 2021-09-01 | 2022 | 2022 | Combined with PRE-09361.127 (FID 10501150)
Leidos | 2020 | 2020 | PRE-09361.128 | LUG ESA 13454.90429155 | Lateral Hardening-Fuse-90429155 | CKT: 13454 - 90429155 | 2277417 | LUG ESA 13454.90429155 OH | 2277418 | LUG ESA 13454.90429155 UG | LUG C005 | 4500271952 | N/A | N/A | 2020 | LUG - TBD339 | PRE-09361.104 | DNU LUG ESA 13454.60140423 | DNU Lateral Hardening-Fuse-60140423 | DNU CKT: 13454 - 60140423 | 2290450 | DNU LUG ESA 13454.60140423 OH | 2290459 | DNU LUG ESA 13454.60140423 UG | 13454 | LAKEWOOD | ESA | 0.51231 | 33 | 290 | 2020-07-01 | 2021-01-01 | 2021-04-01 | Combined with PRE-09361.128 (FID 90429155) PRE-09361.130 (FID 10472634)
Leidos | 2020 | 2020 | PRE-09361.128 | LUG ESA 13454.90429155 | Lateral Hardening-Fuse-90429155 | CKT: 13454 - 90429155 | 2277417 | LUG ESA 13454.90429155 OH | 2277418 | LUG ESA 13454.90429155 UG | LUG C005 | 4500271952 | N/A | N/A | 2020 | LUG - TBD363 | PRE-09361.128 | LUG ESA 13454.90429155 | Lateral Hardening-Fuse-90429155 | CKT: 13454 - 90429155 | 2277417 | LUG ESA 13454.90429155 OH | 2277418 | LUG ESA 13454.90429155 UG | 13454 | LAKEWOOD | ESA | 0.63826 | 34 | 148 | 2020-10-01 | 2021-08-01 | 2021-12-01 | Combined with PRE-09361.104 (FID 60140423) & PRE-09361.130 (FID 10472634)
Leidos | 2020 | 2020 | PRE-09361.128 | LUG ESA 13454.90429155 | Lateral Hardening-Fuse-90429155 | CKT: 13454 - 90429155 | 2277417 | LUG ESA 13454.90429155 OH | 2277418 | LUG ESA 13454.90429155 UG | LUG C005 | 4500271952 | N/A | N/A | 2020 | LUG - TBD365 | PRE-09361.130 | DNU LUG ESA 13454.10472634 | DNU Lateral Hardening-Fuse-10472634 | DNU CKT: 13454 - 10472634 | 2277422 | DNU LUG ESA 13454.10472634 OH | 2277423 | DNU LUG ESA 13454.10472634 UG | 13454 | LAKEWOOD | ESA | 0.38409 | 27 | 35 | 2020-11-01 | 2021-10-01 | 2021-12-01 | Combined with PRE-09361.104 (FID 60140423) & PRE-09361.128 (FID 90429155)
Leidos | 2020 | 2020 | PRE-09361.129 | LUG ESA 13454.90397369 | Lateral Hardening-Fuse-90397369 | CKT: 13454 - 90397369 | 2277419 | LUG ESA 13454.90397369 OH | 2277420 | LUG ESA 13454.90397369 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD364 | PRE-09361.129 | LUG ESA 13454.90397369 | Lateral Hardening-Fuse-90397369 | CKT: 13454 - 90397369 | 2277419 | LUG ESA 13454.90397369 OH | 2277420 | LUG ESA 13454.90397369 UG | 13454 | LAKEWOOD | ESA | 0.49053 | 26 | 19 | 2020-11-01 | 2021-08-01 | 2021-12-01
Leidos | 2020 | 2020 | PRE-09361.17 | LUG ESA 13174.10913196 | Lateral Hardening-Fuse-10913196 | CKT: 13174 - 10913196 | 2277381 | LUG ESA 13174.10913196 OH | 2277382 | LUG ESA 13174.10913196 UG | LUG C066/2/3 | 4500271952 | N/A | N/A | 2020 | LUG - TBD328 | PRE-09361.13 | DNU LUG ESA 13174.60451701 | DNU Lateral Hardening-Fuse-60451701 | DNU CKT: 13174 - 60451701 | 2277343 | DNU LUG ESA 13174.60451701 OH | 2277348 | DNU LUG ESA 13174.60451701 UG | 13174 | MADISON | ESA | 0.2447 | 14 | 301 | 2020-06-01 | 2020-10-01 | 2020-12-01 | Combined with LUG-TBD382 (FID 10913197) as LUG CO03 initially, then combined with PRE-09361.17 (10913196) as LUG C066/2/3
Leidos | 2020 | 2021 | PRE-09361.17 | LUG ESA 13174.10913196 | Lateral Hardening-Fuse-10913196 | CKT: 13174 - 10913196 | 2277381 | LUG ESA 13174.10913196 OH | 2277382 | LUG ESA 13174.10913196 UG | LUG C066/2/3 | 4500271952 | N/A | N/A | 2021 | LUG - TBD382 | PRE-09361.13 | DNU LUG ESA 13174.10913197 | DNU Lateral Hardening-Fuse-10913197 | N/A | N/A | N/A | N/A | N/A | 13174 | MADISON | ESA | 0.077273 | 2 | 301 | 2021-01-01 | 2022 | 2022 | Combined with PRE-09361.13 (FID 60451701) as LUG C003 initially, then combined with PRE-09361.17 (10913196) as LUG C066/2/3
Leidos | 2020 | 2020 | PRE-09361.131 | LUG ESA 13433.93369551 | Lateral Hardening-Fuse-93369551 | CKT: 13433 - 93369551 | 2277424 | LUG ESA 13433.93369551 OH | 2277425 | LUG ESA 13433.93369551 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD366 | PRE-09361.131 | LUG ESA 13433.93369551 | Lateral Hardening-Fuse-93369551 | CKT: 13433 - 93369551 | 2277424 | LUG ESA 13433.93369551 OH | 2277425 | LUG ESA 13433.93369551 UG | 13433 | TWELFTH AVENUE | ESA | 0.60587 | 37 | 5 | 2020-11-01 | 2021-08-01 | 2021-12-01
Leidos | 2020 | 2020 | PRE-09361.132 | LUG ESA 13174.92555763 | Lateral Hardening-Fuse-92555763 | CKT: 13174 - 92555763 | 2277426 | LUG ESA 13174.92555763 OH | 2277427 | LUG ESA 13174.92555763 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD367 | PRE-09361.132 | LUG ESA 13174.92555763 | Lateral Hardening-Fuse-92555763 | CKT: 13174 - 92555763 | 2277426 | LUG ESA 13174.92555763 OH | 2277427 | LUG ESA 13174.92555763 UG | 13174 | MADISON | ESA | 0.026894 | 3 | 138 | 2020-10-01 | 2021-08-01 | 2021-09-01
Leidos | 2020 | 2020 | PRE-09361.133 | LUG ESA 13883.92008787 | Lateral Hardening-Fuse-92008787 | CKT: 13883 - 92008787 | 2277428 | LUG ESA 13883.92008787 OH | 2277429 | LUG ESA 13883.92008787 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD368 | PRE-09361.133 | LUG ESA 13883.92008787 | Lateral Hardening-Fuse-92008787 | CKT: 13883 - 92008787 | 2277428 | LUG ESA 13883.92008787 OH | 2277429 | LUG ESA 13883.92008787 UG | 13883 | PROVIDENCE ROAD | ESA | 0.058333 | 8 | 3 | 2020-10-01 | 2021-11-01 | 2021-12-01
Leidos | 2020 | 2020 | PRE-09361.134 | LUG ESA 13230.92180224 | Lateral Hardening-Fuse-92180224 | CKT: 13230 - 92180224 | 2277432 | LUG ESA 13230.92180224 OH | 2277435 | LUG ESA 13230.92180224 UG | LUG C061/72 | 4500271952 | N/A | N/A | 2020 | LUG - TBD352 | PRE-09361.117 | DNU LUG ESA 13230.93279980 | DNU Lateral Hardening-Fuse-93279980 | DNU CKT: 13230 - 93279980 | 2290539 | DNU LUG ESA 13230.93279980 OH | 2290540 | DNU LUG ESA 13230.93279980 UG | 13230 | BRANDON | ESA | 0.15777 | 15 | 37 | 2020-10-01 | 2021-05-01 | 2021-07-01 | Combined with PRE-09361.134 (FID 92180224) and PRE-09361.107 (FID 92208546); Incorrectly opened as FID 60258173)
Leidos | 2020 | 2020 | PRE-09361.134 | LUG ESA 13230.92180224 | Lateral Hardening-Fuse-92180224 | CKT: 13230 - 92180224 | 2277432 | LUG ESA 13230.92180224 OH | 2277435 | LUG ESA 13230.92180224 UG | LUG C061/72 | 4500271952 | N/A | N/A | 2020 | LUG - TBD369 | PRE-09361.134 | LUG ESA 13230.92180224 | Lateral Hardening-Fuse-92180224 | CKT: 13230 - 92180224 | 2277432 | LUG ESA 13230.92180224 OH | 2277435 | LUG ESA 13230.92180224 UG | 13230 | BRANDON | ESA | 0.27992 | 21 | 58 | 2020-11-01 | 2021-09-01 | 2021-12-01 | Combined with PRE-09361.117 (FID 93279980) and PRE-09361.107 (FID 92208546)
Leidos | 2020 | 2020 | PRE-09361.14 | LUG ESA 13710.92881445 | Lateral Hardening-Fuse-92881445 | CKT: 13710 - 92881445 | 2277357 | LUG ESA 13710.92881445 OH | 2277359 | LUG ESA 13710.92881445 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD329 | PRE-09361.14 | LUG ESA 13710.92881445 | Lateral Hardening-Fuse-92881445 | CKT: 13710 - 92881445 | 2277357 | LUG ESA 13710.92881445 OH | 2277359 | LUG ESA 13710.92881445 UG | 13710 | BUCKHORN | ESA | 0.44867 | 32 | 158 | 2020-06-01 | 2020-11-01 | 2021-03-01
Leidos | 2020 | 2020 | PRE-09361.15 | LUG ESA 13509.60287236 | Lateral Hardening-Fuse-60287236 | CKT: 13509 - 60287236 | 2277364 | LUG ESA 13509.60287236 OH | 2277368 | LUG ESA 13509.60287236 UG | LUG C067 | 4500271952 | N/A | N/A | 2020 | LUG - TBD330 | PRE-09361.15 | LUG ESA 13509.60287236 | Lateral Hardening-Fuse-60287236 | CKT: 13509 - 60287236 | 2277364 | LUG ESA 13509.60287236 OH | 2277368 | LUG ESA 13509.60287236 UG | 13509 | STATE ROAD 574 | ESA | 0.14527 | 14 | 144 | 2020-07-01 | 2021-01-01 | 2021-03-01 | Combined with PRE-09361.120 (FID 92577310)
Leidos | 2020 | 2020 | PRE-09361.16 | LUG SHA 13897.10933151 | Lateral Hardening-Fuse-10933151 | CKT: 13897 - 10933151 | 2277378 | LUG SHA 13897.10933151 OH | 2277380 | LUG SHA 13897.10933151 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD331 | PRE-09361.16 | LUG SHA 13897.10933151 | Lateral Hardening-Fuse-10933151 | CKT: 13897 - 10933151 | 2277378 | LUG SHA 13897.10933151 OH | 2277380 | LUG SHA 13897.10933151 UG | 13897 | FIRST STREET | SHA | 0.78845 | 33 | 64 | 2020-07-01 | 2021-01-01 | 2021-07-01
Leidos | 2020 | 2020 | PRE-09361.17 | LUG ESA 13174.10913196 | Lateral Hardening-Fuse-10913196 | CKT: 13174 - 10913196 | 2277381 | LUG ESA 13174.10913196 OH | 2277382 | LUG ESA 13174.10913196 UG | LUG C066/2/3 | 4500271952 | N/A | N/A | 2020 | LUG - TBD332 | PRE-09361.17 | LUG ESA 13174.10913196 | Lateral Hardening-Fuse-10913196 | CKT: 13174 - 10913196 | 2277381 | LUG ESA 13174.10913196 OH | 2277382 | LUG ESA 13174.10913196 UG | 13174 | MADISON | ESA | 0.21269 | 8 | 241 | 2020-07-01 | 2021-01-01 | 2021-03-01 | Combined with LUG-TBD373 (FID 93310101) as LUG C002 initially, then combined with PRE-09361.13 (10913196) as LUG CO66/2/3
Leidos | 2020 | 2021 | PRE-09361.17 | LUG ESA 13174.10913196 | Lateral Hardening-Fuse-10913196 | CKT: 13174 - 10913196 | 2277381 | LUG ESA 13174.10913196 OH | 2277382 | LUG ESA 13174.10913196 UG | LUG C066/2/3 | 4500271952 | N/A | N/A | 2021 | LUG - TBD373 | PRE-09361.17 | DNU LUG ESA 13174.93310101 | DNU Lateral Hardening-Fuse-93310101 | N/A | N/A | N/A | N/A | N/A | 13174 | MADISON | ESA | 0.50587 | 29 | 2 | 2021-01-01 | 2022 | 2022 | Combined with PRE-09361.17 (FID 10913196) as LUG C002 initially, then combined with PRE-09361.13 (10913196) as LUG C066/2/3
Leidos | 2020 | 2020 | PRE-09361.18 | LUG ESA 13171.90598389 | Lateral Hardening-Fuse-90598389 | CKT: 13171 - 90598389 | 2277383 | LUG ESA 13171.90598389 OH | 2277385 | LUG ESA 13171.90598389 UG | LUG C006 | 4500271952 | N/A | N/A | 2020 | LUG - TBD333 | PRE-09361.18 | LUG ESA 13171.90598389 | Lateral Hardening-Fuse-90598389 | CKT: 13171 - 90598389 | 2277383 | LUG ESA 13171.90598389 OH | 2277385 | LUG ESA 13171.90598389 UG | 13171 | MADISON | ESA | 0.21383 | 11 | 370 | 2020-07-01 | 2021-01-01 | 2021-03-01 | Combined with PRE-09361.118 (FID 90374558) & LUG-TBD376 (FID 10455414)
Leidos | 2020 | 2020 | PRE-09361.18 | LUG ESA 13171.90598389 | Lateral Hardening-Fuse-90598389 | CKT: 13171 - 90598389 | 2277383 | LUG ESA 13171.90598389 OH | 2277385 | LUG ESA 13171.90598389 UG | LUG C006 | 4500271952 | N/A | N/A | 2020 | LUG - TBD353 | PRE-09361.118 | DNU LUG ESA 13171.90374558 | DNU Lateral Hardening-Fuse-90374558 | DNU CKT: 13171 - 90374558 | 2290542 | DNU LUG ESA 13171.90374558 OH | 2290543 | DNU LUG ESA 13171.90374558 UG | 13171 | MADISON | ESA | 0.58144 | 39 | 325 | 2020-10-01 | 2021-05-01 | 2021-08-01 | Combined with PRE-09361.18 (FID 90598389) & LUG-TBD376 (FID 10455414)
Leidos | 2020 | 2021 | PRE-09361.18 | LUG ESA 13171.90598389 | Lateral Hardening-Fuse-90598389 | CKT: 13171 - 90598389 | 2277383 | LUG ESA 13171.90598389 OH | 2277385 | LUG ESA 13171.90598389 UG | LUG C006 | 4500271952 | N/A | N/A | 2021 | LUG - TBD376 | PRE-09361.18 | DNU LUG ESA 13171.10455414 | DNU Lateral Hardening-Fuse-10455414 | N/A | N/A | N/A | N/A | N/A | 13171 | MADISON | ESA | 0.59356 | 40 | 36 | 2021-01-01 | 2022 | 2022 | Combined with PRE-09361.18 (FID 90598389) & PRE-09361.118 (FID 90374558)
Leidos | 2020 | 2020 | PRE-09361.19 | LUG ESA 13211.60044019 | Lateral Hardening-Fuse-60044019 | CKT: 13211 - 60044019 | 2277387 | LUG ESA 13211.60044019 OH | 2277389 | LUG ESA 13211.60044019 UG |  | 4500271952 | N/A | N/A | 2020 | LUG - TBD334 | PRE-09361.19 | LUG ESA 13211.60044019 | Lateral Hardening-Fuse-60044019 | CKT: 13211 - 60044019 | 2277387 | LUG ESA 13211.60044019 OH | 2277389 | LUG ESA 13211.60044019 UG | 13211 | FAIRGROUNDS | ESA | 0.52746 | 43 | 395 | 2020-07-01 | 2021-01-01 | 2021-04-01
Leidos | 2020 | 2020 | PRE-09361.20 | LUG ESA 13231.10868138 | Lateral Hardening-Fuse-10868138 | CKT: 13231 - 10868138 | 2290199 | LUG ESA 13231.10868138 OH | 2290200 | LUG ESA 13231.10868138 UG | LUG C004 | 4500271952 | N/A | N/A | 2020 | LUG - TBD335 | PRE-09361.20 | LUG ESA 13231.10868138 | Lateral Hardening-Fuse-10868138 | CKT: 13231 - 10868138 | 2290199 | LUG ESA 13231.10868138 OH | 2290200 | LUG ESA 13231.10868138 UG | 13231 | BRANDON | ESA | 0.53977 | 34 | 269 | 2020-07-01 | 2021-01-01 | 2021-04-01 | Combined with LUG-TBD381 (FID 10868120)
Leidos | 2020 | 2021 | PRE-09361.20 | LUG ESA 13231.10868138 | Lateral Hardening-Fuse-10868138 | CKT: 13231 - 10868138 | 2290199 | LUG ESA 13231.10868138 OH | 2290200 | LUG ESA 13231.10868138 UG | LUG C004 | 4500271952 | N/A | N/A | 2021 | LUG - TBD381 | PRE-09361.20 | DNU LUG ESA 13231.10868120 | DNU Lateral Hardening-Fuse-10868120 | N/A | N/A | N/A | N/A | N/A | 13231 | BRANDON | ESA | 0.41648 | 29 | 35 | 2021-01-01 | 2022 | 2022 | Combined with PRE-09361.20 (FID 10868138)
Leidos | 2021 | 2021 | PRE-09361.406 | LUG ESA 13230.10471377 | Lateral Hardening-Fuse-10471377 | CKT: 13230 - 10471377 | 2309472 | LUG ESA 13230.10471377 OH | 2309473 | LUG ESA 13230.10471377 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD370 | PRE-09361.406 | LUG ESA 13230.10471377 | Lateral Hardening-Fuse-10471377 | CKT: 13230 - 10471377 | 2309472 | LUG ESA 13230.10471377 OH | 2309473 | LUG ESA 13230.10471377 UG | 13230 | BRANDON | ESA | 0.47973 | 31 | 54 | 2021-01-01 | 2021-10-01 | 2021-12-01
Leidos | 2021 | 2021 | PRE-09361.407 | LUG ESA 13509.60346595 | Lateral Hardening-Fuse-60346595 | CKT: 13509 - 60346595 | 2309657 | LUG ESA 13509.60346595 OH | 2309658 | LUG ESA 13509.60346595 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD371 | PRE-09361.407 | LUG ESA 13509.60346595 | Lateral Hardening-Fuse-60346595 | CKT: 13509 - 60346595 | 2309657 | LUG ESA 13509.60346595 OH | 2309658 | LUG ESA 13509.60346595 UG | 13509 | STATE ROAD 574 | ESA | 0.14754 | 10 | 14 | 2021-01-01 | 2021-10-01 | 2021-12-01
Leidos | 2021 | 2021 | PRE-09361.408 | LUG ESA 13502.10497396 | Lateral Hardening-Fuse-10497396 | CKT: 13502 - 10497396 | 2309691 | LUG ESA 13502.10497396 OH | 2309695 | LUG ESA 13502.10497396 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD372 | PRE-09361.408 | LUG ESA 13502.10497396 | Lateral Hardening-Fuse-10497396 | CKT: 13502 - 10497396 | 2309691 | LUG ESA 13502.10497396 OH | 2309695 | LUG ESA 13502.10497396 UG | 13502 | STATE ROAD 574 | ESA | 0.29545 | 22 | 70 | 2021-01-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.410 | LUG ESA 13796.92356181 | Lateral Hardening-Fuse-92356181 | CKT: 13796 - 92356181 | 2309696 | LUG ESA 13796.92356181 OH | 2309700 | LUG ESA 13796.92356181 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD374 | PRE-09361.410 | LUG ESA 13796.92356181 | Lateral Hardening-Fuse-92356181 | CKT: 13796 - 92356181 | 2309696 | LUG ESA 13796.92356181 OH | 2309700 | LUG ESA 13796.92356181 UG | 13796 | SAINT CLOUD | ESA | 0.26477 | 14 | 6 | 2021-01-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.411 | LUG ESA 13509.92890860 | Lateral Hardening-Fuse-92890860 | CKT: 13509 - 92890860 | 2309701 | LUG ESA 13509.92890860 OH | 2309702 | LUG ESA 13509.92890860 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD375 | PRE-09361.411 | LUG ESA 13509.92890860 | Lateral Hardening-Fuse-92890860 | CKT: 13509 - 92890860 | 2309701 | LUG ESA 13509.92890860 OH | 2309702 | LUG ESA 13509.92890860 UG | 13509 | STATE ROAD 574 | ESA | 0.33485 | 30 | 7 | 2021-01-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.412 | LUG ESA 13230.92496254 | Lateral Hardening-Fuse-92496254 | CKT: 13230 - 92496254 | 2309703 | LUG ESA 13230.92496254 OH | 2309705 | LUG ESA 13230.92496254 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD377 | PRE-09361.412 | LUG ESA 13230.92496254 | Lateral Hardening-Fuse-92496254 | CKT: 13230 - 92496254 | 2309703 | LUG ESA 13230.92496254 OH | 2309705 | LUG ESA 13230.92496254 UG | 13230 | BRANDON | ESA | 0.28977 | 23 | 12 | 2021-01-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.413 | LUG ESA 13509.10501141 | Lateral Hardening-Fuse-10501141 | CKT: 13509 - 10501141 | 2309706 | LUG ESA 13509.10501141 OH | 2309707 | LUG ESA 13509.10501141 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD378 | PRE-09361.413 | LUG ESA 13509.10501141 | Lateral Hardening-Fuse-10501141 | CKT: 13509 - 10501141 | 2309706 | LUG ESA 13509.10501141 OH | 2309707 | LUG ESA 13509.10501141 UG | 13509 | STATE ROAD 574 | ESA | 0.16364 | 15 | 13 | 2021-01-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.414 | LUG ESA 13454.91522987 | Lateral Hardening-Fuse-91522987 | CKT: 13454 - 91522987 | 2309709 | LUG ESA 13454.91522987 OH | 2309710 | LUG ESA 13454.91522987 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD379 | PRE-09361.414 | LUG ESA 13454.91522987 | Lateral Hardening-Fuse-91522987 | CKT: 13454 - 91522987 | 2309709 | LUG ESA 13454.91522987 OH | 2309710 | LUG ESA 13454.91522987 UG | 13454 | LAKEWOOD | ESA | 0.043371 | 9 | 47 | 2021-01-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.415 | LUG ESA 13509.10501110 | Lateral Hardening-Fuse-10501110 | CKT: 13509 - 10501110 | 2309713 | LUG ESA 13509.10501110 OH | 2309715 | LUG ESA 13509.10501110 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD380 | PRE-09361.415 | LUG ESA 13509.10501110 | Lateral Hardening-Fuse-10501110 | CKT: 13509 - 10501110 | 2309713 | LUG ESA 13509.10501110 OH | 2309715 | LUG ESA 13509.10501110 UG | 13509 | STATE ROAD 574 | ESA | 0.089962 | 6 | 3 | 2021-01-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.416 | LUG ESA 13797.93185703 | Lateral Hardening-Fuse-93185703 | CKT: 13797 - 93185703 | 2309716 | LUG ESA 13797.93185703 OH | 2309718 | LUG ESA 13797.93185703 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD384 | PRE-09361.416 | LUG ESA 13797.93185703 | Lateral Hardening-Fuse-93185703 | CKT: 13797 - 93185703 | 2309716 | LUG ESA 13797.93185703 OH | 2309718 | LUG ESA 13797.93185703 UG | 13797 | SAINT CLOUD | ESA | 0.044697 | 5 | 2 | 2021-01-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.417 | LUG ESA 14116.91073265 | Lateral Hardening-Fuse-91073265 | CKT: 14116 - 91073265 | 2309719 | LUG ESA 14116.91073265 OH | 2309720 | LUG ESA 14116.91073265 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD385 | PRE-09361.417 | LUG ESA 14116.91073265 | Lateral Hardening-Fuse-91073265 | CKT: 14116 - 91073265 | 2309719 | LUG ESA 14116.91073265 OH | 2309720 | LUG ESA 14116.91073265 UG | 14116 | LAKEWOOD | ESA | 0.092614 | 7 | 10 | 2021-01-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.418 | LUG SHA 13900.10717269 | Lateral Hardening-Fuse-10717269 | CKT: 13900 - 10717269 | 2309723 | LUG SHA 13900.10717269 OH | 2309724 | LUG SHA 13900.10717269 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD386 | PRE-09361.418 | LUG SHA 13900.10717269 | Lateral Hardening-Fuse-10717269 | CKT: 13900 - 10717269 | 2309723 | LUG SHA 13900.10717269 OH | 2309724 | LUG SHA 13900.10717269 UG | 13900 | FIRST STREET | SHA | 0.41818 | 21 | 136 | 2021-01-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.419 | LUG SHA 13652.92748361 | Lateral Hardening-Fuse-92748361 | CKT: 13652 - 92748361 | 2309725 | LUG SHA 13652.92748361 OH | 2309728 | LUG SHA 13652.92748361 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD387 | PRE-09361.419 | LUG SHA 13652.92748361 | Lateral Hardening-Fuse-92748361 | CKT: 13652 - 92748361 | 2309725 | LUG SHA 13652.92748361 OH | 2309728 | LUG SHA 13652.92748361 UG | 13652 | RHODINE ROAD | SHA | 0.47689 | 23 | 23 | 2021-01-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.420 | LUG SHA 13001.93346473 | Lateral Hardening-Fuse-93346473 | CKT: 13001 - 93346473 | 2309729 | LUG SHA 13001.93346473 OH | 2309731 | LUG SHA 13001.93346473 UG | LUG C032 | N/A | 4500283885 | N/A | 2021 | LUG - TBD388 | PRE-09361.420 | LUG SHA 13001.93346473 | Lateral Hardening-Fuse-93346473 | CKT: 13001 - 93346473 | 2309729 | LUG SHA 13001.93346473 OH | 2309731 | LUG SHA 13001.93346473 UG | 13001 | RUSKIN | SHA | 0.80947 | 48 | 483 | 2021-02-01 | 2022 | 2022 | Combined with LUG-TBD402 (FID 90251758)
Leidos | 2021 | 2021 | PRE-09361.420 | LUG SHA 13001.93346473 | Lateral Hardening-Fuse-93346473 | CKT: 13001 - 93346473 | 2309729 | LUG SHA 13001.93346473 OH | 2309731 | LUG SHA 13001.93346473 UG | LUG C032 | N/A | 4500283885 | N/A | 2021 | LUG - TBD402 | PRE-09361.420 | DNU LUG SHA 13001.90251758 | DNU Lateral Hardening-Fuse-90251758 | N/A | N/A | N/A | N/A | N/A | 13001 | RUSKIN | SHA | 0.58939 | 38 | 50 | 2021-04-01 | 2022 | 2022 | Combined with LUG-TBD388 (FID 93346473)
Leidos | 2021 | 2021 | PRE-09361.421 | LUG SHA 14022.90591555 | Lateral Hardening-Fuse-90591555 | CKT: 14022 - 90591555 | 2309733 | LUG SHA 14022.90591555 OH | 2309734 | LUG SHA 14022.90591555 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD389 | PRE-09361.421 | LUG SHA 14022.90591555 | Lateral Hardening-Fuse-90591555 | CKT: 14022 - 90591555 | 2309733 | LUG SHA 14022.90591555 OH | 2309734 | LUG SHA 14022.90591555 UG | 14022 | RIVERVIEW | SHA | 0.75833 | 49 | 485 | 2021-02-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.422 | LUG SHA 13001.60179144 | Lateral Hardening-Fuse-60179144 | CKT: 13001 - 60179144 | 2309735 | LUG SHA 13001.60179144 OH | 2309737 | LUG SHA 13001.60179144 UG | LUG C033 | N/A | 4500283885 | N/A | 2021 | LUG - TBD390 | PRE-09361.422 | LUG SHA 13001.60179144 | Lateral Hardening-Fuse-60179144 | CKT: 13001 - 60179144 | 2309735 | LUG SHA 13001.60179144 OH | 2309737 | LUG SHA 13001.60179144 UG | 13001 | RUSKIN | SHA | 0.66742 | 42 | 162 | 2021-02-01 | 2022 | 2022 | Combined with LUG-TBD391 (FID 10663246)
Leidos | 2021 | 2021 | PRE-09361.422 | LUG SHA 13001.60179144 | Lateral Hardening-Fuse-60179144 | CKT: 13001 - 60179144 | 2309735 | LUG SHA 13001.60179144 OH | 2309737 | LUG SHA 13001.60179144 UG | LUG C033 | N/A | 4500283885 | N/A | 2021 | LUG - TBD391 | PRE-09361.422 | DNU LUG SHA 13001.10663246 | DNU Lateral Hardening-Fuse-10663246 | N/A | N/A | N/A | N/A | N/A | 13001 | RUSKIN | SHA | 0.50189 | 27 | 244 | 2021-03-01 | 2022 | 2022 | Combined with LUG-TBD390 (FID 60179144)
Leidos | 2021 | 2021 | PRE-09361.423 | LUG SHA 13645.91519309 | Lateral Hardening-Fuse-91519309 | CKT: 13645 - 91519309 | 2309783 | LUG SHA 13645.91519309 OH | 2309786 | LUG SHA 13645.91519309 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD392 | PRE-09361.423 | LUG SHA 13645.91519309 | Lateral Hardening-Fuse-91519309 | CKT: 13645 - 91519309 | 2309783 | LUG SHA 13645.91519309 OH | 2309786 | LUG SHA 13645.91519309 UG | 13645 | RHODINE ROAD | SHA | 0.49508 | 22 | 36 | 2021-03-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.424 | LUG SHA 13780.10723993 | Lateral Hardening-Fuse-10723993 | CKT: 13780 - 10723993 | 2309787 | LUG SHA 13780.10723993 OH | 2309788 | LUG SHA 13780.10723993 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD393 | PRE-09361.424 | LUG SHA 13780.10723993 | Lateral Hardening-Fuse-10723993 | CKT: 13780 - 10723993 | 2309787 | LUG SHA 13780.10723993 OH | 2309788 | LUG SHA 13780.10723993 UG | 13780 | MILLER MAC | SHA | 0.27008 | 17 | 97 | 2021-03-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.425 | LUG SHA 13001.92048269 | Lateral Hardening-Fuse-92048269 | CKT: 13001 - 92048269 | 2309791 | LUG SHA 13001.92048269 OH | 2309792 | LUG SHA 13001.92048269 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD394 | PRE-09361.425 | LUG SHA 13001.92048269 | Lateral Hardening-Fuse-92048269 | CKT: 13001 - 92048269 | 2309791 | LUG SHA 13001.92048269 OH | 2309792 | LUG SHA 13001.92048269 UG | 13001 | RUSKIN | SHA | 0.23845 | 17 | 137 | 2021-03-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.426 | LUG SHA 13001.60179191 | Lateral Hardening-Fuse-60179191 | CKT: 13001 - 60179191 | 2309794 | LUG SHA 13001.60179191 OH | 2309796 | LUG SHA 13001.60179191 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD395 | PRE-09361.426 | LUG SHA 13001.60179191 | Lateral Hardening-Fuse-60179191 | CKT: 13001 - 60179191 | 2309794 | LUG SHA 13001.60179191 OH | 2309796 | LUG SHA 13001.60179191 UG | 13001 | RUSKIN | SHA | 0.36439 | 30 | 139 | 2021-03-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.427 | LUG SHA 13001.10663240 | Lateral Hardening-Fuse-10663240 | CKT: 13001 - 10663240 | 2309797 | LUG SHA 13001.10663240 OH | 2309798 | LUG SHA 13001.10663240 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD396 | PRE-09361.427 | LUG SHA 13001.10663240 | Lateral Hardening-Fuse-10663240 | CKT: 13001 - 10663240 | 2309797 | LUG SHA 13001.10663240 OH | 2309798 | LUG SHA 13001.10663240 UG | 13001 | RUSKIN | SHA | 0.45189 | 26 | 16 | 2021-03-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.428 | LUG SHA 13900.92336596 | Lateral Hardening-Fuse-92336596 | CKT: 13900 - 92336596 | 2309852 | LUG SHA 13900.92336596 OH | 2309853 | LUG SHA 13900.92336596 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD397 | PRE-09361.428 | LUG SHA 13900.92336596 | Lateral Hardening-Fuse-92336596 | CKT: 13900 - 92336596 | 2309852 | LUG SHA 13900.92336596 OH | 2309853 | LUG SHA 13900.92336596 UG | 13900 | FIRST STREET | SHA | 0.45928 | 21 | 3 | 2021-03-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.429 | LUG SHA 13645.92207754 | Lateral Hardening-Fuse-92207754 | CKT: 13645 - 92207754 | 2309854 | LUG SHA 13645.92207754 OH | 2309855 | LUG SHA 13645.92207754 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD398 | PRE-09361.429 | LUG SHA 13645.92207754 | Lateral Hardening-Fuse-92207754 | CKT: 13645 - 92207754 | 2309854 | LUG SHA 13645.92207754 OH | 2309855 | LUG SHA 13645.92207754 UG | 13645 | RHODINE ROAD | SHA | 0.73258 | 28 | 7 | 2021-03-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.430 | LUG SHA 13900.91863298 | Lateral Hardening-Fuse-91863298 | CKT: 13900 - 91863298 | 2309856 | LUG SHA 13900.91863298 OH | 2309857 | LUG SHA 13900.91863298 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD399 | PRE-09361.430 | LUG SHA 13900.91863298 | Lateral Hardening-Fuse-91863298 | CKT: 13900 - 91863298 | 2309856 | LUG SHA 13900.91863298 OH | 2309857 | LUG SHA 13900.91863298 UG | 13900 | FIRST STREET | SHA | 0.26648 | 18 | 169 | 2021-03-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.431 | LUG SHA 13001.10663269 | Lateral Hardening-Fuse-10663269 | CKT: 13001 - 10663269 | 2309858 | LUG SHA 13001.10663269 OH | 2309860 | LUG SHA 13001.10663269 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD400 | PRE-09361.431 | LUG SHA 13001.10663269 | Lateral Hardening-Fuse-10663269 | CKT: 13001 - 10663269 | 2309858 | LUG SHA 13001.10663269 OH | 2309860 | LUG SHA 13001.10663269 UG | 13001 | RUSKIN | SHA | 0.11818 | 8 | 16 | 2021-03-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.432 | LUG SHA 13001.10663262 | Lateral Hardening-Fuse-10663262 | CKT: 13001 - 10663262 | 2309861 | LUG SHA 13001.10663262 OH | 2309862 | LUG SHA 13001.10663262 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD401 | PRE-09361.432 | LUG SHA 13001.10663262 | Lateral Hardening-Fuse-10663262 | CKT: 13001 - 10663262 | 2309861 | LUG SHA 13001.10663262 OH | 2309862 | LUG SHA 13001.10663262 UG | 13001 | RUSKIN | SHA | 0.092045 | 8 | 63 | 2021-03-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.433 | LUG ESA 13127.90334707 | Lateral Hardening-Fuse-90334707 | CKT: 13127 - 90334707 | 2309863 | LUG ESA 13127.90334707 OH | 2309864 | LUG ESA 13127.90334707 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD403 | PRE-09361.433 | LUG ESA 13127.90334707 | Lateral Hardening-Fuse-90334707 | CKT: 13127 - 90334707 | 2309863 | LUG ESA 13127.90334707 OH | 2309864 | LUG ESA 13127.90334707 UG | 13127 | SOUTH SEFFNER | ESA | 0.36061 | 24 | 150 | 2021-05-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.434 | LUG ESA 13878.10105723 | Lateral Hardening-Fuse-10105723 | CKT: 13878 - 10105723 | 2309865 | LUG ESA 13878.10105723 OH | 2309866 | LUG ESA 13878.10105723 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD405 | PRE-09361.434 | LUG ESA 13878.10105723 | Lateral Hardening-Fuse-10105723 | CKT: 13878 - 10105723 | 2309865 | LUG ESA 13878.10105723 OH | 2309866 | LUG ESA 13878.10105723 UG | 13878 | PROVIDENCE ROAD | ESA | 0.31307 | 25 | 46 | 2021-05-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.435 | LUG ESA 13911.92679866 | Lateral Hardening-Fuse-92679866 | CKT: 13911 - 92679866 | 2309867 | LUG ESA 13911.92679866 OH | 2309869 | LUG ESA 13911.92679866 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD406 | PRE-09361.435 | LUG ESA 13911.92679866 | Lateral Hardening-Fuse-92679866 | CKT: 13911 - 92679866 | 2309867 | LUG ESA 13911.92679866 OH | 2309869 | LUG ESA 13911.92679866 UG | 13911 | PEACH AVENUE | ESA | 0.55549 | 50 | 80 | 2021-05-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.436 | LUG ESA 13229.92525393 | Lateral Hardening-Fuse-92525393 | CKT: 13229 - 92525393 | 2309870 | LUG ESA 13229.92525393 OH | 2309871 | LUG ESA 13229.92525393 UG | LUG C025 | N/A | 4500283885 | N/A | 2021 | LUG - TBD404 | PRE-09361.436 | DNU LUG ESA 13229.10457704 | DNU Lateral Hardening-Fuse-10457704 | N/A | N/A | N/A | N/A | N/A | 13229 | BRANDON | ESA | 0.068939 | 8 | 152 | 2021-05-01 | 2022 | 2022 | Combined with LUG-TBD407 (FID 92525393)
Leidos | 2021 | 2021 | PRE-09361.436 | LUG ESA 13229.92525393 | Lateral Hardening-Fuse-92525393 | CKT: 13229 - 92525393 | 2309870 | LUG ESA 13229.92525393 OH | 2309871 | LUG ESA 13229.92525393 UG | LUG C025 | N/A | 4500283885 | N/A | 2021 | LUG - TBD407 | PRE-09361.436 | LUG ESA 13229.92525393 | Lateral Hardening-Fuse-92525393 | CKT: 13229 - 92525393 | 2309870 | LUG ESA 13229.92525393 OH | 2309871 | LUG ESA 13229.92525393 UG | 13229 | BRANDON | ESA | 0.21496 | 21 | 141 | 2021-05-01 | 2022 | 2022 | Combined with LUG-TBD404 (FID 10457704)
Leidos | 2021 | 2021 | PRE-09361.437 | LUG ESA 13909.92173076 | Lateral Hardening-Fuse-92173076 | CKT: 13909 - 92173076 | 2309872 | LUG ESA 13909.92173076 OH | 2309873 | LUG ESA 13909.92173076 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD408 | PRE-09361.437 | LUG ESA 13909.92173076 | Lateral Hardening-Fuse-92173076 | CKT: 13909 - 92173076 | 2309872 | LUG ESA 13909.92173076 OH | 2309873 | LUG ESA 13909.92173076 UG | 13909 | PEACH AVENUE | ESA | 0.31155 | 22 | 8 | 2021-05-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.438 | LUG ESA 14355.60258173 | Lateral Hardening-Fuse-60258173 | CKT: 14355 - 60258173 | 2309874 | LUG ESA 14355.60258173 OH | 2309875 | LUG ESA 14355.60258173 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD409 | PRE-09361.438 | LUG ESA 14355.60258173 | Lateral Hardening-Fuse-60258173 | CKT: 14355 - 60258173 | 2309874 | LUG ESA 14355.60258173 OH | 2309875 | LUG ESA 14355.60258173 UG | 14355 | CAUSEWAY | ESA | 0.15777 | 15 | 356 | 2021-05-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.439 | LUG ESA 13457.10482593 | Lateral Hardening-Fuse-10482593 | CKT: 13457 - 10482593 | 2309876 | LUG ESA 13457.10482593 OH | 2309877 | LUG ESA 13457.10482593 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD410 | PRE-09361.439 | LUG ESA 13457.10482593 | Lateral Hardening-Fuse-10482593 | CKT: 13457 - 10482593 | 2309876 | LUG ESA 13457.10482593 OH | 2309877 | LUG ESA 13457.10482593 UG | 13457 | LAKEWOOD | ESA | 0.13693 | 9 | 137 | 2021-05-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.440 | LUG ESA 13127.90334731 | Lateral Hardening-Fuse-90334731 | CKT: 13127 - 90334731 | 2309878 | LUG ESA 13127.90334731 OH | 2309879 | LUG ESA 13127.90334731 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD411 | PRE-09361.440 | LUG ESA 13127.90334731 | Lateral Hardening-Fuse-90334731 | CKT: 13127 - 90334731 | 2309878 | LUG ESA 13127.90334731 OH | 2309879 | LUG ESA 13127.90334731 UG | 13127 | SOUTH SEFFNER | ESA | 0.43826 | 22 | 56 | 2021-05-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.441 | LUG ESA 13906.10096968 | Lateral Hardening-Fuse-10096968 | CKT: 13906 - 10096968 | 2309880 | LUG ESA 13906.10096968 OH | 2309881 | LUG ESA 13906.10096968 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD412 | PRE-09361.441 | LUG ESA 13906.10096968 | Lateral Hardening-Fuse-10096968 | CKT: 13906 - 10096968 | 2309880 | LUG ESA 13906.10096968 OH | 2309881 | LUG ESA 13906.10096968 UG | 13906 | PEACH AVENUE | ESA | 0.55739 | 53 | 99 | 2021-05-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.442 | LUG ESA 13909.90380435 | Lateral Hardening-Fuse-90380435 | CKT: 13909 - 90380435 | 2309882 | LUG ESA 13909.90380435 OH | 2309883 | LUG ESA 13909.90380435 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD413 | PRE-09361.442 | LUG ESA 13909.90380435 | Lateral Hardening-Fuse-90380435 | CKT: 13909 - 90380435 | 2309882 | LUG ESA 13909.90380435 OH | 2309883 | LUG ESA 13909.90380435 UG | 13909 | PEACH AVENUE | ESA | 0.20095 | 11 | 41 | 2021-05-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.443 | LUG ESA 13906.92282884 | Lateral Hardening-Fuse-92282884 | CKT: 13906 - 92282884 | 2309884 | LUG ESA 13906.92282884 OH | 2309885 | LUG ESA 13906.92282884 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD415 | PRE-09361.443 | LUG ESA 13906.92282884 | Lateral Hardening-Fuse-92282884 | CKT: 13906 - 92282884 | 2309884 | LUG ESA 13906.92282884 OH | 2309885 | LUG ESA 13906.92282884 UG | 13906 | PEACH AVENUE | ESA | 0.095455 | 7 | 26 | 2021-05-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.444 | LUG ESA 13911.60157737 | Lateral Hardening-Fuse-60157737 | CKT: 13911 - 60157737 | 2309886 | LUG ESA 13911.60157737 OH | 2309887 | LUG ESA 13911.60157737 UG | LUG C028 | N/A | 4500283885 | N/A | 2021 | LUG - TBD416 | PRE-09361.444 | LUG ESA 13911.60157737 | Lateral Hardening-Fuse-60157737 | CKT: 13911 - 60157737 | 2309886 | LUG ESA 13911.60157737 OH | 2309887 | LUG ESA 13911.60157737 UG | 13911 | PEACH AVENUE | ESA | 0.65909 | 48 | 747 | 2021-05-01 | 2022 | 2022 | Combined with LUG-TBD424 (FID 91276385), LUG-TBD435 (FID 91556649) & LUG-TBD449 (FID 91665193)
Leidos | 2021 | 2021 | PRE-09361.444 | LUG ESA 13911.60157737 | Lateral Hardening-Fuse-60157737 | CKT: 13911 - 60157737 | 2309886 | LUG ESA 13911.60157737 OH | 2309887 | LUG ESA 13911.60157737 UG | LUG C028 | N/A | 4500283885 | N/A | 2021 | LUG - TBD424 | PRE-09361.444 | DNU LUG ESA 13911.91276385 | DNU Lateral Hardening-Fuse-91276385 | N/A | N/A | N/A | N/A | N/A | 13911 | PEACH AVENUE | ESA | 0.50284 | 45 | 253 | 2021-07-01 | 2022 | 2022 | Combined with LUG-TBD416 (FID 60157737),LUG-TBD435 (FID 91556649) & LUG-TBD449 (FID 91665193)
Leidos | 2021 | 2021 | PRE-09361.444 | LUG ESA 13911.60157737 | Lateral Hardening-Fuse-60157737 | CKT: 13911 - 60157737 | 2309886 | LUG ESA 13911.60157737 OH | 2309887 | LUG ESA 13911.60157737 UG | LUG C028 | N/A | 4500283885 | N/A | 2021 | LUG - TBD435 | PRE-09361.444 | DNU LUG ESA 13911.91556649 | DNU Lateral Hardening-Fuse-91556649 | N/A | N/A | N/A | N/A | N/A | 13911 | PEACH AVENUE | ESA | 0.50739 | 37 | 251 | 2021-08-01 | 2022 | 2022 | Combined with LUG-TBD416 (FID 60157737), LUG-TBD424 (FID 91276385) & LUG-TBD449 (FID 91665193)
Leidos | 2021 | 2021 | PRE-09361.444 | LUG ESA 13911.60157737 | Lateral Hardening-Fuse-60157737 | CKT: 13911 - 60157737 | 2309886 | LUG ESA 13911.60157737 OH | 2309887 | LUG ESA 13911.60157737 UG | LUG C028 | N/A | 4500283885 | N/A | 2021 | LUG - TBD449 | PRE-09361.444 | DNU LUG ESA 13911.91665193 | DNU Lateral Hardening-Fuse-91665193 | N/A | N/A | N/A | N/A | N/A | 13911 | PEACH AVENUE | ESA | 0.49034 | 32 | 179 | 2021-10-01 | 2022 | 2022 | Combined with LUG-TBD416 (FID 60157737), LUG-TBD424 (FID 91276385) & LUG-TBD435 (FID 91556649)
Leidos | 2021 | 2021 | PRE-09361.445 | LUG ESA 13710.92354144 | Lateral Hardening-Fuse-92354144 | CKT: 13710 - 92354144 | 2309888 | LUG ESA 13710.92354144 OH | 2309889 | LUG ESA 13710.92354144 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD417 | PRE-09361.445 | LUG ESA 13710.92354144 | Lateral Hardening-Fuse-92354144 | CKT: 13710 - 92354144 | 2309888 | LUG ESA 13710.92354144 OH | 2309889 | LUG ESA 13710.92354144 UG | 13710 | BUCKHORN | ESA | 0.28371 | 30 | 229 | 2021-06-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.446 | LUG ESA 13793.92685255 | Lateral Hardening-Fuse-92685255 | CKT: 13793 - 92685255 | 2309890 | LUG ESA 13793.92685255 OH | 2309891 | LUG ESA 13793.92685255 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD418 | PRE-09361.446 | LUG ESA 13793.92685255 | Lateral Hardening-Fuse-92685255 | CKT: 13793 - 92685255 | 2309890 | LUG ESA 13793.92685255 OH | 2309891 | LUG ESA 13793.92685255 UG | 13793 | SAINT CLOUD | ESA | 0.18996 | 6 | 26 | 2021-06-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.447 | LUG ESA 13906.10096960 | Lateral Hardening-Fuse-10096960 | CKT: 13906 - 10096960 | 2309892 | LUG ESA 13906.10096960 OH | 2309893 | LUG ESA 13906.10096960 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD419 | PRE-09361.447 | LUG ESA 13906.10096960 | Lateral Hardening-Fuse-10096960 | CKT: 13906 - 10096960 | 2309892 | LUG ESA 13906.10096960 OH | 2309893 | LUG ESA 13906.10096960 UG | 13906 | PEACH AVENUE | ESA | 0.37689 | 26 | 56 | 2021-06-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.448 | LUG ESA 13793.92686002 | Lateral Hardening-Fuse-92686002 | CKT: 13793 - 92686002 | 2309894 | LUG ESA 13793.92686002 OH | 2309895 | LUG ESA 13793.92686002 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD420 | PRE-09361.448 | LUG ESA 13793.92686002 | Lateral Hardening-Fuse-92686002 | CKT: 13793 - 92686002 | 2309894 | LUG ESA 13793.92686002 OH | 2309895 | LUG ESA 13793.92686002 UG | 13793 | SAINT CLOUD | ESA | 0.22879 | 17 | 1 | 2021-06-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.449 | LUG ESA 13686.93697046 | Lateral Hardening-Fuse-93697046 | CKT: 13686 - 93697046 | 2309896 | LUG ESA 13686.93697046 OH | 2309897 | LUG ESA 13686.93697046 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD421 | PRE-09361.449 | LUG ESA 13686.93697046 | Lateral Hardening-Fuse-93697046 | CKT: 13686 - 93697046 | 2309896 | LUG ESA 13686.93697046 OH | 2309897 | LUG ESA 13686.93697046 UG | 13686 | PEARSON ROAD | ESA | 0.40322 | 32 | 29 | 2021-06-01 | 2022 | 2022 | Incorrectly labeled as FID 10840113 initially
Leidos | 2021 | 2021 | PRE-09361.450 | LUG ESA 13906.10096964 | Lateral Hardening-Fuse-10096964 | CKT: 13906 - 10096964 | 2309898 | LUG ESA 13906.10096964 OH | 2309899 | LUG ESA 13906.10096964 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD422 | PRE-09361.450 | LUG ESA 13906.10096964 | Lateral Hardening-Fuse-10096964 | CKT: 13906 - 10096964 | 2309898 | LUG ESA 13906.10096964 OH | 2309899 | LUG ESA 13906.10096964 UG | 13906 | PEACH AVENUE | ESA | 0.6767 | 40 | 31 | 2021-06-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.451 | LUG ESA 13911.90130568 | Lateral Hardening-Fuse-90130568 | CKT: 13911 - 90130568 | 2309900 | LUG ESA 13911.90130568 OH | 2309902 | LUG ESA 13911.90130568 UG | LUG C027 | N/A | 4500283885 | N/A | 2021 | LUG - TBD423 | PRE-09361.451 | LUG ESA 13911.90130568 | Lateral Hardening-Fuse-90130568 | CKT: 13911 - 90130568 | 2309900 | LUG ESA 13911.90130568 OH | 2309902 | LUG ESA 13911.90130568 UG | 13911 | PEACH AVENUE | ESA | 0.85871 | 53 | 108 | 2021-06-01 | 2022 | 2022 | Combined with LUG-TBD433 (FID 10554588)
Leidos | 2021 | 2021 | PRE-09361.451 | LUG ESA 13911.90130568 | Lateral Hardening-Fuse-90130568 | CKT: 13911 - 90130568 | 2309900 | LUG ESA 13911.90130568 OH | 2309902 | LUG ESA 13911.90130568 UG | LUG C027 | N/A | 4500283885 | N/A | 2021 | LUG - TBD433 | PRE-09361.451 | DNU LUG ESA 13911.10554588 | DNU Lateral Hardening-Fuse-10554588 | N/A | N/A | N/A | N/A | N/A | 13911 | PEACH AVENUE | ESA | 0.40208 | 29 | 33 | 2021-08-01 | 2022 | 2022 | Combined with LUG-TBD423 (FID 90130568)
Leidos | 2021 | 2021 | PRE-09361.452 | LUG ESA 13906.90137810 | Lateral Hardening-Fuse-90137810 | CKT: 13906 - 90137810 | 2309903 | LUG ESA 13906.90137810 OH | 2309904 | LUG ESA 13906.90137810 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD425 | PRE-09361.452 | LUG ESA 13906.90137810 | Lateral Hardening-Fuse-90137810 | CKT: 13906 - 90137810 | 2309903 | LUG ESA 13906.90137810 OH | 2309904 | LUG ESA 13906.90137810 UG | 13906 | PEACH AVENUE | ESA | 0.80322 | 53 | 62 | 2021-07-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.453 | LUG ESA 13793.92686712 | Lateral Hardening-Fuse-92686712 | CKT: 13793 - 92686712 | 2309905 | LUG ESA 13793.92686712 OH | 2309906 | LUG ESA 13793.92686712 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD426 | PRE-09361.453 | LUG ESA 13793.92686712 | Lateral Hardening-Fuse-92686712 | CKT: 13793 - 92686712 | 2309905 | LUG ESA 13793.92686712 OH | 2309906 | LUG ESA 13793.92686712 UG | 13793 | SAINT CLOUD | ESA | 0.044318 | 4 | 85 | 2021-07-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.454 | LUG ESA 13127.92663180 | Lateral Hardening-Fuse-92663180 | CKT: 13127 - 92663180 | 2309907 | LUG ESA 13127.92663180 OH | 2309908 | LUG ESA 13127.92663180 UG | LUG C026 | N/A | 4500283885 | N/A | 2021 | LUG - TBD414 | PRE-09361.454 | DNU LUG ESA 13127.10836901 | DNU Lateral Hardening-Fuse-10836901 | N/A | N/A | N/A | N/A | N/A | 13127 | SOUTH SEFFNER | ESA | 0.44602 | 30 | 127 | 2021-05-01 | 2022 | 2022 | Combined with LUG-TBD427 (FID 92663180)
Leidos | 2021 | 2021 | PRE-09361.454 | LUG ESA 13127.92663180 | Lateral Hardening-Fuse-92663180 | CKT: 13127 - 92663180 | 2309907 | LUG ESA 13127.92663180 OH | 2309908 | LUG ESA 13127.92663180 UG | LUG C026 | N/A | 4500283885 | N/A | 2021 | LUG - TBD427 | PRE-09361.454 | LUG ESA 13127.92663180 | Lateral Hardening-Fuse-92663180 | CKT: 13127 - 92663180 | 2309907 | LUG ESA 13127.92663180 OH | 2309908 | LUG ESA 13127.92663180 UG | 13127 | SOUTH SEFFNER | ESA | 0.61761 | 42 | 33 | 2021-07-01 | 2022 | 2022 | Combined with LUG-TBD414 (FID 10836901)
Leidos | 2021 | 2021 | PRE-09361.455 | LUG ESA 13457.90176591 | Lateral Hardening-Fuse-90176591 | CKT: 13457 - 90176591 | 2309909 | LUG ESA 13457.90176591 OH | 2309910 | LUG ESA 13457.90176591 UG | LUG C029 | N/A | 4500283885 | N/A | 2021 | LUG - TBD428 | PRE-09361.455 | DNU LUG ESA 13457.90291488 | DNU Lateral Hardening-Fuse-90291488 | N/A | N/A | N/A | N/A | N/A | 13457 | LAKEWOOD | ESA | 0.10871 | 12 | 188 | 2021-07-01 | 2022 | 2022 | Combined with LUG-TBD432 (FID 90176591)
Leidos | 2021 | 2021 | PRE-09361.455 | LUG ESA 13457.90176591 | Lateral Hardening-Fuse-90176591 | CKT: 13457 - 90176591 | 2309909 | LUG ESA 13457.90176591 OH | 2309910 | LUG ESA 13457.90176591 UG | LUG C029 | N/A | 4500283885 | N/A | 2021 | LUG - TBD432 | PRE-09361.455 | LUG ESA 13457.90176591 | Lateral Hardening-Fuse-90176591 | CKT: 13457 - 90176591 | 2309909 | LUG ESA 13457.90176591 OH | 2309910 | LUG ESA 13457.90176591 UG | 13457 | LAKEWOOD | ESA | 0.31136 | 18 | 155 | 2021-08-01 | 2022 | 2022 | Combined with LUG-TBD428 (FID 90291488)
Leidos | 2021 | 2021 | PRE-09361.456 | LUG ESA 14355.92354352 | Lateral Hardening-Fuse-92354352 | CKT: 14355 - 92354352 | 2309911 | LUG ESA 14355.92354352 OH | 2309912 | LUG ESA 14355.92354352 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD434 | PRE-09361.456 | LUG ESA 14355.92354352 | Lateral Hardening-Fuse-92354352 | CKT: 14355 - 92354352 | 2309911 | LUG ESA 14355.92354352 OH | 2309912 | LUG ESA 14355.92354352 UG | 14355 | CAUSEWAY | ESA | 0.31856 | 22 | 51 | 2021-08-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.457 | LUG ESA 13793.92686736 | Lateral Hardening-Fuse-92686736 | CKT: 13793 - 92686736 | 2309914 | LUG ESA 13793.92686736 OH | 2309915 | LUG ESA 13793.92686736 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD436 | PRE-09361.457 | LUG ESA 13793.92686736 | Lateral Hardening-Fuse-92686736 | CKT: 13793 - 92686736 | 2309914 | LUG ESA 13793.92686736 OH | 2309915 | LUG ESA 13793.92686736 UG | 13793 | SAINT CLOUD | ESA | 0.032197 | 4 | 85 | 2021-08-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.458 | LUG ESA 13911.10554595 | Lateral Hardening-Fuse-10554595 | CKT: 13911 - 10554595 | 2309917 | LUG ESA 13911.10554595 OH | 2309918 | LUG ESA 13911.10554595 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD437 | PRE-09361.458 | LUG ESA 13911.10554595 | Lateral Hardening-Fuse-10554595 | CKT: 13911 - 10554595 | 2309917 | LUG ESA 13911.10554595 OH | 2309918 | LUG ESA 13911.10554595 UG | 13911 | PEACH AVENUE | ESA | 0.1303 | 16 | 4 | 2021-08-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.459 | LUG ESA 13911.91995336 | Lateral Hardening-Fuse-91995336 | CKT: 13911 - 91995336 | 2309919 | LUG ESA 13911.91995336 OH | 2309920 | LUG ESA 13911.91995336 UG | LUG C030 | N/A | 4500283885 | N/A | 2021 | LUG - TBD429 | PRE-09361.459 | DNU LUG ESA 13911.10544635 | DNU Lateral Hardening-Fuse-10544635 | N/A | N/A | N/A | N/A | N/A | 13911 | PEACH AVENUE | ESA | 0.2267 | 14 | 136 | 2021-07-01 | 2022 | 2022 | Combined with LUG-TBD430 (FID 10544633), LUG-TBD431 (FID 92018843) & LUG-TBD438 (FID 91995336)
Leidos | 2021 | 2021 | PRE-09361.459 | LUG ESA 13911.91995336 | Lateral Hardening-Fuse-91995336 | CKT: 13911 - 91995336 | 2309919 | LUG ESA 13911.91995336 OH | 2309920 | LUG ESA 13911.91995336 UG | LUG C030 | N/A | 4500283885 | N/A | 2021 | LUG - TBD430 | PRE-09361.459 | DNU LUG ESA 13911.10544633 | DNU Lateral Hardening-Fuse-10544633 | N/A | N/A | N/A | N/A | N/A | 13911 | PEACH AVENUE | ESA | 0.17917 | 12 | 20 | 2021-08-01 | 2022 | 2022 | Combined with LUG-TBD429 (FID 10544635), LUG-TBD431 (FID 92018843) & LUG-TBD438 (FID 91995336)
Leidos | 2021 | 2021 | PRE-09361.459 | LUG ESA 13911.91995336 | Lateral Hardening-Fuse-91995336 | CKT: 13911 - 91995336 | 2309919 | LUG ESA 13911.91995336 OH | 2309920 | LUG ESA 13911.91995336 UG | LUG C030 | N/A | 4500283885 | N/A | 2021 | LUG - TBD431 | PRE-09361.459 | DNU LUG ESA 13911.92018843 | DNU Lateral Hardening-Fuse-92018843 | N/A | N/A | N/A | N/A | N/A | 13911 | PEACH AVENUE | ESA | 0.12216 | 6 | 14 | 2021-08-01 | 2022 | 2022 | Combined with LUG-TBD429 (FID 10544635), LUG-TBD430 (FID 10544633) & LUG-TBD438 (FID 91995336)
Leidos | 2021 | 2021 | PRE-09361.459 | LUG ESA 13911.91995336 | Lateral Hardening-Fuse-91995336 | CKT: 13911 - 91995336 | 2309919 | LUG ESA 13911.91995336 OH | 2309920 | LUG ESA 13911.91995336 UG | LUG C030 | N/A | 4500283885 | N/A | 2021 | LUG - TBD438 | PRE-09361.459 | LUG ESA 13911.91995336 | Lateral Hardening-Fuse-91995336 | CKT: 13911 - 91995336 | 2309919 | LUG ESA 13911.91995336 OH | 2309920 | LUG ESA 13911.91995336 UG | 13911 | PEACH AVENUE | ESA | 0.30095 | 19 | 93 | 2021-08-01 | 2022 | 2022 | Combined with LUG-TBD429 (FID 10544635), LUG-TBD430 (FID 10544633) & LUG-TBD431 (FID 92018843)
Leidos | 2021 | 2021 | PRE-09361.460 | LUG ESA 13127.92661768 | Lateral Hardening-Fuse-92661768 | CKT: 13127 - 92661768 | 2309921 | LUG ESA 13127.92661768 OH | 2309922 | LUG ESA 13127.92661768 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD439 | PRE-09361.460 | LUG ESA 13127.92661768 | Lateral Hardening-Fuse-92661768 | CKT: 13127 - 92661768 | 2309921 | LUG ESA 13127.92661768 OH | 2309922 | LUG ESA 13127.92661768 UG | 13127 | SOUTH SEFFNER | ESA | 0.53409 | 34 | 170 | 2021-09-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.461 | LUG ESA 13878.10105726 | Lateral Hardening-Fuse-10105726 | CKT: 13878 - 10105726 | 2309923 | LUG ESA 13878.10105726 OH | 2309924 | LUG ESA 13878.10105726 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD441 | PRE-09361.461 | LUG ESA 13878.10105726 | Lateral Hardening-Fuse-10105726 | CKT: 13878 - 10105726 | 2309923 | LUG ESA 13878.10105726 OH | 2309924 | LUG ESA 13878.10105726 UG | 13878 | PROVIDENCE ROAD | ESA | 0.54015 | 44 | 137 | 2021-09-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.462 | LUG ESA 13454.90188551 | Lateral Hardening-Fuse-90188551 | CKT: 13454 - 90188551 | 2309925 | LUG ESA 13454.90188551 OH | 2309926 | LUG ESA 13454.90188551 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD442 | PRE-09361.462 | LUG ESA 13454.90188551 | Lateral Hardening-Fuse-90188551 | CKT: 13454 - 90188551 | 2309925 | LUG ESA 13454.90188551 OH | 2309926 | LUG ESA 13454.90188551 UG | 13454 | LAKEWOOD | ESA | 0.21004 | 13 | 37 | 2021-09-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.463 | LUG ESA 13878.10105717 | Lateral Hardening-Fuse-10105717 | CKT: 13878 - 10105717 | 2309928 | LUG ESA 13878.10105717 OH | 2309929 | LUG ESA 13878.10105717 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD443 | PRE-09361.463 | LUG ESA 13878.10105717 | Lateral Hardening-Fuse-10105717 | CKT: 13878 - 10105717 | 2309928 | LUG ESA 13878.10105717 OH | 2309929 | LUG ESA 13878.10105717 UG | 13878 | PROVIDENCE ROAD | ESA | 0.31288 | 23 | 346 | 2021-09-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.464 | LUG ESA 13231.10868121 | Lateral Hardening-Fuse-10868121 | CKT: 13231 - 10868121 | 2309930 | LUG ESA 13231.10868121 OH | 2309931 | LUG ESA 13231.10868121 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD444 | PRE-09361.464 | LUG ESA 13231.10868121 | Lateral Hardening-Fuse-10868121 | CKT: 13231 - 10868121 | 2309930 | LUG ESA 13231.10868121 OH | 2309931 | LUG ESA 13231.10868121 UG | 13231 | BRANDON | ESA | 0.27311 | 22 | 23 | 2021-11-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.465 | LUG ESA 13911.60157736 | Lateral Hardening-Fuse-60157736 | CKT: 13911 - 60157736 | 2309932 | LUG ESA 13911.60157736 OH | 2309933 | LUG ESA 13911.60157736 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD445 | PRE-09361.465 | LUG ESA 13911.60157736 | Lateral Hardening-Fuse-60157736 | CKT: 13911 - 60157736 | 2309932 | LUG ESA 13911.60157736 OH | 2309933 | LUG ESA 13911.60157736 UG | 13911 | PEACH AVENUE | ESA | 0.051894 | 5 | 62 | 2021-09-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.466 | LUG ESA 13171.10455381 | Lateral Hardening-Fuse-10455381 | CKT: 13171 - 10455381 | 2309934 | LUG ESA 13171.10455381 OH | 2309935 | LUG ESA 13171.10455381 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD447 | PRE-09361.466 | LUG ESA 13171.10455381 | Lateral Hardening-Fuse-10455381 | CKT: 13171 - 10455381 | 2309934 | LUG ESA 13171.10455381 OH | 2309935 | LUG ESA 13171.10455381 UG | 13171 | MADISON | ESA | 0.12462 | 11 | 5 | 2021-11-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.467 | LUG ESA 13878.10105728 | Lateral Hardening-Fuse-10105728 | CKT: 13878 - 10105728 | 2309936 | LUG ESA 13878.10105728 OH | 2309938 | LUG ESA 13878.10105728 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD448 | PRE-09361.467 | LUG ESA 13878.10105728 | Lateral Hardening-Fuse-10105728 | CKT: 13878 - 10105728 | 2309936 | LUG ESA 13878.10105728 OH | 2309938 | LUG ESA 13878.10105728 UG | 13878 | PROVIDENCE ROAD | ESA | 0.23201 | 14 | 26 | 2021-10-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.468 | LUG SHA 14024.10747874 | Lateral Hardening-Fuse-10747874 | CKT: 14024 - 10747874 | 2309939 | LUG SHA 14024.10747874 OH | 2309940 | LUG SHA 14024.10747874 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD451 | PRE-09361.468 | LUG SHA 14024.10747874 | Lateral Hardening-Fuse-10747874 | CKT: 14024 - 10747874 | 2309939 | LUG SHA 14024.10747874 OH | 2309940 | LUG SHA 14024.10747874 UG | 14024 | RIVERVIEW | SHA | 0.15057 | 13 | 135 | 2021-11-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.469 | LUG SHA 13342.91010293 | Lateral Hardening-Fuse-91010293 | CKT: 13342 - 91010293 | 2309941 | LUG SHA 13342.91010293 OH | 2309942 | LUG SHA 13342.91010293 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD452 | PRE-09361.469 | LUG SHA 13342.91010293 | Lateral Hardening-Fuse-91010293 | CKT: 13342 - 91010293 | 2309941 | LUG SHA 13342.91010293 OH | 2309942 | LUG SHA 13342.91010293 UG | 13342 | EAST BAY | SHA | 0.35966 | 27 | 190 | 2021-11-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.470 | LUG SHA 14020.60223573 | Lateral Hardening-Fuse-60223573 | CKT: 14020 - 60223573 | 2309943 | LUG SHA 14020.60223573 OH | 2309944 | LUG SHA 14020.60223573 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD453 | PRE-09361.470 | LUG SHA 14020.60223573 | Lateral Hardening-Fuse-60223573 | CKT: 14020 - 60223573 | 2309943 | LUG SHA 14020.60223573 OH | 2309944 | LUG SHA 14020.60223573 UG | 14020 | RIVERVIEW | SHA | 0.48087 | 45 | 415 | 2021-11-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.471 | LUG SHA 13342.10925094 | Lateral Hardening-Fuse-10925094 | CKT: 13342 - 10925094 | 2309945 | LUG SHA 13342.10925094 OH | 2309946 | LUG SHA 13342.10925094 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD454 | PRE-09361.471 | LUG SHA 13342.10925094 | Lateral Hardening-Fuse-10925094 | CKT: 13342 - 10925094 | 2309945 | LUG SHA 13342.10925094 OH | 2309946 | LUG SHA 13342.10925094 UG | 13342 | EAST BAY | SHA | 0.32689 | 22 | 45 | 2021-11-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.472 | LUG SHA 14024.90116190 | Lateral Hardening-Fuse-90116190 | CKT: 14024 - 90116190 | 2309947 | LUG SHA 14024.90116190 OH | 2309948 | LUG SHA 14024.90116190 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD455 | PRE-09361.472 | LUG SHA 14024.90116190 | Lateral Hardening-Fuse-90116190 | CKT: 14024 - 90116190 | 2309947 | LUG SHA 14024.90116190 OH | 2309948 | LUG SHA 14024.90116190 UG | 14024 | RIVERVIEW | SHA | 0.1267 | 11 | 12 | 2021-11-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.473 | LUG SHA 13817.10722417 | Lateral Hardening-Fuse-10722417 | CKT: 13817 - 10722417 | 2309949 | LUG SHA 13817.10722417 OH | 2309950 | LUG SHA 13817.10722417 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD456 | PRE-09361.473 | LUG SHA 13817.10722417 | Lateral Hardening-Fuse-10722417 | CKT: 13817 - 10722417 | 2309949 | LUG SHA 13817.10722417 OH | 2309950 | LUG SHA 13817.10722417 UG | 13817 | RUSKIN | SHA | 1.7845 | 123 | 570 | 2021-10-01 | 2022 | 2022
Leidos | 2021 | 2021 | PRE-09361.474 | LUG SHA 13003.10895211 | Lateral Hardening-Fuse-10895211 | CKT: 13003 - 10895211 | 2309951 | LUG SHA 13003.10895211 OH | 2309952 | LUG SHA 13003.10895211 UG | LUG C031 | N/A | 4500283885 | N/A | 2021 | LUG - TBD450 | PRE-09361.474 | DNU LUG SHA 13003.10895225 | DNU Lateral Hardening-Fuse-10895225 | N/A | N/A | N/A | N/A | N/A | 13003 | RUSKIN | SHA | 0.66477 | 34 | 198 | 2021-11-01 | 2022 | 2022 | Combined with LUG-TBD457 (FID 10895211)
Leidos | 2021 | 2021 | PRE-09361.474 | LUG SHA 13003.10895211 | Lateral Hardening-Fuse-10895211 | CKT: 13003 - 10895211 | 2309951 | LUG SHA 13003.10895211 OH | 2309952 | LUG SHA 13003.10895211 UG | LUG C031 | N/A | 4500283885 | N/A | 2021 | LUG - TBD457 | PRE-09361.474 | LUG SHA 13003.10895211 | Lateral Hardening-Fuse-10895211 | CKT: 13003 - 10895211 | 2309951 | LUG SHA 13003.10895211 OH | 2309952 | LUG SHA 13003.10895211 UG | 13003 | RUSKIN | SHA | 2.4676 | 116 | 179 | 2021-04-01 | 2022 | 2022 | Combined with LUG-TBD450 (FID 10895225)
Leidos | 2021 | 2021 | PRE-09361.475 | LUG SHA 13342.90527363 | Lateral Hardening-Fuse-90527363 | CKT: 13342 - 90527363 | 2309954 | LUG SHA 13342.90527363 OH | 2309955 | LUG SHA 13342.90527363 UG |  | N/A | 4500283885 | N/A | 2021 | LUG - TBD458 | PRE-09361.475 | LUG SHA 13342.90527363 | Lateral Hardening-Fuse-90527363 | CKT: 13342 - 90527363 | 2309954 | LUG SHA 13342.90527363 OH | 2309955 | LUG SHA 13342.90527363 UG | 13342 | EAST BAY | SHA | 0.15606 | 10 | 29 | 2021-07-01
Pike | 2020 | 2020 | PRE-09361.100 | LUG CSA 13948.10442385 | Lateral Hardening-Fuse-10442385 | CKT: 13948 - 10442385 | 2275183 | LUG CSA 13948.10442385 OH | 2275184 | LUG CSA 13948.10442385 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD165 | PRE-09361.100 | LUG CSA 13948.10442385 | Lateral Hardening-Fuse-10442385 | CKT: 13948 - 10442385 | 2275183 | LUG CSA 13948.10442385 OH | 2275184 | LUG CSA 13948.10442385 UG | 13948 | YUKON | CSA | 0.30436 | 23 | 130 | 2020-10-01 | 2021-04-01 | 2021-06-01
Pike | 2020 | 2020 | PRE-09361.21 | LUG CSA 14040.10786382 | Lateral Hardening-Fuse-10786382 | CKT: 14040 - 10786382 | 2271067 | LUG CSA 14040.10786382 OH | 2271080 | LUG CSA 14040.10786382 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD130 | PRE-09361.21 | LUG CSA 14040.10786382 | Lateral Hardening-Fuse-10786382 | CKT: 14040 - 10786382 | 2271067 | LUG CSA 14040.10786382 OH | 2271080 | LUG CSA 14040.10786382 UG | 14040 | HARNEY ROAD | CSA | 0.23409 | 13 | 98 | 2020-06-01 | 2021-01-01 | 2021-03-01
Pike | 2020 | 2020 | PRE-09361.22 | LUG CSA 13840.93019714 | Lateral Hardening-Fuse-93019714 | CKT: 13840 - 93019714 | 2271581 | LUG CSA 13840.93019714 OH | 2271592 | LUG CSA 13840.93019714 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD131 | PRE-09361.22 | LUG CSA 13840.93019714 | Lateral Hardening-Fuse-93019714 | CKT: 13840 - 93019714 | 2271581 | LUG CSA 13840.93019714 OH | 2271592 | LUG CSA 13840.93019714 UG | 13840 | FLORIDA AVENUE | CSA | 0.13371 | 9 | 39 | 2020-06-01 | 2021-01-01 | 2021-03-01
Pike | 2020 | 2021 | PRE-09361.23 | LUG CSA 14040.10786374 | Lateral Hardening-Fuse-10786374 | CKT: 14040 - 10786374 | 2271630 | LUG CSA 14040.10786374 OH | 2271645 | LUG CSA 14040.10786374 UG | LUG C012 | 4500276922 | N/A | N/A | 2021 | LUG - TBD226 | PRE-09361.23 | DNU LUG CSA 14040.90485522 | DNU Lateral Hardening-Fuse-90485522 | N/A | N/A | N/A | N/A | N/A | 14040 | HARNEY ROAD | CSA | 0.1125 | 10 | 22 | 2021-07-01 | 2022 | 2022 | Combined with PRE-09361.23 (FID 10786374)
Pike | 2020 | 2020 | PRE-09361.23 | LUG CSA 14040.10786374 | Lateral Hardening-Fuse-10786374 | CKT: 14040 - 10786374 | 2271630 | LUG CSA 14040.10786374 OH | 2271645 | LUG CSA 14040.10786374 UG | LUG C012 | 4500276922 | N/A | N/A | 2020 | LUG - TBD132 | PRE-09361.23 | LUG CSA 14040.10786374 | Lateral Hardening-Fuse-10786374 | CKT: 14040 - 10786374 | 2271630 | LUG CSA 14040.10786374 OH | 2271645 | LUG CSA 14040.10786374 UG | 14040 | HARNEY ROAD | CSA | 0.27254 | 16 | 205 | 2020-06-01 | 2021-01-01 | 2021-03-01 | Combined with LUG - TBD226 (FID 90485522)
Pike | 2020 | 2020 | PRE-09361.27 | LUG DCA 13815.93026469 | Lateral Hardening-Fuse-93026469 | CKT: 13815 - 93026469 | 2274978 | LUG DCA 13815.93026469 OH | 2274982 | LUG DCA 13815.93026469 UG | LUG C011 | 4500276922 | N/A | N/A | 2020 | LUG - TBD134 | PRE-09361.25 | DNU LUG DCA 13815.92407065 | DNU Lateral Hardening-Fuse-92407065 | DNU CKT: 13815 - 92407065 | 2274969 | DNU LUG DCA 13815.92407065 OH | 2274971 | DNU LUG DCA 13815.92407065 UG | 13815 | BLANTON | DCA | 0.37557 | 15 | 12 | 2020-07-01 | 2021-01-01 | 2021-03-01 | Combined with PRE-09361.26 (FID 90288627) and PRE-09361.27 (FID 93026469); work related to .25 "on hold" pending easement issues, will likely be uncombined from .27 after projection filing is completed
Pike | 2020 | 2020 | PRE-09361.27 | LUG DCA 13815.93026469 | Lateral Hardening-Fuse-93026469 | CKT: 13815 - 93026469 | 2274978 | LUG DCA 13815.93026469 OH | 2274982 | LUG DCA 13815.93026469 UG | LUG C011 | 4500276922 | N/A | N/A | 2020 | LUG - TBD135 | PRE-09361.26 | DNU LUG DCA 13815.90288627 | DNU Lateral Hardening-Fuse-90288627 | DNU CKT: 13815 - 90288627 | 2274973 | DNU LUG DCA 13815.90288627 OH | 2274976 | DNU LUG DCA 13815.90288627 UG | 13815 | BLANTON | DCA | 0.88144 | 32 | 51 | 2020-07-01 | 2021-01-01 | 2021-03-01 | Combined with PRE-09361.25 (FID 92407065) and PRE-09361.27 (FID 93026469)
Pike | 2020 | 2020 | PRE-09361.27 | LUG DCA 13815.93026469 | Lateral Hardening-Fuse-93026469 | CKT: 13815 - 93026469 | 2274978 | LUG DCA 13815.93026469 OH | 2274982 | LUG DCA 13815.93026469 UG | LUG C011 | 4500276922 | N/A | N/A | 2020 | LUG - TBD136 | PRE-09361.27 | LUG DCA 13815.93026469 | Lateral Hardening-Fuse-93026469 | CKT: 13815 - 93026469 | 2274978 | LUG DCA 13815.93026469 OH | 2274982 | LUG DCA 13815.93026469 UG | 13815 | BLANTON | DCA | 0.49489 | 15 | 27 | 2020-07-01 | 2021-01-01 | 2021-03-01 | Combined with PRE-09361.25 (FID 92407065) and PRE-09361.26 (FID 90288627)
Pike | 2020 | 2020 | PRE-09361.28 | LUG CSA 13183.60036344 | Lateral Hardening-Fuse-60036344 | CKT: 13183 - 60036344 | 2274984 | LUG CSA 13183.60036344 OH | 2274985 | LUG CSA 13183.60036344 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD137 | PRE-09361.28 | LUG CSA 13183.60036344 | Lateral Hardening-Fuse-60036344 | CKT: 13183 - 60036344 | 2274984 | LUG CSA 13183.60036344 OH | 2274985 | LUG CSA 13183.60036344 UG | 13183 | ELEVENTH AVENUE | CSA | 0.094318 | 13 | 22 | 2020-07-01 | 2021-01-01 | 2021-03-01
Pike | 2020 | 2020 | PRE-09361.30 | LUG CSA 13934.10467606 | Lateral Hardening-Fuse-10467606 | CKT: 13934 - 10467606 | 2274993 | LUG CSA 13934.10467606 OH | 2274994 | LUG CSA 13934.10467606 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD139 | PRE-09361.30 | LUG CSA 13934.10467606 | Lateral Hardening-Fuse-10467606 | CKT: 13934 - 10467606 | 2274993 | LUG CSA 13934.10467606 OH | 2274994 | LUG CSA 13934.10467606 UG | 13934 | LAKE MAGDALENE | CSA | 0.30852 | 16 | 199 | 2020-08-01 | 2021-01-01 | 2021-03-01
Pike | 2021 | 2021 | PRE-09361.341 | LUG CSA 13205.90929181 | Lateral Hardening-Fuse-90929181 | CKT: 13205 - 90929181 | 2308083 | LUG CSA 13205.90929181 OH | 2308084 | LUG CSA 13205.90929181 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD166 | PRE-09361.341 | LUG CSA 13205.90929181 | Lateral Hardening-Fuse-90929181 | CKT: 13205 - 90929181 | 2308083 | LUG CSA 13205.90929181 OH | 2308084 | LUG CSA 13205.90929181 UG | 13205 | TEMPLE TERRACE | CSA | 0.19943 | 15 | 32 | 2021-01-01 | 2021-04-01 | 2021-06-01
Pike | 2021 | 2021 | PRE-09361.342 | LUG CSA 13021.10051153 | Lateral Hardening-Fuse-10051153 | CKT: 13021 - 10021153 | 2308242 | LUG CSA 13021.10051153 OH | 2308254 | LUG CSA 13021.10051153 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD167 | PRE-09361.342 | LUG CSA 13021.10051153 | Lateral Hardening-Fuse-10051153 | CKT: 13021 - 10021153 | 2308242 | LUG CSA 13021.10051153 OH | 2308254 | LUG CSA 13021.10051153 UG | 13021 | JUNEAU | CSA | 0.15189 | 6 | 14 | 2021-01-01 | 2021-04-01 | 2021-06-01
Pike | 2021 | 2021 | PRE-09361.343 | LUG CSA 13026.60059524 | Lateral Hardening-Fuse-60059524 | CKT: 13026 - 60059524 | 2308256 | LUG CSA 13026.60059524 OH | 2308264 | LUG CSA 13026.60059524 UG | LUG C063 | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD168 | PRE-09361.343 | LUG CSA 13026.60059524 | Lateral Hardening-Fuse-60059524 | CKT: 13026 - 60059524 | 2308256 | LUG CSA 13026.60059524 OH | 2308264 | LUG CSA 13026.60059524 UG | 13026 | TEMPLE TERRACE | CSA | 0.18939 | 16 | 115 | 2021-01-01 | 2021-04-01 | 2021-06-01 | Combined with PRE-09361.404 (FID 91490707)
Pike | 2021 | 2021 | PRE-09361.343 | LUG CSA 13026.60059524 | Lateral Hardening-Fuse-60059524 | CKT: 13026 - 60059524 | 2308256 | LUG CSA 13026.60059524 OH | 2308264 | LUG CSA 13026.60059524 UG | LUG C063 | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD250 | PRE-09361.404 | DNU LUG CSA 13026.91490707 | DNU Lateral Hardening-Fuse-91490707 | DNU CKT: 13026 - 91490707 | 2310348 | DNU LUG CSA 13026.91490707 OH | 2310349 | DNU LUG CSA 13026.91490707 UG | 13026 | TEMPLE TERRACE | CSA | 0.28409 | 15 | 98 | 2021-10-01 | 2022 | 2022 | Combined with PRE-09361.343 (FID 60059524)
Pike | 2021 | 2021 | PRE-09361.344 | LUG CSA 13835.10429522 | Lateral Hardening-Fuse-10429522 | CKT: 13835 - 10429522 | 2308307 | LUG CSA 13835.10429522 OH | 2308309 | LUG CSA 13835.10429522 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD169 | PRE-09361.344 | LUG CSA 13835.10429522 | Lateral Hardening-Fuse-10429522 | CKT: 13835 - 10429522 | 2308307 | LUG CSA 13835.10429522 OH | 2308309 | LUG CSA 13835.10429522 UG | 13835 | FLORIDA AVENUE | CSA | 0.69015 | 41 | 163 | 2021-01-01 | 2021-04-01 | 2021-06-01
Pike | 2021 | 2021 | PRE-09361.345 | LUG CSA 13204.91532149 | Lateral Hardening-Fuse-91532149 | CKT: 13204 - 91532149 | 2308318 | LUG CSA 13204.91532149 OH | 2308319 | LUG CSA 13204.91532149 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD170 | PRE-09361.345 | LUG CSA 13204.91532149 | Lateral Hardening-Fuse-91532149 | CKT: 13204 - 91532149 | 2308318 | LUG CSA 13204.91532149 OH | 2308319 | LUG CSA 13204.91532149 UG | 13204 | TEMPLE TERRACE | CSA | 0.50114 | 39 | 591 | 2021-01-01 | 2021-04-01 | 2021-06-01
Pike | 2021 | 2021 | PRE-09361.346 | HOLD LUG CSA 13836.91406642 | Lateral Hardening-Fuse-91406642 | CKT: 13836 - 91406642 | 2308333 | HOLD LUG CSA 13836.91406642 OH | 2308341 | HOLD LUG CSA 13836.91406642 UG | Delayed LUG CO13/HOLD | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD171 | PRE-09361.346 | LUG CSA 13836.91406642 | Lateral Hardening-Fuse-91406642 | CKT: 13836 - 91406642 | 2308333 | LUG CSA 13836.91406642 OH | 2308341 | LUG CSA 13836.91406642 UG | 13836 | FLORIDA AVENUE | CSA | 0.098295 | 7 | 42 | 2021-01-01 | 2021-05-01 | 2021-07-01 | Identified as a part of LUG CO13, but not transitioned to DS PRE-09361.84 financials, due to delayed work scope; project on hold until 2022, per Kanesha, as of 6/18/2021
Pike | 2021 | 2021 | PRE-09361.347 | LUG CSA 13590.91231633 | Lateral Hardening-Fuse-91231633 | CKT: 13590 - 91231633 | 2308378 | LUG CSA 13590.91231633 OH | 2308380 | LUG CSA 13590.91231633 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD173 | PRE-09361.347 | LUG CSA 13590.91231633 | Lateral Hardening-Fuse-91231633 | CKT: 13590 - 91231633 | 2308378 | LUG CSA 13590.91231633 OH | 2308380 | LUG CSA 13590.91231633 UG | 13590 | SENECA STREET | CSA | 0.34205 | 29 | 47 | 2021-01-01 | 2021-06-01 | 2021-08-01
Pike | 2021 | 2021 | PRE-09361.348 | LUG CSA 13102.91293905 | Lateral Hardening-Fuse-91293905 | CKT: 13102 - 91293905 | 2308387 | LUG CSA 13102.91293905 OH | 2308393 | LUG CSA 13102.91293905 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD174 | PRE-09361.348 | LUG CSA 13102.91293905 | Lateral Hardening-Fuse-91293905 | CKT: 13102 - 91293905 | 2308387 | LUG CSA 13102.91293905 OH | 2308393 | LUG CSA 13102.91293905 UG | 13102 | YUKON | CSA | 0.11629 | 10 | 47 | 2021-01-01 | 2021-06-01 | 2021-08-01
Pike | 2021 | 2021 | PRE-09361.349 | LUG CSA 13831.10427677 | Lateral Hardening-Fuse-10427677 | CKT: 13831 - 10427677 | 2308403 | LUG CSA 13831.10427677 OH | 2308407 | LUG CSA 13831.10427677 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD176 | PRE-09361.349 | LUG CSA 13831.10427677 | Lateral Hardening-Fuse-10427677 | CKT: 13831 - 10427677 | 2308403 | LUG CSA 13831.10427677 OH | 2308407 | LUG CSA 13831.10427677 UG | 13831 | FOWLER AVENUE | CSA | 0.25417 | 18 | 313 | 2021-01-01 | 2021-06-01 | 2021-08-01
Pike | 2021 | 2021 | PRE-09361.350 | LUG CSA 14040.60233886 | Lateral Hardening-Fuse-60233886 | CKT: 14040 - 60233886 | 2308411 | LUG CSA 14040.60233886 OH | 2308414 | LUG CSA 14040.60233886 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD177 | PRE-09361.350 | LUG CSA 14040.60233886 | Lateral Hardening-Fuse-60233886 | CKT: 14040 - 60233886 | 2308411 | LUG CSA 14040.60233886 OH | 2308414 | LUG CSA 14040.60233886 UG | 14040 | HARNEY ROAD | CSA | 0.12614 | 12 | 96 | 2021-01-01 | 2021-07-01 | 2021-08-01
Pike | 2021 | 2021 | PRE-09361.351 | LUG CSA 13939.60144164 | Lateral Hardening-Fuse-60144164 | CKT: 13939 - 60144164 | 2308420 | LUG CSA 13939.60144164 OH | 2308424 | LUG CSA 13939.60144164 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD178 | PRE-09361.351 | LUG CSA 13939.60144164 | Lateral Hardening-Fuse-60144164 | CKT: 13939 - 60144164 | 2308420 | LUG CSA 13939.60144164 OH | 2308424 | LUG CSA 13939.60144164 UG | 13939 | LAKE MAGDALENE | CSA | 0.12121 | 8 | 38 | 2021-01-01 | 2021-07-01 | 2021-09-01
Pike | 2021 | 2021 | PRE-09361.352 | LUG CSA 13021.60058683 | Lateral Hardening-Fuse-60058683 | CKT: 13021 - 60058683 | 2308837 | LUG CSA 13021.60058683 OH | 2308838 | LUG CSA 13021.60058683 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD180 | PRE-09361.352 | LUG CSA 13021.60058683 | Lateral Hardening-Fuse-60058683 | CKT: 13021 - 60058683 | 2308837 | LUG CSA 13021.60058683 OH | 2308838 | LUG CSA 13021.60058683 UG | 13021 | JUNEAU | CSA | 0.30682 | 28 | 130 | 2021-01-01 | 2021-07-01 | 2021-09-01
Pike | 2021 | 2021 | PRE-09361.353 | LUG CSA 13104.91643108 | Lateral Hardening-Fuse-91643108 | CKT: 13104 - 91643108 | 2308844 | LUG CSA 13104.91643108 OH | 2308849 | LUG CSA 13104.91643108 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD182 | PRE-09361.353 | LUG CSA 13104.91643108 | Lateral Hardening-Fuse-91643108 | CKT: 13104 - 91643108 | 2308844 | LUG CSA 13104.91643108 OH | 2308849 | LUG CSA 13104.91643108 UG | 13104 | MCFARLAND | CSA | 0.33845 | 33 | 74 | 2021-01-01 | 2021-07-01 | 2021-10-01
Pike | 2021 | 2021 | PRE-09361.354 | LUG CSA 13835.60314670 | Lateral Hardening-Fuse-60314670 | CKT: 13835 - 60314670 | 2308862 | LUG CSA 13835.60314670 OH | 2308867 | LUG CSA 13835.60314670 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD184 | PRE-09361.354 | LUG CSA 13835.60314670 | Lateral Hardening-Fuse-60314670 | CKT: 13835 - 60314670 | 2308862 | LUG CSA 13835.60314670 OH | 2308867 | LUG CSA 13835.60314670 UG | 13835 | FLORIDA AVENUE | CSA | 0.21458 | 18 | 256 | 2021-01-01 | 2021-07-01 | 2021-09-01
Pike | 2021 | 2021 | PRE-09361.355 | LUG CSA 13107.10376186 | Lateral Hardening-Fuse-10376186 | CKT: 13107 - 10376186 | 2308912 | LUG CSA 13107.10376186 OH | 2308914 | LUG CSA 13107.10376186 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD185 | PRE-09361.355 | LUG CSA 13107.10376186 | Lateral Hardening-Fuse-10376186 | CKT: 13107 - 10376186 | 2308912 | LUG CSA 13107.10376186 OH | 2308914 | LUG CSA 13107.10376186 UG | 13107 | MCFARLAND | CSA | 0.12348 | 10 | 179 | 2021-01-01 | 2021-07-01 | 2021-08-01
Pike | 2021 | 2021 | PRE-09361.356 | LUG CSA 13592.91365233 | Lateral Hardening-Fuse-91365233 | CKT: 13592 - 91365233 | 2308917 | LUG CSA 13592.91365233 OH | 2308921 | LUG CSA 13592.91365233 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD186 | PRE-09361.356 | LUG CSA 13592.91365233 | Lateral Hardening-Fuse-91365233 | CKT: 13592 - 91365233 | 2308917 | LUG CSA 13592.91365233 OH | 2308921 | LUG CSA 13592.91365233 UG | 13592 | SENECA STREET | CSA | 0.30777 | 25 | 121 | 2021-02-01 | 2021-07-01 | 2021-09-01
Pike | 2021 | 2021 | PRE-09361.357 | LUG CSA 13993.10372414 | Lateral Hardening-Fuse-10372414 | CKT: 13993 - 10372414 | 2308925 | LUG CSA 13993.10372414 OH | 2308929 | LUG CSA 13993.10372414 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD187 | PRE-09361.357 | LUG CSA 13993.10372414 | Lateral Hardening-Fuse-10372414 | CKT: 13993 - 10372414 | 2308925 | LUG CSA 13993.10372414 OH | 2308929 | LUG CSA 13993.10372414 UG | 13993 | SUNSET LANE | CSA | 0.42367 | 27 | 31 | 2021-03-01 | 2021-07-01 | 2021-10-01
Pike | 2021 | 2021 | PRE-09361.358 | LUG CSA 13354.10582069 | Lateral Hardening-Fuse-10582069 | CKT: 13354 - 10582069 | 2308998 | LUG CSA 13354.10582069 OH | 2308999 | LUG CSA 13354.10582069 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD189 | PRE-09361.358 | LUG CSA 13354.10582069 | Lateral Hardening-Fuse-10582069 | CKT: 13354 - 10582069 | 2308998 | LUG CSA 13354.10582069 OH | 2308999 | LUG CSA 13354.10582069 UG | 13354 | TWENTY SEVENTH STREET | CSA | 0.19205 | 21 | 281 | 2021-03-01 | 2021-10-01 | 2021-12-01
Pike | 2021 | 2021 | PRE-09361.359 | LUG CSA 13468.60128378 | Lateral Hardening-Fuse-60128378 | CKT: 13468 - 60128378 | 2308961 | LUG CSA 13468.60128378 OH | 2308964 | LUG CSA 13468.60128378 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD191 | PRE-09361.359 | LUG CSA 13468.60128378 | Lateral Hardening-Fuse-60128378 | CKT: 13468 - 60128378 | 2308961 | LUG CSA 13468.60128378 OH | 2308964 | LUG CSA 13468.60128378 UG | 13468 | FIFTY SIXTH STREET | CSA | 0.75398 | 56 | 444 | 2021-03-01 | 2021-07-01 | 2021-12-01
Pike | 2021 | 2021 | PRE-09361.360 | LUG CSA 13632.60305848 | Lateral Hardening-Fuse-60305848 | CKT: 13632 - 60305848 | 2308982 | LUG CSA 13632.60305848 OH | 2308983 | LUG CSA 13632.60305848 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD192 | PRE-09361.360 | LUG CSA 13632.60305848 | Lateral Hardening-Fuse-60305848 | CKT: 13632 - 60305848 | 2308982 | LUG CSA 13632.60305848 OH | 2308983 | LUG CSA 13632.60305848 UG | 13632 | PINE LAKE | CSA | 0.40417 | 33 | 43 | 2021-03-01 | 2021-09-01 | 2021-12-01
Pike | 2021 | 2021 | PRE-09361.361 | LUG CSA 13176.10375148 | Lateral Hardening-Fuse-10375148 | CKT: 13176 - 10375148 | 2308967 | LUG CSA 13176.10375148 OH | 2308969 | LUG CSA 13176.10375148 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD194 | PRE-09361.361 | LUG CSA 13176.10375148 | Lateral Hardening-Fuse-10375148 | CKT: 13176 - 10375148 | 2308967 | LUG CSA 13176.10375148 OH | 2308969 | LUG CSA 13176.10375148 UG | 13176 | ELEVENTH AVENUE | CSA | 0.48087 | 54 | 26 | 2021-04-01 | 2021-07-01 | 2021-12-01
Pike | 2021 | 2021 | PRE-09361.362 | LUG CSA 13099.60125388 | Lateral Hardening-Fuse-60125388 | CKT: 13099 - 60125388 | 2309004 | LUG CSA 13099.60125388 OH | 2309005 | LUG CSA 13099.60125388 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD195 | PRE-09361.362 | LUG CSA 13099.60125388 | Lateral Hardening-Fuse-60125388 | CKT: 13099 - 60125388 | 2309004 | LUG CSA 13099.60125388 OH | 2309005 | LUG CSA 13099.60125388 UG | 13099 | SUNSET LANE | CSA | 0.43447 | 24 | 68 | 2021-04-01 | 2021-10-01 | 2021-12-01
Pike | 2021 | 2021 | PRE-09361.363 | LUG CSA 14102.91582612 | Lateral Hardening-Fuse-91582612 | CKT: 14102 - 91582612 | 2309016 | LUG CSA 14102.91582612 OH | 2309017 | LUG CSA 14102.91582612 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD197 | PRE-09361.363 | LUG CSA 14102.91582612 | Lateral Hardening-Fuse-91582612 | CKT: 14102 - 91582612 | 2309016 | LUG CSA 14102.91582612 OH | 2309017 | LUG CSA 14102.91582612 UG | 14102 | CROSS CREEK | CSA | 0.2964 | 18 | 136 | 2021-04-01 | 2021-10-01 | 2021-12-01
Pike | 2021 | 2021 | PRE-09361.364 | LUG CSA 13468.60128362 | Lateral Hardening-Fuse-60128362 | CKT: 13468 - 60128362 | 2308977 | LUG CSA 13468.60128362 OH | 2308979 | LUG CSA 13468.60128362 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD198 | PRE-09361.364 | LUG CSA 13468.60128362 | Lateral Hardening-Fuse-60128362 | CKT: 13468 - 60128362 | 2308977 | LUG CSA 13468.60128362 OH | 2308979 | LUG CSA 13468.60128362 UG | 13468 | FIFTY SIXTH STREET | CSA | 0.53409 | 38 | 147 | 2021-04-01 | 2021-08-01 | 2021-12-01
Pike | 2021 | 2021 | PRE-09361.365 | LUG CSA 13399.60037987 | Lateral Hardening-Fuse-60037987 | CKT: 13399 - 60037987 | 2309031 | LUG CSA 13399.60037987 OH | 2309036 | LUG CSA 13399.60037987 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD199 | PRE-09361.365 | LUG CSA 13399.60037987 | Lateral Hardening-Fuse-60037987 | CKT: 13399 - 60037987 | 2309031 | LUG CSA 13399.60037987 OH | 2309036 | LUG CSA 13399.60037987 UG | 13399 | THIRD AVENUE | CSA | 0.18902 | 19 | 19 | 2021-04-01 | 2021-10-01 | 2021-12-01
Pike | 2021 | 2021 | PRE-09361.394 | LUG CSA 13835.10429505 | Lateral Hardening-Fuse-10429505 | CKT: 13835 - 10429505 | 2310287 | LUG CSA 13835.10429505 OH | 2310291 | LUG CSA 13835.10429505 UG | LUG C068 | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD200 | PRE-09361.366 | DNU LUG CSA 13835.91773975 | Lateral Hardening-Fuse-91773975 | MISSING | MISSING | MISSING | MISSING | MISSING | 13835 | FLORIDA AVENUE | CSA | 0.2714 | 21 | 12 | 2021-04-01 | 2021-10-01 | 2021-12-01 | Combined with PRE-09361.394 (FID 10429505)
Pike | 2021 | 2021 | PRE-09361.367 | LUG CSA 13418.92018190 | Lateral Hardening-Fuse-92018190 | CKT: 13418 - 92018190 | 2309045 | LUG CSA 13418.92018190 OH | 2309046 | LUG CSA 13418.92018190 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD201 | PRE-09361.367 | LUG CSA 13418.92018190 | Lateral Hardening-Fuse-92018190 | CKT: 13418 - 92018190 | 2309045 | LUG CSA 13418.92018190 OH | 2309046 | LUG CSA 13418.92018190 UG | 13418 | JUNEAU | CSA | 0.32898 | 21 | 79 | 2021-04-01 | 2021-10-01 | 2021-12-01
Pike | 2021 | 2021 | PRE-09361.368 | LUG CSA 13105.10580690 | Lateral Hardening-Fuse-10580690 | CKT: 13105 - 10580690 | 2309047 | LUG CSA 13105.10580690 OH | 2309048 | LUG CSA 13105.10580690 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD203 | PRE-09361.368 | LUG CSA 13105.10580690 | Lateral Hardening-Fuse-10580690 | CKT: 13105 - 10580690 | 2309047 | LUG CSA 13105.10580690 OH | 2309048 | LUG CSA 13105.10580690 UG | 13105 | MCFARLAND | CSA | 0.23314 | 21 | 122 | 2021-05-01 | 2021-10-01 | 2021-12-01
Pike | 2021 | 2021 | PRE-09361.369 | LUG CSA 13205.90022802 | Lateral Hardening-Fuse-90022802 | CKT: 13205 - 90022802 | 2309279 | LUG CSA 13205.90022802 OH | 2309281 | LUG CSA 13205.90022802 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD204 | PRE-09361.369 | LUG CSA 13205.90022802 | Lateral Hardening-Fuse-90022802 | CKT: 13205 - 90022802 | 2309279 | LUG CSA 13205.90022802 OH | 2309281 | LUG CSA 13205.90022802 UG | 13205 | TEMPLE TERRACE | CSA | 0.20152 | 18 | 20 | 2021-05-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.370 | LUG CSA 13418.91924595 | Lateral Hardening-Fuse-91924595 | CKT: 13418 - 91924595 | 2309285 | LUG CSA 13418.91924595 OH | 2309295 | LUG CSA 13418.91924595 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD205 | PRE-09361.370 | LUG CSA 13418.91924595 | Lateral Hardening-Fuse-91924595 | CKT: 13418 - 91924595 | 2309285 | LUG CSA 13418.91924595 OH | 2309295 | LUG CSA 13418.91924595 UG | 13418 | JUNEAU | CSA | 0.21515 | 20 | 25 | 2021-06-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.371 | LUG CSA 13105.60164901 | Lateral Hardening-Fuse-60164901 | CKT: 13105 - 60164901 | 2309300 | LUG CSA 13105.60164901 OH | 2309301 | LUG CSA 13105.60164901 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD206 | PRE-09361.371 | LUG CSA 13105.60164901 | Lateral Hardening-Fuse-60164901 | CKT: 13105 - 60164901 | 2309300 | LUG CSA 13105.60164901 OH | 2309301 | LUG CSA 13105.60164901 UG | 13105 | MCFARLAND | CSA | 0.11439 | 10 | 79 | 2021-06-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.372 | LUG CSA 13934.10467597 | Lateral Hardening-Fuse-10467597 | CKT: 13934 - 10467597 | 2309304 | LUG CSA 13934.10467597 OH | 2309305 | LUG CSA 13934.10467597 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD207 | PRE-09361.372 | LUG CSA 13934.10467597 | Lateral Hardening-Fuse-10467597 | CKT: 13934 - 10467597 | 2309304 | LUG CSA 13934.10467597 OH | 2309305 | LUG CSA 13934.10467597 UG | 13934 | LAKE MAGDALENE | CSA | 0.55871 | 30 | 51 | 2021-06-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.373 | LUG CSA 13205.90442230 | Lateral Hardening-Fuse-90442230 | CKT: 13205 - 90442230 | 2309348 | LUG CSA 13205.90442230 OH | 2309349 | LUG CSA 13205.90442230 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD208 | PRE-09361.373 | LUG CSA 13205.90442230 | Lateral Hardening-Fuse-90442230 | CKT: 13205 - 90442230 | 2309348 | LUG CSA 13205.90442230 OH | 2309349 | LUG CSA 13205.90442230 UG | 13205 | TEMPLE TERRACE | CSA | 0.2517 | 25 | 60 | 2021-06-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.374 | LUG CSA 14040.10786358 | Lateral Hardening-Fuse-10786358 | CKT: 14040 - 10786358 | 2309351 | LUG CSA 14040.10786358 OH | 2309353 | LUG CSA 14040.10786358 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD210 | PRE-09361.374 | LUG CSA 14040.10786358 | Lateral Hardening-Fuse-10786358 | CKT: 14040 - 10786358 | 2309351 | LUG CSA 14040.10786358 OH | 2309353 | LUG CSA 14040.10786358 UG | 14040 | HARNEY ROAD | CSA | 0.42727 | 19 | 12 | 2021-06-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.375 | LUG CSA 13105.10580689 | Lateral Hardening-Fuse-10580689 | CKT: 13105 - 10580689 | 2309355 | LUG CSA 13105.10580689 OH | 2309356 | LUG CSA 13105.10580689 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD212 | PRE-09361.375 | LUG CSA 13105.10580689 | Lateral Hardening-Fuse-10580689 | CKT: 13105 - 10580689 | 2309355 | LUG CSA 13105.10580689 OH | 2309356 | LUG CSA 13105.10580689 UG | 13105 | MCFARLAND | CSA | 0.12765 | 10 | 44 | 2021-06-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.376 | LUG CSA 13107.10376201 | Lateral Hardening-Fuse-10376201 | CKT: 13107 - 10376201 | 2309358 | LUG CSA 13107.10376201 OH | 2309359 | LUG CSA 13107.10376201 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD213 | PRE-09361.376 | LUG CSA 13107.10376201 | Lateral Hardening-Fuse-10376201 | CKT: 13107 - 10376201 | 2309358 | LUG CSA 13107.10376201 OH | 2309359 | LUG CSA 13107.10376201 UG | 13107 | MCFARLAND | CSA | 0.13485 | 10 | 8 | 2021-06-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.377 | LUG CSA 13105.10580676 | Lateral Hardening-Fuse-10580676 | CKT: 13105 - 10580676 | 2309367 | LUG CSA 13105.10580676 OH | 2309368 | LUG CSA 13105.10580676 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD215 | PRE-09361.377 | LUG CSA 13105.10580676 | Lateral Hardening-Fuse-10580676 | CKT: 13105 - 10580676 | 2309367 | LUG CSA 13105.10580676 OH | 2309368 | LUG CSA 13105.10580676 UG | 13105 | MCFARLAND | CSA | 0.13239 | 13 | 14 | 2021-06-01 | 2022 | 2022 | Pike to ensure WR's listed on Melody's list aren't used (2311967 & 2311968)
Pike | 2020 | 2021 | PRE-09361.92 | LUG CSA 13100.91340554 | Lateral Hardening-Fuse-91340554 | CKT: 13100 - 91340554 | 2275159 | LUG CSA 13100.91340554 OH | 2275160 | LUG CSA 13100.91340554 UG | LUG C016 | 4500276922 | N/A | TBD | 2021 | LUG - TBD217 | PRE-09361.378 | DNU LUG CSA 13100.10371697 | DNU Lateral Hardening-Fuse-10371697 | N/A | N/A | N/A | N/A | N/A | 13100 | YUKON | CSA | 0.38409 | 32 | 114 | 2021-07-01 | 2022 | 2022 | Combined with PRE-09361.92 (FID 91340554) & LUG-TBD188 (FID 10371703); originally not included as part of LUG C016
Pike | 2021 | 2021 | PRE-09361.379 | LUG CSA 13993.10433144 | Lateral Hardening-Fuse-10433144 | CKT: 13993 - 10433144 | 2309369 | LUG CSA 13993.10433144 OH | 2309370 | LUG CSA 13993.10433144 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD218 | PRE-09361.379 | LUG CSA 13993.10433144 | Lateral Hardening-Fuse-10433144 | CKT: 13993 - 10433144 | 2309369 | LUG CSA 13993.10433144 OH | 2309370 | LUG CSA 13993.10433144 UG | 13993 | SUNSET LANE | CSA | 0.11913 | 10 | 123 | 2021-07-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.380 | LUG CSA 13939.60144172 | Lateral Hardening-Fuse-60144172 | CKT: 13939 - 60144172 | 2309371 | LUG CSA 13939.60144172 OH | 2309372 | LUG CSA 13939.60144172 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD219 | PRE-09361.380 | LUG CSA 13939.60144172 | Lateral Hardening-Fuse-60144172 | CKT: 13939 - 60144172 | 2309371 | LUG CSA 13939.60144172 OH | 2309372 | LUG CSA 13939.60144172 UG | 13939 | LAKE MAGDALENE | CSA | 0.14943 | 15 | 2 | 2021-07-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.381 | LUG CSA 13158.91461782 | Lateral Hardening-Fuse-91461782 | CKT: 13158 - 91461782 | 2309376 | LUG CSA 13158.91461782 OH | 2309377 | LUG CSA 13158.91461782 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD220 | PRE-09361.381 | LUG CSA 13158.91461782 | Lateral Hardening-Fuse-91461782 | CKT: 13158 - 91461782 | 2309376 | LUG CSA 13158.91461782 OH | 2309377 | LUG CSA 13158.91461782 UG | 13158 | THIRTIETH STREET | CSA | 0.33428 | 30 | 39 | 2021-07-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.382 | LUG CSA 13633.91847345 | Lateral Hardening-Fuse-91847345 | CKT: 13633 - 91847345 | 2309380 | LUG CSA 13633.91847345 OH | 2309382 | LUG CSA 13633.91847345 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD221 | PRE-09361.382 | LUG CSA 13633.91847345 | Lateral Hardening-Fuse-91847345 | CKT: 13633 - 91847345 | 2309380 | LUG CSA 13633.91847345 OH | 2309382 | LUG CSA 13633.91847345 UG | 13633 | PINE LAKE | CSA | 0.086174 | 7 | 1 | 2021-07-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.383 | LUG CSA 13934.10467575 | Lateral Hardening-Fuse-10467575 | CKT: 13934 - 10467575 | 2309573 | LUG CSA 13934.10467575 OH | 2309574 | LUG CSA 13934.10467575 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD222 | PRE-09361.383 | LUG CSA 13934.10467575 | Lateral Hardening-Fuse-10467575 | CKT: 13934 - 10467575 | 2309573 | LUG CSA 13934.10467575 OH | 2309574 | LUG CSA 13934.10467575 UG | 13934 | LAKE MAGDALENE | CSA | 0.091288 | 6 | 1 | 2021-07-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.384 | LUG CSA 13188.92070695 | Lateral Hardening-Fuse-92070695 | CKT: 13188 - 92070695 | 2309575 | LUG CSA 13188.92070695 OH | 2309576 | LUG CSA 13188.92070695 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD223 | PRE-09361.384 | LUG CSA 13188.92070695 | Lateral Hardening-Fuse-92070695 | CKT: 13188 - 92070695 | 2309575 | LUG CSA 13188.92070695 OH | 2309576 | LUG CSA 13188.92070695 UG | 13188 | PINE LAKE | CSA | 0.1697 | 11 | 17 | 2021-07-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.385 | LUG CSA 13948.10442391 | Lateral Hardening-Fuse-10442391 | CKT: 13948 - 10442391 | 2309577 | LUG CSA 13948.10442391 OH | 2309578 | LUG CSA 13948.10442391 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD225 | PRE-09361.385 | LUG CSA 13948.10442391 | Lateral Hardening-Fuse-10442391 | CKT: 13948 - 10442391 | 2309577 | LUG CSA 13948.10442391 OH | 2309578 | LUG CSA 13948.10442391 UG | 13948 | JUNEAU | CSA | 0.21534 | 19 | 34 | 2021-07-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.386 | HOLD LUG CSA 13158.92347931 | Lateral Hardening-Fuse-92347931 | CKT: 13158 - 92347931 | 2309580 | HOLD LUG CSA 13158.92347931 OH | 2309581 | HOLD LUG CSA 13158.92347931 UG | HOLD | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD227 | PRE-09361.386 | LUG CSA 13158.92347931 | Lateral Hardening-Fuse-92347931 | CKT: 13158 - 92347931 | 2309580 | LUG CSA 13158.92347931 OH | 2309581 | LUG CSA 13158.92347931 UG | 13158 | THIRTIETH STREET | CSA | 0.29242 | 29 |  | 2021-07-01 | 2022 | 2022 | Placed On Hold, per Jason Blackwell, on 5/24/2021
Pike | 2021 | 2021 | PRE-09361.387 | LUG DCA 13006.92949400 | Lateral Hardening-Fuse-92949400 | CKT: 13006 - 92949400 | 2309584 | LUG DCA 13006.92949400 OH | 2309586 | LUG DCA 13006.92949400 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD229 | PRE-09361.387 | LUG DCA 13006.92949400 | Lateral Hardening-Fuse-92949400 | CKT: 13006 - 92949400 | 2309584 | LUG DCA 13006.92949400 OH | 2309586 | LUG DCA 13006.92949400 UG | 13006 | FORT KING HIGHWAY | DCA | 1.2864 | 48 | 41 | 2021-07-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.388 | LUG DCA 13432.10761257 | Lateral Hardening-Fuse-10761257 | CKT: 13432 - 10761257 | 2309582 | LUG DCA 13432.10761257 OH | 2309583 | LUG DCA 13432.10761257 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD230 | PRE-09361.388 | LUG DCA 13432.10761257 | Lateral Hardening-Fuse-10761257 | CKT: 13432 - 10761257 | 2309582 | LUG DCA 13432.10761257 OH | 2309583 | LUG DCA 13432.10761257 UG | 13432 | SAN ANTONIO | DCA | 1.2106 | 38 | 21 | 2021-08-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.389 | LUG CSA 13826.60127680 | Lateral Hardening-Fuse-60127680 | CKT: 13826 - 60127680 | 2309587 | LUG CSA 13826.60127680 OH | 2309589 | LUG CSA 13826.60127680 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD231 | PRE-09361.389 | LUG CSA 13826.60127680 | Lateral Hardening-Fuse-60127680 | CKT: 13826 - 60127680 | 2309587 | LUG CSA 13826.60127680 OH | 2309589 | LUG CSA 13826.60127680 UG | 13826 | FOWLER AVENUE | CSA | 0.2733 | 13 | 243 | 2021-08-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.390 | LUG CSA 13632.10408290 | Lateral Hardening-Fuse-10408290 | CKT: 13632 - 10408290 | 2310269 | LUG CSA 13632.10408290 OH | 2310270 | LUG CSA 13632.10408290 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD232 | PRE-09361.390 | LUG CSA 13632.10408290 | Lateral Hardening-Fuse-10408290 | CKT: 13632 - 10408290 | 2310269 | LUG CSA 13632.10408290 OH | 2310270 | LUG CSA 13632.10408290 UG | 13632 | PINE LAKE | CSA | 1.0176 | 55 | 245 | 2021-09-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.391 | LUG CSA 13204.60170504 | Lateral Hardening-Fuse-60170504 | CKT: 13204 - 60170504 | 2310274 | LUG CSA 13204.60170504 OH | 2310275 | LUG CSA 13204.60170504 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD233 | PRE-09361.391 | LUG CSA 13204.60170504 | Lateral Hardening-Fuse-60170504 | CKT: 13204 - 60170504 | 2310274 | LUG CSA 13204.60170504 OH | 2310275 | LUG CSA 13204.60170504 UG | 13204 | TEMPLE TERRACE | CSA | 0.37992 | 31 | 113 | 2021-09-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.392 | LUG CSA 13176.10375141 | Lateral Hardening-Fuse-10375141 | CKT: 13176 - 10375141 | 2310278 | LUG CSA 13176.10375141 OH | 2310283 | LUG CSA 13176.10375141 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD234 | PRE-09361.392 | LUG CSA 13176.10375141 | Lateral Hardening-Fuse-10375141 | CKT: 13176 - 10375141 | 2310278 | LUG CSA 13176.10375141 OH | 2310283 | LUG CSA 13176.10375141 UG | 13176 | ELEVENTH AVENUE | CSA | 0.62348 | 51 | 89 | 2021-09-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.393 | LUG CSA 13948.10442379 | Lateral Hardening-Fuse-10442379 | CKT: 13948 - 10442379 | 2310284 | LUG CSA 13948.10442379 OH | 2310286 | LUG CSA 13948.10442379 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD235 | PRE-09361.393 | LUG CSA 13948.10442379 | Lateral Hardening-Fuse-10442379 | CKT: 13948 - 10442379 | 2310284 | LUG CSA 13948.10442379 OH | 2310286 | LUG CSA 13948.10442379 UG | 13948 | YUKON | CSA | 0.13788 | 12 | 5 | 2021-09-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.394 | LUG CSA 13835.10429505 | Lateral Hardening-Fuse-10429505 | CKT: 13835 - 10429505 | 2310287 | LUG CSA 13835.10429505 OH | 2310291 | LUG CSA 13835.10429505 UG | LUG C068 | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD236 | PRE-09361.394 | LUG CSA 13835.10429505 | Lateral Hardening-Fuse-10429505 | CKT: 13835 - 10429505 | 2310287 | LUG CSA 13835.10429505 OH | 2310291 | LUG CSA 13835.10429505 UG | 13835 | FLORIDA AVENUE | CSA | 0.20303 | 17 | 41 | 2021-09-01 | 2022 | 2022 | Combined with PRE-09361.366 (FID 91773975)
Pike | 2021 | 2021 | PRE-09361.395 | LUG CSA 13026.60059509 | Lateral Hardening-Fuse-60059509 | CKT: 13026 - 60059509 | 2310293 | LUG CSA 13026.60059509 OH | 2310296 | LUG CSA 13026.60059509 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD237 | PRE-09361.395 | LUG CSA 13026.60059509 | Lateral Hardening-Fuse-60059509 | CKT: 13026 - 60059509 | 2310293 | LUG CSA 13026.60059509 OH | 2310296 | LUG CSA 13026.60059509 UG | 13026 | TEMPLE TERRACE | CSA | 0.085795 | 8 | 84 | 2021-09-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.396 | LUG CSA 13021.92350282 | Lateral Hardening-Fuse-92350282 | CKT: 13021 - 92350282 | 2310299 | LUG CSA 13021.92350282 OH | 2310300 | LUG CSA 13021.92350282 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD238 | PRE-09361.396 | LUG CSA 13021.92350282 | Lateral Hardening-Fuse-92350282 | CKT: 13021 - 92350282 | 2310299 | LUG CSA 13021.92350282 OH | 2310300 | LUG CSA 13021.92350282 UG | 13021 | JUNEAU | CSA | 0.3178 | 27 | 14 | 2021-09-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.397 | LUG CSA 13468.91640192 | Lateral Hardening-Fuse-91640192 | CKT: 13468 - 91640192 | 2310304 | LUG CSA 13468.91640192 OH | 2310305 | LUG CSA 13468.91640192 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD240 | PRE-09361.397 | LUG CSA 13468.91640192 | Lateral Hardening-Fuse-91640192 | CKT: 13468 - 91640192 | 2310304 | LUG CSA 13468.91640192 OH | 2310305 | LUG CSA 13468.91640192 UG | 13468 | FIFTY SIXTH STREET | CSA | 0.10682 | 7 | 6 | 2021-09-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.398 | LUG CSA 13106.91722510 | Lateral Hardening-Fuse-91722510 | CKT: 13106 - 91722510 | 2310323 | LUG CSA 13106.91722510 OH | 2310324 | LUG CSA 13106.91722510 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD241 | PRE-09361.398 | LUG CSA 13106.91722510 | Lateral Hardening-Fuse-91722510 | CKT: 13106 - 91722510 | 2310323 | LUG CSA 13106.91722510 OH | 2310324 | LUG CSA 13106.91722510 UG | 13106 | MCFARLAND | CSA | 0.10852 | 9 | 166 | 2021-10-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.399 | LUG CSA 13026.60059452 | Lateral Hardening-Fuse-60059452 | CKT: 13026 - 60059452 | 2310327 | LUG CSA 13026.60059452 OH | 2310330 | LUG CSA 13026.60059452 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD242 | PRE-09361.399 | LUG CSA 13026.60059452 | Lateral Hardening-Fuse-60059452 | CKT: 13026 - 60059452 | 2310327 | LUG CSA 13026.60059452 OH | 2310330 | LUG CSA 13026.60059452 UG | 13026 | TEMPLE TERRACE | CSA | 0.16383 | 11 | 64 | 2021-10-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.400 | LUG CSA 13632.10408272 | Lateral Hardening-Fuse-10408272 | CKT: 13632 - 10408272 | 2310332 | LUG CSA 13632.10408272 OH | 2310334 | LUG CSA 13632.10408272 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD243 | PRE-09361.400 | LUG CSA 13632.10408272 | Lateral Hardening-Fuse-10408272 | CKT: 13632 - 10408272 | 2310332 | LUG CSA 13632.10408272 OH | 2310334 | LUG CSA 13632.10408272 UG | 13632 | PINE LAKE | CSA | 0.097727 | 9 | 12 | 2021-11-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.401 | LUG CSA 13026.60059457 | Lateral Hardening-Fuse-60059457 | CKT: 13026 - 60059457 | 2310335 | LUG CSA 13026.60059457 OH | 2310336 | LUG CSA 13026.60059457 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD247 | PRE-09361.401 | LUG CSA 13026.60059457 | Lateral Hardening-Fuse-60059457 | CKT: 13026 - 60059457 | 2310335 | LUG CSA 13026.60059457 OH | 2310336 | LUG CSA 13026.60059457 UG | 13026 | TEMPLE TERRACE | CSA | 0.20814 | 15 | 24 | 2021-10-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.402 | LUG CSA 13099.10368943 | Lateral Hardening-Fuse-10368943 | CKT: 13099 - 10368943 | 2310338 | LUG CSA 13099.10368943 OH | 2310340 | LUG CSA 13099.10368943 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD248 | PRE-09361.402 | LUG CSA 13099.10368943 | Lateral Hardening-Fuse-10368943 | CKT: 13099 - 10368943 | 2310338 | LUG CSA 13099.10368943 OH | 2310340 | LUG CSA 13099.10368943 UG | 13099 | SUNSET LANE | CSA | 0.24242 | 13 | 2 | 2021-10-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.403 | LUG CSA 13104.91668251 | Lateral Hardening-Fuse-91668251 | CKT: 13104 - 91668251 | 2310343 | LUG CSA 13104.91668251 OH | 2310345 | LUG CSA 13104.91668251 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD249 | PRE-09361.403 | LUG CSA 13104.91668251 | Lateral Hardening-Fuse-91668251 | CKT: 13104 - 91668251 | 2310343 | LUG CSA 13104.91668251 OH | 2310345 | LUG CSA 13104.91668251 UG | 13104 | MCFARLAND | CSA | 0.20265 | 17 | 16 | 2021-10-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.405 | LUG CSA 13104.91241032 | Lateral Hardening-Fuse-91241032 | CKT: 13104 - 91241032 | 2310351 | LUG CSA 13104.91241032 OH | 2310353 | LUG CSA 13104.91241032 UG |  | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD252 | PRE-09361.405 | LUG CSA 13104.91241032 | Lateral Hardening-Fuse-91241032 | CKT: 13104 - 91241032 | 2310351 | LUG CSA 13104.91241032 OH | 2310353 | LUG CSA 13104.91241032 UG | 13104 | MCFARLAND | CSA | 0.15038 | 18 | 19 | 2021-11-01 | 2022 | 2022
Pike | 2021 | 2021 | PRE-09361.476 | LUG CSA 13104.10362869 | Lateral Hardening-Fuse-10362869 | CKT: 13104 - 10362869 | 2311870 | LUG CSA 13104.10362869 OH | 2311875 | LUG CSA 13104.10362869 UG | LUG C037 | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD175 | PRE-09361.476 | LUG CSA 13104.10362869 | Lateral Hardening-Fuse-10362869 | CKT: 13104 - 10362869 | 2311870 | LUG CSA 13104.10362869 OH | 2311875 | LUG CSA 13104.10362869 UG | 13104 | MCFARLAND | CSA | 0.3803 | 30 | 67 | 2021-01-01 | 2021-06-01 | 2021-09-01 | Combined with LUG - TBD193 (FID 10362882)
Pike | 2021 | 2021 | PRE-09361.476 | LUG CSA 13104.10362869 | Lateral Hardening-Fuse-10362869 | CKT: 13104 - 10362869 | 2311870 | LUG CSA 13104.10362869 OH | 2311875 | LUG CSA 13104.10362869 UG | LUG C037 | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD193 | PRE-09361.476 | DNU LUG CSA 13104.10362882 | DNU Lateral Hardening-Fuse-10362882 | N/A | N/A | N/A | N/A | N/A | 13104 | MCFARLAND | CSA | 0.11572 | 8 | 26 | 2021-04-01 | 2021-10-01 | 2021-12-01 | Combined with LUG - TBD175/PRE-09361.476 (FID 10362869)
Pike | 2021 | 2021 | PRE-09361.477 | LUG CSA 13158.90816343 | Lateral Hardening-Fuse-90816343 | CKT: 13158 - 90816343 | 2311878 | LUG CSA 13158.90816343 OH | 2311879 | LUG CSA 13158.90816343 UG | LUG C038 | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD179 | PRE-09361.477 | LUG CSA 13158.90816343 | Lateral Hardening-Fuse-90816343 | CKT: 13158 - 90816343 | 2311878 | LUG CSA 13158.90816343 OH | 2311879 | LUG CSA 13158.90816343 UG | 13158 | THIRTIETH STREET | CSA | 0.25019 | 18 | 123 | 2021-01-01 | 2021-07-01 | 2021-09-01 | Combined with LUG - TBD181 (FID 93317809)
Pike | 2021 | 2021 | PRE-09361.477 | LUG CSA 13158.90816343 | Lateral Hardening-Fuse-90816343 | CKT: 13158 - 90816343 | 2311878 | LUG CSA 13158.90816343 OH | 2311879 | LUG CSA 13158.90816343 UG | LUG C038 | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD181 | PRE-09361.477 | DNU LUG CSA 13158.93317809 | DNU Lateral Hardening-Fuse-93317809 | N/A | N/A | N/A | N/A | N/A | 13158 | THIRTIETH STREET | CSA | 0.16534 | 13 | 60 | 2021-01-01 | 2021-07-01 | 2021-09-01 | Combined with LUG - TBD179/PRE-09361.477 (FID 90816343)
Pike | 2021 | 2021 | PRE-09361.478 | LUG CSA 13158.60011810 | Lateral Hardening-Fuse-60011810 | CKT : 13158 - 60011810 | 2311887 | LUG CSA 13158.60011810 OH | 2311889 | LUG CSA 13158.60011810 UG | LUG C041 | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD202 | PRE-09361.478 | LUG CSA 13158.60011810 | Lateral Hardening-Fuse-60011810 | CKT : 13158 - 60011810 | 2311887 | LUG CSA 13158.60011810 OH | 2311889 | LUG CSA 13158.60011810 UG | 13158 | THIRTIETH STREET | CSA | 0.75795 | 56 | 226 | 2021-03-01 | 2021-07-01 | 2021-12-01 | Combined with LUG - TBD209 (FID 92290015)
Pike | 2021 | 2021 | PRE-09361.478 | LUG CSA 13158.60011810 | Lateral Hardening-Fuse-60011810 | CKT : 13158 - 60011810 | 2311887 | LUG CSA 13158.60011810 OH | 2311889 | LUG CSA 13158.60011810 UG | LUG C041 | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD209 | PRE-09361.478 | DNU LUG CSA 13158.92290015 | DNU Lateral Hardening-Fuse-92290015 | N/A | N/A | N/A | N/A | N/A | 13158 | THIRTIETH STREET | CSA | 0.0625 | 7 | 101 | 2021-06-01 | 2022 | 2022 | Combined with LUG - TBD202/PRE-09361.478 (FID 60011810)
Pike | 2021 | 2021 | PRE-09361.479 | LUG CSA 13633.90564142 | Lateral Hardening-Fuse-90564142 | CKT : 13633 - 90564142 | 2311932 | LUG CSA 13633.90564142 OH | 2311937 | LUG CSA 13633.90564142 UG | LUG C042 | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD214 | PRE-09361.479 | DNU LUG CSA 13633.90633859 | DNU Lateral Hardening-Fuse-90633859 | DNU CKT : 13633 - 90633859 | 2311932 | DNU LUG CSA 13633.90633859 OH | 2311937 | DNU LUG CSA 13633.90633859 UG | 13633 | PINE LAKE | CSA | 0.18087 | 6 | 11 | 2021-06-01 | 2022 | 2022 | Combined with LUG - TBD228/PRE-09361.479 (FID 90564142); incorrectly opened in WP with 13633.90633859
Pike | 2021 | 2021 | PRE-09361.479 | LUG CSA 13633.90564142 | Lateral Hardening-Fuse-90564142 | CKT : 13633 - 90564142 | 2311932 | LUG CSA 13633.90564142 OH | 2311937 | LUG CSA 13633.90564142 UG | LUG C042 | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD228 | PRE-09361.479 | LUG CSA 13633.90564142 | Lateral Hardening-Fuse-90564142 | DNU CKT : 13633 - 90633859 | 2311932 | DNU LUG CSA 13633.90633859 OH | 2311937 | DNU LUG CSA 13633.90633859 UG | 13633 | PINE LAKE | CSA | 0.073106 | 3 | 2 | 2021-08-01 | 2022 | 2022 | Combined with LUG - TBD214 (FID 90633859); incorrectly opened in WP with 13633.90633859
Pike | 2021 | 2021 | PRE-09361.480 | LUG CSA 13106.10361901 | Lateral Hardening-Fuse-10361901 | CKT : 13106 - 10361901 | 2311881 | LUG CSA 13106.10361901 OH | 2311882 | LUG CSA 13106.10361901 UG | LUG C039 | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD183 | PRE-09361.480 | DNU LUG CSA 13106.91795934 | DNU Lateral Hardening-Fuse-91795934 | DNU CKT : 13106 - 91795934 | 2311881 | LUG CSA 13106.91795934 OH | 2311882 | LUG CSA 13106.91795934 UG | 13106 | MCFARLAND | CSA | 0.77973 | 55 | 314 | 2021-01-01 | 2021-07-01 | 2021-10-01 | Combined with LUG - TBD239/PRE-09361.480 (FID 10361901); incorrectly opened in WP with description & street name for 13106.91795934
Pike | 2021 | 2021 | PRE-09361.480 | LUG CSA 13106.10361901 | Lateral Hardening-Fuse-10361901 | CKT : 13106 - 10361901 | 2311881 | LUG CSA 13106.10361901 OH | 2311882 | LUG CSA 13106.10361901 UG | LUG C039 | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD239 | PRE-09361.480 | LUG CSA 13106.10361901 | Lateral Hardening-Fuse-10361901 | DNU CKT : 13106 - 91795934 | 2311881 | LUG CSA 13106.91795934 OH | 2311882 | LUG CSA 13106.91795934 UG | 13106 | MCFARLAND | CSA | 0.74848 | 52 | 274 | 2021-09-01 | 2022 | 2022 | Combined with LUG - TBD183 (FID 91795934); incorrectly opened in WP with description & street name for 13106.91795934
Pike | 2021 | 2021 | PRE-09361.481 | LUG CSA 13102.90748252 | Lateral Hardening-Fuse-90748252 | CKT : 13102 - 90748252 | 2311918 | LUG CSA 13102.90748252 OH | 2311920 | LUG CSA 13102.90748252 UG | LUG C040 | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD196 | PRE-09361.481 | DNU LUG CSA 13102.60123660 | DNU Lateral Hardening-Fuse-60123660 | DNU CKT : 13102 - 60123660 | 2311918 | LUG CSA 13102.60123660 OH | 2311920 | LUG CSA 13102.60123660 UG | 13102 | YUKON | CSA | 0.15795 | 6 | 36 | 2021-04-01 | 2021-10-01 | 2021-12-01 | Combined with LUG - TBD244/PRE-09361.481 (FID 90748252); incorrectly opened in WP with description & street name for 13106.60123660
Pike | 2021 | 2021 | PRE-09361.481 | LUG CSA 13102.90748252 | Lateral Hardening-Fuse-90748252 | CKT : 13102 - 90748252 | 2311918 | LUG CSA 13102.90748252 OH | 2311920 | LUG CSA 13102.90748252 UG | LUG C040 | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD244 | PRE-09361.481 | LUG CSA 13102.90748252 | Lateral Hardening-Fuse-90748252 | DNU CKT : 13102 - 60123660 | 2311918 | LUG CSA 13102.60123660 OH | 2311920 | LUG CSA 13102.60123660 UG | 13102 | YUKON | CSA | 0.23333 | 23 | 29 | 2021-10-01 | 2022 | 2022 | Combined with LUG - TBD196 (FID 60123660); incorrectly opened in WP with description & street name for 13106.60123660
Pike | 2021 | 2021 | PRE-09361.482 | LUG CSA 13176.10375136 | Lateral Hardening-Fuse-10375136 | CKT: 13176 - 10375136 | 2311474 | LUG CSA 13176.10375136 OH | 2311477 | LUG CSA 13176.10375136 UG | U - LUG C015 | N/A | 4500282886 | 4500291221 | 2021 | LUG - TBD251 | PRE-09361.482 | LUG CSA 13176.10375136 | Lateral Hardening-Fuse-10375136 | CKT: 13176 - 10375136 | 2311474 | LUG CSA 13176.10375136 OH | 2311477 | LUG CSA 13176.10375136 UG | 13176 | ELEVENTH AVENUE | CSA | 0.65701 | 57 | 11 | 2021-09-01 | 2022 | 2022 | Originally combined with PRE-09361.87 (FID 10375134), but now uncombined
Pike | 2020 | 2020 | PRE-09361.75 | LUG CSA 13633.92740152 | Lateral Hardening-Fuse-92740152 | CKT: 13633 - 92740152 | 2274995 | LUG CSA 13633.92740152 OH | 2274996 | LUG CSA 13633.92740152 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD140 | PRE-09361.75 | LUG CSA 13633.92740152 | Lateral Hardening-Fuse-92740152 | CKT: 13633 - 92740152 | 2274995 | LUG CSA 13633.92740152 OH | 2274996 | LUG CSA 13633.92740152 UG | 13633 | PINE LAKE | CSA | 0.27973 | 23 | 52 | 2020-08-01 | 2021-01-01 | 2021-03-01
Pike | 2020 | 2020 | PRE-09361.76 | LUG CSA 13592.10402239 | Lateral Hardening-Fuse-10402239 | CKT: 13592 - 10402239 | 2275090 | LUG CSA 13592.10402239 OH | 2275091 | LUG CSA 13592.10402239 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD141 | PRE-09361.76 | LUG CSA 13592.10402239 | Lateral Hardening-Fuse-10402239 | CKT: 13592 - 10402239 | 2275090 | LUG CSA 13592.10402239 OH | 2275091 | LUG CSA 13592.10402239 UG | 13592 | SENECA STREET | CSA | 0.16477 | 15 | 57 | 2020-08-01 | 2021-01-01 | 2021-03-01
Pike | 2020 | 2020 | PRE-09361.77 | LUG CSA 13351.93283733 | Lateral Hardening-Fuse-93283733 | CKT: 13351 - 93283733 | 2275110 | LUG CSA 13351.93283733 OH | 2275114 | LUG CSA 13351.93283733 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD142 | PRE-09361.77 | LUG CSA 13351.93283733 | Lateral Hardening-Fuse-93283733 | CKT: 13351 - 93283733 | 2275110 | LUG CSA 13351.93283733 OH | 2275114 | LUG CSA 13351.93283733 UG | 13351 | TWENTY SEVENTH STREET | CSA | 0.17841 | 15 | 66 | 2020-08-01 | 2021-01-01 | 2021-03-01
Pike | 2020 | 2021 | PRE-09361.78 | LUG CSA 13099.90882614 | Lateral Hardening-Fuse-90882614 | CKT: 13099 - 90882614 | 2275116 | LUG CSA 13099.90882614 OH | 2275117 | LUG CSA 13099.90882614 UG | LUG C008 | 4500276922 | N/A | N/A | 2021 | LUG - TBD172 | PRE-09361.78 | DNU LUG CSA 13099.60563698 | DNU Lateral Hardening-Fuse-60563698 | N/A | N/A | N/A | N/A | N/A | 13099 | SUNSET LANE | CSA | 0.38144 | 23 | 8 | 2021-01-01 | 2021-05-01 | 2021-07-01 | Combined with PRE-09361.78 (FID 90882614)
Pike | 2020 | 2020 | PRE-09361.78 | LUG CSA 13099.90882614 | Lateral Hardening-Fuse-90882614 | CKT: 13099 - 90882614 | 2275116 | LUG CSA 13099.90882614 OH | 2275117 | LUG CSA 13099.90882614 UG | LUG C008 | 4500276922 | N/A | N/A | 2020 | LUG - TBD143 | PRE-09361.78 | LUG CSA 13099.90882614 | Lateral Hardening-Fuse-90882614 | CKT: 13099 - 90882614 | 2275116 | LUG CSA 13099.90882614 OH | 2275117 | LUG CSA 13099.90882614 UG | 13099 | SUNSET LANE | CSA | 0.23731 | 18 | 128 | 2020-09-01 | 2021-01-01 | 2021-03-01 | Combined with LUG-TBD172 (FID 60563698)
Pike | 2020 | 2021 | PRE-09361.79 | LUG CSA 13093.91004837 | Lateral Hardening-Fuse-91004837 | CKT: 13093 - 91004837 | 2275118 | LUG CSA 13093.91004837 OH | 2275120 | LUG CSA 13093.91004837 UG | LUG C009 | 4500276922 | N/A | N/A | 2021 | LUG - TBD245 | PRE-09361.79 | DNU LUG CSA 13093.60029740 | DNU Lateral Hardening-Fuse-60029740 | N/A | N/A | N/A | N/A | N/A | 13093 | PLYMOUTH STREET | CSA | 0.29716 | 24 | 65 | 2021-10-01 | 2022 | 2022 | Combined with PRE-09361.79 (FID 91004837) & PRE-09361.83 (FID 91004843)
Pike | 2020 | 2020 | PRE-09361.79 | LUG CSA 13093.91004837 | Lateral Hardening-Fuse-91004837 | CKT: 13093 - 91004837 | 2275118 | LUG CSA 13093.91004837 OH | 2275120 | LUG CSA 13093.91004837 UG | LUG C009 | 4500276922 | N/A | N/A | 2020 | LUG - TBD144 | PRE-09361.79 | LUG CSA 13093.91004837 | Lateral Hardening-Fuse-91004837 | CKT: 13093 - 91004837 | 2275118 | LUG CSA 13093.91004837 OH | 2275120 | LUG CSA 13093.91004837 UG | 13093 | PLYMOUTH STREET | CSA | 0.18504 | 17 | 143 | 2020-09-01 | 2021-01-01 | 2021-03-01 | Combined with PRE-09361.83 (FID 91004843) & LUG-TBD245 (FID 60029740)
Pike | 2020 | 2020 | PRE-09361.79 | LUG CSA 13093.91004837 | Lateral Hardening-Fuse-91004837 | CKT: 13093 - 91004837 | 2275118 | LUG CSA 13093.91004837 OH | 2275120 | LUG CSA 13093.91004837 UG | LUG C009 | 4500276922 | N/A | N/A | 2020 | LUG - TBD148 | PRE-09361.83 | DNU LUG CSA 13093.91004843 | DNU Lateral Hardening-Fuse-91004843 | DNU CKT: 13093 - 91004843 | 2275131 | DNU LUG CSA 13093.91004843 OH | 2275132 | DNU LUG CSA 13093.91004843 UG | 13093 | PLYMOUTH STREET | CSA | 0.25947 | 27 | 122 | 2020-09-01 | 2021-01-01 | 2021-03-01 | Combined with PRE-09361.79 (FID 91004837) & LUG-TBD245 (FID 60029740)
Pike | 2020 | 2020 | PRE-09361.80 | LUG CSA 13630.10429536 | Lateral Hardening-Fuse-10429536 | CKT: 13630 - 10429536 | 2275122 | LUG CSA 13630.10429536 OH | 2275123 | LUG CSA 13630.10429536 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD145 | PRE-09361.80 | LUG CSA 13630.10429536 | Lateral Hardening-Fuse-10429536 | CKT: 13630 - 10429536 | 2275122 | LUG CSA 13630.10429536 OH | 2275123 | LUG CSA 13630.10429536 UG | 13630 | PINE LAKE | CSA | 0.082008 | 9 | 59 | 2020-09-01 | 2021-01-01 | 2021-03-01
Pike | 2020 | 2020 | PRE-09361.81 | LUG CSA 13205.90998414 | Lateral Hardening-Fuse-90998414 | CKT: 13205 - 90998414 | 2275124 | LUG CSA 13205.90998414 OH | 2275125 | LUG CSA 13205.90998414 UG | LUG C010 | 4500276922 | N/A | N/A | 2020 | LUG - TBD138 | PRE-09361.29 | DNU LUG CSA 13205.60059346 | DNU Lateral Hardening-Fuse-60059346 | DNU CKT: 13205 - 60059346 | 2274986 | DNU LUG CSA 13205.60059346 OH | 2274989 | DNU LUG CSA 13205.60059346 UG | 13205 | TEMPLE TERRACE | CSA | 0.17462 | 18 | 216 | 2020-08-01 | 2021-01-01 | 2021-03-01 | Combined with PRE-09361.81 (FID 90998414)
Pike | 2020 | 2020 | PRE-09361.81 | LUG CSA 13205.90998414 | Lateral Hardening-Fuse-90998414 | CKT: 13205 - 90998414 | 2275124 | LUG CSA 13205.90998414 OH | 2275125 | LUG CSA 13205.90998414 UG | LUG C010 | 4500276922 | N/A | N/A | 2020 | LUG - TBD146 | PRE-09361.81 | LUG CSA 13205.90998414 | Lateral Hardening-Fuse-90998414 | CKT: 13205 - 90998414 | 2275124 | LUG CSA 13205.90998414 OH | 2275125 | LUG CSA 13205.90998414 UG | 13205 | TEMPLE TERRACE | CSA | 0.083902 | 12 | 212 | 2020-09-01 | 2021-01-01 | 2021-03-01 | Combined with PRE-09361.29 )FID 60059346)
Pike | 2020 | 2020 | PRE-09361.82 | LUG CSA 13948.91837409 | Lateral Hardening-Fuse-91837409 | CKT: 13948 - 91837409 | 2275128 | LUG CSA 13948.91837409 OH | 2275129 | LUG CSA 13948.91837409 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD147 | PRE-09361.82 | LUG CSA 13948.91837409 | Lateral Hardening-Fuse-91837409 | CKT: 13948 - 91837409 | 2275128 | LUG CSA 13948.91837409 OH | 2275129 | LUG CSA 13948.91837409 UG | 13948 | YUKON | CSA | 0.14451 | 13 | 68 | 2020-09-01 | 2021-01-01 | 2021-03-01
Pike | 2020 | 2021 | PRE-09361.84 | LUG CSA 13836.91377944 | Lateral Hardening-Fuse-91377944 | CKT: 13836 - 91377944 | 2275133 | LUG CSA 13836.91377944 OH | 2275134 | LUG CSA 13836.91377944 UG | LUG C013 | 4500276922 | N/A | N/A | 2021 | LUG - TBD211 | PRE-09361.84 | DNU LUG CSA 13836.93321406 | DNU Lateral Hardening-Fuse-93321406 | N/A | N/A | N/A | N/A | N/A | 13836 | FLORIDA AVENUE | CSA | 0.13277 | 8 | 4 | 2021-06-01 | 2022 | 2022 | Combined with PRE-09361.84 (FID 91377944), PRE-09361.24 (FID 91406672) and other 2021 projects
Pike | 2020 | 2021 | PRE-09361.84 | LUG CSA 13836.91377944 | Lateral Hardening-Fuse-91377944 | CKT: 13836 - 91377944 | 2275133 | LUG CSA 13836.91377944 OH | 2275134 | LUG CSA 13836.91377944 UG | LUG C013 | 4500276922 | N/A | N/A | 2021 | LUG - TBD216 | PRE-09361.84 | DNU LUG CSA 13836.60133704 | DNU Lateral Hardening-Fuse-60133704 | N/A | N/A | N/A | N/A | N/A | 13836 | FLORIDA AVENUE | CSA | 0.18258 | 9 | 1 | 2021-07-01 | 2022 | 2022 | Combined with PRE-09361.84 (FID 91377944), PRE-09361.24 (FID 91406672) and other 2021 projects
Pike | 2020 | 2021 | PRE-09361.84 | LUG CSA 13836.91377944 | Lateral Hardening-Fuse-91377944 | CKT: 13836 - 91377944 | 2275133 | LUG CSA 13836.91377944 OH | 2275134 | LUG CSA 13836.91377944 UG | LUG C013 | 4500276922 | N/A | N/A | 2021 | LUG - TBD224 | PRE-09361.84 | DNU LUG CSA 13836.60133698 | DNU Lateral Hardening-Fuse-60133698 | N/A | N/A | N/A | N/A | N/A | 13836 | FLORIDA AVENUE | CSA | 0.44489 | 26 | 76 | 2021-07-01 | 2022 | 2022 | Combined with PRE-09361.84 (FID 91377944), PRE-09361.24 (FID 91406672) and other 2021 projects
Pike | 2020 | 2020 | PRE-09361.84 | LUG CSA 13836.91377944 | Lateral Hardening-Fuse-91377944 | CKT: 13836 - 91377944 | 2275133 | LUG CSA 13836.91377944 OH | 2275134 | LUG CSA 13836.91377944 UG | LUG C013 | 4500276922 | N/A | N/A | 2020 | LUG - TBD133 | PRE-09361.24 | DNU LUG CSA 13836.91406672 | DNU Lateral Hardening-Fuse-91406672 | DNU CKT: 13836 - 91406672 | 2274929 | DNU LUG CSA 13836.91406672 OH | 2274966 | DNU LUG CSA 13836.91406672 UG | 13836 | FLORIDA AVENUE | CSA | 0.34621 | 25 | 91 | 2020-06-01 | 2021-01-01 | 2021-03-01 | Combined with PRE-09361.84 (FID 91377944) and other 2021 projects
Pike | 2020 | 2020 | PRE-09361.84 | LUG CSA 13836.91377944 | Lateral Hardening-Fuse-91377944 | CKT: 13836 - 91377944 | 2275133 | LUG CSA 13836.91377944 OH | 2275134 | LUG CSA 13836.91377944 UG | LUG C013 | 4500276922 | N/A | N/A | 2020 | LUG - TBD149 | PRE-09361.84 | LUG CSA 13836.91377944 | Lateral Hardening-Fuse-91377944 | CKT: 13836 - 91377944 | 2275133 | LUG CSA 13836.91377944 OH | 2275134 | LUG CSA 13836.91377944 UG | 13836 | FLORIDA AVENUE | CSA | 0.59167 | 41 | 276 | 2020-09-01 | 2021-01-01 | 2021-03-01 | Combined with PRE-0361.24 (FID 91406672) and other 2021 projects
Pike | 2020 | 2021 | PRE-09361.85 | LUG CSA 13102.60123654 | Lateral Hardening-Fuse-60123654 | CKT: 13102 - 60123654 | 2275137 | LUG CSA 13102.60123654 OH | 2275138 | LUG CSA 13102.60123654 UG | LUG C014 | 4500276922 | N/A | N/A | 2021 | LUG - TBD246 | PRE-09361.85 | DNU LUG CSA 13102.60123656 | DNU Lateral Hardening-Fuse-60123656 | N/A | N/A | N/A | N/A | N/A | 13102 | YUKON | CSA | 0.14867 | 18 | 26 | 2021-10-01 | 2022 | 2022 | Combined with PRE-09361.85 (FID 60123654)
Pike | 2020 | 2020 | PRE-09361.85 | LUG CSA 13102.60123654 | Lateral Hardening-Fuse-60123654 | CKT: 13102 - 60123654 | 2275137 | LUG CSA 13102.60123654 OH | 2275138 | LUG CSA 13102.60123654 UG | LUG C014 | 4500276922 | N/A | N/A | 2020 | LUG - TBD150 | PRE-09361.85 | LUG CSA 13102.60123654 | Lateral Hardening-Fuse-60123654 | CKT: 13102 - 60123654 | 2275137 | LUG CSA 13102.60123654 OH | 2275138 | LUG CSA 13102.60123654 UG | 13102 | YUKON | CSA | 0.19034 | 15 | 72 | 2020-10-01 | 2021-01-01 | 2021-03-01 | Combined with LUG-TBD246 (FID 60123656)
Pike | 2020 | 2020 | PRE-09361.86 | LUG CSA 13158.92874802 | Lateral Hardening-Fuse-92874802 | CKT: 13158 - 92874802 | 2275139 | LUG CSA 13158.92874802 OH | 2275142 | LUG CSA 13158.92874802 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD151 | PRE-09361.86 | LUG CSA 13158.92874802 | Lateral Hardening-Fuse-92874802 | CKT: 13158 - 92874802 | 2275139 | LUG CSA 13158.92874802 OH | 2275142 | LUG CSA 13158.92874802 UG | 13158 | THIRTIETH STREET | CSA | 0.14905 | 14 | 47 | 2020-10-01 | 2021-01-01 | 2021-03-01
Pike | 2020 | 2020 | PRE-09361.87 | LUG CSA 13176.10375134 | Lateral Hardening-Fuse-10375134 | CKT: 13176 - 10375134 | 2275144 | LUG CSA 13176.10375134 OH | 2275145 | LUG CSA 13176.10375134 UG | U - LUG C015 | 4500276922 | N/A | N/A | 2020 | LUG - TBD152 | PRE-09361.87 | LUG CSA 13176.10375134 | Lateral Hardening-Fuse-10375134 | CKT: 13176 - 10375134 | 2275144 | LUG CSA 13176.10375134 OH | 2275145 | LUG CSA 13176.10375134 UG | 13176 | ELEVENTH AVENUE | CSA | 0.13504 | 10 | 89 | 2020-10-01 | 2021-02-01 | 2021-04-01 | Originally combined with PRE-09361.482 (FID 10375136), but now uncombined
Pike | 2020 | 2020 | PRE-09361.88 | LUG CSA 13107.10376173 | Lateral Hardening-Fuse-10376173 | CKT: 13107 - 10376173 | 2275146 | LUG CSA 13107.10376173 OH | 2275148 | LUG CSA 13107.10376173 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD153 | PRE-09361.88 | LUG CSA 13107.10376173 | Lateral Hardening-Fuse-10376173 | CKT: 13107 - 10376173 | 2275146 | LUG CSA 13107.10376173 OH | 2275148 | LUG CSA 13107.10376173 UG | 13107 | MCFARLAND | CSA | 0.43542 | 28 | 119 | 2020-10-01 | 2021-03-01 | 2021-05-01
Pike | 2020 | 2020 | PRE-09361.89 | LUG CSA 13057.10121709 | Lateral Hardening-Fuse-10121709 | CKT: 13057 - 10121709 | 2275149 | LUG CSA 13057.10121709 OH | 2275150 | LUG CSA 13057.10121709 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD154 | PRE-09361.89 | LUG CSA 13057.10121709 | Lateral Hardening-Fuse-10121709 | CKT: 13057 - 10121709 | 2275149 | LUG CSA 13057.10121709 OH | 2275150 | LUG CSA 13057.10121709 UG | 13057 | MCKINLEY | CSA | 0.16326 | 14 | 80 | 2020-10-01 | 2021-03-01 | 2021-04-01
Pike | 2020 | 2021 | PRE-09361.90 | LUG CSA 13418.92357188 | Lateral Hardening-Fuse-92357188 | CKT: 13418 - 92357188 | 2275151 | LUG CSA 13418.92357188 OH | 2275152 | LUG CSA 13418.92357188 UG | LUG C017 | 4500276922 | N/A | N/A | 2021 | LUG - TBD190 | PRE-09361.90 | DNU LUG CSA 13418.92292295 | DNU Lateral Hardening-Fuse-92292295 | N/A | N/A | N/A | N/A | N/A | 13418 | JUNEAU | CSA | 0.2375 | 18 | 17 | 2021-03-01 | 2021-10-01 | 2021-12-01 | Combined with PRE-09361.90 (FID 92357188)
Pike | 2020 | 2020 | PRE-09361.90 | LUG CSA 13418.92357188 | Lateral Hardening-Fuse-92357188 | CKT: 13418 - 92357188 | 2275151 | LUG CSA 13418.92357188 OH | 2275152 | LUG CSA 13418.92357188 UG | LUG C017 | 4500276922 | N/A | N/A | 2020 | LUG - TBD155 | PRE-09361.90 | LUG CSA 13418.92357188 | Lateral Hardening-Fuse-92357188 | CKT: 13418 - 92357188 | 2275151 | LUG CSA 13418.92357188 OH | 2275152 | LUG CSA 13418.92357188 UG | 13418 | JUNEAU | CSA | 0.47045 | 33 | 61 | 2020-10-01 | 2021-03-01 | 2021-05-01 | Combined with LUG-TBD190 (FID 92292295)
Pike | 2020 | 2020 | PRE-09361.91 | LUG CSA 13592.91213055 | Lateral Hardening-Fuse-91213055 | CKT: 13592 - 91213055 | 2275154 | LUG CSA 13592.91213055 OH | 2275156 | LUG CSA 13592.91213055 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD156 | PRE-09361.91 | LUG CSA 13592.91213055 | Lateral Hardening-Fuse-91213055 | CKT: 13592 - 91213055 | 2275154 | LUG CSA 13592.91213055 OH | 2275156 | LUG CSA 13592.91213055 UG | 13592 | SENECA STREET | CSA | 0.27235 | 23 | 72 | 2020-10-01 | 2021-03-01 | 2021-06-01
Pike | 2020 | 2021 | PRE-09361.92 | LUG CSA 13100.91340554 | Lateral Hardening-Fuse-91340554 | CKT: 13100 - 91340554 | 2275159 | LUG CSA 13100.91340554 OH | 2275160 | LUG CSA 13100.91340554 UG | LUG C016 | 4500276922 | N/A | N/A | 2021 | LUG - TBD188 | PRE-09361.92 | DNU LUG CSA 13100.10371703 | DNU Lateral Hardening-Fuse-10371703 | N/A | N/A | N/A | N/A | N/A | 13100 | YUKON | CSA | 0.67973 | 35 | 302 | 2021-03-01 | 2021-07-01 | 2021-10-01 | Combined with PRE-09361.92 (FID 91340554) & PRE-09361.378 (FID 10371697)
Pike | 2020 | 2020 | PRE-09361.92 | LUG CSA 13100.91340554 | Lateral Hardening-Fuse-91340554 | CKT: 13100 - 91340554 | 2275159 | LUG CSA 13100.91340554 OH | 2275160 | LUG CSA 13100.91340554 UG | LUG C016 | 4500276922 | N/A | N/A | 2020 | LUG - TBD157 | PRE-09361.92 | LUG CSA 13100.91340554 | Lateral Hardening-Fuse-91340554 | CKT: 13100 - 91340554 | 2275159 | LUG CSA 13100.91340554 OH | 2275160 | LUG CSA 13100.91340554 UG | 13100 | YUKON | CSA | 0.41193 | 28 | 403 | 2020-11-01 | 2021-04-01 | 2021-06-01 | Combined with LUG-TBD188 (FID 10371703) and PRE-09361.378 (FID 10371697)
Pike | 2020 | 2020 | PRE-09361.93 | LUG CSA 13715.90737020 | Lateral Hardening-Fuse-90737020 | CKT: 13715 - 90737020 | 2275161 | LUG CSA 13715.90737020 OH | 2275162 | LUG CSA 13715.90737020 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD158 | PRE-09361.93 | LUG CSA 13715.90737020 | Lateral Hardening-Fuse-90737020 | CKT: 13715 - 90737020 | 2275161 | LUG CSA 13715.90737020 OH | 2275162 | LUG CSA 13715.90737020 UG | 13715 | TAMPA PALMS | CSA | 0.082008 | 3 | 10 | 2020-11-01 | 2021-04-01 | 2021-05-01
Pike | 2020 | 2020 | PRE-09361.94 | LUG CSA 13176.91029163 | Lateral Hardening-Fuse-91029163 | CKT: 13176 - 91029163 | 2275163 | LUG CSA 13176.91029163 OH | 2275166 | LUG CSA 13176.91029163 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD159 | PRE-09361.94 | LUG CSA 13176.91029163 | Lateral Hardening-Fuse-91029163 | CKT: 13176 - 91029163 | 2275163 | LUG CSA 13176.91029163 OH | 2275166 | LUG CSA 13176.91029163 UG | 13176 | ELEVENTH AVENUE | CSA | 0.069697 | 7 | 89 | 2020-11-01 | 2021-04-01 | 2021-05-01
Pike | 2020 | 2020 | PRE-09361.95 | LUG CSA 13835.60131429 | Lateral Hardening-Fuse-60131429 | CKT: 13835 - 60131429 | 2275167 | LUG CSA 13835.60131429 OH | 2275170 | LUG CSA 13835.60131429 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD160 | PRE-09361.95 | LUG CSA 13835.60131429 | Lateral Hardening-Fuse-60131429 | CKT: 13835 - 60131429 | 2275167 | LUG CSA 13835.60131429 OH | 2275170 | LUG CSA 13835.60131429 UG | 13835 | FLORIDA AVENUE | CSA | 0.2714 | 19 | 43 | 2020-11-01 | 2021-04-01 | 2021-06-01
Pike | 2020 | 2020 | PRE-09361.96 | LUG CSA 13593.93057902 | Lateral Hardening-Fuse-93057902 | CKT: 13593 - 93057902 | 2275171 | LUG CSA 13593.93057902 OH | 2275172 | LUG CSA 13593.93057902 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD161 | PRE-09361.96 | LUG CSA 13593.93057902 | Lateral Hardening-Fuse-93057902 | CKT: 13593 - 93057902 | 2275171 | LUG CSA 13593.93057902 OH | 2275172 | LUG CSA 13593.93057902 UG | 13593 | SENECA STREET | CSA | 0.45455 | 39 | 83 | 2020-10-01 | 2021-04-01 | 2021-06-01
Pike | 2020 | 2020 | PRE-09361.97 | LUG CSA 13105.10580678 | Lateral Hardening-Fuse-10580678 | CKT: 13105 - 10580678 | 2275174 | LUG CSA 13105.10580678 OH | 2275175 | LUG CSA 13105.10580678 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD162 | PRE-09361.97 | LUG CSA 13105.10580678 | Lateral Hardening-Fuse-10580678 | CKT: 13105 - 10580678 | 2275174 | LUG CSA 13105.10580678 OH | 2275175 | LUG CSA 13105.10580678 UG | 13105 | MCFARLAND | CSA | 0.23163 | 17 | 217 | 2020-11-01 | 2021-04-01 | 2021-06-01
Pike | 2020 | 2020 | PRE-09361.98 | LUG CSA 13188.10655453 | Lateral Hardening-Fuse-10655453 | CKT: 13188 - 10655453 | 2275176 | LUG CSA 13188.10655453 OH | 2275178 | LUG CSA 13188.10655453 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD163 | PRE-09361.98 | LUG CSA 13188.10655453 | Lateral Hardening-Fuse-10655453 | CKT: 13188 - 10655453 | 2275176 | LUG CSA 13188.10655453 OH | 2275178 | LUG CSA 13188.10655453 UG | 13188 | PINE LAKE | CSA | 0.12235 | 15 | 46 | 2020-11-01 | 2021-04-01 | 2021-06-01
Pike | 2020 | 2020 | PRE-09361.99 | LUG CSA 13592.10402259 | Lateral Hardening-Fuse-10402259 | CKT: 13592 - 10402259 | 2275180 | LUG CSA 13592.10402259 OH | 2275181 | LUG CSA 13592.10402259 UG |  | 4500276922 | N/A | N/A | 2020 | LUG - TBD164 | PRE-09361.99 | LUG CSA 13592.10402259 | Lateral Hardening-Fuse-10402259 | CKT: 13592 - 10402259 | 2275180 | LUG CSA 13592.10402259 OH | 2275181 | LUG CSA 13592.10402259 UG | 13592 | SENECA STREET | CSA | 0.1983 | 21 | 20 | 2020-11-01 | 2021-04-01 | 2021-05-01

## DNU Original Master
Contractor | CWO Project List Year | Original Project List Year | Placeholder Funding Project | Designated Survivor Funding Project | Original TECO Funding Project | Original Project Name | Designated Survivor Project Name | Parent No. | Substation | Original Lateral Project Name | Designated Survivor Lateral Project Name | Service Area | Length (miles) | Count of Structures | Count of Customers | Eng Start | Construx Start | Construx End | 2020 PO # | 2021 Eng PO # | 2021 Const PO # | LUG CO # | Original WorkPro Street Name | Designated Survivor WorkPro Street Name | Original TECO OH Removal Work Request # | Original TECO OH Removal Work Request Description | Original TECO UG Install Work Request # | Original TECO UG Removal Work Request Description | Designated Survivor TECO OH Removal Work Request # | Designated Survivor TECO OH Removal Work Request Description | Designated Survivor TECO UG Install Work Request # | Designated Survivor TECO UG Removal Work Request Description | Notes
Fishel | 2021 | 2021 | LUG - TBD18 | PRE-09361.47 | PRE-09361.47 | DNU LUG PCA 13785.90239166 | LUG PCA 13785.92466250 | 13785 | PINECREST | DNU Lateral Hardening-Fuse-90239166 | Lateral Hardening-Fuse-92466250 | PCA | 2.5172 | 115 | 182 | 2021-01-01 | 2021-08-01 | 2021-12-01 | 4500272910 | N/A | N/A | LUG C034 | N/A | CKT: 13785 - 92466250 | N/A | N/A | N/A | N/A | 2274189 | LUG PCA 13785.92466250 OH | 2274190 | LUG PCA 13785.92466250 UG | Combined with PRE-09361.10 (FID 10676209), PRE-09361.42 (FID 93159006) & PRE-09361.47 (FID 92466250)
Fishel | 2021 | 2021 | LUG - TBD19 | PRE-09361.285 | PRE-09361.285 | LUG PCA 13961.10696431 | LUG PCA 13961.10696431 | 13961 | TERRACE | Lateral Hardening-Fuse-10696431 | Lateral Hardening-Fuse-10696431 | PCA | 0.15795 | 8 | 4 | 2021-01-01 | 2021-04-01 | 2021-05-01 | N/A | 4500282909 | TBD |  | CKT: 13961 - 10696431 | CKT: 13961 - 10696431 | 2310526 | LUG PCA 13961.10696431 OH | 2310527 | LUG PCA 13961.10696431 UG | 2310526 | LUG PCA 13961.10696431 OH | 2310527 | LUG PCA 13961.10696431 UG
Fishel | 2021 | 2021 | LUG - TBD20 | CANCELLED | CANCELLED | LUG PCA 13961.10696419 | LUG PCA 13961.10696419 | 13961 | TERRACE | Lateral Hardening-Fuse-10696419 | Lateral Hardening-Fuse-10696419 | PCA | 0.5589 | 26 | 3 | 2021-01-01 | 2021-04-01 | 2021-06-01 | N/A | 4500282909 | TBD |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Project cancelled, as of 11/15, due to new construction project in area
Fishel | 2021 | 2021 | LUG - TBD21 | PRE-09361.286 | PRE-09361.286 | LUG PCA 13785.92299245 | LUG PCA 13785.92299245 | 13785 | PINECREST | Lateral Hardening-Fuse-92299245 | Lateral Hardening-Fuse-92299245 | PCA | 1.0799 | 57 | 174 | 2021-01-01 | 2021-04-01 | 2021-06-01 | N/A | 4500282909 | TBD |  | CKT: 13785 - 92299245 | CKT: 13785 - 92299245 | 2310665 | LUG PCA 13785.92299245 OH | 2310666 | LUG PCA 13785.92299245 UG | 2310665 | LUG PCA 13785.92299245 OH | 2310666 | LUG PCA 13785.92299245 UG
Fishel | 2021 | 2021 | LUG - TBD22 | PRE-09361.287 | PRE-09361.287 | LUG PCA 13961.92834683 | LUG PCA 13961.92834683 | 13961 | TERRACE | Lateral Hardening-Fuse-92834683 | Lateral Hardening-Fuse-92834683 | PCA | 0.72027 | 37 | 23 | 2021-01-01 | 2021-05-01 | 2021-07-01 | N/A | 4500282909 | TBD |  | CKT: 13961 - 92834683 | CKT: 13961 - 92834683 | 2310667 | LUG PCA 13961.92834683 OH | 2310668 | LUG PCA 13961.92834683 UG | 2310667 | LUG PCA 13961.92834683 OH | 2310668 | LUG PCA 13961.92834683 UG
Fishel | 2021 | 2021 | LUG - TBD23 | PRE-09361.288 | PRE-09361.288 | LUG PCA 13462.91412064 | LUG PCA 13462.91412064 | 13462 | ALEXANDER ROAD | Lateral Hardening-Fuse-91412064 | Lateral Hardening-Fuse-91412064 | PCA | 0.050379 | 5 | 46 | 2021-01-01 | 2021-04-01 | 2021-05-01 | N/A | 4500282909 | TBD |  | CKT: 13462 - 91412064 | CKT: 13462 - 91412064 | 2310493 | LUG PCA 13462.91412064 OH | 2310496 | LUG PCA 13462.91412064 UG | 2310493 | LUG PCA 13462.91412064 OH | 2310496 | LUG PCA 13462.91412064 UG
Fishel | 2021 | 2021 | LUG - TBD24 | PRE-09361.289 | PRE-09361.289 | LUG PCA 13961.10696486 | LUG PCA 13961.10696486 | 13961 | TERRACE | Lateral Hardening-Fuse-10696486 | Lateral Hardening-Fuse-10696486 | PCA | 0.5447 | 32 | 38 | 2021-01-01 | 2021-05-01 | 2021-07-01 | N/A | 4500282909 | TBD |  | CKT: 13961 - 10696486 | CKT: 13961 - 10696486 | 2310528 | LUG PCA 13961.10696486 OH | 2310529 | LUG PCA 13961.10696486 UG | 2310528 | LUG PCA 13961.10696486 OH | 2310529 | LUG PCA 13961.10696486 UG
Fishel | 2021 | 2021 | LUG - TBD25 | PRE-09361.290 | PRE-09361.290 | LUG PCA 13961.91967308 | LUG PCA 13961.91967308 | 13961 | TERRACE | Lateral Hardening-Fuse-91967308 | Lateral Hardening-Fuse-91967308 | PCA | 0.48693 | 32 | 28 | 2021-01-01 | 2021-06-01 | 2021-08-01 | N/A | 4500282909 | TBD |  | CKT: 13961 - 91967308 | CKT: 13961 - 91967308 | 2310530 | LUG PCA 13961.91967308 OH | 2310532 | LUG PCA 13961.91967308 UG | 2310530 | LUG PCA 13961.91967308 OH | 2310532 | LUG PCA 13961.91967308 UG
Fishel | 2021 | 2021 | LUG - TBD26 | PRE-09361.291 | PRE-09361.291 | LUG PCA 13961.10696417 | LUG PCA 13961.10696417 | 13961 | TERRACE | Lateral Hardening-Fuse-10696417 | Lateral Hardening-Fuse-10696417 | PCA | 0.11345 | 7 | 3 | 2021-01-01 | 2021-07-01 | 2021-08-01 | N/A | 4500282909 | TBD |  | CKT: 13961 - 10696417 | CKT: 13961 - 10696417 | 2310672 | LUG PCA 13961.10696417 OH | 2310673 | LUG PCA 13961.10696417 UG | 2310672 | LUG PCA 13961.10696417 OH | 2310673 | LUG PCA 13961.10696417 UG
Fishel | 2021 | 2021 | LUG - TBD27 | PRE-09361.292 | PRE-09361.292 | LUG WHA 13916.60279623 | LUG WHA 13916.60279623 | 13916 | LAKE RUBY | Lateral Hardening-Fuse-60279623 | Lateral Hardening-Fuse-60279623 | WHA | 0.18561 | 9 | 282 | 2021-01-01 | 2021-07-01 | 2021-08-01 | N/A | 4500282909 | TBD |  | CKT: 13916 - 60279623 | CKT: 13916 - 60279623 | 2310521 | LUG WHA 13916.60279623 OH | 2310523 | LUG WHA 13916.60279623 UG | 2310521 | LUG WHA 13916.60279623 OH | 2310523 | LUG WHA 13916.60279623 UG
Fishel | 2021 | 2021 | LUG - TBD28 | PRE-09361.293 | PRE-09361.293 | LUG WHA 13297.10560430 | LUG WHA 13297.10560430 | 13297 | JAN PHYL | Lateral Hardening-Fuse-10560430 | Lateral Hardening-Fuse-10560430 | WHA | 0.42064 | 27 | 333 | 2021-01-01 | 2021-07-01 | 2021-09-01 | N/A | 4500282909 | TBD |  | CKT: 13297 - 10560430 | CKT: 13297 - 10560430 | 2310678 | LUG WHA 13297.10560430 OH | 2310679 | LUG WHA 13297.10560430 UG | 2310678 | LUG WHA 13297.10560430 OH | 2310679 | LUG WHA 13297.10560430 UG
Fishel | 2021 | 2021 | LUG - TBD29 | PRE-09361.294 | PRE-09361.294 | LUG WHA 13314.92426509 | LUG WHA 13314.92426509 | 13314 | EAST WINTER HAVEN | Lateral Hardening-Fuse-92426509 | Lateral Hardening-Fuse-92426509 | WHA | 0.40208 | 33 | 246 | 2021-03-01 | 2021-07-01 | 2021-09-01 | N/A | 4500282909 | TBD |  | CKT: 13314 - 92426509 | CKT: 13314 - 92426509 | 2310682 | LUG WHA 13314.92426509 OH | 2310684 | LUG WHA 13314.92426509 UG | 2310682 | LUG WHA 13314.92426509 OH | 2310684 | LUG WHA 13314.92426509 UG
Fishel | 2021 | 2021 | LUG - TBD30 | PRE-09361.295 | PRE-09361.295 | LUG WHA 13118.92612349 | LUG WHA 13118.92612349 | 13118 | LAKE ALFRED | Lateral Hardening-Fuse-92612349 | Lateral Hardening-Fuse-92612349 | WHA | 0.93693 | 39 | 220 | 2021-03-01 | 2021-07-01 | 2021-09-01 | N/A | 4500282909 | TBD |  | CKT: 13118 - 92612349 | CKT: 13118 - 92612349 | 2310454 | LUG WHA 13118.92612349 OH | 2310456 | LUG WHA 13118.92612349 UG | 2310454 | LUG WHA 13118.92612349 OH | 2310456 | LUG WHA 13118.92612349 UG
Fishel | 2021 | 2021 | LUG - TBD31 | PRE-09361.296 | PRE-09361.296 | LUG WHA 13313.90084626 | LUG WHA 13313.90084626 | 13313 | EAST WINTER HAVEN | Lateral Hardening-Fuse-90084626 | Lateral Hardening-Fuse-90084626 | WHA | 0.092045 | 9 | 35 | 2021-03-01 | 2021-07-01 | 2021-08-01 | N/A | 4500282909 | TBD |  | CKT: 13313 - 90084626 | CKT: 13313 - 90084626 | 2310490 | LUG WHA 13313.90084626 OH | 2310491 | LUG WHA 13313.90084626 UG | 2310490 | LUG WHA 13313.90084626 OH | 2310491 | LUG WHA 13313.90084626 UG
Fishel | 2021 | 2021 | LUG - TBD32 | PRE-09361.297 | PRE-09361.297 | LUG WHA 13699.10637242 | LUG WHA 13699.10637242 | 13699 | BERKLEY ROAD | Lateral Hardening-Fuse-10637242 | Lateral Hardening-Fuse-10637242 | WHA | 0.62462 | 37 | 284 | 2021-03-01 | 2021-07-01 | 2021-09-01 | N/A | 4500282909 | TBD |  | CKT: 13699 - 10637242 | CKT: 13699 - 10637242 | 2310505 | LUG WHA 13699.10637242 OH | 2310506 | LUG WHA 13699.10637242 UG | 2310505 | LUG WHA 13699.10637242 OH | 2310506 | LUG WHA 13699.10637242 UG
Fishel | 2021 | 2021 | LUG - TBD33 | PRE-09361.298 | PRE-09361.298 | LUG WHA 13313.10684614 | LUG WHA 13313.10684614 | 13313 | EAST WINTER HAVEN | Lateral Hardening-Fuse-10684614 | Lateral Hardening-Fuse-10684614 | WHA | 0.1358 | 16 | 106 | 2021-03-01 | 2021-07-01 | 2021-09-01 | N/A | 4500282909 | TBD |  | CKT: 13313 - 10684614 | CKT: 13313 - 10684614 | 2310685 | LUG WHA 13313.10684614 OH | 2310686 | LUG WHA 13313.10684614 UG | 2310685 | LUG WHA 13313.10684614 OH | 2310686 | LUG WHA 13313.10684614 UG
Fishel | 2021 | 2021 | LUG - TBD34 | PRE-09361.299 | PRE-09361.299 | LUG WHA 13296.92376304 | LUG WHA 13296.92376304 | 13296 | JAN PHYL | Lateral Hardening-Fuse-92376304 | Lateral Hardening-Fuse-92376304 | WHA | 0.29015 | 20 | 200 | 2021-03-01 | 2021-07-01 | 2021-09-01 | N/A | 4500282909 | TBD |  | CKT: 13296 - 92376304 | CKT: 13296 - 92376304 | 2310688 | LUG WHA 13296.92376304 OH | 2310689 | LUG WHA 13296.92376304 UG | 2310688 | LUG WHA 13296.92376304 OH | 2310689 | LUG WHA 13296.92376304 UG
Fishel | 2021 | 2021 | LUG - TBD35 | PRE-09361.300 | PRE-09361.300 | LUG WHA 13313.60568375 | LUG WHA 13313.60568375 | 13313 | EAST WINTER HAVEN | Lateral Hardening-Fuse-60568375 | Lateral Hardening-Fuse-60568375 | WHA | 0.22765 | 34 | 33 | 2021-03-01 | 2021-07-01 | 2021-09-01 | N/A | 4500282909 | TBD |  | CKT: 13313 - 60568375 | CKT: 13313 - 60568375 | 2310701 | LUG WHA 13313.60568375 OH | 2310702 | LUG WHA 13313.60568375 UG | 2310701 | LUG WHA 13313.60568375 OH | 2310702 | LUG WHA 13313.60568375 UG
Fishel | 2021 | 2021 | LUG - TBD36 | PRE-09361.301 | PRE-09361.301 | LUG WHA 13297.60269456 | LUG WHA 13297.60269456 | 13297 | JAN PHYL | Lateral Hardening-Fuse-60269456 | Lateral Hardening-Fuse-60269456 | WHA | 0.30625 | 30 | 59 | 2021-03-01 | 2021-08-01 | 2021-10-01 | N/A | 4500282909 | TBD |  | CKT: 13297 - 60269456 | CKT: 13297 - 60269456 | 2310703 | LUG WHA 13297.60269456 OH | 2310705 | LUG WHA 13297.60269456 UG | 2310703 | LUG WHA 13297.60269456 OH | 2310705 | LUG WHA 13297.60269456 UG
Fishel | 2021 | 2021 | LUG - TBD37 | PRE-09361.302 | PRE-09361.302 | LUG WHA 13699.10637259 | LUG WHA 13699.10637259 | 13699 | BERKLEY ROAD | Lateral Hardening-Fuse-10637259 | Lateral Hardening-Fuse-10637259 | WHA | 0.15587 | 13 | 26 | 2021-04-01 | 2021-08-01 | 2021-09-01 | N/A | 4500282909 | TBD |  | CKT: 13699 - 10637259 | CKT: 13699 - 10637259 | 2310513 | LUG WHA 13699.10637259 OH | 2310516 | LUG WHA 13699.10637259 UG | 2310513 | LUG WHA 13699.10637259 OH | 2310516 | LUG WHA 13699.10637259 UG
Fishel | 2021 | 2021 | LUG - TBD38 | PRE-09361.303 | PRE-09361.303 | LUG WHA 13473.60168916 | LUG WHA 13473.60168916 | 13473 | SOUTH ELOISE | Lateral Hardening-Fuse-60168916 | Lateral Hardening-Fuse-60168916 | WHA | 0.34356 | 24 | 419 | 2021-04-01 | 2021-08-01 | 2021-10-01 | N/A | 4500282909 | TBD |  | CKT: 13473 - 60168916 | CKT: 13473 - 60168916 | 2310498 | LUG WHA 13473.60168916 OH | 2310499 | LUG WHA 13473.60168916 UG | 2310498 | LUG WHA 13473.60168916 OH | 2310499 | LUG WHA 13473.60168916 UG
Fishel | 2021 | 2021 | LUG - TBD39 | PRE-09361.304 | PRE-09361.304 | LUG WHA 13296.10562356 | LUG WHA 13296.10562356 | 13296 | JAN PHYL | Lateral Hardening-Fuse-10562356 | Lateral Hardening-Fuse-10562356 | WHA | 0.22064 | 17 | 29 | 2021-04-01 | 2021-08-01 | 2021-09-01 | N/A | 4500282909 | TBD |  | CKT: 13296 - 10562356 | CKT: 13296 - 10562356 | 2310706 | LUG WHA 13296.10562356 OH | 2310709 | LUG WHA 13296.10562356 UG | 2310706 | LUG WHA 13296.10562356 OH | 2310709 | LUG WHA 13296.10562356 UG
Fishel | 2021 | 2021 | LUG - TBD40 | PRE-09361.305 | PRE-09361.305 | LUG WHA 13916.92509975 | LUG WHA 13916.92509975 | 13916 | LAKE RUBY | Lateral Hardening-Fuse-92509975 | Lateral Hardening-Fuse-92509975 | WHA | 0.45057 | 35 | 71 | 2021-04-01 | 2021-08-01 | 2021-10-01 | N/A | 4500282909 | TBD |  | CKT: 13916 - 92509975 | CKT: 13916 - 92509975 | 2310435 | LUG WHA 13916.92509975 OH | 2310437 | LUG WHA 13916.92509975 UG | 2310435 | LUG WHA 13916.92509975 OH | 2310437 | LUG WHA 13916.92509975 UG
Fishel | 2021 | 2021 | LUG - TBD41 | PRE-09361.306 | PRE-09361.306 | LUG WHA 13297.10560425 | LUG WHA 13297.10560425 | 13297 | JAN PHYL | Lateral Hardening-Fuse-10560425 | Lateral Hardening-Fuse-10560425 | WHA | 0.3142 | 21 | 72 | 2021-04-01 | 2021-08-01 | 2021-10-01 | N/A | 4500282909 | TBD |  | CKT: 13297 - 10560425 | CKT: 13297 - 10560425 | 2310711 | LUG WHA 13297.10560425 OH | 2310714 | LUG WHA 13297.10560425 UG | 2310711 | LUG WHA 13297.10560425 OH | 2310714 | LUG WHA 13297.10560425 UG
Fishel | 2021 | 2021 | LUG - TBD42 | PRE-09361.307 | PRE-09361.307 | LUG WHA 13296.60531111 | LUG WHA 13296.60531111 | 13296 | JAN PHYL | Lateral Hardening-Fuse-60531111 | Lateral Hardening-Fuse-60531111 | WHA | 0.95246 | 68 | 90 | 2021-04-01 | 2021-10-01 | 2021-10-01 | N/A | 4500282909 | TBD |  | CKT: 13296 - 60531111 | CKT: 13296 - 60531111 | 2310717 | LUG WHA 13296.60531111 OH | 2310719 | LUG WHA 13296.60531111 UG | 2310717 | LUG WHA 13296.60531111 OH | 2310719 | LUG WHA 13296.60531111 UG
Fishel | 2021 | 2021 | LUG - TBD43 | PRE-09361.308 | PRE-09361.308 | LUG WHA 13699.10637247 | LUG WHA 13699.10637247 | 13699 | BERKLEY ROAD | Lateral Hardening-Fuse-10637247 | Lateral Hardening-Fuse-10637247 | WHA | 0.18996 | 11 | 119 | 2021-05-01 | 2021-08-01 | 2021-09-01 | N/A | 4500282909 | TBD |  | CKT: 13699 - 10637247 | CKT: 13699 - 10637247 | 2310507 | LUG WHA 13699.10637247 OH | 2310509 | LUG WHA 13699.10637247 UG | 2310507 | LUG WHA 13699.10637247 OH | 2310509 | LUG WHA 13699.10637247 UG
Fishel | 2021 | 2021 | LUG - TBD44 | PRE-09361.309 | PRE-09361.309 | LUG WHA 13473.60168942 | LUG WHA 13473.60168942 | 13473 | SOUTH ELOISE | Lateral Hardening-Fuse-60168942 | Lateral Hardening-Fuse-60168942 | WHA | 0.34678 | 27 | 187 | 2021-05-01 | 2021-08-01 | 2021-10-01 | N/A | 4500282909 | TBD |  | CKT: 13473 - 60168942 | CKT: 13473 - 60168942 | 2310722 | LUG WHA 13473.60168942 OH | 2310725 | LUG WHA 13473.60168942 UG | 2310722 | LUG WHA 13473.60168942 OH | 2310725 | LUG WHA 13473.60168942 UG
Fishel | 2021 | 2021 | LUG - TBD45 | PRE-09361.310 | PRE-09361.310 | LUG WHA 13118.92659353 | LUG WHA 13118.92659353 | 13118 | LAKE ALFRED | Lateral Hardening-Fuse-92659353 | Lateral Hardening-Fuse-92659353 | WHA | 0.40833 | 30 | 52 | 2021-05-01 | 2021-08-01 | 2021-10-01 | N/A | 4500282909 | TBD |  | CKT: 13118 - 92659353 | CKT: 13118 - 92659353 | 2310464 | LUG WHA 13118.92659353 OH | 2310467 | LUG WHA 13118.92659353 UG | 2310464 | LUG WHA 13118.92659353 OH | 2310467 | LUG WHA 13118.92659353 UG
Fishel | 2021 | 2021 | LUG - TBD46 | PRE-09361.311 | PRE-09361.311 | LUG WHA 13118.10535995 | LUG WHA 13118.10535995 | 13118 | LAKE ALFRED | Lateral Hardening-Fuse-10535995 | Lateral Hardening-Fuse-10535995 | WHA | 0.95057 | 63 | 363 | 2021-05-01 | 2021-09-01 | 2021-11-01 | N/A | 4500282909 | TBD |  | CKT: 13118 - 10535995 | CKT: 13118 - 10535995 | 2310727 | LUG WHA 13118.10535995 OH | 2310730 | LUG WHA 13118.10535995 UG | 2310727 | LUG WHA 13118.10535995 OH | 2310730 | LUG WHA 13118.10535995 UG | previously listed incorrectly as Fuse 10676209
Fishel | 2021 | 2021 | LUG - TBD47 | PRE-09361.312 | PRE-09361.312 | LUG WHA 13699.10637240 | LUG WHA 13699.10637240 | 13699 | BERKLEY ROAD | Lateral Hardening-Fuse-10637240 | Lateral Hardening-Fuse-10637240 | WHA | 1.0178 | 48 | 137 | 2021-06-01 | 2021-10-01 | 2021-12-01 | N/A | 4500282909 | TBD |  | CKT: 13699 - 10637240 | CKT: 13699 - 10637240 | 2310502 | LUG WHA 13699.10637240 OH | 2310503 | LUG WHA 13699.10637240 UG | 2310502 | LUG WHA 13699.10637240 OH | 2310503 | LUG WHA 13699.10637240 UG
Fishel | 2021 | 2021 | LUG - TBD48 | PRE-09361.313 | PRE-09361.313 | LUG WHA 13313.93103371 | LUG WHA 13313.93103371 | 13313 | EAST WINTER HAVEN | Lateral Hardening-Fuse-93103371 | Lateral Hardening-Fuse-93103371 | WHA | 0.10095 | 13 | 20 | 2021-06-01 | 2021-10-01 | 2021-12-01 | N/A | 4500282909 | TBD |  | CKT: 13313 - 93103371 | CKT: 13313 - 93103371 | 2310733 | LUG WHA 13313.93103371 OH | 2310735 | LUG WHA 13313.93103371 UG | 2310733 | LUG WHA 13313.93103371 OH | 2310735 | LUG WHA 13313.93103371 UG
Fishel | 2021 | 2021 | LUG - TBD49 | PRE-09361.314 | PRE-09361.314 | LUG WHA 13118.92204382 | LUG WHA 13118.92204382 | 13118 | LAKE ALFRED | Lateral Hardening-Fuse-92204382 | Lateral Hardening-Fuse-92204382 | WHA | 0.69129 | 41 | 88 | 2021-06-01 | 2021-10-01 | 2021-12-01 | N/A | 4500282909 | TBD |  | CKT: 13118 - 92204382 | CKT: 13118 - 92204382 | 2310737 | LUG WHA 13118.92204382 OH | 2310738 | LUG WHA 13118.92204382 UG | 2310737 | LUG WHA 13118.92204382 OH | 2310738 | LUG WHA 13118.92204382 UG
Fishel | 2021 | 2021 | LUG - TBD50 | PRE-09361.315 | PRE-09361.315 | LUG WHA 13118.92659172 | LUG WHA 13118.92659172 | 13118 | LAKE ALFRED | Lateral Hardening-Fuse-92659172 | Lateral Hardening-Fuse-92659172 | WHA | 0.275 | 26 | 18 | 2021-06-01 | 2021-10-01 | 2021-12-01 | N/A | 4500282909 | TBD |  | CKT: 13118 - 92659172 | CKT: 13118 - 92659172 | 2310458 | LUG WHA 13118.92659172 OH | 2310459 | LUG WHA 13118.92659172 UG | 2310458 | LUG WHA 13118.92659172 OH | 2310459 | LUG WHA 13118.92659172 UG
Fishel | 2021 | 2021 | LUG - TBD51 | PRE-09361.316 | PRE-09361.316 | LUG WHA 13473.92097460 | LUG WHA 13473.92097460 | 13473 | SOUTH ELOISE | Lateral Hardening-Fuse-92097460 | Lateral Hardening-Fuse-92097460 | WHA | 0.24015 | 19 | 152 | 2021-06-01 | 2021-10-01 | 2021-12-01 | N/A | 4500282909 | TBD |  | CKT: 13473 - 92097460 | CKT: 13473 - 92097460 | 2310740 | LUG WHA 13473.92097460 OH | 2310743 | LUG WHA 13473.92097460 UG | 2310740 | LUG WHA 13473.92097460 OH | 2310743 | LUG WHA 13473.92097460 UG
Fishel | 2021 | 2021 | LUG - TBD52 | PRE-09361.317 | PRE-09361.317 | LUG WHA 13296.90010289 | LUG WHA 13296.90010289 | 13296 | JAN PHYL | Lateral Hardening-Fuse-90010289 | Lateral Hardening-Fuse-90010289 | WHA | 1.3356 | 81 | 82 | 2021-06-01 | 2021-09-01 | 2021-12-01 | N/A | 4500282909 | TBD |  | CKT: 13296 - 90010289 | CKT: 13296 - 90010289 | 2310746 | LUG WHA 13296.90010289 OH | 2310751 | LUG WHA 13296.90010289 UG | 2310746 | LUG WHA 13296.90010289 OH | 2310751 | LUG WHA 13296.90010289 UG
Fishel | 2021 | 2021 | LUG - TBD53 | PRE-09361.318 | PRE-09361.318 | LUG WHA 13313.10684581 | LUG WHA 13313.10684581 | 13313 | EAST WINTER HAVEN | Lateral Hardening-Fuse-10684581 | Lateral Hardening-Fuse-10684581 | WHA | 0.24015 | 23 | 38 | 2021-07-01 | 2021-09-01 | 2021-12-01 | N/A | 4500282909 | TBD |  | CKT: 13313 - 10684581 | CKT: 13313 - 10684581 | 2310752 | LUG WHA 13313.10684581 OH | 2310754 | LUG WHA 13313.10684581 UG | 2310752 | LUG WHA 13313.10684581 OH | 2310754 | LUG WHA 13313.10684581 UG | previously listed incorrectly as Fuse 92097460
Fishel | 2021 | 2021 | LUG - TBD54 | PRE-09361.319 | PRE-09361.319 | LUG WHA 13118.10535999 | LUG WHA 13118.10535999 | 13118 | LAKE ALFRED | Lateral Hardening-Fuse-10535999 | Lateral Hardening-Fuse-10535999 | WHA | 0.35492 | 26 | 101 | 2021-07-01 | 2021-10-01 | 2021-12-01 | N/A | 4500282909 | TBD |  | CKT: 13118 - 10535999 | CKT: 13118 - 10535999 | 2310443 | LUG WHA 13118.10535999 OH | 2310452 | LUG WHA 13118.10535999 UG | 2310443 | LUG WHA 13118.10535999 OH | 2310452 | LUG WHA 13118.10535999 UG
Fishel | 2021 | 2021 | LUG - TBD55 | PRE-09361.320 | PRE-09361.320 | LUG WHA 13699.60165416 | LUG WHA 13699.60165416 | 13699 | BERKLEY ROAD | Lateral Hardening-Fuse-60165416 | Lateral Hardening-Fuse-60165416 | WHA | 0.35795 | 18 | 10 | 2021-07-01 | 2021-10-01 | 2021-12-01 | N/A | 4500282909 | TBD |  | CKT: 13699 - 60165416 | CKT: 13699 - 60165416 | 2310518 | LUG WHA 13699.60165416 OH | 2310519 | LUG WHA 13699.60165416 UG | 2310518 | LUG WHA 13699.60165416 OH | 2310519 | LUG WHA 13699.60165416 UG
Fishel | 2021 | 2021 | LUG - TBD56 | PRE-09361.321 | PRE-09361.321 | LUG WHA 13916.91386005 | LUG WHA 13916.91386005 | 13916 | LAKE RUBY | Lateral Hardening-Fuse-91386005 | Lateral Hardening-Fuse-91386005 | WHA | 0.52822 | 36 | 199 | 2021-07-01 | 2021-10-01 | 2021-12-01 | N/A | 4500282909 | TBD |  | CKT: 13916 - 91386005 | CKT: 13916 - 91386005 | 2310757 | LUG WHA 13916.91386005 OH | 2310762 | LUG WHA 13916.91386005 UG | 2310757 | LUG WHA 13916.91386005 OH | 2310762 | LUG WHA 13916.91386005 UG
Fishel | 2021 | 2021 | LUG - TBD57 | PRE-09361.322 | PRE-09361.322 | LUG WHA 13314.10567076 | LUG WHA 13314.10567076 | 13314 | EAST WINTER HAVEN | Lateral Hardening-Fuse-10567076 | Lateral Hardening-Fuse-10567076 | WHA | 0.42443 | 32 | 89 | 2021-07-01 | 2022 | 2022 | N/A | 4500282909 | TBD |  | CKT: 13314 - 10567076 | CKT: 13314 - 10567076 | 2310764 | LUG WHA 13314.10567076 OH | 2310765 | LUG WHA 13314.10567076 UG | 2310764 | LUG WHA 13314.10567076 OH | 2310765 | LUG WHA 13314.10567076 UG
Fishel | 2021 | 2021 | LUG - TBD58 | PRE-09361.323 | PRE-09361.323 | LUG WHA 13296.10562361 | LUG WHA 13296.10562361 | 13296 | JAN PHYL | Lateral Hardening-Fuse-10562361 | Lateral Hardening-Fuse-10562361 | WHA | 0.225 | 19 | 37 | 2021-07-01 | 2022 | 2022 | N/A | 4500282909 | TBD |  | CKT: 13296 - 10562361 | CKT: 13296 - 10562361 | 2310767 | LUG WHA 13296.10562361 OH | 2310770 | LUG WHA 13296.10562361 UG | 2310767 | LUG WHA 13296.10562361 OH | 2310770 | LUG WHA 13296.10562361 UG
Fishel | 2021 | 2021 | LUG - TBD59 | PRE-09361.324 | PRE-09361.324 | LUG WHA 13297.10560432 | LUG WHA 13297.10560432 | 13297 | JAN PHYL | Lateral Hardening-Fuse-10560432 | Lateral Hardening-Fuse-10560432 | WHA | 0.43068 | 29 | 362 | 2021-08-01 | 2022 | 2022 | N/A | 4500282909 | TBD |  | CKT: 13297 - 10560432 | CKT: 13297 - 10560432 | 2310484 | LUG WHA 13297.10560432 OH | 2310488 | LUG WHA 13297.10560432 UG | 2310484 | LUG WHA 13297.10560432 OH | 2310488 | LUG WHA 13297.10560432 UG
Fishel | 2021 | 2021 | LUG - TBD60 | PRE-09361.325 | PRE-09361.325 | LUG WHA 13972.10618037 | LUG WHA 13972.10618037 | 13972 | LUCERNE PARK | Lateral Hardening-Fuse-10618037 | Lateral Hardening-Fuse-10618037 | WHA | 0.2517 | 13 | 1 | 2021-08-01 | 2022 | 2022 | N/A | 4500282909 | TBD |  | CKT: 13972 - 10618037 | CKT: 13972 - 10618037 | 2310771 | LUG WHA 13972.10618037 OH | 2310776 | LUG WHA 13972.10618037 UG | 2310771 | LUG WHA 13972.10618037 OH | 2310776 | LUG WHA 13972.10618037 UG
Fishel | 2021 | 2021 | LUG - TBD61 | PRE-09361.326 | PRE-09361.326 | LUG PCA 13724.10671283 | LUG PCA 13724.10671283 | 13724 | GALLAGHER ROAD | Lateral Hardening-Fuse-10671283 | Lateral Hardening-Fuse-10671283 | PCA | 0.38011 | 13 | 77 | 2021-08-01 | 2022 | 2022 | N/A | 4500282909 | TBD |  | CKT: 13724 - 10671283 | CKT: 13724 - 10671283 | 2310778 | LUG PCA 13724.10671283 OH | 2310782 | LUG PCA 13724.10671283 UG | 2310778 | LUG PCA 13724.10671283 OH | 2310782 | LUG PCA 13724.10671283 UG
Fishel | 2021 | 2021 | LUG - TBD62 | PRE-09361.327 | PRE-09361.327 | LUG PCA 13722.60360851 | LUG PCA 13722.60360851 | 13722 | GALLAGHER ROAD | Lateral Hardening-Fuse-60360851 | Lateral Hardening-Fuse-60360851 | PCA | 0.21288 | 17 | 124 | 2021-09-01 | 2022 | 2022 | N/A | 4500282909 | TBD |  | CKT: 13722 - 60360851 | CKT: 13722 - 60360851 | 2310412 | LUG PCA 13722.60360851 OH | 2310417 | LUG PCA 13722.60360851 UG | 2310412 | LUG PCA 13722.60360851 OH | 2310417 | LUG PCA 13722.60360851 UG
Fishel | 2021 | 2021 | LUG - TBD63 | PRE-09361.328 | PRE-09361.328 | LUG PCA 13268.91633548 | LUG PCA 13268.91633548 | 13268 | J.D. PAGE | Lateral Hardening-Fuse-91633548 | Lateral Hardening-Fuse-91633548 | PCA | 0.8911 | 48 | 216 | 2021-09-01 | 2022 | 2022 | N/A | 4500282909 | TBD |  | CKT: 13268 - 91633548 | CKT: 13268 - 91633548 | 2310784 | LUG PCA 13268.91633548 OH | 2310785 | LUG PCA 13268.91633548 UG | 2310784 | LUG PCA 13268.91633548 OH | 2310785 | LUG PCA 13268.91633548 UG
Fishel | 2021 | 2021 | LUG - TBD64 | PRE-09361.329 | PRE-09361.329 | LUG PCA 13724.10671319 | LUG PCA 13724.10671319 | 13724 | GALLAGHER ROAD | Lateral Hardening-Fuse-10671319 | Lateral Hardening-Fuse-10671319 | PCA | 1.7574 | 83 | 181 | 2021-09-01 | 2022 | 2022 | N/A | 4500282909 | TBD |  | CKT: 13724 - 10671319 | CKT: 13724 - 10671319 | 2310790 | LUG PCA 13724.10671319 OH | 2310795 | LUG PCA 13724.10671319 UG | 2310790 | LUG PCA 13724.10671319 OH | 2310795 | LUG PCA 13724.10671319 UG
Fishel | 2021 | 2021 | LUG - TBD65 | PRE-09361.330 | PRE-09361.330 | LUG PCA 13243.10791853 | LUG PCA 13243.10791853 | 13243 | WILSON | Lateral Hardening-Fuse-10791853 | Lateral Hardening-Fuse-10791853 | PCA | 0.42102 | 31 | 99 | 2021-09-01 | 2022 | 2022 | N/A | 4500282909 | TBD |  | CKT: 13243 - 10791853 | CKT: 13243 - 10791853 | 2310471 | LUG PCA 13243.10791853 OH | 2310475 | LUG PCA 13243.10791853 UG | 2310471 | LUG PCA 13243.10791853 OH | 2310475 | LUG PCA 13243.10791853 UG
Fishel | 2021 | 2021 | LUG - TBD66 | PRE-09361.331 | PRE-09361.331 | LUG PCA 13724.10671334 | LUG PCA 13724.10671334 | 13724 | GALLAGHER ROAD | Lateral Hardening-Fuse-10671334 | Lateral Hardening-Fuse-10671334 | PCA | 0.57254 | 31 | 120 | 2021-09-01 | 2022 | 2022 | N/A | 4500282909 | TBD |  | CKT: 13724 - 10671334 | CKT: 13724 - 10671334 | 2310797 | LUG PCA 13724.10671334 OH | 2310799 | LUG PCA 13724.10671334 UG | 2310797 | LUG PCA 13724.10671334 OH | 2310799 | LUG PCA 13724.10671334 UG
Fishel | 2021 | 2021 | LUG - TBD67 | PRE-09361.332 | PRE-09361.332 | LUG PCA 13243.91351288 | LUG PCA 13243.91351288 | 13243 | WILSON | Lateral Hardening-Fuse-91351288 | Lateral Hardening-Fuse-91351288 | PCA | 0.28617 | 18 | 223 | 2021-09-01 | 2022 | 2022 | N/A | 4500282909 | TBD |  | CKT: 13243 - 91351288 | CKT: 13243 - 91351288 | 2310479 | LUG PCA 13243.91351288 OH | 2310480 | LUG PCA 13243.91351288 UG | 2310479 | LUG PCA 13243.91351288 OH | 2310480 | LUG PCA 13243.91351288 UG
Fishel | 2021 | 2021 | LUG - TBD68 | PRE-09361.333 | PRE-09361.333 | LUG PCA 13655.90431393 | LUG PCA 13655.90431393 | 13655 | HAMPTON | Lateral Hardening-Fuse-90431393 | Lateral Hardening-Fuse-90431393 | PCA | 1.2312 | 70 | 298 | 2021-09-01 | 2022 | 2022 | N/A | 4500282909 | TBD |  | CKT: 13655 - 90431393 | CKT: 13655 - 90431393 | 2310803 | LUG PCA 13655.90431393 OH | 2310807 | LUG PCA 13655.90431393 UG | 2310803 | LUG PCA 13655.90431393 OH | 2310807 | LUG PCA 13655.90431393 UG
Fishel | 2021 | 2021 | LUG - TBD69 | PRE-09361.334 | PRE-09361.334 | LUG PCA 13243.90684154 | LUG PCA 13243.90684154 | 13243 | WILSON | Lateral Hardening-Fuse-90684154 | Lateral Hardening-Fuse-90684154 | PCA | 0.22841 | 19 | 7 | 2021-09-01 | 2022 | 2022 | N/A | 4500282909 | TBD |  | CKT: 13243 - 90684154 | CKT: 13243 - 90684154 | 2310810 | LUG PCA 13243.90684154 OH | 2310812 | LUG PCA 13243.90684154 UG | 2310810 | LUG PCA 13243.90684154 OH | 2310812 | LUG PCA 13243.90684154 UG
Fishel | 2021 | 2021 | LUG - TBD70 | PRE-09361.335 | PRE-09361.335 | LUG PCA 13268.10705945 | LUG PCA 13268.10705945 | 13268 | J.D. PAGE | Lateral Hardening-Fuse-10705945 | Lateral Hardening-Fuse-10705945 | PCA | 1.4027 | 67 | 76 | 2021-10-01 | 2022 | 2022 | N/A | 4500282909 | TBD |  | CKT: 13268 - 10705945 | CKT: 13268 - 10705945 | 2310816 | LUG PCA 13268.10705945 OH | 2310818 | LUG PCA 13268.10705945 UG | 2310816 | LUG PCA 13268.10705945 OH | 2310818 | LUG PCA 13268.10705945 UG
Fishel | 2021 | 2021 | LUG - TBD71 | PRE-09361.336 | PRE-09361.336 | LUG PCA 13724.10671229 | LUG PCA 13724.10671229 | 13724 | GALLAGHER ROAD | Lateral Hardening-Fuse-10671229 | Lateral Hardening-Fuse-10671229 | PCA | 0.29678 | 16 | 9 | 2021-12-01 | 2022 | 2022 | N/A | 4500282909 | TBD |  | CKT: 13724 - 10671229 | CKT: 13724 - 10671229 | 2310819 | LUG PCA 13724.10671229 OH | 2310822 | LUG PCA 13724.10671229 UG | 2310819 | LUG PCA 13724.10671229 OH | 2310822 | LUG PCA 13724.10671229 UG
Fishel | 2021 | 2021 | LUG - TBD72 | PRE-09361.337 | PRE-09361.337 | LUG PCA 13268.92962459 | LUG PCA 13268.92962459 | 13268 | J.D. PAGE | Lateral Hardening-Fuse-92962459 | Lateral Hardening-Fuse-92962459 | PCA | 0.43333 | 28 | 48 | 2021-11-01 | 2022 | 2022 | N/A | 4500282909 | TBD |  | CKT: 13268 - 92962459 | CKT: 13268 - 92962459 | 2310824 | LUG PCA 13268.92962459 OH | 2310826 | LUG PCA 13268.92962459 UG | 2310824 | LUG PCA 13268.92962459 OH | 2310826 | LUG PCA 13268.92962459 UG
Fishel | 2021 | 2021 | LUG - TBD73 | PRE-09361.338 | PRE-09361.338 | LUG PCA 13724.93103251 | LUG PCA 13724.93103251 | 13724 | GALLAGHER ROAD | Lateral Hardening-Fuse-93103251 | Lateral Hardening-Fuse-93103251 | PCA | 0.44072 | 29 | 30 | 2021-11-01 | 2022 | 2022 | N/A | 4500282909 | TBD |  | CKT: 13724 - 93103251 | CKT: 13724 - 93103251 | 2310827 | LUG PCA 13724.93103251 OH | 2310829 | LUG PCA 13724.93103251 UG | 2310827 | LUG PCA 13724.93103251 OH | 2310829 | LUG PCA 13724.93103251 UG
Fishel | 2021 | 2021 | LUG - TBD74 | PRE-09361.339 | PRE-09361.339 | LUG PCA 13243.90586047 | LUG PCA 13243.90586047 | 13243 | WILSON | Lateral Hardening-Fuse-90586047 | Lateral Hardening-Fuse-90586047 | PCA | 0.27405 | 17 | 21 | 2021-12-01 | 2022 | 2022 | N/A | 4500282909 | TBD |  | CKT: 13243 - 90586047 | CKT: 13243 - 90586047 | 2310831 | LUG PCA 13243.90586047 OH | 2310832 | LUG PCA 13243.90586047 UG | 2310831 | LUG PCA 13243.90586047 OH | 2310832 | LUG PCA 13243.90586047 UG
Fishel | 2021 | 2021 | LUG - TBD75 | PRE-09361.340 | PRE-09361.340 | LUG PCA 13724.91049435 | LUG PCA 13724.91049435 | 13724 | GALLAGHER ROAD | Lateral Hardening-Fuse-91049435 | Lateral Hardening-Fuse-91049435 | PCA | 1.9932 | 103 | 97 | 2021-09-01 | 2022 | 2022 | N/A | 4500282909 | TBD |  | CKT: 13724 - 91049435 | CKT: 13724 - 91049435 | 2310833 | LUG PCA 13724.91049435 OH | 2310834 | LUG PCA 13724.91049435 UG | 2310833 | LUG PCA 13724.91049435 OH | 2310834 | LUG PCA 13724.91049435 UG
Enercon | 2021 | 2021 | LUG - TBD497 | PRE-09361.135 | PRE-09361.135 | LUG WSA 13162.92185426 | LUG WSA 13162.92185426 | 13162 | MATANZAS | Lateral Hardening-Fuse-92185426 | Lateral Hardening-Fuse-92185426 | WSA | 0.36572 | 26 | 19 | 2021-01-01 | 2021-09-01 | 2021-12-01 | N/A | 4500279866 | TBD |  | CKT: 13162 - 92185426 | CKT: 13162 - 92185426 | 2304567 | LUG WSA 13162.92185426 OH | 2304570 | LUG WSA 13162.92185426 UG | 2304567 | LUG WSA 13162.92185426 OH | 2304570 | LUG WSA 13162.92185426 UG
Enercon | 2021 | 2021 | LUG - TBD496 | PRE-09361.71 | PRE-09361.71 | DNU LUG WSA 13605.90568909 | LUG WSA 13605.91052996 | 13605 | MACDILL | DNU Lateral Hardening-Fuse-90568909 | Lateral Hardening-Fuse-91052996 | WSA | [6 empty] | 4500274705 | N/A | N/A | LUG C001 | N/A | CKT: 13605 - 91052996 | N/A | N/A | N/A | N/A | 2273278 | LUG WSA 13605.91052996 OH | 2273280 | LUG WSA 13605.91052996 UG | Combined with PRE-09361.71 (FID 91052996) & LUG-TBD526 (FID 90427351)
Enercon | 2021 | 2021 | LUG - TBD498 | PRE-09361.136 | PRE-09361.136 | LUG WSA 13194.90645535 | LUG WSA 13194.90645535 | 13194 | DOUBLE BRANCH | Lateral Hardening-Fuse-90645535 | Lateral Hardening-Fuse-90645535 | WSA | 1.0994 | 50 | 285 | 2021-01-01 | 2021-07-01 | 2021-12-01 | N/A | 4500279866 | TBD |  | CKT: 13194 - 90645535 | CKT: 13194 - 90645535 | 2304573 | LUG WSA 13194.90645535 OH | 2304576 | LUG WSA 13194.90645535 UG | 2304573 | LUG WSA 13194.90645535 OH | 2304576 | LUG WSA 13194.90645535 UG
Enercon | 2021 | 2021 | LUG - TBD499 | PRE-09361.137 | PRE-09361.137 | LUG WSA 13079.60077624 | LUG WSA 13079.60077624 | 13079 | COOLIDGE | Lateral Hardening-Fuse-60077624 | Lateral Hardening-Fuse-60077624 | WSA | 0.33655 | 30 | 58 | 2021-01-01 | 2021-08-01 | 2021-12-01 | N/A | 4500279866 | TBD |  | CKT: 13079 - 60077624 | CKT: 13079 - 60077624 | 2304579 | LUG WSA 13079.60077624 OH | 2304581 | LUG WSA 13079.60077624 UG | 2304579 | LUG WSA 13079.60077624 OH | 2304581 | LUG WSA 13079.60077624 UG
Enercon | 2021 | 2021 | LUG - TBD500 | PRE-09361.138 | PRE-09361.138 | LUG WSA 13586.91748729 | LUG WSA 13586.91748729 | 13586 | DALE MABRY | Lateral Hardening-Fuse-91748729 | Lateral Hardening-Fuse-91748729 | WSA | 0.6714 | 42 | 45 | 2021-01-01 | 2021-08-01 | 2021-11-01 | N/A | 4500279866 | TBD |  | CKT: 13586 - 91748729 | CKT: 13586 - 91748729 | 2304584 | LUG WSA 13586.91748729 OH | 2304586 | LUG WSA 13586.91748729 UG | 2304584 | LUG WSA 13586.91748729 OH | 2304586 | LUG WSA 13586.91748729 UG
Enercon | 2021 | 2021 | LUG - TBD501 | PRE-09361.139 | PRE-09361.139 | LUG WSA 13162.10158432 | LUG WSA 13162.10158432 | 13162 | MATANZAS | Lateral Hardening-Fuse-10158432 | Lateral Hardening-Fuse-10158432 | WSA | 0.16439 | 10 | 61 | 2021-01-01 | 2021-10-01 | 2021-12-01 | N/A | 4500279866 | TBD |  | CKT: 13162 - 10158432 | CKT: 13162 - 10158432 | 2304589 | LUG WSA 13162.10158432 OH | 2304590 | LUG WSA 13162.10158432 UG | 2304589 | LUG WSA 13162.10158432 OH | 2304590 | LUG WSA 13162.10158432 UG
Enercon | 2021 | 2021 | LUG - TBD502 | PRE-09361.140 | PRE-09361.140 | LUG WSA 13864.10310477 | LUG WSA 13864.10310477 | 13864 | PATTERSON ROAD | Lateral Hardening-Fuse-10310477 | Lateral Hardening-Fuse-10310477 | WSA | 0.7108 | 57 | 18 | 2021-01-01 | TBD |  | N/A | 4500279866 | TBD |  | CKT: 13864 - 10310477 | CKT: 13864 - 10310477 | 2304592 | LUG WSA 13864.10310477 OH | 2304593 | LUG WSA 13864.10310477 UG | 2304592 | LUG WSA 13864.10310477 OH | 2304593 | LUG WSA 13864.10310477 UG
Enercon | 2021 | 2021 | LUG - TBD503 | PRE-09361.141 | PRE-09361.141 | LUG WSA 13113.92909503 | LUG WSA 13113.92909503 | 13113 | MANHATTAN | Lateral Hardening-Fuse-92909503 | Lateral Hardening-Fuse-92909503 | WSA | 0.072538 | 9 | 215 | 2021-01-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13113 - 92909503 | CKT: 13113 - 92909503 | 2304596 | LUG WSA 13113.92909503 OH | 2304599 | LUG WSA 13113.92909503 UG | 2304596 | LUG WSA 13113.92909503 OH | 2304599 | LUG WSA 13113.92909503 UG
Enercon | 2021 | 2021 | LUG - TBD504 | PRE-09361.142 | PRE-09361.142 | LUG WSA 13516.60169592 | LUG WSA 13516.60169592 | 13516 | GEORGE ROAD | Lateral Hardening-Fuse-60169592 | Lateral Hardening-Fuse-60169592 | WSA | 0.26042 | 19 | 11 | 2021-01-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13516 - 60169592 | CKT: 13516 - 60169592 | 2304601 | LUG WSA 13516.60169592 OH | 2304602 | LUG WSA 13516.60169592 UG | 2304601 | LUG WSA 13516.60169592 OH | 2304602 | LUG WSA 13516.60169592 UG
Enercon | 2021 | 2021 | LUG - TBD505 | PRE-09361.143 | PRE-09361.143 | LUG WSA 13192.90932106 | LUG WSA 13192.90932106 | 13192 | DOUBLE BRANCH | Lateral Hardening-Fuse-90932106 | Lateral Hardening-Fuse-90932106 | WSA | 0.19318 | 13 | 2 | 2021-01-01 |  |  | N/A | 4500279866 | TBD | LUG C044 | CKT: 13192 - 90932106 | CKT: 13192 - 90932106 | 2308106 | LUG WSA 13192.90932106 OH | 2308108 | LUG WSA 13192.90932106 UG | 2308106 | LUG WSA 13192.90932106 OH | 2308108 | LUG WSA 13192.90932106 UG | Combined with PRE-09361.157 (FID 90932283)
Enercon | 2021 | 2021 | LUG - TBD506 | PRE-09361.144 | PRE-09361.144 | LUG WSA 13333.91785740 | LUG WSA 13333.91785740 | 13333 | WATERS AVENUE | Lateral Hardening-Fuse-91785740 | Lateral Hardening-Fuse-91785740 | WSA | 0.23277 | 26 | 13 | 2021-01-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13333 - 91785740 | CKT: 13333 - 91785740 | 2304604 | LUG WSA 13333.91785740 OH | 2304606 | LUG WSA 13333.91785740 UG | 2304604 | LUG WSA 13333.91785740 OH | 2304606 | LUG WSA 13333.91785740 UG
Enercon | 2021 | 2021 | LUG - TBD507 | PRE-09361.145 | PRE-09361.145 | LUG WSA 13863.60279838 | LUG WSA 13863.60279838 | 13863 | PATTERSON ROAD | Lateral Hardening-Fuse-60279838 | Lateral Hardening-Fuse-60279838 | WSA | 0.46989 | 32 | 259 | 2021-01-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13863 - 60279838 | CKT: 13863 - 60279838 | 2304611 | LUG WSA 13863.60279838 OH | 2304613 | LUG WSA 13863.60279838 UG | 2304611 | LUG WSA 13863.60279838 OH | 2304613 | LUG WSA 13863.60279838 UG
Enercon | 2021 | 2021 | LUG - TBD508 | PRE-09361.146 | PRE-09361.146 | LUG WSA 13109.90643551 | LUG WSA 13109.90643551 | 13109 | MANHATTAN | Lateral Hardening-Fuse-90643551 | Lateral Hardening-Fuse-90643551 | WSA | 0.66761 | 50 | 95 | 2021-01-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13109 - 90643551 | CKT: 13109 - 90643551 | 2304615 | LUG WSA 13109.90643551 OH | 2304617 | LUG WSA 13109.90643551 UG | 2304615 | LUG WSA 13109.90643551 OH | 2304617 | LUG WSA 13109.90643551 UG
Enercon | 2021 | 2021 | LUG - TBD509 | PRE-09361.147 | PRE-09361.147 | LUG WSA 13332.91700188 | LUG WSA 13332.91700188 | 13332 | WATERS AVENUE | Lateral Hardening-Fuse-91700188 | Lateral Hardening-Fuse-91700188 | WSA | 0.10833 | 10 | 60 | 2021-01-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13332 - 91700188 | CKT: 13332 - 91700188 | 2304621 | LUG WSA 13332.91700188 OH | 2304622 | LUG WSA 13332.91700188 UG | 2304621 | LUG WSA 13332.91700188 OH | 2304622 | LUG WSA 13332.91700188 UG
Enercon | 2021 | 2021 | LUG - TBD510 | PRE-09361.148 | PRE-09361.148 | LUG WSA 13756.90207831 | LUG WSA 13756.90207831 | 13756 | GRANADA | Lateral Hardening-Fuse-90207831 | Lateral Hardening-Fuse-90207831 | WSA | 0.37917 | 36 | 181 | 2021-01-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13756 - 90207831 | CKT: 13756 - 90207831 | 2304624 | LUG WSA 13756.90207831 OH | 2304626 | LUG WSA 13756.90207831 UG | 2304624 | LUG WSA 13756.90207831 OH | 2304626 | LUG WSA 13756.90207831 UG
Enercon | 2021 | 2021 | LUG - TBD511 | PRE-09361.149 | PRE-09361.149 | LUG WSA 13672.60106849 | LUG WSA 13672.60106849 | 13672 | MEADOW PARK | Lateral Hardening-Fuse-60106849 | Lateral Hardening-Fuse-60106849 | WSA | 0.2678 | 26 | 256 | 2021-01-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13672 - 60106849 | CKT: 13672 - 60106849 | 2304745 | LUG WSA 13672.60106849 OH | 2304747 | LUG WSA 13672.60106849 UG | 2304745 | LUG WSA 13672.60106849 OH | 2304747 | LUG WSA 13672.60106849 UG
Enercon | 2021 | 2021 | LUG - TBD512 | PRE-09361.150 | PRE-09361.150 | LUG WSA 13860.10307215 | LUG WSA 13860.10307215 | 13860 | PATTERSON ROAD | Lateral Hardening-Fuse-10307215 | Lateral Hardening-Fuse-10307215 | WSA | 0.27917 | 26 | 219 | 2021-01-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13860 - 10307215 | CKT: 13860 - 10307215 | 2304734 | LUG WSA 13860.10307215 OH | 2304736 | LUG WSA 13860.10307215 UG | 2304734 | LUG WSA 13860.10307215 OH | 2304736 | LUG WSA 13860.10307215 UG
Enercon | 2021 | 2021 | LUG - TBD513 | PRE-09361.151 | PRE-09361.151 | LUG WSA 13756.60165355 | LUG WSA 13756.60165355 | 13756 | GRANADA | Lateral Hardening-Fuse-60165355 | Lateral Hardening-Fuse-60165355 | WSA | 0.082955 | 12 | 55 | 2021-01-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13756 - 60165355 | CKT: 13756 - 60165355 | 2304892 | LUG WSA 13756.60165355 OH | 2304902 | LUG WSA 13756.60165355 UG | 2304892 | LUG WSA 13756.60165355 OH | 2304902 | LUG WSA 13756.60165355 UG
Enercon | 2021 | 2021 | LUG - TBD514 | PRE-09361.152 | PRE-09361.152 | LUG WSA 13672.10493801 | LUG WSA 13672.10493801 | 13672 | MEADOW PARK | Lateral Hardening-Fuse-10493801 | Lateral Hardening-Fuse-10493801 | WSA | 0.57973 | 43 | 368 | 2021-01-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13672 - 10493801 | CKT: 13672 - 10493801 | 2304907 | LUG WSA 13672.10493801 OH | 2304908 | LUG WSA 13672.10493801 UG | 2304907 | LUG WSA 13672.10493801 OH | 2304908 | LUG WSA 13672.10493801 UG
Enercon | 2021 | 2021 | LUG - TBD515 | PRE-09361.153 | PRE-09361.153 | LUG WSA 13864.10310468 | LUG WSA 13864.10310468 | 13864 | PATTERSON ROAD | Lateral Hardening-Fuse-10310468 | Lateral Hardening-Fuse-10310468 | WSA | 0.21061 | 22 | 28 | 2021-01-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13864 - 10310468 | CKT: 13864 - 10310468 | 2304909 | LUG WSA 13864.10310468 OH | 2304912 | LUG WSA 13864.10310468 UG | 2304909 | LUG WSA 13864.10310468 OH | 2304912 | LUG WSA 13864.10310468 UG
Enercon | 2021 | 2021 | LUG - TBD516 | PRE-09361.154 | PRE-09361.154 | LUG WSA 13864.10310497 | LUG WSA 13864.10310497 | 13864 | PATTERSON ROAD | Lateral Hardening-Fuse-10310497 | Lateral Hardening-Fuse-10310497 | WSA | 0.15 | 10 | 10 | 2021-01-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13864 - 10310497 | CKT: 13864 - 10310497 | 2304913 | LUG WSA 13864.10310497 OH | 2304914 | LUG WSA 13864.10310497 UG | 2304913 | LUG WSA 13864.10310497 OH | 2304914 | LUG WSA 13864.10310497 UG
Enercon | 2021 | 2021 | LUG - TBD517 | PRE-09361.155 | PRE-09361.155 | LUG WSA 13586.92442286 | LUG WSA 13586.92442286 | 13586 | DALE MABRY | Lateral Hardening-Fuse-92442286 | Lateral Hardening-Fuse-92442286 | WSA | 0.48902 | 40 | 180 | 2021-01-01 |  |  | N/A | 4500279866 | TBD | LUG C051 | CKT: 13586 - 92442286 | CKT: 13586 - 92442286 | 2308109 | LUG WSA 13586.92442286 OH | 2308110 | LUG WSA 13586.92442286 UG | 2308109 | LUG WSA 13586.92442286 OH | 2308110 | LUG WSA 13586.92442286 UG | Combined with PRE-09361.175 (FID 10255361)
Enercon | 2021 | 2021 | LUG - TBD518 | PRE-09361.156 | PRE-09361.156 | LUG WSA 13672.91971930 | LUG WSA 13672.91971930 | 13672 | MEADOW PARK | Lateral Hardening-Fuse-91971930 | Lateral Hardening-Fuse-91971930 | WSA | 0.1947 | 19 | 27 | 2021-01-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13672 - 91971930 | CKT: 13672 - 91971930 | 2304916 | LUG WSA 13672.91971930 OH | 2304918 | LUG WSA 13672.91971930 UG | 2304916 | LUG WSA 13672.91971930 OH | 2304918 | LUG WSA 13672.91971930 UG
Enercon | 2021 | 2021 | LUG - TBD519 | PRE-09361.143 | PRE-09361.157 | DNU LUG WSA 13192.90932283 | LUG WSA 13192.90932106 | 13192 | DOUBLE BRANCH | DNU Lateral Hardening-Fuse-90932283 | Lateral Hardening-Fuse-90932106 | WSA | 0.15379 | 8 | 2 | 2021-01-01 |  |  | N/A | 4500279866 | TBD | LUG C044 | N/A | CKT: 13192 - 90932106 | N/A | N/A | N/A | N/A | 2308106 | LUG WSA 13192.90932106 OH | 2308108 | LUG WSA 13192.90932106 UG | Combined with PRE-09361.143 (FID 90932106)
Enercon | 2021 | 2021 | LUG - TBD520 | PRE-09361.158 | PRE-09361.158 | LUG WSA 13678.10254063 | LUG WSA 13678.10254063 | 13678 | TURKEY FORD | Lateral Hardening-Fuse-10254063 | Lateral Hardening-Fuse-10254063 | WSA | 0.275 | 18 | 11 | 2021-01-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13678 - 10254063 | CKT: 13678 - 10254063 | 2304919 | LUG WSA 13678.10254063 OH | 2304920 | LUG WSA 13678.10254063 UG | 2304919 | LUG WSA 13678.10254063 OH | 2304920 | LUG WSA 13678.10254063 UG
Enercon | 2021 | 2021 | LUG - TBD521 | PRE-09361.159 | PRE-09361.159 | LUG WSA 13141.10147344 | LUG WSA 13141.10147344 | 13141 | HYDE PARK | Lateral Hardening-Fuse-10147344 | Lateral Hardening-Fuse-10147344 | WSA | 0.098485 | 7 | 12 | 2021-01-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13141 - 10147344 | CKT: 13141 - 10147344 | 2304739 | LUG WSA 13141.10147344 OH | 2304742 | LUG WSA 13141.10147344 UG | 2304739 | LUG WSA 13141.10147344 OH | 2304742 | LUG WSA 13141.10147344 UG
Enercon | 2021 | 2021 | LUG - TBD522 | PRE-09361.160 | PRE-09361.160 | LUG WSA 13756.10589587 | LUG WSA 13756.10589587 | 13756 | GRANADA | Lateral Hardening-Fuse-10589587 | Lateral Hardening-Fuse-10589587 | WSA | 0.14356 | 13 | 8 | 2021-01-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13756 - 10589587 | CKT: 13756 - 10589587 | 2304921 | LUG WSA 13756.10589587 OH | 2304922 | LUG WSA 13756.10589587 UG | 2304921 | LUG WSA 13756.10589587 OH | 2304922 | LUG WSA 13756.10589587 UG
Enercon | 2021 | 2021 | LUG - TBD523 | PRE-09361.161 | PRE-09361.161 | LUG WSA 13864.10310505 | LUG WSA 13864.10310505 | 13864 | PATTERSON ROAD | Lateral Hardening-Fuse-10310505 | Lateral Hardening-Fuse-10310505 | WSA | 0.50568 | 41 | 3 | 2021-01-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13864 - 10310505 | CKT: 13864 - 10310505 | 2304729 | LUG WSA 13864.10310505 OH | 2304731 | LUG WSA 13864.10310505 UG | 2304729 | LUG WSA 13864.10310505 OH | 2304731 | LUG WSA 13864.10310505 UG
Enercon | 2021 | 2021 | LUG - TBD524 | PRE-09361.162 | PRE-09361.162 | LUG WSA 13860.10307212 | LUG WSA 13860.10307212 | 13860 | PATTERSON ROAD | Lateral Hardening-Fuse-10307212 | Lateral Hardening-Fuse-10307212 | WSA | 0.25227 | 28 | 2 | 2021-01-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13860 - 10307212 | CKT: 13860 - 10307212 | 2304744 | LUG WSA 13860.10307212 OH | 2304746 | LUG WSA 13860.10307212 UG | 2304744 | LUG WSA 13860.10307212 OH | 2304746 | LUG WSA 13860.10307212 UG
Enercon | 2021 | 2021 | LUG - TBD525 | PRE-09361.163 | PRE-09361.163 | LUG WSA 13111.60072751 | LUG WSA 13111.60072751 | 13111 | MANHATTAN | Lateral Hardening-Fuse-60072751 | Lateral Hardening-Fuse-60072751 | WSA | 0.20379 | 17 | 18 | 2021-01-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13111 - 60072751 | CKT: 13111 - 60072751 | 2304923 | LUG WSA 13111.60072751 OH | 2304925 | LUG WSA 13111.60072751 UG | 2304923 | LUG WSA 13111.60072751 OH | 2304925 | LUG WSA 13111.60072751 UG
Enercon | 2021 | 2021 | LUG - TBD526 | PRE-09361.71 | PRE-09361.71 | DNU LUG WSA 13605.90427351 | LUG WSA 13605.91052996 | 13605 | MACDILL | DNU Lateral Hardening-Fuse-91052996 | Lateral Hardening-Fuse-91052996 | WSA | 0 | 29 | 50 | 2021-01-01 |  |  | 4500274705 | N/A | N/A | LUG C001 | N/A | CKT: 13605 - 91052996 | N/A | N/A | N/A | N/A | 2273278 | LUG WSA 13605.91052996 OH | 2273280 | LUG WSA 13605.91052996 UG | Combined with LUG-TBD496 (FID 90568909) & PRE-09361.71 (FID 90427351)
Enercon | 2021 | 2021 | LUG - TBD527 | PRE-09361.164 | PRE-09361.164 | LUG WSA 13333.10007588 | LUG WSA 13333.10007588 | 13333 | WATERS AVENUE | Lateral Hardening-Fuse-10007588 | Lateral Hardening-Fuse-10007588 | WSA | 0.16004 | 16 | 16 | 2021-02-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13333 - 10007588 | CKT: 13333 - 10007588 | 2304749 | LUG WSA 13333.10007588 OH | 2304751 | LUG WSA 13333.10007588 UG | 2304749 | LUG WSA 13333.10007588 OH | 2304751 | LUG WSA 13333.10007588 UG
Enercon | 2021 | 2021 | LUG - TBD528 | PRE-09361.165 | PRE-09361.165 | LUG WSA 13164.90252716 | LUG WSA 13164.90252716 | 13164 | MATANZAS | Lateral Hardening-Fuse-90252716 | Lateral Hardening-Fuse-90252716 | WSA | 0.21572 | 15 | 59 | 2021-02-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13164 - 90252716 | CKT: 13164 - 90252716 | 2304926 | LUG WSA 13164.90252716 OH | 2304927 | LUG WSA 13164.90252716 UG | 2304926 | LUG WSA 13164.90252716 OH | 2304927 | LUG WSA 13164.90252716 UG
Enercon | 2021 | 2021 | LUG - TBD529 | PRE-09361.166 | PRE-09361.166 | LUG WSA 13491.91827162 | LUG WSA 13491.91827162 | 13491 | JACKSON ROAD | Lateral Hardening-Fuse-91827162 | Lateral Hardening-Fuse-91827162 | WSA | 0.2392 | 21 | 34 | 2021-02-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13491 - 91827162 | CKT: 13491 - 91827162 | 2304928 | LUG WSA 13491.91827162 OH | 2304930 | LUG WSA 13491.91827162 UG | 2304928 | LUG WSA 13491.91827162 OH | 2304930 | LUG WSA 13491.91827162 UG
Enercon | 2021 | 2021 | LUG - TBD530 | PRE-09361.167 | PRE-09361.167 | LUG WSA 13113.90422522 | LUG WSA 13113.90422522 | 13113 | MANHATTAN | Lateral Hardening-Fuse-90422522 | Lateral Hardening-Fuse-90422522 | WSA | 0.10985 | 6 | 3 | 2021-02-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13113 - 90422522 | CKT: 13113 - 90422522 | 2304932 | LUG WSA 13113.90422522 OH | 2304934 | LUG WSA 13113.90422522 UG | 2304932 | LUG WSA 13113.90422522 OH | 2304934 | LUG WSA 13113.90422522 UG
Enercon | 2021 | 2021 | LUG - TBD531 | PRE-09361.168 | PRE-09361.168 | LUG WSA 13756.10589595 | LUG WSA 13756.10589595 | 13756 | GRANADA | Lateral Hardening-Fuse-10589595 | Lateral Hardening-Fuse-10589595 | WSA | 0.24924 | 22 | 93 | 2021-02-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13756 - 10589595 | CKT: 13756 - 10589595 | 2304936 | LUG WSA 13756.10589595 OH | 2304937 | LUG WSA 13756.10589595 UG | 2304936 | LUG WSA 13756.10589595 OH | 2304937 | LUG WSA 13756.10589595 UG
Enercon | 2021 | 2021 | LUG - TBD532 | PRE-09361.169 | PRE-09361.169 | LUG WSA 13586.10255333 | LUG WSA 13586.10255333 | 13586 | DALE MABRY | Lateral Hardening-Fuse-10255333 | Lateral Hardening-Fuse-10255333 | WSA | 0.12159 | 9 | 4 | 2021-02-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13586 - 10255333 | CKT: 13586 - 10255333 | 2304730 | LUG WSA 13586.10255333 OH | 2304732 | LUG WSA 13586.10255333 UG | 2304730 | LUG WSA 13586.10255333 OH | 2304732 | LUG WSA 13586.10255333 UG
Enercon | 2021 | 2021 | LUG - TBD533 | PRE-09361.170 | PRE-09361.170 | LUG WSA 13428.90423835 | LUG WSA 13428.90423835 | 13428 | ROCKY CREEK | Lateral Hardening-Fuse-90423835 | Lateral Hardening-Fuse-90423835 | WSA | 0.26326 | 16 | 208 | 2021-03-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13428 - 90423835 | CKT: 13428 - 90423835 | 2304755 | LUG WSA 13428.90423835 OH | 2304757 | LUG WSA 13428.90423835 UG | 2304755 | LUG WSA 13428.90423835 OH | 2304757 | LUG WSA 13428.90423835 UG
Enercon | 2021 | 2021 | LUG - TBD534 | PRE-09361.67 | PRE-09361.171 | DNU LUG WSA 13113.60340774 | LUG WSA 13113.90796385 | 13113 | MANHATTAN | DNU Lateral Hardening-Fuse-60340774 | Lateral Hardening-Fuse-90796385 | WSA | 0.20398 | 19 | 35 | 2021-03-01 |  |  | 4500274705 | N/A | N/A | LUG C021 | N/A | CKT: 13113 - 90796385 | N/A | N/A | N/A | N/A | 2273299 | LUG WSA 13113.90796385 OH | 2273301 | LUG WSA 13113.90796385 UG | Combined with PRE-09361.67 (FID 90796385)
Enercon | 2021 | 2021 | LUG - TBD535 | PRE-09361.172 | PRE-09361.172 | LUG WSA 13141.91575422 | LUG WSA 13141.91575422 | 13141 | HYDE PARK | Lateral Hardening-Fuse-91575422 | Lateral Hardening-Fuse-91575422 | WSA | 0.095455 | 8 | 34 | 2021-03-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13141 - 91575422 | CKT: 13141 - 91575422 | 2304938 | LUG WSA 13141.91575422 OH | 2304939 | LUG WSA 13141.91575422 UG | 2304938 | LUG WSA 13141.91575422 OH | 2304939 | LUG WSA 13141.91575422 UG
Enercon | 2021 | 2021 | LUG - TBD536 | PRE-09361.173 | PRE-09361.173 | LUG WSA 13678.90514672 | LUG WSA 13678.90514672 | 13678 | TURKEY FORD | Lateral Hardening-Fuse-90514672 | Lateral Hardening-Fuse-90514672 | WSA | 0.5358 | 29 | 9 | 2021-03-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13678 - 90514672 | CKT: 13678 - 90514672 | 2304733 | LUG WSA 13678.90514672 OH | 2304735 | LUG WSA 13678.90514672 UG | 2304733 | LUG WSA 13678.90514672 OH | 2304735 | LUG WSA 13678.90514672 UG
Enercon | 2021 | 2021 | LUG - TBD537 | PRE-09361.174 | PRE-09361.174 | LUG WSA 13164.10158912 | LUG WSA 13164.10158912 | 13164 | MATANZAS | Lateral Hardening-Fuse-10158912 | Lateral Hardening-Fuse-10158912 | WSA | 0.21023 | 19 | 236 | 2021-03-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13164 - 10158912 | CKT: 13164 - 10158912 | 2304900 | LUG WSA 13164.10158912 OH | 2304903 | LUG WSA 13164.10158912 UG | 2304900 | LUG WSA 13164.10158912 OH | 2304903 | LUG WSA 13164.10158912 UG
Enercon | 2021 | 2021 | LUG - TBD538 | PRE-09361.155 | PRE-09361.175 | DNU LUG WSA 13586.10255361 | LUG WSA 13586.92442286 | 13586 | DALE MABRY | DNU Lateral Hardening-Fuse-10255361 | Lateral Hardening-Fuse-92442286 | WSA | 0.28106 | 19 | 22 | 2021-03-01 |  |  | N/A | 4500279866 | TBD | LUG C051 | N/A | CKT: 13586 - 92442286 | N/A | N/A | N/A | N/A | 2308109 | LUG WSA 13586.92442286 OH | 2308110 | LUG WSA 13586.92442286 UG | Combined with PRE-09361.155 (FID 92442286)
Enercon | 2021 | 2021 | LUG - TBD539 | PRE-09361.176 | PRE-09361.176 | LUG WSA 13544.10053269 | LUG WSA 13544.10053269 | 13544 | CARROLLWOOD VILLAGE | Lateral Hardening-Fuse-10053269 | Lateral Hardening-Fuse-10053269 | WSA | 0.16174 | 16 | 19 | 2021-03-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13544 - 10053269 | CKT: 13544 - 10053269 | 2304718 | LUG WSA 13544.10053269 OH | 2304720 | LUG WSA 13544.10053269 UG | 2304718 | LUG WSA 13544.10053269 OH | 2304720 | LUG WSA 13544.10053269 UG
Enercon | 2021 | 2021 | LUG - TBD540 | PRE-09361.177 | PRE-09361.177 | LUG WSA 13864.60380454 | LUG WSA 13864.60380454 | 13864 | PATTERSON ROAD | Lateral Hardening-Fuse-60380454 | Lateral Hardening-Fuse-60380454 | WSA | 0.15795 | 13 | 1 | 2021-03-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13864 - 60380454 | CKT: 13864 - 60380454 | 2304759 | LUG WSA 13864.60380454 OH | 2304762 | LUG WSA 13864.60380454 UG | 2304759 | LUG WSA 13864.60380454 OH | 2304762 | LUG WSA 13864.60380454 UG
Enercon | 2021 | 2021 | LUG - TBD541 | PRE-09361.178 | PRE-09361.178 | LUG WSA 13141.92442350 | LUG WSA 13141.92442350 | 13141 | HYDE PARK | Lateral Hardening-Fuse-92442350 | Lateral Hardening-Fuse-92442350 | WSA | 0.087689 | 13 | 12 | 2021-03-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13141 - 92442350 | CKT: 13141 - 92442350 | 2304898 | LUG WSA 13141.92442350 OH | 2304899 | LUG WSA 13141.92442350 UG | 2304898 | LUG WSA 13141.92442350 OH | 2304899 | LUG WSA 13141.92442350 UG
Enercon | 2021 | 2021 | LUG - TBD542 | PRE-09361.179 | PRE-09361.179 | LUG WSA 13141.10147371 | LUG WSA 13141.10147371 | 13141 | HYDE PARK | Lateral Hardening-Fuse-10147371 | Lateral Hardening-Fuse-10147371 | WSA | 0.47027 | 49 | 94 | 2021-03-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13141 - 10147371 | CKT: 13141 - 10147371 | 2304894 | LUG WSA 13141.10147371 OH | 2304896 | LUG WSA 13141.10147371 UG | 2304894 | LUG WSA 13141.10147371 OH | 2304896 | LUG WSA 13141.10147371 UG
Enercon | 2021 | 2021 | LUG - TBD543 | PRE-09361.180 | PRE-09361.180 | LUG WSA 13678.10288738 | LUG WSA 13678.10288738 | 13678 | TURKEY FORD | Lateral Hardening-Fuse-10288738 | Lateral Hardening-Fuse-10288738 | WSA | 0.57784 | 28 | 4 | 2021-03-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13678 - 10288738 | CKT: 13678 - 10288738 | 2304890 | LUG WSA 13678.10288738 OH | 2304891 | LUG WSA 13678.10288738 UG | 2304890 | LUG WSA 13678.10288738 OH | 2304891 | LUG WSA 13678.10288738 UG
Enercon | 2021 | 2022 | LUG - TBD544 | PRE-09361.238 | PRE-09361.181 | DNU LUG WSA 13612.90440184 | LUG WSA 13612.92956326 | 13612 | EL PRADO | DNU Lateral Hardening-Fuse-90440184 | Lateral Hardening-Fuse-92956326 | WSA | 0.25208 | 16 | 170 | 2021-03-01 |  |  | N/A | 4500279866 | TBD | LUG C057 | N/A | CKT: 13612 - 92956326 | N/A | N/A | N/A | N/A | 2308129 | LUG WSA 13612.92956326 OH | 2308130 | LUG WSA 13612.92956326 UG | Combined with PRE-09361.238 (FID 92956326)
Enercon | 2021 | 2022 | LUG - TBD545 | PRE-09361.182 | PRE-09361.182 | LUG WSA 13533.91957169 | LUG WSA 13533.91957169 | 13533 | COOLIDGE | Lateral Hardening-Fuse-91957169 | Lateral Hardening-Fuse-91957169 | WSA | 0.24432 | 21 | 354 | 2021-03-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13533 - 91957169 | CKT: 13533 - 91957169 | 2304711 | LUG WSA 13533.91957169 OH | 2304715 | LUG WSA 13533.91957169 UG | 2304711 | LUG WSA 13533.91957169 OH | 2304715 | LUG WSA 13533.91957169 UG
Enercon | 2021 | 2022 | LUG - TBD546 | PRE-09361.256 | PRE-09361.183 | DNU LUG WSA 14030.60131389 | LUG WSA 14030.60125643 | 14030 | PAGLEN ROAD | DNU Lateral Hardening-Fuse-60131389 | Lateral Hardening-Fuse-60125643 | WSA | 0.15152 | 9 | 111 | 2021-03-01 |  |  | N/A | 4500279866 | TBD | LUG C045 | N/A | CKT: 14030 - 60125643 | N/A | N/A | N/A | N/A | 2308135 | LUG WSA 14030.60125643 OH | 2308136 | LUG WSA 14030.60125643 UG | Combined with PRE-09361.256 (FID 60125643)
Enercon | 2021 | 2022 | LUG - TBD547 | PRE-09361.184 | PRE-09361.184 | LUG WSA 13865.90531031 | LUG WSA 13865.90531031 | 13865 | PATTERSON ROAD | Lateral Hardening-Fuse-90531031 | Lateral Hardening-Fuse-90531031 | WSA | 0.26383 | 19 | 21 | 2021-04-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13865 - 90531031 | CKT: 13865 - 90531031 | 2304754 | LUG WSA 13865.90531031 OH | 2304756 | LUG WSA 13865.90531031 UG | 2304754 | LUG WSA 13865.90531031 OH | 2304756 | LUG WSA 13865.90531031 UG
Enercon | 2021 | 2022 | LUG - TBD548 | PRE-09361.185 | PRE-09361.185 | LUG WSA 13535.92983670 | LUG WSA 13535.92983670 | 13535 | CARROLLWOOD VILLAGE | Lateral Hardening-Fuse-92983670 | Lateral Hardening-Fuse-92983670 | WSA | 0.21269 | 14 | 164 | 2021-04-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13535 - 92983670 | CKT: 13535 - 92983670 | 2304883 | LUG WSA 13535.92983670 OH | 2304884 | LUG WSA 13535.92983670 UG | 2304883 | LUG WSA 13535.92983670 OH | 2304884 | LUG WSA 13535.92983670 UG
Enercon | 2021 | 2022 | LUG - TBD549 | PRE-09361.186 | PRE-09361.186 | LUG WSA 13589.93177909 | LUG WSA 13589.93177909 | 13589 | DALE MABRY | Lateral Hardening-Fuse-93177909 | Lateral Hardening-Fuse-93177909 | WSA | 0.11951 | 6 | 33 | 2021-04-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13589 - 93177909 | CKT: 13589 - 93177909 | 2304722 | LUG WSA 13589.93177909 OH | 2304724 | LUG WSA 13589.93177909 UG | 2304722 | LUG WSA 13589.93177909 OH | 2304724 | LUG WSA 13589.93177909 UG
Enercon | 2021 | 2022 | LUG - TBD550 | PRE-09361.247 | PRE-09361.187 | DNU LUG WSA 13522.91934653 | LUG WSA 13522.10392882 | 13522 | ROME AVENUE | DNU Lateral Hardening-Fuse-91934653 | Lateral Hardening-Fuse-10392882 | WSA | 0.47045 | 41 | 128 | 2021-04-01 |  |  | N/A | 4500279866 | TBD | LUG C058 | N/A | CKT: 13522 - 10392882 | N/A | N/A | N/A | N/A | 2308133 | LUG WSA 13522.10392882 OH | 2308134 | LUG WSA 13522.10392882 UG | Combined with PRE-09361.247 (FID 10392882) & PRE-09361.283 (FID 60305728)
Enercon | 2021 | 2022 | LUG - TBD551 | PRE-09361.188 | PRE-09361.188 | LUG WSA 13522.10392924 | LUG WSA 13522.10392924 | 13522 | ROME AVENUE | Lateral Hardening-Fuse-10392924 | Lateral Hardening-Fuse-10392924 | WSA | 0.11591 | 9 | 10 | 2021-04-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13522 - 10392924 | CKT: 13522 - 10392924 | 2304881 | LUG WSA 13522.10392924 OH | 2304882 | LUG WSA 13522.10392924 UG | 2304881 | LUG WSA 13522.10392924 OH | 2304882 | LUG WSA 13522.10392924 UG
Enercon | 2021 | 2022 | LUG - TBD552 | PRE-09361.189 | PRE-09361.189 | LUG WSA 13737.10297943 | LUG WSA 13737.10297943 | 13737 | CLEARVIEW | Lateral Hardening-Fuse-10297943 | Lateral Hardening-Fuse-10297943 | WSA | 0.20208 | 18 | 84 | 2021-04-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13737 - 10297943 | CKT: 13737 - 10297943 | 2304878 | LUG WSA 13737.10297943 OH | 2304879 | LUG WSA 13737.10297943 UG | 2304878 | LUG WSA 13737.10297943 OH | 2304879 | LUG WSA 13737.10297943 UG
Enercon | 2021 | 2022 | LUG - TBD553 | PRE-09361.190 | PRE-09361.190 | LUG WSA 14030.90886759 | LUG WSA 14030.90886759 | 14030 | PAGLEN ROAD | Lateral Hardening-Fuse-90886759 | Lateral Hardening-Fuse-90886759 | WSA | 0.53788 | 49 | 161 | 2021-04-01 |  |  | N/A | 4500279866 | TBD | LUG C053 | CKT: 14030 - 90886759 | CKT: 14030 - 90886759 | 2308111 | LUG WSA 14030.90886759 OH | 2308112 | LUG WSA 14030.90886759 UG | 2308111 | LUG WSA 14030.90886759 OH | 2308112 | LUG WSA 14030.90886759 UG | Combined with PRE-09361.206 (FID 90242104) & PRE-09361.257 (FID 92669080)
Enercon | 2021 | 2022 | LUG - TBD554 | PRE-09361.191 | PRE-09361.191 | LUG WSA 13207.90147316 | LUG WSA 13207.90147316 | 13207 | LOIS AVENUE | Lateral Hardening-Fuse-90147316 | Lateral Hardening-Fuse-90147316 | WSA | 0.20473 | 17 | 23 | 2021-04-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13207 - 90147316 | CKT: 13207 - 90147316 | 2304874 | LUG WSA 13207.90147316 OH | 2304876 | LUG WSA 13207.90147316 UG | 2304874 | LUG WSA 13207.90147316 OH | 2304876 | LUG WSA 13207.90147316 UG
Enercon | 2021 | 2022 | LUG - TBD555 | PRE-09361.208 | PRE-09361.192 | DNU LUG WSA 13207.90216846 | LUG WSA 13207.90613782 | 13207 | LOIS AVENUE | DNU Lateral Hardening-Fuse-90216846 | Lateral Hardening-Fuse-90613782 | WSA | 0.27178 | 23 | 99 | 2021-04-01 |  |  | N/A | 4500279866 | TBD | LUG C054 | N/A | CKT: 13207 - 90613782 | N/A | N/A | N/A | N/A | 2308117 | LUG WSA 13207.90613782 OH | 2308118 | LUG WSA 13207.90613782 UG | Combined with PRE-09361.208 (FID 90613782)
Enercon | 2021 | 2022 | LUG - TBD556 | PRE-09361.193 | PRE-09361.193 | LUG WSA 13059.60302601 | LUG WSA 13059.60302601 | 13059 | HIMES | Lateral Hardening-Fuse-60302601 | Lateral Hardening-Fuse-60302601 | WSA | 0.50701 | 51 | 291 | 2021-04-01 |  |  | N/A | 4500279866 | TBD | LUG C060 | CKT: 13059 - 60302601 | CKT: 13059 - 60302601 | 2308113 | LUG WSA 13059.60302601 OH | 2308114 | LUG WSA 13059.60302601 UG | 2308113 | LUG WSA 13059.60302601 OH | 2308114 | LUG WSA 13059.60302601 UG | Combined with PRE-09361.195 (FID 93006225)
Enercon | 2021 | 2022 | LUG - TBD557 | PRE-09361.194 | PRE-09361.194 | LUG WSA 13738.10298299 | LUG WSA 13738.10298299 | 13738 | CLEARVIEW | Lateral Hardening-Fuse-10298299 | Lateral Hardening-Fuse-10298299 | WSA | 0.31307 | 27 | 71 | 2021-04-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13738 - 10298299 | CKT: 13738 - 10298299 | 2304872 | LUG WSA 13738.10298299 OH | 2304873 | LUG WSA 13738.10298299 UG | 2304872 | LUG WSA 13738.10298299 OH | 2304873 | LUG WSA 13738.10298299 UG
Enercon | 2021 | 2022 | LUG - TBD558 | PRE-09361.193 | PRE-09361.195 | DNU LUG WSA 13059.93006225 | LUG WSA 13059.60302601 | 13059 | HIMES | DNU Lateral Hardening-Fuse-93006225 | Lateral Hardening-Fuse-60302601 | WSA | 0.28258 | 20 | 336 | 2021-05-01 |  |  | N/A | 4500279866 | TBD | LUG C060 | N/A | CKT: 13059 - 60302601 | N/A | N/A | N/A | N/A | 2308113 | LUG WSA 13059.60302601 OH | 2308114 | LUG WSA 13059.60302601 UG | Combined with PRE-09361.193 (FID 60302601)
Enercon | 2021 | 2022 | LUG - TBD559 | PRE-09361.196 | PRE-09361.196 | LUG WSA 13207.90146892 | LUG WSA 13207.90146892 | 13207 | LOIS AVENUE | Lateral Hardening-Fuse-90146892 | Lateral Hardening-Fuse-90146892 | WSA | 0.26402 | 25 | 60 | 2021-05-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13207 - 90146892 | CKT: 13207 - 90146892 | 2304870 | LUG WSA 13207.90146892 OH | 2304871 | LUG WSA 13207.90146892 UG | 2304870 | LUG WSA 13207.90146892 OH | 2304871 | LUG WSA 13207.90146892 UG
Enercon | 2021 | 2022 | LUG - TBD560 | PRE-09361.197 | PRE-09361.197 | LUG WSA 13162.10158434 | LUG WSA 13162.10158434 | 13162 | MATANZAS | Lateral Hardening-Fuse-10158434 | Lateral Hardening-Fuse-10158434 | WSA | 0.38182 | 30 | 47 | 2021-05-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13162 - 10158434 | CKT: 13162 - 10158434 | 2304868 | LUG WSA 13162.10158434 OH | 2304869 | LUG WSA 13162.10158434 UG | 2304868 | LUG WSA 13162.10158434 OH | 2304869 | LUG WSA 13162.10158434 UG
Enercon | 2021 | 2022 | LUG - TBD561 | PRE-09361.198 | PRE-09361.198 | LUG WSA 13079.60077605 | LUG WSA 13079.60077605 | 13079 | COOLIDGE | Lateral Hardening-Fuse-60077605 | Lateral Hardening-Fuse-60077605 | WSA | 0.1803 | 17 | 32 | 2021-05-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13079 - 60077605 | CKT: 13079 - 60077605 | 2304706 | LUG WSA 13079.60077605 OH | 2304708 | LUG WSA 13079.60077605 UG | 2304706 | LUG WSA 13079.60077605 OH | 2304708 | LUG WSA 13079.60077605 UG
Enercon | 2021 | 2022 | LUG - TBD562 | PRE-09361.199 | PRE-09361.199 | LUG WSA 13870.90428273 | LUG WSA 13870.90428273 | 13870 | HENDERSON ROAD | Lateral Hardening-Fuse-90428273 | Lateral Hardening-Fuse-90428273 | WSA | 0.4017 | 25 | 104 | 2021-05-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13870 - 90428273 | CKT: 13870 - 90428273 | 2304758 | LUG WSA 13870.90428273 OH | 2304760 | LUG WSA 13870.90428273 UG | 2304758 | LUG WSA 13870.90428273 OH | 2304760 | LUG WSA 13870.90428273 UG
Enercon | 2021 | 2022 | LUG - TBD563 | PRE-09361.200 | PRE-09361.200 | LUG WSA 13737.91960399 | LUG WSA 13737.91960399 | 13737 | CLEARVIEW | Lateral Hardening-Fuse-91960399 | Lateral Hardening-Fuse-91960399 | WSA | 0.43277 | 32 | 56 | 2021-05-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13737 - 91960399 | CKT: 13737 - 91960399 | 2304866 | LUG WSA 13737.91960399 OH | 2304867 | LUG WSA 13737.91960399 UG | 2304866 | LUG WSA 13737.91960399 OH | 2304867 | LUG WSA 13737.91960399 UG
Enercon | 2021 | 2022 | LUG - TBD564 | PRE-09361.201 | PRE-09361.201 | LUG WSA 13674.10277747 | LUG WSA 13674.10277747 | 13674 | MEADOW PARK | Lateral Hardening-Fuse-10277747 | Lateral Hardening-Fuse-10277747 | WSA | 0.56723 | 36 | 361 | 2021-05-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13674 - 10277747 | CKT: 13674 - 10277747 | 2304737 | LUG WSA 13674.10277747 OH | 2304738 | LUG WSA 13674.10277747 UG | 2304737 | LUG WSA 13674.10277747 OH | 2304738 | LUG WSA 13674.10277747 UG
Enercon | 2021 | 2022 | LUG - TBD565 | PRE-09361.202 | PRE-09361.202 | LUG WSA 13078.10127958 | LUG WSA 13078.10127958 | 13078 | COOLIDGE | Lateral Hardening-Fuse-10127958 | Lateral Hardening-Fuse-10127958 | WSA | 0.74545 | 35 | 554 | 2021-05-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13078 - 10127958 | CKT: 13078 - 10127958 | 2304716 | LUG WSA 13078.10127958 OH | 2304717 | LUG WSA 13078.10127958 UG | 2304716 | LUG WSA 13078.10127958 OH | 2304717 | LUG WSA 13078.10127958 UG
Enercon | 2021 | 2022 | LUG - TBD566 | PRE-09361.263 | PRE-09361.203 | DNU LUG WSA 13162.60154843 | LUG WSA 13162.90435139 | 13162 | MATANZAS | DNU Lateral Hardening-Fuse-60154843 | Lateral Hardening-Fuse-90435139 | WSA | 0.26667 | 25 | 32 | 2021-05-01 |  |  | N/A | 4500279866 | TBD | LUG C046 | N/A | CKT: 13162 - 90435139 | N/A | N/A | N/A | N/A | 2308137 | LUG WSA 13162.90435139 OH | 2308138 | LUG WSA 13162.90435139 UG | Combined with PRE-09361.263 (FID 90435139)
Enercon | 2021 | 2022 | LUG - TBD567 | PRE-09361.204 | PRE-09361.204 | LUG WSA 13510.10218990 | LUG WSA 13510.10218990 | 13510 | GEORGE ROAD | Lateral Hardening-Fuse-10218990 | Lateral Hardening-Fuse-10218990 | WSA | 0.35814 | 37 | 20 | 2021-05-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13510 - 10218990 | CKT: 13510 - 10218990 | 2304864 | LUG WSA 13510.10218990 OH | 2304865 | LUG WSA 13510.10218990 UG | 2304864 | LUG WSA 13510.10218990 OH | 2304865 | LUG WSA 13510.10218990 UG
Enercon | 2021 | 2022 | LUG - TBD568 | PRE-09361.205 | PRE-09361.205 | LUG WSA 13669.60107076 | LUG WSA 13669.60107076 | 13669 | MEADOW PARK | Lateral Hardening-Fuse-60107076 | Lateral Hardening-Fuse-60107076 | WSA | 0.12254 | 9 | 4 | 2021-05-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13669 - 60107076 | CKT: 13669 - 60107076 | 2304741 | LUG WSA 13669.60107076 OH | 2304743 | LUG WSA 13669.60107076 UG | 2304741 | LUG WSA 13669.60107076 OH | 2304743 | LUG WSA 13669.60107076 UG
Enercon | 2021 | 2022 | LUG - TBD569 | PRE-09361.190 | PRE-09361.206 | DNU LUG WSA 14030.90242104 | LUG WSA 14030.90886759 | 14030 | PAGLEN ROAD | DNU Lateral Hardening-Fuse-90242104 | Lateral Hardening-Fuse-90886759 | WSA | 0.079167 | 6 | 92 | 2021-05-01 |  |  | N/A | 4500279866 | TBD | LUG C053 | N/A | CKT: 14030 - 90886759 | N/A | N/A | N/A | N/A | 2308111 | LUG WSA 14030.90886759 OH | 2308112 | LUG WSA 14030.90886759 UG | Combined with PRE-09361.190 (FID 90886759) & PRE-09361.257 (FID 92669080)
Enercon | 2021 | 2022 | LUG - TBD570 | PRE-09361.207 | PRE-09361.207 | LUG WSA 13873.60311122 | LUG WSA 13873.60311122 | 13873 | HENDERSON ROAD | Lateral Hardening-Fuse-60311122 | Lateral Hardening-Fuse-60311122 | WSA | 0.79261 | 61 | 235 | 2021-05-01 |  |  | N/A | 4500279866 | TBD | LUG C050 | CKT: 13873 - 60311122 | CKT: 13873 - 60311122 | 2308115 | LUG WSA 13873.60311122 OH | 2308116 | LUG WSA 13873.60311122 UG | 2308115 | LUG WSA 13873.60311122 OH | 2308116 | LUG WSA 13873.60311122 UG | Combined with PRE-09361.264 (FID 10820612)
Enercon | 2021 | 2022 | LUG - TBD571 | PRE-09361.208 | PRE-09361.208 | LUG WSA 13207.90613782 | LUG WSA 13207.90613782 | 13207 | LOIS AVENUE | Lateral Hardening-Fuse-90613782 | Lateral Hardening-Fuse-90613782 | WSA | 0.37973 | 31 | 64 | 2021-05-01 |  |  | N/A | 4500279866 | TBD | LUG C054 | CKT: 13207 - 90613782 | CKT: 13207 - 90613782 | 2308117 | LUG WSA 13207.90613782 OH | 2308118 | LUG WSA 13207.90613782 UG | 2308117 | LUG WSA 13207.90613782 OH | 2308118 | LUG WSA 13207.90613782 UG | Combined with PRE-09361.192 (FID 90216846)
Enercon | 2021 | 2022 | LUG - TBD572 | PRE-09361.274 | PRE-09361.209 | DNU LUG WSA 13612.90266817 | LUG WSA 13612.90291123 | 13612 | EL PRADO | DNU Lateral Hardening-Fuse-90266817 | Lateral Hardening-Fuse-90291123 | WSA | 0.20985 | 19 | 103 | 2021-05-01 |  |  | N/A | 4500279866 | TBD | LUG C055 | N/A | CKT: 13612 - 90291123 | N/A | N/A | N/A | N/A | 2308140 | LUG WSA 13612.90291123 OH | 2308141 | LUG WSA 13612.90291123 UG | Combined with PRE-09361.274 (FID 90291123)
Enercon | 2021 | 2022 | LUG - TBD573 | PRE-09361.210 | PRE-09361.210 | LUG WSA 13208.92767537 | LUG WSA 13208.92767537 | 13208 | LOIS AVENUE | Lateral Hardening-Fuse-92767537 | Lateral Hardening-Fuse-92767537 | WSA | 0.18352 | 18 | 117 | 2021-06-01 |  |  | N/A | 4500279866 | TBD | LUG C047 | CKT: 13208 - 92767537 | CKT: 13208 - 92767537 | 2308119 | LUG WSA 13208.92767537 OH | 2308120 | LUG WSA 13208.92767537 UG | 2308119 | LUG WSA 13208.92767537 OH | 2308120 | LUG WSA 13208.92767537 UG | Combined with PRE-09361.233 (FID 90449608)
Enercon | 2021 | 2022 | LUG - TBD574 | PRE-09361.211 | PRE-09361.211 | LUG WSA 13737.60311396 | LUG WSA 13737.60311396 | 13737 | CLEARVIEW | Lateral Hardening-Fuse-60311396 | Lateral Hardening-Fuse-60311396 | WSA | 0.19205 | 8 | 16 | 2021-06-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13737 - 60311396 | CKT: 13737 - 60311396 | 2304769 | LUG WSA 13737.60311396 OH | 2304771 | LUG WSA 13737.60311396 UG | 2304769 | LUG WSA 13737.60311396 OH | 2304771 | LUG WSA 13737.60311396 UG
Enercon | 2021 | 2022 | LUG - TBD575 | PRE-09361.212 | PRE-09361.212 | LUG WSA 13198.92655424 | LUG WSA 13198.92655424 | 13198 | GRAY STREET | Lateral Hardening-Fuse-92655424 | Lateral Hardening-Fuse-92655424 | WSA | 0.094129 | 8 | 11 | 2021-06-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13198 - 92655424 | CKT: 13198 - 92655424 | 2304772 | LUG WSA 13198.92655424 OH | 2304773 | LUG WSA 13198.92655424 UG | 2304772 | LUG WSA 13198.92655424 OH | 2304773 | LUG WSA 13198.92655424 UG
Enercon | 2021 | 2022 | LUG - TBD576 | PRE-09361.213 | PRE-09361.213 | LUG WSA 13514.10624934 | LUG WSA 13514.10624934 | 13514 | GEORGE ROAD | Lateral Hardening-Fuse-10624934 | Lateral Hardening-Fuse-10624934 | WSA | 0.23523 | 20 | 18 | 2021-06-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13514 - 10624934 | CKT: 13514 - 10624934 | 2304861 | LUG WSA 13514.10624934 OH | 2304862 | LUG WSA 13514.10624934 UG | 2304861 | LUG WSA 13514.10624934 OH | 2304862 | LUG WSA 13514.10624934 UG
Enercon | 2021 | 2022 | LUG - TBD577 | PRE-09361.231 | PRE-09361.214 | DNU LUG WSA 13535.92959083 | LUG WSA 13535.91618829 | 13535 | CARROLLWOOD VILLAGE | DNU Lateral Hardening-Fuse-92959083 | Lateral Hardening-Fuse-91618829 | WSA | 0.10227 | 9 | 6 | 2021-06-01 |  |  | N/A | 4500279866 | TBD | LUG C049 | N/A | CKT: 13535 - 91618829 | N/A | N/A | N/A | N/A | 2308125 | LUG WSA 13535.91618829 OH | 2308126 | LUG WSA 13535.91618829 UG | Combined with PRE-09361.231 (FID 91618829) & PRE-09361.252 (FID 92969194)
Enercon | 2021 | 2022 | LUG - TBD578 | PRE-09361.232 | PRE-09361.215 | DNU LUG WSA 13669.92774744 | LUG WSA 13669.92770538 | 13669 | MEADOW PARK | DNU Lateral Hardening-Fuse-92774744 | Lateral Hardening-Fuse-92770538 | WSA | 0.27803 | 24 | 268 | 2021-06-01 |  |  | N/A | 4500279866 | TBD | LUG C048 | N/A | CKT: 13669 - 92770538 | N/A | N/A | N/A | N/A | 2308127 | LUG WSA 13669.92770538 | 2308128 | LUG WSA 13669.92770538 UG | Combined with PRE-09361.232 (FID 92770538)
Enercon | 2021 | 2022 | LUG - TBD579 | PRE-09361.216 | PRE-09361.216 | LUG WSA 13483.60393455 | LUG WSA 13483.60393455 | 13483 | WOODLANDS | Lateral Hardening-Fuse-60393455 | Lateral Hardening-Fuse-60393455 | WSA | 1.3216 | 100 | 526 | 2021-06-01 |  |  | N/A | 4500279866 | TBD | LUG C056 | CKT: 13483 - 60393455 | CKT: 13483 - 60393455 | 2308121 | LUG WSA 13483.60393455 OH | 2308122 | LUG WSA 13483.60393455 UG | 2308121 | LUG WSA 13483.60393455 OH | 2308122 | LUG WSA 13483.60393455 UG | Combined with PRE-09361.242 (FID 10173513) & PRE-09361.260 (FID 60079455)
Enercon | 2021 | 2022 | LUG - TBD580 | PRE-09361.217 | PRE-09361.217 | LUG WSA 13520.10242257 | LUG WSA 13520.10242257 | 13520 | STADIUM | Lateral Hardening-Fuse-10242257 | Lateral Hardening-Fuse-10242257 | WSA | 0.45095 | 44 | 28 | 2021-06-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13520 - 10242257 | CKT: 13520 - 10242257 | 2304859 | LUG WSA 13520.10242257 OH | 2304860 | LUG WSA 13520.10242257 UG | 2304859 | LUG WSA 13520.10242257 OH | 2304860 | LUG WSA 13520.10242257 UG
Enercon | 2021 | 2022 | LUG - TBD581 | PRE-09361.218 | PRE-09361.218 | LUG WSA 13892.10338448 | LUG WSA 13892.10338448 | 13892 | EHRLICH ROAD | Lateral Hardening-Fuse-10338448 | Lateral Hardening-Fuse-10338448 | WSA | 1.1121 | 71 | 256 | 2021-06-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13892 - 10338448 | CKT: 13892 - 10338448 | 2304854 | LUG WSA 13892.10338448 OH | 2304856 | LUG WSA 13892.10338448 UG | 2304854 | LUG WSA 13892.10338448 OH | 2304856 | LUG WSA 13892.10338448 UG
Enercon | 2021 | 2022 | LUG - TBD582 | PRE-09361.219 | PRE-09361.219 | LUG WSA 13612.90312305 | LUG WSA 13612.90312305 | 13612 | EL PRADO | Lateral Hardening-Fuse-90312305 | Lateral Hardening-Fuse-90312305 | WSA | 0.094886 | 7 | 72 | 2021-06-01 |  |  | N/A | 4500279866 | TBD | LUG C043 | CKT: 13612 - 90312305 | CKT: 13612 - 90312305 | 2308123 | LUG WSA 13612.90312305 OH | 2308124 | LUG WSA 13612.90312305 UG | 2308123 | LUG WSA 13612.90312305 OH | 2308124 | LUG WSA 13612.90312305 UG | Combined with PRE-09361.280 (FID 90312570)
Enercon | 2021 | 2022 | LUG - TBD583 | PRE-09361.220 | PRE-09361.220 | LUG WSA 13522.91947423 | LUG WSA 13522.91947423 | 13522 | ROME AVENUE | Lateral Hardening-Fuse-91947423 | Lateral Hardening-Fuse-91947423 | WSA | 0.52614 | 50 | 47 | 2021-06-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13522 - 91947423 | CKT: 13522 - 91947423 | 2304851 | LUG WSA 13522.91947423 OH | 2304852 | LUG WSA 13522.91947423 UG | 2304851 | LUG WSA 13522.91947423 OH | 2304852 | LUG WSA 13522.91947423 UG
Enercon | 2021 | 2022 | LUG - TBD584 | PRE-09361.221 | PRE-09361.221 | LUG WSA 13334.91645657 | LUG WSA 13334.91645657 | 13334 | WATERS AVENUE | Lateral Hardening-Fuse-91645657 | Lateral Hardening-Fuse-91645657 | WSA | 0.48428 | 46 | 142 | 2021-07-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13334 - 91645657 | CKT: 13334 - 91645657 | 2304847 | LUG WSA 13334.91645657 OH | 2304849 | LUG WSA 13334.91645657 UG | 2304847 | LUG WSA 13334.91645657 OH | 2304849 | LUG WSA 13334.91645657 UG
Enercon | 2021 | 2022 | LUG - TBD585 | PRE-09361.222 | PRE-09361.222 | LUG WSA 13490.92815117 | LUG WSA 13490.92815117 | 13490 | JACKSON ROAD | Lateral Hardening-Fuse-92815117 | Lateral Hardening-Fuse-92815117 | WSA | 0.16723 | 13 | 163 | 2021-07-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13490 - 92815117 | CKT: 13490 - 92815117 | 2304767 | LUG WSA 13490.92815117 OH | 2304770 | LUG WSA 13490.92815117 UG | 2304767 | LUG WSA 13490.92815117 OH | 2304770 | LUG WSA 13490.92815117 UG
Enercon | 2021 | 2022 | LUG - TBD586 | PRE-09361.223 | PRE-09361.223 | LUG WSA 13522.10392902 | LUG WSA 13522.10392902 | 13522 | ROME AVENUE | Lateral Hardening-Fuse-10392902 | Lateral Hardening-Fuse-10392902 | WSA | 0.66591 | 68 | 103 | 2021-07-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13522 - 10392902 | CKT: 13522 - 10392902 | 2304845 | LUG WSA 13522.10392902 OH | 2304846 | LUG WSA 13522.10392902 UG | 2304845 | LUG WSA 13522.10392902 OH | 2304846 | LUG WSA 13522.10392902 UG
Enercon | 2021 | 2022 | LUG - TBD587 | PRE-09361.224 | PRE-09361.224 | LUG WSA 14030.60341032 | LUG WSA 14030.60341032 | 14030 | PAGLEN ROAD | Lateral Hardening-Fuse-60341032 | Lateral Hardening-Fuse-60341032 | WSA | 0.13239 | 10 | 81 | 2021-07-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 14030 - 60341032 | CKT: 14030 - 60341032 | 2304841 | LUG WSA 14030.60341032 OH | 2304844 | LUG WSA 14030.60341032 UG | 2304841 | LUG WSA 14030.60341032 OH | 2304844 | LUG WSA 14030.60341032 UG
Enercon | 2021 | 2022 | LUG - TBD588 | PRE-09361.225 | PRE-09361.225 | LUG WSA 13574.10250638 | LUG WSA 13574.10250638 | 13574 | ROCKY CREEK | Lateral Hardening-Fuse-10250638 | Lateral Hardening-Fuse-10250638 | WSA | 0.17083 | 12 | 10 | 2021-07-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13574 - 10250638 | CKT: 13574 - 10250638 | 2304763 | LUG WSA 13574.10250638 OH | 2304766 | LUG WSA 13574.10250638 UG | 2304763 | LUG WSA 13574.10250638 OH | 2304766 | LUG WSA 13574.10250638 UG
Enercon | 2021 | 2022 | LUG - TBD589 | PRE-09361.65 | PRE-09361.226 | DNU LUG WSA 13138.10145602 | LUG WSA 13138.10145625 | 13138 | HABANA AVENUE | DNU Lateral Hardening-Fuse-10145602 | Lateral Hardening-Fuse-10145625 | WSA | 0.22027 | 23 | 257 | 2021-07-01 |  |  | 4500274705 | N/A | N/A | LUG C036 | N/A | CKT: 13138 - 10145625 | N/A | N/A | N/A | N/A | 2273309 | LUG WSA 13138.10145625 OH | 2273313 | LUG WSA 13138.10145625 UG | Combined with PRE-09361.65 (FID 10145625)
Enercon | 2021 | 2022 | LUG - TBD590 | PRE-09361.227 | PRE-09361.227 | LUG WSA 13220.10191173 | LUG WSA 13220.10191173 | 13220 | HABANA AVENUE | Lateral Hardening-Fuse-10191173 | Lateral Hardening-Fuse-10191173 | WSA | 0.5178 | 45 | 66 | 2021-07-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13220 - 10191173 | CKT: 13220 - 10191173 | 2304836 | LUG WSA 13220.10191173 OH | 2304837 | LUG WSA 13220.10191173 UG | 2304836 | LUG WSA 13220.10191173 OH | 2304837 | LUG WSA 13220.10191173 UG
Enercon | 2021 | 2022 | LUG - TBD591 | PRE-09361.228 | PRE-09361.228 | LUG WSA 13612.60022877 | LUG WSA 13612.60022877 | 13612 | EL PRADO | Lateral Hardening-Fuse-60022877 | Lateral Hardening-Fuse-60022877 | WSA | 0.061174 | 7 | 22 | 2021-07-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13612 - 60022877 | CKT: 13612 - 60022877 | 2304776 | LUG WSA 13612.60022877 OH | 2304777 | LUG WSA 13612.60022877 UG | 2304776 | LUG WSA 13612.60022877 OH | 2304777 | LUG WSA 13612.60022877 UG
Enercon | 2021 | 2022 | LUG - TBD592 | PRE-09361.229 | PRE-09361.229 | LUG WSA 13220.90901917 | LUG WSA 13220.90901917 | 13220 | HABANA AVENUE | Lateral Hardening-Fuse-90901917 | Lateral Hardening-Fuse-90901917 | WSA | 0.48977 | 38 | 55 | 2021-07-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13220 - 90901917 | CKT: 13220 - 90901917 | 2304834 | LUG WSA 13220.90901917 OH | 2304835 | LUG WSA 13220.90901917 UG | 2304834 | LUG WSA 13220.90901917 OH | 2304835 | LUG WSA 13220.90901917 UG
Enercon | 2021 | 2022 | LUG - TBD593 | PRE-09361.230 | PRE-09361.230 | LUG WSA 13535.92983661 | LUG WSA 13535.92983661 | 13535 | CARROLLWOOD VILLAGE | Lateral Hardening-Fuse-92983661 | Lateral Hardening-Fuse-92983661 | WSA | 0.33314 | 32 | 10 | 2021-07-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13535 - 92983661 | CKT: 13535 - 92983661 | 2304831 | LUG WSA 13535.92983661 OH | 2304832 | LUG WSA 13535.92983661 UG | 2304831 | LUG WSA 13535.92983661 OH | 2304832 | LUG WSA 13535.92983661 UG
Enercon | 2021 | 2022 | LUG - TBD594 | PRE-09361.231 | PRE-09361.231 | LUG WSA 13535.91618829 | LUG WSA 13535.91618829 | 13535 | CARROLLWOOD VILLAGE | Lateral Hardening-Fuse-91618829 | Lateral Hardening-Fuse-91618829 | WSA | 0.50265 | 34 | 70 | 2021-08-01 |  |  | N/A | 4500279866 | TBD | LUG C049 | CKT: 13535 - 91618829 | CKT: 13535 - 91618829 | 2308125 | LUG WSA 13535.91618829 OH | 2308126 | LUG WSA 13535.91618829 UG | 2308125 | LUG WSA 13535.91618829 OH | 2308126 | LUG WSA 13535.91618829 UG | Combined with PRE-09361.214 (FID 92959083) PRE-09361.252 (FID 92969194)
Enercon | 2021 | 2022 | LUG - TBD595 | PRE-09361.232 | PRE-09361.232 | LUG WSA 13669.92770538 | LUG WSA 13669.92770538 | 13669 | MEADOW PARK | Lateral Hardening-Fuse-92770538 | Lateral Hardening-Fuse-92770538 | WSA | 0.30152 | 37 | 204 | 2021-08-01 |  |  | N/A | 4500279866 | TBD | LUG C048 | CKT: 13669 - 92770538 | CKT: 13669 - 92770538 | 2308127 | LUG WSA 13669.92770538 | 2308128 | LUG WSA 13669.92770538 UG | 2308127 | LUG WSA 13669.92770538 | 2308128 | LUG WSA 13669.92770538 UG | Combined with PRE-09361.215 (FID 92774744)
Enercon | 2021 | 2022 | LUG - TBD596 | PRE-09361.210 | PRE-09361.233 | DNU LUG WSA 13208.90449608 | LUG WSA 13208.92767537 | 13208 | LOIS AVENUE | DNU Lateral Hardening-Fuse-90449608 | Lateral Hardening-Fuse-92767537 | WSA | 0.22386 | 19 | 83 | 2021-08-01 |  |  | N/A | 4500279866 | TBD | LUG C047 | N/A | CKT: 13208 - 92767537 | N/A | N/A | N/A | N/A | 2308119 | LUG WSA 13208.92767537 OH | 2308120 | LUG WSA 13208.92767537 UG | Combined with PRE-09361.210 (FID 92767537)
Enercon | 2021 | 2022 | LUG - TBD597 | PRE-09361.234 | PRE-09361.234 | LUG WSA 13079.60104344 | LUG WSA 13079.60104344 | 13079 | COOLIDGE | Lateral Hardening-Fuse-60104344 | Lateral Hardening-Fuse-60104344 | WSA | 0.1411 | 21 | 25 | 2021-08-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13079 - 60104344 | CKT: 13079 - 60104344 | 2304709 | LUG WSA 13079.60104344 OH | 2304710 | LUG WSA 13079.60104344 UG | 2304709 | LUG WSA 13079.60104344 OH | 2304710 | LUG WSA 13079.60104344 UG
Enercon | 2021 | 2022 | LUG - TBD598 | PRE-09361.235 | PRE-09361.235 | LUG WSA 13575.90054924 | LUG WSA 13575.90054924 | 13575 | ROCKY CREEK | Lateral Hardening-Fuse-90054924 | Lateral Hardening-Fuse-90054924 | WSA | 0.1072 | 12 | 238 | 2021-08-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13575 - 90054924 | CKT: 13575 - 90054924 | 2304750 | LUG WSA 13575.90054924 OH | 2304752 | LUG WSA 13575.90054924 UG | 2304750 | LUG WSA 13575.90054924 OH | 2304752 | LUG WSA 13575.90054924 UG
Enercon | 2021 | 2022 | LUG - TBD599 | PRE-09361.236 | PRE-09361.236 | LUG WSA 13750.60110680 | LUG WSA 13750.60110680 | 13750 | CASEY ROAD | Lateral Hardening-Fuse-60110680 | Lateral Hardening-Fuse-60110680 | WSA | 0.18561 | 12 | 43 | 2021-08-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13750 - 60110680 | CKT: 13750 - 60110680 | 2304725 | LUG WSA 13750.60110680 OH | 2304727 | LUG WSA 13750.60110680 UG | 2304725 | LUG WSA 13750.60110680 OH | 2304727 | LUG WSA 13750.60110680 UG
Enercon | 2021 | 2022 | LUG - TBD600 | PRE-09361.237 | PRE-09361.237 | LUG WSA 13198.10051875 | LUG WSA 13198.10051875 | 13198 | GRAY STREET | Lateral Hardening-Fuse-10051875 | Lateral Hardening-Fuse-10051875 | WSA | 0.097348 | 8 | 20 | 2021-08-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13198 - 10051875 | CKT: 13198 - 10051875 | 2304774 | LUG WSA 13198.10051875 OH | 2304775 | LUG WSA 13198.10051875 UG | 2304774 | LUG WSA 13198.10051875 OH | 2304775 | LUG WSA 13198.10051875 UG
Enercon | 2021 | 2022 | LUG - TBD601 | PRE-09361.238 | PRE-09361.238 | LUG WSA 13612.92956326 | LUG WSA 13612.92956326 | 13612 | EL PRADO | Lateral Hardening-Fuse-92956326 | Lateral Hardening-Fuse-92956326 | WSA | 0.23428 | 25 | 20 | 2021-08-01 |  |  | N/A | 4500279866 | TBD | LUG C057 | CKT: 13612 - 92956326 | CKT: 13612 - 92956326 | 2308129 | LUG WSA 13612.92956326 OH | 2308130 | LUG WSA 13612.92956326 UG | 2308129 | LUG WSA 13612.92956326 OH | 2308130 | LUG WSA 13612.92956326 UG | Combined with PRE-09361.181 (FID 90440184); WR info shown incorrectly on previous list from Leidos as LUG WSA 13522.10392882
Enercon | 2021 | 2022 | LUG - TBD602 | PRE-09361.239 | PRE-09361.239 | LUG WSA 13514.91361858 | LUG WSA 13514.91361858 | 13514 | GEORGE ROAD | Lateral Hardening-Fuse-91361858 | Lateral Hardening-Fuse-91361858 | WSA | 0.16231 | 18 | 70 | 2021-08-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13514 - 91361858 | CKT: 13514 - 91361858 | 2304656 | LUG WSA 13514.91361858 OH | 2304657 | LUG WSA 13514.91361858 UG | 2304656 | LUG WSA 13514.91361858 OH | 2304657 | LUG WSA 13514.91361858 UG
Enercon | 2021 | 2022 | LUG - TBD603 | PRE-09361.240 | PRE-09361.240 | LUG WSA 13522.10392905 | LUG WSA 13522.10392905 | 13522 | ROME AVENUE | Lateral Hardening-Fuse-10392905 | Lateral Hardening-Fuse-10392905 | WSA | 0.47481 | 50 | 105 | 2021-08-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13522 - 10392905 | CKT: 13522 - 10392905 | 2304654 | LUG WSA 13522.10392905 OH | 2304655 | LUG WSA 13522.10392905 UG | 2304654 | LUG WSA 13522.10392905 OH | 2304655 | LUG WSA 13522.10392905 UG
Enercon | 2021 | 2022 | LUG - TBD604 | PRE-09361.241 | PRE-09361.241 | LUG WSA 14030.92669942 | LUG WSA 14030.92669942 | 14030 | PAGLEN ROAD | Lateral Hardening-Fuse-92669942 | Lateral Hardening-Fuse-92669942 | WSA | 0.55814 | 34 | 112 | 2021-08-01 |  |  | N/A | 4500279866 | TBD | LUG C052 | CKT: 14030 - 92669942 | CKT: 14030 - 92669942 | 2308131 | LUG WSA 14030.92669942 OH | 2308132 | LUG WSA 14030.92669942 UG | 2308131 | LUG WSA 14030.92669942 OH | 2308132 | LUG WSA 14030.92669942 UG | Combined with PRE-09361.279 (FID 92669914) & PRE-09361.282 (FID 92669923)
Enercon | 2021 | 2022 | LUG - TBD605 | PRE-09361.216 | PRE-09361.242 | DNU LUG WSA 13483.10173513 | LUG WSA 13483.60393455 | 13483 | WOODLANDS | DNU Lateral Hardening-Fuse-10173513 | Lateral Hardening-Fuse-60393455 | WSA | 0.54678 | 47 | 140 | 2021-09-01 |  |  | N/A | 4500279866 | TBD | LUG C056 | N/A | CKT: 13483 - 60393455 | N/A | N/A | N/A | N/A | 2308121 | LUG WSA 13483.60393455 OH | 2308122 | LUG WSA 13483.60393455 UG | Combined with PRE-09361.216 (FID 90393455) & PRE-09361.260 (FID 60079455)
Enercon | 2021 | 2022 | LUG - TBD606 | PRE-09361.243 | PRE-09361.243 | LUG WSA 13612.60003135 | LUG WSA 13612.60003135 | 13612 | EL PRADO | Lateral Hardening-Fuse-60003135 | Lateral Hardening-Fuse-60003135 | WSA | 0.3036 | 33 | 81 | 2021-09-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13612 - 60003135 | CKT: 13612 - 60003135 | 2304652 | LUG WSA 13612.60003135 OH | 2304653 | LUG WSA 13612.60003135 UG | 2304652 | LUG WSA 13612.60003135 OH | 2304653 | LUG WSA 13612.60003135 UG
Enercon | 2021 | 2022 | LUG - TBD607 | PRE-09361.72 | PRE-09361.72 | DNU LUG WSA 13071.93035682 | LUG WSA 13071.60170422 | 13071 | KEYSTONE | DNU Lateral Hardening-Fuse-93035682 | Lateral Hardening-Fuse-60170422 | WSA | 0.63447 | 40 | 178 | 2021-09-01 |  |  | 4500274705 | N/A | N/A | LUG C022 | N/A | CKT: 13071 - 60170422 | N/A | N/A | N/A | N/A | 2273270 | LUG WSA 13071.60170422 OH | 2273272 | LUG WSA 13071.60170422 UG | Combined with PRE-09361.72 (FID 60170422)
Enercon | 2021 | 2022 | LUG - TBD608 | PRE-09361.245 | PRE-09361.245 | LUG WSA 13522.92169062 | LUG WSA 13522.92169062 | 13522 | ROME AVENUE | Lateral Hardening-Fuse-92169062 | Lateral Hardening-Fuse-92169062 | WSA | 0.31686 | 29 | 77 | 2021-09-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13522 - 92169062 | CKT: 13522 - 92169062 | 2304648 | LUG WSA 13522.92169062 OH | 2304649 | LUG WSA 13522.92169062 UG | 2304648 | LUG WSA 13522.92169062 OH | 2304649 | LUG WSA 13522.92169062 UG
Enercon | 2021 | 2022 | LUG - TBD609 | PRE-09361.246 | PRE-09361.246 | LUG WSA 13575.90054386 | LUG WSA 13575.90054386 | 13575 | ROCKY CREEK | Lateral Hardening-Fuse-90054386 | Lateral Hardening-Fuse-90054386 | WSA | 0.1017 | 13 | 105 | 2021-09-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13575 - 90054386 | CKT: 13575 - 90054386 | 2304646 | LUG WSA 13575.90054386 OH | 2304647 | LUG WSA 13575.90054386 UG | 2304646 | LUG WSA 13575.90054386 OH | 2304647 | LUG WSA 13575.90054386 UG
Enercon | 2021 | 2022 | LUG - TBD610 | PRE-09361.247 | PRE-09361.247 | LUG WSA 13522.10392882 | LUG WSA 13522.10392882 | 13522 | ROME AVENUE | Lateral Hardening-Fuse-10392882 | Lateral Hardening-Fuse-10392882 | WSA | 0.68731 | 61 | 162 | 2021-09-01 |  |  | N/A | 4500279866 | TBD | LUG C058 | CKT: 13522 - 10392882 | CKT: 13522 - 10392882 | 2308133 | LUG WSA 13522.10392882 OH | 2308134 | LUG WSA 13522.10392882 UG | 2308133 | LUG WSA 13522.10392882 OH | 2308134 | LUG WSA 13522.10392882 UG | Combined with PRE-09361.187 (FID 91934653) & PRE-09361.283 (FID 60305728)
Enercon | 2021 | 2022 | LUG - TBD611 | PRE-09361.248 | PRE-09361.248 | LUG WSA 13198.10051851 | LUG WSA 13198.10051851 | 13198 | GRAY STREET | Lateral Hardening-Fuse-10051851 | Lateral Hardening-Fuse-10051851 | WSA | 0.21231 | 21 | 33 | 2021-09-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13198 - 10051851 | CKT: 13198 - 10051851 | 2304641 | LUG WSA 13198.10051851 OH | 2304645 | LUG WSA 13198.10051851 UG | 2304641 | LUG WSA 13198.10051851 OH | 2304645 | LUG WSA 13198.10051851 UG
Enercon | 2021 | 2022 | LUG - TBD612 | PRE-09361.249 | PRE-09361.249 | LUG WSA 14030.92670479 | LUG WSA 14030.92670479 | 14030 | PAGLEN ROAD | Lateral Hardening-Fuse-92670479 | Lateral Hardening-Fuse-92670479 | WSA | 0.1089 | 6 | 3 | 2021-09-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 14030 - 92670479 | CKT: 14030 - 92670479 | 2304639 | LUG WSA 14030.92670479 OH | 2304640 | LUG WSA 14030.92670479 UG | 2304639 | LUG WSA 14030.92670479 OH | 2304640 | LUG WSA 14030.92670479 UG
Enercon | 2021 | 2022 | LUG - TBD613 | PRE-09361.250 | PRE-09361.250 | LUG WSA 13522.10392874 | LUG WSA 13522.10392874 | 13522 | ROME AVENUE | Lateral Hardening-Fuse-10392874 | Lateral Hardening-Fuse-10392874 | WSA | 0.15758 | 12 | 4 | 2021-09-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13522 - 10392874 | CKT: 13522 - 10392874 | 2304637 | LUG WSA 13522.10392874 OH | 2304638 | LUG WSA 13522.10392874 UG | 2304637 | LUG WSA 13522.10392874 OH | 2304638 | LUG WSA 13522.10392874 UG
Enercon | 2021 | 2022 | LUG - TBD614 | PRE-09361.251 | PRE-09361.251 | LUG WSA 13162.93124277 | LUG WSA 13162.93124277 | 13162 | MATANZAS | Lateral Hardening-Fuse-93124277 | Lateral Hardening-Fuse-93124277 | WSA | 0.15701 | 23 | 5 | 2021-09-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13162 - 93124277 | CKT: 13162 - 93124277 | 2304632 | LUG WSA 13162.93124277 OH | 2304636 | LUG WSA 13162.93124277 UG | 2304632 | LUG WSA 13162.93124277 OH | 2304636 | LUG WSA 13162.93124277 UG
Enercon | 2021 | 2022 | LUG - TBD615 | PRE-09361.231 | PRE-09361.252 | DNU LUG WSA 13535.92969194 | LUG WSA 13535.91618829 | 13535 | CARROLLWOOD VILLAGE | DNU Lateral Hardening-Fuse-92969194 | Lateral Hardening-Fuse-91618829 | WSA | 0.073295 | 6 | 4 | 2021-09-01 |  |  | N/A | 4500279866 | TBD | LUG C049 | N/A | CKT: 13535 - 91618829 | N/A | N/A | N/A | N/A | 2308125 | LUG WSA 13535.91618829 OH | 2308126 | LUG WSA 13535.91618829 UG | Combined with PRE-09361.214 (FID 92959083) & PRE-09361.231 (FID 91618829)
Enercon | 2021 | 2022 | LUG - TBD616 | PRE-09361.253 | PRE-09361.253 | LUG WSA 13198.10051896 | LUG WSA 13198.10051896 | 13198 | GRAY STREET | Lateral Hardening-Fuse-10051896 | Lateral Hardening-Fuse-10051896 | WSA | 0.13258 | 11 | 18 | 2021-10-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13198 - 10051896 | CKT: 13198 - 10051896 | 2304630 | LUG WSA 13198.10051896 OH | 2304631 | LUG WSA 13198.10051896 UG | 2304630 | LUG WSA 13198.10051896 OH | 2304631 | LUG WSA 13198.10051896 UG
Enercon | 2021 | 2022 | LUG - TBD617 | PRE-09361.55 | PRE-09361.254 | DNU LUG WSA 13109.10846390 | LUG WSA 13109.90641822 | 13109 | MANHATTAN | DNU Lateral Hardening-Fuse-10846390 | Lateral Hardening-Fuse-90641822 | WSA | 0.2411 | 27 | 29 | 2021-10-01 |  |  | 4500274705 | N/A | N/A | LUG C019 | N/A | CKT: 13109 - 90641822 | N/A | N/A | N/A | N/A | 2273297 | LUG WSA 13109.90641822 OH | 2273300 | LUG WSA 13109.90641822 UG | Combined with PRE-09361.55 (FID 90641822)
Enercon | 2021 | 2022 | LUG - TBD618 | PRE-09361.255 | PRE-09361.255 | LUG WSA 13612.60002970 | LUG WSA 13612.60002970 | 13612 | EL PRADO | Lateral Hardening-Fuse-60002970 | Lateral Hardening-Fuse-60002970 | WSA | 0.24811 | 23 | 131 | 2021-10-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13612 - 60002970 | CKT: 13612 - 60002970 | 2304628 | LUG WSA 13612.60002970 OH | 2304629 | LUG WSA 13612.60002970 UG | 2304628 | LUG WSA 13612.60002970 OH | 2304629 | LUG WSA 13612.60002970 UG
Enercon | 2021 | 2022 | LUG - TBD619 | PRE-09361.256 | PRE-09361.256 | LUG WSA 14030.60125643 | LUG WSA 14030.60125643 | 14030 | PAGLEN ROAD | Lateral Hardening-Fuse-60125643 | Lateral Hardening-Fuse-60125643 | WSA | 0.089205 | 14 | 101 | 2021-10-01 |  |  | N/A | 4500279866 | TBD | LUG C045 | CKT: 14030 - 60125643 | CKT: 14030 - 60125643 | 2308135 | LUG WSA 14030.60125643 OH | 2308136 | LUG WSA 14030.60125643 UG | 2308135 | LUG WSA 14030.60125643 OH | 2308136 | LUG WSA 14030.60125643 UG | Combined with PRE-09361.183 (FID 60131389)
Enercon | 2021 | 2022 | LUG - TBD620 | PRE-09361.190 | PRE-09361.257 | DNU LUG WSA 14030.92669080 | LUG WSA 14030.90886759 | 14030 | PAGLEN ROAD | DNU Lateral Hardening-Fuse-92669080 | Lateral Hardening-Fuse-90886759 | WSA | 0.27254 | 19 | 46 | 2021-10-01 |  |  | N/A | 4500279866 | TBD | LUG C053 | N/A | CKT: 14030 - 90886759 | N/A | N/A | N/A | N/A | 2308111 | LUG WSA 14030.90886759 OH | 2308112 | LUG WSA 14030.90886759 UG | Combined with PRE-09361.190 (FID 90886759) & PRE-09361.206 (FID 90242104)
Enercon | 2021 | 2022 | LUG - TBD621 | PRE-09361.258 | PRE-09361.258 | LUG WSA 13071.92377934 | LUG WSA 13071.92377934 | 13071 | KEYSTONE | Lateral Hardening-Fuse-92377934 | Lateral Hardening-Fuse-92377934 | WSA | 0.98239 | 66 | 63 | 2021-07-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13071 - 92377934 | CKT: 13071 - 92377934 | 2304623 | LUG WSA 13071.92377934 OH | 2304625 | LUG WSA 13071.92377934 UG | 2304623 | LUG WSA 13071.92377934 OH | 2304625 | LUG WSA 13071.92377934 UG
Enercon | 2021 | 2022 | LUG - TBD622 | PRE-09361.259 | PRE-09361.259 | LUG WSA 13138.60170460 | LUG WSA 13138.60170460 | 13138 | HABANA AVENUE | Lateral Hardening-Fuse-60170460 | Lateral Hardening-Fuse-60170460 | WSA | 0.26458 | 23 | 170 | 2021-10-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13138 - 60170460 | CKT: 13138 - 60170460 | 2304618 | LUG WSA 13138.60170460 OH | 2304620 | LUG WSA 13138.60170460 UG | 2304618 | LUG WSA 13138.60170460 OH | 2304620 | LUG WSA 13138.60170460 UG
Enercon | 2021 | 2022 | LUG - TBD623 | PRE-09361.216 | PRE-09361.260 | DNU LUG WSA 13483.60079455 | LUG WSA 13483.60393455 | 13483 | WOODLANDS | DNU Lateral Hardening-Fuse-60079455 | Lateral Hardening-Fuse-60393455 | WSA | 0.25606 | 19 | 65 | 2021-10-01 |  |  | N/A | 4500279866 | TBD | LUG C056 | N/A | CKT: 13483 - 60393455 | N/A | N/A | N/A | N/A | 2308121 | LUG WSA 13483.60393455 OH | 2308122 | LUG WSA 13483.60393455 UG | Combined with PRE-09361.216 (FID 90393455) & PRE-09361.242 (FID 10173513)
Enercon | 2021 | 2022 | LUG - TBD624 | PRE-09361.261 | PRE-09361.261 | LUG WSA 13535.92952190 | LUG WSA 13535.92952190 | 13535 | CARROLLWOOD VILLAGE | Lateral Hardening-Fuse-92952190 | Lateral Hardening-Fuse-92952190 | WSA | 0.2572 | 18 | 78 | 2021-10-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13535 - 92952190 | CKT: 13535 - 92952190 | 2304614 | LUG WSA 13535.92952190 OH | 2304616 | LUG WSA 13535.92952190 UG | 2304614 | LUG WSA 13535.92952190 OH | 2304616 | LUG WSA 13535.92952190 UG
Enercon | 2021 | 2022 | LUG - TBD625 | PRE-09361.48 | PRE-09361.262 | DNU LUG WSA 13198.10051852 | LUG WSA 13198.92183966 | 13198 | GRAY STREET | DNU Lateral Hardening-Fuse-10051852 | Lateral Hardening-Fuse-92183966 | WSA | 0.15549 | 12 | 9 | 2021-10-01 |  |  | 4500274705 | N/A | N/A | LUG C020 | N/A | CKT: 13198 - 92183966 | N/A | N/A | N/A | N/A | 2273238 | LUG WSA 13198.92183966 OH | 2273240 | LUG WSA 13198.92183966 UG | Combined with PRE-09361.48 (FID 92183966) & PRE-09361.262 (FID 10051852)
Enercon | 2021 | 2022 | LUG - TBD626 | PRE-09361.263 | PRE-09361.263 | LUG WSA 13162.90435139 | LUG WSA 13162.90435139 | 13162 | MATANZAS | Lateral Hardening-Fuse-90435139 | Lateral Hardening-Fuse-90435139 | WSA | 0.29773 | 24 | 23 | 2021-10-01 |  |  | N/A | 4500279866 | TBD | LUG C046 | CKT: 13162 - 90435139 | CKT: 13162 - 90435139 | 2308137 | LUG WSA 13162.90435139 OH | 2308138 | LUG WSA 13162.90435139 UG | 2308137 | LUG WSA 13162.90435139 OH | 2308138 | LUG WSA 13162.90435139 UG | Combined with PRE-09361.203 (FID 60154843)
Enercon | 2021 | 2022 | LUG - TBD627 | PRE-09361.207 | PRE-09361.264 | DNU LUG WSA 13873.10820612 | LUG WSA 13873.60311122 | 13873 | HENDERSON ROAD | DNU Lateral Hardening-Fuse-10820612 | Lateral Hardening-Fuse-60311122 | WSA | 0.10076 | 6 | 2 | 2021-10-01 |  |  | N/A | 4500279866 | TBD | LUG C050 | N/A | CKT: 13873 - 60311122 | N/A | N/A | N/A | N/A | 2308115 | LUG WSA 13873.60311122 OH | 2308116 | LUG WSA 13873.60311122 UG | Combined with PRE-09361.207 (FID 60311122)
Enercon | 2021 | 2022 | LUG - TBD628 | PRE-09361.265 | PRE-09361.265 | LUG WSA 13138.10145618 | LUG WSA 13138.10145618 | 13138 | HABANA AVENUE | Lateral Hardening-Fuse-10145618 | Lateral Hardening-Fuse-10145618 | WSA | 0.071023 | 6 | 92 | 2021-10-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13138 - 10145618 | CKT: 13138 - 10145618 | 2304610 | LUG WSA 13138.10145618 OH | 2304612 | LUG WSA 13138.10145618 UG | 2304610 | LUG WSA 13138.10145618 OH | 2304612 | LUG WSA 13138.10145618 UG
Enercon | 2021 | 2022 | LUG - TBD629 | PRE-09361.266 | PRE-09361.266 | LUG WSA 13737.90740214 | LUG WSA 13737.90740214 | 13737 | CLEARVIEW | Lateral Hardening-Fuse-90740214 | Lateral Hardening-Fuse-90740214 | WSA | 0.10114 | 12 | 15 | 2021-10-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13737 - 90740214 | CKT: 13737 - 90740214 | 2304607 | LUG WSA 13737.90740214 OH | 2304609 | LUG WSA 13737.90740214 UG | 2304607 | LUG WSA 13737.90740214 OH | 2304609 | LUG WSA 13737.90740214 UG
Enercon | 2021 | 2022 | LUG - TBD630 | PRE-09361.281 | PRE-09361.267 | DNU LUG WSA 13138.10145629 | LUG WSA 13138.10145606 | 13138 | HABANA AVENUE | DNU Lateral Hardening-Fuse-10145629 | Lateral Hardening-Fuse-10145606 | WSA | 0.12197 | 10 | 5 | 2021-10-01 |  |  | N/A | 4500279866 | TBD | LUG C059 | N/A | CKT: 13138 - 10145606 | N/A | N/A | N/A | N/A | 2308143 | LUG WSA 13138.10145606 OH | 2308144 | LUG WSA 13138.10145606 UG | Combined with PRE-09361.281 (FID 10145606)
Enercon | 2021 | 2022 | LUG - TBD631 | PRE-09361.268 | PRE-09361.268 | LUG WSA 13737.90740699 | LUG WSA 13737.90740699 | 13737 | CLEARVIEW | Lateral Hardening-Fuse-90740699 | Lateral Hardening-Fuse-90740699 | WSA | 0.16553 | 13 | 17 | 2021-10-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13737 - 90740699 | CKT: 13737 - 90740699 | 2304603 | LUG WSA 13737.90740699 OH | 2304605 | LUG WSA 13737.90740699 UG | 2304603 | LUG WSA 13737.90740699 OH | 2304605 | LUG WSA 13737.90740699 UG
Enercon | 2021 | 2022 | LUG - TBD632 | PRE-09361.269 | PRE-09361.269 | LUG WSA 13079.90517178 | LUG WSA 13079.90517178 | 13079 | COOLIDGE | Lateral Hardening-Fuse-90517178 | Lateral Hardening-Fuse-90517178 | WSA | 0.12973 | 16 | 56 | 2021-10-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13079 - 90517178 | CKT: 13079 - 90517178 | 2304585 | LUG WSA 13079.90517178 OH | 2304588 | LUG WSA 13079.90517178 UG | 2304585 | LUG WSA 13079.90517178 OH | 2304588 | LUG WSA 13079.90517178 UG
Enercon | 2021 | 2022 | LUG - TBD633 | PRE-09361.270 | PRE-09361.270 | LUG WSA 13078.10127955 | LUG WSA 13078.10127955 | 13078 | COOLIDGE | Lateral Hardening-Fuse-10127955 | Lateral Hardening-Fuse-10127955 | WSA | 0.17822 | 15 | 33 | 2021-10-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13078 - 10127955 | CKT: 13078 - 10127955 | 2304582 | LUG WSA 13078.10127955 OH | 2304583 | LUG WSA 13078.10127955 UG | 2304582 | LUG WSA 13078.10127955 OH | 2304583 | LUG WSA 13078.10127955 UG
Enercon | 2021 | 2022 | LUG - TBD634 | PRE-09361.271 | PRE-09361.271 | LUG WSA 14030.92669557 | LUG WSA 14030.92669557 | 14030 | PAGLEN ROAD | Lateral Hardening-Fuse-92669557 | Lateral Hardening-Fuse-92669557 | WSA | 0.0089015 | 5 | 78 | 2021-11-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 14030 - 92669557 | CKT: 14030 - 92669557 | 2304577 | LUG WSA 14030.92669557 OH | 2304580 | LUG WSA 14030.92669557 UG | 2304577 | LUG WSA 14030.92669557 OH | 2304580 | LUG WSA 14030.92669557 UG
Enercon | 2021 | 2022 | LUG - TBD635 | PRE-09361.272 | PRE-09361.272 | LUG WSA 13522.10392864 | LUG WSA 13522.10392864 | 13522 | ROME AVENUE | Lateral Hardening-Fuse-10392864 | Lateral Hardening-Fuse-10392864 | WSA | 0.10587 | 7 | 10 | 2021-11-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13522 - 10392864 | CKT: 13522 - 10392864 | 2304574 | LUG WSA 13522.10392864 OH | 2304575 | LUG WSA 13522.10392864 UG | 2304574 | LUG WSA 13522.10392864 OH | 2304575 | LUG WSA 13522.10392864 UG
Enercon | 2021 | 2022 | LUG - TBD636 | PRE-09361.273 | PRE-09361.273 | LUG WSA 13674.90420693 | LUG WSA 13674.90420693 | 13674 | MEADOW PARK | Lateral Hardening-Fuse-90420693 | Lateral Hardening-Fuse-90420693 | WSA | 0.3233 | 29 | 125 | 2021-10-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13674 - 90420693 | CKT: 13674 - 90420693 | 2304569 | LUG WSA 13674.90420693 OH | 2304572 | LUG WSA 13674.90420693 UG | 2304569 | LUG WSA 13674.90420693 OH | 2304572 | LUG WSA 13674.90420693 UG
Enercon | 2021 | 2022 | LUG - TBD637 | PRE-09361.274 | PRE-09361.274 | LUG WSA 13612.90291123 | LUG WSA 13612.90291123 | 13612 | EL PRADO | Lateral Hardening-Fuse-90291123 | Lateral Hardening-Fuse-90291123 | WSA | 0.13333 | 15 | 10 | 2021-11-01 |  |  | N/A | 4500279866 | TBD | LUG C055 | CKT: 13612 - 90291123 | CKT: 13612 - 90291123 | 2308140 | LUG WSA 13612.90291123 OH | 2308141 | LUG WSA 13612.90291123 UG | 2308140 | LUG WSA 13612.90291123 OH | 2308141 | LUG WSA 13612.90291123 UG | Combined with PRE-09361.209 (FID 90291123)
Enercon | 2021 | 2022 | LUG - TBD638 | PRE-09361.275 | PRE-09361.275 | LUG WSA 13109.60233901 | LUG WSA 13109.60233901 | 13109 | MANHATTAN | Lateral Hardening-Fuse-60233901 | Lateral Hardening-Fuse-60233901 | WSA | 0.47254 | 42 | 282 | 2021-10-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13109 - 60233901 | CKT: 13109 - 60233901 | 2304565 | LUG WSA 13109.60233901 OH | 2304568 | LUG WSA 13109.60233901 UG | 2304565 | LUG WSA 13109.60233901 OH | 2304568 | LUG WSA 13109.60233901 UG
Enercon | 2021 | 2022 | LUG - TBD639 | PRE-09361.276 | PRE-09361.276 | LUG WSA 13737.10297934 | LUG WSA 13737.10297934 | 13737 | CLEARVIEW | Lateral Hardening-Fuse-10297934 | Lateral Hardening-Fuse-10297934 | WSA | 0.19678 | 18 | 24 | 2021-11-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13737 - 10297934 | CKT: 13737 - 10297934 | 2304560 | LUG WSA 13737.10297934 OH | 2304563 | LUG WSA 13737.10297934 UG | 2304560 | LUG WSA 13737.10297934 OH | 2304563 | LUG WSA 13737.10297934 UG
Enercon | 2021 | 2022 | LUG - TBD640 | PRE-09361.277 | PRE-09361.277 | LUG WSA 13589.93162023 | LUG WSA 13589.93162023 | 13589 | DALE MABRY | Lateral Hardening-Fuse-93162023 | Lateral Hardening-Fuse-93162023 | WSA | 0.3267 | 16 | 1 | 2021-10-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13589 - 93162023 | CKT: 13589 - 93162023 | 2304547 | LUG WSA 13589.93162023 OH | 2304552 | LUG WSA 13589.93162023 UG | 2304547 | LUG WSA 13589.93162023 OH | 2304552 | LUG WSA 13589.93162023 UG
Enercon | 2021 | 2022 | LUG - TBD641 | PRE-09361.48 | PRE-09361.278 | DNU LUG WSA 13198.92585443 | LUG WSA 13198.92183966 | 13198 | GRAY STREET | DNU Lateral Hardening-Fuse-92585443 | Lateral Hardening-Fuse-92183966 | WSA | 0.089583 | 12 | 27 | 2021-11-01 |  |  | 4500274705 | N/A | N/A | LUG C020 | N/A | CKT: 13198 - 92183966 | N/A | N/A | N/A | N/A | 2273238 | LUG WSA 13198.92183966 OH | 2273240 | LUG WSA 13198.92183966 UG | Combined with PRE-09361.48 (FID 92183966) & PRE-09361.278 (FID 92585443)
Enercon | 2021 | 2022 | LUG - TBD642 | PRE-09361.241 | PRE-09361.279 | DNU LUG WSA 14030.92669914 | LUG WSA 14030.92669942 | 14030 | PAGLEN ROAD | DNU Lateral Hardening-Fuse-92669914 | Lateral Hardening-Fuse-92669942 | WSA | 0.20303 | 19 | 25 | 2021-11-01 |  |  | N/A | 4500279866 | TBD | LUG C052 | N/A | CKT: 14030 - 92669942 | N/A | N/A | N/A | N/A | 2308131 | LUG WSA 14030.92669942 OH | 2308132 | LUG WSA 14030.92669942 UG | Combined with PRE-09361.241 (FID 92669942) PRE-09361.282 (FID 92669923)
Enercon | 2021 | 2022 | LUG - TBD643 | PRE-09361.219 | PRE-09361.280 | DNU LUG WSA 13612.90312570 | LUG WSA 13612.90312305 | 13612 | EL PRADO | DNU Lateral Hardening-Fuse-90312570 | Lateral Hardening-Fuse-90312305 | WSA | 0.18542 | 18 | 25 | 2021-11-01 |  |  | N/A | 4500279866 | TBD | LUG C043 | N/A | CKT: 13612 - 90312305 | N/A | N/A | N/A | N/A | 2308123 | LUG WSA 13612.90312305 OH | 2308124 | LUG WSA 13612.90312305 UG | Combined with PRE-09361.219 (FID 90312305)
Enercon | 2021 | 2022 | LUG - TBD644 | PRE-09361.281 | PRE-09361.281 | LUG WSA 13138.10145606 | LUG WSA 13138.10145606 | 13138 | HABANA AVENUE | Lateral Hardening-Fuse-10145606 | Lateral Hardening-Fuse-10145606 | WSA | 0.25587 | 24 | 222 | 2021-11-01 |  |  | N/A | 4500279866 | TBD | LUG C059 | CKT: 13138 - 10145606 | CKT: 13138 - 10145606 | 2308143 | LUG WSA 13138.10145606 OH | 2308144 | LUG WSA 13138.10145606 UG | 2308143 | LUG WSA 13138.10145606 OH | 2308144 | LUG WSA 13138.10145606 UG | Combined with PRE-09361.267 (FID 10145629)
Enercon | 2021 | 2022 | LUG - TBD645 | PRE-09361.241 | PRE-09361.282 | DNU LUG WSA 14030.92669923 | LUG WSA 14030.92669942 | 14030 | PAGLEN ROAD | DNU Lateral Hardening-Fuse-92669923 | Lateral Hardening-Fuse-92669942 | WSA | 0.20701 | 15 | 36 | 2021-11-01 |  |  | N/A | 4500279866 | TBD | LUG C052 | N/A | CKT: 14030 - 92669942 | N/A | N/A | N/A | N/A | 2308131 | LUG WSA 14030.92669942 OH | 2308132 | LUG WSA 14030.92669942 UG | Combined with PRE-09361.241 (FID 92669942) & PRE-09361.279 (FID 92669914)
Enercon | 2021 | 2022 | LUG - TBD646 | PRE-09361.247 | PRE-09361.283 | DNU LUG WSA 13522.60305728 | LUG WSA 13522.10392882 | 13522 | ROME AVENUE | DNU Lateral Hardening-Fuse-60305728 | Lateral Hardening-Fuse-10392882 | WSA | 0.095644 | 8 | 11 | 2021-11-01 |  |  | N/A | 4500279866 | TBD | LUG C058 | N/A | CKT: 13522 - 10392882 | N/A | N/A | N/A | N/A | 2308133 | LUG WSA 13522.10392882 OH | 2308134 | LUG WSA 13522.10392882 UG | Combined with PRE-09361.187 (FID 91934653) & PRE-09361.247 (FID 10392882)
Enercon | 2021 | 2022 | LUG - TBD647 | PRE-09361.284 | PRE-09361.284 | LUG WSA 13522.60305720 | LUG WSA 13522.60305720 | 13522 | ROME AVENUE | Lateral Hardening-Fuse-60305720 | Lateral Hardening-Fuse-60305720 | WSA | 0.068371 | 6 | 10 | 2021-11-01 |  |  | N/A | 4500279866 | TBD |  | CKT: 13522 - 60305720 | CKT: 13522 - 60305720 | 2304522 | LUG WSA 13522.60305720 OH | 2304536 | LUG WSA 13522.60305720 UG | 2304522 | LUG WSA 13522.60305720 OH | 2304536 | LUG WSA 13522.60305720 UG
Pike | 2021 | 2021 | LUG - TBD166 | PRE-09361.341 | PRE-09361.341 | LUG CSA 13205.90929181 | LUG CSA 13205.90929181 | 13205 | TEMPLE TERRACE | Lateral Hardening-Fuse-90929181 | Lateral Hardening-Fuse-90929181 | CSA | 0.19943 | 15 | 32 | 2021-01-01 | 2021-04-01 | 2021-06-01 | N/A | 4500282886 | TBD |  | CKT: 13205 - 90929181 | CKT: 13205 - 90929181 | 2308083 | LUG CSA 13205.90929181 OH | 2308084 | LUG CSA 13205.90929181 UG | 2308083 | LUG CSA 13205.90929181 OH | 2308084 | LUG CSA 13205.90929181 UG
Pike | 2021 | 2021 | LUG - TBD167 | PRE-09361.342 | PRE-09361.342 | LUG CSA 13021.10051153 | LUG CSA 13021.10051153 | 13021 | JUNEAU | Lateral Hardening-Fuse-10051153 | Lateral Hardening-Fuse-10051153 | CSA | 0.15189 | 6 | 14 | 2021-01-01 | 2021-04-01 | 2021-06-01 | N/A | 4500282886 | TBD |  | CKT: 13021 - 10021153 | CKT: 13021 - 10021153 | 2308242 | LUG CSA 13021.10051153 OH | 2308254 | LUG CSA 13021.10051153 UG | 2308242 | LUG CSA 13021.10051153 OH | 2308254 | LUG CSA 13021.10051153 UG
Pike | 2021 | 2021 | LUG - TBD168 | PRE-09361.343 | PRE-09361.343 | LUG CSA 13026.60059524 | LUG CSA 13026.60059524 | 13026 | TEMPLE TERRACE | Lateral Hardening-Fuse-60059524 | Lateral Hardening-Fuse-60059524 | CSA | 0.18939 | 16 | 115 | 2021-01-01 | 2021-04-01 | 2021-06-01 | N/A | 4500282886 | TBD | LUG C062 | CKT: 13026 - 60059524 | CKT: 13026 - 60059524 | 2308256 | LUG CSA 13026.60059524 OH | 2308264 | LUG CSA 13026.60059524 UG | 2308256 | LUG CSA 13026.60059524 OH | 2308264 | LUG CSA 13026.60059524 UG | Combined with PRE-09361.404 (FID 91490707)
Pike | 2021 | 2021 | LUG - TBD169 | PRE-09361.344 | PRE-09361.344 | LUG CSA 13835.10429522 | LUG CSA 13835.10429522 | 13835 | FLORIDA AVENUE | Lateral Hardening-Fuse-10429522 | Lateral Hardening-Fuse-10429522 | CSA | 0.69015 | 41 | 163 | 2021-01-01 | 2021-04-01 | 2021-06-01 | N/A | 4500282886 | TBD |  | CKT: 13835 - 10429522 | CKT: 13835 - 10429522 | 2308307 | LUG CSA 13835.10429522 OH | 2308309 | LUG CSA 13835.10429522 UG | 2308307 | LUG CSA 13835.10429522 OH | 2308309 | LUG CSA 13835.10429522 UG
Pike | 2021 | 2021 | LUG - TBD170 | PRE-09361.345 | PRE-09361.345 | LUG CSA 13204.91532149 | LUG CSA 13204.91532149 | 13204 | TEMPLE TERRACE | Lateral Hardening-Fuse-91532149 | Lateral Hardening-Fuse-91532149 | CSA | 0.50114 | 39 | 591 | 2021-01-01 | 2021-04-01 | 2021-06-01 | N/A | 4500282886 | TBD |  | CKT: 13204 - 91532149 | CKT: 13204 - 91532149 | 2308318 | LUG CSA 13204.91532149 OH | 2308319 | LUG CSA 13204.91532149 UG | 2308318 | LUG CSA 13204.91532149 OH | 2308319 | LUG CSA 13204.91532149 UG
Pike | 2021 | 2021 | LUG - TBD171 | PRE-09361.346 | PRE-09361.346 | LUG CSA 13836.91406642 | LUG CSA 13836.91406642 | 13836 | FLORIDA AVENUE | Lateral Hardening-Fuse-91406642 | Lateral Hardening-Fuse-91406642 | CSA | 0.098295 | 7 | 42 | 2021-01-01 | 2021-05-01 | 2021-07-01 | N/A | 4500282886 | TBD |  | CKT: 13836 - 91406642 | CKT: 13836 - 91406642 | 2308333 | LUG CSA 13836.91406642 OH | 2308341 | LUG CSA 13836.91406642 UG | 2308333 | LUG CSA 13836.91406642 OH | 2308341 | LUG CSA 13836.91406642 UG
Pike | 2021 | 2021 | LUG - TBD172 | PRE-09361.78 | PRE-09361.78 | DNU LUG CSA 13099.60563698 | LUG CSA 13099.90882614 | 13099 | SUNSET LANE | DNU Lateral Hardening-Fuse-60563698 | Lateral Hardening-Fuse-90882614 | CSA | 0.38144 | 23 | 8 | 2021-01-01 | 2021-05-01 | 2021-07-01 | 4500276922 | N/A | TBD | LUG C008 | N/A | CKT: 13099 - 90882614 | N/A | N/A | N/A | N/A | 2275116 | LUG CSA 13099.90882614 OH | 2275117 | LUG CSA 13099.90882614 UG | Combined with PRE-09361.78 (FID 90882614)
Pike | 2021 | 2021 | LUG - TBD173 | PRE-09361.347 | PRE-09361.347 | LUG CSA 13590.91231633 | LUG CSA 13590.91231633 | 13590 | SENECA STREET | Lateral Hardening-Fuse-91231633 | Lateral Hardening-Fuse-91231633 | CSA | 0.34205 | 29 | 47 | 2021-01-01 | 2021-06-01 | 2021-08-01 | N/A | 4500282886 | TBD |  | CKT: 13590 - 91231633 | CKT: 13590 - 91231633 | 2308378 | LUG CSA 13590.91231633 OH | 2308380 | LUG CSA 13590.91231633 UG | 2308378 | LUG CSA 13590.91231633 OH | 2308380 | LUG CSA 13590.91231633 UG
Pike | 2021 | 2021 | LUG - TBD174 | PRE-09361.348 | PRE-09361.348 | LUG CSA 13102.91293905 | LUG CSA 13102.91293905 | 13102 | YUKON | Lateral Hardening-Fuse-91293905 | Lateral Hardening-Fuse-91293905 | CSA | 0.11629 | 10 | 47 | 2021-01-01 | 2021-06-01 | 2021-08-01 | N/A | 4500282886 | TBD |  | CKT: 13102 - 91293905 | CKT: 13102 - 91293905 | 2308387 | LUG CSA 13102.91293905 OH | 2308393 | LUG CSA 13102.91293905 UG | 2308387 | LUG CSA 13102.91293905 OH | 2308393 | LUG CSA 13102.91293905 UG
Pike | 2021 | 2021 | LUG - TBD175 | PRE-09361.476 | PRE-09361.476 | LUG CSA 13104.10362869 | LUG CSA 13104.10362869 | 13104 | MCFARLAND | Lateral Hardening-Fuse-10362869 | Lateral Hardening-Fuse-10362869 | CSA | 0.3803 | 30 | 67 | 2021-01-01 | 2021-06-01 | 2021-09-01 | N/A | 4500282886 | TBD | LUG C037 | CKT: 13104 - 10362869 | CKT: 13104 - 10362869 | 2311870 | LUG CSA 13104.10362869 OH | 2311875 | LUG CSA 13104.10362869 UG | 2311870 | LUG CSA 13104.10362869 OH | 2311875 | LUG CSA 13104.10362869 UG | Combined with LUG - TBD193 (FID 10362882)
Pike | 2021 | 2021 | LUG - TBD176 | PRE-09361.349 | PRE-09361.349 | LUG CSA 13831.10427677 | LUG CSA 13831.10427677 | 13831 | FOWLER AVENUE | Lateral Hardening-Fuse-10427677 | Lateral Hardening-Fuse-10427677 | CSA | 0.25417 | 18 | 313 | 2021-01-01 | 2021-06-01 | 2021-08-01 | N/A | 4500282886 | TBD |  | CKT: 13831 - 10427677 | CKT: 13831 - 10427677 | 2308403 | LUG CSA 13831.10427677 OH | 2308407 | LUG CSA 13831.10427677 UG | 2308403 | LUG CSA 13831.10427677 OH | 2308407 | LUG CSA 13831.10427677 UG
Pike | 2021 | 2021 | LUG - TBD177 | PRE-09361.350 | PRE-09361.350 | LUG CSA 14040.60233886 | LUG CSA 14040.60233886 | 14040 | HARNEY ROAD | Lateral Hardening-Fuse-60233886 | Lateral Hardening-Fuse-60233886 | CSA | 0.12614 | 12 | 96 | 2021-01-01 | 2021-07-01 | 2021-08-01 | N/A | 4500282886 | TBD |  | CKT: 14040 - 60233886 | CKT: 14040 - 60233886 | 2308411 | LUG CSA 14040.60233886 OH | 2308414 | LUG CSA 14040.60233886 UG | 2308411 | LUG CSA 14040.60233886 OH | 2308414 | LUG CSA 14040.60233886 UG
Pike | 2021 | 2021 | LUG - TBD178 | PRE-09361.351 | PRE-09361.351 | LUG CSA 13939.60144164 | LUG CSA 13939.60144164 | 13939 | LAKE MAGDALENE | Lateral Hardening-Fuse-60144164 | Lateral Hardening-Fuse-60144164 | CSA | 0.12121 | 8 | 38 | 2021-01-01 | 2021-07-01 | 2021-09-01 | N/A | 4500282886 | TBD |  | CKT: 13939 - 60144164 | CKT: 13939 - 60144164 | 2308420 | LUG CSA 13939.60144164 OH | 2308424 | LUG CSA 13939.60144164 UG | 2308420 | LUG CSA 13939.60144164 OH | 2308424 | LUG CSA 13939.60144164 UG
Pike | 2021 | 2021 | LUG - TBD179 | PRE-09361.477 | PRE-09361.477 | LUG CSA 13158.90816343 | LUG CSA 13158.90816343 | 13158 | THIRTIETH STREET | Lateral Hardening-Fuse-90816343 | Lateral Hardening-Fuse-90816343 | CSA | 0.25019 | 18 | 123 | 2021-01-01 | 2021-07-01 | 2021-09-01 | N/A | 4500282886 | TBD | LUG C038 | CKT: 13158 - 90816343 | CKT: 13158 - 90816343 | 2311878 | LUG CSA 13158.90816343 OH | 2311879 | LUG CSA 13158.90816343 UG | 2311878 | LUG CSA 13158.90816343 OH | 2311879 | LUG CSA 13158.90816343 UG | Combined with LUG - TBD181 (FID 93317809)
Pike | 2021 | 2021 | LUG - TBD180 | PRE-09361.352 | PRE-09361.352 | LUG CSA 13021.60058683 | LUG CSA 13021.60058683 | 13021 | JUNEAU | Lateral Hardening-Fuse-60058683 | Lateral Hardening-Fuse-60058683 | CSA | 0.30682 | 28 | 130 | 2021-01-01 | 2021-07-01 | 2021-09-01 | N/A | 4500282886 | TBD |  | CKT: 13021 - 60058683 | CKT: 13021 - 60058683 | 2308837 | LUG CSA 13021.60058683 OH | 2308838 | LUG CSA 13021.60058683 UG | 2308837 | LUG CSA 13021.60058683 OH | 2308838 | LUG CSA 13021.60058683 UG
Pike | 2021 | 2021 | LUG - TBD181 | PRE-09361.477 | PRE-09361.477 | DNU LUG CSA 13158.93317809 | LUG CSA 13158.90816343 | 13158 | THIRTIETH STREET | DNU Lateral Hardening-Fuse-93317809 | Lateral Hardening-Fuse-90816343 | CSA | 0.16534 | 13 | 60 | 2021-01-01 | 2021-07-01 | 2021-09-01 | N/A | 4500282886 | TBD | LUG C038 | N/A | CKT: 13158 - 90816343 | N/A | N/A | N/A | N/A | 2311878 | LUG CSA 13158.90816343 OH | 2311879 | LUG CSA 13158.90816343 UG | Combined with LUG - TBD179/PRE-09361.477 (FID 90816343)
Pike | 2021 | 2021 | LUG - TBD182 | PRE-09361.353 | PRE-09361.353 | LUG CSA 13104.91643108 | LUG CSA 13104.91643108 | 13104 | MCFARLAND | Lateral Hardening-Fuse-91643108 | Lateral Hardening-Fuse-91643108 | CSA | 0.33845 | 33 | 74 | 2021-01-01 | 2021-07-01 | 2021-10-01 | N/A | 4500282886 | TBD |  | CKT: 13104 - 91643108 | CKT: 13104 - 91643108 | 2308844 | LUG CSA 13104.91643108 OH | 2308849 | LUG CSA 13104.91643108 UG | 2308844 | LUG CSA 13104.91643108 OH | 2308849 | LUG CSA 13104.91643108 UG
Pike | 2021 | 2021 | LUG - TBD183 | PRE-09361.480 | PRE-09361.480 | DNU LUG CSA 13106.91795934 | LUG CSA 13106.10361901 | 13106 | MCFARLAND | DNU Lateral Hardening-Fuse-91795934 | Lateral Hardening-Fuse-10361901 | CSA | 0.77973 | 55 | 314 | 2021-01-01 | 2021-07-01 | 2021-10-01 | N/A | 4500282886 | TBD | LUG C039 | DNU CKT : 13106 - 91795934 | CKT : 13106 - 10361901 | 2311881 | LUG CSA 13106.91795934 OH | 2311882 | LUG CSA 13106.91795934 UG | 2311881 | LUG CSA 13106.10361901 OH | 2311882 | LUG CSA 13106.10361901 UG | Combined with LUG - TBD239/PRE-09361.480 (FID 10361901); incorrectly opened in WP with description & street name for 13106.91795934
Pike | 2021 | 2021 | LUG - TBD184 | PRE-09361.354 | PRE-09361.354 | LUG CSA 13835.60314670 | LUG CSA 13835.60314670 | 13835 | FLORIDA AVENUE | Lateral Hardening-Fuse-60314670 | Lateral Hardening-Fuse-60314670 | CSA | 0.21458 | 18 | 256 | 2021-01-01 | 2021-07-01 | 2021-09-01 | N/A | 4500282886 | TBD |  | CKT: 13835 - 60314670 | CKT: 13835 - 60314670 | 2308862 | LUG CSA 13835.60314670 OH | 2308867 | LUG CSA 13835.60314670 UG | 2308862 | LUG CSA 13835.60314670 OH | 2308867 | LUG CSA 13835.60314670 UG
Pike | 2021 | 2021 | LUG - TBD185 | PRE-09361.355 | PRE-09361.355 | LUG CSA 13107.10376186 | LUG CSA 13107.10376186 | 13107 | MCFARLAND | Lateral Hardening-Fuse-10376186 | Lateral Hardening-Fuse-10376186 | CSA | 0.12348 | 10 | 179 | 2021-01-01 | 2021-07-01 | 2021-08-01 | N/A | 4500282886 | TBD |  | CKT: 13107 - 10376186 | CKT: 13107 - 10376186 | 2308912 | LUG CSA 13107.10376186 OH | 2308914 | LUG CSA 13107.10376186 UG | 2308912 | LUG CSA 13107.10376186 OH | 2308914 | LUG CSA 13107.10376186 UG
Pike | 2021 | 2021 | LUG - TBD186 | PRE-09361.356 | PRE-09361.356 | LUG CSA 13592.91365233 | LUG CSA 13592.91365233 | 13592 | SENECA STREET | Lateral Hardening-Fuse-91365233 | Lateral Hardening-Fuse-91365233 | CSA | 0.30777 | 25 | 121 | 2021-02-01 | 2021-07-01 | 2021-09-01 | N/A | 4500282886 | TBD |  | CKT: 13592 - 91365233 | CKT: 13592 - 91365233 | 2308917 | LUG CSA 13592.91365233 OH | 2308921 | LUG CSA 13592.91365233 UG | 2308917 | LUG CSA 13592.91365233 OH | 2308921 | LUG CSA 13592.91365233 UG
Pike | 2021 | 2021 | LUG - TBD187 | PRE-09361.357 | PRE-09361.357 | LUG CSA 13993.10372414 | LUG CSA 13993.10372414 | 13993 | SUNSET LANE | Lateral Hardening-Fuse-10372414 | Lateral Hardening-Fuse-10372414 | CSA | 0.42367 | 27 | 31 | 2021-03-01 | 2021-07-01 | 2021-10-01 | N/A | 4500282886 | TBD |  | CKT: 13993 - 10372414 | CKT: 13993 - 10372414 | 2308925 | LUG CSA 13993.10372414 OH | 2308929 | LUG CSA 13993.10372414 UG | 2308925 | LUG CSA 13993.10372414 OH | 2308929 | LUG CSA 13993.10372414 UG
Pike | 2021 | 2021 | LUG - TBD188 | PRE-09361.92 | PRE-09361.92 | DNU LUG CSA 13100.10371703 | LUG CSA 13100.91340554 | 13100 | YUKON | DNU Lateral Hardening-Fuse-10371703 | Lateral Hardening-Fuse-91340554 | CSA | 0.67973 | 35 | 302 | 2021-03-01 | 2021-07-01 | 2021-10-01 | 4500276922 | N/A | N/A | LUG C016 | N/A | CKT: 13100 - 91340554 | N/A | N/A | N/A | N/A | 2275159 | LUG CSA 13100.91340554 OH | 2275160 | LUG CSA 13100.91340554 UG | Combined with PRE-09361.92 (FID 91340554)
Pike | 2021 | 2021 | LUG - TBD189 | PRE-09361.358 | PRE-09361.358 | LUG CSA 13354.10582069 | LUG CSA 13354.10582069 | 13354 | TWENTY SEVENTH STREET | Lateral Hardening-Fuse-10582069 | Lateral Hardening-Fuse-10582069 | CSA | 0.19205 | 21 | 281 | 2021-03-01 | 2021-10-01 | 2021-12-01 | N/A | 4500282886 | TBD |  | CKT: 13354 - 10582069 | CKT: 13354 - 10582069 | 2308998 | LUG CSA 13354.10582069 OH | 2308999 | LUG CSA 13354.10582069 UG | 2308998 | LUG CSA 13354.10582069 OH | 2308999 | LUG CSA 13354.10582069 UG
Pike | 2021 | 2021 | LUG - TBD190 | PRE-09361.90 | PRE-09361.90 | DNU LUG CSA 13418.92292295 | LUG CSA 13418.92357188 | 13418 | JUNEAU | DNU Lateral Hardening-Fuse-92292295 | Lateral Hardening-Fuse-92357188 | CSA | 0.2375 | 18 | 17 | 2021-03-01 | 2021-10-01 | 2021-12-01 | 4500276922 | N/A | N/A | LUG C017 | N/A | CKT: 13418 - 92357188 | N/A | N/A | N/A | N/A | 2275151 | LUG CSA 13418.92357188 OH | 2275152 | LUG CSA 13418.92357188 UG | Combined with PRE-09361.90 (FID 92357188)
Pike | 2021 | 2021 | LUG - TBD191 | PRE-09361.359 | PRE-09361.359 | LUG CSA 13468.60128378 | LUG CSA 13468.60128378 | 13468 | FIFTY SIXTH STREET | Lateral Hardening-Fuse-60128378 | Lateral Hardening-Fuse-60128378 | CSA | 0.75398 | 56 | 444 | 2021-03-01 | 2021-07-01 | 2021-12-01 | N/A | 4500282886 | TBD |  | CKT: 13468 - 60128378 | CKT: 13468 - 60128378 | 2308961 | LUG CSA 13468.60128378 OH | 2308964 | LUG CSA 13468.60128378 UG | 2308961 | LUG CSA 13468.60128378 OH | 2308964 | LUG CSA 13468.60128378 UG
Pike | 2021 | 2021 | LUG - TBD192 | PRE-09361.360 | PRE-09361.360 | LUG CSA 13632.60305848 | LUG CSA 13632.60305848 | 13632 | PINE LAKE | Lateral Hardening-Fuse-60305848 | Lateral Hardening-Fuse-60305848 | CSA | 0.40417 | 33 | 43 | 2021-03-01 | 2021-09-01 | 2021-12-01 | N/A | 4500282886 | TBD |  | CKT: 13632 - 60305848 | CKT: 13632 - 60305848 | 2308982 | LUG CSA 13632.60305848 OH | 2308983 | LUG CSA 13632.60305848 UG | 2308982 | LUG CSA 13632.60305848 OH | 2308983 | LUG CSA 13632.60305848 UG
Pike | 2021 | 2021 | LUG - TBD193 | PRE-09361.476 | PRE-09361.476 | DNU LUG CSA 13104.10362882 | LUG CSA 13104.10362869 | 13104 | MCFARLAND | DNU Lateral Hardening-Fuse-10362882 | Lateral Hardening-Fuse-10362869 | CSA | 0.11572 | 8 | 26 | 2021-04-01 | 2021-10-01 | 2021-12-01 | N/A | 4500282886 | TBD | LUG C037 | N/A | CKT: 13104 - 10362869 | N/A | N/A | N/A | N/A | 2311870 | LUG CSA 13104.10362869 OH | 2311875 | LUG CSA 13104.10362869 UG | Combined with LUG - TBD175/PRE-09361.476 (FID 10362869)
Pike | 2021 | 2021 | LUG - TBD194 | PRE-09361.361 | PRE-09361.361 | LUG CSA 13176.10375148 | LUG CSA 13176.10375148 | 13176 | ELEVENTH AVENUE | Lateral Hardening-Fuse-10375148 | Lateral Hardening-Fuse-10375148 | CSA | 0.48087 | 54 | 26 | 2021-04-01 | 2021-07-01 | 2021-12-01 | N/A | 4500282886 | TBD |  | CKT: 13176 - 10375148 | CKT: 13176 - 10375148 | 2308967 | LUG CSA 13176.10375148 OH | 2308969 | LUG CSA 13176.10375148 UG | 2308967 | LUG CSA 13176.10375148 OH | 2308969 | LUG CSA 13176.10375148 UG
Pike | 2021 | 2021 | LUG - TBD195 | PRE-09361.362 | PRE-09361.362 | LUG CSA 13099.60125388 | LUG CSA 13099.60125388 | 13099 | SUNSET LANE | Lateral Hardening-Fuse-60125388 | Lateral Hardening-Fuse-60125388 | CSA | 0.43447 | 24 | 68 | 2021-04-01 | 2021-10-01 | 2021-12-01 | N/A | 4500282886 | TBD |  | CKT: 13099 - 60125388 | CKT: 13099 - 60125388 | 2309004 | LUG CSA 13099.60125388 OH | 2309005 | LUG CSA 13099.60125388 UG | 2309004 | LUG CSA 13099.60125388 OH | 2309005 | LUG CSA 13099.60125388 UG
Pike | 2021 | 2021 | LUG - TBD196 | PRE-09361.481 | PRE-09361.481 | DNU LUG CSA 13102.60123660 | LUG CSA 13102.90748252 | 13102 | YUKON | DNU Lateral Hardening-Fuse-60123660 | Lateral Hardening-Fuse-90748252 | CSA | 0.15795 | 6 | 36 | 2021-04-01 | 2021-10-01 | 2021-12-01 | N/A | 4500282886 | TBD | LUG C040 | DNU CKT : 13102 - 60123660 | CKT : 13102 - 90748252 | 2311918 | LUG CSA 13102.60123660 OH | 2311920 | LUG CSA 13102.60123660 UG | 2311918 | LUG CSA 13102.90748252 OH | 2311920 | LUG CSA 13102.90748252 UG | Combined with LUG - TBD244/PRE-09361.481 (FID 90748252); incorrectly opened in WP with description & street name for 13106.60123660
Pike | 2021 | 2021 | LUG - TBD197 | PRE-09361.363 | PRE-09361.363 | LUG CSA 14102.91582612 | LUG CSA 14102.91582612 | 14102 | CROSS CREEK | Lateral Hardening-Fuse-91582612 | Lateral Hardening-Fuse-91582612 | CSA | 0.2964 | 18 | 136 | 2021-04-01 | 2021-10-01 | 2021-12-01 | N/A | 4500282886 | TBD |  | CKT: 14102 - 91582612 | CKT: 14102 - 91582612 | 2309016 | LUG CSA 14102.91582612 OH | 2309017 | LUG CSA 14102.91582612 UG | 2309016 | LUG CSA 14102.91582612 OH | 2309017 | LUG CSA 14102.91582612 UG
Pike | 2021 | 2021 | LUG - TBD198 | PRE-09361.364 | PRE-09361.364 | LUG CSA 13468.60128362 | LUG CSA 13468.60128362 | 13468 | FIFTY SIXTH STREET | Lateral Hardening-Fuse-60128362 | Lateral Hardening-Fuse-60128362 | CSA | 0.53409 | 38 | 147 | 2021-04-01 | 2021-08-01 | 2021-12-01 | N/A | 4500282886 | TBD |  | CKT: 13468 - 60128362 | CKT: 13468 - 60128362 | 2308977 | LUG CSA 13468.60128362 OH | 2308979 | LUG CSA 13468.60128362 UG | 2308977 | LUG CSA 13468.60128362 OH | 2308979 | LUG CSA 13468.60128362 UG
Pike | 2021 | 2021 | LUG - TBD199 | PRE-09361.365 | PRE-09361.365 | LUG CSA 13399.60037987 | LUG CSA 13399.60037987 | 13399 | THIRD AVENUE | Lateral Hardening-Fuse-60037987 | Lateral Hardening-Fuse-60037987 | CSA | 0.18902 | 19 | 19 | 2021-04-01 | 2021-10-01 | 2021-12-01 | N/A | 4500282886 | TBD |  | CKT: 13399 - 60037987 | CKT: 13399 - 60037987 | 2309031 | LUG CSA 13399.60037987 OH | 2309036 | LUG CSA 13399.60037987 UG | 2309031 | LUG CSA 13399.60037987 OH | 2309036 | LUG CSA 13399.60037987 UG
Pike | 2021 | 2021 | LUG - TBD200 | PRE-09361.366 | PRE-09361.366 | LUG CSA 13835.91773975 | LUG CSA 13835.91773975 | 13835 | FLORIDA AVENUE | Lateral Hardening-Fuse-91773975 | Lateral Hardening-Fuse-91773975 | CSA | 0.2714 | 21 | 12 | 2021-04-01 | 2021-10-01 | 2021-12-01 | N/A | 4500282886 | TBD |  | MISSING | MISSING | MISSING | MISSING | MISSING | MISSING | MISSING | MISSING | MISSING | MISSING | OH & UG WR's NEED TO BE OPENED BY 3/5
Pike | 2021 | 2021 | LUG - TBD201 | PRE-09361.367 | PRE-09361.367 | LUG CSA 13418.92018190 | LUG CSA 13418.92018190 | 13418 | JUNEAU | Lateral Hardening-Fuse-92018190 | Lateral Hardening-Fuse-92018190 | CSA | 0.32898 | 21 | 79 | 2021-04-01 | 2021-10-01 | 2021-12-01 | N/A | 4500282886 | TBD |  | CKT: 13418 - 92018190 | CKT: 13418 - 92018190 | 2309045 | LUG CSA 13418.92018190 OH | 2309046 | LUG CSA 13418.92018190 UG | 2309045 | LUG CSA 13418.92018190 OH | 2309046 | LUG CSA 13418.92018190 UG
Pike | 2021 | 2021 | LUG - TBD202 | PRE-09361.478 | PRE-09361.478 | LUG CSA 13158.60011810 | LUG CSA 13158.60011810 | 13158 | THIRTIETH STREET | Lateral Hardening-Fuse-60011810 | Lateral Hardening-Fuse-60011810 | CSA | 0.75795 | 56 | 226 | 2021-03-01 | 2021-07-01 | 2021-12-01 | N/A | 4500282886 | TBD | LUG C041 | CKT : 13158 - 60011810 | CKT : 13158 - 60011810 | 2311887 | LUG CSA 13158.60011810 OH | 2311889 | LUG CSA 13158.60011810 UG | 2311887 | LUG CSA 13158.60011810 OH | 2311889 | LUG CSA 13158.60011810 UG | Combined with LUG - TBD209 (FID 92290015)
Pike | 2021 | 2021 | LUG - TBD203 | PRE-09361.368 | PRE-09361.368 | LUG CSA 13105.10580690 | LUG CSA 13105.10580690 | 13105 | MCFARLAND | Lateral Hardening-Fuse-10580690 | Lateral Hardening-Fuse-10580690 | CSA | 0.23314 | 21 | 122 | 2021-05-01 | 2021-10-01 | 2021-12-01 | N/A | 4500282886 | TBD |  | CKT: 13105 - 10580690 | CKT: 13105 - 10580690 | 2309047 | LUG CSA 13105.10580690 OH | 2309048 | LUG CSA 13105.10580690 UG | 2309047 | LUG CSA 13105.10580690 OH | 2309048 | LUG CSA 13105.10580690 UG
Pike | 2021 | 2021 | LUG - TBD204 | PRE-09361.369 | PRE-09361.369 | LUG CSA 13205.90022802 | LUG CSA 13205.90022802 | 13205 | TEMPLE TERRACE | Lateral Hardening-Fuse-90022802 | Lateral Hardening-Fuse-90022802 | CSA | 0.20152 | 18 | 20 | 2021-05-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13205 - 90022802 | CKT: 13205 - 90022802 | 2309279 | LUG CSA 13205.90022802 OH | 2309281 | LUG CSA 13205.90022802 UG | 2309279 | LUG CSA 13205.90022802 OH | 2309281 | LUG CSA 13205.90022802 UG
Pike | 2021 | 2021 | LUG - TBD205 | PRE-09361.370 | PRE-09361.370 | LUG CSA 13418.91924595 | LUG CSA 13418.91924595 | 13418 | JUNEAU | Lateral Hardening-Fuse-91924595 | Lateral Hardening-Fuse-91924595 | CSA | 0.21515 | 20 | 25 | 2021-06-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13418 - 91924595 | CKT: 13418 - 91924595 | 2309285 | LUG CSA 13418.91924595 OH | 2309295 | LUG CSA 13418.91924595 UG | 2309285 | LUG CSA 13418.91924595 OH | 2309295 | LUG CSA 13418.91924595 UG
Pike | 2021 | 2021 | LUG - TBD206 | PRE-09361.371 | PRE-09361.371 | LUG CSA 13105.60164901 | LUG CSA 13105.60164901 | 13105 | MCFARLAND | Lateral Hardening-Fuse-60164901 | Lateral Hardening-Fuse-60164901 | CSA | 0.11439 | 10 | 79 | 2021-06-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13105 - 60164901 | CKT: 13105 - 60164901 | 2309300 | LUG CSA 13105.60164901 OH | 2309301 | LUG CSA 13105.60164901 UG | 2309300 | LUG CSA 13105.60164901 OH | 2309301 | LUG CSA 13105.60164901 UG
Pike | 2021 | 2021 | LUG - TBD207 | PRE-09361.372 | PRE-09361.372 | LUG CSA 13934.10467597 | LUG CSA 13934.10467597 | 13934 | LAKE MAGDALENE | Lateral Hardening-Fuse-10467597 | Lateral Hardening-Fuse-10467597 | CSA | 0.55871 | 30 | 51 | 2021-06-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13934 - 10467597 | CKT: 13934 - 10467597 | 2309304 | LUG CSA 13934.10467597 OH | 2309305 | LUG CSA 13934.10467597 UG | 2309304 | LUG CSA 13934.10467597 OH | 2309305 | LUG CSA 13934.10467597 UG
Pike | 2021 | 2021 | LUG - TBD208 | PRE-09361.373 | PRE-09361.373 | LUG CSA 13205.90442230 | LUG CSA 13205.90442230 | 13205 | TEMPLE TERRACE | Lateral Hardening-Fuse-90442230 | Lateral Hardening-Fuse-90442230 | CSA | 0.2517 | 25 | 60 | 2021-06-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13205 - 90442230 | CKT: 13205 - 90442230 | 2309348 | LUG CSA 13205.90442230 OH | 2309349 | LUG CSA 13205.90442230 UG | 2309348 | LUG CSA 13205.90442230 OH | 2309349 | LUG CSA 13205.90442230 UG
Pike | 2021 | 2021 | LUG - TBD209 | PRE-09361.478 | PRE-09361.478 | DNU LUG CSA 13158.92290015 | LUG CSA 13158.60011810 | 13158 | THIRTIETH STREET | DNU Lateral Hardening-Fuse-92290015 | Lateral Hardening-Fuse-60011810 | CSA | 0.0625 | 7 | 101 | 2021-06-01 | 2022 | 2022 | N/A | 4500282886 | TBD | LUG C041 | N/A | CKT : 13158 - 60011810 | N/A | N/A | N/A | N/A | 2311887 | LUG CSA 13158.60011810 OH | 2311889 | LUG CSA 13158.60011810 UG | Combined with LUG - TBD202/PRE-09361.478 (FID 60011810)
Pike | 2021 | 2021 | LUG - TBD210 | PRE-09361.374 | PRE-09361.374 | LUG CSA 14040.10786358 | LUG CSA 14040.10786358 | 14040 | HARNEY ROAD | Lateral Hardening-Fuse-10786358 | Lateral Hardening-Fuse-10786358 | CSA | 0.42727 | 19 | 12 | 2021-06-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 14040 - 10786358 | CKT: 14040 - 10786358 | 2309351 | LUG CSA 14040.10786358 OH | 2309353 | LUG CSA 14040.10786358 UG | 2309351 | LUG CSA 14040.10786358 OH | 2309353 | LUG CSA 14040.10786358 UG
Pike | 2021 | 2021 | LUG - TBD211 | PRE-09361.84 | PRE-09361.84 | DNU LUG CSA 13836.93321406 | LUG CSA 13836.91377944 | 13836 | FLORIDA AVENUE | DNU Lateral Hardening-Fuse-93321406 | Lateral Hardening-Fuse-91377944 | CSA | 0.13277 | 8 | 4 | 2021-06-01 | 2022 | 2022 | 4500276922 | N/A | N/A | LUG C013 | N/A | CKT: 13836 - 91377944 | N/A | N/A | N/A | N/A | 2275133 | LUG CSA 13836.91377944 OH | 2275134 | LUG CSA 13836.91377944 UG | Combined with PRE-09361.84 (FID 91377944), PRE-09361.24 (FID 91406672) and other 2021 projects
Pike | 2021 | 2021 | LUG - TBD212 | PRE-09361.375 | PRE-09361.375 | LUG CSA 13105.10580689 | LUG CSA 13105.10580689 | 13105 | MCFARLAND | Lateral Hardening-Fuse-10580689 | Lateral Hardening-Fuse-10580689 | CSA | 0.12765 | 10 | 44 | 2021-06-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13105 - 10580689 | CKT: 13105 - 10580689 | 2309355 | LUG CSA 13105.10580689 OH | 2309356 | LUG CSA 13105.10580689 UG | 2309355 | LUG CSA 13105.10580689 OH | 2309356 | LUG CSA 13105.10580689 UG
Pike | 2021 | 2021 | LUG - TBD213 | PRE-09361.376 | PRE-09361.376 | LUG CSA 13107.10376201 | LUG CSA 13107.10376201 | 13107 | MCFARLAND | Lateral Hardening-Fuse-10376201 | Lateral Hardening-Fuse-10376201 | CSA | 0.13485 | 10 | 8 | 2021-06-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13107 - 10376201 | CKT: 13107 - 10376201 | 2309358 | LUG CSA 13107.10376201 OH | 2309359 | LUG CSA 13107.10376201 UG | 2309358 | LUG CSA 13107.10376201 OH | 2309359 | LUG CSA 13107.10376201 UG
Pike | 2021 | 2021 | LUG - TBD214 | PRE-09361.479 | PRE-09361.479 | DNU LUG CSA 13633.90633859 | LUG CSA 13633.90564142 | 13633 | PINE LAKE | DNU Lateral Hardening-Fuse-90633859 | Lateral Hardening-Fuse-90564142 | CSA | 0.18087 | 6 | 11 | 2021-06-01 | 2022 | 2022 | N/A | 4500282886 | TBD | LUG C042 | DNU CKT : 13633 - 90633859 | CKT : 13633 - 90564142 | 2311932 | DNU LUG CSA 13633.90633859 OH | 2311937 | DNU LUG CSA 13633.90633859 UG | 2311932 | LUG CSA 13633.90564142 OH | 2311937 | LUG CSA 13633.90633859 UG | Combined with LUG - TBD228/PRE-09361.479 (FID 90564142); incorrectly opened in WP with 13633.90633859
Pike | 2021 | 2021 | LUG - TBD215 | PRE-09361.377 | PRE-09361.377 | LUG CSA 13105.10580676 | LUG CSA 13105.10580676 | 13105 | MCFARLAND | Lateral Hardening-Fuse-10580676 | Lateral Hardening-Fuse-10580676 | CSA | 0.13239 | 13 | 14 | 2021-06-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13105 - 10580676 | CKT: 13105 - 10580676 | 2309367 | LUG CSA 13105.10580676 OH | 2309368 | LUG CSA 13105.10580676 UG | 2309367 | LUG CSA 13105.10580676 OH | 2309368 | LUG CSA 13105.10580676 UG | Pike to ensure WR's listed on Melody's list aren't used (2311967 & 2311968)
Pike | 2021 | 2021 | LUG - TBD216 | PRE-09361.84 | PRE-09361.84 | DNU LUG CSA 13836.60133704 | LUG CSA 13836.91377944 | 13836 | FLORIDA AVENUE | DNU Lateral Hardening-Fuse-60133704 | Lateral Hardening-Fuse-91377944 | CSA | 0.18258 | 9 | 1 | 2021-07-01 | 2022 | 2022 | 4500276922 | N/A | N/A | LUG C013 | N/A | CKT: 13836 - 91377944 | N/A | N/A | N/A | N/A | 2275133 | LUG CSA 13836.91377944 OH | 2275134 | LUG CSA 13836.91377944 UG | Combined with PRE-09361.84 (FID 91377944), PRE-09361.24 (FID 91406672) and other 2021 projects
Pike | 2021 | 2021 | LUG - TBD217 | PRE-09361.378 | PRE-09361.378 | LUG CSA 13100.10371697 | LUG CSA 13100.10371697 | 13100 | YUKON | Lateral Hardening-Fuse-10371697 | Lateral Hardening-Fuse-10371697 | CSA | 0.38409 | 32 | 114 | 2021-07-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | MISSING | MISSING | MISSING | MISSING | MISSING | MISSING | MISSING | MISSING | MISSING | MISSING | Melody's list shows WR's as 2275159/2275160, but that is PRE-09361.92, so WR's need to be opened for this project by 3/5, unless they've already been opened
Pike | 2021 | 2021 | LUG - TBD218 | PRE-09361.379 | PRE-09361.379 | LUG CSA 13993.10433144 | LUG CSA 13993.10433144 | 13993 | SUNSET LANE | Lateral Hardening-Fuse-10433144 | Lateral Hardening-Fuse-10433144 | CSA | 0.11913 | 10 | 123 | 2021-07-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13993 - 10433144 | CKT: 13993 - 10433144 | 2309369 | LUG CSA 13993.10433144 OH | 2309370 | LUG CSA 13993.10433144 UG | 2309369 | LUG CSA 13993.10433144 OH | 2309370 | LUG CSA 13993.10433144 UG
Pike | 2021 | 2021 | LUG - TBD219 | PRE-09361.380 | PRE-09361.380 | LUG CSA 13939.60144172 | LUG CSA 13939.60144172 | 13939 | LAKE MAGDALENE | Lateral Hardening-Fuse-60144172 | Lateral Hardening-Fuse-60144172 | CSA | 0.14943 | 15 | 2 | 2021-07-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13939 - 60144172 | CKT: 13939 - 60144172 | 2309371 | LUG CSA 13939.60144172 OH | 2309372 | LUG CSA 13939.60144172 UG | 2309371 | LUG CSA 13939.60144172 OH | 2309372 | LUG CSA 13939.60144172 UG
Pike | 2021 | 2021 | LUG - TBD220 | PRE-09361.381 | PRE-09361.381 | LUG CSA 13158.91461782 | LUG CSA 13158.91461782 | 13158 | THIRTIETH STREET | Lateral Hardening-Fuse-91461782 | Lateral Hardening-Fuse-91461782 | CSA | 0.33428 | 30 | 39 | 2021-07-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13158 - 91461782 | CKT: 13158 - 91461782 | 2309376 | LUG CSA 13158.91461782 OH | 2309377 | LUG CSA 13158.91461782 UG | 2309376 | LUG CSA 13158.91461782 OH | 2309377 | LUG CSA 13158.91461782 UG
Pike | 2021 | 2021 | LUG - TBD221 | PRE-09361.382 | PRE-09361.382 | LUG CSA 13633.91847345 | LUG CSA 13633.91847345 | 13633 | PINE LAKE | Lateral Hardening-Fuse-91847345 | Lateral Hardening-Fuse-91847345 | CSA | 0.086174 | 7 | 1 | 2021-07-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13633 - 91847345 | CKT: 13633 - 91847345 | 2309380 | LUG CSA 13633.91847345 OH | 2309382 | LUG CSA 13633.91847345 UG | 2309380 | LUG CSA 13633.91847345 OH | 2309382 | LUG CSA 13633.91847345 UG
Pike | 2021 | 2021 | LUG - TBD222 | PRE-09361.383 | PRE-09361.383 | LUG CSA 13934.10467575 | LUG CSA 13934.10467575 | 13934 | LAKE MAGDALENE | Lateral Hardening-Fuse-10467575 | Lateral Hardening-Fuse-10467575 | CSA | 0.091288 | 6 | 1 | 2021-07-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13934 - 10467575 | CKT: 13934 - 10467575 | 2309573 | LUG CSA 13934.10467575 OH | 2309574 | LUG CSA 13934.10467575 UG | 2309573 | LUG CSA 13934.10467575 OH | 2309574 | LUG CSA 13934.10467575 UG
Pike | 2021 | 2021 | LUG - TBD223 | PRE-09361.384 | PRE-09361.384 | LUG CSA 13188.92070695 | LUG CSA 13188.92070695 | 13188 | PINE LAKE | Lateral Hardening-Fuse-92070695 | Lateral Hardening-Fuse-92070695 | CSA | 0.1697 | 11 | 17 | 2021-07-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13188 - 92070695 | CKT: 13188 - 92070695 | 2309575 | LUG CSA 13188.92070695 OH | 2309576 | LUG CSA 13188.92070695 UG | 2309575 | LUG CSA 13188.92070695 OH | 2309576 | LUG CSA 13188.92070695 UG
Pike | 2021 | 2021 | LUG - TBD224 | PRE-09361.84 | PRE-09361.84 | DNU LUG CSA 13836.60133698 | LUG CSA 13836.91377944 | 13836 | FLORIDA AVENUE | DNU Lateral Hardening-Fuse-60133698 | Lateral Hardening-Fuse-91377944 | CSA | 0.44489 | 26 | 76 | 2021-07-01 | 2022 | 2022 | 4500276922 | N/A | N/A | LUG C013 | N/A | CKT: 13836 - 91377944 | N/A | N/A | N/A | N/A | 2275133 | LUG CSA 13836.91377944 OH | 2275134 | LUG CSA 13836.91377944 UG | Combined with PRE-09361.84 (FID 91377944), PRE-09361.24 (FID 91406672) and other 2021 projects
Pike | 2021 | 2021 | LUG - TBD225 | PRE-09361.385 | PRE-09361.385 | LUG CSA 13948.10442391 | LUG CSA 13948.10442391 | 13948 | JUNEAU | Lateral Hardening-Fuse-10442391 | Lateral Hardening-Fuse-10442391 | CSA | 0.21534 | 19 | 34 | 2021-07-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13948 - 10442391 | CKT: 13948 - 10442391 | 2309577 | LUG CSA 13948.10442391 OH | 2309578 | LUG CSA 13948.10442391 UG | 2309577 | LUG CSA 13948.10442391 OH | 2309578 | LUG CSA 13948.10442391 UG
Pike | 2021 | 2021 | LUG - TBD226 | PRE-09361.23 | PRE-09361.23 | DNU LUG CSA 14040.90485522 | LUG CSA 14040.10786374 | 14040 | HARNEY ROAD | DNU Lateral Hardening-Fuse-90485522 | Lateral Hardening-Fuse-10786374 | CSA | 0.1125 | 10 | 22 | 2021-07-01 | 2022 | 2022 | 4500276922 | N/A | N/A | LUG C012 | N/A | CKT: 14040 - 10786374 | N/A | N/A | N/A | N/A | 2271630 | LUG CSA 14040.10786374 OH | 2271645 | LUG CSA 14040.10786374 UG | Combined with PRE-09361.23 (FID 10786374)
Pike | 2021 | 2021 | LUG - TBD227 | PRE-09361.386 | PRE-09361.386 | LUG CSA 13158.92347931 | LUG CSA 13158.92347931 | 13158 | THIRTIETH STREET | Lateral Hardening-Fuse-92347931 | Lateral Hardening-Fuse-92347931 | CSA | 0.29242 | 29 |  | 2021-07-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13158 - 92347931 | CKT: 13158 - 92347931 | 2309580 | LUG CSA 13158.92347931 OH | 2309581 | LUG CSA 13158.92347931 UG | 2309580 | LUG CSA 13158.92347931 OH | 2309581 | LUG CSA 13158.92347931 UG
Pike | 2021 | 2021 | LUG - TBD228 | PRE-09361.479 | PRE-09361.479 | LUG CSA 13633.90564142 | LUG CSA 13633.90564142 | 13633 | PINE LAKE | Lateral Hardening-Fuse-90564142 | Lateral Hardening-Fuse-90564142 | CSA | 0.073106 | 3 | 2 | 2021-08-01 | 2022 | 2022 | N/A | 4500282886 | TBD | LUG C042 | DNU CKT : 13633 - 90633859 | CKT : 13633 - 90564142 | 2311932 | DNU LUG CSA 13633.90633859 OH | 2311937 | DNU LUG CSA 13633.90633859 UG | 2311932 | LUG CSA 13633.90564142 OH | 2311937 | LUG CSA 13633.90633859 UG | Combined with LUG - TBD214 (FID 90633859); incorrectly opened in WP with 13633.90633859
Pike | 2021 | 2021 | LUG - TBD229 | PRE-09361.387 | PRE-09361.387 | LUG DCA 13006.92949400 | LUG DCA 13006.92949400 | 13006 | FORT KING HIGHWAY | Lateral Hardening-Fuse-92949400 | Lateral Hardening-Fuse-92949400 | DCA | 1.2864 | 48 | 41 | 2021-07-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13006 - 92949400 | CKT: 13006 - 92949400 | 2309584 | LUG DCA 13006.92949400 OH | 2309586 | LUG DCA 13006.92949400 UG | 2309584 | LUG DCA 13006.92949400 OH | 2309586 | LUG DCA 13006.92949400 UG
Pike | 2021 | 2021 | LUG - TBD230 | PRE-09361.388 | PRE-09361.388 | LUG DCA 13432.10761257 | LUG DCA 13432.10761257 | 13432 | SAN ANTONIO | Lateral Hardening-Fuse-10761257 | Lateral Hardening-Fuse-10761257 | DCA | 1.2106 | 38 | 21 | 2021-08-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13432 - 10761257 | CKT: 13432 - 10761257 | 2309582 | LUG DCA 13432.10761257 OH | 2309583 | LUG DCA 13432.10761257 UG | 2309582 | LUG DCA 13432.10761257 OH | 2309583 | LUG DCA 13432.10761257 UG
Pike | 2021 | 2021 | LUG - TBD231 | PRE-09361.389 | PRE-09361.389 | LUG CSA 13826.60127680 | LUG CSA 13826.60127680 | 13826 | FOWLER AVENUE | Lateral Hardening-Fuse-60127680 | Lateral Hardening-Fuse-60127680 | CSA | 0.2733 | 13 | 243 | 2021-08-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13826 - 60127680 | CKT: 13826 - 60127680 | 2309587 | LUG CSA 13826.60127680 OH | 2309589 | LUG CSA 13826.60127680 UG | 2309587 | LUG CSA 13826.60127680 OH | 2309589 | LUG CSA 13826.60127680 UG
Pike | 2021 | 2021 | LUG - TBD232 | PRE-09361.390 | PRE-09361.390 | LUG CSA 13632.10408290 | LUG CSA 13632.10408290 | 13632 | PINE LAKE | Lateral Hardening-Fuse-10408290 | Lateral Hardening-Fuse-10408290 | CSA | 1.0176 | 55 | 245 | 2021-09-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13632 - 10408290 | CKT: 13632 - 10408290 | 2310269 | LUG CSA 13632.10408290 OH | 2310270 | LUG CSA 13632.10408290 UG | 2310269 | LUG CSA 13632.10408290 OH | 2310270 | LUG CSA 13632.10408290 UG
Pike | 2021 | 2021 | LUG - TBD233 | PRE-09361.391 | PRE-09361.391 | LUG CSA 13204.60170504 | LUG CSA 13204.60170504 | 13204 | TEMPLE TERRACE | Lateral Hardening-Fuse-60170504 | Lateral Hardening-Fuse-60170504 | CSA | 0.37992 | 31 | 113 | 2021-09-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13204 - 60170504 | CKT: 13204 - 60170504 | 2310274 | LUG CSA 13204.60170504 OH | 2310275 | LUG CSA 13204.60170504 UG | 2310274 | LUG CSA 13204.60170504 OH | 2310275 | LUG CSA 13204.60170504 UG
Pike | 2021 | 2021 | LUG - TBD234 | PRE-09361.392 | PRE-09361.392 | LUG CSA 13176.10375141 | LUG CSA 13176.10375141 | 13176 | ELEVENTH AVENUE | Lateral Hardening-Fuse-10375141 | Lateral Hardening-Fuse-10375141 | CSA | 0.62348 | 51 | 89 | 2021-09-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13176 - 10375141 | CKT: 13176 - 10375141 | 2310278 | LUG CSA 13176.10375141 OH | 2310283 | LUG CSA 13176.10375141 UG | 2310278 | LUG CSA 13176.10375141 OH | 2310283 | LUG CSA 13176.10375141 UG
Pike | 2021 | 2021 | LUG - TBD235 | PRE-09361.393 | PRE-09361.393 | LUG CSA 13948.10442379 | LUG CSA 13948.10442379 | 13948 | YUKON | Lateral Hardening-Fuse-10442379 | Lateral Hardening-Fuse-10442379 | CSA | 0.13788 | 12 | 5 | 2021-09-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13948 - 10442379 | CKT: 13948 - 10442379 | 2310284 | LUG CSA 13948.10442379 OH | 2310286 | LUG CSA 13948.10442379 UG | 2310284 | LUG CSA 13948.10442379 OH | 2310286 | LUG CSA 13948.10442379 UG
Pike | 2021 | 2021 | LUG - TBD236 | PRE-09361.394 | PRE-09361.394 | LUG CSA 13835.10429505 | LUG CSA 13835.10429505 | 13835 | FLORIDA AVENUE | Lateral Hardening-Fuse-10429505 | Lateral Hardening-Fuse-10429505 | CSA | 0.20303 | 17 | 41 | 2021-09-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13835 - 10429505 | CKT: 13835 - 10429505 | 2310287 | LUG CSA 13835.10429505 OH | 2310291 | LUG CSA 13835.10429505 UG | 2310287 | LUG CSA 13835.10429505 OH | 2310291 | LUG CSA 13835.10429505 UG
Pike | 2021 | 2021 | LUG - TBD237 | PRE-09361.395 | PRE-09361.395 | LUG CSA 13026.60059509 | LUG CSA 13026.60059509 | 13026 | TEMPLE TERRACE | Lateral Hardening-Fuse-60059509 | Lateral Hardening-Fuse-60059509 | CSA | 0.085795 | 8 | 84 | 2021-09-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13026 - 60059509 | CKT: 13026 - 60059509 | 2310293 | LUG CSA 13026.60059509 OH | 2310296 | LUG CSA 13026.60059509 UG | 2310293 | LUG CSA 13026.60059509 OH | 2310296 | LUG CSA 13026.60059509 UG
Pike | 2021 | 2021 | LUG - TBD238 | PRE-09361.396 | PRE-09361.396 | LUG CSA 13021.92350282 | LUG CSA 13021.92350282 | 13021 | JUNEAU | Lateral Hardening-Fuse-92350282 | Lateral Hardening-Fuse-92350282 | CSA | 0.3178 | 27 | 14 | 2021-09-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13021 - 92350282 | CKT: 13021 - 92350282 | 2310299 | LUG CSA 13021.92350282 OH | 2310300 | LUG CSA 13021.92350282 UG | 2310299 | LUG CSA 13021.92350282 OH | 2310300 | LUG CSA 13021.92350282 UG
Pike | 2021 | 2021 | LUG - TBD239 | PRE-09361.480 | PRE-09361.480 | LUG CSA 13106.10361901 | LUG CSA 13106.10361901 | 13106 | MCFARLAND | Lateral Hardening-Fuse-10361901 | Lateral Hardening-Fuse-10361901 | CSA | 0.74848 | 52 | 274 | 2021-09-01 | 2022 | 2022 | N/A | 4500282886 | TBD | LUG C039 | DNU CKT : 13106 - 91795934 | CKT : 13106 - 10361901 | 2311881 | LUG CSA 13106.91795934 OH | 2311882 | LUG CSA 13106.91795934 UG | 2311881 | LUG CSA 13106.10361901 OH | 2311882 | LUG CSA 13106.10361901 UG | Combined with LUG - TBD183 (FID 91795934); incorrectly opened in WP with description & street name for 13106.91795934
Pike | 2021 | 2021 | LUG - TBD240 | PRE-09361.397 | PRE-09361.397 | LUG CSA 13468.91640192 | LUG CSA 13468.91640192 | 13468 | FIFTY SIXTH STREET | Lateral Hardening-Fuse-91640192 | Lateral Hardening-Fuse-91640192 | CSA | 0.10682 | 7 | 6 | 2021-09-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13468 - 91640192 | CKT: 13468 - 91640192 | 2310304 | LUG CSA 13468.91640192 OH | 2310305 | LUG CSA 13468.91640192 UG | 2310304 | LUG CSA 13468.91640192 OH | 2310305 | LUG CSA 13468.91640192 UG
Pike | 2021 | 2021 | LUG - TBD241 | PRE-09361.398 | PRE-09361.398 | LUG CSA 13106.91722510 | LUG CSA 13106.91722510 | 13106 | MCFARLAND | Lateral Hardening-Fuse-91722510 | Lateral Hardening-Fuse-91722510 | CSA | 0.10852 | 9 | 166 | 2021-10-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13106 - 91722510 | CKT: 13106 - 91722510 | 2310323 | LUG CSA 13106.91722510 OH | 2310324 | LUG CSA 13106.91722510 UG | 2310323 | LUG CSA 13106.91722510 OH | 2310324 | LUG CSA 13106.91722510 UG
Pike | 2021 | 2021 | LUG - TBD242 | PRE-09361.399 | PRE-09361.399 | LUG CSA 13026.60059452 | LUG CSA 13026.60059452 | 13026 | TEMPLE TERRACE | Lateral Hardening-Fuse-60059452 | Lateral Hardening-Fuse-60059452 | CSA | 0.16383 | 11 | 64 | 2021-10-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13026 - 60059452 | CKT: 13026 - 60059452 | 2310327 | LUG CSA 13026.60059452 OH | 2310330 | LUG CSA 13026.60059452 UG | 2310327 | LUG CSA 13026.60059452 OH | 2310330 | LUG CSA 13026.60059452 UG
Pike | 2021 | 2021 | LUG - TBD243 | PRE-09361.400 | PRE-09361.400 | LUG CSA 13632.10408272 | LUG CSA 13632.10408272 | 13632 | PINE LAKE | Lateral Hardening-Fuse-10408272 | Lateral Hardening-Fuse-10408272 | CSA | 0.097727 | 9 | 12 | 2021-11-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13632 - 10408272 | CKT: 13632 - 10408272 | 2310332 | LUG CSA 13632.10408272 OH | 2310334 | LUG CSA 13632.10408272 UG | 2310332 | LUG CSA 13632.10408272 OH | 2310334 | LUG CSA 13632.10408272 UG
Pike | 2021 | 2021 | LUG - TBD244 | PRE-09361.481 | PRE-09361.481 | LUG CSA 13102.90748252 | LUG CSA 13102.90748252 | 13102 | YUKON | Lateral Hardening-Fuse-90748252 | Lateral Hardening-Fuse-90748252 | CSA | 0.23333 | 23 | 29 | 2021-10-01 | 2022 | 2022 | N/A | 4500282886 | TBD | LUG C040 | DNU CKT : 13102 - 60123660 | CKT : 13102 - 90748252 | 2311918 | LUG CSA 13102.60123660 OH | 2311920 | LUG CSA 13102.60123660 UG | 2311918 | LUG CSA 13102.90748252 OH | 2311920 | LUG CSA 13102.90748252 UG | Combined with LUG - TBD196 (FID 60123660); incorrectly opened in WP with description & street name for 13106.60123660
Pike | 2021 | 2021 | LUG - TBD245 | PRE-09361.79 | PRE-09361.79 | DNU LUG CSA 13093.60029740 | LUG CSA 13093.91004837 | 13093 | PLYMOUTH STREET | DNU Lateral Hardening-Fuse-60029740 | Lateral Hardening-Fuse-91004837 | CSA | 0.29716 | 24 | 65 | 2021-10-01 | 2022 | 2022 | 4500276922 | N/A | N/A | LUG C009 | N/A | CKT: 13093 - 91004837 | N/A | N/A | N/A | N/A | 2275118 | LUG CSA 13093.91004837 OH | 2275120 | LUG CSA 13093.91004837 UG | Combined with PRE-09361.79 (FID 91004837) & PRE-09361.83 (FID 91004843)
Pike | 2021 | 2021 | LUG - TBD246 | PRE-09361.85 | PRE-09361.85 | DNU LUG CSA 13102.60123656 | LUG CSA 13102.60123654 | 13102 | YUKON | DNU Lateral Hardening-Fuse-60123656 | Lateral Hardening-Fuse-60123654 | CSA | 0.14867 | 18 | 26 | 2021-10-01 | 2022 | 2022 | 4500276922 | N/A | N/A | LUG C014 | N/A | CKT: 13102 - 60123654 | N/A | N/A | N/A | N/A | 2275137 | LUG CSA 13102.60123654 OH | 2275138 | LUG CSA 13102.60123654 UG | Combined with PRE-09361.85 (FID 60123654)
Pike | 2021 | 2021 | LUG - TBD247 | PRE-09361.401 | PRE-09361.401 | LUG CSA 13026.60059457 | LUG CSA 13026.60059457 | 13026 | TEMPLE TERRACE | Lateral Hardening-Fuse-60059457 | Lateral Hardening-Fuse-60059457 | CSA | 0.20814 | 15 | 24 | 2021-10-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13026 - 60059457 | CKT: 13026 - 60059457 | 2310335 | LUG CSA 13026.60059457 OH | 2310336 | LUG CSA 13026.60059457 UG | 2310335 | LUG CSA 13026.60059457 OH | 2310336 | LUG CSA 13026.60059457 UG
Pike | 2021 | 2021 | LUG - TBD248 | PRE-09361.402 | PRE-09361.402 | LUG CSA 13099.10368943 | LUG CSA 13099.10368943 | 13099 | SUNSET LANE | Lateral Hardening-Fuse-10368943 | Lateral Hardening-Fuse-10368943 | CSA | 0.24242 | 13 | 2 | 2021-10-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13099 - 10368943 | CKT: 13099 - 10368943 | 2310338 | LUG CSA 13099.10368943 OH | 2310340 | LUG CSA 13099.10368943 UG | 2310338 | LUG CSA 13099.10368943 OH | 2310340 | LUG CSA 13099.10368943 UG
Pike | 2021 | 2021 | LUG - TBD249 | PRE-09361.403 | PRE-09361.403 | LUG CSA 13104.91668251 | LUG CSA 13104.91668251 | 13104 | MCFARLAND | Lateral Hardening-Fuse-91668251 | Lateral Hardening-Fuse-91668251 | CSA | 0.20265 | 17 | 16 | 2021-10-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13104 - 91668251 | CKT: 13104 - 91668251 | 2310343 | LUG CSA 13104.91668251 OH | 2310345 | LUG CSA 13104.91668251 UG | 2310343 | LUG CSA 13104.91668251 OH | 2310345 | LUG CSA 13104.91668251 UG
Pike | 2021 | 2021 | LUG - TBD250 | PRE-09361.343 | PRE-09361.404 | DNU LUG CSA 13026.91490707 | LUG CSA 13026.60059524 | 13026 | TEMPLE TERRACE | DNU Lateral Hardening-Fuse-91490707 | Lateral Hardening-Fuse-60059524 | CSA | 0.28409 | 15 | 98 | 2021-10-01 | 2022 | 2022 | N/A | 4500282886 | TBD | LUG C062 | DNU CKT: 13026 - 91490707 | CKT: 13026 - 60059524 | 2310348 | DNU LUG CSA 13026.91490707 OH | 2310349 | DNU LUG CSA 13026.91490707 UG | 2308256 | LUG CSA 13026.60059524 OH | 2308264 | LUG CSA 13026.60059524 UG | Combined with PRE-09361.343 (FID 60059524)
Pike | 2021 | 2021 | LUG - TBD251 | PRE-09361.482 | PRE-09361.482 | LUG CSA 13176.10375136 | LUG CSA 13176.10375136 | 13176 | ELEVENTH AVENUE | Lateral Hardening-Fuse-10375136 | Lateral Hardening-Fuse-10375136 | CSA | 0.65701 | 57 | 11 | 2021-09-01 | 2022 | 2022 | N/A | 4500282886 | TBD | U - LUG C015 | CKT: 13176 - 10375136 | CKT: 13176 - 10375136 | 2311474 | LUG CSA 13176.10375136 OH | 2311477 | LUG CSA 13176.10375136 UG | 2311474 | LUG CSA 13176.10375136 OH | 2311477 | LUG CSA 13176.10375136 UG | Originally combined with PRE-09361.87 (FID 10375134), but now uncombined
Pike | 2021 | 2021 | LUG - TBD252 | PRE-09361.405 | PRE-09361.405 | LUG CSA 13104.91241032 | LUG CSA 13104.91241032 | 13104 | MCFARLAND | Lateral Hardening-Fuse-91241032 | Lateral Hardening-Fuse-91241032 | CSA | 0.15038 | 18 | 19 | 2021-11-01 | 2022 | 2022 | N/A | 4500282886 | TBD |  | CKT: 13104 - 91241032 | CKT: 13104 - 91241032 | 2310351 | LUG CSA 13104.91241032 OH | 2310353 | LUG CSA 13104.91241032 UG | 2310351 | LUG CSA 13104.91241032 OH | 2310353 | LUG CSA 13104.91241032 UG
Leidos | 2020 | 2020 | LUG - TBD326 | PRE-09361.11 | PRE-09361.11 | LUG ESA 13174.60588225 | LUG ESA 13174.60588225 | 13174 | MADISON | Lateral Hardening-Fuse-60588225 | Lateral Hardening-Fuse-60588225 | ESA | 0.29091 | 15 | 374 | 2020-06-01 | 2020-12-01 | 2020-12-01 | 4500271952 | N/A | N/A |  | CKT: 13174 - 60588225 | CKT: 13174 - 60588225 | 2271218 | LUG ESA 13174.60588225 OH | 2271221 | LUG ESA 13174.60588225 UG | 2271218 | LUG ESA 13174.60588225 OH | 2271221 | LUG ESA 13174.60588225 UG
Leidos | 2020 | 2020 | LUG - TBD327 | PRE-09361.12 | PRE-09361.12 | LUG ESA 13454.90755954 | LUG ESA 13454.90755954 | 13454 | LAKEWOOD | Lateral Hardening-Fuse-90755954 | Lateral Hardening-Fuse-90755954 | ESA | 0.29564 | 23 | 292 | 2020-06-01 | 2020-11-01 | 2020-12-01 | 4500271952 | N/A | N/A |  | CKT: 13454 - 90755954 | CKT: 13454 - 90755954 | 2277333 | LUG ESA 13454.90755954 OH | 2277335 | LUG ESA 13454.90755954 UG | 2277333 | LUG ESA 13454.90755954 OH | 2277335 | LUG ESA 13454.90755954 UG
Leidos | 2020 | 2020 | LUG - TBD328 | PRE-09361.13 | PRE-09361.13 | LUG ESA 13174.60451701 | LUG ESA 13174.60451701 | 13174 | MADISON | Lateral Hardening-Fuse-60451701 | Lateral Hardening-Fuse-60451701 | ESA | 0.2447 | 14 | 301 | 2020-06-01 | 2020-10-01 | 2020-12-01 | 4500271952 | N/A | N/A | LUG C003 | CKT: 13174 - 60451701 | CKT: 13174 - 60451701 | 2277343 | LUG ESA 13174.60451701 OH | 2277348 | LUG ESA 13174.60451701 UG | 2277343 | LUG ESA 13174.60451701 OH | 2277348 | LUG ESA 13174.60451701 UG | Combined with LUG-TBD382 (FID 10913197)
Leidos | 2020 | 2020 | LUG - TBD329 | PRE-09361.14 | PRE-09361.14 | LUG ESA 13710.92881445 | LUG ESA 13710.92881445 | 13710 | BUCKHORN | Lateral Hardening-Fuse-92881445 | Lateral Hardening-Fuse-92881445 | ESA | 0.44867 | 32 | 158 | 2020-06-01 | 2020-11-01 | 2021-03-01 | 4500271952 | N/A | N/A |  | CKT: 13710 - 92881445 | CKT: 13710 - 92881445 | 2277357 | LUG ESA 13710.92881445 OH | 2277359 | LUG ESA 13710.92881445 UG | 2277357 | LUG ESA 13710.92881445 OH | 2277359 | LUG ESA 13710.92881445 UG
Leidos | 2020 | 2020 | LUG - TBD330 | PRE-09361.15 | PRE-09361.15 | LUG ESA 13509.60287236 | LUG ESA 13509.60287236 | 13509 | STATE ROAD 574 | Lateral Hardening-Fuse-60287236 | Lateral Hardening-Fuse-60287236 | ESA | 0.14527 | 14 | 144 | 2020-07-01 | 2021-01-01 | 2021-03-01 | 4500271952 | N/A | N/A |  | CKT: 13509 - 60287236 | CKT: 13509 - 60287236 | 2277364 | LUG ESA 13509.60287236 OH | 2277368 | LUG ESA 13509.60287236 UG | 2277364 | LUG ESA 13509.60287236 OH | 2277368 | LUG ESA 13509.60287236 UG
Leidos | 2020 | 2020 | LUG - TBD331 | PRE-09361.16 | PRE-09361.16 | LUG SHA 13897.10933151 | LUG SHA 13897.10933151 | 13897 | FIRST STREET | Lateral Hardening-Fuse-10933151 | Lateral Hardening-Fuse-10933151 | SHA | 0.78845 | 33 | 64 | 2020-07-01 | 2021-01-01 | 2021-07-01 | 4500271952 | N/A | N/A |  | CKT: 13897 - 10933151 | CKT: 13897 - 10933151 | 2277378 | LUG SHA 13897.10933151 OH | 2277380 | LUG SHA 13897.10933151 UG | 2277378 | LUG SHA 13897.10933151 OH | 2277380 | LUG SHA 13897.10933151 UG
Leidos | 2020 | 2020 | LUG - TBD332 | PRE-09361.17 | PRE-09361.17 | LUG ESA 13174.10913196 | LUG ESA 13174.10913196 | 13174 | MADISON | Lateral Hardening-Fuse-10913196 | Lateral Hardening-Fuse-10913196 | ESA | 0.21269 | 8 | 241 | 2020-07-01 | 2021-01-01 | 2021-03-01 | 4500271952 | N/A | N/A | LUG C002 | CKT: 13174 - 10913196 | CKT: 13174 - 10913196 | 2277381 | LUG ESA 13174.10913196 OH | 2277382 | LUG ESA 13174.10913196 UG | 2277381 | LUG ESA 13174.10913196 OH | 2277382 | LUG ESA 13174.10913196 UG | Combined with LUG-TBD373 (FID 93310101)
Leidos | 2020 | 2020 | LUG - TBD333 | PRE-09361.18 | PRE-09361.18 | LUG ESA 13171.90598389 | LUG ESA 13171.90598389 | 13171 | MADISON | Lateral Hardening-Fuse-90598389 | Lateral Hardening-Fuse-90598389 | ESA | 0.21383 | 11 | 370 | 2020-07-01 | 2021-01-01 | 2021-03-01 | 4500271952 | N/A | N/A | LUG C006 | CKT: 13171 - 90598389 | CKT: 13171 - 90598389 | 2277383 | LUG ESA 13171.90598389 OH | 2277385 | LUG ESA 13171.90598389 UG | 2277383 | LUG ESA 13171.90598389 OH | 2277385 | LUG ESA 13171.90598389 UG | Combined with PRE-09361.118 (FID 90374558) & LUG-TBD376 (FID 10455414)
Leidos | 2020 | 2020 | LUG - TBD334 | PRE-09361.19 | PRE-09361.19 | LUG ESA 13211.60044019 | LUG ESA 13211.60044019 | 13211 | FAIRGROUNDS | Lateral Hardening-Fuse-60044019 | Lateral Hardening-Fuse-60044019 | ESA | 0.52746 | 43 | 395 | 2020-07-01 | 2021-01-01 | 2021-04-01 | 4500271952 | N/A | N/A |  | CKT: 13211 - 60044019 | CKT: 13211 - 60044019 | 2277387 | LUG ESA 13211.60044019 OH | 2277389 | LUG ESA 13211.60044019 UG | 2277387 | LUG ESA 13211.60044019 OH | 2277389 | LUG ESA 13211.60044019 UG
Leidos | 2020 | 2020 | LUG - TBD335 | PRE-09361.20 | PRE-09361.20 | LUG ESA 13231.10868138 | LUG ESA 13231.10868138 | 13231 | BRANDON | Lateral Hardening-Fuse-10868138 | Lateral Hardening-Fuse-10868138 | ESA | 0.53977 | 34 | 269 | 2020-07-01 | 2021-01-01 | 2021-04-01 | 4500271952 | N/A | N/A | LUG C004 | CKT: 13231 - 10868138 | CKT: 13231 - 10868138 | 2290199 | LUG ESA 13231.10868138 OH | 2290200 | LUG ESA 13231.10868138 UG | 2290199 | LUG ESA 13231.10868138 OH | 2290200 | LUG ESA 13231.10868138 UG | Combined with LUG-TBD381 (FID 10868120)
Leidos | 2020 | 2020 | LUG - TBD336 | PRE-09361.101 | PRE-09361.101 | LUG ESA 13230.10471354 | LUG ESA 13230.10471354 | 13230 | BRANDON | Lateral Hardening-Fuse-10471354 | Lateral Hardening-Fuse-10471354 | ESA | 0.44242 | 38 | 49 | 2020-07-01 | 2021-01-01 | 2021-04-01 | 4500271952 | N/A | N/A |  | CKT: 13230 - 10471354 | CKT: 13230 - 10471354 | 2290383 | LUG ESA 13230.10471354 OH | 2290386 | LUG ESA 13230.10471354 UG | 2290383 | LUG ESA 13230.10471354 OH | 2290386 | LUG ESA 13230.10471354 UG
Leidos | 2020 | 2020 | LUG - TBD337 | PRE-09361.102 | PRE-09361.102 | LUG ESA 13502.92679861 | LUG ESA 13502.92679861 | 13502 | STATE ROAD 574 | Lateral Hardening-Fuse-92679861 | Lateral Hardening-Fuse-92679861 | ESA | 0.17614 | 16 | 50 | 2020-07-01 | 2021-01-01 | 2021-03-01 | 4500271952 | N/A | N/A |  | CKT: 13502 - 92679861 | CKT: 13502 - 92679861 | 2290442 | LUG ESA 13502.92679861 OH | 2290446 | LUG ESA 13502.92679861 UG | 2290442 | LUG ESA 13502.92679861 OH | 2290446 | LUG ESA 13502.92679861 UG
Leidos | 2020 | 2020 | LUG - TBD338 | PRE-09361.103 | PRE-09361.103 | LUG ESA 13796.10842826 | LUG ESA 13796.10842826 | 13796 | SAINT CLOUD | Lateral Hardening-Fuse-10842826 | Lateral Hardening-Fuse-10842826 | ESA | 0.15189 | 13 | 353 | 2020-07-01 | 2021-01-01 | 2021-03-01 | 4500271952 | N/A | N/A |  | CKT: 13796 - 10842826 | CKT: 13796 - 10842826 | 2290447 | LUG ESA 13796.10842826 OH | 2290448 | LUG ESA 13796.10842826 UG | 2290447 | LUG ESA 13796.10842826 OH | 2290448 | LUG ESA 13796.10842826 UG
Leidos | 2020 | 2020 | LUG - TBD339 | PRE-09361.128 | PRE-09361.104 | DNU LUG ESA 13454.60140423 | LUG ESA 13454.90429155 | 13454 | LAKEWOOD | DNU Lateral Hardening-Fuse-60140423 | Lateral Hardening-Fuse-90429155 | ESA | 0.51231 | 33 | 290 | 2020-07-01 | 2021-01-01 | 2021-04-01 | 4500271952 | N/A | N/A | LUG C005 | DNU CKT: 13454 - 60140423 | CKT: 13454 - 90429155 | 2290450 | DNU LUG ESA 13454.60140423 OH | 2290459 | DNU LUG ESA 13454.60140423 UG | 2277417 | LUG ESA 13454.90429155 OH | 2277418 | LUG ESA 13454.90429155 UG | Combined with PRE-09361.128 (FID 90429155) PRE-09361.130 (FID 10472634)
Leidos | 2020 | 2020 | LUG - TBD340 | PRE-09361.105 | PRE-09361.105 | LUG ESA 13509.10501132 | LUG ESA 13509.10501132 | 13509 | STATE ROAD 574 | Lateral Hardening-Fuse-10501132 | Lateral Hardening-Fuse-10501132 | ESA | 0.10814 | 6 | 7 | 2020-08-01 | 2021-01-01 | 2021-03-01 | 4500271952 | N/A | N/A |  | CKT: 13509 - 10501132 | CKT: 13509 - 10501132 | 2290461 | LUG ESA 13509.10501132 OH | 2290465 | LUG ESA 13509.10501132 UG | 2290461 | LUG ESA 13509.10501132 OH | 2290465 | LUG ESA 13509.10501132 UG
Leidos | 2020 | 2020 | LUG - TBD341 | PRE-09361.106 | PRE-09361.106 | LUG ESA 13433.10466911 | LUG ESA 13433.10466911 | 13433 | TWELFTH AVENUE | Lateral Hardening-Fuse-10466911 | Lateral Hardening-Fuse-10466911 | ESA | 0.70568 | 47 | 159 | 2020-08-01 | 2021-01-01 | 2021-05-01 | 4500271952 | N/A | N/A |  | CKT: 13433 - 10466911 | CKT: 13433 - 10466911 | 2290485 | LUG ESA 13433.10466911 OH | 2290488 | LUG ESA 13433.10466911 UG | 2290485 | LUG ESA 13433.10466911 OH | 2290488 | LUG ESA 13433.10466911 UG
Leidos | 2020 | 2020 | LUG - TBD342 | PRE-09361.107 | PRE-09361.107 | LUG ESA 13230.92208546 | LUG ESA 13230.92208546 | 13230 | BRANDON | Lateral Hardening-Fuse-92208546 | Lateral Hardening-Fuse-92208546 | ESA | 0.17462 | 16 | 32 | 2020-08-01 | 2021-01-01 | 2021-03-01 | 4500271952 | N/A | N/A |  | CKT: 13230 - 92208546 | CKT: 13230 - 92208546 | 2290489 | LUG ESA 13230.92208546 OH | 2290490 | LUG ESA 13230.92208546 UG | 2290489 | LUG ESA 13230.92208546 OH | 2290490 | LUG ESA 13230.92208546 UG
Leidos | 2020 | 2020 | LUG - TBD343 | PRE-09361.108 | PRE-09361.108 | LUG ESA 13171.93104605 | LUG ESA 13171.93104605 | 13171 | MADISON | Lateral Hardening-Fuse-93104605 | Lateral Hardening-Fuse-93104605 | ESA | 0.36345 | 21 | 48 | 2020-08-01 | 2021-01-01 | 2021-04-01 | 4500271952 | N/A | N/A |  | CKT: 13171 - 93104605 | CKT: 13171 - 93104605 | 2290491 | LUG ESA 13171.93104605 OH | 2290493 | LUG ESA 13171.93104605 UG | 2290491 | LUG ESA 13171.93104605 OH | 2290493 | LUG ESA 13171.93104605 UG
Leidos | 2020 | 2020 | LUG - TBD344 | PRE-09361.109 | PRE-09361.109 | LUG ESA 13509.90504849 | LUG ESA 13509.90504849 | 13509 | STATE ROAD 574 | Lateral Hardening-Fuse-90504849 | Lateral Hardening-Fuse-90504849 | ESA | 0.95928 | 56 | 675 | 2020-08-01 | 2021-01-01 | 2021-07-01 | 4500271952 | N/A | N/A |  | CKT: 13509 - 90504849 | CKT: 13509 - 90504849 | 2290494 | LUG ESA 13509.90504849 OH | 2290496 | LUG ESA 13509.90504849 UG | 2290494 | LUG ESA 13509.90504849 OH | 2290496 | LUG ESA 13509.90504849 UG
Leidos | 2020 | 2020 | LUG - TBD345 | PRE-09361.110 | PRE-09361.110 | LUG ESA 13502.92573944 | LUG ESA 13502.92573944 | 13502 | STATE ROAD 574 | Lateral Hardening-Fuse-92573944 | Lateral Hardening-Fuse-92573944 | ESA | 0.61894 | 40 | 514 | 2020-08-01 | 2021-04-01 | 2021-08-01 | 4500271952 | N/A | N/A |  | CKT: 13502 - 92573944 | CKT: 13502 - 92573944 | 2290497 | LUG ESA 13502.92573944 OH | 2290498 | LUG ESA 13502.92573944 UG | 2290497 | LUG ESA 13502.92573944 OH | 2290498 | LUG ESA 13502.92573944 UG
Leidos | 2020 | 2020 | LUG - TBD346 | PRE-09361.111 | PRE-09361.111 | LUG ESA 13799.60395568 | LUG ESA 13799.60395568 | 13799 | SAINT CLOUD | Lateral Hardening-Fuse-60395568 | Lateral Hardening-Fuse-60395568 | ESA | 0.45739 | 45 | 260 | 2020-08-01 | 2021-04-01 | 2021-07-01 | 4500271952 | N/A | N/A |  | CKT: 13799 - 60395568 | CKT: 13799 - 60395568 | 2290520 | LUG ESA 13799.60395568 OH | 2290524 | LUG ESA 13799.60395568 UG | 2290520 | LUG ESA 13799.60395568 OH | 2290524 | LUG ESA 13799.60395568 UG
Leidos | 2020 | 2020 | LUG - TBD347 | PRE-09361.112 | PRE-09361.112 | LUG ESA 13226.10462583 | LUG ESA 13226.10462583 | 13226 | BRANDON | Lateral Hardening-Fuse-10462583 | Lateral Hardening-Fuse-10462583 | ESA | 0.12178 | 19 | 190 | 2020-08-01 | 2021-04-01 | 2021-06-01 | 4500271952 | N/A | N/A |  | CKT: 13226 - 10462583 | CKT: 13226 - 10462583 | 2290525 | LUG ESA 13226.10462583 OH | 2290526 | LUG ESA 13226.10462583 UG | 2290525 | LUG ESA 13226.10462583 OH | 2290526 | LUG ESA 13226.10462583 UG
Leidos | 2020 | 2020 | LUG - TBD348 | PRE-09361.113 | PRE-09361.113 | LUG ESA 14116.60140011 | LUG ESA 14116.60140011 | 14116 | LAKEWOOD | Lateral Hardening-Fuse-60140011 | Lateral Hardening-Fuse-60140011 | ESA | 0.32595 | 29 | 50 | 2020-09-01 | 2021-04-01 | 2021-06-01 | 4500271952 | N/A | N/A |  | CKT: 14116 - 60140011 | CKT: 14116 - 60140011 | 2290527 | LUG ESA 14116.60140011 OH | 2290529 | LUG ESA 14116.60140011 UG | 2290527 | LUG ESA 14116.60140011 OH | 2290529 | LUG ESA 14116.60140011 UG
Leidos | 2020 | 2020 | LUG - TBD349 | PRE-09361.114 | PRE-09361.114 | LUG ESA 13797.93188519 | LUG ESA 13797.93188519 | 13797 | SAINT CLOUD | Lateral Hardening-Fuse-93188519 | Lateral Hardening-Fuse-93188519 | ESA | 0.65966 | 50 | 152 | 2020-09-01 | 2021-04-01 | 2021-10-01 | 4500271952 | N/A | N/A |  | CKT: 13797 - 93188519 | CKT: 13797 - 93188519 | 2290531 | LUG ESA 13797.93188519 OH | 2290532 | LUG ESA 13797.93188519 UG | 2290531 | LUG ESA 13797.93188519 OH | 2290532 | LUG ESA 13797.93188519 UG
Leidos | 2020 | 2020 | LUG - TBD350 | PRE-09361.115 | PRE-09361.115 | LUG ESA 13226.92664597 | LUG ESA 13226.92664597 | 13226 | BRANDON | Lateral Hardening-Fuse-92664597 | Lateral Hardening-Fuse-92664597 | ESA | 0.30947 | 16 | 348 | 2020-09-01 | 2021-05-01 | 2021-07-01 | 4500271952 | N/A | N/A |  | CKT: 13226 - 92664597 | CKT: 13226 - 92664597 | 2290534 | LUG ESA 13226.92664597 OH | 2290535 | LUG ESA 13226.92664597 UG | 2290534 | LUG ESA 13226.92664597 OH | 2290535 | LUG ESA 13226.92664597 UG
Leidos | 2020 | 2020 | LUG - TBD351 | PRE-09361.116 | PRE-09361.116 | LUG ESA 13796.92728705 | LUG ESA 13796.92728705 | 13796 | SAINT CLOUD | Lateral Hardening-Fuse-92728705 | Lateral Hardening-Fuse-92728705 | ESA | 0.44981 | 34 | 318 | 2020-09-01 | 2021-05-01 | 2021-08-01 | 4500271952 | N/A | N/A |  | CKT: 13796 - 92728705 | CKT: 13796 - 92728705 | 2290536 | LUG ESA 13796.92728705 OH | 2290537 | LUG ESA 13796.92728705 UG | 2290536 | LUG ESA 13796.92728705 OH | 2290537 | LUG ESA 13796.92728705 UG
Leidos | 2020 | 2020 | LUG - TBD352 | PRE-09361.134 | PRE-09361.117 | DNU LUG ESA 13230.93279980 | LUG ESA 13230.92180224 | 13230 | BRANDON | DNU Lateral Hardening-Fuse-93279980 | Lateral Hardening-Fuse-92180224 | ESA | 0.15777 | 15 | 37 | 2020-10-01 | 2021-05-01 | 2021-07-01 | 4500271952 | N/A | N/A | LUG C061 | DNU CKT: 13230 - 93279980 | CKT: 13230 - 92180224 | 2290539 | DNU LUG ESA 13230.93279980 OH | 2290540 | DNU LUG ESA 13230.93279980 UG | 2277432 | LUG ESA 13230.92180224 OH | 2277435 | LUG ESA 13230.92180224 UG | Combined with PRE-09361.134 (FID 92180224); Incorrectly opened as FID 60258173)
Leidos | 2020 | 2020 | LUG - TBD353 | PRE-09361.18 | PRE-09361.118 | DNU LUG ESA 13171.90374558 | LUG ESA 13171.90598389 | 13171 | MADISON | DNU Lateral Hardening-Fuse-90374558 | Lateral Hardening-Fuse-90598389 | ESA | 0.58144 | 39 | 325 | 2020-10-01 | 2021-05-01 | 2021-08-01 | 4500271952 | N/A | N/A | LUG C006 | DNU CKT: 13171 - 90374558 | CKT: 13171 - 90598389 | 2290542 | DNU LUG ESA 13171.90374558 OH | 2290543 | DNU LUG ESA 13171.90374558 UG | 2277383 | LUG ESA 13171.90598389 OH | 2277385 | LUG ESA 13171.90598389 UG | Combined with PRE-09361.18 (FID 90598389) & LUG-TBD376 (FID 10455414)
Leidos | 2020 | 2020 | LUG - TBD354 | PRE-09361.119 | PRE-09361.119 | LUG ESA 13796.92884623 | LUG ESA 13796.92884623 | 13796 | SAINT CLOUD | Lateral Hardening-Fuse-92884623 | Lateral Hardening-Fuse-92884623 | ESA | 1.2991 | 54 | 52 | 2020-10-01 | 2021-06-01 | 2021-12-01 | 4500271952 | N/A | N/A | LUG C007 | CKT: 13796 - 92884623 | CKT: 13796 - 92884623 | 2277391 | LUG ESA 13796.92884623 OH | 2277392 | LUG ESA 13796.92884623 UG | 2277391 | LUG ESA 13796.92884623 OH | 2277392 | LUG ESA 13796.92884623 UG | Combined with LUG-TBD440 (FID 92884644)
Leidos | 2020 | 2020 | LUG - TBD355 | PRE-09361.120 | PRE-09361.120 | LUG ESA 13502.92577310 | LUG ESA 13502.92577310 | 13502 | STATE ROAD 574 | Lateral Hardening-Fuse-92577310 | Lateral Hardening-Fuse-92577310 | ESA | 0.16458 | 12 | 268 | 2020-11-01 | 2021-05-01 | 2021-07-01 | 4500271952 | N/A | N/A |  | CKT: 13502 - 92577310 | CKT: 13502 - 92577310 | 2277393 | LUG ESA 13502.92577310 OH | 2277394 | LUG ESA 13502.92577310 UG | 2277393 | LUG ESA 13502.92577310 OH | 2277394 | LUG ESA 13502.92577310 UG
Leidos | 2020 | 2020 | LUG - TBD356 | PRE-09361.121 | PRE-09361.121 | LUG ESA 13225.60139973 | LUG ESA 13225.60139973 | 13225 | BRANDON | Lateral Hardening-Fuse-60139973 | Lateral Hardening-Fuse-60139973 | ESA | 0.80549 | 54 | 41 | 2020-10-01 | 2021-05-01 | 2021-12-01 | 4500271952 | N/A | N/A | LUG C024 | CKT: 13225 - 60139973 | CKT: 13225 - 60139973 | 2277396 | LUG ESA 13225.60139973 OH | 2277398 | LUG ESA 13225.60139973 UG | 2277396 | LUG ESA 13225.60139973 OH | 2277398 | LUG ESA 13225.60139973 UG | Combined with LUG-TBD383 (FID 92750192)
Leidos | 2020 | 2020 | LUG - TBD357 | PRE-09361.122 | PRE-09361.122 | LUG ESA 13796.10842823 | LUG ESA 13796.10842823 | 13796 | SAINT CLOUD | Lateral Hardening-Fuse-10842823 | Lateral Hardening-Fuse-10842823 | ESA | 0.44811 | 34 | 21 | 2020-10-01 | 2021-09-01 | 2021-12-01 | 4500271952 | N/A | N/A |  | CKT: 13796 - 10842823 | CKT: 13796 - 10842823 | 2277399 | LUG ESA 13796.10842823 OH | 2277400 | LUG ESA 13796.10842823 UG | 2277399 | LUG ESA 13796.10842823 OH | 2277400 | LUG ESA 13796.10842823 UG
Leidos | 2020 | 2020 | LUG - TBD358 | PRE-09361.123 | PRE-09361.123 | LUG ESA 13226.92670950 | LUG ESA 13226.92670950 | 13226 | BRANDON | Lateral Hardening-Fuse-92670950 | Lateral Hardening-Fuse-92670950 | ESA | 0.2017 | 23 | 37 | 2020-11-01 | 2021-07-01 | 2021-09-01 | 4500271952 | N/A | N/A |  | CKT: 13226 - 92670950 | CKT: 13226 - 92670950 | 2277406 | LUG ESA 13226.92670950 OH | 2277407 | LUG ESA 13226.92670950 UG | 2277406 | LUG ESA 13226.92670950 OH | 2277407 | LUG ESA 13226.92670950 UG
Leidos | 2020 | 2020 | LUG - TBD359 | PRE-09361.124 | PRE-09361.124 | LUG ESA 13226.92665539 | LUG ESA 13226.92665539 | 13226 | BRANDON | Lateral Hardening-Fuse-92665539 | Lateral Hardening-Fuse-92665539 | ESA | 0.087879 | 5 | 13 | 2020-12-01 | 2021-09-01 | 2021-10-01 | 4500271952 | N/A | N/A |  | CKT: 13226 - 92665539 | CKT: 13226 - 92665539 | 2277408 | LUG ESA 13226.92665539 OH | 2277409 | LUG ESA 13226.92665539 UG | 2277408 | LUG ESA 13226.92665539 OH | 2277409 | LUG ESA 13226.92665539 UG
Leidos | 2020 | 2020 | LUG - TBD360 | PRE-09361.125 | PRE-09361.125 | LUG ESA 13883.91179506 | LUG ESA 13883.91179506 | 13883 | PROVIDENCE ROAD | Lateral Hardening-Fuse-91179506 | Lateral Hardening-Fuse-91179506 | ESA | 0.075 | 6 | 151 | 2020-12-01 | 2021-09-01 | 2021-10-01 | 4500271952 | N/A | N/A |  | CKT: 13883 - 91179506 | CKT: 13883 - 91179506 | 2277410 | LUG ESA 13883.91179506 OH | 2277411 | LUG ESA 13883.91179506 UG | 2277410 | LUG ESA 13883.91179506 OH | 2277411 | LUG ESA 13883.91179506 UG
Leidos | 2020 | 2020 | LUG - TBD361 | PRE-09361.126 | PRE-09361.126 | LUG ESA 13509.91772133 | LUG ESA 13509.91772133 | 13509 | STATE ROAD 574 | Lateral Hardening-Fuse-91772133 | Lateral Hardening-Fuse-91772133 | ESA | 0.051705 | 8 | 22 | 2020-12-01 | 2021-09-01 | 2021-10-01 | 4500271952 | N/A | N/A |  | CKT: 13509 - 91772133 | CKT: 13509 - 91772133 | 2277412 | LUG ESA 13509.91772133 OH | 2277413 | LUG ESA 13509.91772133 UG | 2277412 | LUG ESA 13509.91772133 OH | 2277413 | LUG ESA 13509.91772133 UG
Leidos | 2020 | 2020 | LUG - TBD362 | PRE-09361.127 | PRE-09361.127 | LUG ESA 13509.10501150 | LUG ESA 13509.10501150 | 13509 | STATE ROAD 574 | Lateral Hardening-Fuse-10501150 | Lateral Hardening-Fuse-10501150 | ESA | 0.50871 | 33 | 37 | 2020-10-01 | 2021-08-01 | 2021-11-01 | 4500271952 | N/A | N/A | LUG C023 | CKT: 13509 - 10501150 | CKT: 13509 - 10501150 | 2277415 | LUG ESA 13509.10501150 OH | 2277416 | LUG ESA 13509.10501150 UG | 2277415 | LUG ESA 13509.10501150 OH | 2277416 | LUG ESA 13509.10501150 UG | Combined with LUG-TBD446 (FID 10501133)
Leidos | 2020 | 2020 | LUG - TBD363 | PRE-09361.128 | PRE-09361.128 | LUG ESA 13454.90429155 | LUG ESA 13454.90429155 | 13454 | LAKEWOOD | Lateral Hardening-Fuse-90429155 | Lateral Hardening-Fuse-90429155 | ESA | 0.63826 | 34 | 148 | 2020-10-01 | 2021-08-01 | 2021-12-01 | 4500271952 | N/A | N/A | LUG C005 | CKT: 13454 - 90429155 | CKT: 13454 - 90429155 | 2277417 | LUG ESA 13454.90429155 OH | 2277418 | LUG ESA 13454.90429155 UG | 2277417 | LUG ESA 13454.90429155 OH | 2277418 | LUG ESA 13454.90429155 UG | Combined with PRE-09361.104 (FID 60140423) & PRE-09361.130 (FID 10472634)
Leidos | 2020 | 2020 | LUG - TBD364 | PRE-09361.129 | PRE-09361.129 | LUG ESA 13454.90397369 | LUG ESA 13454.90397369 | 13454 | LAKEWOOD | Lateral Hardening-Fuse-90397369 | Lateral Hardening-Fuse-90397369 | ESA | 0.49053 | 26 | 19 | 2020-11-01 | 2021-08-01 | 2021-12-01 | 4500271952 | N/A | N/A |  | CKT: 13454 - 90397369 | CKT: 13454 - 90397369 | 2277419 | LUG ESA 13454.90397369 OH | 2277420 | LUG ESA 13454.90397369 UG | 2277419 | LUG ESA 13454.90397369 OH | 2277420 | LUG ESA 13454.90397369 UG
Leidos | 2020 | 2020 | LUG - TBD365 | PRE-09361.128 | PRE-09361.130 | DNU LUG ESA 13454.10472634 | LUG ESA 13454.90429155 | 13454 | LAKEWOOD | DNU Lateral Hardening-Fuse-10472634 | Lateral Hardening-Fuse-90429155 | ESA | 0.38409 | 27 | 35 | 2020-11-01 | 2021-10-01 | 2021-12-01 | 4500271952 | N/A | N/A | LUG C005 | DNU CKT: 13454 - 10472634 | CKT: 13454 - 90429155 | 2277422 | DNU LUG ESA 13454.10472634 OH | 2277423 | DNU LUG ESA 13454.10472634 UG | 2277417 | LUG ESA 13454.90429155 OH | 2277418 | LUG ESA 13454.90429155 UG | Combined with PRE-09361.104 (FID 60140423) & PRE-09361.128 (FID 90429155)
Leidos | 2020 | 2020 | LUG - TBD366 | PRE-09361.131 | PRE-09361.131 | LUG ESA 13433.93369551 | LUG ESA 13433.93369551 | 13433 | TWELFTH AVENUE | Lateral Hardening-Fuse-93369551 | Lateral Hardening-Fuse-93369551 | ESA | 0.60587 | 37 | 5 | 2020-11-01 | 2021-08-01 | 2021-12-01 | 4500271952 | N/A | N/A |  | CKT: 13433 - 93369551 | CKT: 13433 - 93369551 | 2277424 | LUG ESA 13433.93369551 OH | 2277425 | LUG ESA 13433.93369551 UG | 2277424 | LUG ESA 13433.93369551 OH | 2277425 | LUG ESA 13433.93369551 UG
Leidos | 2020 | 2020 | LUG - TBD367 | PRE-09361.132 | PRE-09361.132 | LUG ESA 13174.92555763 | LUG ESA 13174.92555763 | 13174 | MADISON | Lateral Hardening-Fuse-92555763 | Lateral Hardening-Fuse-92555763 | ESA | 0.026894 | 3 | 138 | 2020-10-01 | 2021-08-01 | 2021-09-01 | 4500271952 | N/A | N/A |  | CKT: 13174 - 92555763 | CKT: 13174 - 92555763 | 2277426 | LUG ESA 13174.92555763 OH | 2277427 | LUG ESA 13174.92555763 UG | 2277426 | LUG ESA 13174.92555763 OH | 2277427 | LUG ESA 13174.92555763 UG
Leidos | 2020 | 2020 | LUG - TBD368 | PRE-09361.133 | PRE-09361.133 | LUG ESA 13883.92008787 | LUG ESA 13883.92008787 | 13883 | PROVIDENCE ROAD | Lateral Hardening-Fuse-92008787 | Lateral Hardening-Fuse-92008787 | ESA | 0.058333 | 8 | 3 | 2020-10-01 | 2021-11-01 | 2021-12-01 | 4500271952 | N/A | N/A |  | CKT: 13883 - 92008787 | CKT: 13883 - 92008787 | 2277428 | LUG ESA 13883.92008787 OH | 2277429 | LUG ESA 13883.92008787 UG | 2277428 | LUG ESA 13883.92008787 OH | 2277429 | LUG ESA 13883.92008787 UG
Leidos | 2020 | 2020 | LUG - TBD369 | PRE-09361.134 | PRE-09361.134 | LUG ESA 13230.92180224 | LUG ESA 13230.92180224 | 13230 | BRANDON | Lateral Hardening-Fuse-92180224 | Lateral Hardening-Fuse-92180224 | ESA | 0.27992 | 21 | 58 | 2020-11-01 | 2021-09-01 | 2021-12-01 | 4500271952 | N/A | N/A | LUG C061 | CKT: 13230 - 92180224 | CKT: 13230 - 92180224 | 2277432 | LUG ESA 13230.92180224 OH | 2277435 | LUG ESA 13230.92180224 UG | 2277432 | LUG ESA 13230.92180224 OH | 2277435 | LUG ESA 13230.92180224 UG | Combined with PRE-09361.117 (FID 93279980)
Leidos | 2021 | 2021 | LUG - TBD370 | PRE-09361.406 | PRE-09361.406 | LUG ESA 13230.10471377 | LUG ESA 13230.10471377 | 13230 | BRANDON | Lateral Hardening-Fuse-10471377 | Lateral Hardening-Fuse-10471377 | ESA | 0.47973 | 31 | 54 | 2021-01-01 | 2021-10-01 | 2021-12-01 | N/A | 4500283885 | N/A |  | CKT: 13230 - 10471377 | CKT: 13230 - 10471377 | 2309472 | LUG ESA 13230.10471377 OH | 2309473 | LUG ESA 13230.10471377 UG | 2309472 | LUG ESA 13230.10471377 OH | 2309473 | LUG ESA 13230.10471377 UG
Leidos | 2021 | 2021 | LUG - TBD371 | PRE-09361.407 | PRE-09361.407 | LUG ESA 13509.60346595 | LUG ESA 13509.60346595 | 13509 | STATE ROAD 574 | Lateral Hardening-Fuse-60346595 | Lateral Hardening-Fuse-60346595 | ESA | 0.14754 | 10 | 14 | 2021-01-01 | 2021-10-01 | 2021-12-01 | N/A | 4500283885 | N/A |  | CKT: 13509 - 60346595 | CKT: 13509 - 60346595 | 2309657 | LUG ESA 13509.60346595 OH | 2309658 | LUG ESA 13509.60346595 UG | 2309657 | LUG ESA 13509.60346595 OH | 2309658 | LUG ESA 13509.60346595 UG
Leidos | 2021 | 2021 | LUG - TBD372 | PRE-09361.408 | PRE-09361.408 | LUG ESA 13502.10497396 | LUG ESA 13502.10497396 | 13502 | STATE ROAD 574 | Lateral Hardening-Fuse-10497396 | Lateral Hardening-Fuse-10497396 | ESA | 0.29545 | 22 | 70 | 2021-01-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13502 - 10497396 | CKT: 13502 - 10497396 | 2309691 | LUG ESA 13502.10497396 OH | 2309695 | LUG ESA 13502.10497396 UG | 2309691 | LUG ESA 13502.10497396 OH | 2309695 | LUG ESA 13502.10497396 UG
Leidos | 2021 | 2021 | LUG - TBD373 | PRE-09361.17 | PRE-09361.17 | DNU LUG ESA 13174.93310101 | LUG ESA 13174.10913196 | 13174 | MADISON | DNU Lateral Hardening-Fuse-93310101 | Lateral Hardening-Fuse-10913196 | ESA | 0.50587 | 29 | 2 | 2021-01-01 | 2022 | 2022 | 4500271952 | N/A | N/A | LUG C002 | N/A | CKT: 13174 - 10913196 | N/A | N/A | N/A | N/A | 2277381 | LUG ESA 13174.10913196 OH | 2277382 | LUG ESA 13174.10913196 UG | Combined with PRE-09361.17 (FID 10913196)
Leidos | 2021 | 2021 | LUG - TBD374 | PRE-09361.410 | PRE-09361.410 | LUG ESA 13796.92356181 | LUG ESA 13796.92356181 | 13796 | SAINT CLOUD | Lateral Hardening-Fuse-92356181 | Lateral Hardening-Fuse-92356181 | ESA | 0.26477 | 14 | 6 | 2021-01-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13796 - 92356181 | CKT: 13796 - 92356181 | 2309696 | LUG ESA 13796.92356181 OH | 2309700 | LUG ESA 13796.92356181 UG | 2309696 | LUG ESA 13796.92356181 OH | 2309700 | LUG ESA 13796.92356181 UG
Leidos | 2021 | 2021 | LUG - TBD375 | PRE-09361.411 | PRE-09361.411 | LUG ESA 13509.92890860 | LUG ESA 13509.92890860 | 13509 | STATE ROAD 574 | Lateral Hardening-Fuse-92890860 | Lateral Hardening-Fuse-92890860 | ESA | 0.33485 | 30 | 7 | 2021-01-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13509 - 92890860 | CKT: 13509 - 92890860 | 2309701 | LUG ESA 13509.92890860 OH | 2309702 | LUG ESA 13509.92890860 UG | 2309701 | LUG ESA 13509.92890860 OH | 2309702 | LUG ESA 13509.92890860 UG
Leidos | 2021 | 2021 | LUG - TBD376 | PRE-09361.18 | PRE-09361.18 | DNU LUG ESA 13171.10455414 | LUG ESA 13171.90598389 | 13171 | MADISON | DNU Lateral Hardening-Fuse-10455414 | Lateral Hardening-Fuse-90598389 | ESA | 0.59356 | 40 | 36 | 2021-01-01 | 2022 | 2022 | 4500271952 | N/A | N/A | LUG C006 | N/A | CKT: 13171 - 90598389 | N/A | N/A | N/A | N/A | 2277383 | LUG ESA 13171.90598389 OH | 2277385 | LUG ESA 13171.90598389 UG | Combined with PRE-09361.18 (FID 90598389) & PRE-09361.118 (FID 90374558)
Leidos | 2021 | 2021 | LUG - TBD377 | PRE-09361.412 | PRE-09361.412 | LUG ESA 13230.92496254 | LUG ESA 13230.92496254 | 13230 | BRANDON | Lateral Hardening-Fuse-92496254 | Lateral Hardening-Fuse-92496254 | ESA | 0.28977 | 23 | 12 | 2021-01-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13230 - 92496254 | CKT: 13230 - 92496254 | 2309703 | LUG ESA 13230.92496254 OH | 2309705 | LUG ESA 13230.92496254 UG | 2309703 | LUG ESA 13230.92496254 OH | 2309705 | LUG ESA 13230.92496254 UG
Leidos | 2021 | 2021 | LUG - TBD378 | PRE-09361.413 | PRE-09361.413 | LUG ESA 13509.10501141 | LUG ESA 13509.10501141 | 13509 | STATE ROAD 574 | Lateral Hardening-Fuse-10501141 | Lateral Hardening-Fuse-10501141 | ESA | 0.16364 | 15 | 13 | 2021-01-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13509 - 10501141 | CKT: 13509 - 10501141 | 2309706 | LUG ESA 13509.10501141 OH | 2309707 | LUG ESA 13509.10501141 UG | 2309706 | LUG ESA 13509.10501141 OH | 2309707 | LUG ESA 13509.10501141 UG
Leidos | 2021 | 2021 | LUG - TBD379 | PRE-09361.414 | PRE-09361.414 | LUG ESA 13454.91522987 | LUG ESA 13454.91522987 | 13454 | LAKEWOOD | Lateral Hardening-Fuse-91522987 | Lateral Hardening-Fuse-91522987 | ESA | 0.043371 | 9 | 47 | 2021-01-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13454 - 91522987 | CKT: 13454 - 91522987 | 2309709 | LUG ESA 13454.91522987 OH | 2309710 | LUG ESA 13454.91522987 UG | 2309709 | LUG ESA 13454.91522987 OH | 2309710 | LUG ESA 13454.91522987 UG
Leidos | 2021 | 2021 | LUG - TBD380 | PRE-09361.415 | PRE-09361.415 | LUG ESA 13509.10501110 | LUG ESA 13509.10501110 | 13509 | STATE ROAD 574 | Lateral Hardening-Fuse-10501110 | Lateral Hardening-Fuse-10501110 | ESA | 0.089962 | 6 | 3 | 2021-01-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13509 - 10501110 | CKT: 13509 - 10501110 | 2309713 | LUG ESA 13509.10501110 OH | 2309715 | LUG ESA 13509.10501110 UG | 2309713 | LUG ESA 13509.10501110 OH | 2309715 | LUG ESA 13509.10501110 UG
Leidos | 2021 | 2021 | LUG - TBD381 | PRE-09361.20 | PRE-09361.20 | DNU LUG ESA 13231.10868120 | LUG ESA 13231.10868138 | 13231 | BRANDON | DNU Lateral Hardening-Fuse-10868120 | Lateral Hardening-Fuse-10868138 | ESA | 0.41648 | 29 | 35 | 2021-01-01 | 2022 | 2022 | 4500271952 | N/A | N/A | LUG C004 | N/A | CKT: 13231 - 10868138 | N/A | N/A | N/A | N/A | 2290199 | LUG ESA 13231.10868138 OH | 2290200 | LUG ESA 13231.10868138 UG | Combined with PRE-09361.20 (FID 10868138)
Leidos | 2021 | 2021 | LUG - TBD382 | PRE-09361.13 | PRE-09361.13 | DNU LUG ESA 13174.10913197 | LUG ESA 13174.60451701 | 13174 | MADISON | DNU Lateral Hardening-Fuse-10913197 | Lateral Hardening-Fuse-60451701 | ESA | 0.077273 | 2 | 301 | 2021-01-01 | 2022 | 2022 | 4500271952 | N/A | N/A | LUG C003 | N/A | CKT: 13174 - 60451701 | N/A | N/A | N/A | N/A | 2277343 | LUG ESA 13174.60451701 OH | 2277348 | LUG ESA 13174.60451701 UG | Combined with PRE-09361.13 (FID 60451701)
Leidos | 2021 | 2021 | LUG - TBD383 | PRE-09361.121 | PRE-09361.121 | DNU LUG ESA 13225.92750192 | LUG ESA 13225.60139973 | 13225 | BRANDON | DNU Lateral Hardening-Fuse-92750192 | Lateral Hardening-Fuse-60139973 | ESA | 0.09375 | 9 | 6 | 2021-01-01 | 2022 | 2022 | 4500271952 | N/A | N/A | LUG C024 | N/A | CKT: 13225 - 60139973 | N/A | N/A | N/A | N/A | 2277396 | LUG ESA 13225.60139973 OH | 2277398 | LUG ESA 13225.60139973 UG | Combined with PRE-09361.121 (FID 60139973)
Leidos | 2021 | 2021 | LUG - TBD384 | PRE-09361.416 | PRE-09361.416 | LUG ESA 13797.93185703 | LUG ESA 13797.93185703 | 13797 | SAINT CLOUD | Lateral Hardening-Fuse-93185703 | Lateral Hardening-Fuse-93185703 | ESA | 0.044697 | 5 | 2 | 2021-01-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13797 - 93185703 | CKT: 13797 - 93185703 | 2309716 | LUG ESA 13797.93185703 OH | 2309718 | LUG ESA 13797.93185703 UG | 2309716 | LUG ESA 13797.93185703 OH | 2309718 | LUG ESA 13797.93185703 UG
Leidos | 2021 | 2021 | LUG - TBD385 | PRE-09361.417 | PRE-09361.417 | LUG ESA 14116.91073265 | LUG ESA 14116.91073265 | 14116 | LAKEWOOD | Lateral Hardening-Fuse-91073265 | Lateral Hardening-Fuse-91073265 | ESA | 0.092614 | 7 | 10 | 2021-01-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 14116 - 91073265 | CKT: 14116 - 91073265 | 2309719 | LUG ESA 14116.91073265 OH | 2309720 | LUG ESA 14116.91073265 UG | 2309719 | LUG ESA 14116.91073265 OH | 2309720 | LUG ESA 14116.91073265 UG
Leidos | 2021 | 2021 | LUG - TBD386 | PRE-09361.418 | PRE-09361.418 | LUG SHA 13900.10717269 | LUG SHA 13900.10717269 | 13900 | FIRST STREET | Lateral Hardening-Fuse-10717269 | Lateral Hardening-Fuse-10717269 | SHA | 0.41818 | 21 | 136 | 2021-01-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13900 - 10717269 | CKT: 13900 - 10717269 | 2309723 | LUG SHA 13900.10717269 OH | 2309724 | LUG SHA 13900.10717269 UG | 2309723 | LUG SHA 13900.10717269 OH | 2309724 | LUG SHA 13900.10717269 UG
Leidos | 2021 | 2021 | LUG - TBD387 | PRE-09361.419 | PRE-09361.419 | LUG SHA 13652.92748361 | LUG SHA 13652.92748361 | 13652 | RHODINE ROAD | Lateral Hardening-Fuse-92748361 | Lateral Hardening-Fuse-92748361 | SHA | 0.47689 | 23 | 23 | 2021-01-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13652 - 92748361 | CKT: 13652 - 92748361 | 2309725 | LUG SHA 13652.92748361 OH | 2309728 | LUG SHA 13652.92748361 UG | 2309725 | LUG SHA 13652.92748361 OH | 2309728 | LUG SHA 13652.92748361 UG
Leidos | 2021 | 2021 | LUG - TBD388 | PRE-09361.420 | PRE-09361.420 | LUG SHA 13001.93346473 | LUG SHA 13001.93346473 | 13001 | RUSKIN | Lateral Hardening-Fuse-93346473 | Lateral Hardening-Fuse-93346473 | SHA | 0.80947 | 48 | 483 | 2021-02-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C032 | CKT: 13001 - 93346473 | CKT: 13001 - 93346473 | 2309729 | LUG SHA 13001.93346473 OH | 2309731 | LUG SHA 13001.93346473 UG | 2309729 | LUG SHA 13001.93346473 OH | 2309731 | LUG SHA 13001.93346473 UG | Combined with LUG-TBD402 (FID 90251758)
Leidos | 2021 | 2021 | LUG - TBD389 | PRE-09361.421 | PRE-09361.421 | LUG SHA 14022.90591555 | LUG SHA 14022.90591555 | 14022 | RIVERVIEW | Lateral Hardening-Fuse-90591555 | Lateral Hardening-Fuse-90591555 | SHA | 0.75833 | 49 | 485 | 2021-02-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 14022 - 90591555 | CKT: 14022 - 90591555 | 2309733 | LUG SHA 14022.90591555 OH | 2309734 | LUG SHA 14022.90591555 UG | 2309733 | LUG SHA 14022.90591555 OH | 2309734 | LUG SHA 14022.90591555 UG
Leidos | 2021 | 2021 | LUG - TBD390 | PRE-09361.422 | PRE-09361.422 | LUG SHA 13001.60179144 | LUG SHA 13001.60179144 | 13001 | RUSKIN | Lateral Hardening-Fuse-60179144 | Lateral Hardening-Fuse-60179144 | SHA | 0.66742 | 42 | 162 | 2021-02-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C033 | CKT: 13001 - 60179144 | CKT: 13001 - 60179144 | 2309735 | LUG SHA 13001.60179144 OH | 2309737 | LUG SHA 13001.60179144 UG | 2309735 | LUG SHA 13001.60179144 OH | 2309737 | LUG SHA 13001.60179144 UG | Combined with LUG-TBD391 (FID 10663246)
Leidos | 2021 | 2021 | LUG - TBD391 | PRE-09361.422 | PRE-09361.422 | DNU LUG SHA 13001.10663246 | LUG SHA 13001.60179144 | 13001 | RUSKIN | DNU Lateral Hardening-Fuse-10663246 | Lateral Hardening-Fuse-60179144 | SHA | 0.50189 | 27 | 244 | 2021-03-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C033 | N/A | CKT: 13001 - 60179144 | N/A | N/A | N/A | N/A | 2309735 | LUG SHA 13001.60179144 OH | 2309737 | LUG SHA 13001.60179144 UG | Combined with LUG-TBD390 (FID 60179144)
Leidos | 2021 | 2021 | LUG - TBD392 | PRE-09361.423 | PRE-09361.423 | LUG SHA 13645.91519309 | LUG SHA 13645.91519309 | 13645 | RHODINE ROAD | Lateral Hardening-Fuse-91519309 | Lateral Hardening-Fuse-91519309 | SHA | 0.49508 | 22 | 36 | 2021-03-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13645 - 91519309 | CKT: 13645 - 91519309 | 2309783 | LUG SHA 13645.91519309 OH | 2309786 | LUG SHA 13645.91519309 UG | 2309783 | LUG SHA 13645.91519309 OH | 2309786 | LUG SHA 13645.91519309 UG
Leidos | 2021 | 2021 | LUG - TBD393 | PRE-09361.424 | PRE-09361.424 | LUG SHA 13780.10723993 | LUG SHA 13780.10723993 | 13780 | MILLER MAC | Lateral Hardening-Fuse-10723993 | Lateral Hardening-Fuse-10723993 | SHA | 0.27008 | 17 | 97 | 2021-03-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13780 - 10723993 | CKT: 13780 - 10723993 | 2309787 | LUG SHA 13780.10723993 OH | 2309788 | LUG SHA 13780.10723993 UG | 2309787 | LUG SHA 13780.10723993 OH | 2309788 | LUG SHA 13780.10723993 UG
Leidos | 2021 | 2021 | LUG - TBD394 | PRE-09361.425 | PRE-09361.425 | LUG SHA 13001.92048269 | LUG SHA 13001.92048269 | 13001 | RUSKIN | Lateral Hardening-Fuse-92048269 | Lateral Hardening-Fuse-92048269 | SHA | 0.23845 | 17 | 137 | 2021-03-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13001 - 92048269 | CKT: 13001 - 92048269 | 2309791 | LUG SHA 13001.92048269 OH | 2309792 | LUG SHA 13001.92048269 UG | 2309791 | LUG SHA 13001.92048269 OH | 2309792 | LUG SHA 13001.92048269 UG
Leidos | 2021 | 2021 | LUG - TBD395 | PRE-09361.426 | PRE-09361.426 | LUG SHA 13001.60179191 | LUG SHA 13001.60179191 | 13001 | RUSKIN | Lateral Hardening-Fuse-60179191 | Lateral Hardening-Fuse-60179191 | SHA | 0.36439 | 30 | 139 | 2021-03-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13001 - 60179191 | CKT: 13001 - 60179191 | 2309794 | LUG SHA 13001.60179191 OH | 2309796 | LUG SHA 13001.60179191 UG | 2309794 | LUG SHA 13001.60179191 OH | 2309796 | LUG SHA 13001.60179191 UG
Leidos | 2021 | 2021 | LUG - TBD396 | PRE-09361.427 | PRE-09361.427 | LUG SHA 13001.10663240 | LUG SHA 13001.10663240 | 13001 | RUSKIN | Lateral Hardening-Fuse-10663240 | Lateral Hardening-Fuse-10663240 | SHA | 0.45189 | 26 | 16 | 2021-03-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13001 - 10663240 | CKT: 13001 - 10663240 | 2309797 | LUG SHA 13001.10663240 OH | 2309798 | LUG SHA 13001.10663240 UG | 2309797 | LUG SHA 13001.10663240 OH | 2309798 | LUG SHA 13001.10663240 UG
Leidos | 2021 | 2021 | LUG - TBD397 | PRE-09361.428 | PRE-09361.428 | LUG SHA 13900.92336596 | LUG SHA 13900.92336596 | 13900 | FIRST STREET | Lateral Hardening-Fuse-92336596 | Lateral Hardening-Fuse-92336596 | SHA | 0.45928 | 21 | 3 | 2021-03-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13900 - 92336596 | CKT: 13900 - 92336596 | 2309852 | LUG SHA 13900.92336596 OH | 2309853 | LUG SHA 13900.92336596 UG | 2309852 | LUG SHA 13900.92336596 OH | 2309853 | LUG SHA 13900.92336596 UG
Leidos | 2021 | 2021 | LUG - TBD398 | PRE-09361.429 | PRE-09361.429 | LUG SHA 13645.92207754 | LUG SHA 13645.92207754 | 13645 | RHODINE ROAD | Lateral Hardening-Fuse-92207754 | Lateral Hardening-Fuse-92207754 | SHA | 0.73258 | 28 | 7 | 2021-03-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13645 - 92207754 | CKT: 13645 - 92207754 | 2309854 | LUG SHA 13645.92207754 OH | 2309855 | LUG SHA 13645.92207754 UG | 2309854 | LUG SHA 13645.92207754 OH | 2309855 | LUG SHA 13645.92207754 UG
Leidos | 2021 | 2021 | LUG - TBD399 | PRE-09361.430 | PRE-09361.430 | LUG SHA 13900.91863298 | LUG SHA 13900.91863298 | 13900 | FIRST STREET | Lateral Hardening-Fuse-91863298 | Lateral Hardening-Fuse-91863298 | SHA | 0.26648 | 18 | 169 | 2021-03-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13900 - 91863298 | CKT: 13900 - 91863298 | 2309856 | LUG SHA 13900.91863298 OH | 2309857 | LUG SHA 13900.91863298 UG | 2309856 | LUG SHA 13900.91863298 OH | 2309857 | LUG SHA 13900.91863298 UG
Leidos | 2021 | 2021 | LUG - TBD400 | PRE-09361.431 | PRE-09361.431 | LUG SHA 13001.10663269 | LUG SHA 13001.10663269 | 13001 | RUSKIN | Lateral Hardening-Fuse-10663269 | Lateral Hardening-Fuse-10663269 | SHA | 0.11818 | 8 | 16 | 2021-03-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13001 - 10663269 | CKT: 13001 - 10663269 | 2309858 | LUG SHA 13001.10663269 OH | 2309860 | LUG SHA 13001.10663269 UG | 2309858 | LUG SHA 13001.10663269 OH | 2309860 | LUG SHA 13001.10663269 UG
Leidos | 2021 | 2021 | LUG - TBD401 | PRE-09361.432 | PRE-09361.432 | LUG SHA 13001.10663262 | LUG SHA 13001.10663262 | 13001 | RUSKIN | Lateral Hardening-Fuse-10663262 | Lateral Hardening-Fuse-10663262 | SHA | 0.092045 | 8 | 63 | 2021-03-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13001 - 10663262 | CKT: 13001 - 10663262 | 2309861 | LUG SHA 13001.10663262 OH | 2309862 | LUG SHA 13001.10663262 UG | 2309861 | LUG SHA 13001.10663262 OH | 2309862 | LUG SHA 13001.10663262 UG
Leidos | 2021 | 2021 | LUG - TBD402 | PRE-09361.420 | PRE-09361.420 | DNU LUG SHA 13001.90251758 | LUG SHA 13001.93346473 | 13001 | RUSKIN | DNU Lateral Hardening-Fuse-90251758 | Lateral Hardening-Fuse-93346473 | SHA | 0.58939 | 38 | 50 | 2021-04-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C032 | N/A | CKT: 13001 - 93346473 | N/A | N/A | N/A | N/A | 2309729 | LUG SHA 13001.93346473 OH | 2309731 | LUG SHA 13001.93346473 UG | Combined with LUG-TBD388 (FID 93346473)
Leidos | 2021 | 2021 | LUG - TBD403 | PRE-09361.433 | PRE-09361.433 | LUG ESA 13127.90334707 | LUG ESA 13127.90334707 | 13127 | SOUTH SEFFNER | Lateral Hardening-Fuse-90334707 | Lateral Hardening-Fuse-90334707 | ESA | 0.36061 | 24 | 150 | 2021-05-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13127 - 90334707 | CKT: 13127 - 90334707 | 2309863 | LUG ESA 13127.90334707 OH | 2309864 | LUG ESA 13127.90334707 UG | 2309863 | LUG ESA 13127.90334707 OH | 2309864 | LUG ESA 13127.90334707 UG
Leidos | 2021 | 2021 | LUG - TBD404 | PRE-09361.436 | PRE-09361.436 | DNU LUG ESA 13229.10457704 | LUG ESA 13229.92525393 | 13229 | BRANDON | DNU Lateral Hardening-Fuse-10457704 | Lateral Hardening-Fuse-92525393 | ESA | 0.068939 | 8 | 152 | 2021-05-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C025 | N/A | CKT: 13229 - 92525393 | N/A | N/A | N/A | N/A | 2309870 | LUG ESA 13229.92525393 OH | 2309871 | LUG ESA 13229.92525393 UG | Combined with LUG-TBD407 (FID 92525393)
Leidos | 2021 | 2021 | LUG - TBD405 | PRE-09361.434 | PRE-09361.434 | LUG ESA 13878.10105723 | LUG ESA 13878.10105723 | 13878 | PROVIDENCE ROAD | Lateral Hardening-Fuse-10105723 | Lateral Hardening-Fuse-10105723 | ESA | 0.31307 | 25 | 46 | 2021-05-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13878 - 10105723 | CKT: 13878 - 10105723 | 2309865 | LUG ESA 13878.10105723 OH | 2309866 | LUG ESA 13878.10105723 UG | 2309865 | LUG ESA 13878.10105723 OH | 2309866 | LUG ESA 13878.10105723 UG
Leidos | 2021 | 2021 | LUG - TBD406 | PRE-09361.435 | PRE-09361.435 | LUG ESA 13911.92679866 | LUG ESA 13911.92679866 | 13911 | PEACH AVENUE | Lateral Hardening-Fuse-92679866 | Lateral Hardening-Fuse-92679866 | ESA | 0.55549 | 50 | 80 | 2021-05-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13911 - 92679866 | CKT: 13911 - 92679866 | 2309867 | LUG ESA 13911.92679866 OH | 2309869 | LUG ESA 13911.92679866 UG | 2309867 | LUG ESA 13911.92679866 OH | 2309869 | LUG ESA 13911.92679866 UG
Leidos | 2021 | 2021 | LUG - TBD407 | PRE-09361.436 | PRE-09361.436 | LUG ESA 13229.92525393 | LUG ESA 13229.92525393 | 13229 | BRANDON | Lateral Hardening-Fuse-92525393 | Lateral Hardening-Fuse-92525393 | ESA | 0.21496 | 21 | 141 | 2021-05-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C025 | CKT: 13229 - 92525393 | CKT: 13229 - 92525393 | 2309870 | LUG ESA 13229.92525393 OH | 2309871 | LUG ESA 13229.92525393 UG | 2309870 | LUG ESA 13229.92525393 OH | 2309871 | LUG ESA 13229.92525393 UG | Combined with LUG-TBD404 (FID 10457704)
Leidos | 2021 | 2021 | LUG - TBD408 | PRE-09361.437 | PRE-09361.437 | LUG ESA 13909.92173076 | LUG ESA 13909.92173076 | 13909 | PEACH AVENUE | Lateral Hardening-Fuse-92173076 | Lateral Hardening-Fuse-92173076 | ESA | 0.31155 | 22 | 8 | 2021-05-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13909 - 92173076 | CKT: 13909 - 92173076 | 2309872 | LUG ESA 13909.92173076 OH | 2309873 | LUG ESA 13909.92173076 UG | 2309872 | LUG ESA 13909.92173076 OH | 2309873 | LUG ESA 13909.92173076 UG
Leidos | 2021 | 2021 | LUG - TBD409 | PRE-09361.438 | PRE-09361.438 | LUG ESA 14355.60258173 | LUG ESA 14355.60258173 | 14355 | CAUSEWAY | Lateral Hardening-Fuse-60258173 | Lateral Hardening-Fuse-60258173 | ESA | 0.15777 | 15 | 356 | 2021-05-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 14355 - 60258173 | CKT: 14355 - 60258173 | 2309874 | LUG ESA 14355.60258173 OH | 2309875 | LUG ESA 14355.60258173 UG | 2309874 | LUG ESA 14355.60258173 OH | 2309875 | LUG ESA 14355.60258173 UG
Leidos | 2021 | 2021 | LUG - TBD410 | PRE-09361.439 | PRE-09361.439 | LUG ESA 13457.10482593 | LUG ESA 13457.10482593 | 13457 | LAKEWOOD | Lateral Hardening-Fuse-10482593 | Lateral Hardening-Fuse-10482593 | ESA | 0.13693 | 9 | 137 | 2021-05-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13457 - 10482593 | CKT: 13457 - 10482593 | 2309876 | LUG ESA 13457.10482593 OH | 2309877 | LUG ESA 13457.10482593 UG | 2309876 | LUG ESA 13457.10482593 OH | 2309877 | LUG ESA 13457.10482593 UG
Leidos | 2021 | 2021 | LUG - TBD411 | PRE-09361.440 | PRE-09361.440 | LUG ESA 13127.90334731 | LUG ESA 13127.90334731 | 13127 | SOUTH SEFFNER | Lateral Hardening-Fuse-90334731 | Lateral Hardening-Fuse-90334731 | ESA | 0.43826 | 22 | 56 | 2021-05-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13127 - 90334731 | CKT: 13127 - 90334731 | 2309878 | LUG ESA 13127.90334731 OH | 2309879 | LUG ESA 13127.90334731 UG | 2309878 | LUG ESA 13127.90334731 OH | 2309879 | LUG ESA 13127.90334731 UG
Leidos | 2021 | 2021 | LUG - TBD412 | PRE-09361.441 | PRE-09361.441 | LUG ESA 13906.10096968 | LUG ESA 13906.10096968 | 13906 | PEACH AVENUE | Lateral Hardening-Fuse-10096968 | Lateral Hardening-Fuse-10096968 | ESA | 0.55739 | 53 | 99 | 2021-05-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13906 - 10096968 | CKT: 13906 - 10096968 | 2309880 | LUG ESA 13906.10096968 OH | 2309881 | LUG ESA 13906.10096968 UG | 2309880 | LUG ESA 13906.10096968 OH | 2309881 | LUG ESA 13906.10096968 UG
Leidos | 2021 | 2021 | LUG - TBD413 | PRE-09361.442 | PRE-09361.442 | LUG ESA 13909.90380435 | LUG ESA 13909.90380435 | 13909 | PEACH AVENUE | Lateral Hardening-Fuse-90380435 | Lateral Hardening-Fuse-90380435 | ESA | 0.20095 | 11 | 41 | 2021-05-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13909 - 90380435 | CKT: 13909 - 90380435 | 2309882 | LUG ESA 13909.90380435 OH | 2309883 | LUG ESA 13909.90380435 UG | 2309882 | LUG ESA 13909.90380435 OH | 2309883 | LUG ESA 13909.90380435 UG
Leidos | 2021 | 2021 | LUG - TBD414 | PRE-09361.454 | PRE-09361.454 | DNU LUG ESA 13127.10836901 | LUG ESA 13127.92663180 | 13127 | SOUTH SEFFNER | DNU Lateral Hardening-Fuse-10836901 | Lateral Hardening-Fuse-92663180 | ESA | 0.44602 | 30 | 127 | 2021-05-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C026 | N/A | CKT: 13127 - 92663180 | N/A | N/A | N/A | N/A | 2309907 | LUG ESA 13127.92663180 OH | 2309908 | LUG ESA 13127.92663180 UG | Combined with LUG-TBD427 (FID 92663180)
Enercon | 2020 | 2020 | LUG - TBD459 | PRE-09361.31 | PRE-09361.31 | LUG WSA 14032.10820614 | LUG WSA 14032.10820614 | 14032 | PAGLEN ROAD | Lateral Hardening-Fuse-10820614 | Lateral Hardening-Fuse-10820614 | WSA | 0.34943 | 25 | 204 | 2020-06-01 | 2021-01-01 | 2021-04-01 | 4500274705 | N/A | N/A |  | CKT: 14032 - 10820614 | CKT: 14032 - 10820614 | 2271231 | LUG WSA 14032.10820614 OH | 2271237 | LUG WSA 14032.10820614 UG | 2271231 | LUG WSA 14032.10820614 OH | 2271237 | LUG WSA 14032.10820614 UG
Enercon | 2020 | 2020 | LUG - TBD460 | PRE-09361.32 | PRE-09361.32 | LUG WSA 13071.90738378 | LUG WSA 13071.90738378 | 13071 | KEYSTONE | Lateral Hardening-Fuse-90738378 | Lateral Hardening-Fuse-90738378 | WSA | 0.16288 | 20 | 296 | 2020-06-01 | 2021-01-01 | 2021-03-01 | 4500274705 | N/A | N/A |  | CKT: 13071 - 90738378 | CKT: 13071 - 90738378 | 2272328 | LUG WSA 13071.90738378 OH | 2272333 | LUG WSA 13071.90738378 UG | 2272328 | LUG WSA 13071.90738378 OH | 2272333 | LUG WSA 13071.90738378 UG
Enercon | 2020 | 2020 | LUG - TBD461 | PRE-09361.33 | PRE-09361.33 | LUG WSA 14032.92634300 | LUG WSA 14032.92634300 | 14032 | PAGLEN ROAD | Lateral Hardening-Fuse-92634300 | Lateral Hardening-Fuse-92634300 | WSA | 0.31383 | 21 | 306 | 2020-06-01 | 2021-01-01 | 2021-04-01 | 4500274705 | N/A | N/A |  | CKT: 14032 - 92634300 | CKT: 14032 - 92634300 | 2272329 | LUG WSA 14032.92634300 OH | 2272334 | LUG WSA 14032.92634300 UG | 2272329 | LUG WSA 14032.92634300 OH | 2272334 | LUG WSA 14032.92634300 UG
Enercon | 2020 | 2020 | LUG - TBD462 | PRE-09361.34 | PRE-09361.34 | LUG WSA 13071.91245761 | LUG WSA 13071.91245761 | 13071 | KEYSTONE | Lateral Hardening-Fuse-91245761 | Lateral Hardening-Fuse-91245761 | WSA | 0.2892 | 17 | 6 | 2020-06-01 | 2021-01-01 | 2021-03-01 | 4500274705 | N/A | N/A |  | CKT: 13071 - 91245761 | CKT: 13071 - 91245761 | 2272893 | LUG WSA 13071.91245761 OH | 2272895 | LUG WSA 13071.91245761 UG | 2272893 | LUG WSA 13071.91245761 OH | 2272895 | LUG WSA 13071.91245761 UG
Enercon | 2020 | 2020 | LUG - TBD463 | PRE-09361.35 | PRE-09361.35 | LUG WSA 14032.91487301 | LUG WSA 14032.91487301 | 14032 | PAGLEN ROAD | Lateral Hardening-Fuse-91487301 | Lateral Hardening-Fuse-91487301 | WSA | 0.2786 | 25 | 199 | 2020-07-01 | 2021-01-01 | 2021-04-01 | 4500274705 | N/A | N/A |  | CKT: 14032 - 91487301 | CKT: 14032 - 91487301 | 2272897 | LUG WSA 14032.91487301 OH | 2272899 | LUG WSA 14032.91487301 UG | 2272897 | LUG WSA 14032.91487301 OH | 2272899 | LUG WSA 14032.91487301 UG
Enercon | 2020 | 2020 | LUG - TBD464 | PRE-09361.36 | PRE-09361.36 | LUG WSA 14032.10339836 | LUG WSA 14032.10339836 | 14032 | PAGLEN ROAD | Lateral Hardening-Fuse-10339836 | Lateral Hardening-Fuse-10339836 | WSA | 0.12841 | 11 | 2 | 2020-07-01 | 2021-01-01 | 2021-03-01 | 4500274705 | N/A | N/A |  | CKT: 14032 - 10339836 | CKT: 14032 - 10339836 | 2272920 | LUG WSA 14032.10339836 OH | 2272921 | LUG WSA 14032.10339836 UG | 2272920 | LUG WSA 14032.10339836 OH | 2272921 | LUG WSA 14032.10339836 UG
Enercon | 2020 | 2020 | LUG - TBD465 | PRE-09361.37 | PRE-09361.37 | LUG WSA 14032.92803239 | LUG WSA 14032.92803239 | 14032 | PAGLEN ROAD | Lateral Hardening-Fuse-92803239 | Lateral Hardening-Fuse-92803239 | WSA | 0.23977 | 8 | 5 | 2020-07-01 | 2021-01-01 | 2021-04-01 | 4500274705 | N/A | N/A |  | CKT: 14032 - 92803239 | CKT: 14032 - 92803239 | 2272923 | LUG WSA 14032.92803239 OH | 2272925 | LUG WSA 14032.92803239 UG | 2272923 | LUG WSA 14032.92803239 OH | 2272925 | LUG WSA 14032.92803239 UG
Enercon | 2020 | 2020 | LUG - TBD466 | PRE-09361.39 | PRE-09361.38 | DNU LUG WSA 13071.91432110 | LUG WSA 13071.91432109 | 13071 | KEYSTONE | DNU Lateral Hardening-Fuse-91432110 | Lateral Hardening-Fuse-91432109 | WSA | 0.22443 | 17 | 11 | 2020-07-01 | 2021-01-01 | 2021-02-01 | 4500274705 | N/A | N/A | LUG C018 | DNU CKT: 13071 - 91432110 | CKT: 13071 - 91432109 | 2272931 | DNU LUG WSA 13071.91432110 OH | 2272933 | DNU LUG WSA 13071.91432110 UG | 2272936 | LUG WSA 13071.91432109 OH | 2272937 | LUG WSA 13071.91432109 UG | Combined with PRE-09361.39 (FID 91432109)
Enercon | 2020 | 2020 | LUG - TBD467 | PRE-09361.39 | PRE-09361.39 | LUG WSA 13071.91432109 | LUG WSA 13071.91432109 | 13071 | KEYSTONE | Lateral Hardening-Fuse-91432109 | Lateral Hardening-Fuse-91432109 | WSA | 0.14261 | 15 | 20 | 2020-07-01 | 2021-01-01 | 2021-03-01 | 4500274705 | N/A | N/A | LUG C018 | CKT: 13071 - 91432109 | CKT: 13071 - 91432109 | 2272936 | LUG WSA 13071.91432109 OH | 2272937 | LUG WSA 13071.91432109 UG | 2272936 | LUG WSA 13071.91432109 OH | 2272937 | LUG WSA 13071.91432109 UG | Combined with PRE-09361.38 (FID 91432110)
Enercon | 2020 | 2020 | LUG - TBD468 | PRE-09361.40 | PRE-09361.40 | LUG WSA 14032.92729035 | LUG WSA 14032.92729035 | 14032 | PAGLEN ROAD | Lateral Hardening-Fuse-92729035 | Lateral Hardening-Fuse-92729035 | WSA | 0.36364 | 27 | 5 | 2020-07-01 | 2021-01-01 | 2021-04-01 | 4500274705 | N/A | N/A |  | CKT: 14032 - 92729035 | CKT: 14032 - 92729035 | 2272939 | LUG WSA 14032.92729035 OH | 2272940 | LUG WSA 14032.92729035 UG | 2272939 | LUG WSA 14032.92729035 OH | 2272940 | LUG WSA 14032.92729035 UG
Enercon | 2020 | 2020 | LUG - TBD469 | PRE-09361.48 | PRE-09361.48 | LUG WSA 13198.92183966 | LUG WSA 13198.92183966 | 13198 | GRAY STREET | Lateral Hardening-Fuse-92183966 | Lateral Hardening-Fuse-92183966 | WSA | 0.16629 | 12 | 86 | 2020-07-01 | 2021-01-01 | 2021-03-01 | 4500274705 | N/A | N/A | LUG C020 | CKT: 13198 - 92183966 | CKT: 13198 - 92183966 | 2273238 | LUG WSA 13198.92183966 OH | 2273240 | LUG WSA 13198.92183966 UG | 2273238 | LUG WSA 13198.92183966 OH | 2273240 | LUG WSA 13198.92183966 UG | Combined with PRE-09361.262 (FID 10051852) & PRE-09361.278 (FID 92585443)
Enercon | 2020 | 2020 | LUG - TBD470 | PRE-09361.49 | PRE-09361.49 | LUG WSA 13678.90514649 | LUG WSA 13678.90514649 | 13678 | TURKEY FORD | Lateral Hardening-Fuse-90514649 | Lateral Hardening-Fuse-90514649 | WSA | 0.50966 | 13 | 42 | 2020-07-01 | 2021-01-01 | 2021-04-01 | 4500274705 | N/A | N/A |  | CKT: 13678 - 90514649 | CKT: 13678 - 90514649 | 2273257 | LUG WSA 13678.90514649 OH | 2273259 | LUG WSA 13678.90514649 UG | 2273257 | LUG WSA 13678.90514649 OH | 2273259 | LUG WSA 13678.90514649 UG
Enercon | 2020 | 2020 | LUG - TBD471 | PRE-09361.50 | PRE-09361.50 | LUG WSA 13425.10244449 | LUG WSA 13425.10244449 | 13425 | ROCKY CREEK | Lateral Hardening-Fuse-10244449 | Lateral Hardening-Fuse-10244449 | WSA | 0.69659 | 33 | 195 | 2020-07-01 | 2021-01-01 | 2021-05-01 | 4500274705 | N/A | N/A |  | CKT: 13425 - 10244449 | CKT: 13425 - 10244449 | 2273263 | LUG WSA 13425.10244449 OH | 2273265 | LUG WSA 13425.10244449 UG | 2273263 | LUG WSA 13425.10244449 OH | 2273265 | LUG WSA 13425.10244449 UG
Enercon | 2020 | 2020 | LUG - TBD472 | PRE-09361.51 | PRE-09361.51 | LUG WSA 13670.93124410 | LUG WSA 13670.93124410 | 13670 | MEADOW PARK | Lateral Hardening-Fuse-93124410 | Lateral Hardening-Fuse-93124410 | WSA | 0.71345 | 25 | 383 | 2020-07-01 | 2021-01-01 | 2021-05-01 | 4500274705 | N/A | N/A |  | CKT: 13670 - 93124410 | CKT: 13670 - 93124410 | 2273274 | LUG WSA 13670.93124410 OH | 2273276 | LUG WSA 13670.93124410 UG | 2273274 | LUG WSA 13670.93124410 OH | 2273276 | LUG WSA 13670.93124410 UG
Enercon | 2020 | 2020 | LUG - TBD473 | PRE-09361.52 | PRE-09361.52 | LUG WSA 13428.91540495 | LUG WSA 13428.91540495 | 13428 | ROCKY CREEK | Lateral Hardening-Fuse-91540495 | Lateral Hardening-Fuse-91540495 | WSA | 0.23314 | 30 | 402 | 2020-08-01 | 2021-01-01 | 2021-03-01 | 4500274705 | N/A | N/A |  | CKT: 13428 - 91540495 | CKT: 13428 - 91540495 | 2273279 | LUG WSA 13428.91540495 OH | 2273281 | LUG WSA 13428.91540495 UG | 2273279 | LUG WSA 13428.91540495 OH | 2273281 | LUG WSA 13428.91540495 UG
Enercon | 2020 | 2020 | LUG - TBD474 | PRE-09361.53 | PRE-09361.53 | LUG WSA 13332.91335523 | LUG WSA 13332.91335523 | 13332 | WATERS AVENUE | Lateral Hardening-Fuse-91335523 | Lateral Hardening-Fuse-91335523 | WSA | 0.29205 | 23 | 230 | 2020-08-01 | 2021-01-01 | 2021-03-01 | 4500274705 | N/A | N/A |  | CKT: 13332 - 91335523 | CKT: 13332 - 91335523 | 2273285 | LUG WSA 13332.91335523 OH | 2273287 | LUG WSA 13332.91335523 UG | 2273285 | LUG WSA 13332.91335523 OH | 2273287 | LUG WSA 13332.91335523 UG
Enercon | 2020 | 2020 | LUG - TBD475 | PRE-09361.54 | PRE-09361.54 | LUG WSA 13544.10053266 | LUG WSA 13544.10053266 | 13544 | CARROLLWOOD VILLAGE | Lateral Hardening-Fuse-10053266 | Lateral Hardening-Fuse-10053266 | WSA | 0.29072 | 20 | 161 | 2020-08-01 | 2021-04-01 | 2021-06-01 | 4500274705 | N/A | N/A |  | CKT: 13544 - 10053266 | CKT: 13544 - 10053266 | 2273289 | LUG WSA 13544.10053266 OH | 2273292 | LUG WSA 13544.10053266 UG | 2273289 | LUG WSA 13544.10053266 OH | 2273292 | LUG WSA 13544.10053266 UG
Enercon | 2020 | 2020 | LUG - TBD476 | PRE-09361.55 | PRE-09361.55 | LUG WSA 13109.90641822 | LUG WSA 13109.90641822 | 13109 | MANHATTAN | Lateral Hardening-Fuse-90641822 | Lateral Hardening-Fuse-90641822 | WSA | 0.21742 | 22 | 413 | 2020-08-01 | 2021-04-01 | 2021-07-01 | 4500274705 | N/A | N/A | LUG C019 | CKT: 13109 - 90641822 | CKT: 13109 - 90641822 | 2273297 | LUG WSA 13109.90641822 OH | 2273300 | LUG WSA 13109.90641822 UG | 2273297 | LUG WSA 13109.90641822 OH | 2273300 | LUG WSA 13109.90641822 UG | Combined with PRE-09361.254 (FID 10846390/LUG-TBD617)
Enercon | 2020 | 2020 | LUG - TBD477 | PRE-09361.56 | PRE-09361.56 | LUG WSA 13747.10299739 | LUG WSA 13747.10299739 | 13747 | CASEY ROAD | Lateral Hardening-Fuse-10299739 | Lateral Hardening-Fuse-10299739 | WSA | 0.10038 | 5 | 128 | 2020-08-01 | 2021-04-01 | 2021-06-01 | 4500274705 | N/A | N/A |  | CKT: 13747 - 10299739 | CKT: 13747 - 10299739 | 2273306 | LUG WSA 13747.10299739 OH | 2273308 | LUG WSA 13747.10299739 UG | 2273306 | LUG WSA 13747.10299739 OH | 2273308 | LUG WSA 13747.10299739 UG
Enercon | 2020 | 2020 | LUG - TBD478 | PRE-09361.57 | PRE-09361.57 | LUG WSA 13756.60165357 | LUG WSA 13756.60165357 | 13756 | GRANADA | Lateral Hardening-Fuse-60165357 | Lateral Hardening-Fuse-60165357 | WSA | 0.26989 | 26 | 133 | 2020-09-01 | 2021-04-01 | 2021-07-01 | 4500274705 | N/A | N/A |  | CKT: 13756 - 60165357 | CKT: 13756 - 60165357 | 2273311 | LUG WSA 13756.60165357 OH | 2273314 | LUG WSA 13756.60165357 UG | 2273311 | LUG WSA 13756.60165357 OH | 2273314 | LUG WSA 13756.60165357 UG
Enercon | 2020 | 2020 | LUG - TBD479 | PRE-09361.58 | PRE-09361.58 | LUG WSA 13491.10230118 | LUG WSA 13491.10230118 | 13491 | JACKSON ROAD | Lateral Hardening-Fuse-10230118 | Lateral Hardening-Fuse-10230118 | WSA | 0.51477 | 36 | 94 | 2020-09-01 | 2021-04-01 | 2021-07-01 | 4500274705 | N/A | N/A |  | CKT: 13491 - 10230118 | CKT: 13491 - 10230118 | 2273318 | LUG WSA 13491.10230118 OH | 2273320 | LUG WSA 13491.10230118 UG | 2273318 | LUG WSA 13491.10230118 OH | 2273320 | LUG WSA 13491.10230118 UG
Enercon | 2020 | 2020 | LUG - TBD480 | PRE-09361.59 | PRE-09361.59 | LUG WSA 13141.92630916 | LUG WSA 13141.92630916 | 13141 | HYDE PARK | Lateral Hardening-Fuse-92630916 | Lateral Hardening-Fuse-92630916 | WSA | 0.40398 | 35 | 41 | 2020-10-01 | 2021-05-01 | 2021-08-01 | 4500274705 | N/A | N/A |  | CKT: 13141 - 92630916 | CKT: 13141 - 92630916 | 2273323 | LUG WSA 13141.92630916 OH | 2273326 | LUG WSA 13141.92630916 UG | 2273323 | LUG WSA 13141.92630916 OH | 2273326 | LUG WSA 13141.92630916 UG
Enercon | 2020 | 2020 | LUG - TBD481 | PRE-09361.60 | PRE-09361.60 | LUG WSA 13673.10277744 | LUG WSA 13673.10277744 | 13673 | MEADOW PARK | Lateral Hardening-Fuse-10277744 | Lateral Hardening-Fuse-10277744 | WSA | 1.0036 | 56 | 266 | 2020-09-01 | 2021-05-01 | 2021-08-01 | 4500274705 | N/A | N/A |  | CKT: 13673 - 10277744 | CKT: 13673 - 10277744 | 2273330 | LUG WSA 13673.10277744 OH | 2273332 | LUG WSA 13673.10277744 UG | 2273330 | LUG WSA 13673.10277744 OH | 2273332 | LUG WSA 13673.10277744 UG
Enercon | 2020 | 2020 | LUG - TBD482 | PRE-09361.61 | PRE-09361.61 | LUG WSA 13138.60079254 | LUG WSA 13138.60079254 | 13138 | HABANA AVENUE | Lateral Hardening-Fuse-60079254 | Lateral Hardening-Fuse-60079254 | WSA | 0.092045 | 13 | 152 | 2020-10-01 | 2021-05-01 | 2021-07-01 | 4500274705 | N/A | N/A |  | CKT: 13138 - 60079254 | CKT: 13138 - 60079254 | 2273333 | LUG WSA 13138.60079254 OH | 2273334 | LUG WSA 13138.60079254 UG | 2273333 | LUG WSA 13138.60079254 OH | 2273334 | LUG WSA 13138.60079254 UG
Enercon | 2020 | 2020 | LUG - TBD483 | PRE-09361.62 | PRE-09361.62 | LUG WSA 13141.92442349 | LUG WSA 13141.92442349 | 13141 | HYDE PARK | Lateral Hardening-Fuse-92442349 | Lateral Hardening-Fuse-92442349 | WSA | 0.40189 | 43 | 122 | 2020-10-01 | 2021-04-01 | 2021-09-01 | 4500274705 | N/A | N/A |  | CKT: 13141 - 92442349 | CKT: 13141 - 92442349 | 2273327 | LUG WSA 13141.92442349 OH | 2273331 | LUG WSA 13141.92442349 UG | 2273327 | LUG WSA 13141.92442349 OH | 2273331 | LUG WSA 13141.92442349 UG
Enercon | 2020 | 2020 | LUG - TBD484 | PRE-09361.63 | PRE-09361.63 | LUG WSA 13333.10007582 | LUG WSA 13333.10007582 | 13333 | WATERS AVENUE | Lateral Hardening-Fuse-10007582 | Lateral Hardening-Fuse-10007582 | WSA | 0.30455 | 27 | 24 | 2020-10-01 | 2021-05-01 | 2021-07-01 | 4500274705 | N/A | N/A |  | CKT: 13333 - 10007582 | CKT: 13333 - 10007582 | 2273321 | LUG WSA 13333.10007582 OH | 2273324 | LUG WSA 13333.10007582 UG | 2273321 | LUG WSA 13333.10007582 OH | 2273324 | LUG WSA 13333.10007582 UG
Enercon | 2020 | 2020 | LUG - TBD485 | PRE-09361.64 | PRE-09361.64 | LUG WSA 13586.92298267 | LUG WSA 13586.92298267 | 13586 | DALE MABRY | Lateral Hardening-Fuse-92298267 | Lateral Hardening-Fuse-92298267 | WSA | 0.44905 | 45 | 459 | 2020-10-01 | 2021-05-01 | 2021-08-01 | 4500274705 | N/A | N/A |  | CKT: 13586 - 92298267 | CKT: 13586 - 92298267 | 2273317 | LUG WSA 13586.92298267 OH | 2273319 | LUG WSA 13586.92298267 UG | 2273317 | LUG WSA 13586.92298267 OH | 2273319 | LUG WSA 13586.92298267 UG
Enercon | 2020 | 2020 | LUG - TBD486 | PRE-09361.65 | PRE-09361.65 | LUG WSA 13138.10145625 | LUG WSA 13138.10145625 | 13138 | HABANA AVENUE | Lateral Hardening-Fuse-10145625 | Lateral Hardening-Fuse-10145625 | WSA | 0.3 | 27 | 343 | 2020-10-01 | 2021-09-01 | 2021-12-01 | 4500274705 | N/A | N/A | LUG C036 | CKT: 13138 - 10145625 | CKT: 13138 - 10145625 | 2273309 | LUG WSA 13138.10145625 OH | 2273313 | LUG WSA 13138.10145625 UG | 2273309 | LUG WSA 13138.10145625 OH | 2273313 | LUG WSA 13138.10145625 UG | Combined with PRE-09361.226 (FID 10145602)
Enercon | 2020 | 2020 | LUG - TBD487 | PRE-09361.66 | PRE-09361.66 | LUG WSA 13140.10013916 | LUG WSA 13140.10013916 | 13140 | HYDE PARK | Lateral Hardening-Fuse-10013916 | Lateral Hardening-Fuse-10013916 | WSA | 0.10284 | 13 | 143 | 2020-10-01 | 2021-10-01 | 2021-12-01 | 4500274705 | N/A | N/A |  | CKT: 13140 - 10013916 | CKT: 13140 - 10013916 | 2273304 | LUG WSA 13140.10013916 OH | 2273307 | LUG WSA 13140.10013916 UG | 2273304 | LUG WSA 13140.10013916 OH | 2273307 | LUG WSA 13140.10013916 UG
Enercon | 2020 | 2020 | LUG - TBD488 | PRE-09361.67 | PRE-09361.67 | LUG WSA 13113.90796385 | LUG WSA 13113.90796385 | 13113 | MANHATTAN | Lateral Hardening-Fuse-90796385 | Lateral Hardening-Fuse-90796385 | WSA | 0.51326 | 34 | 233 | 2020-10-01 | 2021-09-01 | 2021-12-01 | 4500274705 | N/A | N/A | LUG C021 | CKT: 13113 - 90796385 | CKT: 13113 - 90796385 | 2273299 | LUG WSA 13113.90796385 OH | 2273301 | LUG WSA 13113.90796385 UG | 2273299 | LUG WSA 13113.90796385 OH | 2273301 | LUG WSA 13113.90796385 UG | Combined with PRE-09361.171 (FID 60340774)
Enercon | 2020 | 2020 | LUG - TBD489 | PRE-09361.68 | PRE-09361.68 | LUG WSA 13138.10145628 | LUG WSA 13138.10145628 | 13138 | HABANA AVENUE | Lateral Hardening-Fuse-10145628 | Lateral Hardening-Fuse-10145628 | WSA | 0.30379 | 18 | 352 | 2020-09-01 | 2021-09-01 | 2021-12-01 | 4500274705 | N/A | N/A |  | CKT: 13138 - 10145628 | CKT: 13138 - 10145628 | 2273294 | LUG WSA 13138.10145628 OH | 2273296 | LUG WSA 13138.10145628 UG | 2273294 | LUG WSA 13138.10145628 OH | 2273296 | LUG WSA 13138.10145628 UG
Enercon | 2020 | 2020 | LUG - TBD490 | PRE-09361.69 | PRE-09361.69 | LUG WSA 13164.10158909 | LUG WSA 13164.10158909 | 13164 | MATANZAS | Lateral Hardening-Fuse-10158909 | Lateral Hardening-Fuse-10158909 | WSA | 0.79432 | 68 | 270 | 2020-09-01 | 2021-06-01 | 2021-12-01 | 4500274705 | N/A | N/A |  | CKT: 13164 - 10158909 | CKT: 13164 - 10158909 | 2273288 | LUG WSA 13164.10158909 OH | 2273291 | LUG WSA 13164.10158909 UG | 2273288 | LUG WSA 13164.10158909 OH | 2273291 | LUG WSA 13164.10158909 UG
Enercon | 2020 | 2020 | LUG - TBD491 | PRE-09361.70 | PRE-09361.70 | LUG WSA 13140.91873275 | LUG WSA 13140.91873275 | 13140 | HYDE PARK | Lateral Hardening-Fuse-91873275 | Lateral Hardening-Fuse-91873275 | WSA | 0.5267 | 55 | 31 | 2020-10-01 | 2021-02-01 | 2021-06-01 | 4500274705 | N/A | N/A |  | CKT: 13140 - 91873275 | CKT: 13140 - 91873275 | 2273284 | LUG WSA 13140.91873275 OH | 2273286 | LUG WSA 13140.91873275 UG | 2273284 | LUG WSA 13140.91873275 OH | 2273286 | LUG WSA 13140.91873275 UG
Enercon | 2020 | 2020 | LUG - TBD492 | PRE-09361.71 | PRE-09361.71 | LUG WSA 13605.91052996 | LUG WSA 13605.91052996 | 13605 | MACDILL | Lateral Hardening-Fuse-91052996 | Lateral Hardening-Fuse-91052996 | WSA | 0.33201 | 27 | 115 | 2020-10-01 | 2021-08-01 | 2021-10-01 | 4500274705 | N/A | N/A | LUG C001 | CKT: 13605 - 91052996 | CKT: 13605 - 91052996 | 2273278 | LUG WSA 13605.91052996 OH | 2273280 | LUG WSA 13605.91052996 UG | 2273278 | LUG WSA 13605.91052996 OH | 2273280 | LUG WSA 13605.91052996 UG | Combined with LUG-TBD496 (FID 90568909) & LUG-TBD526 (FID 90427351)
Enercon | 2020 | 2020 | LUG - TBD493 | PRE-09361.72 | PRE-09361.72 | LUG WSA 13071.60170422 | LUG WSA 13071.60170422 | 13071 | KEYSTONE | Lateral Hardening-Fuse-60170422 | Lateral Hardening-Fuse-60170422 | WSA | 0.9947 | 74 | 362 | 2020-09-01 | 2021-06-01 | 2021-11-01 | 4500274705 | N/A | N/A | LUG C022 | CKT: 13071 - 60170422 | CKT: 13071 - 60170422 | 2273270 | LUG WSA 13071.60170422 OH | 2273272 | LUG WSA 13071.60170422 UG | 2273270 | LUG WSA 13071.60170422 OH | 2273272 | LUG WSA 13071.60170422 UG | Combined with PRE-09361.244 (FID 93035682)
Enercon | 2020 | 2020 | LUG - TBD494 | PRE-09361.73 | PRE-09361.73 | LUG WSA 13111.92999604 | LUG WSA 13111.92999604 | 13111 | MANHATTAN | Lateral Hardening-Fuse-92999604 | Lateral Hardening-Fuse-92999604 | WSA | 0.41705 | 32 | 61 | 2020-10-01 | 2021-10-01 | 2021-12-01 | 4500274705 | N/A | N/A |  | CKT: 13111 - 92999604 | CKT: 13111 - 92999604 | 2273262 | LUG WSA 13111.92999604 OH | 2273266 | LUG WSA 13111.92999604 UG | 2273262 | LUG WSA 13111.92999604 OH | 2273266 | LUG WSA 13111.92999604 UG
Enercon | 2020 | 2020 | LUG - TBD495 | PRE-09361.74 | PRE-09361.74 | LUG WSA 13586.60303627 | LUG WSA 13586.60303627 | 13586 | DALE MABRY | Lateral Hardening-Fuse-60303627 | Lateral Hardening-Fuse-60303627 | WSA | 1.0686 | 67 | 69 | 2020-09-01 | 2021-07-01 | 2021-12-01 | 4500274705 | N/A | N/A |  | CKT: 13586 - 60303627 | CKT: 13586 - 60303627 | 2273255 | LUG WSA 13586.60303627 OH | 2273260 | LUG WSA 13586.60303627 UG | 2273255 | LUG WSA 13586.60303627 OH | 2273260 | LUG WSA 13586.60303627 UG
Fishel | 2020 | 2020 | LUG - TBD1 | PRE-09361.1 | PRE-09361.1 | LUG PCA 13390.92599119 | LUG PCA 13390.92599119 | 13390 | KIRKLAND ROAD | Lateral Hardening-Fuse-92599119 | Lateral Hardening-Fuse-92599119 | PCA | 0.72367 | 46 | 266 | 2020-06-01 | 2020-06-20 | 2020-12-20 | 4500272910 | N/A | N/A | LUG C035 | CKT: 13390 - 92599119 | CKT: 13390 - 92599119 | 2271216 | LUG PCA 13390.92599119 OH | 2271217 | LUG PCA 13390.92599119 UG | 2271216 | LUG PCA 13390.92599119 OH | 2271217 | LUG PCA 13390.92599119 UG | Combined with PRE-09361.45 (FID 10643541)
Fishel | 2020 | 2020 | LUG - TBD2 | PRE-09361.2 | PRE-09361.2 | LUG PCA 13961.92829453 | LUG PCA 13961.92829453 | 13961 | TERRACE | Lateral Hardening-Fuse-92829453 | Lateral Hardening-Fuse-92829453 | PCA | 0.33693 | 25 | 447 | 2020-06-01 | 2021-01-01 | 2021-03-01 | 4500272910 | N/A | N/A |  | CKT: 13961 - 92829453 | CKT: 13961 - 92829453 | 2274016 | LUG PCA 13961.92829453 OH | 2274027 | LUG PCA 13961.92829453 UG | 2274016 | LUG PCA 13961.92829453 OH | 2274027 | LUG PCA 13961.92829453 UG
Fishel | 2020 | 2020 | LUG - TBD3 | PRE-09361.3 | PRE-09361.3 | LUG PCA 13724.90911087 | LUG PCA 13724.90911087 | 13724 | GALLAGHER ROAD | Lateral Hardening-Fuse-90911087 | Lateral Hardening-Fuse-90911087 | PCA | 0.5392 | 32 | 31 | 2020-06-01 | 2021-01-01 | 2021-03-01 | 4500272910 | N/A | N/A |  | CKT: 13724 - 90911087 | CKT: 13724 - 90911087 | 2274044 | LUG PCA 13724.90911087 OH | 2274045 | LUG PCA 13724.90911087 UG | 2274044 | LUG PCA 13724.90911087 OH | 2274045 | LUG PCA 13724.90911087 UG
Fishel | 2020 | 2020 | LUG - TBD4 | PRE-09361.4 | PRE-09361.4 | LUG PCA 13146.10629014 | LUG PCA 13146.10629014 | 13146 | HOPEWELL | Lateral Hardening-Fuse-10629014 | Lateral Hardening-Fuse-10629014 | PCA | 0.54337 | 30 | 91 | 2020-06-01 | 2021-01-01 | 2021-03-01 | 4500272910 | N/A | N/A |  | CKT: 13146 - 10629014 | CKT: 13146 - 10629014 | 2274142 | LUG PCA 13146.10629014 OH | 2274147 | LUG PCA 13146.10629014 UG | 2274142 | LUG PCA 13146.10629014 OH | 2274147 | LUG PCA 13146.10629014 UG
Fishel | 2020 | 2020 | LUG - TBD5 | PRE-09361.5 | PRE-09361.5 | LUG WHA 13972.92421291 | LUG WHA 13972.92421291 | 13972 | LUCERNE PARK | Lateral Hardening-Fuse-92421291 | Lateral Hardening-Fuse-92421291 | WHA | 0.43693 | 23 | 379 | 2020-07-01 | 2021-01-01 | 2021-03-01 | 4500272910 | N/A | N/A |  | CKT: 13972 - 92421291 | CKT: 13972 - 92421291 | 2274151 | LUG WHA 13972.92421291 OH | 2274626 | LUG WHA 13972.92421291 UG | 2274151 | LUG WHA 13972.92421291 OH | 2274626 | LUG WHA 13972.92421291 UG
Fishel | 2020 | 2020 | LUG - TBD6 | PRE-09361.6 | PRE-09361.6 | LUG WHA 13312.60182741 | LUG WHA 13312.60182741 | 13312 | EAST WINTER HAVEN | Lateral Hardening-Fuse-60182741 | Lateral Hardening-Fuse-60182741 | WHA | 0.1483 | 15 | 52 | 2020-07-01 | 2021-01-01 | 2021-03-01 | 4500272910 | N/A | N/A |  | CKT: 13312 - 60182741 | CKT: 13312 - 60182741 | 2274153 | LUG WHA 13312.60182741 OH | 2274156 | LUG WHA 13312.60182741 UG | 2274153 | LUG WHA 13312.60182741 OH | 2274156 | LUG WHA 13312.60182741 UG
Fishel | 2020 | 2020 | LUG - TBD7 | PRE-09361.7 | PRE-09361.7 | LUG WHA 13972.90241880 | LUG WHA 13972.90241880 | 13972 | LUCERNE PARK | Lateral Hardening-Fuse-90241880 | Lateral Hardening-Fuse-90241880 | WHA | 0.90379 | 49 | 130 | 2020-08-01 | 2021-01-01 | 2021-03-01 | 4500272910 | N/A | N/A |  | CKT: 13972 - 90241880 | CKT: 13972 - 90241880 | 2274158 | LUG WHA 13972.90241880 OH | 2274159 | LUG WHA 13972.90241880 UG | 2274158 | LUG WHA 13972.90241880 OH | 2274159 | LUG WHA 13972.90241880 UG
Fishel | 2020 | 2020 | LUG - TBD8 | PRE-09361.8 | PRE-09361.8 | LUG PCA 13961.92820848 | LUG PCA 13961.92820848 | 13961 | TERRACE | Lateral Hardening-Fuse-92820848 | Lateral Hardening-Fuse-92820848 | PCA | 0.49451 | 26 | 509 | 2020-09-01 | 2021-01-01 | 2021-03-01 | 4500272910 | N/A | N/A |  | CKT: 13961 - 92820848 | CKT: 13961 - 92820848 | 2274161 | LUG PCA 13961.92820848 OH | 2274162 | LUG PCA 13961.92820848 UG | 2274161 | LUG PCA 13961.92820848 OH | 2274162 | LUG PCA 13961.92820848 UG
Fishel | 2020 | 2020 | LUG - TBD9 | PRE-09361.9 | PRE-09361.9 | LUG PCA 13961.60193482 | LUG PCA 13961.60193482 | 13961 | TERRACE | Lateral Hardening-Fuse-60193482 | Lateral Hardening-Fuse-60193482 | PCA | 0.4822 | 35 | 118 | 2020-09-01 | 2021-01-01 | 2021-03-01 | 4500272910 | N/A | N/A |  | CKT: 13961 - 60193482 | CKT: 13961 - 60193482 | 2274163 | LUG PCA 13961.60193482 OH | 2274166 | LUG PCA 13961.60193482 UG | 2274163 | LUG PCA 13961.60193482 OH | 2274166 | LUG PCA 13961.60193482 UG
Fishel | 2020 | 2020 | LUG - TBD10 | PRE-09361.47 | PRE-09361.10 | DNU LUG PCA 13785.10676209 | LUG PCA 13785.92466250 | 13785 | PINECREST | DNU Lateral Hardening-Fuse-10676209 | Lateral Hardening-Fuse-92466250 | PCA | 0.95057 | 54 | 266 | 2020-09-01 | 2021-01-01 | 2021-03-01 | 4500272910 | N/A | N/A | LUG C034 | DNU CKT: 13785 - 10676209 | CKT: 13785 - 92466250 | 2274167 | DNU LUG PCA 13785.10676209 OH | 2274169 | DNU LUG PCA 13785.10676209 UG | 2274189 | LUG PCA 13785.92466250 OH | 2274190 | LUG PCA 13785.92466250 UG | Combined with PRE-09361.42 (FID 93159006), PRE-09361.47 (FID 92466250) & LUG TBD18 (FID 90239166)
Fishel | 2020 | 2020 | LUG - TBD11 | PRE-09361.41 | PRE-09361.41 | LUG PCA 13462.60458175 | LUG PCA 13462.60458175 | 13462 | ALEXANDER ROAD | Lateral Hardening-Fuse-60458175 | Lateral Hardening-Fuse-60458175 | PCA | 0.66004 | 32 | 65 | 2020-09-01 | 2021-01-01 | 2021-03-01 | 4500272910 | N/A | N/A |  | CKT: 13462 - 60458175 | CKT: 13462 - 60458175 | 2274170 | LUG PCA 13462.60458175 OH | 2274174 | LUG PCA 13462.60458175 UG | 2274170 | LUG PCA 13462.60458175 OH | 2274174 | LUG PCA 13462.60458175 UG
Fishel | 2020 | 2020 | LUG - TBD12 | PRE-09361.47 | PRE-09361.42 | DNU LUG PCA 14121.93159006 | LUG PCA 13785.92466250 | 14121 | FISHHAWK | DNU Lateral Hardening-Fuse-93159006 | Lateral Hardening-Fuse-92466250 | PCA | 0.56951 | 31 | 74 | 2020-10-01 | 2021-01-01 | 2021-03-01 | 4500272910 | N/A | N/A | LUG C034 | DNU CKT: 14121 - 93159006 | CKT: 13785 - 92466250 | 2274175 | DNU LUG PCA 14121.93159006 OH | 2274176 | DNU LUG PCA 14121.93159006 UG | 2274189 | LUG PCA 13785.92466250 OH | 2274190 | LUG PCA 13785.92466250 UG | Combined with PRE-09361.10 (FID 10676209), PRE-09361.47 (FID 92466250) & LUG TBD18 (FID 90239166)
Fishel | 2020 | 2020 | LUG - TBD13 | PRE-09361.43 | PRE-09361.43 | LUG PCA 13462.60180762 | LUG PCA 13462.60180762 | 13462 | ALEXANDER ROAD | Lateral Hardening-Fuse-60180762 | Lateral Hardening-Fuse-60180762 | PCA | 0.13371 | 14 | 88 | 2020-11-01 | 2021-02-01 | 2021-03-01 | 4500272910 | N/A | N/A |  | CKT: 13462 - 60180762 | CKT: 13462 - 60180762 | 2274177 | LUG PCA 13462.60180762 OH | 2274179 | LUG PCA 13462.60180762 UG | 2274177 | LUG PCA 13462.60180762 OH | 2274179 | LUG PCA 13462.60180762 UG
Fishel | 2020 | 2020 | LUG - TBD14 | PRE-09361.44 | PRE-09361.44 | LUG PCA 13462.91407512 | LUG PCA 13462.91407512 | 13462 | ALEXANDER ROAD | Lateral Hardening-Fuse-91407512 | Lateral Hardening-Fuse-91407512 | PCA | 0.28106 | 24 | 81 | 2020-11-01 | 2021-02-01 | 2021-03-01 | 4500272910 | N/A | N/A |  | CKT: 13462 - 91407512 | CKT: 13462 - 91407512 | 2274180 | LUG PCA 13462.91407512 OH | 2274183 | LUG PCA 13462.91407512 UG | 2274180 | LUG PCA 13462.91407512 OH | 2274183 | LUG PCA 13462.91407512 UG
Fishel | 2020 | 2020 | LUG - TBD15 | PRE-09361.1 | PRE-09361.45 | DNU LUG PCA 13390.10643541 | LUG PCA 13390.92599119 | 13390 | KIRKLAND ROAD | DNU Lateral Hardening-Fuse-10643541 | Lateral Hardening-Fuse-92599119 | PCA | 1.1722 | 67 | 221 | 2020-09-01 | 2021-03-01 | 2021-06-01 | 4500272910 | N/A | N/A | LUG C035 | DNU CKT: 13390 - 10643541 | CKT: 13390 - 92599119 | 2274185 | DNU LUG PCA 13390.10643541 OH | 2274186 | DNU LUG PCA 13390.10643541 UG | 2271216 | LUG PCA 13390.92599119 OH | 2271217 | LUG PCA 13390.92599119 UG | Combined with PRE-09361.1 (FID 92599119)
Fishel | 2020 | 2020 | LUG - TBD16 | PRE-09361.46 | PRE-09361.46 | LUG PCA 13120.60015632 | LUG PCA 13120.60015632 | 13120 | ALEXANDER ROAD | Lateral Hardening-Fuse-60015632 | Lateral Hardening-Fuse-60015632 | PCA | 0.20303 | 14 | 135 | 2020-12-01 | 2021-04-01 | 2021-06-01 | 4500272910 | N/A | N/A |  | CKT: 13120 - 60015632 | CKT: 13120 - 60015632 | 2274187 | LUG PCA 13120.60015632 OH | 2274188 | LUG PCA 13120.60015632 UG | 2274187 | LUG PCA 13120.60015632 OH | 2274188 | LUG PCA 13120.60015632 UG
Fishel | 2020 | 2020 | LUG - TBD17 | PRE-09361.47 | PRE-09361.47 | LUG PCA 13785.92466250 | LUG PCA 13785.92466250 | 13785 | PINECREST | Lateral Hardening-Fuse-92466250 | Lateral Hardening-Fuse-92466250 | PCA | 0.72008 | 31 | 72 | 2020-10-01 | 2021-04-01 | 2021-06-01 | 4500272910 | N/A | N/A | LUG C034 | CKT: 13785 - 92466250 | CKT: 13785 - 92466250 | 2274189 | LUG PCA 13785.92466250 OH | 2274190 | LUG PCA 13785.92466250 UG | 2274189 | LUG PCA 13785.92466250 OH | 2274190 | LUG PCA 13785.92466250 UG | Combined with PRE-09361.10 (FID 10676209), PRE-09361.42 (FID 93159006) & LUG TBD18 (FID 90239166)
Leidos | 2021 | 2021 | LUG - TBD415 | PRE-09361.443 | PRE-09361.443 | LUG ESA 13906.92282884 | LUG ESA 13906.92282884 | 13906 | PEACH AVENUE | Lateral Hardening-Fuse-92282884 | Lateral Hardening-Fuse-92282884 | ESA | 0.095455 | 7 | 26 | 2021-05-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13906 - 92282884 | CKT: 13906 - 92282884 | 2309884 | LUG ESA 13906.92282884 OH | 2309885 | LUG ESA 13906.92282884 UG | 2309884 | LUG ESA 13906.92282884 OH | 2309885 | LUG ESA 13906.92282884 UG
Leidos | 2021 | 2021 | LUG - TBD416 | PRE-09361.444 | PRE-09361.444 | LUG ESA 13911.60157737 | LUG ESA 13911.60157737 | 13911 | PEACH AVENUE | Lateral Hardening-Fuse-60157737 | Lateral Hardening-Fuse-60157737 | ESA | 0.65909 | 48 | 747 | 2021-05-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C028 | CKT: 13911 - 60157737 | CKT: 13911 - 60157737 | 2309886 | LUG ESA 13911.60157737 OH | 2309887 | LUG ESA 13911.60157737 UG | 2309886 | LUG ESA 13911.60157737 OH | 2309887 | LUG ESA 13911.60157737 UG | Combined with LUG-TBD424 (FID 91276385), LUG-TBD435 (FID 91556649) & LUG-TBD449 (FID 91665193)
Leidos | 2021 | 2021 | LUG - TBD417 | PRE-09361.445 | PRE-09361.445 | LUG ESA 13710.92354144 | LUG ESA 13710.92354144 | 13710 | BUCKHORN | Lateral Hardening-Fuse-92354144 | Lateral Hardening-Fuse-92354144 | ESA | 0.28371 | 30 | 229 | 2021-06-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13710 - 92354144 | CKT: 13710 - 92354144 | 2309888 | LUG ESA 13710.92354144 OH | 2309889 | LUG ESA 13710.92354144 UG | 2309888 | LUG ESA 13710.92354144 OH | 2309889 | LUG ESA 13710.92354144 UG
Leidos | 2021 | 2021 | LUG - TBD418 | PRE-09361.446 | PRE-09361.446 | LUG ESA 13793.92685255 | LUG ESA 13793.92685255 | 13793 | SAINT CLOUD | Lateral Hardening-Fuse-92685255 | Lateral Hardening-Fuse-92685255 | ESA | 0.18996 | 6 | 26 | 2021-06-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13793 - 92685255 | CKT: 13793 - 92685255 | 2309890 | LUG ESA 13793.92685255 OH | 2309891 | LUG ESA 13793.92685255 UG | 2309890 | LUG ESA 13793.92685255 OH | 2309891 | LUG ESA 13793.92685255 UG
Leidos | 2021 | 2021 | LUG - TBD419 | PRE-09361.447 | PRE-09361.447 | LUG ESA 13906.10096960 | LUG ESA 13906.10096960 | 13906 | PEACH AVENUE | Lateral Hardening-Fuse-10096960 | Lateral Hardening-Fuse-10096960 | ESA | 0.37689 | 26 | 56 | 2021-06-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13906 - 10096960 | CKT: 13906 - 10096960 | 2309892 | LUG ESA 13906.10096960 OH | 2309893 | LUG ESA 13906.10096960 UG | 2309892 | LUG ESA 13906.10096960 OH | 2309893 | LUG ESA 13906.10096960 UG
Leidos | 2021 | 2021 | LUG - TBD420 | PRE-09361.448 | PRE-09361.448 | LUG ESA 13793.92686002 | LUG ESA 13793.92686002 | 13793 | SAINT CLOUD | Lateral Hardening-Fuse-92686002 | Lateral Hardening-Fuse-92686002 | ESA | 0.22879 | 17 | 1 | 2021-06-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13793 - 92686002 | CKT: 13793 - 92686002 | 2309894 | LUG ESA 13793.92686002 OH | 2309895 | LUG ESA 13793.92686002 UG | 2309894 | LUG ESA 13793.92686002 OH | 2309895 | LUG ESA 13793.92686002 UG
Leidos | 2021 | 2021 | LUG - TBD421 | PRE-09361.449 | PRE-09361.449 | LUG ESA 13686.93697046 | LUG ESA 13686.93697046 | 13686 | PEARSON ROAD | Lateral Hardening-Fuse-93697046 | Lateral Hardening-Fuse-93697046 | ESA | 0.40322 | 32 | 29 | 2021-06-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13686 - 93697046 | CKT: 13686 - 93697046 | 2309896 | LUG ESA 13686.93697046 OH | 2309897 | LUG ESA 13686.93697046 UG | 2309896 | LUG ESA 13686.93697046 OH | 2309897 | LUG ESA 13686.93697046 UG | Incorrectly labeled as FID 10840113 initially
Leidos | 2021 | 2021 | LUG - TBD422 | PRE-09361.450 | PRE-09361.450 | LUG ESA 13906.10096964 | LUG ESA 13906.10096964 | 13906 | PEACH AVENUE | Lateral Hardening-Fuse-10096964 | Lateral Hardening-Fuse-10096964 | ESA | 0.6767 | 40 | 31 | 2021-06-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13906 - 10096964 | CKT: 13906 - 10096964 | 2309898 | LUG ESA 13906.10096964 OH | 2309899 | LUG ESA 13906.10096964 UG | 2309898 | LUG ESA 13906.10096964 OH | 2309899 | LUG ESA 13906.10096964 UG
Leidos | 2021 | 2021 | LUG - TBD423 | PRE-09361.451 | PRE-09361.451 | LUG ESA 13911.90130568 | LUG ESA 13911.90130568 | 13911 | PEACH AVENUE | Lateral Hardening-Fuse-90130568 | Lateral Hardening-Fuse-90130568 | ESA | 0.85871 | 53 | 108 | 2021-06-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C027 | CKT: 13911 - 90130568 | CKT: 13911 - 90130568 | 2309900 | LUG ESA 13911.90130568 OH | 2309902 | LUG ESA 13911.90130568 UG | 2309900 | LUG ESA 13911.90130568 OH | 2309902 | LUG ESA 13911.90130568 UG | Combined with LUG-TBD433 (FID 10554588)
Leidos | 2021 | 2021 | LUG - TBD424 | PRE-09361.444 | PRE-09361.444 | DNU LUG ESA 13911.91276385 | LUG ESA 13911.60157737 | 13911 | PEACH AVENUE | DNU Lateral Hardening-Fuse-91276385 | Lateral Hardening-Fuse-60157737 | ESA | 0.50284 | 45 | 253 | 2021-07-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C028 | N/A | CKT: 13911 - 60157737 | N/A | N/A | N/A | N/A | 2309886 | LUG ESA 13911.60157737 OH | 2309887 | LUG ESA 13911.60157737 UG | Combined with LUG-TBD416 (FID 60157737),LUG-TBD435 (FID 91556649) & LUG-TBD449 (FID 91665193)
Leidos | 2021 | 2021 | LUG - TBD425 | PRE-09361.452 | PRE-09361.452 | LUG ESA 13906.90137810 | LUG ESA 13906.90137810 | 13906 | PEACH AVENUE | Lateral Hardening-Fuse-90137810 | Lateral Hardening-Fuse-90137810 | ESA | 0.80322 | 53 | 62 | 2021-07-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13906 - 90137810 | CKT: 13906 - 90137810 | 2309903 | LUG ESA 13906.90137810 OH | 2309904 | LUG ESA 13906.90137810 UG | 2309903 | LUG ESA 13906.90137810 OH | 2309904 | LUG ESA 13906.90137810 UG
Leidos | 2021 | 2021 | LUG - TBD426 | PRE-09361.453 | PRE-09361.453 | LUG ESA 13793.92686712 | LUG ESA 13793.92686712 | 13793 | SAINT CLOUD | Lateral Hardening-Fuse-92686712 | Lateral Hardening-Fuse-92686712 | ESA | 0.044318 | 4 | 85 | 2021-07-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13793 - 92686712 | CKT: 13793 - 92686712 | 2309905 | LUG ESA 13793.92686712 OH | 2309906 | LUG ESA 13793.92686712 UG | 2309905 | LUG ESA 13793.92686712 OH | 2309906 | LUG ESA 13793.92686712 UG
Leidos | 2021 | 2021 | LUG - TBD427 | PRE-09361.454 | PRE-09361.454 | LUG ESA 13127.92663180 | LUG ESA 13127.92663180 | 13127 | SOUTH SEFFNER | Lateral Hardening-Fuse-92663180 | Lateral Hardening-Fuse-92663180 | ESA | 0.61761 | 42 | 33 | 2021-07-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C026 | CKT: 13127 - 92663180 | CKT: 13127 - 92663180 | 2309907 | LUG ESA 13127.92663180 OH | 2309908 | LUG ESA 13127.92663180 UG | 2309907 | LUG ESA 13127.92663180 OH | 2309908 | LUG ESA 13127.92663180 UG | Combined with LUG-TBD414 (FID 10836901)
Leidos | 2021 | 2021 | LUG - TBD428 | PRE-09361.455 | PRE-09361.455 | DNU LUG ESA 13457.90291488 | LUG ESA 13457.90176591 | 13457 | LAKEWOOD | DNU Lateral Hardening-Fuse-90291488 | Lateral Hardening-Fuse-90176591 | ESA | 0.10871 | 12 | 188 | 2021-07-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C029 | N/A | CKT: 13457 - 90176591 | N/A | N/A | N/A | N/A | 2309909 | LUG ESA 13457.90176591 OH | 2309910 | LUG ESA 13457.90176591 UG | Combined with LUG-TBD432 (FID 90176591)
Leidos | 2021 | 2021 | LUG - TBD429 | PRE-09361.459 | PRE-09361.459 | DNU LUG ESA 13911.10544635 | LUG ESA 13911.91995336 | 13911 | PEACH AVENUE | DNU Lateral Hardening-Fuse-10544635 | Lateral Hardening-Fuse-91995336 | ESA | 0.2267 | 14 | 136 | 2021-07-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C030 | N/A | CKT: 13911 - 91995336 | N/A | N/A | N/A | N/A | 2309919 | LUG ESA 13911.91995336 OH | 2309920 | LUG ESA 13911.91995336 UG | Combined with LUG-TBD430 (FID 10544633), LUG-TBD431 (FID 92018843) & LUG-TBD438 (FID 91995336)
Leidos | 2021 | 2021 | LUG - TBD430 | PRE-09361.459 | PRE-09361.459 | DNU LUG ESA 13911.10544633 | LUG ESA 13911.91995336 | 13911 | PEACH AVENUE | DNU Lateral Hardening-Fuse-10544633 | Lateral Hardening-Fuse-91995336 | ESA | 0.17917 | 12 | 20 | 2021-08-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C030 | N/A | CKT: 13911 - 91995336 | N/A | N/A | N/A | N/A | 2309919 | LUG ESA 13911.91995336 OH | 2309920 | LUG ESA 13911.91995336 UG | Combined with LUG-TBD429 (FID 10544635), LUG-TBD431 (FID 92018843) & LUG-TBD438 (FID 91995336)
Leidos | 2021 | 2021 | LUG - TBD431 | PRE-09361.459 | PRE-09361.459 | DNU LUG ESA 13911.92018843 | LUG ESA 13911.91995336 | 13911 | PEACH AVENUE | DNU Lateral Hardening-Fuse-92018843 | Lateral Hardening-Fuse-91995336 | ESA | 0.12216 | 6 | 14 | 2021-08-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C030 | N/A | CKT: 13911 - 91995336 | N/A | N/A | N/A | N/A | 2309919 | LUG ESA 13911.91995336 OH | 2309920 | LUG ESA 13911.91995336 UG | Combined with LUG-TBD429 (FID 10544635), LUG-TBD430 (FID 10544633) & LUG-TBD438 (FID 91995336)
Leidos | 2021 | 2021 | LUG - TBD432 | PRE-09361.455 | PRE-09361.455 | LUG ESA 13457.90176591 | LUG ESA 13457.90176591 | 13457 | LAKEWOOD | Lateral Hardening-Fuse-90176591 | Lateral Hardening-Fuse-90176591 | ESA | 0.31136 | 18 | 155 | 2021-08-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C029 | CKT: 13457 - 90176591 | CKT: 13457 - 90176591 | 2309909 | LUG ESA 13457.90176591 OH | 2309910 | LUG ESA 13457.90176591 UG | 2309909 | LUG ESA 13457.90176591 OH | 2309910 | LUG ESA 13457.90176591 UG | Combined with LUG-TBD428 (FID 90291488)
Leidos | 2021 | 2021 | LUG - TBD433 | PRE-09361.451 | PRE-09361.451 | DNU LUG ESA 13911.10554588 | LUG ESA 13911.90130568 | 13911 | PEACH AVENUE | DNU Lateral Hardening-Fuse-10554588 | Lateral Hardening-Fuse-90130568 | ESA | 0.40208 | 29 | 33 | 2021-08-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C027 | N/A | CKT: 13911 - 90130568 | N/A | N/A | N/A | N/A | 2309900 | LUG ESA 13911.90130568 OH | 2309902 | LUG ESA 13911.90130568 UG | Combined with LUG-TBD423 (FID 90130568)
Leidos | 2021 | 2021 | LUG - TBD434 | PRE-09361.456 | PRE-09361.456 | LUG ESA 14355.92354352 | LUG ESA 14355.92354352 | 14355 | CAUSEWAY | Lateral Hardening-Fuse-92354352 | Lateral Hardening-Fuse-92354352 | ESA | 0.31856 | 22 | 51 | 2021-08-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 14355 - 92354352 | CKT: 14355 - 92354352 | 2309911 | LUG ESA 14355.92354352 OH | 2309912 | LUG ESA 14355.92354352 UG | 2309911 | LUG ESA 14355.92354352 OH | 2309912 | LUG ESA 14355.92354352 UG
Leidos | 2021 | 2021 | LUG - TBD435 | PRE-09361.444 | PRE-09361.444 | DNU LUG ESA 13911.91556649 | LUG ESA 13911.60157737 | 13911 | PEACH AVENUE | DNU Lateral Hardening-Fuse-91556649 | Lateral Hardening-Fuse-60157737 | ESA | 0.50739 | 37 | 251 | 2021-08-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C028 | N/A | CKT: 13911 - 60157737 | N/A | N/A | N/A | N/A | 2309886 | LUG ESA 13911.60157737 OH | 2309887 | LUG ESA 13911.60157737 UG | Combined with LUG-TBD416 (FID 60157737), LUG-TBD424 (FID 91276385) & LUG-TBD449 (FID 91665193)
Leidos | 2021 | 2021 | LUG - TBD436 | PRE-09361.457 | PRE-09361.457 | LUG ESA 13793.92686736 | LUG ESA 13793.92686736 | 13793 | SAINT CLOUD | Lateral Hardening-Fuse-92686736 | Lateral Hardening-Fuse-92686736 | ESA | 0.032197 | 4 | 85 | 2021-08-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13793 - 92686736 | CKT: 13793 - 92686736 | 2309914 | LUG ESA 13793.92686736 OH | 2309915 | LUG ESA 13793.92686736 UG | 2309914 | LUG ESA 13793.92686736 OH | 2309915 | LUG ESA 13793.92686736 UG
Leidos | 2021 | 2021 | LUG - TBD437 | PRE-09361.458 | PRE-09361.458 | LUG ESA 13911.10554595 | LUG ESA 13911.10554595 | 13911 | PEACH AVENUE | Lateral Hardening-Fuse-10554595 | Lateral Hardening-Fuse-10554595 | ESA | 0.1303 | 16 | 4 | 2021-08-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13911 - 10554595 | CKT: 13911 - 10554595 | 2309917 | LUG ESA 13911.10554595 OH | 2309918 | LUG ESA 13911.10554595 UG | 2309917 | LUG ESA 13911.10554595 OH | 2309918 | LUG ESA 13911.10554595 UG
Leidos | 2021 | 2021 | LUG - TBD438 | PRE-09361.459 | PRE-09361.459 | LUG ESA 13911.91995336 | LUG ESA 13911.91995336 | 13911 | PEACH AVENUE | Lateral Hardening-Fuse-91995336 | Lateral Hardening-Fuse-91995336 | ESA | 0.30095 | 19 | 93 | 2021-08-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C030 | CKT: 13911 - 91995336 | CKT: 13911 - 91995336 | 2309919 | LUG ESA 13911.91995336 OH | 2309920 | LUG ESA 13911.91995336 UG | 2309919 | LUG ESA 13911.91995336 OH | 2309920 | LUG ESA 13911.91995336 UG | Combined with LUG-TBD429 (FID 10544635), LUG-TBD430 (FID 10544633) & LUG-TBD431 (FID 92018843)
Leidos | 2021 | 2021 | LUG - TBD439 | PRE-09361.460 | PRE-09361.460 | LUG ESA 13127.92661768 | LUG ESA 13127.92661768 | 13127 | SOUTH SEFFNER | Lateral Hardening-Fuse-92661768 | Lateral Hardening-Fuse-92661768 | ESA | 0.53409 | 34 | 170 | 2021-09-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13127 - 92661768 | CKT: 13127 - 92661768 | 2309921 | LUG ESA 13127.92661768 OH | 2309922 | LUG ESA 13127.92661768 UG | 2309921 | LUG ESA 13127.92661768 OH | 2309922 | LUG ESA 13127.92661768 UG
Leidos | 2021 | 2021 | LUG - TBD440 | PRE-09361.119 | PRE-09361.119 | DNU LUG ESA 13796.92884644 | LUG ESA 13796.92884623 | 13796 | SAINT CLOUD | DNU Lateral Hardening-Fuse-92884644 | Lateral Hardening-Fuse-92884623 | ESA | 0.28542 | 16 | 16 | 2021-09-01 | 2022 | 2022 | 4500271952 | N/A | N/A | LUG C007 | N/A | CKT: 13796 - 92884623 | N/A | N/A | N/A | N/A | 2277391 | LUG ESA 13796.92884623 OH | 2277392 | LUG ESA 13796.92884623 UG | Combined with PRE-09361.119 (FID 92884623)
Leidos | 2021 | 2021 | LUG - TBD441 | PRE-09361.461 | PRE-09361.461 | LUG ESA 13878.10105726 | LUG ESA 13878.10105726 | 13878 | PROVIDENCE ROAD | Lateral Hardening-Fuse-10105726 | Lateral Hardening-Fuse-10105726 | ESA | 0.54015 | 44 | 137 | 2021-09-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13878 - 10105726 | CKT: 13878 - 10105726 | 2309923 | LUG ESA 13878.10105726 OH | 2309924 | LUG ESA 13878.10105726 UG | 2309923 | LUG ESA 13878.10105726 OH | 2309924 | LUG ESA 13878.10105726 UG
Leidos | 2021 | 2021 | LUG - TBD442 | PRE-09361.462 | PRE-09361.462 | LUG ESA 13454.90188551 | LUG ESA 13454.90188551 | 13454 | LAKEWOOD | Lateral Hardening-Fuse-90188551 | Lateral Hardening-Fuse-90188551 | ESA | 0.21004 | 13 | 37 | 2021-09-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13454 - 90188551 | CKT: 13454 - 90188551 | 2309925 | LUG ESA 13454.90188551 OH | 2309926 | LUG ESA 13454.90188551 UG | 2309925 | LUG ESA 13454.90188551 OH | 2309926 | LUG ESA 13454.90188551 UG
Leidos | 2021 | 2021 | LUG - TBD443 | PRE-09361.463 | PRE-09361.463 | LUG ESA 13878.10105717 | LUG ESA 13878.10105717 | 13878 | PROVIDENCE ROAD | Lateral Hardening-Fuse-10105717 | Lateral Hardening-Fuse-10105717 | ESA | 0.31288 | 23 | 346 | 2021-09-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13878 - 10105717 | CKT: 13878 - 10105717 | 2309928 | LUG ESA 13878.10105717 OH | 2309929 | LUG ESA 13878.10105717 UG | 2309928 | LUG ESA 13878.10105717 OH | 2309929 | LUG ESA 13878.10105717 UG
Leidos | 2021 | 2021 | LUG - TBD444 | PRE-09361.464 | PRE-09361.464 | LUG ESA 13231.10868121 | LUG ESA 13231.10868121 | 13231 | BRANDON | Lateral Hardening-Fuse-10868121 | Lateral Hardening-Fuse-10868121 | ESA | 0.27311 | 22 | 23 | 2021-11-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13231 - 10868121 | CKT: 13231 - 10868121 | 2309930 | LUG ESA 13231.10868121 OH | 2309931 | LUG ESA 13231.10868121 UG | 2309930 | LUG ESA 13231.10868121 OH | 2309931 | LUG ESA 13231.10868121 UG
Leidos | 2021 | 2021 | LUG - TBD445 | PRE-09361.465 | PRE-09361.465 | LUG ESA 13911.60157736 | LUG ESA 13911.60157736 | 13911 | PEACH AVENUE | Lateral Hardening-Fuse-60157736 | Lateral Hardening-Fuse-60157736 | ESA | 0.051894 | 5 | 62 | 2021-09-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13911 - 60157736 | CKT: 13911 - 60157736 | 2309932 | LUG ESA 13911.60157736 OH | 2309933 | LUG ESA 13911.60157736 UG | 2309932 | LUG ESA 13911.60157736 OH | 2309933 | LUG ESA 13911.60157736 UG
Leidos | 2021 | 2021 | LUG - TBD446 | PRE-09361.127 | PRE-09361.127 | DNU LUG ESA 13509.10501133 | LUG ESA 13509.10501150 | 13509 | STATE ROAD 574 | DNU Lateral Hardening-Fuse-10501133 | Lateral Hardening-Fuse-10501150 | ESA | 0.27481 | 20 | 27 | 2021-09-01 | 2022 | 2022 | 4500271952 | N/A | N/A | LUG C023 | N/A | CKT: 13509 - 10501150 | N/A | N/A | N/A | N/A | 2277415 | LUG ESA 13509.10501150 OH | 2277416 | LUG ESA 13509.10501150 UG | Combined with PRE-09361.127 (FID 10501150)
Leidos | 2021 | 2021 | LUG - TBD447 | PRE-09361.466 | PRE-09361.466 | LUG ESA 13171.10455381 | LUG ESA 13171.10455381 | 13171 | MADISON | Lateral Hardening-Fuse-10455381 | Lateral Hardening-Fuse-10455381 | ESA | 0.12462 | 11 | 5 | 2021-11-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13171 - 10455381 | CKT: 13171 - 10455381 | 2309934 | LUG ESA 13171.10455381 OH | 2309935 | LUG ESA 13171.10455381 UG | 2309934 | LUG ESA 13171.10455381 OH | 2309935 | LUG ESA 13171.10455381 UG
Leidos | 2021 | 2021 | LUG - TBD448 | PRE-09361.467 | PRE-09361.467 | LUG ESA 13878.10105728 | LUG ESA 13878.10105728 | 13878 | PROVIDENCE ROAD | Lateral Hardening-Fuse-10105728 | Lateral Hardening-Fuse-10105728 | ESA | 0.23201 | 14 | 26 | 2021-10-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13878 - 10105728 | CKT: 13878 - 10105728 | 2309936 | LUG ESA 13878.10105728 OH | 2309938 | LUG ESA 13878.10105728 UG | 2309936 | LUG ESA 13878.10105728 OH | 2309938 | LUG ESA 13878.10105728 UG
Leidos | 2021 | 2021 | LUG - TBD449 | PRE-09361.444 | PRE-09361.444 | DNU LUG ESA 13911.91665193 | LUG ESA 13911.60157737 | 13911 | PEACH AVENUE | DNU Lateral Hardening-Fuse-91665193 | Lateral Hardening-Fuse-60157737 | ESA | 0.49034 | 32 | 179 | 2021-10-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C028 | N/A | CKT: 13911 - 60157737 | N/A | N/A | N/A | N/A | 2309886 | LUG ESA 13911.60157737 OH | 2309887 | LUG ESA 13911.60157737 UG | Combined with LUG-TBD416 (FID 60157737), LUG-TBD424 (FID 91276385) & LUG-TBD435 (FID 91556649)
Leidos | 2021 | 2021 | LUG - TBD450 | PRE-09361.474 | PRE-09361.474 | DNU LUG SHA 13003.10895225 | LUG SHA 13003.10895211 | 13003 | RUSKIN | DNU Lateral Hardening-Fuse-10895225 | Lateral Hardening-Fuse-10895211 | SHA | 0.66477 | 34 | 198 | 2021-11-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C031 | N/A | CKT: 13003 - 10895211 | N/A | N/A | N/A | N/A | 2309951 | LUG SHA 13003.10895211 OH | 2309952 | LUG SHA 13003.10895211 UG | Combined with LUG-TBD457 (FID 10895211)
Leidos | 2021 | 2021 | LUG - TBD451 | PRE-09361.468 | PRE-09361.468 | LUG SHA 14024.10747874 | LUG SHA 14024.10747874 | 14024 | RIVERVIEW | Lateral Hardening-Fuse-10747874 | Lateral Hardening-Fuse-10747874 | SHA | 0.15057 | 13 | 135 | 2021-11-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 14024 - 10747874 | CKT: 14024 - 10747874 | 2309939 | LUG SHA 14024.10747874 OH | 2309940 | LUG SHA 14024.10747874 UG | 2309939 | LUG SHA 14024.10747874 OH | 2309940 | LUG SHA 14024.10747874 UG
Leidos | 2021 | 2021 | LUG - TBD452 | PRE-09361.469 | PRE-09361.469 | LUG SHA 13342.91010293 | LUG SHA 13342.91010293 | 13342 | EAST BAY | Lateral Hardening-Fuse-91010293 | Lateral Hardening-Fuse-91010293 | SHA | 0.35966 | 27 | 190 | 2021-11-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13342 - 91010293 | CKT: 13342 - 91010293 | 2309941 | LUG SHA 13342.91010293 OH | 2309942 | LUG SHA 13342.91010293 UG | 2309941 | LUG SHA 13342.91010293 OH | 2309942 | LUG SHA 13342.91010293 UG
Leidos | 2021 | 2021 | LUG - TBD453 | PRE-09361.470 | PRE-09361.470 | LUG SHA 14020.60223573 | LUG SHA 14020.60223573 | 14020 | RIVERVIEW | Lateral Hardening-Fuse-60223573 | Lateral Hardening-Fuse-60223573 | SHA | 0.48087 | 45 | 415 | 2021-11-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 14020 - 60223573 | CKT: 14020 - 60223573 | 2309943 | LUG SHA 14020.60223573 OH | 2309944 | LUG SHA 14020.60223573 UG | 2309943 | LUG SHA 14020.60223573 OH | 2309944 | LUG SHA 14020.60223573 UG
Leidos | 2021 | 2021 | LUG - TBD454 | PRE-09361.471 | PRE-09361.471 | LUG SHA 13342.10925094 | LUG SHA 13342.10925094 | 13342 | EAST BAY | Lateral Hardening-Fuse-10925094 | Lateral Hardening-Fuse-10925094 | SHA | 0.32689 | 22 | 45 | 2021-11-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13342 - 10925094 | CKT: 13342 - 10925094 | 2309945 | LUG SHA 13342.10925094 OH | 2309946 | LUG SHA 13342.10925094 UG | 2309945 | LUG SHA 13342.10925094 OH | 2309946 | LUG SHA 13342.10925094 UG
Leidos | 2021 | 2021 | LUG - TBD455 | PRE-09361.472 | PRE-09361.472 | LUG SHA 14024.90116190 | LUG SHA 14024.90116190 | 14024 | RIVERVIEW | Lateral Hardening-Fuse-90116190 | Lateral Hardening-Fuse-90116190 | SHA | 0.1267 | 11 | 12 | 2021-11-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 14024 - 90116190 | CKT: 14024 - 90116190 | 2309947 | LUG SHA 14024.90116190 OH | 2309948 | LUG SHA 14024.90116190 UG | 2309947 | LUG SHA 14024.90116190 OH | 2309948 | LUG SHA 14024.90116190 UG
Leidos | 2021 | 2021 | LUG - TBD456 | PRE-09361.473 | PRE-09361.473 | LUG SHA 13817.10722417 | LUG SHA 13817.10722417 | 13817 | RUSKIN | Lateral Hardening-Fuse-10722417 | Lateral Hardening-Fuse-10722417 | SHA | 1.7845 | 123 | 570 | 2021-10-01 | 2022 | 2022 | N/A | 4500283885 | N/A |  | CKT: 13817 - 10722417 | CKT: 13817 - 10722417 | 2309949 | LUG SHA 13817.10722417 OH | 2309950 | LUG SHA 13817.10722417 UG | 2309949 | LUG SHA 13817.10722417 OH | 2309950 | LUG SHA 13817.10722417 UG
Leidos | 2021 | 2021 | LUG - TBD457 | PRE-09361.474 | PRE-09361.474 | LUG SHA 13003.10895211 | LUG SHA 13003.10895211 | 13003 | RUSKIN | Lateral Hardening-Fuse-10895211 | Lateral Hardening-Fuse-10895211 | SHA | 2.4676 | 116 | 179 | 2021-04-01 | 2022 | 2022 | N/A | 4500283885 | N/A | LUG C031 | CKT: 13003 - 10895211 | CKT: 13003 - 10895211 | 2309951 | LUG SHA 13003.10895211 OH | 2309952 | LUG SHA 13003.10895211 UG | 2309951 | LUG SHA 13003.10895211 OH | 2309952 | LUG SHA 13003.10895211 UG | Combined with LUG-TBD450 (FID 10895225)
Leidos | 2021 | 2021 | LUG - TBD458 | PRE-09361.475 | PRE-09361.475 | LUG SHA 13342.90527363 | LUG SHA 13342.90527363 | 13342 | EAST BAY | Lateral Hardening-Fuse-90527363 | Lateral Hardening-Fuse-90527363 | SHA | 0.15606 | 10 | 29 | 2021-07-01 |  |  | N/A | 4500283885 | N/A |  | CKT: 13342 - 90527363 | CKT: 13342 - 90527363 | 2309954 | LUG SHA 13342.90527363 OH | 2309955 | LUG SHA 13342.90527363 UG | 2309954 | LUG SHA 13342.90527363 OH | 2309955 | LUG SHA 13342.90527363 UG
Pike | 2020 | 2020 | LUG - TBD130 | PRE-09361.21 | PRE-09361.21 | LUG CSA 14040.10786382 | LUG CSA 14040.10786382 | 14040 | HARNEY ROAD | Lateral Hardening-Fuse-10786382 | Lateral Hardening-Fuse-10786382 | CSA | 0.23409 | 13 | 98 | 2020-06-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A |  | CKT: 14040 - 10786382 | CKT: 14040 - 10786382 | 2271067 | LUG CSA 14040.10786382 OH | 2271080 | LUG CSA 14040.10786382 UG | 2271067 | LUG CSA 14040.10786382 OH | 2271080 | LUG CSA 14040.10786382 UG
Pike | 2020 | 2020 | LUG - TBD131 | PRE-09361.22 | PRE-09361.22 | LUG CSA 13840.93019714 | LUG CSA 13840.93019714 | 13840 | FLORIDA AVENUE | Lateral Hardening-Fuse-93019714 | Lateral Hardening-Fuse-93019714 | CSA | 0.13371 | 9 | 39 | 2020-06-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A |  | CKT: 13840 - 93019714 | CKT: 13840 - 93019714 | 2271581 | LUG CSA 13840.93019714 OH | 2271592 | LUG CSA 13840.93019714 UG | 2271581 | LUG CSA 13840.93019714 OH | 2271592 | LUG CSA 13840.93019714 UG
Pike | 2020 | 2020 | LUG - TBD132 | PRE-09361.23 | PRE-09361.23 | LUG CSA 14040.10786374 | LUG CSA 14040.10786374 | 14040 | HARNEY ROAD | Lateral Hardening-Fuse-10786374 | Lateral Hardening-Fuse-10786374 | CSA | 0.27254 | 16 | 205 | 2020-06-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A | LUG C012 | CKT: 14040 - 10786374 | CKT: 14040 - 10786374 | 2271630 | LUG CSA 14040.10786374 OH | 2271645 | LUG CSA 14040.10786374 UG | 2271630 | LUG CSA 14040.10786374 OH | 2271645 | LUG CSA 14040.10786374 UG | Combined with LUG - TBD226 (FID 90485522)
Pike | 2020 | 2020 | LUG - TBD133 | PRE-09361.84 | PRE-09361.24 | DNU LUG CSA 13836.91406672 | LUG CSA 13836.91377944 | 13836 | FLORIDA AVENUE | DNU Lateral Hardening-Fuse-91406672 | Lateral Hardening-Fuse-91377944 | CSA | 0.34621 | 25 | 91 | 2020-06-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A | LUG C013 | DNU CKT: 13836 - 91406672 | CKT: 13836 - 91377944 | 2274929 | DNU LUG CSA 13836.91406672 OH | 2274966 | DNU LUG CSA 13836.91406672 UG | 2275133 | LUG CSA 13836.91377944 OH | 2275134 | LUG CSA 13836.91377944 UG | Combined with PRE-09361.84 (FID 91377944) and other 2021 projects
Pike | 2020 | 2020 | LUG - TBD134 | PRE-09361.27 | PRE-09361.25 | DNU LUG DCA 13815.92407065 | LUG DCA 13815.93026469 | 13815 | BLANTON | DNU Lateral Hardening-Fuse-92407065 | Lateral Hardening-Fuse-93026469 | DCA | 0.37557 | 15 | 12 | 2020-07-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A | LUG C011 | DNU CKT: 13815 - 92407065 | CKT: 13815 - 93026469 | 2274969 | DNU LUG DCA 13815.92407065 OH | 2274971 | DNU LUG DCA 13815.92407065 UG | 2274978 | LUG DCA 13815.93026469 OH | 2274982 | LUG DCA 13815.93026469 UG | Combined with PRE-09361.26 (FID 90288627) and PRE-09361.27 (FID 93026469)
Pike | 2020 | 2020 | LUG - TBD135 | PRE-09361.27 | PRE-09361.26 | DNU LUG DCA 13815.90288627 | LUG DCA 13815.93026469 | 13815 | BLANTON | DNU Lateral Hardening-Fuse-90288627 | Lateral Hardening-Fuse-93026469 | DCA | 0.88144 | 32 | 51 | 2020-07-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A | LUG C011 | DNU CKT: 13815 - 90288627 | CKT: 13815 - 93026469 | 2274973 | DNU LUG DCA 13815.90288627 OH | 2274976 | DNU LUG DCA 13815.90288627 UG | 2274978 | LUG DCA 13815.93026469 OH | 2274982 | LUG DCA 13815.93026469 UG | Combined with PRE-09361.25 (FID 92407065) and PRE-09361.27 (FID 93026469)
Pike | 2020 | 2020 | LUG - TBD136 | PRE-09361.27 | PRE-09361.27 | LUG DCA 13815.93026469 | LUG DCA 13815.93026469 | 13815 | BLANTON | Lateral Hardening-Fuse-93026469 | Lateral Hardening-Fuse-93026469 | DCA | 0.49489 | 15 | 27 | 2020-07-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A | LUG C011 | CKT: 13815 - 93026469 | CKT: 13815 - 93026469 | 2274978 | LUG DCA 13815.93026469 OH | 2274982 | LUG DCA 13815.93026469 UG | 2274978 | LUG DCA 13815.93026469 OH | 2274982 | LUG DCA 13815.93026469 UG | Combined with PRE-09361.25 (FID 92407065) and PRE-09361.26 (FID 90288627)
Pike | 2020 | 2020 | LUG - TBD137 | PRE-09361.28 | PRE-09361.28 | LUG CSA 13183.60036344 | LUG CSA 13183.60036344 | 13183 | ELEVENTH AVENUE | Lateral Hardening-Fuse-60036344 | Lateral Hardening-Fuse-60036344 | CSA | 0.094318 | 13 | 22 | 2020-07-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A |  | CKT: 13183 - 60036344 | CKT: 13183 - 60036344 | 2274984 | LUG CSA 13183.60036344 OH | 2274985 | LUG CSA 13183.60036344 UG | 2274984 | LUG CSA 13183.60036344 OH | 2274985 | LUG CSA 13183.60036344 UG
Pike | 2020 | 2020 | LUG - TBD138 | PRE-09361.81 | PRE-09361.29 | DNU LUG CSA 13205.60059346 | LUG CSA 13205.90998414 | 13205 | TEMPLE TERRACE | DNU Lateral Hardening-Fuse-60059346 | Lateral Hardening-Fuse-90998414 | CSA | 0.17462 | 18 | 216 | 2020-08-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A | LUG C010 | DNU CKT: 13205 - 60059346 | CKT: 13205 - 90998414 | 2274986 | DNU LUG CSA 13205.60059346 OH | 2274989 | DNU LUG CSA 13205.60059346 UG | 2275124 | LUG CSA 13205.90998414 OH | 2275125 | LUG CSA 13205.90998414 UG | Combined with PRE-09361.81 (FID 90998414)
Pike | 2020 | 2020 | LUG - TBD139 | PRE-09361.30 | PRE-09361.30 | LUG CSA 13934.10467606 | LUG CSA 13934.10467606 | 13934 | LAKE MAGDALENE | Lateral Hardening-Fuse-10467606 | Lateral Hardening-Fuse-10467606 | CSA | 0.30852 | 16 | 199 | 2020-08-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A |  | CKT: 13934 - 10467606 | CKT: 13934 - 10467606 | 2274993 | LUG CSA 13934.10467606 OH | 2274994 | LUG CSA 13934.10467606 UG | 2274993 | LUG CSA 13934.10467606 OH | 2274994 | LUG CSA 13934.10467606 UG
Pike | 2020 | 2020 | LUG - TBD140 | PRE-09361.75 | PRE-09361.75 | LUG CSA 13633.92740152 | LUG CSA 13633.92740152 | 13633 | PINE LAKE | Lateral Hardening-Fuse-92740152 | Lateral Hardening-Fuse-92740152 | CSA | 0.27973 | 23 | 52 | 2020-08-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A |  | CKT: 13633 - 92740152 | CKT: 13633 - 92740152 | 2274995 | LUG CSA 13633.92740152 OH | 2274996 | LUG CSA 13633.92740152 UG | 2274995 | LUG CSA 13633.92740152 OH | 2274996 | LUG CSA 13633.92740152 UG
Pike | 2020 | 2020 | LUG - TBD141 | PRE-09361.76 | PRE-09361.76 | LUG CSA 13592.10402239 | LUG CSA 13592.10402239 | 13592 | SENECA STREET | Lateral Hardening-Fuse-10402239 | Lateral Hardening-Fuse-10402239 | CSA | 0.16477 | 15 | 57 | 2020-08-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A |  | CKT: 13592 - 10402239 | CKT: 13592 - 10402239 | 2275090 | LUG CSA 13592.10402239 OH | 2275091 | LUG CSA 13592.10402239 UG | 2275090 | LUG CSA 13592.10402239 OH | 2275091 | LUG CSA 13592.10402239 UG
Pike | 2020 | 2020 | LUG - TBD142 | PRE-09361.77 | PRE-09361.77 | LUG CSA 13351.93283733 | LUG CSA 13351.93283733 | 13351 | TWENTY SEVENTH STREET | Lateral Hardening-Fuse-93283733 | Lateral Hardening-Fuse-93283733 | CSA | 0.17841 | 15 | 66 | 2020-08-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A |  | CKT: 13351 - 93283733 | CKT: 13351 - 93283733 | 2275110 | LUG CSA 13351.93283733 OH | 2275114 | LUG CSA 13351.93283733 UG | 2275110 | LUG CSA 13351.93283733 OH | 2275114 | LUG CSA 13351.93283733 UG
Pike | 2020 | 2020 | LUG - TBD143 | PRE-09361.78 | PRE-09361.78 | LUG CSA 13099.90882614 | LUG CSA 13099.90882614 | 13099 | SUNSET LANE | Lateral Hardening-Fuse-90882614 | Lateral Hardening-Fuse-90882614 | CSA | 0.23731 | 18 | 128 | 2020-09-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A | LUG C008 | CKT: 13099 - 90882614 | CKT: 13099 - 90882614 | 2275116 | LUG CSA 13099.90882614 OH | 2275117 | LUG CSA 13099.90882614 UG | 2275116 | LUG CSA 13099.90882614 OH | 2275117 | LUG CSA 13099.90882614 UG | Combined with LUG-TBD172 (FID 60563698)
Pike | 2020 | 2020 | LUG - TBD144 | PRE-09361.79 | PRE-09361.79 | LUG CSA 13093.91004837 | LUG CSA 13093.91004837 | 13093 | PLYMOUTH STREET | Lateral Hardening-Fuse-91004837 | Lateral Hardening-Fuse-91004837 | CSA | 0.18504 | 17 | 143 | 2020-09-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A | LUG C009 | CKT: 13093 - 91004837 | CKT: 13093 - 91004837 | 2275118 | LUG CSA 13093.91004837 OH | 2275120 | LUG CSA 13093.91004837 UG | 2275118 | LUG CSA 13093.91004837 OH | 2275120 | LUG CSA 13093.91004837 UG | Combined with PRE-09361.83 (FID 91004843) & LUG-TBD245 (FID 60029740)
Pike | 2020 | 2020 | LUG - TBD145 | PRE-09361.80 | PRE-09361.80 | LUG CSA 13630.10429536 | LUG CSA 13630.10429536 | 13630 | PINE LAKE | Lateral Hardening-Fuse-10429536 | Lateral Hardening-Fuse-10429536 | CSA | 0.082008 | 9 | 59 | 2020-09-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A |  | CKT: 13630 - 10429536 | CKT: 13630 - 10429536 | 2275122 | LUG CSA 13630.10429536 OH | 2275123 | LUG CSA 13630.10429536 UG | 2275122 | LUG CSA 13630.10429536 OH | 2275123 | LUG CSA 13630.10429536 UG
Pike | 2020 | 2020 | LUG - TBD146 | PRE-09361.81 | PRE-09361.81 | LUG CSA 13205.90998414 | LUG CSA 13205.90998414 | 13205 | TEMPLE TERRACE | Lateral Hardening-Fuse-90998414 | Lateral Hardening-Fuse-90998414 | CSA | 0.083902 | 12 | 212 | 2020-09-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A | LUG C010 | CKT: 13205 - 90998414 | CKT: 13205 - 90998414 | 2275124 | LUG CSA 13205.90998414 OH | 2275125 | LUG CSA 13205.90998414 UG | 2275124 | LUG CSA 13205.90998414 OH | 2275125 | LUG CSA 13205.90998414 UG | Combined with PRE-09361.29 )FID 60059346)
Pike | 2020 | 2020 | LUG - TBD147 | PRE-09361.82 | PRE-09361.82 | LUG CSA 13948.91837409 | LUG CSA 13948.91837409 | 13948 | YUKON | Lateral Hardening-Fuse-91837409 | Lateral Hardening-Fuse-91837409 | CSA | 0.14451 | 13 | 68 | 2020-09-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A |  | CKT: 13948 - 91837409 | CKT: 13948 - 91837409 | 2275128 | LUG CSA 13948.91837409 OH | 2275129 | LUG CSA 13948.91837409 UG | 2275128 | LUG CSA 13948.91837409 OH | 2275129 | LUG CSA 13948.91837409 UG
Pike | 2020 | 2020 | LUG - TBD148 | PRE-09361.79 | PRE-09361.83 | DNU LUG CSA 13093.91004843 | LUG CSA 13093.91004837 | 13093 | PLYMOUTH STREET | DNU Lateral Hardening-Fuse-91004843 | Lateral Hardening-Fuse-91004837 | CSA | 0.25947 | 27 | 122 | 2020-09-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A | LUG C009 | DNU CKT: 13093 - 91004843 | CKT: 13093 - 91004837 | 2275131 | DNU LUG CSA 13093.91004843 OH | 2275132 | DNU LUG CSA 13093.91004843 UG | 2275118 | LUG CSA 13093.91004837 OH | 2275120 | LUG CSA 13093.91004837 UG | Combined with PRE-09361.79 (FID 91004837) & LUG-TBD245 (FID 60029740)
Pike | 2020 | 2020 | LUG - TBD149 | PRE-09361.84 | PRE-09361.84 | LUG CSA 13836.91377944 | LUG CSA 13836.91377944 | 13836 | FLORIDA AVENUE | Lateral Hardening-Fuse-91377944 | Lateral Hardening-Fuse-91377944 | CSA | 0.59167 | 41 | 276 | 2020-09-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A | LUG C013 | CKT: 13836 - 91377944 | CKT: 13836 - 91377944 | 2275133 | LUG CSA 13836.91377944 OH | 2275134 | LUG CSA 13836.91377944 UG | 2275133 | LUG CSA 13836.91377944 OH | 2275134 | LUG CSA 13836.91377944 UG | Combined with PRE-0361.24 (FID 91406672) and other 2021 projects
Pike | 2020 | 2020 | LUG - TBD150 | PRE-09361.85 | PRE-09361.85 | LUG CSA 13102.60123654 | LUG CSA 13102.60123654 | 13102 | YUKON | Lateral Hardening-Fuse-60123654 | Lateral Hardening-Fuse-60123654 | CSA | 0.19034 | 15 | 72 | 2020-10-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A | LUG C014 | CKT: 13102 - 60123654 | CKT: 13102 - 60123654 | 2275137 | LUG CSA 13102.60123654 OH | 2275138 | LUG CSA 13102.60123654 UG | 2275137 | LUG CSA 13102.60123654 OH | 2275138 | LUG CSA 13102.60123654 UG | Combined with LUG-TBD246 (FID 60123656)
Pike | 2020 | 2020 | LUG - TBD151 | PRE-09361.86 | PRE-09361.86 | LUG CSA 13158.92874802 | LUG CSA 13158.92874802 | 13158 | THIRTIETH STREET | Lateral Hardening-Fuse-92874802 | Lateral Hardening-Fuse-92874802 | CSA | 0.14905 | 14 | 47 | 2020-10-01 | 2021-01-01 | 2021-03-01 | 4500276922 | N/A | N/A |  | CKT: 13158 - 92874802 | CKT: 13158 - 92874802 | 2275139 | LUG CSA 13158.92874802 OH | 2275142 | LUG CSA 13158.92874802 UG | 2275139 | LUG CSA 13158.92874802 OH | 2275142 | LUG CSA 13158.92874802 UG
Pike | 2020 | 2020 | LUG - TBD152 | PRE-09361.87 | PRE-09361.87 | LUG CSA 13176.10375134 | LUG CSA 13176.10375134 | 13176 | ELEVENTH AVENUE | Lateral Hardening-Fuse-10375134 | Lateral Hardening-Fuse-10375134 | CSA | 0.13504 | 10 | 89 | 2020-10-01 | 2021-02-01 | 2021-04-01 | 4500276922 | N/A | N/A | U - LUG C015 | CKT: 13176 - 10375134 | CKT: 13176 - 10375134 | 2275144 | LUG CSA 13176.10375134 OH | 2275145 | LUG CSA 13176.10375134 UG | 2275144 | LUG CSA 13176.10375134 OH | 2275145 | LUG CSA 13176.10375134 UG | Originally combined with PRE-09361.482 (FID 10375136), but now uncombined
Pike | 2020 | 2020 | LUG - TBD153 | PRE-09361.88 | PRE-09361.88 | LUG CSA 13107.10376173 | LUG CSA 13107.10376173 | 13107 | MCFARLAND | Lateral Hardening-Fuse-10376173 | Lateral Hardening-Fuse-10376173 | CSA | 0.43542 | 28 | 119 | 2020-10-01 | 2021-03-01 | 2021-05-01 | 4500276922 | N/A | N/A |  | CKT: 13107 - 10376173 | CKT: 13107 - 10376173 | 2275146 | LUG CSA 13107.10376173 OH | 2275148 | LUG CSA 13107.10376173 UG | 2275146 | LUG CSA 13107.10376173 OH | 2275148 | LUG CSA 13107.10376173 UG
Pike | 2020 | 2020 | LUG - TBD154 | PRE-09361.89 | PRE-09361.89 | LUG CSA 13057.10121709 | LUG CSA 13057.10121709 | 13057 | MCKINLEY | Lateral Hardening-Fuse-10121709 | Lateral Hardening-Fuse-10121709 | CSA | 0.16326 | 14 | 80 | 2020-10-01 | 2021-03-01 | 2021-04-01 | 4500276922 | N/A | N/A |  | CKT: 13057 - 10121709 | CKT: 13057 - 10121709 | 2275149 | LUG CSA 13057.10121709 OH | 2275150 | LUG CSA 13057.10121709 UG | 2275149 | LUG CSA 13057.10121709 OH | 2275150 | LUG CSA 13057.10121709 UG
Pike | 2020 | 2020 | LUG - TBD155 | PRE-09361.90 | PRE-09361.90 | LUG CSA 13418.92357188 | LUG CSA 13418.92357188 | 13418 | JUNEAU | Lateral Hardening-Fuse-92357188 | Lateral Hardening-Fuse-92357188 | CSA | 0.47045 | 33 | 61 | 2020-10-01 | 2021-03-01 | 2021-05-01 | 4500276922 | N/A | N/A | LUG C017 | CKT: 13418 - 92357188 | CKT: 13418 - 92357188 | 2275151 | LUG CSA 13418.92357188 OH | 2275152 | LUG CSA 13418.92357188 UG | 2275151 | LUG CSA 13418.92357188 OH | 2275152 | LUG CSA 13418.92357188 UG | Combined with LUG-TBD190 (FID 92292295)
Pike | 2020 | 2020 | LUG - TBD156 | PRE-09361.91 | PRE-09361.91 | LUG CSA 13592.91213055 | LUG CSA 13592.91213055 | 13592 | SENECA STREET | Lateral Hardening-Fuse-91213055 | Lateral Hardening-Fuse-91213055 | CSA | 0.27235 | 23 | 72 | 2020-10-01 | 2021-03-01 | 2021-06-01 | 4500276922 | N/A | N/A |  | CKT: 13592 - 91213055 | CKT: 13592 - 91213055 | 2275154 | LUG CSA 13592.91213055 OH | 2275156 | LUG CSA 13592.91213055 UG | 2275154 | LUG CSA 13592.91213055 OH | 2275156 | LUG CSA 13592.91213055 UG
Pike | 2020 | 2020 | LUG - TBD157 | PRE-09361.92 | PRE-09361.92 | LUG CSA 13100.91340554 | LUG CSA 13100.91340554 | 13100 | YUKON | Lateral Hardening-Fuse-91340554 | Lateral Hardening-Fuse-91340554 | CSA | 0.41193 | 28 | 403 | 2020-11-01 | 2021-04-01 | 2021-06-01 | 4500276922 | N/A | N/A | LUG C016 | CKT: 13100 - 91340554 | CKT: 13100 - 91340554 | 2275159 | LUG CSA 13100.91340554 OH | 2275160 | LUG CSA 13100.91340554 UG | 2275159 | LUG CSA 13100.91340554 OH | 2275160 | LUG CSA 13100.91340554 UG | Combined with LUG-TBD188 (FID 10371703)
Pike | 2020 | 2020 | LUG - TBD158 | PRE-09361.93 | PRE-09361.93 | LUG CSA 13715.90737020 | LUG CSA 13715.90737020 | 13715 | TAMPA PALMS | Lateral Hardening-Fuse-90737020 | Lateral Hardening-Fuse-90737020 | CSA | 0.082008 | 3 | 10 | 2020-11-01 | 2021-04-01 | 2021-05-01 | 4500276922 | N/A | N/A |  | CKT: 13715 - 90737020 | CKT: 13715 - 90737020 | 2275161 | LUG CSA 13715.90737020 OH | 2275162 | LUG CSA 13715.90737020 UG | 2275161 | LUG CSA 13715.90737020 OH | 2275162 | LUG CSA 13715.90737020 UG
Pike | 2020 | 2020 | LUG - TBD159 | PRE-09361.94 | PRE-09361.94 | LUG CSA 13176.91029163 | LUG CSA 13176.91029163 | 13176 | ELEVENTH AVENUE | Lateral Hardening-Fuse-91029163 | Lateral Hardening-Fuse-91029163 | CSA | 0.069697 | 7 | 89 | 2020-11-01 | 2021-04-01 | 2021-05-01 | 4500276922 | N/A | N/A |  | CKT: 13176 - 91029163 | CKT: 13176 - 91029163 | 2275163 | LUG CSA 13176.91029163 OH | 2275166 | LUG CSA 13176.91029163 UG | 2275163 | LUG CSA 13176.91029163 OH | 2275166 | LUG CSA 13176.91029163 UG
Pike | 2020 | 2020 | LUG - TBD160 | PRE-09361.95 | PRE-09361.95 | LUG CSA 13835.60131429 | LUG CSA 13835.60131429 | 13835 | FLORIDA AVENUE | Lateral Hardening-Fuse-60131429 | Lateral Hardening-Fuse-60131429 | CSA | 0.2714 | 19 | 43 | 2020-11-01 | 2021-04-01 | 2021-06-01 | 4500276922 | N/A | N/A |  | CKT: 13835 - 60131429 | CKT: 13835 - 60131429 | 2275167 | LUG CSA 13835.60131429 OH | 2275170 | LUG CSA 13835.60131429 UG | 2275167 | LUG CSA 13835.60131429 OH | 2275170 | LUG CSA 13835.60131429 UG
Pike | 2020 | 2020 | LUG - TBD161 | PRE-09361.96 | PRE-09361.96 | LUG CSA 13593.93057902 | LUG CSA 13593.93057902 | 13593 | SENECA STREET | Lateral Hardening-Fuse-93057902 | Lateral Hardening-Fuse-93057902 | CSA | 0.45455 | 39 | 83 | 2020-10-01 | 2021-04-01 | 2021-06-01 | 4500276922 | N/A | N/A |  | CKT: 13593 - 93057902 | CKT: 13593 - 93057902 | 2275171 | LUG CSA 13593.93057902 OH | 2275172 | LUG CSA 13593.93057902 UG | 2275171 | LUG CSA 13593.93057902 OH | 2275172 | LUG CSA 13593.93057902 UG
Pike | 2020 | 2020 | LUG - TBD162 | PRE-09361.97 | PRE-09361.97 | LUG CSA 13105.10580678 | LUG CSA 13105.10580678 | 13105 | MCFARLAND | Lateral Hardening-Fuse-10580678 | Lateral Hardening-Fuse-10580678 | CSA | 0.23163 | 17 | 217 | 2020-11-01 | 2021-04-01 | 2021-06-01 | 4500276922 | N/A | N/A |  | CKT: 13105 - 10580678 | CKT: 13105 - 10580678 | 2275174 | LUG CSA 13105.10580678 OH | 2275175 | LUG CSA 13105.10580678 UG | 2275174 | LUG CSA 13105.10580678 OH | 2275175 | LUG CSA 13105.10580678 UG
Pike | 2020 | 2020 | LUG - TBD163 | PRE-09361.98 | PRE-09361.98 | LUG CSA 13188.10655453 | LUG CSA 13188.10655453 | 13188 | PINE LAKE | Lateral Hardening-Fuse-10655453 | Lateral Hardening-Fuse-10655453 | CSA | 0.12235 | 15 | 46 | 2020-11-01 | 2021-04-01 | 2021-06-01 | 4500276922 | N/A | N/A |  | CKT: 13188 - 10655453 | CKT: 13188 - 10655453 | 2275176 | LUG CSA 13188.10655453 OH | 2275178 | LUG CSA 13188.10655453 UG | 2275176 | LUG CSA 13188.10655453 OH | 2275178 | LUG CSA 13188.10655453 UG
Pike | 2020 | 2020 | LUG - TBD164 | PRE-09361.99 | PRE-09361.99 | LUG CSA 13592.10402259 | LUG CSA 13592.10402259 | 13592 | SENECA STREET | Lateral Hardening-Fuse-10402259 | Lateral Hardening-Fuse-10402259 | CSA | 0.1983 | 21 | 20 | 2020-11-01 | 2021-04-01 | 2021-05-01 | 4500276922 | N/A | N/A |  | CKT: 13592 - 10402259 | CKT: 13592 - 10402259 | 2275180 | LUG CSA 13592.10402259 OH | 2275181 | LUG CSA 13592.10402259 UG | 2275180 | LUG CSA 13592.10402259 OH | 2275181 | LUG CSA 13592.10402259 UG
Pike | 2020 | 2020 | LUG - TBD165 | PRE-09361.100 | PRE-09361.100 | LUG CSA 13948.10442385 | LUG CSA 13948.10442385 | 13948 | YUKON | Lateral Hardening-Fuse-10442385 | Lateral Hardening-Fuse-10442385 | CSA | 0.30436 | 23 | 130 | 2020-10-01 | 2021-04-01 | 2021-06-01 | 4500276922 | N/A | N/A |  | CKT: 13948 - 10442385 | CKT: 13948 - 10442385 | 2275183 | LUG CSA 13948.10442385 OH | 2275184 | LUG CSA 13948.10442385 UG | 2275183 | LUG CSA 13948.10442385 OH | 2275184 | LUG CSA 13948.10442385 UG