## DPL-11 LUG Appendix
Tampa Electric's Distribution Lateral Undergrounding - Year 2022 Details
Project ID | Circuit No. | Specific Project Detail |  | Customers |  |  |  | Priority Customers | Project Start Qtr | Construction |  | Project Cost in 2022
|  | OH to UG Length Converted (miles) | Poles | Residential | Small C&I | Large C&I | Total |  |  | Start Qtr | End Qtr
LUG CSA 13021.60058683 | 13021 | 0.30682 | 28 | 130 | 11 | 1 | 142 | 3 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 634109.091
LUG CSA 13021.92350282 | 13021 | 0.3178 | 27 | 14 | 11 | 0 | 25 | 12 | Q1 - 2021 | Q4 - 2021 | Q1 - 2022 | 140500
LUG CSA 13026.60059452 | 13026 | 0.16383 | 11 | 64 | 7 | 2 | 73 | 0 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 152871.2122
LUG CSA 13026.60059457 | 13026 | 0.20814 | 15 | 24 | 13 | 0 | 37 | 0 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 208780.3029
LUG CSA 13026.60059509 | 13026 | 0.085795 | 8 | 84 | 11 | 2 | 97 | 0 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 86294.4474
LUG CSA 13026.60059524 | 13026 | 0.18939 | 16 | 115 | 13 | 0 | 128 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 484875.7274
LUG CSA 13093.91004837 | 13093 | 0.18504 | 17 | 143 | 29 | 3 | 175 | 18 | Q3 - 2020 | Q1 - 2022 | Q2 - 2022 | 664204.5455
LUG CSA 13099.10368943 | 13099 | 0.24242 | 13 | 2 | 3 | 0 | 5 | 0 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 238465.4078
LUG CSA 13099.60125388 | 13099 | 0.43447 | 24 | 68 | 5 | 0 | 73 | 0 | Q1 - 2021 | Q3 - 2022 | Q2 - 2023 | 747872.1252
LUG CSA 13099.90882614 | 13099 | 0.23731 | 18 | 128 | 9 | 2 | 139 | 0 | Q3 - 2020 | Q2 - 2022 | Q3 - 2022 | 577003.0303
LUG CSA 13100.91340554 | 13100 | 0.41193 | 28 | 403 | 7 | 3 | 413 | 0 | Q4 - 2020 | Q4 - 2022 | Q3 - 2023 | 154710.58
LUG CSA 13102.60123654 | 13102 | 0.19034 | 15 | 72 | 1 | 2 | 75 | 0 | Q3 - 2020 | Q3 - 2021 | Q1 - 2022 | 55000
LUG CSA 13102.90748252 | 13102 | 0.23333 | 23 | 29 | 2 | 1 | 32 | 0 | Q2 - 2021 | Q3 - 2022 | Q4 - 2022 | 854885.3758
LUG CSA 13102.91293905 | 13102 | 0.11629 | 10 | 47 | 13 | 4 | 64 | 1 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 123608.3661
LUG CSA 13104.10362869 | 13104 | 0.3803 | 30 | 67 | 20 | 3 | 90 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 497526.3636
LUG CSA 13104.91241032 | 13104 | 0.15038 | 18 | 19 | 2 | 2 | 23 | 0 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 148692.2606
LUG CSA 13104.91643108 | 13104 | 0.33845 | 33 | 74 | 19 | 1 | 94 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 430741.9816
LUG CSA 13104.91668251 | 13104 | 0.20265 | 17 | 16 | 8 | 0 | 24 | 0 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 187342.4242
LUG CSA 13105.10580676 | 13105 | 0.13239 | 13 | 14 | 3 | 0 | 17 | 0 | Q1 - 2021 | Q3 - 2021 | Q1 - 2022 | 14000
LUG CSA 13105.10580689 | 13105 | 0.12765 | 10 | 44 | 3 | 0 | 47 | 0 | Q1 - 2021 | Q1 - 2022 | Q2 - 2022 | 120742.4242
LUG CSA 13105.10580690 | 13105 | 0.23314 | 21 | 122 | 15 | 1 | 138 | 0 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 238847.4429
LUG CSA 13105.60164901 | 13105 | 0.11439 | 10 | 79 | 5 | 1 | 85 | 0 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 104230.3029
LUG CSA 13106.10361901 | 13106 | 0.74848 | 52 | 274 | 21 | 0 | 295 | 0 | Q1 - 2021 | Q4 - 2021 | Q2 - 2022 | 188155.12
LUG CSA 13106.91722510 | 13106 | 0.10852 | 9 | 166 | 10 | 1 | 177 | 0 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 259986.3636
LUG CSA 13107.10376173 | 13107 | 0.43542 | 28 | 119 | 27 | 2 | 148 | 0 | Q4 - 2020 | Q2 - 2022 | Q4 - 2022 | 389526.71
LUG CSA 13107.10376186 | 13107 | 0.12348 | 10 | 179 | 4 | 0 | 183 | 0 | Q1 - 2021 | Q4 - 2021 | Q1 - 2022 | 28000
LUG CSA 13107.10376201 | 13107 | 0.13485 | 10 | 8 | 1 | 0 | 9 | 0 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 130871.3758
LUG CSA 13158.60011810 | 13158 | 0.75795 | 56 | 226 | 10 | 1 | 237 | 1 | Q1 - 2021 | Q1 - 2022 | Q2 - 2022 | 245476.3
LUG CSA 13158.90816343 | 13158 | 0.25019 | 18 | 123 | 4 | 1 | 128 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 612548.4848
LUG CSA 13158.91461782 | 13158 | 0.33428 | 30 | 39 | 3 | 0 | 42 | 0 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 314198.4848
LUG CSA 13176.10375136 | 13176 | 0.65701 | 57 | 11 | 9 | 11 | 31 | 2 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 621962.1213
LUG CSA 13176.10375141 | 13176 | 0.62348 | 51 | 89 | 9 | 4 | 102 | 8 | Q1 - 2021 | Q4 - 2022 | Q2 - 2023 | 78658.06
LUG CSA 13176.10375148 | 13176 | 0.48087 | 54 | 26 | 5 | 3 | 34 | 0 | Q1 - 2021 | Q4 - 2021 | Q2 - 2022 | 131000
LUG CSA 13188.10655453 | 13188 | 0.12235 | 15 | 46 | 15 | 3 | 64 | 9 | Q4 - 2020 | Q3 - 2022 | Q4 - 2022 | 116100
LUG CSA 13188.92070695 | 13188 | 0.1697 | 11 | 17 | 2 | 0 | 19 | 0 | Q1 - 2021 | Q4 - 2022 | Q1 - 2023 | 83831.42
LUG CSA 13204.60170504 | 13204 | 0.37992 | 31 | 113 | 8 | 1 | 122 | 12 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 522778.7878
LUG CSA 13205.90022802 | 13205 | 0.20152 | 18 | 20 | 5 | 1 | 26 | 6 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 262324.2426
LUG CSA 13205.90442230 | 13205 | 0.2517 | 25 | 60 | 0 | 3 | 63 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 506543.4726
LUG CSA 13205.90929181 | 13205 | 0.19943 | 15 | 32 | 19 | 2 | 53 | 0 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 380640.909
LUG CSA 13354.10582069 | 13354 | 0.19205 | 21 | 281 | 15 | 0 | 296 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 40179.72
LUG CSA 13399.60037987 | 13399 | 0.18902 | 19 | 19 | 13 | 4 | 36 | 11 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 400026.4426
LUG CSA 13418.91924595 | 13418 | 0.21515 | 20 | 25 | 12 | 0 | 37 | 0 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 220188.0442
LUG CSA 13418.92018190 | 13418 | 0.32898 | 21 | 79 | 5 | 1 | 85 | 6 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 323959.4964
LUG CSA 13418.92357188 | 13418 | 0.47045 | 33 | 61 | 28 | 1 | 90 | 0 | Q4 - 2020 | Q3 - 2022 | Q1 - 2023 | 655600
LUG CSA 13468.60128362 | 13468 | 0.53409 | 38 | 147 | 32 | 0 | 179 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 494945.4545
LUG CSA 13468.60128378 | 13468 | 0.75398 | 56 | 444 | 17 | 0 | 461 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 564226.34
LUG CSA 13468.91640192 | 13468 | 0.10682 | 7 | 6 | 4 | 0 | 10 | 0 | Q1 - 2021 | Q4 - 2022 | Q1 - 2023 | 113931.811
LUG CSA 13590.91231633 | 13590 | 0.34205 | 29 | 47 | 11 | 2 | 60 | 0 | Q1 - 2021 | Q4 - 2021 | Q1 - 2022 | 142000
LUG CSA 13592.91365233 | 13592 | 0.30777 | 25 | 121 | 12 | 0 | 133 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 616480.5426
LUG CSA 13593.93057902 | 13593 | 0.45455 | 39 | 83 | 52 | 4 | 139 | 0 | Q4 - 2020 | Q1 - 2022 | Q3 - 2022 | 368400
LUG CSA 13632.10408272 | 13632 | 0.097727 | 9 | 12 | 8 | 0 | 20 | 0 | Q1 - 2021 | Q4 - 2022 | Q1 - 2023 | 93642.52
LUG CSA 13632.10408290 | 13632 | 1.0176 | 55 | 245 | 10 | 0 | 255 | 0 | Q1 - 2021 | Q4 - 2022 | Q3 - 2023 | 948857.22
LUG CSA 13632.60305848 | 13632 | 0.40417 | 33 | 43 | 15 | 0 | 58 | 0 | Q1 - 2021 | Q4 - 2022 | Q2 - 2023 | 196308.43
LUG CSA 13633.90564142 | 13633 | 0.073106 | 3 | 2 | 1 | 0 | 3 | 0 | Q2 - 2021 | Q1 - 2022 | Q2 - 2022 | 60945.17
LUG CSA 13633.91847345 | 13633 | 0.086174 | 7 | 1 | 10 | 0 | 11 | 5 | Q1 - 2021 | Q4 - 2022 | Q2 - 2023 | 5185.08
LUG CSA 13826.60127680 | 13826 | 0.2733 | 13 | 243 | 17 | 2 | 262 | 1 | Q2 - 2021 | Q3 - 2022 | Q4 - 2022 | 81217.33
LUG CSA 13831.10427677 | 13831 | 0.25417 | 18 | 313 | 18 | 0 | 331 | 6 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 233666.6668
LUG CSA 13835.10429505 | 13835 | 0.20303 | 17 | 41 | 5 | 2 | 48 | 0 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 541440.909
LUG CSA 13835.10429522 | 13835 | 0.69015 | 41 | 163 | 8 | 1 | 172 | 1 | Q1 - 2021 | Q2 - 2022 | Q1 - 2023 | 1215306.4842
LUG CSA 13835.60314670 | 13835 | 0.21458 | 18 | 256 | 15 | 1 | 272 | 0 | Q1 - 2021 | Q4 - 2022 | Q1 - 2023 | 102547.94
LUG CSA 13836.91377944 | 13836 | 0.59167 | 41 | 276 | 22 | 2 | 300 | 9 | Q3 - 2020 | Q4 - 2022 | Q1 - 2023 | 102040.98
LUG CSA 13934.10467575 | 13934 | 0.091288 | 6 | 1 | 3 | 3 | 7 | 3 | Q1 - 2021 | Q4 - 2021 | Q1 - 2022 | 33500
LUG CSA 13934.10467597 | 13934 | 0.55871 | 30 | 51 | 0 | 2 | 53 | 1 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 525439.3939
LUG CSA 13939.60144164 | 13939 | 0.12121 | 8 | 38 | 6 | 4 | 48 | 5 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 112739.3939
LUG CSA 13939.60144172 | 13939 | 0.14943 | 15 | 2 | 4 | 2 | 8 | 0 | Q1 - 2021 | Q4 - 2021 | Q1 - 2022 | 97000
LUG CSA 13948.10442379 | 13948 | 0.13788 | 12 | 5 | 0 | 1 | 6 | 1 | Q3 - 2021 | Q3 - 2022 | Q4 - 2022 | 137902.2006
LUG CSA 13948.10442391 | 13948 | 0.21534 | 13 | 23 | 6 | 0 | 29 | 0 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 266895.4545
LUG CSA 13993.10372414 | 13993 | 0.42367 | 27 | 31 | 3 | 2 | 36 | 1 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 429828.7878
LUG CSA 13993.10433144 | 13993 | 0.11913 | 10 | 123 | 2 | 0 | 125 | 6 | Q1 - 2021 | Q1 - 2022 | Q2 - 2022 | 90517.79
LUG CSA 14040.10786358 | 14040 | 0.42727 | 19 | 12 | 3 | 0 | 15 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 137792.83
LUG CSA 14040.10786382 | 14040 | 0.23409 | 13 | 98 | 6 | 2 | 106 | 10 | Q2 - 2020 | Q1 - 2022 | Q3 - 2022 | 213950
LUG CSA 14102.91582612 | 14102 | 0.2964 | 18 | 136 | 6 | 0 | 142 | 0 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 278492.4242
LUG DCA 13006.92949400 | 13006 | 1.2864 | 48 | 41 | 2 | 3 | 46 | 2 | Q1 - 2021 | Q3 - 2022 | Q3 - 2023 | 546981.8181
LUG DCA 13432.10761257 | 13432 | 1.2106 | 38 | 21 | 8 | 1 | 30 | 0 | Q2 - 2021 | Q1 - 2022 | Q4 - 2022 | 821237.75
LUG DCA 13815.93026469 | 13815 | 0.49489 | 15 | 27 | 2 | 0 | 29 | 0 | Q3 - 2020 | Q4 - 2021 | Q3 - 2022 | 1205600
LUG ESA 13127.90334707 | 13127 | 0.36061 | 24 | 150 | 4 | 0 | 154 | 11 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 60345.16
LUG ESA 13127.90334731 | 13127 | 0.43826 | 22 | 56 | 1 | 0 | 57 | 3 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 434237.88
LUG ESA 13127.92661768 | 13127 | 0.53409 | 34 | 170 | 3 | 0 | 173 | 1 | Q4 - 2020 | Q1 - 2023 | Q3 - 2023 | 25000
LUG ESA 13127.92663180 | 13127 | 0.61761 | 42 | 33 | 7 | 1 | 41 | 0 | Q1 - 2021 | Q1 - 2023 | Q1 - 2024 | 28500
LUG ESA 13171.10455381 | 13171 | 0.12462 | 11 | 5 | 18 | 1 | 24 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 30449.12
LUG ESA 13171.90598389 | 13171 | 0.21383 | 11 | 370 | 19 | 3 | 392 | 25 | Q3 - 2020 | Q2 - 2023 | Q4 - 2023 | 53000
LUG ESA 13171.93104605 | 13171 | 0.36345 | 21 | 48 | 2 | 2 | 52 | 4 | Q4 - 2020 | Q2 - 2023 | Q4 - 2023 | 11000
LUG ESA 13174.10913196 | 13174 | 0.21269 | 8 | 241 | 14 | 4 | 259 | 4 | Q3 - 2020 | Q3 - 2022 | Q1 - 2023 | 1609359
LUG ESA 13174.60588225 | 13174 | 0.29091 | 15 | 374 | 34 | 1 | 409 | 1 | Q3 - 2020 | Q2 - 2022 | Q3 - 2022 | 165000
LUG ESA 13211.60044019 | 13211 | 0.52746 | 43 | 395 | 27 | 3 | 425 | 0 | Q3 - 2020 | Q2 - 2022 | Q4 - 2022 | 521400
LUG ESA 13225.60139973 | 13225 | 0.80549 | 54 | 41 | 26 | 6 | 73 | 8 | Q3 - 2020 | Q1 - 2023 | Q1 - 2024 | 101000
LUG ESA 13226.10462583 | 13226 | 0.12178 | 19 | 190 | 19 | 2 | 211 | 0 | Q4 - 2020 | Q2 - 2022 | Q3 - 2022 | 130844
LUG ESA 13226.92664597 | 13226 | 0.30947 | 16 | 348 | 4 | 0 | 352 | 0 | Q4 - 2020 | Q1 - 2023 | Q2 - 2023 | 11000
LUG ESA 13226.92665539 | 13226 | 0.087879 | 5 | 13 | 2 | 2 | 17 | 9 | Q3 - 2020 | Q2 - 2023 | Q1 - 2024 | 5000
LUG ESA 13226.92670950 | 13226 | 0.2017 | 23 | 37 | 15 | 5 | 57 | 0 | Q3 - 2020 | Q2 - 2022 | Q4 - 2022 | 213000
LUG ESA 13229.92525393 | 13229 | 0.21496 | 21 | 141 | 21 | 2 | 164 | 4 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 22500
LUG ESA 13230.10471354 | 13230 | 0.44242 | 38 | 49 | 41 | 8 | 98 | 27 | Q4 - 2020 | Q2 - 2023 | Q1 - 2024 | 15000
LUG ESA 13230.10471377 | 13230 | 0.47973 | 31 | 54 | 2 | 2 | 58 | 0 | Q1 - 2021 | Q1 - 2023 | Q3 - 2023 | 18000
LUG ESA 13230.92180224 | 13230 | 0.27992 | 21 | 58 | 16 | 0 | 74 | 0 | Q3 - 2020 | Q3 - 2022 | Q1 - 2023 | 866800
LUG ESA 13230.92496254 | 13230 | 0.28977 | 23 | 12 | 8 | 0 | 20 | 8 | Q1 - 2021 | Q1 - 2023 | Q2 - 2023 | 53170.38
LUG ESA 13231.10868121 | 13231 | 0.27311 | 22 | 23 | 2 | 0 | 25 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 58320.82
LUG ESA 13231.10868138 | 13231 | 0.53977 | 34 | 269 | 17 | 4 | 290 | 8 | Q4 - 2020 | Q1 - 2023 | Q3 - 2023 | 112000
LUG ESA 13433.10466911 | 13433 | 0.70568 | 47 | 159 | 32 | 0 | 191 | 0 | Q4 - 2020 | Q2 - 2022 | Q4 - 2022 | 739800
LUG ESA 13433.93369551 | 13433 | 0.60587 | 37 | 5 | 3 | 2 | 10 | 2 | Q3 - 2020 | Q1 - 2023 | Q3 - 2023 | 16000
LUG ESA 13454.90188551 | 13454 | 0.21004 | 13 | 37 | 2 | 0 | 39 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 65019.94
LUG ESA 13454.90397369 | 13454 | 0.49053 | 26 | 19 | 10 | 1 | 30 | 0 | Q3 - 2020 | Q1 - 2022 | Q3 - 2022 | 343370
LUG ESA 13454.90429155 | 13454 | 0.63826 | 34 | 148 | 6 | 2 | 156 | 4 | Q3 - 2020 | Q3 - 2022 | Q1 - 2023 | 1106500
LUG ESA 13454.90755954 | 13454 | 0.29564 | 23 | 292 | 21 | 1 | 314 | 0 | Q3 - 2020 | Q4 - 2021 | Q2 - 2022 | 216950
LUG ESA 13454.91522987 | 13454 | 0.043371 | 9 | 47 | 3 | 0 | 50 | 1 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 55899.12
LUG ESA 13457.10482593 | 13457 | 0.13693 | 9 | 137 | 8 | 2 | 147 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 30048.68
LUG ESA 13457.90176591 | 13457 | 0.31136 | 18 | 155 | 2 | 0 | 157 | 2 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 27500
LUG ESA 13502.10497396 | 13502 | 0.29545 | 22 | 70 | 2 | 0 | 72 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 44796.48
LUG ESA 13502.92573944 | 13502 | 0.61894 | 40 | 514 | 18 | 0 | 532 | 0 | Q4 - 2020 | Q1 - 2023 | Q3 - 2023 | 46000
LUG ESA 13502.92679861 | 13502 | 0.17614 | 16 | 50 | 25 | 0 | 75 | 0 | Q4 - 2020 | Q2 - 2022 | Q3 - 2022 | 188706
LUG ESA 13509.10501110 | 13509 | 0.089962 | 6 | 3 | 1 | 0 | 4 | 0 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 35373.9
LUG ESA 13509.10501132 | 13509 | 0.10814 | 6 | 7 | 22 | 11 | 40 | 1 | Q4 - 2020 | Q2 - 2023 | Q1 - 2024 | 10300
LUG ESA 13509.10501141 | 13509 | 0.16364 | 15 | 13 | 0 | 2 | 15 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 18000
LUG ESA 13509.10501150 | 13509 | 0.50871 | 33 | 37 | 7 | 0 | 44 | 0 | Q3 - 2020 | Q1 - 2023 | Q1 - 2024 | 73000
LUG ESA 13509.60287236 | 13509 | 0.14527 | 14 | 144 | 14 | 0 | 158 | 0 | Q3 - 2020 | Q2 - 2023 | Q1 - 2024 | 5000
LUG ESA 13509.60346595 | 13509 | 0.14754 | 10 | 14 | 1 | 1 | 16 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 18000
LUG ESA 13509.90504849 | 13509 | 0.95928 | 56 | 676 | 20 | 1 | 697 | 4 | Q4 - 2020 | Q2 - 2023 | Q1 - 2024 | 7000
LUG ESA 13509.91772133 | 13509 | 0.051705 | 8 | 22 | 0 | 1 | 23 | 1 | Q3 - 2020 | Q3 - 2022 | Q4 - 2022 | 94000
LUG ESA 13509.92890860 | 13509 | 0.33485 | 30 | 7 | 1 | 1 | 9 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 18000
LUG ESA 13686.93697046 | 13686 | 0.402 | 14 | 14 | 0 | 0 | 14 | 1 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 23500
LUG ESA 13710.92354144 | 13710 | 0.28371 | 30 | 229 | 12 | 2 | 243 | 4 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 69469.06
LUG ESA 13710.92881445 | 13710 | 0.44867 | 32 | 158 | 17 | 0 | 175 | 0 | Q3 - 2020 | Q2 - 2022 | Q4 - 2022 | 586222
LUG ESA 13793.92685255 | 13793 | 0.18996 | 6 | 26 | 2 | 2 | 30 | 0 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 206879.9
LUG ESA 13793.92686002 | 13793 | 0.22879 | 17 | 1 | 7 | 6 | 14 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 25774.34
LUG ESA 13793.92686712 | 13793 | 0.044318 | 4 | 85 | 2 | 0 | 87 | 0 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 66724.34
LUG ESA 13793.92686736 | 13793 | 0.032197 | 4 | 85 | 4 | 1 | 90 | 0 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 57249.56
LUG ESA 13796.10842823 | 13796 | 0.44811 | 34 | 21 | 20 | 0 | 41 | 0 | Q3 - 2020 | Q3 - 2022 | Q1 - 2023 | 466500
LUG ESA 13796.10842826 | 13796 | 0.15189 | 13 | 353 | 11 | 0 | 364 | 0 | Q4 - 2020 | Q3 - 2022 | Q4 - 2022 | 156000
LUG ESA 13796.92356181 | 13796 | 0.26477 | 14 | 6 | 1 | 3 | 10 | 7 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 205985.68
LUG ESA 13796.92728705 | 13796 | 0.44981 | 34 | 318 | 6 | 1 | 325 | 0 | Q4 - 2020 | Q2 - 2023 | Q1 - 2024 | 13000
LUG ESA 13796.92884623 | 13796 | 1.2991 | 54 | 52 | 15 | 1 | 68 | 1 | Q3 - 2020 | Q1 - 2023 | Q1 - 2024 | 6000
LUG ESA 13797.93185703 | 13797 | 0.044697 | 5 | 2 | 0 | 1 | 3 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 60874.78
LUG ESA 13797.93188519 | 13797 | 0.65966 | 50 | 152 | 6 | 5 | 163 | 0 | Q4 - 2020 | Q2 - 2022 | Q4 - 2022 | 654560
LUG ESA 13799.60395568 | 13799 | 0.45739 | 45 | 260 | 16 | 1 | 277 | 0 | Q4 - 2020 | Q1 - 2023 | Q3 - 2023 | 43000
LUG ESA 13878.10105717 | 13878 | 0.31288 | 23 | 346 | 5 | 0 | 351 | 2 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 86367.3
LUG ESA 13878.10105723 | 13878 | 0.31307 | 25 | 46 | 37 | 8 | 91 | 4 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 22500
LUG ESA 13878.10105726 | 13878 | 0.54015 | 44 | 137 | 2 | 0 | 139 | 2 | Q1 - 2021 | Q1 - 2023 | Q3 - 2023 | 24000
LUG ESA 13878.10105728 | 13878 | 0.23201 | 14 | 26 | 0 | 0 | 26 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 59995.6
LUG ESA 13883.91179506 | 13883 | 0.075 | 6 | 151 | 7 | 1 | 159 | 0 | Q3 - 2020 | Q4 - 2021 | Q2 - 2022 | 60500
LUG ESA 13883.92008787 | 13883 | 0.058333 | 8 | 3 | 0 | 1 | 4 | 0 | Q3 - 2020 | Q3 - 2022 | Q4 - 2022 | 66050
LUG ESA 13906.10096960 | 13906 | 0.37689 | 26 | 56 | 4 | 0 | 60 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 61500
LUG ESA 13906.10096964 | 13906 | 0.6767 | 40 | 31 | 2 | 3 | 36 | 10 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 23500
LUG ESA 13906.10096968 | 13906 | 0.55739 | 53 | 99 | 9 | 5 | 113 | 12 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 26250
LUG ESA 13906.90137810 | 13906 | 0.80322 | 53 | 62 | 4 | 2 | 68 | 0 | Q1 - 2021 | Q2 - 2023 | Q4 - 2023 | 25000
LUG ESA 13906.92282884 | 13906 | 0.095455 | 7 | 26 | 2 | 1 | 29 | 0 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 119524.32
LUG ESA 13909.90380435 | 13909 | 0.20095 | 11 | 41 | 4 | 0 | 45 | 0 | Q1 - 2021 | Q2 - 2023 | Q4 - 2023 | 32973.46
LUG ESA 13909.92173076 | 13909 | 0.31155 | 22 | 8 | 10 | 4 | 22 | 6 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 23500
LUG ESA 13911.10554595 | 13911 | 0.1303 | 16 | 4 | 0 | 2 | 6 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 20000
LUG ESA 13911.60157736 | 13911 | 0.051894 | 5 | 62 | 1 | 0 | 63 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 26849.56
LUG ESA 13911.60157737 | 13911 | 0.65909 | 48 | 747 | 13 | 1 | 761 | 4 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 198750
LUG ESA 13911.90130568 | 13911 | 0.85871 | 53 | 108 | 18 | 0 | 126 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 22500
LUG ESA 13911.91995336 | 13911 | 0.30095 | 19 | 93 | 2 | 0 | 95 | 0 | Q1 - 2021 | Q1 - 2023 | Q3 - 2023 | 23500
LUG ESA 13911.92679866 | 13911 | 0.55549 | 50 | 80 | 27 | 0 | 107 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 27500
LUG ESA 14116.60140011 | 14116 | 0.32595 | 29 | 50 | 4 | 3 | 57 | 4 | Q4 - 2020 | Q1 - 2022 | Q3 - 2022 | 328562
LUG ESA 14116.91073265 | 14116 | 0.092614 | 7 | 10 | 8 | 0 | 18 | 0 | Q1 - 2021 | Q1 - 2024 | Q1 - 2024 | 34747.8
LUG ESA 14355.60258173 | 14355 | 0.15777 | 15 | 356 | 21 | 2 | 379 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 31298.86
LUG ESA 14355.92354352 | 14355 | 0.31856 | 22 | 51 | 3 | 3 | 57 | 1 | Q1 - 2021 | Q1 - 2024 | Q1 - 2024 | 21250
LUG PCA 13120.60015632 | 13120 | 0.20303 | 14 | 135 | 8 | 1 | 144 | 1 | Q3 - 2020 | Q4 - 2021 | Q2 - 2022 | 194372
LUG PCA 13146.10629014 | 13146 | 0.54337 | 30 | 91 | 6 | 0 | 97 | 0 | Q3 - 2020 | Q1 - 2023 | Q3 - 2023 | 56106
LUG PCA 13243.90684154 | 13243 | 0.22841 | 19 | 7 | 0 | 4 | 11 | 0 | Q3 - 2021 | Q1 - 2023 | Q2 - 2023 | 122978
LUG PCA 13243.91351288 | 13243 | 0.28617 | 18 | 223 | 18 | 0 | 241 | 0 | Q1 - 2021 | Q1 - 2023 | Q3 - 2023 | 298166
LUG PCA 13268.10705945 | 13268 | 1.4027 | 67 | 76 | 19 | 0 | 95 | 0 | Q2 - 2021 | Q1 - 2023 | Q4 - 2023 | 122156
LUG PCA 13268.91633548 | 13268 | 0.8911 | 48 | 216 | 23 | 2 | 241 | 1 | Q1 - 2021 | Q2 - 2022 | Q1 - 2023 | 802646
LUG PCA 13268.92962459 | 13268 | 0.43333 | 28 | 48 | 6 | 1 | 55 | 0 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 129753
LUG PCA 13390.92599119 | 13390 | 0.72367 | 46 | 266 | 27 | 3 | 296 | 0 | Q3 - 2020 | Q3 - 2021 | Q2 - 2022 | 1511052
LUG PCA 13655.90431393 | 13655 | 1.2312 | 70 | 298 | 26 | 3 | 327 | 0 | Q2 - 2021 | Q1 - 2023 | Q4 - 2023 | 152476
LUG PCA 13722.60360851 | 13722 | 0.21288 | 17 | 124 | 18 | 1 | 143 | 0 | Q1 - 2021 | Q1 - 2023 | Q4 - 2023 | 185066
LUG PCA 13724.10671229 | 13724 | 0.29678 | 16 | 9 | 5 | 0 | 14 | 0 | Q1 - 2021 | Q4 - 2021 | Q4 - 2022 | 375122
LUG PCA 13724.10671319 | 13724 | 1.7574 | 83 | 181 | 35 | 2 | 218 | 0 | Q1 - 2021 | Q3 - 2022 | Q3 - 2023 | 1803592
LUG PCA 13724.10671334 | 13724 | 0.57254 | 31 | 120 | 22 | 0 | 142 | 0 | Q1 - 2021 | Q3 - 2022 | Q3 - 2023 | 145165
LUG PCA 13724.90911087 | 13724 | 0.5392 | 32 | 31 | 4 | 0 | 35 | 6 | Q3 - 2020 | Q3 - 2022 | Q2 - 2023 | 340878
LUG PCA 13724.91049435 | 13724 | 1.9932 | 103 | 97 | 17 | 2 | 116 | 0 | Q1 - 2021 | Q1 - 2023 | Q3 - 2023 | 122648
LUG PCA 13785.92299245 | 13785 | 1.0799 | 57 | 174 | 10 | 0 | 184 | 0 | Q1 - 2021 | Q4 - 2021 | Q4 - 2022 | 1001289
LUG PCA 13785.92466250 | 13785 | 0.72008 | 31 | 72 | 13 | 1 | 86 | 0 | Q3 - 2020 | Q4 - 2021 | Q4 - 2022 | 858204
LUG PCA 13961.10696431 | 13961 | 0.15795 | 8 | 4 | 0 | 2 | 6 | 4 | Q1 - 2021 | Q1 - 2023 | Q3 - 2023 | 54732
LUG PCA 13961.10696486 | 13961 | 0.5447 | 32 | 38 | 5 | 0 | 43 | 0 | Q1 - 2021 | Q1 - 2022 | Q4 - 2022 | 267570
LUG PCA 13961.60193482 | 13961 | 0.4822 | 35 | 118 | 13 | 4 | 135 | 0 | Q3 - 2020 | Q4 - 2021 | Q3 - 2022 | 225732
LUG PCA 13961.91967308 | 13961 | 0.48693 | 32 | 28 | 4 | 1 | 33 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 157398
LUG PCA 13961.92820848 | 13961 | 0.49451 | 26 | 509 | 10 | 2 | 521 | 0 | Q3 - 2020 | Q1 - 2022 | Q3 - 2022 | 196174
LUG PCA 13961.92829453 | 13961 | 0.33693 | 25 | 447 | 3 | 2 | 452 | 0 | Q3 - 2020 | Q1 - 2023 | Q3 - 2023 | 59592
LUG PCA 13961.92834683 | 13961 | 0.72027 | 37 | 23 | 4 | 1 | 28 | 0 | Q1 - 2021 | Q1 - 2022 | Q4 - 2022 | 789692
LUG SHA 13001.10663240 | 13001 | 0.45189 | 26 | 16 | 5 | 2 | 23 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 43272.14
LUG SHA 13001.10663262 | 13001 | 0.092045 | 8 | 63 | 4 | 0 | 67 | 10 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 21500
LUG SHA 13001.10663269 | 13001 | 0.11818 | 8 | 16 | 4 | 0 | 20 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 23774.34
LUG SHA 13001.60179144 | 13001 | 0.66742 | 42 | 162 | 14 | 2 | 178 | 4 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 138000
LUG SHA 13001.60179191 | 13001 | 0.36439 | 30 | 139 | 11 | 1 | 151 | 1 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 60019.94
LUG SHA 13001.92048269 | 13001 | 0.23845 | 17 | 137 | 15 | 0 | 152 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 34323.02
LUG SHA 13001.93346473 | 13001 | 0.80947 | 48 | 483 | 22 | 3 | 508 | 5 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 47114.44
LUG SHA 13003.10895211 | 13003 | 2.4676 | 116 | 179 | 34 | 1 | 214 | 14 | Q1 - 2021 | Q1 - 2023 | Q4 - 2023 | 24000
LUG SHA 13342.10925094 | 13342 | 0.32689 | 22 | 45 | 12 | 1 | 58 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 26500
LUG SHA 13342.90527363 | 13342 | 0.15606 | 10 | 29 | 5 | 0 | 34 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 500
LUG SHA 13342.91010293 | 13342 | 0.35966 | 27 | 190 | 5 | 2 | 197 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 26500
LUG SHA 13645.91519309 | 13645 | 0.49508 | 22 | 36 | 3 | 1 | 40 | 0 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 551701.76
LUG SHA 13645.92207754 | 13645 | 0.73258 | 28 | 7 | 3 | 2 | 12 | 3 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 23774.34
LUG SHA 13652.92748361 | 13652 | 0.47689 | 23 | 23 | 21 | 0 | 44 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 31398.24
LUG SHA 13780.10723993 | 13780 | 0.27008 | 17 | 97 | 4 | 0 | 101 | 1 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 38097.36
LUG SHA 13817.10722417 | 13817 | 1.7845 | 123 | 569 | 35 | 1 | 605 | 2 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 33000
LUG SHA 13897.10933151 | 13897 | 0.78845 | 33 | 64 | 20 | 1 | 85 | 1 | Q3 - 2020 | Q1 - 2022 | Q3 - 2022 | 785112
LUG SHA 13900.10717269 | 13900 | 0.41818 | 21 | 136 | 15 | 1 | 152 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 63619.5
LUG SHA 13900.91863298 | 13900 | 0.26648 | 18 | 169 | 3 | 0 | 172 | 8 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 100464.66
LUG SHA 13900.92336596 | 13818 | 0.45928 | 21 | 3 | 1 | 5 | 9 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 23774.34
LUG SHA 14020.60223573 | 14020 | 0.48087 | 45 | 415 | 8 | 3 | 426 | 2 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 24250
LUG SHA 14022.90591555 | 14022 | 0.75833 | 49 | 485 | 7 | 3 | 495 | 29 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 763012.48
LUG SHA 14024.10747874 | 14024 | 0.15057 | 13 | 135 | 7 | 0 | 142 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 40997.8
LUG SHA 14024.90116190 | 14024 | 0.1267 | 11 | 12 | 8 | 0 | 20 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 32373.9
LUG WHA 13118.10535995 | 13118 | 0.95057 | 63 | 363 | 15 | 0 | 378 | 0 | Q1 - 2021 | Q1 - 2022 | Q4 - 2022 | 937189
LUG WHA 13118.10535999 | 13118 | 0.35492 | 26 | 101 | 5 | 0 | 106 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 393652
LUG WHA 13118.92204382 | 13118 | 0.69129 | 41 | 88 | 6 | 0 | 94 | 0 | Q2 - 2021 | Q1 - 2022 | Q1 - 2023 | 867707
LUG WHA 13118.92612349 | 13118 | 0.93693 | 39 | 220 | 17 | 1 | 238 | 0 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 926697
LUG WHA 13118.92659172 | 13118 | 0.275 | 26 | 18 | 10 | 3 | 31 | 1 | Q1 - 2021 | Q1 - 2023 | Q3 - 2023 | 207720
LUG WHA 13296.10562361 | 13296 | 0.225 | 19 | 37 | 5 | 0 | 42 | 0 | Q1 - 2021 | Q2 - 2022 | Q1 - 2023 | 438832
LUG WHA 13296.60531111 | 13296 | 0.95246 | 68 | 90 | 14 | 2 | 106 | 1 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 888621
LUG WHA 13296.90010289 | 13296 | 1.3356 | 81 | 82 | 12 | 1 | 95 | 4 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 1206963
LUG WHA 13296.92376304 | 13296 | 0.29015 | 20 | 200 | 18 | 0 | 218 | 0 | Q3 - 2021 | Q1 - 2022 | Q1 - 2023 | 342484
LUG WHA 13297.10560425 | 13297 | 0.3142 | 21 | 72 | 3 | 4 | 79 | 0 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 747463
LUG WHA 13297.10560432 | 13297 | 0.43068 | 29 | 362 | 6 | 0 | 368 | 0 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 713526
LUG WHA 13297.60269456 | 13297 | 0.30625 | 30 | 59 | 32 | 4 | 95 | 0 | Q3 - 2021 | Q1 - 2022 | Q1 - 2023 | 359801
LUG WHA 13312.60182741 | 13312 | 0.1483 | 15 | 52 | 11 | 7 | 70 | 0 | Q3 - 2020 | Q1 - 2022 | Q3 - 2022 | 102002
LUG WHA 13313.10684581 | 13313 | 0.24015 | 23 | 38 | 7 | 3 | 48 | 0 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 302581
LUG WHA 13313.10684614 | 13313 | 0.1358 | 16 | 106 | 16 | 3 | 125 | 0 | Q3 - 2021 | Q1 - 2022 | Q1 - 2023 | 246592
LUG WHA 13313.90084626 | 13313 | 0.092045 | 9 | 35 | 78 | 10 | 123 | 0 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 439597
LUG WHA 13314.10567076 | 13314 | 0.42443 | 32 | 89 | 3 | 2 | 94 | 0 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 417912
LUG WHA 13473.60168916 | 13473 | 0.34356 | 24 | 419 | 22 | 1 | 442 | 0 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 241437
LUG WHA 13473.60168942 | 13473 | 0.34678 | 27 | 187 | 7 | 1 | 195 | 0 | Q3 - 2021 | Q1 - 2022 | Q4 - 2022 | 411291
LUG WHA 13473.92097460 | 13473 | 0.24015 | 19 | 152 | 5 | 0 | 157 | 0 | Q2 - 2021 | Q3 - 2023 | Q1 - 2024 | 279503
LUG WHA 13699.10637240 | 13699 | 1.0178 | 48 | 137 | 3 | 1 | 141 | 0 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 690882
LUG WHA 13699.10637242 | 13699 | 0.62462 | 37 | 284 | 27 | 1 | 312 | 0 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 621815
LUG WHA 13699.10637247 | 13699 | 0.18996 | 11 | 119 | 5 | 0 | 124 | 0 | Q1 - 2021 | Q4 - 2022 | Q3 - 2023 | 150226
LUG WHA 13699.10637259 | 13699 | 0.15587 | 13 | 26 | 4 | 0 | 30 | 0 | Q1 - 2021 | Q4 - 2022 | Q3 - 2023 | 169173
LUG WHA 13699.60165416 | 13699 | 0.35795 | 18 | 10 | 20 | 1 | 31 | 0 | Q1 - 2021 | Q3 - 2022 | Q2 - 2023 | 180975
LUG WHA 13916.60279623 | 13916 | 0.18561 | 9 | 282 | 15 | 1 | 298 | 0 | Q1 - 2021 | Q3 - 2022 | Q2 - 2023 | 337807
LUG WHA 13916.91386005 | 13916 | 0.52822 | 36 | 199 | 6 | 0 | 205 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 596018
LUG WHA 13916.92509975 | 13916 | 0.45057 | 35 | 71 | 18 | 0 | 89 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 402018
LUG WHA 13972.10618037 | 13972 | 0.2517 | 13 | 1 | 2 | 2 | 5 | 0 | Q3 - 2021 | Q3 - 2022 | Q1 - 2023 | 311368
LUG WHA 13972.90241880 | 13972 | 0.90379 | 49 | 130 | 7 | 6 | 143 | 0 | Q3 - 2020 | Q1 - 2023 | Q3 - 2023 | 54732
LUG WHA 13972.92421291 | 13972 | 0.43693 | 23 | 379 | 6 | 1 | 386 | 0 | Q3 - 2020 | Q1 - 2023 | Q3 - 2023 | 54798
LUG WSA 13059.60302601 | 13059 | 0.50701 | 51 | 291 | 18 | 2 | 311 | 0 | Q2 - 2021 | Q3 - 2022 | Q3 - 2023 | 95048.294
LUG WSA 13071.60170422 | 13071 | 0.9947 | 74 | 362 | 11 | 3 | 376 | 10 | Q3 - 2020 | Q1 - 2022 | Q2 - 2023 | 1451993.878
LUG WSA 13071.92377934 | 13071 | 0.98239 | 66 | 63 | 7 | 0 | 70 | 0 | Q2 - 2021 | Q4 - 2022 | Q4 - 2023 | 95048.294
LUG WSA 13078.10127955 | 13078 | 0.17822 | 15 | 33 | 2 | 1 | 36 | 1 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 208039.0828
LUG WSA 13078.10127958 | 13078 | 0.74545 | 35 | 554 | 7 | 2 | 563 | 18 | Q1 - 2021 | Q3 - 2022 | Q3 - 2023 | 65585.4806
LUG WSA 13079.60077605 | 13079 | 0.1803 | 17 | 32 | 6 | 5 | 43 | 5 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 159726.917
LUG WSA 13079.60077624 | 13079 | 0.33655 | 30 | 58 | 4 | 5 | 67 | 0 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 66535.0346
LUG WSA 13079.60104344 | 13079 | 0.1411 | 21 | 25 | 8 | 6 | 39 | 3 | Q1 - 2021 | Q4 - 2021 | Q2 - 2022 | 172906.3078
LUG WSA 13079.90517178 | 13079 | 0.12973 | 16 | 56 | 10 | 3 | 69 | 0 | Q1 - 2021 | Q1 - 2022 | Q2 - 2022 | 64432.4
LUG WSA 13109.60233901 | 13109 | 0.47254 | 42 | 282 | 9 | 0 | 291 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 65585.4806
LUG WSA 13109.90643551 | 13109 | 0.66761 | 50 | 95 | 10 | 4 | 109 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 45330.75
LUG WSA 13111.60072751 | 13111 | 0.20379 | 17 | 18 | 1 | 2 | 21 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 318842.4637
LUG WSA 13111.92999604 | 13111 | 0.41705 | 32 | 61 | 9 | 2 | 72 | 0 | Q3 - 2020 | Q3 - 2022 | Q1 - 2023 | 65585.4806
LUG WSA 13113.90422522 | 13113 | 0.10985 | 6 | 3 | 5 | 4 | 12 | 6 | Q3 - 2021 | Q4 - 2022 | Q2 - 2023 | 65585.4806
LUG WSA 13113.90796385 | 13113 | 0.51326 | 34 | 233 | 19 | 1 | 253 | 0 | Q3 - 2020 | Q1 - 2022 | Q3 - 2022 | 565310.3898
LUG WSA 13113.92909503 | 13113 | 0.072538 | 9 | 215 | 8 | 0 | 223 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 68672.4561
LUG WSA 13138.10145618 | 13138 | 0.071023 | 6 | 92 | 2 | 0 | 94 | 0 | Q1 - 2021 | Q1 - 2022 | Q2 - 2022 | 40845.3
LUG WSA 13138.10145628 | 13138 | 0.30379 | 18 | 352 | 5 | 4 | 361 | 0 | Q3 - 2020 | Q4 - 2021 | Q2 - 2022 | 335531.1407
LUG WSA 13138.60170460 | 13138 | 0.26458 | 23 | 170 | 9 | 0 | 179 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 344455.3419
LUG WSA 13140.10013916 | 13140 | 0.10284 | 13 | 143 | 7 | 4 | 154 | 0 | Q3 - 2020 | Q3 - 2022 | Q1 - 2023 | 65585.4806
LUG WSA 13141.10147344 | 13141 | 0.098485 | 7 | 12 | 6 | 1 | 19 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 77385.5515
LUG WSA 13141.10147371 | 13141 | 0.47027 | 49 | 94 | 3 | 1 | 98 | 0 | Q2 - 2021 | Q4 - 2022 | Q2 - 2023 | 65585.4806
LUG WSA 13141.91575422 | 13141 | 0.095455 | 8 | 34 | 1 | 1 | 36 | 25 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 102196.5312
LUG WSA 13141.92442350 | 13141 | 0.087689 | 13 | 12 | 0 | 1 | 13 | 0 | Q3 - 2021 | Q3 - 2022 | Q1 - 2023 | 65585.4806
LUG WSA 13162.10158432 | 13162 | 0.16439 | 10 | 61 | 3 | 0 | 64 | 12 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 93355.9125
LUG WSA 13162.10158434 | 13162 | 0.38182 | 30 | 47 | 23 | 3 | 73 | 6 | Q2 - 2021 | Q4 - 2022 | Q2 - 2023 | 235331.4629
LUG WSA 13162.90435139 | 13162 | 0.29773 | 24 | 23 | 50 | 5 | 78 | 0 | Q1 - 2021 | Q1 - 2023 | Q3 - 2023 | 66535.0346
LUG WSA 13162.92185426 | 13162 | 0.36572 | 26 | 19 | 23 | 16 | 58 | 0 | Q4 - 2020 | Q1 - 2023 | Q3 - 2023 | 59732.8746
LUG WSA 13162.93124277 | 13162 | 0.15701 | 23 | 5 | 15 | 5 | 25 | 5 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 162651.7639
LUG WSA 13164.90252716 | 13164 | 0.21572 | 15 | 59 | 13 | 2 | 74 | 3 | Q1 - 2022 | Q3 - 2023 | Q1 - 2024 | 65585.4806
LUG WSA 13192.90932106 | 13192 | 0.19318 | 13 | 2 | 2 | 5 | 9 | 9 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 145753.3245
LUG WSA 13194.90645535 | 13194 | 1.0994 | 50 | 285 | 2 | 0 | 287 | 0 | Q1 - 2021 | Q1 - 2023 | Q3 - 2023 | 65585.4806
LUG WSA 13198.10051851 | 13198 | 0.21231 | 21 | 33 | 50 | 2 | 85 | 6 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 195984.5373
LUG WSA 13198.10051875 | 13198 | 0.097348 | 8 | 20 | 2 | 2 | 24 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 165710.9744
LUG WSA 13198.10051896 | 13198 | 0.13258 | 11 | 18 | 2 | 1 | 21 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 120992.8353
LUG WSA 13198.92183966 | 13198 | 0.16629 | 12 | 86 | 26 | 4 | 116 | 0 | Q3 - 2020 | Q3 - 2022 | Q1 - 2023 | 308072.944
LUG WSA 13198.92655424 | 13198 | 0.094129 | 8 | 11 | 7 | 2 | 20 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 174468.8658
LUG WSA 13207.90146892 | 13207 | 0.26402 | 25 | 60 | 9 | 4 | 73 | 0 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 66535.0346
LUG WSA 13207.90147316 | 13207 | 0.20473 | 17 | 23 | 33 | 0 | 56 | 0 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 65585.4806
LUG WSA 13207.90613782 | 13207 | 0.37973 | 31 | 64 | 1 | 2 | 67 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 65585.4806
LUG WSA 13208.92767537 | 13208 | 0.18352 | 18 | 117 | 3 | 1 | 121 | 0 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 90410.4577
LUG WSA 13220.10191173 | 13220 | 0.5178 | 45 | 66 | 17 | 4 | 87 | 9 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 66535.0346
LUG WSA 13220.90901917 | 13220 | 0.48977 | 38 | 55 | 18 | 0 | 73 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 435673.9312
LUG WSA 13333.10007588 | 13333 | 0.16004 | 16 | 16 | 31 | 2 | 49 | 0 | Q1 - 2021 | Q4 - 2022 | Q2 - 2023 | 88822.372
LUG WSA 13333.91785740 | 13333 | 0.23277 | 26 | 13 | 34 | 3 | 50 | 0 | Q4 - 2020 | Q1 - 2022 | Q3 - 2022 | 147333.9586
LUG WSA 13334.91645657 | 13334 | 0.48428 | 46 | 142 | 7 | 1 | 150 | 0 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 59732.8746
LUG WSA 13425.10244449 | 13425 | 0.69659 | 33 | 195 | 12 | 4 | 211 | 0 | Q3 - 2020 | Q3 - 2021 | Q2 - 2022 | 89888.927
LUG WSA 13428.90423835 | 13428 | 0.26326 | 16 | 208 | 1 | 0 | 209 | 12 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 127957.55
LUG WSA 13428.91540495 | 13428 | 0.23314 | 30 | 402 | 20 | 1 | 423 | 1 | Q3 - 2020 | Q1 - 2022 | Q3 - 2022 | 353201.85
LUG WSA 13483.60393455 | 13483 | 1.3216 | 100 | 525 | 31 | 1 | 557 | 4 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 65585.4806
LUG WSA 13490.92815117 | 13490 | 0.16723 | 13 | 163 | 2 | 1 | 166 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 181350.9861
LUG WSA 13491.10230118 | 13491 | 0.51477 | 36 | 94 | 2 | 4 | 100 | 2 | Q3 - 2020 | Q3 - 2021 | Q1 - 2022 | 147295.6787
LUG WSA 13491.91827162 | 13491 | 0.2392 | 21 | 34 | 1 | 1 | 36 | 7 | Q2 - 2021 | Q2 - 2022 | Q4 - 2022 | 137389.8166
LUG WSA 13510.10218990 | 13510 | 0.35814 | 37 | 20 | 18 | 2 | 40 | 0 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 59732.8746
LUG WSA 13514.10624934 | 13514 | 0.23523 | 20 | 18 | 0 | 1 | 19 | 0 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 95048.294
LUG WSA 13514.91361858 | 13514 | 0.16231 | 18 | 70 | 7 | 0 | 77 | 19 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 157418.9783
LUG WSA 13516.60169592 | 13516 | 0.26042 | 19 | 11 | 16 | 4 | 31 | 5 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 267994.0108
LUG WSA 13520.10242257 | 13520 | 0.45095 | 44 | 28 | 9 | 4 | 41 | 0 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 59732.8746
LUG WSA 13522.10392874 | 13522 | 0.15758 | 12 | 4 | 6 | 4 | 14 | 10 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 121523.0444
LUG WSA 13522.10392882 | 13522 | 0.68731 | 61 | 162 | 8 | 0 | 170 | 0 | Q2 - 2021 | Q2 - 2022 | Q4 - 2022 | 65585.4806
LUG WSA 13522.10392902 | 13522 | 0.66591 | 68 | 103 | 30 | 3 | 136 | 0 | Q3 - 2021 | Q1 - 2023 | Q3 - 2023 | 90410.4577
LUG WSA 13522.10392905 | 13522 | 0.47481 | 50 | 105 | 5 | 3 | 113 | 1 | Q2 - 2021 | Q4 - 2022 | Q2 - 2023 | 274069.2817
LUG WSA 13522.10392924 | 13522 | 0.11591 | 9 | 10 | 3 | 2 | 15 | 0 | Q2 - 2021 | Q4 - 2022 | Q3 - 2023 | 65585.4806
LUG WSA 13522.60305720 | 13522 | 0.068371 | 6 | 10 | 0 | 1 | 11 | 0 | Q2 - 2021 | Q2 - 2022 | Q4 - 2022 | 64556.4834
LUG WSA 13522.91947423 | 13522 | 0.52614 | 50 | 47 | 10 | 3 | 60 | 5 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 399055.7495
LUG WSA 13522.92169062 | 13522 | 0.31686 | 29 | 77 | 13 | 0 | 90 | 0 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 66535.0346
LUG WSA 13533.91957169 | 13533 | 0.24432 | 21 | 354 | 15 | 3 | 372 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 251854.93
LUG WSA 13535.91618829 | 13535 | 0.50265 | 34 | 70 | 4 | 1 | 75 | 0 | Q3 - 2021 | Q1 - 2023 | Q3 - 2023 | 79176.5874
LUG WSA 13535.92952190 | 13535 | 0.2572 | 18 | 78 | 2 | 0 | 80 | 0 | Q4 - 2020 | Q2 - 2022 | Q4 - 2022 | 220147.4845
LUG WSA 13535.92983661 | 13535 | 0.33314 | 32 | 10 | 0 | 3 | 13 | 0 | Q3 - 2021 | Q2 - 2022 | Q4 - 2022 | 266452.3115
LUG WSA 13535.92983670 | 13535 | 0.21269 | 14 | 164 | 10 | 1 | 175 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 198828.4689
LUG WSA 13544.10053269 | 13544 | 0.16174 | 16 | 19 | 2 | 0 | 21 | 0 | Q1 - 2021 | Q4 - 2021 | Q2 - 2022 | 41888.25
LUG WSA 13574.10250638 | 13574 | 0.17083 | 12 | 10 | 6 | 4 | 20 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 97585.5962
LUG WSA 13575.90054386 | 13575 | 0.1017 | 13 | 105 | 8 | 3 | 116 | 1 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 120187.6855
LUG WSA 13575.90054924 | 13575 | 0.1072 | 12 | 238 | 2 | 0 | 240 | 5 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 139012.3935
LUG WSA 13586.10255333 | 13586 | 0.12159 | 9 | 4 | 1 | 0 | 5 | 0 | Q1 - 2021 | Q3 - 2021 | Q1 - 2022 | 21743.9297
LUG WSA 13586.60303627 | 13586 | 1.0686 | 67 | 69 | 8 | 5 | 82 | 0 | Q3 - 2020 | Q3 - 2022 | Q1 - 2023 | 678421.45
LUG WSA 13586.91748729 | 13586 | 0.6714 | 42 | 45 | 0 | 3 | 48 | 0 | Q2 - 2021 | Q2 - 2023 | Q1 - 2024 | 90410.4577
LUG WSA 13586.92442286 | 13586 | 0.48902 | 40 | 180 | 7 | 0 | 187 | 1 | Q4 - 2021 | Q4 - 2022 | Q4 - 2023 | 65585.4806
LUG WSA 13589.93162023 | 13589 | 0.3267 | 16 | 1 | 5 | 0 | 6 | 5 | Q2 - 2021 | Q2 - 2022 | Q4 - 2022 | 149294.5055
LUG WSA 13589.93177909 | 13589 | 0.11951 | 6 | 33 | 13 | 0 | 46 | 0 | Q1 - 2021 | Q3 - 2021 | Q1 - 2022 | 24024.4967
LUG WSA 13605.91052996 | 13605 | 0.33201 | 27 | 115 | 12 | 0 | 127 | 0 | Q3 - 2020 | Q1 - 2022 | Q3 - 2022 | 783753.6182
LUG WSA 13612.60002970 | 13612 | 0.24811 | 23 | 131 | 3 | 1 | 135 | 0 | Q1 - 2021 | Q4 - 2021 | Q2 - 2022 | 178914.0068
LUG WSA 13612.60003135 | 13612 | 0.3036 | 33 | 81 | 3 | 1 | 85 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 65585.4806
LUG WSA 13612.60022877 | 13612 | 0.061174 | 7 | 22 | 11 | 0 | 33 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 177278.5764
LUG WSA 13612.90291123 | 13612 | 0.13333 | 15 | 10 | 9 | 1 | 20 | 0 | Q2 - 2021 | Q2 - 2023 | Q1 - 2024 | 90410.4577
LUG WSA 13612.90312305 | 13612 | 0.094886 | 7 | 72 | 4 | 1 | 77 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 95048.294
LUG WSA 13612.92956326 | 13612 | 0.23428 | 25 | 20 | 12 | 4 | 36 | 8 | Q2 - 2021 | Q4 - 2022 | Q2 - 2023 | 282539.9151
LUG WSA 13669.60107076 | 13669 | 0.12254 | 9 | 4 | 1 | 4 | 9 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 131882.6147
LUG WSA 13669.92770538 | 13669 | 0.30152 | 37 | 204 | 10 | 0 | 214 | 1 | Q2 - 2021 | Q2 - 2023 | Q1 - 2024 | 79176.5874
LUG WSA 13670.93124410 | 13670 | 0.71345 | 25 | 383 | 3 | 1 | 387 | 0 | Q3 - 2020 | Q2 - 2022 | Q4 - 2022 | 289212.544
LUG WSA 13672.10493801 | 13672 | 0.57973 | 43 | 368 | 9 | 1 | 378 | 8 | Q2 - 2021 | Q2 - 2023 | Q1 - 2024 | 65585.4806
LUG WSA 13672.60106849 | 13672 | 0.2678 | 26 | 256 | 12 | 0 | 268 | 0 | Q4 - 2020 | Q3 - 2022 | Q1 - 2023 | 226556.857
LUG WSA 13672.91971930 | 13672 | 0.1947 | 19 | 27 | 3 | 1 | 31 | 3 | Q2 - 2021 | Q2 - 2023 | Q1 - 2024 | 95048.294
LUG WSA 13674.10277747 | 13674 | 0.56723 | 36 | 361 | 6 | 1 | 368 | 2 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 269610.6011
LUG WSA 13674.90420693 | 13674 | 0.3233 | 29 | 125 | 0 | 0 | 125 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 65585.4806
LUG WSA 13678.10254063 | 13678 | 0.275 | 18 | 11 | 6 | 0 | 17 | 0 | Q2 - 2021 | Q4 - 2022 | Q2 - 2023 | 223422.372
LUG WSA 13678.10288738 | 13678 | 0.57784 | 28 | 4 | 1 | 0 | 5 | 0 | Q3 - 2021 | Q3 - 2022 | Q1 - 2023 | 431533.0221
LUG WSA 13678.90514672 | 13678 | 0.5358 | 29 | 9 | 5 | 0 | 14 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 361928.0774
LUG WSA 13737.10297934 | 13737 | 0.19678 | 18 | 24 | 1 | 1 | 26 | 0 | Q2 - 2021 | Q4 - 2022 | Q2 - 2023 | 151120.8568
LUG WSA 13737.10297943 | 13737 | 0.20208 | 18 | 84 | 5 | 3 | 92 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 515924.2419
LUG WSA 13737.60311396 | 13737 | 0.19205 | 8 | 16 | 13 | 0 | 29 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 169528.155
LUG WSA 13737.90740214 | 13737 | 0.10114 | 12 | 15 | 3 | 0 | 18 | 0 | Q2 - 2021 | Q2 - 2022 | Q4 - 2022 | 90477.2148
LUG WSA 13737.90740699 | 13737 | 0.16553 | 13 | 17 | 4 | 0 | 21 | 0 | Q2 - 2021 | Q4 - 2022 | Q2 - 2023 | 136970.8568
LUG WSA 13737.91960399 | 13737 | 0.43277 | 32 | 56 | 3 | 3 | 62 | 0 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 243488.9154
LUG WSA 13738.10298299 | 13738 | 0.31307 | 27 | 71 | 7 | 4 | 82 | 0 | Q3 - 2021 | Q3 - 2023 | Q1 - 2024 | 66535.0346
LUG WSA 13747.10299739 | 13747 | 0.10038 | 5 | 128 | 16 | 2 | 146 | 0 | Q3 - 2020 | Q4 - 2021 | Q1 - 2022 | 28009.845
LUG WSA 13750.60110680 | 13750 | 0.18561 | 12 | 43 | 6 | 0 | 49 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 91375.9471
LUG WSA 13756.10589587 | 13756 | 0.14356 | 13 | 8 | 4 | 0 | 12 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 170400.3783
LUG WSA 13756.10589595 | 13756 | 0.24924 | 22 | 93 | 7 | 0 | 100 | 0 | Q2 - 2021 | Q4 - 2022 | Q2 - 2023 | 105022.372
LUG WSA 13756.60165355 | 13756 | 0.082955 | 12 | 55 | 10 | 3 | 68 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 115052.3412
LUG WSA 13756.90207831 | 13756 | 0.37917 | 36 | 181 | 18 | 1 | 200 | 44 | Q2 - 2021 | Q2 - 2023 | Q4 - 2023 | 59732.8746
LUG WSA 13860.10307212 | 13860 | 0.25227 | 28 | 2 | 20 | 9 | 31 | 0 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 172514.3964
LUG WSA 13860.10307215 | 13860 | 0.27917 | 26 | 219 | 17 | 4 | 240 | 3 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 255757.2254
LUG WSA 13863.60279838 | 13863 | 0.46989 | 32 | 259 | 5 | 0 | 264 | 2 | Q1 - 2021 | Q4 - 2022 | Q2 - 2023 | 340426.671
LUG WSA 13864.10310477 | 13864 | 0.7108 | 57 | 18 | 233 | 67 | 318 | 16 | Q3 - 2021 | Q3 - 2022 | Q1 - 2023 | 573160.295
LUG WSA 13864.10310497 | 13864 | 0.15 | 10 | 10 | 41 | 9 | 60 | 2 | Q2 - 2021 | Q4 - 2022 | Q2 - 2023 | 319952.477
LUG WSA 13864.10310505 | 13864 | 0.50568 | 41 | 3 | 49 | 31 | 83 | 6 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 491416.5619
LUG WSA 13864.60380454 | 13864 | 0.15795 | 13 | 1 | 1 | 1 | 3 | 1 | Q1 - 2021 | Q3 - 2021 | Q1 - 2022 | 47404.3375
LUG WSA 13865.90531031 | 13865 | 0.26383 | 19 | 21 | 11 | 5 | 37 | 9 | Q1 - 2021 | Q2 - 2023 | Q4 - 2023 | 59732.8746
LUG WSA 13870.90428273 | 13870 | 0.4017 | 25 | 104 | 8 | 0 | 112 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 318493.3002
LUG WSA 13873.60311122 | 13873 | 0.79261 | 61 | 235 | 7 | 3 | 245 | 3 | Q3 - 2021 | Q2 - 2023 | Q1 - 2024 | 79176.5874
LUG WSA 13892.10338448 | 13892 | 1.1121 | 71 | 256 | 8 | 2 | 266 | 2 | Q3 - 2021 | Q2 - 2023 | Q1 - 2024 | 59732.8746
LUG WSA 14030.60125643 | 14030 | 0.089205 | 14 | 101 | 3 | 0 | 104 | 1 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 70412.544
LUG WSA 14030.60341032 | 14030 | 0.13239 | 10 | 81 | 1 | 0 | 82 | 0 | Q2 - 2021 | Q2 - 2022 | Q4 - 2022 | 94885.4148
LUG WSA 14030.90886759 | 14030 | 0.53788 | 49 | 161 | 15 | 1 | 177 | 12 | Q2 - 2021 | Q2 - 2023 | Q1 - 2024 | 79176.5874
LUG WSA 14030.92669557 | 14030 | 0.0089015 | 5 | 78 | 12 | 0 | 90 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 91248.5228
LUG WSA 14030.92669942 | 14030 | 0.55814 | 34 | 112 | 6 | 0 | 118 | 0 | Q2 - 2021 | Q1 - 2023 | Q1 - 2024 | 66535.0346
LUG WSA 14030.92670479 | 14030 | 0.1089 | 6 | 3 | 3 | 0 | 6 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 100347.5571
Lateral Hardening-Fuse-10007252,1 | 13737 | 0.087689 | 9 | 4 | 0 | 1 | 5 | 0 | Q3 - 2022 | Q1 - 2023 | Q2 - 2023 | 28849.8106
Lateral Hardening-Fuse-10050730,3 | 13199 | 0.53106 | 52 | 271 | 22 | 0 | 293 | 0 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 174718.9393
Lateral Hardening-Fuse-10051863,1 | 13198 | 0.076705 | 10 | 62 | 5 | 0 | 67 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 25235.7955
Lateral Hardening-Fuse-10055000,2 | 13419 | 0.36061 | 28 | 33 | 11 | 0 | 44 | 0 | Q3 - 2022 | Q3 - 2022 | Q1 - 2023 | 118639.3939
Lateral Hardening-Fuse-10055941,1 | 13420 | 0.14659 | 10 | 4 | 1 | 1 | 6 | 0 | Q3 - 2022 | Q2 - 2023 | Q1 - 2024 | 48228.4091
Lateral Hardening-Fuse-10075304,1 | 13656 | 0.11136 | 4 | 2 | 0 | 1 | 3 | 3 | Q4 - 2022 | Q1 - 2024 | Q3 - 2024 | 36638.6364
Lateral Hardening-Fuse-10075336,1 | 13656 | 0.19432 | 15 | 17 | 2 | 5 | 24 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 63930.6818
Lateral Hardening-Fuse-10087587,1 | 13389 | 0.10019 | 6 | 5 | 4 | 0 | 9 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 32962.3106
Lateral Hardening-Fuse-10089965,1 | 13279 | 0.090341 | 12 | 10 | 2 | 1 | 13 | 0 | Q2 - 2022 | Q1 - 2025 | Q3 - 2025 | 29722.1591
Lateral Hardening-Fuse-10092875,1 | 13611 | 0.24659 | 26 | 119 | 2 | 1 | 122 | 75 | Q2 - 2022 | Q2 - 2023 | Q1 - 2024 | 81128.4091
Lateral Hardening-Fuse-10093646,2 | 13043 | 0.37652 | 26 | 47 | 2 | 1 | 50 | 0 | Q3 - 2022 | Q3 - 2022 | Q1 - 2023 | 123873.4848
Lateral Hardening-Fuse-10093658,1 | 13043 | 0.099621 | 11 | 19 | 1 | 1 | 21 | 0 | Q1 - 2022 | Q1 - 2023 | Q3 - 2023 | 32775.3788
Lateral Hardening-Fuse-10093683,1 | 13043 | 0.085038 | 8 | 8 | 4 | 2 | 14 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 27977.4621
Lateral Hardening-Fuse-10100716,1 | 13048 | 0.44186 | 44 | 85 | 2 | 1 | 88 | 12 | Q3 - 2022 | Q3 - 2022 | Q1 - 2023 | 145370.6439
Lateral Hardening-Fuse-10100722,1 | 13048 | 0.062121 | 6 | 14 | 4 | 0 | 18 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 20437.8788
Lateral Hardening-Fuse-10101247,3 | 13046 | 0.40795 | 41 | 57 | 2 | 2 | 61 | 5 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 134217.0454
Lateral Hardening-Fuse-10120786,1 | 13053 | 0.25511 | 28 | 73 | 11 | 0 | 84 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 83932.3864
Lateral Hardening-Fuse-10120788,1 | 13053 | 0.25644 | 23 | 38 | 2 | 1 | 41 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 84368.5606
Lateral Hardening-Fuse-10124545,1 | 13063 | 0.29337 | 26 | 43 | 3 | 1 | 47 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 96519.1288
Lateral Hardening-Fuse-10126980,1 | 13065 | 0.23466 | 23 | 35 | 4 | 0 | 39 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 77202.8409
Lateral Hardening-Fuse-10142238,1 | 13034 | 0.17992 | 15 | 16 | 1 | 1 | 18 | 0 | Q3 - 2022 | Q3 - 2022 | Q1 - 2023 | 59195.0758
Lateral Hardening-Fuse-10144159,1 | 13123 | 0.56117 | 38 | 8 | 34 | 3 | 45 | 17 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 184626.3258
Lateral Hardening-Fuse-10147338,1 | 13141 | 0.18939 | 22 | 56 | 2 | 0 | 58 | 0 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 62310.6061
Lateral Hardening-Fuse-10153131,1 | 13154 | 0.11023 | 14 | 5 | 14 | 4 | 23 | 10 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 36264.7727
Lateral Hardening-Fuse-10158932,1 | 13164 | 0.092045 | 10 | 12 | 0 | 1 | 13 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 30282.9545
Lateral Hardening-Fuse-10160212,1 | 13167 | 0.072348 | 8 | 51 | 4 | 0 | 55 | 0 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 23802.6515
Lateral Hardening-Fuse-10163224,4 | 13091 | 0.41193 | 41 | 50 | 7 | 0 | 57 | 0 | Q2 - 2022 | Q2 - 2022 | Q1 - 2023 | 135525.5681
Lateral Hardening-Fuse-10163228,1 | 13091 | 0.13864 | 15 | 16 | 10 | 0 | 26 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 45611.3636
Lateral Hardening-Fuse-10165356,4 | 13045 | 0.67973 | 62 | 81 | 15 | 4 | 100 | 7 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 223632.765
Lateral Hardening-Fuse-10165381,2 | 13045 | 0.30663 | 28 | 53 | 14 | 3 | 70 | 0 | Q2 - 2022 | Q2 - 2023 | Q1 - 2024 | 100880.8712
Lateral Hardening-Fuse-10165382,1 | 13045 | 0.035227 | 5 | 6 | 10 | 1 | 17 | 0 | Q3 - 2022 | Q2 - 2023 | Q1 - 2024 | 13160
Lateral Hardening-Fuse-10165789,1 | 13072 | 0.22235 | 18 | 16 | 13 | 3 | 32 | 8 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 73152.6515
Lateral Hardening-Fuse-10165797,1 | 13072 | 0.14659 | 15 | 6 | 6 | 1 | 13 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 48228.4091
Lateral Hardening-Fuse-10165803,1 | 13072 | 0.11894 | 12 | 8 | 1 | 2 | 11 | 0 | Q2 - 2022 | Q1 - 2024 | Q2 - 2024 | 39131.0606
Lateral Hardening-Fuse-10167762,1 | 13206 | 0.18409 | 20 | 24 | 3 | 1 | 28 | 2 | Q3 - 2022 | Q1 - 2024 | Q2 - 2024 | 60565.9091
Lateral Hardening-Fuse-10173494,1 | 13191 | 0.20587 | 20 | 20 | 1 | 2 | 23 | 1 | Q2 - 2022 | Q2 - 2023 | Q1 - 2024 | 67731.6288
Lateral Hardening-Fuse-10173500,1 | 13191 | 0.21439 | 17 | 47 | 5 | 0 | 52 | 0 | Q3 - 2022 | Q1 - 2024 | Q2 - 2024 | 70535.6061
Lateral Hardening-Fuse-10173522,1 | 13191 | 0.34867 | 34 | 4 | 25 | 8 | 37 | 9 | Q2 - 2022 | Q1 - 2024 | Q2 - 2024 | 114713.8258
Lateral Hardening-Fuse-10218987,1 | 13510 | 0.085227 | 10 | 206 | 11 | 2 | 219 | 1 | Q3 - 2022 | Q1 - 2024 | Q2 - 2024 | 28039.7727
Lateral Hardening-Fuse-10247860,1 | 13533 | 0.035985 | 5 | 45 | 2 | 0 | 47 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 13160
Lateral Hardening-Fuse-10274748,1 | 13624 | 0.27955 | 19 | 22 | 3 | 0 | 25 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 91970.4545
Lateral Hardening-Fuse-10297412,1 | 13754 | 0.059091 | 8 | 10 | 0 | 1 | 11 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 19440.9091
Lateral Hardening-Fuse-10297440,1 | 13754 | 0.11572 | 14 | 87 | 3 | 0 | 90 | 0 | Q2 - 2022 | Q1 - 2024 | Q2 - 2024 | 38071.7803
Lateral Hardening-Fuse-10297442,1 | 13754 | 0.13788 | 16 | 33 | 12 | 2 | 47 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 45362.1212
Lateral Hardening-Fuse-10361894,1 | 13106 | 0.1322 | 10 | 35 | 2 | 2 | 39 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 43492.803
Lateral Hardening-Fuse-10362869,3 | 13104 | 0.62443 | 47 | 67 | 20 | 3 | 90 | 0 | Q3 - 2022 | Q3 - 2022 | Q1 - 2023 | 63016.4153
Lateral Hardening-Fuse-10363933,1 | 13096 | 0.13068 | 8 | 6 | 2 | 1 | 9 | 8 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 42994.3182
Lateral Hardening-Fuse-10382337,1 | 13224 | 0.087121 | 10 | 15 | 2 | 1 | 18 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 28662.8788
Lateral Hardening-Fuse-10384706,1 | 13351 | 0.10985 | 8 | 26 | 3 | 0 | 29 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 36140.1515
Lateral Hardening-Fuse-10384723,1 | 13351 | 0.25587 | 20 | 65 | 6 | 1 | 72 | 1 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 84181.6288
Lateral Hardening-Fuse-10389247,2 | 13365 | 0.38163 | 35 | 206 | 6 | 0 | 212 | 0 | Q3 - 2022 | Q3 - 2022 | Q1 - 2023 | 125555.8711
Lateral Hardening-Fuse-10392877,1 | 13522 | 0.093371 | 11 | 10 | 2 | 1 | 13 | 8 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 30719.1288
Lateral Hardening-Fuse-10424221,1 | 13828 | 0.047538 | 4 | 2 | 1 | 6 | 9 | 8 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 15639.9621
Lateral Hardening-Fuse-10425054,1 | 13829 | 0.11894 | 9 | 48 | 7 | 0 | 55 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 39131.0606
Lateral Hardening-Fuse-10427678,1 | 13831 | 0.046402 | 4 | 36 | 3 | 0 | 39 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 15266.0985
Lateral Hardening-Fuse-10429550,1 | 13835 | 0.20909 | 16 | 32 | 5 | 0 | 37 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 68790.9091
Lateral Hardening-Fuse-10457713,1 | 13229 | 0.054735 | 8 | 42 | 4 | 0 | 46 | 7 | Q2 - 2022 | Q1 - 2024 | Q4 - 2024 | 18007.7652
Lateral Hardening-Fuse-10475330,1 | 14117 | 0.15985 | 14 | 5 | 5 | 3 | 13 | 0 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 52590.1515
Lateral Hardening-Fuse-10477228,1 | 13326 | 0.18864 | 14 | 8 | 16 | 5 | 29 | 0 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 62061.3636
Lateral Hardening-Fuse-10535991,1 | 13115 | 0.25492 | 20 | 25 | 0 | 1 | 26 | 0 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 83870.0758
Lateral Hardening-Fuse-10545847,1 | 13910 | 0.084659 | 6 | 6 | 1 | 1 | 8 | 1 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 27852.8409
Lateral Hardening-Fuse-10565125,1 | 13291 | 0.16572 | 16 | 19 | 1 | 1 | 21 | 0 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 54521.7803
Lateral Hardening-Fuse-10565130,1 | 13291 | 0.21439 | 20 | 20 | 3 | 1 | 24 | 0 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 70535.6061
Lateral Hardening-Fuse-10565136,1 | 13291 | 0.13447 | 13 | 14 | 3 | 2 | 19 | 0 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 44240.5303
Lateral Hardening-Fuse-10565887,1 | 13290 | 0.34735 | 34 | 129 | 7 | 0 | 136 | 0 | Q1 - 2022 | Q1 - 2025 | Q4 - 2025 | 114277.6515
Lateral Hardening-Fuse-10565895,1 | 13290 | 0.071023 | 9 | 15 | 5 | 0 | 20 | 0 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 23366.4773
Lateral Hardening-Fuse-10572982,1 | 13371 | 0.17102 | 15 | 17 | 9 | 0 | 26 | 0 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 56266.4773
Lateral Hardening-Fuse-10589590,1 | 13756 | 0.1428 | 21 | 29 | 2 | 0 | 31 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 46982.197
Lateral Hardening-Fuse-10616460,1 | 13124 | 0.068182 | 8 | 11 | 1 | 0 | 12 | 0 | Q4 - 2022 | Q1 - 2024 | Q3 - 2024 | 22431.8182
Lateral Hardening-Fuse-10625698,1 | 13011 | 0.24848 | 21 | 28 | 2 | 0 | 30 | 0 | Q4 - 2022 | Q1 - 2024 | Q3 - 2024 | 81751.5152
Lateral Hardening-Fuse-10632726,1 | 13312 | 0.11951 | 17 | 7 | 7 | 3 | 17 | 0 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 39317.9924
Lateral Hardening-Fuse-10632727,1 | 13312 | 0.12367 | 12 | 24 | 14 | 0 | 38 | 0 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 40688.8258
Lateral Hardening-Fuse-10633695,1 | 13241 | 0.064394 | 4 | 8 | 3 | 0 | 11 | 0 | Q3 - 2022 | Q1 - 2025 | Q4 - 2025 | 21185.6061
Lateral Hardening-Fuse-10637218,1 | 13696 | 0.24261 | 26 | 25 | 7 | 0 | 32 | 0 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 79819.8864
Lateral Hardening-Fuse-10640103,1 | 13724 | 0.18409 | 16 | 2 | 4 | 3 | 9 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 60565.9091
Lateral Hardening-Fuse-10668889,1 | 13723 | 0.50625 | 20 | 29 | 4 | 0 | 33 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 166556.25
Lateral Hardening-Fuse-10671179,1 | 13724 | 0.030492 | 5 | 2 | 2 | 0 | 4 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 13160
Lateral Hardening-Fuse-10674224,1 | 13414 | 0.095076 | 9 | 7 | 0 | 1 | 8 | 0 | Q4 - 2022 | Q1 - 2024 | Q3 - 2024 | 31279.9242
Lateral Hardening-Fuse-10674240,1 | 13414 | 0.17121 | 14 | 21 | 3 | 1 | 25 | 6 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 56328.7879
Lateral Hardening-Fuse-10674784,1 | 13464 | 0.49337 | 33 | 55 | 3 | 0 | 58 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 162319.1288
Lateral Hardening-Fuse-10675160,1 | 13464 | 0.21023 | 10 | 21 | 7 | 0 | 28 | 2 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 69164.7727
Lateral Hardening-Fuse-10686006,1 | 13808 | 0.28788 | 19 | 2 | 0 | 3 | 5 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 94712.1212
Lateral Hardening-Fuse-10688316,1 | 13068 | 0.10246 | 10 | 9 | 7 | 0 | 16 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 33710.0379
Lateral Hardening-Fuse-10692795,1 | 13463 | 0.072727 | 6 | 12 | 2 | 0 | 14 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 23927.2727
Lateral Hardening-Fuse-10692803,1 | 13463 | 0.088636 | 7 | 13 | 2 | 0 | 15 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 29161.3636
Lateral Hardening-Fuse-10696420,1 | 13961 | 0.071591 | 9 | 18 | 2 | 0 | 20 | 0 | Q4 - 2022 | Q1 - 2024 | Q3 - 2024 | 23553.4091
Lateral Hardening-Fuse-10696464,1 | 13961 | 0.051136 | 4 | 2 | 2 | 0 | 4 | 0 | Q4 - 2022 | Q1 - 2024 | Q3 - 2024 | 16823.8636
Lateral Hardening-Fuse-10710623,1 | 14000 | 0.19451 | 14 | 5 | 4 | 0 | 9 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 63992.9924
Lateral Hardening-Fuse-10716303,1 | 13959 | 0.28542 | 17 | 14 | 2 | 0 | 16 | 0 | Q4 - 2022 | Q1 - 2024 | Q3 - 2024 | 93902.0833
Lateral Hardening-Fuse-10716315,1 | 13959 | 0.097159 | 9 | 17 | 4 | 0 | 21 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 31965.3409
Lateral Hardening-Fuse-10716318,1 | 13959 | 0.087121 | 7 | 1 | 1 | 0 | 2 | 0 | Q4 - 2022 | Q3 - 2023 | Q1 - 2024 | 28662.8788
Lateral Hardening-Fuse-10791877,1 | 13243 | 0.085038 | 6 | 43 | 0 | 1 | 44 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 27977.4621
Lateral Hardening-Fuse-10791889,1 | 13243 | 0.26117 | 18 | 48 | 5 | 0 | 53 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 85926.3258
Lateral Hardening-Fuse-10823013,1 | 13651 | 0.17348 | 12 | 39 | 3 | 2 | 44 | 5 | Q2 - 2022 | Q1 - 2025 | Q3 - 2025 | 57076.5152
Lateral Hardening-Fuse-10916743,1 | 13805 | 0.32689 | 16 | 5 | 2 | 1 | 8 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 107548.1061
Lateral Hardening-Fuse-10928275,1 | 13143 | 0.094318 | 10 | 17 | 12 | 0 | 29 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 31030.6818
Lateral Hardening-Fuse-10933157,1 | 13896 | 0.27557 | 16 | 9 | 12 | 0 | 21 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 90661.9318
Lateral Hardening-Fuse-60005954,1 | 13899 | 0.16761 | 13 | 5 | 2 | 1 | 8 | 0 | Q2 - 2022 | Q1 - 2025 | Q3 - 2025 | 55144.8864
Lateral Hardening-Fuse-60008652,1 | 13081 | 0.082576 | 9 | 26 | 5 | 0 | 31 | 0 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 27167.4242
Lateral Hardening-Fuse-60011392,1 | 13047 | 0.24432 | 25 | 37 | 1 | 1 | 39 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 80380.6818
Lateral Hardening-Fuse-60013778,1 | 13094 | 0.25455 | 27 | 84 | 7 | 1 | 92 | 2 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 83745.4545
Lateral Hardening-Fuse-60015117,1 | 13008 | 0.26951 | 18 | 28 | 2 | 2 | 32 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 88667.9924
Lateral Hardening-Fuse-60015427,1 | 13008 | 0.35568 | 19 | 6 | 1 | 2 | 9 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 117019.3182
Lateral Hardening-Fuse-60016282,1 | 13049 | 0.058712 | 5 | 31 | 0 | 1 | 32 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 19316.2879
Lateral Hardening-Fuse-60016353,1 | 13049 | 0.074621 | 9 | 9 | 1 | 1 | 11 | 4 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 24550.3788
Lateral Hardening-Fuse-60017429,2 | 13029 | 0.42519 | 40 | 4 | 21 | 15 | 40 | 7 | Q3 - 2022 | Q3 - 2022 | Q1 - 2023 | 139887.3105
Lateral Hardening-Fuse-60028650,1 | 13007 | 0.098864 | 10 | 15 | 5 | 1 | 21 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 32526.1364
Lateral Hardening-Fuse-60029011,1 | 13088 | 0.073485 | 9 | 6 | 11 | 1 | 18 | 0 | Q3 - 2022 | Q3 - 2022 | Q1 - 2023 | 24176.5152
Lateral Hardening-Fuse-60029776,1 | 13093 | 0.28617 | 29 | 61 | 2 | 1 | 64 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 94151.3258
Lateral Hardening-Fuse-60029925,3 | 13091 | 0.5678 | 53 | 101 | 12 | 0 | 113 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 186807.1969
Lateral Hardening-Fuse-60031511,1 | 13093 | 0.18068 | 16 | 28 | 0 | 1 | 29 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 59444.3182
Lateral Hardening-Fuse-60033370,1 | 13163 | 0.12803 | 12 | 17 | 12 | 3 | 32 | 0 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 42121.9697
Lateral Hardening-Fuse-60033388,1 | 13163 | 0.17955 | 18 | 19 | 17 | 1 | 37 | 10 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 59070.4545
Lateral Hardening-Fuse-60034479,1 | 13143 | 0.30189 | 32 | 48 | 1 | 0 | 49 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 99323.1061
Lateral Hardening-Fuse-60044927,1 | 13288 | 0.17008 | 22 | 15 | 9 | 6 | 30 | 1 | Q2 - 2022 | Q1 - 2025 | Q3 - 2025 | 55954.9242
Lateral Hardening-Fuse-60046437,1 | 13310 | 0.19072 | 19 | 46 | 9 | 3 | 58 | 0 | Q2 - 2022 | Q1 - 2025 | Q3 - 2025 | 62746.7803
Lateral Hardening-Fuse-60047463,1 | 13350 | 0.11288 | 10 | 64 | 6 | 0 | 70 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 37137.1212
Lateral Hardening-Fuse-60048514,1 | 13405 | 0.12992 | 6 | 2 | 2 | 2 | 6 | 6 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 42745.0758
Lateral Hardening-Fuse-60048809,1 | 13622 | 0.14659 | 6 | 3 | 3 | 0 | 6 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 48228.4091
Lateral Hardening-Fuse-60058546,1 | 13279 | 0.10871 | 10 | 15 | 9 | 1 | 25 | 0 | Q2 - 2022 | Q1 - 2025 | Q3 - 2025 | 35766.2879
Lateral Hardening-Fuse-60058616,1 | 13610 | 0.11534 | 14 | 17 | 3 | 1 | 21 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 37947.1591
Lateral Hardening-Fuse-60060554,1 | 13175 | 0.17822 | 16 | 14 | 6 | 0 | 20 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 58634.2803
Lateral Hardening-Fuse-60060564,1 | 13175 | 0.12955 | 13 | 20 | 5 | 0 | 25 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 42620.4545
Lateral Hardening-Fuse-60060568,1 | 13175 | 0.096023 | 13 | 16 | 6 | 0 | 22 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 31591.4773
Lateral Hardening-Fuse-60061785,1 | 13668 | 0.094886 | 5 | 288 | 17 | 2 | 307 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 31217.6136
Lateral Hardening-Fuse-60065898,1 | 14275 | 0.03447 | 9 | 2 | 2 | 0 | 4 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 13160
Lateral Hardening-Fuse-60073788,1 | 13082 | 0.24583 | 25 | 40 | 5 | 1 | 46 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 80879.1667
Lateral Hardening-Fuse-60073803,1 | 13082 | 0.16155 | 18 | 31 | 2 | 0 | 33 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 53150.947
Lateral Hardening-Fuse-60077860,1 | 13153 | 0.10625 | 10 | 13 | 0 | 3 | 16 | 0 | Q2 - 2022 | Q1 - 2025 | Q3 - 2025 | 34956.25
Lateral Hardening-Fuse-60087052,1 | 13359 | 0.059848 | 7 | 29 | 8 | 4 | 41 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 19690.1515
Lateral Hardening-Fuse-60088186,1 | 13139 | 0.21951 | 18 | 27 | 4 | 0 | 31 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 72217.9924
Lateral Hardening-Fuse-60088567,1 | 13510 | 0.29867 | 34 | 25 | 4 | 0 | 29 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 98263.8258
Lateral Hardening-Fuse-60124027,1 | 13218 | 0.63977 | 53 | 64 | 9 | 0 | 73 | 0 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 210485.2273
Lateral Hardening-Fuse-60181011,1 | 13388 | 0.11951 | 7 | 6 | 2 | 0 | 8 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 39317.9924
Lateral Hardening-Fuse-60190659,1 | 13308 | 0.21572 | 15 | 15 | 9 | 2 | 26 | 0 | Q2 - 2022 | Q1 - 2025 | Q3 - 2025 | 70971.7803
Lateral Hardening-Fuse-60200737,1 | 13961 | 0.078788 | 7 | 7 | 1 | 0 | 8 | 0 | Q4 - 2022 | Q3 - 2023 | Q1 - 2024 | 25921.2121
Lateral Hardening-Fuse-60241209,1 | 13137 | 0.09072 | 10 | 159 | 4 | 0 | 163 | 0 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 29846.7803
Lateral Hardening-Fuse-60289071,1 | 13045 | 0.098485 | 12 | 12 | 3 | 1 | 16 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 32401.5152
Lateral Hardening-Fuse-60302651,1 | 13091 | 0.15833 | 13 | 28 | 14 | 0 | 42 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 52091.6667
Lateral Hardening-Fuse-60305740,1 | 13865 | 0.13996 | 15 | 38 | 4 | 0 | 42 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 46047.5379
Lateral Hardening-Fuse-60337684,1 | 14001 | 0.055492 | 4 | 2 | 14 | 0 | 16 | 0 | Q4 - 2022 | Q2 - 2023 | Q4 - 2023 | 18257.0076
Lateral Hardening-Fuse-60350024,5 | 13097 | 1.3943 | 92 | 67 | 9 | 2 | 78 | 0 | Q2 - 2022 | Q1 - 2024 | Q4 - 2024 | 458730.6816
Lateral Hardening-Fuse-60365361,1 | 13962 | 0.064394 | 6 | 5 | 0 | 1 | 6 | 0 | Q3 - 2022 | Q1 - 2023 | Q3 - 2023 | 21185.6061
Lateral Hardening-Fuse-60422059,1 | 13723 | 0.31345 | 21 | 45 | 16 | 2 | 63 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 103124.053
Lateral Hardening-Fuse-60463714,1 | 13853 | 0.21269 | 16 | 3 | 8 | 7 | 18 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 69974.8106
Lateral Hardening-Fuse-60474882,1 | 13191 | 0.25587 | 32 | 11 | 29 | 9 | 49 | 6 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 84181.6288
Lateral Hardening-Fuse-60518342,1 | 13219 | 0.13201 | 10 | 5 | 8 | 4 | 17 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 43430.4924
Lateral Hardening-Fuse-60614298,1 | 13740 | 0.17008 | 17 | 20 | 13 | 0 | 33 | 0 | Q2 - 2022 | Q1 - 2023 | Q3 - 2024 | 55954.9242
Lateral Hardening-Fuse-90097474,7 | 13754 | 1.9714 | 170 | 200 | 18 | 2 | 220 | 0 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 648591.0981
Lateral Hardening-Fuse-90098676,4 | 13190 | 2.1623 | 170 | 445 | 19 | 0 | 464 | 9 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 711400.189
Lateral Hardening-Fuse-90152415,1 | 13208 | 0.083333 | 8 | 13 | 15 | 1 | 29 | 0 | Q2 - 2022 | Q1 - 2023 | Q3 - 2023 | 27416.6667
Lateral Hardening-Fuse-90157556,1 | 13067 | 0.19261 | 18 | 12 | 6 | 0 | 18 | 5 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 63369.8864
Lateral Hardening-Fuse-90165527,1 | 13431 | 0.1947 | 12 | 4 | 2 | 1 | 7 | 0 | Q3 - 2022 | Q1 - 2023 | Q3 - 2023 | 64055.303
Lateral Hardening-Fuse-90179103,1 | 13630 | 0.23807 | 17 | 19 | 17 | 0 | 36 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 78324.4318
Lateral Hardening-Fuse-90211134,1 | 13162 | 0.082955 | 10 | 23 | 2 | 0 | 25 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 27292.0455
Lateral Hardening-Fuse-90267141,1 | 13738 | 0.02803 | 8 | 305 | 5 | 5 | 315 | 1 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 13160
Lateral Hardening-Fuse-90297635,1 | 13007 | 0.12879 | 12 | 11 | 0 | 1 | 12 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 42371.2121
Lateral Hardening-Fuse-90377733,1 | 13389 | 0.11496 | 9 | 3 | 0 | 1 | 4 | 3 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 37822.5379
Lateral Hardening-Fuse-90393849,1 | 13147 | 0.07822 | 5 | 21 | 4 | 0 | 25 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 25734.2803
Lateral Hardening-Fuse-90398961,1 | 13795 | 0.070265 | 7 | 20 | 2 | 1 | 23 | 0 | Q2 - 2022 | Q1 - 2025 | Q3 - 2025 | 23117.2348
Lateral Hardening-Fuse-90399851,6 | 13419 | 0.76402 | 64 | 111 | 2 | 3 | 116 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 251360.9847
Lateral Hardening-Fuse-90416605,1 | 13081 | 0.089773 | 10 | 222 | 2 | 1 | 225 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 29535.2273
Lateral Hardening-Fuse-90441325,1 | 13612 | 0.072727 | 8 | 7 | 6 | 1 | 14 | 6 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 23927.2727
Lateral Hardening-Fuse-90482454,4 | 13206 | 0.6786 | 58 | 73 | 18 | 0 | 91 | 0 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 223258.9014
Lateral Hardening-Fuse-90487798,1 | 13740 | 0.12197 | 6 | 9 | 6 | 0 | 15 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 40128.0303
Lateral Hardening-Fuse-90522517,5 | 13359 | 1.2025 | 115 | 125 | 2 | 1 | 128 | 1 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 395610.0377
Lateral Hardening-Fuse-90526768,1 | 13199 | 0.18485 | 15 | 20 | 3 | 0 | 23 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 60815.1515
Lateral Hardening-Fuse-90630567,1 | 13754 | 0.13144 | 14 | 13 | 2 | 1 | 16 | 5 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 43243.5606
Lateral Hardening-Fuse-90668793,1 | 14042 | 0.18674 | 12 | 55 | 1 | 2 | 58 | 1 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 61438.2576
Lateral Hardening-Fuse-90704066,4 | 13370 | 0.78201 | 65 | 16 | 20 | 9 | 45 | 1 | Q1 - 2022 | Q4 - 2024 | Q2 - 2025 | 257280.4923
Lateral Hardening-Fuse-90748138,1 | 13103 | 0.083712 | 8 | 9 | 5 | 0 | 14 | 0 | Q3 - 2022 | Q2 - 2022 | Q4 - 2022 | 27541.2879
Lateral Hardening-Fuse-90823812,1 | 13329 | 0.049811 | 4 | 7 | 0 | 1 | 8 | 0 | Q3 - 2022 | Q2 - 2022 | Q4 - 2022 | 16387.6894
Lateral Hardening-Fuse-90830976,1 | 13328 | 0.081818 | 8 | 3 | 1 | 2 | 6 | 0 | Q3 - 2022 | Q2 - 2022 | Q4 - 2022 | 26918.1818
Lateral Hardening-Fuse-90847913,1 | 13754 | 0.24602 | 25 | 55 | 5 | 1 | 61 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 80941.4773
Lateral Hardening-Fuse-90848130,1 | 13656 | 0.16723 | 11 | 9 | 0 | 1 | 10 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 55020.2652
Lateral Hardening-Fuse-90852788,1 | 13148 | 0.34527 | 23 | 10 | 3 | 1 | 14 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 113592.2348
Lateral Hardening-Fuse-91016874,2 | 13046 | 0.37519 | 34 | 52 | 4 | 3 | 59 | 7 | Q3 - 2022 | Q3 - 2022 | Q1 - 2023 | 123437.3105
Lateral Hardening-Fuse-91060899,1 | 13533 | 0.22746 | 21 | 142 | 3 | 1 | 146 | 1 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 74835.0379
Lateral Hardening-Fuse-91066431,1 | 13163 | 0.22614 | 15 | 18 | 3 | 3 | 24 | 0 | Q3 - 2022 | Q3 - 2022 | Q1 - 2023 | 74398.8636
Lateral Hardening-Fuse-91076397,1 | 13048 | 0.056439 | 7 | 3 | 0 | 3 | 6 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 18568.5606
Lateral Hardening-Fuse-91096289,1 | 13787 | 0.091288 | 6 | 3 | 1 | 0 | 4 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 30033.7121
Lateral Hardening-Fuse-91147533,3 | 13097 | 0.67197 | 41 | 39 | 5 | 1 | 45 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 221078.0302
Lateral Hardening-Fuse-91151734,1 | 13364 | 0.092992 | 9 | 52 | 0 | 1 | 53 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 30594.5076
Lateral Hardening-Fuse-91154995,2 | 13048 | 0.53049 | 50 | 74 | 3 | 2 | 79 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 174532.0075
Lateral Hardening-Fuse-91161524,1 | 13146 | 0.23845 | 15 | 16 | 1 | 1 | 18 | 6 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 78449.053
Lateral Hardening-Fuse-91177941,3 | 13638 | 0.86534 | 82 | 79 | 12 | 1 | 92 | 1 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 284697.1589
Lateral Hardening-Fuse-91232937,1 | 13103 | 0.48939 | 47 | 117 | 7 | 0 | 124 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 161010.6061
Lateral Hardening-Fuse-91234338,1 | 13124 | 0.4589 | 33 | 56 | 3 | 0 | 59 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 150978.5985
Lateral Hardening-Fuse-91334566,1 | 13464 | 0.38182 | 27 | 60 | 1 | 1 | 62 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 125618.1818
Lateral Hardening-Fuse-91337725,1 | 13464 | 0.20246 | 13 | 11 | 2 | 2 | 15 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 66610.0379
Lateral Hardening-Fuse-91354294,1 | 13065 | 0.16307 | 18 | 136 | 10 | 1 | 147 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 53649.4318
Lateral Hardening-Fuse-91382618,1 | 13462 | 0.31932 | 27 | 51 | 3 | 4 | 58 | 3 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 105055.6818
Lateral Hardening-Fuse-91404359,1 | 13805 | 0.56023 | 28 | 35 | 9 | 0 | 44 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 184314.7727
Lateral Hardening-Fuse-91418404,1 | 13621 | 0.15777 | 11 | 10 | 2 | 0 | 12 | 0 | Q3 - 2022 | Q4 - 2023 | Q2 - 2024 | 51904.7348
Lateral Hardening-Fuse-91421327,1 | 13124 | 0.10057 | 14 | 1 | 4 | 4 | 9 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 33086.9318
Lateral Hardening-Fuse-91532289,1 | 13832 | 0.10227 | 11 | 12 | 22 | 1 | 35 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 33647.7273
Lateral Hardening-Fuse-91532301,1 | 13832 | 0.087121 | 7 | 10 | 7 | 0 | 17 | 0 | Q3 - 2022 | Q2 - 2022 | Q1 - 2023 | 28662.8788
Lateral Hardening-Fuse-91550764,1 | 13592 | 0.061553 | 4 | 16 | 3 | 1 | 20 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 20250.947
Lateral Hardening-Fuse-91565159,4 | 13044 | 0.51345 | 55 | 14 | 1 | 1 | 16 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 168924.0529
Lateral Hardening-Fuse-91623641,1 | 13141 | 0.15038 | 19 | 39 | 3 | 1 | 43 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 49474.6212
Lateral Hardening-Fuse-91643964,1 | 13106 | 0.13144 | 12 | 123 | 9 | 0 | 132 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 43243.5606
Lateral Hardening-Fuse-91702481,1 | 14012 | 0.077273 | 8 | 1 | 0 | 1 | 2 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 25422.7273
Lateral Hardening-Fuse-91774500,1 | 13631 | 0.28409 | 21 | 56 | 17 | 0 | 73 | 16 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 93465.9091
Lateral Hardening-Fuse-91782844,1 | 13434 | 0.15379 | 13 | 7 | 0 | 2 | 9 | 0 | Q2 - 2022 | Q4 - 2024 | Q2 - 2025 | 50596.2121
Lateral Hardening-Fuse-91868130,1 | 13201 | 0.11098 | 11 | 123 | 3 | 1 | 127 | 0 | Q3 - 2022 | Q4 - 2023 | Q2 - 2024 | 36514.0152
Lateral Hardening-Fuse-91910924,1 | 13165 | 0.23409 | 20 | 53 | 5 | 5 | 63 | 3 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 77015.9091
Lateral Hardening-Fuse-92005809,1 | 13219 | 0.23939 | 24 | 42 | 11 | 1 | 54 | 0 | Q2 - 2022 | Q4 - 2023 | Q2 - 2024 | 78760.6061
Lateral Hardening-Fuse-92027991,1 | 13420 | 0.23731 | 18 | 24 | 7 | 0 | 31 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 78075.1894
Lateral Hardening-Fuse-92035203,1 | 13417 | 0.079924 | 9 | 30 | 4 | 0 | 34 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 26295.0758
Lateral Hardening-Fuse-92079502,1 | 13638 | 0.12955 | 15 | 41 | 12 | 2 | 55 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 42620.4545
Lateral Hardening-Fuse-92097014,1 | 13217 | 0.19053 | 11 | 16 | 1 | 1 | 18 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 62684.4697
Lateral Hardening-Fuse-92132257,1 | 13016 | 0.12102 | 13 | 57 | 4 | 0 | 61 | 0 | Q3 - 2022 | Q4 - 2023 | Q2 - 2024 | 39816.4773
Lateral Hardening-Fuse-92197131,1 | 13330 | 0.18655 | 13 | 73 | 2 | 1 | 76 | 1 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 61375.947
Lateral Hardening-Fuse-92238609,1 | 13065 | 0.13617 | 13 | 25 | 2 | 0 | 27 | 0 | Q3 - 2022 | Q4 - 2023 | Q2 - 2024 | 44801.3258
Lateral Hardening-Fuse-92257437,1 | 13227 | 0.14773 | 19 | 12 | 9 | 0 | 21 | 0 | Q2 - 2022 | Q4 - 2023 | Q2 - 2024 | 48602.2727
Lateral Hardening-Fuse-92320131,1 | 13656 | 0.24205 | 16 | 8 | 3 | 2 | 13 | 3 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 79632.9545
Lateral Hardening-Fuse-92354169,1 | 13787 | 0.13807 | 6 | 2 | 2 | 4 | 8 | 5 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 45424.4318
Lateral Hardening-Fuse-92398222,1 | 13167 | 0.11799 | 15 | 11 | 0 | 2 | 13 | 0 | Q3 - 2022 | Q4 - 2023 | Q2 - 2025 | 38819.5076
Lateral Hardening-Fuse-92408051,1 | 13140 | 0.088636 | 10 | 40 | 7 | 1 | 48 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 29161.3636
Lateral Hardening-Fuse-92418323,1 | 13696 | 0.059848 | 8 | 111 | 3 | 0 | 114 | 0 | Q2 - 2022 | Q4 - 2024 | Q2 - 2025 | 19690.1515
Lateral Hardening-Fuse-92448697,1 | 13510 | 0.040341 | 5 | 5 | 2 | 2 | 9 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 13272.1591
Lateral Hardening-Fuse-92486363,1 | 13312 | 0.22292 | 17 | 16 | 3 | 1 | 20 | 0 | Q2 - 2022 | Q4 - 2023 | Q2 - 2024 | 73339.5833
Lateral Hardening-Fuse-92497118,1 | 13146 | 0.22746 | 8 | 4 | 2 | 0 | 6 | 0 | Q4 - 2022 | Q3 - 2023 | Q1 - 2024 | 74835.0379
Lateral Hardening-Fuse-92527630,1 | 13219 | 0.1089 | 8 | 17 | 1 | 1 | 19 | 1 | Q3 - 2022 | Q4 - 2023 | Q2 - 2024 | 35828.5985
Lateral Hardening-Fuse-92527637,1 | 13219 | 0.21364 | 24 | 38 | 2 | 1 | 41 | 0 | Q3 - 2022 | Q4 - 2023 | Q2 - 2024 | 70286.3636
Lateral Hardening-Fuse-92529635,1 | 13210 | 0.10852 | 12 | 13 | 3 | 0 | 16 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 35703.9773
Lateral Hardening-Fuse-92529638,1 | 13210 | 0.087121 | 10 | 21 | 1 | 1 | 23 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 28662.8788
Lateral Hardening-Fuse-92537158,1 | 13150 | 0.071591 | 7 | 10 | 0 | 2 | 12 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 23553.4091
Lateral Hardening-Fuse-92543665,1 | 13004 | 0.28049 | 23 | 70 | 5 | 0 | 75 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 92282.0076
Lateral Hardening-Fuse-92570284,1 | 13020 | 0.068182 | 3 | 9 | 1 | 4 | 14 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 22431.8182
Lateral Hardening-Fuse-92597622,1 | 13390 | 0.18958 | 12 | 42 | 6 | 0 | 48 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 62372.9167
Lateral Hardening-Fuse-92599120,1 | 13390 | 0.61686 | 37 | 45 | 5 | 0 | 50 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 202945.6439
Lateral Hardening-Fuse-92602262,1 | 13010 | 0.094508 | 6 | 15 | 2 | 0 | 17 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 31092.9924
Lateral Hardening-Fuse-92603717,1 | 13390 | 0.24886 | 15 | 32 | 4 | 0 | 36 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 81876.1364
Lateral Hardening-Fuse-92605327,1 | 13390 | 0.20511 | 16 | 65 | 15 | 0 | 80 | 21 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 67482.3864
Lateral Hardening-Fuse-92605381,1 | 13390 | 0.34583 | 33 | 130 | 4 | 0 | 134 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 113779.1667
Lateral Hardening-Fuse-92609981,1 | 13390 | 0.17083 | 13 | 31 | 3 | 0 | 34 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 56204.1667
Lateral Hardening-Fuse-92610250,1 | 13390 | 0.92689 | 46 | 48 | 11 | 0 | 59 | 5 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 304948.1061
Lateral Hardening-Fuse-92612860,1 | 13390 | 0.44924 | 27 | 17 | 3 | 0 | 20 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 147800.7576
Lateral Hardening-Fuse-92620889,1 | 13390 | 0.24129 | 15 | 66 | 3 | 0 | 69 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 79383.7121
Lateral Hardening-Fuse-92622569,1 | 13390 | 0.61155 | 30 | 86 | 11 | 4 | 101 | 5 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 201200.947
Lateral Hardening-Fuse-92655421,1 | 13198 | 0.075189 | 6 | 8 | 2 | 0 | 10 | 0 | Q3 - 2022 | Q4 - 2023 | Q2 - 2024 | 24737.3106
Lateral Hardening-Fuse-92678765,1 | 13805 | 0.19432 | 12 | 3 | 3 | 0 | 6 | 0 | Q3 - 2022 | Q2 - 2022 | Q4 - 2022 | 63930.6818
Lateral Hardening-Fuse-92701725,1 | 13299 | 0.1839 | 13 | 123 | 28 | 2 | 153 | 2 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 60503.5985
Lateral Hardening-Fuse-92773510,1 | 13373 | 0.3197 | 27 | 13 | 13 | 0 | 26 | 0 | Q1 - 2022 | Q3 - 2024 | Q1 - 2025 | 105180.303
Lateral Hardening-Fuse-92814355,1 | 13344 | 0.047727 | 7 | 37 | 5 | 2 | 44 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 15702.2727
Lateral Hardening-Fuse-92835651,4 | 13329 | 0.8267 | 55 | 89 | 21 | 1 | 111 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 271985.7953
Lateral Hardening-Fuse-92856634,1 | 13224 | 0.25227 | 23 | 16 | 17 | 1 | 34 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 82997.7273
Lateral Hardening-Fuse-92859507,1 | 13460 | 0.096402 | 7 | 25 | 0 | 1 | 26 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 31716.0985
Lateral Hardening-Fuse-92867406,1 | 13010 | 0.068939 | 8 | 2 | 4 | 1 | 7 | 0 | Q3 - 2022 | Q1 - 2024 | Q4 - 2024 | 22681.0606
Lateral Hardening-Fuse-92874488,1 | 13112 | 0.13447 | 14 | 38 | 1 | 1 | 40 | 1 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 44240.5303
Lateral Hardening-Fuse-92890357,1 | 13112 | 0.1767 | 13 | 49 | 6 | 1 | 56 | 0 | Q2 - 2022 | Q3 - 2023 | Q2 - 2024 | 58135.7955
Lateral Hardening-Fuse-92897362,1 | 13147 | 0.1892 | 12 | 26 | 3 | 0 | 29 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 62248.2955
Lateral Hardening-Fuse-92901825,1 | 13147 | 0.46212 | 20 | 123 | 2 | 1 | 126 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 152037.8788
Lateral Hardening-Fuse-92905104,1 | 13826 | 0.19735 | 10 | 183 | 7 | 2 | 192 | 39 | Q1 - 2022 | Q3 - 2023 | Q1 - 2024 | 64927.6515
Lateral Hardening-Fuse-92907479,1 | 13060 | 0.057197 | 9 | 267 | 24 | 2 | 293 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 18817.803
Lateral Hardening-Fuse-92922162,1 | 13224 | 0.10852 | 13 | 16 | 2 | 1 | 19 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 35703.9773
Lateral Hardening-Fuse-92937437,1 | 13241 | 0.22216 | 17 | 22 | 9 | 0 | 31 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 73090.3409
Lateral Hardening-Fuse-93033231,1 | 13838 | 0.19981 | 13 | 61 | 13 | 4 | 78 | 27 | Q1 - 2022 | Q3 - 2023 | Q1 - 2024 | 65737.6894
Lateral Hardening-Fuse-93082436,1 | 13612 | 0.07197 | 7 | 8 | 5 | 0 | 13 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 23678.0303
Lateral Hardening-Fuse-93090160,1 | 13039 | 0.21042 | 10 | 15 | 7 | 0 | 22 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 69227.0833
Lateral Hardening-Fuse-93113905,1 | 13034 | 0.035985 | 4 | 8 | 1 | 1 | 10 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 13160
Lateral Hardening-Fuse-93118733,1 | 13324 | 0.11307 | 11 | 6 | 4 | 1 | 11 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 37199.4318
Lateral Hardening-Fuse-93172625,1 | 13213 | 0.13466 | 12 | 21 | 3 | 0 | 24 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 44302.8409
Lateral Hardening-Fuse-93218070,1 | 13656 | 0.10701 | 6 | 2 | 1 | 0 | 3 | 0 | Q4 - 2022 | Q2 - 2023 | Q4 - 2023 | 35205.4924
Lateral Hardening-Fuse-93233174,1 | 13696 | 0.1392 | 17 | 46 | 5 | 0 | 51 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 45798.2955
Lateral Hardening-Fuse-93235148,1 | 13696 | 0.098674 | 9 | 28 | 12 | 2 | 42 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 32463.8258
Lateral Hardening-Fuse-93247243,1 | 13175 | 0.17689 | 18 | 33 | 4 | 0 | 37 | 0 | Q3 - 2022 | Q2 - 2022 | Q4 - 2022 | 58198.1061
Lateral Hardening-Fuse-93249426,1 | 13175 | 0.1536 | 14 | 10 | 1 | 2 | 13 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 50533.9015
Lateral Hardening-Fuse-93263741,1 | 13042 | 0.12405 | 12 | 18 | 0 | 2 | 20 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 40813.447
Lateral Hardening-Fuse-93263753,1 | 13042 | 0.24924 | 21 | 27 | 2 | 1 | 30 | 0 | Q1 - 2022 | Q3 - 2023 | Q1 - 2024 | 82000.7576
Lateral Hardening-Fuse-93264130,1 | 13042 | 0.21705 | 22 | 23 | 6 | 2 | 31 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 71407.9545
Lateral Hardening-Fuse-93266650,1 | 13042 | 0.33996 | 32 | 55 | 0 | 1 | 56 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 111847.5379
Lateral Hardening-Fuse-93267158,1 | 13042 | 0.18068 | 18 | 37 | 3 | 1 | 41 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 59444.3182
Lateral Hardening-Fuse-93276507,1 | 13213 | 0.13598 | 8 | 6 | 2 | 1 | 9 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 44739.0152
Lateral Hardening-Fuse-93283244,2 | 13351 | 0.64375 | 49 | 73 | 9 | 1 | 83 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 211793.7499
Lateral Hardening-Fuse-93283740,1 | 13351 | 0.056818 | 8 | 110 | 8 | 2 | 120 | 0 | Q1 - 2022 | Q1 - 2023 | Q3 - 2023 | 18693.1818
Lateral Hardening-Fuse-93292955,1 | 14356 | 0.11686 | 10 | 184 | 10 | 2 | 196 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 38445.6439
Lateral Hardening-Fuse-93294943,1 | 13808 | 0.13523 | 9 | 5 | 0 | 1 | 6 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 44489.7727
Lateral Hardening-Fuse-93324791,1 | 13723 | 0.13902 | 6 | 9 | 2 | 0 | 11 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 45735.9848
Lateral Hardening-Fuse-93355196,1 | 13303 | 0.066856 | 6 | 10 | 2 | 2 | 14 | 0 | Q2 - 2022 | Q2 - 2024 | Q4 - 2024 | 21995.6439
Lateral Hardening-Fuse-93432382,1 | 13532 | 0.28902 | 22 | 36 | 0 | 1 | 37 | 0 | Q3 - 2022 | Q3 - 2024 | Q1 - 2025 | 95085.9848