## 2020-2029 SPP Total Costs
Tampa Electric's 2020-2029 Storm Protection Plan Total Costs by Program (in Millions)
[13 empty] | Projection |  | Delta
Capital | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | Total |  | 2020 | 2021 | 2020 | 2021
Distribution Lateral Undergrounding | 8 | 79.4501 | 108.076 | 101.4406 | 107 | 110.7752 | 113.96 | 111.4229 | 115.5238 | 121.1662 | 976.8148 |  | 9.836 | 85.601 | -1.836 | -6.1509
Transmission Asset Upgrades | 5.5 | 15.2104 | 14.9848 | 16.5133 | 11.9941 | 19.0446 | 17.9241 | 16.2768 | 19.5621 | 12.1056 | 149.1157 |  | 5.517 | 15.152 | -0.017 | 0.058373
Substation Extreme Weather Protection | 0 | 0 | 0 | 0 | 7.3389 | 5.5381 | 4.6657 | 6.7129 | 5.2373 | 2.8754 | 32.3683 |  | 0 | 0 | 0 | 0
Distribution Overhead Feeder Hardening | 6.5 | 15.3837 | 29.5814 | 33.3884 | 32.4869 | 33.193 | 33.8242 | 32.7563 | 36.3643 | 36.2491 | 289.7275 |  | 6.361 | 15.334 | 0.139 | 0.049744 | Capital Accuracy
Transmission Access Enhancements | 0 | 1.3833 | 1.5179 | 1.5591 | 1.6609 | 1.3967 | 0.54058 | 3.1703 | 1.926 | 1.5716 | 14.7263 |  | 0 | 1.328 | 0 | 0.05526 | -1.714 | -5.9875
Distribution Pole Replacements | 9.4192 | 11.1833 | 14.7165 | 15.1609 | 15.6188 | 16.0905 | 10.6422 | 10.8551 | 11.0722 | 11.2936 | 126.0523
O&M | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | Total
Distribution Vegetation Management - planned | 16.4879 | 19.7586 | 21.1798 | 24.0014 | 24.2234 | 25.5459 | 26.7688 | 27.9922 | 29.416 | 30.9404 | 246.3145 |  | 9.807 | 19.792 | -1.5631 | -0.033361
Distribution Vegetation Management - unplanned | 1.3 | 1.3 | 1.2 | 1.1 | 1.1 | 1.1 | 1.2 | 1.2 | 1.3 | 1.3 | 12.1
Transmission Vegetation Management - planned | 2.6324 | 3.5272 | 3.5933 | 3.661 | 3.0352 | 3.1304 | 3.2271 | 3.3023 | 3.3793 | 3.4581 | 32.9463 |  | 0.685 | 3.535 | 0.63122 | -0.0077681
Transmission Vegetation Management - unplanned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transmission Asset Upgrades | 0.11 | 0.30421 | 0.2997 | 0.33027 | 0.23988 | 0.38089 | 0.35848 | 0.32554 | 0.39124 | 0.24211 | 2.9823 |  | 0.165 | 0.449 | -0.11 | -0.14479
Distribution Overhead Feeder Hardening | 0.21 | 0.38148 | 0.40055 | 0.79378 | 0.82157 | 1.0202 | 1.0592 | 1.1688 | 1.4242 | 1.6367 | 8.9163 |  | 0.176 | 0.345 | -0.071 | 0.03648
Distribution Infrastructure Inspections | 0.708 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 10.4626 |  | 0.015 | 1.003 | 0.339 | -0.003
Transmission Infrastructure Inspections | 0.465 | 0.4743 | 0.48379 | 0.49346 | 0.50333 | 0.5134 | 0.52367 | 0.53414 | 0.54482 | 0.55572 | 5.0916 |  | 0.375 | 0.581 | -0.1425 | -0.1067
SPP Planning & Common | 0.994 | 0.38872 | 0.19976 | 0.20375 | 0.20783 | 0.21198 | 0.21622 | 0.22055 | 0.22496 | 0.22946 | 3.0972 |  | 0.263 | 0.402 | 0.234 | -0.01328
Other Legacy Storm Hardening Plan Items | 0.275 | 0.2805 | 0.28611 | 0.29183 | 0.29767 | 0.30362 | 0.30969 | 0.31589 | 0.32221 | 0.32865 | 3.0112 | Substation | 0 | 0.25 | 0 | 0.25 | O&M Accuracy
Distribution Pole Replacements | 0.51806 | 0.61508 | 0.80941 | 0.83385 | 0.85903 | 0.88498 | 0.58532 | 0.59703 | 0.60897 | 0.62115 | 6.9329 |  | 0 | 0 |  |  | -0.68234 | -0.022422
sum of just clause | 41.6073 | 137.262 | 181.3371 | 183.4255 | 190.5732 | 201.8327 | 204.1721 | 205.0089 | 215.1427 | 212.2019 | 1772.5635 |  | 33.2 | 143.772 |  | -6.51
less base rate adjust | -10.4 | -15 | -15 | -15 | -15 | -15 | -15 | -15 | -15 | -15 | -145.4
1627.1635
[12 empty] | sum of just clause Original | 41.6073 | 137.262
[10 empty] | VM, II |  |  | 10.882 | 24.911

## 2022-2031 SPP Total Costs
Tampa Electric's 2022-2031 Storm Protection Plan Total Costs by Program (in Millions)
Capital | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Distribution Lateral Undergrounding | 105.6627 | 104.5427 | 105 | 105 | 105 | 105 | 105 | 105 | 115 | 115 | 1070.2054 | 105662671.4 | 104542727.7135 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 115000000 | 115000000
Transmission Asset Upgrades | 16.479 | 17.4638 | 17.54 | 17.9168 | 18.2401 | 16.8898 | 17.3476 | 17.2424 | 0 | 0 | 139.1195 | 16478997.81 | 17463787.2 | 17540040 | 17916840 | 18240120 | 16889760 | 17347560 | 17242440 | 0 | 0
Distribution - Substation Extreme Weather Protection | 0 | 0.7 | 2.2212 | 1.3821 | 1.7276 | 1.5301 | 2.468 | 0.71052 | 3.7513 | 0.80923 | 15.3 | 0 | 700000 | 2221174.3772 | 1382064.0569 | 1727580.0712 | 1530142.3488 | 2467971.5302 | 710516.0142 | 3751316.726 | 809234.8754
Transmission - Substation Extreme Weather Protection | 0 | 0 | 2.0538 | 1.2779 | 1.5974 | 1.4149 | 2.282 | 0.65698 | 3.4687 | 0.74827 | 13.5 | 0 | 0 | 2053825.6228 | 1277935.9431 | 1597419.9288 | 1414857.6512 | 2282028.4698 | 656983.9858 | 3468683.274 | 748265.1246
Distribution Overhead Feeder Hardening | 32.8427 | 30.1152 | 29.9982 | 29.9885 | 29.9897 | 29.9967 | 29.993 | 29.9873 | 36.9949 | 36.9923 | 316.8984 | 32842657.4462 | 30115183 | 29998165.0388 | 29988469.8542 | 29989699.9579 | 29996667.7522 | 29993019.5494 | 29987340.3851 | 36994874.8486 | 36992343.9856
Transmission Access Enhancements | 2.41 | 3.0374 | 3.0066 | 3.7029 | 3.4465 | 3.4037 | 3.1423 | 2.8388 | 2.0408 | 4.4248 | 31.4538 | 2409956.08 | 3037445.88 | 3006580 | 3702893 | 3446516 | 3403726 | 3142341 | 2838771 | 2040824 | 4424772
Distribution Pole Replacements | 12.509 | 12.8868 | 13.276 | 13.6769 | 9.0459 | 9.2268 | 9.4114 | 9.5996 | 11.2234 | 11.3998 | 112.2556 | 12509019.4506 | 12886791.838 | 13275972.9515 | 13676907.3346 | 9045899.6327 | 9226817.6254 | 9411353.9779 | 9599581.0575 | 11223435.7867 | 11399848.025
O&M | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Distribution Lateral Undergrounding | 0.18072 | 0.17619 | 0.18103 | 0.14794 | 0.19072 | 0.19557 | 0.20042 | 0.20527 | 0.21011 | 0.33042 | 2.0184 | 180715.8094 | 176186.534 | 181025.843 | 147937.3168 | 190718.8699 | 195569.104 | 200419.376 | 205267.7635 | 210112.2608 | 330415.6395
Distribution Vegetation Management - planned | 21.1607 | 24.0014 | 24.2234 | 25.6459 | 26.7688 | 27.9922 | 29.516 | 30.9404 | 32.5024 | 34.2675 | 277.0187 | 21160688 | 24001407.6202 | 24223435.7727 | 25645904.4881 | 26768822.5779 | 27992199.0294 | 29516043.01 | 30940363.8702 | 32502382.0637 | 34267501.1669
Distribution Vegetation Management - unplanned | 1.4 | 1.4 | 1.4 | 1.3 | 1.3 | 1.3 | 1.4 | 1.4 | 1.3 | 1.3 | 13.5 | 1400000 | 1400000 | 1400000 | 1300000 | 1300000 | 1300000 | 1400000 | 1400000 | 1300000 | 1300000
Transmission Vegetation Management - planned | 3.6124 | 3.661 | 3.0352 | 3.1304 | 3.2271 | 3.3023 | 3.3793 | 3.4581 | 3.631 | 3.8126 | 34.2493 | 3612445 | 3660969.0521 | 3035211.5863 | 3130376.8277 | 3227059.2878 | 3302286.6241 | 3379285.6609 | 3458098.5111 | 3631003.4366 | 3812553.6085
Transmission Vegetation Management - unplanned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transmission Asset Upgrades | 0.49437 | 0.52391 | 0.53439 | 0.54508 | 0.55598 | 0.5671 | 0.57844 | 0.59001 | 0.60181 | 0.61385 | 5.605 | 494369.934 | 523913.616 | 534391.8883 | 545079.7261 | 555981.3206 | 567100.947 | 578442.966 | 590011.8253 | 601812.0618 | 613848.303
Distribution - Substation Extreme Weather Protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transmission - Substation Extreme Weather Protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Distribution Overhead Feeder Hardening | 0.55685 | 0.61865 | 0.6703 | 0.72018 | 0.77031 | 0.82068 | 0.8713 | 0.91818 | 0.97332 | 1.0247 | 7.9445 | 556853.1478 | 618654 | 670300.08 | 720183.0816 | 770307.7432 | 820678.8981 | 871301.4761 | 918180.5056 | 973321.1157 | 1024728.538
Transmission Access Enhancements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Distribution Infrastructure Inspections | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.104 | 1.1261 | 1.1486 | 1.1716 | 1.195 | 1.2189 | 11.1683 | 1020000 | 1040358 | 1061165.16 | 1082388.4632 | 1104036.2325 | 1126116.9571 | 1148639.2963 | 1171612.0822 | 1195044.3238 | 1218945.2103
Transmission Infrastructure Inspections | 0.58299 | 0.54364 | 0.55452 | 0.56561 | 0.57692 | 0.58846 | 0.60023 | 0.61223 | 0.62448 | 0.63697 | 5.886 | 582985 | 543644.1 | 554516.982 | 565607.3216 | 576919.4681 | 588457.8574 | 600227.0146 | 612231.5549 | 624476.186 | 636965.7097
SPP Planning & Common | 0.9243 | 0.8663 | 0.88363 | 0.9013 | 0.91932 | 0.93771 | 0.95647 | 0.97559 | 0.99511 | 1.015 | 9.3747 | 924300 | 866300 | 883626 | 901298.52 | 919324.4904 | 937710.9802 | 956465.1998 | 975594.5038 | 995106.3939 | 1015008.5218
Other Legacy Storm Hardening Plan Items | 0.28611 | 0.29183 | 0.29767 | 0.30362 | 0.30969 | 0.31589 | 0.32221 | 0.32865 | 0.34 | 0.34 | 3.1357 | 286110 | 291832.2 | 297668.844 | 303622.2209 | 309694.6653 | 315888.5586 | 322206.3298 | 328650.4564 | 340000 | 340000
Distribution Pole Replacements | 0.80941 | 0.83385 | 0.85903 | 0.88498 | 0.58532 | 0.59703 | 0.60897 | 0.62115 | 0.71 | 0.72 | 7.2297 | 809407.1409 | 833851.2366 | 859033.5439 | 884976.3569 | 585322.9174 | 597029.3758 | 608969.9633 | 621149.3625 | 710000 | 720000
Total Capital | 169.9033 | 168.7459 | 173.0958 | 172.9451 | 169.0472 | 167.462 | 169.6443 | 166.0356 | 172.4791 | 169.3745 | 1698.7328
Total O&M | 31.0279 | 33.9571 | 33.7004 | 35.2274 | 36.3082 | 37.743 | 39.582 | 41.2212 | 43.0833 | 45.28 | 377.1304
Total SPP Costs | 200.9312 | 202.7031 | 206.7961 | 208.1725 | 205.3554 | 205.205 | 209.2263 | 207.2568 | 215.5624 | 214.6544 | 2075.8632
Total Clause Capital related Items | 157.3943 | 155.8591 | 159.8198 | 159.2682 | 160.0013 | 158.2352 | 160.2329 | 156.4361 | 161.2557 | 157.9746 | 1586.4772
Total Clause O&M related Items | 28.5324 | 31.4314 | 31.1437 | 32.7388 | 34.1132 | 35.5301 | 37.2508 | 38.8714 | 40.7333 | 42.92 | 353.2649
Total SPP Clause Costs | 185.9266 | 187.2906 | 190.9635 | 192.007 | 194.1145 | 193.7653 | 197.4837 | 195.3074 | 201.989 | 200.8946 | 1939.7421

## 2022-2031 SPP Total RR
Tampa Electric's 2022-2031 Storm Protection Plan Total Revenue Requirements by Program (in Millions)
Capital | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Distribution Lateral Undergrounding | 9.2153 | 19.8723 | 30.8108 | 42.1632 | 53.8731 | 65.4357 | 76.789 | 87.9331 | 99.2537 | 110.7107 | 596.0569 | 9215279 | 19872327 | 30810798 | 42163167 | 53873142 | 65435701 | 76789017 | 87933087 | 99253747 | 110710668
Transmission Asset Upgrades | 2.8973 | 4.9893 | 6.72 | 8.433 | 10.2647 | 12.035 | 13.7109 | 15.3508 | 16.3332 | 16.2792 | 107.0135 | 2897301.22 | 4989274.14 | 6720010.15 | 8433040.82 | 10264659.99 | 12035015.59 | 13710901.38 | 15350787.31 | 16333247.62 | 16279221.72
Distribution - Substation Extreme Weather Protection | 0 | 0.015166 | 0.15116 | 0.34234 | 0.53613 | 0.71532 | 0.92642 | 1.1092 | 1.3382 | 1.5644 | 6.6984 | 0 | 15166 | 151160 | 342337 | 536134 | 715317 | 926420 | 1109181 | 1338244 | 1564443
Transmission - Substation Extreme Weather Protection | 0 | 0 | 0.075793 | 0.22562 | 0.39541 | 0.55228 | 0.73659 | 0.89668 | 1.0961 | 1.2936 | 5.272 | 0 | 0 | 75792.92 | 225623.9 | 395411.11 | 552280.19 | 736586.49 | 896679.04 | 1096076.06 | 1293599.81
Distribution Overhead Feeder Hardening | 3.3094 | 7.3634 | 10.6098 | 13.821 | 17.3748 | 20.8361 | 24.2052 | 27.4814 | 30.9268 | 34.6873 | 190.6152 | 3309447 | 7363357 | 10609753 | 13820986 | 17374846 | 20836140 | 24205164 | 27481395 | 30926849 | 34687306
Transmission Access Enhancements | 0.15437 | 0.41887 | 0.71323 | 1.0348 | 1.3874 | 1.7297 | 2.0513 | 2.3424 | 2.5795 | 2.8559 | 15.2676 | 154370.13 | 418870.51 | 713228.74 | 1034808.79 | 1387437.39 | 1729700.97 | 2051333.22 | 2342433.49 | 2579509.69 | 2855931.39
Distribution Pole Replacements | 1.5905 | 3.1367 | 4.6937 | 6.2619 | 7.5733 | 8.5273 | 9.4774 | 10.4236 | 11.446 | 12.5684 | 75.6989 | 1590485 | 3136696 | 4693735 | 6261939 | 7573347 | 8527290 | 9477391 | 10423580 | 11445970 | 12568428
O&M | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Distribution Lateral Undergrounding | 0.18072 | 0.17619 | 0.18103 | 0.14794 | 0.19072 | 0.19557 | 0.20042 | 0.20527 | 0.21011 | 0.33042 | 2.0184 | 180715.8094 | 176186.534 | 181025.843 | 147937.3168 | 190718.8699 | 195569.104 | 200419.376 | 205267.7635 | 210112.2608 | 330415.6395
Distribution Vegetation Management - planned | 21.1607 | 24.0014 | 24.2234 | 25.6459 | 26.7688 | 27.9922 | 29.516 | 30.9404 | 32.5024 | 34.2675 | 277.0187 | 21160688 | 24001407.6202 | 24223435.7727 | 25645904.4881 | 26768822.5779 | 27992199.0294 | 29516043.01 | 30940363.8702 | 32502382.0637 | 34267501.1669
Distribution Vegetation Management - unplanned | 1.4 | 1.4 | 1.4 | 1.3 | 1.3 | 1.3 | 1.4 | 1.4 | 1.3 | 1.3 | 13.5 | 1400000 | 1400000 | 1400000 | 1300000 | 1300000 | 1300000 | 1400000 | 1400000 | 1300000 | 1300000
Transmission Vegetation Management - planned | 3.3684 | 3.4137 | 2.8302 | 2.9189 | 3.0091 | 3.0792 | 3.151 | 3.2245 | 3.3857 | 3.555 | 31.9356 | 3368409.2041 | 3413655.2532 | 2830170.3261 | 2918906.7567 | 3009057.9115 | 3079203.3261 | 3151000.7553 | 3224489.4672 | 3385713.9406 | 3554999.6376
Transmission Vegetation Management - unplanned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transmission Asset Upgrades | 0.46097 | 0.48852 | 0.49829 | 0.50826 | 0.51842 | 0.52879 | 0.53937 | 0.55015 | 0.56116 | 0.57238 | 5.2263 | 460973.1735 | 488521.056 | 498291.4772 | 508257.3067 | 518422.4528 | 528790.9019 | 539366.7199 | 550154.0543 | 561157.1354 | 572380.2781
Distribution - Substation Extreme Weather Protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transmission - Substation Extreme Weather Protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Distribution Overhead Feeder Hardening | 0.55685 | 0.61865 | 0.6703 | 0.72018 | 0.77031 | 0.82068 | 0.8713 | 0.91818 | 0.97332 | 1.0247 | 7.9445 | 556853.1478 | 618654 | 670300.08 | 720183.0816 | 770307.7432 | 820678.8981 | 871301.4761 | 918180.5056 | 973321.1157 | 1024728.538
Transmission Access Enhancements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Distribution Infrastructure Inspections | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.104 | 1.1261 | 1.1486 | 1.1716 | 1.195 | 1.2189 | 11.1683 | 1020000 | 1040358 | 1061165.16 | 1082388.4632 | 1104036.2325 | 1126116.9571 | 1148639.2963 | 1171612.0822 | 1195044.3238 | 1218945.2103
Transmission Infrastructure Inspections | 0.5436 | 0.50692 | 0.51706 | 0.5274 | 0.53795 | 0.54871 | 0.55968 | 0.57087 | 0.58229 | 0.59394 | 5.4884 | 543601.9205 | 506918.6632 | 517057.0364 | 527398.1772 | 537946.1407 | 548705.0635 | 559679.1648 | 570872.7481 | 582290.2031 | 593936.0071
SPP Planning & Common | 0.9243 | 0.8663 | 0.88363 | 0.9013 | 0.91932 | 0.93771 | 0.95647 | 0.97559 | 0.99511 | 1.015 | 9.3747 | 924300 | 866300 | 883626 | 901298.52 | 919324.4904 | 937710.9802 | 956465.1998 | 975594.5038 | 995106.3939 | 1015008.5218
Other Legacy Storm Hardening Plan Items | 0.28611 | 0.29183 | 0.29767 | 0.30362 | 0.30969 | 0.31589 | 0.32221 | 0.32865 | 0.34 | 0.34 | 3.1357 | 286110 | 291832.2 | 297668.844 | 303622.2209 | 309694.6653 | 315888.5586 | 322206.3298 | 328650.4564 | 340000 | 340000
Distribution Pole Replacements | 0.80941 | 0.83385 | 0.85903 | 0.88498 | 0.58532 | 0.59703 | 0.60897 | 0.62115 | 0.71 | 0.72 | 7.2297 | 809407.1409 | 833851.2366 | 859033.5439 | 884976.3569 | 585322.9174 | 597029.3758 | 608969.9633 | 621149.3625 | 710000 | 720000
Total Capital Revenue Requirements | 17.1669 | 35.7957 | 53.7745 | 72.2819 | 91.405 | 109.8314 | 127.8968 | 145.5371 | 162.9736 | 179.9596 | 996.6226 | 47877940.7463 | 69433375.2132 | 87196251.8932 | 107222775.1981 | 127418631.4916 | 147273336.9447 | 167170904.3812 | 186443477.6539 | 205728770.807 | 224897512.9194
Total O&M Revenue Requirements | 30.7111 | 33.6377 | 33.4218 | 34.9409 | 36.0137 | 37.4419 | 39.2741 | 40.9063 | 42.7551 | 44.9379 | 374.0404
Total SPP Revenue Requirements | 47.8779 | 69.4334 | 87.1963 | 107.2228 | 127.4186 | 147.2733 | 167.1709 | 186.4435 | 205.7288 | 224.8975 | 1370.663
Total Clause Capital related Items | 15.5764 | 32.659 | 49.0807 | 66.02 | 83.8316 | 101.3042 | 118.4194 | 135.1136 | 151.5277 | 167.3912 | 920.9237
Total Clause O&M related Items | 28.2155 | 31.112 | 30.8651 | 32.4523 | 33.8186 | 35.229 | 36.9429 | 38.5565 | 40.4051 | 42.5779 | 350.175
Total SPP Clause Revenue Requirements | 43.7919 | 63.771 | 79.9458 | 98.4722 | 117.6503 | 136.5331 | 155.3623 | 173.6701 | 191.9328 | 209.9691 | 1271.0987

## SPP Projection Summary
Tampa Electric's 2020-2029 Storm Protection Plan Total Costs by Program (in Millions) | [13 empty] | All values in Millions
[14 empty] | 2020 SPP Filed Costs |  | SPPCRC Projection | 2022 SPP Filed Costs |  | Delta | Delta
Capital | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | Total |  |  | 2022 | 2023 | 2022 | 2022 | 2023 | 2022 | 2023
Distribution Lateral Undergrounding | 8 | 79.4501 | 108.076 | 101.4406 | 107 | 110.7752 | 113.96 | 111.4229 | 115.5238 | 121.1662 | 976.8148 | Capital | Distribution Lateral Undergrounding | 108.076 | 101.4406 |  | 105.6627 | 104.5427 | -2.4134 | 3.1021
Transmission Asset Upgrades | 5.5 | 15.2104 | 14.9848 | 16.5133 | 11.9941 | 19.0446 | 17.9241 | 16.2768 | 19.5621 | 12.1056 | 149.1157 |  | Transmission Asset Upgrades | 14.9848 | 16.5133 |  | 16.479 | 17.4638 | 1.4942 | 0.95047
Substation Extreme Weather Protection | 0 | 0 | 0 | 0 | 7.3389 | 5.5381 | 4.6657 | 6.7129 | 5.2373 | 2.8754 | 32.3683 |  | Substation Extreme Weather Protection | 0 | 0 |  | 0 | 0.7 | 0 | 0.7
Distribution Overhead Feeder Hardening | 6.5 | 15.3837 | 29.5814 | 33.3884 | 32.4869 | 33.193 | 33.8242 | 32.7563 | 36.3643 | 36.2491 | 289.7275 |  | Distribution Overhead Feeder Hardening | 29.5814 | 33.3884 |  | 32.8427 | 30.1152 | 3.2612 | -3.2732
Transmission Access Enhancements | 0 | 1.3833 | 1.5179 | 1.5591 | 1.6609 | 1.3967 | 0.54058 | 3.1703 | 1.926 | 1.5716 | 14.7263 |  | Transmission Access Enhancements | 1.5179 | 1.5591 |  | 2.41 | 3.0374 | 0.89202 | 1.4783
Distribution Pole Replacements | 9.4192 | 11.1833 | 14.7165 | 15.1609 | 15.6188 | 16.0905 | 10.6422 | 10.8551 | 11.0722 | 11.2936 | 126.0523 | [7 empty] | 3.2341 | 2.9577 | (positive indicates an increase in cost projection)
O&M | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | Total
Distribution Vegetation Management - planned | 16.4879 | 19.7586 | 21.1798 | 24.0014 | 24.2234 | 25.5459 | 26.7688 | 27.9922 | 29.416 | 30.9404 | 246.3145 | O&M | Distribution Lateral Undergrounding | 0 | 0 |  | 0.18072 | 0.17619 | 0.18072 | 0.17619
Distribution Vegetation Management - planned | 16.4879 | 19.7586 | 21.1798 | 24.0014 | 24.2234 | 25.5459 | 26.7688 | 27.9922 | 29.416 | 30.9404 | 246.3145 |  | Distribution Vegetation Management - planned | 21.1798 | 24.0014 |  | 21.1607 | 24.0014 | -0.019123 | 0
Distribution Vegetation Management - unplanned | 1.3 | 1.3 | 1.2 | 1.1 | 1.1 | 1.1 | 1.2 | 1.2 | 1.3 | 1.3 | 12.1 |  | Transmission Vegetation Management - planned | 3.5933 | 3.661 |  | 3.6124 | 3.661 | 0.019124 | 0
Transmission Vegetation Management - planned | 2.6324 | 3.5272 | 3.5933 | 3.661 | 3.0352 | 3.1304 | 3.2271 | 3.3023 | 3.3793 | 3.4581 | 32.9463 |  | Transmission Asset Upgrades | 0.2997 | 0.33027 |  | 0.49437 | 0.52391 | 0.19467 | 0.19365
[13 empty] | Substation Extreme Weather Protection | 0 | 0 |  | 0 | 0 | 0 | 0
Transmission Vegetation Management - unplanned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Distribution Overhead Feeder Hardening | 0.40055 | 0.79378 |  | 0.55685 | 0.61865 | 0.1563 | -0.17513
Transmission Asset Upgrades | 0.11 | 0.30421 | 0.2997 | 0.33027 | 0.23988 | 0.38089 | 0.35848 | 0.32554 | 0.39124 | 0.24211 | 2.9823 |  | Distribution Infrastructure Inspections | 1.02 | 1.0404 |  | 1.02 | 1.0404 | 0 | -4.2e-05
Distribution Overhead Feeder Hardening | 0.21 | 0.38148 | 0.40055 | 0.79378 | 0.82157 | 1.0202 | 1.0592 | 1.1688 | 1.4242 | 1.6367 | 8.9163 |  | Transmission Infrastructure Inspections | 0.48379 | 0.49346 |  | 0.58299 | 0.54364 | 0.099199 | 0.050182
Transmission Infrastructure Inspections | 0.465 | 0.4743 | 0.48379 | 0.49346 | 0.50333 | 0.5134 | 0.52367 | 0.53414 | 0.54482 | 0.55572 | 5.0916 |  | SPP Planning & Common | 0.19976 | 0.20375 |  | 0.9243 | 0.8663 | 0.72454 | 0.66255
SPP Planning & Common | 0.994 | 0.38872 | 0.19976 | 0.20375 | 0.20783 | 0.21198 | 0.21622 | 0.22055 | 0.22496 | 0.22946 | 3.0972 | [7 empty] | 1.1747 | 0.73121 | (positive indicates an increase in cost projection)
Other Legacy Storm Hardening Plan Items | 0.275 | 0.2805 | 0.28611 | 0.29183 | 0.29767 | 0.30362 | 0.30969 | 0.31589 | 0.32221 | 0.32865 | 3.0112
Distribution Pole Replacements | 0.51806 | 0.61508 | 0.80941 | 0.83385 | 0.85903 | 0.88498 | 0.58532 | 0.59703 | 0.60897 | 0.62115 | 6.9329
sum of just clause | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
less base rate adjust | -10.4 | -15 | -15 | -15 | -15 | -15 | -15 | -15 | -15 | -15 | -145.4
#REF!
VM, II

## Summary Data
| SPP Costs by Year | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
| Capital Total | 169.9033 | 168.7459 | 173.0958 | 172.9451 | 169.0472 | 167.462 | 169.6443 | 166.0356 | 172.4791 | 169.3745 | 1698.7328
| O&M Toal | 31.0279 | 33.9571 | 33.7004 | 35.2274 | 36.3082 | 37.743 | 39.582 | 41.2212 | 43.0833 | 45.28 | 377.1304
| Overall Total | 200.9312 | 202.7031 | 206.7961 | 208.1725 | 205.3554 | 205.205 | 209.2263 | 207.2568 | 215.5624 | 214.6544 | 2075.8632
SPP Revenue Requirements by Year |  | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Capital Total |  | 17.1669 | 35.7957 | 53.7745 | 72.2819 | 91.405 | 109.8314 | 127.8968 | 145.5371 | 162.9736 | 179.9596 | 996.6226
O&M Toal |  | 30.7111 | 33.6377 | 33.4218 | 34.9409 | 36.0137 | 37.4419 | 39.2741 | 40.9063 | 42.7551 | 44.9379 | 374.0404
Overall Total |  | 47.8779 | 69.4334 | 87.1963 | 107.2228 | 127.4186 | 147.2733 | 167.1709 | 186.4435 | 205.7288 | 224.8975 | 1370.663

## SL-1 RevReqby Year
YEAR | Revenue Requirements
2022 | 47877940.7463
2023 | 69433375.2132
2024 | 87196251.8932
2025 | 107222775.1981
2026 | 127418631.4916
2027 | 147273336.9447
2028 | 167170904.3812
2029 | 186443477.6539
2030 | 205728770.807
2031 | 224897512.9194

## SL-2 RateImpacts
Tampa Electric's Storm Protection Plan "Total Cost" Customer Bill Impacts (in percent)
Customer Class
| Residential 1000 kWh | Residential 1250 kWh | Commercial 1 MW 60 percent Load Factor | Industrial 10 MW 60 percent Load Factor
2022 | 2.696% | 2.696% | 1.167% | 1.078%
2023 | 4.127% | 4.127% | 1.277% | 1.191%
2024 | 5.31% | 5.31% | 1.368% | 1.286%

## SL-3 SPP Total RR
Tampa Electric's 2022-2031 Storm Protection Plan Total Revenue Requirements by Program (in Millions)
Capital | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Distribution Lateral Undergrounding | 9.2153 | 19.8723 | 30.8108 | 42.1632 | 53.8731 | 65.4357 | 76.789 | 87.9331 | 99.2537 | 110.7107 | 596.0569 | 9215279 | 19872327 | 30810798 | 42163167 | 53873142 | 65435701 | 76789017 | 87933087 | 99253747 | 110710668
Transmission Asset Upgrades | 2.8973 | 4.9893 | 6.72 | 8.433 | 10.2647 | 12.035 | 13.7109 | 15.3508 | 16.3332 | 16.2792 | 107.0135 | 2897301.22 | 4989274.14 | 6720010.15 | 8433040.82 | 10264659.99 | 12035015.59 | 13710901.38 | 15350787.31 | 16333247.62 | 16279221.72
Distribution - Substation Extreme Weather Protection | 0 | 0.015166 | 0.15116 | 0.34234 | 0.53613 | 0.71532 | 0.92642 | 1.1092 | 1.3382 | 1.5644 | 6.6984 | 0 | 15166 | 151160 | 342337 | 536134 | 715317 | 926420 | 1109181 | 1338244 | 1564443
Transmission - Substation Extreme Weather Protection | 0 | 0 | 0.075793 | 0.22562 | 0.39541 | 0.55228 | 0.73659 | 0.89668 | 1.0961 | 1.2936 | 5.272 | 0 | 0 | 75792.92 | 225623.9 | 395411.11 | 552280.19 | 736586.49 | 896679.04 | 1096076.06 | 1293599.81
Distribution Overhead Feeder Hardening | 3.3094 | 7.3634 | 10.6098 | 13.821 | 17.3748 | 20.8361 | 24.2052 | 27.4814 | 30.9268 | 34.6873 | 190.6152 | 3309447 | 7363357 | 10609753 | 13820986 | 17374846 | 20836140 | 24205164 | 27481395 | 30926849 | 34687306
Transmission Access Enhancements | 0.15437 | 0.41887 | 0.71323 | 1.0348 | 1.3874 | 1.7297 | 2.0513 | 2.3424 | 2.5795 | 2.8559 | 15.2676 | 154370.13 | 418870.51 | 713228.74 | 1034808.79 | 1387437.39 | 1729700.97 | 2051333.22 | 2342433.49 | 2579509.69 | 2855931.39
Distribution Pole Replacements | 1.5905 | 3.1367 | 4.6937 | 6.2619 | 7.5733 | 8.5273 | 9.4774 | 10.4236 | 11.446 | 12.5684 | 75.6989 | 1590485 | 3136696 | 4693735 | 6261939 | 7573347 | 8527290 | 9477391 | 10423580 | 11445970 | 12568428
O&M | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Distribution Lateral Undergrounding | 0.18072 | 0.17619 | 0.18103 | 0.14794 | 0.19072 | 0.19557 | 0.20042 | 0.20527 | 0.21011 | 0.33042 | 2.0184 | 180715.8094 | 176186.534 | 181025.843 | 147937.3168 | 190718.8699 | 195569.104 | 200419.376 | 205267.7635 | 210112.2608 | 330415.6395
Distribution Vegetation Management - planned | 21.1607 | 24.0014 | 24.2234 | 25.6459 | 26.7688 | 27.9922 | 29.516 | 30.9404 | 32.5024 | 34.2675 | 277.0187 | 21160688 | 24001407.6202 | 24223435.7727 | 25645904.4881 | 26768822.5779 | 27992199.0294 | 29516043.01 | 30940363.8702 | 32502382.0637 | 34267501.1669
Distribution Vegetation Management - unplanned | 1.4 | 1.4 | 1.4 | 1.3 | 1.3 | 1.3 | 1.4 | 1.4 | 1.3 | 1.3 | 13.5 | 1400000 | 1400000 | 1400000 | 1300000 | 1300000 | 1300000 | 1400000 | 1400000 | 1300000 | 1300000
Transmission Vegetation Management - planned | 3.3684 | 3.4137 | 2.8302 | 2.9189 | 3.0091 | 3.0792 | 3.151 | 3.2245 | 3.3857 | 3.555 | 31.9356 | 3368409.2041 | 3413655.2532 | 2830170.3261 | 2918906.7567 | 3009057.9115 | 3079203.3261 | 3151000.7553 | 3224489.4672 | 3385713.9406 | 3554999.6376
Transmission Vegetation Management - unplanned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transmission Asset Upgrades | 0.46097 | 0.48852 | 0.49829 | 0.50826 | 0.51842 | 0.52879 | 0.53937 | 0.55015 | 0.56116 | 0.57238 | 5.2263 | 460973.1735 | 488521.056 | 498291.4772 | 508257.3067 | 518422.4528 | 528790.9019 | 539366.7199 | 550154.0543 | 561157.1354 | 572380.2781
Distribution - Substation Extreme Weather Protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transmission - Substation Extreme Weather Protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Distribution Overhead Feeder Hardening | 0.55685 | 0.61865 | 0.6703 | 0.72018 | 0.77031 | 0.82068 | 0.8713 | 0.91818 | 0.97332 | 1.0247 | 7.9445 | 556853.1478 | 618654 | 670300.08 | 720183.0816 | 770307.7432 | 820678.8981 | 871301.4761 | 918180.5056 | 973321.1157 | 1024728.538
Transmission Access Enhancements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Distribution Infrastructure Inspections | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.104 | 1.1261 | 1.1486 | 1.1716 | 1.195 | 1.2189 | 11.1683 | 1020000 | 1040358 | 1061165.16 | 1082388.4632 | 1104036.2325 | 1126116.9571 | 1148639.2963 | 1171612.0822 | 1195044.3238 | 1218945.2103
Transmission Infrastructure Inspections | 0.5436 | 0.50692 | 0.51706 | 0.5274 | 0.53795 | 0.54871 | 0.55968 | 0.57087 | 0.58229 | 0.59394 | 5.4884 | 543601.9205 | 506918.6632 | 517057.0364 | 527398.1772 | 537946.1407 | 548705.0635 | 559679.1648 | 570872.7481 | 582290.2031 | 593936.0071
SPP Planning & Common | 0.9243 | 0.8663 | 0.88363 | 0.9013 | 0.91932 | 0.93771 | 0.95647 | 0.97559 | 0.99511 | 1.015 | 9.3747 | 924300 | 866300 | 883626 | 901298.52 | 919324.4904 | 937710.9802 | 956465.1998 | 975594.5038 | 995106.3939 | 1015008.5218
Other Legacy Storm Hardening Plan Items | 0.28611 | 0.29183 | 0.29767 | 0.30362 | 0.30969 | 0.31589 | 0.32221 | 0.32865 | 0.34 | 0.34 | 3.1357 | 286110 | 291832.2 | 297668.844 | 303622.2209 | 309694.6653 | 315888.5586 | 322206.3298 | 328650.4564 | 340000 | 340000
Distribution Pole Replacements | 0.80941 | 0.83385 | 0.85903 | 0.88498 | 0.58532 | 0.59703 | 0.60897 | 0.62115 | 0.71 | 0.72 | 7.2297 | 809407.1409 | 833851.2366 | 859033.5439 | 884976.3569 | 585322.9174 | 597029.3758 | 608969.9633 | 621149.3625 | 710000 | 720000

## SL SPP Total Costs
Tampa Electric's 2022-2031 Storm Protection Plan Total Costs by Program (in Millions)
Capital | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Distribution Lateral Undergrounding | 105.6627 | 104.5427 | 105 | 105 | 105 | 105 | 105 | 105 | 115 | 115 | 1070.2054 | 105662671.4 | 104542727.7135 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 115000000 | 115000000
Transmission Asset Upgrades | 16.479 | 17.4638 | 17.54 | 17.9168 | 18.2401 | 16.8898 | 17.3476 | 17.2424 | 0 | 0 | 139.1195 | 16478997.81 | 17463787.2 | 17540040 | 17916840 | 18240120 | 16889760 | 17347560 | 17242440 | 0 | 0
Distribution - Substation Extreme Weather Protection | 0 | 0.7 | 2.2212 | 1.3821 | 1.7276 | 1.5301 | 2.468 | 0.71052 | 3.7513 | 0.80923 | 15.3 | 0 | 700000 | 2221174.3772 | 1382064.0569 | 1727580.0712 | 1530142.3488 | 2467971.5302 | 710516.0142 | 3751316.726 | 809234.8754
Transmission - Substation Extreme Weather Protection | 0 | 0 | 2.0538 | 1.2779 | 1.5974 | 1.4149 | 2.282 | 0.65698 | 3.4687 | 0.74827 | 13.5 | 0 | 0 | 2053825.6228 | 1277935.9431 | 1597419.9288 | 1414857.6512 | 2282028.4698 | 656983.9858 | 3468683.274 | 748265.1246
Distribution Overhead Feeder Hardening | 32.8427 | 30.1152 | 29.9982 | 29.9885 | 29.9897 | 29.9967 | 29.993 | 29.9873 | 36.9949 | 36.9923 | 316.8984 | 32842657.4462 | 30115183 | 29998165.0388 | 29988469.8542 | 29989699.9579 | 29996667.7522 | 29993019.5494 | 29987340.3851 | 36994874.8486 | 36992343.9856
Transmission Access Enhancements | 2.41 | 3.0374 | 3.0066 | 3.7029 | 3.4465 | 3.4037 | 3.1423 | 2.8388 | 2.0408 | 4.4248 | 31.4538 | 2409956.08 | 3037445.88 | 3006580 | 3702893 | 3446516 | 3403726 | 3142341 | 2838771 | 2040824 | 4424772
Distribution Pole Replacements | 12.509 | 12.8868 | 13.276 | 13.6769 | 9.0459 | 9.2268 | 9.4114 | 9.5996 | 11.2234 | 11.3998 | 112.2556 | 12509019.4506 | 12886791.838 | 13275972.9515 | 13676907.3346 | 9045899.6327 | 9226817.6254 | 9411353.9779 | 9599581.0575 | 11223435.7867 | 11399848.025
O&M | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Distribution Lateral Undergrounding | 0.18072 | 0.17619 | 0.18103 | 0.14794 | 0.19072 | 0.19557 | 0.20042 | 0.20527 | 0.21011 | 0.33042 | 2.0184 | 180715.8094 | 176186.534 | 181025.843 | 147937.3168 | 190718.8699 | 195569.104 | 200419.376 | 205267.7635 | 210112.2608 | 330415.6395
Distribution Vegetation Management - planned | 21.1607 | 24.0014 | 24.2234 | 25.6459 | 26.7688 | 27.9922 | 29.516 | 30.9404 | 32.5024 | 34.2675 | 277.0187 | 21160688 | 24001407.6202 | 24223435.7727 | 25645904.4881 | 26768822.5779 | 27992199.0294 | 29516043.01 | 30940363.8702 | 32502382.0637 | 34267501.1669
Distribution Vegetation Management - unplanned | 1.4 | 1.4 | 1.4 | 1.3 | 1.3 | 1.3 | 1.4 | 1.4 | 1.3 | 1.3 | 13.5 | 1400000 | 1400000 | 1400000 | 1300000 | 1300000 | 1300000 | 1400000 | 1400000 | 1300000 | 1300000
Transmission Vegetation Management - planned | 3.6124 | 3.661 | 3.0352 | 3.1304 | 3.2271 | 3.3023 | 3.3793 | 3.4581 | 3.631 | 3.8126 | 34.2493 | 3612445 | 3660969.0521 | 3035211.5863 | 3130376.8277 | 3227059.2878 | 3302286.6241 | 3379285.6609 | 3458098.5111 | 3631003.4366 | 3812553.6085
Transmission Vegetation Management - unplanned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transmission Asset Upgrades | 0.49437 | 0.52391 | 0.53439 | 0.54508 | 0.55598 | 0.5671 | 0.57844 | 0.59001 | 0.60181 | 0.61385 | 5.605 | 494369.934 | 523913.616 | 534391.8883 | 545079.7261 | 555981.3206 | 567100.947 | 578442.966 | 590011.8253 | 601812.0618 | 613848.303
Distribution - Substation Extreme Weather Protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transmission - Substation Extreme Weather Protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Distribution Overhead Feeder Hardening | 0.55685 | 0.61865 | 0.6703 | 0.72018 | 0.77031 | 0.82068 | 0.8713 | 0.91818 | 0.97332 | 1.0247 | 7.9445 | 556853.1478 | 618654 | 670300.08 | 720183.0816 | 770307.7432 | 820678.8981 | 871301.4761 | 918180.5056 | 973321.1157 | 1024728.538
Transmission Access Enhancements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Distribution Infrastructure Inspections | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.104 | 1.1261 | 1.1486 | 1.1716 | 1.195 | 1.2189 | 11.1683 | 1020000 | 1040358 | 1061165.16 | 1082388.4632 | 1104036.2325 | 1126116.9571 | 1148639.2963 | 1171612.0822 | 1195044.3238 | 1218945.2103
Transmission Infrastructure Inspections | 0.58299 | 0.54364 | 0.55452 | 0.56561 | 0.57692 | 0.58846 | 0.60023 | 0.61223 | 0.62448 | 0.63697 | 5.886 | 582985 | 543644.1 | 554516.982 | 565607.3216 | 576919.4681 | 588457.8574 | 600227.0146 | 612231.5549 | 624476.186 | 636965.7097
SPP Planning & Common | 0.9243 | 0.8663 | 0.88363 | 0.9013 | 0.91932 | 0.93771 | 0.95647 | 0.97559 | 0.99511 | 1.015 | 9.3747 | 924300 | 866300 | 883626 | 901298.52 | 919324.4904 | 937710.9802 | 956465.1998 | 975594.5038 | 995106.3939 | 1015008.5218
Other Legacy Storm Hardening Plan Items | 0.28611 | 0.29183 | 0.29767 | 0.30362 | 0.30969 | 0.31589 | 0.32221 | 0.32865 | 0.34 | 0.34 | 3.1357 | 286110 | 291832.2 | 297668.844 | 303622.2209 | 309694.6653 | 315888.5586 | 322206.3298 | 328650.4564 | 340000 | 340000
Distribution Pole Replacements | 0.80941 | 0.83385 | 0.85903 | 0.88498 | 0.58532 | 0.59703 | 0.60897 | 0.62115 | 0.71 | 0.72 | 7.2297 | 809407.1409 | 833851.2366 | 859033.5439 | 884976.3569 | 585322.9174 | 597029.3758 | 608969.9633 | 621149.3625 | 710000 | 720000
|  |  |  | 1.648 | 1.681 | 1.7146 | 1.7489 | 1.7838 | 1.8195 | 1.8559

## Rate% calc sheet
|  | per 1,000 kWh | per kW
|  | RS | GSD | GSLDPR | GSLDSU
|  | 3.29 | 0.59 | 0.53 | 0.06
| 2022 | 3.26 | 0.64 | 0.57 | 0.06
| 2023 | 4.99 | 0.7 | 0.63 | 0.09
| 2024 | 6.42 | 0.75 | 0.68 | 0.11
|  | RS | RS | GSD | GSLDPR | GSLDSU
| Percentage of | 1,000 kWh | 1,250 kWh | 900 kW 60% LF | 10MW 60% LF | 10 MW 60%LF
Base bill |  | 120.91 | 151.1375
| 2022 | 2.696% | 2.696%
| 2023 | 4.127% | 4.127%
| 2024 | 5.31% | 5.31%
|  |  |  | GSD | GSLDPR | GSLDSU
|  |  | Demand | 900 | 10000 | 10000 | kW
|  |  | Enegry | 388800 | 4320000 | 4320000 | kWh
|  |  | Fuel | 3.057 | 3.026 | 2.996 | kwh | cents
|  |  | ECRC | 0.13 | 0.123 | 0.12 | kwh | cents
|  |  | ECCR | 0.81 | 0.84 | 0.74 | kW | dollars
|  |  | SPPCRC | 0.59 | 0.53 | 0.06 | kw | dollars
|  |  | Demand | 13.75 | 11.5 | 8.99 | kW | dollars
|  |  | Energy | 0.73 | 1.034 | 1.142 | kwh | cents
|  |  |  | 28864.296 | 309405.6 | 281845.6
|  |  | tax | 0.025641 | 0.025641 | 0.025641
|  |  | after tax base | 29604.4054 | 317339.069 | 289072.403
|  | 2022 |  | 1.167% | 1.078% | 0.1245%
|  | 2023 |  | 1.277% | 1.191% | 0.1868%
|  | 2024 |  | 1.368% | 1.286% | 0.2283%

## DPL-1 LUG 22-24
Tampa Electric's Distribution Lateral Undergrounding Program Projects by Year and Projected Costs (in millions)
| Projects | Costs
2022 | 646 | 105.8434
2023 | 399 | 104.7189
2024 | 436 | 105.181

## DPL-2 TransAccess B&C
Tampa Electric - Proposed 2022-2031 Storm Protection Plan Transmission Access Enhancements Program Projected Costs versus Benefits
Storm Protection Program | Projected Costs (in Millions) |  | Projected Reduction in Restoration Costs (Approximate Benefits in Percent) | Projected Reduction in Customer Minutes of Interruption (Approximate Benefits in Percent) | Program Start Date | Program End Date
| Capital | O&M
Transmission Access Enhancements | 31.4538 | 0 | 28 | 55 | Q1 2021 | After 2031

## DPL-3 TransAccess 22-24
Tampa Electric's Transmission Access Enhancements Program Projects by Year and Projected Costs (in millions)
| Projects | Costs
2022 | 25 | 2.41
2023 | 25 | 3.0374
2024 | 13 | 3.0066

## DPL-4 TransAccess-Combine
Total Transmission Access Enhancements Program Costs (in thousands)
| Access Road Projects Costs | Access Bridge Project Costs | Total Transmission Access Project Costs
2022 | 724 | 1686 | 2410
2023 | 879 | 2158 | 3037
2024 | 1844.017 | 1162.563 | 3006.58
2025 | 1613.762 | 2089.131 | 3702.893
2026 | 2838.058 | 608.458 | 3446.516
2027 | 3403.726 | 0 | 3403.726
2028 | 1931.687 | 1210.654 | 3142.341
2029 | 1166.574 | 1672.197 | 2838.771
2030 | 997.361 | 1043.463 | 2040.824
2031 | 4424.772 | 0 | 4424.772

## DPL-5 TransAsset 22-24
Tampa Electric's Transmission Asset Upgrades Program Projects by Year and Projected Costs (in millions)
| Projects | Costs
2022 | 37 | 16.9734
2023 | 26 | 17.9877
2024 | 10 | 18.0744

## DPL-6 Dist OFH 22-24
Tampa Electric's Distribution Overhead Feeder Hardening Program Projects by Year and Projected Costs (in millions)
| Projects | Costs
2022 | 36 | 33.3995
2023 | 31 | 30.7338
2024 | 23 | 30.6685

## DPL-7 Infra inspect
Projected Number of Infrastructure Inspections
| 2022 | 2023 | 2024
Joint Use Audit | Note 1
Distribution
Wood Pole Inspections | 35625 | 35625 | 16625
Transmission
Wood Pole/Groundline Inspections | 663 | 479 | 401
Above Ground Inspections | 3386 | 2641 | 2702
Aerial Infrared Patrols | Annually | Annually | Annually
Ground Patrols | Annually | Annually | Annually
Substation Inspections | Annually | Annually | Annually

## DPL-8 Infra inspect Cost
Projected Costs of Infrastructure Inspections (in thousands)
| 2022 | 2023 | 2024
Distribution
Wood Pole Inspections | 1020 | 1040 | 1061
Transmission
Wood Pole/Groundline Inspections | 62 | 64 | 65
Above Ground Inspections | 10 | 11 | 11
Aerial Infrared Patrols | 114 | 117 | 119
Ground Patrols | 201 | 154 | 157
Substation Inspections | 146 | 146 | 148
| 1553 | 1532 | 1561

## DPL- 9 Legacy Prgm cost 22-242
Tampa Electric's Legacy Storm Hardening Plan Initiatives Projected Costs(in millions)
| Disaster Preparedness and Recovery Plan | Distribution Pole Replacements
2022 | 0.3 | 13.3184
2023 | 0.3 | 13.7206
2024 | 0.3 | 14.135

## DPL-10 SPP BC Summary
Tampa Electric - Proposed 2022-2031 Storm Protection Plan Projected Costs versus Benefits
Storm Protection Program | Projected Costs (in Millions) |  | Projected Reduction in Restoration Costs (Approximate Benefits in Percent) | Projected Reduction in Customer Minutes of Interruption (Approximate Benefits in Percent) | Program Start Date | Program End Date
| Capital | O&M
Distribution Lateral Undergrounding | 1070.2054 | 2.0184 | 32 | 45 | Q2 2020 | After 2031
Vegetation Management | 0 | 324.768 | 21 | 22 to 29 | Q2 2020 | After 2031
Transmission Asset Upgrades | 139.1195 | 5.605 | 85 | 14 | Q2 2020 | 2029
Substation Extreme Weather Hardening | 28.8 | 0 | 20 to 25 | 12 to 45 | Q1 2021 | After 2031
Distribution Overhead Feeder Hardening | 316.8984 | 7.9445 | 54 | 46 | Q2 2020 | After 2031
Transmission Access Enhancements | 31.4538 | 0 | 28 | 55 | Q1 2021 | After 2031

## DPL-11 LUG Appendix
Tampa Electric's Distribution Lateral Undergrounding - Year 2022 Details
Project ID | Circuit No. | Specific Project Detail |  | Customers |  |  |  | Priority Customers | Project Start Qtr | Construction |  | Project Cost in 2022
|  | OH to UG Length Converted (miles) | Poles | Residential | Small C&I | Large C&I | Total |  |  | Start Qtr | End Qtr
LUG CSA 13021.60058683 | 13021 | 0.30682 | 28 | 130 | 11 | 1 | 142 | 3 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 634109.091
LUG CSA 13021.92350282 | 13021 | 0.3178 | 27 | 14 | 11 | 0 | 25 | 12 | Q1 - 2021 | Q4 - 2021 | Q1 - 2022 | 140500
LUG CSA 13026.60059452 | 13026 | 0.16383 | 11 | 64 | 7 | 2 | 73 | 0 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 152871.2122
LUG CSA 13026.60059457 | 13026 | 0.20814 | 15 | 24 | 13 | 0 | 37 | 0 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 208780.3029
LUG CSA 13026.60059509 | 13026 | 0.085795 | 8 | 84 | 11 | 2 | 97 | 0 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 86294.4474
LUG CSA 13026.60059524 | 13026 | 0.18939 | 16 | 115 | 13 | 0 | 128 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 484875.7274
LUG CSA 13093.91004837 | 13093 | 0.18504 | 17 | 143 | 29 | 3 | 175 | 18 | Q3 - 2020 | Q1 - 2022 | Q2 - 2022 | 664204.5455
LUG CSA 13099.10368943 | 13099 | 0.24242 | 13 | 2 | 3 | 0 | 5 | 0 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 238465.4078
LUG CSA 13099.60125388 | 13099 | 0.43447 | 24 | 68 | 5 | 0 | 73 | 0 | Q1 - 2021 | Q3 - 2022 | Q2 - 2023 | 747872.1252
LUG CSA 13099.90882614 | 13099 | 0.23731 | 18 | 128 | 9 | 2 | 139 | 0 | Q3 - 2020 | Q2 - 2022 | Q3 - 2022 | 577003.0303
LUG CSA 13100.91340554 | 13100 | 0.41193 | 28 | 403 | 7 | 3 | 413 | 0 | Q4 - 2020 | Q4 - 2022 | Q3 - 2023 | 154710.58
LUG CSA 13102.60123654 | 13102 | 0.19034 | 15 | 72 | 1 | 2 | 75 | 0 | Q3 - 2020 | Q3 - 2021 | Q1 - 2022 | 55000
LUG CSA 13102.90748252 | 13102 | 0.23333 | 23 | 29 | 2 | 1 | 32 | 0 | Q2 - 2021 | Q3 - 2022 | Q4 - 2022 | 854885.3758
LUG CSA 13102.91293905 | 13102 | 0.11629 | 10 | 47 | 13 | 4 | 64 | 1 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 123608.3661
LUG CSA 13104.10362869 | 13104 | 0.3803 | 30 | 67 | 20 | 3 | 90 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 497526.3636
LUG CSA 13104.91241032 | 13104 | 0.15038 | 18 | 19 | 2 | 2 | 23 | 0 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 148692.2606
LUG CSA 13104.91643108 | 13104 | 0.33845 | 33 | 74 | 19 | 1 | 94 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 430741.9816
LUG CSA 13104.91668251 | 13104 | 0.20265 | 17 | 16 | 8 | 0 | 24 | 0 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 187342.4242
LUG CSA 13105.10580676 | 13105 | 0.13239 | 13 | 14 | 3 | 0 | 17 | 0 | Q1 - 2021 | Q3 - 2021 | Q1 - 2022 | 14000
LUG CSA 13105.10580689 | 13105 | 0.12765 | 10 | 44 | 3 | 0 | 47 | 0 | Q1 - 2021 | Q1 - 2022 | Q2 - 2022 | 120742.4242
LUG CSA 13105.10580690 | 13105 | 0.23314 | 21 | 122 | 15 | 1 | 138 | 0 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 238847.4429
LUG CSA 13105.60164901 | 13105 | 0.11439 | 10 | 79 | 5 | 1 | 85 | 0 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 104230.3029
LUG CSA 13106.10361901 | 13106 | 0.74848 | 52 | 274 | 21 | 0 | 295 | 0 | Q1 - 2021 | Q4 - 2021 | Q2 - 2022 | 188155.12
LUG CSA 13106.91722510 | 13106 | 0.10852 | 9 | 166 | 10 | 1 | 177 | 0 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 259986.3636
LUG CSA 13107.10376173 | 13107 | 0.43542 | 28 | 119 | 27 | 2 | 148 | 0 | Q4 - 2020 | Q2 - 2022 | Q4 - 2022 | 389526.71
LUG CSA 13107.10376186 | 13107 | 0.12348 | 10 | 179 | 4 | 0 | 183 | 0 | Q1 - 2021 | Q4 - 2021 | Q1 - 2022 | 28000
LUG CSA 13107.10376201 | 13107 | 0.13485 | 10 | 8 | 1 | 0 | 9 | 0 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 130871.3758
LUG CSA 13158.60011810 | 13158 | 0.75795 | 56 | 226 | 10 | 1 | 237 | 1 | Q1 - 2021 | Q1 - 2022 | Q2 - 2022 | 245476.3
LUG CSA 13158.90816343 | 13158 | 0.25019 | 18 | 123 | 4 | 1 | 128 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 612548.4848
LUG CSA 13158.91461782 | 13158 | 0.33428 | 30 | 39 | 3 | 0 | 42 | 0 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 314198.4848
LUG CSA 13176.10375136 | 13176 | 0.65701 | 57 | 11 | 9 | 11 | 31 | 2 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 621962.1213
LUG CSA 13176.10375141 | 13176 | 0.62348 | 51 | 89 | 9 | 4 | 102 | 8 | Q1 - 2021 | Q4 - 2022 | Q2 - 2023 | 78658.06
LUG CSA 13176.10375148 | 13176 | 0.48087 | 54 | 26 | 5 | 3 | 34 | 0 | Q1 - 2021 | Q4 - 2021 | Q2 - 2022 | 131000
LUG CSA 13188.10655453 | 13188 | 0.12235 | 15 | 46 | 15 | 3 | 64 | 9 | Q4 - 2020 | Q3 - 2022 | Q4 - 2022 | 116100
LUG CSA 13188.92070695 | 13188 | 0.1697 | 11 | 17 | 2 | 0 | 19 | 0 | Q1 - 2021 | Q4 - 2022 | Q1 - 2023 | 83831.42
LUG CSA 13204.60170504 | 13204 | 0.37992 | 31 | 113 | 8 | 1 | 122 | 12 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 522778.7878
LUG CSA 13205.90022802 | 13205 | 0.20152 | 18 | 20 | 5 | 1 | 26 | 6 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 262324.2426
LUG CSA 13205.90442230 | 13205 | 0.2517 | 25 | 60 | 0 | 3 | 63 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 506543.4726
LUG CSA 13205.90929181 | 13205 | 0.19943 | 15 | 32 | 19 | 2 | 53 | 0 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 380640.909
LUG CSA 13354.10582069 | 13354 | 0.19205 | 21 | 281 | 15 | 0 | 296 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 40179.72
LUG CSA 13399.60037987 | 13399 | 0.18902 | 19 | 19 | 13 | 4 | 36 | 11 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 400026.4426
LUG CSA 13418.91924595 | 13418 | 0.21515 | 20 | 25 | 12 | 0 | 37 | 0 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 220188.0442
LUG CSA 13418.92018190 | 13418 | 0.32898 | 21 | 79 | 5 | 1 | 85 | 6 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 323959.4964
LUG CSA 13418.92357188 | 13418 | 0.47045 | 33 | 61 | 28 | 1 | 90 | 0 | Q4 - 2020 | Q3 - 2022 | Q1 - 2023 | 655600
LUG CSA 13468.60128362 | 13468 | 0.53409 | 38 | 147 | 32 | 0 | 179 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 494945.4545
LUG CSA 13468.60128378 | 13468 | 0.75398 | 56 | 444 | 17 | 0 | 461 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 564226.34
LUG CSA 13468.91640192 | 13468 | 0.10682 | 7 | 6 | 4 | 0 | 10 | 0 | Q1 - 2021 | Q4 - 2022 | Q1 - 2023 | 113931.811
LUG CSA 13590.91231633 | 13590 | 0.34205 | 29 | 47 | 11 | 2 | 60 | 0 | Q1 - 2021 | Q4 - 2021 | Q1 - 2022 | 142000
LUG CSA 13592.91365233 | 13592 | 0.30777 | 25 | 121 | 12 | 0 | 133 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 616480.5426
LUG CSA 13593.93057902 | 13593 | 0.45455 | 39 | 83 | 52 | 4 | 139 | 0 | Q4 - 2020 | Q1 - 2022 | Q3 - 2022 | 368400
LUG CSA 13632.10408272 | 13632 | 0.097727 | 9 | 12 | 8 | 0 | 20 | 0 | Q1 - 2021 | Q4 - 2022 | Q1 - 2023 | 93642.52
LUG CSA 13632.10408290 | 13632 | 1.0176 | 55 | 245 | 10 | 0 | 255 | 0 | Q1 - 2021 | Q4 - 2022 | Q3 - 2023 | 948857.22
LUG CSA 13632.60305848 | 13632 | 0.40417 | 33 | 43 | 15 | 0 | 58 | 0 | Q1 - 2021 | Q4 - 2022 | Q2 - 2023 | 196308.43
LUG CSA 13633.90564142 | 13633 | 0.073106 | 3 | 2 | 1 | 0 | 3 | 0 | Q2 - 2021 | Q1 - 2022 | Q2 - 2022 | 60945.17
LUG CSA 13633.91847345 | 13633 | 0.086174 | 7 | 1 | 10 | 0 | 11 | 5 | Q1 - 2021 | Q4 - 2022 | Q2 - 2023 | 5185.08
LUG CSA 13826.60127680 | 13826 | 0.2733 | 13 | 243 | 17 | 2 | 262 | 1 | Q2 - 2021 | Q3 - 2022 | Q4 - 2022 | 81217.33
LUG CSA 13831.10427677 | 13831 | 0.25417 | 18 | 313 | 18 | 0 | 331 | 6 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 233666.6668
LUG CSA 13835.10429505 | 13835 | 0.20303 | 17 | 41 | 5 | 2 | 48 | 0 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 541440.909
LUG CSA 13835.10429522 | 13835 | 0.69015 | 41 | 163 | 8 | 1 | 172 | 1 | Q1 - 2021 | Q2 - 2022 | Q1 - 2023 | 1215306.4842
LUG CSA 13835.60314670 | 13835 | 0.21458 | 18 | 256 | 15 | 1 | 272 | 0 | Q1 - 2021 | Q4 - 2022 | Q1 - 2023 | 102547.94
LUG CSA 13836.91377944 | 13836 | 0.59167 | 41 | 276 | 22 | 2 | 300 | 9 | Q3 - 2020 | Q4 - 2022 | Q1 - 2023 | 102040.98
LUG CSA 13934.10467575 | 13934 | 0.091288 | 6 | 1 | 3 | 3 | 7 | 3 | Q1 - 2021 | Q4 - 2021 | Q1 - 2022 | 33500
LUG CSA 13934.10467597 | 13934 | 0.55871 | 30 | 51 | 0 | 2 | 53 | 1 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 525439.3939
LUG CSA 13939.60144164 | 13939 | 0.12121 | 8 | 38 | 6 | 4 | 48 | 5 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 112739.3939
LUG CSA 13939.60144172 | 13939 | 0.14943 | 15 | 2 | 4 | 2 | 8 | 0 | Q1 - 2021 | Q4 - 2021 | Q1 - 2022 | 97000
LUG CSA 13948.10442379 | 13948 | 0.13788 | 12 | 5 | 0 | 1 | 6 | 1 | Q3 - 2021 | Q3 - 2022 | Q4 - 2022 | 137902.2006
LUG CSA 13948.10442391 | 13948 | 0.21534 | 13 | 23 | 6 | 0 | 29 | 0 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 266895.4545
LUG CSA 13993.10372414 | 13993 | 0.42367 | 27 | 31 | 3 | 2 | 36 | 1 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 429828.7878
LUG CSA 13993.10433144 | 13993 | 0.11913 | 10 | 123 | 2 | 0 | 125 | 6 | Q1 - 2021 | Q1 - 2022 | Q2 - 2022 | 90517.79
LUG CSA 14040.10786358 | 14040 | 0.42727 | 19 | 12 | 3 | 0 | 15 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 137792.83
LUG CSA 14040.10786382 | 14040 | 0.23409 | 13 | 98 | 6 | 2 | 106 | 10 | Q2 - 2020 | Q1 - 2022 | Q3 - 2022 | 213950
LUG CSA 14102.91582612 | 14102 | 0.2964 | 18 | 136 | 6 | 0 | 142 | 0 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 278492.4242
LUG DCA 13006.92949400 | 13006 | 1.2864 | 48 | 41 | 2 | 3 | 46 | 2 | Q1 - 2021 | Q3 - 2022 | Q3 - 2023 | 546981.8181
LUG DCA 13432.10761257 | 13432 | 1.2106 | 38 | 21 | 8 | 1 | 30 | 0 | Q2 - 2021 | Q1 - 2022 | Q4 - 2022 | 821237.75
LUG DCA 13815.93026469 | 13815 | 0.49489 | 15 | 27 | 2 | 0 | 29 | 0 | Q3 - 2020 | Q4 - 2021 | Q3 - 2022 | 1205600
LUG ESA 13127.90334707 | 13127 | 0.36061 | 24 | 150 | 4 | 0 | 154 | 11 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 60345.16
LUG ESA 13127.90334731 | 13127 | 0.43826 | 22 | 56 | 1 | 0 | 57 | 3 | Q1 - 2021 | Q2 - 2022 | Q3 - 2022 | 434237.88
LUG ESA 13127.92661768 | 13127 | 0.53409 | 34 | 170 | 3 | 0 | 173 | 1 | Q4 - 2020 | Q1 - 2023 | Q3 - 2023 | 25000
LUG ESA 13127.92663180 | 13127 | 0.61761 | 42 | 33 | 7 | 1 | 41 | 0 | Q1 - 2021 | Q1 - 2023 | Q1 - 2024 | 28500
LUG ESA 13171.10455381 | 13171 | 0.12462 | 11 | 5 | 18 | 1 | 24 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 30449.12
LUG ESA 13171.90598389 | 13171 | 0.21383 | 11 | 370 | 19 | 3 | 392 | 25 | Q3 - 2020 | Q2 - 2023 | Q4 - 2023 | 53000
LUG ESA 13171.93104605 | 13171 | 0.36345 | 21 | 48 | 2 | 2 | 52 | 4 | Q4 - 2020 | Q2 - 2023 | Q4 - 2023 | 11000
LUG ESA 13174.10913196 | 13174 | 0.21269 | 8 | 241 | 14 | 4 | 259 | 4 | Q3 - 2020 | Q3 - 2022 | Q1 - 2023 | 1609359
LUG ESA 13174.60588225 | 13174 | 0.29091 | 15 | 374 | 34 | 1 | 409 | 1 | Q3 - 2020 | Q2 - 2022 | Q3 - 2022 | 165000
LUG ESA 13211.60044019 | 13211 | 0.52746 | 43 | 395 | 27 | 3 | 425 | 0 | Q3 - 2020 | Q2 - 2022 | Q4 - 2022 | 521400
LUG ESA 13225.60139973 | 13225 | 0.80549 | 54 | 41 | 26 | 6 | 73 | 8 | Q3 - 2020 | Q1 - 2023 | Q1 - 2024 | 101000
LUG ESA 13226.10462583 | 13226 | 0.12178 | 19 | 190 | 19 | 2 | 211 | 0 | Q4 - 2020 | Q2 - 2022 | Q3 - 2022 | 130844
LUG ESA 13226.92664597 | 13226 | 0.30947 | 16 | 348 | 4 | 0 | 352 | 0 | Q4 - 2020 | Q1 - 2023 | Q2 - 2023 | 11000
LUG ESA 13226.92665539 | 13226 | 0.087879 | 5 | 13 | 2 | 2 | 17 | 9 | Q3 - 2020 | Q2 - 2023 | Q1 - 2024 | 5000
LUG ESA 13226.92670950 | 13226 | 0.2017 | 23 | 37 | 15 | 5 | 57 | 0 | Q3 - 2020 | Q2 - 2022 | Q4 - 2022 | 213000
LUG ESA 13229.92525393 | 13229 | 0.21496 | 21 | 141 | 21 | 2 | 164 | 4 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 22500
LUG ESA 13230.10471354 | 13230 | 0.44242 | 38 | 49 | 41 | 8 | 98 | 27 | Q4 - 2020 | Q2 - 2023 | Q1 - 2024 | 15000
LUG ESA 13230.10471377 | 13230 | 0.47973 | 31 | 54 | 2 | 2 | 58 | 0 | Q1 - 2021 | Q1 - 2023 | Q3 - 2023 | 18000
LUG ESA 13230.92180224 | 13230 | 0.27992 | 21 | 58 | 16 | 0 | 74 | 0 | Q3 - 2020 | Q3 - 2022 | Q1 - 2023 | 866800
LUG ESA 13230.92496254 | 13230 | 0.28977 | 23 | 12 | 8 | 0 | 20 | 8 | Q1 - 2021 | Q1 - 2023 | Q2 - 2023 | 53170.38
LUG ESA 13231.10868121 | 13231 | 0.27311 | 22 | 23 | 2 | 0 | 25 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 58320.82
LUG ESA 13231.10868138 | 13231 | 0.53977 | 34 | 269 | 17 | 4 | 290 | 8 | Q4 - 2020 | Q1 - 2023 | Q3 - 2023 | 112000
LUG ESA 13433.10466911 | 13433 | 0.70568 | 47 | 159 | 32 | 0 | 191 | 0 | Q4 - 2020 | Q2 - 2022 | Q4 - 2022 | 739800
LUG ESA 13433.93369551 | 13433 | 0.60587 | 37 | 5 | 3 | 2 | 10 | 2 | Q3 - 2020 | Q1 - 2023 | Q3 - 2023 | 16000
LUG ESA 13454.90188551 | 13454 | 0.21004 | 13 | 37 | 2 | 0 | 39 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 65019.94
LUG ESA 13454.90397369 | 13454 | 0.49053 | 26 | 19 | 10 | 1 | 30 | 0 | Q3 - 2020 | Q1 - 2022 | Q3 - 2022 | 343370
LUG ESA 13454.90429155 | 13454 | 0.63826 | 34 | 148 | 6 | 2 | 156 | 4 | Q3 - 2020 | Q3 - 2022 | Q1 - 2023 | 1106500
LUG ESA 13454.90755954 | 13454 | 0.29564 | 23 | 292 | 21 | 1 | 314 | 0 | Q3 - 2020 | Q4 - 2021 | Q2 - 2022 | 216950
LUG ESA 13454.91522987 | 13454 | 0.043371 | 9 | 47 | 3 | 0 | 50 | 1 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 55899.12
LUG ESA 13457.10482593 | 13457 | 0.13693 | 9 | 137 | 8 | 2 | 147 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 30048.68
LUG ESA 13457.90176591 | 13457 | 0.31136 | 18 | 155 | 2 | 0 | 157 | 2 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 27500
LUG ESA 13502.10497396 | 13502 | 0.29545 | 22 | 70 | 2 | 0 | 72 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 44796.48
LUG ESA 13502.92573944 | 13502 | 0.61894 | 40 | 514 | 18 | 0 | 532 | 0 | Q4 - 2020 | Q1 - 2023 | Q3 - 2023 | 46000
LUG ESA 13502.92679861 | 13502 | 0.17614 | 16 | 50 | 25 | 0 | 75 | 0 | Q4 - 2020 | Q2 - 2022 | Q3 - 2022 | 188706
LUG ESA 13509.10501110 | 13509 | 0.089962 | 6 | 3 | 1 | 0 | 4 | 0 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 35373.9
LUG ESA 13509.10501132 | 13509 | 0.10814 | 6 | 7 | 22 | 11 | 40 | 1 | Q4 - 2020 | Q2 - 2023 | Q1 - 2024 | 10300
LUG ESA 13509.10501141 | 13509 | 0.16364 | 15 | 13 | 0 | 2 | 15 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 18000
LUG ESA 13509.10501150 | 13509 | 0.50871 | 33 | 37 | 7 | 0 | 44 | 0 | Q3 - 2020 | Q1 - 2023 | Q1 - 2024 | 73000
LUG ESA 13509.60287236 | 13509 | 0.14527 | 14 | 144 | 14 | 0 | 158 | 0 | Q3 - 2020 | Q2 - 2023 | Q1 - 2024 | 5000
LUG ESA 13509.60346595 | 13509 | 0.14754 | 10 | 14 | 1 | 1 | 16 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 18000
LUG ESA 13509.90504849 | 13509 | 0.95928 | 56 | 676 | 20 | 1 | 697 | 4 | Q4 - 2020 | Q2 - 2023 | Q1 - 2024 | 7000
LUG ESA 13509.91772133 | 13509 | 0.051705 | 8 | 22 | 0 | 1 | 23 | 1 | Q3 - 2020 | Q3 - 2022 | Q4 - 2022 | 94000
LUG ESA 13509.92890860 | 13509 | 0.33485 | 30 | 7 | 1 | 1 | 9 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 18000
LUG ESA 13686.93697046 | 13686 | 0.402 | 14 | 14 | 0 | 0 | 14 | 1 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 23500
LUG ESA 13710.92354144 | 13710 | 0.28371 | 30 | 229 | 12 | 2 | 243 | 4 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 69469.06
LUG ESA 13710.92881445 | 13710 | 0.44867 | 32 | 158 | 17 | 0 | 175 | 0 | Q3 - 2020 | Q2 - 2022 | Q4 - 2022 | 586222
LUG ESA 13793.92685255 | 13793 | 0.18996 | 6 | 26 | 2 | 2 | 30 | 0 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 206879.9
LUG ESA 13793.92686002 | 13793 | 0.22879 | 17 | 1 | 7 | 6 | 14 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 25774.34
LUG ESA 13793.92686712 | 13793 | 0.044318 | 4 | 85 | 2 | 0 | 87 | 0 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 66724.34
LUG ESA 13793.92686736 | 13793 | 0.032197 | 4 | 85 | 4 | 1 | 90 | 0 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 57249.56
LUG ESA 13796.10842823 | 13796 | 0.44811 | 34 | 21 | 20 | 0 | 41 | 0 | Q3 - 2020 | Q3 - 2022 | Q1 - 2023 | 466500
LUG ESA 13796.10842826 | 13796 | 0.15189 | 13 | 353 | 11 | 0 | 364 | 0 | Q4 - 2020 | Q3 - 2022 | Q4 - 2022 | 156000
LUG ESA 13796.92356181 | 13796 | 0.26477 | 14 | 6 | 1 | 3 | 10 | 7 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 205985.68
LUG ESA 13796.92728705 | 13796 | 0.44981 | 34 | 318 | 6 | 1 | 325 | 0 | Q4 - 2020 | Q2 - 2023 | Q1 - 2024 | 13000
LUG ESA 13796.92884623 | 13796 | 1.2991 | 54 | 52 | 15 | 1 | 68 | 1 | Q3 - 2020 | Q1 - 2023 | Q1 - 2024 | 6000
LUG ESA 13797.93185703 | 13797 | 0.044697 | 5 | 2 | 0 | 1 | 3 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 60874.78
LUG ESA 13797.93188519 | 13797 | 0.65966 | 50 | 152 | 6 | 5 | 163 | 0 | Q4 - 2020 | Q2 - 2022 | Q4 - 2022 | 654560
LUG ESA 13799.60395568 | 13799 | 0.45739 | 45 | 260 | 16 | 1 | 277 | 0 | Q4 - 2020 | Q1 - 2023 | Q3 - 2023 | 43000
LUG ESA 13878.10105717 | 13878 | 0.31288 | 23 | 346 | 5 | 0 | 351 | 2 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 86367.3
LUG ESA 13878.10105723 | 13878 | 0.31307 | 25 | 46 | 37 | 8 | 91 | 4 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 22500
LUG ESA 13878.10105726 | 13878 | 0.54015 | 44 | 137 | 2 | 0 | 139 | 2 | Q1 - 2021 | Q1 - 2023 | Q3 - 2023 | 24000
LUG ESA 13878.10105728 | 13878 | 0.23201 | 14 | 26 | 0 | 0 | 26 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 59995.6
LUG ESA 13883.91179506 | 13883 | 0.075 | 6 | 151 | 7 | 1 | 159 | 0 | Q3 - 2020 | Q4 - 2021 | Q2 - 2022 | 60500
LUG ESA 13883.92008787 | 13883 | 0.058333 | 8 | 3 | 0 | 1 | 4 | 0 | Q3 - 2020 | Q3 - 2022 | Q4 - 2022 | 66050
LUG ESA 13906.10096960 | 13906 | 0.37689 | 26 | 56 | 4 | 0 | 60 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 61500
LUG ESA 13906.10096964 | 13906 | 0.6767 | 40 | 31 | 2 | 3 | 36 | 10 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 23500
LUG ESA 13906.10096968 | 13906 | 0.55739 | 53 | 99 | 9 | 5 | 113 | 12 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 26250
LUG ESA 13906.90137810 | 13906 | 0.80322 | 53 | 62 | 4 | 2 | 68 | 0 | Q1 - 2021 | Q2 - 2023 | Q4 - 2023 | 25000
LUG ESA 13906.92282884 | 13906 | 0.095455 | 7 | 26 | 2 | 1 | 29 | 0 | Q1 - 2021 | Q3 - 2022 | Q4 - 2022 | 119524.32
LUG ESA 13909.90380435 | 13909 | 0.20095 | 11 | 41 | 4 | 0 | 45 | 0 | Q1 - 2021 | Q2 - 2023 | Q4 - 2023 | 32973.46
LUG ESA 13909.92173076 | 13909 | 0.31155 | 22 | 8 | 10 | 4 | 22 | 6 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 23500
LUG ESA 13911.10554595 | 13911 | 0.1303 | 16 | 4 | 0 | 2 | 6 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 20000
LUG ESA 13911.60157736 | 13911 | 0.051894 | 5 | 62 | 1 | 0 | 63 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 26849.56
LUG ESA 13911.60157737 | 13911 | 0.65909 | 48 | 747 | 13 | 1 | 761 | 4 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 198750
LUG ESA 13911.90130568 | 13911 | 0.85871 | 53 | 108 | 18 | 0 | 126 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 22500
LUG ESA 13911.91995336 | 13911 | 0.30095 | 19 | 93 | 2 | 0 | 95 | 0 | Q1 - 2021 | Q1 - 2023 | Q3 - 2023 | 23500
LUG ESA 13911.92679866 | 13911 | 0.55549 | 50 | 80 | 27 | 0 | 107 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 27500
LUG ESA 14116.60140011 | 14116 | 0.32595 | 29 | 50 | 4 | 3 | 57 | 4 | Q4 - 2020 | Q1 - 2022 | Q3 - 2022 | 328562
LUG ESA 14116.91073265 | 14116 | 0.092614 | 7 | 10 | 8 | 0 | 18 | 0 | Q1 - 2021 | Q1 - 2024 | Q1 - 2024 | 34747.8
LUG ESA 14355.60258173 | 14355 | 0.15777 | 15 | 356 | 21 | 2 | 379 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 31298.86
LUG ESA 14355.92354352 | 14355 | 0.31856 | 22 | 51 | 3 | 3 | 57 | 1 | Q1 - 2021 | Q1 - 2024 | Q1 - 2024 | 21250
LUG PCA 13120.60015632 | 13120 | 0.20303 | 14 | 135 | 8 | 1 | 144 | 1 | Q3 - 2020 | Q4 - 2021 | Q2 - 2022 | 194372
LUG PCA 13146.10629014 | 13146 | 0.54337 | 30 | 91 | 6 | 0 | 97 | 0 | Q3 - 2020 | Q1 - 2023 | Q3 - 2023 | 56106
LUG PCA 13243.90684154 | 13243 | 0.22841 | 19 | 7 | 0 | 4 | 11 | 0 | Q3 - 2021 | Q1 - 2023 | Q2 - 2023 | 122978
LUG PCA 13243.91351288 | 13243 | 0.28617 | 18 | 223 | 18 | 0 | 241 | 0 | Q1 - 2021 | Q1 - 2023 | Q3 - 2023 | 298166
LUG PCA 13268.10705945 | 13268 | 1.4027 | 67 | 76 | 19 | 0 | 95 | 0 | Q2 - 2021 | Q1 - 2023 | Q4 - 2023 | 122156
LUG PCA 13268.91633548 | 13268 | 0.8911 | 48 | 216 | 23 | 2 | 241 | 1 | Q1 - 2021 | Q2 - 2022 | Q1 - 2023 | 802646
LUG PCA 13268.92962459 | 13268 | 0.43333 | 28 | 48 | 6 | 1 | 55 | 0 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 129753
LUG PCA 13390.92599119 | 13390 | 0.72367 | 46 | 266 | 27 | 3 | 296 | 0 | Q3 - 2020 | Q3 - 2021 | Q2 - 2022 | 1511052
LUG PCA 13655.90431393 | 13655 | 1.2312 | 70 | 298 | 26 | 3 | 327 | 0 | Q2 - 2021 | Q1 - 2023 | Q4 - 2023 | 152476
LUG PCA 13722.60360851 | 13722 | 0.21288 | 17 | 124 | 18 | 1 | 143 | 0 | Q1 - 2021 | Q1 - 2023 | Q4 - 2023 | 185066
LUG PCA 13724.10671229 | 13724 | 0.29678 | 16 | 9 | 5 | 0 | 14 | 0 | Q1 - 2021 | Q4 - 2021 | Q4 - 2022 | 375122
LUG PCA 13724.10671319 | 13724 | 1.7574 | 83 | 181 | 35 | 2 | 218 | 0 | Q1 - 2021 | Q3 - 2022 | Q3 - 2023 | 1803592
LUG PCA 13724.10671334 | 13724 | 0.57254 | 31 | 120 | 22 | 0 | 142 | 0 | Q1 - 2021 | Q3 - 2022 | Q3 - 2023 | 145165
LUG PCA 13724.90911087 | 13724 | 0.5392 | 32 | 31 | 4 | 0 | 35 | 6 | Q3 - 2020 | Q3 - 2022 | Q2 - 2023 | 340878
LUG PCA 13724.91049435 | 13724 | 1.9932 | 103 | 97 | 17 | 2 | 116 | 0 | Q1 - 2021 | Q1 - 2023 | Q3 - 2023 | 122648
LUG PCA 13785.92299245 | 13785 | 1.0799 | 57 | 174 | 10 | 0 | 184 | 0 | Q1 - 2021 | Q4 - 2021 | Q4 - 2022 | 1001289
LUG PCA 13785.92466250 | 13785 | 0.72008 | 31 | 72 | 13 | 1 | 86 | 0 | Q3 - 2020 | Q4 - 2021 | Q4 - 2022 | 858204
LUG PCA 13961.10696431 | 13961 | 0.15795 | 8 | 4 | 0 | 2 | 6 | 4 | Q1 - 2021 | Q1 - 2023 | Q3 - 2023 | 54732
LUG PCA 13961.10696486 | 13961 | 0.5447 | 32 | 38 | 5 | 0 | 43 | 0 | Q1 - 2021 | Q1 - 2022 | Q4 - 2022 | 267570
LUG PCA 13961.60193482 | 13961 | 0.4822 | 35 | 118 | 13 | 4 | 135 | 0 | Q3 - 2020 | Q4 - 2021 | Q3 - 2022 | 225732
LUG PCA 13961.91967308 | 13961 | 0.48693 | 32 | 28 | 4 | 1 | 33 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 157398
LUG PCA 13961.92820848 | 13961 | 0.49451 | 26 | 509 | 10 | 2 | 521 | 0 | Q3 - 2020 | Q1 - 2022 | Q3 - 2022 | 196174
LUG PCA 13961.92829453 | 13961 | 0.33693 | 25 | 447 | 3 | 2 | 452 | 0 | Q3 - 2020 | Q1 - 2023 | Q3 - 2023 | 59592
LUG PCA 13961.92834683 | 13961 | 0.72027 | 37 | 23 | 4 | 1 | 28 | 0 | Q1 - 2021 | Q1 - 2022 | Q4 - 2022 | 789692
LUG SHA 13001.10663240 | 13001 | 0.45189 | 26 | 16 | 5 | 2 | 23 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 43272.14
LUG SHA 13001.10663262 | 13001 | 0.092045 | 8 | 63 | 4 | 0 | 67 | 10 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 21500
LUG SHA 13001.10663269 | 13001 | 0.11818 | 8 | 16 | 4 | 0 | 20 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 23774.34
LUG SHA 13001.60179144 | 13001 | 0.66742 | 42 | 162 | 14 | 2 | 178 | 4 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 138000
LUG SHA 13001.60179191 | 13001 | 0.36439 | 30 | 139 | 11 | 1 | 151 | 1 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 60019.94
LUG SHA 13001.92048269 | 13001 | 0.23845 | 17 | 137 | 15 | 0 | 152 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 34323.02
LUG SHA 13001.93346473 | 13001 | 0.80947 | 48 | 483 | 22 | 3 | 508 | 5 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 47114.44
LUG SHA 13003.10895211 | 13003 | 2.4676 | 116 | 179 | 34 | 1 | 214 | 14 | Q1 - 2021 | Q1 - 2023 | Q4 - 2023 | 24000
LUG SHA 13342.10925094 | 13342 | 0.32689 | 22 | 45 | 12 | 1 | 58 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 26500
LUG SHA 13342.90527363 | 13342 | 0.15606 | 10 | 29 | 5 | 0 | 34 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 500
LUG SHA 13342.91010293 | 13342 | 0.35966 | 27 | 190 | 5 | 2 | 197 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 26500
LUG SHA 13645.91519309 | 13645 | 0.49508 | 22 | 36 | 3 | 1 | 40 | 0 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 551701.76
LUG SHA 13645.92207754 | 13645 | 0.73258 | 28 | 7 | 3 | 2 | 12 | 3 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 23774.34
LUG SHA 13652.92748361 | 13652 | 0.47689 | 23 | 23 | 21 | 0 | 44 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 31398.24
LUG SHA 13780.10723993 | 13780 | 0.27008 | 17 | 97 | 4 | 0 | 101 | 1 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 38097.36
LUG SHA 13817.10722417 | 13817 | 1.7845 | 123 | 569 | 35 | 1 | 605 | 2 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 33000
LUG SHA 13897.10933151 | 13897 | 0.78845 | 33 | 64 | 20 | 1 | 85 | 1 | Q3 - 2020 | Q1 - 2022 | Q3 - 2022 | 785112
LUG SHA 13900.10717269 | 13900 | 0.41818 | 21 | 136 | 15 | 1 | 152 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 63619.5
LUG SHA 13900.91863298 | 13900 | 0.26648 | 18 | 169 | 3 | 0 | 172 | 8 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 100464.66
LUG SHA 13900.92336596 | 13818 | 0.45928 | 21 | 3 | 1 | 5 | 9 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 23774.34
LUG SHA 14020.60223573 | 14020 | 0.48087 | 45 | 415 | 8 | 3 | 426 | 2 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 24250
LUG SHA 14022.90591555 | 14022 | 0.75833 | 49 | 485 | 7 | 3 | 495 | 29 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 763012.48
LUG SHA 14024.10747874 | 14024 | 0.15057 | 13 | 135 | 7 | 0 | 142 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 40997.8
LUG SHA 14024.90116190 | 14024 | 0.1267 | 11 | 12 | 8 | 0 | 20 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 32373.9
LUG WHA 13118.10535995 | 13118 | 0.95057 | 63 | 363 | 15 | 0 | 378 | 0 | Q1 - 2021 | Q1 - 2022 | Q4 - 2022 | 937189
LUG WHA 13118.10535999 | 13118 | 0.35492 | 26 | 101 | 5 | 0 | 106 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 393652
LUG WHA 13118.92204382 | 13118 | 0.69129 | 41 | 88 | 6 | 0 | 94 | 0 | Q2 - 2021 | Q1 - 2022 | Q1 - 2023 | 867707
LUG WHA 13118.92612349 | 13118 | 0.93693 | 39 | 220 | 17 | 1 | 238 | 0 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 926697
LUG WHA 13118.92659172 | 13118 | 0.275 | 26 | 18 | 10 | 3 | 31 | 1 | Q1 - 2021 | Q1 - 2023 | Q3 - 2023 | 207720
LUG WHA 13296.10562361 | 13296 | 0.225 | 19 | 37 | 5 | 0 | 42 | 0 | Q1 - 2021 | Q2 - 2022 | Q1 - 2023 | 438832
LUG WHA 13296.60531111 | 13296 | 0.95246 | 68 | 90 | 14 | 2 | 106 | 1 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 888621
LUG WHA 13296.90010289 | 13296 | 1.3356 | 81 | 82 | 12 | 1 | 95 | 4 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 1206963
LUG WHA 13296.92376304 | 13296 | 0.29015 | 20 | 200 | 18 | 0 | 218 | 0 | Q3 - 2021 | Q1 - 2022 | Q1 - 2023 | 342484
LUG WHA 13297.10560425 | 13297 | 0.3142 | 21 | 72 | 3 | 4 | 79 | 0 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 747463
LUG WHA 13297.10560432 | 13297 | 0.43068 | 29 | 362 | 6 | 0 | 368 | 0 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 713526
LUG WHA 13297.60269456 | 13297 | 0.30625 | 30 | 59 | 32 | 4 | 95 | 0 | Q3 - 2021 | Q1 - 2022 | Q1 - 2023 | 359801
LUG WHA 13312.60182741 | 13312 | 0.1483 | 15 | 52 | 11 | 7 | 70 | 0 | Q3 - 2020 | Q1 - 2022 | Q3 - 2022 | 102002
LUG WHA 13313.10684581 | 13313 | 0.24015 | 23 | 38 | 7 | 3 | 48 | 0 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 302581
LUG WHA 13313.10684614 | 13313 | 0.1358 | 16 | 106 | 16 | 3 | 125 | 0 | Q3 - 2021 | Q1 - 2022 | Q1 - 2023 | 246592
LUG WHA 13313.90084626 | 13313 | 0.092045 | 9 | 35 | 78 | 10 | 123 | 0 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 439597
LUG WHA 13314.10567076 | 13314 | 0.42443 | 32 | 89 | 3 | 2 | 94 | 0 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 417912
LUG WHA 13473.60168916 | 13473 | 0.34356 | 24 | 419 | 22 | 1 | 442 | 0 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 241437
LUG WHA 13473.60168942 | 13473 | 0.34678 | 27 | 187 | 7 | 1 | 195 | 0 | Q3 - 2021 | Q1 - 2022 | Q4 - 2022 | 411291
LUG WHA 13473.92097460 | 13473 | 0.24015 | 19 | 152 | 5 | 0 | 157 | 0 | Q2 - 2021 | Q3 - 2023 | Q1 - 2024 | 279503
LUG WHA 13699.10637240 | 13699 | 1.0178 | 48 | 137 | 3 | 1 | 141 | 0 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 690882
LUG WHA 13699.10637242 | 13699 | 0.62462 | 37 | 284 | 27 | 1 | 312 | 0 | Q1 - 2021 | Q1 - 2022 | Q1 - 2023 | 621815
LUG WHA 13699.10637247 | 13699 | 0.18996 | 11 | 119 | 5 | 0 | 124 | 0 | Q1 - 2021 | Q4 - 2022 | Q3 - 2023 | 150226
LUG WHA 13699.10637259 | 13699 | 0.15587 | 13 | 26 | 4 | 0 | 30 | 0 | Q1 - 2021 | Q4 - 2022 | Q3 - 2023 | 169173
LUG WHA 13699.60165416 | 13699 | 0.35795 | 18 | 10 | 20 | 1 | 31 | 0 | Q1 - 2021 | Q3 - 2022 | Q2 - 2023 | 180975
LUG WHA 13916.60279623 | 13916 | 0.18561 | 9 | 282 | 15 | 1 | 298 | 0 | Q1 - 2021 | Q3 - 2022 | Q2 - 2023 | 337807
LUG WHA 13916.91386005 | 13916 | 0.52822 | 36 | 199 | 6 | 0 | 205 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 596018
LUG WHA 13916.92509975 | 13916 | 0.45057 | 35 | 71 | 18 | 0 | 89 | 0 | Q1 - 2021 | Q1 - 2024 | Q4 - 2024 | 402018
LUG WHA 13972.10618037 | 13972 | 0.2517 | 13 | 1 | 2 | 2 | 5 | 0 | Q3 - 2021 | Q3 - 2022 | Q1 - 2023 | 311368
LUG WHA 13972.90241880 | 13972 | 0.90379 | 49 | 130 | 7 | 6 | 143 | 0 | Q3 - 2020 | Q1 - 2023 | Q3 - 2023 | 54732
LUG WHA 13972.92421291 | 13972 | 0.43693 | 23 | 379 | 6 | 1 | 386 | 0 | Q3 - 2020 | Q1 - 2023 | Q3 - 2023 | 54798
LUG WSA 13059.60302601 | 13059 | 0.50701 | 51 | 291 | 18 | 2 | 311 | 0 | Q2 - 2021 | Q3 - 2022 | Q3 - 2023 | 95048.294
LUG WSA 13071.60170422 | 13071 | 0.9947 | 74 | 362 | 11 | 3 | 376 | 10 | Q3 - 2020 | Q1 - 2022 | Q2 - 2023 | 1451993.878
LUG WSA 13071.92377934 | 13071 | 0.98239 | 66 | 63 | 7 | 0 | 70 | 0 | Q2 - 2021 | Q4 - 2022 | Q4 - 2023 | 95048.294
LUG WSA 13078.10127955 | 13078 | 0.17822 | 15 | 33 | 2 | 1 | 36 | 1 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 208039.0828
LUG WSA 13078.10127958 | 13078 | 0.74545 | 35 | 554 | 7 | 2 | 563 | 18 | Q1 - 2021 | Q3 - 2022 | Q3 - 2023 | 65585.4806
LUG WSA 13079.60077605 | 13079 | 0.1803 | 17 | 32 | 6 | 5 | 43 | 5 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 159726.917
LUG WSA 13079.60077624 | 13079 | 0.33655 | 30 | 58 | 4 | 5 | 67 | 0 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 66535.0346
LUG WSA 13079.60104344 | 13079 | 0.1411 | 21 | 25 | 8 | 6 | 39 | 3 | Q1 - 2021 | Q4 - 2021 | Q2 - 2022 | 172906.3078
LUG WSA 13079.90517178 | 13079 | 0.12973 | 16 | 56 | 10 | 3 | 69 | 0 | Q1 - 2021 | Q1 - 2022 | Q2 - 2022 | 64432.4
LUG WSA 13109.60233901 | 13109 | 0.47254 | 42 | 282 | 9 | 0 | 291 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 65585.4806
LUG WSA 13109.90643551 | 13109 | 0.66761 | 50 | 95 | 10 | 4 | 109 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 45330.75
LUG WSA 13111.60072751 | 13111 | 0.20379 | 17 | 18 | 1 | 2 | 21 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 318842.4637
LUG WSA 13111.92999604 | 13111 | 0.41705 | 32 | 61 | 9 | 2 | 72 | 0 | Q3 - 2020 | Q3 - 2022 | Q1 - 2023 | 65585.4806
LUG WSA 13113.90422522 | 13113 | 0.10985 | 6 | 3 | 5 | 4 | 12 | 6 | Q3 - 2021 | Q4 - 2022 | Q2 - 2023 | 65585.4806
LUG WSA 13113.90796385 | 13113 | 0.51326 | 34 | 233 | 19 | 1 | 253 | 0 | Q3 - 2020 | Q1 - 2022 | Q3 - 2022 | 565310.3898
LUG WSA 13113.92909503 | 13113 | 0.072538 | 9 | 215 | 8 | 0 | 223 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 68672.4561
LUG WSA 13138.10145618 | 13138 | 0.071023 | 6 | 92 | 2 | 0 | 94 | 0 | Q1 - 2021 | Q1 - 2022 | Q2 - 2022 | 40845.3
LUG WSA 13138.10145628 | 13138 | 0.30379 | 18 | 352 | 5 | 4 | 361 | 0 | Q3 - 2020 | Q4 - 2021 | Q2 - 2022 | 335531.1407
LUG WSA 13138.60170460 | 13138 | 0.26458 | 23 | 170 | 9 | 0 | 179 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 344455.3419
LUG WSA 13140.10013916 | 13140 | 0.10284 | 13 | 143 | 7 | 4 | 154 | 0 | Q3 - 2020 | Q3 - 2022 | Q1 - 2023 | 65585.4806
LUG WSA 13141.10147344 | 13141 | 0.098485 | 7 | 12 | 6 | 1 | 19 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 77385.5515
LUG WSA 13141.10147371 | 13141 | 0.47027 | 49 | 94 | 3 | 1 | 98 | 0 | Q2 - 2021 | Q4 - 2022 | Q2 - 2023 | 65585.4806
LUG WSA 13141.91575422 | 13141 | 0.095455 | 8 | 34 | 1 | 1 | 36 | 25 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 102196.5312
LUG WSA 13141.92442350 | 13141 | 0.087689 | 13 | 12 | 0 | 1 | 13 | 0 | Q3 - 2021 | Q3 - 2022 | Q1 - 2023 | 65585.4806
LUG WSA 13162.10158432 | 13162 | 0.16439 | 10 | 61 | 3 | 0 | 64 | 12 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 93355.9125
LUG WSA 13162.10158434 | 13162 | 0.38182 | 30 | 47 | 23 | 3 | 73 | 6 | Q2 - 2021 | Q4 - 2022 | Q2 - 2023 | 235331.4629
LUG WSA 13162.90435139 | 13162 | 0.29773 | 24 | 23 | 50 | 5 | 78 | 0 | Q1 - 2021 | Q1 - 2023 | Q3 - 2023 | 66535.0346
LUG WSA 13162.92185426 | 13162 | 0.36572 | 26 | 19 | 23 | 16 | 58 | 0 | Q4 - 2020 | Q1 - 2023 | Q3 - 2023 | 59732.8746
LUG WSA 13162.93124277 | 13162 | 0.15701 | 23 | 5 | 15 | 5 | 25 | 5 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 162651.7639
LUG WSA 13164.90252716 | 13164 | 0.21572 | 15 | 59 | 13 | 2 | 74 | 3 | Q1 - 2022 | Q3 - 2023 | Q1 - 2024 | 65585.4806
LUG WSA 13192.90932106 | 13192 | 0.19318 | 13 | 2 | 2 | 5 | 9 | 9 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 145753.3245
LUG WSA 13194.90645535 | 13194 | 1.0994 | 50 | 285 | 2 | 0 | 287 | 0 | Q1 - 2021 | Q1 - 2023 | Q3 - 2023 | 65585.4806
LUG WSA 13198.10051851 | 13198 | 0.21231 | 21 | 33 | 50 | 2 | 85 | 6 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 195984.5373
LUG WSA 13198.10051875 | 13198 | 0.097348 | 8 | 20 | 2 | 2 | 24 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 165710.9744
LUG WSA 13198.10051896 | 13198 | 0.13258 | 11 | 18 | 2 | 1 | 21 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 120992.8353
LUG WSA 13198.92183966 | 13198 | 0.16629 | 12 | 86 | 26 | 4 | 116 | 0 | Q3 - 2020 | Q3 - 2022 | Q1 - 2023 | 308072.944
LUG WSA 13198.92655424 | 13198 | 0.094129 | 8 | 11 | 7 | 2 | 20 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 174468.8658
LUG WSA 13207.90146892 | 13207 | 0.26402 | 25 | 60 | 9 | 4 | 73 | 0 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 66535.0346
LUG WSA 13207.90147316 | 13207 | 0.20473 | 17 | 23 | 33 | 0 | 56 | 0 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 65585.4806
LUG WSA 13207.90613782 | 13207 | 0.37973 | 31 | 64 | 1 | 2 | 67 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 65585.4806
LUG WSA 13208.92767537 | 13208 | 0.18352 | 18 | 117 | 3 | 1 | 121 | 0 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 90410.4577
LUG WSA 13220.10191173 | 13220 | 0.5178 | 45 | 66 | 17 | 4 | 87 | 9 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 66535.0346
LUG WSA 13220.90901917 | 13220 | 0.48977 | 38 | 55 | 18 | 0 | 73 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 435673.9312
LUG WSA 13333.10007588 | 13333 | 0.16004 | 16 | 16 | 31 | 2 | 49 | 0 | Q1 - 2021 | Q4 - 2022 | Q2 - 2023 | 88822.372
LUG WSA 13333.91785740 | 13333 | 0.23277 | 26 | 13 | 34 | 3 | 50 | 0 | Q4 - 2020 | Q1 - 2022 | Q3 - 2022 | 147333.9586
LUG WSA 13334.91645657 | 13334 | 0.48428 | 46 | 142 | 7 | 1 | 150 | 0 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 59732.8746
LUG WSA 13425.10244449 | 13425 | 0.69659 | 33 | 195 | 12 | 4 | 211 | 0 | Q3 - 2020 | Q3 - 2021 | Q2 - 2022 | 89888.927
LUG WSA 13428.90423835 | 13428 | 0.26326 | 16 | 208 | 1 | 0 | 209 | 12 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 127957.55
LUG WSA 13428.91540495 | 13428 | 0.23314 | 30 | 402 | 20 | 1 | 423 | 1 | Q3 - 2020 | Q1 - 2022 | Q3 - 2022 | 353201.85
LUG WSA 13483.60393455 | 13483 | 1.3216 | 100 | 525 | 31 | 1 | 557 | 4 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 65585.4806
LUG WSA 13490.92815117 | 13490 | 0.16723 | 13 | 163 | 2 | 1 | 166 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 181350.9861
LUG WSA 13491.10230118 | 13491 | 0.51477 | 36 | 94 | 2 | 4 | 100 | 2 | Q3 - 2020 | Q3 - 2021 | Q1 - 2022 | 147295.6787
LUG WSA 13491.91827162 | 13491 | 0.2392 | 21 | 34 | 1 | 1 | 36 | 7 | Q2 - 2021 | Q2 - 2022 | Q4 - 2022 | 137389.8166
LUG WSA 13510.10218990 | 13510 | 0.35814 | 37 | 20 | 18 | 2 | 40 | 0 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 59732.8746
LUG WSA 13514.10624934 | 13514 | 0.23523 | 20 | 18 | 0 | 1 | 19 | 0 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 95048.294
LUG WSA 13514.91361858 | 13514 | 0.16231 | 18 | 70 | 7 | 0 | 77 | 19 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 157418.9783
LUG WSA 13516.60169592 | 13516 | 0.26042 | 19 | 11 | 16 | 4 | 31 | 5 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 267994.0108
LUG WSA 13520.10242257 | 13520 | 0.45095 | 44 | 28 | 9 | 4 | 41 | 0 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 59732.8746
LUG WSA 13522.10392874 | 13522 | 0.15758 | 12 | 4 | 6 | 4 | 14 | 10 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 121523.0444
LUG WSA 13522.10392882 | 13522 | 0.68731 | 61 | 162 | 8 | 0 | 170 | 0 | Q2 - 2021 | Q2 - 2022 | Q4 - 2022 | 65585.4806
LUG WSA 13522.10392902 | 13522 | 0.66591 | 68 | 103 | 30 | 3 | 136 | 0 | Q3 - 2021 | Q1 - 2023 | Q3 - 2023 | 90410.4577
LUG WSA 13522.10392905 | 13522 | 0.47481 | 50 | 105 | 5 | 3 | 113 | 1 | Q2 - 2021 | Q4 - 2022 | Q2 - 2023 | 274069.2817
LUG WSA 13522.10392924 | 13522 | 0.11591 | 9 | 10 | 3 | 2 | 15 | 0 | Q2 - 2021 | Q4 - 2022 | Q3 - 2023 | 65585.4806
LUG WSA 13522.60305720 | 13522 | 0.068371 | 6 | 10 | 0 | 1 | 11 | 0 | Q2 - 2021 | Q2 - 2022 | Q4 - 2022 | 64556.4834
LUG WSA 13522.91947423 | 13522 | 0.52614 | 50 | 47 | 10 | 3 | 60 | 5 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 399055.7495
LUG WSA 13522.92169062 | 13522 | 0.31686 | 29 | 77 | 13 | 0 | 90 | 0 | Q2 - 2021 | Q1 - 2023 | Q3 - 2023 | 66535.0346
LUG WSA 13533.91957169 | 13533 | 0.24432 | 21 | 354 | 15 | 3 | 372 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 251854.93
LUG WSA 13535.91618829 | 13535 | 0.50265 | 34 | 70 | 4 | 1 | 75 | 0 | Q3 - 2021 | Q1 - 2023 | Q3 - 2023 | 79176.5874
LUG WSA 13535.92952190 | 13535 | 0.2572 | 18 | 78 | 2 | 0 | 80 | 0 | Q4 - 2020 | Q2 - 2022 | Q4 - 2022 | 220147.4845
LUG WSA 13535.92983661 | 13535 | 0.33314 | 32 | 10 | 0 | 3 | 13 | 0 | Q3 - 2021 | Q2 - 2022 | Q4 - 2022 | 266452.3115
LUG WSA 13535.92983670 | 13535 | 0.21269 | 14 | 164 | 10 | 1 | 175 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 198828.4689
LUG WSA 13544.10053269 | 13544 | 0.16174 | 16 | 19 | 2 | 0 | 21 | 0 | Q1 - 2021 | Q4 - 2021 | Q2 - 2022 | 41888.25
LUG WSA 13574.10250638 | 13574 | 0.17083 | 12 | 10 | 6 | 4 | 20 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 97585.5962
LUG WSA 13575.90054386 | 13575 | 0.1017 | 13 | 105 | 8 | 3 | 116 | 1 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 120187.6855
LUG WSA 13575.90054924 | 13575 | 0.1072 | 12 | 238 | 2 | 0 | 240 | 5 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 139012.3935
LUG WSA 13586.10255333 | 13586 | 0.12159 | 9 | 4 | 1 | 0 | 5 | 0 | Q1 - 2021 | Q3 - 2021 | Q1 - 2022 | 21743.9297
LUG WSA 13586.60303627 | 13586 | 1.0686 | 67 | 69 | 8 | 5 | 82 | 0 | Q3 - 2020 | Q3 - 2022 | Q1 - 2023 | 678421.45
LUG WSA 13586.91748729 | 13586 | 0.6714 | 42 | 45 | 0 | 3 | 48 | 0 | Q2 - 2021 | Q2 - 2023 | Q1 - 2024 | 90410.4577
LUG WSA 13586.92442286 | 13586 | 0.48902 | 40 | 180 | 7 | 0 | 187 | 1 | Q4 - 2021 | Q4 - 2022 | Q4 - 2023 | 65585.4806
LUG WSA 13589.93162023 | 13589 | 0.3267 | 16 | 1 | 5 | 0 | 6 | 5 | Q2 - 2021 | Q2 - 2022 | Q4 - 2022 | 149294.5055
LUG WSA 13589.93177909 | 13589 | 0.11951 | 6 | 33 | 13 | 0 | 46 | 0 | Q1 - 2021 | Q3 - 2021 | Q1 - 2022 | 24024.4967
LUG WSA 13605.91052996 | 13605 | 0.33201 | 27 | 115 | 12 | 0 | 127 | 0 | Q3 - 2020 | Q1 - 2022 | Q3 - 2022 | 783753.6182
LUG WSA 13612.60002970 | 13612 | 0.24811 | 23 | 131 | 3 | 1 | 135 | 0 | Q1 - 2021 | Q4 - 2021 | Q2 - 2022 | 178914.0068
LUG WSA 13612.60003135 | 13612 | 0.3036 | 33 | 81 | 3 | 1 | 85 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 65585.4806
LUG WSA 13612.60022877 | 13612 | 0.061174 | 7 | 22 | 11 | 0 | 33 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 177278.5764
LUG WSA 13612.90291123 | 13612 | 0.13333 | 15 | 10 | 9 | 1 | 20 | 0 | Q2 - 2021 | Q2 - 2023 | Q1 - 2024 | 90410.4577
LUG WSA 13612.90312305 | 13612 | 0.094886 | 7 | 72 | 4 | 1 | 77 | 0 | Q1 - 2021 | Q2 - 2023 | Q1 - 2024 | 95048.294
LUG WSA 13612.92956326 | 13612 | 0.23428 | 25 | 20 | 12 | 4 | 36 | 8 | Q2 - 2021 | Q4 - 2022 | Q2 - 2023 | 282539.9151
LUG WSA 13669.60107076 | 13669 | 0.12254 | 9 | 4 | 1 | 4 | 9 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 131882.6147
LUG WSA 13669.92770538 | 13669 | 0.30152 | 37 | 204 | 10 | 0 | 214 | 1 | Q2 - 2021 | Q2 - 2023 | Q1 - 2024 | 79176.5874
LUG WSA 13670.93124410 | 13670 | 0.71345 | 25 | 383 | 3 | 1 | 387 | 0 | Q3 - 2020 | Q2 - 2022 | Q4 - 2022 | 289212.544
LUG WSA 13672.10493801 | 13672 | 0.57973 | 43 | 368 | 9 | 1 | 378 | 8 | Q2 - 2021 | Q2 - 2023 | Q1 - 2024 | 65585.4806
LUG WSA 13672.60106849 | 13672 | 0.2678 | 26 | 256 | 12 | 0 | 268 | 0 | Q4 - 2020 | Q3 - 2022 | Q1 - 2023 | 226556.857
LUG WSA 13672.91971930 | 13672 | 0.1947 | 19 | 27 | 3 | 1 | 31 | 3 | Q2 - 2021 | Q2 - 2023 | Q1 - 2024 | 95048.294
LUG WSA 13674.10277747 | 13674 | 0.56723 | 36 | 361 | 6 | 1 | 368 | 2 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 269610.6011
LUG WSA 13674.90420693 | 13674 | 0.3233 | 29 | 125 | 0 | 0 | 125 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 65585.4806
LUG WSA 13678.10254063 | 13678 | 0.275 | 18 | 11 | 6 | 0 | 17 | 0 | Q2 - 2021 | Q4 - 2022 | Q2 - 2023 | 223422.372
LUG WSA 13678.10288738 | 13678 | 0.57784 | 28 | 4 | 1 | 0 | 5 | 0 | Q3 - 2021 | Q3 - 2022 | Q1 - 2023 | 431533.0221
LUG WSA 13678.90514672 | 13678 | 0.5358 | 29 | 9 | 5 | 0 | 14 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 361928.0774
LUG WSA 13737.10297934 | 13737 | 0.19678 | 18 | 24 | 1 | 1 | 26 | 0 | Q2 - 2021 | Q4 - 2022 | Q2 - 2023 | 151120.8568
LUG WSA 13737.10297943 | 13737 | 0.20208 | 18 | 84 | 5 | 3 | 92 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 515924.2419
LUG WSA 13737.60311396 | 13737 | 0.19205 | 8 | 16 | 13 | 0 | 29 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 169528.155
LUG WSA 13737.90740214 | 13737 | 0.10114 | 12 | 15 | 3 | 0 | 18 | 0 | Q2 - 2021 | Q2 - 2022 | Q4 - 2022 | 90477.2148
LUG WSA 13737.90740699 | 13737 | 0.16553 | 13 | 17 | 4 | 0 | 21 | 0 | Q2 - 2021 | Q4 - 2022 | Q2 - 2023 | 136970.8568
LUG WSA 13737.91960399 | 13737 | 0.43277 | 32 | 56 | 3 | 3 | 62 | 0 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 243488.9154
LUG WSA 13738.10298299 | 13738 | 0.31307 | 27 | 71 | 7 | 4 | 82 | 0 | Q3 - 2021 | Q3 - 2023 | Q1 - 2024 | 66535.0346
LUG WSA 13747.10299739 | 13747 | 0.10038 | 5 | 128 | 16 | 2 | 146 | 0 | Q3 - 2020 | Q4 - 2021 | Q1 - 2022 | 28009.845
LUG WSA 13750.60110680 | 13750 | 0.18561 | 12 | 43 | 6 | 0 | 49 | 0 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 91375.9471
LUG WSA 13756.10589587 | 13756 | 0.14356 | 13 | 8 | 4 | 0 | 12 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 170400.3783
LUG WSA 13756.10589595 | 13756 | 0.24924 | 22 | 93 | 7 | 0 | 100 | 0 | Q2 - 2021 | Q4 - 2022 | Q2 - 2023 | 105022.372
LUG WSA 13756.60165355 | 13756 | 0.082955 | 12 | 55 | 10 | 3 | 68 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 115052.3412
LUG WSA 13756.90207831 | 13756 | 0.37917 | 36 | 181 | 18 | 1 | 200 | 44 | Q2 - 2021 | Q2 - 2023 | Q4 - 2023 | 59732.8746
LUG WSA 13860.10307212 | 13860 | 0.25227 | 28 | 2 | 20 | 9 | 31 | 0 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 172514.3964
LUG WSA 13860.10307215 | 13860 | 0.27917 | 26 | 219 | 17 | 4 | 240 | 3 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 255757.2254
LUG WSA 13863.60279838 | 13863 | 0.46989 | 32 | 259 | 5 | 0 | 264 | 2 | Q1 - 2021 | Q4 - 2022 | Q2 - 2023 | 340426.671
LUG WSA 13864.10310477 | 13864 | 0.7108 | 57 | 18 | 233 | 67 | 318 | 16 | Q3 - 2021 | Q3 - 2022 | Q1 - 2023 | 573160.295
LUG WSA 13864.10310497 | 13864 | 0.15 | 10 | 10 | 41 | 9 | 60 | 2 | Q2 - 2021 | Q4 - 2022 | Q2 - 2023 | 319952.477
LUG WSA 13864.10310505 | 13864 | 0.50568 | 41 | 3 | 49 | 31 | 83 | 6 | Q1 - 2021 | Q1 - 2022 | Q3 - 2022 | 491416.5619
LUG WSA 13864.60380454 | 13864 | 0.15795 | 13 | 1 | 1 | 1 | 3 | 1 | Q1 - 2021 | Q3 - 2021 | Q1 - 2022 | 47404.3375
LUG WSA 13865.90531031 | 13865 | 0.26383 | 19 | 21 | 11 | 5 | 37 | 9 | Q1 - 2021 | Q2 - 2023 | Q4 - 2023 | 59732.8746
LUG WSA 13870.90428273 | 13870 | 0.4017 | 25 | 104 | 8 | 0 | 112 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 318493.3002
LUG WSA 13873.60311122 | 13873 | 0.79261 | 61 | 235 | 7 | 3 | 245 | 3 | Q3 - 2021 | Q2 - 2023 | Q1 - 2024 | 79176.5874
LUG WSA 13892.10338448 | 13892 | 1.1121 | 71 | 256 | 8 | 2 | 266 | 2 | Q3 - 2021 | Q2 - 2023 | Q1 - 2024 | 59732.8746
LUG WSA 14030.60125643 | 14030 | 0.089205 | 14 | 101 | 3 | 0 | 104 | 1 | Q1 - 2021 | Q2 - 2022 | Q4 - 2022 | 70412.544
LUG WSA 14030.60341032 | 14030 | 0.13239 | 10 | 81 | 1 | 0 | 82 | 0 | Q2 - 2021 | Q2 - 2022 | Q4 - 2022 | 94885.4148
LUG WSA 14030.90886759 | 14030 | 0.53788 | 49 | 161 | 15 | 1 | 177 | 12 | Q2 - 2021 | Q2 - 2023 | Q1 - 2024 | 79176.5874
LUG WSA 14030.92669557 | 14030 | 0.0089015 | 5 | 78 | 12 | 0 | 90 | 0 | Q2 - 2021 | Q3 - 2022 | Q1 - 2023 | 91248.5228
LUG WSA 14030.92669942 | 14030 | 0.55814 | 34 | 112 | 6 | 0 | 118 | 0 | Q2 - 2021 | Q1 - 2023 | Q1 - 2024 | 66535.0346
LUG WSA 14030.92670479 | 14030 | 0.1089 | 6 | 3 | 3 | 0 | 6 | 0 | Q1 - 2021 | Q3 - 2022 | Q1 - 2023 | 100347.5571
Lateral Hardening-Fuse-10007252,1 | 13737 | 0.087689 | 9 | 4 | 0 | 1 | 5 | 0 | Q3 - 2022 | Q1 - 2023 | Q2 - 2023 | 28849.8106
Lateral Hardening-Fuse-10050730,3 | 13199 | 0.53106 | 52 | 271 | 22 | 0 | 293 | 0 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 174718.9393
Lateral Hardening-Fuse-10051863,1 | 13198 | 0.076705 | 10 | 62 | 5 | 0 | 67 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 25235.7955
Lateral Hardening-Fuse-10055000,2 | 13419 | 0.36061 | 28 | 33 | 11 | 0 | 44 | 0 | Q3 - 2022 | Q3 - 2022 | Q1 - 2023 | 118639.3939
Lateral Hardening-Fuse-10055941,1 | 13420 | 0.14659 | 10 | 4 | 1 | 1 | 6 | 0 | Q3 - 2022 | Q2 - 2023 | Q1 - 2024 | 48228.4091
Lateral Hardening-Fuse-10075304,1 | 13656 | 0.11136 | 4 | 2 | 0 | 1 | 3 | 3 | Q4 - 2022 | Q1 - 2024 | Q3 - 2024 | 36638.6364
Lateral Hardening-Fuse-10075336,1 | 13656 | 0.19432 | 15 | 17 | 2 | 5 | 24 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 63930.6818
Lateral Hardening-Fuse-10087587,1 | 13389 | 0.10019 | 6 | 5 | 4 | 0 | 9 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 32962.3106
Lateral Hardening-Fuse-10089965,1 | 13279 | 0.090341 | 12 | 10 | 2 | 1 | 13 | 0 | Q2 - 2022 | Q1 - 2025 | Q3 - 2025 | 29722.1591
Lateral Hardening-Fuse-10092875,1 | 13611 | 0.24659 | 26 | 119 | 2 | 1 | 122 | 75 | Q2 - 2022 | Q2 - 2023 | Q1 - 2024 | 81128.4091
Lateral Hardening-Fuse-10093646,2 | 13043 | 0.37652 | 26 | 47 | 2 | 1 | 50 | 0 | Q3 - 2022 | Q3 - 2022 | Q1 - 2023 | 123873.4848
Lateral Hardening-Fuse-10093658,1 | 13043 | 0.099621 | 11 | 19 | 1 | 1 | 21 | 0 | Q1 - 2022 | Q1 - 2023 | Q3 - 2023 | 32775.3788
Lateral Hardening-Fuse-10093683,1 | 13043 | 0.085038 | 8 | 8 | 4 | 2 | 14 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 27977.4621
Lateral Hardening-Fuse-10100716,1 | 13048 | 0.44186 | 44 | 85 | 2 | 1 | 88 | 12 | Q3 - 2022 | Q3 - 2022 | Q1 - 2023 | 145370.6439
Lateral Hardening-Fuse-10100722,1 | 13048 | 0.062121 | 6 | 14 | 4 | 0 | 18 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 20437.8788
Lateral Hardening-Fuse-10101247,3 | 13046 | 0.40795 | 41 | 57 | 2 | 2 | 61 | 5 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 134217.0454
Lateral Hardening-Fuse-10120786,1 | 13053 | 0.25511 | 28 | 73 | 11 | 0 | 84 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 83932.3864
Lateral Hardening-Fuse-10120788,1 | 13053 | 0.25644 | 23 | 38 | 2 | 1 | 41 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 84368.5606
Lateral Hardening-Fuse-10124545,1 | 13063 | 0.29337 | 26 | 43 | 3 | 1 | 47 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 96519.1288
Lateral Hardening-Fuse-10126980,1 | 13065 | 0.23466 | 23 | 35 | 4 | 0 | 39 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 77202.8409
Lateral Hardening-Fuse-10142238,1 | 13034 | 0.17992 | 15 | 16 | 1 | 1 | 18 | 0 | Q3 - 2022 | Q3 - 2022 | Q1 - 2023 | 59195.0758
Lateral Hardening-Fuse-10144159,1 | 13123 | 0.56117 | 38 | 8 | 34 | 3 | 45 | 17 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 184626.3258
Lateral Hardening-Fuse-10147338,1 | 13141 | 0.18939 | 22 | 56 | 2 | 0 | 58 | 0 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 62310.6061
Lateral Hardening-Fuse-10153131,1 | 13154 | 0.11023 | 14 | 5 | 14 | 4 | 23 | 10 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 36264.7727
Lateral Hardening-Fuse-10158932,1 | 13164 | 0.092045 | 10 | 12 | 0 | 1 | 13 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 30282.9545
Lateral Hardening-Fuse-10160212,1 | 13167 | 0.072348 | 8 | 51 | 4 | 0 | 55 | 0 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 23802.6515
Lateral Hardening-Fuse-10163224,4 | 13091 | 0.41193 | 41 | 50 | 7 | 0 | 57 | 0 | Q2 - 2022 | Q2 - 2022 | Q1 - 2023 | 135525.5681
Lateral Hardening-Fuse-10163228,1 | 13091 | 0.13864 | 15 | 16 | 10 | 0 | 26 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 45611.3636
Lateral Hardening-Fuse-10165356,4 | 13045 | 0.67973 | 62 | 81 | 15 | 4 | 100 | 7 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 223632.765
Lateral Hardening-Fuse-10165381,2 | 13045 | 0.30663 | 28 | 53 | 14 | 3 | 70 | 0 | Q2 - 2022 | Q2 - 2023 | Q1 - 2024 | 100880.8712
Lateral Hardening-Fuse-10165382,1 | 13045 | 0.035227 | 5 | 6 | 10 | 1 | 17 | 0 | Q3 - 2022 | Q2 - 2023 | Q1 - 2024 | 13160
Lateral Hardening-Fuse-10165789,1 | 13072 | 0.22235 | 18 | 16 | 13 | 3 | 32 | 8 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 73152.6515
Lateral Hardening-Fuse-10165797,1 | 13072 | 0.14659 | 15 | 6 | 6 | 1 | 13 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 48228.4091
Lateral Hardening-Fuse-10165803,1 | 13072 | 0.11894 | 12 | 8 | 1 | 2 | 11 | 0 | Q2 - 2022 | Q1 - 2024 | Q2 - 2024 | 39131.0606
Lateral Hardening-Fuse-10167762,1 | 13206 | 0.18409 | 20 | 24 | 3 | 1 | 28 | 2 | Q3 - 2022 | Q1 - 2024 | Q2 - 2024 | 60565.9091
Lateral Hardening-Fuse-10173494,1 | 13191 | 0.20587 | 20 | 20 | 1 | 2 | 23 | 1 | Q2 - 2022 | Q2 - 2023 | Q1 - 2024 | 67731.6288
Lateral Hardening-Fuse-10173500,1 | 13191 | 0.21439 | 17 | 47 | 5 | 0 | 52 | 0 | Q3 - 2022 | Q1 - 2024 | Q2 - 2024 | 70535.6061
Lateral Hardening-Fuse-10173522,1 | 13191 | 0.34867 | 34 | 4 | 25 | 8 | 37 | 9 | Q2 - 2022 | Q1 - 2024 | Q2 - 2024 | 114713.8258
Lateral Hardening-Fuse-10218987,1 | 13510 | 0.085227 | 10 | 206 | 11 | 2 | 219 | 1 | Q3 - 2022 | Q1 - 2024 | Q2 - 2024 | 28039.7727
Lateral Hardening-Fuse-10247860,1 | 13533 | 0.035985 | 5 | 45 | 2 | 0 | 47 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 13160
Lateral Hardening-Fuse-10274748,1 | 13624 | 0.27955 | 19 | 22 | 3 | 0 | 25 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 91970.4545
Lateral Hardening-Fuse-10297412,1 | 13754 | 0.059091 | 8 | 10 | 0 | 1 | 11 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 19440.9091
Lateral Hardening-Fuse-10297440,1 | 13754 | 0.11572 | 14 | 87 | 3 | 0 | 90 | 0 | Q2 - 2022 | Q1 - 2024 | Q2 - 2024 | 38071.7803
Lateral Hardening-Fuse-10297442,1 | 13754 | 0.13788 | 16 | 33 | 12 | 2 | 47 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 45362.1212
Lateral Hardening-Fuse-10361894,1 | 13106 | 0.1322 | 10 | 35 | 2 | 2 | 39 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 43492.803
Lateral Hardening-Fuse-10362869,3 | 13104 | 0.62443 | 47 | 67 | 20 | 3 | 90 | 0 | Q3 - 2022 | Q3 - 2022 | Q1 - 2023 | 63016.4153
Lateral Hardening-Fuse-10363933,1 | 13096 | 0.13068 | 8 | 6 | 2 | 1 | 9 | 8 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 42994.3182
Lateral Hardening-Fuse-10382337,1 | 13224 | 0.087121 | 10 | 15 | 2 | 1 | 18 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 28662.8788
Lateral Hardening-Fuse-10384706,1 | 13351 | 0.10985 | 8 | 26 | 3 | 0 | 29 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 36140.1515
Lateral Hardening-Fuse-10384723,1 | 13351 | 0.25587 | 20 | 65 | 6 | 1 | 72 | 1 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 84181.6288
Lateral Hardening-Fuse-10389247,2 | 13365 | 0.38163 | 35 | 206 | 6 | 0 | 212 | 0 | Q3 - 2022 | Q3 - 2022 | Q1 - 2023 | 125555.8711
Lateral Hardening-Fuse-10392877,1 | 13522 | 0.093371 | 11 | 10 | 2 | 1 | 13 | 8 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 30719.1288
Lateral Hardening-Fuse-10424221,1 | 13828 | 0.047538 | 4 | 2 | 1 | 6 | 9 | 8 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 15639.9621
Lateral Hardening-Fuse-10425054,1 | 13829 | 0.11894 | 9 | 48 | 7 | 0 | 55 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 39131.0606
Lateral Hardening-Fuse-10427678,1 | 13831 | 0.046402 | 4 | 36 | 3 | 0 | 39 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 15266.0985
Lateral Hardening-Fuse-10429550,1 | 13835 | 0.20909 | 16 | 32 | 5 | 0 | 37 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 68790.9091
Lateral Hardening-Fuse-10457713,1 | 13229 | 0.054735 | 8 | 42 | 4 | 0 | 46 | 7 | Q2 - 2022 | Q1 - 2024 | Q4 - 2024 | 18007.7652
Lateral Hardening-Fuse-10475330,1 | 14117 | 0.15985 | 14 | 5 | 5 | 3 | 13 | 0 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 52590.1515
Lateral Hardening-Fuse-10477228,1 | 13326 | 0.18864 | 14 | 8 | 16 | 5 | 29 | 0 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 62061.3636
Lateral Hardening-Fuse-10535991,1 | 13115 | 0.25492 | 20 | 25 | 0 | 1 | 26 | 0 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 83870.0758
Lateral Hardening-Fuse-10545847,1 | 13910 | 0.084659 | 6 | 6 | 1 | 1 | 8 | 1 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 27852.8409
Lateral Hardening-Fuse-10565125,1 | 13291 | 0.16572 | 16 | 19 | 1 | 1 | 21 | 0 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 54521.7803
Lateral Hardening-Fuse-10565130,1 | 13291 | 0.21439 | 20 | 20 | 3 | 1 | 24 | 0 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 70535.6061
Lateral Hardening-Fuse-10565136,1 | 13291 | 0.13447 | 13 | 14 | 3 | 2 | 19 | 0 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 44240.5303
Lateral Hardening-Fuse-10565887,1 | 13290 | 0.34735 | 34 | 129 | 7 | 0 | 136 | 0 | Q1 - 2022 | Q1 - 2025 | Q4 - 2025 | 114277.6515
Lateral Hardening-Fuse-10565895,1 | 13290 | 0.071023 | 9 | 15 | 5 | 0 | 20 | 0 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 23366.4773
Lateral Hardening-Fuse-10572982,1 | 13371 | 0.17102 | 15 | 17 | 9 | 0 | 26 | 0 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 56266.4773
Lateral Hardening-Fuse-10589590,1 | 13756 | 0.1428 | 21 | 29 | 2 | 0 | 31 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 46982.197
Lateral Hardening-Fuse-10616460,1 | 13124 | 0.068182 | 8 | 11 | 1 | 0 | 12 | 0 | Q4 - 2022 | Q1 - 2024 | Q3 - 2024 | 22431.8182
Lateral Hardening-Fuse-10625698,1 | 13011 | 0.24848 | 21 | 28 | 2 | 0 | 30 | 0 | Q4 - 2022 | Q1 - 2024 | Q3 - 2024 | 81751.5152
Lateral Hardening-Fuse-10632726,1 | 13312 | 0.11951 | 17 | 7 | 7 | 3 | 17 | 0 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 39317.9924
Lateral Hardening-Fuse-10632727,1 | 13312 | 0.12367 | 12 | 24 | 14 | 0 | 38 | 0 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 40688.8258
Lateral Hardening-Fuse-10633695,1 | 13241 | 0.064394 | 4 | 8 | 3 | 0 | 11 | 0 | Q3 - 2022 | Q1 - 2025 | Q4 - 2025 | 21185.6061
Lateral Hardening-Fuse-10637218,1 | 13696 | 0.24261 | 26 | 25 | 7 | 0 | 32 | 0 | Q2 - 2022 | Q1 - 2025 | Q4 - 2025 | 79819.8864
Lateral Hardening-Fuse-10640103,1 | 13724 | 0.18409 | 16 | 2 | 4 | 3 | 9 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 60565.9091
Lateral Hardening-Fuse-10668889,1 | 13723 | 0.50625 | 20 | 29 | 4 | 0 | 33 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 166556.25
Lateral Hardening-Fuse-10671179,1 | 13724 | 0.030492 | 5 | 2 | 2 | 0 | 4 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 13160
Lateral Hardening-Fuse-10674224,1 | 13414 | 0.095076 | 9 | 7 | 0 | 1 | 8 | 0 | Q4 - 2022 | Q1 - 2024 | Q3 - 2024 | 31279.9242
Lateral Hardening-Fuse-10674240,1 | 13414 | 0.17121 | 14 | 21 | 3 | 1 | 25 | 6 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 56328.7879
Lateral Hardening-Fuse-10674784,1 | 13464 | 0.49337 | 33 | 55 | 3 | 0 | 58 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 162319.1288
Lateral Hardening-Fuse-10675160,1 | 13464 | 0.21023 | 10 | 21 | 7 | 0 | 28 | 2 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 69164.7727
Lateral Hardening-Fuse-10686006,1 | 13808 | 0.28788 | 19 | 2 | 0 | 3 | 5 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 94712.1212
Lateral Hardening-Fuse-10688316,1 | 13068 | 0.10246 | 10 | 9 | 7 | 0 | 16 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 33710.0379
Lateral Hardening-Fuse-10692795,1 | 13463 | 0.072727 | 6 | 12 | 2 | 0 | 14 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 23927.2727
Lateral Hardening-Fuse-10692803,1 | 13463 | 0.088636 | 7 | 13 | 2 | 0 | 15 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 29161.3636
Lateral Hardening-Fuse-10696420,1 | 13961 | 0.071591 | 9 | 18 | 2 | 0 | 20 | 0 | Q4 - 2022 | Q1 - 2024 | Q3 - 2024 | 23553.4091
Lateral Hardening-Fuse-10696464,1 | 13961 | 0.051136 | 4 | 2 | 2 | 0 | 4 | 0 | Q4 - 2022 | Q1 - 2024 | Q3 - 2024 | 16823.8636
Lateral Hardening-Fuse-10710623,1 | 14000 | 0.19451 | 14 | 5 | 4 | 0 | 9 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 63992.9924
Lateral Hardening-Fuse-10716303,1 | 13959 | 0.28542 | 17 | 14 | 2 | 0 | 16 | 0 | Q4 - 2022 | Q1 - 2024 | Q3 - 2024 | 93902.0833
Lateral Hardening-Fuse-10716315,1 | 13959 | 0.097159 | 9 | 17 | 4 | 0 | 21 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 31965.3409
Lateral Hardening-Fuse-10716318,1 | 13959 | 0.087121 | 7 | 1 | 1 | 0 | 2 | 0 | Q4 - 2022 | Q3 - 2023 | Q1 - 2024 | 28662.8788
Lateral Hardening-Fuse-10791877,1 | 13243 | 0.085038 | 6 | 43 | 0 | 1 | 44 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 27977.4621
Lateral Hardening-Fuse-10791889,1 | 13243 | 0.26117 | 18 | 48 | 5 | 0 | 53 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 85926.3258
Lateral Hardening-Fuse-10823013,1 | 13651 | 0.17348 | 12 | 39 | 3 | 2 | 44 | 5 | Q2 - 2022 | Q1 - 2025 | Q3 - 2025 | 57076.5152
Lateral Hardening-Fuse-10916743,1 | 13805 | 0.32689 | 16 | 5 | 2 | 1 | 8 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 107548.1061
Lateral Hardening-Fuse-10928275,1 | 13143 | 0.094318 | 10 | 17 | 12 | 0 | 29 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 31030.6818
Lateral Hardening-Fuse-10933157,1 | 13896 | 0.27557 | 16 | 9 | 12 | 0 | 21 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 90661.9318
Lateral Hardening-Fuse-60005954,1 | 13899 | 0.16761 | 13 | 5 | 2 | 1 | 8 | 0 | Q2 - 2022 | Q1 - 2025 | Q3 - 2025 | 55144.8864
Lateral Hardening-Fuse-60008652,1 | 13081 | 0.082576 | 9 | 26 | 5 | 0 | 31 | 0 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 27167.4242
Lateral Hardening-Fuse-60011392,1 | 13047 | 0.24432 | 25 | 37 | 1 | 1 | 39 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 80380.6818
Lateral Hardening-Fuse-60013778,1 | 13094 | 0.25455 | 27 | 84 | 7 | 1 | 92 | 2 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 83745.4545
Lateral Hardening-Fuse-60015117,1 | 13008 | 0.26951 | 18 | 28 | 2 | 2 | 32 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 88667.9924
Lateral Hardening-Fuse-60015427,1 | 13008 | 0.35568 | 19 | 6 | 1 | 2 | 9 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 117019.3182
Lateral Hardening-Fuse-60016282,1 | 13049 | 0.058712 | 5 | 31 | 0 | 1 | 32 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 19316.2879
Lateral Hardening-Fuse-60016353,1 | 13049 | 0.074621 | 9 | 9 | 1 | 1 | 11 | 4 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 24550.3788
Lateral Hardening-Fuse-60017429,2 | 13029 | 0.42519 | 40 | 4 | 21 | 15 | 40 | 7 | Q3 - 2022 | Q3 - 2022 | Q1 - 2023 | 139887.3105
Lateral Hardening-Fuse-60028650,1 | 13007 | 0.098864 | 10 | 15 | 5 | 1 | 21 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 32526.1364
Lateral Hardening-Fuse-60029011,1 | 13088 | 0.073485 | 9 | 6 | 11 | 1 | 18 | 0 | Q3 - 2022 | Q3 - 2022 | Q1 - 2023 | 24176.5152
Lateral Hardening-Fuse-60029776,1 | 13093 | 0.28617 | 29 | 61 | 2 | 1 | 64 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 94151.3258
Lateral Hardening-Fuse-60029925,3 | 13091 | 0.5678 | 53 | 101 | 12 | 0 | 113 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 186807.1969
Lateral Hardening-Fuse-60031511,1 | 13093 | 0.18068 | 16 | 28 | 0 | 1 | 29 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 59444.3182
Lateral Hardening-Fuse-60033370,1 | 13163 | 0.12803 | 12 | 17 | 12 | 3 | 32 | 0 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 42121.9697
Lateral Hardening-Fuse-60033388,1 | 13163 | 0.17955 | 18 | 19 | 17 | 1 | 37 | 10 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 59070.4545
Lateral Hardening-Fuse-60034479,1 | 13143 | 0.30189 | 32 | 48 | 1 | 0 | 49 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 99323.1061
Lateral Hardening-Fuse-60044927,1 | 13288 | 0.17008 | 22 | 15 | 9 | 6 | 30 | 1 | Q2 - 2022 | Q1 - 2025 | Q3 - 2025 | 55954.9242
Lateral Hardening-Fuse-60046437,1 | 13310 | 0.19072 | 19 | 46 | 9 | 3 | 58 | 0 | Q2 - 2022 | Q1 - 2025 | Q3 - 2025 | 62746.7803
Lateral Hardening-Fuse-60047463,1 | 13350 | 0.11288 | 10 | 64 | 6 | 0 | 70 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 37137.1212
Lateral Hardening-Fuse-60048514,1 | 13405 | 0.12992 | 6 | 2 | 2 | 2 | 6 | 6 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 42745.0758
Lateral Hardening-Fuse-60048809,1 | 13622 | 0.14659 | 6 | 3 | 3 | 0 | 6 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 48228.4091
Lateral Hardening-Fuse-60058546,1 | 13279 | 0.10871 | 10 | 15 | 9 | 1 | 25 | 0 | Q2 - 2022 | Q1 - 2025 | Q3 - 2025 | 35766.2879
Lateral Hardening-Fuse-60058616,1 | 13610 | 0.11534 | 14 | 17 | 3 | 1 | 21 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 37947.1591
Lateral Hardening-Fuse-60060554,1 | 13175 | 0.17822 | 16 | 14 | 6 | 0 | 20 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 58634.2803
Lateral Hardening-Fuse-60060564,1 | 13175 | 0.12955 | 13 | 20 | 5 | 0 | 25 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 42620.4545
Lateral Hardening-Fuse-60060568,1 | 13175 | 0.096023 | 13 | 16 | 6 | 0 | 22 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 31591.4773
Lateral Hardening-Fuse-60061785,1 | 13668 | 0.094886 | 5 | 288 | 17 | 2 | 307 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 31217.6136
Lateral Hardening-Fuse-60065898,1 | 14275 | 0.03447 | 9 | 2 | 2 | 0 | 4 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 13160
Lateral Hardening-Fuse-60073788,1 | 13082 | 0.24583 | 25 | 40 | 5 | 1 | 46 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 80879.1667
Lateral Hardening-Fuse-60073803,1 | 13082 | 0.16155 | 18 | 31 | 2 | 0 | 33 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 53150.947
Lateral Hardening-Fuse-60077860,1 | 13153 | 0.10625 | 10 | 13 | 0 | 3 | 16 | 0 | Q2 - 2022 | Q1 - 2025 | Q3 - 2025 | 34956.25
Lateral Hardening-Fuse-60087052,1 | 13359 | 0.059848 | 7 | 29 | 8 | 4 | 41 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 19690.1515
Lateral Hardening-Fuse-60088186,1 | 13139 | 0.21951 | 18 | 27 | 4 | 0 | 31 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 72217.9924
Lateral Hardening-Fuse-60088567,1 | 13510 | 0.29867 | 34 | 25 | 4 | 0 | 29 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 98263.8258
Lateral Hardening-Fuse-60124027,1 | 13218 | 0.63977 | 53 | 64 | 9 | 0 | 73 | 0 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 210485.2273
Lateral Hardening-Fuse-60181011,1 | 13388 | 0.11951 | 7 | 6 | 2 | 0 | 8 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 39317.9924
Lateral Hardening-Fuse-60190659,1 | 13308 | 0.21572 | 15 | 15 | 9 | 2 | 26 | 0 | Q2 - 2022 | Q1 - 2025 | Q3 - 2025 | 70971.7803
Lateral Hardening-Fuse-60200737,1 | 13961 | 0.078788 | 7 | 7 | 1 | 0 | 8 | 0 | Q4 - 2022 | Q3 - 2023 | Q1 - 2024 | 25921.2121
Lateral Hardening-Fuse-60241209,1 | 13137 | 0.09072 | 10 | 159 | 4 | 0 | 163 | 0 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 29846.7803
Lateral Hardening-Fuse-60289071,1 | 13045 | 0.098485 | 12 | 12 | 3 | 1 | 16 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 32401.5152
Lateral Hardening-Fuse-60302651,1 | 13091 | 0.15833 | 13 | 28 | 14 | 0 | 42 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 52091.6667
Lateral Hardening-Fuse-60305740,1 | 13865 | 0.13996 | 15 | 38 | 4 | 0 | 42 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 46047.5379
Lateral Hardening-Fuse-60337684,1 | 14001 | 0.055492 | 4 | 2 | 14 | 0 | 16 | 0 | Q4 - 2022 | Q2 - 2023 | Q4 - 2023 | 18257.0076
Lateral Hardening-Fuse-60350024,5 | 13097 | 1.3943 | 92 | 67 | 9 | 2 | 78 | 0 | Q2 - 2022 | Q1 - 2024 | Q4 - 2024 | 458730.6816
Lateral Hardening-Fuse-60365361,1 | 13962 | 0.064394 | 6 | 5 | 0 | 1 | 6 | 0 | Q3 - 2022 | Q1 - 2023 | Q3 - 2023 | 21185.6061
Lateral Hardening-Fuse-60422059,1 | 13723 | 0.31345 | 21 | 45 | 16 | 2 | 63 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 103124.053
Lateral Hardening-Fuse-60463714,1 | 13853 | 0.21269 | 16 | 3 | 8 | 7 | 18 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 69974.8106
Lateral Hardening-Fuse-60474882,1 | 13191 | 0.25587 | 32 | 11 | 29 | 9 | 49 | 6 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 84181.6288
Lateral Hardening-Fuse-60518342,1 | 13219 | 0.13201 | 10 | 5 | 8 | 4 | 17 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 43430.4924
Lateral Hardening-Fuse-60614298,1 | 13740 | 0.17008 | 17 | 20 | 13 | 0 | 33 | 0 | Q2 - 2022 | Q1 - 2023 | Q3 - 2024 | 55954.9242
Lateral Hardening-Fuse-90097474,7 | 13754 | 1.9714 | 170 | 200 | 18 | 2 | 220 | 0 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 648591.0981
Lateral Hardening-Fuse-90098676,4 | 13190 | 2.1623 | 170 | 445 | 19 | 0 | 464 | 9 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 711400.189
Lateral Hardening-Fuse-90152415,1 | 13208 | 0.083333 | 8 | 13 | 15 | 1 | 29 | 0 | Q2 - 2022 | Q1 - 2023 | Q3 - 2023 | 27416.6667
Lateral Hardening-Fuse-90157556,1 | 13067 | 0.19261 | 18 | 12 | 6 | 0 | 18 | 5 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 63369.8864
Lateral Hardening-Fuse-90165527,1 | 13431 | 0.1947 | 12 | 4 | 2 | 1 | 7 | 0 | Q3 - 2022 | Q1 - 2023 | Q3 - 2023 | 64055.303
Lateral Hardening-Fuse-90179103,1 | 13630 | 0.23807 | 17 | 19 | 17 | 0 | 36 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 78324.4318
Lateral Hardening-Fuse-90211134,1 | 13162 | 0.082955 | 10 | 23 | 2 | 0 | 25 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 27292.0455
Lateral Hardening-Fuse-90267141,1 | 13738 | 0.02803 | 8 | 305 | 5 | 5 | 315 | 1 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 13160
Lateral Hardening-Fuse-90297635,1 | 13007 | 0.12879 | 12 | 11 | 0 | 1 | 12 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 42371.2121
Lateral Hardening-Fuse-90377733,1 | 13389 | 0.11496 | 9 | 3 | 0 | 1 | 4 | 3 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 37822.5379
Lateral Hardening-Fuse-90393849,1 | 13147 | 0.07822 | 5 | 21 | 4 | 0 | 25 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 25734.2803
Lateral Hardening-Fuse-90398961,1 | 13795 | 0.070265 | 7 | 20 | 2 | 1 | 23 | 0 | Q2 - 2022 | Q1 - 2025 | Q3 - 2025 | 23117.2348
Lateral Hardening-Fuse-90399851,6 | 13419 | 0.76402 | 64 | 111 | 2 | 3 | 116 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 251360.9847
Lateral Hardening-Fuse-90416605,1 | 13081 | 0.089773 | 10 | 222 | 2 | 1 | 225 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 29535.2273
Lateral Hardening-Fuse-90441325,1 | 13612 | 0.072727 | 8 | 7 | 6 | 1 | 14 | 6 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 23927.2727
Lateral Hardening-Fuse-90482454,4 | 13206 | 0.6786 | 58 | 73 | 18 | 0 | 91 | 0 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 223258.9014
Lateral Hardening-Fuse-90487798,1 | 13740 | 0.12197 | 6 | 9 | 6 | 0 | 15 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 40128.0303
Lateral Hardening-Fuse-90522517,5 | 13359 | 1.2025 | 115 | 125 | 2 | 1 | 128 | 1 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 395610.0377
Lateral Hardening-Fuse-90526768,1 | 13199 | 0.18485 | 15 | 20 | 3 | 0 | 23 | 0 | Q3 - 2022 | Q1 - 2024 | Q3 - 2024 | 60815.1515
Lateral Hardening-Fuse-90630567,1 | 13754 | 0.13144 | 14 | 13 | 2 | 1 | 16 | 5 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 43243.5606
Lateral Hardening-Fuse-90668793,1 | 14042 | 0.18674 | 12 | 55 | 1 | 2 | 58 | 1 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 61438.2576
Lateral Hardening-Fuse-90704066,4 | 13370 | 0.78201 | 65 | 16 | 20 | 9 | 45 | 1 | Q1 - 2022 | Q4 - 2024 | Q2 - 2025 | 257280.4923
Lateral Hardening-Fuse-90748138,1 | 13103 | 0.083712 | 8 | 9 | 5 | 0 | 14 | 0 | Q3 - 2022 | Q2 - 2022 | Q4 - 2022 | 27541.2879
Lateral Hardening-Fuse-90823812,1 | 13329 | 0.049811 | 4 | 7 | 0 | 1 | 8 | 0 | Q3 - 2022 | Q2 - 2022 | Q4 - 2022 | 16387.6894
Lateral Hardening-Fuse-90830976,1 | 13328 | 0.081818 | 8 | 3 | 1 | 2 | 6 | 0 | Q3 - 2022 | Q2 - 2022 | Q4 - 2022 | 26918.1818
Lateral Hardening-Fuse-90847913,1 | 13754 | 0.24602 | 25 | 55 | 5 | 1 | 61 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 80941.4773
Lateral Hardening-Fuse-90848130,1 | 13656 | 0.16723 | 11 | 9 | 0 | 1 | 10 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 55020.2652
Lateral Hardening-Fuse-90852788,1 | 13148 | 0.34527 | 23 | 10 | 3 | 1 | 14 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 113592.2348
Lateral Hardening-Fuse-91016874,2 | 13046 | 0.37519 | 34 | 52 | 4 | 3 | 59 | 7 | Q3 - 2022 | Q3 - 2022 | Q1 - 2023 | 123437.3105
Lateral Hardening-Fuse-91060899,1 | 13533 | 0.22746 | 21 | 142 | 3 | 1 | 146 | 1 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 74835.0379
Lateral Hardening-Fuse-91066431,1 | 13163 | 0.22614 | 15 | 18 | 3 | 3 | 24 | 0 | Q3 - 2022 | Q3 - 2022 | Q1 - 2023 | 74398.8636
Lateral Hardening-Fuse-91076397,1 | 13048 | 0.056439 | 7 | 3 | 0 | 3 | 6 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 18568.5606
Lateral Hardening-Fuse-91096289,1 | 13787 | 0.091288 | 6 | 3 | 1 | 0 | 4 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 30033.7121
Lateral Hardening-Fuse-91147533,3 | 13097 | 0.67197 | 41 | 39 | 5 | 1 | 45 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 221078.0302
Lateral Hardening-Fuse-91151734,1 | 13364 | 0.092992 | 9 | 52 | 0 | 1 | 53 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 30594.5076
Lateral Hardening-Fuse-91154995,2 | 13048 | 0.53049 | 50 | 74 | 3 | 2 | 79 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 174532.0075
Lateral Hardening-Fuse-91161524,1 | 13146 | 0.23845 | 15 | 16 | 1 | 1 | 18 | 6 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 78449.053
Lateral Hardening-Fuse-91177941,3 | 13638 | 0.86534 | 82 | 79 | 12 | 1 | 92 | 1 | Q2 - 2022 | Q1 - 2024 | Q3 - 2024 | 284697.1589
Lateral Hardening-Fuse-91232937,1 | 13103 | 0.48939 | 47 | 117 | 7 | 0 | 124 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 161010.6061
Lateral Hardening-Fuse-91234338,1 | 13124 | 0.4589 | 33 | 56 | 3 | 0 | 59 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 150978.5985
Lateral Hardening-Fuse-91334566,1 | 13464 | 0.38182 | 27 | 60 | 1 | 1 | 62 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 125618.1818
Lateral Hardening-Fuse-91337725,1 | 13464 | 0.20246 | 13 | 11 | 2 | 2 | 15 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 66610.0379
Lateral Hardening-Fuse-91354294,1 | 13065 | 0.16307 | 18 | 136 | 10 | 1 | 147 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 53649.4318
Lateral Hardening-Fuse-91382618,1 | 13462 | 0.31932 | 27 | 51 | 3 | 4 | 58 | 3 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 105055.6818
Lateral Hardening-Fuse-91404359,1 | 13805 | 0.56023 | 28 | 35 | 9 | 0 | 44 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 184314.7727
Lateral Hardening-Fuse-91418404,1 | 13621 | 0.15777 | 11 | 10 | 2 | 0 | 12 | 0 | Q3 - 2022 | Q4 - 2023 | Q2 - 2024 | 51904.7348
Lateral Hardening-Fuse-91421327,1 | 13124 | 0.10057 | 14 | 1 | 4 | 4 | 9 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 33086.9318
Lateral Hardening-Fuse-91532289,1 | 13832 | 0.10227 | 11 | 12 | 22 | 1 | 35 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 33647.7273
Lateral Hardening-Fuse-91532301,1 | 13832 | 0.087121 | 7 | 10 | 7 | 0 | 17 | 0 | Q3 - 2022 | Q2 - 2022 | Q1 - 2023 | 28662.8788
Lateral Hardening-Fuse-91550764,1 | 13592 | 0.061553 | 4 | 16 | 3 | 1 | 20 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 20250.947
Lateral Hardening-Fuse-91565159,4 | 13044 | 0.51345 | 55 | 14 | 1 | 1 | 16 | 0 | Q2 - 2022 | Q2 - 2023 | Q4 - 2023 | 168924.0529
Lateral Hardening-Fuse-91623641,1 | 13141 | 0.15038 | 19 | 39 | 3 | 1 | 43 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 49474.6212
Lateral Hardening-Fuse-91643964,1 | 13106 | 0.13144 | 12 | 123 | 9 | 0 | 132 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 43243.5606
Lateral Hardening-Fuse-91702481,1 | 14012 | 0.077273 | 8 | 1 | 0 | 1 | 2 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 25422.7273
Lateral Hardening-Fuse-91774500,1 | 13631 | 0.28409 | 21 | 56 | 17 | 0 | 73 | 16 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 93465.9091
Lateral Hardening-Fuse-91782844,1 | 13434 | 0.15379 | 13 | 7 | 0 | 2 | 9 | 0 | Q2 - 2022 | Q4 - 2024 | Q2 - 2025 | 50596.2121
Lateral Hardening-Fuse-91868130,1 | 13201 | 0.11098 | 11 | 123 | 3 | 1 | 127 | 0 | Q3 - 2022 | Q4 - 2023 | Q2 - 2024 | 36514.0152
Lateral Hardening-Fuse-91910924,1 | 13165 | 0.23409 | 20 | 53 | 5 | 5 | 63 | 3 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 77015.9091
Lateral Hardening-Fuse-92005809,1 | 13219 | 0.23939 | 24 | 42 | 11 | 1 | 54 | 0 | Q2 - 2022 | Q4 - 2023 | Q2 - 2024 | 78760.6061
Lateral Hardening-Fuse-92027991,1 | 13420 | 0.23731 | 18 | 24 | 7 | 0 | 31 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 78075.1894
Lateral Hardening-Fuse-92035203,1 | 13417 | 0.079924 | 9 | 30 | 4 | 0 | 34 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 26295.0758
Lateral Hardening-Fuse-92079502,1 | 13638 | 0.12955 | 15 | 41 | 12 | 2 | 55 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 42620.4545
Lateral Hardening-Fuse-92097014,1 | 13217 | 0.19053 | 11 | 16 | 1 | 1 | 18 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 62684.4697
Lateral Hardening-Fuse-92132257,1 | 13016 | 0.12102 | 13 | 57 | 4 | 0 | 61 | 0 | Q3 - 2022 | Q4 - 2023 | Q2 - 2024 | 39816.4773
Lateral Hardening-Fuse-92197131,1 | 13330 | 0.18655 | 13 | 73 | 2 | 1 | 76 | 1 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 61375.947
Lateral Hardening-Fuse-92238609,1 | 13065 | 0.13617 | 13 | 25 | 2 | 0 | 27 | 0 | Q3 - 2022 | Q4 - 2023 | Q2 - 2024 | 44801.3258
Lateral Hardening-Fuse-92257437,1 | 13227 | 0.14773 | 19 | 12 | 9 | 0 | 21 | 0 | Q2 - 2022 | Q4 - 2023 | Q2 - 2024 | 48602.2727
Lateral Hardening-Fuse-92320131,1 | 13656 | 0.24205 | 16 | 8 | 3 | 2 | 13 | 3 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 79632.9545
Lateral Hardening-Fuse-92354169,1 | 13787 | 0.13807 | 6 | 2 | 2 | 4 | 8 | 5 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 45424.4318
Lateral Hardening-Fuse-92398222,1 | 13167 | 0.11799 | 15 | 11 | 0 | 2 | 13 | 0 | Q3 - 2022 | Q4 - 2023 | Q2 - 2025 | 38819.5076
Lateral Hardening-Fuse-92408051,1 | 13140 | 0.088636 | 10 | 40 | 7 | 1 | 48 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 29161.3636
Lateral Hardening-Fuse-92418323,1 | 13696 | 0.059848 | 8 | 111 | 3 | 0 | 114 | 0 | Q2 - 2022 | Q4 - 2024 | Q2 - 2025 | 19690.1515
Lateral Hardening-Fuse-92448697,1 | 13510 | 0.040341 | 5 | 5 | 2 | 2 | 9 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 13272.1591
Lateral Hardening-Fuse-92486363,1 | 13312 | 0.22292 | 17 | 16 | 3 | 1 | 20 | 0 | Q2 - 2022 | Q4 - 2023 | Q2 - 2024 | 73339.5833
Lateral Hardening-Fuse-92497118,1 | 13146 | 0.22746 | 8 | 4 | 2 | 0 | 6 | 0 | Q4 - 2022 | Q3 - 2023 | Q1 - 2024 | 74835.0379
Lateral Hardening-Fuse-92527630,1 | 13219 | 0.1089 | 8 | 17 | 1 | 1 | 19 | 1 | Q3 - 2022 | Q4 - 2023 | Q2 - 2024 | 35828.5985
Lateral Hardening-Fuse-92527637,1 | 13219 | 0.21364 | 24 | 38 | 2 | 1 | 41 | 0 | Q3 - 2022 | Q4 - 2023 | Q2 - 2024 | 70286.3636
Lateral Hardening-Fuse-92529635,1 | 13210 | 0.10852 | 12 | 13 | 3 | 0 | 16 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 35703.9773
Lateral Hardening-Fuse-92529638,1 | 13210 | 0.087121 | 10 | 21 | 1 | 1 | 23 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 28662.8788
Lateral Hardening-Fuse-92537158,1 | 13150 | 0.071591 | 7 | 10 | 0 | 2 | 12 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 23553.4091
Lateral Hardening-Fuse-92543665,1 | 13004 | 0.28049 | 23 | 70 | 5 | 0 | 75 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 92282.0076
Lateral Hardening-Fuse-92570284,1 | 13020 | 0.068182 | 3 | 9 | 1 | 4 | 14 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 22431.8182
Lateral Hardening-Fuse-92597622,1 | 13390 | 0.18958 | 12 | 42 | 6 | 0 | 48 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 62372.9167
Lateral Hardening-Fuse-92599120,1 | 13390 | 0.61686 | 37 | 45 | 5 | 0 | 50 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 202945.6439
Lateral Hardening-Fuse-92602262,1 | 13010 | 0.094508 | 6 | 15 | 2 | 0 | 17 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 31092.9924
Lateral Hardening-Fuse-92603717,1 | 13390 | 0.24886 | 15 | 32 | 4 | 0 | 36 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 81876.1364
Lateral Hardening-Fuse-92605327,1 | 13390 | 0.20511 | 16 | 65 | 15 | 0 | 80 | 21 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 67482.3864
Lateral Hardening-Fuse-92605381,1 | 13390 | 0.34583 | 33 | 130 | 4 | 0 | 134 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 113779.1667
Lateral Hardening-Fuse-92609981,1 | 13390 | 0.17083 | 13 | 31 | 3 | 0 | 34 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 56204.1667
Lateral Hardening-Fuse-92610250,1 | 13390 | 0.92689 | 46 | 48 | 11 | 0 | 59 | 5 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 304948.1061
Lateral Hardening-Fuse-92612860,1 | 13390 | 0.44924 | 27 | 17 | 3 | 0 | 20 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 147800.7576
Lateral Hardening-Fuse-92620889,1 | 13390 | 0.24129 | 15 | 66 | 3 | 0 | 69 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 79383.7121
Lateral Hardening-Fuse-92622569,1 | 13390 | 0.61155 | 30 | 86 | 11 | 4 | 101 | 5 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 201200.947
Lateral Hardening-Fuse-92655421,1 | 13198 | 0.075189 | 6 | 8 | 2 | 0 | 10 | 0 | Q3 - 2022 | Q4 - 2023 | Q2 - 2024 | 24737.3106
Lateral Hardening-Fuse-92678765,1 | 13805 | 0.19432 | 12 | 3 | 3 | 0 | 6 | 0 | Q3 - 2022 | Q2 - 2022 | Q4 - 2022 | 63930.6818
Lateral Hardening-Fuse-92701725,1 | 13299 | 0.1839 | 13 | 123 | 28 | 2 | 153 | 2 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 60503.5985
Lateral Hardening-Fuse-92773510,1 | 13373 | 0.3197 | 27 | 13 | 13 | 0 | 26 | 0 | Q1 - 2022 | Q3 - 2024 | Q1 - 2025 | 105180.303
Lateral Hardening-Fuse-92814355,1 | 13344 | 0.047727 | 7 | 37 | 5 | 2 | 44 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 15702.2727
Lateral Hardening-Fuse-92835651,4 | 13329 | 0.8267 | 55 | 89 | 21 | 1 | 111 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 271985.7953
Lateral Hardening-Fuse-92856634,1 | 13224 | 0.25227 | 23 | 16 | 17 | 1 | 34 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 82997.7273
Lateral Hardening-Fuse-92859507,1 | 13460 | 0.096402 | 7 | 25 | 0 | 1 | 26 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 31716.0985
Lateral Hardening-Fuse-92867406,1 | 13010 | 0.068939 | 8 | 2 | 4 | 1 | 7 | 0 | Q3 - 2022 | Q1 - 2024 | Q4 - 2024 | 22681.0606
Lateral Hardening-Fuse-92874488,1 | 13112 | 0.13447 | 14 | 38 | 1 | 1 | 40 | 1 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 44240.5303
Lateral Hardening-Fuse-92890357,1 | 13112 | 0.1767 | 13 | 49 | 6 | 1 | 56 | 0 | Q2 - 2022 | Q3 - 2023 | Q2 - 2024 | 58135.7955
Lateral Hardening-Fuse-92897362,1 | 13147 | 0.1892 | 12 | 26 | 3 | 0 | 29 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 62248.2955
Lateral Hardening-Fuse-92901825,1 | 13147 | 0.46212 | 20 | 123 | 2 | 1 | 126 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 152037.8788
Lateral Hardening-Fuse-92905104,1 | 13826 | 0.19735 | 10 | 183 | 7 | 2 | 192 | 39 | Q1 - 2022 | Q3 - 2023 | Q1 - 2024 | 64927.6515
Lateral Hardening-Fuse-92907479,1 | 13060 | 0.057197 | 9 | 267 | 24 | 2 | 293 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 18817.803
Lateral Hardening-Fuse-92922162,1 | 13224 | 0.10852 | 13 | 16 | 2 | 1 | 19 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 35703.9773
Lateral Hardening-Fuse-92937437,1 | 13241 | 0.22216 | 17 | 22 | 9 | 0 | 31 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 73090.3409
Lateral Hardening-Fuse-93033231,1 | 13838 | 0.19981 | 13 | 61 | 13 | 4 | 78 | 27 | Q1 - 2022 | Q3 - 2023 | Q1 - 2024 | 65737.6894
Lateral Hardening-Fuse-93082436,1 | 13612 | 0.07197 | 7 | 8 | 5 | 0 | 13 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 23678.0303
Lateral Hardening-Fuse-93090160,1 | 13039 | 0.21042 | 10 | 15 | 7 | 0 | 22 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 69227.0833
Lateral Hardening-Fuse-93113905,1 | 13034 | 0.035985 | 4 | 8 | 1 | 1 | 10 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 13160
Lateral Hardening-Fuse-93118733,1 | 13324 | 0.11307 | 11 | 6 | 4 | 1 | 11 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 37199.4318
Lateral Hardening-Fuse-93172625,1 | 13213 | 0.13466 | 12 | 21 | 3 | 0 | 24 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 44302.8409
Lateral Hardening-Fuse-93218070,1 | 13656 | 0.10701 | 6 | 2 | 1 | 0 | 3 | 0 | Q4 - 2022 | Q2 - 2023 | Q4 - 2023 | 35205.4924
Lateral Hardening-Fuse-93233174,1 | 13696 | 0.1392 | 17 | 46 | 5 | 0 | 51 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 45798.2955
Lateral Hardening-Fuse-93235148,1 | 13696 | 0.098674 | 9 | 28 | 12 | 2 | 42 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 32463.8258
Lateral Hardening-Fuse-93247243,1 | 13175 | 0.17689 | 18 | 33 | 4 | 0 | 37 | 0 | Q3 - 2022 | Q2 - 2022 | Q4 - 2022 | 58198.1061
Lateral Hardening-Fuse-93249426,1 | 13175 | 0.1536 | 14 | 10 | 1 | 2 | 13 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 50533.9015
Lateral Hardening-Fuse-93263741,1 | 13042 | 0.12405 | 12 | 18 | 0 | 2 | 20 | 0 | Q3 - 2022 | Q3 - 2023 | Q1 - 2024 | 40813.447
Lateral Hardening-Fuse-93263753,1 | 13042 | 0.24924 | 21 | 27 | 2 | 1 | 30 | 0 | Q1 - 2022 | Q3 - 2023 | Q1 - 2024 | 82000.7576
Lateral Hardening-Fuse-93264130,1 | 13042 | 0.21705 | 22 | 23 | 6 | 2 | 31 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 71407.9545
Lateral Hardening-Fuse-93266650,1 | 13042 | 0.33996 | 32 | 55 | 0 | 1 | 56 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 111847.5379
Lateral Hardening-Fuse-93267158,1 | 13042 | 0.18068 | 18 | 37 | 3 | 1 | 41 | 0 | Q1 - 2022 | Q2 - 2023 | Q4 - 2023 | 59444.3182
Lateral Hardening-Fuse-93276507,1 | 13213 | 0.13598 | 8 | 6 | 2 | 1 | 9 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 44739.0152
Lateral Hardening-Fuse-93283244,2 | 13351 | 0.64375 | 49 | 73 | 9 | 1 | 83 | 0 | Q2 - 2022 | Q3 - 2023 | Q1 - 2024 | 211793.7499
Lateral Hardening-Fuse-93283740,1 | 13351 | 0.056818 | 8 | 110 | 8 | 2 | 120 | 0 | Q1 - 2022 | Q1 - 2023 | Q3 - 2023 | 18693.1818
Lateral Hardening-Fuse-93292955,1 | 14356 | 0.11686 | 10 | 184 | 10 | 2 | 196 | 0 | Q2 - 2022 | Q3 - 2024 | Q1 - 2025 | 38445.6439
Lateral Hardening-Fuse-93294943,1 | 13808 | 0.13523 | 9 | 5 | 0 | 1 | 6 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 44489.7727
Lateral Hardening-Fuse-93324791,1 | 13723 | 0.13902 | 6 | 9 | 2 | 0 | 11 | 0 | Q3 - 2022 | Q2 - 2023 | Q4 - 2023 | 45735.9848
Lateral Hardening-Fuse-93355196,1 | 13303 | 0.066856 | 6 | 10 | 2 | 2 | 14 | 0 | Q2 - 2022 | Q2 - 2024 | Q4 - 2024 | 21995.6439
Lateral Hardening-Fuse-93432382,1 | 13532 | 0.28902 | 22 | 36 | 0 | 1 | 37 | 0 | Q3 - 2022 | Q3 - 2024 | Q1 - 2025 | 95085.9848

## DPL-12 Trans Asset Appendix
Tampa Electric's Transmission Asset Upgrades - Year 2022 Details
Project ID | Circuit No. | Pole Count | Project Start Month | Construction |  | Project Cost in 2020
|  |  |  | Start Month | End Month
Transmission Upgrades-138/230 kV-230006 | 230006 | 101 | 2022-09-21 | 2022-11-21 | 2022-04-22 | 1500000
Transmission Upgrades-138/230 kV-230402 | 230402 | 14 | 2022-03-22 | 2022-08-22 | 2022-12-22 | 300100
Transmission Upgrades-69 kV-66048 | 66048 | 5 | 2022-12-20 | 2022-04-21 | 2022-04-22 | 50000
Transmission Upgrades-138/230 kV-230606 | 230606 | 28 | 2022-07-21 | 2022-10-21 | 2022-03-22 | 210000
Transmission Upgrades-138/230 kV-230012 | 230012 | 16 | 2022-07-21 | 2022-10-21 | 2022-03-22 | 50000
Transmission Upgrades-138/230 kV-230020 | 230020 | 61 | 2022-08-22 | 2022-01-23 | 2022-06-23 | 41939.2
Transmission Upgrades-69 kV-66022 | 66022 | 50 | 2022-12-20 | 2022-08-21 | 2022-08-22 | 672980
Transmission Upgrades-69 kV-66001 | 66001 | 70 | 2022-03-21 | 2022-10-21 | 2022-06-22 | 1877473
Transmission Upgrades-69 kV-66016 | 66016 | 40 | 2022-11-20 | 2022-06-21 | 2022-06-22 | 400000
Transmission Upgrades-69 kV-66032 | 66032 | 40 | 2022-02-22 | 2022-01-23 | 2022-08-23 | 40576
Transmission Upgrades-69 kV-66020 | 66020 | 10 | 2022-07-21 | 2022-03-22 | 2022-08-22 | 305900.245
Transmission Upgrades-69 kV-66035 | 66035 | 65 | 2022-08-22 | 2022-01-23 | 2022-08-23 | 35028.5
Transmission Upgrades-138/230 kV-230602 | 230602 | 112 | 2022-05-21 | 2022-08-21 | 2022-03-22 | 50000
Transmission Upgrades-69 kV-66008 | 66008 | 9 | 2022-10-21 | 2022-07-21 | 2022-12-21 | 281970
Transmission Upgrades-69 kV-66030 | 66030 | 50 | 2022-07-21 | 2022-04-22 | 2022-09-22 | 1498910
Transmission Upgrades-69 kV-66045 | 66045 | 52 | 2022-09-21 | 2022-05-22 | 2022-12-22 | 1708376
Transmission Upgrades-138/230 kV-230033 | 230033 | 14 | 2022-06-21 | 2022-03-22 | 2022-06-22 | 294699.519
Transmission Upgrades-69 kV-66025 | 66025 | 105 | 2022-03-21 | 2022-08-21 | 2022-08-22 | 2324840
Transmission Upgrades-138/230 kV-230623 | 230623 | 65 | 2022-10-22 | 2022-01-23 | 2022-07-23 | 44720
Transmission Upgrades-69 kV-66021 | 66021 | 45 | 2022-02-22 | 2022-06-22 | 2022-03-23 | 45648
Transmission Upgrades-69 kV-66017 | 66017 | 97 | 2022-02-22 | 2022-07-22 | 2022-06-23 | 234972.43
Transmission Upgrades-138/230 kV-230609 | 230609 | 5 | 2022-12-21 | 2022-12-21 | 2022-03-22 | 105250.025
Transmission Upgrades-69 kV-66033 | 66033 | 26 | 2022-11-20 | 2022-11-21 | 2022-05-22 | 50000
Transmission Upgrades-69 kV-66036 | 66036 | 31 | 2022-11-20 | 2022-06-21 | 2022-05-22 | 300000
Transmission Upgrades-69 kV-66027 | 66027 | 17 | 2022-07-21 | 2022-02-22 | 2022-06-22 | 550620
Transmission Upgrades-69 kV-66060 | 66060 | 6 | 2022-11-20 | 2022-07-21 | 2022-04-22 | 10000
Transmission Upgrades-138/230 kV-230604 | 230604 | 36 | 2022-10-22 | 2022-02-23 | 2022-07-23 | 24768
Transmission Upgrades-69 kV-66407 | 66407 | 29 | 2022-12-20 | 2022-05-21 | 2022-05-22 | 10000
Transmission Upgrades-138/230 kV-230013 | 230013 | 20 | 2022-07-21 | 2022-03-22 | 2022-06-22 | 421000
Transmission Upgrades-69 kV-66427 | 66427 | 7 | 2022-11-20 | 2022-06-21 | 2022-06-22 | 10000
Transmission Upgrades-69 kV-66026 | 66026 | 83 | 2022-10-21 | 2022-04-22 | 2022-10-22 | 2582952
Transmission Upgrades-69 kV-66098 | 66098 | 22 | 2022-09-22 | 2022-01-23 | 2022-06-23 | 22210.24
Transmission Upgrades-69 kV-66011 | 66011 | 24 | 2022-09-21 | 2022-05-22 | 2022-12-22 | 22316.8
Transmission Upgrades-69 kV-66028 | 66028 | 49 | 2022-09-22 | 2022-01-23 | 2022-06-23 | 49243.84
Transmission Upgrades-69 kV-66047 | 66047 | 1 | 2022-02-21 | 2022-04-22 | 2022-06-22 | 1014.4
Transmission Upgrades-69 kV-66415 | 66415 | 10 | 2022-12-20 | 2022-03-22 | 2022-08-22 | 317000
Transmission Upgrades-69 kV-66436 | 66436 | 36 | 2022-08-22 | 2022-02-23 | 2022-08-23 | 34489.6
The North American Electric Reliability Corporation ("NERC") defines the transmission system as lines operated at relatively high voltages varying from 69kV up to 765kV and capable of delivery large quantities of electricity. Tampa Electric's transmission system is made up of 69kV, 138kV and 230kV voltages and is designed to transmit power to the end-user 13.2kV distribution substations. As such, Tampa Electric does not attribute customer counts directly to individual transmission lines. It should be noted, that without Tampa Electric's transmission network in place, power could not be delivered to the distribution network which would result in automatic load loss.

## DPL-13 Dist OFH Appendix
Tampa Electric's Distribution Overhead Feeder Hardening - Year 2022 Details
Project ID | Circuit No. | Specific Project Detail | Customers |  |  |  | Priority Customers | Project Start Month | Construction |  | Project Cost in 2022
|  |  | Residential | Small C&I | Large C&I | Total |  |  | Start Month | End Month
SPP FH - 13008 | 13008 | (2) new reclosers, (18) fuses, (3) trip savers, and upgrade (62) feeder poles | 249 | 159 | 25 | 433 | 0 | 2022-07-15 | 2023-01-15 | 2023-06-15 | 50000
SPP FH - 13028 | 13028 | (6) new reclosers, (43) fuses, (27) trip savers, and upgrade (52) feeder poles | 3595 | 242 | 24 | 3861 | 35 | 2022-08-15 | 2023-01-15 | 2023-06-15 | 50000
SPP FH - 13039 | 13039 | (2) new reclosers, (18) fuses, (3) trip savers, and upgrade (62) feeder poles | 299 | 178 | 24 | 501 | 29 | 2022-09-15 | 2023-01-15 | 2023-08-15 | 50000
SPP FH - 13040 | 13040 | (17) new reclosers, (74) fuses, (16) trip savers, and upgrade (148) feeder poles | 992 | 112 | 51 | 1155 | 18 | 2022-10-15 | 2023-01-15 | 2023-10-15 | 50000
SPP FH - 13048 | 13048 | (6) new reclosers, (43) fuses, (27) trip savers, and upgrade (52) feeder poles | 2720 | 324 | 81 | 3125 | 84 | 2022-06-08 | 2022-08-22 | 2022-10-15 | 2077656.91
SPP FH - 13077 | 13077 | (2) new reclosers, (18) fuses, (3) trip savers, and upgrade (62) feeder poles | 105 | 332 | 48 | 485 | 15 | 2022-09-15 | 2023-01-15 | 2023-09-15 | 50000
SPP FH - 13094 | 13094 | (7) new reclosers, (50) fuses, (28) trip savers, and upgrade (100) feeder poles | 1191 | 375 | 83 | 1649 | 15 | This one we had to put it on hold due to multiple of conflicts |  |  | 5554203.195
SPP FH - 13118 | 13118 | (17) new reclosers, (74) fuses, (16) trip savers, and upgrade (148) feeder poles | 1696 | 199 | 23 | 1918 | 3 | 2021-11-16 | 2022-03-01 | 2022-08-15 | 3377800
SPP FH - 13148 | 13148 | (17) new reclosers, (74) fuses, (16) trip savers, and upgrade (148) feeder poles | 1393 | 91 | 16 | 1500 | 13 | 2022-01-24 | 2022-03-01 | 2022-08-15 | 1219092.66
SPP FH - 13187 | 13187 | (9) new reclosers, (37) fuses, (21) trip savers, and upgrade (77) feeder poles | 1560 | 191 | 30 | 1781 | 30 | 2022-11-15 | 2023-01-15 | 2023-11-15 | 50000
SPP FH - 13227 | 13227 | (9) new reclosers, (37) fuses, (21) trip savers, and upgrade (77) feeder poles | 1447 | 159 | 19 | 1625 | 46 | 2020-11-09 | 2021-01-01 | 2022-02-04 | 50000
SPP FH - 13230 | 13230 | (2) new reclosers, (54) fuses, (42) trip savers, and upgrade (107) feeder poles | 572 | 411 | 22 | 1005 | 46 | 2022-11-15 | 2023-01-15 | 2023-11-15 | 50000
SPP FH - 13292 | 13292 | (2) new reclosers, (18) fuses, (3) trip savers, and upgrade (62) feeder poles | 730 | 33 | 8 | 771 | 14 | 2022-08-15 | 2023-01-15 | 2023-03-15 | 50000
SPP FH - 13296 | 13296 | (10) new reclosers, (35) fuses, (12) trip savers, and upgrade (70) feeder poles | 1430 | 120 | 14 | 1564 | 4 | 2022-02-10 | 2022-03-21 | 2022-09-15 | 4494493.645
SPP FH - 13299 | 13299 | (2) new reclosers, (18) fuses, (3) trip savers, and upgrade (62) feeder poles | 729 | 55 | 18 | 802 | 2 | 2022-12-15 | 2023-01-15 | 2023-11-15 | 50000
SPP FH - 13308 | 13308 | (3) new reclosers, (45) fuses, (27) trip savers, and upgrade (52) feeder poles | 1220 | 260 | 36 | 1516 | 26 | 2020-06-29 | 2020-08-01 | 2022-03-21 | 50000
SPP FH - 13312 | 13312 | (1) new reclosers, (3) fuses, (9) trip savers, and upgrade (96) feeder poles | 986 | 351 | 97 | 1434 | 4 | 2022-04-11 | 2022-06-06 | 2022-11-15 | 312010.92
SPP FH - 13313 | 13313 | (2) new reclosers, (18) fuses, (3) trip savers, and upgrade (62) feeder poles | 196 | 459 | 74 | 729 | 25 | 2021-04-12 | 2021-10-01 | 2022-05-15 | 73036
SPP FH - 13314 | 13314 | (2) new reclosers, (97) fuses, (13) trip savers, and upgrade (61) feeder poles | 683 | 240 | 85 | 1008 | 4 | 2021-04-07 | 2021-10-01 | 2022-05-15 | 29668
SPP FH - 13346 | 13346 | (2) new reclosers, (74) fuses, (51) trip savers, and upgrade (148) feeder poles | 1404 | 238 | 94 | 1736 | 12 | 2022-02-24 | 2022-04-30 | 2022-10-15 | 80785.575
SPP FH - 13433 | 13433 | (2) new reclosers, (111) fuses, (42) trip savers, and upgrade (101) feeder poles | 339 | 318 | 69 | 726 | 61 | 2021-04-22 | 2021-10-01 | 2022-04-15 | 688400
SPP FH - 13651 | 13651 | (2) new reclosers, (70) fuses, (35) trip savers, and upgrade (139) feeder poles | 2453 | 63 | 10 | 2526 | 50 | 2022-03-21 | 2022-05-21 | 2022-11-15 | 50386.215
SPP FH - 13687 | 13687 | (2) new reclosers, (70) fuses, (35) trip savers, and upgrade (139) feeder poles | 2054 | 70 | 2 | 2126 | 17 | 2022-10-15 | 2023-01-15 | 2023-09-15 | 50000
SPP FH - 13770 | 13770 | (9) new reclosers, (52) fuses, (3) trip savers, and upgrade (103) feeder poles | 1769 | 57 | 5 | 1831 | 3 | 2022-01-24 | 2022-03-15 | 2022-11-15 | 5898016.9062
SPP FH - 13984 | 13984 | (6) new reclosers, (37) fuses, (51) trip savers, and upgrade (73) feeder poles | 1415 | 114 | 51 | 1580 | 51 | 2022-05-23 | 2022-07-10 | 2022-11-15 | 1171851.395
SPP FH - 13989 | 13989 | (3) new reclosers, (27) fuses, (10) trip savers, and upgrade (54) feeder poles | 2216 | 53 | 7 | 2276 | 26 | 2022-02-10 | 2022-04-10 | 2022-08-15 | 832493.145
SPP FH - 14094 | 14094 | (2) new reclosers, (12) fuses, (6) trip savers, and upgrade (23) feeder poles | 2584 | 256 | 45 | 2885 | 6 | 2022-06-01 | 2022-07-17 | 2022-12-15 | 8559.0225
SPP FH - 14123 | 14123 | (2) new reclosers, (54) fuses, (42) trip savers, and upgrade (107) feeder poles | 1069 | 59 | 6 | 1134 | 13 | 2022-05-02 | 2022-06-27 | 2022-11-15 | 1248735.8025
SPP FH - East Winter Haven 13309 | 13309 | (1) new reclosers, (35) fuses, (6) trip savers, and upgrade (61) feeder poles | 0 | 0 | 0 | 0 | 0 | 2021-04-12 | 2021-10-01 | 2022-05-15 | 125468

## DPL-14 SUB 22-24
Tampa Electric's Substation Extreme Weather Hardening Program Projects by Year and Projected Costs (in millions)
| Projects | Costs
2022 | 0 | 0
2023 | 1 | 0.7
2024 | 1 | 4.28

## DPI-3 Rule Adherance
Tampa Electric's 2022-2031 Storm Protection Plan Adherence to Rule 25-6.030 F.A.C.
Required Contents of Plan | Section of the Storm Protection Plan
25-6.030(3)(a)-(b) | Section 3 - SPP Overview
25-6.030(3)(c) | Section 1 - Tampa Electric’s Service Area
25-6.030(3)(d)1-4 | Section 6 – Storm Protection Programs
25-6.030(3)(d)5 | Section 3 – SPP Overview
25-6.030(3)(e) | Section 6 – Storm Protection Programs
25-6.030(3)(f) | Section 6.2 – Vegetation Management
25-6.030(3)(g) | Section 7 – Projected Costs and Benefits
25-6.030(3)(h) | Section 8 – Estimated Rate Impacts
25-6.030(3)(i) | Section 9 – Alternatives and Considerations
25-6.030(3)(j) | N/A (optional)

## DPI-5 Named Storms
Table 1: Named Storms Affecting Tampa Electric Service Area since 1960
Year | Storm Name | Size 1 | Wind Speed 2
1960 | Donna | Cat 3 | 115
1995 | Erin | TS | 57
2004 | Charley | Cat 2 | 86
2004 | Francis | Cat 1 | 63
2004 | Jeanne | Cat 1 | 63
2005 | Dennis | TS | 43
2005 | Wilma | TS | 44
2006 | Alberto | TS | 45
2007 | Barry | TS | 31
2012 | Debby | TS | 53
2012 | Isaac | TS | 36
2013 | Andrea | TS | 47
2015 | Erika | TS | <39 | Add storms and years as necessary
2016 | Colin | TS | <39
2016 | Hermine | Cat 1 | 37
2016 | Matthew | TS | 20
2017 | Emily | TS | <39
2017 | Irma | Cat 1 | 90
2018 | Alberto | TS | 29
2019 | Nestor | TS | 26
2021 | Elsa | TS | 43

## DPI-6 Loading Map
Please send in jpg format

## DPI-7 Hurricane Coastline
Please send in jpg format

## DPI-8 OH-vs-Reliability Chart
Tampa Electric's Distribution System Overhead versus Underground Outage Comparison (in Percent)
| Distribution System | Day-to-Day Outages | Major Event Day Outages | Irma Repair/Replace
Overhead | 53 | 81 | 89 | 99.6
Underground | 47 | 19 | 11 | 0.4

## DPI-10 Supp VM Data
Supplemental Vegetation Management Project Schedule by Service Area
| 2022 |  | 2023 |  | 2024
Service Area | Miles | Customers | Miles | Customers | Miles | Customers
Central | 113.5 | 20418 | 127.1 | 19538 | 201.9991 | 26880
Dade City | 127.6 | 5578 | 44.9 | 681 | 100.4056 | 4627
Eastern | 72.9 | 8794 | 149.8 | 18918 | 97.8987 | 9524
Plant City | 202.2 | 8347 | 31.1 | 3579 | 174.0438 | 5645
South Hillsborough | 20.2 | 3236 | 138.9 | 28399 | 16.4338 | 2874
Western | 112.4 | 20376 | 155.8 | 27165 | 88.1519 | 10391
Winter Haven | 43.2 | 5784 | 53.2 | 7950 | 24.7811 | 1276
Total | 692 | 72533 | 700.8 | 106230 | 703.7141 | 61217

## DPI-11 Supp VM Costs
Supplemental Vegetation Management Project Costs (in thousands)
2022 | 6100
2023 | 7100
2024 | 4800
2025 | 5300
2026 | 6500
2027 | 5900
2028 | 5900
2029 | 5900
2030 | 6200
2031 | 6500

## DPI-12 Mid-cycle VM Data
Mid-Cycle Vegetation Management Project Schedule by Service Area
| 2022 |  | 2023 |  | 2024
Service Area | Miles | Customers | Miles | Customers | Miles | Customers
Central | 36 | 9488 | 176.8 | 25321 | 138.1 | 18058
Dade City | 5.1 | 904 | 0 | 0 | 0 | 0
Eastern | 34.5 | 12007 | 115.3 | 16234 | 129.3 | 15835
Plant City | 12 | 7191 | 231 | 12380 | 174.9 | 6627
South Hillsborough | 23 | 13900 | 82.1 | 3925 | 108.6 | 3446
Western | 53.3 | 19073 | 171.2 | 27479 | 156.8 | 22301
Winter Haven | 32.1 | 14565 | 241.5 | 7779 | 293 | 10032
Total | 196 | 77128 | 1017.9 | 93118 | 1000.7 | 76299

## DPI-13 Mid-cycle VM Costs
Mid-Cycle Vegetation Management Project Costs (in thousands)
2022 | 3500
2023 | 4000
2024 | 5600
2025 | 6000
2026 | 5700
2027 | 6200
2028 | 7300
2029 | 6300
2030 | 6600
2031 | 6900

## DPI-14 69KV Proj Scope VM
Project Scope |  |  | Total Project Costs (in thousands)
Circuits | Customers | Length (miles)
170 | 84000 | 83.2 | 2185

## DPI-16 Substation 22-24
add chart to DPL testimony
Tampa Electric's Substation Extreme Weather Hardening Program Projects by Year and Projected Costs (in millions)
| Projects | Costs
2022 | 0 | 0
2023 | 1 | 0.7
2024 | 1 | 4.3

## DPI-18 Access Road Costs
Access Road Projects Costs (in thousands)
2022 | 724
2023 | 879
2024 | 1844.017
2025 | 1613.762
2026 | 2838.058
2027 | 3403.726
2028 | 1931.687
2029 | 1166.574
2030 | 997.361
2031 | 4424.772

## DPI-19 Access Bridge Costs
Access Bridge Project Costs (in thousands)
2022 | 1686
2023 | 2158
2024 | 1162.563
2025 | 2089.131
2026 | 608.458
2027 | 0
2028 | 1210.654
2029 | 1672.197
2030 | 1043.463
2031 | 0

## DPI-24 SPP Total Costs
Tampa Electric's 2022-2031 Storm Protection Plan Total Costs by Program (in Millions)
Capital | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Distribution Lateral Undergrounding | 105.6627 | 104.5427 | 105 | 105 | 105 | 105 | 105 | 105 | 115 | 115 | 1070.2054 | 105662671.4 | 104542727.7135 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 115000000 | 115000000
Transmission Asset Upgrades | 16.479 | 17.4638 | 17.54 | 17.9168 | 18.2401 | 16.8898 | 17.3476 | 17.2424 | 0 | 0 | 139.1195 | 16478997.81 | 17463787.2 | 17540040 | 17916840 | 18240120 | 16889760 | 17347560 | 17242440 | 0 | 0
Distribution - Substation Extreme Weather Protection | 0 | 0.7 | 2.2212 | 1.3821 | 1.7276 | 1.5301 | 2.468 | 0.71052 | 3.7513 | 0.80923 | 15.3 | 0 | 700000 | 2221174.3772 | 1382064.0569 | 1727580.0712 | 1530142.3488 | 2467971.5302 | 710516.0142 | 3751316.726 | 809234.8754
Transmission - Substation Extreme Weather Protection | 0 | 0 | 2.0538 | 1.2779 | 1.5974 | 1.4149 | 2.282 | 0.65698 | 3.4687 | 0.74827 | 13.5 | 0 | 0 | 2053825.6228 | 1277935.9431 | 1597419.9288 | 1414857.6512 | 2282028.4698 | 656983.9858 | 3468683.274 | 748265.1246
Distribution Overhead Feeder Hardening | 32.8427 | 30.1152 | 29.9982 | 29.9885 | 29.9897 | 29.9967 | 29.993 | 29.9873 | 36.9949 | 36.9923 | 316.8984 | 32842657.4462 | 30115183 | 29998165.0388 | 29988469.8542 | 29989699.9579 | 29996667.7522 | 29993019.5494 | 29987340.3851 | 36994874.8486 | 36992343.9856
Transmission Access Enhancements | 2.41 | 3.0374 | 3.0066 | 3.7029 | 3.4465 | 3.4037 | 3.1423 | 2.8388 | 2.0408 | 4.4248 | 31.4538 | 2409956.08 | 3037445.88 | 3006580 | 3702893 | 3446516 | 3403726 | 3142341 | 2838771 | 2040824 | 4424772
Distribution Pole Replacements | 12.509 | 12.8868 | 13.276 | 13.6769 | 9.0459 | 9.2268 | 9.4114 | 9.5996 | 11.2234 | 11.3998 | 112.2556 | 12509019.4506 | 12886791.838 | 13275972.9515 | 13676907.3346 | 9045899.6327 | 9226817.6254 | 9411353.9779 | 9599581.0575 | 11223435.7867 | 11399848.025
O&M | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Distribution Lateral Undergrounding | 0.18072 | 0.17619 | 0.18103 | 0.14794 | 0.19072 | 0.19557 | 0.20042 | 0.20527 | 0.21011 | 0.33042 | 2.0184 | 180715.8094 | 176186.534 | 181025.843 | 147937.3168 | 190718.8699 | 195569.104 | 200419.376 | 205267.7635 | 210112.2608 | 330415.6395
Distribution Vegetation Management - planned | 21.1607 | 24.0014 | 24.2234 | 25.6459 | 26.7688 | 27.9922 | 29.516 | 30.9404 | 32.5024 | 34.2675 | 277.0187 | 21160688 | 24001407.6202 | 24223435.7727 | 25645904.4881 | 26768822.5779 | 27992199.0294 | 29516043.01 | 30940363.8702 | 32502382.0637 | 34267501.1669
Distribution Vegetation Management - unplanned | 1.4 | 1.4 | 1.4 | 1.3 | 1.3 | 1.3 | 1.4 | 1.4 | 1.3 | 1.3 | 13.5 | 1400000 | 1400000 | 1400000 | 1300000 | 1300000 | 1300000 | 1400000 | 1400000 | 1300000 | 1300000
Transmission Vegetation Management - planned | 3.6124 | 3.661 | 3.0352 | 3.1304 | 3.2271 | 3.3023 | 3.3793 | 3.4581 | 3.631 | 3.8126 | 34.2493 | 3612445 | 3660969.0521 | 3035211.5863 | 3130376.8277 | 3227059.2878 | 3302286.6241 | 3379285.6609 | 3458098.5111 | 3631003.4366 | 3812553.6085
Transmission Vegetation Management - unplanned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transmission Asset Upgrades | 0.49437 | 0.52391 | 0.53439 | 0.54508 | 0.55598 | 0.5671 | 0.57844 | 0.59001 | 0.60181 | 0.61385 | 5.605 | 494369.934 | 523913.616 | 534391.8883 | 545079.7261 | 555981.3206 | 567100.947 | 578442.966 | 590011.8253 | 601812.0618 | 613848.303
Distribution - Substation Extreme Weather Protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transmission - Substation Extreme Weather Protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Distribution Overhead Feeder Hardening | 0.55685 | 0.61865 | 0.6703 | 0.72018 | 0.77031 | 0.82068 | 0.8713 | 0.91818 | 0.97332 | 1.0247 | 7.9445 | 556853.1478 | 618654 | 670300.08 | 720183.0816 | 770307.7432 | 820678.8981 | 871301.4761 | 918180.5056 | 973321.1157 | 1024728.538
Transmission Access Enhancements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Distribution Infrastructure Inspections | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.104 | 1.1261 | 1.1486 | 1.1716 | 1.195 | 1.2189 | 11.1683 | 1020000 | 1040358 | 1061165.16 | 1082388.4632 | 1104036.2325 | 1126116.9571 | 1148639.2963 | 1171612.0822 | 1195044.3238 | 1218945.2103
Transmission Infrastructure Inspections | 0.58299 | 0.54364 | 0.55452 | 0.56561 | 0.57692 | 0.58846 | 0.60023 | 0.61223 | 0.62448 | 0.63697 | 5.886 | 582985 | 543644.1 | 554516.982 | 565607.3216 | 576919.4681 | 588457.8574 | 600227.0146 | 612231.5549 | 624476.186 | 636965.7097
SPP Planning & Common | 0.9243 | 0.8663 | 0.88363 | 0.9013 | 0.91932 | 0.93771 | 0.95647 | 0.97559 | 0.99511 | 1.015 | 9.3747 | 924300 | 866300 | 883626 | 901298.52 | 919324.4904 | 937710.9802 | 956465.1998 | 975594.5038 | 995106.3939 | 1015008.5218
Other Legacy Storm Hardening Plan Items | 0.28611 | 0.29183 | 0.29767 | 0.30362 | 0.30969 | 0.31589 | 0.32221 | 0.32865 | 0.34 | 0.34 | 3.1357 | 286110 | 291832.2 | 297668.844 | 303622.2209 | 309694.6653 | 315888.5586 | 322206.3298 | 328650.4564 | 340000 | 340000
Distribution Pole Replacements | 0.80941 | 0.83385 | 0.85903 | 0.88498 | 0.58532 | 0.59703 | 0.60897 | 0.62115 | 0.71 | 0.72 | 7.2297 | 809407.1409 | 833851.2366 | 859033.5439 | 884976.3569 | 585322.9174 | 597029.3758 | 608969.9633 | 621149.3625 | 710000 | 720000

## DPI-33 VM Summary
Tampa Electric's Vegetation Management Program Projected Costs (in thousands)
| 2022 | 2023 | 2024
Supplemental Vegetation Management Project Costs | 6100 | 7100 | 4800
Mid-Cycle Vegetation Management Project Costs | 3500 | 4000 | 5600
69 kV Reclamation | 695 | 695 | 0
Planned Distribution | 11561 | 12901 | 13823
Planned Transmission | 2917 | 2966 | 3035
Unplanned | 1400 | 1400 | 1400
Total | 26173 | 29062 | 28658

## DPI-32 Trans Access Appendix
Tampa Electric's Transmission Access Enhancement - 2022 Schedule
Project ID | Project Type Road/Bridge | Project Start Qtr | Project End Qtr | Project Cost in 2022
HAMPTON SUBSTATION | Bridge | Qtr 2 2021 | Qtr 4 2022 | 622025
WEST OF FORBES RD | Bridge | Qtr 2 2021 | Qtr 4 2024 | 92429
EAST OF SYDNEY WASHER RD | Bridge | Qtr 2 2021 | Qtr 4 2024 | 100525
TAMPA PALMS #1 | Bridge | Qtr 2 2021 | Qtr 4 2023 | 94755
TAMPA PALMS #2 | Bridge | Qtr 2 2021 | Qtr 4 2023 | 106899
TAMPA PALMS #3 | Bridge | Qtr 2 2021 | Qtr 4 2023 | 102851
TAMPA PALMS #4 | Bridge | Qtr 2 2021 | Qtr 4 2023 | 108249
MORRIS BRIDGE RD | Bridge | Qtr 2 2021 | Qtr 4 2022 | 434769
COLUMBUS DRIVE #1 | Bridge | Qtr 2 2021 | Qtr 4 2025 | 27000
COLUMBUS DRIVE #2 | Bridge | Qtr 2 2021 | Qtr 4 2025 | 22000
230606 | Road | Qtr 2 2021 | Qtr 4 2025 | 20000
230020 | Road | Qtr 2 2021 | Qtr 4 2024 | 219221
230008 | Road | Qtr 2 2021 | Qtr 4 2022 | 146924
230007 | Road | Qtr 2 2021 | Qtr 4 2023 | 67399
66839 | Road | Qtr 2 2021 | Qtr 4 2025 | 26000
66046 | Road | Qtr 1 2022 | Qtr 4 2024 | 90914
66035 | Road | Qtr 2 2021 | Qtr 4 2025 | 26000
66033 | Road | Qtr 1 2022 | Qtr 4 2023 | 45072
66016 | Road | Qtr 2 2021 | Qtr 4 2025 | 20000
66007 | Road | Qtr 2 2021 | Qtr 4 2023 | 21229
66001 | Road | Qtr 1 2022 | Qtr 4 2023 | 48641

## VM SPP-TOTAL
Not updated - we'll see if we need it for info
Tampa Electric's Vegetation Management Storm Protection Plan Total Costs (in thousands)
|  | Supplemental Vegetation Management Project Costs | Mid-Cycle Vegetation Management Project Costs | 69 kV Reclamation | Distribution | Transmission | Total
| 2020 | 3200 | 100 | 100 | 13190 | 2532 | 19122 |  | 13.1879 | 13.3586 | 11.5798 | 12.9014 | 13.8234 | 14.2459 | 14.5688 | 15.8922 | 16.216 | 18.7404
| 2021 | 5200 | 1200 | 695 | 13360 | 2832 | 23287 |  | 2.5324 | 2.8322 | 2.8983 | 2.966 | 3.0352 | 3.1304 | 3.2271 | 3.3023 | 3.3793 | 3.4581
| 2022 | 6100 | 3500 | 695 | 11580 | 2898 | 24773
| 2023 | 7100 | 4000 | 695 | 12900 | 2966 | 27661
| 2024 | 4800 | 5600 | 0 | 13820 | 3035 | 27255
| 2025 | 5300 | 6000 | 0 | 14250 | 3130 | 28680
| 2026 | 6500 | 5700 | 0 | 14570 | 3227 | 29997
| 2027 | 5900 | 6200 | 0 | 15890 | 3302 | 31292
| 2028 | 5900 | 7300 | 0 | 16220 | 3379 | 32799
| 2029 | 5900 | 6300 | 0 | 18740 | 3458 | 34398
|  |  |  | Vegetation Management |  | 19.1203 | 23.2859 | 24.7731 | 27.6624 | 27.2586 | 28.6763 | 29.9959 | 31.2945 | 32.7953 | 34.3985
|  |  |  | Distribution SPP Veg Mgmnt |  | 16.4879 | 19.7586 | 21.1798 | 24.0014 | 24.2234 | 25.5459 | 26.7688 | 27.9922 | 29.416 | 30.9404
|  |  |  | Internal Staffing (Dx only) |  | 0.53788 | 0.54864 | 0.55961 | 0.5708 | 0.58222 | 0.59386 | 0.60574 | 0.61786 | 0.63021 | 0.64282
|  |  |  | Incremental Staffing (Dx only) |  | 0.25 | 0.51 | 0.5202 | 0.5306 | 0.54122 | 0.55204 | 0.56308 | 0.57434 | 0.58583 | 0.59755
|  |  |  | Planned |  | 12.4 | 12.3 | 10.5 | 11.8 | 12.7 | 13.1 | 13.4 | 14.7 | 15 | 17.5
|  |  |  | Supplemental |  | 3.2 | 5.2 | 6.1 | 7.1 | 4.8 | 5.3 | 6.5 | 5.9 | 5.9 | 5.9
|  |  |  | Mid-cycle |  | 0.1 | 1.2 | 3.5 | 4 | 5.6 | 6 | 5.7 | 6.2 | 7.3 | 6.3
|  |  |  | Transmission SPP Veg Mgmnt |  | 2.6324 | 3.5272 | 3.5933 | 3.661 | 3.0352 | 3.1304 | 3.2271 | 3.3023 | 3.3793 | 3.4581
|  |  |  | Planned |  | 1.843 | 1.889 | 1.9362 | 1.9846 | 2.0342 | 2.0851 | 2.1372 | 2.1907 | 2.2454 | 2.3016
|  |  |  | Internal Staffing (Tx only) |  | 0.13944 | 0.14223 | 0.14508 | 0.14798 | 0.15094 | 0.15396 | 0.15704 | 0.16018 | 0.16338 | 0.16665
|  |  |  | ROW Maintenance (Mowing, etc) |  | 0.55 | 0.801 | 0.81702 | 0.83336 | 0.85003 | 0.89132 | 0.93279 | 0.95145 | 0.97048 | 0.98989
|  |  |  | 69kv Incremental |  | 0.1 | 0.695 | 0.695 | 0.695 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 2.5324 | 2.8322 | 2.8983 | 2.966 | 3.0352 | 3.1304 | 3.2271 | 3.3023 | 3.3793 | 3.4581

## TECO Facts
System Facts | [6 empty] | Pickles | Plusquellic | SPP
General |  | Total Circuit Miles | % | Count | Area Miles |  | DPI | DPL | Report
| Distribution | 12138 | [6 empty] | X | 0.51368
| OH | 6235 |  |  |  |  | X | X | X
| UG | 5903 |  |  |  |  | X |  | X
| Total OH Lateral | 4441 | [5 empty] | X | X
| Total OH Feeder | 1794 | [6 empty] | X
| Total UG Lateral | 5240 | [6 empty] | X
| Total UG Feeder | 662 | [6 empty] | X
| Customer Served off Laterals |  | 94 |  |  |  |  | X | X
| Customer Served off Feeders |  | 6 | [5 empty] | X
| Distribution OH Laterals |  |  | 13806 |  |  |  | X
| Service Area Miles |  |  |  | 2000 |  | X
| Total Retail Electric Customers |  |  | 824322 |  |  | X
| Total Poles |  |  | 422500 |  |  | X
Transmission/Substation |  |  |  | Count | Miles
| Substations |  |  | 216 |  |  | X
| Transmission Circuits |  |  | 225 |  |  |  | X
| Transmission Circuits with at least 1 wood pole |  |  | 126 |  | includes 34 kv circuits |  | X
| OH Transmission Lines |  |  |  | 1334 | approx 1,300 | X | X
| Total UG Transmission Lines |  |  |  | 9 |  | X
Get information from Mark Peer (GIS) and Mark Moyer
Vegetation Management
| Contracted Transmission Tree Trimming Personnel | 36
| Dedicated Distribution Tree Trimming Personnel | 295
| Proactive Distribution Tree Trimming Resources | 261 |  | Add up to the Dedicated Personnel
| Reactive Tree Trimming Personnel Resources | 34 |  | Add up to the Dedicated Personnel
| Dedicated Transmission Tree Trimming Personnel | 36
| Approx OH Distribution Lines (miles) | 6300 |  | compared to 6,235 above
| # Miles trimmed in 4-year cycle | 1560 | [5 empty] | X
| # Miles trimmed annually | 530 | [5 empty] | X
| Bulk Miles | 280 | [5 empty] | X
| Non-Bulk Miles | 250 | [5 empty] | X
Transmission Asset Upgrades
| Poles & Structures | 26000 |  |  |  |  | X
| Circuit Miles of Transmission Facilities | 1350
| Total Transmission Poles | 25157 |  |  |  |  | X
Infrastructure Inspections
| Distribution & Lighting Wood Poles | 285000 | [5 empty] | X
| Transmission Poles | 26000 | [5 empty] | X
| Total |  | 311000
| Average Wood Distribution Poles |  | 35625 | Round to next highest thousand - ie $36k
Tranmission Access Enhancement
| Approx Total of Transmission Facilities | 1350 |  | Compare to 1,343 above, Line 22 and 23 |  |  | X