BEFORE THE FLORIDA PUBLIC SERVICE COMMISSION

DIRECT TESTIMONY OF

JAVIER PORTUONDO

ON BEHALF OF

PROGRESS ENERGY FLORIDA

DOCKET NO. 040007

AUGUST 4, 2004

(REVISED SEPTEMBER 3, 2004)

Q.	Please state your name and business address,

A.	My name is Javier J. Portuondo.  My business address is Post Office Box 14042, St. Petersburg, Florida 33733.

- Q.	By whom are you employed and in what capacity?

A.	I am employed by Progress Energy Service Company, LLC as Director of Regulatory Services - Florida.

- Q.	Have your duties and responsibilities remained the same since you last filed testimony in this proceeding?

A.	Yes.

Q.	Have you previously filed testimony before this Commission in connection with Progress Energy Florida's Environmental Cost Recovery Clause (ECRC)?

A.	Yes, I have.

- Q.	What is the purpose of your testimony?

A.	The purpose of my testimony is to present, for Commission review and approval, Progress Energy Florida's Estimated/Actual True-up costs associated with Environmental Compliance activities for the period January 2004 through December 2004.

Q.	Have you prepared or caused to be prepared under your direction, supervision or control any exhibits in this proceeding?

A.	Yes.  I am sponsoring revised Exhibit No. __ (JP-2), which consists of revised PSC Forms 42-1E through 42-8E.  These forms provide a summary and detail of the Estimated/Actual True-up O&M and Capital Environmental costs for the period January 2004 through December 2004.

Q.	What is the Estimated/Actual True-up amount that PEF is requesting recovery for the period of January 2004 through December 2004?

A.	The Estimated/Actual True-up amount for 2004 is an under-recovery, including interest, of $19,027,266, as shown in revised Exhibit No. __ (JP-2), Form 42-1E, Line 4.

Q.	Please explain the calculation of the ECRC Estimated/Actual True-up amount you are requesting this Commission to approve.

A.	Revised Forms 42-2E and 42-3E show the calculation of the ECRC Estimated/Actual True-up amount for the period of January 2004 through December 2004.

Q.	Are all the costs listed in Forms 42-1E through 42-8E attributable to Environmental Compliance projects previously approved by the Commission?

A.	Yes.

Q.	How do the Estimated/Actual project expenditures for January 2004 through December 2004 compare with original projections?

A.	As shown on revised Form 42-4E, total O&M project costs are projected to be $18,745,199 or 178% higher than originally projected.  Total recoverable capital investments itemized on revised Form 42-6E, are projected to be $710,778 or 764% higher than originally projected.  Below are variance explanations for those O&M projects and Capital Investment Projects with significant variances.  Individual project variances are provided on revised Forms 42-4E and 42-6E.  Return on Capital Investment, Depreciation and Taxes for each project for the Estimated/Actual period are provided on revised Form 42-8E, pages 1 through 5.

- Substation Environmental Investigation, Remediation, and Pollution Prevention (Project #1) - O&M

Project expenditures are estimated to be $432,669 or 57% lower than previously projected.  The original projection assumed remediation of 52 substations.  The new projection is based on remediation of 9 substations.  These projects have been delayed due to the longer time period than planned to obtain the required FDEP approval of the Substation Inspection Plan and the Substation Assessment and Remedial Action Plan.  This project is discussed further in Kent D. Hedrick’s testimony.

2.  Distribution System Environmental Investigation, Remediation, and Pollution Prevention (Project #2) - O&M

Project expenditures are estimated to be $2,930,034 or 57% higher than previously projected.  This variance is primarily due to an increase in the estimated number of sites requiring remediation.  The Company identified an additional 364 single-phase sites requiring remediation.  The average cost per 3-phase site also increased from the previously estimated $10,000 per site to the current estimate of $14,000 per site, primarily due to  the higher skill level necessary to perform 3-phase remediation activities.  This project is discussed further in Kent D. Hedrick’s testimony.

3.  Pipeline Integrity Management (Project #3a) – O&M

Project expenditures are estimated to be $745,000 or 304% higher than previously projected.  This variance is primarily due to more current estimates of the costs associated with required preventative measures, based on the results of pipeline inspections.  PEF originally projected a total of $215,000 in O&M costs for the baseline integrity assessment of the Bartow/Anclote pipeline.   Based on actual costs incurred to date and contractor bids for the remaining work, the estimated project costs have escalated by $75,000.  Another $140,000 of this increase is attributable to costs associated with a new position devoted to management and oversight of the PIM program.    Further, in accordance with the PIM Plan, the Company has identified unanticipated O&M project costs of approximately $550,000.  These projects are necessary in order to provide protection against potential threats to pipeline integrity in accordance with the PIM regulations and the company’s PIM Plan.  These projects are discussed further in the testimony of Patricia Q. West.

- Pipeline Integrity Management – Bartow/Anclote Pipeline (Project #3b) – Capital

Project expenditures are estimated to be $692,706 higher than previously forecasted.  This is primarily attributable to $525,940 of expenses that were erroneously charged to non-recoverable O&M and should have been charged to recoverable capital and additional costs of $211,060 for the Bartow/Anclote Pipeline leak detection system to reduce risk in accordance with the PIM Plan.  These projects are further discussed in the testimony of Patricia Q. West’s testimony.

- SO2 Emissions Allowances (Project #5) – O&M

Project expenditures are estimated to be $15,502,833 or 352% higher than originally projected.  This variance is driven by increases in projected tons of SO2 emissions and by higher market prices for allowances.  The price variance is due in part to increased demand in the marketplace due to uncertainty associated with pending legislation on the Clean Air Interstate Ruling.  The price of allowances increased from the previously projected average price of $160 per ton to the current projected average price of $400 - $600 per ton.  The increase in projected tons is driven by higher natural gas prices which have resulted in more residual oil in the 2004 projected generation plan.

Q.	Does this conclude your testimony?

A.	Yes, it does.