D.9.0  RCID’s Consequences of Delay

The proposed TEC is unique compared to the other supply-side alternatives considered in this analysis, because the project is significantly further along in the development process than the other options presented in Section A.6.0 and considered to meet RCID’s capacity and energy needs.  As a result, the consequences of delaying the commercial operation of TEC are significant from an economic and reliability standpoint for RCID.  This section describes the negative consequences of delaying the TEC project.

D.9.1  Economic Consequences

If the commercial operation of TEC is delayed by 1 year to May 1, 2013, RCID would not be able to realize the economic benefit of the low cost, baseload energy from TEC.  RCID would need to satisfy its demand and energy requirements with higher cost energy from natural gas, oil, and purchased power.  The optimal capacity expansion plan with TEC installed in May 2013 would consist of a brownfield LM6000 1x1 combined cycle unit in 2011 and two brownfield LM6000 1x1 combined cycle units in 2018.  The CPWC of this plan is $1,796.7 million, which is about $25.5 million higher in CPWC over the planning period than the base case plan with TEC in 2012 (presented in Section D.5.0).  The CPWC of the plan with TEC delayed by 1 year is still $245.4 million lower in cost than the lowest cost plan without TEC, presented in Section D.5.0.

D.9.2  Reliability Consequences

If TEC is delayed, RCID will be able to maintain its 15 percent reserve margin through its existing purchase power agreement with TECO.  However, the generating resources owned by RCID will consist entirely of natural gas and fuel oil fired generating units, with natural gas fired units comprising approximately 92 percent of the capacity owned by RCID.  This percentage decreases to approximately 59 percent of capacity from natural gas, if TEC is available in 2012.  Continuing to rely so heavily on natural gas fired generating units will increase the probability that RCID will not be able to satisfy its demand and energy requirements in the event of natural gas supply disruptions.  RCID’s customers will also likely be exposed to potentially high energy costs from emergency purchases if TEC is not available, in the event of a natural gas supply disruption.