167

1                              BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

DOCKET NO. 080009-EI

3

In the Matter of:

4

NUCLEAR COST RECOVERY CLAUSE.

5       _____________________________/

6

VOLUME 2

7

Pages 167 through 369

8

ELECTRONIC VERSIONS OF THIS TRANSCRIPT ARE

9                  A CONVENIENCE COPY ONLY AND ARE NOT

THE OFFICIAL TRANSCRIPT OF THE HEARING.

10             THE .PDF VERSION INCLUDES PREFILED TESTIMONY.

11

12       PROCEEDINGS:           HEARING

13

BEFORE:                CHAIRMAN MATTHEW M. CARTER, II

14                              COMMISSIONER LISA POLAK EDGAR

COMMISSIONER KATRINA J. McMURRIAN

15                              COMMISSIONER NANCY ARGENZIANO

COMMISSIONER NATHAN A. SKOP

16

17       DATE:                  Thursday, September 11, 2008

18

TIME:                  Commenced at 9:30 p.m.

19                              Concluded at 5:20 p.m.

20

PLACE:                 Betty Easley Conference Center

21                              Room 148

4075 Esplanade Way

22                              Tallahassee, Florida

23

REPORTED BY:           MARY ALLEN NEEL, RPR, FPR

24

25       APPEARANCES:           (As heretofore noted.)

168

1                               I N D E X

2                               WITNESSES

3

NAME                                                PAGE

4

GARRY MILLER

5

Pre-filed Direct Testimony Inserted                  172

6

DANIEL L. RODERICK

7

Direct Examination by Ms. Triplett                   183

8       Prefiled Testimonies Inserted                        186

Cross-Examination by Mr. McWhirter                   284

9       Cross-Examination by Mr. Brew                        290

10       WILLIAM R. JACOBS, JR., Ph.D.

11       Direct Examination by Mr. Burgess                    301

Prefiled Testimony Inserted                          305

12

JEFFERY A. SMALL

13

Prefiled Direct Testimony Inserted                   334

14

CARL VINSON and ROBERT LYNN FISHER

15

Direct Examination by Mr. Young                      341

16       Prefiled Direct Testimony Inserted                   345

Cross-Examination by Mr. Brew                        351

17

WILL GARRETT

18

Prefiled Rebuttal Testimony Inserted                 360

19

CERTIFICATE OF REPORTER                              369

20

21

22

23

24

25

169

1                               I N D E X

2                               EXHIBITS

3       NUMBER                                     ID.    ADMTD.

4       14   DLR-1                                           300

5       15   WRJ-1                                           332

6       16   JAS-1                                           333

7       17   JAS-2                                           333

8       18   JAS-3                                           333

9       19   VF-1                                            357

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

170

1                          P R O C E E D I N G S

2                 (Transcript follows in sequence from

3       Volume 1.)

4                 CHAIRMAN CARTER:  We are back on the record.

5       And when we left last time, we had finished the direct,

6       cross, and exhibits for witness Cross.  And I think with

7       that, Ms. Triplett, you are recognized.

8                 MS. TRIPLETT:  Thank you.  I think at this

9       point we would like to ask that the prefiled written

10       testimony for Garry Miller, who was excused from the

11       proceeding, be inserted into the record.

12                 CHAIRMAN CARTER:  Let's do this before you go

13       there.  And I'm sorry for cutting you off, but you did

14       -- we asked you, and you did provide it for us.

15                 Commissioners, it's a one-page errata sheet

16       for witness Cross, and it has got the numbers that we

17       were asking about.  Show it entered into the record.

18       Without objection, show it done.

19                 You did provide a copy to all the parties too;

20       right?

21                 MS. TRIPLETT:  Yes, sir.

22                 CHAIRMAN CARTER:  Thank you so kindly.

23                 MS. TRIPLETT:  Yes, sir.

24                 CHAIRMAN CARTER:  Sorry to interrupt you.

25       Ms. Triplett, you're recognized.

171

1                 I didn't mean to throw your rhythm off like

2       that.

3                 MS. TRIPLETT:  No, I'm sorry.  It doesn't take

4       much to throw my rhythm off.

5                 Yes.  I think we're up to Garry Miller's

6       testimony, so we would ask that the prefiled testimony

7       for Mr. Garry Miller be inserted into the record as

8       though read.

9                 CHAIRMAN CARTER:  The prefiled testimony of

10       the witness will be entered into the record as though

11       read.

12                 MS. TRIPLETT:  Thank you.  And he did not have

13       any exhibits.

14                 CHAIRMAN CARTER:  Okay.  Is this a stipulated

15       witness?

16                 MS. TRIPLETT:  Mr. Miller?

17                 CHAIRMAN CARTER:  Yes.

18                 MS. TRIPLETT:  Yes, he was stipulated and

19       excused.

20                 CHAIRMAN CARTER:  Okay.

21                 MS. TRIPLETT:  And now we're up to Mr. --

22                 CHAIRMAN CARTER:  Is that okay with the

23       parties?  Is that correct?  Commissioners?  Okay.  Show

24       it done.  No exhibits with Mr. Miller?

25                 MS. TRIPLETT:  Correct, no exhibits.

183

1                 CHAIRMAN CARTER:  Okay.  You're recognized.

2                 MS. TRIPLETT:  Thank you.  And Progress Energy

3       would call Daniel Roderick to the stand.

4                 CHAIRMAN CARTER:  Daniel Roderick.

5       Thereupon,

6                          DANIEL L. RODERICK

7       was called as a witness on behalf of Progress Energy

8       Florida and, having been first duly sworn, was examined

9       and testified as follows:

10                          DIRECT EXAMINATION

11       BY MS. TRIPLETT:

12            Q.   Would you please introduce yourself to the

13       Commission and provide your address?

14            A.   Yes.  My name is Daniel Roderick.  My business

15       address is 15760 West Power Line Street, Crystal River,

16       Florida.

17            Q.   And who do you work for, and what is your

18       position?

19            A.   I work for Progress Energy.  I'm the Vice

20       President for Nuclear Projects and Construction.

21            Q.   And have you filed prefiled direct testimony

22       regarding PEF's 2008 actual/estimated and 2009 projected

23       costs associated with the CR3 uprate project?

24            A.   Yes.

25            Q.   Have you filed prefiled direct testimony

184

1       regarding PEF's costs incurred in 2006 and 2007 for the

2       CR3 uprate project?

3            A.   Yes.

4            Q.   Have you filed prefiled supplemental direct

5       testimony regarding PEF's 2008 estimated/actual costs

6       and 2009 projected costs associated with the CR3 uprate?

7            A.   Yes.

8            Q.   Have you filed rebuttal testimony regarding

9       the CR3 uprate project costs?

10            A.   Yes.

11            Q.   Have you filed prefiled revised direct

12       testimony regarding PEF's 2008 estimated/actual and 2009

13       projected costs associated with the Levy nuclear plant?

14            A.   Yes.

15            Q.   Have you filed prefiled direct testimony

16       regarding PEF's site selection costs associated with the

17       Levy nuclear construction project?

18            A.   Yes.

19            Q.   Have you filed prefiled supplemental direct

20       testimony regarding PEF's site selection,

21       actual/estimated, and projected costs associated with

22       the Levy nuclear project?

23            A.   Yes.

24            Q.   And does this supplemental testimony

25       supplement your revised prefiled direct testimony?

185

1            A.   Yes.

2            Q.   And do you have any changes to make to your

3       prefiled testimony and exhibits?

4            A.   I have one correction that I want to make in

5       my direct testimony for in support of 2008

6       actual/estimated costs and 2009 projected costs.  That's

7       on the May 1, 2008 testimony, and it's on page 9 on line

8       17.  Where it says "approximately 12 million, gross of

9       joint owner billing and exclusive of carrying," the

10       12 million should be 8.4 million.  That does not change

11       any of the exhibits or any of the other filings.  It's

12       just an error in this particular document.

13            Q.   And if I asked you the same questions in your

14       prefiled testimony today, would you give the same

15       answers, with the correction that you just made?

16            A.   Yes.

17                 MS. TRIPLETT:  We would request that the

18       prefiled testimonies be moved into evidence as though

19       read in the record.

20                 CHAIRMAN CARTER:  The prefiled testimony will

21       be entered into the record as though read.

22

23

24

25

284

1       BY MS. TRIPLETT:

2            Q.   Do you have a summary of your prefiled

3       testimonies?

4            A.   Yes.  I basically have submitted theses

5       testimonies, and I'm opening myself up for questions.

6                 MS. TRIPLETT:  We tender Mr. Roderick for

7       cross-examination.

8                 MR. BURGESS:  No questions.

9                 CHAIRMAN CARTER:  Thank you.  Mr. Twomey?

10                 MR. TWOMEY:  No, sir.

11                 CHAIRMAN CARTER:  Mr. McWhirter?

12                           CROSS-EXAMINATION

13       BY MR. McWHIRTER:

14            Q.   Mr. Roderick, do you project your costs

15       further into the future than 2009?

16            A.   Yes.  As part of our project management tools

17       that we have, we looked at total project costs, which

18       would go the entire life cycle of the project.

19            Q.   Do you project that the costs in your

20       pass-through will remain fairly static from this time

21       forward, or will they fall off?

22            A.   Well, you know, the cash flows right now,

23       until we have all of our contracts in place, we don't

24       know exactly for sure.  I don't see them falling off in

25       the next several years.  I think that with the way the

285

1       construction schedule is to support the 2016 in-service

2       date for Unit 1 and 2017 for Unit 2, we will see that

3       number go up over the next several years over what we're

4       at right now.

5            Q.   It will be 420 million this year, and will it

6       be an additional 420-plus next year?

7            A.   Yes.  I believe when you look at 2009, it will

8       be very consistent with this year, in that range.

9            Q.   Does that mean that it will be an additional

10       420, or will it be a repeat on the same number?

11            A.   No, it will be an additional 420.

12            Q.   So this time next year, we'll be looking at

13       $800 million a year charges to customers based upon the

14       nuclear program?

15            A.   No.  I think what we're saying is, what we're

16       filing this year is actuals to date.  Once actuals are

17       spent, you know, they're gone, and then a projection for

18       next year.  What we're saying is, after you pay those,

19       then you still have new costs coming in, and the new

20       costs coming in are going to be fairly similar in nature

21       into next year with what the project demands are.

22            Q.   If I understand you correctly, then it looks

23       like we're going to have a level 420 million in those

24       numbers every year until after the plant is completed.

25            A.   No, I didn't say that at all.  I said what I

286

1       saw between this year, what we're filing, and what we

2       have projected for next year, that those two numbers are

3       about the same.

4                 When you get after this and we get in further

5       in the licensing process -- and realize, we're very

6       early in this process for the new nuclear plant.  We

7       have, you know, a site certification that we filed that

8       we talked about.  We have the combined operating license

9       that we have filed, and all the pre-construction costs

10       with the site itself are all going to start coming into

11       the project for us to support the 2016 in-service date.

12            Q.   Okay.  I guess I'm still not quite

13       understanding what you're saying.  The charge for

14       customers this year is going to be 420 million including

15       income tax, according to Ms. Cross.  What will the

16       charge next year be?

17            A.   I don't know.  I don't calculate the rate, the

18       per month.  What I can say is that from a cash flow

19       standpoint, for the project needs, to continue the

20       project, that our projection for next year is very

21       similar to this year, based on the schedule.  It's based

22       on physical work that we have laid out.

23                 For example, we're working right now with the

24       Department of Environmental Protection on wetland

25       mitigations for the property, and so some of those costs

287

1       will incur as we, you know, work out the agreement for

2       the site certification process.  So we've projected

3       those into next year into the overall, you know, project

4       costs that we have.  And so the estimates that we

5       provided before earlier this year, you know, we still

6       have those estimates in front of us and are still

7       working towards those.

8            Q.   Now, the biggest number, as I understand it,

9       in this group is the site costs, the 300 and -- what was

10       that amount?  207 million that she said?

11            A.   Well, the largest portion of this is really in

12       the costs for the pre-construction that we have,

13       primarily with our letter of intent that we signed and

14       in buying long lead time materials.

15            Q.   And so what you're doing is paying in advance

16       for those items, and since construction hasn't started

17       yet, you're collecting the entire cost of the item as

18       opposed to carrying costs?

19            A.   No.  What we -- and again, I'm not into the

20       filing part of this.  But what we need to do is, we have

21       to assure ourselves that we could get the major

22       components that we needed to keep the construction

23       schedule in 2016, reactor vessels, the pressurizer, the

24       internals of the reactor.  We needed to get those locked

25       in because of the market conditions of those major

288

1       components.

2                 We also saw that those components were

3       escalating at a rate that we -- when we looked at our

4       risk matrix to talk about how could we stabilize the

5       price on this, we made the decision to go ahead and sign

6       that letter of intent to lock in those prices and to

7       lock in the delivery schedule for those large

8       components.

9            Q.   And how much did you pay with that letter of

10       intent?

11            A.   Well, that's -- it's a confidential document.

12       It has been provided to all of the intervenors as well

13       as OPC.  It has been provided to the Commission.  It has

14       also been provided to -- all of you have been provided

15       that information.

16            Q.   Do you know whether Progress borrowed the

17       money to make that payment?

18            A.   I don't know.  That's not my area.

19            Q.   I'm still a little bit unclear.  If I were

20       making a mortgage payment of $400 million a year, I

21       would know that I had a level term payment each year of

22       400 million.  But from what you're telling me, are you

23       saying that it's going to be a level 400 million from

24       now on out, or is it going to be 400 million plus

25       another 400 million?

289

1            A.   No.  What I said was, this year, you have the

2       projection in front of you, and I said that next year

3       when we come back to this, I would expect that number to

4       be somewhere in that same range, about 400 million.  As

5       the construction, as the EPC, the engineering

6       procurement and construction contract comes to

7       completion for negotiation, then we'll revisit the cash

8       flows for that.  That may do something different in the

9       out years.  But no matter how you go to get into the

10       construction schedule, this number is going to get

11       bigger every single year up until we get to the

12       substantial completion of the unit, at which time, then

13       it's done, and the costs will go back down.

14            Q.   Do I understand that to mean that it's going

15       to be more than 400 million next year that is going to

16       be passed through to the consumer?

17            A.   Well, I think we've provided the information

18       of what the total plant cost is of 17.2 billion.  That's

19       our current -- it's our current estimate.  We're very

20       early in this process, and we're still working with all

21       the licensing agencies to get what their requirements

22       are.  We're working with our engineering procurement

23       contract to get the final numbers in place.  But nothing

24       I'm seeing right now from what we testified in the need

25       case is any different in cost from what we laid out

290

1       there.  There's been ebbs and flows in that, but over

2       the course of the next eight years, you know, we will

3       incur those expenses.  So, you know, that number is

4       going to go up until we get to 17.2 billion.

5            Q.   Are you the person involved with negotiating

6       potential sales to other wholesale customers or unit

7       sales?

8            A.   No.

9            Q.   Who is the person that's responsible for that

10       in your company?

11            A.   I think that's a combination of people under

12       Jeff Lyash with Progress Energy Florida.

13                 MR. McWHIRTER:  I tender the witness,

14       Mr. Chairman.

15                 CHAIRMAN CARTER:  Thank you, Mr. McWhirter.

16       Mr. Brew.

17                           CROSS-EXAMINATION

18       BY MR. BREW:

19            Q.   Thank you, Mr. Roderick.  I hadn't planned any

20       questions, but your discussion with Mr. McWhirter just

21       confused me a little bit, if you could.  Are there

22       points in the licensing or construction process where

23       we're likely to see a step change in what's being asked

24       for recovery in the nuclear recovery?

25            A.   What we need to do is finish the EPC contract.

291

1       And realize, we have joint teams working.  And when you

2       have a project like this, over 30 percent of the project

3       is the carrying cost of money.  And so, you know, we

4       don't want to spend money any earlier than we have to to

5       be able to stay with the in-service date.

6                 By the same point in time, you can't afford to

7       spend it late, or then you deprive the benefit of the

8       result of the $92 billion we're expecting in savings in

9       fuel for the unit.  So we have teams working very hard

10       right now to get that cash flow just right so that it is

11       the least impact to the total cost of the project.

12                 Until we have that EPC contract, engineering

13       procurement and construction contract, finalized and

14       done, and negotiate all of those moves around the

15       schedule to get that optimal schedule and the least cost

16       that we can produce, then your -- that's why I'm saying

17       it's going to change, but it will build over time.

18            Q.   And the EPC is supposed to be done this year?

19            A.   We don't know.  We're working on it extremely

20       hard.  We have dedicated teams that are working full

21       time on it, but it takes two parties to sign that

22       contract, and I can't speak for the other side.

23                 MR. BREW:  Thank you.  That's all I have.

24                 CHAIRMAN CARTER:  Thank you, Mr. Brew.  Staff?

25                 MR. YOUNG:  No questions.

292

1                 CHAIRMAN CARTER:  Commissioner Argenziano.

2                 COMMISSIONER ARGENZIANO:  Thank you.  Sorry.

3                 In regards to the parcels that were needed and

4       bought, I think there were two parcels for the plant

5       site.  I understand -- from what I read, I believe we

6       needed actually 200 acres for the plant itself, but had

7       to acquire 2,100 acres.  And I guess there's a few

8       questions that I had.

9                 What are you going to do with the remainder of

10       the acreage?  Is that extra acreage calculated into used

11       and useful?  And for people at home, if they are

12       listening, if they're not glazed over, so that they have

13       a good understanding of what's going to happen with

14       that, if the land is sold in the future, does that then

15       get refunded back to the consumers?

16                 THE WITNESS:  I want to answer your second

17       question first.  I don't know the answer of what happens

18       to it when it gets sold back, but I'll talk to you about

19       the land itself.

20                 You know, when you build a nuclear power

21       plant, you need to build your buffer between you and the

22       nearest residence.  And so by the location of this site

23       and the geographic of that site, our nearest neighbor

24       where someone physically lives is just over a mile away.

25       It's 6,000 feet to the nearest neighbor.  That allows us

293

1       to put the security perimeters that we need at the plant

2       for protection and to be able to defend the plant, to

3       define that outer perimeter.  And so while the plant

4       itself may sit, you know, on 200 acres, you have buffer

5       zones around that that we are required to have with the

6       Nuclear Regulatory Commission.  And then, you know, we

7       have just the whole border patrolled area that allows us

8       to control what comes in and out of that site.

9                 The other thing on the site --

10                 COMMISSIONER ARGENZIANO:  I'm sorry.  May I

11       ask --

12                 CHAIRMAN CARTER:  You're recognized.

13                 COMMISSIONER ARGENZIANO:  What is the required

14       buffer zone?

15                 THE WITNESS:  Well, you know, we will

16       typically keep a half a mile diameter around that.  But

17       every site has specific requirements that we -- we have

18       to work with the Nuclear Regulatory Commission to

19       establish those.  Most plant sites, we keep it as a mile

20       as a general rule of thumb.  That bounds, you know,

21       future regulations or changes with that.

22                 COMMISSIONER ARGENZIANO:  And if can I

23       elaborate on that, and then you were going to say

24       something else.  But in the acquisition of the land, I

25       think it was indicated that originally you needed 200

294

1       acres.  Did that include the buffer zone?

2                 THE WITNESS:  The 200 acres is actually where

3       the plant, the physical power block sits.  The reactor,

4       the turbine, the cooling towers, the switch yard, all

5       those components sit on that part of the plant.

6                 COMMISSIONER ARGENZIANO:  And that didn't

7       include the buffer zone?

8                 THE WITNESS:  No, no.  And also, in addition

9       to that, you also have -- we have to have runoff ponds

10       for water drainage.  We have to have a security training

11       zone for shooting practice and things like that.  So

12       when you add all those things together, that's why the

13       acreage, the actual acreage that the plant consumes is a

14       little -- is bigger than just what the plant site sits

15       on.

16                 COMMISSIONER ARGENZIANO:  Okay.  Let me ask it

17       a different way.  Did you need 2,100 acres?

18                 THE WITNESS:  Well, when you make a purchase

19       like that and realize -- define that kind of acreage,

20       most people don't like to peel off just that corner of

21       it.

22                 So when you say do you need it, we know we're

23       going to need wetland mitigation property.  We don't --

24       you know, when you go try to find that in Levy County,

25       unlike counties further south that have land banks for

295

1       wetland mitigation, we don't have that in Levy.  There

2       is no wetland mitigation bank.  And so we strategically

3       want to try to work with the DEP and others, the

4       Department of Environmental Protection and others in the

5       state and try to take advantage of where that makes

6       sense or where it doesn't make sense and how we can

7       aggregately mitigate all those properties.

8                 So, you know, that's how we ended up with the

9       2,200 acres.  It was that block of land that -- the

10       seller of that was not potentially amenable --

11                 COMMISSIONER ARGENZIANO:  That was the Lybass?

12                 THE WITNESS:  This is Rayonier.

13                 COMMISSIONER ARGENZIANO:  Okay.  What about

14       the Lybass?

15                 THE WITNESS:  You know, Lybass is a little

16       different situation.  That is the south property that we

17       have.  We spent a lot of time and a lot of detail with

18       them.  We originally, you know, looked at that site

19       because it's closer to the water, and we couldn't really

20       come to any agreement on the whole purchase of that

21       property.  And that's when we went north and found good

22       rock up north and found that our construction costs

23       could even, you know, be a little bit lower because we

24       had better rock on the north property.  We knew that we

25       needed to get from the north property down to the water

296

1       at the barge canal, and so as we negotiated that, you

2       know, we had to look at all the options of how to get

3       that property, whether we condemned it, you know, how we

4       went about getting that south property.  And we

5       basically did discussions with them and came to an

6       agreement on the south property for what we needed

7       there.

8                 COMMISSIONER ARGENZIANO:  Okay.  You came to

9       agreement on the Lybass property.

10                 THE WITNESS:  The south property.

11                 COMMISSIONER ARGENZIANO:  Which is for

12       transmission and to enable you to get to the barge

13       canal.

14                 THE WITNESS:  It give you the water to and

15       from the plant.  It's the transmission corridor.  It's

16       where our heavy road, rail -- not rail, but the heavy

17       haul path that -- when the barges bring the big

18       construction modules in, they'll be offloaded, and then,

19       instead of us having to go on the highways and disturb

20       the highways, we basically can cut across over to the

21       Lybass property, to that south property, and then go

22       straight up to the site.

23                 COMMISSIONER ARGENZIANO:  Okay.  And then

24       maybe just one more.  On the Lybass property, that's a

25       bigger piece than you really needed.  Isn't there extra

297

1       land there?  And I think that's probably what my

2       original questions go to.

3                 THE WITNESS:  And my only answer is that I

4       don't know right know that they have any extra land,

5       because right now, when I look at the wetland

6       mitigations and the strategies behind that, they may

7       consume all that land.  I have to give that up to

8       preserve for the State just for the wetland mitigation.

9       That's all still in discussion right now.  So I don't

10       know that I have any extra land.

11                 COMMISSIONER ARGENZIANO:  Okay.  Thank you.

12                 THE WITNESS:  As a matter of fact, I would

13       tell you that before this is done, I believe we will

14       have to purchase additional land just because of the

15       regulations with, you know, getting through DEP.

16                 COMMISSIONER ARGENZIANO:  Thank you.

17                 CHAIRMAN CARTER:  Thank you.  Anything further

18       from the bench?

19                 Ms. Triplett.

20                 One second.  Commissioner Skop, you're

21       recognized, sir.

22                 COMMISSIONER SKOP:  Thank you, Mr. Chairman.

23                 In the mounds and mounds of paper, I actually

24       had some of the same concerns in reviewing the prefiled

25       testimony as Commissioner Argenziano, but I cannot find

298

1       it directly in front of me at the moment.  But I heard

2       Mr. Roderick testify, at least with respect to the

3       Lybass property, that the acquisition of that property

4       was somewhat probably strategic, to the extent that it

5       was critical to being able to have access with this

6       property to the barge canal, that it was necessary for

7       the water supply and the transport.  Would that be

8       correct?

9                 THE WITNESS:  Yes.

10                 COMMISSIONER SKOP:  And also it's mentioned

11       somewhere, but I think you may have stated that

12       additional property would be required.  But I thought

13       that I read somewhere else in the prefiled testimony to

14       the extent that some of the excess property may be used

15       for future generation sites, like for a combined cycle

16       plant or something like that, if there were some excess

17       that was suitable and feasible within that.  Would that

18       be also correct?

19                 THE WITNESS:  Yes.  I mean, there is some

20       strategic value, and that was separated out from the

21       part that we needed for the plant.  So I don't know, you

22       know, on that.

23                 COMMISSIONER SKOP:  And then just one final

24       question.  In making that acquisition, I guess they had

25       done some internal analysis on looking at what the

299

1       landowner was willing to sell versus the other

2       alternatives which would enable the company to go get

3       the parcel of property or access down to the barge canal

4       that it needed; is that correct?

5                 THE WITNESS:  Yes.

6                 COMMISSIONER SKOP:  All right.  Thank you.

7                 COMMISSIONER ARGENZIANO:  Just one other

8       thing.

9                 CHAIRMAN CARTER:  Commissioner Argenziano.

10                 COMMISSIONER ARGENZIANO:  I'm just thinking,

11       because I know that area very well.  I live in that

12       area.  I don't know if I -- maybe I better not ask this

13       now.  I'm trying to think of appraised value of land,

14       and I'm just wondering if it was within the realm of

15       everything else that sold in that area.

16                 THE WITNESS:  I'll answer that very globally,

17       because the --

18                 COMMISSIONER ARGENZIANO:  Okay.  Right, right.

19                 THE WITNESS:  -- details of that I can't

20       really discuss.  But, you know, we looked very hard at

21       that.  And we use an independent person to represent us

22       when we're dealing with a landowner, because if they

23       hear a power plant is coming, then prices will skyrocket

24       for that large of a property.

25                 And so, you know, one of the reasons we left

300

1       the south property was because we felt with the volume

2       of real estate that they were going to drive us to

3       purchase at the price, it was -- we just said, "We're

4       not going to do that."  So I do believe we found

5       property that was within market of the size and scope

6       and nature that we needed.

7                 COMMISSIONER ARGENZIANO:  Thank you.

8                 CHAIRMAN CARTER:  Thank you, Commissioners.

9       Ms. Triplett.

10                 MS. TRIPLETT:  No redirect.

11                 CHAIRMAN CARTER:  Okay.  Do we have any -- I

12       think we've got one.  Is that Exhibit 14?

13                 MS. TRIPLETT:  Yes, sir.  We would ask that

14       Exhibit 14 be moved into the record.

15                 CHAIRMAN CARTER:  Any objections?  Without

16       objection, show it done, Exhibit 14 entered into the

17       record.

18                 (Exhibit Number 14 was admitted into the

19       record.)

20                 CHAIRMAN CARTER:  And I believe the witness

21       may be excused.

22                 MS. TRIPLETT:  Thank you.  You anticipated my

23       question.

24                 CHAIRMAN CARTER:  Okay.  Ms. Triplett,

25       anything further?

301

1                 MS. TRIPLETT:  No.  Progress Energy would

2       rest.

3                 CHAIRMAN CARTER:  Okay.  Mr. -- hang on one

4       second.  Let me look at my notes here.  Mr. Burgess,

5       you're recognized, sir.

6                 MR. BURGESS:  Thank you.  We would call

7       Dr. Jacobs to the witness stand, please.

8       Thereupon,

9                    WILLIAM R. JACOBS, JR., Ph.D.

10       was called as a witness on behalf of the Citizens of the

11       State of Florida and, having been first duly sworn, was

12       examined and testified as follows:

13                          DIRECT EXAMINATION

14       BY MR. BURGESS:

15            Q.   Would you state your name and business address

16       for the record, please.

17            A.   Yes, sir.  My name is William R. Jacobs.  My

18       business address is 1850 Parkway Place, Marietta,

19       Georgia.

20            Q.   Dr. Jacobs, did you prefile testimony in July

21       2008 in this docket?

22            A.   Yes, I did.

23            Q.   And did you have exhibits attached to the

24       testimony that was prefiled?

25            A.   Yes, I did.

302

1            Q.   As it pertains to Progress Energy -- let me

2       back up and just make sure that we understand

3       organizationally.  When you filed the prefiled

4       testimony, did it pertain to both Florida Power & Light

5       and Progress Energy?

6            A.   Yes, that's correct.

7            Q.   And you understand that what we're going to be

8       discussing now pertains specifically only to Progress

9       Energy?

10            A.   Yes, I do.

11            Q.   With regard to Progress Energy and its

12       application, did you also have Exhibit 1 attached to

13       your prefiled testimony that consists of your resum and your experience, and we

8       appreciate you being with us today.  Thank you.

9                 THE WITNESS:  Thank you, sir.  I'm glad to be

10       here.

11                 CHAIRMAN CARTER:  Mr. Burgess.

12                 MR. BURGESS:  Commissioner, we would ask that

13       Exhibit 1 --

14                 CHAIRMAN CARTER:  Fifteen?

15                 MR. BURGESS:  It's labeled as, yes, Exhibit

16       15, be entered into the record.

17                 CHAIRMAN CARTER:  Without objection, show it

18       done.

19                 (Exhibit Number 15 was admitted into the

20       record.)

21                 CHAIRMAN CARTER:  Call your next witness.

22       Wait a minute.  Staff, are you next?

23                 MS. BENNETT:  Yes, Chairman.  Our next staff

24       witness is Jeffery Small.  He has been excused.  We

25       would ask that Jeffery Small's testimony be entered into

333

1       the record as read, as well as Exhibits 16, 17, and 18.

2                 CHAIRMAN CARTER:  Let's do the testimony

3       first.  The prefiled testimony will be entered into the

4       record as though read.  Now we'll go with the exhibits.

5                 MS. BENNETT:  Thank you.  Exhibits 16, 17, and

6       18, we ask that they be entered the record.

7                 CHAIRMAN CARTER:  Any objections?  Without

8       objection, show it done.  Exhibits 16, 17, and 18 are

9       entered into the record.

10                 (Exhibits Number 16, 17, and 18 were admitted

11       into the record.)

12

13

14

15

16

17

18

19

20

21

22

23

24

25

341

1                 CHAIRMAN CARTER:  You're recognized.

2                 MR. YOUNG:  Mr. Chairman, at this time, we

3       would call -- staff would call Carl Vinson and Lynn

4       Fisher to the stand.

5                 CHAIRMAN CARTER:  Okay.  I'm guessing, and I

6       believe that I see that everyone for Progress has

7       already been sworn in.  I'm looking, and the faces look

8       familiar to me.  So everyone has already been sworn in

9       for today for Progress; correct?  Right?  Thank you.

10                 Staff, you're recognized.  I guess I should

11       have asked that earlier, huh?

12       Thereupon,

13                  CARL VINSON and ROBERT LYNN FISHER

14       were called as witnesses on behalf of the FPSC Staff

15       and, having been first duly sworn, were examined and

16       testified as follows:

17                          DIRECT EXAMINATION

18       BY MR. YOUNG:

19            Q.   Good afternoon, gentlemen.

20            A.   (By Mr. Fisher)  Good afternoon.

21            Q.   Have you been sworn?

22            A.   (By Mr. Vinson)  Yes, we have.

23            A.   (By Mr. Fisher)  Yes, we have.

24            Q.   Can you please state your name and business

25       address for the record?

342

1            A.   (By Mr. Vinson)  Carl Vinson, 2540 Shumard Oak

2       Boulevard, Tallahassee, Florida.

3            A.   (By Mr. Fisher)  Robert Lynn Fisher, 2540

4       Shumard Oak Boulevard, Tallahassee, Florida.

5            Q.   By whom are you employed, and in what

6       capacity?

7            A.   (By Mr. Vinson)  I'm employed by this

8       Commission as a Public Utilities Supervisor.

9            A.   (By Mr. Fisher)  I'm employed by the Florida

10       Public Service Commission as a Government Analyst II.

11            Q.   Okay.  Have you jointly prefiled testimony

12       consisting of five pages in this case?

13            A.   (By Mr. Vinson)  Yes, we have.

14            A.   (By Mr. Fisher)  Yes, we have.

15            Q.   Do you have any changes or corrections to that

16       testimony?

17            A.   (By Mr. Vinson)  Yes, I do.  On page 2 of our

18       testimony, the first full paragraph that begins on line

19       4, looking down to the final sentence of that paragraph

20       at line 9, there's a sentence that begins, "In each

21       case, the assignments required."  I would like to delete

22       the words "in each case" and the comma, so that the

23       sentence --

24                 CHAIRMAN CARTER:  I'm sorry.  Could you start

25       over?  I had some technical difficulties with my book

343

1       here.

2                 WITNESS VINSON:  Okay.  I'm looking at line 9

3       on page 2.

4                 CHAIRMAN CARTER:  Give me the page, please.  I

5       mean, start at the beginning, the page and line, so I

6       can follow you.

7                 WITNESS VINSON:  Okay.  On page 2, line 9, the

8       sentence that begins, "In each case, the assignments

9       required," I want to strike the words "in each case" and

10       the comma, so that the sentence would begin with the

11       words "the assignments required."

12                 CHAIRMAN CARTER:  Okay.

13                 WITNESS VINSON:  That's the only change.

14       BY MR. YOUNG:

15            Q.   With that change, if I were to ask you the

16       same questions today as in your joint prefiled

17       testimony, would your answers be the same?

18            A.   (By Mr. Vinson)  Yes, they would.

19            A.   (By Mr. Fisher)  Yes, they would.

20                 MR. YOUNG:  Mr. Chairman, at this time, I ask

21       that the joint prefiled testimony of Mr. Carl Vinson and

22       Mr. Robert Lynn Fisher be entered into the record as

23       though read.

24                 CHAIRMAN CARTER:  The joint prefiled testimony

25       witnesses Vinson and Fisher will be entered into the

344

1       record as though read.

2                 MR. YOUNG:  Pardon me, sir?  Okay.

3       BY MR. YOUNG:

4            Q.   Did you have one exhibit attached to your

5       testimony as it relates to Progress Energy Florida,

6       which is the project management internal controls

7       relating to Progress Energy Florida's nuclear plant

8       uprate and construction projects?

9            A.   (By Mr. Fisher)  Yes.

10            A.   (By Mr. Vinson)  Yes.

11            Q.   Do you have any changes or correction to that

12       exhibit?

13            A.   (By Mr. Vinson)  No.

14                 MR. YOUNG:  And that Exhibit, Mr. Chairman, is

15       marked as VF-1 and is Number 19 on the comprehensive

16       exhibit list.

17                 CHAIRMAN CARTER:  Thank you.

18

19

20

21

22

23

24

25

350

1       BY MR. YOUNG:

2            Q.   Could you please summarize your testimony as

3       it relates to Progress Energy Florida, please?

4            A.   (By Mr. Vinson)  Yes.  Our testimony presents,

5       as we established, the audit report, which is a

6       management audit as distinguished from a financial

7       audit, our audit report on our review of the project

8       management internal controls that Progress Energy is

9       using in managing the Crystal River nuclear unit uprate

10       and then construction of the two new Levy County units.

11                 Our testimony also provides some comments on

12       the nuclear cost recovery process that the Commission is

13       using.

14                 MR. YOUNG:  With that, Mr. Chairman, we tender

15       Mr. Vinson and Mr. Fisher for cross.

16                 CHAIRMAN CARTER:  Thank you.  Ms. Triplett.

17                 MS. TRIPLETT:  No questions.

18                 CHAIRMAN CARTER:  Mr. Burgess.

19                 MR. BURGESS:  No questions.

20                 CHAIRMAN CARTER:  Mr. McWhirter.

21                 MR. McWHIRTER:  No, sir.

22                 CHAIRMAN CARTER:  Mr. Brew, you're recognized,

23       sir.

24                 MR. BREW:  Thank you.

25

351

1                           CROSS-EXAMINATION

2       BY MR. BREW:

3            Q.   Good afternoon, gentlemen.

4            A.   (By Mr. Vinson)  Good afternoon.

5            Q.   I would just like to talk for a minute about

6       your recommendations on page 5 of your testimony.  Do

7       you see it?

8            A.   Uh-huh.

9            Q.   And beginning at line 5, you say that you

10       believe that even more extensive and detailed

11       examinations of internal controls and project management

12       controls should be performed.  Do you see that?

13            A.   Yes.

14            Q.   Now, in making that recommendation, did you

15       take into account or -- let me strike that.  Are you

16       familiar with the requirements of the nuclear cost

17       recovery rule?

18            A.   Yes.

19            Q.   Okay.  And in making your recommendations

20       here, did you take into account the requirements of the

21       nuclear cost recovery rule?

22            A.   Yes.

23            Q.   Okay.  And would you agree with me that under

24       that rule, once the Commission has made a prudence

25       determination, that you can't subsequently go back and

352

1       relook at those costs; is that right?

2            A.   That is my understanding.

3            Q.   Okay.  And in your recommendations that begin

4       at line 11, for example, you say beginning at line 13,

5       "Internal audit results would serve to familiarize the

6       parties with the relevant project management issues that

7       arose during the preceding year."  Do you see that?

8            A.   Yes.

9            Q.   Would you agree that all active parties should

10       have an opportunity for -- an adequate opportunity to

11       review those materials?

12            A.   I'm sorry.  I missed part of your question.

13            Q.   Would you agree that all parties, as you've

14       referenced there, should have an adequate opportunity to

15       review those materials in order to make their

16       presentations in these dockets?

17            A.   Yes.

18            Q.   Okay.  Would you agree that the issues that

19       are presented there may be relatively complicated?

20            A.   Which issues are those?

21            Q.   Any.  Management controls, let's say.

22            A.   Yes.

23            Q.   Okay.  And would you agree that problems that

24       may be encountered there could lead to rate impacts that

25       could be significant?

353

1            A.   Problems encountered by?

2            Q.   In the project related to project controls,

3       costs, and schedule.

4            A.   Right.

5            Q.   Could lead to rate impacts that could be

6       significant?

7            A.   Yes.

8                 MR. BREW:  That's all I have.

9                 CHAIRMAN CARTER:  Thank you, Mr. Brew.

10                 Commissioners?  Commissioner Argenziano,

11       you're recognized.

12                 COMMISSIONER ARGENZIANO:  Thank you,

13       Mr. Chair.  I had some of the same questions, and they

14       were answered, so I'll just skip and move forward,

15       because if people are watching at home too, I'm really

16       trying to give them a little bit more information that

17       we have in front of us that they may not.

18                 And I guess -- and I don't want to put words

19       in your mouth, but in doing what you did for the reasons

20       that, obviously, I think were to help the Commission and

21       also to help protect the ratepayer, is that correct, to

22       make sure these reports are done with reasonable -- let

23       me see the words.  Reasonableness and adequacy of the

24       internal controls in place at the time; right?

25                 WITNESS VINSON:  Yes.

354

1                 COMMISSIONER ARGENZIANO:  Okay.  So that's

2       correct.  But now, since we've brought those

3       recommendations out and the things that you pointed out

4       in your testimony, let me ask you, what is it that you

5       will do in the future as we move forward to make sure

6       that these things have been put into place?

7                 WITNESS VINSON:  I take your question to mean

8       what will we do in --

9                 COMMISSIONER ARGENZIANO:  What would we do,

10       yes.

11                 WITNESS VINSON:  That hasn't been fully

12       decided at this point.  I assume that after this

13       proceeding is completed, staff will need to rethink what

14       is needed next year.  Of course, this lays a baseline

15       down.  We understand some of the basic controls and have

16       gotten some good, solid initial understanding.  There

17       may be a need in next year's proceeding and potentially

18       thereafter to revisit these issues and to update the

19       information we've presented, but that decision, as I

20       understand, has not been made yet.

21                 COMMISSIONER ARGENZIANO:  But -- can I

22       elaborate on that for my own self?

23                 CHAIRMAN CARTER:  Go ahead.

24                 COMMISSIONER ARGENZIANO:  If you've indicated

25       that there needs to be -- let me see if I can put it in

355

1       your words.  "In addition to this testimony, each

2       company could provide an internal audit report

3       describing a complete review of the adequacy and

4       effectiveness of internal controls," and then going back

5       to line 13 on page 5, "Internal audit results will serve

6       to familiarize the parties with the relevant project

7       management issues that arose during the preceding year

8       and provide insight to how management corrected any

9       problems noted."

10                 So if we don't decide to do anything, how

11       would we know if management corrected the problems?  I

12       guess that's what I'm trying to get out to anybody or

13       even one person who may be watching from home.

14                 WITNESS VINSON:  Well, I believe the thoughts

15       that we were expressing here were that that needs to be

16       done.  Just a minute ago, I was specifically answering

17       would my work unit be doing it or would we be doing it

18       in the same way that we did.  That may very well be a

19       good course to pursue.

20                 If, as I suggested, the companies provide

21       additional information, that could perform part of the

22       function we performed.  But, yes, it definitely does

23       need to be done.  Just the actual mechanism and who does

24       that is to be decided.

25                 COMMISSIONER ARGENZIANO:  Okay.  Thank you.

356

1                 CHAIRMAN CARTER:  And the context of that is

2       that these audits are necessary and helpful for staff to

3       make a recommendation in terms what actions the

4       Commission should take further; correct?

5                 WITNESS VINSON:  Yes, that was the intent.

6                 CHAIRMAN CARTER:  Thank you.  Commissioner

7       Skop, you're recognized.

8                 COMMISSIONER SKOP:  Thank you, Mr. Chairman.

9       And to Commissioner Argenziano and Chairman Carter's

10       point, I just wanted to make sure that in your opinion,

11       staff's opinion, that based upon the report that was

12       prepared, that in staff's opinion, they feel that

13       adequate project management and internal controls are

14       currently in place to move forward.

15                 WITNESS VINSON:  Yes.

16                 COMMISSIONER SKOP:  Subject to further fine

17       tuning and monitoring and auditing.

18                 WITNESS VINSON:  Yes.

19                 COMMISSIONER SKOP:  All right.  Thank you.

20                 CHAIRMAN CARTER:  Thank you.  Anything further

21       from the bench?

22                 Staff?

23                 MR. YOUNG:  No redirect.

24                 CHAIRMAN CARTER:  Okay.  Then we have Exhibit

25       19.  Any objection?  Without objection, show it done.

357

1       Exhibit 19 moved into the record.  The witnesses may be

2       excused.

3                 (Exhibit Number 19 was admitted into the

4       record.)

5                 CHAIRMAN CARTER:  Call your next witness,

6       staff.  Wait a minute.  I think that's it for staff.

7                 MR. YOUNG:  Yes, Mr. Chairman.

8                 CHAIRMAN CARTER:  Is that correct?

9                 MR. YOUNG:  But Mr. Fisher and Mr. Vinson will

10       be back for FP&L.

11                 CHAIRMAN CARTER:  Well, don't leave the

12       building, guys.  I tried to get you out of here.

13                 Ms. Triplett, you're recognized.

14                 MS. TRIPLETT:  Thank you.  I misunderstood.

15       When I called Mr. Roderick to the stand, among all those

16       testimonies, I also included the rebuttal testimony, but

17       I could --

18                 CHAIRMAN CARTER:  Let me ask the parties.

19       Mr. -- I'm struggling here.  Mr. Burgess, on rebuttal

20       for Mr. Roderick, Ms. Triplett said that she had

21       presented both his direct and rebuttal at that time.

22                 MR. BURGESS:  We had no questions, and we

23       would have no questions if he came back up exclusively

24       for rebuttal.

25                 MR. McWHIRTER:  No questions.

358

1                 MR. BREW:  No questions.

2                 CHAIRMAN CARTER:  Staff?

3                 MR. YOUNG:  No questions.

4                 CHAIRMAN CARTER:  Commissioners, anything

5       further for witness Roderick?

6                 Thank you.

7                 MS. TRIPLETT:  Thank you.

8                 CHAIRMAN CARTER:  You may call your next

9       witness.

10                 MS. TRIPLETT:  I don't think there's anyone

11       else.

12                 CHAIRMAN CARTER:  You don't have anybody left;

13       right?

14                 MS. BENNETT:  We do have -- Mr. Chairman,

15       Mr. Garrett, I don't know if -- he had rebuttal

16       testimony.  You may have moved that in at the same time.

17                 MS. TRIPLETT:  No, I did not.

18                 CHAIRMAN CARTER:  Okay.  Well, let's do that,

19       then.

20                 MS. TRIPLETT:  Thank you, Ms. Bennett.  At

21       this time, we would ask for the rebuttal testimony of

22       Mr. Will Garrett to be read into record as though --

23       inserted into the record as though read.  He did not

24       have any exhibits.

25                 CHAIRMAN CARTER:  The testimony of the witness

359

1       will be entered into the record as though read, and no

2       exhibits.  Okay.  And this witness was excused?

3                 MS. TRIPLETT:  Yes, sir.

4

5

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

367

1                 CHAIRMAN CARTER:  Okay.  Thank you.

2       Ms. Bennett?

3                 MS. BENNETT:  I believe that concludes the

4       case of Progress Energy Florida, and we would be ready

5       to begin with Florida Power & Light when the Commission

6       is ready to do so.

7                 CHAIRMAN CARTER:  Let's do this.  Let's

8       give --

9                 COMMISSIONER EDGAR:  Can we take a break?

10                 CHAIRMAN CARTER:  Oh, one second.

11       Commissioner Edgar.

12                 COMMISSIONER EDGAR:  I'm sorry, Mr. Chairman.

13       This moved a little quicker than I was expecting, and I

14       left some of my documents for the FPL case up in my

15       office.  Would it possible to take a five-minute break

16       before we move into the next --

17                 CHAIRMAN CARTER:  Yes.  We're going to need --

18       staff is going to need to change out too, so let's make

19       it -- let's come back at 20 of by this clock to my

20       right.  That's this one over here.  They're not exactly

21       on the same time.  That way, we'll give staff time to

22       change out, give the court reporter a break, and give

23       the parties an opportunity to change.

24                 Thank you.  We are adjourned on the Progress

25       Energy case.

368

1                 (Short recess.)

2                 (Transcript continues in sequence in

3       Volume 3.)

4

5

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

369

1                        CERTIFICATE OF REPORTER

2

3       STATE OF FLORIDA:

4       COUNTY OF LEON:

5                  I, MARY ALLEN NEEL, Registered Professional

6       Reporter, do hereby certify that the foregoing

7       proceedings were taken before me at the time and place

8       therein designated; that my shorthand notes were

9       thereafter translated under my supervision; and the

10       foregoing pages numbered 167 through 368 are a true and

11       correct record of the aforesaid proceedings.

12                 I FURTHER CERTIFY that I am not a relative,

13       employee, attorney or counsel of any of the parties, nor

14       relative or employee of such attorney or counsel, or

15       financially interested in the foregoing action.

16                 DATED THIS 12th day of September, 2008.

17

18

____________________________

19                                 MARY ALLEN NEEL, RPR, FPR

2894-A Remington Green Lane

20                                 Tallahassee, Florida  32308

(850) 878-2221

21

22

23

24

25