370

1                              BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

DOCKET NO. 080009-EI

3

In the Matter of:

4

NUCLEAR COST RECOVERY CLAUSE.

5       _____________________________/

6

VOLUME 3

7

Pages 370 through 612

8

ELECTRONIC VERSIONS OF THIS TRANSCRIPT ARE

9                  A CONVENIENCE COPY ONLY AND ARE NOT

THE OFFICIAL TRANSCRIPT OF THE HEARING.

10             THE .PDF VERSION INCLUDES PREFILED TESTIMONY.

11

12       PROCEEDINGS:           HEARING

13

BEFORE:                CHAIRMAN MATTHEW M. CARTER, II

14                              COMMISSIONER LISA POLAK EDGAR

COMMISSIONER KATRINA J. McMURRIAN

15                              COMMISSIONER NANCY ARGENZIANO

COMMISSIONER NATHAN A. SKOP

16

17       DATE:                  Thursday, September 11, 2008

18

TIME:                  Commenced at 9:30 p.m.

19                              Concluded at 5:20 p.m.

20

PLACE:                 Betty Easley Conference Center

21                              Room 148

4075 Esplanade Way

22                              Tallahassee, Florida

23

REPORTED BY:           MARY ALLEN NEEL, RPR, FPR

24

25       APPEARANCES:           (As heretofore noted.)

371

1                               I N D E X

2                               WITNESSES

3

NAME                                                PAGE

4

KIM OUSDAHL

5

Direct Examination by Mr. Anderson                   388

6       Prefiled Direct Testimony Inserted                   391

7       WILLIAM P. LABBE, JR.

8       Direct Examination by Mr. Anderson                   420

Prefiled Direct Testimony Inserted                   423

9

STEVEN D. SCROGGS

10

Direct Examination by Mr. Anderson                   449

11       Prefiled Direct Testimony Inserted                   452

12       STEVEN R. SIM

13       Direct Examination by Mr. Anderson                   493

Prefiled Direct Examination Inserted                 495

14       Cross-Examination by Mr. McWhirter                   512

15       JOHN J. REED

16       Direct Examination by Mr. Anderson                   515

Prefiled Direct Testimony Inserted                   518

17       Cross-Examination by Mr. McWhirter                   560

18       WILLIAM R. JACOBS, JR., PH.D.

19       Direct Examination by Mr. McGlothlin                 565

Cross-Examination by Mr. Anderson                    570

20       Redirect Examination by Mr. McGlothlin               600

Recross-Examination by Mr. Anderson                  610

21

CERTIFICATE OF REPORTER                              612

22

23

24

25

372

1                               I N D E X

2                               EXHIBITS

3       NUMBER                                     ID.    ADMTD.

4       20   STH-1                                           419

5       21   STH-2                                           419

6       22   SDS-1                                           419

7       23   SDS-2                                           419

8       24   SDS-3                                           492

9       25   SDS-4                                           492

10       26   JJR-1                                           563

11       27   JJR-2                                           563

12       28   WRJ-1                                           611

13       29   WRJ-2                                           611

14       30   WRJ-3                                           611

15       31   WRJ-4                                           611

16       32   WRJ-5                                           611

17       33   WRJ-6                                           611

18       34   WRJ-7                                           611

19       35   WRJ-8                                           611

20       43   Ousdahl Errata Sheet                    389     420

21

22

23

24

25

373

1                          P R O C E E D I N G S

2                 (Transcript follows in sequence from

3       Volume 2.)

4                 CHAIRMAN CARTER:  We are on the record.  We'll

5       call this hearing to order, and we'll start at the

6       beginning.  We've already had the staff read the notice,

7       and you read the notice for both cases when you did

8       that; correct?

9                 MS. BENNETT:  Yes, Chairman.

10                 CHAIRMAN CARTER:  And we've completed phase 1,

11       so as we go to part 2 of our case -- let me get my notes

12       here.  We'll begin -- I think we've done everything up

13       to the opening statements for this case; is that

14       correct?

15                 MS. BENNETT:  That's correct.  We would be

16       hearing opening statements from FPL and the other

17       parties.

18                 CHAIRMAN CARTER:  Okay.  Well, let's get

19       going.

20                 Mr. Anderson, you're recognized, sir.

21                 MR. ANDERSON:  Before we begin, we have two

22       more witnesses who could be sworn if you want to do

23       that, if that streamlines things.

24                 CHAIRMAN CARTER:  Brilliant.  Outstanding.

25       Will the witnesses please stand.

374

1                 I only see one.

2                 MR. ANDERSON:  Okay.  Did everybody else --

3                 CHAIRMAN CARTER:  Have we lost one?

4                 MR. ANDERSON:  We're good.

5                 (Witness sworn.)

6                 CHAIRMAN CARTER:  Mr. Anderson, you're

7       recognized.

8                 MR. ANDERSON:  Thank you, Chairman Carter.

9                 Good afternoon, Chairman and Commissioners.

10       FPL appreciates the opportunity to appear before you

11       today in this first nuclear cost recovery rule

12       proceeding for FPL's Turkey Point 6 and 7 and nuclear

13       uprate projects.

14                 Let's recall the scope and expected benefits

15       of those projects for FPL's customers.  FPL's Turkey

16       Point 6 and 7 project is expected to provide two new

17       nuclear generating units on existing company property.

18       These units will provide large amounts of base load

19       generation with zero greenhouse gas emissions without

20       using fossil fuel.  FPL expects that the project will

21       save customers more than $1 billion per year in fuel

22       costs when the units are in operation.

23                 FPL's updated feasibility analyses, which are

24       before you today -- Dr. Sim will tell you about those --

25       confirm these or even greater economic benefits for

375

1       FPL's customers, and improved benefits for from the

2       uprates as well.  FPL's director of this project, Steve

3       Scroggs, is here today, and he's here to answer your

4       questions about any aspect of the Turkey Point 6 and 7

5       project.

6                 Let's think about the uprate projects for a

7       moment.  Those projects will add more than 400 megawatts

8       of new nuclear capacity to existing units.  They'll come

9       online in 2011 and 2012.  They're going to deliver

10       round-the-clock, zero-emission capacity and energy,

11       again without using fossil fuel.  These uprates will

12       also provide major fuel cost savings for customers, and

13       the updated economics show at least another $100 million

14       cumulative present value revenue requirement benefit to

15       customers in the update before you today.  We have the

16       director of FPL's uprate projects, Bill Labbe, here to

17       answer any questions you have about the project.

18                 With the projects in mind, let's focus on the

19       issues before us for consideration.  These projects are

20       structured like other clause proceedings, in the sense

21       that prior year actuals get filed in March, current year

22       actual/estimated and projected costs in May.

23                 For Turkey Point 6 and 7, of course, all of us

24       were working together on the need determination case,

25       and the order didn't come out until March.  That's why

376

1       the first Turkey Point 6 and 7 filings were in May and

2       why we're really in the position of reasonableness

3       determinations for the new nuclear plants, which is

4       different than uprates, because you approved those last

5       December.  The order came out in January.  You've got

6       the March filing with 2007 actuals.  You've got the

7       2008-2009 projections of things.  So this case is ripe

8       for a prudence determination for the 2007 uprate costs.

9                 I would like to call the Commission's

10       attention to a recent change to our 2008

11       actual/estimated costs.  It's set forth in the revised

12       prehearing order now.  It will be explained by FPL's

13       director of the Turkey Point 6 and 7 project,

14       Mr. Scroggs, also mentioned by our controller, Kim

15       Ousdahl.

16                 FPL follows a very deliberate, step-by-step

17       approach to project development and risk management.

18       The company recently determined that at this time, it's

19       not necessary to incur certain long lead procurement

20       costs during the fourth quarter of 2008.  FPL has

21       therefore reduced its 2008 actual/estimated costs and

22       decreased by 14 percent the total amount sought by FPL

23       for 2009 recovery.  This amounts to a 35 million nominal

24       reduction.  When carrying costs are added in, it reduces

25       the amount requested from about 258 million to about

377

1       221 million.

2                 Turning to the uprate projects, in this case,

3       FPL is seeking a prudence determination concerning its

4       approximate $8.6 million in 2007 actual costs.  About

5       8.2 million of that is FPSC jurisdictional.  We're also

6       seeking reasonableness determinations for '08 and '09

7       costs for this, and the new nuclear plants, of course,

8       as well.

9                 I want to talk a little bit about where that

10       uprate work went and what those dollars were spent for

11       in looking forward to providing service to our

12       customers.  In 2007, FPL focused on nuclear engineering

13       and design that must be performed in order to submit

14       these projects on schedule to the Nuclear Regulatory

15       Commission.  They have to do their safety review.  They

16       have to do their license amendments of our plant

17       licenses, and meeting this NRC filing is essential for

18       the company to be able to complete the uprates during

19       scheduled refueling outages.  Those are the slots we're

20       looking at down the road to do the work, not special

21       outages, regular scheduled outages at FPL's nuclear

22       stations during 2011 and 2012.

23                 You'll hear that the evidence in this case

24       shows that FPL hired uniquely qualified vendors for this

25       limited scope of engineering and design work in 2007.

378

1       OPC has submitted some criticisms that FPL entered into

2       these contracts without competitive bidding.

3                 To be clear, single and sole source contracts

4       are an important and useful tool for nuclear projects

5       and are expressly provided for under FPL's procurement

6       procedures.  For nuclear plant work, there are few

7       qualified vendors generally, sometimes only one

8       qualified vendor at all.  This is because not just any

9       company is qualified to do work on a nuclear plant.

10       It's especially true when we're speaking of nuclear

11       safety related work, such as fuel design, safety

12       analyses for reactor internals, that type of thing, all

13       of which was done during 2007 by these vendors.

14                 That said, FPL competitively bids work

15       wherever it reasonably can.  For the uprate projects,

16       the large majority of costs ultimately are expected to

17       be competitively bid, probably more than a billion

18       dollars of those costs.

19                 For the essential uprate nuclear steam supply

20       engineering and design work during 2007, you'll be

21       hearing about work done by Westinghouse Electric Company

22       and the Areva company.  These are some of the contracts

23       criticized by OPC.  You'll hear that these companies

24       were uniquely qualified to do this work.  Concerning

25       design information, it's design information which only

379

1       they own.  Only they have the right to use the design

2       information.  It's work they've successfully performed

3       before for FPL and others in the nuclear industry.

4                 By the same example, FPL's use of Shaw Stone &

5       Webster makes perfect sense as a good use of single or

6       sole source contracting.  Shaw Stone & Webster has

7       performed engineering and design and other work on 46

8       prior nuclear uprate projects in the United States,

9       including at FPL's plants.  This is a vendor we know

10       very well.  It's the right vendor selection at the right

11       price.  Our witnesses, Mr. Labbe and Mr. Reed, will

12       speak to these points.

13                 In addition, there are similar solid business

14       reasons for where we used single and sole source

15       contracting for Turkey Point 6 and 7.  Our witnesses,

16       Mr. Scroggs and Mr. Reed, will speak to those points.

17                 It's worth remembering that your Commission

18       staff spent a great deal of effort this year performing

19       detailed management audits which reviewed FPL's

20       management and accounting practices in place for Turkey

21       Point 6 and 7 and the uprate projects.  Among many other

22       positive findings, the staff audit found that FPL's

23       practices and procedures are reasonable and confirmed

24       that these practices were followed for the single and

25       sole source procurements.

380

1                 This proceeding provides the Commission, the

2       parties, and the public a window into FPL's uprate and

3       new nuclear projects.  It's a different way of doing

4       regulation a little bit.  A great deal of information

5       has been provided to staff and the parties.  FPL looks

6       forward to further enhancing public understanding and

7       Commission understanding and that of the parties about

8       these important projects.  Our goal is that the

9       Commission, the parties, and our customers have comfort

10       and confidence that these major projects undertaken to

11       provide clean, zero-emitting base load electric

12       generation for FPL customers are being managed in a

13       cost-effective and safe way.

14                 In conclusion, FPL requests that the

15       Commission's order in this proceeding enter prudence and

16       reasonableness findings, as stated in FPL's positions in

17       the prehearing order, and approve FPL's requested 2009

18       nuclear cost recovery.

19                 Thank you.

20                 CHAIRMAN CARTER:  Thank you, Mr. Anderson.

21       Mr. McWhirter?

22                 MR. McWHIRTER:  No comments, sir.

23                 CHAIRMAN CARTER:  Mr. Twomey.

24                 MR. TWOMEY:  No, sir.

25                 CHAIRMAN CARTER:  Mr. McGlothlin.

381

1                 MR. McGLOTHLIN:  Joe McGlothlin for the Office

2       of Public Counsel.

3                 Commissioners, as I was thinking about what

4       the Commission and the parties are about today, it

5       occurred to me that this proceeding probably satisfies

6       the definition of test case better than any other

7       proceeding in recent memory.  Consider that, like many

8       other cases that come before you, this case involves

9       requests by utilities for authority to collect hundreds

10       of millions of dollars from customers, and you certainly

11       have the traditional role of reviewing those requests

12       and making a decision.

13                 But this is also an instance in which we are

14       implementing the nuclear cost recovery rule for the

15       first time.  It's a proceeding in which the so-called

16       Nuclear Filing Requirements, the NFRs, are being tested

17       for adequacy for the first time.  And another novel

18       feature of this proceeding, soon to be no longer novel,

19       but it is in this case, is that you're called on to

20       review the beginnings of a nuclear project as opposed to

21       being called on to review a plant that's about to enter

22       commercial service.  All these aspects make this case

23       very different from most that come before you.

24                 In the evidence you're about to hear, you will

25       learn that our office has initiated issues and pursued

382

1       issues that are related to each of those aspects that I

2       enumerated.  With respect to money, we have identified

3       an issue that pertains to Florida Power & Company which

4       in our view does warrant consideration of an adjustment

5       to the company's request.  With respect to the

6       application of the new rule, we initiated and pursued

7       with parties our view as to the proper limits that

8       should be imposed on the application of the rule as it

9       relates to uprate projects so that non-uprate project

10       costs will not be borne through the cost recovery rule.

11                 With respect to the Nuclear Filing

12       Requirements, which have been the product of basically

13       an informal collaboration to this point, we have

14       recommended an addition to those requirements which will

15       enable the utilities to understand what's expected of

16       them next year and will give the Commission and parties

17       more information up front when we go through this

18       exercise in the next cycle.

19                 Our witness with respect to all these

20       contentions is Dr. William Jacobs.  As you heard, he

21       holds a Ph.D. in nuclear engineering and has worked on

22       projects at numerous nuclear power plants across the

23       country and across the globe.  He will testify on three

24       issues, and the first is common to both Progress Energy

25       and Florida Power & Light.  And you've heard something

383

1       about it before, but I think I will summarize it very

2       briefly here.

3                 Dr. Jacobs -- and it's also specific to uprate

4       projects.  Dr. Jacobs will testify that a utility should

5       be made to perform and show an analysis designed to

6       differentiate between those costs that are incurred and

7       are essential to an uprate project on the one hand and

8       those costs that do not qualify for the clause because

9       they are in the nature of operation and maintenance

10       costs that the utility would incur to maintain service

11       from its unit even in the absence of an uprate project.

12                 As it develops, we have learned that Florida

13       Power & Light Company and Progress Energy Corporation do

14       not disagree with our view of the scope of the rule, and

15       that has led to something of a workout that you've heard

16       about already with respect to the agreement to develop

17       an additional Nuclear Filing Requirement specific to the

18       type of analysis that will be required of the utilities

19       in the next cycle.

20                 Dr. Jacobs will also testify that while

21       Florida Power & Light Company's management processes

22       appropriately stress the desirability of competitive

23       bidding as the standard for choosing contractors, FPL

24       too often has awarded contracts without competitive

25       bidding and without sufficient justification.

384

1                 He will testify that FP&L has fallen short of

2       its own internal requirements that FPL first justify the

3       decision to forgo competitive bidding, and a related and

4       equally important requirement that in that instance, FPL

5       demonstrate that the costs of a contract entered into

6       without the benefit of competitive bids is reasonable in

7       amount.

8                 He will show that the justification memoranda

9       that serve as the basis for the decision to depart from

10       the otherwise applicable standard of competitive bidding

11       too often consists of standardized, perfunctory,

12       conclusory language instead of a rationale or an

13       analysis that is specific to the contract in question.

14                 He will testify that FPL's practice of

15       referring to past experience, and in the case of one

16       major contract, a "back of the envelope" type of

17       analysis, are insufficient to enable this Commission to

18       gauge that the costs of the single source and sole

19       source contracts that have been entered into to this

20       point are reasonable in amount.

21                 Dr. Jacobs will offer three suggestions, three

22       alternative regulatory actions designed to communicate

23       the Commission's insistence that FPL adhere to its own

24       standard of competitive bidding and demonstrate adequate

25       justification when it departs from that standard.

385

1                 First, he identifies a very large contract

2       related to one of the uprate projects and suggests that

3       the Commission use that large contract as a proxy for

4       the general shortcoming in terms of competitive bidding

5       and disallow a portion of the return on investment that

6       FPL is seeking with respect to the investments called

7       for in that contract.

8                 In order of decreasing severity, recognizing

9       that this is a test case and we're perhaps all of us

10       finding our way through this process, he suggests that

11       the Commission could withhold a portion of the revenue

12       requirements or carrying charges associated with that

13       contract and tell FPL that it cannot collect that

14       portion unless and until it is able to demonstrate the

15       reasonableness of the decision to enter a single source

16       contract in the next cycle.

17                 And the final alternative, if the Commission

18       declines to undertake a financial adjustment, would be,

19       at a minimum, to admonish Florida Power & Light Company

20       that the Commission expects the utility to adhere to its

21       practice of competitive bidding and to be prepared to

22       fully justify any departure from that standard in the

23       future.

24                 Thank you.

25                 CHAIRMAN CARTER:  Thank you, Mr. McGlothlin.

386

1                 Just procedurally, we did it in our other

2       case, and just to dot the I's and cross the T's, staff's

3       composite exhibit list is entered into the record

4       without objections.  I believe the other -- 41 and --

5       wait a minute.  Let me see.  Forty-one is -- we did 42

6       in the prior case, but 41, we need to add this to our

7       list.

8                 MS. BENNETT:  We've entered 41 into the record

9       previously.  We entered all of the exhibits, the

10       comprehensive exhibit list, the composite exhibits, and

11       FPL's composite exhibits.

12                 CHAIRMAN CARTER:  FPL's composite exhibit,

13       that's 41.  And, Mr. Anderson, at the appropriate time,

14       we can move to enter that into evidence.

15                 MR. TWOMEY:  Mr. Chairman.

16                 CHAIRMAN CARTER:  Hang on one second.  I'll

17       get right back to you.

18                 MR. TWOMEY:  Yes, sir.

19                 CHAIRMAN CARTER:  We did that already?  Did we

20       enter FPL's exhibit already?

21                 MS. BENNETT:  We did.  At the very beginning

22       of the proceeding, at the opening of the record, we

23       entered all of the composites in, a little bit fast.

24                 CHAIRMAN CARTER:  Well, let's re-enter, then.

25       Since we've already entered it, I know there's no

387

1       objection, so let's show it done for Exhibit 41, just to

2       dot the I's and cross all the T's.

3                 Mr. Twomey.

4                 MR. TWOMEY:  Mr. Chairman, thank you.  While I

5       didn't want to make a formal opening statement as I did

6       in the Progress case, I want to reiterate that AARP is

7       here supportive fully of the work of the Office of

8       Public Counsel, and to that end, as reflected in the

9       prehearing order, we have supported all their positions

10       on all issues.  Thank you.

11                 CHAIRMAN CARTER:  Thank you.  For the record,

12       AARP has adopted and supports the positions of OPC in

13       toto; correct?

14                 MR. TWOMEY:  Yes, sir.

15                 CHAIRMAN CARTER:  Thank you, sir.

16                 Okay.  Now, let's see here.  All preliminary

17       matters taken care of, staff?

18                 MS. BENNETT:  All that staff is aware of.

19                 CHAIRMAN CARTER:  Any more from the parties

20       before we begin?

21                 Mr. Anderson, you're recognized, sir.

22                 MR. ANDERSON:  Thank you, Chairman Carter.

23       FPL would call as its first witness its controller, Kim

24       Ousdahl.

25                 CHAIRMAN CARTER:  Kim Ousdahl.

388

1       Thereupon,

2                             KIM OUSDAHL

3       was called as a witness on behalf of Florida Power &

4       Light Company and, having been first duly sworn, was

5       examined and testified as follows:

6                          DIRECT EXAMINATION

7       BY MR. ANDERSON:

8            Q.   Good afternoon, Ms. Ousdahl.

9            A.   Good afternoon.

10            Q.   Have you been sworn?

11            A.   Yes, I have.

12            Q.   Would you tell us your name and business

13       address?

14            A.   My name is Kim Ousdahl.  My business address

15       is 700 Universe Boulevard, Juno Beach, Florida.

16            Q.   By whom are you employed, and in what

17       capacity?

18            A.   By Florida Power & Light Company as

19       controller.

20            Q.   Have you prepared and caused to be filed seven

21       pages of prefiled direct testimony in this proceeding on

22       March 3, 2008?

23            A.   I have.

24            Q.   Did you also prepare and cause to be filed 17

25       files of prefiled direct testimony on May 1, 2008?

389

1            A.   I have.

2            Q.   Did you submit an errata, I believe it was

3       yesterday, in relation to your testimony?

4            A.   I did.

5                 MR. ANDERSON:  Chairman Carter, I would note

6       that the copy of the errata is being distributed.  It

7       basically calls out each figure which would change in

8       her testimony, principally to implement this $35 million

9       reduction we've talked about.  There has also been one

10       other small financial adjustment between here and there,

11       but the main purpose was to implement the reduction that

12       we talked about.  And Ms. Ousdahl, of course, can answer

13       any --

14                 CHAIRMAN CARTER:  Do we need to admit this?

15       Let's mark it as 43.

16                 MR. ANDERSON:  Ms. Ousdahl -- I'm sorry.

17                 CHAIRMAN CARTER:  Excuse me, Ms. Ousdahl.  One

18       second here.  You want to call it the Ousdahl errata

19       sheet?

20                 MR. ANDERSON:  Yes, sir.

21                 CHAIRMAN CARTER:  Sounds nice that way.

22                 (Exhibit Number 43 was marked for

23       identification.)

24                 CHAIRMAN CARTER:  Okay.  You may proceed.

25       BY MR. ANDERSON:

390

1            Q.   Other than your errata, do you have any

2       changes or revisions to your prefiled direct testimony?

3            A.   I do not.

4            Q.   If I asked you the same questions contained in

5       your prefiled direct testimony with your errata, would

6       your answers be the same?

7            A.   They would.

8                 MR. ANDERSON:  Chairman Carter, FPL asks that

9       Ms. Ousdahl's prefiled direct testimony be inserted into

10       the record as though read.

11                 CHAIRMAN CARTER:  The prefiled testimony of

12       the witness will be inserted into the record as though

13       read.

14       BY MR. ANDERSON:

15            Q.   Are you co-sponsoring any exhibits to your

16       direct testimony?

17            A.   I am.

18            Q.   Are those portions of Exhibits STH-1, STH-2,

19       SDS-1, and SDS-2?

20            A.   They are.

21                 MR. ANDERSON:  Mr. Chairman, I would note

22       these exhibits have been premarked for identification in

23       staff's list as Numbers 20 through 23.

24

25

415

1       BY MR. ANDERSON:

2            Q.   Ms. Ousdahl, have you prepared a summary of

3       your testimony?

4            A.   I have.

5            Q.   Would you please provide your summary to the

6       Commission?

7            A.   Good afternoon Commissioners.  The purpose of

8       my testimony is to provide an overview of FPL's filing

9       and to demonstrate that it complies with the nuclear

10       power plant cost recovery rule and the related statute.

11       I present the Nuclear Filing Requirements, these

12       documents we call the NFRs that quantify the request for

13       the Commission determination as to the prudence and

14       reasonableness or our costs.

15                 Specifically, the company requests the

16       Commission find FPL's 2007 uprate costs were prudently

17       incurred and the revenue requirement related to the

18       total cost incurred and projected for new nuclear and

19       uprate projects of 220.5 million is reasonable and

20       eligible for recovery effective January 1, 2009, through

21       the capacity cost recovery clause.

22                 The Commission adopted the rule on March 20,

23       2007, to implement Section 366.93 of the Florida

24       Statutes enacted by the legislation specifically to

25       promote investments in nuclear power plants.  The

416

1       statute directed the Commission to establish these

2       alternative mechanisms for cost recovery with stepwise

3       periodic prudence determinations.  The rule provides

4       those mechanisms and the annual recovery of these costs

5       through the CCRC.

6                 FPL filed the final true-up schedules

7       containing the 2007 cost information for its uprate

8       project on March 3rd and is requesting the Commission

9       determine these costs to be prudently incurred.

10                 On May 1st, FPL filed its '08 and '09 NFRs for

11       the uprate project in Appendix I of the filing, its 2007

12       through 2009 NFRs for Turkey Point 6 and 7

13       pre-construction costs in Appendix II of the filing, and

14       its 2006 through 2009 NFRs for Turkey Point 6 and 7 site

15       selection in Appendix III.  We revised these NFRs on

16       August 6, 2008, to provide for a correction resulting in

17       a small reduction in the overall request.

18                 More recently, as we've discussed this morning

19       and as will be provided by FPL witness Scroggs, we

20       recalculated the revenue requirements for 2008 Turkey

21       Point 6 and 7 pre-construction costs to reflect this

22       reduction in the estimate required in that year, 2008,

23       of 35 million, which has resulted in a decrease to

24       revenue requirements of 37.9 million.

25                 In order to ensure reasonable and prudent

417

1       costs are properly incurred and reported for the uprate

2       and Turkey Point 6 and 7 projects, the company has

3       relied on its comprehensive and overlapping accounting

4       and business unit controls for incurring costs and

5       recording transactions.  The above-mentioned controls

6       are documented, assessed, audited, and tested on an

7       ongoing basis by both FPL's internal and external

8       auditors.

9                 FPL's internal audit department finalized its

10       initial audit of the uprate costs and controls, and for

11       the adjustments that were found, we've either committed

12       -- we've either made those or committed to making those

13       adjustments.  The summary finding in this first initial

14       audit is that the controls over the uprate project are

15       adequate.  The internal audit department is currently in

16       the process of conducting its audit, initial audit of

17       Turkey Point 6 and 7 costs and controls, and the company

18       will provide those results when finalized.

19                 In summary, we request that the Commission

20       confirm that our filing complies with the requirements

21       of the rule and the statute, determine that our '07

22       uprate costs were prudently incurred, and determine that

23       our revenue requirements related to costs incurred for

24       the Turkey Point 6 and 7 and uprate projects totaling

25       220.5 million are reasonable and eligible for recovery

418

1       effective January 1, 2009, through the CCRC.

2                 This concludes my summary.

3                 MR. ANDERSON:  Ms. Ousdahl is available for

4       cross-examination.

5                 CHAIRMAN CARTER:  Thank you.  Mr. McGlothlin.

6                 MR. McGLOTHLIN:  No questions.

7                 CHAIRMAN CARTER:  Mr. Twomey.

8                 MR. TWOMEY:  No, sir.

9                 CHAIRMAN CARTER:  Mr. --

10                 MR. McWHIRTER:  No questions.

11                 CHAIRMAN CARTER:  Very good.  You anticipated,

12       grasshopper.

13                 Any questions, staff?

14                 MR. YOUNG:  No questions, sir.

15                 CHAIRMAN CARTER:  From the bench?

16                 You wowed us.

17                 Okay.  Mr. Anderson?

18                 MR. ANDERSON:  FPL would call as its next

19       witness --

20                 CHAIRMAN CARTER:  Wait.

21                 MR. ANDERSON:  I'm sorry.

22                 CHAIRMAN CARTER:  Exhibits 20 --

23                 MR. ANDERSON:  These are co-sponsored

24       exhibits, and my thought was we could offer them now or

25       we could offer them after the other co-sponsors,

419

1       whatever your pleasure is.

2                 CHAIRMAN CARTER:  Efficiency is always

3       appreciated, so let's take care of them now.

4                 MR. ANDERSON:  Okay.  May I offer Exhibits 20,

5       21, 22, and 23 into evidence.

6                 CHAIRMAN CARTER:  Any objections?  Without

7       objection, show it done.  Exhibits 21, 22, and 23, and

8       24 -- 20, 21, 22, and 23.

9                 MS. BENNETT:  That's correct.

10                 CHAIRMAN CARTER:  Okay.  Show it done.

11                 (Exhibit Numbers 20, 21, 22, and 23 were

12       admitted into the record.)

13                 CHAIRMAN CARTER:  Mr. Anderson.

14                 MR. ANDERSON:  Thank you.  FPL would call as

15       its next witness Mr. Bill Labbe.  And may Ms. Ousdahl be

16       excused?

17                 CHAIRMAN CARTER:  Let me look at the list.

18       Absolutely.

19                 MR. ANDERSON:  Thank you.

20                 CHAIRMAN CARTER:  Stay dry.

21                 MR. ANDERSON:  Could we also show the errata

22       admitted evidence?

23                 CHAIRMAN CARTER:  That would be Exhibit 43, if

24       my memory serves me correctly.

25                 MR. ANDERSON:  That's right.

420

1                 CHAIRMAN CARTER:  Without objection, show it

2       done.

3                 MR. ANDERSON:  Thank you.

4                 (Exhibit Number 43 was admitted into the

5       record.)

6                 CHAIRMAN CARTER:  Give me one second to get my

7       notes together here.

8                 Witness Labbe.  You may proceed.

9                 MR. ANDERSON:  Thank you.

10       Thereupon,

11                        WILLIAM P. LABBE, JR.

12       was called as a witness on behalf of Florida Power &

13       Light Company and, having been first duly sworn, was

14       examined and testified as follows:

15                          DIRECT EXAMINATION

16       BY MR. ANDERSON:

17            Q.   Good afternoon, Mr. Labbe.

18            A.   Good afternoon.

19            Q.   Have you been sworn?

20            A.   Yes, I have.

21            Q.   Would you tell us your full name and business

22       address?

23            A.   Bill Labbe, 700 Universe Boulevard, Juno

24       Beach, Florida.

25            Q.   By whom are you employed, and in what

421

1       capacity?

2            A.   Florida Power & Light Company, Director of EPU

3       Projects.

4            Q.   And when you say EPU, what does that mean?

5            A.   Extended power uprate.

6            Q.   Thanks.  Have you adopted the prefiled

7       testimony of Mr. Hale, one of your colleagues in the

8       Nuclear Division?

9            A.   Yes, I have.

10            Q.   And that consisted of a March 3rd filing and a

11       May 1 filing, ten pages and eight pages; is that right?

12            A.   That's correct.

13            Q.   Do you have any changes or revisions to that

14       prefiled direct testimony that you're adopting?

15            A.   No, I do not.

16            Q.   If I asked you the same questions contained in

17       your prefiled direct testimony, would your answers be

18       the same?

19            A.   Yes, they would.

20                 MR. ANDERSON:  FPL asks that the prefiled

21       direct testimony be inserted into the record as though

22       read.

23                 CHAIRMAN CARTER:  The prefiled testimony will

24       be entered into the record as though read.

25       BY MR. ANDERSON:

422

1            Q.   Are you also sponsoring or co-sponsoring any

2       exhibits to your direct testimony?

3            A.   Not at this time.

4                 MR. ANDERSON:  Okay.  We've already admitted

5       into the record 20, 21, and those things.

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

441

1       BY MR. ANDERSON:

2            Q.   Have you prepared a summary of your testimony,

3       Mr. Labbe?

4            A.   Yes, I have.

5            Q.   Would you please provide your summary to the

6       Commission?

7            A.   Good afternoon, Chairman Carter and

8       Commissioners.  My name is Bill Labbe.  I'm responsible

9       for leading FPL's nuclear power plant uprate.  Our team

10       is safely and cost-effectively implementing the major

11       power plant uprates at FPL's St. Lucie and Turkey Point

12       nuclear plants.

13                 When complete, the uprates will provide FPL's

14       customers more than 400 megawatts of additional clean,

15       zero-emission electric generation without expanding the

16       footprint of these existing plants.  FPL requests that

17       the Commission find the 2007 actual costs for the uprate

18       projects totaling about 8.6 million be found prudent,

19       and the FPSC jurisdictional amount of these, which total

20       about 8.2 million, are prudent.  FPL requests that the

21       Commission find that the 2008 actual/estimated and 2009

22       projected uprate costs are reasonable.

23                 Let me describe the 2007 work that resulted in

24       the 2007 costs.  FPL's 2007 work focused on nuclear

25       engineering and design supporting all four uprate

442

1       projects.  This engineering and design work had to be

2       performed in 2007 in order for FPL to stay on schedule

3       and submit each project to the Nuclear Regulatory

4       Commission for safety reviews and nuclear plant license

5       amendments.  These NRC reviews and amendments must occur

6       well in advance of the nuclear unit outages, during

7       which uprate component installation and plant

8       modifications will be performed.

9                 Other 2007 costs include reservation payments

10       for long lead procurement of specially designed and

11       manufactured plant equipment, such as unique turbine

12       rotors that must be delivered prior to the planned

13       outages during which this equipment will be installed.

14                 As described in my testimony, a substantial

15       portion of FPL's 2007 actual costs are for procurement

16       of goods and services for several uniquely well

17       qualified vendors that FPL had entered into single and

18       sole source contracts at a reasonable cost and in

19       compliance with FPL's policies and procedures.  Detailed

20       reasons for these procurements are in my testimony and

21       FPL's procurement documentation.

22                 Retaining these vendors was the right decision

23       and in the best interests of the customers.  For

24       example, 5.6 million of FPL's 2007 total costs was for

25       engineering and design work from Westinghouse.  FPL

443

1       selected Westinghouse to perform initial engineering and

2       design work related to the nuclear steam supply system

3       because Westinghouse is the original equipment

4       manufacturer that designed and made those systems which

5       are unique, proprietary, and safety related.

6                 In addition to Westinghouse having access to

7       its own proprietary engineering and design information,

8       FPL had successful uprate experience with Westinghouse,

9       and the costs were benchmarked by FPL to be found

10       reasonable.  As can be seen from my testimony, in FPL's

11       procurement documentation, FPL has similar compelling

12       reasons for contracting with Areva, Shaw Stone &

13       Webster, and Siemens, together with Westinghouse, to

14       make up the bulk of 2007 actual uprate costs.

15                 Let me provide some additional information

16       concerning the business processes underlying all the

17       uprate costs and information provided in this proceeding

18       which supports the prudence of FPL's costs and

19       reasonableness of these projections.  At this point in

20       the process, FPL has identified with a high degree of

21       certainty each component that needs to be procured and

22       installed and each process that needs to be followed in

23       order to successfully each uprate of the four nuclear

24       units.  Only the work needed to increase the uprate of

25       each unit is included in the project scope and the costs

444

1       presented by it FPL.

2                 All of FPL's 2007 uprate work was performed

3       and the costs incurred using FPL's well-established,

4       highly effective project management system.  FPL's

5       project management system is implemented through a

6       series of nuclear policies and procedures that govern

7       our business practice.  The effectiveness of the system

8       has been demonstrated through successful completion of

9       major projects at FPL's nuclear plants.

10                 All of FPL's planning and budgeting for 2008

11       actual uprate costs and 2009 projected were conducted

12       under the requirements of FPL's project management

13       system, which were audited in detail by your staff this

14       year.  In short, FPL has the right scope being

15       implemented with the right resources and the right

16       sequence of time.

17                 In addition, the personnel assigned to key

18       positions of the uprate project have a proven track

19       record of success managing large projects, including NRC

20       license renewal for the St. Lucie and Turkey Point and

21       uprate project at FPL Energy's Seabrook Station.  These

22       projects were completed on schedule and under budget.

23                 This concludes my summary.

24                 MR. ANDERSON:  Mr. Labbe is available for

25       cross-examination.

445

1                 CHAIRMAN CARTER:  Thank you.  Mr. McGlothlin.

2                 MR. McGLOTHLIN:  I need some clarification

3       from counsel.  Is Mr. Labbe here only on direct and only

4       on Mr. Hale, or is he being offered on rebuttal as well?

5                 MR. ANDERSON:  This is the two pieces of

6       direct.  Mr. Labbe will return after Dr. Jacobs

7       testifies on rebuttal.

8                 MR. McGLOTHLIN:  I'll reserve my questions

9       until he returns on rebuttal.

10                 CHAIRMAN CARTER:  Okay.  Thank you.

11                 Mr. Twomey.

12                 MR. TWOMEY:  No, sir.

13                 CHAIRMAN CARTER:  Mr. McWhirter.

14                 MR. McWHIRTER:  No questions.

15                 CHAIRMAN CARTER:  Staff.

16                 MR. YOUNG:  No questions.

17                 CHAIRMAN CARTER:  Commissioner Edgar, you're

18       recognized.

19                 COMMISSIONER EDGAR:  Thank you.  I would like

20       to ask you just a couple of questions about the issue of

21       the sole source for the uprates.  Can you describe

22       briefly for me what steps FPL has taken to ensure that

23       those sole source contracts are cost-effective or lowest

24       cost?

25                 THE WITNESS:  Certainly.  Those contracts were

446

1       entered into with the engineering firms and those

2       companies to do the engineering analysis work for the

3       license amendment, and that information, that

4       engineering analysis is proprietary information with

5       those companies.  We have done previous uprates.  We

6       have experience at St. Lucie and Turkey Point and our

7       FPL Energy units.  And we looked at -- we understand the

8       scope of the work.  We understand the appropriate

9       billing rates that that work has required, and we can do

10       an internal comparison of those costs as it relates to

11       the analysis that needs to be performed.

12                 COMMISSIONER EDGAR:  And when you say that

13       some of that is proprietary to those companies, does

14       that mean that it's your understanding, or I guess my

15       understanding, that there aren't other vendors out there

16       that have that same skill set or knowledge?

17                 THE WITNESS:  They may have that same skill

18       set, but they wouldn't have that knowledge.  That

19       information is proprietary to the company.

20                 COMMISSIONER EDGAR:  Give me just a second to

21       think here.

22                 So when you say that FPL has done other

23       uprates, have the similar necessary steps been done

24       through sole source for those previous uprates, or were

25       they put out for bid?

447

1                 THE WITNESS:  That is correct.  It was done

2       under sole source.

3                 COMMISSIONER EDGAR:  They were done under sole

4       source as well?

5                 THE WITNESS:  Yes.

6                 COMMISSIONER EDGAR:  Okay.  Thank you.

7                 CHAIRMAN CARTER:  Commissioners, anything

8       further?  Commissioner Skop, you're recognized.

9                 COMMISSIONER SKOP:  Thank you, Mr. Chairman.

10       Just a quick question.  The original manufacturer of the

11       reactor that's being operated would be also

12       Westinghouse?

13                 THE WITNESS:  That's correct.  The st. Lucie

14       unit was originally Combustion Engineering, but that is

15       now owned by Westinghouse.

16                 COMMISSIONER SKOP:  Okay.  And with respect to

17       the turbine deck, the existing turbines at the St. Lucie

18       facility are also Westinghouse?

19                 THE WITNESS:  It's a Siemens.

20                 COMMISSIONER SKOP:  Siemens?  All right.

21                 And just briefly, I think Mr. Anderson

22       mentioned that in relation to some of the costs being

23       considered that some of the long lead materials FPL had

24       chosen not to go forward with at this time, through

25       ordering those.  Can you just briefly describe what

448

1       those long lead items would be?

2                 THE WITNESS:  I think the long lead items that

3       you're referring to are for the new units, Turkey Point

4       6 and 7.

5                 COMMISSIONER SKOP:  Okay.  I'll direct my

6       question to the appropriate witness, then.  Thank you.

7                 MR. ANDERSON:  That would be Mr. Scroggs,

8       Commissioner.

9                 COMMISSIONER SKOP:  Thank you.

10                 CHAIRMAN CARTER:  Thank you.  Commissioners,

11       anything further?  Thank you.  I think we've already

12       entered the exhibits for this witness.

13                 MR. ANDERSON:  Yes, sir, we have.

14                 CHAIRMAN CARTER:  And he'll be back on

15       rebuttal.

16                 MR. ANDERSON:  Yes.

17                 CHAIRMAN CARTER:  Okay.  Thank you, sir.

18                 Mr. Anderson.

19                 MR. ANDERSON:  FPL would call Steven Scroggs

20       as its next witness, please.

21                 CHAIRMAN CARTER:  Steven Scroggs.

22       Thereupon,

23                          STEVEN D. SCROGGS

24       was called as a witness on behalf of Florida Power &

25       Light Company and, having been first duly sworn, was

449

1       examined and testified as follows:

2                          DIRECT EXAMINATION

3       BY MR. ANDERSON:

4            Q.   Good afternoon, Mr. Scroggs.

5            A.   Good afternoon.

6            Q.   Have you been sworn?

7            A.   Yes, I have.

8            Q.   Please tell us your name and business address.

9            A.   My name is Steven Scroggs.  My business

10       address is 700 Universe Boulevard, Juno Beach, Florida.

11            Q.   By whom are you employed, and in what

12       capacity?

13            A.   I'm employed by Florida Power & Light Company

14       as the Director of New Nuclear Development.

15            Q.   Have you prepared 30 pages of prefiled direct

16       testimony in this proceeding?

17            A.   Yes, I have.

18            Q.   Do you have any changes, revisions, additions,

19       or deletions to your prefiled direct testimony?

20            A.   Yes, I do.

21            Q.   Would you please provide that at this time?

22            A.   Yes.  On page 23 at line 16, please insert the

23       following additional testimony:  "As a result of recent

24       developments, FPL is able to lower its 2008

25       actual/estimated pre-construction expenditure, reducing

450

1       the overall recovery request in this docket by

2       approximately 14 percent.  Based on the most current

3       market information available, FPL has determined that it

4       will not be necessary to make the identified long lead

5       purchases during 2008 and that they can be deferred to

6       2010 or beyond.  While the market for nuclear equipment

7       remains dynamic and negotiations with vendors are not

8       complete, FPL does have sufficient information to make a

9       singular adjustment in its 2008 actual/estimated

10       pre-construction costs.  The revision results in

11       eliminating a long lead procurement line item from the

12       October, November, and December 2008 estimate, more

13       specifically, the entries in the 2008 pre-construction

14       cost Schedule AE-6 at line 6, columns K, L, and M.  This

15       revision reduces to total requested recovery amount in

16       this proceeding from 258 million to approximately

17       221 million."

18            Q.   Any other changes or additions to your

19       testimony?

20            A.   No, sir.

21            Q.   If you were to be asked the same questions,

22       would your answers be the same today with the addition

23       that you just provided us?

24            A.   Yes, sir.

25                 MR. ANDERSON:  FPL would ask that Mr. Scroggs'

451

1       testimony be admitted into the record as though read.

2                 CHAIRMAN CARTER:  The testimony of the witness

3       will be entered into the record as though read.

4       BY MR. ANDERSON:

5            Q.   Are you also sponsoring some exhibits to your

6       direct testimony?

7            A.   Yes.

8            Q.   Those are Exhibits SDS-1 and SDS-2, as well as

9       SDS-3 and SDS-4.  These have been premarked as 22, 23,

10       24, and 25.  I would note that 24 and 25 have not been

11       moved.

12            A.   That's correct.

13

14

15

16

17

18

19

20

21

22

23

24

25

482

1       BY MR. ANDERSON:

2            Q.   Have you prepared a summary of your direct

3       testimony?

4            A.   I do.

5            Q.   Would you please provide your summary to the

6       Commission?

7            A.   Thank you.  Mr. Chairman and Commissioners, I

8       appreciate the opportunity to come before you today.

9                 The purpose of my testimony is to provide an

10       understanding of how the Turkey Point 6 and 7 project is

11       being developed, managed, and controlled to meet the

12       objective of delivering reliable, cost-effective, and

13       fuel-diverse generation to FPL customers.  My testimony

14       describes how project activities are being actively

15       managed in a deliberate, transparent, and stepwise

16       process crafted to manage project risk in the face of

17       challenges and uncertainties that are unique to new

18       nuclear deployment.

19                 My testimony lays out the approach taken by

20       FPL for managing the Turkey Point 6 and 7 project to

21       meet these objectives.  This includes monitoring

22       regulatory and commercial issues in the industry and

23       adapting the project plan as needed to maintain schedule

24       and manage risk.  Further, I describe the project

25       controls and risk management processes that the project

483

1       team uses, combine the adaptive management style and

2       proven project controls, provide a firm basis for the

3       responsible and prudent management of the project.

4                 The balance of my testimony then describes the

5       site selection costs incurred from April 2006 to October

6       16, 2007, and pre-construction costs that have been or

7       are estimated to be incurred in the period from

8       October 16, 2007, through December 31, 2009.  Moreover,

9       I discuss the rationale for these costs or projections

10       and how expenditures will be managed going forward to

11       meet the project objectives.

12                 This concludes my summary.

13                 MR. ANDERSON:  Mr. Scroggs is available for

14       cross-examination.

15                 CHAIRMAN CARTER:  Thank you.  Mr. McGlothlin.

16                 MR. McGLOTHLIN:  I'll reserve my questions for

17       the rebuttal phase.

18                 CHAIRMAN CARTER:  Mr. McWhirter.

19                 MR. McWHIRTER:  FIPUG has no questions,

20       Mr. Chairman.

21                 CHAIRMAN CARTER:  Staff?

22                 MS. BENNETT:  No questions.

23                 CHAIRMAN CARTER:  Commissioner Argenziano.

24                 COMMISSIONER ARGENZIANO:  Thank you,

25       Mr. Chairman.  And I'm not sure if it's more appropriate

484

1       to ask the next witness, and just feel free to tell me

2       if it is.

3                 Just out of curiosity, a couple of things.

4       Why is it not necessary to ask for the long lead

5       procurements now?  What was that change?  And if you

6       said it, I just didn't focus in on it.

7                 THE WITNESS:  It's kind of two factors.  One,

8       we're in the process of watching the market.  And

9       essentially, there's a small group of companies that can

10       produce these specific items in an advance time that

11       they're in time for our schedule.  We're watching our

12       schedule.  That hasn't changed.

13                 But the market, we were prepared for a market

14       that was very dynamic and where a lot of orders were

15       being placed.  There are several other similar AP1000

16       projects ahead of us, including the Progress Levy

17       project.  So we were watching the market, and we were

18       ready to respond to secure it if it were necessary.  The

19       market hasn't developed to be that dynamic, so that is

20       not going to be necessary in 2008.

21                 As we look into 2009, we'll be entering a

22       contract with Westinghouse/Shaw associated with the

23       engineering and procurement.  Some of those activities

24       will be incorporated in that contract.  The moneys that

25       we've already forecasted for that activity in 2009 seem

485

1       to be a sufficient amount to cover that right now.  So

2       again, we're able to cover with what we've already

3       budgeted and defer these costs until a later time in the

4       project.

5                 COMMISSIONER ARGENZIANO:  And part of that is

6       because you feel there are companies out there who can

7       meet the need when you get to them?

8                 THE WITNESS:  Yes.

9                 COMMISSIONER ARGENZIANO:  And you wouldn't

10       need that long a period of time, which, of course, then

11       would save the current customers money?

12                 THE WITNESS:  Yes, ma'am.

13                 COMMISSIONER ARGENZIANO:  Okay.  And what

14       makes it more cost-effective than previously thought to

15       build now?

16                 THE WITNESS:  Again, we haven't taken that

17       $35 million out of the project.  It has been deferred to

18       a later point in time in the project.  There will be

19       savings to the customer by not having to pay the

20       interest on that now.  They won't feel the effects of

21       that on their bill in the early years.  But that money,

22       again, hasn't gone away.  It hasn't changed our

23       assessment of cost.  It's just moved later.

24                 COMMISSIONER ARGENZIANO:  Moved to a later

25       date.  Okay.  Thank you very much.

486

1                 CHAIRMAN CARTER:  Thank you.  Commissioner

2       Skop.

3                 COMMISSIONER SKOP:  Thank you, Mr. Chairman.

4       I have to navigate around the caffeine here that's

5       blocking the button.

6                 Just a quick question with respect to the

7       witness's testimony.  On page 22 of the prefiled

8       testimony, I guess they discuss some of the long lead

9       procurement, and I guess it was my understanding, and I

10       just wanted to get some brief clarification.  With

11       respect to the long lead items and the reductions and

12       the magnitude of those reductions, at least on 22, it

13       seems that FPL has gone forward with the reservation or

14       is in the process of finalizing the reservation

15       agreement for the ultraheavy forgings with Japan Steel

16       Works that we previously addressed in the need

17       determination.  Would that be correct?

18                 THE WITNESS:  That's correct.  In fact, we

19       have entered into that agreement through Westinghouse

20       Corporation, and that money has been expended in the

21       project.

22                 COMMISSIONER SKOP:  Okay.  And I think on page

23       23, they address an additional amount of 35 million of

24       funds for long lead procurement, the reactor coolant

25       pump and some of the other containment vessel materials.

487

1       Can you just briefly explain which long lead items are

2       being deferred at this time and the magnitude of those

3       deferrals?

4                 THE WITNESS:  Yes, sir.  In the prefiled

5       testimony, page 23, lines 7 through 15, all the long

6       lead items involved in that paragraph make up the

7       $35 million that is being deferred to 2010 or beyond.

8                 COMMISSIONER SKOP:  Okay.  Thank you.  I guess

9       that matches up.  That would result -- that 35 million

10       would be the reduction from the 258 million down to the

11       221 million for long lead procurement.

12                 THE WITNESS:  Yes, sir.

13                 COMMISSIONER SKOP:  Thank you.

14                 CHAIRMAN CARTER:  Thank you.  Commissioner

15       Argenziano.

16                 COMMISSIONER ARGENZIANO:  Yes.  I forgot

17       something, Mr. Chair.  As I asked before with Progress,

18       is there a way you can break down for me by statutory

19       categories, you know, the costs, the site selection,

20       pre-construction, carrying charges?  Can you do that?

21                 THE WITNESS:  Yes, ma'am.

22                 COMMISSIONER ARGENZIANO:  Okay.  Great.

23                 THE WITNESS:  With the exception of carrying

24       charges, I'm afraid.

25                 COMMISSIONER ARGENZIANO:  Okay.

488

1                 THE WITNESS:  With respect to site selection

2       costs, those were costs that were incurred up to our

3       filing for need determination in October of last year.

4       Those costs were incurred in 2006 and 2007 and total

5       $6,424,121, again, without AFUDC.

6                 In the pre-construction, beginning in

7       October 2007, for the balance of 2007, we incurred

8       approximately $2,533,000 in pre-construction costs.  In

9       2008, we expect to incur approximately $70 million in

10       pre-construction costs.  And in 2009, we're projecting

11       $110 million in pre-construction costs, for a total of

12       182,500,000 pre-construction costs.

13                 COMMISSIONER ARGENZIANO:  Okay.  That's fine.

14       Thank you.

15                 CHAIRMAN CARTER:  Thank you.  Commissioner

16       Skop.

17                 COMMISSIONER SKOP:  Thank you, Mr. Chairman.

18       Just one final question.  Page 19 of the prefiled

19       testimony mentions that FPL is a member of the NuStart

20       Consortium and pays the annual membership fee.  Can you

21       briefly just further elaborate on the benefits of that

22       membership?  Is that a recoverable cost?  And then also

23       the expected benefit to the extent of lessons learned

24       that would mitigate the cost of membership if that is in

25       fact a recoverable cost.

489

1                 THE WITNESS:  Yes, sir.  The NuStart

2       Consortium, of course, is a group of industry --

3       potential owners of new nuclear plants as well as

4       vendors that are involved in the production, including

5       General Electric and Westinghouse Corporation.

6                 This group was formed essentially to provide a

7       private industry response or pairing with the federal

8       regulators to develop the combined operating license

9       process, to test it, and to help work the bugs out of

10       system.  Without this organization, no individual

11       utility would have taken on the task and considerable

12       effort to get to the point where we are today.

13                 So FPL's involvement in NuStart has been

14       extremely valuable for our customers to spread the cost

15       over multiple industry participants, to kick-start the

16       new nuclear deployment process in the United States.  So

17       that has really been the right thing for us to do, is to

18       be involved with a group of other interested potential

19       owners for power and to work together to solve these

20       early problems so that at the time that Progress and

21       ourselves submit our license application, a lot of these

22       bugs have already been worked out, a lot of the path has

23       been well paved, and everybody understands their roles

24       and responsibilities as we're going forward.

25                 So our participation in NuStart at present is

490

1       approximately a million dollars a year and has been a

2       real bargain in terms of allowing the national level

3       licensing and industry support to be ready and mature

4       enough to take on the challenges of new nuclear

5       deployment.

6                 COMMISSIONER SKOP:  Mr. Chairman, just two

7       follow-ups.

8                 So essentially, that should serve to

9       streamline the licensing process to avoid cost delays

10       resulting from -- to streamline the regulatory process

11       and avoid cost increases resulting from regulatory

12       delays in siting and permitting and licensing and all

13       the above?

14                 THE WITNESS:  Absolutely.  A good portion of

15       our combined operating license application will be

16       directly adopted from the Tennessee Valley Authority

17       Bellefonte application, which is determined to be the

18       reference application for this technology.  So in a

19       sense, we'll just be taking the sections out of their

20       application and adopting it in total.  It will be

21       something that the NRC has already seen and reviewed and

22       should greatly facilitate our process.

23                 COMMISSIONER SKOP:  So in a sense, it's like

24       bootstrapping based on lessons learned such that the

25       first one that's the straw horse, if you will, the next

491

1       one goes through smoother and assures a continual

2       approval process.

3                 THE WITNESS:  Absolutely.

4                 COMMISSIONER SKOP:  And also, too, in relation

5       to the consortium, at least from my knowledge, many

6       members of the consortium have picked the AP1000 as

7       their reactor, and certainly those that come online

8       sooner than later should be able to share their lessons

9       learned throughout the consortium to avoid any

10       additional increases and lessons learned.  Would that be

11       also correct?

12                 THE WITNESS:  That's correct.  In fact, maybe

13       not through the NuStart Consortium, but through a group

14       called the AP Owners Group that has been developed

15       specifically with an eye towards those pre-operational

16       and operational issues to share procedures, to share the

17       best practices in the company and the industry so that

18       everybody is operating from the same manual and

19       benefiting from the same streamlining.

20                 COMMISSIONER SKOP:  Thank you.

21                 CHAIRMAN CARTER:  Thank you, Commissioner.

22                 Commissioners, anything further from the

23       bench?

24                 Okay.  Hearing none, Mr. Anderson.

25                 MR. ANDERSON:  We have no questions for

492

1       Mr. Scroggs.

2                 CHAIRMAN CARTER:  Will Mr. Scroggs be coming

3       back for rebuttal?

4                 MR. ANDERSON:  Yes, sir, he will.  We would

5       like to offer his Exhibits 23 and 24.

6                 CHAIRMAN CARTER:  Exhibits 23 and 24.  I think

7       23 is in; right?

8                 MS. BENNETT:  It's 24 and 25.

9                 MR. ANDERSON:  Thank you.  My notes are wrong.

10       Twenty-four and 25.

11                 CHAIRMAN CARTER:  Twenty-four and 25, any

12       objections?  Without objection, show it done.

13                 (Exhibit Numbers 24 and 25 were admitted into

14       the record.)

15                 CHAIRMAN CARTER:  Call your next witness.

16                 MR. ANDERSON:  FPL would call as its next

17       witness Dr. Steven Sim.

18                 CHAIRMAN CARTER:  You're recognized.

19                 MR. ANDERSON:  Thank you.

20       Thereupon,

21                            STEVEN R. SIM

22       was called as a witness on behalf of Florida Power &

23       Light Company and, having been first duly sworn, was

24       examined and testified as follows:

25

493

1                          DIRECT EXAMINATION

2       BY MR. ANDERSON:

3            Q.   Good afternoon, Dr. Sim.

4            A.   Good afternoon.

5            Q.   Have you been sworn?

6            A.   Yes, I have.

7            Q.   Please state your name and business address.

8            A.   My name is Steve Sim.  My business address is

9       9250 West Flagler Street, Miami.

10            Q.   By whom are you employed, and in what

11       capacity?

12            A.   By Florida Power & Light Company as a senior

13       manager in the Integrated Resource Planning Group.

14            Q.   Have you prepared and caused to be filed 11

15       pages of prefiled direct testimony in this proceeding?

16            A.   Yes, I have.

17            Q.   Do you have any changes or revisions to your

18       prefiled direct testimony?

19            A.   No, I don't.

20            Q.   If I asked you the same questions contained in

21       your prefiled direct testimony, would your answers be

22       the same?

23            A.   Yes, they would.

24                 MR. ANDERSON:  FPL asks that Dr. Sim's

25       prefiled direct be inserted into the record as though

494

1       read.

2                 CHAIRMAN CARTER:  The prefiled testimony will

3       be adopted into the testimony as though read.

4       BY MR. ANDERSON:

5            Q.   I think you co-sponsored some exhibits already

6       in evidence, Numbers 21 and 22?

7            A.   Yes.

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

506

1       BY MR. ANDERSON:

2            Q.   Do you have a summary for the Commission?

3            A.   Yes, I do.

4            Q.   Would you please present your summary?

5            A.   Certainly.  Good afternoon, Chairman Carter

6       and Commissioners.  My testimony discusses the detailed

7       feasibility analysis conducted for FPL's nuclear uprates

8       and Turkey Point 6 and 7 projects and presents the

9       results of those analyses.

10                 First, in regard to the analytical approach

11       and the assumptions, let me start by going back to the

12       analytical approach that we used in the determination of

13       need filings for both projects.  Essentially, we looked

14       at one resource plan that had the nuclear capacity

15       addition in question versus one or more resource plans

16       that did not have the new nuclear capacity, and we

17       analyzed both resource plans in regard to nine different

18       scenarios of fuel cost forecasts and environmental

19       compliance cost forecasts.

20                 We utilized the same basic analytical approach

21       in the detailed feasibility analysis presented in this

22       docket.  However, there were a few changes in regard to

23       what I'll call tightening the scope of the analysis as

24       well as a few assumption changes.  In regard to

25       tightening the scope, one of those was in regard to the

507

1       Turkey Point 6 and 7 project.  We originally in the

2       determination of need filing had compared that to

3       competing combined cycle capacity as well as competing

4       integrated gasification combined cycle capacity.  In

5       that, the IGCC turned out to be a distant third in the

6       economic analysis, and for that reason, we chose not to

7       continue that comparison in the updated analysis that is

8       before you today.

9                 Also, in both the uprates and in the Turkey

10       Point 6 and 7, we chose in this analysis to focus solely

11       on the economics of the projects.  We felt that it was

12       clearly developed in the determination of need analyses

13       that both projects would supply significant increases in

14       fuel diversity, as well as result in significant

15       decreases in system emissions.

16                 In regard to the assumptions, there were a

17       number of assumption changes that were made this

18       go-round.  We updated the capital cost expenditure

19       schedules for both of the nuclear projects, and we also

20       used updated forecasts for fuel costs, environmental

21       compliance costs, load forecasts, the combined cycle

22       unit cost, and updated cost of debt and discount rate

23       values.

24                 Let me turn to the results of the analyses.

25       First let me tackle the nuclear uprates.  In the

508

1       determination of need filings, our results were that the

2       nuclear uprates were projected to have a significantly

3       lower cumulative present value of revenue requirements

4       costs in eight of the nine scenarios that we examined,

5       and in the one scenario in which it was not projected to

6       be the most economic option, that was in a scenario of

7       low gas costs and low environmental compliance costs,

8       which we felt was a fairly unlikely occurrence.

9                 In the updated analysis, we saw essentially

10       the same thing.  The uprates are still projected to be

11       the cost-effective addition in eight of the nine

12       scenarios.  However, the projected economics for the

13       nuclear uprates has improved in seven of those scenarios

14       to the tune of roughly 70 million to 300 million

15       cumulative present value revenue requirements of cost

16       savings for FPL's customers.  Therefore, for the

17       uprates, the economics have definitely improved in the

18       updated analysis.

19                 In regard to the Turkey Point 6 and 7 project,

20       in the determination of need filing, we had compared the

21       breakeven cost of new nuclear capacity to a nonbinding

22       cost range for new nuclear units of roughly $3,100 a kW

23       to $4,500 a kW in 2007 dollars.  And what we found is

24       that the projected breakeven costs for the new nuclear

25       units were above that cost range in eight of the nine

509

1       scenarios, and it was within that range in the ninth

2       scenario.

3                 In the updated analysis, what we see now is

4       that we have essentially the same result in terms of

5       higher breakeven costs in eight of the nine scenarios

6       and within the range in the ninth.  However, we see

7       improvement, significant improvement economically in all

8       nine scenarios for the new nuclear units, and the

9       breakeven costs have increased from a range from $900 a

10       kW to about $2,100 a kW in 2007 dollars.

11                 In conclusion, for both projects, the already

12       significant projected economic advantage of the nuclear

13       uprates and the projected breakeven costs for Turkey

14       Point 6 and 7 are even now more promising in the updated

15       analysis than in the need filings, and these results

16       fully support the feasibility of continuing both

17       projects.

18                 And that concludes my summary.

19                 MR. ANDERSON:  Dr. Sim is available for

20       cross-examination.

21                 CHAIRMAN CARTER:  Thank you.  Dr. Sim, you

22       said that the uprate saved how much?  And I'm going to

23       ask you the same on Turkey Point, too, in terms of your

24       projections.

25                 THE WITNESS:  In regard to the uprates, we saw

510

1       the economics had improved in seven of the nine

2       scenarios, and the range of that improvement in

3       cumulative present value of revenue requirements was

4       from 70 million to 300 million.

5                 CHAIRMAN CARTER:  Okay.

6                 THE WITNESS:  And in regard to Turkey Point 6

7       and 7, in regard to breakeven costs, the breakeven costs

8       increased in all nine scenarios, and that range was from

9       $900 a kW to $2,100 a kW in 2007 dollars.

10                 CHAIRMAN CARTER:  How much is that in American

11       money?

12                 THE WITNESS:  Well, to give you an example, a

13       brand new combined cycle would cost you approximate

14       $1,000 a kW.

15                 CHAIRMAN CARTER:  So $1,000 at --

16                 THE WITNESS:  It would depend upon the number

17       of kW you're --

18                 CHAIRMAN CARTER:  I don't have my solar

19       powered calculator.  Have you got a bottom line number

20       for me?  I think -- and I'm sure you were here today as

21       Commissioner Argenziano was asking questions that really

22       relate to the folks out there at home trying to -- they

23       don't know a kW from a megawatt, so I'm really just

24       trying to get a bottom line number.  That's all we're

25       really trying to find, so can you just kind of break it

511

1       down?  I do read Greek, but don't put it in Greek.  Just

2       put it in English for us today.

3                 THE WITNESS:  Yes, sir.  Perhaps the easiest

4       way to convert this is to look at this in terms of the

5       increase in the breakeven cost as if we were talking

6       about a combined cycle, since the Commission has seen

7       those most recently from FPL.  The $1,000 a kW is

8       roughly the cost of, say, the West County 3 unit and the

9       conversions that we had, and those were on the order of,

10       again, in very round numbers, about a billion dollars.

11                 CHAIRMAN CARTER:  Okay.  Thank you.  I know

12       that you're getting ready for cross-examination, but I

13       wanted to ask that, Commissioners, before I lost my

14       train of thought.

15                 Commissioner Skop.

16                 COMMISSIONER SKOP:  Thank, Mr. Chairman.  Just

17       one quick question with respect to the ongoing

18       feasibility analysis and studies that have been

19       conducted and the more beneficial economic advantage.

20       Was that analysis rerun in correlation to, you know, gas

21       has recently run up, and then over the last month or so,

22       the price of natural gas has kind of receded back to,

23       thank God, $7 per MMBtu, around there.  But I'm just

24       trying to get some perspective on the influence of gas

25       prices in terms of the numbers that you just presented.

512

1                 THE WITNESS:  Yes, sir.  The analysis used

2       assumptions that were virtually identical to those used

3       in the recent West County 3 and conversion filing, which

4       were looked into place in roughly the February-March

5       time frame.  So it would not reflect any changes in

6       assumptions that occurred since the filing for this

7       docket.

8                 COMMISSIONER SKOP:  Okay.  Thank you.

9                 CHAIRMAN CARTER:  Okay.  Commissioners,

10       anything further at this time?

11                 Mr. McGlothlin.

12                 MR. McGLOTHLIN:  No questions.

13                 CHAIRMAN CARTER:  Mr. Twomey.

14                 MR. TWOMEY:  No, sir.

15                 CHAIRMAN CARTER:  Mr. McWhirter.

16                           CROSS-EXAMINATION

17       BY MR. McWHIRTER:

18            Q.   You indicated that a combined cycle would cost

19       a thousand per kW.  My recollection of the need

20       proceeding was that this would cost -- the nuclear

21       plants would cost between 4,500 and 7,500 per kW.

22            A.   I'm sorry.  Could you rephrase or repeat the

23       question, please, sir?

24            Q.   What will be the cost of these nuclear plants

25       that you're building based on the kilowatt of capacity?

513

1            A.   I think it's safe to say that we don't know

2       with a great deal of accuracy at this point what the

3       units will cost.  For our original determination in the

4       need filing, we used a nonbinding capital cost estimate

5       of, in 2007 dollars, between roughly $3,100 a kW and

6       $4,500 a kW.

7            Q.   And if you compare the fixed costs of the

8       capacity to the fixed costs of the combined cycle, it

9       sounds like the nuclear plant costs considerably more

10       than a combined cycle.  Can you explain why it is that

11       these savings come into play in your economic analysis?

12            A.   Yes, sir.  Commissioner, as we indicated in

13       the determination of need filing for Turkey Point 6 and

14       7, and I believe as Mr. Anderson alluded to earlier this

15       afternoon, we were projecting at that time, using the

16       fuel cost forecasts that were somewhat lower than what

17       we are currently projecting, that once both nuclear

18       units come into service, we are projecting or were

19       projecting at that time $1 billion a year for the first

20       year of fuel savings on our system from the nuclear

21       units, growing a bit every year, to where at the end of

22       the 40-year projected life, our projection at that time

23       was about $93 billion nominal in fuel savings for our

24       customers, and with higher fuel cost forecasts, that

25       93 billion number would be even higher today.  And that

514

1       does not count the environmental compliance cost savings

2       that are also higher today than what we projected in the

3       determination of need filing.

4            Q.   And what year do those cost savings begin?

5            A.   The cost savings would begin -- the $1 billion

6       number I mentioned would be the first year in which both

7       units were in service for the full year, and that would

8       be in 2021, assuming a 2018 and 2020 in-service date,

9       midyear, for both units.  We would begin to see fuel

10       savings in 2018 as the first nuclear unit went in

11       service, but the full $1 billion number is based upon

12       both units being in service nor a full year.

13            Q.   Are you using 2007 dollars in those savings

14       calculations, or are you using some other --

15            A.   The 1 billion and $93 billion are not

16       discounted to 2007.  Those are nominal, in that year

17       dollars for each year.

18            Q.   And how much do you anticipate that 2007

19       dollars will depreciate in value between now and 2021?

20            A.   I'm not sure I would think of it in terms of

21       depreciation, but I don't have that number in front of

22       me, sir.

23                 MR. McWHIRTER:  I have no further questions.

24                 CHAIRMAN CARTER:  Thank you, Mr. McWhirter.

25       Staff.

515

1                 MR. YOUNG:  No questions.

2                 CHAIRMAN CARTER:  Commissioners.

3                 Okay.  Mr. Anderson.

4                 MR. ANDERSON:  We have no questions.  He had

5       no exhibits also.

6                 CHAIRMAN CARTER:  No exhibits?  Okay.  Good.

7       Thank you.  Dr. Sim, thank you.  You may be excused.

8       He's not a rebuttal witness, so --

9                 MR. ANDERSON:  We would ask that he be

10       excused, yes.

11                 CHAIRMAN CARTER:  Hasta la bye-bye.

12                 Mr. Anderson.

13                 MR. ANDERSON:  FPL would call as its next

14       witness John Reed.

15                 CHAIRMAN CARTER:  Mr. John Reed.

16       Thereupon,

17                             JOHN J. REED

18       was called as a witness on behalf of Florida Power &

19       Light Company and, having been first duly sworn, was

20       examined and testified as follows:

21                          DIRECT EXAMINATION

22       BY MR. ANDERSON:

23            Q.   Good afternoon, Mr. Reed.

24            A.   Good afternoon.

25            Q.   Have you been sworn?

516

1            A.   Yes, I have.

2            Q.   Would you tell us your full name and business

3       address?

4            A.   My name is John J. Reed.  My business address

5       is 293 Boston Post Road, Marlborough, Massachusetts.

6            Q.   By whom are you employed, and in what

7       capacity?

8            A.   I am the chief executive officer of Concentric

9       Energy Advisors.

10            Q.   Have you prepared and caused to be filed 38

11       pages of prefiled direct testimony in this proceeding?

12            A.   Yes, I have.

13            Q.   Do you have any changes or revision to your

14       prefiled direct testimony?

15            A.   No, I do not.

16            Q.   If I asked you the same questions contained in

17       your prefiled direct testimony, would your answers be

18       the same?

19            A.   Yes, they would.

20                 MR. ANDERSON:  FPL asks that the prefiled

21       direct testimony of Mr. Reed be inserted into the record

22       as though read.

23                 COMMISSIONER EDGAR:  The prefiled direct

24       testimony will be entered into the record as though

25       read.

517

1       BY MR. ANDERSON:

2            Q.   You are sponsoring two exhibits?

3            A.   Yes.

4            Q.   Those are JJR-1 and JJR-2?

5            A.   That is correct.

6                 MR. ANDERSON:  These have been premarked in

7       staff's list as Exhibits 26 and 27.

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

556

1       BY MR. ANDERSON:

2            Q.   Have you prepared a summary of your testimony,

3       Mr. Reed?

4            A.   Yes, I have.

5            Q.   Would you please provide your summary to the

6       Commission?

7            A.   Certainly.  Good afternoon.  As I said, my

8       name is John J. Reed, and I'm the chief executive

9       officer of Concentric Energy Advisors.  I have over 30

10       years of experience in the energy industry, and I've

11       provided expert testimony on a wide variety of economic

12       and financial issues related to the energy and utility

13       industry, including nuclear construction projects.  My

14       prefiled testimony presents a list of 16 existing

15       nuclear units that I provided consulting services to.

16       As well, there are nine proposed nuclear units that I'm

17       currently providing services for.

18                 The purpose of my testimony is to review the

19       processes and procedures used by FPL to manage the

20       development and implementation of the EPU projects and

21       the new nuclear projects at Turkey Point.  My testimony

22       presents my opinion as to the reasonableness of these

23       policies and procedures relative to other nuclear

24       generating facilities currently being developed in the

25       United States.  I have not reviewed and don't offer an

557

1       opinion as to the reasonableness of the specific costs

2       of which FPL requests recovery in this proceeding.

3                 As part of my firm's work on this matter, my

4       staff and I reviewed thousands of documents and

5       interviewed several FPL members in order to evaluate

6       FPL's project management capabilities.  Specifically, we

7       reviewed six elements for each of five processes that

8       are integral to the company's project management

9       capabilities.  These six elements included defined

10       corporate procedures, written project execution plans,

11       involvement of key internal stakeholders, reporting and

12       oversight mechanisms, corrective action mechanisms, and

13       reliance upon a viable technology.

14                 The six elements were reviewed for the

15       following five processes:  Cost estimation and

16       budgeting, schedule management, contract management and

17       administration, internal oversight, and external

18       oversight.

19                 Within the cost estimation and budgeting

20       process, we have concluded that FPL has corporate

21       procedures in place that explicitly document the process

22       for developing a cost estimate, and Concentric has found

23       that FPL has complied with those procedures in

24       developing its estimates.  These procedures outline the

25       process for cost estimation on a basis that is well

558

1       within nuclear industry standards and viewed as being

2       the most accurate means of developing a preliminary cost

3       estimate.  The FPL cost estimates have also included a

4       reasonable contingency factor that is consistent with

5       industry guidelines.  Concentric has also confirmed the

6       use of a process to track actual expenditures relative

7       to budget on a weekly, monthly, and annual basis.

8                 Within the schedule management function, FPL

9       has specific corporate policies for developing project

10       schedules and has complied with those procedures in

11       developing the extended power uprate and new nuclear

12       project schedules.  These procedures use industry

13       standard critical path scheduling methods, and FPL

14       relies upon industry standard software to optimize each

15       schedule and to define the relationship between

16       activities.  The EPU projects track their schedule

17       performance on a weekly, monthly, and annual basis,

18       while the Turkey Point new nuclear project currently

19       tracks progress on a monthly and annual basis.

20                 We have also concluded that FPL has a robust

21       process for initiating corrective action mechanisms when

22       a project falls behind schedule.

23                 Within the contract management function, we

24       noted that a large portion of the cost of both projects

25       will be associated with contract management and the

559

1       administration of outside vendors.  FPL also has very

2       robust procedures that appear to cover every facet of

3       contract development, and FPL has complied with those

4       procedures.

5                 FPL has a preference for competitive bidding

6       where that is possible and where it is in the best

7       interest of the company and its ratepayers.  For those

8       instances where the company has not utilized competitive

9       bidding, it has valid, documented reasons for doing so.

10                 With regard to the internal and external

11       oversight mechanisms, FPL has established both internal

12       and external oversight mechanisms to gauge the project

13       performance and to institute best practices on a

14       going-forward basis.  This includes the development of

15       executive reporting requirements, internal audit

16       requirements, and a corporate risk committee which are

17       responsible for reviewing both projects.  The company

18       has also relied on outside resources to bolster its

19       internal oversight, including two reviews of its project

20       management practices.

21                 My conclusions are, first, that I found that

22       FPL's project management practices and procedures for

23       both projects are reasonable and meet or exceed industry

24       norms.  These practices and procedures include an

25       appropriate level of senior level oversight of the

560

1       projects as well as including internal audits to ensure

2       compliance with all of the company's policies.

3                 That concludes my summary.

4                 MR. ANDERSON:  Mr. Reed is available for

5       cross-examination.

6                 CHAIRMAN CARTER:  Thank you.  One moment.  I

7       did promise the court reporter a break.  Do you feel

8       like you can go on for another hour?  We've got a good

9       streak going here.

10                 Okay.  Let's continue.  Mr. McGlothlin.

11                 MR. McGLOTHLIN:  I will reserve my questions

12       until he comes back on rebuttal.

13                 CHAIRMAN CARTER:  Mr. Twomey?

14                 MR. TWOMEY:  No questions.

15                 MR. McWHIRTER:  Just a couple.

16                           CROSS-EXAMINATION

17       BY MR. McWHIRTER:

18            Q.   Are you familiar with the cost of nuclear

19       plants around the world as opposed to around the United

20       States?

21            A.   In general terms, yes.

22            Q.   How do FP&L's nuclear costs compare to

23       building a nuclear plant in France?

24            A.   The nuclear plants that are built in France

25       use a different technology.  It uses what's called the

561

1       Areva EPR technology currently.  That technology, which

2       is more of a passive safety system as opposed to active

3       safety systems in the AP1000, results in it having a

4       different cost structure.

5                 In general, the most recent estimate for an

6       EPR is that it's about $4,500 per kW for constructions

7       costs today in 2008 dollars.  That compares of course,

8       to the most recent estimate for FPL of 3,100 to 4,500.

9       So the EPR is at the upper end of that range in France.

10                 MR. McWHIRTER:  Thank you.

11                 CHAIRMAN CARTER:  Thank you, Mr. McWhirter.

12                 Staff?

13                 MR. YOUNG:  No questions.

14                 CHAIRMAN CARTER:  Commissioner Skop, you're

15       recognized.

16                 COMMISSIONER SKOP:  Thank you, Mr. Chairman.

17       Just one quick question, and this is in the witness's

18       professional opinion.  Does he believe that FPL's

19       existing project management, risk management, and cost

20       estimation capabilities are adequate to move forward at

21       this time?

22                 THE WITNESS:  Yes, I do.  They are as good as

23       any we have seen in the industry for those companies

24       that are currently pursuing new nuclear programs.

25                 COMMISSIONER SKOP:  Thank you.

562

1                 CHAIRMAN CARTER:  Commissioner Argenziano.

2                 COMMISSIONER ARGENZIANO:  Thank you.  On the

3       same line, did you find any areas that could be improved

4       as far as being more extensive and detailed on the

5       internal controls and project management controls that

6       would better help in the adequacy and effectiveness of

7       the report?

8                 THE WITNESS:  We have identified, and the

9       company agrees with, the need for additional controls

10       going forward.  As the programs increase their level of

11       funding and their level of activities, what has worked

12       well in the past won't be adequate to cover what's

13       happening in the future.  So in terms of adding staff,

14       and internal controls is one of the areas that we both

15       recognize need to have staff added, the company is in

16       agreement with us that they should add staff there and

17       they should expand that function.

18                 So, yes, we did identify the need for

19       additional resources in that area on a going-forward

20       basis.  What has happened is fully adequate, but the

21       company fully agrees with that assessment that

22       additional resources are needed there, especially on

23       Turkey Point as the project goes forward.

24                 COMMISSIONER ARGENZIANO:  Okay.  Thank you.

25                 CHAIRMAN CARTER:  Thank you.  Commissioners,

563

1       anything further?

2                 Mr. Anderson.

3                 MR. ANDERSON:  We have no questions.

4                 CHAIRMAN CARTER:  Okay.  We have an exhibit

5       marked for identification, number -- is 26 and 27?

6                 MR. ANDERSON:  Yes, sir.

7                 CHAIRMAN CARTER:  Any objections?  Without

8       objection, show it done.  They're moved into evidence,

9       Exhibits 26 and 27.

10                 (Exhibits Number 26 and 27 were admitted into

11       the record.)

12                 CHAIRMAN CARTER:  And this witness will be

13       available for rebuttal; correct?

14                 MR. ANDERSON:  Yes, sir.

15                 CHAIRMAN CARTER:  Thank you.  You're excused,

16       Mr. Reed, at this point in time.

17                 And now, Mr. McGlothlin, you're recognized,

18       sir.

19                 MR. McGLOTHLIN:  OPC calls Dr. Jacobs.

20                 CHAIRMAN CARTER:  Okay.  Dr. Jacobs, William

21       Jacobs.

22                 Okay.

23                 MR. McGLOTHLIN:  It appears he has stepped

24       away for, I'm sure, just for a moment.

25                 CHAIRMAN CARTER:  Okay.  All right.  Then I

564

1       guess the court reporter gets her break after all.  I'm

2       looking at the clock on the wall to my right.  We'll

3       come back at 15 after.

4                 (Short recess.)

5                 MR. McGLOTHLIN:  Before we ask Dr. Jacobs to

6       summarize his testimony, there's one housekeeping matter

7       I would like to bring to the Commissioners' attention.

8                 CHAIRMAN CARTER:  You're recognized.

9                 MR. McGLOTHLIN:  When we submitted the

10       prefiled testimony, most of it was redacted because FPL

11       at the time was claiming confidentiality for many of the

12       exhibits and the discussion of those exhibits.  Very

13       recently, FPL withdrew its claim, and I'm informed that

14       staff has provided to the Commissioners somewhere in

15       your packets a new version of that testimony and

16       exhibits that is largely unredacted at this point, so it

17       should be far more accessible to you than it was

18       previously.

19                 CHAIRMAN CARTER:  Commissioners, it's the one

20       that looks like this.

21                 Thank you, Mr. McGlothlin.  You may proceed.

22       Thereupon,

23                    WILLIAM R. JACOBS, JR., Ph.D.

24       was called as a witness for the citizens of the State of

25       Florida and, having been first duly sworn, was examined

565

1       and testified as follows:

2                          DIRECT EXAMINATION

3       BY MR. McGLOTHLIN:

4            Q.   Please state your name and business address.

5            A.   William R. Jacobs, 1850 Parkway Place,

6       Marietta, Georgia.

7            Q.   Dr. Jacobs, do you have before you a document

8       dated July 30, 2008, and captioned the revised direct

9       testimony and exhibits of William R. Jacobs, Jr.?

10            A.   Yes, I do.

11            Q.   Did you prepare that prefiled testimony on

12       behalf of the Office of Public Counsel?

13            A.   Yes.

14            Q.   With respect to the portions of testimony that

15       relate to your review and comments on FPL's pending

16       request, do you have any changes, additions or

17       correction to make to that testimony?

18            A.   No, I do not.

19            Q.   Do you accept the questions and answers

20       contained in this prefiled document as your testimony

21       today?

22            A.   Yes.

23                 MR. McGLOTHLIN:  Earlier Mr. Burgess asked

24       that the prefiled testimony be incorporated into the

25       record as though read.  It wasn't clear to me whether

566

1       there was effort to pull out only the PEF-related

2       portions, but in an abundance of caution, I request that

3       the testimony be inserted at this point.

4                 CHAIRMAN CARTER:  I like your style.  The

5       testimony will be entered into the record as though

6       read.

7       BY MR. McGLOTHLIN:

8            Q.   Dr. Jacobs, did you also prepare the exhibits

9       to the testimony that were marked as WRJ-2 through 8?

10            A.   Yes.

11                 MR. McGLOTHLIN:  Commissioners, those have now

12       been identified as Exhibit Numbers 29 through 35.

13                 CHAIRMAN CARTER:  It will be 28 through 35.

14                 MR. McGLOTHLIN:  Twenty-eight, yes.

15       BY MR. McGLOTHLIN:

16            Q.   Have you prepared a summary of your testimony

17       as it relates to Florida Power & Light Company?

18            A.   Yes, I have.

19            Q.   Please provide that to the Commissioners.

20            A.   Okay.  Good afternoon again, Mr. Chairman and

21       Commissioners.  I will now summarize my testimony as it

22       relates to FPL's pending request.

23                 Earlier I described my view of the analysis

24       needed to identify the incremental costs that requesting

25       utilities should be required to perform to demonstrate

567

1       they are adhering to the limited scope of the rule as it

2       relates to uprate projects.  That summary applies to FPL

3       as well as PEF, and I will not repeat it here.

4                 The second issue that relates to FPL's request

5       involves FPL's frequent decisions to award contracts

6       without first seeking competitive bids.  Although FPL's

7       management procedures stress a preference for

8       competitive bidding, to date, FPL has used sole or

9       single source contracts extensively in both the extended

10       uprate and the Turkey Point 6 and 7 projects.

11                 A sole source contract is one in which FPL

12       regards the contractor as the only available provider of

13       that service.  A single source contract is one in which

14       other providers are available, but the utility decides

15       that a particular contractor should be selected without

16       first soliciting competitive bids.

17                 In several cases, FPL cited the need to meet a

18       project schedule as justification for using the sole or

19       single source contracts.  The use of schedule pressure

20       to justify using a single or sole source contract is not

21       allowed per FPL's nuclear procedure, NP 1100.

22                 Further, FPL adopted a casual approach to the

23       preparation of the justification that is intended to

24       serve as the principal basis for a decision to depart

25       from the standard of competitive bidding.  The language

568

1       in many of FPL's justification memoranda is so similar

2       that it appears their preparation is a matter of rote

3       rather than a specific individual analysis.

4       Specifically, the phrase, "Performing this work scope

5       with another vendor would not be cost-effective or

6       prudent from a schedule perspective," appears in

7       memoranda time and again.  Among others, this

8       justification appears in the memorandum prepared by FPL

9       to justify awarding the contract to Westinghouse without

10       seeking competitive bids.

11                 When we asked about the Westinghouse situation

12       in discovery, FPL said it would be required to change

13       fuel vendors if it used any contractor other than

14       Westinghouse.  That is a very different consideration

15       than anything contained in the standardized language in

16       the justification memo.  The disconnect between the

17       reason given in the required justification memorandum

18       and the very different reason later given by FPL

19       illustrates the casualness to which I refer.

20                 Because the memoranda are the principal

21       instruments on which senior management bases the

22       decision to require or not require bids, they should be

23       fully developed.  The fact that they are not means FPL

24       is not adhering to its own management procedures.  At

25       this early stage of a nuclear project, it is important

569

1       that management establish high expectations that

2       procedures for procurement and project management be

3       followed.  If management does not set high standards in

4       this area, the outlook for a successful project is

5       diminished.

6                 Next, in my opinion, many of the

7       justifications do not demonstrate that the costs of

8       these single or sole source contracts are reasonable.

9       In my testimony, I provide an example of a $100 million

10       contract to replace the low pressure turbine rotors at

11       St. Lucie.  This is part of the St. Lucie uprate

12       project.  The project was awarded to Siemens on a single

13       source basis.  When asked to provide documentation

14       demonstrating that the costs of the project were

15       reasonable, FPL provided a single page, "back of the

16       envelope" type of analysis that used five-year-old bids

17       to another company to demonstrate the reasonableness of

18       the costs.  In my opinion, the documentation offered by

19       FPL is inadequate to prove that the costs of a contract

20       of this magnitude entered into without bids are

21       reasonable.

22                 To emphasize the importance of following the

23       requirements for single and sole source contracting and

24       the need to demonstrate the reasonableness of the costs

25       associated with these contracts, I recommend that the

570

1       Commission disallow FLP's return on the equity portion

2       of the investment associated with the low pressure rotor

3       contract.  Alternatively, the Commission could withhold

4       a portion of the requested carrying charges associated

5       with the low pressure turbine contract unless and until

6       FPL can demonstrate the costs are reasonable in the next

7       hearing cycle.

8                 If the Commission does not wish to impose

9       financial penalties because this is the first round of

10       the NCRC hearings, at a minimum, the Commission should

11       place FPL on notice that it intends to require a

12       rigorous and detailed justification for any departure

13       from the competitive bidding process in future

14       proceedings.

15                 This concludes my opening statement.

16                 MR. McGLOTHLIN:  Dr. Jacobs is available for

17       cross.

18                 CHAIRMAN CARTER:  Thank you, Mr. McGlothlin.

19                 Mr. McWhirter?

20                 MR. McWHIRTER:  No questions, sir.

21                 CHAIRMAN CARTER:  Mr. Anderson.

22                 MR. ANDERSON:  Thank you.

23                           CROSS-EXAMINATION

24       BY MR. ANDERSON:

25            Q.   Good afternoon, Dr. Jacobs.

571

1            A.   Good afternoon.

2            Q.   My name is Bryan Anderson.  I'm an attorney

3       representing Florida Power & Light company.

4                 Your testimony discusses sole source and

5       single source contracting; is that right?

6            A.   Yes, sir.

7            Q.   Your firm, GDS, previously did work for the

8       Office of Public Counsel?

9            A.   Yes, sir.

10            Q.   That was back in the mid-1990s?

11            A.   That's correct.

12            Q.   For this project, you were telephoned by

13       Mr. McGlothlin; is that right?

14            A.   For this particular project?

15            Q.   Yes.

16            A.   Yes.

17            Q.   He described the nuclear cost recovery rule

18       project?

19            A.   Is that a question?

20            Q.   Yes.

21            A.   Yes.

22            Q.   Did he ask you if GDS had the time and

23       expertise needed to assist OPC?

24            A.   Yes, he did.

25            Q.   Your firm did not respond to a competitive

572

1       bidding request from OPC issued to an array of nuclear

2       consulting firms, did you?

3            A.   No, it did not.

4            Q.   OPC hired GDS with a single source contract;

5       isn't that right?

6            A.   I believe that's true.  I don't know what

7       evaluation process OPC went through to reach that.

8            Q.   Was it --

9            A.   -- conclusion.

10            Q.   Go ahead.  I'm sorry.

11            A.   To reach that conclusion, but as you've

12       described it, that is how we were hired.

13            Q.   Was it cost-effective for OPC to hire your

14       firm?

15            A.   I believe it was, yes.

16            Q.   Is cost-effectiveness a reasonable factor to

17       consider in assessing a single or sole source contract?

18            A.   Yes, it clearly is.

19            Q.   Your firm has the right experience to be

20       retained for this project; is that right?

21            A.   That's correct.

22            Q.   Is a firm's experience a reasonable factor to

23       consider in assessing a single or sole source contract?

24            A.   Yes.  There are a number of different factors.

25            Q.   Are there efficiencies from your firm being

573

1       familiar with OPC and working in Florida?

2            A.   Yes.

3            Q.   Are efficiencies from having previously

4       performed similar work a reasonable factor to consider

5       in assessing a single or sole source contract?

6            A.   That's one of many factors, yes.

7            Q.   And you've had success, in the sense that OPC

8       was satisfied with your work?  They hired you again; is

9       that right?

10            A.   I believe so, yes.

11            Q.   Is past successful experience also a

12       reasonable factor to consider in assessing a single or

13       sole source contract?

14            A.   Yes, it is.

15            Q.   I've had distributed some documents entitled

16       "Summary of Reasons for Choosing Westinghouse", which

17       contain direct quotations from an exhibit to your

18       testimony, which was the sole source justification for

19       Westinghouse.

20            A.   Yes.

21            Q.   Do you see that, with the cost-effectiveness,

22       experience, et cetera, words on there?

23            A.   Yes, I do.

24            Q.   Okay.  First, let me ask you to take a minute

25       and read the words contained in the summary of reasons

574

1       for choosing Westinghouse to yourself, and I'm going to

2       ask you this question.  Do you agree with me that all of

3       the words on that summary exhibit appear in the single

4       and sole source document?

5            A.   Okay.  Let's take a moment.

6                 I believe they do.  I haven't done a

7       point-by-point check, but I will agree that these

8       sound -- I recall them from reading the justification

9       memo.

10            Q.   Good.  Focusing on Westinghouse, you were

11       employed by Westinghouse for a number of years; is that

12       right?

13            A.   That's correct.

14            Q.   And you told me at your deposition that

15       Westinghouse was not in the habit of sharing proprietary

16       information with competitors, it protected its

17       information?

18            A.   That's correct.

19            Q.   Okay.  Isn't it a fact that the work that FPL

20       hired Westinghouse for was to work on licensing and

21       engineering for major nuclear steam supply system

22       components for FPL's plant?

23            A.   That's correct.

24            Q.   And you would agree with me that that is

25       safety significant work as we think about those things

575

1       in NRC regulation?

2            A.   Yes.

3            Q.   You have to have credibility in the industry

4       to be able to submit those engineering analyses and have

5       them accepted for a license amendment?

6            A.   Yes.

7            Q.   The fact that Westinghouse had performed all

8       of the current licensing basis analyses for the major

9       nuclear steam supply system components, that would be a

10       relevant factor, wouldn't it be, in selecting a company

11       like Westinghouse?

12            A.   Yes, it would.

13            Q.   How about the fact that Westinghouse had done

14       this scope of work in the past for numerous uprates,

15       including the Turkey Point uprate, another FPL plant?

16            A.   That would be a factor, yes.

17            Q.   Wouldn't you expect there would be

18       efficiencies from Westinghouse using its own design and

19       engineering analysis for its own design basis in

20       performing this scope of work for FPL?

21            A.   Yes, you would expect this.  But I think the

22       point is that you don't know it for sure absent a

23       competitive bidding process.  I mean, you can --

24       Westinghouse certainly has advantages, and you've

25       enumerated them here.  And you would think due to these

576

1       advantages, Westinghouse would have a price advantage as

2       well, but without doing competitive bidding, you don't

3       really know that for sure.

4            Q.   Isn't it true that no other company in the

5       world has the right to use Westinghouse's proprietary

6       information, which FPL is asking be used for its

7       project?

8            A.   That's correct, but other companies have

9       similar processes.

10            Q.   Isn't it true that -- let me move on to

11       another thing here.  I think that's sufficient on

12       Westinghouse here.

13                 I would like to turn to Areva.  There's an

14       exhibit a couple of pages down.

15            A.   Yes.

16            Q.   I'll ask you to please take a look at that

17       summary of reasons for choosing Areva.  And if you wish,

18       the sole source justification is right behind the

19       attachment.  I would like you to just agree with me that

20       each of the reasons stated in this exhibit are stated in

21       the sole source justification.

22            A.   Okay.  I agree with that.

23            Q.   Okay.  And despite all these things stated in

24       these summaries, you didn't see fit to mention them in

25       your testimony, did you?

577

1            A.   Well, I included the justification memorandum

2       in my testimony as an exhibit, so they're all included.

3            Q.   Right.  You attached the exhibit, and I'm glad

4       you did, because that's what we're talking about.  But

5       when you gave your opinion and provided your testimony

6       asserting we had an insufficient basis, you didn't

7       disclose any of this information which reveals the

8       unique nature of these vendors and the information they

9       have which we relied on in making our decisions.

10                 MR. McGLOTHLIN:  I'm going to object to the

11       form of the question in that it is inconsistent with the

12       previous answer, which was that the witness attached the

13       entire justification memorandum to his testimony as an

14       exhibit.  100 percent of it was there attached to his

15       testimony, so to say that he refused to disclose is a

16       mischaracterization of his testimony.

17                 MR. ANDERSON:  I'm happy to move on to another

18       question.

19       BY MR. ANDERSON:

20            Q.   You used the word in your summary "back of the

21       envelope" analysis.  Do you remember that?

22            A.   Yes, I do.

23            Q.   And this is a confidential exhibit that's

24       going around, and I'm going to structure these questions

25       in such a way as not divulge the information contained

578

1       in it.

2                 Are you ready?

3            A.   Yes, sir.

4            Q.   Thank you very much.  Please turn to your

5       testimony, Exhibit WRJ-8.

6            A.   I'm looking in it.

7            Q.   This is the document you referred to as the

8       "back of the envelope" analysis; is that right?

9            A.   That's correct.

10            Q.   Okay.  Do you see down towards the bottom of

11       the page there, there's a "W" for a Word document

12       attachment to this e-mail?

13            A.   Yes, I do.

14            Q.   Okay.  Did you include that Word document

15       attachment as an exhibit to your testimony?

16            A.   No, I did not.

17            Q.   Okay.  So this "back of the envelope" analysis

18       you're talking about actually contained a Word document

19       attachment; is that right?

20            A.   Yes.

21            Q.   Okay.  And then turning to that document,

22       which has been distributed to the Commission and to you,

23       I'm just going to count the pages.  I'm counting the

24       first page, which is an e-mail.  And I'll just count.

25       One, two, three, four, five, six, seven, eight pages; is

579

1       that right?

2            A.   Yes, that's correct.

3            Q.   And down at the bottom, it says Office of

4       Public Counsel, Late-filed Exhibit Number 7, EPU

5       Project; right?

6            A.   Yes.

7            Q.   This is one of the documents you asked for

8       when our witness's deposition was taken; is that right?

9            A.   That's correct.

10            Q.   Okay.  And you did not mention in your

11       criticism of the "back of the envelope" analysis this

12       multi-page, single-spaced, detailed analysis anywhere in

13       your testimony.  All you chose to do was include the

14       e-mail transmittal; right?

15            A.   That's correct.  That's because this multi --

16       seven or eight pages are not related to a determination

17       of the reasonableness of the costs.  These pages are

18       showing their analysis of which option to take.  They

19       talk about various options for repair and replacement of

20       the rotors, and they ultimately choose one of these

21       options, and the chosen option is then analyzed in this

22       "back of the envelope" e-mail for cost reasonableness.

23       So those attached pages aren't really a part of their

24       determination of the reasonableness of cost of the

25       option selected.

580

1            Q.   Well, that's your interpretation.  You're

2       saying that FPL in justifying a very, very large capital

3       cost attached an irrelevant document to the e-mail.  Is

4       that what you're saying?

5            A.   It's not relevant to their attempt to

6       demonstrate that the cost was reasonable.  It

7       demonstrates which option they chose, which was, I

8       believe, Option 4.  And then Option 4 is shown or

9       attempted to be shown to be reasonable by this

10       comparison to five-year-old data from another utility.

11                 MR. ANDERSON:  FPL has no more questions.

12                 CHAIRMAN CARTER:  Thank you, Mr. Anderson.

13       Commissioner Skop.

14                 COMMISSIONER SKOP:  Thank you, Mr. Chairman.

15       I just have a few questions for Mr. Jacobs.

16                 I guess, just trying to get your opinion, I

17       recognize the tensions and the issues before us, and

18       generally when it comes to a competitive bid process,

19       I'm in favor of one when it's in favor to do so.  But,

20       you know, a combined cycle plant that's readily

21       available, commercial, off the shelf, is significantly

22       different than a nuclear reactor plant that no one has

23       built in 30 years.

24                 But that being said, I wanted to go back to

25       some points that you made in your testimony to try and

581

1       better understand from your perspective.  I've heard

2       FPL's.  But with respect to the sole source issue that

3       OPC is raising, could FPL's decision to sole source

4       various contracts be justified in a sense as a business

5       reality or a necessity resulting from the significant

6       decline of the U.S. nuclear construction industrial base

7       that we've seen?  I mean, there's not a lot of suppliers

8       out there, so I just wanted to just ask that straight up

9       and get a straightforward answer.

10                 THE WITNESS:  Well, it depends on -- there are

11       certainly certain of the tasks involved that would

12       logically fall to one particular vendor.  However,

13       that's not to say that there aren't other vendors in the

14       world that can perform that task.  And so in my mind,

15       the approach would be to put it out for competitive bid,

16       see who wants to compete.  You know, it's likely that

17       the logical vendor should have a cost advantage and

18       should win the project, but you don't really know that

19       unless you do it.

20                 COMMISSIONER SKOP:  I understand.  And to that

21       point, I mean, I can understand that various vendors may

22       have technical capability to do something, but how do

23       you overcome the proprietary information argument?

24       Because there's many people that can build a house, but

25       unless they have the blueprints, they're going to kind

582

1       of be hamstrung.

2                 THE WITNESS:  Well, that can be developed

3       independently, or it can be transferred to one or the

4       other under confidentiality agreements, you know, for a

5       certain utility.

6                 COMMISSIONER SKOP:  But to develop it

7       independently rather than transfer it would result in

8       significant increased costs.

9                 THE WITNESS:  That's true, and that would be

10       reflected in their bid.

11                 COMMISSIONER SKOP:  And on page 13 of your

12       prefiled testimony, the confidential exhibit -- and I'm

13       not going to go into confidential matters.

14                 THE WITNESS:  Okay.

15                 COMMISSIONER SKOP:  But you reference NP 1100,

16       and I think that, at least from what I've heard in the

17       summary of your testimony, that OPC is taking issue to

18       the extent that apparently FPL in OPC's opinion is not

19       adhering to its own internal procedures as well as some

20       might like.  Is that simply, in your opinion, maybe a

21       matter of semantics or presenting the information or

22       providing a better justification that would read better,

23       or is that endemic of a larger problem?

24                 THE WITNESS:  Well, that's a good question.

25                 COMMISSIONER SKOP:  And just to put that in

583

1       context, in light of the fact that the industrial base

2       is so diminished, I mean, reactors not built -- I had

3       the same reaction when we were building nuclear

4       submarines, the industrial base.  So if you could

5       respond in the context of, are there --- if you don't

6       have options, then what may be presented as nefarious

7       may not be nefarious, to the extent that, you know,

8       they're doing the best you can, and there's not a whole

9       lot of options.

10                 THE WITNESS:  Well, there are several points I

11       want to make here.  We talked a lot about schedule and

12       that the NP 1100 does not allow schedule pressure to

13       enter into -- to be a requirement for a sole source or

14       single source bid.

15                 Now, obviously, every project has a schedule,

16       and the schedule has to be met, and if you go out for

17       competitive bids, one of the requirements would be that

18       you can meet the schedule.  That would be in your bid

19       package.  The schedule pressure that the NP 1100 is

20       referring to is, "We don't have time to do competitive

21       bidding, so we're going to issue a sole source

22       contract."  That is the type of schedule pressure that

23       should not aloud as a justification.

24                 Many of these sole source contracts that I

25       looked at did in fact talk about schedule pressure.  I'm

584

1       looking at the one -- it's my Exhibit WRJ-5, and it's

2       for McNabb Hydrologic Consulting, and in the fourth

3       paragraph it says, "Due to the project schedule, and

4       considering the time required to obtain quotes and other

5       schedule necessities" -- you have the complexity and so

6       forth, that they want to issue this contract as a sole

7       source.  So, again, the time required to obtain quotes

8       should not be a factor in determining if you use a sole

9       source contract.  You should be able to plan your work

10       far enough in advance to have time for that.

11                 COMMISSIONER SKOP:  And I respect that, and

12       I'll move on to -- I just have two more questions.

13                 I noticed that there was some discussion made

14       on what the appropriate remedy the Commission should

15       adopt in response to what OPC is asserting on this issue

16       with respect to perhaps deviating from internal

17       procedure or what have you.  But I guess where I'm

18       coming from, would penalizing FPL as you suggest have a

19       chilling effect on management discretion and their

20       ability to make cost-effective decisions?  I guess to

21       me, we're talking about a procedural issue that's based

22       somewhat on management discretion and somewhat on the

23       realities of the situation, that there's not a whole lot

24       of competition out there for these type of nuclear

25       construction activities.

585

1                 THE WITNESS:  Yes, sir.  I don't see that it

2       would have a chilling effect on that.  They have the

3       burden, the company has the burden to demonstrate that

4       their costs are reasonable.  They have to demonstrate it

5       their up upper management and ultimately to the

6       Commission.  And in this particular case we're talking

7       about, I don't believe they did.

8                 COMMISSIONER SKOP:  Okay.  And just in

9       relation -- on page 9, you give an example, and I guess

10       this is an ongoing discussion and tension that comes

11       into -- I think the example you cited was that a reactor

12       had been extended beyond its useful life, and there was

13       the main generator, a step-up transformer that would

14       need to be replaced.

15                 THE WITNESS:  Yes, sir.

16                 COMMISSIONER SKOP:  And I guess the issue that

17       I'm struggling with is, I see both sides of the

18       argument, as my colleagues probably do also.  To me, if

19       you look at it like an uprate situation, because I think

20       a transformer is at issue in one of the uprates.  But if

21       you do nothing, there's an argument to be made, well,

22       you would have to replace the generator at some point in

23       the future later.  But there's also an equally valid

24       argument that but for uprate, you wouldn't have to

25       replace the generator, you need the -- I mean the

586

1       transformer, you need the transformer for reliability

2       and the additional incremental generation that it's

3       going to be able to -- you know, the power that's

4       produced.

5                 So I guess I'm trying to understand -- and I

6       appreciate the cost impact analysis, but the nexus

7       relationship between, you know, improvements that are

8       deemed supportive of adding additional nuclear

9       generation, whether they be new nuclear units or whether

10       they be uprates to existing units, versus the

11       legislative mandate that basically states that nuclear

12       related -- and I think as this Commission has construed

13       in its need determination as well as its subsequent --

14       I'm having an over 40 moment here -- declaratory

15       statement basically provided some guidance to the extent

16       that the Legislature has expressly mandated that certain

17       nuclear related costs be recoverable subject to

18       prudency.

19                 And I guess -- how do you distinguish between

20       what has a logical -- where do you draw the line?  I

21       mean, there seems to be a logical nexus for having to

22       add components, you know, factoring in reliability.  So

23       it's easy to nitpick, but I don't think there's an

24       extremely bright line.  And perhaps if you know of one

25       other than, you know, just embracing both sides of the

587

1       argument, but also relating those to the statutory

2       direction that we've been given from our Legislature.

3                 THE WITNESS:  Yes, sir.  Well, first of all, I

4       think both PEF and FPL have agreed with this concept,

5       and they've agreed to provide analyses in future filings

6       that would show the relationship there between what's

7       needed for the uprate and what's needed for ongoing

8       maintenance.  We're not saying that they wouldn't

9       recover the cost.  For example, if they need a new

10       transformer, if it weren't for the uprate, they would

11       buy a new transformer, and it would be recovered through

12       the normal ratemaking mechanism.  And what we're saying

13       is, if they buy a transformer for the uprate that they

14       would have had to buy anyway, but perhaps it has to be a

15       bigger transformer because you're getting more power out

16       of it, then the nuclear cost recovery clause would be

17       used to recover the incremental costs between what they

18       would have done in a normal maintenance situation and

19       what they did to support the uprate.  But they would --

20       in any event, they would recover the full cost.  It's

21       just a matter of how they would recover them.

22                 MR. ANDERSON:  Commissioner Carter, I'm sorry.

23       Just for clarification, for our case, we didn't put in

24       any information on the separate and apart things.  And I

25       take it -- we, of course, have no objection to the

588

1       Commission getting whatever information it needs about

2       the projects generally.  But to be clear, our

3       understanding is that this is a stipulated issue.  We

4       put on nothing in our summaries and things, and I just

5       want to make sure that we're good relying on that.

6                 COMMISSIONER SKOP:  And I respect that.  I'm

7       not going down that direction.  I guess what I'm saying

8       is that there's such a breadth and volume of

9       information, and some things tend to merge in.  I'm

10       looking at each individual witness's testimony, and

11       sometimes those issues tend to blend in with themselves.

12       So if it is pre-stipulated issue, I respect that.  I

13       remember that from earlier this morning.

14                 But I guess just one final question in

15       passing.  You know, there's a lot of discussion over the

16       sole source, but there's equally not a lot of industrial

17       base.  So taking that into account, what improvements

18       would you state?  I mean, what would be your solution

19       for addressing such a situation where it implicates

20       management discretion without unduly penalizing FPL for

21       trying to do the right thing in accordance with the

22       needs of its customers and the needs for Florida to

23       bring on additional nuclear generation?

24                 THE WITNESS:  I guess one of the things I was

25       concerned with was, as I mentioned in my testimony, it

589

1       seemed like the justifications were sort of being done

2       by rote.  The same language appeared in many of them.

3       It didn't seem like it was given the importance that it

4       should have been given.  And perhaps -- one thing we

5       asked for was all the material that the vice president

6       who would be approving it would see, and we didn't

7       receive any additional information.  I think he's

8       looking at this one-page justification.

9                 So, you know, I would say they need to do a

10       better job of using competitive bidding when it's

11       available and don't just assume that, well, there's not

12       anybody else here that can do it, because there may be

13       other folks out there and they're want to get in the

14       business of doing it.  And ultimately, there would be a

15       number of factors.  That's just one of them.  There

16       would be a number of factors in selecting the

17       contractor.  But I would say they need to do a better

18       job of following their own corporate guidance to use

19       competitive bidding whenever possible.

20                 COMMISSIONER SKOP:  Thank you.

21                 CHAIRMAN CARTER:  Thank you.  Commissioner

22       Argenziano.

23                 COMMISSIONER ARGENZIANO:  Yes.  On that line

24       of questioning, I understand what OPC is indicating.  I

25       mean, I guess -- let me ask it this way.  The way this

590

1       is done now, without competitive bidding or going out

2       and looking, do you know that -- is it known that there

3       could be a better price or cost someplace else?

4                 THE WITNESS:  I think that's the whole point.

5       It's not known.  There's no way of knowing that without

6       doing the competitive bidding.

7                 COMMISSIONER ARGENZIANO:  Thank you.

8                 CHAIRMAN CARTER:  Thank you.  Commissioner

9       Edgar, is it on the same line here?  If not, I'll follow

10       up, and then I'll come back to you, Commissioner.

11                 COMMISSIONER EDGAR:  I believe so,

12       Mr. Chairman.

13                 CHAIRMAN CARTER:  Commissioner Edgar, you're

14       recognized.

15                 COMMISSIONER EDGAR:  Thank you.

16                 Are you aware of vendors in the market that

17       provide the same service with the same expertise?

18                 THE WITNESS:  Anyone in particular that you're

19       referring to, or just in general?

20                 COMMISSIONER EDGAR:  In general, in general.

21                 THE WITNESS:  Yes, there's a number of vendors

22       in the market.  For example, they selected Shaw, Stone &

23       Webster to do some design work.  There's a company

24       called Bechtel, which is a large nuclear engineering

25       company.  It likely could have done the same work.

591

1       Whether it would be more expensive or less is unknown

2       until you give them a chance to bid on it.

3                 COMMISSIONER EDGAR:  Okay.  So with your

4       answer there, are you telling me that it's your belief

5       that there are other vendors that could provide the same

6       level of management, contracting, oversight, control

7       services as an outside vendor?

8                 THE WITNESS:  Yes.

9                 COMMISSIONER EDGAR:  But you're not aware as

10       to whether that would be more or less cost-effective?

11                 THE WITNESS:  That's correct.  We don't know.

12                 COMMISSIONER EDGAR:  Okay.  And then following

13       up I think on a comment or an answer that you gave in

14       response a few moments ago, can you describe to me how

15       you see this -- what has gone on here as a departure

16       from their normal competitive bidding practice?

17                 THE WITNESS:  Well, they didn't -- I mean, the

18       departure is that they didn't use competitive bidding.

19       They used sole source and single source contracting,

20       which is a departure from their stated corporate

21       preference and belief to use competitive bidding when

22       possible.

23                 COMMISSIONER EDGAR:  Because I thought that I

24       heard -- and I don't remember which witness.  I

25       apologize vice for that.  But I think one of the FPL

592

1       witnesses just a little earlier this afternoon said that

2       for this -- excuse me.  For this step in the process,

3       that they had sole source previously.

4                 THE WITNESS:  Yes, I recall hearing that, yes,

5       for another -- I believe it was for another uprate

6       project on a different plant, that they had used a sole

7       source.

8                 COMMISSIONER EDGAR:  Okay.  Then I guess I'm a

9       little confused as to why then you see this as a

10       departure from their general corporate practice or

11       policies.  And if I've missed it or confused it, please

12       feel free to clarify for me.

13                 THE WITNESS:  Well, they departed in both

14       cases.

15                 COMMISSIONER EDGAR:  Okay.  All right.  Thank

16       you.

17                 CHAIRMAN CARTER:  Thank you.  Before you,

18       Commissioner McMurrian, I'm on that same line.

19                 Dr. Jacobs, on the charts that were before

20       you, you agreed that the -- and I think it's from your

21       exhibits in terms of the parameters for doing sole

22       source, cost-effectiveness, experience, efficiency,

23       success; is that correct?

24                 THE WITNESS:  Yes.

25                 CHAIRMAN CARTER:  Now, unlike my colleague,

593

1       I've not built nuclear submarines, but I've done a lot

2       of contracts, I mean, thousands of regular contracts,

3       and maybe a couple hundred sole source.  And you go with

4       the sole source contract for, as I can see it -- there

5       was some testimony given that was objected to,

6       cross-examination and whatever the case may be, credible

7       testimony given that this was a specific design by a

8       specific manufacturer that had specific knowledge about

9       its equipment; is that correct?

10                 THE WITNESS:  That's correct.

11                 CHAIRMAN CARTER:  Secondly, and I think you

12       said in response to a question from Commissioner Skop,

13       in that context, that the sole source would probably be

14       cheaper.  That's my term, cheaper.  You said less

15       expensive.

16                 THE WITNESS:  That's correct.

17                 CHAIRMAN CARTER:  Now, let me kind of stop

18       there for a moment and back up.  In the regular

19       contracting process in those thousand or so contracts

20       that I've handled, generally it's a very litigious

21       process, even if you're not the success bidder, whether

22       you could do the work or not, and a lot of that

23       litigation goes on to drag the process out.  Wouldn't

24       you agree with that?

25                 THE WITNESS:  I'm sorry.  I don't quite follow

594

1       that.

2                 CHAIRMAN CARTER:  Okay.  Contracting.  We're

3       talking about contracting, not single source, but just

4       general contracting.

5                 THE WITNESS:  Okay.

6                 CHAIRMAN CARTER:  And I believe that you've

7       examined more than just sole source contracts; right?

8                 THE WITNESS:  Yes.

9                 CHAIRMAN CARTER:  Wouldn't you agree that a

10       lot of times in the process of going through the normal

11       parameters that a lot of contractors, unsuccessful

12       contractors, will go through a highly litigious process

13       that will drag the process on, raise the cost, and then

14       subject the process to sometimes going back and

15       rebidding the whole process?

16                 THE WITNESS:  That may be.  That has not been

17       my experience, but as an attorney, you've probably been

18       on that end of a lot of it.

19                 CHAIRMAN CARTER:  Yes, sir.

20                 THE WITNESS:  But I've been in a lot of

21       contracts and bid on a lot of contracts and didn't win

22       some of them, and that was, you know, the end of the

23       story.

24                 CHAIRMAN CARTER:  And you would agree that

25       time is of the essence in this contract in terms of this

595

1       process?

2                 THE WITNESS:  There is a schedule that needs

3       to be met.

4                 CHAIRMAN CARTER:  Yes, sir.  And also I think

5       with Commissioner Skop in you response that experience

6       was I -- I think to Mr. Anderson you talked about the

7       experience as well, about it being critical,

8       particularly having subject matter knowledge of the

9       equipment.

10                 THE WITNESS:  Yes.  There's a number of

11       factors that would be determinative.

12                 CHAIRMAN CARTER:  And I think initially on in

13       the process, from cost-effectiveness, experience,

14       efficiencies, and success, unless I misread you, you

15       said those are the parameters that you would use in

16       justifying a sole source or a single source contract; is

17       that correct?

18                 THE WITNESS:  Or any contract.

19                 CHAIRMAN CARTER:  Or any contract.

20                 THE WITNESS:  I mean, those are all factors

21       that would need to be considered in selecting the

22       winning bidder.

23                 CHAIRMAN CARTER:  So my problem is, I'm at a

24       loss trying to ascertain why, if that's appropriate,

25       where did this not occur in the case at bar.

596

1                 THE WITNESS:  Well, the point is, I think

2       there may be other firms that also have these same

3       qualifications.

4                 CHAIRMAN CARTER:  But they may be more

5       expensive, or they may take longer time.

6                 THE WITNESS:  Or they may not, and you don't

7       know that until you put it out for bid.

8                 CHAIRMAN CARTER:  But the subject matter

9       knowledge of the equipment is such that there's some

10       prior -- what's the word I'm looking for?

11                 THE WITNESS:  Proprietary.

12                 CHAIRMAN CARTER:  Proprietary knowledge about

13       the equipment.  That's significant, isn't it?

14                 THE WITNESS:  Yes.

15                 CHAIRMAN CARTER:  So you see, I'm just trying

16       to understand --

17                 THE WITNESS:  I guess what we're -- you know,

18       we're not saying that they ended up with the wrong

19       contractor per se.  It's probably the right contractor.

20       But they didn't follow their process, and because they

21       didn't follow the process, you don't really know for

22       sure that it couldn't have been done by somebody else as

23       well for less cost.

24                 CHAIRMAN CARTER:  And in your response to

25       Commissioner Edgar, you said that in the prior time they

597

1       used the sole source, they didn't follow their process.

2       But they followed the same process in this sole source

3       as they did in that sole source; is that correct?

4                 THE WITNESS:  Yes.  I don't know what they did

5       the prior time it came up, but if they did a sole source

6       contract and the corporate preference was for

7       competitive bidding, you know, it appears they didn't

8       follow that.

9                 CHAIRMAN CARTER:  Commissioner Argenziano.

10                 COMMISSIONER ARGENZIANO:  I guess -- can I ask

11       staff a question at this point?

12                 CHAIRMAN CARTER:  You're recognized.

13                 COMMISSIONER ARGENZIANO:  If we are -- let's

14       say this is -- somewhere down the line, the sole

15       sourcing is subject to prudency.  How do you determine

16       prudency at that point if there are no other bids?

17                 MS. BENNETT:  That's a good question.  The

18       standard legal definition of prudency is what would a

19       reasonable, in this situation, nuclear utility do in

20       this set of facts and circumstances.  And you have to

21       weigh the facts and circumstances of what they present

22       to you at that time to determine if they were reasonable

23       or not.

24                 COMMISSIONER ARGENZIANO:  Let me just put it

25       as -- because it's late and my brain is almost somewhere

598

1       else.  Let me ask it as bluntly as I can.  Here's a

2       dilemma we're trying to figure out.  If you go to sole

3       sourcing, how do you ever know that couldn't have gotten

4       a better bid?  How do you know you couldn't have saved

5       the public money?  And that's a concern.  On the other

6       hand, you have designs and proprietary information that

7       are in there.  Are there any rules or statutes that say

8       that they have to go to competitive bidding?  That's my

9       first question.

10                 MS. BENNETT:  There are no rules or statutes.

11       What I believe the witness is telling you is, in the

12       testimony, they have some procedures that FPL

13       established on how to sole source and single source, and

14       I think the witness is telling you --

15                 COMMISSIONER ARGENZIANO:  Okay.  So FPU&L is

16       not following its own procedures is what the witness is

17       probably saying, but yet FPL probably has a full -- a

18       better understanding of what it really needs and how

19       fast and all those things.  My concern was, is there a

20       rule or a statute.  And if not, okay, then I go back to

21       the original question, and we say, well, how do we know

22       that, because you didn't go out for bid, you didn't save

23       anybody any money.  But then again, if there's no rule

24       or statute -- but how do we get to prudency?  And I

25       guess what you're saying is you just take into

599

1       consideration the factors of maybe scheduling, of

2       proprietary information, and that type of thing.

3                 Okay.  All right.  Thank you.

4                 CHAIRMAN CARTER:  Thank you, Commissioner.

5       Commissioner McMurrian.

6                 COMMISSIONER McMURRIAN:  Thank you.  My

7       question is somewhat along those lines, but a little bit

8       different too.  I was looking over your recommendations,

9       and I guess I was just trying to clear something up in

10       my mind with respect to the positions in this case where

11       the parties have agreed to defer a prudence

12       determination on some aspects of the case, where we

13       would have been if we had had the information perhaps

14       sooner.  Had those stipulations to defer a prudence

15       determination on some of those costs in any way affected

16       your recommendations?

17                 THE WITNESS:  No, not in this particular case.

18       On this one particular contract, we feel the company as

19       imprudent in their demonstration or determination that

20       the cost was reasonable.

21                 COMMISSIONER McMURRIAN:  And then to follow up

22       on that, Mr. Chairman, I was looking kind of more

23       specifically, I think, at number 2, where you're talking

24       about withholding a portion of the carrying charges.

25       You suggested 10 percent, and only give it to them if

600

1       they can demonstrate the costs are reasonable in the

2       next hearing cycle.  So you're saying that even with the

3       reasonableness determination that you would suggest, at

4       least with respect to number 2 -- and I realize you have

5       three different recommendations, and they are somewhat

6       varying in degree.  You're saying you would not allow

7       10 percent of those costs as reasonable, and then they

8       would be able to address that in the next hearing cycle

9       as reasonable or prudent, depending on whether or not

10       we're at that final stage with those dollars or still in

11       a reprojection phase.

12                 THE WITNESS:  Yes, yes.

13                 COMMISSIONER McMURRIAN:  Okay.  Thank you.

14                 CHAIRMAN CARTER:  Thank you.  Anything further

15       from the bench?

16                 Mr. McGlothlin.

17                 MR. McGLOTHLIN:  Yes.  Commissioners, I have

18       some redirect, and because of the significance of some

19       of the questions that have been put to the witness, I

20       will need maybe 10 or 12 minutes.  I know it's toward

21       the end of the day. What's your preference in terms

22       of --

23                 CHAIRMAN CARTER:  You have 10 or 12 minutes.

24       Proceed.

25                         REDIRECT EXAMINATION

601

1       BY MR. McGLOTHLIN:

2            Q.   Dr. Jacobs, counsel for FPL asked you to agree

3       that your firm did not submit a bid to an RFP type

4       solicitation from our office.  Do you recall that

5       exchange?

6            A.   Yes.

7            Q.   Now, a request for proposals where the RFP is

8       disseminated to a universe of potential bidders and then

9       everybody provides an answer by the deadline is one way

10       to test the market.  In your opinion, is that the only

11       way that testing the market can be done?

12            A.   No.  It could be done by using a benchmarking

13       process for very similar projects in the same time

14       frame.  Another way would be, if the scope of the

15       project is very well known, you could evaluate the

16       man-hours and hourly rates and so forth to come up with

17       a conclusion of the reasonableness of the cost.

18            Q.   Now, if hypothetically our office were to call

19       you and say, "Dr. Jacobs, what are your qualifications

20       and what would it cost to use you in this case?" and

21       then without your knowledge we called consultants B and

22       C and put the same question to them, would that be

23       another way of testing the market in terms of ensuring

24       that we've assessed the qualifications and chosen the

25       most cost-effective?

602

1            A.   It certainly would.  In fact, that almost is a

2       competitive bidding process, it would seem to me.  It's

3       not an open competitive bidding, but it is competitive

4       bidding.

5            Q.   Now, when you answered Mr. Anderson's question

6       and as you're answering mine, do you know to whom we

7       talked other than yourself?

8            A.   No, I do not.

9            Q.   Now, counsel for FPL distributed the

10       confidential document that consists of the one-page

11       document that you had described as the "back of an

12       envelope" type of analysis; correct?

13            A.   That's correct.

14            Q.   And attached to that is the Word document that

15       was the source of some questions?

16            A.   Yes.

17            Q.   And you recall that counsel for FPL counted

18       for everybody that there were eight pages attached to

19       that and made the point that you did not refer to them

20       in your testimony?

21            A.   That's correct.

22            Q.   I think this is important.  If you will, turn

23       to the Word document, and look at the first page of

24       eight.  Is there anything on this first of eight pages

25       that adds anything to the treatment of the

603

1       reasonableness of the contract that appears on the

2       one-pager that you characterized as "back of the

3       envelope"?

4            A.   No, it does not.

5            Q.   Same question with page 2.  Is there anything

6       on page 2 of 8 that adds to the treatment of the

7       reasonableness of the cost of the contract that you

8       referred to as "back of the envelope"?

9            A.   No.  This is an evaluation of one particular

10       repair option that they were evaluating against other

11       options.

12            Q.   Same question with respect to page 3 of 8.  Is

13       there anything on that page of the Word document that

14       contributes to the analysis of the reasonableness of the

15       contract?

16            A.   No.

17            Q.   Page 4 of 8?

18            A.   No.

19            Q.   Page 5 of 8?

20            A.   No, sir.

21            Q.   Page 6 of 8?

22            A.   No.

23            Q.   Page 7 of 8?

24            A.   No.

25            Q.   Page 8 of 8?

604

1            A.   No.

2            Q.   So this one-pager was before your cross, and

3       it remains the only justification in terms of the

4       reasonableness of the contract that has been offered by

5       FPL in this case?

6            A.   That's correct.

7            Q.   Now, during the questioning, reference was

8       made to the idea that timing and scheduling may be an

9       important consideration; is that correct?

10            A.   That's correct.

11            Q.   Is there a way to conduct competitive bids in

12       a way that incorporates and reflects the importance of

13       the ability to maintain a schedule?

14            A.   Yes, and I thought I had addressed that.  But

15       as part of your request for a proposal, you would have a

16       schedule requirement in the RFP, that you must be able

17       to meet the schedule, and that would incorporate that

18       requirement into your bidding process.

19            Q.   Now, reference was made to experience as an

20       important consideration.  Do you recall that?

21            A.   That's correct.

22            Q.   Is there a way to structure a competitive

23       bidding process that tests the market while

24       incorporating and giving due weight to the importance of

25       experience?

605

1            A.   Yes, of course.  As part of your evaluation of

2       the bids that you receive from the competitive bidding,

3       one of the criteria would be the experience of the

4       bidder in that area.

5            Q.   Reference was made to proprietary information.

6       Do you recall those questions and answers?

7            A.   Yes.

8            Q.   And in response to one question, you

9       acknowledged that Westinghouse would have certain

10       advantages by virtue of its experience and proprietary

11       information.  Do you recall that?

12            A.   That's correct.

13            Q.   Is there a way to structure a competitive

14       solicitation in a manner that would test the market

15       while giving due consideration to any advantages such as

16       proprietary information that the particular vendor may

17       have as an advantage?

18            A.   Well, I think you would have to make them

19       aware in the RFP that there was proprietary information

20       that they would either have to re-create on their own or

21       perhaps get from the original vendor.

22            Q.   On the same subject, in response to a question

23       that made the point that Westinghouse uses proprietary

24       information, you said other companies have similar --

25       may have similar processes.  Would you explain further

606

1       what you meant by that?

2            A.   Yes.  There's a number of -- internationally,

3       a number of companies that design and build nuclear

4       power stations.  There are Japanese companies, French

5       companies.  Some of them are actually bidding and

6       getting their designs licensed in the U.S.  So any of

7       those companies would have the requisite skills and

8       experience to be able to perform those designs.

9            Q.   If a vendor performs work for a utility such

10       as FP&L, and in the course of doing that applies and

11       uses proprietary information, does it follow necessarily

12       that the vendor having proprietary information will

13       always be the vendor of choice in future projects.

14            A.   No, not necessarily.  I think an example of

15       that would be in the supply and fabrication of nuclear

16       fuel.  That's under proprietary information, but that's

17       a highly competitive market, and utilities bid out

18       typically their contracts for nuclear fuel on a regular

19       basis, and sometimes new vendors are chosen and use

20       their own processes to conduct the design.

21            Q.   Let me refer you to the first document that

22       counsel for FPL distributed captioned "Summary of

23       Reasons for Choosing Westinghouse."  Do you have that

24       available to you?

25            A.   Yes.

607

1            Q.   And attached to that is the sole source

2       justification for the Westinghouse contract?

3            A.   That's correct.

4            Q.   Now, counsel for FPL asked you to agree that

5       each of the items enumerated in paragraphs 1 through 4,

6       with quotations from the justification memo, appear in

7       that memo.  Do you recall that question and answer?

8            A.   Yes.

9            Q.   Have you read FPL's rebuttal testimony as it

10       relates to your criticism of the sole source contract

11       awarded to Westinghouse?

12            A.   Yes.

13            Q.   Is there anything in rebuttal testimony

14       offered in support of the contracting process that is

15       contained in their testimony, but does not appear in the

16       justification memo?

17            A.   Not that I can recall.

18            Q.   If you recall, does the justification memo

19       develop to the same extent the theme of the difficulty

20       of using contractors other than one who has the fuel

21       specifications that is contained in the rebuttal

22       testimony?

23            A.   I'm sorry.  Could you repeat that?

24            Q.   I'll move on.

25                 In one answer you referred to the decision of

608

1       the vice president.

2            A.   Yes.

3            Q.   Would you take a moment and explain for the

4       Commissioners how the management procedure that you've

5       identified as NP 1100 works with respect to the standard

6       for competitive bidding, the preparation of a

7       justification memo in support of a departure from that,

8       and the role of the vice president to whom you referred

9       in your answer?

10            A.   Yes.  If the manager of the project decides

11       that he wants to use a sole source bid, he is required

12       to develop the reasons and the rationale in what's

13       called a sole source justification memo.  And in that

14       memo, he puts down -- there are certain requirements

15       that shows why it's needed, why it would be to the

16       company's advantage, and how they have determined that

17       the costs will be reasonable use being sole source.  And

18       then this is put together in a memo and submitted to a

19       vice president, or even perhaps a higher level manager,

20       depending on the value of the contract, for his

21       signature and approval.

22            Q.   And when it's presented to the vice president,

23       what decision, what choice does the vice president make

24       based upon the justification memo offered?

25            A.   Well, he either agrees that it can proceed as

609

1       a sole source contract, or if he rejects that, then they

2       would be forced to go back to bid it competitively.

3                 MR. McGLOTHLIN:  Those are all my questions on

4       redirect.

5                 CHAIRMAN CARTER:  Thank you, Mr. McGlothlin.

6       Let's look at the exhibits.

7                 MR. McGLOTHLIN:  We move Exhibits 29 through

8       35.

9                 CHAIRMAN CARTER:  Twenty-eight.

10                 MR. McGLOTHLIN:  Well, 28 through 35.

11                 CHAIRMAN CARTER:  Twenty-eight through 35?

12                 MR. McGLOTHLIN:  Twenty-eight through 35.

13                 CHAIRMAN CARTER:  Any objections?

14                 MR. ANDERSON:  No, but I just had a couple of

15       very, very short recross questions.

16                 MR. McGLOTHLIN:  That's very unusual.  I'm not

17       sure that I've done anything by redirect should occasion

18       recross.

19                 CHAIRMAN CARTER:  Mr. Anderson, is it

20       absolutely, positively necessary?

21                 MR. ANDERSON:  I think it will be helpful to

22       you, because it will tell you who to ask about this.

23                 CHAIRMAN CARTER:  Mr. McGlothlin, I'll give

24       you leave -- after he asks further questions, I'll give

25       you leave for further redirect.

610

1                 MR. McGLOTHLIN:  All right.

2                 CHAIRMAN CARTER:  You're recognized.

3                 MR. ANDERSON:  Thank you.

4                          RECROSS-EXAMINATION

5       BY MR. ANDERSON:

6            Q.   At the top of the confidential document -- do

7       you have that in front of you?

8            A.   No.  I just put it away, but I'll dig it back

9       out.

10            Q.   Do you see who that is to?

11            A.   Yes.

12            Q.   That's William Labbe, our witness and project

13       director; is that right?

14            A.   That's correct.

15            Q.   Okay.  Who do you think knows more about this

16       document, this attachment, and this procurement, you or

17       Mr. Labbe?

18                 MR. McGLOTHLIN:  Object.  That's not anything

19       that flows from any question I posed to the witness

20       during redirect.

21                 MR. ANDERSON:  Well, he speculated about all

22       kinds of things, about how the document was not related

23       to the decision.  And in fact, this document is a

24       important element of the decision that Mr. Labbe knew

25       and relied on.  And the right question there is, who

611

1       would know these facts, is it this witness who's

2       speculating, or is it our witness, Mr. Labbe, who will

3       be available to testify.  The document, by the way,

4       already speaks for itself.  That's was my only point.

5                 MR. McGLOTHLIN:  That's completely

6       argumentative and does not demonstrate any basis for

7       recross that stems from anything I asked the witness.

8                 CHAIRMAN CARTER:  You know, I think this a

9       good point of -- you always have a point of beginning,

10       and you need to have a point of ending too.  And we've

11       entered the -- without objection, the exhibits have been

12       entered in evidence.

13                 (Exhibits Number 28 through 35 were admitted

14       into the record.)

15                 CHAIRMAN CARTER:  We will pick up tomorrow

16       morning at 9:30.

17                 (Proceedings recessed at 5:20 p.m.)

18

19

20

21

22

23

24

25

612

1                        CERTIFICATE OF REPORTER

2

3       STATE OF FLORIDA:

4       COUNTY OF LEON:

5                  I, MARY ALLEN NEEL, Registered Professional

6       Reporter, do hereby certify that the foregoing

7       proceedings were taken before me at the time and place

8       therein designated; that my shorthand notes were

9       thereafter translated under my supervision; and the

10       foregoing pages numbered 370 through 611 are a true and

11       correct record of the aforesaid proceedings.

12                 I FURTHER CERTIFY that I am not a relative,

13       employee, attorney or counsel of any of the parties, nor

14       relative or employee of such attorney or counsel, or

15       financially interested in the foregoing action.

16                 DATED THIS 12th day of September, 2008.

17

18

____________________________

19                                 MARY ALLEN NEEL, RPR, FPR

2894-A Remington Green Lane

20                                 Tallahassee, Florida  32308

(850) 878-2221

21

22

23

24

25