613

1                             BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

DOCKET NO. 080009-EI

3

In the Matter of:

4

NUCLEAR COST RECOVERY CLAUSE.

5                                /

6

7

8                              VOLUME 4

9                        Pages 613 through 766

10             ELECTRONIC VERSIONS OF THIS TRANSCRIPT ARE

A CONVENIENCE COPY ONLY AND ARE NOT

11               THE OFFICIAL TRANSCRIPT OF THE HEARING,

THE .PDF VERSION INCLUDES PREFILED TESTIMONY.

12

13

PROCEEDINGS:        HEARING

14

BEFORE:             CHAIRMAN MATTHEW M. CARTER, II

15                       COMMISSIONER LISA POLAK EDGAR

COMMISSIONER KATRINA J. McMURRIAN

16                       COMMISSIONER NANCY ARGENZIANO

COMMISSIONER NATHAN A. SKOP

17

DATE:               Friday, September 12, 2008

18

TIME:               Commenced at 9:40 a.m.

19                       Concluded at 12:14 p.m.

20   PLACE:              Betty Easley Conference Center

Room 148

21                       4075 Esplanade Way

Tallahassee, Florida

22

REPORTED BY:        LINDA BOLES, RPR, CRR

23                       Official FPSC Reporter

(850) 413-6734

24

APPEARANCES:        (As heretofore noted.)

25

FLORIDA PUBLIC SERVICE COMMISSION

614

1                              I N D E X

2                              WITNESSES

3

NAME:                                               PAGE NO.

4

5   KATHY L. WELCH

6        Prefiled Direct Testimony Inserted              621

7   CARL VINSON and ROBERT LYNN FISHER (Panel)

8        Direct Examination by Mr. Young                 629

Joint Prefiled Direct Testimony Inserted        633

9        Cross Examination by Mr. McGlothlin             638

Cross Examination by Ms. Cano                   645

10        Redirect Examination by Mr. Young               647

11   WILLIAM P. LABBE, JR.

12        Direct Examination by Mr. Anderson              655

Prefiled Rebuttal Testimony Inserted            657

13        Cross Examination by Mr. McGlothlin             671

Cross Examination by Mr. McWhirter              692

14        Redirect Examination by Mr. Anderson            707

15   STEVEN D. SCROGGS

16        Direct Examination by Mr. Anderson              712

Prefiled Rebuttal Testimony Inserted            714

17        Cross Examination by Mr. McGlothlin             724

18   JOHN J. REED

19        Direct Examination by Ms. Pettus                734

Prefiled Rebuttal Testimony Inserted            736

20        Cross Examination by Mr. McGlothlin             757

21

22

23

24   CERTIFICATE OF REPORTER                              766

25

FLORIDA PUBLIC SERVICE COMMISSION

615

1                              EXHIBITS

2

NUMBER:                                        ID.  ADMTD.

3

4   36                                                   620

5   37                                                   620

6   38                                                   620

7   39                                                   620

8   40                                                   654

9   44   FPL Sole Source Justification                   617

10   45   (Confidential) Modification Estimate            618

Summary

11

46   NADB Procurement Policies and Procedures  760   764

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

616

1                         P R O C E E D I N G S

2             (Transcript follows in sequence from Volume 3.)

3             CHAIRMAN CARTER:  Good morning to one and all.

4             COMMISSIONER ARGENZIANO:  Good morning.

5             CHAIRMAN CARTER:  Hope everyone is doing well this

6   morning.

7             Staff, preliminary matters before we get started

8   on -- I think when we finished yesterday we finished with OPC's

9   case in chief on OPC and we're beginning today with staff's

10   case.  But are there some preliminary matters?

11             MS. BENNETT:  Yes, Chairman.  There are two exhibits

12   that we looked at yesterday that did not get into the record.

13             Exhibit 44 was Nuclear Plant Overview and Sole Source

14   Justification and 45 was a confidential FPL exhibit.  At least

15   I've got them identified as 44 and 45.  I don't know whether

16   FPL wants to have it entered into the record and if there's any

17   objections to it.

18             CHAIRMAN CARTER:  Mr. Anderson.

19             MR. ANDERSON:  FPL offers them into evidence.

20             CHAIRMAN CARTER:  Okay.

21             MR. McGLOTHLIN:  I think I'll object to 45 for lack

22   of relevance.

23             CHAIRMAN CARTER:  For 45?

24             MR. McGLOTHLIN:  Yes.

25             CHAIRMAN CARTER:  And 45 was again -- what's 45?

FLORIDA PUBLIC SERVICE COMMISSION

617

1             MS. BENNETT:  45 was the confidential exhibit.  I'm

2   struggling to explain what it is.  I know that we --

3             CHAIRMAN CARTER:  Let's do this then, let's back up

4   to 44 first.  There's no objections on 44.  Give me a title for

5   44.

6             MS. BENNETT:  44 I have as Nuclear Overview and Sole

7   Source Justification.

8             CHAIRMAN CARTER:  How about sole source, FPL Sole

9   Source Justification?  Does that work for you guys?

10             MR. McGLOTHLIN:  I need a bit more help in

11   identifying which document that was.

12             CHAIRMAN CARTER:  I beg your pardon?

13             MR. McGLOTHLIN:  Was that one of FPL's handouts

14   yesterday?

15             MS. BENNETT:  Yes.  It was the, the nuclear plant

16   overview and then the one with the sole source.

17             CHAIRMAN CARTER:  Yes.  It's the one with the

18   pictures, the color coded.

19             MR. McGLOTHLIN:  Okay.  No objection to that one.

20             CHAIRMAN CARTER:  Okay.  All right.

21             (Exhibit 44 admitted into the record.)

22             Now the objection is on 45, which is what's been

23   shown as Exhibit B which is the redacted rebuttal testimony.

24   Is that --

25             MR. McGLOTHLIN:  I'm going to withdraw my objection.

FLORIDA PUBLIC SERVICE COMMISSION

618

1             CHAIRMAN CARTER:  I beg your pardon?

2             MR. McGLOTHLIN:  I withdraw my objection.

3             CHAIRMAN CARTER:  Okay.  Great.  I love it when a

4   plan comes together.

5             Subject for this one?

6             MS. BENNETT:  If Mr. Anderson would help me here

7   because I don't know which parts are confidential and which are

8   not.

9             MR. ANDERSON:  A good name for this would be FPL

10   Modification Cost Estimate Summary.

11             CHAIRMAN CARTER:  That's -- let's try, let's break it

12   down a little more, shorten it.  Let's shorten it a little bit.

13             MR. ANDERSON:  Just call it Modification Estimate

14   Summary.  Is that okay?

15             CHAIRMAN CARTER:  Excellente.  Modification Estimate

16   Summary.

17             MS. BENNETT:  And that would be Number 45.

18             CHAIRMAN CARTER:  And without objection, show it

19   done.  Okay.

20             (Exhibit 45 admitted into the record.)

21             MR. ANDERSON:  Could this please be considered my

22   verbal notice of intent with respect to confidentiality for

23   that exhibit, which will be followed by the appropriate

24   paperwork?

25             CHAIRMAN CARTER:  Okay.  That'll be fine.

FLORIDA PUBLIC SERVICE COMMISSION

619

1             Now before staff gets into its case in chief, let me

2   ask the parties, anything preliminary from the parties before

3   we go forward?

4             Okay.  Hearing none, Ms. Bennett, you're recognized.

5             MS. BENNETT:  Staff's witness Kathy L. Welch has been

6   excused from the proceeding.  We would ask that her testimony

7   be entered into the record as if read.

8             CHAIRMAN CARTER:  Any objections?  The prefiled

9   testimony of Witness Welch will be entered into the record as

10   though read.

11             MS. BENNETT:  And with Ms. Welch's testimony she

12   provided four exhibits.  They are identified as 36, 37, 38 and

13   39.  We'd ask that they be entered into the record at this time

14   also.

15             CHAIRMAN CARTER:  Hang on a second.  Before we do

16   that, let me ask the parties, are there any objections to

17   Ms. Welch -- I think she's a stipulated witness.  Is there any

18   objection to her being stipulated as a witness?

19             MR. ANDERSON:  No objection.

20             MR. McWHIRTER:  No objection.

21             MR. McGLOTHLIN:  No objection.

22             CHAIRMAN CARTER:  Commissioners?  Okay.  Now that

23   we've got her in, now let's deal with her exhibits.  You're

24   recognized.

25             MS. BENNETT:  Exhibits 36, 37, 38 and 39 are

FLORIDA PUBLIC SERVICE COMMISSION

620

1   sponsored by Ms. Welch.  We'd ask that they be entered into the

2   record at this time.

3             CHAIRMAN CARTER:  Okay.  Exhibits 36 through 39.  Are

4   there objections?  Without objection, show it done.  Exhibits

5   36 through 39.

6             (Exhibits 36, 37, 38 and 39 admitted into the

7   record.)

8             Okay.  Ms. Bennett.

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

629

1             MS. BENNETT:  And with that we would call Carl Vinson

2   and Lynn Fisher to the stand.

3             CHAIRMAN CARTER:  Mr. Vinson and Mr. Fisher, you've

4   already been sworn.  No problem.  Good morning and welcome

5   again.

6             MR. VINSON:  Good morning.

7             CHAIRMAN CARTER:  You're recognized.

8             MR. YOUNG:  Thank you, sir.

9   Whereupon,

10                 CARL VINSON and ROBERT LYNN FISHER

11   were called as witnesses on behalf of Staff and, having been

12   duly sworn, testified as follows:

13                         DIRECT EXAMINATION

14   BY MR. YOUNG:

15        Q    Good morning, gentlemen.

16        A    (By Mr. Vinson) Good morning.

17        A    (By Mr. Fisher) Good morning.

18        Q    You've been sworn; correct?

19        A    (By Mr. Vinson) Yes.

20        A    (By Mr. Fisher) Yes.

21        Q    All right.  Can you please state your name and

22   business address for the record, please?

23        A    (By Mr. Vinson) Carl Vinson, 2540 Shumard Oak

24   Boulevard, Tallahassee, Florida.

25        A    (By Mr. Fisher) Robert Lynn Fisher, and the business

FLORIDA PUBLIC SERVICE COMMISSION

630

1   address is 2540 Shumard Oak Boulevard.

2        Q    By whom are you employed and in what capacity?

3        A    (By Mr. Vinson) Florida Public Service Commission as

4   a Public Utilities Supervisor.

5        A    (By Mr. Fisher) And I'm employed by the Florida

6   Public Service Commission as a Government Analyst II.

7        Q    You have jointly, you have jointly prefiled testimony

8   consisting of five pages in this docket; correct?

9        A    (By Mr. Vinson) Yes.

10        A    (By Mr. Fisher) That's correct.

11        Q    And part of that testimony pertains to Florida Power

12   & Light; correct?

13        A    (By Mr. Vinson) Yes.

14        A    (By Mr. Fisher) Yes.

15        Q    Do you have any changes or corrections to that

16   testimony?

17        A    (By Mr. Vinson) Yes.  I have the same correction that

18   I made yesterday in the, in presenting this testimony regarding

19   Progress Energy, and that is on Page 2, Line 9, I would like to

20   delete the words "In each case" in the sentence that begins

21   with those words so that that sentence would now begin "The

22   assignments required extensive."

23        Q    Okay.  With that change, if I were to ask you the

24   same questions today as in your joint prefiled testimony, would

25   your answers be the same?

FLORIDA PUBLIC SERVICE COMMISSION

631

1        A    (By Mr. Vinson) Yes, they would.

2        A    (By Mr. Fisher) Yes.

3             MR. YOUNG:  Mr. Chairman, we did this for Progress

4   Energy Florida, but at this time I'd ask that the joint

5   prefiled testimony be inserted into the record as though read

6   for Florida Power & Light.

7             CHAIRMAN CARTER:  The prefiled testimony will

8   be entered into the record as though read for Florida Power &

9   Light.

10   BY MR. YOUNG:

11        Q    Do you have one exhibit attached to your testimony

12   which is the project management internal controls relating to

13   Florida Power & Light nuclear plant uprate and construction

14   projects?

15        A    (By Mr. Vinson) Yes.

16        Q    Do you have any changes or corrections to that

17   exhibit?

18        A    No.

19             MR. YOUNG:  Mr. Chairman, for identification purposes

20   that will be Number 40 on the staff Comprehensive Exhibit List,

21   VF-2.

22             CHAIRMAN CARTER:  For identification purposes

23   Commissioners, that's number 40 on our list and VF-2.  Thank

24   you.

25             MR. YOUNG:  Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

632

1             CHAIRMAN CARTER:  For identification.

2

3

4

5

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

638

1   BY MR. YOUNG:

2        Q    Can you please summarize your testimony?

3        A    (By Mr. Vinson) Yes, sir.

4             Commissioners, our testimony presents the management

5   audit report regarding the internal controls for project

6   management that Florida Power & Light is using on its uprate

7   projects and its new unit construction at the Turkey Point

8   6 and 7 units.  We also present in our testimony some comments

9   about the nuclear cost recovery process that the Commission is

10   using.

11             MR. YOUNG:  With that, Mr. Chairman, we tender the

12   witnesses for cross.

13             CHAIRMAN CARTER:  Thank you, Mr. Young.

14             Mr. McGlothlin.

15                          CROSS EXAMINATION

16   BY MR. McGLOTHLIN:

17        Q    Good morning.

18        A    (By Mr. Vinson) Good morning.

19        A    (By Mr. Fisher) Good morning.

20        Q    I believe, based upon the way questions were divvied

21   up in the deposition, the questions I have this morning are for

22   Mr. Vinson.  But if I'm mistaken about that, please correct me.

23             As I understand it, one of staff's points in its

24   testimony and in Exhibit 40 or VF-2 is that with respect to

25   this initial cycle of hearing activities you were constrained

FLORIDA PUBLIC SERVICE COMMISSION

639

1   in terms of the scope and depth of the analysis that you were

2   able to perform by the, by the time requirements and by the

3   fact that we're engaged in a new undertaking.  Is that a fair

4   summary of your comments at the outset?

5        A    (By Mr. Vinson) Yes, largely the time available.

6        Q    Okay.  With respect to Exhibit VF-2, on Page 20 of

7   that document this statement appears in bold following

8   discussion of contractor selection.  "FPL appears to have

9   followed its contractor selection procedures.  Given the unique

10   challenges and circumstances of the nuclear industry, FPL's use

11   of sole source selections for the uprate project to date is in

12   keeping with reasonable business practices."  And that is with

13   respect to the uprate projects; correct?

14        A    (By Mr. Vinson) Yes.

15        Q    And a similar statement with respect to the new units

16   appears on Page 38; correct?

17        A    (By Mr. Vinson) Yes.

18        Q    Turning back to Page 19 of the exhibit, you have a

19   chart there displaying information about one, two, three, four

20   contracts.  Do I understand correctly that these four contracts

21   comprise contracts in excess of $1 million value that are

22   screened and identified by the nuclear filing requirements that

23   FPL prepared?

24        A    (By Mr. Vinson) Yes.

25        Q    Of course, FPL in conjunction with its uprate

FLORIDA PUBLIC SERVICE COMMISSION

640

1   activities entered into numerous other contracts; is that

2   correct?  The universe of contracts associated with the uprate

3   is far larger than these four.

4        A    (By Mr. Vinson) Yes.  There are additional contracts.

5        Q    And the two of you did in the course of your review

6   look at contracts other than these four.

7        A    (By Mr. Vinson) That's correct.

8        Q    And some of those other contracts were either single

9   source or sole source contracts; correct?

10        A    (By Mr. Vinson) Yes.

11        Q    Do I understand correctly that with respect to the

12   depth of review these four that were filtered by the criteria

13   of the NFRs received more attention than the others that you

14   reviewed?

15        A    (By Mr. Vinson) That is correct.

16        Q    And is it -- do I also understand correctly that with

17   respect to the others, not these four but the others, you did

18   not assess (phonetic) whether FPL followed its contractor

19   selection criteria to depart from competitive bidding on those

20   contracts?

21        A    (By Mr. Vinson) I think that would be a correct

22   statement.

23        Q    So, so when we look at this statement that says "FPL

24   appears to have followed its contractor selection procedures,"

25   you're referring solely to the four contracts that exceeded

FLORIDA PUBLIC SERVICE COMMISSION

641

1   $1 million in costs that are shown on Page 19.

2        A    (By Mr. Vinson) Yes.

3        Q    Now I believe yesterday you mentioned at the outset

4   of the testimony in the first phase that the two of you

5   performed a management audit and not a financial audit.  Do you

6   recall that statement?

7        A    (By Mr. Vinson) Right.  That's correct.

8        Q    Is that true of your work on the FPL aspects also?

9        A    (By Mr. Vinson) Yes.

10        Q    Do I understand correctly that in your review of

11   these four contracts and the others you were not concerned with

12   assessing the reasonableness of the amounts of the contract?

13        A    (By Mr. Vinson) Right.  Not the dollar amount.

14        Q    Not the dollar amount.  Well, the dollar amount or

15   whether that dollar amount was reasonable; correct?

16        A    (By Mr. Vinson) Correct.

17        Q    Okay.  Now in conjunction with your review you became

18   familiar with what we've referred to as NP-1100 and the, and

19   the corresponding contractor selection criteria that FPL

20   follows for the new units, have you not?

21        A    (By Mr. Vinson) Yes.

22        Q    Is it your understanding that FPL's standard for

23   procurement is competitive bidding, that it prefers competitive

24   bidding?

25        A    (By Mr. Vinson) Yes.  That's stated in the

FLORIDA PUBLIC SERVICE COMMISSION

642

1   procedures.

2        Q    And do you approve of that?  Do you think that

3   competitive bidding has advantages relative to other forms of

4   procurement?

5        A    (By Mr. Vinson) Yes, it does in many cases.

6        Q    Okay.  And is it your understanding that sole source

7   or single source contracts are exceptions to the otherwise

8   acceptable standard of competitive bidding?

9        A    (By Mr. Vinson) For FPL that is, that is as stated in

10   their procedures.  That's correct.

11        Q    Okay.  And to justify the departure from competitive

12   bidding, FPL is required by its procedures to show that

13   competitive bidding is infeasible either because there's only

14   one source or because, even though there's more than one

15   source, for compelling reasons the contract should be awarded

16   to one without soliciting bids.  Is that the way it works?

17        A    (By Mr. Vinson) I'm not sure I followed your question

18   in its entirety.  Could you repeat that?

19        Q    All right.  We've established that competitive

20   bidding is the standard and that sole source and single source

21   contracts are an exception that have to be justified.

22        A    (By Mr. Vinson) Yes.

23        Q    Okay.  With respect to the required justification,

24   the first aspect of that is to, is that FPL must demonstrate to

25   its internal decision-maker that for whatever reason, either

FLORIDA PUBLIC SERVICE COMMISSION

643

1   because there's only one provider or there's business reasons

2   why bids should not be solicited, the contract should be

3   awarded without first entertaining bids.  In other words,

4   competitive bidding is infeasible under the circumstances.

5             MR. YOUNG:  Mr. Chairman, at this time I'm going to

6   object to that line of questioning.  I think this might be

7   outside the scope of Mr. Carl Vinson and Mr. Robert Lynn

8   Fisher's testimony.  So I would basically object, object based

9   on outside the scope of testimony.

10             MR. McGLOTHLIN:  Mr. Chairman --

11             CHAIRMAN CARTER:  Mr. McGlothlin.

12             MR. McGLOTHLIN:  Yes.  The, the conclusion that staff

13   is sponsoring is that in their view FPL has followed their

14   contractor selection criteria.  I think fundamental to that is,

15   is a discussion of what those criteria are that in staff's view

16   FPL has followed.  I'm simply trying to establish the framework

17   that, that they considered in, in their analysis.

18             MR. YOUNG:  With that, Mr. Chairman, I'll make it

19   easier.  I'll withdraw that objection.

20             CHAIRMAN CARTER:  Okay.  You may proceed.

21             MR. VINSON:  To answer the question, I believe you're

22   asking me to ascertain the intent of the FPL procedure.  To the

23   extent that's what you're asking, I believe that's the general

24   intent of that procedure.

25   BY MR. McGLOTHLIN:

FLORIDA PUBLIC SERVICE COMMISSION

644

1        Q    Is it, is it true also that there's a second prong to

2   the criteria, and that is that when FPL seeks permission to

3   depart from competitive bidding, it has to provide assurance

4   that the cost of the sole source or single source contract is

5   reasonable?

6        A    (By Mr. Vinson) I believe that's correct.

7        Q    Okay.  And again with respect to the statement that

8   appears on Pages 20 and 38 of Exhibit 40, when you say that FPL

9   appears to have followed its contractor selection procedures,

10   you are speaking only to the contracts that exceed $1 million

11   and only to the decision to go sole source and single source,

12   but not to the reasonableness of the resulting contracts.

13        A    (By Mr. Vinson) That's correct.

14             MR. McGLOTHLIN:  I have no further questions.

15             CHAIRMAN CARTER:  Thank you, Mr. McGlothlin.

16             Mr. McWhirter.

17             MR. McWHIRTER:  No, sir.

18             CHAIRMAN CARTER:  McWhirter.

19             MR. McWHIRTER:  I have no questions.

20             CHAIRMAN CARTER:  I gave you a promotion today.

21             Mr. Twomey.

22             MR. TWOMEY:  No, sir.

23             MS. CANO:  Good morning.  Thank you.

24             CHAIRMAN CARTER:  You're recognized.

25                          CROSS EXAMINATION

FLORIDA PUBLIC SERVICE COMMISSION

645

1   BY MS. CANO:

2        Q    I just have a few questions for you, Mr. Vinson.

3        A    (By Mr. Vinson) Okay.

4        Q    You conducted an audit of the project management

5   controls used by FPL for both the uprates and Turkey Point

6   6 and 7; correct?

7        A    (By Mr. Vinson) Yes.

8        Q    And the result of that audit was a 46-page audit

9   report.

10        A    (By Mr. Vinson) I think it's 41.

11        Q    Okay.  Thank you.

12        A    (By Mr. Vinson) Plus the testimony would total 46.

13        Q    Okay.  And in that report you made certain findings

14   or reached certain conclusions with respect to FPL's project

15   management controls; correct?

16        A    (By Mr. Vinson) Yes.

17        Q    Okay.  Certain of those controls and procedures that

18   you reviewed are specifically designed to manage contractor

19   selection; right?

20        A    (By Mr. Vinson) Yes.

21        Q    And with respect to the uprates project you

22   determined both that FPL followed its procedures and that its

23   selection of those sole source contractors was in keeping with

24   reasonable business practices; correct?

25        A    (By Mr. Vinson) That's correct.

FLORIDA PUBLIC SERVICE COMMISSION

646

1        Q    And similarly with respect to the Turkey Point

2   6 and 7 project you concluded that FPL followed its contractor

3   selection procedures and that FPL's use of sole source

4   contractors was in keeping with reasonable business practices.

5        A    (By Mr. Vinson) Yes.  That's correct.

6        Q    Okay.  Now the scope of your detailed review of the

7   contracts was for those that were in excess of $1 million.  Is

8   that what you stated?

9        A    (By Mr. Vinson) Yes.

10        Q    But in your review of the smaller contracts did you

11   see anything that would lead you to believe that FPL would not

12   follow its procedures with respect to those?

13             MR. McGLOTHLIN:  Objection.  The witness has stated

14   in earlier answers that they did not consider --

15             CHAIRMAN CARTER:  You went down this line, so I'm

16   going to allow her some leverage on that.  You opened this area

17   up, so I'm going to allow her to ask a question on that matter.

18   You may proceed.

19             MS. CANO:  Thank you.

20   BY MS. CANO:

21        Q    Would you like me to repeat the question?

22        A    (By Mr. Vinson) Regarding -- no.  Regarding the

23   smaller contracts, we did not see anything that gave us

24   concern.

25             MS. CANO:  Okay.  Thank you.  That's all the

FLORIDA PUBLIC SERVICE COMMISSION

647

1   questions I have.

2             CHAIRMAN CARTER:  Thank you.  Commissioners?  Staff?

3             MR. YOUNG:  Just two quick questions.

4                        REDIRECT EXAMINATION

5   BY MR. YOUNG:

6        Q    Can you briefly tell me what was the purpose of your

7   audit?

8        A    (By Mr. Vinson) The purpose of our audit was, was to

9   establish and to examine the internal control procedures by

10   which the company will manage and keep track and control both

11   the costs and the schedule of these major projects.

12        Q    Okay.  Did you -- and the determination that you

13   reached, you said FPL -- did you say FPL followed its

14   procedures or appeared to follow its procedures?

15        A    (By Mr. Vinson) The statement reads, "FPL appears to

16   have followed its contractor selection procedures."

17        Q    Do you think that's different from "FPL followed its

18   procedures"?

19        A    (By Mr. Vinson) I'm sorry.  Could you repeat that?

20        Q    Do you think that's distinguishable from the

21   statement "FPL followed its procedures"?

22        A    (By Mr. Vinson) It's barely to be distinguished from

23   that.  There's barely a difference.  Of course, an audit by

24   definition is somewhat of a sampling.  We do not see every

25   effort that FPL made over this period of time.  We do not know

FLORIDA PUBLIC SERVICE COMMISSION

648

1   every single analysis made.  But from the work we did, from the

2   information we gathered they appear to have followed their

3   procedures.

4             MR. YOUNG:  Okay.  Thank you, Mr. Chairman.  No

5   further questions.

6             CHAIRMAN CARTER:  Commissioner Argenziano.

7             COMMISSIONER ARGENZIANO:  I guess just a question to

8   make sure it's -- in reading, I guess, hold on one second, your

9   direct on Page 5, you do indicate though that -- let me read

10   it.  We note that Progress -- sorry -- and Florida Power &

11   Light, witness did prefile testimony -- hold on a minute.

12   "However, we believe that even more extensive and detailed and

13   examinations of internal controls and project management

14   controls should be performed to fully substantiate their

15   adequacy and effectiveness."  Is that -- that is correct?

16             MR. VINSON:  Yes.

17             COMMISSIONER ARGENZIANO:  Okay.  And in the future

18   what is your position?  What do you do as public service staff

19   to ensure that that is taking place?

20             MR. VINSON:  Well, as I stated yesterday, there are

21   likely to be meetings among staff after this initial

22   run-through of the nuclear cost recovery proceeding to

23   strategize and plan for next year.  And our role is not

24   certain, it's not been defined yet.  As I said yesterday, I

25   believe that the role we played this year needs to be carried

FLORIDA PUBLIC SERVICE COMMISSION

649

1   out through a combination of whatever actors or whatever means

2   are used, but our role is not certain.

3             And part of this, let me add this, that part of

4   what I stated on Page 5, I mean, I'm sorry, on Page, yeah,

5   Page 5 pertains to additional activity by the companies that

6   could be done.  So there's two sides of it, what staff does and

7   what the companies do.

8             COMMISSIONER ARGENZIANO:  Right.  And I understand

9   that.  But in, in reading those words what I see is that we

10   think that so far they've, you know, done pretty good here and

11   it's looking okay, but we think that more extensive and more,

12   you know, examination needs to be done to make sure that we

13   have this adequacy and effectiveness.

14             MR. VINSON:  Right.  More by the company and then a

15   continued effort like we've done.

16             COMMISSIONER ARGENZIANO:  So when you say your role

17   is not certain in the future, I'm not sure who goes and checks

18   if they have continued to strengthen that, the effectiveness

19   and the adequacy.  Is that part of your role in the future or

20   do you --

21             MR. VINSON:  It could, it could be, and I would

22   encourage it to be a role of staff.  I'm speaking here

23   specifically for my --

24             COMMISSIONER ARGENZIANO:  So does that, does that

25   come, I'm sorry, from direction from the Commission?  How does

FLORIDA PUBLIC SERVICE COMMISSION

650

1   that happen?  Because if people are looking at this out

2   there -- I'm having a question if you're telling me you're not

3   certain of your role.  Do we give them that, that direction?

4   And if somebody could help me.  Because if somebody is watching

5   this at home, they probably have the same question.  I'm not

6   certain and --

7             CHAIRMAN CARTER:  I believe, I believe we do in that

8   process because in addition to looking at the reasonableness

9   and the prudency, I always mess that word up when I say

10   prudency, but as we look at the prudency and look at the

11   reasonableness and look at whether they dotted the I's and

12   crossed the T's as well as was the money spent in a manner

13   consistent with what they proposed to do, we will look at all

14   of those things.  And as staff brings those recommendations to

15   us after having conducted those audits they'll say we think we

16   need more information here or more information here so that we

17   can give you, the Commission, an opportunity to look at all of

18   the facts and have an open and transparent process.

19             COMMISSIONER ARGENZIANO:  And I appreciate that.  But

20   I'd like to get it on record that I would like to make sure

21   that staff has that direction to, to keep looking to making

22   sure.  I'm pleased that the company, you know, has done a

23   pretty good job.  But as we mentioned yesterday with Progress,

24   the same thing applies here if -- and I think I asked the

25   question yesterday, if it's, if it's sole bidding that has

FLORIDA PUBLIC SERVICE COMMISSION

651

1   occurred and they have the right to do that, then how do we

2   know at the point -- all we have left to us at that point is

3   prudency.  And I asked the question, how do we know what is

4   prudent if we don't have other bids?

5             So I would hope that staff would continue to work

6   with the company to make sure that, that there is, that we can

7   prove prudency.  And, you know, if we have a combination of

8   factors that have to go into determining what is prudent at

9   that time, I don't want staff at that time smack up against

10   that time we have to make a decision to finally say, well, you

11   know, we're just looking back into it.  And I'd like continued

12   direction to the staff to, to work with the company and hoping

13   that they do improve.

14             I mean, I'm glad that they are where they are.  But

15   just for safeguarding I'd like to make sure that's on the

16   record and that people maybe at home understand.  Because when

17   you hear staff say, well, we're not sure what our role is, that

18   would make me scratch my head and go, oh, you know.  So I think

19   explaining that helped me and maybe anybody who is watching at

20   home.

21             CHAIRMAN CARTER:  And, staff, for the record, staff,

22   for the record as we proceed further, we want all of this

23   information readily available to all of the Commissioners so

24   that we can have an open and transparent process so that the

25   people -- I mean, I think it's important that they understand

FLORIDA PUBLIC SERVICE COMMISSION

652

1   what we're doing and why we're doing it the way we're doing it.

2   And I think that, staff, govern yourselves accordingly when you

3   bring back to us the recommendations and also the information

4   both from our legal staff as well as from technical staff.

5             MS. BENNETT:  That's correct.  We -- the legal staff

6   and the technical staff will be following through with the,

7   especially the recommendations that we've heard from the

8   auditors.  It's, it's more a matter of which person is assigned

9   the job.

10             CHAIRMAN CARTER:  Okay.

11             COMMISSIONER ARGENZIANO:  Commissioner, that sounds a

12   lot better than we're not certain what we're doing.

13             MR. VINSON:  Right.  That -- could I just add --

14             COMMISSIONER ARGENZIANO:  And I don't mean that

15   derogatory against you.

16             MR. VINSON:  Right.  I just wanted to add that in, I

17   think what Ms. Bennett is saying that in our role as auditors

18   we're not in the decision-making to decide and assign

19   (phonetic).  But by virtue of the fact that they engaged us, I

20   believe they would have those same concerns that you have and

21   want to continue with our effort.

22             COMMISSIONER ARGENZIANO:  Absolutely.  Thank you.

23             CHAIRMAN CARTER:  Okay.  Thank you.

24             Commissioner Skop.

25             COMMISSIONER SKOP:  Thank you, Mr. Chairman.

FLORIDA PUBLIC SERVICE COMMISSION

653

1             And I think Commissioner Argenziano's points are well

2   taken.  It seems, at least listening to the discussion from my

3   colleagues as well as the points being made, that OPC, their

4   central issue seems to be directed more towards that the

5   sufficiency of the justification provided within the sole

6   source procurement justification, not necessarily that FPL has

7   departed from its underlying procedures or done anything wrong,

8   but also too that perhaps that, you know, competitive bidding

9   would be the preferred course over sole source procurement.

10   But in instances, nuclear, like I say, I think that there's,

11   there's not very many people that you can go to in some cases.

12             But I did have two quick questions for staff, if I

13   could, and just to try and clarify the point.  Because I think

14   that, you know, I've been trying to follow along and I'm pretty

15   good at that, but I think it's getting blurred in terms of what

16   the issues were.  And, again, I'm trying to better understand

17   what OPC is trying to allege that FPL has done wrong because

18   it's not very clear to me.

19             So to staff, I guess in reading NP-1100, does

20   Section 2.2 of NP-1100 require FPL to prepare a sole source

21   justification in those instances where valid business reasons

22   support sole source procurement?

23             MR. VINSON:  Yes.

24             COMMISSIONER SKOP:  And I guess you guys, staff is

25   best positioned to know this because they've reviewed the

FLORIDA PUBLIC SERVICE COMMISSION

654

1   contracts extensively.  But for each contract under which you

2   reviewed that sole source procurement was selected, was there a

3   supporting sole source justification provided in each of those

4   instances?

5             MR. VINSON:  Yes.

6             COMMISSIONER SKOP:  So in accordance with NP-1100,

7   FPL followed its internal procedures?

8             MR. VINSON:  Yes.

9             COMMISSIONER SKOP:  All right.  Thank you.

10             CHAIRMAN CARTER:  Thank you.  Thank you,

11   Commissioners.  Anything further from the bench?  Thank you.

12             We're ready for our exhibit.  That would be Number

13   40.

14             MR. YOUNG:  Yes, sir.

15             CHAIRMAN CARTER:  Any objections?  Without objection,

16   show it done.

17             (Exhibit 40 admitted into the record.)

18             MR. YOUNG:  Mr. Chairman, can these witnesses be

19   excused?

20             CHAIRMAN CARTER:  We want to keep them here and let

21   them -- no.  Thank you, guys, very much for your participation,

22   Mr. Vinson and Mr. Fisher.  Have a great day.

23             Okay.  I believe that -- staff, anything further on

24   your case in chief?

25             MS. BENNETT:  No.

FLORIDA PUBLIC SERVICE COMMISSION

655

1             CHAIRMAN CARTER:  Okay.  I think we're back to you,

2   Mr. Anderson.

3             MR. ANDERSON:  Thank you.  FPL would call as its next

4   witness Mr. Labbe, who previously testified and has been

5   previously sworn.

6             CHAIRMAN CARTER:  Good.  Mr. Labbe, good morning to

7   you.

8             THE WITNESS:  Good morning.

9             MR. ANDERSON:  May we proceed?

10             CHAIRMAN CARTER:  You're recognized.

11             MR. ANDERSON:  Thank you.

12   Whereupon,

13                        WILLIAM P. LABBE, JR.

14   was called as a rebuttal witness on behalf of Florida Power &

15   Light Company and, having been duly sworn, testified as

16   follows:

17                         DIRECT EXAMINATION

18   BY MR. ANDERSON:

19        Q    Good morning, Mr. Labbe.

20        A    Good morning.

21        Q    You've been previously sworn?

22        A    Yes.  That's correct.

23        Q    Have you prepared and caused to be filed 12 pages of

24   rebuttal testimony in this proceeding?

25        A    Yes, I have.

FLORIDA PUBLIC SERVICE COMMISSION

656

1        Q    Do you have any changes or revisions to your rebuttal

2   testimony?

3        A    No, I do not.

4        Q    If I asked you the same questions contained in your

5   rebuttal testimony, would your answers be the same?

6        A    Yes, they would.

7             MR. ANDERSON:  FPL asks that Mr. Labbe's rebuttal

8   testimony be inserted into the record as though read.

9             CHAIRMAN CARTER:  The rebuttal testimony of the

10   witness will be inserted into the record as though read.

11   BY MR. ANDERSON:

12        Q    And to be clear, you're the same Mr. Labbe who

13   testified yesterday, and the same position and the same address

14   and all those things; right?

15        A    That's correct.

16        Q    Okay.  There are no exhibits to your rebuttal

17   testimony; is that right?

18        A    That's correct.

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

669

1   BY MR. ANDERSON:

2        Q    Have you prepared a summary of your rebuttal

3   testimony?

4        A    Yes, I have.

5        Q    Please provide your summary to the Commission.

6        A    Good morning, Chairman Carter and Commissioners.

7             My rebuttal testimony responds to claims made by

8   Dr. Jacobs concerning FPL's selection of several uniquely

9   qualified vendors to perform engineering design work at the

10   beginning of the uprate project in a cost-effective way.

11             Let me be clear, FPL fully complied with its

12   procurement procedures.  FPL had numerous good reasons for

13   retaining these vendors.  The work performed and costs incurred

14   for the uprate projects in 2007 are prudent.

15             For purposes of time I'd like to focus FPL's

16   selection on two vendors.  Westinghouse Electric Company

17   designed the nuclear steam supply system for the proprietary

18   nuclear fuel design at FPL's Turkey Point.  No other company in

19   the world has that design information or the right to use that

20   design information.

21             Westinghouse has also successfully with FPL, worked

22   successfully with FPL on other nuclear projects in a

23   cost-effective way.  It should therefore be no surprise that

24   FPL hired Westinghouse because it is the only vendor capable of

25   performing the preliminary engineering design work for the

FLORIDA PUBLIC SERVICE COMMISSION

670

1   nuclear steam supply system at Turkey Point.

2             Westinghouse's costs were also reviewed for

3   reasonableness based on FPL's past experience.  FPL's selection

4   and documentation complied with FPL's procedures.  Clearly this

5   was the right business decision for FPL to make on behalf of

6   the customers.

7             The same thing is true for FPL's use of Areva

8   Company.  The St. Lucie plant uses a fuel design performed and

9   owned by Areva.  Areva was therefore hired to perform the same

10   kind of work as Westinghouse did for Turkey Point.  Each vendor

11   did preliminary engineering and design that it only had the

12   information and expertise to perform.

13             Dr. Jacobs criticized the fact that FPL's procurement

14   documents mentioned the ability to meet schedule as the factor

15   for hiring Westinghouse.  What was missing from Dr. Jacob's

16   testimony is any mention of any of the good reasons for hiring

17   Westinghouse, which is described in my testimony and appear in

18   FPL's single sole source documentation.  These include having

19   the required design information, having performed the current

20   license basis for major nuclear components, having performed

21   the same scope of work for many of the other uprates, including

22   Turkey Point and Seabrook uprates.

23             With Areva, as with Westinghouse, Dr. Jacobs

24   criticized the fact that FPL's procurement documents mention

25   Areva's ability to satisfy schedule requirements.  Again, he

FLORIDA PUBLIC SERVICE COMMISSION

671

1   makes no mention in his testimony of the many good reasons for

2   FPL's decision to use Areva to perform work that it is uniquely

3   qualified to do.  This document has complied with FPL's

4   procurement controls and is properly documented.  I am happy to

5   answer questions you may have on these procurements or FPL's

6   processes.

7             In conclusion, FPL fully complied with its

8   procurement guidelines.  The uprate project is being properly

9   managed with close scrutiny of all costs.  We request that the

10   Commission approve the 2007 uprate costs as prudent and 2008

11   and 2009 costs as reasonable.  This concludes my testimony.

12             MR. ANDERSON:  Mr. Labbe is available for

13   cross-examination.

14             CHAIRMAN CARTER:  Thank you.

15             Mr. McGlothlin.

16                          CROSS EXAMINATION

17   BY MR. McGLOTHLIN:

18        Q    Mr. Labbe, do you have with you or available to you a

19   copy of the nuclear division nuclear policy procurement control

20   that we've referred to in your testimony and others?

21        A    Yes, I do.

22             MR. McGLOTHLIN:  Commissioners, that's item number

23   11 in the staff's comprehensive exhibit stack.  But for my

24   purposes I'm going to refer to only three or four sentences, so

25   it may serve just that we do it this way.

FLORIDA PUBLIC SERVICE COMMISSION

672

1   BY MR. McGLOTHLIN:

2        Q    I'm looking at the first page of that document,

3   Mr. Labbe.  And just to establish a few basics for the

4   questions to follow, referring to Section 1.2, is it true that

5   competitive bidding is FPL's standard approach for the

6   procurement of materials and services with an estimated total

7   value of $25,000 or greater?

8        A    That's correct.

9        Q    And referring to Section 2.1, does that provide that

10   sole or single source procurement should be used on a limited

11   exception basis and only when they can be justified?

12        A    In Section 1.2 (sic.), that's correct.

13        Q    And in terms of the required justification, looking

14   at Section 2.6, the following page, does that section require

15   FPL, when considering a sole source or single source contract,

16   to explain why the chosen contractor has a unique capacity to

17   meet procurement requirements or it's not in the best business

18   interest of FPL to obtain multiple bids?

19        A    Section 2.6 describes that.

20        Q    And does the policy also require that in the course

21   of justifying a sole source or single source contract other

22   than competitive bidding the requester within FPL provide

23   assurance that the resulting contract is reasonable?

24        A    That's correct.

25        Q    And looking at the last bullet on the page that

FLORIDA PUBLIC SERVICE COMMISSION

673

1   begins with 2.6, does it provide that "Except for emergent

2   issues, schedule adherence criteria and/or inadequate timing

3   for bidding are not justifiable circumstances to proceed with

4   sole and/or single source procurement"?

5        A    Yeah.  That is described.

6        Q    Now this is the procurement policy that governs the

7   uprate activities; correct?

8        A    Uprate activities are in compliance with NP-1100.

9        Q    Uprate activities must conform to and adhere to those

10   policies; correct?

11        A    That's correct.

12        Q    And the NP-1100 was not suspended or, or caused to be

13   inapplicable to the uprate project, was it?

14        A    No.  This NP-1100 is in effect today.

15        Q    Okay.  I'm going to ask my co-counsel to pass out a

16   document.  It's been previously identified as an exhibit to

17   Dr. Jacobs' testimony.  It's WRJ-2, which is the sole source

18   justification prepared by FPL in conjunction with the

19   Westinghouse contract.

20             CHAIRMAN CARTER:  Thank you.

21   BY MR. McGLOTHLIN:

22        Q    Let me revert for one more question to the

23   NP-1100 and how that is implemented.  As I understand it, if

24   someone within FPL wishes to utilize sole source or single

25   source contracts in lieu of competitive bidding, that request

FLORIDA PUBLIC SERVICE COMMISSION

674

1   must be presented to the company vice president, who has

2   responsibility for the actual procurement; is that correct?

3        A    That's correct.  That's correct.

4        Q    And the requester would submit to that vice president

5   who has the decision-making authority the justification for

6   using the sole source or single source contract; correct?

7        A    Yeah.  That vice president would be actively involved

8   in that decision-making.

9        Q    Yes.  And what I've distributed is the sole source

10   justification that was presented for approval of a contract

11   with Westinghouse without first soliciting bids; correct?

12        A    That's correct.

13        Q    And this is, this was prepared in terms of the

14   implementation of NP-1100; correct?

15        A    That's correct.

16        Q    I'll direct you to the second full paragraph under

17   the caption "Justification" and ask you to read the sentence

18   that begins, "Meeting this schedule."

19        A    I'm sorry.  Can you state that again?

20        Q    Yes.  Do you see the caption on Page 1 of 2,

21   "Justification"?

22        A    Yes.

23        Q    The second full paragraph under that caption contains

24   a last sentence that begins "Meeting this schedule."  Would you

25   read that, please?

FLORIDA PUBLIC SERVICE COMMISSION

675

1        A    "Meeting this schedule requires performance of the

2   technical work on a very aggressive timeline in order to

3   receive the necessary regulatory approvals."

4        Q    Now there follows a paragraph in which there's a

5   discussion of the items that you mentioned in your summary;

6   correct?

7        A    That's correct.

8        Q    Now near the bottom of the page there's a sentence

9   that begins, "Performing the work scope."  Would you read that

10   sentence, please?

11        A    Right after the parens, "Which are required to

12   perform this work.  Westinghouse has performed this work in the

13   past for numerous uprates, including Turkey Point performed in

14   the mid-1990s and the recent Seabrook station.  No other vendor

15   has the required documentation for, for St. Lucie or Turkey

16   Point.  Performing this scope of work with another vendor would

17   not be cost-effective or prudent from a schedule perspective."

18        Q    Yes, sir.  That last sentence is the one I have in

19   mind for purposes of the next question.

20             Isn't it true, sir, that the discussion of such

21   things as the possession of design information and other items

22   are all considered in conjunction with whether or not the work

23   can be done within the schedule that FPL has, has set for this

24   activity?

25        A    It would be a, one of the considerations.  That's

FLORIDA PUBLIC SERVICE COMMISSION

676

1   correct.

2        Q    Well --

3        A    It is not the sole consideration.

4        Q    Well, again, referring to this sentence which appears

5   to me to be the bottom line conclusion that follows the

6   discussion above, "Performing this work scope with another

7   vendor would not be cost-effective or prudent from a schedule

8   perspective."  Isn't it true that this entire discussion of who

9   has information and who has certain advantages are all geared

10   toward a determination of whether the schedule can be met?

11        A    Yeah.  Perhaps I need to describe that in a little

12   bit more detail what, how we can put that statement in the

13   justification for the sole source justification.

14             But the Westinghouse is a good example for the

15   reasons why, as we have described, they are the sole proprietor

16   of the information.  That information is not available to

17   another vendor.  In order to make that information available to

18   another vendor we would have to change the fuels that are

19   inside that station right now.  So in order to change the fuel,

20   that's a three-cycle evolution not normally performed, the fuel

21   is a competitive bid.  The fuel, the fuel that we purchase is

22   on a, on a plan that could be five to seven or longer years.

23   In order to interrupt that process and insert a new vendor is

24   not practical.

25        Q    Yes, sir.  Is any of that information contained in

FLORIDA PUBLIC SERVICE COMMISSION

677

1   this sole source justification that was submitted to the vice

2   president for decision?

3        A    That's the uniqueness of this industry.  When I write

4   that statement, the vice president that signed this document is

5   very familiar with the requirements associated with what would

6   be required in order to have a new fuel vendor selected.

7        Q    Does it state that a new fuel vendor would be, would

8   be required anywhere in this docket?

9        A    It does not state that.  That's what's inferred.

10   We've had multiple discussions with the vice president.  He

11   understands why that statement is in there.

12        Q    And so again, the, the impact of the selection of

13   someone other than Westinghouse relates to schedule primarily,

14   correct, because of your reference to the three-cycle necessity

15   of going with anyone else?

16        A    The schedule is a, is a factor, but it's not the only

17   factor.

18        Q    Okay.  Let me ask Mr. Burgess to hand out one more

19   document.

20             Mr. Labbe, we have provided to you and the

21   Commissioners and parties a document captioned "Sole Source

22   Justification for Areva."  It was previously attached and

23   admitted in evidence as an exhibit to Dr. Jacobs' testimony.

24   You're familiar with this document?

25        A    Yes, I am.

FLORIDA PUBLIC SERVICE COMMISSION

678

1        Q    Turning to Page 1 of 2, in the first, in the second

2   full paragraph under "Justification," would you read the

3   sentence that begins "Meeting this schedule"?

4        A    "Meeting this schedule requires performance of the

5   technical work on a very aggressive timeline in order to

6   receive the necessary regulatory approvals."

7        Q    And that is identical to the sentence that appeared

8   in the earlier justification memo, is it not?

9        A    Yeah.  That's correct.  Because Areva is performing a

10   similar scope of work that Westinghouse would be performing.

11        Q    And, similarly, toward the bottom of the page there's

12   a reference to the conclusion that performing this work scope

13   with another vendor would not be cost-effective or prudent from

14   a schedule perspective.  That is also identical language, is it

15   not?

16        A    That's correct.  And perhaps it's best to describe

17   how we can, how we can come up with that statement inserted in

18   the justification.  And I could describe the process by which

19   we ensure that it's prudent and it's, and it's reasonable.

20             And probably the best example is -- and I'll just

21   have some similarities between Westinghouse and Areva as I go

22   through my discussion.  But back to the point on the fuels

23   analysis, that's proprietary information that's held by the

24   vendor.  In order to change out the fuels, that would be, that

25   would take three cycles.  That would be 4.5 years.  The

FLORIDA PUBLIC SERVICE COMMISSION

679

1   schedule does not fit in 4.5 years.  I plan to have this

2   project done in 4.5 years.

3             But as it relates to Westinghouse, let me describe

4   the process by which we can ensure that this is prudent and

5   reasonable.  The engineering staff that we have wrote a

6   technical document that describes the scope of work.  The

7   technical document was given to Westinghouse to review and come

8   back with their proposal.  That proposal was returned to us and

9   it had a detailed description of the man-hours that were

10   required and the analysis that would be performed in order to

11   support the uprate.

12             In order to ensure that that information, that we

13   were comfortable and fully vetted, I took the director of the

14   fuels organization for the Florida Power & Light Company and

15   had him go to Westinghouse to review that document in detail

16   with the senior managers and with their staff.  He spent

17   approximately four weeks in Pittsburgh going through that to

18   ensure that that document was robust and it met our

19   deliverables.

20             He then brought that proposal back to the engineering

21   director for the project.  They reviewed it, had a challenge

22   session, and then we brought the senior managers for

23   Westinghouse to our Juno office and had a separate one-off

24   challenge session with them to ensure that the scope was clear,

25   the man-hours were appropriate and that they had the staff and

FLORIDA PUBLIC SERVICE COMMISSION

680

1   the resources to support our project.

2             Now realize in addition to Point Beach we have two

3   other projects that are going on at the same time, St. Lucie

4   and Turkey Point.  So we wanted to ensure that this project

5   would not jeopardize the other projects.

6             That review was conducted in Juno Beach.  After the

7   two directors, Mr. Villard for fuels, Mr. Hale for the

8   engineering, for the project had gone through it, had that

9   challenge session, the results of that challenge session were

10   presented to the vice president to ensure that he had a full

11   understanding that there was scope, man-hours and the schedule

12   would be satisfied.

13        Q    I have a more general question about proprietary

14   information.  We've seen several references to vendors who use

15   proprietary information.

16             Let's assume that, and, again, this is a general

17   question, we have a, FPL has a vendor who has, who has been

18   awarded a contract and fulfills that contract and either

19   because it already has proprietary information or develops it

20   in the course of the work continues to hold the proprietary

21   information, and the occasion arises where FPL needs similar or

22   related work in a new project and a new contract.  Does the

23   fact that a vendor has worked for FPL in the past and in the

24   course of the work has used or has gained proprietary

25   information, does that mean that the same vendor necessarily is

FLORIDA PUBLIC SERVICE COMMISSION

681

1   going to have a lock on future business because of the

2   proprietary nature of the information?

3        A    No.  The, the best way to think about proprietary

4   information is it's tiered.  There's multiple levels of

5   proprietary information.  If an analysis is done by the

6   original equipment manufacturer, the results of that analysis

7   is given to us, it could be proprietary.  And then they -- it

8   doesn't mean that we cannot share that information with

9   somebody else, but it doesn't mean that that business is going

10   to be rewarded to them in the future.

11             But proprietary information, again, back to, you

12   know, the tiered level approaches to it, the results of an

13   analysis, in the case of Westinghouse, the results of a

14   calculation, the results of a methodology verification, those

15   results are proprietary, but it can be shared with other

16   vendors, provided that there's an agreement on the proprietary

17   information with that other vendor.  And that does happen every

18   day.  It is going on in this project with our other vendors.

19   It is a case of normal business with Siemens and a case of

20   normal business for Shaw.  It's the results of that proprietary

21   information that is shared as it relates to the execution of

22   this project, which is different than the -- if you go back to

23   what I was saying, the results are shared but the method by

24   which you calculated those results, that methodology is not

25   shared and that's what they are holding as proprietary.

FLORIDA PUBLIC SERVICE COMMISSION

682

1        Q    Is it possible you could have a situation in which a

2   vendor has performed work and possesses proprietary

3   information, but the same or similar work could be performed by

4   a separate vendor using a separate system or proprietary

5   information that is specific to them?

6        A    Well, again, I go back to my original example.  The

7   results that can be shared as proprietary, the methodology by

8   which that analysis is performed is not shared.  It would

9   have to -- it could be performed by somebody else, but that

10   would require prior NRC approval in order for that to happen.

11        Q    It would have to have what kind of approval?

12        A    Prior NRC approval.

13        Q    NRC approval?

14        A    That's correct.

15        Q    Well, let's take an example of a situation in which

16   Vendor A which has proprietary information has done work for

17   FPL before.  FPL has a need for similar work, scope of work for

18   a new project, and you approach the vendor and, and say can you

19   do it and how much would you charge?  And they say, well, yes,

20   we can do it and the price is X.  And you say, well, that's

21   three times as much as you charged last time.  And the vendor

22   says, well, let me remind you, we have proprietary information

23   and, come to think of it, we want two X.  Is FPL without

24   recourse in a situation like that?  Does the fact that the

25   vendor has worked for FPL before with proprietary information

FLORIDA PUBLIC SERVICE COMMISSION

683

1   mean that it's suddenly an unregulated monopoly?

2        A    No.  I understand your question.  And we don't -- I

3   mean, there are other mechanisms, there are other ways in

4   which, you know, we're not held hostage to that example that

5   you've just proposed.

6        Q    What other ways are those?

7        A    There's -- let me give you an example as it relates

8   to the work that we have with Siemens.

9             When you look at the scope of work that we have for

10   the uprate projects, it's a replacement of the high pressure

11   turbine, low pressure turbines at St. Lucie, the main generator

12   rotor, it's a stator rewind and an exciter replacement.  Those

13   are all Siemens, Siemens documents.  Siemens manufactures the

14   equipment and they've installed it.

15             And we did do a competitive bidding at Point Beach

16   for those components, and there's an analysis that was

17   performed on, it would be the turbine overspeed analysis.

18   There's analysis that would be required for the uprate and we'd

19   have to take that analysis and submit it into the LAR.  That's

20   part of the document that we'd get approval from the NRC.  In

21   order to use another vendor we would still need that analysis

22   from Siemens; say it was another vendor for the turbine.  We do

23   use as, you know, owners and operators of that equipment rights

24   to take that analysis and transfer it to a successful bidder

25   that could use that analysis as it relates to the LAR.

FLORIDA PUBLIC SERVICE COMMISSION

684

1        Q    And that comes about as a, as a term or condition of

2   your prior arrangement with the successful vendor?  You retain

3   the ability to acquire and transfer the proprietary information

4   if you're not able, if they are not able to win the contract?

5        A    That's correct.

6        Q    Do I understand correctly then that even though a

7   vendor may have proprietary information, it would be possible

8   to conduct a solicitation and it would be possible that a new

9   vendor could be the successful bidder and be entitled by virtue

10   of your relationship with the first vendor to have access to

11   the information necessary to perform the work?

12        A    That's the case with some equipment manufacturers but

13   it's not the case with fuels.

14        Q    But, again, speaking generally, and, and I note your

15   comment about the three-cycle implications of the Westinghouse

16   situation.

17        A    It's significant.

18        Q    Yes.  But in a more general view of the role that

19   proprietary information takes, it is possible and even feasible

20   based upon contractual terms to entertain bids from vendors

21   other than the one that has performed the work before with

22   proprietary information.

23        A    And that's, that's correct.  When you look at the

24   scope of work that we have for Turkey Point and St. Lucie,

25   we're just at the phase now where we have completed our

FLORIDA PUBLIC SERVICE COMMISSION

685

1   analysis.  We will be in a position now to start procurement of

2   long-lead materials, and we'll be changing out a lot of

3   components, feedwater heaters, pumps, motors, valves.  All of

4   those components will be competitively bid.

5        Q    Even though proprietary information is involved in

6   some or all of those situations?

7        A    In those cases, it will be, the proprietary

8   information may no longer be applicable because we'll be using

9   new components, new motors, new pumps, new valves.  That's why

10   all of the components that we are going to procure for these

11   uprates will be competitively bid.

12        Q    Then it would follow, would it not, that the presence

13   of proprietary information in and of itself would not be

14   sufficient justification for a sole source or a single source

15   contract?

16        A    Only when it relates to the accident analysis and the

17   fuels.

18        Q    To provide some more context to the subject of fuels,

19   did you hear Dr. Jacobs say yesterday, yesterday that the

20   provision of nuclear fuel is a competitive business?

21        A    Yes, I did.

22        Q    Do you agree with that?

23        A    The nuclear fuels is competitively bid at Florida.

24        Q    Have there been situations in the utility industry

25   where a utility would decide to change providers of fuels over

FLORIDA PUBLIC SERVICE COMMISSION

686

1   the course of a nuclear unit?

2        A    I believe that's the case.

3        Q    Has FPL ever changed fuel suppliers?

4        A    Yes, they have.

5        Q    When, when and where was that?

6        A    I don't know the, the date of when that occurred, but

7   it was at the St. Lucie unit.

8        Q    Who was the first provider and who became the second

9   provider?

10        A    I'm not familiar with that.

11        Q    Well, certainly each provider of fuel has its own

12   proprietary design.

13        A    That's, that's correct.  And they carry with it that

14   design and they're not going to share that with somebody else.

15        Q    Right.  But it is possible within the right situation

16   for a utility to decide to, notwithstanding the specific design

17   criteria, the first provider, to change providers and

18   prospectively use that second design criteria.

19        A    Yeah.  That's correct.

20        Q    Let's take the example of a vendor or contractor who

21   has performed work for FPL in the past with whom FPL has a good

22   track record, a good experience and who has some advantage in

23   the form of knowledge of the operation.  Let's even assume that

24   vendor has the advantage of proprietary information.

25             Do you think that if that vendor is aware that it has

FLORIDA PUBLIC SERVICE COMMISSION

687

1   been singled out as a single source contractor it would have

2   less incentive to take a sharp pencil to the costs than it

3   would have if it were aware that FPL was entertaining other

4   potential providers?

5        A    No, I do not believe that's the case.  And as I

6   described, you know, the evolution that we went through for the

7   selection of Westinghouse at St. Lucie Unit 2 and Turkey Point

8   was a detailed line-by-line review of the scope and the

9   associated man-hours with that.  Those man-hours are very

10   competitive with the rest of the industry.  Those man-hour

11   billing rates are competitive with the rest of the industry.

12   So the rest of the industry knows the billing rates for

13   engineers, analysts, technicians.  That band, if you will, of

14   rates is very competitive.

15        Q    When FPL decides to award a contract on the basis of

16   a single source determination, does that contractor know that

17   there will be no additional bids or, or competitors for the

18   business?

19        A    If I understand your question correctly, would the

20   vendor know that there would be no other bidders?

21        Q    Yes.

22        A    Perhaps.  But it's not something that we would

23   necessarily communicate with them.  We wouldn't, you know, make

24   that knowledge -- that wouldn't necessarily be part of the

25   conversation.

FLORIDA PUBLIC SERVICE COMMISSION

688

1        Q    And why would you not disclose that?

2        A    There would be no reason to.

3        Q    Well, wouldn't one reason be the fact that if they

4   were aware there were no competitors, they would have no

5   incentive to provide the lowest price?

6        A    Yeah.  Probably the best way to --

7        Q    If you would, answer my question first, sir.

8        A    Yeah.  The -- this -- all of our vendors are, have

9   other work associated --

10        Q    Excuse me.  The pending question, the pending

11   question is one reason would be that you would not want them to

12   realize that there is no competing price that they would have

13   to match or better.

14        A    Their price -- you know, if the price is not

15   reasonable, then we're going to have a conversation with them

16   to ensure that the price is reasonable.  Just because -- if, if

17   they provide a proposal and they come up with a rate for that

18   proposal and a cost for that proposal, that doesn't mean that's

19   what we've accepted for that proposal.  There's a lot of

20   negotiation that goes on to ensure that the price is reasonable

21   for the scope of work that's performed.  Just because the

22   proposal is received by us doesn't mean that we accept that

23   proposal.  As I described, we spent two and a half to three

24   months going through the Westinghouse proposal just as it

25   relates to St. Lucie 2 and Turkey Point 3 and 4.

FLORIDA PUBLIC SERVICE COMMISSION

689

1        Q    I don't --

2        A    But, I was going to say, let me close with what I was

3   going to say in the beginning.

4             Now there is other work that Westinghouse or Areva or

5   these other vendors do perform for us.  What we're talking

6   about is a small scope of work as it relates to the uprates.

7   They are a partner with FPL for other scopes of work that is

8   competitively bid.  So it's not like this is the only scope of

9   work that is performed.

10        Q    If you will, Mr. Labbe, turn to Page 10 of your pre,

11   of your rebuttal testimony.  Under the discussion of the Shaw

12   Stone & Webster contract beginning at Line 15 you say, "There

13   is a very real benefit to having access to an experienced,

14   capable vendor with a proven track record at the very project

15   you are asking them to perform."

16             Would you agree that there are other vendors in the

17   same business with Shaw Stone & Webster who, who are

18   experienced and capable?

19        A    I would agree that there are other vendors available.

20        Q    Now you also say, "The fact that they are also the

21   only firm that meets your desired schedule is an additional

22   benefit as well."

23             Did you ask any other vendor whether they could meet

24   your desired schedule?

25        A    Yeah.  As you know, this, this is, we've done many

FLORIDA PUBLIC SERVICE COMMISSION

690

1   uprates, a previous uprate at Seabrook station, which is an FPL

2   Energy affiliate.  And at FPL Energy Seabrook Station we

3   competitively bid the license amendment scope of work and we

4   tested the market, and through that competitive bid process

5   there were two other vendors.  Technically they met the

6   requirements of that competitive bid process but they were not

7   able to meet the deliverable or their price was significantly

8   higher than the Shaw Stone & Webster.  So having that

9   information just recently performed for the Seabrook uprate was

10   a consideration for competitively bidding the other Turkey

11   Point and St. Lucie.

12             In addition to that, the other piece that -- and,

13   again, I'll go back to this, this unit is, Turkey Point is not

14   the only uprate that's being performed.  We have the St. Lucie

15   uprate and we have the Point Beach for the FPL affiliate

16   uprate.  There's six units that are being uprated.  That scope

17   of work is being performed by Shaw Stone & Webster.  And a key

18   consideration for that:  Is the vendor capable of performing

19   multiple uprates at the same time?  And Shaw Stone & Webster

20   has that experience to perform multiple uprates.  They have

21   previously completed eight simultaneously.  So that was a key

22   consideration to that decision, and based on the knowledge that

23   we had with the Seabrook Station competitive bid process.

24        Q    To be clear though, you did not provide an

25   opportunity to anyone other than Shaw Stone & Webster to say

FLORIDA PUBLIC SERVICE COMMISSION

691

1   they could or could not meet the schedule for the uprate here

2   in Florida.

3        A    That's correct.  The other piece that is very

4   important to this is the risk associated with using another

5   vendor.  We've had previous success with Shaw Stone & Webster.

6   And a key consideration for the license -- this is specific to

7   the license amendment work for the balance of plant components.

8   It's nonnuclear safety.  This is back to the turbine and

9   generator.

10             But the license amendment, there's a lot of analysis

11   performed, as we've discussed, with Westinghouse, but that

12   information, that sharing information has to go back and forth

13   to the balance of plant person that is putting together the

14   license amendment.  They have done a significant number of

15   uprates and that has been in connection with Westinghouse

16   units.  So there's a very good, strong working relationship

17   with Westinghouse.  We have the two organizations sitting

18   together at the stations so that there is clear alignment,

19   there is efficiencies that are gained and there's transfer of

20   knowledge that is very critical for this to be successful.

21        Q    Speaking more generally now and not limiting it to

22   the Shaw Stone & Webster situation, would you agree with me

23   that it is possible to construct a request for proposals that

24   would identify as one of the criteria for evaluating bids the

25   ability and commitment of the bidder to conform to the schedule

FLORIDA PUBLIC SERVICE COMMISSION

692

1   identified by the issuer --

2        A    By the proposal.

3        Q    -- of the RFP?

4        A    That's correct.

5        Q    Would you agree that it's possible to construct an

6   RFP that would identify the experience and qualifications as

7   one of the criteria that would be evaluated by those, by the

8   issuer of the RFP?

9        A    Yeah.  That's correct.

10        Q    Do you think those are good ways to accomplish both

11   the objectives of, of the utility issuing the bid while

12   continuing to test the market before determining the, before

13   awarding the contract?

14        A    And that was the case that, that we had just

15   previously completed for Seabrook.

16        Q    For Seabrook but not in Florida?

17        A    That's correct.

18             MR. McGLOTHLIN:  Those are all the questions I have.

19             CHAIRMAN CARTER:  Thank you.

20             Mr. McWhirter.

21                          CROSS EXAMINATION

22   BY MR. McWHIRTER:

23        Q    Mr. Labbe, what is the current status of the Stone &

24   Webster bankruptcy action?

25        A    I am not familiar with that case.

FLORIDA PUBLIC SERVICE COMMISSION

693

1        Q    Did the fact that the company was in bankruptcy, was

2   it given any consideration in your determination to deal with

3   that company?

4        A    Yes.  Part of the contract review and approval

5   process looks at the health of the organization.  The criteria

6   by which they review and approve that I'm not familiar with.

7   But I get a recommendation from the legal team and our

8   contracts organization.

9        Q    When you approve a purchase under the new legislation

10   that is the subject matter of this proceeding, is there any

11   portion of the cost that FPL is required to pay that is

12   retained by FPL as opposed to passed directly through to the

13   customers or a return on that amount of money you pay passed

14   through to the customers?

15        A    I'm not sure I understand that question.  Could you

16   repeat it again?

17        Q    I'm not sure I understand it either.

18        A    I'll try to stay with you.

19        Q    Do you know how this legislation differs, the

20   legislation, the subject matter of this proceeding, do you know

21   how it differs from the existing regulatory procedures that

22   govern the oversight of your company?

23             MR. ANDERSON:  I'd just note that this is beyond the

24   scope of the direct.  Our witness really isn't testifying

25   concerning the operation of the rule and things.  That was

FLORIDA PUBLIC SERVICE COMMISSION

694

1   Ms. Ousdahl.  It's more of a legal matter.

2             CHAIRMAN CARTER:  Mr. McWhirter?

3             MR. McWHIRTER:  Well, my question was is he aware of

4   the difference?  But if he isn't aware --

5             CHAIRMAN CARTER:  Well, wait.  Wait.  Don't ask the

6   question.  We're dealing with the objection right now.

7             MR. McWHIRTER:  All right.  Well, my question is does

8   he know?  And then I would ask questions about what he knew.

9             CHAIRMAN CARTER:  Did you hear Mr. Anderson's

10   objection?

11             MR. McWHIRTER:  But the objection is that it's a

12   legal matter.  And he may know the legal matter since he's

13   responsible for purchasing for the company and should be aware

14   of the law that governs those purchases.

15             MS. HELTON:  I think he can ask if he's aware of the

16   regulatory scheme and the statutes.  And I guess I don't think

17   we have gone far enough yet to know whether his knowledge, if

18   he has any, would be relevant to the prefiled testimony that

19   he's filed and subject to cross-examination.

20             CHAIRMAN CARTER:  Okay.

21             MR. McWHIRTER:  Do you overrule the objection?

22             CHAIRMAN CARTER:  You may proceed.  You may proceed.

23   BY MR. McWHIRTER:

24        Q    Are you aware, Mr. Labbe?

25        A    Yes, I am.

FLORIDA PUBLIC SERVICE COMMISSION

695

1        Q    And would you briefly describe the difference in the

2   procedure under the new legislation from the procedure under

3   the old legislation?

4        A    Yeah.  I am aware but I couldn't articulate very well

5   the difference between the old and the new.  The only thing I

6   will say, it doesn't change the manner in which we execute the

7   nature of this project.  Those procedures and policies and

8   programs are established irregardless of how the costs are

9   associated with it.

10        Q    Are you aware that under the new legislation the risk

11   of the cost that's related to the purchases you make is assumed

12   entirely by the consumer as opposed to being assumed by the

13   company?

14        A    I am aware.

15        Q    And is that an accurate statement?

16             MR. ANDERSON:  Could -- I'm sorry.  I couldn't hear

17   the question or answer.  Could we -- what was that question?

18   BY MR. McWHIRTER:

19        Q    Could you read it back?  I'm not sure I can restate

20   it back.

21        A    What you're interested in is how does that compare

22   previous legislation to today's legislation?

23        Q    Yes, sir.

24        A    Yeah, I am aware of it, but I am not familiar with

25   how the financial accounting is associated.  The way that I

FLORIDA PUBLIC SERVICE COMMISSION

696

1   operate the project is no different today than I have operated

2   previous projects; the same manner in which we've always

3   conducted our business.

4             MR. McWHIRTER:  All right, sir.  I have no further

5   questions of this witness, Mr. Chairman.

6             CHAIRMAN CARTER:  Thank you, Mr. McWhirter.

7             Staff?

8             MR. YOUNG:  No questions.

9             CHAIRMAN CARTER:  Commissioner Argenziano, you're

10   recognized.

11             COMMISSIONER ARGENZIANO:  Just one, maybe just one.

12   I guess everybody is aware that bidding, putting out for

13   proposal can be, you know, more cost-effective sometimes and

14   sometimes I guess sole source procurement given particular

15   criteria could be more cost-effective.  And to that point, and

16   I'm going to reverse this in a sense, and I guess I know the

17   answer but I want to hear it, I guess, could it be less

18   cost-effective to not meet schedules that are especially

19   aggressively pursued?  Could it wind up costing more money to

20   be off schedule?

21             THE WITNESS:  I don't believe so.  You know, we look

22   at the capability, vendor capability and make sure that, you

23   know, the time lines that we lay out, the milestones that we

24   want to satisfy, that they can fit inside of those, you know,

25   that it's a reasonable approach to executing the project.

FLORIDA PUBLIC SERVICE COMMISSION

697

1   Where we don't want to be is having to ensure that the vendor

2   has to do extra, you know, work additional hours or bring in,

3   you know, somebody else to help them to meet those milestones.

4   As long as we can ensure that they are capable of performing

5   the work in the window we've provided, then I think, you know,

6   then we can say that we're not incurring additional costs for

7   an aggressive schedule.

8             COMMISSIONER ARGENZIANO:  No.  I think what, I think

9   what I'm really asking is if you are off schedule, can you, can

10   it be less cost-effective?

11             THE WITNESS:  If we, if the project falls behind

12   schedule, then there is risk associated with that.  And the

13   risk is that you'll have to spend extra time, extra resources

14   to make, to recover that schedule.

15             COMMISSIONER ARGENZIANO:  And just one other question

16   because I've been involved with procurement at the state level.

17   When you do go into contract on those bids, whether they're

18   sole source procurements or proposals for bid, does the

19   contract, can the, can the lowest bidder come in and then amend

20   later on?  I know this is kind of off, but it's for me.

21             THE WITNESS:  No.  That's okay.

22             COMMISSIONER ARGENZIANO:  Can they amend that later

23   on to then increase costs if they find that costs have gone up

24   and does that happen?

25             THE WITNESS:  There's probably a couple of pieces

FLORIDA PUBLIC SERVICE COMMISSION

698

1   that I'd like to answer on this.

2             In the, in the procurement process, as I was

3   describing, we have a scope description document that just

4   articulates all the requirements that we're looking for on the

5   deliverables.  That scope description document goes through a

6   technical evaluation to make sure that that vendor can deliver,

7   you know, what we're interested in.

8             At the same time we have a commercial evaluation done

9   by a separate organization to make sure that the commercial

10   aspect of it makes sense.  And then the two documents come

11   together at the manager level to make sure that, you know, we

12   choose the best evaluated bidder as it relates to the scope of

13   work that needs to be performed.  Then that contract is entered

14   into as it relates to that scope document.

15             So the only reason we would have a change is if they

16   were not able to perform that scope of document or we were

17   asking, we were asking for a change to that scope of document

18   to do something additional.  And if there's a change to that

19   document, then it goes through the same review and approval

20   process as the original document.  So there is the potential,

21   but it would be at the request of the, of the vendor or at our

22   request and it would have to make sense to both parties.

23             COMMISSIONER ARGENZIANO:  And I guess what I'm trying

24   to get at is that I've seen before -- and I'm not saying it

25   would happen in this case, and I'm trying to look at all sides

FLORIDA PUBLIC SERVICE COMMISSION

699

1   of this.  I've seen with state procurement that there have been

2   the lowest bidders who come in in the hopes of getting, you

3   know, the best deal that you can, the best bang for your buck,

4   and then many times later see amendments to that contract that

5   then the price goes up afterwards.  And I didn't know if

6   that's, if there's a possibility there or if that's taken care

7   of through some type of contracting language or something.

8             THE WITNESS:  Yes, Commissioner.  As you described,

9   you have to be extremely careful that you don't take the lowest

10   bidder if there is risk associated with the lowest bidder not

11   being qualified to perform that scope of work.  So that's

12   partially that commercial evaluation as I described.

13             COMMISSIONER ARGENZIANO:  Okay.  Thank you.

14             CHAIRMAN CARTER:  Commissioner McMurrian, then

15   Commissioner Skop.

16             COMMISSIONER McMURRIAN:  Oh, thank you.  Hello.

17             THE WITNESS:  Good morning.

18             COMMISSIONER McMURRIAN:  I wanted to follow up a

19   little bit, and I think we've had a lot of questions along this

20   same line this morning, but I just wanted to ask it maybe a

21   different way.

22             I know yesterday when Mr. Anderson was questioning

23   Mr. Jacobs there was some discussion about no other company in

24   the world having the proprietary design info.  And I believe

25   that Mr. Jacobs said, yes, but others have similar design info.

FLORIDA PUBLIC SERVICE COMMISSION

700

1   And I guess I'm just trying to get straight in my mind the fact

2   that others may have similar design info.  What is it, what is

3   your testimony with respect to statements like that?  How do I

4   get straight in my mind that with the single source contracts

5   that you have, and we've gone through the justifications and we

6   explained why you've made the decisions you've made with these

7   single and sole source contracts, but how can we be sure that

8   ratepayers are getting the best deal even with those, those

9   contracts?

10             THE WITNESS:  It -- Commissioner, let me describe

11   that in a, in a couple of ways.  The -- as it related to the

12   first piece, the analysis, is there any other person in the

13   world that has access to that analysis?  And the answer as it

14   relates to the fuels is no because the fuels analysis is

15   protected and that fuels analysis is not going to be shared.

16   But there are other analyses that are performed.  So there's

17   probably three that you need to be aware of.  One is the fuels

18   analysis, and that stays with the fuel that's in the reactor

19   vessel.  The next is the component analysis, and that's the

20   components that are inside of the containment building.  And

21   then there's the accident analysis, and that's the result of an

22   event that occurs, and that ensures that the structure and the

23   systems respond as a result of that accident.  So there's three

24   tiers to that.  The one that is the most proprietary and the

25   most protected is the fuels analysis, and that is something

FLORIDA PUBLIC SERVICE COMMISSION

701

1   that by its nature a power uprate is going to change.

2             CHAIRMAN CARTER:  You're recognized.

3             COMMISSIONER McMURRIAN:  And actually one, one

4   follow-up along the lines of just how, you know, the

5   competitive bidding process and all works.  Is there any kind

6   of a ballpark number about how much it costs to do a

7   competitive bid and evaluate it in these types of contract

8   negotiations?

9             I mean, are there times -- I guess what I'm getting

10   at is are there times when doing a competitive bidding process

11   is really more expensive than what you would get out of it?

12             THE WITNESS:  Yes.

13             COMMISSIONER McMURRIAN:  And is there any kind of

14   ballpark number?

15             THE WITNESS:  Yeah.  But it can be a very significant

16   burden to the bidders.  We're, you know, we go through the bid

17   process and they do spend a significant amount of time and

18   energy on, on these bids, and we, and so do we.  And we bring

19   the vendors in, we have all-day sessions with these bidders,

20   and they have committed a significant amount of resources on

21   the bid process.  So some -- that depends on the nature of

22   which the bid is, you know, trying to, the scope that we're

23   trying to manage.

24             For smaller scopes of work, you know, if we're going

25   to replace a pump or a motor, the amount of effort is not as

FLORIDA PUBLIC SERVICE COMMISSION

702

1   significant as, hey, we need to competitively bid the

2   engineering associated with all the modifications at Turkey

3   Point and St. Lucie.  So to say that there's a ballpark number

4   for the bidding process is probably, you probably can't give

5   that justification.

6             COMMISSIONER McMURRIAN:  I think that's it.

7             CHAIRMAN CARTER:  Commissioner Skop.

8             COMMISSIONER SKOP:  Thank you, Mr. Chairman.

9             Just some general questions and then some specific

10   questions to the witness.

11             I guess from the discussion I've heard it seems that

12   part of the tension here, although in each instance under which

13   FPL's undertaken sole source procurement there has been the

14   preparation of a sole source justification for each of those

15   instances, it seems like a lot of the discussion is focused on

16   OPC taking exception to the discussion of schedule within the

17   body of each justification.  And I just want to make sure that

18   I'm correct to understand that schedule is not the sole basis

19   for the justifications that have been provided.  Is that

20   correct?

21             THE WITNESS:  That's correct.

22             COMMISSIONER SKOP:  Okay.  And with respect to

23   NP-1100, that's an internal controls document that FPL would be

24   free to revise at any time as it deemed fit; is that correct?

25             THE WITNESS:  Yes.  That's correct.

FLORIDA PUBLIC SERVICE COMMISSION

703

1             COMMISSIONER SKOP:  Okay.  With respect to the sole

2   source justifications that have been provided, I think your

3   testimony indicated that the extent of the discussion is not

4   lengthy or in full detail on some issues to the extent that

5   it's implicitly understood by management that deals directly

6   with nuclear issues on a day-to-day basis of the rationale

7   behind the justification being provided; is that correct?

8             THE WITNESS:  Yes, Commissioner.  That is correct.

9             COMMISSIONER SKOP:  Okay.  Going to move quickly just

10   because I think a point raised, was raised that I guess I'd

11   like to get a little bit more fleshing out on, and that was my

12   general comments.  I'm going to get to a more specific issue.

13   But there was much discussion about the, specifically about the

14   Shaw Stone & Webster procurement contract.  And if you could

15   refresh my memory exactly what that contract, what services

16   were to be provided under that contract.

17             THE WITNESS:  Yes.  Certainly, Commissioner.  The

18   Shaw Stone & Webster scope of work is for the license amendment

19   submittals for St. Lucie and Turkey Point as it relates to the

20   balance of plant components.

21             COMMISSIONER SKOP:  Okay.

22             THE WITNESS:  Now maybe I should carry that a little

23   bit further.

24             COMMISSIONER SKOP:  Let me just stop you because,

25   again, I'm looking at a confidential document, so I don't want

FLORIDA PUBLIC SERVICE COMMISSION

704

1   to go -- you know, I know it was raised, so I assume that -- I

2   don't want to get into any confidential information, but I was

3   just trying to, to better understand, and I'll let you finish

4   your response.

5             THE WITNESS:  Okay.  Now the -- now Westinghouse and

6   Areva will provide a piece of that document, Shaw Stone &

7   Webster will provide a piece of that document.  That will be

8   given to FPL and we have some pieces that we'll put together.

9   We'll assemble, we are responsible for putting the entire

10   document together, and then it will go through the station

11   review and approval process, and then that is the vehicle by

12   which we submit it to the NRC.

13             COMMISSIONER SKOP:  Okay.  And with respect to other

14   vendors, would a firm, say Black & Veatch, be capable of

15   providing similar services for, you know, uprates and balance

16   of plant type analysis?

17             THE WITNESS:  Yes.  And we -- and, again, a unique

18   market knowledge that we're very familiar with as a result of

19   the Seabrook uprate.  That process was competitively bid and,

20   again, Shaw Stone & Webster came in as technically qualified

21   and by a considerable amount the least cost.

22             COMMISSIONER SKOP:  Okay.  Going to the statement

23   that you just made with respect to the Seabrook uprate, which,

24   I guess, is on the --

25             THE WITNESS:  It's now complete.

FLORIDA PUBLIC SERVICE COMMISSION

705

1             COMMISSIONER SKOP:  Excuse me?

2             THE WITNESS:  That uprate is now complete.

3             COMMISSIONER SKOP:  Okay.  That's, that's one of your

4   affiliate company reactor plants that --

5             THE WITNESS:  That's correct.

6             COMMISSIONER SKOP:  Is that the same reactor design

7   as St. Lucie and Turkey Point?

8             THE WITNESS:  It's a similar design but it's not

9   exactly the same.

10             COMMISSIONER SKOP:  Okay.  With respect to the point

11   that was raised about Shaw Stone & Webster being currently in

12   bankruptcy, and, again, I don't know that to be fact, I'm just

13   taking the representation that has been made, what adequate

14   protection is in place to protect the ratepayers from being in

15   a contract with a company that's currently in bankruptcy?

16             THE WITNESS:  And, again, before, before we enter

17   into that contract arrangement the health of that financial

18   organization is reviewed by our legal department, and they --

19   before I enter into that agreement they give me permission, and

20   they are actually signers of the contract.

21             COMMISSIONER SKOP:  Okay.  And with respect to, going

22   back to Seabrook again, the reference to Seabrook is just

23   merely intended to show past performance on a project rather

24   than any relevance to doing the exact same design for the

25   Turkey Point and the St. Lucie units; is that correct?

FLORIDA PUBLIC SERVICE COMMISSION

706

1             THE WITNESS:  Yes.  That's correct.

2             COMMISSIONER SKOP:  Thank you.

3             CHAIRMAN CARTER:  Thank you, Commissioners.  Anything

4   further from the bench?

5             Ms. Pettus or Mr. Anderson.  Mr. Anderson.

6             MR. ANDERSON:  One moment.

7             CHAIRMAN CARTER:  We'll kind of jog in place,

8   Commissioners, and then we'll, after this witness we'll give

9   the court reporter a break.

10             MR. ANDERSON:  I'll have just a couple of questions.

11   And just to clarify, Stone & Webster was acquired by Shaw out

12   of bankruptcy.  So it is not a bankrupt entity, since we're

13   going down that path.  And Mr. Reed can tell you about that, if

14   you want to know, but it's not a bankrupt entity we're in

15   contract with.

16             COMMISSIONER SKOP:  And thank you for that

17   clarification.

18             MR. ANDERSON:  Okay.  Pardon the delay to figure that

19   out.

20             CHAIRMAN CARTER:  That was very helpful.  Thank you.

21             MR. McWHIRTER:  Is that under oath, Mr. Chairman?

22             MR. ANDERSON:  I'm always under oath.

23             CHAIRMAN CARTER:  Neither were you, Mr. McWhirter.

24   Turn about is fair play, wouldn't you agree?  Thank you.

25                        REDIRECT EXAMINATION

FLORIDA PUBLIC SERVICE COMMISSION

707

1   BY MR. ANDERSON:

2        Q    Mr. Labbe, in the big picture the dollars for these

3   fuel analyses and safety designs that go into the NRC licensing

4   document, that's a small amount of work at the beginning of the

5   uprate project; is that right?

6        A    Yes.  That's correct.

7        Q    I think I heard you say earlier in response to a

8   question from Mr. McGlothlin that in order to use a different

9   vendor for this fuel analysis you'd have to be using different

10   fuel inside that reactor vessel.  Do I understand that right?

11        A    Yeah.  That's correct.

12        Q    You mentioned that it's a three-cycle process to

13   change fuel vendors.  How long is that in months?

14        A    Each cycle is 18 months.

15        Q    So that would be -- three times 18 is 54 months or

16   four and a half years to change fuel vendors; is that right?

17        A    That's correct.  And it would be longer than that

18   because the fuel would have to be fabricated, and that's

19   usually a year or longer in advance of that.

20        Q    So in order to potentially save arguably a very small

21   amount of money to competitively bid this engineering and

22   design work at the beginning of the project, would it have been

23   in the best interest of FPL's customers to stop the uprate

24   work, go out, bid the fuel, wait at least four and a half

25   years, maybe five and a half years, come back and with that

FLORIDA PUBLIC SERVICE COMMISSION

708

1   result in hand go ahead and restart the uprate project?

2        A    No, that would not be prudent.

3        Q    Why not?

4             CHAIRMAN CARTER:  Hang on a second, Mr. -- could you

5   remember your train of thought?

6             MR. ANDERSON:  Yes, sir.

7             CHAIRMAN CARTER:  Hang on one second.

8             Commissioner Skop.

9             COMMISSIONER SKOP:  I'm sorry.  And I'll let

10   Mr. Anderson continue, I just had two additional questions.  So

11   at his leisure, I can ask those now or reserve those.

12             MR. ANDERSON:  Okay.  Perhaps if the witness could

13   answer this one, and then we'd turn to yours.

14             CHAIRMAN CARTER:  You're recognized.

15   BY MR. ANDERSON:

16        Q    Do you remember the question, Mr. Labbe?

17        A    Yeah.  That would not meet the project objectives.

18        Q    Well, what do you mean by that?  Would you be able to

19   have these uprates online to save customers money in 2011 and

20   2012?

21        A    That, that is the project objective is to ensure that

22   we can reliably produce 400 megawatts of generation, additional

23   generation by the summer of 2012.

24        Q    And if we took five years to rebid the fuel, that

25   would be what?  2008 plus five is 2013.

FLORIDA PUBLIC SERVICE COMMISSION

709

1             MR. McGLOTHLIN:  Object to the leading form of these

2   questions.  I think counsel can --

3             MR. ANDERSON:  I can put them in an open-ended form.

4   BY MR. ANDERSON:

5        Q    If you were to rebid the nuclear fuel inside the

6   reactor vessel in order to competitively bid the little bit of

7   engineering design work, how long would it be, do you think,

8   before customers would have the benefit of these uprates?

9   Would you meet your schedule?

10        A    No, we would not.  And it would be at least a couple

11   of year delay.

12        Q    So the uprates, if I understand you, would not be in

13   service in 2011 and 2012.  It would be sometime years beyond

14   that.

15        A    That's correct.

16             MR. ANDERSON:  That's all we had.

17             CHAIRMAN CARTER:  Commissioner Skop.

18             COMMISSIONER SKOP:  Thank you, Mr. Chairman.

19             And I guess the question I had was somewhat similar

20   and I should have probably asked it previously, but it goes to

21   a different point.  Certainly with respect to the uprates

22   there's a benefit to the extent that you're gaining additional

23   nuclear generation which is emission free and results in fuel

24   savings.

25             I guess in looking at Section 2.6 of NP-1100 I just

FLORIDA PUBLIC SERVICE COMMISSION

710

1   wanted to get your opinion whether, you know, such an uprate

2   would be an emergent issue under that last bullet on Page 2 of

3   5.  In the context to the extent that if there was ability to

4   theoretically make an investment that would save, ultimately

5   save consumers money in terms of fuel savings, would that

6   arguably be an emergent issue as you see it?  I don't know.

7   I'm just, I'm just merely asking because to me the emergent

8   issue is not very well defined.  It seems to be kind of broad.

9   So I'm just trying to --

10             THE WITNESS:  Commissioner, in the context as it's

11   written on NP-1100 as in the scope of this project, we would

12   not consider the project to be an emergent issue in order to

13   satisfy the deliverables.  This is more in the context of as it

14   relates to the execution and operation of the unit.

15             COMMISSIONER SKOP:  Okay.

16             THE WITNESS:  And if something needed to be done in a

17   very short order, then we would invoke this piece.

18             COMMISSIONER SKOP:  So in that context would it be

19   correct to understand that an emergent issue would be like a

20   failure of a pump or something where you had to go do something

21   quick to get the plant online?

22             THE WITNESS:  That's correct.

23             COMMISSIONER SKOP:  Okay.  All right.  Thank you for

24   that clarification.

25             And then just one point, and to recognize that we're

FLORIDA PUBLIC SERVICE COMMISSION

711

1   dealing with a body of confidential information, but in

2   relation -- and if you can answer it, great, if not -- but in

3   relation to the Areva and the Westinghouse contracts, what is

4   the magnitude of the, the Shaw Webster or Shaw Stone & Webster

5   contract?  Do we know?

6             THE WITNESS:  Yeah, I do.  I'm just trying to --

7             COMMISSIONER SKOP:  Okay.  I mean, much smaller, I

8   mean, much smaller, orders of magnitude smaller or --

9             THE WITNESS:  I can give you order of magnitude for

10   each.  The Westinghouse is, for Lucie and Turkey the

11   Westinghouse scope of work is $44 million.

12             COMMISSIONER SKOP:  Okay.

13             THE WITNESS:  And the Shaw Stone & Webster is 20.

14             COMMISSIONER SKOP:  Okay.  Thank you.

15             CHAIRMAN CARTER:  Thank you.

16             Mr. Labbe, just one question.  Is it true that FPL

17   engaged in the sole source contracts to make sure that they had

18   the most efficient and lowest cost for these, this equipment to

19   the ratepayers?

20             THE WITNESS:  Yes.  That's correct.

21             CHAIRMAN CARTER:  Thank you.

22             Commissioners, anything further from the bench?

23             Mr. Anderson, anything?  Okay.  I think Dr.,

24   Mr. Labbe, I think you may be excused.

25             You may call your next witness.  Wait a minute.  Not

FLORIDA PUBLIC SERVICE COMMISSION

712

1   you, Mr. Labbe.  I forgot about the court reporter.  I'm sorry,

2   Linda.  Let's do this, let's give the court reporter, she's

3   been going a couple of hours -- well, yeah.  Let's take a

4   break.  I looked at the clock to my right yesterday.  How about

5   I look to the one to my left today and we'll come back at, on

6   the half hour.

7             (Recess taken.)

8             We are back on the record.  And we gave the court

9   reporter a break and now, Mr. Anderson, you're recognized.

10             MR. ANDERSON:  Thank you.  FPL would call Steven

11   Scroggs as its next witness.

12   Whereupon,

13                          STEVEN D. SCROGGS

14   was called as a rebuttal witness on behalf of Florida Power &

15   Light Company and, having been duly sworn, testified as

16   follows:

17                         DIRECT EXAMINATION

18   BY MR. ANDERSON:

19        Q    Good morning, Mr. Scroggs.

20        A    Good morning.

21        Q    Have you been sworn?

22        A    I have.

23        Q    Did you previously provide your name, business

24   address and title?

25        A    Yes, I have.

FLORIDA PUBLIC SERVICE COMMISSION

713

1        Q    Have you filed seven pages of prefiled rebuttal

2   testimony in this case?

3        A    Yes, sir, I have.

4        Q    Do you have any changes or revisions to your prefiled

5   rebuttal testimony?

6        A    No, I do not.

7        Q    If I asked you the same questions contained in your

8   rebuttal testimony, would your answers be the same?

9        A    Yes, they would.

10             MR. ANDERSON:  FPL asks that Mr. Scroggs' prefiled

11   rebuttal testimony be inserted into the record as though read.

12             CHAIRMAN CARTER:  The prefiled rebuttal testimony

13   will be entered into the record as though read.

14   BY MR. ANDERSON:

15        Q    Am I correct that you have no exhibits to your

16   rebuttal testimony?

17        A    That's correct.

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

721

1   BY MR. ANDERSON:

2        Q    Have you prepared a summary of your testimony?

3        A    Yes, I have.

4        Q    Please provide your summary to the Commission.

5        A    Yes, I will.

6             Good morning, Chairman Carter and Commissioners.  The

7   purpose of my rebuttal testimony is to respond to claims made

8   by Dr. Jacobs on behalf of the Office of Public Counsel

9   concerning FPL's use of sole and single source procurement as

10   one tool to perform the work supporting the Turkey Point 6 and

11   7 project.

12             Contrary to the characterization provided by

13   Dr. Jacobs, FPL has fully complied with its procurement

14   guidelines and bases its decisions on solid business reasons.

15   I can assure you that senior management at FPL takes its

16   responsibilities in this area seriously and holds myself and

17   the project team to a very high standard.

18             Recognizing the limitation of time in this summary,

19   I'd just like to discuss why FPL is uniquely capable of

20   effectively using single and sole source procurement as a tool

21   and discuss why sole source and single source procurement is

22   going to be necessary as a tool in new nuclear project

23   deployment.

24             FPL has first-hand experience with many national

25   level engineering firms, including knowledge of market-based

FLORIDA PUBLIC SERVICE COMMISSION

722

1   billing rates charged by these service providers for various

2   services.  We not only test the market routinely, but we're, in

3   fact, a sizable portion of the power generation engineering

4   services market in North America.  FPL has extensive experience

5   in designing the scope of the work for engineering assignments

6   that result in tightly focused analyses that can fully satisfy

7   the needs of the project.  Combined this in-depth knowledge of

8   the market, our position in the market and the experience of

9   managing these service providers allows FPL to review any

10   proposal for work with an informed, critical eye that assures

11   procured services will be reasonably priced.

12             As documented in the single source justifications,

13   the selected vendors have unique experience in their selected

14   areas.  It just makes good sense for FPL to bring to bear the

15   most qualified and experienced practitioners in a given area,

16   particularly when it can be done in a way that ensures that FPL

17   will get exactly what it needs and no more for a reasonable

18   market price.

19             Finally, a few comments about the practice of single

20   and sole source procurement.  While it's not FPL's preferred

21   means of procuring goods and services, sole and single source

22   procurement is a necessary and appropriate tool in business and

23   particularly in the business of new nuclear deployment.  The

24   unique nature of building the first new nuclear plants in over

25   25 years will require us to carefully use this tool.

FLORIDA PUBLIC SERVICE COMMISSION

723

1             MR. McGLOTHLIN:  Mr. Chairman, I don't enjoy

2   interrupting a witness, but I find that his summary is not a

3   summary of anything in prefiled rebuttal.  The rebuttal

4   contains comments relating to Dr. Jacobs' specific points, and

5   this is more in the nature of an enlargement of a discussion in

6   direct.  And I think because of the, the nature of the

7   proceeding and our preparation practices, we need to confine

8   the summary to the contents of the rebuttal testimony.

9             CHAIRMAN CARTER:  Mr. Anderson.

10             MR. ANDERSON:  Mr. Scroggs' testimony talks about the

11   types of analyses we use for single and sole source procurement

12   and its role.  I think he's just about done anyway.  Whatever

13   the Chair's preference is.

14             MR. YOUNG:  Mr. Chairman, since I think Mr. Anderson

15   is correct, and also you're dealing with relevancy here and

16   it's a very thin line, a thin threshold for relevancy, so I say

17   overrule the objection.

18             CHAIRMAN CARTER:  Overruled.  You may proceed.

19             THE WITNESS:  Thank you, sir.

20             Speaking to the fact that we're beginning the first

21   new nuclear projects in over 25 years and there's some specific

22   features that bear on our discussion here:  For example, the

23   nature of licensing a new nuclear project requires that a

24   commitment be made to a specific design in order to develop the

25   applications, and that requires the commitment to a specific

FLORIDA PUBLIC SERVICE COMMISSION

724

1   vendor of that design.  And, additionally, there are many

2   specific areas as we've talked about in the need determination

3   process such as ultra heavy forgings where there is only one

4   provider of this capability in the, in the earth, in the world

5   right now.

6             Finally, the last point to make sure we understand is

7   that our experience as an owner and operator of nuclear

8   generation facilities teaches us time and time again that

9   selection of the most qualified service provider commonly

10   reduces both cost and risk for the benefit of our customers.

11   Delays in maintaining the plant, maintaining current existing

12   plants create delays in bringing those plants back online,

13   which costs in additional fuel costs for our customers, they

14   feel that directly; to delay new units, that cost in terms of

15   the billions of dollars of fuel savings that these units are

16   projected to provide.  The fact is that the added scrutiny

17   associated with single and sole source procurement assures that

18   decisions are made in the best interest of FPL customers.  That

19   concludes my summary.

20             CHAIRMAN CARTER:  Thank you.

21             Mr. McGlothlin, you're recognized.

22                          CROSS EXAMINATION

23   BY MR. McGLOTHLIN:

24        Q    Your summary or rather your comments this morning

25   focused heavily on advocating the use of sole source and single

FLORIDA PUBLIC SERVICE COMMISSION

725

1   source contracts.  Is it true with respect to the new units as

2   it is true of the uprates that the standard for procurement

3   under FPL's guidelines is competitive bidding?

4        A    The preferred procurement method is competitive

5   bidding.

6        Q    You're not suggesting by your comments here this

7   morning that you believe competitive bidding should not be the

8   preferred?

9        A    I believe my comments this morning are meant to

10   identify that sole source and single source procurement is a

11   reality of the business that we're in.  It's not to advocate

12   it, it's not to put it above competitive bidding.  It's just to

13   recognize it as a reality of our business.

14        Q    Do you think that reality should continue to be

15   exceptions to preferred preference for competitive bidding as

16   opposed to tools that can be implemented without justification?

17        A    I believe that as we've described and as Mr. Labbe

18   described it we are complying with FPL's procurement procedures

19   by looking first at competitive bidding.  And when that is not

20   available for sound business reasons, that we justify that and

21   get the appropriate approvals.

22        Q    Well, that's the purpose of my question because it

23   appeared to me, listening to your comments this morning, you

24   were advocating the use of sole source and single source

25   contracts without reference to the overriding criterion, which

FLORIDA PUBLIC SERVICE COMMISSION

726

1   is competitive bidding where that is feasible.  So you continue

2   to see the use of sole source or single source contracts as an

3   exception that has to be justified; correct?

4        A    That's our procedures.  Yes, sir.

5        Q    At Page 3, Line 20 of your rebuttal testimony, this

6   is a discussion of the McNabb contract and the Black & Veatch

7   feasibility study.  Have you found Page 3, Line 20?

8        A    Yes, I have.

9        Q    You say, "Further, both vendors have conducted recent

10   similar scope activities for FPL allowing FPL to assess the

11   reasonableness of their costs relative to recent past

12   experience and those of similar service providers."

13             Were McNabb and Black & Veatch awarded their prior

14   contracts as a result of a competitive bid?

15        A    Yes, sir.

16        Q    And so there were other contenders who were

17   unsuccessful in that effort; correct?

18        A    That's correct, sir.

19        Q    Is it possible, do you think, that if FPL were to

20   solicit bids for this work, those same contenders would try to

21   sharpen their pencils and be more competitive on price?

22        A    Our assessment was that the results of the previous

23   competitive bid showed such a strong determination and

24   capability on these vendors that the likelihood was, was low.

25   But also within our procedures and as good business practice

FLORIDA PUBLIC SERVICE COMMISSION

727

1   we're encouraged to leverage our purchasing power with vendors

2   who demonstrate good quality and good competitive costs.  So

3   we're encouraged to leverage that in, in certain instances, and

4   these were certainly instances in which that was applied.

5        Q    Well, when FPL leverages its purchasing power, it

6   leverages that purchasing power across the universe of

7   potential vendors, does it not?

8        A    As was established through the competitive bidding

9   process, yes, sir.

10        Q    The competitive bidding process prior to this use of

11   a single source contract; correct?

12        A    That's correct, sir.

13        Q    So it is possible that unsuccessful contenders in the

14   last RFP would attempt to be more competitive on price if

15   they'd had that opportunity.

16        A    That's a possibility.

17        Q    Would you agree that a competitive bid is the best

18   way to test the market in terms of cost?

19        A    Competitive bidding is simply one way to test the

20   market.  I think in testing the market FPL is continuously out

21   in the market as a procurer of all these types of services.  We

22   have a very strong read on the capability of these contractors,

23   the market price, the going price for these services, and can

24   continually test that in a number of ways, of which competitive

25   bidding is one, only one way.

FLORIDA PUBLIC SERVICE COMMISSION

728

1        Q    Do I understand correctly your earlier answer was

2   just that FPL's preferred method of procurement is competitive

3   bidding?

4        A    That's correct.

5        Q    And it would prefer competitive bidding because it

6   regards competitive bidding as superior to other forms where it

7   can be done; correct?

8        A    I think that the standard is competitive bidding, but

9   the reason that neither rule, statute or our own procedures

10   require competitive bidding in every situation is because it's

11   not equally applicable in every situation, and our procedures

12   recognize that.  Managers are given the responsibility to use

13   that tool when it's appropriate, and we believe we've done so.

14        Q    Where applicable and appropriate do you agree that

15   the competitive bidding is the best way to test the market for

16   price?

17        A    It is definitely a good, sound way to test the

18   market.

19        Q    Are you, are you resisting the notion that it's a

20   superior way?

21        A    Speaking of it hypothetically without a specific

22   instance in front of me, it would be very difficult to agree

23   that in all instances that it's the preferred method.

24        Q    Would you concede that FPL must have a reason to

25   designate competitive bidding as its preferred method of

FLORIDA PUBLIC SERVICE COMMISSION

729

1   procurement?

2        A    Because in most instances that's the case, yes, sir.

3        Q    Turn to Page 4, Line 21, please.

4        A    Yes, sir.

5        Q    The question posed above that asks, "Does

6   Dr. Jacobs draw conclusions regarding the methods by which

7   reasonableness of cost may be demonstrated?"  And you answer,

8   "Yes.  Dr. Jacobs broadly concludes that 'benchmarks or

9   analyses must be provided to demonstrate the reasonableness of

10   the costs.'"

11             And then turning the page, "Are such analyses

12   required by GO Procedure 705.3?"  And your answer is, "No."

13   You're not suggesting by that answer, are you, that under

14   GO Procedures 705.3 FPL has no obligation, responsibility to

15   demonstrate the reasonableness of costs resulting from a sole

16   source or single source contract?

17        A    No, I'm not.  In fact, it does request that we

18   provide an assurance of the reasonableness of proposed costs.

19        Q    And turning to Page 6 in response to another question

20   about whether FPL used benchmarks or conducted analyses, you

21   describe FPL's experience with consultants as a form of

22   benchmark to ensure that the proposed costs were reasonable for

23   the services provided.  Then you say, "These analyses are

24   common in the decision-making process used by managers, albeit

25   not always formally documented."

FLORIDA PUBLIC SERVICE COMMISSION

730

1             Are you, is it your testimony that with respect to

2   the guidelines that govern procurement for the new nuclear

3   units that there is no requirement that this assurance of

4   reasonableness be documented in, in the course of justifying

5   the decision to depart from competitive bidding?

6        A    I believe the, the single source justification

7   portion of the procedure requires the party to explain why it's

8   not in the best interest.  That's the requirement in the

9   procedure.

10             To elaborate on that a little bit, realize these

11   documents are internal controls documents that are meant to go

12   to senior managers that have years of experience in this arena

13   and are knowledgeable of the marketplace themselves.  So we're

14   having the team present memos and documentation to a

15   knowledgeable reviewer.  So they're not meant to be

16   stand-alone, highly specific exhibit type memos.  They're meant

17   to be a communication from a knowledgeable project team to a

18   knowledgeable reviewer.

19        Q    A knowledgeable reviewer who bases a decision upon

20   the facts or evidence presented by the requesting managers;

21   correct?

22        A    Both the facts and evidence presented by the

23   requesting manager, that person's knowledge and any amplifying

24   discussions that that manager would want to have with the

25   person presenting the request.

FLORIDA PUBLIC SERVICE COMMISSION

731

1        Q    And with respect to the assurance that the cost is

2   reasonable, which is one of the, one of the fundamental inputs

3   to the decision to depart from competitive bidding, would that

4   be documented in the course of asking for authority to enter a

5   single source or sole source contract?

6        A    Again, in the process that, in meeting our compliance

7   with our code or our requirements, no specific documentation is

8   mandated.  In general, the requirement that we demonstrate

9   reasonableness of costs through an explanation is there and is

10   contained in the single source justifications that we provide.

11        Q    So you regard the justification memo itself as, as

12   the vehicle, as the document that contains the assurance that

13   is the, that is required by the procedure?

14        A    Yes, sir, I do.

15        Q    Would you agree that that justification memo needs to

16   be adequate for the purpose of supporting the contention that

17   the costs are reasonable?

18        A    Within the context of its application in FPL for a

19   knowledgeable requester and a knowledgeable reviewer, yes, sir.

20        Q    Inasmuch as those decisions and the supporting

21   memoranda justifying the decisions to use single source or sole

22   source contracts are going to be significant not only for FPL's

23   internal purposes but for demonstrating to parties of this

24   proceeding and the FPL's regulators that the request to collect

25   costs are based upon contracts that are reasonable in amount,

FLORIDA PUBLIC SERVICE COMMISSION

732

1   do you think that that perhaps provides increasing impetus to

2   the need to develop the basis for the contention that the costs

3   are reasonable fully in the context of the justification memo?

4        A    These procedures have been in place at FPL for many

5   years before I came along and they've been used before this

6   body to justify single source justifications in the past.  You

7   know, I think we feel that we're doing the right thing, we

8   continue to comply with our own guidance and that that is, is,

9   is what we're doing.

10             MR. McGLOTHLIN:  I have no further questions.

11             CHAIRMAN CARTER:  Thank you.

12             Mr. Twomey.

13             MR. TWOMEY:  No, sir.

14             CHAIRMAN CARTER:  Staff.

15             MR. YOUNG:  No questions.

16             CHAIRMAN CARTER:  Commissioner Skop.

17             COMMISSIONER SKOP:  Thank you, Mr. Chairman.

18             Just one quick question to touch upon the testimony,

19   or actually two questions to touch upon the testimony the

20   witness gave.

21             Am I correct to understand that FPL in making its

22   sole source procurement selections has not expressly violated

23   any statutory provision, Commission rule or any of its internal

24   procedures?

25             THE WITNESS:  To my knowledge that's correct, sir.

FLORIDA PUBLIC SERVICE COMMISSION

733

1             COMMISSIONER SKOP:  Okay.  But in all fairness to

2   OPC, Public Counsel and the Intervenors, in light of some of

3   the concerns that are being raised and in staff testimony that

4   there's always room to fine-tune existing internal controls

5   that, you know, have proven to be adequate over years past, is

6   FPL willing to work with the various parties to address some of

7   the concerns that it brought forth during the course of this

8   hearing?

9             THE WITNESS:  FPL is always willing to accept ideas

10   and incorporate them where they're appropriate.  Yes, sir.

11             COMMISSIONER SKOP:  Thank you.

12             CHAIRMAN CARTER:  Thank you.  Anything further?

13             Mr. Anderson.

14             MR. ANDERSON:  No questions, sir.

15             CHAIRMAN CARTER:  And there are no, no exhibits for

16   rebuttal for this witness; right?

17             MR. ANDERSON:  That is correct.

18             CHAIRMAN CARTER:  Thank you, Mr. Scroggs.  Have a

19   nice day.

20             Call your next witness.

21             MS. PETTUS:  FPL calls John Reed.

22             CHAIRMAN CARTER:  John Reed.

23   Whereupon,

24                            JOHN J. REED

25   was called as a rebuttal witness on behalf of Florida Power &

FLORIDA PUBLIC SERVICE COMMISSION

734

1   Light Company and, having been duly sworn, testified as

2   follows:

3                         DIRECT EXAMINATION

4   BY MS. PETTUS:

5        Q    Mr. Reed, have you been sworn?

6        A    Yes, I have.

7        Q    Would you please state your name and business address

8   for the record, please.

9        A    John Reed, 293 Boston Post Road, Marlborough,

10   Massachusetts.

11        Q    By whom are you employed and in what capacity?

12        A    I am the Chief Executive Officer of Concentric Energy

13   Advisors.

14        Q    Have you prepared and caused to be filed in this

15   proceeding eight pages of rebuttal testimony?

16        A    Yes, I have.

17        Q    Do you have any modifications, additions, revisions

18   to make to your prefiled rebuttal testimony?

19        A    No, I do not.

20        Q    If you were asked the same questions contained in

21   your prefiled rebuttal testimony today, would your answers be

22   the same?

23        A    Yes, they would.

24             MS. PETTUS:  Mr. Chairman, I would ask that

25   Mr. Reed's prefiled rebuttal testimony be entered into the

FLORIDA PUBLIC SERVICE COMMISSION

735

1   record as read.

2             CHAIRMAN CARTER:  The prefiled testimony of, the

3   prefiled rebuttal testimony of the witness will be entered into

4   the record as though read.

5   BY MS. PETTUS:

6        Q    Mr. Reed, you are not sponsoring any exhibits to your

7   rebuttal testimony; is that correct?

8        A    That is correct.

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

754

1             MS. PETTUS:  The witness is available for

2   cross-examination.

3             CHAIRMAN CARTER:  Thank you.

4             Mr. McGlothlin.

5             MS. PETTUS:  I'm sorry.

6             CHAIRMAN CARTER:  Oh, one second.  Hang on.

7   BY MS. PETTUS:

8        Q    Mr. Reed, have you prepared a summary of your

9   rebuttal testimony?

10        A    Yes, I have.

11             CHAIRMAN CARTER:  I was with you.  We had that Jedi

12   Knight thing going on.

13             MS. PETTUS:  I was trying to work with you.  Sorry

14   for the interruption.

15             CHAIRMAN CARTER:  No problem.  Mr. Reed, you're

16   recognized.

17             THE WITNESS:  Thank you.  Good morning.

18             The purpose of my rebuttal testimony is to respond to

19   the direct testimony of Dr. William Jacobs.  My testimony

20   reviews FPL's use of sole and single source procurements and

21   presents Concentric's view within the confines of our audit

22   that FPL has complied with its corporate policies and

23   procedures by documenting reasonable business reasons for such

24   procurements.

25             First, I want to point out that Dr. Jacobs has not

FLORIDA PUBLIC SERVICE COMMISSION

755

1   claimed that any of FPL's costs are unreasonable.  He has also

2   not concluded that FPL picked the wrong contractors not even in

3   a single instance.  Nevertheless, Dr. Jacobs proposes to

4   disallow certain of FPL's costs because of his concerns with

5   the level of documentation provided by FPL while preparing a

6   single or sole source justification memorandum.

7             Concentric reviewed each of the sole and single

8   source justifications with which Dr. Jacobs takes issue and

9   FPL's corporate policies and procedures during our original

10   audit of FPL's project management activities.  He has not

11   raised any issue or any document that we did not review.

12             For reasons more thoroughly described in my rebuttal

13   testimony I believe FPL has complied with its policies and

14   procedures by identifying and documenting valid business

15   reasons for entering into each of these agreements.

16             In addition, FPL's corporate policies and practices

17   are fully consistent with industry standards.  These practices

18   are at times driven by the relatively small number of qualified

19   suppliers which are available to perform nuclear-related work.

20   My testimony addresses industry comments that at the end of the

21   last cycle of nuclear construction there were 500 contractors

22   nationwide that were certified to work on nuclear facilities.

23   Today there are less than 100, one-fifth as many.

24             Concentric has also reviewed the cost benchmarking

25   analysis performed by the company to justify its single source

FLORIDA PUBLIC SERVICE COMMISSION

756

1   justifications with which Dr. Jacobs has taken issue.  Based on

2   my very recent experience with other new nuclear projects, the

3   cost benchmarking performed by the company is consistent with

4   industry standards and reflects the market reality for nuclear

5   project procurement.

6             FPL's cost analysis uses the best available

7   information to which the company has access to ensure that the

8   anticipated cost of the procurement is reasonable.  It is also

9   certainly worth noting that the Florida Public Service

10   Commission staff has agreed with the results of our audit and

11   has concluded that FPL's practices comply with its corporate

12   policies.

13             In conclusion, the question before this Commission is

14   whether the costs FPL is seeking to recover are reasonable.  In

15   my opinion, reasonable costs flow from prudent decisions.  You

16   heard yesterday your counsel's standard that prudence is

17   determined by what a reasonable person in the nuclear power

18   industry would do.  I am firmly convinced that what FPL has

19   done fully satisfies that standard.  Thank you.

20             MS. PETTUS:  Now, Mr. Chairman, the witness is

21   available for cross-examination.

22             CHAIRMAN CARTER:  I'm still with you though.  Thank

23   you.

24             Mr. McGlothlin.

25                          CROSS EXAMINATION

FLORIDA PUBLIC SERVICE COMMISSION

757

1   BY MR. McGLOTHLIN:

2        Q    Mr. Reed, please turn to Page 16 of your prefiled

3   rebuttal testimony.

4        A    Yes, I have that page.

5        Q    Preliminary question, you're aware that FPL's policy

6   is that it prefers competitive bidding where, where that can be

7   applied.  Are you aware of that?

8        A    Could you -- I didn't hear the end of that.  Where it

9   can be applied what?

10        Q    Are you aware of the policy which states that FPL's

11   preferred means of procurement is competitive bidding?

12        A    Yes.

13        Q    Do you approve of that being the preferred method?

14        A    Yes.  Within the confines of their policy where a

15   competitive market exists that is the preferable approach.

16        Q    Okay.  At Page 16, beginning at Line 7 in response to

17   the above, question above, you discuss the company's decision

18   to use a vendor that has performed similar work for other

19   companies.  And at Line 10 you say, "While another vendor may

20   be capable of performing the same work, due to the amount of

21   work that has previously been completed for other clients, it

22   is simply not likely that another vendor could provide a

23   competitive cost with comparable quality."  And a few lines

24   below you say, "Because of the cost of changing multiple pieces

25   of equipment or fuel, the cost of using another vendor may

FLORIDA PUBLIC SERVICE COMMISSION

758

1   simply not be cost competitive without unrealistic discounts."

2   Do you see those statements?

3        A    Yes.

4        Q    Would you agree that the only way to determine

5   whether a cost-effective discount is available is to invite

6   bids to see what the alternatives are?

7        A    No, I would not agree with that.  I think it is very

8   common practice in the industry for people who are experienced

9   in this field to make that judgment based upon their knowledge

10   of the market and the order of magnitude.  If you're talking

11   about a $10 million contract and what is in rough numbers

12   $100 million to change out the equipment necessary to allow

13   another bidder to compete, you're obviously able to make that

14   judgment without having to go through a competitive

15   solicitation.

16        Q    Well, the judgment -- you say it's possible that such

17   a more cost-effective arrangement is not likely; correct?

18        A    Yes.

19        Q    That's different than the ability to say with

20   certainty that it's impossible.  Do you see there's a

21   distinction?

22        A    Yeah.  I certainly see the distinction.

23        Q    You refer at Page 15 to the Federal Aviation

24   Administration's procurement policies.  I'm looking at Lines 12

25   through 19.  Is that the same procurement mechanism that has

FLORIDA PUBLIC SERVICE COMMISSION

759

1   brought us the air traffic control system infrastructure that

2   we appreciate today?

3        A    The FAA does have responsibility for air traffic

4   control.

5        Q    Isn't it true that the FAA's procurement policy

6   documents specify that its objective is to encourage

7   competition in procurement?

8        A    Yes, and that is the same as FPL.

9        Q    You also refer to the North American Development Bank

10   at Lines 5 and 6.  And you say, "Neither of these entities

11   requires the level of analysis advocated by Dr. Jacobs."  The

12   North American Development Bank is a joint undertaking by the

13   governments of the United States and Mexico; is that correct?

14        A    Yes, I believe so.

15        Q    And it has as its purpose the lending of money to

16   develop infrastructure, environmentally sensitive

17   infrastructure near the border of the two countries?

18        A    I don't think it has to be near the border, but, yes.

19        Q    I'm going to ask for Dr. Jacobs to allow me to pass

20   out a document.

21             DR. JACOBS:  Give one to Mr. Reed?

22             MR. McGLOTHLIN:  Yes.  Yes.  The court reporter and

23   the Commissioners.

24             Dr. Jacobs is experienced in this, but he has handed

25   out things less frequently than that.

FLORIDA PUBLIC SERVICE COMMISSION

760

1             Chairman Carter, may I have an exhibit number for

2   identification?

3             CHAIRMAN CARTER:  That would be -- let me get my

4   other stack.

5             MS. BENNETT:  It would be Number 46.

6             CHAIRMAN CARTER:  I think we're at 44, 45.

7             MS. BENNETT:  46.

8             CHAIRMAN CARTER:  I knew that.  That will be

9   Exhibit 46.

10             (Exhibit 46 marked for identification.)

11             Give me one second before we -- let me change my

12   pages here.  How about a good title for it, Mr. McGlothlin?

13             MR. McGLOTHLIN:  North American Development Bank

14   Procurement Policies and Procedures.

15             CHAIRMAN CARTER:  Okay.  Hang on one second before we

16   do that.

17             MR. McGLOTHLIN:  No creativity involved there, but I

18   think it serves the purpose.

19             CHAIRMAN CARTER:  How about NADB Procurement Policies

20   and Procedures, will that work for you?

21             MR. McGLOTHLIN:  That's fine.  Yes, sir.

22             CHAIRMAN CARTER:  Commissioners, NADB Procurement

23   Policies and Procedures.

24   BY MR. McGLOTHLIN:

25        Q    Mr. Reed, we provided to you a document which has

FLORIDA PUBLIC SERVICE COMMISSION

761

1   been marked Exhibit 46 and captioned North American Development

2   Bank Procurement Policies and Procedures.  Is this the

3   procurement policy to which you referred in your testimony?

4        A    Yes, it appears to be.

5        Q    Let me direct your attention to Page 5.  Would you

6   read for us the first sentence that appears under Section 2.1

7   at the top of the page?

8        A    The sentence reads, "The underlying principle of the

9   Bank's policies is that public sector contracts should normally

10   be awarded on the basis of open competitive bidding."

11        Q    And continue to the second sentence, please.

12        A    "Only in special cases should contracts be awarded on

13   the basis of selective bidding or direct purchase."

14        Q    Now if you'll learn, if you'll turn to Page 6 of the

15   document, and I'll give you a moment to review at the bottom of

16   that page Section 3.2.

17        A    I've reviewed that.

18        Q    Would you agree that under this procurement policy

19   document as defined by the North American Development Bank that

20   the bank would consider public utilities to be among those

21   applicants who would be defined as public sector operations?

22        A    Yes, generally.

23        Q    And turning to Page 7 then, a public utility

24   applicant to the North American Development Bank would be

25   subject to the procurement process which includes opportunities

FLORIDA PUBLIC SERVICE COMMISSION

762

1   for bidding.

2        A    Yes.

3        Q    And if you'll now turn to Page 9, I'll give you a

4   moment to familiarize yourself, I'm going to refer to 3.8, Open

5   Bidding, and 3.9, Selective Bidding.

6        A    I've reviewed those.

7        Q    Okay.  Would you agree that if a public utility were

8   to approach the North American Development Bank and inform the

9   bank that the very, the universe of potential vendors is very

10   small, there's only three or four potential candidates, the

11   North American Development Bank would nonetheless regard that

12   as a form of selective bidding and would instruct the applicant

13   for a loan to conduct an RFP even for those few contenders?

14        A    That would depend on whether any condition in

15   Section 3.11 on direct purchase is applicable.  If 3.11 is not

16   applicable, under the circumstances you described selective

17   bidding would be used.

18             MR. McGLOTHLIN:  Okay.  Those are all the questions I

19   have.

20             CHAIRMAN CARTER:  Thank you.

21             Mr. Twomey.  Staff.

22             MR. YOUNG:  No questions.

23             CHAIRMAN CARTER:  Commissioners?

24             Okay.  FPL, we're back to you.

25             MS. PETTUS:  No redirect.

FLORIDA PUBLIC SERVICE COMMISSION

763

1             CHAIRMAN CARTER:  No redirect.  Okay.  So this

2   witness may be excused.  Have a nice trip.

3             MS. BENNETT:  Mr. Chairman, we marked Exhibit 46.  We

4   haven't moved it into the record.

5             CHAIRMAN CARTER:  Oh, hang on a second.  Hold the

6   phone.  Do you have -- you would like to be -- you want this to

7   be entered; right?

8             MR. McGLOTHLIN:  Yes.  I move Exhibit 46.

9             CHAIRMAN CARTER:  Let's hear from the parties.  Do

10   you have any objection to this being entered into the --

11             MR. ANDERSON:  We have no objection to the specific

12   pages referenced if that works for Mr. McGlothlin because the

13   balance of the document hasn't been interrogated about and

14   really isn't relevant to the case.

15             CHAIRMAN CARTER:  Do you want those certain pages or

16   you want the entire document?  What do you --

17             MR. McGLOTHLIN:  I'd move the entire document.  If

18   counsel wants to excerpt the pages, that's all right with me

19   too.

20             CHAIRMAN CARTER:  We can give it whatever weight,

21   Mr. Anderson.

22             MR. ANDERSON:  With that noted we have no objection.

23             CHAIRMAN CARTER:  Thank you.  Show it, Commissioners,

24   this will be, the NADB Procurement Policies and Procedures will

25   be entered into evidence.  Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

764

1             (Exhibit 46 admitted into the record.)

2             Staff, you're recognized for, before we close this

3   out you're recognized for --

4             MS. BENNETT:  We, I think, have been, have finished

5   with the testimony.  I think the record is complete except for

6   the Commission's decision.  And I would note that staff is

7   prepared to, if you were to choose to do a bench decision

8   today, we are prepared, or we also are prepared to provide a

9   written recommendation.

10             CHAIRMAN CARTER:  No, we're not prepared.  Skip over

11   that part.

12             MS. BENNETT:  Okay.  We would ask -- the Prehearing

13   Order says that prehearing briefs are due on the 24th of

14   September, but that contemplated this hearing going into next

15   week.  Since we are early in our completion, we would ask that

16   prehearing briefs be due on September 19th.  The transcripts

17   will be available September 15th.

18             CHAIRMAN CARTER:  Does that pose any hardships to any

19   of the parties?

20             MR. ANDERSON:  We are here to serve and will meet

21   that schedule.

22             CHAIRMAN CARTER:  Thank you.  Also, staff, did we

23   communicate that yesterday as we closed out the Progress case

24   as well?

25             MS. BENNETT:  I do not believe we did, but I will

FLORIDA PUBLIC SERVICE COMMISSION

765

1   communicate that with --

2             CHAIRMAN CARTER:  Mr. Burnett.

3             MR. BURNETT:  No problem, sir.

4             CHAIRMAN CARTER:  Okay.  Make it so.

5             Ms. Bennett?

6             MS. BENNETT:  There are no other matters to bring to

7   the Commission's attention.

8             CHAIRMAN CARTER:  Ms. Helton, you look like you're

9   ready to say something.  Did I miss --

10             MS. HELTON:  No, sir.  I'm ready to adjourn, just as

11   I think everybody else is.

12             CHAIRMAN CARTER:  I have the unfortunate predicament

13   of standing between y'all and lunch.  So in an exercise of

14   wisdom, I think with all preliminary matters and all matters

15   within both parties' cases in chief, as well as staff, all

16   matters being taken into consideration as well as the

17   posthearing procedures, we are adjourned.

18             (Hearing adjourned at 12:14 p.m.)

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

766

1   STATE OF FLORIDA    )

:         CERTIFICATE OF REPORTER

2   COUNTY OF LEON      )

3

4             I, LINDA BOLES, RPR, CRR, Official Commission

Reporter, do hereby certify that the foregoing proceeding was

5   heard at the time and place herein stated.

6             IT IS FURTHER CERTIFIED that I stenographically

reported the said proceedings; that the same has been

7   transcribed under my direct supervision; and that this

transcript constitutes a true transcription of my notes of said

8   proceedings.

9             I FURTHER CERTIFY that I am not a relative, employee,

attorney or counsel of any of the parties, nor am I a relative

10   or employee of any of the parties' attorneys or counsel

connected with the action, nor am I financially interested in

11   the action.

12              DATED THIS _____ day of ______________________,

13   2008.

14

15                  ________________________________

LINDA BOLES, RPR, CRR

16                  FPSC Official Commission Reporter

(850) 413-6734

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION