1

1                              BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

3                                           DOCKET NO. 090009-EI

4       In the Matter of:

5       NUCLEAR COST RECOVERY CLAUSE.

______________________________/

6

7

8                               VOLUME 1

9                          Pages 1 through 173

10              ELECTRONIC VERSIONS OF THIS TRANSCRIPT ARE

A CONVENIENCE COPY ONLY AND ARE NOT

11                THE OFFICIAL TRANSCRIPT OF THE HEARING.

THE .PDF VERSION INCLUDES PREFILED TESTIMONY.

12

13

PROCEEDINGS:           HEARING

14

15       COMMISSIONERS

PARTICIPATING:         CHAIRMAN MATTHEW M. CARTER, II

16                              COMMISSIONER LISA POLAK EDGAR

COMMISSIONER KATRINA J. McMURRIAN

17                              COMMISSIONER NANCY ARGENZIANO

COMMISSIONER NATHAN A. SKOP

18

19       DATE:                  Tuesday, September 8, 2009

20

TIME:                  Commenced at 9:30 a.m.

21

22       PLACE:                 Betty Easley Conference Center

Room 148

23                              4075 Esplanade Way

Tallahassee, Florida

24

25       REPORTED BY:           MARY ALLEN NEEL, RPR, FPR

2

1       PARTICIPATING:

2                 BRYAN ANDERSON, ESQUIRE, JESSICA CANO,

3       ESQUIRE, and KEN RUBIN, ESQUIRE, Florida Power & Light

4       Company 700 Universe Boulevard, Juno Beach, Florida

5       33418, representing Florida Power & Light Company.

6                 J. MICHAEL WALLS, ESQUIRE, and DIANNE M.

7       TRIPLETT, ESQUIRE, Carlton Fields Law Firm, Post Office

8       Box 3239, Tampa, Florida  33601-3239, representing

9       Progress Energy Florida, Inc.

10                 JOHN T. BURNETT and R. ALEXANDER GLENN,

11       Progress Energy Service Company, LLC, Post Office Box

12       14042, St. Petersburg, Florida  33733-4042, representing

13       Progress Energy Florida, Inc.

14                 EDGAR M. ROACH, JR., ESQUIRE, McGuire Woods,

15       P.O. Box 27507, Raleigh, North Carolina  37611,

16       representing Progress Energy Florida, Inc.

17                 VICKI GORDON KAUFMAN, ESQUIRE, and JON C.

18       MOYLE, JR., ESQUIRE, Keefe, Anchors, Gordon & Moyle, 118

19       North Gadsden Street, Tallahassee, Florida 32301,

20       representing Florida Industrial Power Users Group.

21                 JAMES W. BREW, ESQUIRE, and F. ALVIN TAYLOR,

22       ESQUIRE, Brickfield, Burchette, Ritts & Stone, 1025

23       Thomas Jefferson Street, NW, Eighth Floor, West Tower,

24       Washington, DC  20007, representing White Springs

25       Agricultural Chemicals d/b/a PCS Phosphate.

3

1       PARTICIPATING (Continued):

2                 GARY A. DAVIS, ESQUIRE, Gary A. Davis &

3       Associates, Post Office Box 649, Hot Springs, North

4       Carolina  28779, representing Southern Alliance for

5       Clean Energy.

6                 E. LEON JACOBS, JR., ESQUIRE, c/o Williams Law

7       Firm, 1720 S. Gadsden Street, Suite 201, Tallahassee,

8       Florida  32301, representing Southern Alliance for Clean

9       Energy, Inc.

10                 CAPTAIN SHAYLA L. McNEILL, ESQUIRE, AFCESA,

11       139 Barnes Drive, Suite I, Tyndall Air Force Base,

12       Florida  32403, representing the Federal Executive

13       Agencies.

14                 J. R. KELLY, ESQUIRE, CHARLIE  BECK, ESQUIRE,

15       CHARLES REHWINKEL, ESQUIRE and JOSEPH MCGLOTHLIN,

16       ESQUIRE, Office of Public Counsel, c/o The Florida

17       Legislature, 111 W. Madison Street, Room 812,

18       Tallahassee, Florida  32399-1400, representing the

19       citizens of the State of Florida.

20                 MR. BOB KRASOWSKI, 1086 Michigan Avenue,

21       Naples, Florida  34103.

22                 KEINO YOUNG, ESQUIRE, LISA BENNETT ESQUIRE,

23       and ANNA WILLIAMS, ESQUIRE, FPSC General Counsel's

24       Office, 2540 Shumard Oak Boulevard, Tallahassee, Florida

25       32399-0850, representing the Commission Staff.

4

1       PARTICIPATING (Continued):

2                 MARY ANNE HELTON, Deputy General Counsel,

3       Florida Public Service Commission, 2540 Shumard Oak

4       Boulevard, Tallahassee, Florida  32300-0850, Advisor to

5       the Florida Public Service Commission.

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

5

1                               I N D E X

2       OPENING STATEMENTS                                  PAGE

3            BY MR. ANDERSON                                  19

4            BY MR. McGLOTHLIN                                23

5            BY MR. DAVIS                                     26

6            BY MR. MOYLE                                     30

7

8

9                               WITNESSES

10

NAME                                                PAGE

11

STEVEN D. SCROGGS

12

Direct Examination by Mr. Anderson                    36

13       03/02/09 Prefiled Direct Testimony Inserted           39

Errata to 03/02/09 Prefiled Direct Testimony          88

14       05/01/09 Prefiled Direct Testimony Inserted           89

Errata to 05/01/09 Prefiled Direct Testimony         126

15       Cross-Examination by Mr. Davis                       131

Cross-Examination by Mr. Moyle                       165

16

CERTIFICATE OF REPORTER                              173

17

18

19

20

21

22

23

24

25

6

1                               EXHIBITS

2       NUMBER                                       ID.  ADMTD.

3         1       Comprehensive Exhibit List          10     34

4         2       Stipulated Exhibit List (green)     10     35

5         3       Stipulated Exhibit List (yellow)    10     35

6         4 - 12  SDS-1 through SDS-9                127

7        13 - 16  SDS-1 through SDS-4                127

8       130       CR3 Uprate Project Modifications    17

9       131       Turkey Point 6 and 7 Risk          135

Committee Presentation I

10

132       NRC letter to Westinghouse,        148

11                   8/27/09

12       133       First Wave or Second Wave          158

13       134       A Developer's Perspective on       163

New Nuclear Deployment

14

15

16

17

18

19

20

21

22

23

24

25

7

1                          P R O C E E D I N G S

2                 CHAIRMAN CARTER:  Good morning.  I would like

3       to call this hearing to order.  I would like to begin by

4       asking staff, would you please read the notice.

5                 MR. YOUNG:  Good morning, Commissioners.  By

6       noticed issued on August 14, 2009, this time and place

7       has been set for a hearing in Docket No. 090009-EI.  The

8       purpose of the hearing is set out in the notice.

9                 CHAIRMAN CARTER:  Okay.  Let's take

10       appearances of the parties.

11                 MR. KRASOWSKI:  Excuse me, Mr. Chairman.

12       Could I raise a point of order?  Would that be

13       appropriate at this moment?

14                 CHAIRMAN CARTER:  No, it would not,

15       Mr. Krasowski.

16                 MR. KRASOWSKI:  Okay.  When might it be?

17                 CHAIRMAN CARTER:  I'll have staff to talk to

18       you, but it will not be appropriate in this hearing.

19                 MR. KRASOWSKI:  Okay.  I wanted to ask about

20       public comment.  Is there no time allotted for public

21       comment?

22                 CHAIRMAN CARTER:  Thank you, Mr. Krasowski.

23       Have a nice day.

24                 Mr. Anderson.

25                 MR. ANDERSON:  Thank you.  Good morning,

8

1       Chairman Carter and Commissioners.  Bryan Anderson,

2       Jessica Cano, and Ken Rubin, R-u-b-i-n, appearing for

3       Florida Power & Light Company today.

4                 MR. WALLS:  Good morning.  Mike Walls and

5       Diane Triplett with Carlton Fields on behalf of Progress

6       Energy Florida.  I would also like to enter an

7       appearance for Alex Glenn and John Burnett for Progress

8       Energy Florida.  Mr. Burnett is covering a deposition in

9       the Progress Energy rate case this morning and will join

10       us after that.  And we have one more appearance of Ed

11       Roach with McGuire Woods who is also representing

12       Progress Energy Florida.

13                 CHAIRMAN CARTER:  Okay.  Mr. McGlothlin, good

14       morning.

15                 MR. McGLOTHLIN:  Good morning.  Joe McGlothlin

16       and Charles Rehwinkel with the Office of Public Counsel.

17                 MR. DAVIS:  Good morning, Mr. Chair.  My name

18       is Gary Davis.  I represent the Southern Alliance for

19       Clean Energy, and I'm happy to be with the Commission

20       today.

21                 CHAIRMAN CARTER:  Mr. Jacobs, good morning.

22                 MR. JACOBS:  Good morning, Mr. Chairman.  I'm

23       Leon Jacobs also representing the Southern Alliance.

24                 CHAIRMAN CARTER:  Mr. Moyle, good morning.

25                 MR. MOYLE:  Good morning, Mr. Chairman.  I'm

9

1       Jon Moyle, Keefe, Anchors, Gordon & Moyle law firm,

2       representing the Florida Industrial Power Users Group,

3       FIPUG.

4                 CHAIRMAN CARTER:  Mr. Brew, good to see you

5       again.

6                 MR. BREW:  Thank you.  Good morning,

7       Mr. Chairman and Commissioners.  James Brew with the

8       firm of Brickfield, Burchette, Ritts & Stone for White

9       Springs Agricultural Chemicals doing business as PCS

10       Phosphate.

11                 CHAIRMAN CARTER:  Thank you.

12                 CAPTAIN McNEILL:  Captain Shayla McNeill on

13       behalf of the Federal Executive Agencies and the United

14       States Air Force.

15                 CHAIRMAN CARTER:  Thank you.

16                 MR. YOUNG:  Keino Young, Lisa Bennett, and

17       Anna R. Williams, staff.

18                 MS. HELTON:  Mary Anne Helton, advisor to the

19       Commission.

20                 CHAIRMAN CARTER:  Thank you.  Staff, are there

21       any preliminary matters?

22                 MR. YOUNG:  Yes, Mr. Chairman.  Staff has --

23       as the first preliminary matter, staff has prepared a

24       Comprehensive Exhibit List which all the parties should

25       have.  If you don't have a copy, please let me know.

10

1                 CHAIRMAN CARTER:  Do all parties have the

2       preliminary exhibit list?

3                 Okay.  You may proceed, staff.

4                 MR. YOUNG:  Staff has prepared a Comprehensive

5       Exhibit List.  The list itself is marked as Exhibit

6       Number 1, and there are no objections to the

7       Comprehensive Exhibit List.  Staff will ask that Exhibit

8       Number 1 be entered into the record after opening

9       statements or at the Chairman's pleasure.

10                 CHAIRMAN CARTER:  We'll do it after opening

11       statements.  You may proceed.

12                 (Exhibit Number 1 was identified for the

13       record.)

14                 MR. YOUNG:  Also, Mr. Chairman, staff will ask

15       that staff's Stipulated Exhibit Lists be marked as

16       Exhibits Number 2 and 3.  Mr. Chairman, it's the green

17       and yellow sheets, for ease of reference, which you

18       should have.  And if a party doesn't have a copy, please

19       let me know.

20                 CHAIRMAN CARTER:  Do all parties have a copy

21       of the green and yellow sheets?

22                 (Exhibits Number 2 and 3 were marked for

23       identification.)

24                 CHAIRMAN CARTER:  Okay.  You may proceed,

25       staff.

11

1                 MR. YOUNG:  Mr. Chairman, staff will ask that

2       Exhibits 2 and 3 be entered into the record after

3       opening statements or at the Chairman's pleasure.

4                 CHAIRMAN CARTER:  Okay.  We'll do it right

5       after opening statements after we deal with the

6       Comprehensive Exhibit List.  You may proceed.  Wait a

7       minute.  We'll do it at that point in time.  Are there

8       any objections to that?  Okay.  You may proceed.

9                 MR. YOUNG:  Staff would suggest making the

10       prefiled exhibits as numbered in the Comprehensive

11       Exhibit List and suggest that any other exhibits

12       proffered during the hearing be numbered sequentially

13       following those listed in the Comprehensive Exhibit

14       List.

15                 CHAIRMAN CARTER:  Show it done.  You may

16       proceed.

17                 MR. YOUNG:  Mr. Chairman, all the parties,

18       staff, and Commissioners have indicated that they have

19       no questions for the following witnesses:  Lynn Fisher,

20       David Rich, Jeffrey Small, Gary Furman, and Will

21       Garrett.  These witnesses' testimony and exhibits can be

22       stipulated into the record and the witnesses can be

23       excused.

24                 CHAIRMAN CARTER:  Show it done.  And as we go

25       through the record, when those witnesses' names come up,

12

1       we'll enter their testimony into the record and their

2       exhibits into the record in that sequence.  You may

3       proceed.

4                 COMMISSIONER EDGAR:  Excuse me.  Mr. Chairman,

5       could I just ask our staff to run through that list one

6       more time a little more slowly.

7                 MR. YOUNG:  Okay.  I'm sorry.  It's Lynn

8       Fisher and David Rich, Jeffrey Small.  And all those,

9       the names I just called, are staff witnesses.  Gary

10       Furman, which is Progress Energy's witness, and Will

11       Garrett, which is Progress Energy's witness.

12                 COMMISSIONER EDGAR:  Thank you.

13                 CHAIRMAN CARTER:  Okay.  You may proceed,

14       staff.

15                 MR. YOUNG:  Mr. Chairman, I think you just

16       mentioned this.  The stipulated prefiled testimony and

17       exhibits can be taken up in turn as the witnesses are

18       called at the hearing.

19                 CHAIRMAN CARTER:  Okay.

20                 MR. YOUNG:  And at that time, staff will

21       recommend that the testimony of the stipulated witness

22       be inserted into the record as though read, and staff

23       will request that the stipulated exhibits be moved into

24       the record at that time.

25                 CHAIRMAN CARTER:  Okay.

13

1                 MR. YOUNG:  Staff would note that Mr. Carl

2       Vinson is adopting Mr. Geoff Cryan's prefiled direct

3       testimony.  The parties are aware of Mr. Vinson's

4       adoption of Mr. Cryan's testimony and do not object.

5                 CHAIRMAN CARTER:  Okay.  Should we wait until

6       we get to that point to deal with it?

7                 MR. YOUNG:  Yes, sir.

8                 CHAIRMAN CARTER:  Okay.  Well, let's do it

9       then.  You may proceed.

10                 MR. YOUNG:  Before we do that, Mr. Chairman, I

11       just want to make sure that there are no objections for

12       the record.

13                 CHAIRMAN CARTER:  Are there any objections

14       from any of the parties about Mr. Cryan -- Mr. Vinson

15       adopting Mr. Cryan's prefiled direct testimony?

16                 Without objection, show it done.  We'll deal

17       with it at the appropriate time, but there's no

18       objections.  You may proceed.

19                 MR. YOUNG:  Mr. Chairman, staff would note

20       that FPL and PEF have filed a Joint Petition for Rule

21       Variance of Rule 25-6.0423, subsection (5)(c)4, of the

22       Florida Administrative Code.  The joint petition will be

23       addressed by a separate recommendation that will be

24       taken up at the October 6th agenda conference,

25       Commission agenda conference.

14

1                 CHAIRMAN CARTER:  Okay.

2                 MR. YOUNG:  And just for the record, none of

3       the parties object to the variance.

4                 CHAIRMAN CARTER:  Okay.  Without objection of

5       any of the parties, show it done.  You may proceed.

6                 MR. YOUNG:  Mr. Chairman, all opening

7       statements, testimonies, and exhibits pertaining to

8       FPL's petition shall be taken up first, followed

9       immediately by all opening statements, testimony, and

10       exhibits pertaining to Progress Energy's petition.

11                 CHAIRMAN CARTER:  Okay.  Let's proceed then

12       with -- are there proposed stipulations?

13                 MR. YOUNG:  Yes, sir.

14                 CHAIRMAN CARTER:  We're dealing with -- we're

15       going to deal with -- what's our order?  FPL first and

16       then Progress?  Is that the order?

17                 MR. YOUNG:  Well, the first proposed

18       stipulation includes all the parties.

19                 CHAIRMAN CARTER:  Okay.  Well, let's deal with

20       that.

21                 MR. YOUNG:  That's a legal and policy issue.

22                 CHAIRMAN CARTER:  Okay.  You're recognized.

23                 MR. YOUNG:  Mr. Chairman, staff recommends

24       approval of the stipulations identified in Section 10 of

25       the Prehearing Order and outlined in a separate document

15

1       that I handed out to you entitled "Proposed Category 2

2       Stipulations."  Mr. Chairman, just for the record, the

3       Proposed Category 2 Stipulations are stipulations among

4       FPL, PEF, and staff, between FPL and staff or PEF and

5       staff.  All the other parties have taken no position on

6       these stipulations.

7                 CHAIRMAN CARTER:  Is that the agreement of the

8       parties?

9                 Okay.  Without objection -- Commissioner

10       Edgar, you're recognized.

11                 COMMISSIONER EDGAR:  Mr. Chairman, then I

12       would make a notion per our discussion that our staff

13       has just explained to us that we approve the

14       stipulations identified in Section 10 of the Prehearing

15       Order and in the document entitled "Proposed Category 2

16       Stipulated Issues."

17                 COMMISSIONER SKOP:  Second.

18                 CHAIRMAN CARTER:  It has been moved and

19       properly seconded.  Commissioners, any questions, any

20       concerns, any debate?

21                 Hearing none, all in favor let it be known by

22       the sign of "aye."

23                 (Simultaneous affirmative responses.)

24                 CHAIRMAN CARTER:  All those opposed, like

25       sign.  Show it done.

16

1                 Staff, are there any additional preliminary

2       matters?

3                 MR. YOUNG:  Yes, sir.  It's my understanding

4       that Progress Energy Florida will request that Exhibit

5       SH-1 of Steve Huntington, which was filed with the March

6       2, 2009 testimony, which was adopted by Jon Franke, be

7       moved into the record.  The description is "Summary of

8       Major Modifications of the CR3 Uprate Project."  And I

9       think Ms. Triplett wants to speak on that.

10                 CHAIRMAN CARTER:  You're recognized.

11                 MS. TRIPLETT:  Thank you, Chairman.  I just

12       wanted to say that we inadvertently neglected to include

13       it in the Prehearing Statement, and we would just ask --

14       it was a prefiled direct testimony exhibit, so perhaps

15       we can just take up with the next number on the

16       Comprehensive Exhibit List.

17                 CHAIRMAN CARTER:  Let's see.  Is there --

18                 MR. YOUNG:  And that will be Number 130.

19                 CHAIRMAN CARTER:  Any objection from the

20       parties?  Okay.  Hang on one second.  It will be Exhibit

21       Number 130.

22                 MR. YOUNG:  Yes, sir.

23                 CHAIRMAN CARTER:  Short title?

24                 MR. YOUNG:  "Summary of the Major

25       Modifications of the CR3 Uprate Project."

17

1                 CHAIRMAN CARTER:  How about "CR3 Uprate

2       Project Modifications"?

3                 MR. YOUNG:  That's fine.

4                 MS. TRIPLETT:  That's fine.

5                 CHAIRMAN CARTER:  We're going with a shorter

6       version here.  So we're basically marking it for

7       identification so it will be included, and at the

8       appropriate time with the appropriate witness, we'll

9       move it into the record as evidence.  Okay?

10                 MS. TRIPLETT:  Yes, sir.  Thank you.

11                 (Exhibit Number 130 was marked for

12       identification.)

13                 CHAIRMAN CARTER:  Okay.  Let me get my notes

14       here together.  Give me one second.

15                 Okay.  Staff, any further preliminary matters?

16                 MR. YOUNG:  No, sir.  We can move to opening

17       statements.

18                 CHAIRMAN CARTER:  Now, as we proceed now with

19       the opening statements, first it will be FPL.  Now, the

20       parties know that they have -- I think it's five minutes

21       per party; is that correct?  Is everybody clear on that?

22                 All of you guys have been before the

23       Commission before, so you're familiar with the concept

24       of the lights.  Green is good.  Amber, you have two

25       minutes left.  When the red light comes on, you have 30

18

1       seconds.  Okay?

2                 Mr. Anderson, you're recognized.

3                 MR. MOYLE:  Mr. Chairman, just one --

4                 CHAIRMAN CARTER:  Wait a minute.  Mr. Moyle.

5                 MR. MOYLE:  One more brief preliminary matter.

6                 CHAIRMAN CARTER:  You're recognized.

7                 MR. MOYLE:  Just as a courtesy.  There is a

8       lot happening these days in terms of other cases, and

9       FIPUG is going to do its best to be here, but may have

10       periods of time where it's not here and would ask to be

11       excused.

12                 CHAIRMAN CARTER:  Not a problem, Mr. Moyle.

13                 MR. MOYLE:  Thank you.

14                 CHAIRMAN CARTER:  Not a problem at all.

15                 MR. YOUNG:  Mr. Chairman?

16                 CHAIRMAN CARTER:  Yes, sir.

17                 MR. YOUNG:  Just for the record, we're taking

18       -- as stated, we're taking all of FPL's case first,

19       followed by Progress, so the opening statements will be

20       FPL, then the intervenors.  After FPL's case is

21       completely through, we'll move to Progress's opening

22       statements and then all the intervenors.

23                 CHAIRMAN CARTER:  Does that help?  Mr. Moyle,

24       Mr. Jacobs, does that help everyone to kind of plan for

25       that?  We'll do FPL's case in chief to completion, and

19

1       then we'll come back for Progress.  That may help with

2       scheduling and things of that nature.

3                 Okay.  Any other preliminary matters from any

4       of the parties?

5                 Mr. Anderson, good morning.  You're

6       recognized.

7                 MR. ANDERSON:  Good morning, Chairman Carter

8       and Commissioners.  We're here today to consider FPL's

9       2009 nuclear cost recovery request.

10                 Florida's nuclear cost recovery statute and

11       the Commission's rules are intended to encourage

12       development of additional nuclear generation to serve

13       the needs of Florida's residents.  The Commission

14       previously entered need determination orders for FPL's

15       Turkey Point 6 and 7 new nuclear plant project and the

16       expansion or uprate of the capacity of FPL's existing

17       nuclear plants.  These Commission actions support FPL's

18       work to provide additional cost-effective, zero

19       greenhouse gas emission, fuel diverse electricity for

20       FPL's customers.

21                 Under the cost recovery statute and rules, FPL

22       recovers preconstruction costs for the Turkey Point 6

23       and 7 project.  In contrast, for the uprate projects,

24       FPL mainly recovers carrying costs on the amounts

25       incurred for construction of the uprates.  The bottom

20

1       line bill impact of FPL's requested nuclear cost

2       recovery charge for 2010 is 67 cents per month for the

3       typical 1,000 kilowatt-hour residential bill.

4                 Many issues have been stipulated, so my

5       comments will focus on the remaining disputed issues,

6       first as to Turkey Point 6 and 7.

7                 During 2008, FPL entered into contracts with

8       engineering and consulting firms to perform work to move

9       along the licensing and permitting process for Turkey

10       Point 6 and 7.  This is part of FPL's carefully

11       considered strategy to maintain progress on licensing

12       while encouraging competition for future plant

13       construction work.

14                 OPC's witness Jacobs, in contrast, claims that

15       FPL's strategy, quote, separated the construction

16       function from engineering and procurement and prevents

17       FPL from entering into an engineering, procurement and

18       construction, EPC, contract in the future.  OPC's

19       position is mistaken.  FPL has not separated the

20       construction function from engineering and procurement.

21       FPL has not entered into a separate engineering and

22       procurement contract.

23                 Accordingly, our management actions to

24       maintain progress at a reasonable cost, to create

25       options and foster competition for future work, all

21

1       without committing to large EPC contract expenses at

2       this stage of the project were prudent and reasonable,

3       and OPC's claim should be rejected.

4                 Turning to the uprate project, FPL's 2008 work

5       focused on performing the nuclear engineering and design

6       work required for the uprates.  We also competitively

7       bid and procured major equipment for the uprates.

8                 FPL is committed to ensuring that only the

9       costs necessary for the uprates are included in nuclear

10       cost recovery clause computations.  We provide this

11       assurance through a number of measures which our

12       witnesses talk about.  These include comparing the

13       uprate project scope to our license renewal commitments

14       for the plants to ensure that there is no duplication.

15       We compare the uprate project scope with our detailed

16       seven-year, forward-looking plan for nuclear plant

17       capex, capital expenditure.  This plan is consistent

18       with the industry standards, industry best practices,

19       and FPL's license renewal commitments.

20                 These and other measures we describe provide

21       assurance that our NCRC computations only include the

22       costs of the uprate project, not any other nuclear plant

23       components or work.  Accordingly, OPC's claim that FPL

24       should do a speculative 20-year study instead of relying

25       upon FPL's reliable engineering information gathered

22

1       consistent with the industry best practices should be

2       rejected.

3                 Turning to feasibility, FPL filed a detailed

4       feasibility analysis using the same rigorous analytical

5       process well known from last year's nuclear cost

6       recovery proceeding and from the uprate and Turkey Point

7       6 and 7 need determination cases.  This year's

8       feasibility analysis shows that the uprate project and

9       the Turkey Point 6 and 7 project are both solidly

10       cost-effective for FPL's customers.

11                 The Southern Alliance for Clean Energy, SACE,

12       in contrast provides no such analysis at all.  Its

13       claims challenging FPL's Turkey Point 6 and 7

14       feasibility analysis should be rejected.

15                 There's a contested legal issue I want to

16       highlight for a moment about how to compute carrying

17       costs for the NCRC.  FPL's position, which we'll brief,

18       is legally correct and would result in FPL's customers

19       paying the actual financing costs for the nuclear

20       projects, no more, no less.  Other parties' positions do

21       not provide for this accurate recovery of costs, but

22       instead pose a risk of windfalls occurring either for or

23       against customers, depending on the future financial

24       conditions over which no one has control.  FPL asks that

25       the Commission adopt FPL's position on the carrying cost

23

1       computation issue, which is Issue 3 in your Prehearing

2       Order.

3                 In conclusion, FPL asks that the Commission

4       enter prudence and reasonableness findings and approve

5       the company's NCRC amounts as shown in FPL's positions

6       in the Prehearing Order.  This will result in an

7       estimated .67 per month nuclear cost recovery charge for

8       the typical 1,000 kilowatt-hour residential customer

9       during 2010.

10                 Thank you.

11                 CHAIRMAN CARTER:  Mr. McGlothlin.

12                 MR. McGLOTHLIN:  Good morning.  I will address

13       you with respect to the FPL case.  When you reach the

14       Progress Energy portion of the case, Mr. Rehwinkel will

15       present our opening statement.

16                 Counsel for FP&L said that in this case, the

17       role of the Commission is to support the utility's

18       efforts toward their nuclear projects.  I would add that

19       their role is also to scrutinize those efforts in

20       protection of the customers.

21                 With respect to FP&L, we're going to offer the

22       testimony of Dr. William Jacobs, and with respect to

23       FP&L, Dr. Jacobs' testimony consists of only 12 pages.

24       And again, with respect to FP&L, OPC is not asking for

25       specific disallowances as a result of this hearing.  But

24

1       within those 12 pages, Dr. Jacobs raises three

2       significant issues that we ask the Commission to

3       consider as the case goes forward.

4                 First is the failure of FP&L to perform the

5       analysis needed to demonstrate that all costs associated

6       with the uprate project qualify for this extraordinary

7       ratemaking remedy under the nuclear cost recovery

8       proceeding.  The second is FPL's failure thus far to

9       perform the annual long-term feasibility analysis that

10       is required by the Commission's rule.  And the third is

11       in the area of contractual organization and risk

12       management, and that is to apprise FPL that the

13       Commission is aware that any decision to depart from a

14       combination of all the functions of engineering,

15       procurement and construction give rise to the risk of

16       unreasonable costs, and the Commission will hold the

17       company accountable for any unreasonable costs.

18                 First with respect to the uprate project and

19       the criteria for the inclusion of costs in the clause,

20       last year Dr. Jacobs told the Commission that in his

21       opinion, the test that is necessary to qualify uprate

22       costs is this:  Look at the long-term needs of the

23       existing nuclear project over a horizon of 20 years and

24       determine whether any additions are necessary for the

25       continued reliable operation of the nuclear unit over

25

1       that time period.  If there are, that means that those

2       costs are ordinary O&M costs and don't qualify for the

3       cost recovery clause.

4                 FP&L has resisted the idea that this is a

5       necessary component of its case.  In its testimony

6       today, it will claim that in its own approach, it has

7       used the separate and apart test.  But you'll see when

8       you hear the evidence that FPL's contention is that the

9       engineering analyses conducted for the purpose of

10       identifying what is necessary for the uprate project

11       also satisfy the separate and apart test, and that's

12       simply not the case.  It's more in the form of jumping

13       to a conclusion that's unsupported.

14                 With respect to the feasibility test, FPL

15       updated those components that have to do with

16       projections of demand and other alternative situations.

17       It did not update its forecast of the capital costs

18       associated with the nuclear unit itself.  For that

19       reason, we contend that it has not satisfied the

20       analysis required by your own rule.

21                 They contend that the 2007 forecast or

22       projection of capital costs is sufficient for that

23       purpose, and they say in support of that that this 2000

24       projection is still valid.  But how can they say that

25       the 2000 forecast is still valid if they haven't done

26

1       the update?  Again, it's a leap to a conclusion and does

2       not satisfy the requirements of the rule.

3                 Finally, with respect to risk management,

4       Dr. Jacobs will testify that because of the possibility

5       of quarrels over scope and other considerations, the

6       best way to manage risks and reduce costs is to approach

7       contracting from the standpoint of having a single EPC

8       contract.  FP&L contends in its testimony that it has

9       not foreclosed that possibility.  And if that's the

10       case, well and good.  But in the event that FPL pursues

11       an alternative contractual arrangement, and in the event

12       that the alternative results in increased costs, we ask

13       the Commission to go on record as saying it will be

14       scrutinizing that approach so that the company cannot

15       later claim hindsight regulation.

16                 Thank you.

17                 CHAIRMAN CARTER:  Thank you.

18                 You're recognized, Southern Alliance.

19                 MR. DAVIS:  Good morning.  Yes.  Chairman

20       Carter and members of the Commission, Southern Alliance

21       for Clean Energy intervened in this case to assist the

22       Commission in its exercise of supervision over the

23       expenditures for two massive nuclear projects that will

24       add even more rate increases for Florida ratepayers.

25                 The Commission's rules require that a utility

27

1       seeking cost recovery for nuclear project costs submit

2       for Commission review and approval a detailed analysis

3       of the long-term feasibility of completing the power

4       plant.  SACE is going to focus on the feasibility

5       analysis in this matter.  SACE believes that this is not

6       a hollow requirement, nor is it simply a means to force

7       the utilities to engage in long-range planning for their

8       own good.  The utilities do that anyway.

9                 With the cost recovery, when utilities bet the

10       farm on an $18 billion project, the ratepayers suffer if

11       the bet goes bad.  And for Florida Power & Light's

12       Turkey Point 6 and 7, that bet is looking worse every

13       day.

14                 SACE will present two knowledgeable experts,

15       Dr. Mark Cooper and Mr. Arnie Gundersen, who have

16       reviewed FP&L's feasibility analysis, and they will

17       point out the dramatically changed circumstances in the

18       time since the need determination for Units 6 and 7 that

19       thoroughly undermine the long-term feasibility of

20       completing the power plant at this time.  And I want to

21       focus on "at this time."  We're not saying never.  We're

22       saying at this time, long-term feasibility does not

23       exist.

24                 These dramatically changed circumstances

25       include declining electricity demand, falling natural

28

1       gas prices, licensing delays with the Nuclear Regulatory

2       Commission, the emergence of a renewable portfolio

3       standard in federal legislation, as well as aggressive

4       building and appliance efficiency standards in that

5       legislation, rising costs of nuclear construction,

6       tightened financial markets, and growing concerns on

7       Wall Street about new nuclear reactors.  Any one of

8       these factors might be enough to render a new nuclear

9       plant too risky, but together they are overwhelming at

10       this point.

11                 Florida Power & Light at least acknowledges

12       that the feasibility analysis is a important tool and

13       that economic feasibility is an important part of that

14       tool.  I think that's a step in the right direction, but

15       its economic analysis is not a real analysis and should

16       not approved by the Commission.

17                 FPL has not adjusted the costs of the project

18       since 2007, as was mentioned by my colleague, and it is

19       still relying on natural gas and CO2 costs that are far

20       higher than where current projections are pointing.

21       You'll hear that natural gas costs have plummeted to the

22       point where they're below $3 a million Btu.

23                 FPL also acknowledges many of the factors that

24       SACE has discussed it its prefiled testimony, but it's

25       still clinging to an unrealistic schedule to complete

29

1       the Turkey Point units with no float left in the

2       schedule.  Further slippage in the schedule is not

3       accepted as a possibility, and the costs of likely

4       further slippage are not part of the equation in their

5       analysis.

6                 FPL's response to having these problems

7       pointed out is to present a false picture of the

8       testimony of SACE's experts and to present a false

9       choice to the Commission.

10                 SACE is not suggesting that FPL and the

11       Commission stop evaluating the nuclear option.  That is

12       not what we're advocating.  But we are recommending,

13       instead of stopping continued evaluation, stop further

14       development at this point.  It is clear that the

15       expensive engineering and licensing activities FPL is

16       undertaking in 2009 and 2010 are not evaluation.  They

17       are development.

18                 In the end, the Commission's review of the

19       long-term feasibility of Turkey Point 6 and 7 should be

20       based on the recognition that FPL would not be taking

21       the nuclear risk for Turkey Point 6 and 7 but for the

22       ability to charge the ratepayers along the way and that

23       it is difficult for any utility to back away from a

24       project that would more than double its rate base.

25                 FPL in its direct testimony has talked about

30

1       the concept of off-ramps, halting or limiting project

2       expenditures for defined periods of time to manage cost

3       risks.  We think that's a good concept for the

4       Commission to consider in this hearing.  By denying

5       approval of FPL's feasibility analysis, the Commission

6       can turn on the directional signal and begin turning the

7       wheel toward the nearest off-ramp for Turkey Point 6 and

8       7.

9                 Thank you.

10                 CHAIRMAN CARTER:  Mr. Moyle.

11                 MR. MOYLE:  Thank you.  Thank you,

12       Mr. Chairman.  FIPUG would like to make a few points for

13       you to consider as we engage in this hearing, to

14       consider the appropriatenesses of FP&L recovering moneys

15       related to their nuclear project.

16                 First of all, Mr. Anderson said, "Well, it's

17       only 67 cents per month."  I think it's important to

18       remember the context in which you're being asked to make

19       this decision, with unemployment in the state at an

20       all-time high and still being in the midst of a very

21       difficult economic time.  So while 67 cents per month

22       may not sound like a lot, things add up over time,

23       particularly with families that are struggling to get by

24       in these economic times, so please keep that in mind.

25                 And also, be mindful of the rule which is

31

1       governing these proceedings which relates to the nuclear

2       cost recovery, 25-6.0423.  And there has been some

3       discussion about it, but I think it would be helpful if

4       I just read briefly into the record a provision that

5       you're going to hear a lot about, which is the long-term

6       feasibility of completing the power plant.

7                 Public Counsel said, "Well, FPL submitted some

8       stale information about the capital costs."  You're

9       being asked to interpret your rule, and the provision

10       that we think is pertinent is paragraph 5.  It's

11       (5)(c)5.  It says, "By May 1 of each year, along with

12       the filings required by this paragraph, a utility shall

13       submit for Commission review and approval a detailed

14       analysis of the long-term feasibility of completing the

15       power plant."  I think the modifier before "analysis" is

16       important, a detailed analysis.  It can't be a broad

17       brush.  I don't think it can be dated information.  I

18       think that you all when enacting this rule said, "We

19       want to have a good look at the long-term feasibility.

20       Bring us that information."  And we would respectfully

21       suggest that that has not been provided to you.

22                 You're going to hear some discussion about an

23       EPC contract, engineering, procurement and construction,

24       and typically -- it's called an EPC contract because all

25       these things are together.  Now, FPL is proposing to

32

1       drop the C from it, and that presents some concerns.

2       And I'll use kind of an analogy of building a house.

3       Usually you have a general contractor that you'll hire,

4       and he'll be responsible for getting all of the

5       subcontractors up, and if you have a problem, you go

6       straight to the general contractor.  By dropping the C

7       and only doing the engineering and procurement, with

8       possibly leaving the construction to another entity, we

9       think you're inviting lots of finger pointing as you go

10       forward, with the contractor saying, "Well, that wasn't

11       within my scope."  And it has not been done that way

12       previously, I don't believe, in any nuclear power plant.

13                 FPL will argue, "Well, we're trying to foster

14       competition in this industry," but I think the evidence

15       will show that there is competition.  The engineer that

16       FPL has contracted with has familiarity with a General

17       Electric nuclear turbine, but not the Westinghouse

18       turbine that they've selected for their technology.  So

19       it's kind of like, you know, in some respects hiring a

20       mechanic who works on Mazdas to come work on your Ford.

21       He doesn't have that familiarity with the technology.

22       But we'll explore that in greater detail.

23                 And the final point that I wanted to raise is

24       a policy issue.  You heard counsel suggest that these

25       projects are "bet your farm" endeavors.  And I think

33

1       there will be some indication that some of the rating

2       agencies have said these are big projects, terms like

3       bet the farm, bet the company.  There's a lot of risk

4       associated with them.

5                 And for two Florida utilities to be engaging

6       in these huge projects at the same time, we think it

7       makes some sense for there to be some examination of

8       strategic partnerships.  Indeed, the rating agencies

9       have said to companies, "Explore strategic

10       partnerships," and we do not think that that has been

11       explored enough.  Florida is in a situation where the

12       demand is coming down, and a strategic partnership

13       should be explored.

14                 Thank you, Mr. Chairman.

15                 CHAIRMAN CARTER:  Thank you.  I think we've

16       covered the intervenors for this portion for FPL; is

17       that correct?

18                 Now, all of the witnesses that will be

19       testifying in the FPL case, would you please stand?

20                 Can you all see these three lights here in

21       front of me?  I want to explain the lights before I

22       swear you in as a group.  The green light means --

23       obviously, green is always good.  You'll have five

24       minutes for your summary.  The yellow -- the amber light

25       means you've got two minutes left.  The red light means

34

1       you've got 30 second left.  Okay.  Everybody saw that?

2                 Okay.  Would you please raise your right hand?

3                 (Witnesses collectively sworn.)

4                 CHAIRMAN CARTER:  Thank you.  Please be

5       seated.  You may call your first witness.

6                 MR. YOUNG:  Mr. Chairman, before we move --

7                 CHAIRMAN CARTER:  Mr. Young.

8                 MR. YOUNG:  Before we move to the first

9       witness, staff would note that, as stated in the

10       preliminary matters, staff will ask that the

11       stipulated --

12                 CHAIRMAN CARTER:  Okay.  One second.  That's

13       right.  We need to get back to the -- okay.  Let's deal

14       with that.  Bring us up to date on those that we agreed

15       to enter.  One would be the Comprehensive Exhibit List;

16       is that correct?

17                 MR. YOUNG:  Yes, sir.  That will be Exhibit

18       Number 1.  That will be identified as Exhibit Number 1.

19                 CHAIRMAN CARTER:  Are there any objections?

20       Without objection, show it done.

21                 (Exhibit Number 1 was admitted into the

22       record.)

23                 CHAIRMAN CARTER:  Staff, you're recognized.

24                 MR. YOUNG:  Then staff's Composite Exhibit

25       Lists that are marked 2 and 3 -- again, for ease of

35

1       reference, that's the green and yellow pages, green and

2       yellow sheets.

3                 CHAIRMAN CARTER:  The green and yellow sheets.

4       Which one is 2 and which one is -- okay.  I guess 3 is

5       the yellow and 2 is the green?

6                 MR. YOUNG:  Yes, sir.  It's marked.

7                 CHAIRMAN CARTER:  Are there any objections?

8       Without objection, show it done.

9                 (Exhibits Number 2 and 3 were admitted into

10       the record.)

11                 CHAIRMAN CARTER:  Staff.

12                 MR. YOUNG:  Mr. Chairman, as you mentioned,

13       witness summaries shall not exceed five minutes per

14       witness for each petition.  Several witnesses will be

15       taken up as a panel, and the summary for these witnesses

16       will be five minutes total.

17                 CHAIRMAN CARTER:  Okay.

18                 MR. YOUNG:  And that's more so in the Progress

19       Energy docket.

20                 CHAIRMAN CARTER:  Not in this docket here.

21                 MR. YOUNG:  Not in this docket that I'm aware

22       of.

23                 CHAIRMAN CARTER:  Any further preliminary

24       matters before we go into opening statements from either

25       the parties or staff?  Let me look to the parties first.

36

1       Any preliminary matters?

2                 Staff, any further preliminary matters?

3                 MR. YOUNG:  No, sir.

4                 CHAIRMAN CARTER:  Ms. Helton, did you enter an

5       appearance?

6                 MS. HELTON:  Yes, sir, I did.

7                 CHAIRMAN CARTER:  Okay.  Good morning.

8                 MS. HELTON:  Good morning.

9                 CHAIRMAN CARTER:  Mr. Anderson, call your

10       first witness.

11                 MR. ANDERSON:  Thank you.  FPL calls Steven D.

12       Scroggs.

13       Thereupon,

14                          STEVEN D. SCROGGS

15       was called as a witness on behalf of Florida Power &

16       Light Company and, having been first duly sworn, was

17       examined and testified as follows:

18                          DIRECT EXAMINATION

19       BY MR. ANDERSON:

20            Q.   Good morning, Mr. Scroggs.  Can you hear me

21       okay?

22            A.   Good morning.  Yes, I can.

23                 CHAIRMAN CARTER:  Give us a check there,

24       Mr. Scroggs.  Just say your name for the record.

25                 THE WITNESS:  Steve Scroggs.

37

1                 CHAIRMAN CARTER:  Okay.  Much better.

2       Mr. Anderson.

3       BY MR. ANDERSON:

4            Q.   Would you tell us your name and business

5       address?

6            A.   Yes, sir.  My name is Steven D. Scroggs.  I am

7       employed by Florida Power & Light.  My business address

8       is 700 Universe Boulevard in Juno Beach, Florida.

9            Q.   In what capacity are you employed by FPL?

10            A.   I'm the Senior Director of Project Development

11       in charge of the Turkey Point 6 and 7 project.

12            Q.   Did you prepare and cause to be filed 49 pages

13       of prefiled direct testimony in this proceeding on

14       March 3, 2009?

15            A.   Yes, I have.

16            Q.   Did you also prepare and also cause to be

17       filed 37 pages of prefiled direct testimony on May 1,

18       2009?

19            A.   Yes, I have.

20            Q.   Did you submit some errata in connection with

21       your testimony?

22            A.   Yes, I have.

23            Q.   Do you have any further changes or revisions

24       to your prefiled direct testimony?

25            A.   No, I do not.

38

1            Q.   If I asked you the same questions contained in

2       the prefiled direct testimony, would your answers be the

3       same?

4            A.   Yes.

5                 MR. ANDERSON:  FPL asks that the prefiled

6       direct testimony be inserted into the record as though

7       read.

8                 CHAIRMAN CARTER:  The prefiled testimony of

9       the witness will be inserted into the record as though

10       read.

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

88

1

2

3

4

5

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

127

1       BY MR. ANDERSON:

2            Q.   You're sponsoring some exhibits?

3            A.   Yes.

4            Q.   For your March testimony, these are SDS-1

5       through SDS-9?

6            A.   Yes.

7            Q.   For May, it is SDS-1 to SDS-4; is that right?

8            A.   That's correct.

9                 MR. ANDERSON:  Mr. Chairman, these have been

10       premarked on staff's Comprehensive Exhibit List as staff

11       4 to 12 and 13 to 16.

12                 CHAIRMAN CARTER:  For the record, 4 through 12

13       and 13 through 16 on the Comprehensive Exhibit List.

14       You may proceed.

15                 (Exhibits Number 4 through 16 were identified

16       for the record.)

17       BY MR. ANDERSON:

18            Q.   Have you prepared a summary of your testimony?

19            A.   Yes, I have.

20            Q.   Please provide your summary to the Commission.

21            A.   Thank you.  Mr. Chairman and Commissioners, I

22       appreciate the opportunity to come before you today.

23                 The purpose of my testimony is to describe the

24       activities associated with FPL's management of the

25       Turkey Point 6 and 7 project from its inception to

128

1       present and the plans for the project through the end of

2       2010.  My testimony describes the progress made and how

3       key decisions are addressed through the deliberate,

4       stepwise process FPL is employing to create Turkey Point

5       6 and 7.  My testimony, the exhibits, and the Nuclear

6       Filing Requirements I sponsor will provide the

7       Commission with information necessary to validate that

8       FPL's actual costs through 2008 have been prudently

9       incurred and that FPL's projected costs for 2009 and

10       2010 are reasonable.

11                 Further, my testimony will support the

12       conclusions of the annual feasibility analysis that

13       indicate that the project continues to offer the

14       benefits of cost-effectiveness, increased energy

15       independence, fuel diversity, and reduced greenhouse gas

16       emissions that led to your original affirmative need

17       determination.

18                 The management of the project can be

19       summarized as a series of key decisions that establish

20       the pace and the risk of the project.  To formulate

21       those decisions, FPL continually collects and evaluates

22       information and weighs the risk of acting as opposed to

23       taking no action.

24                 For example, during 2008, FPL identified the

25       Westinghouse AP-1000 as the preferred technology and

129

1       pursued commercial negotiations with Westinghouse/Shaw

2       Stone & Webster to develop a mutually agreeable scope,

3       schedule, terms, and price for the construction of the

4       project.  By continually evaluating the market, it was

5       identified that FPL should act to obtain a critical

6       reservation on manufacturing space for certain key

7       forgings, but it did not need to spend $35 million on

8       other long lead procurement items.

9                 It was also as the result of this process that

10       FPL determined it was in the best interests of our

11       customers to defer entering into a purchase contract and

12       to maintain the option for competitive bidding on future

13       construction scope.  While not precluding a combined

14       engineering, procurement and construction contract, the

15       strategy of pursuing an EP contract first creates an

16       important option for our customers.

17                 Throughout the course of the project, FPL has

18       employed industry-leading project controls and

19       procedures to ensure that expenditures are appropriate

20       and competitive.  We have acted when it was appropriate

21       to act, and we have chosen not to act when circumstances

22       indicated that was appropriate.  All the while, we have

23       continued to make solid progress towards the project

24       goals.  Such adaptive project management is the result

25       of the stepwise, deliberate approach necessary to

130

1       maintain progress and manage risk.

2                 I am confident that you will agree that the

3       Turkey Point 6 and 7 project is being managed in a

4       responsible manner, decisions are reasonable, costs are

5       being prudently incurred, and that the very benefits

6       which started us on this endeavor have not changed and

7       now are as important as ever.  FPL customers benefit

8       every day from the low fuel costs and zero greenhouse

9       gas emissions that are a result of nuclear generation

10       decisions made some 40 years ago.  Continued application

11       of the nuclear cost recovery clause will allow future

12       customers to enjoy these same benefits.

13                 This completes my summary.

14                 MR. ANDERSON:  Mr. Scroggs is available for

15       cross-examination, Mr. Chair.

16                 CHAIRMAN CARTER:  Thank you.  Mr. McGlothlin.

17                 MR. McGLOTHLIN:  OPC will reserve its

18       questions for later.

19                 CHAIRMAN CARTER:  I beg your pardon?

20                 MR. McGLOTHLIN:  OPC has no questions at the

21       present.

22                 CHAIRMAN CARTER:  Are you guys going to do

23       like we did last week?  Is that a new lineup?  Is that

24       the plan, Mr. Moyle, or what's the plan here?

25                 MR. MOYLE:  We're coming straight down the

131

1       line.

2                 CHAIRMAN CARTER:  Oh, straight down the line?

3       Oh, that's great.

4                 MR. DAVIS:  I'm prepared to go, sir.

5                 CHAIRMAN CARTER:  You're recognized.  You may

6       proceed.

7                 MR. DAVIS:  Thank you, Mr. Chairman.

8                           CROSS-EXAMINATION

9       BY MR. DAVIS:

10            Q.   Mr. Scroggs, would you agree that the addition

11       of FP&L Turkey Point 6 and 7 would more than double the

12       rate base for FP&L?

13            A.   Yes.

14            Q.   And that was one important reason for FP&L to

15       decide to invest in these new units; correct?

16            A.   No.  The drivers for new nuclear in our

17       portfolio is to maintain a balance of fuel, to provide

18       fuel diversity, to continue to reduce greenhouse gas

19       emissions, and more importantly, to provide

20       cost-effective, stably priced electricity for our

21       customers.

22            Q.   You don't agree it was one reason to invest?

23            A.   Our resource planning process doesn't look at

24       the capital input to the process.  It tells us what is

25       the best choices through a very objective process.

132

1                 MR. DAVIS:  Mr. Chair, I have not appeared

2       before this Commission before, and I hope I get your

3       procedures correct.

4                 CHAIRMAN CARTER:  Hang on a sec.  Now, you've

5       got a red -- red is always not necessarily good.  It's

6       certainly not bad, but red is different.  Is that a

7       confidential --

8                 MR. DAVIS:  It is, Mr. Chair.

9                 CHAIRMAN CARTER:  Okay.  Have all the parties

10       -- you have not appeared before us before, but have all

11       the parties gotten together on the handling of

12       confidential documents?  Mr. Anderson?

13                 MR. ANDERSON:  I'll ask Ms. Cano to list the

14       parties that have signed agreements, so if there's to be

15       a distribution, it should be limited only to people who

16       have signed the confidentiality agreement.

17                 CHAIRMAN CARTER:  Okay.  All right.  Staff,

18       have you talked to the parties about handling

19       confidential documents before?  Let's do --

20                 MR. YOUNG:  At the prehearing we did talk

21       about it, and it was included in the Prehearing Order.

22                 CHAIRMAN CARTER:  Let's do this,

23       Commissioners.  Let's take five minutes and let staff

24       get with the parties before we go down this road on our

25       confidential documents.  We're just on a brief recess.

133

1                 (Short recess.)

2                 CHAIRMAN CARTER:  We are back on the record.

3       And when we took a break, there was an opportunity for

4       the parties to get together and look over the documents,

5       and let us proceed with our cross-examination.

6                 MR. JACOBS:  Mr. Chairman, just one moment.  I

7       think we're narrowing down our scope of inquiry so that

8       we can alleviate all the concerns.

9                 CHAIRMAN CARTER:  Okay, Mr. Jacobs.

10                 (Off the record briefly.)

11                 CHAIRMAN CARTER:  Mr. Anderson.

12                 MR. ANDERSON:  Mr. Chairman, as you know, the

13       usual process is for people to share things in advance

14       so we can just do the type of review we did, and none of

15       us had a chance to do that because that wasn't put in

16       front of us.  But what we did do is verify with counsel

17       that there are two specific pages, one in one exhibit

18       and one in another, that he wishes to interrogate with

19       respect.

20                 Those specific pages, we do not have a problem

21       with interrogation or being even not confidential if

22       counsel chooses.  There are other portions of the

23       exhibit which do raise considerations, but the

24       individual pages counsel has specified we're okay with,

25       and we think it will make the hearing go better.  Does

134

1       that make sense?

2                 CHAIRMAN CARTER:  Okay.  Let's stay on course.

3       You're recognized.  You may proceed.

4                 MR. DAVIS:  Thank you, Mr. Chair.

5       BY MR. DAVIS:

6            Q.   Mr. Scroggs, do you have what we've marked as

7       Exhibit 131, which would be a SACE cross-examination

8       exhibit?

9                 CHAIRMAN CARTER:  Do you need a number for

10       that?

11                 MR. DAVIS:  Yes.

12                 CHAIRMAN CARTER:  Okay.  You haven't been with

13       us before, so whenever you have a document, if you're

14       going to use it for cross-examination, it may not be

15       necessary, but if you're going to want to eventually try

16       to enter it in, you need to get a number from the Chair.

17                 MR. DAVIS:  Okay.  Mr. Chair, we would like

18       this exhibit which we've provided to the Chair and to

19       the Commissioners to be --

20                 CHAIRMAN CARTER:  It will be Exhibit Number

21       131, Commissioners.  Short title?

22                 MR. DAVIS:  A short title would be Turkey

23       Point 6 and 7 Risk Committee Presentation I.

24                 CHAIRMAN CARTER:  Okay.  Turkey Point 6 and 7

25       Risk Committee Presentation I.  You may proceed.

135

1                 MR. DAVIS:  Thank you.

2                 (Exhibit Number 131 was marked for

3       identification.)

4       BY MR. DAVIS:

5            Q.   Mr. Scroggs, do you have Exhibit 131 in front

6       of you now?

7            A.   Yes, sir, I do.

8            Q.   And if I ask you -- first of all, the cover

9       page -- this Turkey Point 6 and 7 Risk Committee

10       Presentation I, did you make this presentation?

11            A.   I participated in it, yes, sir.

12            Q.   Your name is on this cover sheet; is that

13       correct?

14            A.   Yes, it is.

15            Q.   And that was dated June 25, 2008?

16            A.   That's correct.

17            Q.   And what was the Risk Committee?

18            A.   The Risk Committee is a multifunctional group

19       within FPL that brings together senior managers and

20       directors to provide an independent look at all projects

21       that are under way in the company.  It gives us the

22       ability to obtain perspectives and the benefit of

23       information from managers that have different

24       requirements or different duties than ours.  It gives us

25       a peer group review.

136

1            Q.   Is it go/no go decision-maker within FP&L?

2            A.   Not necessarily, no, sir.

3            Q.   Do they provide recommendations to that

4       effect?

5            A.   Yes, sir, they do.

6            Q.   And do those recommendations go to the board?

7            A.   Yes, sometimes they do go to the board.

8            Q.   Now, on page 9 of Exhibit 131 -- and you'll

9       notice I didn't include all the pages from this lengthy

10       presentation, but page 9, do you have that in front you?

11            A.   Yes, sir, I do.

12            Q.   And the caption of that is "Reasons to

13       Invest"; is that correct?

14            A.   That's correct.

15            Q.   And one of the reasons to invest under

16       economic factors is that Turkey Point 6 and 7 is likely

17       to more than double the rate base; right?

18            A.   That is correct.

19            Q.   So that would correct your previous testimony

20       when you said that was not one of the factors?

21            A.   If I could clarify, I believe the earlier

22       question was, in the resource planning and selection of

23       the process, was the doubling of the rate base or the

24       size of the project a factor.  In our resource planning

25       process, which witness Sim can speak to more directly,

137

1       that is not a factor.

2            Q.   I understand that.  Doubling the rate base,

3       though, would increase FP&L's revenues tremendously,

4       would it not?

5            A.   Yes, sir, and it will also introduce risk, as

6       many have pointed out.

7            Q.   Okay.  Now, during Mr. Anderson's opening,

8       which I believe you were here for, he mentioned that the

9       bill, the average monthly bill for consumers in 2010

10       would increase by 67 cents a month, I believe.  Is that

11       what you understand?

12            A.   The average bill for our customers in 2010

13       will be approximately 67 cents as related to both the

14       Turkey Point 6 and 7 project and the extended power

15       uprate.  So the impact of both projects contribute 67

16       cents to the average customer's bill.

17            Q.   For Turkey Point 6 and 7, is there a separate

18       number that was provided to the staff in an

19       interrogatory answer that you're aware of?

20            A.   I believe that probably has been provided, but

21       I don't have that in front me.

22            Q.   Okay.  Are you aware of higher numbers as the

23       years proceed from 2010 onward, such as in 2011 that the

24       average monthly bill for a 1,000 kilowatt-hour usage

25       would increase by $3.60?

138

1            A.   Yes, that would be the natural progression.

2       As the project moves forward and additional moneys are

3       spent, the increase will be proportionally higher.

4            Q.   And in 2017, which is still before there's any

5       electricity being generated by Turkey Point 6 and 7,

6       assuming it proceeds according to plan, there would be a

7       $7.87 increase in the monthly bill; correct?

8            A.   That would be the amount attributable to this

9       project in our estimate, yes, sir.

10            Q.   Now, this is in addition to the base rate

11       increase that FP&L is now seeking in a separate docket;

12       correct?

13            A.   That's correct.  It's independent.

14            Q.   Now, back to reasons to invest, not

15       necessarily the exhibit that we've referred to, but FP&L

16       would not be building Turkey Point 6 and 7 without the

17       nuclear cost recovery clause, would it?

18            A.   We would not be entering into this project

19       without the benefits of the nuclear cost recovery

20       process, yes, sir.

21            Q.   And that's because the cost recovery provision

22       reduces the risk to FP&L?

23            A.   The cost recovery -- yes, the cost recovery

24       reduces risk.  It also provides a pay-as-you-go

25       opportunity rather than deferring that and building up

139

1       costs for our customers.  So it's a better deal for our

2       customers.

3            Q.   Let me turn your attention to the analysis of

4       long-term feasibility just a minute, which you've spoken

5       about in your direct testimony.  You agree that the

6       annual detailed analysis of long-term feasibility of the

7       Turkey Point 6 and 7 project should include an analysis

8       of economic feasibility?

9            A.   Yes, sir, I do.

10            Q.   As a matter of fact, FP&L uses the feasibility

11       analysis as a mitigation strategy to reduce the risk

12       that market trends may change the economics; is that

13       right?

14            A.   I'm not sure if I understand your question,

15       sir.

16            Q.   Well, do you find the feasibility analysis a

17       useful tool for your own decision-making?

18            A.   Yes, sir.  The feasibility analysis is an

19       extension of our normal resource planning process and is

20       a basis of the need determination and is the basis of

21       our ongoing evaluation of the project.

22            Q.   But in this feasibility analysis that you

23       presented to the Commission, you have not revised the

24       project costs since 2007; correct?

25            A.   We have not needed to revise the project costs

140

1       since 2007.  Our project costs are very representative

2       of where we believe them to be, and in comparison to

3       other AP-1000 projects throughout the Southeast, we find

4       that our project cost estimate, particularly the high

5       end, is quite representative of the projects that have

6       already entered into EPC contracts and have the benefit

7       of a contract to re-evaluate their costs.

8            Q.   Now, when you talk about the project costs, I

9       believe that the numbers are 12.1 to 17.8 billion; is

10       that correct?

11            A.   That's the cost estimate range, yes, sir.

12            Q.   So I'm going to use 12 to 18, because that's

13       what people have been throwing around as numbers.  Is

14       that okay?

15            A.   Yes, sir.

16            Q.   You know, a billion here, a billion there,

17       pretty soon it's real money.  You agree that 12 billion

18       to 18 billion is quite a range, a wide range?

19            A.   Twelve to 18 billion is a wide range, yes,

20       sir.

21            Q.   I mean, if you took the midpoint of that as

22       15 billion, there's a variation of 20 percent either

23       way; right?

24            A.   That's correct.

25            Q.   You've now said, I believe, in response to my

141

1       prior question that the high end is more in line now

2       with what other utilities are estimating and projecting

3       for their cost of building nuclear power plants,

4       particularly the AP-1000?

5            A.   The upper half of the range, yes, sir.

6            Q.   Well, shouldn't you shift the whole range,

7       then, and analyze the new range rather than just assume

8       that the 18 billion is your new number?

9            A.   No.  I believe -- you know, this is an very

10       long-term project.  When FPL originally developed our

11       cost estimate range, we did it without the influence of

12       commercial interests.  We took a very academic look at

13       the cost estimate process.  We built into the process a

14       number of assumptions for high material costs, premiums

15       for labor, and in doing so, we provided ourselves a

16       range that we felt was comfortable.  At the time, it was

17       actually considered quite shocking and quite high.

18                 As time has progressed, things will change.

19       Production cost indices that drive the material costs

20       were rapidly escalating in 2008 and have since turned

21       and are moderating.  So over time, those ranges that

22       produce the cost estimate will fluctuate.

23                 Our purpose and our need to evaluate routinely

24       whether or not that cost estimate range is still valid

25       and produces a cost estimate that is suitable for use in

142

1       the feasibility analysis, that's the kind of review that

2       we've done, and that's why we felt that our cost

3       estimate range is still very valid and suitable for use

4       in the feasibility analysis.

5            Q.   And what you used in the feasibility analysis

6       was a low, medium, and high range; right?

7            A.   It works out that way, yes, sir.

8            Q.   And the high was still 18 billion.  You didn't

9       shift the high to 21 billion, which if you were shifting

10       the whole range you would go to?

11            A.   No.  That's correct.

12            Q.   And you intend to re-evaluate the costs in the

13       near future; right?

14            A.   We are routinely evaluating the costs as we

15       work through negotiations with Westinghouse/Shaw.

16            Q.   What's the time frame now for an EP contract

17       with Westinghouse/Sharp?

18            A.   We're looking at --

19            Q.   Shaw, I mean.

20            A.   Our decision process would be -- we need to

21       make a decision before the end of 2009.

22            Q.   I believe I read the third quarter of 2009,

23       you're going to have an EP contract with

24       Westinghouse/Shaw; is that right?

25            A.   That's not what I said, sir.  We need to make

143

1       a decision before the end of 2009.  We may or may not

2       enter into an EP contract.

3            Q.   Okay.  But if you do enter into an EP

4       contract, then, of course, you'll have much better

5       numbers for the costs?

6            A.   Yes, sir.

7            Q.   Now, those costs aren't going down, are they?

8            A.   Some costs have been going down.  The Producer

9       Price Index and other materials indices have moderated

10       since 2008.

11            Q.   But the cost of components for nuclear power

12       plants is still going up?

13            A.   The cost of components we have not seen come

14       down with the indices.

15            Q.   Let me talk about the schedule for a minute.

16       The original schedule for the application submittals for

17       your NRC combined operating license assumed an

18       aggressive 15-month schedule; is that right?

19            A.   That's correct.

20            Q.   And that was your schedule to prepare and

21       submit the applications, and you've slipped that three

22       months already?

23            A.   That's correct.  We were able to benefit from

24       preceding AP-1000 applications and understand that the

25       NRC had numerous questions about geology and

144

1       hydrogeology with the Progress Levy site.  That has

2       similar geological issues to our site, and instead of

3       submitting an incomplete or insufficient combined

4       operating license application, we were able to extend

5       the time to deliver that and deliver a much better

6       product, a much more complete product.

7            Q.   But those geological issues have not been

8       resolved for Progress Levy nor for FP&L at this point;

9       right?

10            A.   The additional information that the NRC was

11       requesting from Progress was enumerated, and we were

12       able to capture that information in our base

13       application.  So by doing so, we essentially avoided a

14       delay during the review process by submitting a more

15       complete application.

16            Q.   And you don't know yet whether or not the

17       geological issues that you share in common with Progress

18       Levy will cause further delays?

19            A.   We are certainly looking to the NRC to provide

20       their docketing schedule, but last week they did provide

21       a sufficiency letter indicating that our application was

22       sufficient to begin their review.

23            Q.   Have they given you that schedule yet?

24            A.   No, sir.

25            Q.   Have they given you any indication of what the

145

1       schedule will be?

2            A.   We understand that a schedule would be

3       provided to us in probably mid to late October, and we

4       have no more specific information as to what the actual

5       schedule would be.  We expect them to be consistent with

6       past schedules they've issued.

7            Q.   Now, you had an aggressive schedule before the

8       three-month slippage.  Is it even more aggressive now?

9            A.   No, sir.

10            Q.   You didn't change the end date, in other

11       words?

12            A.   No, sir.

13            Q.   Now, in terms of the cost impacts, you haven't

14       determined the impact of that three-month shift on the

15       overall project cost, have you?

16            A.   No.  That would be difficult to determine.

17       But as I stated, because we believe it saves us review

18       time when the NRC is actually looking at our

19       application, we think that that puts us in the best

20       position to get the most expeditious review from the

21       NRC.

22            Q.   Is it expeditious for the NRC to take what has

23       been from June until September to give you a sufficiency

24       letter?  I thought they reacted much faster than that.

25            A.   Our submittal was June 30th, so in fact, it's

146

1       been just a little over seven weeks, and that has been a

2       fairly common interval for a sufficiency letter.

3            Q.   And you're still not going to get a schedule

4       until October, though?

5            A.   That's correct.  And again, that's consistent

6       with the Progress project and others that have gone

7       before.

8            Q.   Now, you know, the Progress project applied

9       for a limited work authorization as part of their COL.

10       You're familiar with that; right?

11            A.   Yes, sir.

12            Q.   And that limited work authorization was

13       denied, at least in part because of the geological

14       issues that the Progress Levy site has; right?

15            A.   That's my understanding, yes, sir.

16            Q.   So FP&L has applied for a limited work

17       authorization as part of its COL; correct?

18            A.   That's correct.

19            Q.   And do you expect that the geological issues

20       are going to be of concern to NRC as part of that LWA?

21            A.   I think that's a part of the initial

22       discussions that the NRC is going to be looking at when

23       they develop their schedule.  We developed the LWA early

24       in the process because of the option it may provide to

25       start some construction components early.  If that

147

1       option turns out not to be realistic or not to be to the

2       overall schedule's benefit, then we would not pursue

3       that LWA.

4            Q.   Well, if you pursue it and it's denied, that

5       would cause further schedule slippage; correct?

6            A.   Not necessarily.  The LWA is simply a way in

7       which the application is organized for the NRC, asking

8       the NRC to review certain sections of the application

9       first.  It doesn't add new application material.  It

10       just would change the sequence in which they would

11       review them.  That's part of the discussion that we're

12       having with the NRC now as they develop their schedule.

13            Q.   The NRC's schedule with regard to the AP-1000

14       reactor is also slipping, is it not?

15            A.   I believe that they're in a design change

16       review and that that is experiencing some delays, yes,

17       sir.

18            Q.   And so the original design of the AP-1000

19       submitted to the Nuclear Regulatory Commission was

20       design 0; right?

21            A.   The actual first application was -- included

22       design changes through design change 15.

23            Q.   Okay.  Well, now they're on design change 17;

24       is that right?

25            A.   That's correct.

148

1            Q.   And that is nowhere in sight for approval at

2       this point because of the failure of Westinghouse/Shaw

3       to provide important information to the NRC about a

4       component of the reactor cooling system called the sump;

5       right?

6            A.   I understand that there are some challenges in

7       Westinghouse providing information.  And I'll point out

8       that that's, you know, exactly why FPL has positioned

9       our project at this stage in the industry, so that we

10       can see how these things proceed, so that we can make

11       decisions in terms of the pace that we pursue the

12       project, and that those decisions can maintain progress

13       towards licensing, but not provide a high risk of

14       exposure to our customers.

15                 MR. DAVIS:  Mr. Chair, I have a exhibit I

16       would like to --

17                 CHAIRMAN CARTER:  Okay.  Number 132.  Short

18       title?

19                 MR. DAVIS:  The short title is "NRC letter to

20       Westinghouse, August 27, 2009."

21                 (Exhibit Number 132 was marked for

22       identification.)

23                 CHAIRMAN CARTER:  You may proceed.

24                 MR. DAVIS:  Thank you, Mr. Chair.

25       BY MR. DAVIS:

149

1            Q.   Mr. Scroggs, you had mentioned you were aware

2       of the information contained in this August 27, 2009

3       letter from Mr. David Matthews, Director of the Division

4       of New Reactor Licensing with the Nuclear Regulatory

5       Commission, to Robert Sisk.  Are you familiar with the

6       delays that the Nuclear Regulatory Commission is stating

7       that will occur as a result of Westinghouse's failure to

8       provide adequate information with its revision 17

9       application?

10            A.   I'm familiar with the existence of this letter

11       through a media article.  I have not read the letter

12       itself.

13            Q.   Florida Power & Light is on the mailing list

14       for the Westinghouse correspondence with the Nuclear

15       Regulatory Commission; correct?

16            A.   Yes.  Our new nuclear project licensing team

17       is in charge of that, yes, sir.

18            Q.   So basically, you're aware then that the

19       Nuclear Regulatory Commission is stating that its prior

20       schedule for -- I believe you called them key milestones

21       for its review of Westinghouse's application -- no

22       longer applies?

23            A.   Are you asking me a question about this

24       specific letter?

25            Q.   Yes.  I mean, are you aware that the key

150

1       milestones that FP&L has relied upon for NRC's approval

2       of the Westinghouse AP-1000 reactor design, revision 17,

3       no longer applies?

4            A.   I don't know that that's the result of this

5       letter.  I know that they're talking about delays and

6       that, as with all project processes, delays generally

7       are revisions to schedule, not total dismissal of

8       schedule.

9            Q.   And you're also aware that the Nuclear

10       Regulatory Commission has changed its so-called

11       reference combined operating license application from

12       what had previously been the Tennessee Valley Authority

13       Bellefonte project to the Georgia -- I'm sorry, Southern

14       Vogtle project; right?

15            A.   Yes.

16            Q.   That's going to cause further delays; correct?

17            A.   It may or may or may not.  In fact, the

18       Tennessee Valley Authority project was sponsored by the

19       NuStart Group to get things moving.  The Southern Vogtle

20       plant seems to be positioned to be in a better position

21       to move to construction, so I would say that that is a

22       wise choice by the organization to move to the Southern

23       plant.

24                 Let me just say that this approach and the

25       concerns that are being identified by schedule delays

151

1       with the NRC is exactly the type of thing that FPL has

2       envisioned.  And in our approach, having a stepwise

3       approach where we can make decisions through continual

4       monitoring of the regulatory process and the commercial

5       process and control the amount of exposure, maintain

6       progress towards licensing, but not take on undue risk,

7       is exactly the type of issues that we've envisioned and

8       why we are monitoring and managing our project in that

9       way.

10            Q.   I'll come back to that stepwise process you

11       described in a few minutes, but when you first started

12       the project, applications for licenses, et cetera, back

13       in 2008, you envisioned signing an EP contract in March

14       of 2009; right?

15            A.   That's correct.  That was the original plan.

16            Q.   And now I believe you said that you will

17       decide whether or not to sign one by the end of 2009?

18            A.   That's correct.

19            Q.   So that's a nine-month slippage in your

20       schedule from the beginning at this point; right?

21            A.   That's correct.

22            Q.   So you've had both the application slippage

23       and the EP contract slippage.  Those are two major

24       slippages at this point, but you haven't changed your

25       ultimate schedule?

152

1            A.   No.  We have accepted that there's more risk

2       to whether or not we attain that schedule.  As my

3       testimony describes, there's three areas that we're

4       looking at.  We want to make sure that we understand

5       legislation and energy policy issues, we're going to

6       make sure that we pursue the best commercial deal for

7       our customers, and we're going to be watching the

8       regulatory process to determine what the schedules for

9       review of our permit applications will be before we, you

10       know, take on additional costs of entering into an EP or

11       an EPC contract, because it basically allows us to

12       understand with better information, more current

13       information, what the true schedule is and what our

14       appropriate investment to get to the next stage should

15       be.

16            Q.   Well, let's talk about the activities that

17       you're seeking the ratepayers to pay for for 2009 and

18       2010.  You've talked about those as being licensing and

19       permitting.  Are those two general categories?

20            A.   In 2009, it's largely licensing and

21       permitting.  In 2010, it's about 40 percent licensing

22       and permitting and 60 percent engineering and design

23       activities.

24            Q.   And there's going to be detailed site-specific

25       design, preliminary engineering, and procurement

153

1       activities necessary to meet the project schedule in

2       2010; is that right?

3            A.   That's correct.

4            Q.   Now, that could require this EP contract; is

5       that right?

6            A.   That's absolutely correct.

7            Q.   The contract with Westinghouse/Shaw.  And if

8       that contract is required, those expenses would rise

9       dramatically, would they not, from what you have

10       estimated going forward?

11            A.   Could you restate your question, sir?

12            Q.   Yes.  You have said that you could end up

13       signing an EP contract in 2009 or 2010.  You've

14       estimated your expenses for 2009 to be 45.6 million and

15       for 2010, 90.5 million.  Do those numbers --

16            A.   Those numbers are correct, yes, sir.

17            Q.   Do either of those two numbers include the

18       cost of signing an EP contract with Westinghouse/Shaw?

19            A.   Yes.  Specifically, the 2010 estimate includes

20       $58 million for engineering and design that is

21       envisioned to be part of the initial stages of an EP

22       contract.

23            Q.   Part, but what would the rest be if you sign

24       that contract?

25            A.   That is our estimate of expenditures on the

154

1       engineering and design during 2010.

2            Q.   So just so we're clear, the activities for

3       2009 and 2010 are not merely evaluation of the nuclear

4       option; is that right?

5            A.   That's correct.  This is not an exercise.  We

6       are making solid progress towards the development of an

7       operating license for construction and operation.  That

8       gives us the option to then exercise the construction

9       decision at the appropriate time.

10            Q.   You have talked several times about this

11       stepwise approach.  You're monitoring the factors that I

12       mentioned in my opening statement and that SACE has

13       provided in the prefiled testimony, correct, the

14       economic downturn for one thing?

15            A.   Yes, sir.

16            Q.   The national and international nuclear

17       activity?

18            A.   Yes, sir.

19            Q.   And the political and regulatory environment?

20            A.   Yes, sir.

21            Q.   So those are important for whether or not you

22       proceed with this project; is that right?

23            A.   Yes, they are.

24            Q.   Now, when you talk about a stepwise process

25       and FP&L decision-making process, does that include the

155

1       Public Service Commission in that process?

2            A.   Absolutely.  Every year as we come before the

3       Public Service Commission to review what we've done and

4       what our plans are, we're keeping them aware through

5       annual audits that their staff performs and what is

6       essentially a fairly continuous discovery process

7       through the year.

8            Q.   And you're trying to maintain an off-ramp

9       approach, I believe you stated in your prefiled

10       testimony?

11            A.   That's correct.

12            Q.   So you could slow down or take an off-ramp in

13       order to manage cost risk at any time?

14            A.   Cost and execution risk, yes, sir.

15            Q.   What would precipitate your off-ramp?

16            A.   We could see significant changes in energy

17       policy in the United States, the Florida Legislature.

18       We could see a regulatory shift in the NRC that would

19       increase the time of expected NRC licensing review.  So

20       again, all those factors are a part of our continuous

21       monitoring to make sure that the decisions we make to

22       take the next step -- and again, we don't just make an

23       annual budget and move forward with that annual budget.

24       We make an annual budget and then evaluate that every

25       month as to whether or not we want to make the large

156

1       expenditures or hold back on the large expenditures

2       relative to the current events and the current

3       expectations of project progress.

4            Q.   And you said that a more complete picture of

5       these three areas of uncertainty, the economic downturn,

6       the national and international nuclear activity, and the

7       political and regulatory environment, will be available

8       in the fourth quarter of this year; right?

9            A.   Yes.  Particularly the schedules for our state

10       site certification application and our Nuclear

11       Regulatory Commission combined operating license

12       application will be much more clear in the fourth

13       quarter.  At the same time, we'll be completing our

14       current round of negotiations with Westinghouse/Shaw

15       Stone & Webster as to the terms, schedule, and pricing

16       for an EP or an EPC contract.

17            Q.   That's a little late for this process that

18       we're undergoing here with the feasibility analysis;

19       right?

20            A.   Well, the feasibility analysis is an annual

21       review.  We actually conduct our analysis in the April

22       time frame consistent with our ten-year power plant site

23       plan, provide that to -- in our May testimony, and then

24       discuss that through the year.  It's a continual cycle.

25       We'll be picking up on that cycle at the beginning of

157

1       next year.

2            Q.   But you didn't reflect any of the uncertainty

3       of these three areas in your analysis that you provided

4       to the Commission in May.

5            A.   Our feasibility analysis is based on a

6       schedule that's achievable, and we placed in that budget

7       estimates of the amounts of money that we would need to

8       achieve the 2018-2020 schedule.

9            Q.   Did you reflect any of the uncertainty in that

10       schedule in your filing?

11            A.   The feasibility analysis is an economic

12       analysis comparing a break-even natural gas combined

13       cycle plant to the high end of the nuclear cost estimate

14       range.  That uncertainty of price and schedule is

15       somewhat captured in the cost estimate range that we've

16       talked about.  In a very conservative way, we're only

17       comparing to the high end of that range, so we believe

18       that we're capturing that within the process.

19            Q.   The schedule slippage has a cost; correct?

20            A.   The schedule may or may not create more cost

21       for the project if it's managed appropriately.  Again,

22       our earlier schedules had us buying long lead

23       procurement items in the fourth quarter of 2008.  We saw

24       that that wasn't necessary, so we were able to defer

25       those costs out into the future.  That doesn't mean that

158

1       they are going to be more expensive.  In fact, they

2       could be less expensive if purchased out into the

3       future.

4            Q.   You've heard of the term "first wave and

5       second wave" with regard to nuclear power construction?

6            A.   Yes.

7                 MR. DAVIS:  Let me show what we'll mark as the

8       next exhibit.

9                 CHAIRMAN CARTER:  It will be Number 133.

10       Short title?

11                 MR. DAVIS:  The title is "First Wave or Second

12       Wave, NERA," N-E-R-A, "Economic Consulting."

13                 CHAIRMAN CARTER:  I'm going to have to see

14       that.  How about we just go with "First Wave or Second

15       Wave"?

16                 MR. DAVIS:  Okay.

17                 CHAIRMAN CARTER:  Would that work for you?

18                 MR. DAVIS:  Yes, that works fine.

19                 CHAIRMAN CARTER:  Okay.  Good.

20                 MR. DAVIS:  Thank you, Mr. Chair.

21                 (Exhibit Number 133 was marked for

22       identification.)

23

24                 CHAIRMAN CARTER:  You may proceed.

25       BY MR. DAVIS:

159

1            Q.   Mr. Scroggs, you're familiar with this NERA

2       article about first wave or second wave?

3            A.   Yes, sir, I am.

4            Q.   And when I say this article, I mean Exhibit

5       132.

6                 CHAIRMAN CARTER:  133.

7                 MR. DAVIS:  I'm sorry.  133.  Thanks.

8       BY MR. DAVIS:

9            Q.   The tenor of the article is that it's better

10       to be in the second wave than the first wave at this

11       stage from an economic standpoint for a nuclear utility;

12       is that right?

13            A.   That's the basis, yes, sir.

14            Q.   And FP&L with Turkey Point 6 and 7 still falls

15       in the first wave, does it not?

16            A.   I don't -- I wouldn't subscribe to that, no,

17       sir.

18            Q.   Well, one of the dates that's used here for

19       the first wave is construction start in 2018.

20            A.   Where are you referring, sir?

21            Q.   Well, it says -- okay.  I'm sorry.

22       Construction start in 2014 is the first wave, and

23       construction start in 2020 is the second wave; right?

24            A.   I don't interpret the author's comments to say

25       exactly that.

160

1            Q.   I'm sorry.  I misspoke.  I meant to say 2012

2       for the first wave and 2020 for the second wave.

3            A.   I don't interpret it quite that way, but --

4            Q.   But be that as it may -- the article speaks

5       for itself.  You would agree, though, that you're among

6       the first nuclear utilities moving through the licensing

7       process in what appears to be a first wave?

8            A.   We're one of 18 applications, one of five

9       AP-1000 projects.  Again, our perspective on this -- and

10       you mentioned off-ramps -- is that we want to move the

11       project as far as we can with an acceptable risk

12       profile, and if necessary, take an off-ramp that slows

13       the process down, and we may very likely be a second

14       wave project.  It talks about construction starting in

15       2020.  Those are arbitrary dates.  I don't know that

16       anybody would know exactly what dates individual

17       projects will actually start construction.

18            Q.   And you're aiming to have Turkey Point 6

19       complete by 2018 and Turkey Point 7 complete by 2020;

20       correct?

21            A.   That's the current schedule, but it's not at

22       any cost or not at any risk.

23            Q.   If the Commission were to decide that it's

24       time for an off-ramp for Turkey Point 6 and 7, could

25       that benefit the FP&L ratepayers?

161

1            A.   I think postponing the benefits of delivering

2       new nuclear show -- we're showing over the first 40

3       years of operation $93 billion in fuel savings against

4       the mid range natural gas case.  We're talking about

5       7 million tons of CO2 a year removed.  And through our

6       need determination and our most recent annual

7       feasibility analysis, we're talking about the most

8       cost-effective form of generation.  So postponing those

9       benefits for our customers would be detrimental to them.

10       I don't know that it would necessarily be a benefit to

11       them to postpone it.

12            Q.   You talked about mid range natural gas

13       projections.  Isn't it true that your natural gas

14       projections are being daily shown to be way too high,

15       that now natural gas is less than $3 a million Btu?

16            A.   Well, witness Sim can answer in more detail

17       with respect to the natural gas cost estimates, but I

18       would propose that at any time point in time, there's a

19       snapshot that could be taken.

20                 Our cost estimate range, and in fact, our

21       annual feasibility analysis is constructed recognizing

22       that from time to time these commodities will go up and

23       down.  They'll fluctuate.  So we developed a nine-matrix

24       process that allows to us look at the range of potential

25       natural gas prices, the range of carbon dioxide

162

1       regulation costs.

2                 And only in the case that we have a

3       combination of the lowest CO2 regulation price and the

4       lowest natural gas scenario is an alternative generation

5       project even economically equitable to the new nuclear

6       project at the high end of the range, and that wouldn't

7       provide the fuel diversity, energy security, and

8       emission-free nature of nuclear.

9            Q.   We'll ask Mr. Scroggs about the details of the

10       analysis that -- I'm sorry.  We'll ask Mr. Sim about the

11       details.  But you understand that you predicted a

12       natural gas price as a low for 2009 of $6.29?

13            A.   That could be correct, yes, sir.

14            Q.   And it's now below $3?

15            A.   In a spot market, perhaps.

16            Q.   And we'll have further testimony on that

17       later.

18                 There are lessons to be learned from the

19       nuclear development boom time of the 1970s; right?

20            A.   Yes, sir.

21            Q.   As a matter of fact, you gave a talk about

22       that back in March of this year, did you not?

23            A.   Yes, I did.

24                 CHAIRMAN CARTER:  Do you need a number?

25                 MR. DAVIS:  Yes, Mr. Chair.

163

1                 CHAIRMAN CARTER:  That will be Number 134.

2       Short title?

3                 MR. DAVIS:  "A Developer's Perspective on New

4       Nuclear Plant Deployment."

5                 CHAIRMAN CARTER:  A Developer's Perspective on

6       New Nuclear Deployment.  Okay.  We'll just take the

7       title off the sheet, guys.

8                 (Exhibit Number 134 was marked for

9       identification.)

10                 CHAIRMAN CARTER:  You may proceed.

11                 MR. DAVIS:  Thank you, Mr. Chair.

12       BY MR. DAVIS:

13            Q.   Mr. Scroggs, again, I've excerpted the whole

14       presentation.  Exhibit 134 is a PowerPoint presentation

15       that you provided to the -- what was the conference, if

16       you recall?  I'm trying to remember the name of the

17       conference.

18            A.   It was a conference hosted by Energy

19       Solutions.

20            Q.   Energy Solutions, correct, on March 18, 2009.

21       And you reflected in this talk about nuclear industry

22       teaching lessons.  And on the third page of Exhibit 134,

23       you said that 116 units were under construction at the

24       time of Three Mile Island in 1979.  Sixty-six were

25       canceled, and only 50 were completed, with an average

164

1       delay of 6.3 years; correct?

2            A.   That's correct.

3            Q.   And on the next page, you show cost overruns

4       even before Three Mile Island of up to 249 percent.

5            A.   That's correct.

6            Q.   I assume that you did a study of the -- or had

7       someone on your staff do a study of these development

8       projects at the time or before you gave this talk?

9            A.   Yes.  These factors are very much in the mind

10       of nuclear power operators who experienced it, such as

11       FPL, and nuclear power operators who are considering new

12       projects.

13            Q.   And you state that cost overruns were the

14       result of multiple issues.  Do these sound a little

15       familiar, regulatory uncertainty, design changes, and

16       economic pressures?

17            A.   All correct.

18            Q.   Do you recall what your recommendations were

19       for dealing with these particular lessons from the

20       1970s?

21            A.   Well, I think the first recommendation is to

22       learn from our history.  And I think everybody would

23       recognize that these plants, particularly the St. Lucie

24       plant and the Turkey Point plant that were built during

25       this time, experienced the same challenges and that

165

1       through active management, we were able to overcome

2       those challenges.  And those plants today, even though

3       they took longer to build than expected and they cost

4       more than they expected, they have been turning out

5       solid benefits for our customers every day since then.

6            Q.   The other recommendation was to develop a

7       better relationship with the regulatory agencies; right?

8            A.   I think clear communication, especially

9       through a process such as this where we're annually and

10       transparently discussing the project and looking at the

11       factors of the project, are very important, yes, sir.

12                 MR. DAVIS:  That's all I have.

13                 CHAIRMAN CARTER:  Mr. Moyle.

14                 MR. MOYLE:  Thank you, Mr. Chairman.

15                           CROSS-EXAMINATION

16       BY MR. MOYLE:

17            Q.   I have a few questions, some follow-up and

18       then a couple of other lines I want to explore with you,

19       Mr. Scroggs.

20                 The number for Turkey Point 6 and 7 is moving

21       around a little bit.  As we sit here today, what is your

22       best estimate for the cost of Turkey Point 6 and 7?

23            A.   We would say it would be in the upper range of

24       our cost estimate range, somewhere between 16 to

25       18 billion in total project costs.

166

1            Q.   And you would agree that in order to determine

2       feasibility, that cost is an important component;

3       correct?

4            A.   Yes, sir.

5            Q.   Okay.  And a swing of 15 to 18 or 12 to 18 or

6       even 16 to 18 billion can make a significant difference

7       in feasibility, can it not?

8            A.   Well, our annual feasibility analysis shows

9       that we could have the highest cost estimate in the

10       range and still be economically more advantageous than

11       eight of nine scenarios and economically equivalent to

12       the ninth scenario, with the added qualitative benefits

13       of emission-free generation, energy security, and fuel

14       supply diversity.

15            Q.   And that's the exhibit that Mr. Sim has

16       attached to his testimony; is that right?

17            A.   That's correct, sir.

18            Q.   Okay.  We'll talk about that in a minute.

19                 I want to ask a little bit about FPL's view

20       with respect to competitive bidding.  Could you just

21       indicate, does the company support competitive bidding

22       as a general rule?

23            A.   Yes.  Our procurement procedures identify

24       competitive bidding as the preferred method.

25            Q.   And you can still do a sole source contract;

167

1       correct?

2            A.   As necessary and appropriate, yes, sir.

3            Q.   And there are limitations on when you can do a

4       sole source contract according to your policy; correct?

5            A.   Yes.  The policy provides us a very specific

6       set of circumstances and requires that the

7       decision-making team enumerate the business reasons for

8       not entering into a competitive bidding process.

9            Q.   One reason would be that there's nobody else

10       that could do the work; correct?

11            A.   In a sole source procurement, that would be

12       the case.

13            Q.   And this Commission has previously expressed

14       concerns about FP&L sole-sourcing work; isn't that

15       correct?

16            A.   There have been discussions about it, yes,

17       sir.

18            Q.   I want to talk a little bit about the EPC and

19       the EP process, and I would like to ask you a little

20       bit.  You had hired Cocentric Energy Advisors to perform

21       a report for you, did you not, Mr. Reed?

22            A.   Mr. Reed has been engaged to do a number of

23       things, an audit being one of them, which may be what

24       you're speaking of.

25            Q.   Do you have a copy of his testimony before

168

1       you?

2            A.   No, sir, I do not.

3                 MR. MOYLE:  Could I ask FPL if they would be

4       so kind as to provide this witness with a copy of

5       Mr. Reed's testimony?  And for the record, I'm going to

6       refer you to his exhibit, page 22.

7                 MS. CANO:  May I ask Mr. Moyle which date of

8       John Reed's testimony you're referring to?

9                 MR. MOYLE:  May 1, 2009.

10                 MS. CANO:  Thank you.

11            A.   You said page 22?

12            Q.   Yes, sir.  And it's a paragraph that I want to

13       spend some time focusing on.  It's a little lengthy, or

14       I would have just read it into the record.

15            A.   I'm sorry.  I don't have a page 22 of his

16       testimony.

17            Q.   It's his exhibit.  It's his exhibit.

18            A.   Of JJR-1?

19            Q.   Yes, sir.  And at the top it says page 26 of

20       36, and at the bottom it says page 22.  If you would

21       just tell me when you're there.

22            A.   Okay.  I'm there.

23            Q.   All right.  It indicates that Turkey Point 6

24       and 7 used a single source procurement strategy when it

25       chose BVZ to provide certain engineering services on

169

1       behalf of the company; correct?

2            A.   Yes.

3            Q.   And the reason that this was done was to

4       familiarize BVZ with the AP design, AP-1000 design; is

5       that right?

6            A.   Well, in part.  I think it's moreover to

7       familiarize Black & Veatch/Zachry with the Turkey Point

8       6 and 7 project, allowing us to work together on this

9       project so that we have in the future a potential for

10       credible vendors to provide competitive bids on other

11       scopes of contract.

12            Q.   Okay.  And this report says, "This procurement

13       strategy was selected in order to enhance the number of

14       potential construction vendors who are familiar with the

15       AP-1000 design."  Is that a correct statement?

16            A.   Correct statement.

17            Q.   And it also indicates that there are three

18       capable construction firms, Shaw, Bechtel, and BVZ;

19       correct?

20            A.   That's what it says, yes, sir.

21            Q.   And then you all have selected BVZ to provide

22       you with engineering drawings, correct, preliminary

23       engineering work?

24            A.   Yes.  The scope of work that Black &

25       Veatch/Zachry has been engaged for is to do some

170

1       preliminary construction planning.  This is a very

2       specific scope of work that helps us understand what's

3       the proper sequence and logistics of the construction

4       activities that lead up to the main power plant

5       construction.  That's a scope of work that Black &

6       Veatch is very qualified to undertake, and in doing so,

7       they become more familiar with our project and can then

8       be a more credible bidder in the future.

9            Q.   Isn't it true that the company that you

10       selected is not familiar and aligned with Westinghouse,

11       the company that is putting forward the AP-1000, that

12       instead, they align themselves with the GE reactor

13       technology?

14            A.   I know that -- I guess I would say that's an

15       incomplete characterization.  Black & Veatch/Zachry has

16       been involved in nuclear plant construction for the GE

17       ABWR, as well as conventional power plant construction

18       for FPL in numerous events.  What we're looking at is a

19       scope of work that's similar to site preparation

20       activities that would be not unique to a nuclear plant.

21       And in doing so, FPL has experience working with Black &

22       Veatch/Zachry, and they're qualified to do so.

23            Q.   But this paragraph, a portion of this sentence

24       says, "Two of the three firms, Bechtel and Shaw, have

25       prior experience with the AP-1000 and the Turkey Point 6

171

1       and 7 project.  BVZ, however, is currently aligned" --

2       and it talks about URS - Washington Group and the GE

3       reactor design.  "By single sourcing the procurement of

4       engineering services from BVZ, this vendor will gain

5       experience with the AP-1000 reactor."

6                 I guess the thinking is it will create an

7       increased competitive environment for construction

8       services; is that right?

9            A.   That's correct.  And I think the GE reactor

10       processes have slowed down, so I think Black & Veatch

11       would be more freed up participate in AP-1000 projects

12       in the future.

13            Q.   Was there a -- you have two companies that can

14       compete currently for the construction, Shaw and

15       Bechtel, according to this report; correct?

16            A.   That's correct.

17            Q.   And both of them are familiar with the AP-1000

18       design?

19            A.   That's correct.

20            Q.   Doesn't it seem a little curious as to why a

21       company not that familiar with the AP-1000 design would

22       be retained to provide engineering services related to a

23       power block unit that's going to be the AP-1000?

24            A.   No.  In fact, if you look at it from our

25       perspective, what we're doing is creating the option of

172

1       construction vendors who can competitively bid for

2       certain specific scopes in the future.  It's a large

3       project.  This project will have a lot of pieces to it.

4       Not all the pieces are specifically the nuclear reactor

5       and the turbine.  There are a number of associated

6       facilities, water treatment plants, buildings, and other

7       activities around the central plant that could be bid

8       out to an independent bidder with proper qualifications.

9                 The good news is that Black & Veatch/Zachry is

10       very qualified to do the work that they're doing.  Their

11       rates have been shown to be very competitive.  And in

12       doing so, we're able to not only deliver value, dollar

13       value for dollars spent today, but we're also creating

14       optionality into the future that may benefit our

15       customers.

16                 (Transcript continues in sequence in

17       Volume 2.)

18

19

20

21

22

23

24

25

173

1                        CERTIFICATE OF REPORTER

2

3       STATE OF FLORIDA:

4       COUNTY OF LEON:

5                  I, MARY ALLEN NEEL, Registered Professional

6       Reporter, do hereby certify that the foregoing

7       proceedings were taken before me at the time and place

8       therein designated; that my shorthand notes were

9       thereafter translated under my supervision; and the

10       foregoing pages numbered 1 through 172 are a true and

11       correct record of the aforesaid proceedings.

12                 I FURTHER CERTIFY that I am not a relative,

13       employee, attorney or counsel of any of the parties, nor

14       relative or employee of such attorney or counsel, or

15       financially interested in the foregoing action.

16                 DATED THIS 8th day of September, 2009.

17

18

____________________________

19                                 MARY ALLEN NEEL, RPR, FPR

2894-A Remington Green Lane

20                                 Tallahassee, Florida  32308

(850) 878-2221

21

22

23

24

25