1247

1                             BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

DOCKET NO. 090009-EI

3       In the Matter of:

4       NUCLEAR COST RECOVERY CLAUSE.

______________________________/

5

6

7                               VOLUME 7

8                       Pages 1247 through 1320

9              ELECTRONIC VERSIONS OF THIS TRANSCRIPT ARE

A CONVENIENCE COPY ONLY AND ARE NOT

10               THE OFFICIAL TRANSCRIPT OF THE HEARING,

THE .PDF VERSION INCLUDES PREFILED TESTIMONY.

11

PROCEEDINGS:        HEARING

12

13       COMMISSIONERS

PARTICIPATING: CHAIRMAN MATTHEW M. CARTER, II

14                      COMMISSIONER LISA POLAK EDGAR

COMMISSIONER KATRINA J. McMURRIAN

15                      COMMISSIONER NANCY ARGENZIANO

COMMISSIONER NATHAN A. SKOP

16

17       DATE:          Wednesday, September 9, 2009

18

TIME:          Commenced at 2:20 p.m.

19                      Concluded at 4:10 p.m.

20

21       PLACE:         Betty Easley Conference Center

Room 148

22                      4075 Esplanade Way

Tallahassee, Florida

23

24       REPORTED BY:   RAY D. CONVERY

Court Reporter

25                      (850) 224-0722

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1248

1                              I N D E X

2                               WITNESS

3       NAME:                                   PAGE NO.

4       GARY MILLER

5          Continued Cross Examination            1254

by Mr. Rehwinkel

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1249

1                              EXHIBITS

2       NUMBER:                              ID.     ADMTD.

3        143  2Q 2007 JVT Doc               1253

144  JVT-11, 2007                  1253

4             Monthly Report Excerpts

145  L&P Status Slides,            1253

5             November 26, 2007

146  Progress NPD Monthly Report   1254

6             Excerpts, Various

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1250

1                         P R O C E E D I N G S

2                 (Transcript follows in sequence from

3       Volume 6.)

4                 ACTING CHAIRMAN EDGAR:  Okay.  We are back

5       from lunch and I think we are about ready to get

6       started.  Mr. Rehwinkel, I will look to you first.

7                 MR. YOUNG:  Madam Chairman.

8                 CHAIRMAN CARTER:  Yes, sir.

9                 MR. YOUNG:  Before we get started, I think

10       Progress has a document.  I don't know if you want to

11       pass that out right now or if you would rather wait.

12                 ACTING CHAIRMAN EDGAR:  Yes.

13                 MS. TRIPLETT:  Madam Chair, the document we

14       circulated to parties and staff with respect to the MUR

15       costs, that came up during the cross of Mr. Franke.  So

16       I think it might be more appropriate to wait until he

17       comes back for rebuttal, because I think Mr. Rehwinkel

18       wants to ask questions about --

19                 ACTING CHAIRMAN EDGAR:  Thank you for bringing

20       that to our attention here at the bench.  And so my

21       understanding is that it's been distributed to staff and

22       to all the parties to have the chance to look at, and

23       then, yes, please do remind me or Chairman Carter,

24       whichever is appropriate at the time, when we come to

25       that.  Thank you.

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1251

1                 MS. TRIPLETT:  Sure.  And we did not provide

2       copies to the Court Reporter or Commissioners at this

3       time because I wanted to give everyone an opportunity to

4       take a look at it.

5                 ACTING CHAIRMAN EDGAR:  That is in keeping

6       with our discussion.  Thank you.

7                 MS. TRIPLETT:  Thank you.

8                 ACTING CHAIRMAN EDGAR:  And, Mr. Rehwinkel, I

9       think right before we went to lunch, you were going to

10       distribute some documents, and I see some here before me

11       and us.  If you would, walk us through what they are and

12       we'll go from there.

13                 MR. REHWINKEL:  Thank you, Madam Chairman.

14                 Before I do that, if I could, I would like to

15       represent to you that Progress has also provided an

16       answer to the question I asked of Mr. Miller about EPC

17       contract and some dollar figures.  They have given me

18       information that I would just like to ask him a couple

19       of clarifying questions about, and I think I could do it

20       in a way that he can speak publicly on such that we will

21       not need to put the confidential information into the

22       record.

23                 ACTING CHAIRMAN EDGAR:  Okay.  Would you like

24       to begin there or do you want to --

25                 MR. REHWINKEL:  I'll do that after we do the

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1252

1       documents here, if that's okay.

2                 ACTING CHAIRMAN EDGAR:  Yes.

3                 MR. REHWINKEL:  I have placed four documents

4       before the Commissioners, the Court Reporter, the

5       Witness, SACE, PCS and FIPUG, as well as staff, that

6       contain information that is subject to a confidential

7       claim by the company, and I would like to identify these

8       for cross-examination purposes at this time.

9                 Whether I seek to move these into evidence is

10       something I would like to address at the end of

11       cross-examination and potentially after discussion with

12       the company about how we can deal with this in the most

13       efficient way that minimizes the amount of confidential

14       information that has to be dealt with, and it may

15       require further redaction of the documents depending on

16       how the answers are given.

17                 ACTING CHAIRMAN EDGAR:  Okay.  That seems

18       reasonable to me, and I'm seeing nods from the other

19       parties, so you may proceed.

20                 MR. REHWINKEL:  Okay.  The first document is a

21       three-page document that is entitled 2Q 2007 JVT

22       Document, and I would just request a number for -- an

23       exhibit number for cross-examination purposes.

24                 ACTING CHAIRMAN EDGAR:  So you would like to

25       go ahead and mark.  I am at 143, and the title, does

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1253

1       this work, 2Q 2007 JVT Doc?

2                 MR. REHWINKEL:  Yes.  And if it's appropriate,

3       I can just do all four of these at one time, if that

4       would be okay.

5                 ACTING CHAIRMAN EDGAR:  So go ahead and mark

6       sequentially?

7                 MR. REHWINKEL:  Yes.

8                 ACTING CHAIRMAN EDGAR:  Okay.  So this will be

9       143.  Let me just catch up here on my paperwork.

10                 (Exhibit No. 143 marked for identification.)

11                 MR. REHWINKEL:  And the second document is a

12       six-page exhibit entitled JVT-11, 2007 Monthly Report

13       Excerpts.

14                 ACTING CHAIRMAN EDGAR:  Okay.  So we will mark

15       that as 144.

16                 (Exhibit No. 144 marked for identification.)

17                 MR. REHWINKEL:  And the next document is a

18       three-page document entitled L&P Status Slides,

19       November 26, 2007.

20                 ACTING CHAIRMAN EDGAR:  Okay.  We will so mark

21       L&P Status Slides, November 26, '07, as 145.

22                 (Exhibit No. 145 marked for identification.)

23                 MR. REHWINKEL:  And then finally the 35-page

24       exhibit entitled Progress NPD Monthly Report Excerpts,

25       Various.

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1254

1                 ACTING CHAIRMAN EDGAR:  Okay.  A document

2       marked as 146, Progress NPD Monthly Report Excerpts,

3       Various.  I think we're all there.

4                 (Exhibit No. 146 marked for identification.)

5                 MR. REHWINKEL:  Thank you.  And before I ask

6       questions about these exhibits, I would like to follow

7       up, if it's okay, with Mr. Miller, about the information

8       the company provided on the break.

9                 ACTING CHAIRMAN EDGAR:  Okay.  Mr. Miller, you

10       have that with you?

11                 THE WITNESS:  I'm aware of what the number is.

12                     CONTINUED CROSS EXAMINATION

13       BY MR. REHWINKEL:

14            Q    Mr. Miller, I would like to ask you if you

15       could answer my question with respect to a percentage of

16       the number that you referred to on TGF-2 Form P-8 at

17       line 15, column H.  Do you recall that number?

18            A    Yes, I do.

19            Q    And you were describing changes to that number

20       that were based on some work authorization, is that

21       correct?

22            A    The correct term would be "change orders."

23            Q    Change order.

24                 Okay.  Now, those -- the number that you

25       showed -- that I was showed on the break does not

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1255

1       represent a change to the EPC as a basis -- as a result

2       of renegotiation, conclusion of renegotiation, is that

3       correct?

4            A    Let me clarify your wording.  That number is a

5       summation of change orders.  The EPC still stands.  We

6       are negotiating a change order related to the schedule

7       change.  It is not the change order related to the

8       schedule change.

9            Q    Okay.  So these are change orders that have

10       been negotiated in 2009 after notifying the Consortium

11       of the delay in the schedule; is that correct?

12            A    They're not necessarily related all to the

13       delay.  Some are, some are not, but they are the

14       compilation of all change orders issued in 2009.

15            Q    Okay.  So do you know a percentage to the EPC

16       number that you identified on the schedule that you

17       could tell me?

18            A    I do.  That number is approximately

19       0.15 percent.

20            Q    Okay.  And -- okay.  That's all I have on that

21       area.  Thank you.

22                 Okay.  Mr. Miller, we had discussed earlier

23       about the selection of the site that you ultimately

24       purchased and are utilizing for purposes of your COLA

25       for the LNP.  Do you recall that conversation?

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1256

1            A    I do recall that.

2            Q    Now, at the time you selected this site, you

3       decided that you needed to employ a firm to do site

4       characterization and other geotechnical-related work for

5       purposes of choosing a site and submitting a COLA; is

6       that correct?

7            A    It's more complicated than what you described.

8       We had contracts to help us in the site selection

9       process, and then, once the site was selected, we then

10       selected through a bidding process a COLA preparer.

11            Q    Okay.  And can you state publicly who your

12       COLA preparer was for purposes of geotechnical support

13       and site characterization?

14            A    Yes.  First of all, the COLA preparer is a

15       consortium.  We refer to them as the JVT, and that is

16       Sargent Lundy, WorleyParsons and CH2M-HILL.  In the case

17       of your specific question, the geotechnical is handled

18       by CH2M-HILL.

19            Q    And when did you engage CH2M-HILL through the

20       JVT?

21            A    That bidding process took place in late 2005,

22       and I believe from memory the contract was executed in

23       January of 2006 to the JVT.

24            Q    Now, did -- that contract for that work, did

25       it encompass work in Florida and in North Carolina?

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1257

1            A    Correct, it did.

2            Q    Okay.  So you had one bid response that you

3       accepted that governed COLA preparation for both the

4       Harris Plant in North Carolina and the Levy County

5       Nuclear Plant in Florida?

6            A    Yes.  We competitively bid this as a package

7       for the preparation of two COL applications for the

8       Harris site near Raleigh and for the Levy site, and,

9       excuse me, for a second site like a Harris site, which

10       ultimately became the Levy site.

11            Q    Now, did CH2M-HILL do some work to assist you

12       in making a final determination about the selection of

13       the site that the LNP project is proposed for?

14            A    Yes, they did.

15            Q    And after you have selected the site, did they

16       fairly quickly begin work on the COLA?

17            A    Yes, they did.  That work began in late 2006

18       as similar to what I said earlier, which the

19       announcement of the site was December of 2006.

20            Q    Okay.  So they did -- is it true that, shortly

21       after they began work on the -- isn't it true that

22       shortly after they began work on the COLA support work

23       related to the geotechnical aspect of the COLA, that

24       problems surfaced with their quality assurance of their

25       work?

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1258

1            A    Yes, and let me explain.  The work on the

2       Harris COLA had started back in January of 2006, and so

3       the evolution to go out and do the geotechnical borings

4       and sample collection was well under way.  In the early

5       part of 2007, we identified some problems with the

6       implementation of their quality assurance program, and

7       that's what you're referring to.

8            Q    Now, you say "we identified."  You're talking

9       about Progress Energy Florida?

10            A    That is correct.  When I say "we," I'm

11       referring to my staff, Nuclear Plant Development.

12       Because they are an Appendix B under 10 CFR Part 50

13       supplier of quality-related services, it is our

14       obligation to audit and monitor the quality of their

15       work, and as we were doing an audit on them in the early

16       part of 2007, we identified problems, and it was on the

17       information and work they had done for Harris.

18            Q    Okay.  Now, isn't it true that the quality of

19       the work that they did -- well, let me strike that and

20       ask it this way:  Isn't it true that any deficiencies in

21       the quality assurance aspect of the work that they did

22       on Harris would affect their ability to submit data

23       collected for the LNP site as well?

24            A    It is -- yes, the potential is there.  And so,

25       as the issues were identified on the Harris COLA, we

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1259

1       then looked for extent of condition across to the other

2       COL which was less far along in terms of its execution,

3       and then applied the same compensatory actions that we

4       did with Harris onto Levy such that we would not impact

5       the scheduled submittal, which was July of 2008.

6            Q    Well, let me ask you this:  When you say

7       "compensatory actions," what do you mean by that?

8            A    Once the analysis of the deficiencies were

9       analyzed, there were corrective actions identified.

10       Some of those corrective actions took months or weeks to

11       implement.  And so, until those were fully in place, we

12       required the contractor to implement additional

13       measures, compensatory measures, if you will, which

14       involved additional reviews and oversight until those

15       final corrective actions were in place, and then -- so

16       we maintained that for quite a while, those comp

17       actions.

18            Q    Now, at the time, in the first quarter of

19       2007, is that when the deficiencies in quality assurance

20       related to CH2M-HILL came to your attention?

21            A    That is when we identified the significant

22       issues.  I believe it was in the March, '07 timeframe.

23            Q    Now, you said earlier in an answer that you

24       identified compensatory measures to be taken in order to

25       meet the July, 2008 COLA deadline; is that correct?

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1260

1            A    I did say that.

2            Q    Okay.  Now, was July 28th, 2008 the targeted

3       COLA application date at that time?

4            A    Yes, it was.

5            Q    Okay.  Was that the understanding of the JVT

6       and CH2M-HILL at that time?

7            A    Yes, it was.

8            Q    Okay.  Did CH2M-HILL do their own internal

9       analysis to look at their quality assurance compliance?

10            A    Yes, CH2M-HILL did do their own independent

11       self-assessments, and they also identified some

12       deficiencies that required corrective action.

13            Q    Was that done before or after you initiated

14       your audit process?

15            A    From memory, I believe it was before.

16            Q    Okay.  Did they do that and advise you of the

17       problems, or did you discover them independently?

18            A    No, they provided their report to us.

19            Q    Okay.  All right.  Now, in March of 2007,

20       isn't true that the company issued a stop work order to

21       CH2M-HILL related to their work at the LNP site?

22            A    That is correct.

23            Q    And this also governed their work at the

24       Harris site?

25            A    That is correct.

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1261

1            Q    And isn't it true that that stop work order

2       lasted for approximately two months?

3            A    In the case of -- it's -- I cannot answer your

4       question yes or no because all work was not ceased for

5       the full two months.  Some work that could be

6       compartmentalized and analyzed specifically was

7       authorized to restart in advance of the two months, but

8       the majority of the deliverables from them were stopped

9       work for two months.

10            Q    Okay.  And did that cause a setback in the

11       schedule?

12            A    I wouldn't characterize it as a setback, but I

13       would characterize it certainly challenged the ability

14       to achieve the July, 2008 submittal.

15            Q    Now, was the stop work order situation

16       communicated to the NRC?

17            A    Yes.  The NRC had scheduled a quality

18       assurance audit of our whole organization, not just

19       CH2M-HILL, but also Sargent Lundy, WorleyParsons and

20       Progress Energy, and at that audit we shared with them

21       all the issues that had been identified with CH2M-HILL,

22       including the stop work order and the condition reports

23       and investigations that had been done following that

24       stop work.

25            Q    When was the NRC's quality assurance audit?

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1262

1            A    Hold on one second.  I can look it up based on

2       the -- one of the exhibits in my rebuttal testimony.

3                 The report was received February 15th -- no,

4       that's not right.  Yes, the report was received

5       February 15th of 2008, but the audit took place well in

6       advance of that in the 2007 timeframe.  It appears -- I

7       cannot recall the date and I'm trying to look for it

8       here.  It was in the spring of 2007 timeframe, but I

9       don't see the specific date of when that occurred.

10            Q    Was the NRC audit --

11            A    Oh, here it is, I found it.  I stand

12       corrected.  The quality assurance conducted by the NRC

13       during the period between October 29th, 2007 and

14       November 2nd, 2007, it was following our stop work

15       order.

16            Q    Okay.  Was it triggered by the audit that you

17       did that resulted in the stop work order?

18            A    No, it was not.  The NRC was visiting several

19       of the AP1000 applicants and they had already been to

20       other sites before they came to us.

21            Q    So it was going to happen no matter what?

22            A    We believe that's correct, and that was

23       considered to be a preapplication audit.

24            Q    Okay.  So it's your testimony here today that

25       you shared the findings of the audit you did of

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1263

1       CH2M-HILL in the spring of 2007 with the NRC, is that

2       correct?

3            A    That's correct.

4            Q    And you shared the internal assessment that

5       CH2M-HILL did with the NRC?

6            A    I believe that was made available to them

7       also.

8            Q    Okay.  And you shared the stop work order, the

9       fact of the stop work order with them as well?

10            A    Yes, we did.

11            Q    Okay.  And, now, you also did -- did you do a

12       followup audit in 2007 of CH2M-HILL?

13            A    We -- after we did the stop work order and

14       then after we reauthorized the work, we reduced the

15       frequency of their audits, and so we had a series of

16       audits that took place on a short timeframe after that.

17       I don't recall the specific dates of it, but most likely

18       there was one in late November.  There was certainly one

19       in 2008 also.  It was a reduced frequency audit of that

20       quality provider.

21            Q    You're saying "reduced frequency."  Do you

22       mean you reduced the interval between audits?

23            A    That's correct.

24            Q    Okay.  So you actually increased the --

25            A    Oh, yes.  It's the reduced period between the

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1264

1       audits.

2            Q    Okay.  I thought that's what you meant.  I

3       understand.

4            A    It's an increased frequency of surveillance.

5            Q    Now, the problems that CH2M-HILL encountered

6       in their quality assurance work or their quality

7       assurance status were a result of a lack of nuclear

8       experience with some of the personnel in their nuclear

9       business group; is that correct?

10            A    That is correct, and the key word you said was

11       "some of the personnel."  The leadership involved in

12       executing our project had previous experience on the

13       early site permit for the Clinton Station which was also

14       a nuclear application.

15            Q    Now, that early site permit for the Clinton

16       Station did not involve an LWA?

17            A    It did not.

18            Q    And it did not involve a site in karst

19       topography or limestone topography?

20            A    I am not familiar with the geology at Clinton.

21            Q    The problems encountered by CH2M-HILL in 2007

22       caused problems with them meeting the schedule that you

23       hoped that they would meet with respect to preparing the

24       geotechnical data, isn't that correct?

25            A    Repeat the question again.

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1265

1            Q    The problems that CH2M-HILL encountered in

2       2007 with respect to the audits and the reviews impacted

3       their ability to meet the schedule that you had -- you

4       wanted them to meet during 2007, isn't that correct?

5            A    It is correct that it did impact it; however,

6       as you know, we did achieve the July, 2008 submittal as

7       planned.

8            Q    Do you have Exhibit 143 in front of you?

9            A    Yes.

10            Q    Okay.  Are you familiar with this document?

11            A    Yes, I am.

12            Q    Is this a quarterly report from the Joint

13       Venture Team to you?

14            A    Yes.  And what I've characterized is this is

15       the document that we would actually review in person

16       every quarter as part of our ongoing oversight of the

17       COLA preparation.

18            Q    Okay.  I would like to ask you to turn to the

19       second page of the exhibit which is Bates-stamped

20       47-009242.  Do you see that?

21            A    I do see that page.

22            Q    Okay.  Now, the very first line up there says,

23       "LNP COLA Report, Session 2Q 2007 Meeting," and that's

24       the meeting you're referring to?

25            A    That's correct.

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1266

1            Q    Okay.  Now, this entire page is marked in

2       yellow, which indicates that there's a claim of

3       confidentiality for this.  So any question I ask you, I

4       would like you to pause and contemplate whether you can

5       answer it out loud or whether you need to refer to

6       information in a nonverbal way.

7            A    Okay.

8            Q    There are five bullet points on this page.

9       The bottom three bullet points that start with the word

10       "submittal," do those relate to the collection of

11       geotechnical information related to your COLA

12       application?

13            A    Stand by.

14                 Yes.

15            Q    Do they relate to the LWA aspect of the COLA

16       application?

17            A    It's not clear whether they would or would not

18       because some of these items relate to the overall review

19       of the geotechnical characteristics of the site.  It may

20       or may not have any impact on LWA.

21            Q    Isn't it true that Progress told the NRC on

22       November 20th, in response to the RAIs -- November 20th,

23       2008, in response to the RAIs that they gave you on

24       October 6th, that, for purposes of evaluating the LWA

25       and the COLA, the geotechnical information applied to

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1267

1       both equally?  You were not limiting the geotechnical

2       data that supported the LWA specifically, is that

3       correct?

4            A    Yes, but I'd characterize it differently.  The

5       information that we provided as part of the application

6       that describes the geotechnical features and

7       geosubstrate, that information was available for either

8       purpose as the NRC needed it.

9            Q    So this information -- this information --

10       well, let me ask you this:  Can you read the information

11       out loud in the bullet points?

12            A    These are associated with what's referred to

13       as an impact evaluation, which is like a change order,

14       so I'd prefer not to.

15            Q    Okay.  The second -- or the second of those

16       three bullet points that starts with the word

17       "submittal" --

18            A    Yes.

19            Q    -- isn't it fair to say that these

20       addressed -- well, can you -- do you see the word "NRC"

21       there?

22            A    I do.

23            Q    All right.  Can you describe whether there was

24       work done to -- related to those three words?

25            A    Yes, and let me see if I can characterize

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1268

1       this.  As part of the preapplication interactions of the

2       NRC with Progress Energy as a COL applicant, they come

3       to our site and they review documents that we're

4       preparation that we're going to be submitting as part of

5       our application.  So they actually visited the Levy

6       site.  And as part of that visit, they were sharing with

7       us things that they considered that needed to be

8       addressed in the application.  And so this language here

9       is referring to one of the subjects, and I'm doing this

10       from memory, but I believe this is what this was.  And

11       so our discussion of this was to do the analysis that

12       they had indicated to us on that preapplication

13       interaction such that we would include that in the COL

14       itself.

15            Q    Okay.  Now, the word after NRC there --

16            A    Yes.

17            Q    -- does that reflect that there was that

18       sentiment on the NRC staff?

19            A    I'm not sure that's the right word to

20       characterize it.  This report was written by our

21       external contractors.  They certainly brought it up and

22       they wanted to see it addressed as part of our

23       application.

24            Q    Okay.  Now, is the subject matter that follows

25       those three words that I asked you about, is that a

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1269

1       subject matter that showed up in 2008 in RAIs that the

2       NRC submitted to you?

3            A    We've had hundreds of RAIs and on very many

4       subjects related to geotechnical.  I would suspect this

5       question, we probably had RAIs on the subject of this

6       same subject.  I don't remember specific details because

7       of the number of RAIs we process.

8            Q    Okay.  But there are RAIs that are attached to

9       Mr. -- or Dr. Jacobs' testimony in the October 6 letter

10       that we could look at at a later point?

11            A    We could, and in that page that you're on, if

12       you go to the fourth bullet and you see the last word on

13       that line?

14            Q    Yes.

15            A    All right.  So that is something that I know

16       that word has been addressed in some RAIs because it has

17       to be addressed as part of, long-term, will that

18       geotechnical substrate change?

19            Q    Okay.  But it's true that you submitted

20       information as part of your COLA and as part of your LWA

21       supplement that you thought addressed these issues and

22       still got additional questions from the NRC staff about

23       them?

24            A    I don't know specifically if we received

25       questions regarding specifically these items.  I would

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1270

1       have to go do a comparison to see that, but that would

2       not be unusual to get RAIs.

3            Q    The individual whose name shows in the last

4       bullet point there, is that something you can state

5       publicly?

6            A    Yes.  CH2M-HILL.

7            Q    I apologize.  Before the parenthetical.

8       There's three that start with "submittal."

9            A    Yes.

10            Q    And there's -- there are two words there, a

11       name of a firm and a man's name.

12            A    Oh, I see.  You're talking about on the last

13       bullet?

14            Q    Yes.  I apologize.

15            A    I believe I can say that.

16            Q    Okay.  Was this individual working with the

17       JVT in the second quarter of 2007?

18            A    Yes.

19            Q    Was he working on geotechnical data

20       collection?

21            A    Yes, he was.

22            Q    Even at that time?

23            A    He was reviewing early boring information as

24       part of his scope of work at that time.

25            Q    Okay.  Now, was his scope of work more related

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1271

1       to supporting the Consortium, the Consortium rather than

2       the JVT and the COLA application work?

3            A    It actually evolved over time.  Their

4       expertise involves also foundation design.  So later on

5       they played a larger role in the foundation design which

6       was submitted in our application.

7            Q    Okay.  Can you turn to the last page of

8       Exhibit 143, please.  I see you've got a black dot and

9       then four subcategories with hollow dots, if you will.

10            A    Yes, I see those.

11            Q    Okay.  The third one there that starts with

12       the two words, "the preliminary," do you see that?

13            A    I see that.

14            Q    Okay.  Is this your recollection of findings

15       that were made as part of the geotechnical data

16       collection at that time?

17            A    Yes.  This period of time, in that third

18       quarter of 2007 leading into the fourth quarter, we were

19       doing fieldwork, and so yes, this is related to what we

20       were seeing from the fieldwork.

21            Q    Okay.  Now, would this condition be supportive

22       of placing a nuclear power plant on top of this area?

23            A    Yes.  The answer to your -- the question

24       you're asking me is, did this information that's

25       contained in this third hollow bullet -- does that

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1272

1       suggest that the power plant cannot be sited on that

2       site?  The answer is no.  It has to be analyzed,

3       however, and it has to be included in the scope of the

4       COL application.

5            Q    Now, would the NRC have been made aware of

6       these preliminary findings?

7            A    The NRC, as part of their geotechnical audit,

8       came to the site and they looked at our analysis, which

9       included both soil samples, core samples and down-hole

10       logging.  So I don'trecall if they actually looked at

11       the specific values from it, but it was certainly

12       available to them.

13            Q    Okay.  Can I ask you to turn to Exhibit 144?

14            A    Okay.

15            Q    Now, do you recognize -- and this is an expert

16       from a document, but do you recognize this document?

17            A    I do.

18            Q    In fact, your name is on here on the first

19       page.

20            A    Yes, I do.

21            Q    And can we say what this document is?

22            A    It's a monthly status report provided by our

23       COLA preparer.

24            Q    And what is the date of it?

25            A    November 20, 2007.

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1273

1            Q    Okay.  If I could get you to turn to the

2       second page.

3            A    Okay.

4            Q    And I believe at the bottom of it it says page

5       2 and it's Bates-stamped 47-007804.

6            A    Yes, I see that.

7            Q    This document is all yellow, so it is under a

8       claim of confidentiality.

9                 Can you tell me -- can you read the first --

10       to yourself, can you read the first line or the first

11       sentence in that top paragraph and tell me if that

12       sentence is confidential?

13            A    Well, certainly the whole report was

14       confidential.  I believe that I could paraphrase this

15       without revealing anything.  So let me read it and

16       decide how I want to state that.

17            Q    Thank you.

18            A    This statement revolves around the overall

19       schedule for the COL preparation.  Certain chapters were

20       not progressing as we preferred, and that's what this

21       statement is talking about.

22            Q    Okay.  Is one of the chapters of the three

23       listed here one that deals with the geotechnical

24       information?

25            A    Yes.

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1274

1            Q    The heading of this section, is that something

2       you can read publicly?

3            A    Yes.  This heading of this particular section

4       was Issues Requiring Management Attention.

5            Q    Is this -- the matter that's described in this

6       document, is this a matter that required further action

7       by the JVT management?

8            A    Yes.

9            Q    Can you tell me whether it required the

10       expenditure of additional funds?

11            A    I do not recall it costing more funds.  We

12       required them to take action because they were under

13       contract to produce the deliverable to us, and we had

14       established dates in that contract, and so it was their

15       requirement to provide what they needed to do to resolve

16       this issue.

17            Q    Is it -- go ahead.

18            A    And again, as I stated earlier, the July, 2008

19       was achieved.

20            Q    The term "impact evaluation" or "IE," is

21       that -- can you describe what that is?

22            A    An impact evaluation is the vehicle that was

23       used under the master service agreements and work

24       authorizations associated with this particular vendor,

25       and they were referred to as an impact evaluation

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1275

1       because a scope change, for example, could have not only

2       a cost element, it could have a schedule element to it,

3       and so we called it the impact evaluation; but it was

4       the mechanism to authorize scope changes, either

5       increase or decrease, and if there was any schedule

6       associated with that, that's how that would be handled.

7            Q    Can you state here today whether -- are you

8       testifying here that there were no impact evaluations

9       made or authorized to resolve the problems that are

10       identified in this paragraph?

11            A    I'm testifying I don't recall.  I know the

12       actions were taken to resolve the issues and they

13       resulted in our timely submittal.  I just don't recall

14       because we processed quite a bit of impact evaluations

15       over the period on different subjects.

16            Q    Isn't it possible that there were impact

17       evaluations authorized to resolve this issue?

18            A    Is it possible?  I suppose it's possible, but

19       I don't recall that that would -- we would not authorize

20       a scope change for -- because they're behind, if that

21       makes sense to you.  We would -- we had contracted with

22       the COL preparer to develop our application for this

23       site on a specific schedule, and the schedule was laid

24       out and they were executing that.  So their requirement

25       was to get the necessary resources and subject matter

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1276

1       experts to deliver that application on time.

2                 Your specific question to me, was there impact

3       evaluation forms for that, I don't recall.  I don't know

4       why we would have unless there was additional scope

5       required that was causing some of the difficulty

6       associated with the schedule execution.  It would have

7       to have been tied to additional scope to be able to

8       execute the COLA preparation and achieve that date.  We

9       would not give them a change order or an impact

10       evaluation because it was taking longer than they

11       expected because we had negotiated a contract for that.

12            Q    Okay.  Under quality -- can you read the next

13       heading there?  Is that -- can I read that publicly?

14            A    Yeah.  The headings that you're referring to

15       in this confidential document were standard over several

16       months, so it's a format question you're asking, so I do

17       not mind saying what that -- it says "Quality Issues."

18            Q    Okay.  So under that heading, there are two

19       items identified here; is that correct?

20            A    That is correct.

21            Q    And these relate specifically to Progress

22       Energy Florida, is that correct?

23            A    That is correct.

24            Q    Now, the first item relates to a discussion we

25       had earlier about NRC; is that right?

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1277

1            A    That is correct.

2            Q    And what was the outcome of that evaluation?

3            A    Ask your question again.  Are you asking me

4       specifically what does this bullet mean?

5            Q    What was the outcome, and I'm -- of the

6       evaluation that's referred to in that line?

7            A    As I said earlier, when we had the stop work

8       order associated with the CH2M-HILL execution, we looked

9       for extended condition across to the Levy COLA, and

10       there was extended condition because they were applying

11       similar processes for Levy.  And so the work associated

12       with the in-field work, we took compensatory actions and

13       made specific changes to address that so that work could

14       be restarted on a shorter time, but the remaining

15       changes that were necessary to be resolved prior to the

16       stop work stopped the work for both the Harris and the

17       Levy COLA.

18            Q    The second item there, what was the reason for

19       that?

20            A    There are two vendors in this bullet listed by

21       name.  Do you see that?

22            Q    Yes, I do.

23            A    Those vendors did work under our COLA

24       preparer, and their work is included in the fieldwork

25       that was done, and this bullet talks about findings that

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1278

1       were identified in the November, '07 timeframe without

2       saying more than I can.

3            Q    Did these findings have an impact on the

4       schedule?

5            A    Again, no.  We submitted our COLA July of

6       2008, as planned.

7            Q    Did they have an impact -- did they delay the

8       vendor's delivery of deliverables?

9            A    They did delay it in terms of the initial

10       baseline schedule for the preparation of various

11       chapters that would be fed into the final COL

12       development.  So yes, in that respect it did; however,

13       for the people with the key date, which was the final

14       submittal of the COL, it did not.

15            Q    There are two items in the parenthetical

16       there.  With respect to the second three-word item in

17       that parenthetical, can you tell me what was the reason

18       for that being done?

19            A    You're talking about in the parentheses of the

20       second bullet under --

21            Q    Yes, sir.

22            A    -- under Quality Issues?

23                 One of those companies, the one that's named,

24       did this evaluation, and we had an independent group do

25       that likewise.

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1279

1            Q    Why did you need an independent group to do

2       that?

3            A    This is for assurance that it was resolved

4       expeditiously.

5            Q    And was this at least an indirect result of

6       the problems that were identified in the spring of '07?

7            A    It was.  Let me point out that independent --

8       the rest of the language in there, that was -- those

9       individuals were under contract already.

10            Q    Can you turn to the next page, which is page 3

11       of this report excerpt?  Do you see that?

12            A    I go from page 2 to page 4.

13            Q    Oh, I'm sorry.  I'm using a slightly different

14       document.

15                 On page 4, yes.  And again, this is the same

16       report, November 20, 2007?

17            A    Yes.

18            Q    All right.  On page 4 here -- and again, this

19       is a confidential document, so I would like to ask you,

20       under the -- I can say "project schedule" --

21            A    Right.

22            Q    -- paragraph, right?

23                 The second paragraph there, can you describe

24       to me the reason for that sentence relative to your

25       assertion that the COLA submittal date was July, 2008?

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1280

1            A    Let me read this.  The first sentence has to

2       do with, based on the status to date, what's likely to

3       happen.  The baseline discussion has to do with what was

4       originally done back in the prior year, what was

5       established in the prior year.  I'm not sure I can

6       answer a question beyond that without saying more.

7            Q    Okay.  Well, let me ask you this:  The second

8       date in that paragraph, is that a typo?

9            A    No.  The original target was later and it was

10       moved up.

11            Q    Well, actually I'm looking at the year.

12            A    Oh, that is a typo, yes.

13            Q    Okay.  So it should be --

14            A    2008.

15            Q    Okay.  All right.  So there are -- so is it

16       true that the schedule changed?

17            A    It is true that we advanced the target for

18       that schedule.

19            Q    Okay.  Now, isn't it true that, to do that,

20       you had to make changes to scope of work?

21            A    The scope of work to prepare a COL application

22       is the same whether you submit it July or August.  It's

23       the same.

24                 MR. REHWINKEL:  Mr. Chairman, I would like to

25       ask permission to approach the witness.  I want to show

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1281

1       the company attorney first what --

2                 CHAIRMAN CARTER:  You may do so.

3                 It's a great day.  Isn't it?

4       BY MR. REHWINKEL:

5            Q    I'll need that document back but --

6            A    My copy does not have the same --

7            Q    It does not, I understand.  I wanted to ask

8       you a question.  If you could look at the middle of page

9       three of that document, which I did not include in the

10       exhibit, and tell me if there were scope changes that

11       were made to achieve a certain target date?

12            A    Yes, in that context, there was a scope change

13       to advance the COL submittal by one month; that is

14       correct.

15            Q    And does that mean that the July, 2008 date

16       was not the original target date?

17            A    When the initial baseline schedule was

18       established by the COL preparer, they had mapped it out

19       and it had resulted in one month later.

20            Q    Thank you.

21                 I apologize for the cumbersomeness of this,

22       but the confidentiality makes it somewhat difficult.

23                 CHAIRMAN CARTER:  You're doing a great job.

24       Keep on.

25       / / / / /

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1282

1       BY MR. REHWINKEL

2            Q    Okay.  In the sentence that begins "JVT is,"

3       do you see that back on page four of the November 20,

4       2007 document?

5            A    Yes, I see that line.

6            Q    Can you just tell me what is involved in

7       executing that sentence there?

8            A    Let me think of how I can paraphrase that

9       without revealing what it is.  If I have a scope of work

10       to do that's going to take 20 hours for one person to do

11       it, potentially I can do that in less than 20 hours if I

12       add a second person and they share that work.  It's in

13       that context.

14            Q    Did doing that increase the expenditures by

15       PEF?

16            A    There was -- as part of our the overall

17       schedule execution and the development of that revised

18       July, 2008 target, I do recall there was a specific

19       impact evaluation form for August to July in order to

20       achieve our final service date.  So that is true, but it

21       was also based, not just on the in-service date that we

22       had for the plants being placed in service, but the

23       production tax credits that was under the energy bill,

24       the EPACT 2005, there was not clarity in what it meant

25       to have your application accepted.  So we wanted to make

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1283

1       sure there was plenty of float in the time that our COL

2       was submitted and docketed in 2008 --

3            Q    Okay.

4            A    -- to maintain eligibility for the production

5       tax credits.

6            Q    Now, the last bullet on that page 4 indicates

7       in the parenthetical a timeframe that the fieldwork for

8       that FSAR section was behind your targeted schedule; is

9       that right?

10            A    Without revealing the content and confidential

11       matter, as of the date of this report, the number in

12       parentheses was for that portion of that identified

13       section of the application.

14            Q    Can I ask you to turn to the next page, which

15       I believe is page 5.  Is that what you show?

16            A    Yes.

17            Q    Okay.  This is November 20th, 2007, and this

18       is a confidential page.  Is the "under-risk" matrix --

19       is that -- those first two sentences there, is that

20       confidential?

21            A    The fact that we have a risk matrix is not

22       confidential.

23            Q    Okay.  What about the item in the

24       parenthetical there?

25            A    It depends on what you're going to ask me

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1284

1       about those -- what it says in the parentheses.

2            Q    Okay.  I guess what I want to know, what I

3       want to ask you about is the items that are in that

4       color at the bottom of the page, the first bullet of the

5       new color.

6            A    Yes.  To be able to answer this question,

7       there were activities going on that represented risks to

8       executing and submitting the COL as planned.

9            Q    And were some of those what we just discussed?

10            A    Correct.

11            Q    Now, the hollow -- the second hollow bullet

12       under the first bullet under that risk matrix item is

13       the same thing we read about in that second quarter,

14       2007 report; is that right?

15            A    The language looks similar.

16            Q    Okay.  Can you turn to the next page in that

17       document, and can you tell me what this document is or

18       represents?

19            A    Yes.  Hold one second.  Let make me make sure

20       I understand.

21            Q    This is Bates 47-007842.  Is that what you

22       show?

23            A    Yes.  This is a schedule of the COLA

24       preparation.

25            Q    Does it show whether the COLA preparation

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1285

1       tasks are on target or not?

2            A    The print is small, so please stand by.

3                 You cannot infer it -- unless I cannot see it,

4       you cannot infer the answer to your question from this

5       page alone because those actions that are in the

6       schedule you're requesting are not on this page.

7            Q    Okay.  Let's turn to the last page then, which

8       has got even smaller print.  This is a similar document?

9            A    It is, and, again, in the WBS of the schedule,

10       there are activities associated with the final prep of

11       the COL, what's referred to as preflighting, before you

12       submit it to make sure all the linkages are correct and

13       the requirement -- to meet the requirements of the NRC,

14       the packaging, and I cannot locate those actions on

15       here, and those are the ones that you would really need

16       to look at.

17            Q    You said WBS?

18            A    Work breakdown structure.

19            Q    Is that what this --

20            A    This is a schedule but the activity names are

21       typically related to a WBS task, and I'm looking for the

22       task that says package the COLA and preflight it and

23       submit it for final owner's review, and I don't see that

24       on these pages.  So the answer to your question is I

25       cannot answer it.

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1286

1            Q    Okay.  Well, halfway down do you see the two

2       blue -- the first three blue lines on that page that go

3       horizontally across?

4            A    You're on page 7848?

5            Q    Yes.

6            A    All right.  I see the heading.

7            Q    Well, there's three large thick blue lines,

8       the first three.  There's more.  There's six of them.

9       I'm talking about the first three.  Do you see those?

10            A    No, I'm not following you.

11            Q    I'm talking about these (indicating)?

12            A    Yes, the headings.

13            Q    Yes.  Between the -- in the two sections that

14       are created by those three headings, and there's a

15       column about halfway across the page that has the

16       letters BL, do you see that?

17            A    A column --

18            Q    A column heading in the green.

19            A    And what does the column heading say?

20            Q    I think it says "baseline variance."

21            A    Yes, I see that.

22            Q    Okay.  I hope I didn't disclose confidential

23       information there.

24            A    That's not a problem.

25            Q    Okay.  If you go down under that column

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1287

1       heading, you see some three-digit numbers with a minus

2       sign in front of them.  Do those relate to tasks?

3            A    In general -- let me answer your question --

4       if you have a schedule and there is a baseline and then

5       there's a variance to that schedule, you would show

6       numbers as positive or negative with respect to where

7       you are with the original baseline.

8            Q    Were these numbers cause for concern at this

9       time?

10            A    Yes, and I think some of the items you pointed

11       out to -- as part of our dialogue, was related to our

12       concern and the actions we were taking to address it.

13            Q    Can I ask you to turn to the third -- I mean,

14       to Exhibit 145, the LNP Status Slide.  Are you familiar

15       with this document?

16            A    Yes.

17            Q    Okay.  It has your name on it.

18            A    Yes.

19            Q    And what was the purpose of this document?

20            A    I do not recall why I prepared it, but

21       obviously I did do it.  I don't remember -- I do not

22       recall what the purpose and what, you know, venue that

23       it was used in.

24            Q    Okay.  Can you turn to the last page of that

25       document, which I think is 47-010372.  Do you see that?

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1288

1            A    I see that.

2            Q    Okay.  And this document is all in yellow.

3            A    Yes.

4            Q    So I assume there's a claim of confidentiality

5       for at least some of the information on it.

6                 The heading here, can I read that?

7            A    Yes.

8            Q    Okay.  So it says, "Levy COLA."  What about

9       the item under the bullet, next to the bullet there; can

10       you read that publicly?

11            A    Which bullet?

12            Q    The first bullet.  I'm sorry.

13            A    "Levy COLA, July 2008 Submittal."

14            Q    All right.  Now, what about the two diamonds

15       underneath that bullet; can those be read publicly?

16            A    No, but I can paraphrase.

17            Q    Okay.

18            A    As we've discussed, in this period in late

19       2007, the progress on the development of specific

20       chapters that would be submitted in the COL application

21       was not meeting our expectations.

22            Q    Okay.  So this is very consistent with what

23       we've been talking about with respect to the schedule?

24            A    That's correct, and we took actions and we

25       submitted July, 2008.

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1289

1                 MR. BURNETT:  Mr. Chair.

2                 CHAIRMAN CARTER:  Sir.

3                 MR. BURNETT:  Apologies for interrupting.  I

4       believe, with confirmation from Mr. Miller, that this

5       document has -- due to the passage of time is no longer

6       confidential.  So this may be -- if you could confirm

7       that, my belief there.

8                 THE WITNESS:  Yeah, I believe this passed to a

9       point where we probably can open this particular page.

10                 MR. BURNETT:  I'm sorry to interrupt, but I

11       believe we can speak about --

12                 CHAIRMAN CARTER:  So it's the page, not the

13       entire document, just this page?

14                 THE WITNESS:  Yeah, this individual page

15       because that's really all he's asking me questions on.

16                 CHAIRMAN CARTER:  Okay.  Mr. Rehwinkel.

17       BY MR. REHWINKEL:

18            Q    Okay.  Thank you.

19                 So this document here says that, with respect

20       to the Levy COLA and the 2008 submittal date for the

21       COLA, that it is challenged based on site geotechnical

22       analysis; is that right?

23            A    That's correct.

24            Q    And "challenged" means that you foresee some

25       difficulty in meeting it, is that right?

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1290

1            A    It means --

2            Q    At this time?

3            A    -- that there was a challenge in meeting the

4       schedule to submit the COL on this particular subject.

5            Q    Now, the fact that this document -- can I --

6       on the first page of it where it says your name, can I

7       read that, that whole --

8            A    Yeah, I believe that's acceptable.

9            Q    Okay.  So it says, "November 26, 2007,

10       developed for Jeff Lyash by Gary Miller," right?

11            A    That's correct.

12            Q    Now, if you're doing this for Jeff Lyash, that

13       must mean Jeff Lyash has to present this -- make a

14       presentation to somebody maybe even above Jeff Lyash; is

15       that right?

16            A    That's correct, but at the same time it could

17       be some other venue.  I just don't recall what it was

18       for.

19            Q    Okay.  And it says in here, going back to the

20       last page here, that "actions being developed to recover

21       schedule."  Do you see that?

22            A    I do.

23            Q    What are those actions, if you can say?

24            A    Well, the actions that we had talked about.

25       The progress by the Consortium was not -- the JVT was

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1291

1       not where we expected to be able to achieve the July

2       2008 submittal.  So we required them to add additional

3       resource and take those necessary actions, including

4       working longer, if necessary, to advance that work so

5       that our July, 2008 submittal would be met, and as I've

6       stated several times, we met it.

7            Q    And it included the expenditure of additional

8       resources?

9            A    That was not the intent.  You'll recall from

10       our previous questions and answers we did authorize an

11       impact evaluation form for advancing the schedule a

12       month because that's what we needed; however, the fact

13       that they fell behind the execution of the work that was

14       in their contract under their existing scope, that was

15       what they had to take care of.

16            Q    Do you know whether they did expend additional

17       resources regardless of whether they got additional

18       funds from Progress, "they" meaning the JVT?

19            A    I suspect they did, but that was not part of

20       what we covered.

21            Q    Okay.  I would like to turn now to Exhibit

22       146, and this is excerpts from -- well, could we state

23       the title of this document on the first page there?  Can

24       you read the -- tell me what this document is?

25            A    Well, generally this whole package is

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1292

1       performance reports.

2            Q    Okay.  And it's reports by whom to whom?

3            A    This report would be from my organization to

4       my management.

5            Q    Okay.  And on this first page, that's your

6       signature there at the bottom?

7            A    That's correct.

8            Q    Okay.  On the second page of this report, this

9       says, "October, 2007" up at the top.

10            A    Yes.

11            Q    And this is page 4 of the document, correct?

12            A    Correct.

13            Q    All right.  Under 1.3, "Schedule," do you see

14       that heading?

15            A    I do.

16            Q    The second paragraph there, is this

17       document -- is this paragraph consistent with what we

18       have been talking about with respect to the JVT and the

19       schedule?

20            A    The first few sentences of this relate to that

21       same subject.

22            Q    Okay.  I'm going to ask you to turn to the

23       next page in the exhibit, and under 1.4, "Key Issues,"

24       do you see that?

25            A    I do.

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1293

1            Q    The second bullet item, can you read the

2       second sentence in that bullet item?

3            A    Because this sentence was stated earlier, I

4       have no problem with stating the sentence.  "The July,

5       2008 submittal was challenged based on site geotechnical

6       analysis requirements."

7            Q    And this is what you reported to your

8       management --

9            A    Yes.

10            Q    -- above you?  Okay.

11                 Down at the last bullet item under Key Issues

12       on this page, can you tell me if you can state any of

13       the information in this bullet item publicly?

14            A    I can summarize.

15            Q    Okay.

16            A    What this particular discussion is talking

17       about is the action planned to deal with the quality

18       assurance findings that were identified both from their

19       audits, our audits, our stop work, and then subsequently

20       what will happen in the next month will be an NRC

21       review.  As part of all that, they're taking actions,

22       and it's talking about the fact that we're going to

23       follow that work and make sure it does -- it's done in a

24       timely manner to support both COLA submittals.

25            Q    Now, is this issue that's discussed here any

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1294

1       different from the NRC audit issue that we discussed

2       earlier?

3            A    The general issue is the same, and, again,

4       remember, it was first they identified some issues, we

5       then did an audit, we did a stop work, and then

6       subsequently the NRC came in and reviewed all of that

7       and then they issued a report on that and had some

8       additional items that they identified.  And so the

9       corrective actions for all those things collectively are

10       embodied in the work going on.

11            Q    In your answer, the first "they" you used, I

12       think you meant -- referred to CH2M-HILL?

13            A    In this case it was CH2M-HILL.

14            Q    I'd like to ask you to turn to page -- you can

15       skip the next page and turn to page 10 of that October,

16       2007 excerpt.  Do you see that?

17            A    Yes.

18            Q    Under the -- at the very bottom under the

19       heading 2.5.2, "PEC Scope Change Authorized," that's not

20       Progress Florida.  That's Carolina, is that right?

21            A    Correct, but it's still confidential.

22            Q    I apologize.

23                 So the action that's referred to in here does

24       not refer to any work done in Florida?

25            A    I think the answer to your question is, if it

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1295

1       says PEC, that's Progress Energy Carolinas.

2            Q    Okay.  Let's go to 2.5.4 on page 11, and this

3       is a confidential document, I'll remind myself.  Do you

4       see that --

5            A    I do.

6            Q    -- on page 11 of the report excerpt?

7                 Can you read this paragraph to yourself and

8       tell me what of this you can state publicly?

9            A    Yes.  There is a similar dialogue in my

10       rebuttal testimony regarding this subject, and it refers

11       back to questions you asked me earlier today.  When we

12       went out and bid the work to prepare two COLAs, we did

13       that with two sites and, because we at that point had

14       not identified where in Florida the Levy -- where we

15       would actually build a nuclear site, we bid it out as

16       two sites like the Harris site.  And so this paragraph

17       is talking about the fact that, after the site was

18       selected -- and again, this is embodied in my rebuttal

19       testimony -- the fact that there are specific

20       differences in the Levy site versus Harris and some of

21       those involve additional scope that had to be done,

22       authorized in order to prepare a full and complete COL

23       for that site.  A prime example:  Levy is a marine site,

24       Harris is not.  And so there are certain aquatic species

25       measurements you do for a marine site that we would not

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1296

1       do at Harris.

2            Q    So the last sentence in that paragraph refers

3       to the scope of work that you did not specifically

4       identify for the Levy site at the time you engaged the

5       JVT?

6            A    That's -- let me see if I can explain it.

7       Again, when we bid out the COL preparation, we bid it as

8       two sites like Harris.  Once Levy was selected, then we

9       looked at what are the unique features of Levy that will

10       require additional analysis or evaluations or field

11       investigations or fieldwork that would be required

12       because that site is not quite the same as a Harris type

13       site, and what this statement is talking about is

14       associated with, as we went through that process, for

15       example, the Cross Florida Barge Canal, we had to do

16       marine sampling on that barge canal and salinity and

17       tidal kind of measurements and bathymetry.  Well, those

18       are things that we would not do at Harris because it's

19       not a marine site, and so they were not in the original

20       Harris scope.  So, while the process of bidding out the

21       two applications collectively results in an overall less

22       cost for both of them, that does not mean that they're

23       exactly the same site, and so Levy had additional scope

24       that had to be authorized as part of that.

25            Q    Okay.  So it wasn't a matter of catching up

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1297

1       because of the time it took to identify the site, the

2       Levy site?

3            A    Oh, no, sir.  This is strictly the fact that

4       it has different features and those features have to be

5       addressed through investigation.

6            Q    Okay.  Thank you.

7                 Bathymetry, is that fish?

8            A    Depth.

9            Q    Depth.  Okay.

10                 Under 2.5.5, can I read this heading?

11            A    The heading, yes.

12            Q    "PEF, Potential and/or Pending Scope Changes."

13       And can you tell me about the first bullet item there?

14       Is that what we've been referring to?

15            A    You recall, yes, the original baseline

16       schedule versus the actual schedule that we targeted,

17       that's what that's referring to.

18            Q    Okay.  And what about the fourth item there,

19       is that the item we referred to on a prior exhibit

20       about --

21            A    That relates to again -- to respond to

22       questions that occurred during the geotechnical audit by

23       the NRC, we concluded it would be best, to make our

24       application more complete, to have an independent

25       review, and that's what that's referring to, and

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1298

1       obviously you can read the subject, what it's about.

2            Q    Is this an independent review of one of the

3       vendor's fieldwork?

4            A    I would characterize it as an independent way

5       of doing the same measurement and presenting that

6       information also.

7            Q    But can you say whose measurements were being

8       reviewed?

9            A    Well, obviously, the work -- the broad scope

10       of work we're talking about is geotechnical; however,

11       under geotechnical, there were subcontractors under that

12       that were under CH2M-HILL, and some of those did certain

13       measurements, and at the time this was -- and I'm doing

14       this from memory -- was we felt like, based on some

15       preapplication submittal interactions with the NRC, our

16       application would be more complete by having an

17       independent measurement of a certain characteristic.

18            Q    Was this independent measurement directly or

19       indirectly related to the issues that surfaced in March,

20       2007?

21            A    If you're asking me, are they related to

22       quality issues, no.

23            Q    Okay.  Under 2.6, "High Risk Issues," the

24       first bullet point here, this relates to -- can you say

25       who this relates to, which company?

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1299

1            A    The first bullet?

2            Q    Yes.

3            A    In the late-'07 NRC audit, they identified

4       some deficiencies, and this is referring to -- it's a

5       discussion about that and what's going on about that.

6            Q    Okay.  Did this have any bearing on the work

7       that was being done in Florida for the LNP site?

8            A    Read the first sentence under this one, under

9       this heading.

10            Q    I understand that, but I'm asking, did it have

11       any bearing on the work that was being done in Florida?

12            A    Well, again, as the issues were identified and

13       we identified as potential extended conditions, so we

14       took actions to resolve that for Levy, and this -- it

15       relates to the fact that Harris was done -- the

16       fieldwork where the problem was identified occurred many

17       months in advance of Levy.

18            Q    All right.  On the next page, which is page 12

19       of this excerpt which is confidential, does this section

20       here at the top of the page relate to Levy work?

21            A    Yes.

22            Q    And on the last bullet point there, can you

23       tell me what that refers to?

24            A    It refers to the subject we have been

25       discussing, which was the execution of one of the COLA

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1300

1       preparer contractors in meeting their schedule.

2            Q    Does this issue persist throughout the

3       engagement of this preparer throughout the COLA

4       preparation?

5            A    I think the question you're asking me, the

6       amount of time that they were behind, did that continue

7       through to the end?  The answer is no because, as they

8       took corrective action as we increased our monitoring of

9       their execution, they began to catch up, and so

10       subsequently we did complete the application and submit

11       it on time, July, 2008.

12            Q    Okay.  Can you turn to page 14 of this

13       exhibit, under Section 4.4.1, "NRC QA Audit."  Do you

14       see that?

15            A    Yes.

16            Q    Now, is this section related specifically to

17       one company or is this an overall progress issue?

18            A    In general that would relate to both COLs

19       being developed.

20            Q    Okay.  Let me ask you to turn into the

21       December report and to page five, under 1.5.

22            A    Yes.

23            Q    Is there anything confidential about the third

24       bullet item?

25            A    No.  It is well -- it's in public information

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1301

1       that we had a meeting with the NRC January 10th.

2            Q    Okay.  And this was January 10th of 2008?

3            A    That's correct.

4            Q    Was there any quality assurance issues related

5       to the audit discussed at that meeting?

6            A    I don't recall, and that was not the purpose

7       of that meeting.

8            Q    On page 11 of this excerpt, again, just so I

9       understand, 2.5.4 under the section "DEF Authorized Code

10       Changes," the next to the last sentence of that first

11       bullet point, that's again describing the issues related

12       to the differences in the Levy site versus the Harris

13       site?

14            A    I would take exception.  It's not issues.

15       It's the fact that the Levy site is not the Harris site,

16       and so what was bid as a baseline scope, there were

17       increases for the Levy site.

18            Q    Okay.  The next page, page 12.

19            A    Yes.

20            Q    Is there any -- on the third bullet item

21       there, and this is under the section 2.5, "High Risk

22       Issues," and this is the section of that that relates to

23       PEF; is that correct?

24            A    Yes.

25            Q    The last bullet point here in that section at

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1302

1       the top of page 12, is that again -- is that any

2       different than we've already discussed with respect to

3       this subject matter?

4            A    No, and let me point out, what you're seeing

5       here, as a management team, we had very close oversight

6       of what was going on here and taking actions to ensure

7       our schedule would be recovered and be able to meet our

8       target submittal date, and so you're seeing that

9       reflected in the report.

10            Q    The January, 2008 report, page 9, if we can

11       turn to that page; do you see that?

12            A    All right.

13            Q    Under 2.4.2, "PEF COLA Development."

14            A    What page?

15            Q    I'm sorry.  Page 9.  It's Bates

16       FPSC1-9-0000009.  Do you have that?

17            A    I'm not following you.  I see the June, 2008

18       report is the next one in my package.

19                 Oh, no, I stand -- you're still on the January

20       one?

21            Q    Yeah, the page --

22                 CHAIRMAN CARTER:  One second, Mr. Rehwinkel.

23       Mr. Rehwinkel, one second.  Commissioner Skop?

24                 COMMISSIONER SKOP:  Never mind. I was going to

25       say it was the next page in the document I have, so --

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1303

1                 MR. REHWINKEL:  Okay.  The pages are not --

2       okay, I see.  You're on page 9 of January, 2008.  The

3       cover sheet's missing.  That's what threw me off.

4                 THE WITNESS:  Okay.  Yes, yes.

5                 CHAIRMAN CARTER:  Okay.  We're all on the same

6       page now?

7                 THE WITNESS:  Literally.

8       BY MR. REHWINKEL:

9            Q    The middle of that paragraph there --

10            A    Under which section?

11            Q    2.4.2, "PEF COLA Development," is that

12       sentence there that starts, "The improvement," is that

13       confidential?

14            A    The way that was structured, I would prefer to

15       paraphrase it if I can.  We looked at how -- let's just

16       back up to a higher level.  The COLA is many sections

17       and you can subdivide that down into subsections, and so

18       we went through a process to better define this piece

19       parts of the work to be able to better expedite its

20       execution.  And you see the subjects, the ones it

21       included there.

22            Q    Okay.  And I guess there's a word on the one,

23       two, three, four, five, six, seven -- no, sixth line

24       here, the one that starts with the word "The."  Do you

25       see the fourth word there?  It begins with an S.

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1304

1            A    Yes, I see that word.

2            Q    Okay.  Does that denote some level of effort?

3            A    Yes.

4            Q    Okay.  Resources?

5            A    It denotes resources of our oversight and

6       their leadership team of their contract organization.

7            Q    Okay.  If you could turn to the June report,

8       page 12, can you describe, on the hollow bullet point

9       item that starts with the letter six -- I mean, the word

10       six, what's happening in that as being described there?

11            A    There are two technical subjects addressed in

12       this.  Let me describe this at a high level.

13                 As we talked about earlier, there are

14       preapplication interactions with NRC where they review

15       the progress of your COL development and they provide

16       comment on that and ask questions, and based on the

17       questions we get and some of what they say, what they

18       would expect to see in an application, then we adapt and

19       make sure that we include that in our application so

20       that would facilitate a more efficient review.

21            Q    Okay.  So this wasn't necessarily an area of

22       concern by the NRC?

23            A    No.  All sites, AP1000 sites have gotten these

24       visits, and they've gotten feedback and they've taken

25       action.

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1305

1            Q    Okay.  The next page, page 15, under 5.3, "PEF

2       Site Engineering."

3            A    Yes.

4            Q    Can you tell me what the second sentence there

5       that begins with the word "Specifically" is referring

6       to?  Can you paraphrase that?

7            A    Yes.  The -- let me see how I could describe

8       this.  Let me describe this in a simple way and that

9       will then set the stage for a more complicated answer.

10       If I was at the Harris site, I can go in and I can clear

11       off about ten foot of sandy soil, and it's a rock site

12       so I can create an excavation by blasting a hole in the

13       rock, and that creates the foundation for where the

14       plant will be built.  In the case of Levy, because of

15       groundwater and the layers that exist at that site,

16       sandy soil over a competent limestone base, followed

17       then by bedrock very deep, we -- the foundation design

18       is more complicated and so we brought in an expert, Paul

19       Rizzo, to help support us in the foundation design, but

20       that foundation design, including the engineered

21       backfill, is coupled with the geotechnical of what's

22       below that, because in our case the engineered backfill

23       is not just raising the level of where the plant's going

24       to be built, but it's also providing a bridging

25       function.  In other words, at the Levy site there's

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1306

1       about 60 to 70 foot of sandy soil overburden over the

2       limestone, and we have remove that, and then we have to

3       then put something back on top of that that the reactor

4       foundation will sit on, and the bottom of that

5       foundation is at minus 40 feet.  So you need to go from

6       like minus 70 to minus 40, adding in 30 feet of

7       something in there that will bear that load and then

8       that will have the proper behavior in a seismic event.

9                 Because of the geology in Florida, that

10       bridging mat, which is engineered backfill, has more

11       functions.  And so this is referring to the fact that

12       we're bringing in someone to help us with the final

13       design of that foundation.

14            Q    When you say "bringing in," you're talking

15       about Paul Rizzo?

16            A    Correct, and when I say "bringing in," he was

17       brought in under the JVT as a quality provider of a

18       service.

19            Q    Okay.  When we looked at -- when we just saw

20       his name in an earlier exhibit, that was not work under

21       the JVT?

22            A    It was, but that was a different scope of work

23       than what this is.

24            Q    Okay.  Now, isn't it true that he was also

25       brought in to help with issues that he had been having

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1307

1       with another vendor in the collection of geotechnical

2       data?

3            A    No.  What you say is not the correct

4       characterization.  He was brought in to provide us

5       independent review of that, what was coming up as part

6       of the data coming up out of the ground.

7            Q    Okay.  Were there any responsibilities that

8       were transferred from one vendor to Mr. Rizzo?

9            A    Yes.  As we entered into 2008 and we were

10       approaching the COLA submittal, certain subsections

11       within the FSAR were reassigned to -- for completion

12       from CH2M-HILL to Paul Rizzo because of the close

13       coupling to the foundation design which they were

14       designing.

15            Q    So that was something that needed to be done

16       in order to assure that that aspect of the COLA was

17       completed to meet your deadline?

18            A    That's correct, but it was also more than just

19       a timing issue; it was a subject matter expert

20       requirement because the foundation design for Levy is

21       more complicated because of the fact that the engineered

22       backfill is not just backfill.  It actually serves a

23       bridging mat function over the limestone.

24            Q    But it was initially not contemplated that Mr.

25       Rizzo's firm would need to do that?

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1308

1            A    It was originally not contemplated, but that

2       evolved through the analysis of the site that we

3       determined that we would need that additional capability

4       and subject matter expertise.

5            Q    Now, did any of the information that Mr. Rizzo

6       worked on, did it have any bearing on the LWA

7       evaluation?

8            A    Well, the scope of the work that he worked on,

9       such as the roller-compacted concrete or what's referred

10       to as the bridging mat -- some people would call it the

11       engineered backfill -- that was part of the scope that

12       was in the original LWA request.

13            Q    And by original -- and it was also still in

14       there after September 12th, correct?

15            A    That is correct.

16            Q    Let's go to September, 2008, page 13, excerpt.

17       Now, this is section 2.6, "High Risk/Critical Items."

18            A    Yes.

19            Q    And the last bullet point in that section is

20       one of the risk -- is one of the items that is listed in

21       there, is that correct?

22            A    That's correct.

23            Q    Can it be publicly stated?

24            A    Yes, I can state this.  This has to do with --

25       it's -- under the category of what's requiring

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1309

1       management attention, it's NRC review schedule for the

2       COL.

3            Q    Okay.  And this --

4                 CHAIRMAN CARTER:  Just one second,

5       Mr. Rehwinkel.  Commissioner Skop.

6                 COMMISSIONER SKOP:  Thank you, Mr. Chairman.

7       Mr. Rehwinkel, which page are you on?

8                 MR. REHWINKEL:  I'm on Bates-stamped

9       47-013484, page 13 of the September, 2008 report

10       excerpt.

11                 COMMISSIONER SKOP:  Okay.  All right.  Thank

12       you.

13                 CHAIRMAN CARTER:  You may proceed.

14       BY MR. REHWINKEL:

15            Q    The LWA schedule is not separately identified

16       as a risk in this section?

17            A    It is not.

18            Q    Is that because at this time you had not

19       received the October 6 letter from the NRC?

20            A    It's not in there because we had submitted an

21       LWA request and we had no reason to add it on as a risk

22       because we had not received any information that would

23       suggest we had a problem.

24            Q    Okay.  Page 14 of this report, October, 2008,

25       Section 2.6.

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1310

1            A    Yes.

2            Q    Again, one of the next to the last bullet

3       point items is the same?

4            A    The same.

5            Q    NRC review schedule for COLA.

6            A    Correct.

7            Q    And you're saying you had probably gotten the

8       October 6th letter at this time.  Because this is a

9       report for October, you would have prepared it early

10       November --

11            A    That is correct.

12            Q    -- or completed it?

13            A    We would have had the knowledge of the October

14       6th letter.

15            Q    Okay.

16            A    And we would know that the review schedule was

17       contingent upon our answering the RAIs which are

18       embodied in the October 6th letter.  So we had

19       management attention to get those answers in.

20            Q    Okay.  And on page 19 of this exhibit, under

21       Section 6.2 --

22            A    Yes.

23            Q    -- PEF, can you just tell me generally what's

24       in that section or what that's discussing?

25            A    Stand by.  Let me read it.

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1311

1            Q    Sure.

2            A    This section is summarizing the October 6th

3       letter, and it has cut and paste from that letter in the

4       text here.

5            Q    Is there anything particularly confidential

6       about what's here?

7            A    The portions that are in italics should be

8       verbatim cut and paste from the October 6th letter.  The

9       information at the bottom of this which talks about the

10       scope of the LWA, that is consistent with the September

11       12th public submittal.

12            Q    Okay.  So this is in here more for information

13       to management?

14            A    Well, it's in there because we had received

15       our schedule, and so it's an acknowledgement of what

16       they said in the schedule, that they need more

17       information, and because this is October and it follows

18       the September, it's acknowledging also the scope of the

19       LWA.

20            Q    Okay.  And on page 5 of the November report,

21       if you'll page forward into the November report excerpt,

22       do you see that, Bates 47-013496?

23            A    I see that.

24            Q    Okay.  And this has a section called "Key

25       Issues," 1.4; do you see that?

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1312

1            A    Yes.

2            Q    Is this -- what is the purpose of this section

3       here?

4            A    It's items of management focus just as the

5       second bullet which we just referred to in your our last

6       dialogue.

7            Q    And page 14 of November, 2008, again, you have

8       the bullet point in Section 2.6, NRC Review Schedule for

9       COLA.

10            A    Yes.

11            Q    Page -- let's go to the December, 2008 report,

12       and specifically -- well, look on page five.  Under Key

13       Issues, the fourth bullet point, have you information in

14       there that can be read publicly?

15            A    That is public.  We executed the EPC on

16       December 31st of 2008.

17            Q    Okay.  So this means that at least portions of

18       the information in this document were placed in here

19       after the first of the year 2009?

20            A    In general, this report is created probably

21       ten to 15 days into the next month because it's held up

22       by the completion of financial data that would need to

23       be going into the report.

24            Q    Okay.  On page 13, under Section 2.6, "Risk

25       Critical Items," the last bullet point -- well, first of

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1313

1       all, two, four -- sixth from the bottom we say that "NRC

2       reviews schedule for COLA."

3            A    Yes.

4            Q    Okay.  And then -- but the last bullet point

5       is a new one.  Can you read that one?

6            A    Yes.  LWA, limited work authorization

7       approval.

8            Q    Okay.  Now, why is that in here?

9            A    Because in the execution of the activities

10       leading up to first concrete, the next big evolution,

11       because of the September 12th change in LWA scope, is

12       all constrained by the LWA.  So we're raising this to --

13       on our -- in terms of our management attention because

14       it is the next big evolution that will take place that

15       will govern the control of physical site work.  So we're

16       placing an emphasis on getting that done.  And the

17       reason I say that is because, if you are in the month of

18       let's say September, before September 12th we would have

19       planned on installing the diaphragm wall, installing the

20       grout, and then excavating-dewatering as part of our

21       preconstruction activities.  Because of this

22       September 12th scope-change letter, that now -- LWA

23       is -- that timeline includes those activities, and so

24       you now need the LWA to start that work, and so that's

25       why it's getting visibility here.

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1314

1            Q    Why is it in here and not in the November

2       report?

3            A    I don't recall specifically why it's in

4       December versus November other than the fact that we're

5       now looking ahead to when we're going to start physical

6       work on the site and what's going to constrain you from

7       doing that, which is the LWA.

8            Q    So it was a concern to put in here in the

9       first week or two of January, 2009, but not the first

10       week or two of December of 2008.

11            A    No.  This report clearly is written after the

12       end of December.  It always is because of the financial

13       information which is in the report.

14            Q    But I guess my question is, why isn't this

15       same concern listed as a high-risk critical item in the

16       month before?

17            A    At the time -- let's see, I'm going back and

18       I'm trying to do this from memory.  Back in November,

19       2008, there was no issues or concerns we had with LWA

20       approval.  We had changed the scope as identified in the

21       September 12th letter, but I believe, and this is from

22       memory, that this was just merely stating the fact that,

23       looking ahead, the activities that are going to next

24       come to the site are going to governed by the LWA

25       approval.  So that becomes an important next regulatory

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1315

1       step, no different than some of the other items we have

2       on here, such as land acquisition or other things which

3       are things that we were working on to be able to advance

4       the project.

5            Q    Okay.  In the -- let's see.  If we can go back

6       to the -- let's go back to page 17 of the November

7       report.

8            A    All right.

9            Q    The very top bullet point item on page 17,

10       there is the word "problems."  Do you see that?

11            A    Yes.

12            Q    Okay.  Now, isn't it true that the event

13       that's described here occurred in the first week of

14       December, 2008?

15            A    I don't recall the exact week, but it was end

16       of the year 2008, and that date sounds reasonable.

17            Q    So this is information from December, 2008

18       that's in the November report?

19            A    I don't recall the specifics of when the work

20       started and when the instructions were reviewed in

21       preparation for the work in the field.

22            Q    Well, isn't it true that there was a stop work

23       order issued with respect to this contractor that's

24       referred to in the first line of that bullet point?

25            A    That's correct; however, the work had not

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1316

1       commenced at the site yet.  We reviewed his procedures

2       for executing the work at the site and we were not

3       satisfied, and so the work was not allowed to start.

4            Q    But isn't it true that stop work order was

5       issued in the first week of December of 2008?

6            A    I don't recall the specific date.

7                 It is possible that, when this report was

8       finalized, that someone had insight in what happened in

9       the first week of December and included it in November.

10       That is a possible outcome here.

11            Q    Okay.  But in the first week of December,

12       2008, is it your testimony that the LWA or limited work

13       order -- limited work authorization approval was not an

14       item that should have been included in the High

15       Risk/Critical Items section?

16            A    It is my testimony that I had -- did not have

17       a concern whether we received an LWA in November -- that

18       I had a concern in November, 2008 that we would not get

19       an LWA.  I did have not that concern in November and I

20       did not have that concern in December either.

21            Q    Well, what was -- what happened in the first

22       week of January that caused you to have it?

23            A    Well, again, as I said earlier, this relates

24       to, as you look ahead to what activities are going to

25       occur next on the site, those activities are the work

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1317

1       associated with the diaphragm wall and grout which are

2       now constrained by an LWA.  So we're looking ahead

3       toward the next major approval.

4            Q    Okay.  Let me ask you to turn to page 189 of

5       the December report, under 6.2, PEF, and the first part

6       of that is the same thing -- through the italics, is the

7       same thing that's in the November report; correct?

8            A    That's correct.

9            Q    Now, this next paragraph that starts, "A

10       response," is that confidential, those two sentences?

11            A    Since it's historical, I don't think that

12       would be confidential any longer.

13            Q    Okay.  And it says here in the second

14       sentence, "NRC has indicated that the LNP COLA review

15       schedule will be issued by January 30, 2009."  Do you

16       see that?

17            A    I see that.

18            Q    Okay.  When did you learn about that?

19            A    Well, again, based on when this report was

20       authored, the final version of it, and when it was

21       actually signed out, we had an ongoing dialogue with our

22       project manager for the NRC, and as we continued to ask

23       them when are we going to get our schedule, sometime in

24       December he clearly told us we're going to get it in

25       late January, and that's why this was written in here.

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1318

1            Q    So this information was learned in December?

2            A    Most likely.

3                 MR. REHWINKEL:  Madam Chairman, that's all the

4       questions I have from these four exhibits, but I do have

5       several others.  I don't know if -- I mean, I'm well

6       prepared to continue or we can take a break and get

7       another set of documents ready.

8                 ACTING CHAIRMAN EDGAR:  Okay.  Well, I'll tell

9       you, Rehwinkel, my mental thinking prior to you asking

10       was that we would go till about 4:15, but if this is a

11       more -- again, it's your cross.  If this is a more

12       appropriate break in the action, so to speak, then we

13       can do that now because I know I could use a stretch.

14                 MR. REHWINKEL:  Okay.  Thank you.

15                 ACTING CHAIRMAN EDGAR:  So, should we --

16                 MR. REHWINKEL:  I'll get another set of

17       documents.

18                 ACTING CHAIRMAN EDGAR:  And should we keep

19       these?  I mean, I'm never sure with the red documents --

20                 MR. REHWINKEL:  I'll tell you what, it would

21       probably be appropriate to keep them until we're done

22       with this section of the cross and then maybe we'll take

23       a break and decide how to proceed.

24                 ACTING CHAIRMAN EDGAR:  I'm getting a nod from

25       our staff as far as confidential document treatment.

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1319

1       Okay.  That's sounds good.

2                 Then, Mr. Rehwinkel, thank you for the

3       suggestion, and we are on break until 4:20.

4                 (The transcript continues in sequence with

5       Volume 8.)

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491

1320

1                       CERTIFICATE OF REPORTER

2       STATE OF FLORIDA )

3       COUNTY OF LEON   )

4             I, RAY D. CONVERY, do hereby certify that I was

5       authorized to and did stenographically report the

6       foregoing proceedings at the time and place herein

7       stated.

8             IT IS FURTHER CERTIFIED that the foregoing

9       transcript is a true record of my stenographic notes.

10             I FURTHER CERTIFY that I am not a relative,

11       employee, attorney, or counsel of any of the parties,

12       nor am I a relative or employee of any of the parties'

13       attorney or counsel connected with the action, nor am I

14       financially interested in the action.

15             DATED this 10th day of September, 2009, at

16       Tallahassee, Leon County, Florida.

17

18

19

20

21               _______________________________________

22                          RAY D. CONVERY

23

24

25

FOR THE RECORD REPORTING TALLAHASSEE FLORIDA 850.222.5491