1440

1                              BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

3                                           DOCKET NO. 090009-EI

4       In the Matter of:

5       NUCLEAR COST RECOVERY CLAUSE.

______________________________/

6

7                               VOLUME 9

8                        Pages 1440 through 1688

9              ELECTRONIC VERSIONS OF THIS TRANSCRIPT ARE

A CONVENIENCE COPY ONLY AND ARE NOT

10                THE OFFICIAL TRANSCRIPT OF THE HEARING.

THE .PDF VERSION INCLUDES PREFILED TESTIMONY.

11

12

PROCEEDINGS:           HEARING

13

COMMISSIONERS

14       PARTICIPATING:         CHAIRMAN MATTHEW M. CARTER, II

COMMISSIONER LISA POLAK EDGAR

15                              COMMISSIONER KATRINA J. McMURRIAN

COMMISSIONER NANCY ARGENZIANO

16                              COMMISSIONER NATHAN A. SKOP

17

DATE:                  Thursday, September 10, 2009

18

19       TIME:                  Commenced at 9:30 a.m.

20

PLACE:                 Betty Easley Conference Center

21                              Room 148

4075 Esplanade Way

22                              Tallahassee, Florida

23

REPORTED BY:           MARY ALLEN NEEL, RPR, FPR

24

25       PARTICIPATING:         (As heretofore stated.)

1441

1                               I N D E X

2                               WITNESSES

3

NAME                                                PAGE

4

WILLIAM R. JACOBS, JR., PH.D.

5

Direct Examination by Mr. Rehwinkel                 1443

6       Prefiled Direct Testimony Inserted                  1446

Cross-Examination by Mr. Davis                      1478

7       Cross-Examination by Mr. Moyle                      1481

Cross-Examination by Mr. Walls                      1484

8       Redirect Examination by Mr. Rehwinkel               1502

9       PETER A. BRADFORD

10       Direct Examination by Mr. Brew                      1512

Prefiled Direct Testimony Inserted                  1514

11       Cross-Examination by Ms. Triplett                   1543

12       MARK COOPER, PH.D.

13       Direct Examination by Mr. Davis                     1553

Prefiled Direct Testimony Inserted                  1554

14       Cross-Examination by Ms. Triplett                   1597

Redirect Examination by Mr. Davis                   1598

15

ARNOLD GUNDERSEN

16

Direct Examination by Mr. Davis                     1600

17       Prefiled Direct Testimony Inserted                  1602

Cross-Examination by Ms. Triplett                   1627

18

JEFFREY A. SMALL

19

Prefiled Direct Testimony Inserted                  1632

20

WILLIAM COSTON AND CARL VINSON

21

Direct Examination by Mr. Young                     1641

22       Prefiled Direct Testimony Inserted                  1643

Cross-Examination by Mr. Brew                       1650

23       Cross-Examination by Mr. Moyle                      1653

24

25

1442

1                         WITNESSES CONTINUED

2

NAME                                                PAGE

3       JON FRANKE

4       Direct Examination by Ms. Triplett                  1661

Prefiled Rebuttal Testimony Inserted                1663

5       Cross-Examination by Mr. Rehwinkel                  1685

6       CERTIFICATE OF REPORTER

7

8                               EXHIBITS

9       NUMBER                                       ID.  ADMTD.

10        99       (WRJ)PEF-1                        1474    1511

11       100       (WRJ)PEF-2                        1474    1511

12       101       (WRJ)PEF-3                        1474    1511

13       102       PAB-1                             1538    1552

14       103       PAB-2                             1538    1552

15       104       PAB-3                             1538    1552

16        46 - 60  MNC-1 through MNC-14              1593    1599

17        61 - 69  AG-1 through AG-8                 1623    1631

18       105       JAS-1                             1640    1640

19       106       JAS-2                             1640    1640

20       107       JAS-3                             1640    1640

21       108       CC-1                              1647    1660

22

23

24

25

1443

1                          P R O C E E D I N G S

2                 (Transcript continues in sequence from

3       Volume 8.)

4                 CHAIRMAN CARTER:  We are back on the record.

5       And when we last left, we had completed Progress with

6       their witnesses.  And now, Mr. Rehwinkel, good morning.

7       You're recognized sir.

8                 MR. REHWINKEL:  Good morning, Mr. Chairman and

9       Commissioners.  Public Counsel and the citizens of

10       Florida call Dr. William R. Jacobs to the stand.

11       Thereupon,

12                    WILLIAM R. JACOBS, JR., Ph.D.

13       was called as a witness on behalf of the Citizens of the

14       State of Florida and, having been first duly sworn, was

15       examined and testified as follows:

16                          DIRECT EXAMINATION

17       BY MR. REHWINKEL:

18            Q.   Dr. Jacobs, were you sworn yesterday?

19            A.   Yes, I was.

20            Q.   Could you state your name, address, employer,

21       and who you represent for the record, please?

22            A.   Yes.  My name is William R. Jacobs, Jr.  My

23       business address is 1850 Parkway Place, Marietta,

24       Georgia.  I'm vice president of GDS Associates, and I am

25       representing the Florida Office of Public Counsel in

1444

1       this matter.

2            Q.   Thank you.  Dr. Jacobs, did you cause to be

3       prepared prefiled direct testimony consisting of 28

4       pages in this docket?

5            A.   Yes, I did.

6            Q.   Do you have any changes or corrections to

7       make?

8            A.   Yes.  I have four changes to that testimony.

9                 On page 18, line 11, the last two words in

10       that sentence on line 11, "the project," should be

11       deleted and replaced with "completing the power plant."

12                 On page 21, line 9, between the word "not" and

13       "feasible," the word "be" should be inserted, so it

14       would read "why the project may not be feasible."

15                 On page 23, line 22, in the question there's a

16       capital I-N-T.  The "T" should be deleted so that the

17       word is "in."

18                 And the last one, on page 24, line 17, the

19       word "upgrade" should be changed to "uprate."

20                 That's all.

21            Q.   Thank you, Dr. Jacobs.  With those changes, if

22       I asked you the questions contained in your prefiled

23       direct testimony today, would your answers be the same?

24            A.   Yes, they would.

25                 MR. REHWINKEL:  Mr. Chairman, I would move

1445

1       that Dr. Jacobs' testimony, direct, prefiled direct

2       testimony, with the changes and corrections made, be

3       moved into the record, admitted into the record.

4                 CHAIRMAN CARTER:  The prefiled testimony of

5       the witness will be inserted into the record as though

6       read, with the necessary changes.

7                 MR. REHWINKEL:  Thank you.

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

1474

1       BY MR. REHWINKEL:

2            Q.   Dr. Jacobs, did you also cause to be prepared

3       three exhibits, WRJ-1 PEF -- (WRJ)PEF-1, (WRJ)PEF-2, and

4       (WRJ)PEF-3?

5            A.   Yes, I did.

6            Q.   Do you have any changes or corrections to make

7       to those exhibits?

8            A.   No, I do not.

9                 MR. REHWINKEL:  Mr. Chairman, I would ask that

10       these exhibits be given a number.

11                 CHAIRMAN CARTER:  They are shown in staff's

12       Comprehensive Exhibit List as 99, 100, and 101.  Is that

13       correct, staff, on page 14?

14                 MR. YOUNG:  Yes, sir.

15                 (Exhibits Number 99, 100, and 101 were

16       identified for the record.)

17                 CHAIRMAN CARTER:  You may proceed.

18                 MR. REHWINKEL:  Thank you, Mr. Chairman.

19       BY MR. REHWINKEL:

20            Q.   Mr. Jacobs, Dr. Jacobs, do you have a summary

21       of your testimony, mindful of the five-minute rule that

22       the Chairman reviewed yesterday?

23            A.   Yes, I do.

24            Q.   Could you give that at this time?

25            A.   Yes.  I would be glad to.

1475

1                 Good morning, Mr. Chairman and Commissioners.

2       I have identified several issues with PEF's LNP Crystal

3       River EPU projects that I will describe briefly here.

4                 Concerning the Levy nuclear project, I believe

5       that PEF's signing of the EPC agreement on 12/31/2008

6       was premature, given the lack of a limited work

7       authorization schedule and lack of committed joint

8       owners to the project.  The EPC contract, the schedule

9       in the EPC contract required that the LWA be issued by

10       September of 2010.

11                 When PEF signed the EPC contract, they did not

12       have a firm schedule for review and approval of the LWA

13       by the Nuclear Regulatory Commission, although the NRC

14       had indicated that it would issue the schedule by the

15       end of January 2009.  Three weeks after executing this

16       multi-billion-dollar contract, the NRC informed PEF that

17       they would not be able to issue the LWA on the schedule

18       that had been requested and they would not be able to

19       issue the LWA any sooner than issuing the full combined

20       license for the project.  So therefore, the LWA was

21       really not of value to the project after that point.

22                 Many of the key elements in the EPC contract

23       that PEF had just signed, including the schedule, costs,

24       milestones, and deliverables were now not achievable,

25       and PEF is now having to renegotiate a contract

1476

1       amendment to cover these changes.

2                 Prior to signing the EPC contract, the NRC had

3       indicated that it was unlikely that the requested

4       schedule could be met due to the complexity of the site

5       characteristics and the need for additional information.

6       I believe that PEF should not have signed the EPC

7       contract without assurance that the LWA would be

8       approved on the schedule that was needed for the

9       project.

10                 In addition, although in many PEF documents

11       the need for joint ownership was identified as critical

12       to the project's success, PEF signed the EPC contract

13       with no joint owners committed to the project, and in

14       fact, to this day have no committed joint owners.

15                 I have an issue with the -- a concern with the

16       lack of a feasibility study.  I don't believe that --

17       PEF did not provide an updated feasibility study as

18       required by the nuclear cost recovery rule.

19                 And finally, with the Crystal River 3 extended

20       power uprate, PEF's planning of the CR3 EPU project will

21       result in the majority of the money for the project,

22       hundreds of millions of dollars, being spent before PEF

23       knows affirmatively if the NRC will allow the reactor

24       power increase that would be needed to reach the full

25       level of the project and to achieve the full benefit of

1477

1       the EPC project.

2                 While many nuclear plants have been uprated,

3       this is the first Babcock & Wilcox plant to attempt an

4       uprate of this magnitude, and the NRC's approval of the

5       full power of this uprate is not assured at this point

6       in time.  The requested uprate requires solutions to

7       several technical challenges, and these have resulted in

8       the delayed submission of the license amendment request

9       to the NRC.

10                 That concludes my summary.

11                 CHAIRMAN CARTER:  Outstanding.

12                 MR. REHWINKEL:  Mr. Chairman, before I tender

13       Dr. Jacobs for cross-examination, I just would like to

14       make it -- remind the witness and make it clear that his

15       testimony contains confidential information in it, so

16       there is a public version and a confidential version.  A

17       significant amount of confidential information is in

18       Exhibit 101, and I just want to caution the witness that

19       any answer that he gives that requires him to refer to

20       the confidential information, that he take his time and

21       make sure that he does not disclose information.  And I

22       would also ask the other parties to be careful not to

23       seek to inadvertently solicit that.

24                 CHAIRMAN CARTER:  Thank you.

25                 MR. REHWINKEL:  So with that, Mr. Chairman, I

1478

1       tender Dr. Jacobs for cross-examination.

2                 CHAIRMAN CARTER:  Thank you, Mr. Rehwinkel.

3       And again, as we handle -- I think everybody here should

4       be abreast and aware of how we handle confidential

5       information and govern ourselves accordingly.  Thank you

6       for that information.

7                 Mr. Brew, you're recognized.

8                 MR. BREW:  Thank you.  I have no questions for

9       Dr. Jacobs.

10                 CHAIRMAN CARTER:  Mr. Davis.

11                 MR. DAVIS:  Thank you, Mr. Chair.  I just have

12       a few.

13                           CROSS-EXAMINATION

14       BY MR. DAVIS:

15            Q.   Dr. Jacobs, you have your testimony in front

16       of you?

17            A.   Yes, I do.

18            Q.   On pages 18, 19, and 20, I believe you discuss

19       the issue of feasibility.

20            A.   Yes.

21            Q.   And I would like to direct a few questions to

22       you about that.  Let me know when you're there.

23            A.   I'm on 18.

24            Q.   Now, there's some confidential information on

25       those pages, and I don't intend to ask you about that.

1479

1            A.   Yes.

2            Q.   So let me just ask the first question.  You

3       agree that an economic evaluation of the feasibility of

4       the Levy 1 and 2 projects should be performed as part of

5       a detailed analysis of long-term feasibility?

6            A.   Yes, definitely.

7            Q.   And do you have your deposition in front of

8       you?  You probably recall --

9            A.   I have it, but I also probably recall.

10            Q.   You recall that the company, Progress, did a

11       cost-effectiveness test for its need determination; is

12       that correct?

13            A.   Yes.

14            Q.   And at that time, the company used information

15       available about fuel forecasts, forecasts of carbon

16       dioxide costs, and other costs to justify the

17       cost-effectiveness of Levy 1 and 2?

18            A.   Yes.

19                 MR. WALLS:  Can I object to this line of

20       questioning?  This is friendly cross.  They have the

21       same position on this issue, and this is not an

22       impeachment line of questioning.

23                 CHAIRMAN CARTER:  To the objection, Mr. Davis.

24                 MR. DAVIS:  Yes.  This witness has not fully

25       addressed the cost-effectiveness test for feasibility,

1480

1       and there is a contention that Progress has made in its

2       rebuttal submittals that this witness did not address

3       cost-effectiveness, and I'm trying to pin him down on

4       what his testimony is on that, that's all.

5                 CHAIRMAN CARTER:  Ms. Helton, good morning.

6                 MS. HELTON:  Good morning, Mr. Chairman.  I'm

7       struggling with how this is adverse to SACE and whether

8       SACE could have presented its own testimony with respect

9       to this issue, so maybe if Mr. Davis could help me out.

10                 MR. DAVIS:  Yes, I'll explain that some more.

11       Thank you.  We did present testimony that supports our

12       position on this issue.  However, you should be aware

13       that Progress has claimed that this witness has

14       testified adversely to our position in his deposition,

15       and Progress has attached portions of Dr. Jacobs'

16       deposition to its rebuttal testimony with a statement

17       that misrepresents what Dr. Jacobs's opinions are on the

18       issues that I am cross-examining him on.  And so if the

19       Commission were to accept Progress's interpretation of

20       Dr. Jacobs' deposition testimony, that would definitely

21       be adverse to our position on cost-effectiveness.

22                 CHAIRMAN CARTER:  Mr. Walls.

23                 MR. WALLS:  Well, what they're trying to do is

24       have SACE rehabilitate the witness before he has been

25       impeached.

1481

1                 CHAIRMAN CARTER:  All right.  We're not --

2                 MR. DAVIS:  Mr. Chair --

3                 CHAIRMAN CARTER:  Hold it, hold it.

4       Sustained.  Move on.  We're not going to have any

5       friendly cross.  Move on.  That's the ruling.  Let's go.

6                 MR. DAVIS:  Thank you, Mr. Chair.  That's all

7       I have.

8                 CHAIRMAN CARTER:  Okay.  Mr. Moyle, you're

9       recognized.

10                 MR. MOYLE:  Thank you.

11                 MR. REHWINKEL:  Mr. Chairman, before we move

12       on, I just would like to address something Mr. Walls

13       said.  When he said, "They are trying to rehabilitate

14       Dr. Jacobs," there's no "they" involved.  I have not

15       solicited in any way any friendly cross of this witness.

16       I just want to state that for the record.

17                 CHAIRMAN CARTER:  I take you at your word,

18       Mr. Rehwinkel.

19                 MR. WALLS:  And let me apologize.  I did not

20       mean to include Mr. Rehwinkel in my objection.

21                 CHAIRMAN CARTER:  Duly noted.  Let's get

22       going, guys.  Mr. Moyle.

23                           CROSS-EXAMINATION

24       BY MR. MOYLE:

25            Q.   Sir, I have just a couple of points of

1482

1       clarification that I would like to ask you.  In your

2       summary, you talked about the NRC has not yet approved

3       the uprate project, and I'm unclear.  What is it that

4       you're asking that this Commission do with respect to

5       the fact that the NRC has not approved it, yet moneys

6       are being spent?  Are you suggesting it be at risk, or

7       what's the --

8            A.   Yes, I believe that money is at risk.  I've

9       suggested that the Commission take note of this.  And

10       when the final decision is identified by the NRC

11       regarding the level of power uprate, if it's less than

12       the full amount that the company has requested, then

13       they should investigate the prudence of those

14       expenditures.

15            Q.   And you talked about the EPC contract.  You're

16       of the view that it was prematurely executed?

17            A.   Yes.

18            Q.   That's a disputed issue.  To the extent that

19       the Commission were to adopt your view that it was

20       prematurely executed, what are you asking that -- be

21       done about that, that the Commission do?

22                 MR. WALLS:  I'm going to object again to

23       friendly cross.  It's in his testimony.

24                 CHAIRMAN CARTER:  Mr. Moyle, to the objection.

25                 MR. MOYLE:  Well, it was an effort to try to

1483

1       get clarification on that point.

2                 CHAIRMAN CARTER:  Ms. Helton.

3                 MS. HELTON:  If you'll give me one minute,

4       Mr. Chairman, I want to read the positions in the

5       Prehearing Order.  I have, though, for the record, told

6       the parties that, you know, a short line of

7       clarification questions would be appropriate and would

8       not be considered prohibited friendly cross.  But let me

9       look at the positions, please, and see if --

10                 CHAIRMAN CARTER:  Okay.  Take a minute.

11                 MS. HELTON:  -- I think that clarification is

12       necessary.

13                 CHAIRMAN CARTER:  Take a minute.  We've been

14       doing well so far, so let's don't mess it up on the last

15       day.

16                 MR. MOYLE:  Hopefully last day.

17                 CHAIRMAN CARTER:  Oh, it's the last day, or

18       maybe the last night.

19                 MS. HELTON:  Mr. Chairman, I'm looking at

20       Issue 23, which is on page 26 of the Prehearing Order,

21       and I see Public Counsel's position listed there.  And

22       when you turn to the next page, FIPUG's position is,

23       "Concurs with OPC."  So I'm struggling how clarification

24       is necessary here.

25                 CHAIRMAN CARTER:  Objection sustained.  Move

1484

1       on.

2                 MR. MOYLE:  That's all I have.

3                 CHAIRMAN CARTER:  Thank you.  Staff.

4                 MR. YOUNG:  No questions.

5                 CHAIRMAN CARTER:  Whoa.  Sorry.  Mr. Walls,

6       you're recognized for cross-examination.

7                 MR. WALLS:  Thank you.

8                           CROSS-EXAMINATION

9       BY MR. WALLS:

10            Q.   Good morning, Mr. Jacobs.

11            A.   Good morning.

12            Q.   Dr. Jacobs, you have no opinion that any cost

13       incurred by Progress Energy Florida on the CR3 uprate

14       for 2006, 2007, and 2008 is imprudent; correct?

15            A.   That's correct.

16            Q.   And as well, for the CR3 uprate project, you

17       do not identify any specific cost projections for 2009

18       and 2010 that you challenge as unreasonable; correct?

19            A.   That's correct.

20            Q.   And would you also agree with me that your

21       testimony includes no opinion that Progress Energy

22       Florida's Levy nuclear project costs for the years 2006,

23       2007, and 2008 are imprudent?

24            A.   I agree.  That's correct.

25            Q.   And you also do not question the

1485

1       reasonableness of any specific 2009 and 2010 costs that

2       the company identified for the Levy nuclear project;

3       correct?

4            A.   That's correct.

5            Q.   And you would agree with me that your opinion,

6       after reviewing PEF's project management control -- I'm

7       sorry, project management contract and oversight

8       controls, is that you found nothing unreasonable or

9       imprudent in those controls; correct?

10            A.   That's correct.

11            Q.   And you would also agree with me that nowhere

12       in your testimony do you express an opinion that

13       Progress Energy Florida's accounting and cost oversight

14       controls were unreasonable or imprudent; correct?

15            A.   That's correct.

16            Q.   And with respect to the Levy nuclear project,

17       it's fair to say that your opinions are, one, that PEF

18       was unreasonable in executing the engineering,

19       procurement and construction contract when it did on

20       December 31, 2008; and two, PEF's analysis of the

21       feasibility of completing the nuclear power plant is

22       inadequate; correct?

23            A.   That's correct.

24            Q.   Starting first with your opinions on the EPC

25       contract, Dr. Jacobs, did you review the EPC before you

1486

1       filed your direct testimony and before your deposition

2       was taken in this proceeding?

3            A.   No, I did not review the Levy EPC.  I had

4       reviewed two other very similar EPC contracts, and based

5       on that and what I had read of the Levy EPC contract, I

6       believed they were similar.  Subsequently, I did review

7       the Levy EPC contract, and that confirmed my belief that

8       they are in fact quite similar.

9            Q.   But at the time you filed your direct

10       testimony and at the time I took your deposition, you

11       had not read the EPC contract for the Levy nuclear

12       project; correct?

13            A.   That's correct.

14            Q.   Have you ever negotiated an engineering,

15       procurement and construction contract for a nuclear

16       power plant?

17            A.   I'm sorry.  Could you --

18            Q.   Have you ever negotiated an engineering,

19       procurement and construction contract for a nuclear

20       power plant?

21            A.   No, I have not.  Not many people have done

22       that.

23            Q.   Have you ever managed the application process

24       for a new nuclear power plant at the Nuclear Regulatory

25       Commission?

1487

1            A.   No, I have not.

2            Q.   And you admit that your opinion is that the

3       company -- your opinion is not that the company should

4       not build the Levy nuclear power plant; correct?

5            A.   That's correct.

6            Q.   And you would agree with me that the decision

7       by the company to sign the EPC agreement was a decision

8       to proceed forward with construction of the nuclear

9       power plant; correct?

10            A.   That's correct.

11            Q.   And prior to filing your direct testimony, you

12       were aware that the company had expressed to you in

13       discovery in this case and through documents that there

14       were benefits to signing the EPC by December 31, 2008;

15       correct?

16            A.   That's correct.

17            Q.   And prior to filing your direct testimony, you

18       will admit you did not do any analysis to weigh the

19       benefits of signing the EPC on December 31, 2008,

20       against any perceived risks to determine that signing at

21       that point in time with those risks was not beneficial;

22       correct?

23            A.   I'm sorry.  Could you repeat that?  It was a

24       little lengthy.

25            Q.   Prior to filing your direct testimony, you did

1488

1       not do any analysis to weigh the benefits of signing the

2       EPC by December 31, 2008, against any perceived risks to

3       determine that signing at that point in time with those

4       risks was beneficial; correct?

5            A.   Well, I did not do a quantitative analysis,

6       but I did reach the conclusion that the risks -- that

7       the benefits did not outweigh the risks of signing at

8       that point.

9            Q.   And you did that based on no quantitative

10       analysis; correct?

11            A.   That's correct.

12            Q.   You would agree --

13            A.   I'm not sure.  I'm sorry.  I'm not sure.  A

14       lot of those, it would be very difficult to quantify.

15       It's more of a qualitative judgment.

16            Q.   Would you agree with me that at the time of

17       filing your direct testimony and your deposition that it

18       would have been reasonable for Progress to sign the EPC

19       agreement on December 31, 2008, if it had the review

20       schedule with the LWA and joint owners signed up?

21            A.   If it had the review schedule that met the

22       needs of the EPC contract, yes.

23            Q.   Now, let's turn to your argument about the

24       reasonableness of executing the EPC on December 31.  I

25       believe you identified two reasons in your summary, the

1489

1       lack of LWA and lack of joint owners; correct?

2            A.   Yes.

3            Q.   Now, you reviewed the risk management process

4       that the company had; correct?

5            A.   Yes.

6            Q.   And that was part of the project management

7       documents and processes that you reviewed and found to

8       be reasonable and prudent; correct?

9            A.   That's correct.

10            Q.   And the risk management process included a

11       risk matrix that the company had; right?

12            A.   Yes.

13            Q.   And in that risk matrix, there was a licensing

14       issue with the NRC.  The submittal of the COLA was a

15       risk that was identified; correct?

16            A.   That's correct.

17            Q.   And you understand that when Progress

18       submitted its COLA application to the NRC, it included a

19       limited work authorization; correct?

20            A.   That's correct.

21            Q.   And at the time, they identified that COLA as

22       a risk on its risk matrix; correct?

23            A.   Yes.

24            Q.   And once you identify an item on a risk

25       matrix, you have come up with a risk mitigation or

1490

1       action plan; correct?

2            A.   That's correct.

3            Q.   And you agree that the action plan or

4       mitigation strategy that Progress Energy Florida

5       developed for that risk was what most utilities would

6       do; correct?

7            A.   Yes, I do.  Their actions to mitigate the COLA

8       risk and the LWA risk I thought were reasonable and

9       appropriate.

10            Q.   And you would agree with me that Progress

11       Energy Florida implemented its action plan and risk

12       mitigation strategy with respect to the COLA

13       application, including the LWA; correct?

14            A.   Yes.  But I want to clarify that it would not

15       include signing the EPC contract without the LWA

16       approval.

17            Q.   Well, you don't have any opinion in your

18       testimony that Progress did not do something that it

19       should have done with respect to that risk mitigation

20       strategy; correct?

21            A.   Well, what they did that they should not have

22       done was sign the EPC contract.

23            Q.   Do you have your deposition testimony with

24       you?

25            A.   Yes.

1491

1            Q.   Could you turn to page 48, lines 23 to 25, and

2       page 49, lines 1 to 3?

3            A.   Okay.

4            Q.   Where I ask you the following question, and

5       you gave the following answer.

6                 Question:  "I didn't see anywhere in your

7       opinion -- in your testimony where you had an opinion

8       that Progress did not do something that it should have

9       done with respect to that risk mitigation strategy; is

10       that correct?"

11                 Answer:  "That's correct."

12            A.   That's correct.  It did not do something it

13       should have done, I agree with that.  It did something

14       it should not have done.

15            Q.   Now, would you agree with me that after

16       submitting the COLA application to the NRC, at that

17       point in time, the utility did not have control over the

18       project schedule, rather, the NRC had control over the

19       project schedule; correct?

20            A.   I would agree the NRC had control, but the

21       company certainly was in the position to influence that

22       schedule.  For example, they had to respond to requests

23       for information from the NRC, and their ability to

24       respond sufficiently and in a timely manner to those

25       requests for information would have an influence on the

1492

1       COLA proceeding.

2            Q.   Dr. Jacobs, turning back to joint ownership

3       for a second, you would agree with me that it's not

4       unreasonable for Progress Energy Florida to sign the EPC

5       first and then joint ownership agreements; correct?

6            A.   It's not unreasonable, but I believe that

7       throughout the many PEF documents, it was identified

8       that joint ownership was critical to the project.  And

9       in my view, they should have had joint owners committed

10       before signing, not necessarily signed on the dotted

11       line, but committed to the project.

12            Q.   I understand your view, but you would agree

13       that it was not unreasonable for them to sign the EPC

14       first and then sign up joint owners in a separate

15       agreement; correct?

16            A.   I agree.

17            Q.   Now, would you also agree with me that the

18       decision for joint owners to sign up to a joint

19       ownership agreement is ultimately the decision of those

20       joint owners, and Progress does not have control over

21       those joint owners to make them sign a joint ownership

22       agreement?

23            A.   That's true.  They can certainly influence the

24       joint owners in that regard, but they don't have -- it's

25       ultimately the decision of the joint owners.

1493

1            Q.   And by the way, Progress also had a risk

2       mitigation strategy for dealing with joint ownership

3       that involved continued communication and providing

4       information to them, to work with them to convince them

5       to join the project; correct?

6            A.   That's correct.

7            Q.   And that was Progress's -- I'm sorry.  And

8       Progress in fact undertook and engaged in that risk

9       mitigation strategy, didn't it?

10            A.   Yes.

11            Q.   And you do not have an opinion in your

12       testimony that Progress Energy Florida did not do

13       something that it should have done with respect to that

14       risk mitigation strategy for joint owners; correct?

15            A.   That's correct.

16            Q.   Now, I want to turn to your second opinion

17       regarding the feasibility analysis that PEF provided for

18       the Levy project.

19            A.   Yes.

20            Q.   And I'm sure you're familiar with the

21       cumulative present value revenue requirements

22       cost-effectiveness analysis that PEF provided for the

23       Levy units in the need case; correct?

24            A.   Yes.

25            Q.   And you agree with me that you cannot show me

1494

1       in the rule where it tells the company that a CPVRR

2       analysis is a test that it's supposed to undertake;

3       correct?

4            A.   That's true, not specifically.

5            Q.   And you will admit that if in 2010 the load

6       forecast or the gas forecast or the emission forecast

7       changes such that the CPVRR analysis showed that the LNP

8       would not prove cost-effective that year, the Commission

9       should not make a determination that the project should

10       not go forward based just on that analysis; correct?

11            A.   Yes, I would agree with that.  These projects

12       are long-term projects.  They're planned to run 60

13       years.

14                 You know, need determination is a very

15       difficult thing to do.  There's not one formula that you

16       can put numbers in and the answer comes out.  There are

17       many, many factors that have to be considered.  And the

18       fact that on one specific snapshot in time, due to a

19       variety of factors, the CPVRR calculation indicates that

20       the project is not economic at that time, that in and of

21       itself would not be a reason to not go forward with the

22       project.  You would need to look at all -- the whole

23       spectrum of factors involved in the project.

24            Q.   And just to confirm, you wouldn't think that a

25       one-year change in any of those conditions or factors is

1495

1       sufficient to consider stopping the project; right?

2            A.   That's true.  But it is one factor, you know,

3       among many factors that would need to be considered.

4            Q.   But you would agree, as you said, this is a

5       long-term project?

6            A.   Yes, sir.

7            Q.   For 60 years or more?

8            A.   That's correct.

9            Q.   And no one builds a nuclear power plant for

10       what's going to happen even in the next five years;

11       correct?

12            A.   That's correct.

13            Q.   And in fact, you would agree that the time

14       period you should look at for determining whether it's

15       feasible to build this project is over the time period

16       the project is going to operate, 60 years or more;

17       correct?

18            A.   That's correct.

19            Q.   And so you can't look at year to year about

20       changes in gas forecasts, for example, and decide not to

21       build a nuclear power plant; correct?

22            A.   Not that in and of itself, but I think those

23       factors need to be considered in -- you know, under the

24       nuclear cost recovery rule, the company is receiving a

25       significant benefit and recouping their costs ahead of

1496

1       time.  And as part of that bargain, there's also a

2       responsibility and obligation to show that the project

3       continues to be feasible and the most economic project

4       for the customers, given the long time frame and all the

5       various factors involved.

6            Q.   So you agree with me you wouldn't build any

7       long-term nuclear power plant on that basis, would you?

8            A.   On what basis?

9            Q.   On the basis of that one year change in the

10       CPVRR.

11            A.   That's right.  I agree.

12            Q.   I want to turn to your last issue with respect

13       to the CR3 uprate project, Dr. Jacobs.

14            A.   Okay.

15            Q.   And as I understand, your concern is that PEF

16       is spending money on the balance of plant portion of the

17       uprate work before PEF receives the LAR for the project;

18       correct?

19            A.   That's right.  I think from an engineering and

20       operation perspective, the sequence of events is

21       probably reasonable that they undertook, but from a risk

22       management perspective, it results in PEF spending a

23       significant fraction of the money for this project

24       before knowing that the desired outcome will be

25       achievable.

1497

1            Q.   And your concern is that the uprate project

2       may not be cost-effective unless PEF receives the LAR

3       for the project; correct?

4            A.   That's correct.

5            Q.   And with respect to that opinion, you admit

6       that you do not have an economic analysis to support

7       your opinion other than what you've called a "back of an

8       envelope" calculation that someone else did for you;

9       correct?

10            A.   That's correct, but I still hold to that

11       opinion that $400 million for a 40 megawatt increase

12       would not be economic.

13            Q.   Are you finished?

14            A.   Yes, I am.

15            Q.   Okay.  You admit that no matter whether or not

16       PEF gets the LAR, the uprate will lead to 28 megawatts

17       of increased nuclear energy; correct?

18            A.   Well, including the MUR, I think it's

19       40 megawatts, but that's correct.

20            Q.   And your specific concern regarding the LAR

21       for the project is what you call a possibility that PEF

22       will not be granted a license for the full additional

23       power for the uprate; correct?

24            A.   That's correct.  This is the first Babcock &

25       Wilcox reactor that has been attempted to be uprated to

1498

1       this magnitude.  I think there are some technical

2       challenges involved, and there is a possibility that

3       they will not be granted the full uprate that's

4       requested.

5            Q.   You're not aware of any NRC disapprovals of

6       any uprate project, are you?

7            A.   No.  But again, this is the first B&W plant to

8       be uprated to this level.

9            Q.   And there were 104 approved uprate projects by

10       the NRC; correct?

11            A.   Correct, and none of them B&W plants to this

12       level.

13                 MR. WALLS:  I have no further questions.

14                 CHAIRMAN CARTER:  Thank you.  Staff.

15                 MR. YOUNG:  No questions.

16                 CHAIRMAN CARTER:  Commissioners.  Commissioner

17       McMurrian, you're recognized.

18                 COMMISSIONER McMURRIAN:  Dr. Jacobs.

19                 THE WITNESS:  Yes, ma'am.

20                 COMMISSIONER McMURRIAN:  I just wanted to get

21       a little clarification.  With your statements about how

22       Progress Energy has prematurely signed the EPC contract,

23       I want to clarify.  What is your recommendation to us to

24       do about that if we were to agree with you that they

25       signed prematurely?

1499

1                 THE WITNESS:  Well, I think generally -- I

2       don't know exactly.  I do have a recommendation in my

3       testimony, but the general recommendation would be to

4       identify any additional costs that result from this

5       premature signing, be they additional carrying costs for

6       procurement of equipment earlier than needed or

7       additional costs that result from the renegotiation of

8       the contract.  I think these should be withheld from the

9       recovery.

10                 COMMISSIONER McMURRIAN:  And that's in this

11       case, or are you really talking about more in the

12       future?

13                 THE WITNESS:  I think it would be in the

14       future.  We don't know at this time exactly what the

15       ramifications of this will be, so it would be for a

16       future case.

17                 COMMISSIONER McMURRIAN:  Okay.  Thank you.

18                 THE WITNESS:  Yes, ma'am.

19                 CHAIRMAN CARTER:  Commissioners, anything

20       further from the bench?

21                 COMMISSIONER SKOP:  Just one.

22                 CHAIRMAN CARTER:  Commissioner Skop, you're

23       recognized.

24                 COMMISSIONER SKOP:  Thank you, Mr. Chairman.

25       Good morning, Mr. Jacobs, or Dr. Jacobs.

1500

1                 THE WITNESS:  Good morning.

2                 COMMISSIONER SKOP:  Just a quick follow-up

3       question to, I believe, a question you were previously

4       asked with respect to your experience evaluating EPC

5       contracts.

6                 THE WITNESS:  Yes.

7                 COMMISSIONER SKOP:  Have you ever participated

8       or been involved in a nuclear contract or any contract

9       of this type of magnitude?

10                 THE WITNESS:  Well, there are not many

11       contracts of this type of magnitude.  I have been

12       involved on the two other AP-1000 contracts.

13                 I testified for the Georgia Public Service

14       Commission staff regarding the Vogtle contract, and I am

15       -- I have been identified as the independent

16       construction monitor for the Georgia Public Service

17       Commission, so I'll be monitoring that project

18       throughout its life.

19                 I also work for the South Carolina Office

20       of -- regulatory staff in the evaluation of that

21       contract for the Summer project.  So I've been deeply

22       involved in those two projects.

23                 COMMISSIONER SKOP:  And with respect to that

24       last response about your testimony before the Georgia

25       Public Service Commission, and also in South Carolina,

1501

1       have either of those commissions or respective utilities

2       entered into an EPC contract at this time?

3                 THE WITNESS:  Yes, both of them.

4                 COMMISSIONER SKOP:  Okay.  And in your

5       testimony or consulting to those respective commissions,

6       did you ever in your testimony indicate that those

7       respective decisions by those utilities were imprudent

8       or improper?

9                 THE WITNESS:  No, I did not.

10                 I would like to point out that there's one

11       difference there, and I think it puts a slightly higher

12       burden in Florida.  In both Georgia and South Carolina,

13       there is a cap on the amount that can be spent on the

14       project that the utility will be able to recover, so

15       it -- the liability to the ratepayer is capped at a

16       certain amount.  In Florida, as I understand it, there

17       is no cap, so I think that adds an additional burden to

18       the Florida utilities to continue to demonstrate the

19       ongoing feasibility of the projects.

20                 COMMISSIONER SKOP:  Thank you.

21                 CHAIRMAN CARTER:  Thank you, Commissioners.

22       Anything further from the bench?

23                 Redirect, Mr. Rehwinkel.

24                 MR. REHWINKEL:  Just a few.  Thank you,

25       Mr. Chairman.

1502

1                         REDIRECT EXAMINATION

2       BY MR. REHWINKEL:

3            Q.   Dr. Jacobs, Mr. Walls asked you about whether

4       you had ever negotiated an EPC.  Do you remember that

5       question?

6            A.   Yes.  I think he said for a nuclear power

7       plant or --

8            Q.   Exactly.

9            A.   -- some specific . . .

10            Q.   And I think your response was that very few

11       people have done that?

12            A.   That's correct.

13            Q.   Do you believe that you have to have

14       negotiated a nuclear power plant EPC in order to offer

15       an opinion or an expert opinion about one?

16            A.   No, I don't.  And in fact, to elaborate a

17       little bit on this, I have negotiated EPC contracts for

18       other power generating projects, and I'm on the

19       management committee for a 600 megawatt coal project

20       that's being constructed under an EPC contract, so I'm

21       very familiar with how those contracts operate.

22            Q.   Would anyone be able to offer an expert

23       opinion before a regulatory body if the requirement was

24       that you had to have negotiated a nuclear power plant

25       EPC?

1503

1            A.   Well, very few people, and I think they would

2       have a significant conflict to offer such opinions.

3            Q.   And why would that be?

4            A.   Because the only people with that experience

5       would be the utility employees that negotiated this type

6       of contract.

7            Q.   You were asked some questions about

8       feasibility analysis.

9            A.   Yes.

10            Q.   And I think you agreed that you would not make

11       a decision to build a nuclear power plant based on a

12       one-year snapshot of a feasibility analysis; is that

13       correct?

14            A.   That's correct.

15            Q.   Are there, though, circumstances where changes

16       in costs or circumstances could occur that would make a

17       utility take a closer look at a feasibility analysis?

18            A.   Oh, certainly.  There are many things that

19       could change.  The cost, the projected cost of the

20       project could change dramatically.  The schedule, if the

21       schedule shifted, that could cause it.

22                 One thing that came to my mind would be --

23       most of these nuclear -- probably all of them are

24       dependent on carbon, the costs for carbon in their

25       analysis.  And if something happened such that it became

1504

1       clear that there would be no additional carbon tax on

2       carbon-generating plant, that would have a dramatic

3       impact on the economics.  So there are many factors that

4       could happen that would cause you to take a close look

5       at the feasibility.

6            Q.   In order to know whether factors influence the

7       outcome of your feasibility analysis, wouldn't you have

8       to do one first?

9            A.   Yes, sir.

10            Q.   Did Progress Energy Florida do one?

11            A.   No, they did not.

12            Q.   Why didn't they?  Well, let me ask you this.

13       Could they have done one?

14            A.   Well, it would have been difficult, because

15       the cost of the project is unknown at this point in

16       time, so I think that may be one reason why they didn't

17       do one.

18            Q.   You were asked a question about a "back of the

19       envelope" calculation relating to the CR3 EPU.  Do you

20       recall that question?

21            A.   Yes.

22            Q.   Is that an analysis that you did?

23            A.   It was done by Mr. Jim McGaughy, one of my

24       colleagues.

25            Q.   Did you ask him to do it?

1505

1            A.   No, I did not.

2            Q.   Did you rely on it in any way in your

3       testimony?

4            A.   No, I did not.

5            Q.   With respect to the states of South Carolina

6       and Georgia Public Service Commission testimonies, I

7       think you testified that you did not make any

8       recommendation about prudence or reasonableness of the

9       EPC contracts in those states; is that correct?

10            A.   Well, actually, I think we found that they

11       were reasonable.

12            Q.   Okay.  Were there any analogous situations,

13       such as a two-month -- I mean 20- to 36-month schedule

14       shift at issue in those cases?

15            A.   No, there were not.

16                 MR. REHWINKEL:  That's all the questions I

17       have, Mr. Chair.

18                 COMMISSIONER EDGAR:  Mr. Chairman.

19                 CHAIRMAN CARTER:  Commissioner Edgar.

20                 COMMISSIONER EDGAR:  Thank you.  Just to

21       follow up so that -- I think I understand what I just

22       heard.  I believe I heard you say in response to

23       questions that Progress did not do a feasibility

24       analysis and that they would not have been able to do

25       one because costs were unknown.  Is that --

1506

1                 THE WITNESS:  Yes.  Yes, ma'am.

2                 COMMISSIONER EDGAR:  Okay.  How are you

3       defining feasibility analysis in that context?

4                 THE WITNESS:  Well, in that context, I think

5       Mr. Rehwinkel was referring to a present value revenue

6       requirements type of analysis.

7                 COMMISSIONER EDGAR:  And if, from your

8       comments, they would not have been able to do that

9       feasibility analysis or present value revenue analysis,

10       what, in your opinion, would be, under the circumstances

11       available to them, the appropriate analysis to do?

12                 THE WITNESS:  They could have filed a

13       sensitivity type study with a bound of potential capital

14       costs to sort of demonstrate at what levels of capital

15       costs the project would continue to be economic.  That

16       would have been one possibility.

17                 COMMISSIONER EDGAR:  And is it your testimony

18       that at the point that the decision was made to pursue

19       this project, that that was an incorrect or imprudent

20       decision?

21                 THE WITNESS:  I'm sorry.  At what point?

22       During the need determination?  Is that --

23                 COMMISSIONER EDGAR:  Well, start there.

24                 THE WITNESS:  Well, I -- no.  I think they did

25       an appropriate analysis during the need -- although I

1507

1       was not involved in that docket, I believe their

2       analysis was appropriate.

3                 COMMISSIONER EDGAR:  Okay.  And I'm not trying

4       to mischaracterize, so please make sure that I don't.

5       Is it your testimony now that with the information that

6       is available to the company, and perhaps now during this

7       proceeding to us as well, that the project should not go

8       forward?

9                 THE WITNESS:  No, that's not my testimony at

10       all.  My testimony was that they did not file a detailed

11       feasibility study as required by the rule, and one

12       reason being that due to the delay in the contract --

13       the delay in the project, the contract is being

14       renegotiated at this time with Westinghouse, and so the

15       final price and cost of the project is unknown at this

16       point in time.

17                 COMMISSIONER EDGAR:  I just feel like I'm

18       getting in a circular -- and maybe it's just me, because

19       we're at day whatever --

20                 THE WITNESS:  I'm sorry.

21                 COMMISSIONER EDGAR:  No, no, no, no.  Don't

22       you be.

23                 So is it that your testimony, part of it is

24       that they didn't file a feasibility analysis as

25       required, but yet they couldn't because the costs are

1508

1       unknown?

2                 THE WITNESS:  Yes.

3                 COMMISSIONER EDGAR:  Okay.  Thank you.

4                 MR. REHWINKEL:  Mr. Chairman, may I ask --

5                 CHAIRMAN CARTER:  Hang on.  I'll come back to

6       you.  Commissioner Skop.

7                 COMMISSIONER SKOP:  Thank you, Mr. Chairman.

8                 Dr. Jacobs, I just want to follow up on a

9       question that you were asked by Mr. Rehwinkel on

10       redirect.  In your response, you discussed about your

11       work on reviewing the prudency of a coal plant, a large

12       coal plant; is that correct?

13                 THE WITNESS:  Not the prudency.  I'm on the

14       management committee for the project, so I'm involved in

15       the dealings with the EPC contractor, negotiating change

16       orders, schedule delays, and that type of thing.

17                 COMMISSIONER SKOP:  Okay.  Well, let's just

18       briefly discuss, or I would like to clarify the EPC

19       contract for a coal plant versus a nuclear plant.  Would

20       you agree, generally speaking, there's a substantial

21       difference between those two types of contracts?

22                 THE WITNESS:  Yes.

23                 COMMISSIONER SKOP:  Okay.  You would also

24       agree that with respect to a nuclear contract versus a

25       coal contract that there would be a substantial

1509

1       difference between availability of long lead materials

2       for a nuclear plant?

3                 THE WITNESS:  Yes.

4                 COMMISSIONER SKOP:  Would you also agree that

5       between a coal plant and a nuclear plant, there would

6       also be a substantial difference between the

7       availability of ultraheavy forgings and queue

8       limitations associated with those?

9                 THE WITNESS:  Yes.  Those aren't required for

10       a coal plant.

11                 COMMISSIONER SKOP:  And also, the difference

12       between a coal plant and a nuclear plant, would you also

13       agree that with respect to the overall length of the

14       respective construction cycles, that the nuclear plant

15       would be much longer?

16                 THE WITNESS:  The actual construction cycle is

17       not significantly different between a coal plant and a

18       nuclear plant.  The lengthy part of the nuclear plant is

19       the licensing part of the project.

20                 COMMISSIONER SKOP:  Okay.  And with respect to

21       the licensing part of the program, I think that in a

22       response that you mentioned -- talking about the 20- to

23       24-month delay and how the other respective states, the

24       Georgia Public Service Commission and South Carolina

25       Public Commission have not been faced with such a delay

1510

1       for their respective utilities.  If the NRC continues to

2       have problems with its ability to review submittals in a

3       timely manner, in your professional opinion, would it be

4       reasonably expected that additional delays could occur

5       for those states who have not yet experienced them?

6                 THE WITNESS:  It's possible.  There's a fair

7       amount of margin in the schedule, so it would take a

8       significant delay to impact the commercial operation

9       dates of these units.  I would be very surprised if it

10       were on the magnitude of the 20- to 36-month delay that

11       we're anticipating with Levy, but there could be some.

12                 COMMISSIONER SKOP:  Okay.  Thank you.

13                 CHAIRMAN CARTER:  Anything further from the

14       bench before I go back to Mr. Rehwinkel?

15                 Mr. Rehwinkel.

16       BY MR. REHWINKEL:

17            Q.   Yes.  Just redirect, for clarification.  I

18       would ask Dr. Jacobs to turn to page 28 of your

19       testimony.  And I ask this just to try to help with

20       clarity.  You're not asking -- and look at item 3 there

21       on lines 5 through 8.  You are not asking the Commission

22       through your testimony to take action with regard to the

23       project based on the deficiencies in the feasibility

24       analysis that you found; is that correct?

25            A.   That's correct, yes.

1511

1            Q.   Your purpose here is to ask the Commission to

2       require Progress to do the feasibility once they have

3       gotten the project costs from the renegotiation; is that

4       right?

5            A.   That's correct.  I should have made that more

6       clear.  Yes.

7                 MR. REHWINKEL:  Thank you.

8                 CHAIRMAN CARTER:  Okay.  Anything further?

9       Thank you, Mr. Rehwinkel, for that.

10                 Exhibits.

11                 MR. REHWINKEL:  I would move 99 through 101.

12                 CHAIRMAN CARTER:  Are there any objections?

13       Without objection, show it done.  Thank you.

14                 (Exhibits Number 99, 100, and 101 were

15       admitted into the record.)

16                 MR. REHWINKEL:  May Dr. Jacobs be excused?

17                 CHAIRMAN CARTER:  Yes.  Thank you very much.

18       You're excused.

19                 THE WITNESS:  Thank you.

20                 CHAIRMAN CARTER:  Have a great day.

21                 I think, Mr. Brew, you're up next.  Is that

22       correct?

23                 MR. BREW:  Yes, Mr. Chairman.  We call Peter

24       Bradford.

25                 CHAIRMAN CARTER:  Just one second, Mr. Brew.

1512

1                 Okay.  You may proceed.

2       Thereupon,

3                          PETER A. BRADFORD

4       was called as a witness on behalf of White Springs

5       Agricultural Chemicals and, having been first duly

6       sworn, was examined and testified as follows:

7                          DIRECT EXAMINATION

8       BY MR. BREW:

9            Q.   Good morning, Mr. Bradford.

10            A.   Good morning, Mr. Brew.

11            Q.   Could you please state your name and address

12       for the record?

13            A.   My name is Peter A. Bradford.  I live -- my

14       address is P.O. Box 497, Peru, Vermont.

15            Q.   And who are you appearing for or on behalf of

16       in this proceeding?

17            A.   I'm appearing on behalf of PCS Phosphate,

18       White Springs.

19            Q.   And did you prepare in this matter testimony

20       consisting of 24 pages of questions and answers?

21            A.   Yes.

22            Q.   And do you have any corrections to that

23       testimony?

24            A.   No, I do not.

25            Q.   So if I were to ask you the questions

1513

1       contained in that testimony, would your answers be the

2       same today?

3            A.   They would.

4                 MR. BREW:  Mr. Chairman, I ask that the

5       prefiled direct testimony of Peter Bradford be

6       incorporated into the record.

7                 CHAIRMAN CARTER:  The prefiled testimony of

8       the witness will be inserted into the record as though

9       read.

10                 MR. BREW:  Thank you.

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

1538

1       BY MR. BREW:

2            Q.   Mr. Bradford, did you also cause to be filed

3       three exhibits that accompanied your prefiled testimony?

4            A.   Yes.

5                 MR. BREW:  Your Honor, I note that they are

6       labeled PAB-1 through 3, and on the Composite Exhibit

7       List, they're labeled or numbered 102 through 104.

8                 CHAIRMAN CARTER:  That's on page 16.  Thank

9       you, Mr. Brew.

10                 (Exhibits Number 102, 103, and 104 were

11       identified for the record.)

12       BY MR. BREW:

13            Q.   Mr. Bradford, do you have a summary of your

14       testimony?

15            A.   I do.

16                 CHAIRMAN CARTER:  Mr. Brew, has Mr. Bradford

17       been sworn already?

18       BY MR. BREW:

19            Q.   Excuse me.  Were you sworn yesterday?

20            A.   I was.

21                 CHAIRMAN CARTER:  Okay.  Good.  Thank you.

22       BY MR. BREW:

23            Q.   Do you have a summary of your testimony?

24            A.   Yes.

25            Q.   Would you please give it now?

1539

1            A.   I want to emphasize the following points from

2       my testimony:

3                 First, the concept of feasibility as used in

4       the Commission's cost recovery rule must encompass

5       economic feasibility.  The Commission is, after all,

6       fundamentally an economic regulatory agency, and more

7       reactors have been canceled because they became

8       economically unfeasible than for all other causes

9       combined.  Moreover, builders of nuclear power reactors

10       in regions where cost recovery occurs through power

11       markets routinely recognize that projects that are not

12       economically feasible cannot be built.

13                 Economic feasibility means that the plant must

14       be expected, using current and realistic assumptions, to

15       produce power that will yield lower electric bills for

16       PEC territory than any reasonable alternative, with

17       allowance for the public policies in Florida and the

18       nation.  The present PEF filing makes no detailed

19       feasibility showing, and therefore cannot be a basis for

20       cost recovery.

21                 Second, the changes in the circumstances

22       confronting the Levy project over the past 12 months are

23       no ordinary year-to-year fluctuations.  No other year in

24       my 30 years of experience with the electric industry has

25       seen such a combination of demand drop, economic

1540

1       slowdown, capital market contraction, natural gas price

2       decline, and potential changes in national energy

3       legislation.  In addition, the project is delayed a

4       minimum of 20 months.

5                 These changes are fundamental, and many were

6       in prospect when the EPC was signed in late December.

7       They have altered the structure of long-term electricity

8       and energy markets in Florida and elsewhere.  If they

9       were ordinary fluctuations, a reasonable likelihood

10       would exist that the next year or two would erase them,

11       restoring the PEF 2008 view of Florida energy markets.

12       No such likelihood exists.

13                 In the face of such changes, somewhere between

14       one-quarter and one-third of the U.S. renaissance fleet,

15       including most of the AP-1000s, were canceled or

16       deferred for several years during the first half of

17       2009, largely because the proposed plants were no longer

18       economically feasible.

19                 To protect Florida customers, I urge the

20       Commission to take the following steps:

21                 The Commission should confine the scope of any

22       prudence determination in this proceeding to costs

23       actually incurred in 2008.

24                 The Commission should conduct separate

25       prudence hearings as to the EPC issues discussed in my

1541

1       testimony, hearings at which the Commission staff and

2       other parties have a full opportunity to examine the

3       entire range of prudence issues and their consequences.

4                 To this end, the Commission should limit or

5       suspend all future Levy cost recovery pending receipt

6       and public review of detailed, updated project

7       reasonableness and feasibility analyses that contain

8       updated total project costs and schedule evaluations and

9       a detailed cost-effectiveness demonstration.

10                 The Commission should state that PEF's filings

11       must establish the economic reasonableness and

12       feasibility of each Levy unit individually.

13                 The Commission should admonish PEF to the

14       effect that its filings in this proceeding do not meet

15       the standards of thoroughness expected of a utility

16       undertaking a project with multi-billion-dollar impacts

17       on Florida customers.

18                 The Commission should indicate that continued

19       failure of PEF to live up to the standards to be

20       expected of an entity undertaking construction of such a

21       project will result in the appointment of a special

22       master empowered to take all necessary measures to

23       assure PEF customers of the prudence and reasonableness

24       of PEF decision-making with regard to each Levy unit.

25                 Finally, to reassert a point I made in the

1542

1       need proceeding, the Florida Commission faces a crucial

2       need to avoid commitments to costs and rate impacts that

3       are open-ended and unlimited.  Investors in other

4       utilities have proven unwilling to shoulder such

5       exposure.  This does not mean that the Commission should

6       somehow cancel the Levy units.  Rather, by setting and

7       enforcing clear limits on the amounts that can be

8       charged to customers, the Commission will be benefiting

9       both the customers and the utility investors as well as

10       the Florida economy.

11                 With such limits in place, the interests of

12       Progress Energy shareholders will be properly aligned

13       with those of its customers.  The company could then

14       decide for itself whether the Levy units are in the best

15       interest of its service territory and the company

16       itself.

17                 MR. BREW:  Mr. Chairman, I tender the witness

18       for examination.

19                 CHAIRMAN CARTER:  Thank you.  Great summary,

20       great summary.

21                 Mr. Davis.

22                 MR. DAVIS:  No questions.

23                 CHAIRMAN CARTER:  I was going to ask

24       Mr. Rehwinkel, but I assume he has no cross.

25                 Mr. Moyle.

1543

1                 MR. MOYLE:  No questions, Mr. Chairman.

2                 CHAIRMAN CARTER:  Mr. Walls.  Oh,

3       Ms. Triplett.

4                 MS. TRIPLETT:  Thank you.

5                           CROSS-EXAMINATION

6       BY MS. TRIPLETT:

7            Q.   Good morning, Mr. Bradford.

8            A.   Good morning.

9            Q.   You spent about 25 hours in preparing your

10       testimony in this proceeding; is that right?

11            A.   I -- yes.

12            Q.   Thank you.  And in your testimony, you did not

13       challenge the prudence of any costs with respect to the

14       CR3 uprate project; is that right?

15            A.   That's right.

16            Q.   You also did not challenge the prudence of

17       PEF's accounting and cost controls oversight -- cost

18       oversight controls for the CR3 uprate project; is that

19       right?

20            A.   That's correct.

21            Q.   And you further did not challenge the project

22       management, contracting, or cost oversight controls for

23       the CR3 uprate project; correct?

24            A.   Correct.

25            Q.   And turning to the Levy project, you did not

1544

1       challenge the prudence of PEF's costs for the Levy

2       project for 2006 through 2008; correct?

3            A.   Correct.

4            Q.   And you're also not challenging any of PEF's

5       project management policies and procedures that apply to

6       the Levy project; correct?

7                 Do you need me to repeat the question?

8            A.   No.  I'm weighing -- let me just ask you to be

9       clear what you mean by policies.

10            Q.   Well, let me ask you again.  You are not

11       challenging any of PEF's project management policies and

12       procedures that apply to the Levy project, just the

13       policies and procedures themselves?

14            A.   Let me answer it this way.  I am challenging

15       the wisdom of the decision to sign the EPC.  If within

16       your question you would consider that a management

17       policy, then I'm challenging it.

18            Q.   Do you remember -- do you have your deposition

19       transcript with you?

20            A.   I do.

21            Q.   Could you just turn to page 15 of that

22       transcript?  And on line 5, I asked you the same

23       question there.  I asked you, "Are you challenging any

24       of the company's project management policies and

25       procedures that apply to the Levy project?"  And you

1545

1       answered, "No."  Is that answer -- was that answer

2       correct?

3            A.   You have correctly read my deposition, yes.

4            Q.   And you were under sworn -- you were sworn

5       under oath when you gave your deposition testimony; is

6       that right?

7            A.   That's true.  And I'll stand, though, by my

8       answer today, that if by the concept of project

9       management policy you include the actual decision to

10       sign the EPC, my testimony does challenge that.

11            Q.   Do you have your direct testimony?

12            A.   Yes.

13            Q.   Can you turn to page 16?

14                 Are you there?

15            A.   I'm there.

16            Q.   And looking at this page, we can see the three

17       things that you were challenging in this case regarding

18       the Levy project; is that right?

19            A.   Yes.

20            Q.   And the first thing you challenge there are

21       PEF's actions regarding the limited work authorization

22       or the LWA that PEF requested for the Levy project;

23       right?

24            A.   Yes.

25            Q.   And your opinion with regard to the LWA is

1546

1       that there is a, quote, substantial likelihood that PEF

2       should not have gone forward with the Levy EPC contract

3       until it had the LWA in hand; is that right?

4            A.   I'm sorry.  Are you quoting from my testimony?

5            Q.   I'm quoting from your deposition.  Do you want

6       me to point you to that?

7            A.   I think you should, because my recollection is

8       that the sentence is a little longer than that and that

9       it refers not only to having it in hand, but also having

10       a more definite schedule as to when it could be

11       expected.

12            Q.   Can you turn to page 18 of your deposition

13       transcript?

14            A.   Yes.

15            Q.   And on line 8, I asked you, "What do you opine

16       that PEF should have done differently regarding the

17       LWA?"

18            A.   Right.

19            Q.   And you answer, "What I'm opining is that

20       there is a substantial likelihood that Progress should

21       not have gone forward with the EPC until it either had

22       the LWA in hand or a much higher degree of assurance

23       than turns out to be the case that it would have had the

24       LWA in hand."  Do you see that?

25            A.   Yes.  That's correct.

1547

1            Q.   When I asked you what you meant by the term

2       "substantial likelihood," you told me that your opinion

3       is that there is a better than 50-50 chance that PEF

4       should not have signed the EPC without the LWA in hand;

5       is that right?

6            A.   Or a much higher degree of assurance, yes.

7            Q.   And with respect to your opinions in this

8       regard, you do not allege that there will certainly be

9       any negative financial impact to PEF's customers

10       stemming from PEF's actions regarding the LWA; is that

11       correct?

12            A.   Let's see.  Are you quoting my deposition

13       again, and if so, can you point me to the line?

14            Q.   Certainly.  Page 19, and I'm on line 18.

15            A.   The last line, yes.  And what I said was that

16       it's a possibility, but not a certainty.

17            Q.   So your testimony is that it's possible, but

18       not a certainty, that there would be any negative

19       financial impact to PEF's customers?

20            A.   That's correct.

21            Q.   And the next issue you raise on page 6 of your

22       prefiled testimony is PEF's actions regarding the

23       engineering, procurement and construction contract for

24       the Levy project; is that correct?

25            A.   Yes.

1548

1            Q.   And your opinion in this regard is that there

2       is a substantial likelihood that PEF should have waited

3       until it had the LWA for Levy before signing?

4                 MR. BREW:  Excuse me, Mr. Chairman.  It's a

5       little confusing when she shifts between the deposition

6       and the testimony.  If she's referring to a source,

7       could I ask that she indicate what she's working off of?

8                 CHAIRMAN CARTER:  Well, she can ask her

9       question, and if he's not sure, he can -- like he said

10       before, "Are you at my deposition."  He can just say

11       that.  He'll be able to have her point it to him before

12       he answers.

13                 MR. BREW:  Thank you.

14                 CHAIRMAN CARTER:  You may proceed.

15       BY MS. TRIPLETT:

16            Q.   Do you need me to repeat the question?

17            A.   Yes, would you?

18            Q.   Sure.  I think we just talked about this.

19       Your opinion is that there is a substantial likelihood

20       that PEF should have waited until it had the LWA for

21       Levy before signing the EPC?

22            A.   And you're taking the phrase "substantial

23       likelihood" from my deposition?

24            Q.   Yes, sir.

25            A.   Okay.  And --

1549

1            Q.   Page 25.

2            A.   I'll give you the same answer, then.  I used

3       the phrase "substantial likelihood" in the context of a

4       sentence that said not only had the LWA in hand, but

5       also allowed for a much higher degree of assurance than

6       turns out to be the case that it would have the LWA in

7       hand.

8            Q.   And again, your definition of "substantial

9       likelihood" is greater than a 50-50 chance?

10            A.   Yes.

11            Q.   And using your words from your deposition, you

12       would have to speculate as to whether or not PEF's

13       actions regarding the EPC contract have caused PEF's

14       customers any financial harm; is that right?

15            A.   Yes.

16            Q.   And the final issue you raise on page 16 of

17       your direct testimony is with respect to PEF's actions

18       regarding the joint ownership for the Levy units; is

19       that right?

20            A.   Yes.

21            Q.   And your opinion for this last issue is

22       that --

23            A.   Actually, Ms. Triplett, if I could, let me

24       just be clear, though.  When you say the final issue,

25       all three of those issues are in the context of the

1550

1       sentence that comes ahead of them, which says, "At a

2       minimum, the Commission should investigate the

3       following."  So I don't need to confine the

4       investigation to those three issues.

5            Q.   Understood.  So back to the third issue on

6       page 16 of your testimony, your opinion for this one is

7       that there is a reasonable likelihood that PEF should

8       have obtained joint owners before going forward with the

9       determination of need and the COLA for Levy; is that

10       right?

11            A.   Yes.

12            Q.   And unlike your earlier two opinions where you

13       say there is a substantial likelihood of something

14       happening, for this opinion you used the different term

15       of "reasonable likelihood"; correct?

16            A.   In my deposition I did, yes.

17            Q.   And when I asked you in your deposition what

18       the term "reasonable likelihood" means, you told me it

19       means something significantly more than a slight

20       possibility, but somewhat less than certainty; is that

21       correct?

22            A.   That certainly sounds right, but why don't you

23       point me to the lines and I'll verify it.

24            Q.   Sure.  Starting on page 28, lines 18 to 19,

25       and going forward to the next page, 29.

1551

1            A.   Yes.

2            Q.   So your opinion regarding joint ownership for

3       the Levy project is that there is significantly more

4       than a slight possibility, but somewhat less than a

5       certainty, that PEF should have acquired joint ownership

6       for the Levy project prior to filing a need case or a

7       COLA application; is that right?

8            A.   Yes.

9            Q.   And my final line of questioning, sir, with

10       respect to a feasibility analysis for a nuclear plant

11       such as the Levy project, you agree with me that there

12       is more than one way to do an economic feasibility

13       analysis, and that there is no doubt several different

14       methodologies that could be deemed reasonable; right?

15            A.   I agree with you.  It does sound as though

16       you're quoting from my deposition again.  Can you give

17       me the lines?

18            Q.   Sure.  Page 59, lines 4 through 9.

19            A.   Yes, you've quoted it accurately.

20            Q.   And in determining what kind of feasibility

21       analysis to perform and submit to a regulator, you agree

22       with me that it is up to the utility as to how to do

23       that; correct?

24            A.   Certainly in the first instance.  I mean, they

25       must ultimately comply with the relevant regulatory

1552

1       requirements, but, yes.

2                 MS. TRIPLETT:  Thank you, sir.  No further

3       questions.

4                 CHAIRMAN CARTER:  Thank you.  Staff.

5                 MR. YOUNG:  No questions.

6                 CHAIRMAN CARTER:  Commissioners, anything from

7       the bench?

8                 Redirect.

9                 MR. BREW:  None, Mr. Chairman.

10                 CHAIRMAN CARTER:  Exhibits.  You're showing

11       102, 103, and 104.

12                 MR. BREW:  Yes.  I would like to move 102

13       through 104.

14                 CHAIRMAN CARTER:  Are there any objections?

15       Without objection, show it done.

16                 (Exhibits Number 102, 103, and 104 were

17       admitted into the record.)

18                 CHAIRMAN CARTER:  Thank you, Mr. Brew.  Thank

19       you, Mr. Bradford.  I think you can be excused.  Nothing

20       further for this witness; right?  Thank you very kindly.

21                 Mr. Davis, you're recognized?

22                 MR. DAVIS:  Thank you, Mr. Chair.  SACE calls

23       Dr. Mark Cooper to the stand.

24                 CHAIRMAN CARTER:  You may proceed.

25       Thereupon,

1553

1                          MARK COOPER, Ph.D.

2       was called as a witness on behalf of Southern Alliance

3       for Clean Energy and, having been first duly sworn, was

4       examined and testified as follows:

5                          DIRECT EXAMINATION

6       BY MR. DAVIS:

7            Q.   Good morning, Dr. Cooper.  Can you state your

8       name and your business address, please?

9            A.   My name is Dr. Mark Cooper.  I reside at 504

10       Highgate Terrace, Silver Spring, Maryland.

11            Q.   And have you filed prefiled testimony in this

12       proceeding consisting of 39 pages?

13            A.   Yes, I have.

14            Q.   If I were to ask you the same questions as

15       posed in your prefiled testimony today, would you

16       respond in the same fashion?

17            A.   Yes, I would.

18            Q.   Are there any corrections to your testimony?

19            A.   No.

20                 MR. DAVIS:  Mr. Chair, we tender the testimony

21       of Dr. Cooper.

22                 CHAIRMAN CARTER:  The prefiled testimony of

23       the witness will be inserted into the record as though

24       read.

25

1593

1       BY MR. DAVIS:

2            Q.   And, Dr. Cooper, have you also attached

3       exhibits to your prefiled testimony, which are in this

4       particular case numbered 46 through 69?

5            A.   Yes, I have.

6                 CHAIRMAN CARTER:  It would be 46 through 60.

7                 MR. DAVIS:  I'm sorry.  I jumped ahead.

8                 CHAIRMAN CARTER:  Forty-six through 60.

9                 MR. DAVIS:  Thank you.

10                 CHAIRMAN CARTER:  That's fine.  No problem.

11       You may proceed.

12                 (Exhibits Number 46 through 60 were identified

13       for the record.)

14       BY MR. DAVIS:

15            Q.   Have you prepared a summary of your testimony,

16       Dr. Cooper?

17            A.   Yes, I have.

18            Q.   Would you present that, please.

19            A.   Mr. Chairman and members of the Commission,

20       since the certificates of need were issued for the

21       proposed reactors, there have been dramatic changes in

22       four areas that undermine the long-term feasibility of

23       Progress's reactors.  Demand projections have declined

24       sharply, and federal policy-makers are contemplating

25       substantial reductions in demand as a part of climate

1594

1       policy.  The costs of reactors have risen and are still

2       largely unknown.  The cost of natural gas has plummeted

3       and is uncertain.  The nature and scope of carbon

4       mitigation and compliance cost has yet to be defined.

5       As a result, the financial risk of these plants has

6       grown dramatically.

7                 Moody's now considers the decision to build

8       nuclear reactors a, quote, bet the farm decision.  The

9       last time utilities made such huge bets on nuclear

10       reactors, half of them went bad, and consumers were left

11       holding the bag for huge cost overruns and abandoned and

12       canceled plants.

13                 Because of the dramatic shift in load growth

14       and the other factors I mentioned, there are much less

15       costly, much less risky options available in the near

16       term to meet the need for electricity and buy time for

17       greater certainty before a commitment is made to place

18       the burden of major nuclear construction costs on

19       ratepayers.  My testimony shows that not only cost, but

20       also uncertainty and diversity, all argue for pursuing

21       alternatives rather than nuclear reactors at this time.

22                 The economic analysis presented by Progress

23       does not fully reflect the economic reality that the

24       Levy reactors face today.  The economic recession and

25       the unfolding transformation of economic activity have

1595

1       pushed any possible need for the new reactors out by a

2       half a decade or more, and that is without any major

3       change in federal policy promoting efficiency.  In fact,

4       however, federal requirement policy, which was central

5       to the original justification for the reactors, has

6       changed direction dramatically, increasing the

7       likelihood of requirements for efficiency and

8       renewables, which will delay any need for the reactors

9       even longer.  If the full target of a 20 percent

10       reduction in demand for renewable generation is achieved

11       -- for non-renewable generation is achieved, the peak

12       load projection for 2017 made in the 2008 ten-year plan

13       would not be reached until two decades later.  The

14       pending legislation also will decrease the cost of

15       carbon mitigation, further undermining the economics of

16       the reactor.

17                 The price of natural gas has tumbled and

18       separated from the price of oil.  Our estimates of

19       natural gas resources have increased dramatically,

20       further undermining the long-term economic feasibility

21       of the reactors.  The natural gas prices used in the

22       recent analyses reflect a bubble in natural gas which

23       has burst and is not likely to return.

24                 There's also growing concern about the

25       execution risk of building a new generation of nuclear

1596

1       reactors.  In contrast, confidence in efficiency has

2       grown.

3                 These dramatic changes in the decision-making

4       environment mean that the analysis presented by Progress

5       is centered on a set of assumptions that do not reflect

6       the current or likely future reality in which the

7       reactors would proceed.  If they had a realistic set of

8       scenarios, the preponderance of the evidence would be

9       negative, and they would not pursue these plants in a

10       logical management analysis.

11                 This does not mean the Commission should stop

12       evaluating the nuclear option.  On the contrary, in my

13       testimony I stress that prudent action requires constant

14       evaluation and re-evaluation.  And therefore, I

15       recommend key steps to ensure that the Commission does

16       in fact have a full and comprehensive record before it.

17       These include ensuring the most up-to-date assumptions

18       about critical economic parameters, factoring excess

19       capacity into the analysis so that the costs of carrying

20       excess capacity are fully recognized in the economic

21       analysis, integrating resource planning into the

22       feasibility analysis, and pinning down the cost of

23       nuclear with binding cost estimates.  Only with a full

24       and comprehensive clean slate review can consumers in

25       Florida be protected from the costs of making decisions

1597

1       that are infeasible in the long term.

2                 Thank you.

3                 CHAIRMAN CARTER:  Thank you.

4                 MR. DAVIS:  We tender Dr. Cooper.

5                 CHAIRMAN CARTER:  Thank you.  Mr. Brew.

6                 MR. BREW:  Thank you.  I have no questions for

7       Dr. Cooper.

8                 CHAIRMAN CARTER:  Mr. Moyle.

9                 MR. MOYLE:  No questions.

10                 CHAIRMAN CARTER:  Ms. Triplett or Mr. Walls.

11       Ms. Triplett, you're recognized.

12                 MS. TRIPLETT:  Thank you.

13                           CROSS-EXAMINATION

14       BY MS. TRIPLETT:

15            Q.   Good morning, Dr. Cooper.

16            A.   Good morning.

17            Q.   Could you please remind me as to the

18       educational degrees that you hold?

19            A.   I hold a bachelor's in English, a master's in

20       sociology, and a Ph.D. in sociology.

21                 MS. TRIPLETT:  Thank you, sir.  No further

22       questions.

23                 CHAIRMAN CARTER:  Thank you.  Staff?

24                 MR. YOUNG:  No questions.

25                 CHAIRMAN CARTER:  Commissioners, anything from

1598

1       the bench?  Redirect.

2                         REDIRECT EXAMINATION

3       BY MR. DAVIS:

4            Q.   Dr. Cooper, what is your experience in

5       analyzing the factors that you've described in your

6       testimony?

7            A.   I have been analyzing -- doing economic

8       analysis and analyzing energy and communications policy

9       from an economic point of view for about 30 years.  The

10       first utility case in which I participated 27 years ago

11       was in fact a case involving a nuclear reactor.

12            Q.   And do you perform research and publish in the

13       area of analysis of policy and issues such as we're

14       dealing with in this --

15            A.   Yes.  I have published both chapters and

16       articles in law reviews and trade publications dealing

17       with energy analysis, electricity analysis.

18                 And in fact, the analysis of economics as we

19       know it has in recent years been scrambled by behavioral

20       economics, which is a very large discipline.  Numerous

21       Nobel Laureates have been named in behavioral economics

22       in the past decade.  And so the traditional approach to

23       economics, which is very formal in the U.S. discipline

24       in economics departments, has in fact been expanded, and

25       I frankly find that the sociology training, which sort

1599

1       of stands between the psychology of behavioral economics

2       and the structural analysis of the traditional economics

3       profession, provides a really solid basis for looking at

4       these complex factors.  And as I show in my testimony,

5       it's not only economics, but uncertainty that really

6       determines prudent decisions and reasonable decisions.

7            Q.   Have you recently performed a study and

8       published a record about the economics of the new

9       nuclear power plants?

10            A.   Yes, I have.  Much of the analysis I presented

11       in my testimony was based on that, and a copy of that

12       study was provided in response to a discovery request.

13                 MR. DAVIS:  Thank you, Doctor.

14                 CHAIRMAN CARTER:  Thank you very kindly.

15                 Exhibits 46 through 60.  Are there any

16       objections?  Without objection, show it done.

17                 (Exhibits Number 46 through 60 were admitted

18       into the record.)

19                 CHAIRMAN CARTER:  Thank you, Dr. Cooper.  You

20       are excused, and have a great day.

21                 MR. DAVIS:  SACE would next call Arnold

22       Gunderson.

23       Thereupon,

24                           ARNOLD GUNDERSEN

25       was called as a witness on behalf of Southern Alliance

1600

1       for Clean Energy and, having been first duly sworn, was

2       examined and testified as follows:

3                          DIRECT EXAMINATION

4       BY MR. DAVIS:

5            Q.   Good morning, Mr. Gundersen.

6            A.   Good morning.

7            Q.   Can you state your name and your business

8       address for the record, please.

9            A.   My name is Arnold Gundersen, spelled with an

10       E.  I'm chief engineer with Fairewinds Associates, 376

11       Appletree Point Road, in Burlington, Vermont.

12            Q.   Mr. Gunderson, have you filed prefiled

13       testimony in this matter?

14            A.   Yes, I have.

15            Q.   And have you also prepared exhibits and

16       attached those to your testimony?

17            A.   Yes, I have.

18            Q.   If I were to ask you the same questions as

19       posed in your prefiled testimony today, would your

20       answers be the same?

21            A.   There was a typo on page 10, line 12.  I wrote

22       "coal."  I should have put "fossil".  With that

23       exception, the answer is yes.

24                 MR. DAVIS:  Okay.  We tender his testimony for

25       the record.

1601

1                 CHAIRMAN CARTER:  The prefiled testimony of

2       the witness will be inserted into the record as though

3       read.

4

5

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

1622

1

2

3

4

5

6

7                        THIS PAGE IS LEFT BLANK

8                        FOR PAGINATION PURPOSES

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

1623

1       BY MR. DAVIS:

2            Q.   And do you have exhibits that are numbered 61

3       through 69 that have been attached to your prefiled

4       testimony?

5            A.   Yes, I do.

6                 CHAIRMAN CARTER:  For the record,

7       Commissioners, that's on page 16.

8                 (Exhibits Number 61 through 69 were identified

9       for the record.)

10                 MR. DAVIS:  At this point, we tender the

11       witness for cross.

12                 CHAIRMAN CARTER:  Do you want to do a summary?

13                 MR. DAVIS:  I'm sorry.

14                 CHAIRMAN CARTER:  That's fine.  That's okay.

15       BY MR. DAVIS:

16            Q.   Mr. Gunderson, do you have a summary that you

17       would like to provide to the Commission?

18            A.   Yes, I do.

19            Q.   Please provide it.

20            A.   Good morning, Mr. Chairman and Commissioners.

21       In my 35 years as a nuclear engineer and a senior vice

22       president of a nuclear licensee, including work at 70

23       reactors nationwide during the last industry boom, I

24       never saw a reactor completed on schedule or on budget,

25       yet the whole industry was positive at that time about

1624

1       schedules and budgets, just like Progress is today.

2                 On Tuesday I addressed four problems impacting

3       the schedule, and thus the cost of Turkey Point 6 and 7.

4       All of these problem areas, licensing, equipment delays,

5       personnel shortages, and the complications involved in

6       the construction, are present on Progress's Levy site,

7       and in most cases, they're more advanced.  The reason

8       that is is that Levy started sooner than Progress and

9       has already had to face the reality of an overly

10       aggressive schedule.

11                 I would like to focus on just the distinctions

12       between Levy and Progress as they relate to the Levy

13       site.  One key difference is that the Levy reactors were

14       planned to enter operation sooner, in 2006 -- in 2016,

15       rather, instead of 2018 for the Turkey Point units.

16       That had a greater impact on Levy's licensing schedule.

17       I stated that the licensing process is strewn with

18       obstacles, which I described in my testimony.  It's

19       obvious that the process did not -- it's obvious that

20       Progress did not allow for significant licensing delays

21       that have occurred, and I predicted further licensing

22       delays would occur.

23                  Since I wrote that opinion seven weeks ago,

24       I've been proven correct.  On July 28, the NRC notified

25       Progress that the COL would be delayed because of

1625

1       geology at the Levy site, and then on August 28th, the

2       NRC notified all the AP-1000 applicants that the AP-1000

3       applications would be delayed further because of

4       containment sump design problems.

5                 I am not clairvoyant.  These and other

6       licensing delays were foreseeable long before I wrote my

7       opinion.  While both Levy and Turkey Point are what are

8       called first wave nuclear plants, Levy is at the

9       beginning of the first wave, while Turkey Point is

10       further behind on the wave.

11                 Additionally, I note in the report that

12       further licensing delays may occur at the back end.

13       This Part 52 license is designed to push the burden to

14       the front.  However, there are opportunities for

15       intervention at the end, and this is a process that has

16       not been tested.  I also note that the AP-1000 design

17       has never been constructed and has never been operated,

18       so that there are risks for schedule change in the

19       future.

20                 Now, there's two types of schedule change that

21       I want to touch on.  The first type is what I would call

22       sliding, and that would be taking a five-year

23       construction schedule and pushing it back by 20 or 36

24       months, and that seems to be what we're talking about so

25       far.  But what I'm talking about in addition to sliding

1626

1       the schedule is elongating the schedule.  And by that,

2       the construction delays I'm talking about, the equipment

3       availability delays I'm concerned about, and the

4       shortage of skilled personnel are not going to slide the

5       schedule.  They're going to elongate the schedule.

6                 So the four types of problems that I have

7       acknowledged have been and will continue to be

8       foreseeable.  PEF has been forced to accept the schedule

9       slide of at least 20 months because its original

10       schedule was overly aggressive.  I believe, based on my

11       experience, that schedule elongation from construction

12       delays is also inevitable and is not now being

13       addressed.

14                 The Public Service Commission has not been

15       provided with a feasible Levy plant schedule, and hence

16       there's no reliable cost estimate, and hence the

17       long-term feasibility of Levy has not yet been

18       demonstrated.

19                 Thank you.

20                 MR. DAVIS:  We tender the witness for

21       cross-examination.

22                 CHAIRMAN CARTER:  Thank you.  Mr. Rehwinkel.

23       Mr. Moyle.

24                 MR. MOYLE:  No questions.

25                 CHAIRMAN CARTER:  Ms. Triplett or Mr. Walls.

1627

1       Ms. Triplett, you're recognized.

2                 MS. TRIPLETT:  Thank you.

3                           CROSS-EXAMINATION

4            Q.   Good morning, Ms. Gunderson.

5            A.   Hi.  Nice to meet you in person.

6            Q.   You too.  With respect to your testimony in

7       this case, you did not look at the Crystal River 3

8       uprate project at all; correct?

9            A.   That's correct.

10            Q.   And logically, then, you did not provide any

11       opinions on the CR3 uprate project in this matter;

12       correct?

13            A.   That's correct.

14            Q.   And with respect to the Levy project, your

15       testimony does not address the Levy costs for 2006

16       through 2008; is that correct?

17            A.   My testimony addressed the long-term schedule

18       and the long-term ramifications on cost, but no specific

19       costs in 2006 or 2007, that's correct.

20            Q.   Well, let me just make sure.  For 2006, 2007,

21       and 2008 actual Levy costs, your testimony does not

22       provide any opinions regarding those costs; correct?

23            A.   That's correct.  I only looked at the schedule

24       and long-term effect on cost.

25            Q.   Nor does your testimony address the actual or

1628

1       projected costs for 2009 and 2010 for the Levy project;

2       correct?

3            A.   I only looked at schedule slippages, and that

4       then trickles down into cost.

5            Q.   And your testimony further does not offer any

6       opinion on PEF's accounting and cost oversight controls

7       for the Levy project; correct?

8            A.   I had only looked at the schedule, and I did

9       not look at the accounting oversight controls; that's

10       correct.

11            Q.   Just a few more questions.  Are you familiar

12       with a column that ran in The Vermont Tiger on July 3,

13       2008, called "Emerson Lynn on Politics:  Politics vs.

14       Truth"?

15            A.   I remember an article in The Vermont Tiger

16       blog, but if you could refresh my memory, I'm -- I'm

17       pretty sure I remember it.

18                 MR. DAVIS:  I'm going to object to the

19       question.  I don't even know what this is, Mr. Chair,

20       but if it's going to be used for impeachment, she hasn't

21       lain the proper foundation.

22                 CHAIRMAN CARTER:  Okay.  To the objection,

23       Ms. Triplett.

24                 MS. TRIPLETT:  I'm trying to lay a foundation.

25       He hasn't let me ask any questions about it.  And he

1629

1       just testified that he's generally aware, and then he

2       asked me to refresh his memory, which my next question

3       may in fact do.

4                 CHAIRMAN CARTER:  Okay.  Let's tread lightly,

5       though.

6                 MS. TRIPLETT:  I only have a couple of

7       questions on it.

8                 CHAIRMAN CARTER:  Okay.

9       BY MS. TRIPLETT:

10            Q.   Mr. Gundersen, are you aware in that column

11       that the author spoke about you and stated that your

12       opposition --

13                 MR. DAVIS:  Objection.

14            Q.   -- to nuclear power is well documented?

15                 MR. DAVIS:  Objection.  I believe that's

16       hearsay.  I believe that it is not proper impeachment

17       because this witness is not being asked -- I've got a

18       prior statement that he made that he's being impeached

19       with.  Both of those are reasons why that question is

20       objectionable and should be stricken from the record.

21                 CHAIRMAN CARTER:  Ms. Helton.  Briefly,

22       Ms. Triplett, very briefly, to the objection.

23                 MS. TRIPLETT:  I believe that this goes to the

24       potential bias of the witness, and I think that it's a

25       proper question for an expert who's providing expert

1630

1       testimony.

2                 MR. DAVIS:  You can't impeach a witness --

3                 CHAIRMAN CARTER:  Whoa, whoa, whoa.  Hold it.

4       Let's don't get crazy on me.

5                 MS. DAVIS:  I'm sorry, Your Honor.

6                 CHAIRMAN CARTER:  I heard both of you.  Ms.

7       Helton.

8                 MS. HELTON:  This seems to me to be reliance

9       on a hearsay statement and is not -- it doesn't go to

10       the testimony of the witness, so I believe it's

11       improper.

12                 CHAIRMAN CARTER:  Okay.  Objection sustained.

13       Move on.

14                 MR. DAVIS:  Thank you, Mr. Chair.

15       BY MS. TRIPLETT:

16            Q.   Well, let me ask you this, Mr. Gundersen.

17       Have you ever made the statement that you would rather

18       see windmills on ridge lines and solar panels reflecting

19       across all Vermont roofs than risk the environmental

20       purity of our state to the silent menace of radioactive

21       contamination?

22            A.   After being an expert witness on the Vermont

23       Yankee uprate and on the Vermont Yankee fuel case and

24       reading 200,000 pages of documentation, I came to the

25       conclusion that for Vermont Yankee, not nuclear power in

1631

1       general, but Vermont Yankee is not safe and should not

2       be allowed to run after 2012.

3                 MS. TRIPLETT:  Thank you.  No further

4       questions.

5                 CHAIRMAN CARTER:  Staff.

6                 MR. YOUNG:  No questions.

7                 CHAIRMAN CARTER:  Commissioners.

8                 Redirect?

9                 MR. DAVIS:  No.

10                 CHAIRMAN CARTER:  Okay.  Exhibits.  Sixty-one

11       through 69; is that right, Mr. Davis?

12                 MR. DAVIS:  Yes.  SACE would move those into

13       evidence.

14                 CHAIRMAN CARTER:  Are there any objections?

15       Without objection, show it done.

16                 (Exhibits Number 61 through 69 were admitted

17       into the record.)

18                 CHAIRMAN CARTER:  Anything further for this

19       witness?

20                 Thank you very kindly, Mr. Gundersen.  Have a

21       great day.

22                 Staff, you're recognized.

23                 MR. YOUNG:  Mr. Chairman, per the agreement

24       from all the parties, Jeffrey A. Small's testimony -- at

25       this time, we ask that Jeffrey A. Small's testimony and

1632

1       exhibits be inserted into the record.

2                 CHAIRMAN CARTER:  Are there any objections?

3       Without objection, show it done.  The prefiled testimony

4       of the witness will be inserted into the record as

5       though read.

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

1640

1                 MR. YOUNG:  And that's Exhibit Numbers 105,

2       106, and 107, on page 17 of the Comprehensive Exhibit

3       List.

4                 CHAIRMAN CARTER:  Are there any objections to

5       Exhibits 105, 106, and 107?  Without objection, show it

6       done staff.  You're recognized.

7                 (Exhibit Numbers 105, 106, and 107 were

8       identified and admitted into the record.)

9                 CHAIRMAN CARTER:  Staff, you're recognized.

10                 MR. YOUNG:  At this time, Mr. Chairman, we

11       call William Coston and Carl Vinson to the stand.  And

12       for the record, Mr. Chairman, Mr. Coston and Mr. Vinson

13       have not been sworn.

14                 CHAIRMAN CARTER:  Have not been sworn?

15                 MR. YOUNG:  No, sir, they have not.

16                 CHAIRMAN CARTER:  Okay.  I'll give you guys a

17       chance to get settled in, and then I'll swear you in in

18       just a second.

19                 Mr. Young, what page of the exhibits for these

20       witnesses.

21                 MR. YOUNG:  Page 17, Number 108.  And just for

22       the record, Mr. Chairman, all the parties have agreed,

23       as we took up in preliminary matters, Mr. Vinson is

24       adopting Mr. Cryan's testimony and exhibits.

25                 CHAIRMAN CARTER:  Is that the understanding of

1641

1       the parties.

2                 Okay.  Would you gentlemen please stand and

3       raise your right hand.  I guess I should have said right

4       hands.

5                 (Witnesses collectively sworn.)

6                 CHAIRMAN CARTER:  Thank you.  Please be

7       seated.  Mr. Young, you may proceed.

8                 MR. YOUNG:  Thank you, sir.

9       Thereupon,

10                    WILLIAM COSTON and CARL VINSON

11       were called as witnesses on behalf of the Florida Public

12       Service Commission Staff and, having been first duly

13       sworn, was examined and testified as follows:

14                          DIRECT EXAMINATION

15       BY MR. YOUNG:

16            Q.   Can you please state your name and business

17       address for the record?

18            A.   (By Mr. Vinson) Carl Vinson, 2540 Shumard Oak

19       Boulevard, Tallahassee, 32399.

20            A.   (By Mr. Coston) William Coston, 2540 Shumard

21       Oak Boulevard, Tallahassee, Florida, 32399.

22            Q.   By whom are you employed, and in what

23       capacity?

24            A.   (By Mr. Vinson) I'm employed by the Florida

25       Public Service Commission as a public utilities

1642

1       supervisor.

2            A.   (By Mr. Coston) I'm employed by the Florida

3       Public service commission as an operation review

4       specialist.

5            Q.   Have you jointly prefiled testimony consisting

6       of four pages in this case, in this docket?

7            A.   (By Mr. Vinson) Yes.

8            A.   (By Mr. Coston) Yes.

9            Q.   Do you have any changes or corrections to that

10       testimony at this time?

11            A.   (By Mr. Vinson) No.

12            A.   (By Mr. Coston) No.

13            Q.   If I were to ask you the same questions as

14       those in your joint prefiled testimony, would your

15       answers be the same?

16            A.   (By Mr. Vinson) Yes.

17            A.   (By Mr. Coston) Yes.

18                 MR. YOUNG:  Mr. Chairman, at this time, staff

19       requests that the joint prefiled testimony of Mr. Vinson

20       and Mr. Coston be entered into the record as though

21       read.

22                 CHAIRMAN CARTER:  The prefiled testimony of

23       the witnesses will be inserted into the record as though

24       read.

25

1647

1       BY MR. YOUNG:

2            Q.   Did you have one exhibit attached to your

3       prefiled testimony as relates to Progress Energy which

4       is entitled "Progress Energy Florida's Project

5       Management Internal Controls for Nuclear Plant Uprate

6       and Construction Projects?

7            A.   (By Mr. Coston) Yes.

8            Q.   Do you have any corrections or changes to that

9       exhibit?

10            A.   No.

11            A.   (By Mr. Vinson) No.

12                 MR. YOUNG:  Mr. Chairman, as stated for the

13       record, that Exhibit is marked as CC-1, and it's Number

14       108 on staff's Comprehensive Exhibit List.

15                 CHAIRMAN CARTER:  For the record, on page 17,

16       it's 108.

17                 (Exhibit Number 108 was identified for the

18       record.)

19       BY MR. YOUNG:

20            Q.   Have you prepared a summary of your testimony

21       today?

22            A.   (By Mr. Coston ) Yes, we have.

23                 CHAIRMAN CARTER:  Are you guys familiar with

24       the lights.  Okay.  Good.

25       BY MR. YOUNG:

1648

1            Q.   Can you please provide that summary?

2            A.   (By Mr. Coston) Yes.  Good morning.  Our

3       testimony presents the management audit review of the

4       project management internal controls that Progress

5       Energy is using and managing the Crystal River nuclear

6       unit uprate and the construction of its Levy nuclear

7       project.  The primary objective of this review was to

8       document project key developments along with the

9       organizational management internal controls and

10       oversight that Progress Energy has in place for these

11       projects.  The internal controls examined were related

12       to the following key project activities:  Planning,

13       management and organization, cost controls and schedule

14       controls, contractor selection and management, and

15       auditing and quality assurance.

16                 This concludes our summary.

17                 MR. YOUNG:  Madam Chair, at this time I tender

18       the witnesses for cross.

19                 COMMISSIONER EDGAR:  Thank you.  Mr. Walls.

20                 THE WITNESS:  We have no questions for this

21       witness, but we would ask that we reserve any questions

22       pending any other questions the parties may have.

23                 COMMISSIONER EDGAR:  Well, let's see where we

24       are.  Mr. Rehwinkel, questions?

25                 MR. REHWINKEL:  No questions, but I'm -- this

1649

1       is not Progress's witness.  I don't know why they should

2       reserve the opportunity to redirect.

3                 COMMISSIONER EDGAR:  Well, I was not actually

4       sure what was the appropriate way, so I started at one

5       end to walk down to the other, since it is a staff

6       witness and neither an intervenor witness nor the

7       petitioner's witness.  So let me ask Ms. Helton what her

8       recommendation is as to the best way to proceed with

9       cross.

10                 MS. HELTON:  My initial reaction, Madam

11       Chairman, is, since it's Progress's petition, I think it

12       would be appropriate for the intervenors to

13       cross-examine the witness first and then for Progress to

14       go last.

15                 COMMISSIONER EDGAR:  Okay.  Then my apologies

16       for calling for cross in the wrong order.

17                 Mr. Rehwinkel, any questions?

18                 MR. REHWINKEL:  I have no questions.

19                 MR. BREW:  I have a couple of questions, Madam

20       Commissioner, but I am concerned that if the company has

21       cross-examination as opposed to redirect off of my

22       cross, then that's a separate issue from them wanting to

23       go -- simply to go last.

24                 COMMISSIONER EDGAR:  If indeed that comes up,

25       265I'm sure we'll be able to discuss it at the time.

1650

1                 MR. BREW:  Thank you.

2                 COMMISSIONER EDGAR:  We'll proceed

3       accordingly.  And so you are recognized for cross.

4                           CROSS-EXAMINATION

5       BY MR. BREW:

6            Q.   Good morning, gentlemen?

7            A.   (By Mr. Vinson) Good morning.

8            A.   (By Mr. Coston) Good morning.

9            Q.   Gentlemen, your prefiled testimony at page 3,

10       line 13, says that your report describes key project

11       events and contract activities.  Do you see that?

12            A.   (By Mr. Coston) Is that the testimony or --

13            Q.   The testimony, the testimony.

14            A.   And the line?

15            Q.   It's page 3, line 13.

16            A.   We're there.

17            Q.   What I'm trying to get to, is the purpose of

18       your report to describe those activities, or do you have

19       any opinions as to the reasonableness or prudence of any

20       of the activities that you document?

21            A.   (By Mr. Vinson) Our assignment was to describe

22       the activities, to document the controls that we

23       described in the summary.  It largely does not put

24       forward an opinion on the prudence and adequacy.

25            Q.   You said largely.  Are there decisions that

1651

1       the companies made or actions that were taken that you

2       do have opinions on?

3            A.   At places in the report, we do bring to the

4       attention some suggestions or observations.  I'm not

5       sure if that qualifies for what you're asking about.

6            Q.   Okay.  Let me take it up.  In the Prehearing

7       Order, it states that your testimony goes to Issue 21A,

8       which was whether it was reasonable and prudent for

9       Progress to execute its EPC contract.  And what I'm

10       trying to ask is, are you offering testimony one way or

11       the other on that issue?

12            A.   I would say that we offer information that's

13       relevant for consideration by staff and by the

14       Commission in dealing with Issue 21A.  However, I do not

15       have -- I do not believe that our report issues an

16       opinion about whether it was reasonable or prudent.

17            Q.   So you were endeavoring to offer facts, not

18       opinion?

19            A.   Offer facts; right.

20            Q.   Now, in the report, on page 16, if you can,

21       the first paragraph, the second sentence says, "Once the

22       company submits a request with a regulatory entity, the

23       company, albeit temporarily, relinquishes its ability to

24       control the forward progress of the project."   Do You

25       see that?

1652

1            A.   (By Mr. Coston) Yes.

2            Q.   Do you have any opinion on whether it would be

3       reasonable for the company to believe it can control the

4       progress of the project when the ball is in the NRC's

5       court?

6            A.   (By Mr. Vinson) Could you repeat the question,

7       please?

8            Q.   Sure.  Based on your statement here, taking it

9       more specifically, because you're describing in this

10       section the progress of the Levy project, are you not?

11            A.   Yes.

12            Q.   Okay.  So what I'm asking is, once Progress

13       filed its COL application with the NRC, did it

14       relinquish control over the review schedule at that

15       point?

16            A.   Over the review schedule, yes.  It's largely

17       in the NRC's court at that point.

18            Q.   Okay.  And would it be reasonable for Progress

19       to believe it could control the review schedule at that

20       point?

21            A.   At that point, they would not be controlling

22       the NRC's review.  They are a participant in the request

23       for additional information process.

24            Q.   But the control at that point was with the NRC

25       and its staff?

1653

1            A.   Right.

2                 MR. BREW:  That's all I have.  Thank you.

3                 COMMISSIONER EDGAR:  Thank you.  Mr. Davis.

4                 MR. DAVIS:  Nothing, thank you.

5                 COMMISSIONER EDGAR:  Okay.  Mr. Moyle.

6                 MR. MOYLE:  Just a couple of questions.

7                           CROSS-EXAMINATION

8       BY MR. MOYLE:

9            Q.   In your summary, you indicated that part of

10       your work entailed or dealt with a review of cost

11       controls; is that right?

12            A.   (By Mr. Coston ) Yes.

13            Q.   Now, did you also endeavor to look at cost

14       controls as it relates to your understanding of the

15       total project costs for this -- for the Levy nuclear

16       power project?

17            A.   We did look at how the company documents

18       within their internal controls, how they monitor

19       internally the project costs, the anticipated project

20       costs.

21            Q.   You would agree that a key component for

22       making those judgments with respect to cost controls is

23       having a good understanding as to what the ultimate cost

24       number is; correct?

25            A.   Yes.

1654

1            Q.   And as we sit here today, presumably you've

2       been in the room for the last couple of days or had

3       access to the information.  You would agree, would you

4       not, that the all-in number as to what the Levy nuclear

5       power project is going to cost is, shall we say, less

6       than certain?

7                 MR. YOUNG:  Objection.  Calls for speculation.

8                 CHAIRMAN CARTER:  To the objection, Mr. Moyle.

9       To the objection.

10                 MR. MOYLE:  Well, I don't know that I'm asking

11       them to speculate.  They said they've been here for two

12       days, and there has been a lot of testimony about the

13       need to renegotiate the amendment, and the price of that

14       process is unknown.  I don't think it's calling for

15       speculation.

16                 CHAIRMAN CARTER:  Ms. Helton.

17                 MS. HELTON:  Can I ask, have they testified to

18       the costs in their report or in the prefiled testimony?

19                 MR. VINSON:  The report discusses the current

20       cost estimate.  I'm not sure if I understand your

21       question fully.

22                 MS. HELTON:  Well, maybe if Mr. Moyle can

23       rephrase the question.

24                 CHAIRMAN CARTER:  Hang on one second.

25       Mr. Young.

1655

1                 MR. YOUNG:  Mr. Chairman, the reason I

2       objected is because Mr. Moyle is asking them to

3       speculate as to the uncertainty of the costs.  What the

4       staff witnesses have done is basically document the

5       internal controls.  It never speculated as to the costs.

6       And Mr. Moyle is basing his question on whether the

7       witnesses have heard the testimony here today and wants

8       them to draw a legal conclusion on that, and I think

9       that calls for speculation.

10                 CHAIRMAN CARTER:  To the objection, Mr. Moyle.

11                 MR. MOYLE:  I would agree with Mr. Young if my

12       question was, "What do you think this is going to cost

13       at the end of the day?"  They probably don't have that

14       frame of reference, but I think their testimony is that

15       they've evaluated cost, that the long-term cost is a key

16       component.  And I'm just getting them to admit, or

17       trying to get them to admit that the long-term cost is

18       an unknown factor as we sit here today.

19                 CHAIRMAN CARTER:  What was your question

20       again?

21                 MR. MOYLE:  Whether they would agree that the

22       ultimate all-in cost for Levy is uncertain as we sit

23       here today.

24                 MR. YOUNG:  And again, Mr. Chairman, what the

25       staff witnesses have done was not focus on a review of

1656

1       prospective -- the focus of review is not prospective

2       cost.  It was just documenting internal controls and

3       internal management.  To me, what Mr. Moyle is asking

4       relates to speculating on prospective costs and in terms

5       of the uncertainty of that, and that's the basis for my

6       objection.

7                 CHAIRMAN CARTER:  Rephrase, Mr. Moyle.

8       BY MR. MOYLE:

9            Q.   Did you rely on a cost number -- for looking

10       at future costs, did you rely on an all-in cost number

11       for performing your analysis?

12            A.   (By Mr. Coston) In our review, in looking over

13       the company's responses and documents, we looked at

14       their internal documents that laid out their anticipated

15       project cost.  The company has a master document that

16       lays that out, and we reviewed that.

17            Q.   And as we sit here today, what is that cost,

18       if you know?

19                 MR. WALLS:  Can I interject here?  Is this

20       asking for a confidential number?

21                 MR. MOYLE:  That's not the intent.  I mean, I

22       thought you all had set out a number of 17.2 billion.

23                 MR. WALLS:  I'm just being cautious because I

24       don't know what's on the document he said he reviewed as

25       the cost.

1657

1                 MR. VINSON:  I think I can answer that without

2       divulging confidential information.

3                 CHAIRMAN CARTER:  Okay.  You can answer the

4       question.

5                 MR. VINSON:  The current cost estimate is

6       $17.2 billion.

7                 CHAIRMAN CARTER:  Okay.  Mr. Moyle, you may

8       proceed.

9                 MR. MOYLE:  Thank you.

10       BY MR. MOYLE:

11            Q.   And you're aware that there's a need to

12       renegotiate the EPC contract; correct?

13            A.   (By Mr. Vinson) Yes.

14            Q.   And you're also aware that that renegotiation

15       has the potential to increase project costs; correct?

16            A.   Yes.

17            Q.   Have you had an opportunity to review the

18       testimony of Mr. Lyash in this case, who has filed

19       rebuttal testimony?

20            A.   I have not.

21                 MR. YOUNG:  Mr. Chairman, if I can inquire on

22       the relevancy of Mr. Moyle's question in terms of

23       reviewing Mr. Lyash's testimony.

24                 CHAIRMAN CARTER:  Mr. Moyle, to the objection.

25                 MR. MOYLE:  Sure.  The relevancy goes to the

1658

1       cost component, Mr. Young.  Specifically, the question I

2       wanted to ask, and I'll do it in a way that won't reveal

3       confidential information.  If you look at page 7 of

4       Mr. Lyash's testimony -- sir, can I just have one minute

5       to consult with counsel for Progress?

6                 CHAIRMAN CARTER:  Sure, absolutely.

7                 MR. MOYLE:  I don't want to spill the beans on

8       something that's confidential.

9                 CHAIRMAN CARTER:  Mr. Moyle.

10                 MR. MOYLE:  Yes, sir.  I'm trying to respond

11       to Mr. Young's objection.  The question was going to

12       relate to the first bullet point on page 7 of

13       Mr. Lyash's testimony, which in my discussions with

14       Progress, they indicated I can reveal what that bullet

15       point speaks to without revealing the percentages, but

16       the percentage of fixed or --

17                 CHAIRMAN CARTER:  Hang on, hang on, hang on.

18       We're speaking to the objection right now.

19                 MR. MOYLE:  Right.

20                 CHAIRMAN CARTER:  Let's don't go to --

21                 MR. MOYLE:  The question is going to be with

22       respect to did they review this information with respect

23       to fixed or firm contract pricing in terms of making a

24       judgment about the overall total project cost.

25                 CHAIRMAN CARTER:  Okay.  To the objection,

1659

1       Mr. Young.

2                 MR. YOUNG:  That's fine.  I just want to let

3       you know that, you know, I understand where you're

4       going.  And tread lightly, please, because we didn't

5       talk about dealing with Mr. Lyash.

6                 CHAIRMAN CARTER:  I hope you're not trying to

7       get staff to adopt Mr. Lyash's testimony.  That dog

8       won't hunt.

9                 Mr. Moyle, you may proceed.

10                 MR. MOYLE:  I would object to that.  I'm

11       sorry.  And this is the first time I've had two

12       witnesses at once, so it's a little interesting.

13                 MR. COSTON:  Should we sit closer together?

14       BY MR. MOYLE:

15            Q.   Did you all review Mr. Lyash's confidential

16       testimony?

17            A.   (By Mr. Coston) I did not.

18            A.   (By Mr. Vinson) Not the confidential.

19            Q.   Well, you would agree, would you not, with

20       respect to determining cost ultimately, the all-in cost,

21       that a key component of that could be how much of those

22       costs are fixed as compared to how much of those costs

23       are variable or subject to change based on, you know,

24       indexes or CPI or anything like that?  You would agree

25       with that, wouldn't you?

1660

1            A.   (By Mr. Vinson) Yes.

2            A.   (By Mr. Coston) Yes.

3                 MR. MOYLE:  That's all I have, Mr. Chairman:

4                 CHAIRMAN CARTER:  Thank you, Moyle.  Did we

5       get all the intervenors?

6                 Okay.  Mr. Walls.

7                 MR. WALLS:  This makes it easy.  No questions.

8                 CHAIRMAN CARTER:  Redirect.  Wait a minute.

9       Hang on.  Commissioners, anything from the bench?

10       Redirect.

11                 MR. YOUNG:  No redirect.

12                 CHAIRMAN CARTER:  Okay.  Exhibit Number 108.

13       Any objections?  Without objection, show it done.

14                 (Exhibit Number 108 was admitted into the

15       record.)

16                 MR. YOUNG:  And can my witnesses be excused?

17                 CHAIRMAN CARTER:  You may be excused.  Have a

18       great day.

19                 Okay.  Mr. Walls, or is it Ms. Triplett.

20       Ms. Triplett, you're recognized.  Call your next

21       witness.

22                 MS. TRIPLETT:  PEF calls Jon Franke.

23                 CHAIRMAN CARTER:  You may proceed.

24                 MS. TRIPLETT:  Thank you.

25       Thereupon,

1661

1                              JON FRANKE

2       was called as a rebuttal witness on behalf of Progress

3       Energy Florida and, having been first duly sworn, was

4       examined and testified as follows:

5                          DIRECT EXAMINATION

6       BY MS. TRIPLETT:

7            Q.   Mr. Franke, you were sworn yesterday?

8            A.   That is correct.

9                 CHAIRMAN CARTER:  Excuse me.  Mr. Roach, could

10       you push that microphone down, because it's blocking the

11       camera for Ms. Triplett.  There you go.

12                 MS. TRIPLETT:  I want to make sure I have my

13       15 minutes of fame.

14       BY MS. TRIPLETT:

15            Q.   Would you please reintroduce yourself to the

16       Commission?

17            A.   I'm Jon Franke, and I'm the vice president of

18       the Crystal River Nuclear Plant.

19            Q.   Mr. Franke, have you refiled rebuttal

20       testimony with an exhibit in this proceeding?

21            A.   Yes, I have.

22            Q.   And do you have that prefiled rebuttal

23       testimony and exhibit with you?

24            A.   I do.

25            Q.   Do you have any changes to make to your

1662

1       rebuttal testimony?

2            A.   I have none.

3            Q.   If I asked you the same questions asked in

4       your prefiled testimony today, would you give the same

5       answers that are in that testimony?

6            A.   Yes, I would.

7                 MS. TRIPLETT:  We request that the prefiled

8       rebuttal testimony be moved into evidence as though

9       read.

10                 COMMISSIONER EDGAR:  The prefiled testimony of

11       the witness will be inserted into the record as though

12       read.

13

14

15

16

17

18

19

20

21

22

23

24

25

1684

1       BY MS. TRIPLETT:

2            Q.   Do you have a summary of your rebuttal

3       testimony?

4            A.   I do, and I am prepared to give it at this

5       time.

6            Q.   Okay.  Please proceed.

7            A.   The Office of Public Counsel witness Jacobs'

8       sole criticism of the Crystal River 3 uprate project is

9       that he would have managed the project differently.  He

10       questions the company's decision to incur certain costs

11       for the project before receiving reasonable assurance

12       from the NRC that the full uprate power level would be

13       approved.  He does not, however, testify that Progress

14       Energy Florida should not have incurred any particular

15       costs for the uprate project.

16                 Contrary to Jacobs' assumptions and

17       assertions, the extended power uprate request is no

18       unusual challenge to be licensed by the NRC, in my

19       opinion.  Progress Energy Florida has received

20       reasonable assurance from the NRC regarding its license

21       amendment request through multiple discussions and

22       interactions with the Commission regarding its

23       submittal.  Progress Energy Florida is confident that

24       the NRC will approve its uprate and witness Jacobs'

25       concerns are unfounded.

1685

1                 That is the summary of my testimony.

2                 MS. TRIPLETT:  We tender Mr. Franke for

3       cross-examination.

4                 CHAIRMAN CARTER:  Mr. Rehwinkel.

5                 MR. REHWINKEL:  Thank you, Mr. Chairman.

6       Mr. Chairman, with your indulgence, before I engage in

7       cross-examination of Mr. Franke on his rebuttal, I would

8       like to ask a question that was left over from direct

9       yesterday with the agreement of the company and other

10       parties.

11                 CHAIRMAN CARTER:  Okay.  You may proceed.

12                           CROSS-EXAMINATION

13       BY MR. REHWINKEL:

14            Q.   Mr. Franke, do you recall me asking you

15       questions yesterday about the percentage or the portion

16       of the uprate costs that related to the measurement

17       uncertainty recapture?

18            A.   I certainly do.

19            Q.   Did you check -- and I asked you if you could

20       identify that portion, and I think you have done that;

21       is that correct?

22            A.   Yes, I have.  What I have identified is that

23       in 2008, for the measurement uncertainty recapture

24       portion or Phase 1 of our power uprate program, the

25       total cost experienced, $1.97 million associated with

1686

1       that portion of the cost for 2008 for the program.

2            Q.   Okay.  And after removing the joint owner

3       portion of $162,000, that yields a PEF portion of the

4       MUR cost of 1.8 million?

5            A.   That is correct, 1.8 million.

6            Q.   And with a jurisdictional factor of 93.753,

7       the jurisdictional 2008 MUR capital spending is

8       1,699,222; is that correct?

9            A.   That is correct.

10            Q.   Okay.  Thank you very much.

11                 Can I ask you to turn to page 4 of your

12       rebuttal testimony?

13            A.   I'm at page 4.

14            Q.   You state on line 3 that you have reasonable

15       assurances that the NRC will approve the full uprate,

16       and you state the reasons for that; is that correct?

17            A.   Yes.

18            Q.   And is it your opinion -- is your testimony

19       here today that you should have reasonable assurances in

20       order to go forward with this project?

21            A.   Yes.

22            Q.   On line 5, as part of that sentence, you

23       state -- well, on line 4, you say working with your

24       vendor, Areva, you continue to find confidence from the

25       engineering analysis which addresses uprate project

1687

1       licensing issues.  Do you see that?

2            A.   Yes, I do.

3            Q.   Now, does the statement -- isn't it true that

4       the statement "continuing to find confidence" means that

5       you're still working on solutions to certain engineering

6       problems or engineering issues that have arisen as a

7       part of implementing the uprate project?

8            A.   Yes.  We are continuing to -- we finalized the

9       analyses, and we are providing detail now to some of the

10       modifications required to be installed in 2011.  The

11       details of those modifications in some areas, in some

12       conditions, are part of that license amendment request.

13       So until the modifications work is done and the license

14       amendment has been fully approved, there always will be

15       some issues that will be resolved.  But as of now, we

16       have high confidence that all of our solutions as

17       prescribed will be successful.

18                 (Transcript follows in sequence in Volume 10.)

19

20

21

22

23

24

25

1688

1                        CERTIFICATE OF REPORTER

2

3       STATE OF FLORIDA:

4       COUNTY OF LEON:

5                  I, MARY ALLEN NEEL, Registered Professional

6       Reporter, do hereby certify that the foregoing

7       proceedings were taken before me at the time and place

8       therein designated; that my shorthand notes were

9       thereafter translated under my supervision; and the

10       foregoing pages numbered 1440 through 1687 are a true

11       and correct record of the aforesaid proceedings.

12                 I FURTHER CERTIFY that I am not a relative,

13       employee, attorney or counsel of any of the parties, nor

14       relative or employee of such attorney or counsel, or

15       financially interested in the foregoing action.

16                 DATED THIS 11th day of September, 2009.

17

18

____________________________

19                                 MARY ALLEN NEEL, RPR, FPR

2894-A Remington Green Lane

20                                 Tallahassee, Florida  32308

(850) 878-2221

21

22

23

24

25