1689

1                              BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

DOCKET NO. 090009-EI

3       In the Matter of:

4       NUCLEAR COST RECOVERY CLAUSE.

______________________________/

5

6

7

8

9                              VOLUME 10

10                       Pages 1689 through 1814

11              ELECTRONIC VERSIONS OF THIS TRANSCRIPT ARE

A CONVENIENCE COPY ONLY AND ARE NOT

12               THE OFFICIAL TRANSCRIPT OF THE HEARING,

THE .PDF VERSION INCLUDES PREFILED TESTIMONY.

13

14

PROCEEDINGS:        HEARING

15

COMMISSIONERS

16       PARTICIPATING:      CHAIRMAN MATTHEW M. CARTER, II

COMMISSIONER LISA POLAK EDGAR

17                           COMMISSIONER KATRINA J. McMURRIAN

COMMISSIONER NANCY ARGENZIANO

18                           COMMISSIONER NATHAN A. SKOP

19       DATE:               Thursday, September 10, 2009

20       PLACE:              Betty Easley Conference Center

Room 148

21                           4075 Esplanade Way

Tallahassee, Florida

22

REPORTED BY:        LINDA BOLES, RPR, CRR

23                           Official FPSC Reporter

(850) 413-6734

24

PARTICIPATING:      (As heretofore noted.)

25

FLORIDA PUBLIC SERVICE COMMISSION

1690

1                              I N D E X

2                              WITNESSES

3

NAME:                                         PAGE NO.

4

5       JON FRANKE

6       Continued Cross Examination by Mr. Moyle          1692

7       GARY FURMAN

8       Prefiled Rebuttal Testimony Inserted              1725

9       WILL GARRETT

10       Prefiled Rebuttal Testimony Inserted              1728

11       GARRY MILLER

12       Direct Examination by Mr. Walls                   1731

Prefiled Rebuttal Testimony Inserted              1733

13       Cross Examination by Mr. Rehwinkel                1788

14

15

16

17

18

19

20

21       CERTIFICATE OF REPORTER                           1814

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1691

1                              EXHIBITS

2       NUMBER:                                 ID.      ADMTD.

3       109                                               1723

4       110 GF-1                                1724      1724

5       111 WG-3                                1727      1727

6       112 WG-4                                1727      1727

7       113 WG-5                                1727      1727

8       114 GM-3                                1732      1732

9       115 GM-4                                1732      1732

10       116 GM-5                                1732      1732

11       117 GM-6                                1732      1732

12       118 GM-7                                1732      1732

13       119 GM-8                                1732      1732

14       120 GM-9                                1732      1732

15       121 GM-10                               1732      1732

16       122 GM-11                               1732      1732

17       123 GM-12                               1732      1732

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1692

1                         P R O C E E D I N G S

2                 (Transcript follows in sequence from

3       Volume 9.)

4                     CROSS EXAMINATION CONTINUED

5       BY MR. REHWINKEL:

6            Q.   I asked you a series of questions yesterday

7       relative to this point here with respect to engineering

8       problems that you were initially considering for

9       exemption consideration by the NRC, but you have now

10       decided to utilize the modification approach.  Do you

11       recall that?

12            A.   Yes.

13            Q.   These deal with a low pressure cross tie.  Is

14       that one of them?

15            A.   That is one of them, yes.

16            Q.   And boron precipitation issue?

17            A.   That is the other.  That is correct.

18            Q.   Okay.  Now it's true, is it not, that you can

19       perform those modifications without NRC approval;

20       correct?

21            A.   Yes.

22            Q.   Okay.  But you cannot utilize them in

23       generating the additional electricity from the uprate

24       until the LAR has been approved; is that correct?

25            A.   That is correct.  So we, we can provide the

FLORIDA PUBLIC SERVICE COMMISSION

1693

1       changes to the plant similar to other plants have done

2       the same work, and then once the amendment request is

3       approved by the NRC, we can increase the reactor power.

4            Q.   Okay.  On Lines 19 through 23 of Page 4 you

5       make note that you're doing an engineering analyses and

6       doing work such as other utilities have done on their

7       uprate projects.  Do you see that?

8            A.   Yes.

9            Q.   I'm paraphrasing.

10                 Now the other utilities that you refer to here

11       are utilities other than those with Babcock & Wilcox

12       reactors; isn't that correct?

13            A.   I don't believe that's true.  I believe some

14       uprate projects have been done at Babcock & Wilcox,

15       specifically measurement similar to our Phase

16       1 projects.  So I can't say that there have not been any

17       B&W work where equipment was procured prior to an

18       uprate.

19            Q.   Okay.  Is it true though that with, with, if

20       you exclude the MUR aspect of the uprate, that there are

21       no Babcock & Wilcox precedents for what you are doing?

22            A.   Only that the Davis-Besse facility had

23       equipment which had the capacity similar to what we are

24       purchasing to gain their higher power level than we are

25       currently at.  So that facility is already operating at

FLORIDA PUBLIC SERVICE COMMISSION

1694

1       a power level significantly above our current operating

2       level and they do have equipment in service which

3       supports that operation.

4            Q.   Now are you referring to Davis-Besse's

5       1.6 percent power uprate in 2008?

6            A.   No.  That facility received an original

7       license higher than Crystal River 3.  So they are

8       currently a Babcock & Wilcox facility operating, I

9       believe it's about 7 percent below the target power

10       level for Crystal River 3, approximately 9 or

11       10 percent, percent power above where Crystal River 3

12       currently operates.

13            Q.   But Babcock & Wilcox -- I'm sorry.  The

14       Davis-Besse plant did not engage in an uprate analogous

15       to the testimony that you offer on Page 4, Lines 19

16       through 23; correct?

17            A.   No, they did not have a separate uprate which,

18       which follows the extended power uprate programs.  They

19       started at a higher power level with the same basic

20       technology.

21            Q.   They did not have to go through a modification

22       approval process and a LAR process?

23            A.   They had to go through an original licensing

24       process, which I would characterize as more lengthy and

25       more rigorous.

FLORIDA PUBLIC SERVICE COMMISSION

1695

1            Q.   And when was that?

2            A.   When they achieved their original license.

3            Q.   Would that have been when?

4            A.   I don't know the date of Davis-Besse's

5       original license.

6            Q.   In the '60s or '70s?

7            A.   I believe it's probably more likely late '70s,

8       '80s.

9            Q.   On Page 5 of your testimony you discuss a

10       feasibility analysis that you say is contained in the

11       IPP or integrated project plan for the uprate; is that

12       correct?

13            A.   Yes.  That is correct.

14            Q.   Do you have that with you?

15            A.   I do not have a copy of the integrated project

16       plan.  I did not know that that would be an issue that

17       remained today.

18            Q.   Well, you have, you've noted that that's

19       attached to Dr. Jacobs' testimony as an exhibit;

20       correct?

21            A.   That's correct.

22            Q.   If -- with your counsel's permission, I'd like

23       to -- is the document I've handed you the IPP that you

24       referred to?

25            A.   That is correct.

FLORIDA PUBLIC SERVICE COMMISSION

1696

1            Q.   Okay.  Could you turn to where you have

2       identified the page that you say contains the

3       feasibility analysis?

4            A.   Well, the entire document essentially is a

5       feasibility analysis.  There is an economic evaluation

6       that you have marked on Page 13.

7            Q.   Is that primarily where the feasibility

8       analysis is contained?

9                 And for the record --

10            A.   In conjunction with the following sections

11       that talk about risk management and the susceptible --

12       the conclusion of the integrated project plan which

13       recommends going forward with the project.

14            Q.   So the section I've marked is, is Section 5.0?

15            A.   That is correct.

16            Q.   Okay.  Now is this a confidential document?  I

17       don't think it is, is it?

18                 MS. TRIPLETT:  I believe that portions of it

19       are confidential.

20                 THE WITNESS:  Yeah.  I believe so also.

21                 MS. TRIPLETT:  Can you tell me which section

22       you're asking about again?  I just got it.

23                 MR. REHWINKEL:  I'm looking on Dr. Jacobs'

24       exhibit PEF-3, which I think is 101 -- it's Page 184 of

25       233.  And I've handed the witness the original document

FLORIDA PUBLIC SERVICE COMMISSION

1697

1       that's not marked as an exhibit.

2                 CHAIRMAN CARTER:  Hang on a sec.  Hang on a

3       sec.

4                 Ms. Triplett.

5                 MS. TRIPLETT:  Section -- that page is not

6       confidential.

7                 CHAIRMAN CARTER:  Okay.  Mr. Rehwinkel, you

8       may proceed.

9                 MR. REHWINKEL:  Okay.  Thank you.  So -- you

10       said that it is not?

11                 CHAIRMAN CARTER:  Yes.  It is not.  She said

12       it is not confidential.

13                 MR. REHWINKEL:  It looks to be redacted in

14       Dr. Jacobs' testimony.

15                 CHAIRMAN CARTER:  Okay, guys.  Hang on a

16       second.  Let's get a, get a, get a meeting of the minds

17       on the information.

18                 (Pause.)

19                 Mr. Rehwinkel.

20                 MR. REHWINKEL:  Thank you, Mr. Chairman.

21       BY MR. REHWINKEL:

22            Q.   Mr. Franke, my question to you, and I think

23       your counsel may well advise that it's okay to talk

24       about this, but I may not need that kind of detail, but

25       does the economic evaluation that's contained in this

FLORIDA PUBLIC SERVICE COMMISSION

1698

1       part of the IPP evaluate the cost of the project versus

2       other options to the company absent doing the project?

3            A.   This looks primarily at whether the project is

4       on track for the cost assumptions.  That's what this

5       does.

6            Q.   Okay.  Is there, is there any comparison in

7       this document to other, to options such as not doing the

8       uprate?

9            A.   I do not believe that this document has

10       re-performed the needs analysis.  No.

11            Q.   Okay.  But it does look at the cost of the

12       project based on your current view; is that correct?

13            A.   Yes.  It does provide a summary of that.

14            Q.   Okay.  On Page, Page 8 of your analysis, of

15       your testimony --

16            A.   Yes.

17            Q.   Okay.  And looking on Lines 2 through 5, you

18       state, you testify that Dr. Jacobs has conceded that it

19       is possible that the NRC could approve some percentage

20       of the 140-megawatt requested increase rather than

21       outright denying the request altogether.  Do you see

22       that?

23            A.   Yes.

24            Q.   Does your testimony there also suggest that

25       you agree that that's also a possibility?

FLORIDA PUBLIC SERVICE COMMISSION

1699

1            A.   Of course it is.  I do believe and it is my

2       testimony that I believe we will achieve the entire

3       power uprate as sought.  I have -- you'll never have

4       100 percent certainty with any particular regulatory

5       action, and there's always the possibility that a lower

6       level might be approved by the Commission.  But I

7       believe all sought power level will be achieved.

8            Q.   In the next sentence there you say that Jacobs

9       is just speculating that the full uprate might not be

10       approved, and therefore his argument that PEF should not

11       incur certain uprate costs until it has reasonable

12       assurance that the LAR will be approved is nothing more

13       than his unsupported personal opinion that he would

14       manage the project differently.  Do you see that?

15            A.   Yes, I do.

16            Q.   Are you stating there that the company does

17       not need reasonable assurances before spending money

18       that the ratepayers will have to reimburse them for?

19            A.   Actually if you read my entire testimony,

20       several places in it I provide testimony that I believe

21       we have reasonable assurance.  So, yes, I believe

22       reasonable assurance is required.

23                 My testimony with regard to this was that in

24       my review of Dr. Jacobs' testimony, that he had not

25       personally looked at any of the analyses that he was

FLORIDA PUBLIC SERVICE COMMISSION

1700

1       claiming would be a challenge to the license renewal

2       that I had, and that in my review they provided no

3       challenge to the uprated power.

4            Q.   Now you stated in your summary and you stated

5       just now that there's no challenge to receiving the

6       NRC's approval for your uprate; is that correct?

7            A.   No significant challenge.  You're always

8       dealing with a regulatory body and there is no

9       100 percent certainty.

10            Q.   Okay.  Now has the NRC given you any of these

11       assurances in writing?

12            A.   No.  The NRC's policies do not allow them to

13       provide written approval of a document until they've

14       completed their review.  So, no, they have followed the

15       same program and policies that even Dr. Jacobs

16       described, which is you continue to engage with them,

17       you follow their comments and questions.  And through

18       those interactions and questions we have continued to

19       gain a reasonable assurance that we will achieve the

20       uprate.

21            Q.   And, likewise, they have not stated to you

22       orally or verbally, I should say, that, that they're

23       going to approve your LAR once you submit it, have they?

24            A.   No.  That would be against their rules to be

25       able to do that.

FLORIDA PUBLIC SERVICE COMMISSION

1701

1            Q.   Okay.  So your reasonable assurances are based

2       on your interactions with the staff, their questions,

3       and the way you feel like your engineering analysis and

4       solutions are going; is that correct?

5            A.   No.  My, my reasonable assurance is based on

6       that plus many other factors.  For example, I've

7       personally supervised uprated license amendment requests

8       for two different units including Crystal River 3 and

9       over three different applications.  So I have personal

10       in performing those.  It's also based on industry

11       experience of watching over 104 uprates being approved

12       by the NRC, 20 of which were similar extended power

13       uprates on unique power plants similar, unique in a

14       similar fashion of CR3, all 20 of which have fully been

15       vetted through the NRC, all 20 were approved.  My

16       reasonable assurance is based on those factors.

17            Q.   None of the uprates that you have described,

18       whether ones that you were involved in directly or ones

19       that you have observed, are Babcock & Wilcox pressurized

20       water reactors, are they?

21            A.   Only the MUR and other uprates.  We have

22       uprated Crystal River 3 a small percentage in the past.

23       But, but as I testified yesterday, each uprate is not

24       unique to design.  It's unique to station and site.

25       Every power plant is designed differently.  Even if I

FLORIDA PUBLIC SERVICE COMMISSION

1702

1       were to look at other B&W designs, the designs are

2       varied enough that each would be a unique uprate

3       request.  So each of those 20 that I described were

4       unique; unique enough to, to characterize them as

5       significantly different from all others.

6            Q.   Do you have the document that's attached as

7       HT-4 to Mr. Thompson's testimony with you?

8            A.   No, I do not.

9            Q.   Have you seen it?

10            A.   I'm not sure what it is by tab.

11            Q.   Okay.  This is a document entitled NRC

12       Approved Applications for Power Uprates.

13            A.   No, I have not.

14            Q.   You haven't seen that?  You weren't at Dr. --

15       strike that.

16                 So you weren't aware that Mr. Thompson filed

17       rebuttal testimony to Mr., to Dr. Jacobs?

18            A.   No, I was not.

19            Q.   Okay.  I'd ask you to turn to Page 10 of your

20       testimony.

21            A.   I'm on Page 10.

22            Q.   And this is on Lines 10 through 12.  This is

23       what we were discussing yesterday about your change in

24       your LAR submittal plans and your expected NRC action

25       date; is that correct?

FLORIDA PUBLIC SERVICE COMMISSION

1703

1            A.   That is correct.

2            Q.   Okay.  On Line 14 there starts a Q and A:

3       "Does PEF have reasonable assurances that its LAR will

4       be approved by the NRC?"  Do you see that?

5            A.   Yes, I do.

6            Q.   Okay.  Now as part of your answer continuing

7       on to Page 11, you state on Line 6, well, Lines 5 and 6,

8       "We gain more confidence that our ultimate LAR submittal

9       will be complete and acceptable to the NRC."  Do you see

10       that?

11            A.   Yes, I do.

12            Q.   Okay.  Now that implies, does it not, that

13       when you first started off with this project you were

14       less confident of, of getting an LAR submittal complete

15       and acceptable to the NRC, does it not?

16            A.   I don't understand your question.

17            Q.   Well, by gaining more confidence, it implies

18       that when you started out, you had less confidence; is

19       that correct?

20            A.   Sure.  As you step through the process at each

21       stage, you gain more and more confidence that your

22       approval, your, your project will be approved.  But I

23       can assure you throughout the project we've always had a

24       high level of confidence.

25            Q.   Okay.  But at a time you had less confidence

FLORIDA PUBLIC SERVICE COMMISSION

1704

1       you were spending the bulk of the money that it takes

2       to, to, to do the uprate project; correct?

3            A.   Actually I haven't spent the bulk of the money

4       yet.  Most of that money is being spent this fall in

5       conjunction with the 2009 outage.

6            Q.   But that money is, is being, is subject to

7       recovery in this proceeding; correct?

8            A.   I believe it is.

9            Q.   Okay.  Let's look on Page 11, Line 20, if you

10       will, please.

11            A.   Yes.

12            Q.   You state there, "We recognize that as the

13       first B&W plant to apply from an EPU, we must produce a

14       high quality submittal."  Do you see that?

15            A.   Yes, I do.

16            Q.   That does connote a recognition that there is

17       something about a B&W plant that is important with

18       respect to what you're attempting to achieve; correct?

19            A.   No.  Actually what that denotes, and I'll be

20       clear, as a first-time B&W unit, I'm working with a

21       vendor that is not as familiar with the uprate project

22       as, say, General Electric.  And as such, we've got to

23       work with AREVA, the now original equipment manufacturer

24       owner of the design for the B&W units, and there is --

25       for -- since this is the first time AREVA as a company

FLORIDA PUBLIC SERVICE COMMISSION

1705

1       has done it, we've put in place some additional scrutiny

2       over their processes and what documentation they'll

3       provide.  That's what -- and what I'm talking about here

4       is not a risk to achieving the uprate.  It's that

5       additional considerations must be put in place to ensure

6       that the quality of the documentation, it will be, will

7       be at the level required.

8            Q.   There are other B&W plants out there that are

9       probably waiting to see what happens with the CR3

10       uprate, are there not?

11            A.   I don't doubt that they are.

12            Q.   Okay.  And they're looking to what happens

13       with CR3, are they not, because there is something about

14       the CR3 B&W plant that is similar to what they have;

15       correct?

16            A.   I would actually characterize it differently.

17       I think as we go through the process, they'll be able

18       to, to gain some efficiencies in their own uprates when

19       they choose to uprate.  That's, that's what I would

20       characterize it as.

21            Q.   And that's because they were licensed at a

22       level closer to the CR3 electrical output than the

23       Davis-Besse one such that there is room to uprate

24       efficiently to achieve the efficiencies that you hope to

25       achieve; correct?

FLORIDA PUBLIC SERVICE COMMISSION

1706

1            A.   Not so much.  Let me, let me make sure that

2       I'm clear in how I'm describing this.  Each plant in the

3       United States, each station has a unique set of

4       equipment, a unique set of design parameters and a

5       unique licensing basis.  So as each unit goes through

6       the process of an extended power uprate, which

7       approximately 25 percent of the plants in the United

8       States have gone through, their gains on industry

9       knowledge on how this program and process works, there

10       will be pieces of the uprate at Crystal River 3 which

11       will benefit the other B&W units.  There will be pieces

12       of uprates performed at GE plants' boiling water

13       reactors that will benefit those licensees that follow

14       me as well.  I anticipate other Westinghouse plants who

15       might seek uprates might also benefit just as much as

16       another B&W unit.

17                 The fact that it's B&W really is, it has some

18       relevancy, but it's not an overriding concern.  Once

19       again, each plant is unique.  As the industry gains

20       experience with uprating the power limits of reactors,

21       that benefit provides benefit to the entire industry.

22            Q.   Thank you.  Can you turn to Page 13 of your

23       testimony, your rebuttal testimony.

24            A.   Yes.

25            Q.   Okay.  And on Lines 14 through 17 you note

FLORIDA PUBLIC SERVICE COMMISSION

1707

1       that there are four other -- four of the seven B&W units

2       have a low pressure cross tie system in them; is that

3       correct?

4            A.   That is correct.

5            Q.   Now were those original to the plants or were

6       they added?

7            A.   I believe -- I'm not certain.  I believe at

8       least one of the facilities added the low pressure cross

9       tie after original license.

10            Q.   But it could be more?

11            A.   It could be more.

12            Q.   Okay.  Doesn't that suggest that with respect

13       to the modifications that you're seeking for an increase

14       in power, that there is a design weakness in the B&W PWR

15       reactor?

16            A.   Absolutely not.  The -- there's not any

17       specific design weakness unique to B&W reactors.  In

18       order to uprate power to meet other licensing

19       requirements, many stations, in fact, I would -- I can't

20       say all, but I would say most stations have had to do

21       some form of modification through the years.

22            Q.   And just to be clear, Mr. Franke, I was not

23       suggesting that there's a weakness with respect to the

24       current operation.  My, my question was as to the

25       ability to uprate the unit, and I think that's the

FLORIDA PUBLIC SERVICE COMMISSION

1708

1       answer you've given me.

2                 I just wanted to make clear I wasn't

3       suggesting there's a problem at the plant today because

4       of this low pressure cross tie issue.

5            A.   No.  Actually in this case, if I could be more

6       specific, the design itself would -- and this is one of

7       those cases that you mentioned before where we were

8       dealing with a manual operator action exemption.  And

9       so -- and in fact in this case it had more to do with a

10       new regulatory position.  We, we felt that there was

11       technical justification at some point to do the uprate

12       without this modification, but, after interactions with

13       the NRC, chose for expediency and for regulatory

14       assurance and confidence to go with a modification as

15       opposed to a, an option which used probability

16       assessment to determine if this particular condition

17       would require the modification.

18            Q.   Thank you.  On Page 14 -- I'd like to ask you

19       again about the Davis-Besse issue.  On Lines 3 and 4 you

20       state that the requested uprate requests only a modest

21       increase from the current license power level at other

22       B&W plants, and then you cite the Davis-Besse unit.

23            A.   That's correct.

24            Q.   And you state that they were up, uprated to

25       2,817 megawatts thermal; is that correct?

FLORIDA PUBLIC SERVICE COMMISSION

1709

1            A.   Yes, sir.

2            Q.   Now that only represented though, what, a

3       3.8 percent increase in their license?

4            A.   It represents a significant increase, however,

5       over current licensed power level at CR3.  That was my

6       point.  CR3 is currently licensed at 2,609 megawatts

7       thermal.  So the increase from 2,609 to 2,817, which is

8       a level a similar B&W unit has already been approved for

9       a power level by the NRC, is a significant increase in

10       output.

11            Q.   But the incremental change to the unit's

12       output was only 3.8 percent; correct?

13            A.   The end (phonetic) point is all that really

14       matters.  So it is a small delta between what the

15       original license was and the second one.  But the NRC

16       doesn't look at, in no manner do they look at the

17       increase in power when they're making their, their

18       approval or their conclusions.  They look at the final

19       power level only.  So the final power level is the only

20       number that's worthy of comparison.

21            Q.   I misstated.  I said 3.8.  I think it's

22       1.6 percent.  It was a measurement uncertainty recapture

23       uprate; correct?

24            A.   I believe you are correct.

25            Q.   Okay.  Which is not the bulk of the uprate

FLORIDA PUBLIC SERVICE COMMISSION

1710

1       that you are seeking to achieve with CR3; correct?

2            A.   Actually it's, the 2,817 megawatts thermal

3       represents a large percentage of what we are seeking.

4       We're seeking an increase from 2,609 to 3,014.  So

5       getting to 2,817 would be a substantial uprate to CR3.

6            Q.   And the Davis-Besse uprate was a, basically an

7       improvement to the plant instrumentation; correct?

8            A.   That is correct.  However, they had already

9       achieved a license to a power level with the same

10       technology at a much higher amount than, than Crystal

11       River 3.

12            Q.   So the 1.6 percent increase at Davis-Besse is

13       relatively small compared to the 20 percent or 180

14       megawatt increase that you're seeking at CR3; correct?

15            A.   Only on a percentage basis.  It is only 7

16       percent above the power level we are seeking.

17            Q.   Well, now wasn't there a -- there was a power

18       uprate in 1981 at CR3; correct?

19            A.   Yes.  And then again there was one in this

20       decade as well, I believe.  2003, 2004.

21            Q.   What was that for?

22            A.   That was some margin that had not, had already

23       been previously licensed that we actually took advantage

24       of and increased reactor power.

25            Q.   So is that one of the uprates that you refer

FLORIDA PUBLIC SERVICE COMMISSION

1711

1       to in your earlier testimony?

2            A.   Actually, no, I didn't count that one.  It was

3       relatively small.

4            Q.   Okay.  That was 2007, 1.6 percent, or is that

5       the MUR?

6            A.   No.  The 2007 was the 1.6 percent.

7            Q.   Okay.  On Page 14 down there on Lines 17 and

8       18, with respect to the issues that are discussed above,

9       you say that all of these issues have been resolved?

10            A.   We have resolved -- we are to the point on all

11       these issues where we are confident a separate license

12       submittal would not be required to resolve these issues,

13       or that license amendment has been submitted and is well

14       through the process to have regulatory assurance that

15       they would be resolved.

16            Q.   And is that the control rod ejection?

17            A.   Yes.  Currently one of the four issues that

18       Dr. Jacobs reviewed.  We did submit a separate license

19       amendment request.  That license amendment is currently

20       in the very final stages of review, and we have

21       assurance that it will be approved within the next

22       couple of weeks.

23            Q.   Okay.  But Items 1, 2 and 3 above that --

24       well, on Lines 14 through 17 of Page 14, those have only

25       been resolved in the sense that you do not -- you have

FLORIDA PUBLIC SERVICE COMMISSION

1712

1       decided you do not need to seek a license amendment for

2       that or an exemption; is that correct?

3            A.   Yes.  We're confident we do not require

4       separate license amendments for those particular

5       technical issues.

6            Q.   Okay.  But you have not actually made the

7       modifications.

8            A.   No.  They will not be completed until we spend

9       that money that, that you're suggesting I not spend, as

10       well as finalize the license amendment request.

11                 So, yes, we would have to actually work

12       through the process, spend the money to both do the

13       evaluations and the modifications to resolve them.

14            Q.   Okay.  And they won't ultimately be resolved

15       until they're approved in the LAR in 2011, if then;

16       right?

17            A.   Yes.  But -- and they would be approved in

18       conjunction with the other issues involved with the LAR.

19            Q.   Let me ask you to turn to Page 18 of your

20       testimony.

21            A.   Yes.

22            Q.   The Q and A that starts on Line 12, you state

23       on Line 15 that none of the risks on the risk matrix are

24       risks related to achieving the LAR.  They're related to

25       cost and scheduling.  Do you say that?

FLORIDA PUBLIC SERVICE COMMISSION

1713

1            A.   That is correct.

2            Q.   Okay.  Now is this a matter of semantics?

3       Because if you don't achieve the license amendment for

4       the LAR approval of these items, then -- well, if you

5       don't achieve it by your schedule on your outage

6       schedule, then that is a problem, is it not?

7            A.   Well, let's be careful.  In answering this

8       question I need to be a little more specific.  The risk

9       matrix in this case is tracking cost and schedule risk

10       against budget, not against achieving the goal of the

11       projects.  For example, we are currently developing the

12       modification to be installed in 2011 for the low

13       pressure cross connect.

14                 What I was making the point of is that this is

15       not a risk to achieving a license.  And, in fact, by

16       choosing this option, there is no license condition I

17       need to request from the NRC.  This is a real good

18       example.

19                 You know, the prior license condition of the

20       plant, it required a manual operator action to fulfill a

21       function that the NRC would prefer being an automatic

22       action.  As a result, we had an exemption which allowed

23       a manual operator action.  By choosing to install the

24       low pressure cross connect, I eliminate the need for

25       that exemption.  So I have eliminated the licensing risk

FLORIDA PUBLIC SERVICE COMMISSION

1714

1       that the NRC would, would continue to authorize that

2       exemption under an uprated condition.  So the licensed

3       risk has been eliminated.

4                 Why it remains on my risk matrix is because

5       the modification has not been fully developed.  We are

6       uncertain as to what the actual schedule required for

7       installing that modification.  My 2011 outage is a

8       42-day business plan schedule right now, and I do not

9       know enough about this modification to know for certain

10       that that particular modification can be installed

11       inside a 42-day window.  We have high confidence that it

12       can, but we have not finalized the modification yet.  So

13       once that mod is finalized, we'll understand what

14       actions are required to mitigate that risk against the

15       outage schedule.  However, in no manner does it risk the

16       schedule of achieving the uprated power of the unit,

17       which is right now at the end of my 2011 outage.

18            Q.   Okay.  If you'd give me one minute, I may have

19       just one more question for you.

20                 CHAIRMAN CARTER:  Absolutely, Mr. Rehwinkel.

21                 (Pause.)

22                 MR. REHWINKEL:  That's all I have.  Thank you.

23                 Thank you, Mr. Franke.

24                 CHAIRMAN CARTER:  Mr. Brew.

25                 MR. BREW:  No questions.

FLORIDA PUBLIC SERVICE COMMISSION

1715

1                 CHAIRMAN CARTER:  Mr. Davis.

2                 MR. DAVIS:  No questions.

3                 CHAIRMAN CARTER:  Mr. Moyle, you're

4       recognized.

5                 MR. MOYLE:  Thank you, Mr. Chairman.

6                          CROSS EXAMINATION

7       BY MR. MOYLE:

8            Q.   Mr. Franke --

9            A.   Yes, sir.

10            Q.   -- I have just a couple of questions.

11                 In response to a question posed by

12       Mr. Rehwinkel a second ago, you were talking about

13       tracking your cost and schedule against a budget for the

14       uprate projects.  You do track your cost and schedule

15       against a set budget; correct?

16            A.   Yes, we do.

17            Q.   Okay.  And that budget number is a, is a firm

18       number; correct?

19            A.   The budget is a firm number.  Now we do have

20       processes for revising those budget figures.

21            Q.   And typically when you budget, you put a

22       contingency in for a certain percent, maybe 5 or

23       10 percent?

24            A.   That's correct.  We, we follow a process by

25       which we determine what the cost of a risk might be and

FLORIDA PUBLIC SERVICE COMMISSION

1716

1       then a percentage of that risk challenge, and then that,

2       that ends up with being a certain portion of contingency

3       plan costs might be funded by a contingency.

4            Q.   You're not involved in the, in the Levy

5       nuclear power plant project, in the budgeting process in

6       that, are you?

7            A.   No.

8            Q.   I understand you're the guy with Crystal River

9       3; correct?

10            A.   That is correct.

11            Q.   Okay.  And a couple of points in your

12       testimony that I wanted to refer you to.  Page 4 --

13            A.   Is this my rebuttal testimony?

14            Q.   Yes, sir.

15            A.   Yes.  Page 4.

16            Q.   Yeah.  On Line 11 you state, quote, "Any

17       prudent utility would work with the NRC staff prior to

18       the submittal of its license application to ensure the

19       successful approval of the application after it is

20       submitted."

21                 And then on Page 11 there's some further

22       discussion, I think, up at the top of the page.  You

23       start on Line 10 and you say, "Rather than choose a

24       course of action in a vacuum, without input from the

25       NRC, PEF is more proactive in raising and discussing

FLORIDA PUBLIC SERVICE COMMISSION

1717

1       issues and solutions with the NRC.  Even when PEF is

2       fairly certain about how an issue should be resolved, we

3       discuss it with the NRC in an abundance of caution."

4                 Am I interpreting this correctly that this is

5       part of the process that you engage in to, to get your

6       level of comfort that things will go well for you when

7       you submit your application?

8            A.   Yes.  For, for example, in fact, Dr. Jacobs

9       had the opportunity to review the minutes where we went

10       up to D.C. and met with the technical reviewing staff

11       that would be reviewing our uprate both in 2008 and 2009

12       to discuss those points where we had identified would,

13       might need some special license consideration, some

14       special consideration with regard to the way the

15       information was presented or the technical solution

16       chosen.

17                 And, in fact, the four items that we've been

18       discussing today and that were discussed by Dr. Jacobs

19       and in my own rebuttal testimony were issues that we had

20       brought to the Commission that we wanted to have clear

21       understanding on how to deal with.  So that's, that's

22       what this is representing, that before you spend the

23       money headed down one technical path or you, you commit

24       to a regulatory review schedule that would impact the

25       overall project, that you in essence look down the path

FLORIDA PUBLIC SERVICE COMMISSION

1718

1       to identify places where you need to make sure you've

2       followed the right path so that when you get to the end

3       you're not told to back up and do a different, take a

4       different tack.

5            Q.   Okay.  And you talked about, you know,

6       committing to a regulatory schedule.  I mean, you would

7       agree that it would not be prudent to interact with the

8       NRC and fail to bring up an important point in

9       conversations with them that would impact your project;

10       correct?

11            A.   I just think it's important to maintain a, a

12       good dialogue with the NRC during all stages.  Your

13       question seems to be very specific, and I, I can only

14       answer vaguely.

15            Q.   Well, let's put it, let's frame it this way.

16       There's three key points in your process, A, B and C.

17       You have an interaction with the NRC to make sure things

18       are moving along, you're going to get your reasonable

19       assurance.  It wouldn't be a good idea or it wouldn't be

20       prudent to only bring up A and B and omit to bring up C;

21       correct?

22            A.   I'd have to know what C was.  I don't know

23       what --

24            Q.   Just assume it's something critical to the

25       project or important to the project.

FLORIDA PUBLIC SERVICE COMMISSION

1719

1            A.   It would have to be something that, that --

2       the parameters that we would want to discuss with the

3       NRC would be those parameters which affected the

4       licensing direction that the staff would be reviewing.

5       If it had nothing to do with the licensing aspect of a

6       project, it would not be worthy of discussion.  If it

7       was a licensing condition that was well vetted in the

8       industry and well understood, it would not be worthwhile

9       discussing with the Commission.

10            Q.   If it were a licensing issue that was not well

11       vetted, that there was some uncertainty surrounding it,

12       that would be something you'd want to bring up; correct?

13            A.   If you would anticipate that there might be a

14       problem with that condition.

15            Q.   Okay.  And the final point I wanted to raise

16       with you is, you know, I read your testimony to send a

17       pretty strong message that you think everything is going

18       to go okay.  I mean, you used the term reasonable

19       assurance that you're going to, you're going to get

20       this.  Some have suggested, well, maybe you should wait

21       until you get the NRC to approve before moving forward.

22       And you take a different view; correct?

23            A.   Absolutely.  I think the cost to my customers

24       would be prohibitive of waiting.

25            Q.   Okay.  Do you think, given the high level of

FLORIDA PUBLIC SERVICE COMMISSION

1720

1       certainty that it appears that you all have at this

2       point, to the extent that the NRC did not approve

3       everything as asked and if there was a negative impact

4       on consumers, that it would be appropriate for that risk

5       to be borne by you as compared to the consumers?

6            A.   I don't even understand your question.  Could

7       you please repeat it?

8            Q.   Okay.  Sure.  Let's do a hypothetical.  You're

9       asking for A, B and C from the NRC.  Okay?  All of them

10       are important, all of them have cost.  If the NRC in

11       this process says, thanks for your application, I know

12       we met a number of times, we're only approving A and B

13       and we're not approving C, would you agree that C should

14       not be borne, the costs associated with C, if it were

15       not approved, that those costs should not be borne by

16       ratepayers?

17            A.   I believe the process is a prudency review

18       that we're currently undergoing.  And once those costs

19       were considered prudent, that they would follow the

20       regulation on recovery.  I'm not a recovery expert

21       though.

22                 MR. MOYLE:  That's all I have.

23                 CHAIRMAN CARTER:  Thank you, Mr. Moyle.

24                 Staff.

25                 MR. YOUNG:  No questions.

FLORIDA PUBLIC SERVICE COMMISSION

1721

1                 CHAIRMAN CARTER:  Commissioner Skop, you're

2       recognized.

3                 COMMISSIONER SKOP:  Thank you, Mr. Chairman.

4                 Good morning, Mr. Franke.

5                 THE WITNESS:  Good morning.  Good morning,

6       Commissioner.

7                 COMMISSIONER SKOP:  I just wanted to briefly

8       go over your testimony starting on Page 14, Lines 9

9       through 18.  And on that Dr. Jacobs expressed concerns

10       with respect to the issues discussed or identified

11       during the May 8 -- May 2008 meeting between PEF and the

12       NRC, and I guess those four issues are there.

13                 Taking those issues individually on Page 15,

14       Lines 3 through 15, would it be correct to state that

15       the core flood line break event in conjunction with the

16       electrical loss of power, that Progress has implemented

17       a modification to mitigate approval risk or any approval

18       risk in lieu of seeking the exemption that's discussed

19       on that page?

20                 THE WITNESS:  That's exactly the case I was

21       discussing earlier.  By installing the modification, we

22       have eliminated licensing risk on that item.

23                 COMMISSIONER SKOP:  Okay.  On, moving on to

24       Page 16 with respect to the Page 16, Lines 4 through 19,

25       regarding the boron precipitation question or

FLORIDA PUBLIC SERVICE COMMISSION

1722

1       phenomenon, is it safe to say that Progress is

2       mitigating the approval risk on that issue in the same

3       manner in which it's addressing the core flood line

4       break?

5                 THE WITNESS:  Yes.  I agree.  By installing

6       this modification, the exemption risk for requiring a

7       manual action in this case is eliminated and that risk

8       no longer exists.

9                 COMMISSIONER SKOP:  Okay.  And moving on to

10       Page 17, Lines 4 through 19, they talk about again the

11       small break loss of coolant accident and how the company

12       has addressed it.  And in relation to that, would it be

13       fair to say that Progress has found precedent by virtue

14       of a modification that has been installed on another B&W

15       plant and that it's using that precedent to essentially

16       qualify by extension the same modification?

17                 THE WITNESS:  That is correct.  We're

18       installing equipment that has been used for accident

19       transients at another B&W facility and is part of their

20       technical specifications as approved by the NRC using

21       similar equipment to mitigate the small break LOCA

22       transient at Crystal River 3.

23                 COMMISSIONER SKOP:  Okay.  And then finally on

24       the fourth issue that was identified, Page 18, Lines

25       1 through 10, with respect to the control rod ejection

FLORIDA PUBLIC SERVICE COMMISSION

1723

1       analysis, is it correct to understand that Progress has

2       submitted a separate LAR which, when approved by the

3       NRC, will close this issue?

4                 THE WITNESS:  That is correct.  And my

5       understanding of the status of that LAR is that the

6       safety evaluation has been written by the NRC and it's

7       in its approval process.  So the technical review has

8       already been complete on that license amendment.

9                 COMMISSIONER SKOP:  Okay.  So going, going

10       back to Page 14 in relation to the concerns expressed by

11       Dr. Jacobs, would it be fair to say that Progress is

12       aware of each of those concerns and working prudently to

13       address those concerns to mitigate any regulatory

14       approval risk?

15                 THE WITNESS:  I agree completely.

16                 COMMISSIONER SKOP:  All right.  Thank you.

17                 CHAIRMAN CARTER:  Thank you.

18                 Commissioners, anything further from the

19       bench?

20                 Redirect?

21                 MS. TRIPLETT:  No redirect.  And we would move

22       Exhibit 109 into evidence.

23                 CHAIRMAN CARTER:  Any objections?  Without

24       objection, show it done.

25                 (Exhibit 109 admitted into the record.)

FLORIDA PUBLIC SERVICE COMMISSION

1724

1                 Chris, give me a little volume.  Let's move

2       now with Witness Furman that the parties have stipulated

3       to.

4                 MS. TRIPLETT:  Yes, sir.  We would request

5       that the prefiled rebuttal testimony for Gary Furman be

6       moved into the record as though read.  Entered into the

7       record as though read.

8                 CHAIRMAN CARTER:  That's correct, right, a

9       stipulation on this witness?

10                 The prefiled testimony of the witness will be

11       inserted into the record as though read.

12                 MS. TRIPLETT:  He has one exhibit, Number 110,

13       on the Comprehensive Exhibit List.

14                 CHAIRMAN CARTER:  Any objections to Exhibit

15       110?  Without objection, show it done.

16                 (Exhibit 110 marked for identification and

17       admitted into the record.)

18                 THE WITNESS:  Excuse me.  May I be excused?

19                 MR. BREW:  No.  You stay right there.

20                 (Laughter.)

21                 MS. TRIPLETT:  I'm sorry.  Mr. Chairman, may

22       Mr. Franke be excused from the remainder of the

23       proceeding?

24                 CHAIRMAN CARTER:  Thank you, Mr. Franke.

25                 THE WITNESS:  Thank you, Chairman.

FLORIDA PUBLIC SERVICE COMMISSION

1727

1                 CHAIRMAN CARTER:  Now let's move to Witness

2       Garrett on the rebuttal.

3                 MS. TRIPLETT:  We would request that his

4       rebuttal testimony be entered into the record as though

5       read.

6                 CHAIRMAN CARTER:  And it's my understanding

7       from the parties that this witness has been stipulated

8       to on rebuttal; is that correct?  Is that correct,

9       gentleman?

10                 Okay.  The prefiled testimony of the witness

11       will be inserted into the record as though read.

12                 Were there exhibits for Witness Garrett?

13                 MS. TRIPLETT:  Yes, sir.  111 through 113.

14                 CHAIRMAN CARTER:  Are there any objections?

15       Without objection, show it done.

16                 (Exhibits 111 through 113 marked for

17       identification and admitted into the record.)

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1731

1                 CHAIRMAN CARTER:  Okay.  Call your next

2       witness.

3                 MR. WALLS:  We call Garry Miller.

4                             GARRY MILLER

5       was called as a witness on behalf of Progress Energy

6       Florida and, having been duly sworn, testified as

7       follows:

8                          DIRECT EXAMINATION

9       BY MR. WALLS:

10            Q.   Mr. Miller, would you please introduce

11       yourself again to the Commission and provide your

12       business address?

13            A.   Yes.  My name is Garry Miller.  My address is

14       100 East Davie Street, Raleigh, North Carolina.

15            Q.   And I believe you've already been sworn in;

16       that's correct?

17            A.   That's correct.

18            Q.   Okay.  Who do you work for and what is your

19       position?

20            A.   I work for Progress Energy Carolinas, and my

21       position is General Manager, Nuclear Plant Development.

22            Q.   And have you filed prefiled rebuttal testimony

23       with exhibits in this proceeding?

24            A.   I have.

25            Q.   Okay.  And do you have that with you?

FLORIDA PUBLIC SERVICE COMMISSION

1732

1            A.   I do.

2            Q.   Okay.  Do you have any changes to make to this

3       prefiled rebuttal testimony and exhibits?

4            A.   I do.  There are two typos I would like to

5       correct.  The first typo is on Page 20 of my rebuttal

6       testimony.  It's on Line 21.  The date should be

7       May 1st, 2009.  The second correction is on Page 49 on

8       Line 22.  Again it's a date error, May 1st, 2009.

9            Q.   And with these changes, Mr. Miller, if I asked

10       you the same questions in your prefiled rebuttal

11       testimony today, would you give the same answers?

12            A.   Yes, I would.

13                 MR. WALLS:  We request that the prefiled

14       rebuttal testimony be moved into evidence as if it was

15       read in the record today.

16                 COMMISSIONER EDGAR:  The prefiled rebuttal

17       testimony of this witness will be entered into the

18       record as though read with the changes noted by the

19       witness.

20                 MR. WALLS:  And I believe we have exhibits for

21       identification for Mr. Miller that are Number 114

22       through 123.

23                 COMMISSIONER EDGAR:  So noted.  Thank you.

24                 (Exhibits 114 through 123 marked for

25       identification.)

FLORIDA PUBLIC SERVICE COMMISSION

1786

1       BY MR. WALLS:

2            Q.   Mr. Miller, do you have a summary of your

3       rebuttal testimony?

4            A.   I do.

5            Q.   Would you please provide that?

6            A.   Yes.  The Intervenors make two claims in this

7       proceeding regarding the Levy project.  First, they

8       claim PEF should not have signed the EPC agreement when

9       PEF did at the end of 2008.  They also claim PEF has not

10       demonstrated that the completion of the Levy nuclear

11       power plants is feasible.  Neither claim has any merit.

12                 PEF's execution of the EPC agreement in

13       December 2008 was a reasonable and prudent management

14       decision.  Execution of the EPC agreement at that time

15       was beneficial to PEF and its customers for the reasons

16       explained in my testimony.  Execution of the EPC

17       agreement was also necessary to move the LNP project

18       forward on schedule.

19                 Finally, execution of the EPC agreement

20       provided the necessary framework to address the schedule

21       shift that did occur in an established, orderly and

22       reasonable manner that has benefited PEF and its

23       customers.

24                 Second, the completion of the Levy nuclear

25       power plants is feasible.  There is no reason to believe

FLORIDA PUBLIC SERVICE COMMISSION

1787

1       the Westinghouse AP1000 reactor design cannot be

2       installed at the Levy site, and there is no reason to

3       believe that we cannot obtain the necessary regulatory

4       permits and licenses for the LNP.

5                 Finally, there is no reason to believe that

6       the cost or reasons for the LNP have fundamentally

7       changed.

8                 PEF did not and cannot determine the

9       feasibility of completing the Levy nuclear power plants

10       based on a year-to-year change in load and fuel forecast

11       as the Intervenor suggests.  If that was the feasibility

12       test, no long-term baseload project including any

13       nuclear power plant would ever be built.

14                 I will briefly address the NRC letter

15       identified by SACE witness Mr. Gundersen as a late

16       exhibit.  Mr. Gundersen claims the letter proves his

17       point that the NRC review schedule for the LNP is not

18       realistic.  Quite simply, Mr. Gundersen does not

19       understand our COL review schedule.  We had float in the

20       NRC review schedule with respect to the AP1000 design

21       certification amendment and the referenced COLA, which

22       should help mitigate the effect of recent changes to

23       these specific schedules.  We will incorporate any COL

24       schedule changes into the revised Levy schedule and

25       associated change order to the EPC agreement that we are

FLORIDA PUBLIC SERVICE COMMISSION

1788

1       currently negotiating with the consortium.  Thank you.

2                 MR. WALLS:  We tender the witness for cross.

3                 CHAIRMAN CARTER:  Mr. Rehwinkel.

4                 MR. REHWINKEL:  Thank you, Mr. Chairman.  And,

5       no, I'm not going to say no questions.

6                 CHAIRMAN CARTER:  I would have been

7       disappointed if you said no questions.  You're

8       recognized, sir.

9                 MR. REHWINKEL:  Thank you.

10                          CROSS EXAMINATION

11       BY MR. REHWINKEL:

12            Q.   Good afternoon again, Mr. Miller.

13            A.   Good afternoon.

14            Q.   Can I ask you to turn to Page 12 of your

15       testimony.

16            A.   Okay.  I'm there.

17            Q.   Actually, I apologize, let's go to Page 11 and

18       lines, start with Lines 17 through 20.

19            A.   I'm there.

20            Q.   Okay.  Why is it not true that your surprise

21       that the NRC -- strike that question.

22                 Let me, let me go and ask you about the

23       December 2008, December 4th, 2008, meeting.  I think you

24       testified yesterday you were unaware of the statements

25       that were made at this meeting by Mr. Anderson; is that

FLORIDA PUBLIC SERVICE COMMISSION

1789

1       correct?

2            A.   Yes.  I believe I might have said I didn't

3       recall that because his statement was not remarkable at

4       the time.  It would be something we would expect him to

5       say, so I just didn't recall that he said it.  I was

6       present at the meeting.

7            Q.   Okay.  So after he said it, did you

8       communicate to anyone in the management that he had said

9       that?

10            A.   I did not.  There were other management

11       present at the meeting.  Again, it was -- his comment is

12       what we would expect based on ongoing dialogue with the

13       NRC through the year.

14            Q.   Did you report this statement in any report to

15       management?

16            A.   I did not.

17            Q.   Does this statement by the NRC show up in any

18       LINC document, L-I-N-C?

19            A.   I do not know.

20            Q.   You seem to have a very good memory.  Do you

21       recall it being in one?

22            A.   I do not recall seeing it in a LINC one, but I

23       cannot validate that.

24            Q.   But you wouldn't be surprised if it doesn't

25       show up in any LINC document, would you?

FLORIDA PUBLIC SERVICE COMMISSION

1790

1            A.   I just don't recall.

2            Q.   Okay.  What about the NPD reports that you

3       were responsible for preparing and submitting to

4       management; did it show up in any of those?

5            A.   No, it would not.  But, again, let me point

6       out his comment was not remarkable to us when he said

7       it.  That's what we would expect him to say based on

8       industry understanding of what the LWA process would

9       take.

10            Q.   Is it your testimony that you relied on this

11       statement in any way in making decisions about signing

12       the EPC?

13            A.   It is, it is not my testimony that that's the

14       case.  It's my testimony that that's just another

15       example of how the NRC continued to reinforce that LWAs

16       were viable regulatory vehicles for our project, and

17       clearly he said it three weeks before we executed the

18       EPC.

19            Q.   How many LWAs have been approved under the LWA

20       rule that he was referring to in his statement?

21            A.   At the time he made the statement?

22            Q.   Yes.

23            A.   At that point there was only one LWA under

24       review other than ours.

25            Q.   Okay.  So there were not LWAs that they were

FLORIDA PUBLIC SERVICE COMMISSION

1791

1       referring, that he was referring to when he made this

2       statement; is that correct?

3            A.   I'm not sure what your question means, sir.

4            Q.   In the, in the plural.

5            A.   Let me go to my portion of the testimony where

6       I actually have captured his comment directly.

7            Q.   Okay.

8            A.   And read it.

9            Q.   And where is that?

10            A.   I can get it.  It's also in the -- there's an

11       exhibit to my testimony, it's GM-9, which has the

12       transcript in it.

13            Q.   Okay.

14            A.   He was answering questions regarding when

15       could work start at the site, and he answered the

16       question in the context of what was governed by the LWA.

17       And so he made a comment, and I'm trying to locate it in

18       my testimony here.  And I want to make sure I say it

19       correctly, so if you'll stand by.

20                 MR. WALLS:  Mr. Miller, if you'd turn to Page

21       28 of 29 of that exhibit.

22                 THE WITNESS:  Of the GM?  Thank you.

23                 MR. REHWINKEL:  Where are you looking?

24                 CHAIRMAN CARTER:  I think he said Page 29.  28

25       and 29 I think it was.

FLORIDA PUBLIC SERVICE COMMISSION

1792

1                 THE WITNESS:  All right.  It starts on Page 28

2       of Exhibit GM-9.  And so this was -- so let me explain

3       the backdrop of this.  This was a draft environmental

4       EIS scoping meeting.  In other words, the meeting was

5       the NRC to the public where they were soliciting input

6       for the development of the environmental impact

7       statement for the Levy site.  So this meeting is NRC to

8       public.  However, because of the importance of this

9       meeting, obviously we were there.  And it was on the

10       subject of the Levy project.

11                 He was, he was getting questions associated

12       with when could work start at the Levy site, and he

13       answered in the context of what was restrained by the

14       limited work authorization.  So he made the comment, and

15       it shows up in GM-8 (sic.) on Page 28 of 29, starting at

16       Line 19, "Just to give you a ballpark time frame, we

17       expect that somewhere on the order of two years will be

18       required to complete our entire review process for the

19       limited work authorization.  And that's a ballpark time

20       frame."  And his comments continue.

21            Q.   Okay.  Now you have attached, have you not, a

22       portion of a transcript here, the last page of the

23       transcript?

24            A.   Of GM-9?

25            Q.   Yes.  I'm talking about of the actual

FLORIDA PUBLIC SERVICE COMMISSION

1793

1       transcript itself.  I can't read that.  Is that Page 33

2       is the last page and you're reading from Page 32?

3            A.   Yes.

4            Q.   Okay.  And the page before that is Page 26?

5            A.   It appears to be the case.

6            Q.   Okay.  What was the question that was asked

7       and why didn't you include that?

8            A.   The question, it shows up at the top of the

9       page I was reading from.  "Will they be able to start

10       work on the site like the middle of next year once the

11       state issues the permit to do aux buildings, roads and

12       stuff like that to the site, or will it be a longer

13       process than that?"

14                 Then Mr. Cameron, who was the facilitator of

15       the public meeting, responds.  And then he proceeds on

16       with the, Mr. Anderson answering the question.

17            Q.   Well, who asked the question?

18            A.   I don't have the full transcript here with me

19       at the table.  I just have specific pages out of it as

20       my exhibit.

21            Q.   Now how many times did you or your staff meet

22       with NRC staff and, about the LWA once you filed it on

23       September -- filed it completely on September 11, 2008?

24            A.   I would have to go back and count these up.

25       But we had a meeting after the COL submitted on

FLORIDA PUBLIC SERVICE COMMISSION

1794

1       July 30th, so we had a meeting the following month to do

2       an overview of the COL application and all its

3       constituent parts.  We had a management meeting on

4       September 9th where I attended and our chief nuclear

5       officer, went to the NRC to meet with the NRC leadership

6       on that.  And then we then had obviously a telecon on

7       September 5th to discuss the scope of the LWA, and then

8       we refined that and submitted that September 12th.

9                 And then later in the year, late November,

10       early December time frame, Mr. Jeff Lyash, who was the

11       CEO and President of Progress Energy Florida at the

12       time, along with Bill Johnson, our CEO and President of

13       Progress Energy, Inc., traveled to Washington, D.C., to

14       meet with NRC leadership and certain -- and specific

15       commissioners on our project.

16            Q.   Now at any of those meetings you've just

17       listed did you ask the NRC or the NRC staff when they

18       would be able to give you a decision on the LWA review

19       schedule?

20            A.   I'm not sure if, if the question you asked is

21       the exact way the, the dialogue went.  We submitted our

22       application, and then we had obviously discussions on

23       the LWA scope.  And then until we got into the October

24       6th letter then had questions on, that we had to respond

25       to that we submitted on November 20th, then there became

FLORIDA PUBLIC SERVICE COMMISSION

1795

1       when are we going to receive a schedule?  We did not

2       expect to see the schedule until after we had submitted

3       the RAI responses that were embodied in the October 6th

4       letter.  But after we submitted them, we continued to

5       ask when we would receive the schedule.

6            Q.   What did they tell you?

7            A.   Well, actually it was sort of a sliding

8       schedule.  First it was expected to be in December, then

9       in, then in January of '09.

10            Q.   Okay.  But I'm asking you did you ask them how

11       long it would take them to review your, your, your LWA?

12            A.   I'm sure we had that dialogue in meetings, but

13       I cannot recall on any specific date of when because it

14       was in the context of how it related to an EIS.

15                 And let me explain what I'm saying is an

16       applicant can pursue an LWA with either a partial EIS or

17       a full EIS.  We concluded that the partial EIS had the

18       potential to be challenged and intervened on and certain

19       NRC staff didn't support it.  So because of that, that

20       date, which takes approximately 22 to 24 months to

21       create an EIS, will constrain the ability to issue an

22       LWA.  So in theory you could actually finish the LWA

23       safety evaluation analysis but you cannot issue it

24       because you need the EIS before you can do it.  So

25       that's where the dialogue of 24 months comes from that's

FLORIDA PUBLIC SERVICE COMMISSION

1796

1       typical in the industry because of the waiting for a

2       full EIS.

3            Q.   So in your conversations with the NRC or the

4       NRC staff did they tell you 24 months?

5            A.   I'm sure we had discussions and they said that

6       probably is a typical number.  But I cannot recall

7       specific days because it was generally something that

8       was assumed in the industry.

9            Q.   So you did not make any specific inquiries

10       about how long it would take your LWA to be reviewed and

11       a decision received from the NRC?

12            A.   Oh, I'm sure we did that because I know as an

13       example we probably did it at the February meeting where

14       we had the Army Corps of Engineers there present because

15       they were a partner, if you will, that would make a

16       decision that would tier off the EIS.  And the whole

17       purpose of having that discussion was to facilitate the

18       EIS being completed to support an LWA.

19                 But what I cannot do is give you a specific

20       date and a specific conversation because it was an

21       ongoing dialogue on this subject.

22            Q.   Okay.  Let me be clear.  I'm asking after you

23       filed your, your COLA and supplemented it with your

24       September 12th LWA did you ask the NRC staff or the NRC

25       when you would -- how long it would take them to review

FLORIDA PUBLIC SERVICE COMMISSION

1797

1       your LWA and give you a decision?

2            A.   Yes.  In regard to your specific question, I

3       believe at the September 9th meeting where we went to

4       Washington, D.C., myself and our, our Chief Nuclear

5       Officer, Jim Scarola, I believe we had that discussion,

6       and we probably asked the question and we talked about

7       the schedule.

8            Q.   And what did they tell you?

9            A.   I don't recall anything remarkable from the

10       conversation other than they were going to review the

11       schedule once they made the decision on the docketing.

12            Q.   So isn't it true they did not answer your

13       question about -- they did not give you a time frame?

14            A.   They would not give us a specific commitment

15       because until the COL is docketed and they confirm the

16       sufficiency and technical adequacy of the COL, they're

17       not going to make a commitment on any schedule.

18            Q.   Okay.  And that docketing occurred on October

19       6th, or at least that's when you found out about it.

20            A.   It was actually docketed officially on October

21       6th.  We were given notification prior to that.

22            Q.   Okay.  From that point forward did you ask

23       them how long it would take for your LWA to be reviewed?

24            A.   We probably -- I don't know if we specifically

25       asked that question other than the broader question of

FLORIDA PUBLIC SERVICE COMMISSION

1798

1       when will we get this schedule that has all three dates

2       in it, the EIS, LWA and the COL?

3            Q.   So you were more concerned about when you'd

4       get the letter than what the time frame for review of

5       the LWA would be?

6            A.   No, sir.  What my point is, we wanted all

7       three dates because all three were important to the

8       overall timeline.  We did not focus on any one of the

9       three in particular because all three were assumptions

10       in our logic of our schedule.

11            Q.   Okay.  But you are saying that you did not ask

12       after October 6th directly to the NRC or the NRC staff

13       how long it would take them to review your LWA; is that

14       your testimony?

15            A.   I don't recall specifically in any forum that

16       dialogue.  We clearly had ongoing questions to them when

17       will we get our schedule and, you know, and obviously we

18       wanted all three dates.

19            Q.   But it was important for you to ask on

20       September 9th about that.  You had that, you and

21       Mr. Scarola had that conversation with, I assume, senior

22       NRC officials; is that correct?

23            A.   That's correct.  But we had that same

24       discussion on EIS, LWA and COL --

25            Q.   But you did not --

FLORIDA PUBLIC SERVICE COMMISSION

1799

1            A.   -- because all three dates were important.

2            Q.   I'm sorry.  But you did not have that

3       conversation as you can recall after October 6th.

4            A.   After October 6th I personally was not in a

5       meeting in Washington where I had a one-on-one

6       discussion of that.  However, as I stated, we continued

7       to ask the NRC project manager, Brian Anderson, when we

8       would receive our schedule for all three dates because

9       all three were important.  And then the meeting I

10       referred to earlier of Mr. Lyash and Mr. Johnson

11       traveling to Washington, I was not present at that

12       meeting, so I cannot comment on the discussion at that

13       meeting.

14            Q.   You never asked Mr. Anderson?

15            A.   Mr. -- sir, I don't understand your question.

16            Q.   Well, let me finish it.  You never -- so -- I

17       just want to be clear because this is important.  I want

18       to ask you never asked Mr. Anderson how long it would

19       take to review your LWA after October 6th.

20            A.   I don't recall the specific dates that I would

21       have had that conversation.  But we had ongoing

22       dialogue, just not in publicly noticed meetings or

23       drop-ins in Washington, D.C.  We would -- we had calls,

24       my licensing manager and myself, and we would talk about

25       it, but we were waiting for the date of all three dates,

FLORIDA PUBLIC SERVICE COMMISSION

1800

1       EIS, LWA and COL.

2            Q.   Let me ask you this this way.  If you had

3       received information, somebody from Progress had

4       received a statement from Mr. Anderson or someone senior

5       enough to rely upon their statement that the LWA would

6       be considered over a certain time frame, wouldn't that

7       have been reported in one of the important management

8       documents that you've discussed in your testimony?

9            A.   I'm not sure what your question means, sir.

10       Ask it again, please.

11            Q.   Okay.  If Mr. Anderson had given you a time

12       frame for review of your LWA between October 6th and

13       December 31st, 2008, wouldn't that have been reported in

14       a, in a management report?  Wouldn't that have been

15       significant enough to report?

16            A.   It would only be significant if it was greatly

17       different than what we expected.  So if he would have

18       called and said instead of 30, let's say instead of 24

19       or 30 months to get this approval, we believe it's going

20       to take 42, like which is what's played out, we would

21       certainly have notified management promptly of that

22       information.

23            Q.   Okay.  Do any of the management reports that

24       you provided, let's start with the NPD report, does it

25       state anywhere in there that you expected to get an LWA

FLORIDA PUBLIC SERVICE COMMISSION

1801

1       in 24 months?

2            A.   The, the actual schedule that was actually

3       embodied in the IPP actually assumes that as part of our

4       regulatory approval process based on when the LWA work

5       is, is shown as starting in the field.

6            Q.   So was -- is it correct then that Progress

7       Energy Florida's management strategy was that no news is

8       good news about the LWA schedule?

9            A.   No, sir.  I disagree with that connotation.

10       We had, as evidenced by our, all the information we

11       provided under interrogatories, we had many interactions

12       with the NRC both in publicly noticed meetings, in

13       management drop-ins, in routine conversations on

14       telephone calls.  And so I would not characterize it the

15       way you did.

16            Q.   Did -- would you have been surprised if the

17       NRC staff would have told you their time frame for

18       review of your LWA in advance of, of the written

19       document that you ultimately received on February 18th?

20            A.   In essence they did do that by calling us

21       January 23rd, sir.

22            Q.   Okay.  Would you have been surprised if they'd

23       have told you that before January 23rd?

24            A.   I don't understand your question.

25            Q.   Well, they communicated to you on January 23rd

FLORIDA PUBLIC SERVICE COMMISSION

1802

1       because they had decided it; correct?

2            A.   That's correct.

3            Q.   Okay.  And the letter you got afterwards

4       really was just putting it in writing; isn't that

5       correct?

6            A.   It is except for the fact we tried to

7       intercede after we got the January 23rd call to change

8       the outcome of the February 18th letter.

9            Q.   Okay.  But January 23rd was essentially when

10       they had made their decision.

11            A.   I'm not sure when internally they made the

12       decision.  But on January 23rd they communicated that

13       decision to us via telecon.

14            Q.   Okay.  And that was, that was an official act

15       on their part.  It was not an informal notification; is

16       that correct?

17            A.   I would consider that official because of the

18       people that were on the phone on both sides.  It was a,

19       an important call.

20            Q.   Okay.  So let me ask my question again.

21       Wouldn't you have been surprised if you would have

22       learned on an informal basis what your review schedule

23       was from the NRC staff?

24            A.   Are you asking me would I have expected to

25       hear this informally in advance of an official call?  Is

FLORIDA PUBLIC SERVICE COMMISSION

1803

1       that your question?

2            Q.   Yes.  Yes.

3            A.   I would not expect to hear that because the

4       NRC processes are very deliberate and very, very, if you

5       will, systematic in how they do that.  And their

6       management that reviewed the schedule and made a

7       decision to issue it and authorize Brian Anderson to

8       send it, send it out probably came to a decision-making

9       that culminated in calling us.

10            Q.   Okay.  So isn't it correct then that on

11       December 4th, 2008, Mr. Anderson was not making a

12       statement that rose to the level of significance or as

13       an official act of the agency with respect to the LWA

14       schedule, review schedule?

15            A.   State your, state your question again, please.

16            Q.   Isn't it true that the statement by

17       Mr. Anderson on December 4th to a member of the public

18       did not rise to the level of official, of an officially

19       authorized act of the NRC with respect to your LWA

20       review schedule?

21            A.   He was not making an official notification to

22       us by what he said.  However, as a project manager over

23       the Levy Nuclear Plant representing the NRC in a public

24       forum answering questions to the public, he represented

25       NRC staff when he said that and represented the

FLORIDA PUBLIC SERVICE COMMISSION

1804

1       knowledge of obviously what he had at the time of how an

2       LWA would be processed.

3            Q.   Now was -- do you have any knowledge, any

4       special knowledge about whether Mr. Anderson was making

5       a statement based on kind of generically how they plan

6       to handle LWAs or specifically how they were going to

7       handle yours?

8            A.   In the context of the way the question was

9       asked, the question was asked about our site and the

10       start of work on our site.  So I would have to read from

11       his transcript that he was answering a question with

12       Levy as the backdrop of what he was answering.

13            Q.   Okay.  So let's go to that statement again.  I

14       know you read it out loud.  But on Page 28 of 29 of your

15       exhibit he uses the term "ballpark" on Line 19, does he

16       not?

17            A.   He does.

18            Q.   Okay.  Is that generally the way NRC

19       communicates review schedules to the company?

20            A.   No.  The actual official review schedule is

21       much more specific and has milestone dates with a

22       specific day of the month.

23            Q.   Okay.  And that's because there is an

24       expectation by the industry, you've got a lot of money

25       involved in this, to have some, some ability to rely on

FLORIDA PUBLIC SERVICE COMMISSION

1805

1       these dates; correct?

2            A.   That's correct.

3            Q.   Okay.  And in the next line, Line 20, he uses

4       the word "somewhere," well the phrase "somewhere on the

5       order of."  Does that imply any specificity or

6       preciseness of time frame?

7            A.   That's a judgment of what "somewhere on the

8       order" means "of two years."

9            Q.   Okay.  You're building a 17-plus billion

10       dollar nuclear plant.  That's not precise for your

11       purposes, is it?

12            A.   It's not precise, but I do not read that as

13       42 months.

14            Q.   Okay.  And then on Line 23, or 22 and 23 he

15       closes by recap, recapping, "And that's a ballpark time

16       frame."  Correct?

17            A.   That's correct.

18            Q.   Okay.  So and ballpark and time frame again do

19       not connote any level of specificity; right?

20            A.   Again, they do not.  However, they also do not

21       suggest 42 months.

22            Q.   Now let's go look above that.  I guess this is

23       Mr. Anderson again talking in the paragraph above.  And

24       on Line 15 he says, "And, like I said, we're still

25       developing the complete review schedule.  And once that

FLORIDA PUBLIC SERVICE COMMISSION

1806

1       review schedule is completed that will be publicly, made

2       publicly available."  Do you see that?

3            A.   I do.

4            Q.   Okay.  So he's -- before he gives you this

5       ballpark, somewhere on the order of statement, he's

6       stating that they haven't finished their developing the

7       schedule; right?

8            A.   That's correct.

9            Q.   Okay.  And then again after on Lines 23, 24

10       and then on to the next page, he says, "The detailed

11       review schedule activities will be made publicly

12       available once we've completed the development of our

13       schedule."  Correct?

14            A.   That is correct.

15            Q.   So again he's reiterating that there's no

16       finality to any decision-making with respect to the

17       schedule; correct?

18            A.   As of December 4th he is stating that it is

19       not final, the schedule is not.

20            Q.   Okay.  Would you go back to Page 12 of your

21       rebuttal testimony, please?

22            A.   Okay.

23            Q.   On Lines 5 through 7 you state that Dr. Jacobs

24       says that PEF should have either eliminated all risks or

25       waited until PEF had certainty.  Do you see that?

FLORIDA PUBLIC SERVICE COMMISSION

1807

1            A.   I do.

2            Q.   Where does Dr. Jacobs say that they should

3       have eliminated all risks?

4            A.   I would have to go back and look in his

5       deposition and locate that information.  I don't recall

6       the specific line.

7            Q.   Well, can I, can I give you a copy of his

8       deposition and ask you -- do you have it with you?

9            A.   I do.

10            Q.   Okay.  Can you tell me where that is?

11            A.   If you'll stand by, I will see if I can locate

12       that.

13            Q.   Okay.

14                 (Pause.)

15                 MR. WALLS:  If it will help move things along,

16       we could look this up at lunch and come back and provide

17       it.

18                 MR. REHWINKEL:  That's fine with me.

19                 THE WITNESS:  It's a long document.  Sorry.

20                 MR. REHWINKEL:  I don't mind getting the

21       answer to that.

22                 THE WITNESS:  Okay.  You want to take me to

23       the page?

24       BY MR. REHWINKEL:

25            Q.   Can you look on Page 143 of your testimony, of

FLORIDA PUBLIC SERVICE COMMISSION

1808

1       your -- of Mr. Jacobs' deposition?

2            A.   Can you give me another number sequence?

3       It's -- oh, I see.  Page, I have 78.  There it is

4       right -- I don't have Page 143 with me.  My exhibit only

5       has through 120.

6                 MR. REHWINKEL:  Okay.  Can I approach and hand

7       him the deposition?  Before I do that, I need to consult

8       with counsel.

9                 (Pause.)

10                 Mr. Chairman, due to the potential for

11       Mr. Miller to rely on -- I don't know what he's going to

12       say, but the potential for him to rely on confidential

13       information to answer this question, I'm willing to move

14       on to another line.

15                 CHAIRMAN CARTER:  Move on.

16                 MR. REHWINKEL:  And get this answer at some

17       point further after they've had a chance to look it

18       over.

19                 CHAIRMAN CARTER:  Okay.  Move on.

20                 MR. REHWINKEL:  Thank you.

21       BY MR. REHWINKEL:

22            Q.   Okay.  Okay.  I want to ask you on Page 13,

23       well, Page 12 and 13 of your testimony some questions

24       that you may need to point to the answers to.

25            A.   Okay.

FLORIDA PUBLIC SERVICE COMMISSION

1809

1            Q.   Or paraphrase as you, if you're aware of doing

2       it appropriately.

3                 On Line 4 of Page 13 you describe a certain

4       action that you believe would not have occurred.  Do you

5       understand my question there?

6            A.   I believe I do.  Are you talking about the

7       first few words in Line 4 of Page 13?

8            Q.   Yes.  That and the following "in addition"

9       language there.

10            A.   Yes.

11            Q.   Okay.  Was there any time in 2008 prior to

12       this time frame where a similar statement or condition

13       had been laid down by the consortium?

14            A.   Not the way the one condition that it starts

15       on Page 13, Line 2, where it says, "I was," there.

16            Q.   Yes.

17            A.   That is very specific, and nothing like that

18       had occurred prior.

19            Q.   Was it -- Mr. Chairman, I know the question I

20       need to ask.  It's difficult to ask it with this, this

21       kind of information.

22                 Are you familiar with the date that I have in

23       mind that I'm asking about Mr. Miller?

24            A.   I think I know what you're, what you're

25       thinking about.  Yes.

FLORIDA PUBLIC SERVICE COMMISSION

1810

1                 (Laughter.)

2            Q.   This is going to look bizarre in the

3       transcript.

4                 CHAIRMAN CARTER:  The Lotto drawing was last

5       night.

6                 Is there a way that you can answer the

7       question based upon the confidential information without

8       --

9                 THE WITNESS:  I think I can make some

10       statements that might, that are, that are in the public,

11       not the specific language, but I believe you're asking

12       me a question about the LOI.

13       BY MR. REHWINKEL:

14            Q.   Yes.

15            A.   And some of the language embodied in the LOI.

16            Q.   Yes.

17            A.   And you're asking me is that language like

18       this language?

19            Q.   Yes.

20            A.   And the answer is no.

21            Q.   Was the company given -- I need a thesaurus to

22       get some, some similar kind of words here.

23                 Did a date come and go in 2008 that was

24       analogous to this date?

25            A.   No, sir, not that was analogous to this as

FLORIDA PUBLIC SERVICE COMMISSION

1811

1       represented by Page 13, the statement on Line 2 that

2       started with "I was."

3            Q.   I think I'll, I think I've asked this question

4       to Mr. Lyash in his deposition, so I think I'll try to

5       ask it to him and let you, save you some time on the

6       stand hopefully.

7                 On Page 12, Line 18, you ask a question --

8       there's a question asked there.  Do you see that?

9            A.   Yes, I do.

10            Q.   Okay.  And that's not a confidential question,

11       is it?

12            A.   The question is not confidential.

13            Q.   Okay.  Can you tell me whether the benefits

14       that, that you list in the answer below Line 20 will be

15       preserved in any renegotiation of the EPC or any

16       renegotiation of an amendment to the EPC or change

17       order?

18            A.   The answer to your question is yes.  Because

19       the EPC is still in full effect and what we're doing is

20       negotiating a change order which adjusts certain dates

21       within the EPC agreement, it is our expectation as of

22       today that we would expect these items beginning on row

23       21 of Page 12 and continuing through on Page 13, the

24       bullets, that we would expect those to remain present in

25       the, after the change order is added to the EPC

FLORIDA PUBLIC SERVICE COMMISSION

1812

1       agreement.

2            Q.   Do you have a 100 percent assurance that

3       that's the case?

4            A.   No, sir.  In any negotiation, until it's

5       complete you cannot give a 100 percent.  However, I have

6       been involved in the negotiations and I have not seen

7       any evidence that would suggest that that would happen.

8            Q.   On Line -- on Page 14 -- let me ask you this

9       actually.  Turn on Page 13, the last line there.

10            A.   Line 12?

11            Q.   Yes.  And there is a statement that begins

12       after "senior management," that is confidential.  Do you

13       see that?

14            A.   That is correct.

15            Q.   Okay.  Now the phrase that, that continues on

16       to the next page, the sixth and seventh word there on

17       Line 1, do you see those?

18            A.   Excuse me.  On Line 1 of Page 14?

19            Q.   Yes.  Of Page 14.

20            A.   The sixth word?  I'm sorry.  Your question is

21       what?

22            Q.   Well, if you count the words across including

23       the date as a word --

24            A.   Yes.

25            Q.   Okay.  Do you see those two words, one

FLORIDA PUBLIC SERVICE COMMISSION

1813

1       beginning with an A and the other beginning with a Y?

2            A.   I do.

3            Q.   Okay.  Did anyone suggest that that would be

4       the duration of any extension?

5            A.   I do not understand your question.

6            Q.   Well, was anyone suggesting that that be the

7       time frame that someone should wait?

8            A.   I'm sorry.  I still don't understand your

9       question.

10                 MR. REHWINKEL:  Mr. Chairman, let me consult

11       with staff -- the counsel for the company for a second.

12                 CHAIRMAN CARTER:  Okay.  Take a moment.

13                 (Pause.)

14                 Mr. Rehwinkel, why don't you also take a

15       moment to get with the attorney for the other side so

16       that when we come back, we'll be ready to deal with that

17       other issue that you mentioned that they were going to

18       give you some clarity on.

19                 MR. REHWINKEL:  Okay.

20                 CHAIRMAN CARTER:  Okay.  See you guys at 2:15.

21                 (Recess taken.)

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1814

1       STATE OF FLORIDA    )

:         CERTIFICATE OF REPORTER

2       COUNTY OF LEON      )

3

4                 I, LINDA BOLES, RPR, CRR, Official Commission

Reporter, do hereby certify that the foregoing

5       proceeding was heard at the time and place herein

stated.

6

IT IS FURTHER CERTIFIED that I

7       stenographically reported the said proceedings; that the

same has been transcribed under my direct supervision;

8       and that this transcript constitutes a true

transcription of my notes of said proceedings.

9

I FURTHER CERTIFY that I am not a relative,

10       employee, attorney or counsel of any of the parties, nor

am I a relative or employee of any of the parties'

11       attorneys or counsel connected with the action, nor am I

financially interested in the action.

12

DATED THIS _____ day of _____________________,

13       2009.

14

15                  ________________________________

LINDA BOLES, RPR, CRR

16                 FPSC Official Commission Reporter

(850) 413-6734

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION