487

1                             BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

3                                          DOCKET NO. 100009-EI

4       In the Matter of:

5       NUCLEAR COST RECOVERY CLAUSE.

______________________________/

6

7                               VOLUME 3

8                        Pages 487 through 796

9              ELECTRONIC VERSIONS OF THIS TRANSCRIPT ARE

A CONVENIENCE COPY ONLY AND ARE NOT

10               THE OFFICIAL TRANSCRIPT OF THE HEARING,

THE .PDF VERSION INCLUDES PREFILED TESTIMONY.

11

12       PROCEEDINGS:        HEARING

13       COMMISSIONERS

PARTICIPATING:      CHAIRMAN NANCY ARGENZIANO

14                           COMMISSIONER LISA POLAK EDGAR

COMMISSIONER NATHAN A. SKOP

15                           COMMISSIONER ART GRAHAM

COMMISSIONER RONALD A. BRISÉ

16

DATE:               Wednesday, August 25, 2010

17

TIME:               Commenced at 9:39 a.m.

18

PLACE:              Betty Easley Conference Center

19                           Room 148

4075 Esplanade Way

20                           Tallahassee, Florida

21       REPORTED BY:        LINDA BOLES, RPR, CRR

Official FPSC Reporter

22                           (850) 413-6734

23       APPEARANCES:        (As heretofore noted.)

24

25

FLORIDA PUBLIC SERVICE COMMISSION

488

1                              I N D E X

2                              WITNESSES

3

NAME:                                         PAGE NO.

4

JON FRANKE

5       Cross Examination by Ms. Kaufman               520

6       SUE HARDISON

Direct Examination by Ms. Huhta                531

7       Prefiled Direct Testimony 3-1-10 Inserted      533

Prefiled Direct Testimony 4-30-10 Inserted     557

8       Cross Examination by Mr. Rehwinkel             574

9       KEN KARP

Prefiled Direct Testimony 3-1-10 Inserted      595

10       Prefiled Direct Testimony 4-30-10 Inserted     616

11       DR. MARK COOPER

Prefiled Direct Testimony Inserted             634

12

ARNOLD GUNDERSON

13       Prefiled Direct Testimony Inserted             673

14       WILLIAM R. JACOBS, JR., Ph.D.

Direct Examination by Mr. Rehwinkel            699

15       Prefiled Direct Testimony Inserted             702

Cross Examination by Mr. Walls                 727

16       Cross Examination by Mr. Davis                 737

Redirect Examination by Mr. Rehwinkel          739

17

WILLIAM COSTON and KEVIN CARPENTER

18       Direct Examination by Mr. Young                745

Prefiled Direct Testimony Inserted             748

19       Cross Examination by Mr. Rehwinkel             757

Cross Examination by Mr. Brew                  774

20       Cross Examination by Ms. Kaufman               782

Cross Examination by Mr. Jacobs                784

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

489

1                              EXHIBITS

2       NUMBER:                                    ID.    ADMTD.

3       19                                                   529

4       20                                                   529

5       31   WRJ(PEF)-1                           701        742

6       32   WRJ(PEF)-2                           701        742

7       33   WRJ(PEF)-3                           701        742

8       34   MNC-1                                632        633

9       35   MNC-2                                632        633

10       36   MNC-3                                632        633

11       37   MNC-4                                632        633

12       38   MNC-5                                632        633

13       39   MNC-6                                632        633

14       40   MNC-7                                632        633

15       41   MNC-8                                632        633

16       42   MNC-9                                632        633

17       43   MNC-10                               632        633

18       44   MNC-11                               632        633

19       45   MNC-12                               632        633

20       46   MNC-13                               632        633

21       47   MNC-14                               632        633

22       48   MNC-15                               632        633

23       49   MNC-16                               632        633

24       50   MNC-17                               632        633

25       51   MNC-18                               632        633

FLORIDA PUBLIC SERVICE COMMISSION

490

1                              EXHIBITS

2       NUMBER:                                  ID.      ADMTD.

3       52   MNC-19                               632        633

4       53   MNC-20                               632        633

5       54   AG-1                                 672        672

6       55   AG-2                                 672        672

7       56   AG-3                                 672        672

8       57   AG-4                                 672        672

9       58   AG-5                                 672        672

10       59   AG-6                                 672        672

11       60   AG-7                                 672        672

12       77   Revised CC-1                         747        793

13       191                                                  530

14       193                                                  530

15       194                                                  530

16       195                                                  530

17       196                                                  530

18       197                                                  530

19       198  PRG Minutes and EPV Variance         514        530

Reports

20

199  2009 CR3 Audit                       514        530

21

200  2009 CR3 Audit                       515        530

22

201  March 2009 Uprate Presentation       515        530

23

202  July 2009 Uprate Presentation        515        530

24

203  October 2009 Uprate Presentation     515        530

25

FLORIDA PUBLIC SERVICE COMMISSION

491

1                              EXHIBITS

2       NUMBER:                                    ID.    ADMTD.

3       204  Response to DR-3                     515        530

4       205  Depo Exhibit 2 (Late-Filed)          515        530

5       206  (Confidential) 8-10-10 Depo of       515        530

Jon Franke

6

207  Depo Exhibit 1 (Late-Filed)          519        530

7

208  Janus Interview                      574        592

8

209  LNP Master Plan                      574        592

9

210  Staff Response to PCS ROGs           744        794

10

211  Staff Response to PCS Request for    744        794

11            POD

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

492

1                         P R O C E E D I N G S

2                 (Transcript follows in sequence from

3       Volume 3.)

4                 CHAIRMAN ARGENZIANO:  Okay.  We'll call our

5       meeting to order for this morning, and we will pick up

6       with, I guess, preliminary matters before we go back to

7       our point in our agenda where we left.

8                 MR. YOUNG:  Yes, ma'am.  We'll pick up with

9       the preliminary matters as relates to Commissioner

10       Skop's request.  And I think Ms. Helton had, our General

11       Counsel, Mr. Kiser, is here to respond to those

12       requests, Commissioner.

13                 CHAIRMAN ARGENZIANO:  Yes.

14                 MR. KISER:  Chairman, we did get a phone call

15       this morning, and the, Florida Power & Light will have

16       someone here to respond to the questions that were

17       raised at the end of the meeting regarding making

18       Mr. Olivera available for answering some questions.  So

19       if they have someone, I would recommend we hear from

20       them first off.

21                 CHAIRMAN ARGENZIANO:  Okay.  Why don't we do

22       that now.  I'm going to shift everybody around I guess.

23       Well, we're in place.  Okay.  Very good.

24                 MR. ANDERSON:  Yes.  I believe we're ready to

25       proceed.

FLORIDA PUBLIC SERVICE COMMISSION

493

1                 CHAIRMAN ARGENZIANO:  Okay.  If you would.

2                 MR. ANDERSON:  FPL has been asked to provide

3       its position with respect to a request by Commissioner

4       Skop late yesterday in the middle of Progress's case to

5       have our Chief Executive Officer appear at this hearing.

6       The purpose of this appearance is apparently to answer

7       the Commissioner's questions on matters that, to the

8       limited extent they were described by Commissioner Skop

9       yesterday afternoon, appear nowhere on the issues list

10       in the Prehearing Order.

11                 As you are all well aware, the issues in the

12       Prehearing Order govern the disposition of this case.

13       This is a highly irregular request, it has no legal

14       basis, and would provide a very poor precedent for the

15       Commission.

16                 Permit me to remind the Commission that a week

17       ago FPL filed with the Commission a stipulation to defer

18       consideration of this year's issues into the

19       2011 proceeding.  That stipulation is fully consistent

20       with Commission practice and properly addresses the

21       issues stated in the Prehearing Order.  It is a

22       stipulation which has been filed on behalf of FPL and

23       the Office of Public Counsel and the Florida Industrial

24       Power Users Group.  In addition, the only other

25       Intervenor, the Southern Alliance for Clean Energy, has

FLORIDA PUBLIC SERVICE COMMISSION

494

1       no objection to the stipulation.

2                 So if that stipulation is approved, to be

3       clear, there is no reason for any questions of any

4       witnesses as a legal matter.  But we will come to that

5       stipulation in due course, as I understand, after the

6       conclusion of Progress's case.

7                 Now let me address our concerns with the

8       request by Commissioner Skop to have our Chief Executive

9       Officer appear.

10                 The Administrative Procedure Act and the

11       Commission's rules provide for notice to parties as to

12       the issues in each case.  The Commission has a

13       long-standing procedure for filing prefiled testimony

14       identifying the issues and witnesses that provides a

15       clear roadmap for adjudication of issues before the

16       Commission.  This process implements the requirements of

17       the Administrative Procedure Act to provide notice to

18       parties prior to adjudicatory hearings, which promotes

19       fundamental fairness to all parties.

20                 The purpose of hearings before the Commission

21       is to develop a record and provide information to the

22       Commissioners to inform decision-making.  This

23       Commission has always focused on what is being said and

24       not who is saying it.

25                 Now without the benefit of a specifically

FLORIDA PUBLIC SERVICE COMMISSION

495

1       identified issue, FPL assumes for purposes of this

2       discussion that the issue raised by Commissioner Skop

3       deals with the Concentric report we've talked about.

4       The simple fact is that the Concentric report was

5       provided to audit staff, the Commission and the parties

6       two months ago.  At all times Commissioner Skop has had

7       full and unfettered access to this information.

8                 For the past two months, no party, including

9       Commissioner Skop, has raised any issues regarding the

10       Concentric report.  Moreover, no issue was raised by any

11       party, the staff, Commissioner Skop, prior to or during

12       the Prehearing Conference regarding the report, as

13       required by Commissioner Skop's own Order Establishing

14       Procedure.  Consequently, it should be no surprise that

15       there's no mention of the Concentric report in the

16       August 20, 2010, Prehearing Order issued by Commissioner

17       Skop.

18                 FPL has not been provided notice as to any

19       issue or even the subject of questioning of Mr. Olivera,

20       as required under the law and fundamental principles of

21       due process and fairness.  The complete lack of notice

22       is self-evident.

23                 We'd also point out there is a formal legal

24       process for the issuance of subpoenas by law.  The

25       subpoena would have to be properly served on the

FLORIDA PUBLIC SERVICE COMMISSION

496

1       witness, FPL would have the right to object and litigate

2       at a minimum the relevancy and scope of the subpoena at

3       the Commission and in the appellate courts.  If this

4       route is followed, it would be weeks, if not months,

5       even beyond the balance of the year, before a subpoena

6       could be enforced.  Based on these considerations, it is

7       unlikely that an enforceable subpoena could be issued to

8       compel the appearance of a witness during this week's

9       proceedings.

10                 One could also easily conclude by some of the

11       comments that FPL has been prejudged on the issues

12       without the benefit of testimony or evidence.  I think

13       everyone would agree that the appearance of prejudgment

14       is not good for this Commission or for the reputation of

15       the State of Florida.

16                 Without minimizing the concerns that I've

17       expressed, I wish to also emphasize that FPL places

18       great value in having a cooperative and constructive

19       approach to these important matters before this

20       Commission.  Therefore, we believe there is no need for

21       the Commission to issue a subpoena to compel the

22       appearance of FPL's Chief Executive Officer.

23                 As acknowledged just a few days ago, Friday,

24       by Commissioner Skop, FPL has gone, quote, over and

25       above in good faith, close quote, to add, and I quote,

FLORIDA PUBLIC SERVICE COMMISSION

497

1       transparency, close quote, with respect to FPL's

2       documents for which it had a legitimate claim of

3       confidentiality.

4                 Given the extraordinary nature of this

5       request, we believe it appropriate for the full

6       Commission to provide direction.  If it is the will of

7       the full Commission, then, in the spirit of cooperation

8       and good faith, FPL will have Mr. Olivera appear before

9       the Commission to answer questions germane to this

10       proceeding.

11                 To facilitate that appearance, if it's the

12       will of the full Commission, FPL requests a list as to

13       the specific subjects on which questions will be asked

14       so that Mr. Olivera can adequately prepare.  FPL is

15       making this offer as a good faith gesture in a

16       cooperative spirit and reserves all of its legal

17       arguments, rights and remedies.

18                 CHAIRMAN ARGENZIANO:  If you'd like to, you're

19       recognized.

20                 COMMISSIONER SKOP:  Thank you, Madam Chairman.

21       And thank you, Mr. Anderson, for your thoughts that you

22       shared with the Commission this morning.

23                 Just some brief comments.  The assumptions

24       that you made are inaccurate.  With respect to

25       questioning the impartiality of the Prehearing Officer

FLORIDA PUBLIC SERVICE COMMISSION

498

1       and me as Commissioner, as a member of the Florida Bar,

2       I take extreme exception to your comments.

3                 The question that I presented yesterday was a

4       simple request propounded upon your company.  Your

5       company will either honor the request in good faith or

6       they won't.  So, again, I think that at the end of the

7       day the questions I have are constructive, they're not

8       meant to be inflammatory.  Due process is a two-way

9       street.  And if we want to debate the fine points of due

10       process, I certainly have some concerns that I will get

11       into.

12                 Again, at the end of the day, leadership is

13       set by example, and accountability starts at the top of

14       any organization.  You're fully aware of the documents

15       that were only disclosed as of Friday, and there are

16       other documents that are at issue.  Each of my questions

17       pertain to live issues related to this proceeding and

18       the documentation of the data that's been provided in

19       the, in this proceeding.

20                 So, again, I'm going to leave it as a request.

21       But, again, certainly, you know, from a corporate

22       perspective, it would have been simple enough to just

23       merely honor the request.  But either the company will

24       choose to honor it or they won't.  And if I believe I

25       heard Mr. Anderson correctly, notwithstanding making a

FLORIDA PUBLIC SERVICE COMMISSION

499

1       case to get into the stipulations in this matter, which

2       were filed, if my memory serves me correctly, on the

3       18th or 17th of this month, and I need to check that

4       date, you know, certainly we can get into that.

5                 But what I heard from the company is now

6       they've asked the full Commission to render a decision

7       as to the appropriateness of my questions.  And not only

8       that, prior to producing or making Mr. Olivera

9       available, it's conditioned or predicated upon a

10       specific list of questions.  Again, different companies

11       approach, you know, their interaction with the

12       Commission in different ways.

13                 Knowing some of the issues in this docket,

14       again, if I were similarly situated, I would probably

15       proactively make myself available to this Commission to

16       answer questions.  So I respect FPL's legal position.

17       I'm prepared to, you know, do what the will of the

18       Commission is on this matter.  But I think it's, it was

19       a very simple, reasonable request that apparently got

20       blown out of proportion unnecessarily through additional

21       questioning.

22                 Again, I'm an attorney, I'm a Commissioner, a

23       member of the Bar.  I know, you know, the appropriate

24       questions to ask, and those questions would have been

25       asked with the respect afforded to a person in that

FLORIDA PUBLIC SERVICE COMMISSION

500

1       position.  But at the end of the day, they're fair

2       questions.  And that's basically all I have to say,

3       Madam Chair.  Thank you.

4                 CHAIRMAN ARGENZIANO:  Where does that leave

5       us?

6                 MR. KISER:  Madam Chairman, I take the

7       response from the company is that if the will of the

8       Commission is to have him appear, under the conditions

9       that were stated, they would.  Without that, then they

10       would choose not to present him.  So I think it's a

11       question for the Commission to --

12                 CHAIRMAN ARGENZIANO:  Well, let me ask this

13       question then of Commissioner Skop.  Knowing that the

14       company wants the full Commission to vote on that, does

15       that make a difference to you?  Do you want to just

16       forget it?  Do you want to pursue it?  Let's find out

17       what you would like to do.

18                 COMMISSIONER SKOP:  Again, I have concerns.  I

19       usually, you know, try and show deference to my

20       colleagues.  Obviously, procedurally they've attempted

21       to, you know, basically shift the scales and put the

22       burden on the full Commission vote as to whether they

23       will choose to make him available and which conditions

24       they will make him available under.  And really I didn't

25       really feel that this would get down to a negotiation.

FLORIDA PUBLIC SERVICE COMMISSION

501

1       It was a simple request that should have been honored.

2       You know, I think that, you know, it comes down to, you

3       know, respect for the regulatory process or lack

4       thereof.

5                 So I understand the due process concerns that

6       are raised, but the issues are highly relevant and

7       highly germane to the issues here.  If it is the will of

8       the Commission -- and, again, I apologize to Progress,

9       because, again, under the Order Establishing Procedure,

10       Progress's case in chief was to go first.

11                 I brought this up, correcting what

12       Mr. Anderson represented to the Commission, I brought

13       this up at the end of the day, not in the middle of

14       PEF's case, but as a closing matter for planning

15       purposes.  So that's another exception I take.

16                 But, you know, if it's the will of the

17       Commission, we can take up the stipulation, I can say my

18       piece, the vote will be what it will be, but, or we can

19       address the issue with respect to my request to make

20       Mr. Olivera, you know, ask and see whether he wants to

21       appear.  But apparently that seems to be bogging down

22       into a protracted reluctance on FPL's part to honor what

23       typically would be a simple request.  And I'm reasonably

24       certain if I made the same request upon Progress or

25       another regulated IOU, I wouldn't have this resistance

FLORIDA PUBLIC SERVICE COMMISSION

502

1       under the circumstances.

2                 CHAIRMAN ARGENZIANO:  I'm still not sure where

3       that leaves us.

4                 COMMISSIONER SKOP:  Why don't, why don't we

5       take up the, if it's the will of the Commission, why

6       don't we take up -- because Mr. Anderson, you know, when

7       he spoke, it was supposed to be about my request, but he

8       managed to make a big hoo-ha about this stipulation.  So

9       if we need to have that discussion, we can have it.  And

10       if the Commission decides to approve the FPL

11       stipulations, then I guess it denies me the ability to

12       even ask Mr. Olivera those questions.  So that's

13       probably the better predicate.  And if -- at the Chair's

14       discretion, I'll look to the Chair to figure out what we

15       want to do with respect to proposed stipulations.

16       Because I see this going nowhere and I don't, I don't

17       want to waste Progress's time.

18                 CHAIRMAN ARGENZIANO:  Well, if it's up to me,

19       and everybody else chime in here, what I'd rather do is

20       just continue with Progress's case right now and just

21       move forward.

22                 COMMISSIONER SKOP:  All right.  Very well.

23       And I reserve my rights.  Again, I've made a request.  I

24       guess it's incumbent upon FPL as to whether they choose

25       to honor it or not.  I'll let them make that decision.

FLORIDA PUBLIC SERVICE COMMISSION

503

1                 CHAIRMAN ARGENZIANO:  And then we'll --

2       Commissioner Graham.

3                 COMMISSIONER GRAHAM:  I move that we lay the

4       stipulation on the table and retake up Progress where we

5       left off, and then we can come back and address the

6       stipulation when we're done with Progress.

7                 COMMISSIONER SKOP:  Second.

8                 CHAIRMAN ARGENZIANO:  All those in favor?

9                 (Unanimous affirmative vote.)

10                 Okay.  And I believe that at that time we have

11       a right of, each Commissioner has a right to hear or ask

12       questions that they want to ask, and we'll take it from

13       there.  So let's move on.  Thank you.  Back to our

14       agenda, where we were.

15                 Mr. Rehwinkel?

16                 MR. REHWINKEL:  Yes.  Madam Chairman, after we

17       spent the day going through the testimony and the

18       significant amount of documents, I spent some time last

19       night reviewing the questions that I have for the, for

20       the rest of the case, and I'm fully aware that my

21       questions are probably the real time contributor to us

22       being here.

23                 About two weeks ago I took three depositions,

24       one of Mr. Franke, one of Mr. Lyash, and one of

25       Mr. Elnitsky, and between myself and the other parties,

FLORIDA PUBLIC SERVICE COMMISSION

504

1       we spent most of the day with each witness.  And so

2       there are significant depositions that, testimony that

3       has been provided.

4                 I have approached the parties and the, and the

5       staff about maybe taking a few minutes to sit down and

6       try to work out some protocols for streamlining the rest

7       of the hearing.  And I think everyone is kind of in

8       agreement that if we do so, we could save, we could save

9       a lot of testimony time here.

10                 We're not talking about completely stipulating

11       witnesses in, but narrowing the testimony and the

12       cross-examination and the answers.  And so we would, I

13       think with the consent of everyone, we would ask if we

14       could have maybe 30 minutes to sit down and try to work

15       that out.  To save 30 minutes today, right now would

16       potentially save a lot of time the rest of the day.

17                 CHAIRMAN ARGENZIANO:  I don't see any, any

18       reason why not to.  Why don't we, why don't we do that.

19       Now make sure, because we all get paid a lot of money to

20       sit here and listen, so we'll stay.  If you need to ask,

21       there should be no rush.  But if you feel like you can,

22       you can do that and accommodate, you know, the questions

23       that you have and get it out where you need to get it

24       to, to our ears too, then why don't we just, why don't

25       we just do that, take 30 minutes.  And if you need a few

FLORIDA PUBLIC SERVICE COMMISSION

505

1       more, just --

2                 MR. REHWINKEL:  And let me assure you, I felt

3       no pressure by anyone, the Commission or the other

4       parties, to limit what I'm doing.

5                 CHAIRMAN ARGENZIANO:  Sure.

6                 MR. REHWINKEL:  I just know the nature of

7       these issues are highly technical.  The documentation

8       we're going through is highly technical.  There reaches

9       a point of diminishing returns about what can be

10       explicated in live testimony with technical documents

11       like this.

12                 CHAIRMAN ARGENZIANO:  Sure.

13                 MR. REHWINKEL:  So being aware of that, we're

14       going to try to kind of narrow things down.

15                 CHAIRMAN ARGENZIANO:  Certainly.  And let me

16       just reassure you that I'm just making that comment so

17       you knew that none of us were telling you you had to

18       hurry up.

19                 MR. REHWINKEL:  Thank you.

20                 CHAIRMAN ARGENZIANO:  Okay.  All right.  Let's

21       do that.  Let's take at least 30 minutes.  We'll be

22       back.  Thank you.

23                 (Recess taken.)

24                 Okay.  Let's start her back up.  Commissioner

25       Skop, you're recognized.

FLORIDA PUBLIC SERVICE COMMISSION

506

1                 COMMISSIONER SKOP:  Thank you, Madam Chair.

2       And I apologize for the interruption, but I do believe

3       it's important to correct a prior statement that was

4       made to this Commission.

5                 Mr. Anderson, in his lengthy discussion

6       previously, asserted something, and I would ask the

7       court reporter if she might be so kind to read back four

8       lines that were represented to the Commission by

9       Mr. Anderson.  And that would begin on page 3, lines 24

10       and 25, continuing on to page 4, lines 1 and 2, please.

11                 (Foregoing excerpt read by court reporter.)

12                 Thank you.  And if I may, Madam Chair, to

13       properly rebut that statement that was made to the

14       Commission, I would look to Ms. Harvey from Commission

15       audit staff to speak to when audit staff was provided

16       with the Concentric report and some of the instances

17       surrounding that, as well as my access to that report at

18       that time.

19                 MS. HARVEY:  Commissioners, audit staff

20       requested the Concentric report on May 8th, 2010, and

21       the staff received a copy of the Concentric report on

22       June 23rd, 2010.

23                 COMMISSIONER SKOP:  And, Ms. Harvey, with

24       respect to Commission audit staff receiving such report,

25       I would not have had access to that report at that time;

FLORIDA PUBLIC SERVICE COMMISSION

507

1       is that correct?

2                 MS. HARVEY:  That's correct.

3                 COMMISSIONER SKOP:  Okay.  And I would not

4       have had access to it as a Commissioner until it was

5       properly filed in the docket; is that correct?

6                 MS. HARVEY:  Correct.

7                 COMMISSIONER SKOP:  Okay.  And subject to

8       check, and, Ms. Harvey, if you're not comfortable with

9       this, I'll ask Ms. Bennett from our legal department,

10       but subject to check, the Concentric report was

11       requested by Commission staff in staff's fourth request

12       for production of documents, specifically Document

13       Number 25; is that correct?

14                 MS. HARVEY:  I was not involved in that

15       request.

16                 COMMISSIONER SKOP:  All right.  Thank you,

17       Ms. Harvey.

18                 Ms. Bennett?

19                 MS. BENNETT:  It was, and it was provided on

20       August 17th.

21                 COMMISSIONER SKOP:  Okay.  So I guess what we

22       could reasonably conclude from this, notwithstanding the

23       statements represented to the Commission by

24       Mr. Anderson, was that I indeed did not have full and

25       unfettered access to this report two months ago; is that

FLORIDA PUBLIC SERVICE COMMISSION

508

1       correct?

2                 MS. BENNETT:  The Commissioners are not, don't

3       have access to staff's audit work papers until that's

4       made part of the docket file.

5                 COMMISSIONER SKOP:  Thank you, ma'am.

6                 Thank you, Madam Chair.

7                 CHAIRMAN ARGENZIANO:  Well, let's go one step

8       further.  When was it made part of the docket, what

9       date?

10                 MS. BENNETT:  The, my recollection is that on

11       the day before the prehearing, on August 17 -- 16th --

12       it may have been August 15th, something like that, there

13       was a copy of staff's audit work paper on the Concentric

14       report filed in the docket file.  A few days later,

15       August 16th, 17th, and, again, I would have to go back

16       into CMS to give you the exact dates, but --

17                 CHAIRMAN ARGENZIANO:  Well, can I ask staff a

18       question?  Would someone like Mr. Anderson know that

19       Commissioners don't have access to that?  Because that

20       makes a big difference about what his statement meant.

21       If he doesn't know, then that's a different story.  But

22       if he should know, then that tells me something else.

23                 MS. BENNETT:  I'm not certain what outside

24       parties' understanding of our audit process is and who

25       would have knowledge of Commission staff -- or

FLORIDA PUBLIC SERVICE COMMISSION

509

1       Commissioners' access to staff's work papers.  I don't

2       know that.

3                 CHAIRMAN ARGENZIANO:  So then I guess without

4       asking, it's just an assumption on Mr. Anderson's part

5       that we would have that information.

6                 MS. BENNETT:  Yes.

7                 CHAIRMAN ARGENZIANO:  Okay.  Commissioner

8       Skop, you're recognized.

9                 COMMISSIONER SKOP:  Thank you, Madam Chair.

10       And I'll just make this brief.  Again, it's not at issue

11       is what Mr. Anderson knew.  It's the breadth and

12       cavalierness of the statements made as it pertains to

13       what I knew, which I take again great exception to some

14       of the comments that were made earlier this morning.

15                 And, Ms. Bennett, just one follow-up to the

16       question.  Not to belabor the point, but it's my

17       understanding that the actual Concentric report itself

18       was agreed to be declassified at the evidentiary hearing

19       on the 20th; is that correct?

20                 MS. BENNETT:  That's correct.

21                 COMMISSIONER SKOP:  So until, until the

22       evidentiary hearing on the 20th, the majority of the

23       staff audit report, the Concentric report and the

24       underlying letter were all claimed to be confidential by

25       FPL; is that correct?

FLORIDA PUBLIC SERVICE COMMISSION

510

1                 MS. BENNETT:  Yes.

2                 COMMISSIONER SKOP:  And that was the first

3       time that they were disclosed publicly was August 20th;

4       is that correct?

5                 MS. BENNETT:  Yes.

6                 COMMISSIONER SKOP:  Thank you.

7                 CHAIRMAN ARGENZIANO:  Commissioner Skop, while

8       it may not have been important to you, and I understand

9       the reasons why and I understand what is important to

10       you, but it is important to me of whether he knew or

11       not.  If someone knows that the Commissioners do not

12       have that access, then that was an intentional whatever,

13       and maybe they don't know because -- and that's the

14       reason I asked.  It makes a big difference to me if

15       someone knows ahead of time and then makes that

16       statement while knowing that we don't have that

17       information.  That sends a very, very loud message to

18       me, and it may answer a lot of things that I've seen

19       here and while I've been here.  I'm not sure that's the

20       case though.  That's why I asked the question.  It is

21       important, it is significant.  Okay.

22                 COMMISSIONER SKOP:  Thank you, Madam Chair.

23                 CHAIRMAN ARGENZIANO:  Commissioner Skop, did

24       you --

25                 COMMISSIONER SKOP:  Thank you, Madam Chair.

FLORIDA PUBLIC SERVICE COMMISSION

511

1                 CHAIRMAN ARGENZIANO:  Okay.  Let's, let's put

2       ourselves in the proper posture.  Now that we've, we've

3       gotten this taken care of, I guess, to whatever degree

4       we are and you have corrected that assumption, I guess

5       we are now back on our Progress.

6                 Mr. Rehwinkel.

7                 MR. REHWINKEL:  Thank you, Madam Chairman and

8       Commissioners.  I appreciate your willingness to let us

9       talk because I think it paid off.  I will defer to

10       Ms. Bennett to describe the agreement that the parties

11       have come to to streamline the remaining portions of the

12       Progress segment of the hearing.

13                 CHAIRMAN ARGENZIANO:  Okay.  And I thank all

14       parties for being able to do so.

15                 Ms. Bennett?

16                 MS. BENNETT:  Yes.  We met, and it was

17       actually at the suggestion of OPC to streamline.  The

18       parties have agreed, and if it's at your pleasure,

19       Commissioners, that we finish with Jon Franke, who's on

20       the stand now, his direct only.  Then Sue Hardison,

21       who's also of Progress Energy, will come and provide

22       direct testimony.  I understand that there's limited

23       cross remaining for Ms. Hardison.

24                 Mr. Karp is a Progress witness and he's

25       previously been excused, so all you would need to do is

FLORIDA PUBLIC SERVICE COMMISSION

512

1       admit his testimony and exhibits into the record.

2                 Mr. Elnitsky and Mr. Lyash, Lyash appear next

3       as direct witnesses, but both Progress and the parties

4       have agreed that, instead of putting them on as direct,

5       that they will reserve them until rebuttal and put the

6       direct and rebuttal on together.

7                 So the next witness would be Dr. Mark Cooper

8       from SACE.  And, again, he's been excused, so you would

9       admit his direct testimony and exhibits into the record.

10       Mr. Gunderson is also a SACE witness.  And, again, he's

11       been excused, so you would just admit testimony and

12       exhibits.

13                 Then Dr. William Jacobs, who is OPC's witness,

14       and I understand that there's limited cross, Progress I

15       think has indicated maybe 15 minutes.  Joint testimony

16       of staff witnesses Coston and Carpenter will be next.

17       Again, I think the parties have agreed that there's

18       limited cross, but there is cross-examination of those

19       witnesses.

20                 Then we would move into the PEF rebuttal, with

21       Mr. Franke coming up again for rebuttal, then John

22       Elnitsky for direct and rebuttal together, and finally

23       Jeff Lyash with direct and rebuttal together.

24                 MR. REHWINKEL:  Madam Chairman, I would just

25       add that the Public Counsel's cross-examination of

FLORIDA PUBLIC SERVICE COMMISSION

513

1       Mr. Franke will cease upon the admission of agreed-to

2       exhibits and his deposition and we would go through

3       that.  But I would have no further questions for Mr.

4       Franke, and I think that there would be limited cross

5       from the other parties.

6                 I am not certain whether the cross-examination

7       was intended to occur now or when he came back on

8       rebuttal, but my assumption was it would be now.

9                 CHAIRMAN ARGENZIANO:  Now.  Okay.  Then why

10       don't we just move forward then.  Thank you.

11                 MR. REHWINKEL:  Madam Chairman, I have passed

12       out a set of documents that I would just like to

13       identify for the record and get an exhibit number.  The

14       company is -- while the hearing progresses to

15       conclusion, they will be reviewing the agreed-upon

16       exhibits for confidentiality and will submit to the

17       court reporter -- the, the official record version will

18       be properly highlighted for confidentiality.  But we

19       thought what we'd do is identify for the record the

20       documents, give them a number, and then the

21       administrative work of confidentiality would be taken

22       care of as we go today.

23                 CHAIRMAN ARGENZIANO:  Okay.  Then I believe

24       we're on 198.  Am I correct?  Okay.  198.

25                 MR. YOUNG:  Yes, ma'am.

FLORIDA PUBLIC SERVICE COMMISSION

514

1                 CHAIRMAN ARGENZIANO:  Okay.  And then we can

2       go ahead and do that.  And did you give it a name?  I'm

3       sorry.

4                 MR. REHWINKEL:  Yeah.  So 198 would be, a

5       short title would be PRG Minutes.

6                 (Exhibit 198 marked for identification.)

7                 CHAIRMAN ARGENZIANO:  Okay.

8                 MR. REHWINKEL:  Okay.  The next document would

9       be, I guess, 199, and this would be 2009 CR3 Audit.

10       This is an excerpt from some audit and audit work

11       papers.

12                 CHAIRMAN ARGENZIANO:  Mr. Rehwinkel, are they

13       all to be reviewed for confidentiality?

14                 MR. REHWINKEL:  Yes.

15                 CHAIRMAN ARGENZIANO:  Okay.

16                 MR. REHWINKEL:  Yes, Commissioner.

17                 (Exhibit 199 marked for identification.)

18                 CHAIRMAN ARGENZIANO:  Okay.

19                 MR. REHWINKEL:  The next, 200 would be CR3 EPU

20       IPP.

21                 CHAIRMAN ARGENZIANO:  Eight, was that?  Did

22       you say IP8?

23                 MR. REHWINKEL:  IPP.

24                 CHAIRMAN ARGENZIANO:  IPP.  I'm sorry.  Okay.

25       Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

515

1                 (Exhibit 200 marked for identification.)

2                 MR. REHWINKEL:  And the next one, 201, would

3       be March 2009 Uprate Presentation.

4                 (Exhibit 201 marked for identification.)

5                 CHAIRMAN ARGENZIANO:  Okay.

6                 MR. REHWINKEL:  And for 202, July 2009 Uprate

7       Presentation.

8                 (Exhibit 202 marked for identification.)

9                 CHAIRMAN ARGENZIANO:  Okay.

10                 MR. REHWINKEL:  And for 203, October 2009

11       Uprate Presentation.

12                 (Exhibit 203 marked for identification.)

13                 CHAIRMAN ARGENZIANO:  Okay.

14                 MR. REHWINKEL:  204, response to DR3.

15                 (Exhibit 204 marked for identification.)

16                 CHAIRMAN ARGENZIANO:  Okay.

17                 MR. REHWINKEL:  And 205, deposition Exhibit 2.

18                 (Exhibit 205 marked for identification.)

19                 CHAIRMAN ARGENZIANO:  Okay.

20                 MR. REHWINKEL:  And, Madam Chairman, those

21       are, that is the extent of the exhibits that we have

22       agreed to with the parties on Mr. Franke.  I guess we

23       would need a deposition exhibit for Mr. Franke's July 29

24       deposition.  That would be 206.  So Franke deposition.

25                 (Exhibit 206 marked for identification.)

FLORIDA PUBLIC SERVICE COMMISSION

516

1                 Madam Chairman, this document was taken

2       pursuant to notice as a confidential deposition.  The

3       company has provided confidential designations.  Because

4       of the, the timing between when the, the document was,

5       the court reporter provided the document and their

6       opportunity to do the confidentiality designation, that

7       has just recently happened.  My understanding is they

8       will make redacted copies available shortly today and

9       confidentially designated copies available if needed.

10                 So what we have agreed upon is the full

11       confidential designation, confidentially designated

12       deposition will be what is moved into the record, but

13       they will provide that with the appropriate yellow

14       highlighting and justifications.

15                 Am I correct with that, Mr. Walls?

16                 MR. WALLS:  Yes, you are.

17                 MR. REHWINKEL:  Okay.  So with that, with

18       these documents, with these exhibits identified, Public

19       Counsel's cross-examination of Mr. Franke is over.

20                 CHAIRMAN ARGENZIANO:  Thank you.  That was,

21       I'm sorry, Mr. Rehwinkel, that was 198 to, let me make

22       sure I got it right, 206.  Okay.

23                 COMMISSIONER SKOP:  Thank you, Madam Chair.

24                 Just a point of clarification.  Mr. Rehwinkel,

25       exhibit, what's been marked for Exhibit Number 206 is

FLORIDA PUBLIC SERVICE COMMISSION

517

1       the actual deposition; is that correct?

2                 MR. REHWINKEL:  Yes.

3                 COMMISSIONER SKOP:  Okay.  Thank you.

4                 MR. DAVIS:  Also for point of clarification,

5       did the deposition have any exhibits to it?

6                 MR. REHWINKEL:  Yes.  Mr. Franke's deposition

7       had two late-filed deposition exhibits.  Actually --

8       yes.  And two late-filed deposition exhibits.

9                 COMMISSIONER SKOP:  Will we need numbers for

10       those, or will that be included within the depo?

11                 MR. REHWINKEL:  My -- those had already been

12       provided by the company.  So I think it would be, if

13       it's okay, they could be provided all as one.

14                 COMMISSIONER SKOP:  Mr. Walls?

15                 MR. WALLS:  May I have one moment?

16                 COMMISSIONER SKOP:  Yes, you may.

17                 MR. REHWINKEL:  If that was to be done, then

18       we could -- then we wouldn't need 205, which was

19       Exhibit 2.

20                 MR. WALLS:  Ms. Huhta is probably the best

21       person to speak to this, but my understanding is we

22       filed our notice of confidential classification for the

23       deposition of Mr. Franke with respect to the deposition

24       itself, and then the late-filed exhibits came later and

25       were served on the parties.  So the late-filed exhibits

FLORIDA PUBLIC SERVICE COMMISSION

518

1       were not part of the request for confidential

2       classification for the depo, the deposition.

3                 MS. HUHTA:  Yes.  But they were part of a

4       separate request, all which has already been filed.  And

5       just a point of clarification, August 10th for the

6       deposition of Jon Franke of 2010.  But the parties

7       should have a copy received on Monday, but we will also

8       provide additional copies.  We're having them made as we

9       speak.

10                 COMMISSIONER SKOP:  Very well.  Thank you.

11                 MR. REHWINKEL:  The cover page, she put the

12       wrong date on there.  I didn't realize that.  I was just

13       reading it, but that's correct.

14                 COMMISSIONER SKOP:  All right.  So,

15       Mr. Rehwinkel, in summation, exhibits that have been

16       marked for identification are 198, 199, 200 and 201

17       through 206, which is the depo, and those are fine.

18                 MR. REHWINKEL:  Yes.

19                 COMMISSIONER SKOP:  With no modification

20       required or deletion of 205.

21                 MR. REHWINKEL:  I guess what I'm just pausing

22       on is, is whether we should just make a 207, which would

23       be late-filed deposition Exhibit Number 1.

24                 COMMISSIONER SKOP:  All right.  Very well.

25                 MR. WALLS:  I actually think that probably

FLORIDA PUBLIC SERVICE COMMISSION

519

1       would work better, Charles.

2                 MR. REHWINKEL:  Okay.  Then 207 will be, and I

3       have not provided that, but it's a single piece of

4       paper.  It would be easy to provide to the parties.

5                 COMMISSIONER SKOP:  Ms. Bradley is not here

6       with us today.  Otherwise, she might be objecting to

7       late-filed exhibits.  All right.  So we have what's been

8       marked for identification, Exhibits 198 through 207, as

9       I understand it.

10                 MR. REHWINKEL:  That's correct.

11                 (Exhibit 207 marked for identification.)

12                 COMMISSIONER SKOP:  Very well.  And are you

13       intending to move those in at this time?

14                 MR. REHWINKEL:  I would move those at the, at

15       the conclusion of Mr. Franke's testimony after the

16       cross-examination.

17                 COMMISSIONER SKOP:  All right.  Very well.  So

18       that ends your cross-examination.  I guess we'll look to

19       the next Intervenor.

20                 Mr. Brew, you're recognized.

21                 MR. BREW:  Thank you.  I have no questions for

22       Mr. Franke.

23                 COMMISSIONER SKOP:  Very well.

24                 Ms. Kaufman?

25                 MS. KAUFMAN:  I do have a few questions, Mr.

FLORIDA PUBLIC SERVICE COMMISSION

520

1       Chairman.

2                 COMMISSIONER SKOP:  Please proceed.

3                          CROSS EXAMINATION

4       BY MS. KAUFMAN:

5            Q.   Good morning, Mr. Franke.

6            A.   Good morning.

7            Q.   It's a little bit hard to see you.  I just

8       have a couple of questions.  I just want to understand

9       the relationship between the uprate project and the

10       current Crystal River 3 outage.  And if I understood

11       your testimony, it had been your plan to complete Phase

12       3 of the uprate during the time that Crystal River came

13       back for its refueling in 2011; is that correct?

14            A.   That is correct.  Yes, ma'am.  The Phase 3 of

15       the uprate included modifications that were being

16       performed in conjunction with our 2011 refueling outage.

17       That outage is now delayed due to the delay and restart

18       from our current outage.

19            Q.   You're anticipating where I'm going.  So

20       because of the outage, the delayed, the prolonged outage

21       at Crystal River 3, you're now still wanting to do it in

22       conjunction with the refueling, but that's going to be,

23       right now as you know it, in 2012?

24            A.   Yes, ma'am.

25            Q.   In the fall; is that what you had said?

FLORIDA PUBLIC SERVICE COMMISSION

521

1            A.   It is scheduled for fall of 2012.

2            Q.   Okay.  If you have your April 30th testimony,

3       if you would turn to page 8.

4            A.   Yes, ma'am.

5            Q.   Okay.  And if you look on lines 5 and 6, you

6       say there, "As we complete the current outage, this

7       decision will continue to be evaluated."  Correct?

8            A.   Yes, ma'am.

9            Q.   So fall 2012 is a ways away.  Is it possible

10       that the refueling in 2012 will be pushed further out

11       and thus the uprate will be pushed further out?

12            A.   Anything is possible, but that is very

13       unlikely.

14            Q.   Okay.

15            A.   Right now we understand what the repairs are

16       to the current containment and we'll continue to work

17       through the issues surrounding that containment, and we

18       expect the plant to return during the fourth quarter.

19       With a return of the plant in the fourth quarter, my

20       next outage will be fall of 2012.

21            Q.   But if additional issues arise that you're not

22       aware of right now with the Crystal River 3 outage, then

23       it's certainly possible, isn't it, that the uprate

24       project would be pushed out to another refueling?

25            A.   It would not be pushed out to another

FLORIDA PUBLIC SERVICE COMMISSION

522

1       refueling.  It will be performed during our next

2       refueling.

3            Q.   Right.  But my point being is if for some

4       reason the Crystal 3 outage is longer and the plant

5       doesn't come back as you currently expect, that's also

6       going to push out the uprate project.

7            A.   Yes, ma'am.

8                 MS. KAUFMAN:  Thank you.  Thank you, Mr.

9       Franke.

10                 COMMISSIONER SKOP:  Thank you, Ms. Kaufman.

11                 Any further questions from SACE?

12                 MR. DAVIS:  No.

13                 COMMISSIONER SKOP:  Okay.  Any questions from

14       the bench?  Okay.  I do, I do have some quick ones, and

15       I'll try and make this very brief.

16                 Good afternoon, or is it afternoon?  Good

17       morning, Mr. Franke.

18                 THE WITNESS:  Yes, sir.

19                 COMMISSIONER SKOP:  All right.  In his opening

20       statement, Mr. Glenn was very candid about Progress's

21       concerns on the LAR, and you were very open about that

22       yesterday during your testimony, your extensive

23       testimony.

24                 In your opinion, what are two of the biggest

25       challenges currently faced in this CR3 EPU in terms of

FLORIDA PUBLIC SERVICE COMMISSION

523

1       getting it into service?

2                 THE WITNESS:  Is your question with regard to

3       the LAR specifically or to other issues?

4                 COMMISSIONER SKOP:  Just as a whole, licensing

5       as well as the remaining work scope that needs to be

6       done.

7                 THE WITNESS:  I, I have no concerns about the

8       feasibility of if the project can be successful and

9       eventual uprate of the project.

10                 As I have discussed, we are working through

11       with the NRC on the licensing for the digital

12       instruments.  I think our digital instrument licensing

13       is as about as simple as you can get, but we need to

14       work through that process with the NRC to best

15       understand that schedule and any potential impact on

16       cost and when we'll actually achieve the increase in

17       power, should that be at the conclusion of the next

18       refueling outage or possibly a little bit after that

19       based on the receipt of the licensing application.

20                 COMMISSIONER SKOP:  All right.  Very well.

21       And just so I can be sure what I'm approving, I just

22       want to go quickly through some elements of your

23       testimony; a nutshell summary, if you will.

24                 But on page 7 of your prefiled testimony, I

25       believe you testified that the remaining EPU work scope

FLORIDA PUBLIC SERVICE COMMISSION

524

1       during the next refueling outage will be approximately

2       45 days, subject to any additional changes; is that

3       correct?

4                 THE WITNESS:  I believe you're talking about

5       my, my April 30th testimony?

6                 COMMISSIONER SKOP:  Yes, sir.  Your direct

7       filed testimony.

8                 THE WITNESS:  Yes, sir.  That's the current

9       estimate for that schedule, for that outage.

10                 COMMISSIONER SKOP:  Okay.  And then continuing

11       on to page 8, with respect to the current refueling

12       outage and the delay resulting from the delamination of

13       the concrete in the containment wall building.  On line

14       12 on page 8 you talk about the steam generator

15       replacement.  Those steam generators had to be replaced;

16       is that correct?

17                 THE WITNESS:  Yes, sir.  That was a separate

18       project, and those steam generators have been replaced.

19                 COMMISSIONER SKOP:  Okay.  Very well.  And

20       continuing on to page 9, you talk about the low pressure

21       turbine installation deferral and how that's been

22       shifted from refueling 16 to refueling 17.

23                 THE WITNESS:  Yes, sir.

24                 COMMISSIONER SKOP:  Okay.  And that was

25       resulted, I think, from the blade row disk slipped

FLORIDA PUBLIC SERVICE COMMISSION

525

1       during some testing.  And then subsequent to that,

2       Progress, in your opinion, prudently exercised all of

3       its contractual rights, not only to protect its

4       ratepayers, but to ensure that the equipment provided

5       would protect and maintain the desired uprate output at

6       the plant; is that correct?

7                 THE WITNESS:  Absolutely.  We studied

8       carefully other options other than these turbines and

9       came to a technical and financial decision that lined up

10       in agreement that these were the right turbines for the

11       uprate, provided the best benefit to the customer.  And

12       we have strongly taken advantage of our contractual

13       rights to, to ensure that a cost increase did not occur

14       to the customer, and we're planning on installing those

15       turbines now with confidence.

16                 COMMISSIONER SKOP:  Okay.  And there are some,

17       some -- there is some information that still remains

18       confidential on this issue that I think generally deals

19       with the business acumen that went into making that

20       decision in the best interest of ratepayers and to

21       preserve the uprate option.  Do you see any problem with

22       that coming to fruition in terms of what's been

23       presented?

24                 THE WITNESS:  No.  We're confident that --

25       you're talking about the low pressure turbines?

FLORIDA PUBLIC SERVICE COMMISSION

526

1                 COMMISSIONER SKOP:  Yes, sir.

2                 THE WITNESS:  Yes, sir.  Yes.  I have high

3       confidence that we'll be successful with completion of

4       that contract in, in time for the next outage.  The

5       material's all but manufactured.  There's some more

6       testing to put in place.  But from a contract

7       standpoint, we're in very good condition.  We have the

8       right necessary angles covered in legal space as well.

9                 COMMISSIONER SKOP:  Okay.  And just two or

10       three final questions.  Page 26 of the prefiled

11       testimony.  Progress performed an updated feasibility

12       analysis on the CR3 uprate and it still shows positive

13       economic benefit based on the current state of the

14       project; is that correct?

15                 THE WITNESS:  Yes, sir.  And obviously the

16       factors shift around, but it's in the neighborhood of

17       $800 million of net value to the customer.

18                 COMMISSIONER SKOP:  Positive benefit to the

19       customer?

20                 THE WITNESS:  Yes, sir.

21                 COMMISSIONER SKOP:  Okay.  And that's over the

22       life of the project; is that correct?

23                 THE WITNESS:  That's correct.  It's still a

24       cost saving in fuel to the customer for the uprate of

25       something north of $2 billion and in the neighborhood of

FLORIDA PUBLIC SERVICE COMMISSION

527

1       800 million net present value.

2                 COMMISSIONER SKOP:  Okay.  And on page 27, and

3       I think this is my second to last question, I think you

4       previously stated the project in your professional

5       opinion is still technically feasible and achievable to

6       the uprate.

7                 THE WITNESS:  Yes, sir.

8                 COMMISSIONER SKOP:  Okay.  And from a

9       regulatory and legal perspective, on pages 28 and 29 you

10       speak about lessons learned regarding LARs.  And, you

11       know, certainly in response to some of the

12       cross-examination you had as well as questions from the

13       bench, again, very candid.  You told us the good and the

14       bad in terms of what was happening, and I think that's a

15       constructive part of the review process here.

16                 But in terms of the lessons learned on Point

17       Beach, again, I think you mentioned that's, that's not a

18       Progress project, it's another company's project, and

19       that application for the LAR was denied.  And at this

20       point in the game you're still looking at what the NRC

21       requires in terms of, of specking out the LAR to gain

22       successful NRC approvals.  Is that generally correct of

23       what I've heard your testimony to be?

24                 THE WITNESS:  That is correct.  And if you'll

25       give me just a second.  The Point Beach application

FLORIDA PUBLIC SERVICE COMMISSION

528

1       right now is targeted for approval soon.  But we

2       certainly have been able to apply those lessons to our

3       application, did cost, a cost and scope increase

4       associated with that.  But we're confident we've

5       incorporated in there, we have the Point Beach lessons

6       learned in our application as verified by my expert

7       panel and our own company review.

8                 COMMISSIONER SKOP:  Very well.  Thank you.

9                 And any additional questions from the bench?

10                 Seeing none, staff?

11                 MR. YOUNG:  Staff has no questions at this

12       time.

13                 COMMISSIONER SKOP:  All right.  Very well.

14       And will Mr. Franke be -- I guess he's going to be a

15       rebuttal witness.  So, Mr. Franke, you may step down and

16       we'll recall you at the appropriate time.

17                 All right.  If --

18                 MR. YOUNG:  Mr. Chairman?

19                 COMMISSIONER SKOP:  Yes.

20                 MR. YOUNG:  At this time I think the company

21       would like to request that Mr. Franke's exhibits be

22       moved in.  I know OPC has some exhibits also.

23                 COMMISSIONER SKOP:  Yeah.  I was going, I was

24       going to get to that next, but I just wanted to let him

25       step down, if that's appropriate, which I believe it is.

FLORIDA PUBLIC SERVICE COMMISSION

529

1                 Okay.  I'll take up exhibits.

2                 MR. WALLS:  Yes.  Mr. Franke has two direct

3       exhibits, JF-1 and JF-2, that are identified as staff

4       exhibits on the staff exhibit list, 19 and 20.

5                 COMMISSIONER SKOP:  Okay.  Any objection to

6       entering exhibits 19 and 20 into the record?  Seeing

7       none, show it done.

8                 (Exhibits 19 and 20 admitted into the record.)

9                 MR. REHWINKEL:  Public Counsel would move 198

10       through 207.

11                 COMMISSIONER SKOP:  Okay.  Any objection?

12                 MR. WALLS:  No.

13                 COMMISSIONER SKOP:  Okay.

14                 MR. YOUNG:  No objection.  What about 193

15       through 194, 195, 196 and 197?

16                 COMMISSIONER SKOP:  That was my next point.  I

17       was going to get to that.  So why don't we slow down a

18       little bit there.

19                 Mr. Rehwinkel, it seems when you began your

20       cross-examination --

21                 MR. REHWINKEL:  I apologize.  I was --

22                 COMMISSIONER SKOP:  I think it started with

23       193.

24                 MR. REHWINKEL:  Actually I need to move 191.

25                 MR. YOUNG:  Yes.

FLORIDA PUBLIC SERVICE COMMISSION

530

1                 COMMISSIONER SKOP:  Okay.

2                 MR. REHWINKEL:  And then 193.

3                 COMMISSIONER SKOP:  Hold on.  Any objection to

4       191?

5                 MR. WALLS:  No.

6                 COMMISSIONER SKOP:  Hearing none, show it

7       entered.

8                 (Exhibit 191 admitted into the record.)

9                 MR. REHWINKEL:  And then 193 through 197.

10                 COMMISSIONER SKOP:  Okay.

11                 MR. WALLS:  No objection.

12                 COMMISSIONER SKOP:  All right.  No objection

13       on 193 through 197.  Show that done.

14                 (Exhibits 193 through 197 admitted into the

15       record.)

16                 And that leaves us with Exhibits 198 through

17       207, I believe, are the remaining exhibits.

18                 MR. REHWINKEL:  Yes, I would move those.

19                 COMMISSIONER SKOP:  All right.  Any objection?

20                 MR. WALLS:  No.

21                 COMMISSIONER SKOP:  Okay.  Hearing none, show

22       Exhibits 198 through 207 entered into the record.

23                 (Exhibits 198 through 207 admitted into the

24       record.)

25                 And I believe that will allow us to call the

FLORIDA PUBLIC SERVICE COMMISSION

531

1       next witness.

2                 MS. HUHTA:  Progress calls Sue Hardison.

3                 COMMISSIONER SKOP:  All right.  Very well.

4       And has Ms. Hardison been previously sworn?

5                 THE WITNESS:  Yes, I have.

6                 COMMISSIONER SKOP:  All right.  Thank you.

7                             SUE HARDISON

8       was called as a witness on behalf of Progress Energy

9       Florida and, having been duly sworn, testified as

10       follows:

11                          DIRECT EXAMINATION

12       BY MS. HUHTA:

13            Q.   Good morning, Ms. Hardison.  Will you please

14       introduce yourself to the Commission and provide your

15       business address.

16            A.   Yes.  Good morning.  My name is Sue Hardison.

17       My business address is 410 South Wilmington Street in

18       Raleigh, North Carolina.

19            Q.   And you have already been sworn in; correct?

20            A.   Yes, I have.

21            Q.   And who do you work for and what is your

22       position?

23            A.   I work for Progress Energy Carolina.  I'm

24       employed by them as the General Manager, Business

25       Services Corporate Development Group.

FLORIDA PUBLIC SERVICE COMMISSION

532

1            Q.   Have you filed direct testimony on March 1st,

2       2010, and April 30th, 2010, in this proceeding?

3            A.   Yes, I have.

4            Q.   Do you have copies with you?

5            A.   I have copies of both my testimony and

6       exhibits that I cosponsor with Witness Garrett, and

7       exhibits that I cosponsor with Witness Foster.

8            Q.   Okay.  Thank you.  Do you have any changes to

9       make to your prefiled testimony and exhibits?

10            A.   Yes.  Actually I do have one change to make to

11       my March 1 testimony.  It is on page 22.  The sentence

12       that begins on line 5, "The COLA was docketed by the NRC

13       in 2009."  I apologize.  That is a typo.  It should be

14       2008.

15            Q.   Other than this one correction, Ms. Hardison,

16       if I asked you the same questions in your prefiled

17       testimony today, would you give the same answers that

18       are in your testimony?

19            A.   Yes, I would.

20                 MS. HUHTA:  We request that the prefiled

21       testimony from March 1st, 2010, and April 30th, 2010, of

22       Ms. Hardison be moved into evidence today as if read.

23                 COMMISSIONER SKOP:  All right.  The prefiled

24       testimony of witness Hardison will be entered into the

25       record as though read.  Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

573

1       BY MS. HUHTA:

2            Q.   Thank you.  Ms. Hardison, do you have a

3       summary of your prefiled testimony?

4            A.   Yes, I do.

5            Q.   Will you please provide that summary to the

6       Commission?

7            A.   Certainly.

8                 My name is Sue Hardison.  My direct testimony

9       filed March 1, 2010, explains the prudence of the

10       company's Levy nuclear project, or LNP, actual costs

11       incurred in 2009, and its project management,

12       contracting and cost oversight controls for 2009.

13                 I also filed direct testimony on April 30,

14       2010, explaining the reasonableness of the LNP actual

15       estimated cost for 2010 and projected cost for 2011.

16                 I am available to answer questions regarding

17       my testimony.

18                 MS. HUHTA:  We tender Ms. Hardison for cross.

19                 COMMISSIONER SKOP:  Very well.  Thank you.

20                 Mr. Rehwinkel, you're recognized for

21       cross-examination.

22                 MR. REHWINKEL:  Thank you, Mr. Chairman.  I

23       would like to -- I'm going to pass out two exhibits at

24       this point in time.

25                 COMMISSIONER SKOP:  All right.  Those, do

FLORIDA PUBLIC SERVICE COMMISSION

574

1       those need to be marked?

2                 MR. REHWINKEL:  Yes.

3                 COMMISSIONER SKOP:  That would be Number 208

4       and 209.

5                 MR. REHWINKEL:  208 would be, on the cover it

6       says James, but it should say Janus, J-A-N-U-S, Janus

7       Interview.  And 209 would be LNP Master Plan.

8                 COMMISSIONER SKOP:  It sounds like something

9       out of a Mad Max movie.

10                 MR. REHWINKEL:  That is the LNP Integrated

11       Master Plan.

12                 COMMISSIONER SKOP:  All right.  Those have

13       been marked.

14                 (Exhibits 208 and 209 marked for

15       identification.)

16                          CROSS EXAMINATION

17       BY MR. REHWINKEL:

18            Q.   Good morning, Ms. Hardison.

19            A.   Good morning, sir.

20            Q.   Just a few questions about your testimony.

21       You are an accountant by training?

22            A.   Yes, sir, I am.

23            Q.   Okay.  You are a CPA?

24            A.   Yes, sir, in North Carolina.

25            Q.   Okay.  And do you have any -- are you an

FLORIDA PUBLIC SERVICE COMMISSION

575

1       engineer in any way?

2            A.   No, sir, I am not.

3            Q.   Okay.  You have not overseen the construction

4       of a nuclear plant.

5            A.   No, sir, I have not.

6            Q.   Have you overseen the construction of an

7       electric generation facility?

8            A.   I have not overseen it, sir, but I have

9       provided project control support for the construction of

10       combined cycle plants.

11            Q.   Okay.  And does project control support

12       involve the administration of contracts governing the

13       contractors?

14            A.   We typically do contract administration

15       regarding change order management as part of the

16       process, and ensuring that the invoices are paid in

17       accordance with the terms and conditions of the

18       contract.

19            Q.   Okay.  In your role, your current role with

20       regard to the Levy project, did you have a predecessor?

21            A.   The information under Levy financial services,

22       sir, previously was managed by another organization, so

23       I did have a predecessor.

24            Q.   Okay.  With respect to your role of the

25       nuclear, of the Levy nuclear plant project, would you

FLORIDA PUBLIC SERVICE COMMISSION

576

1       say that you are in, more in the role of contract

2       administration and oversight than construction

3       oversight?

4            A.   Contract administration and support, sir, is

5       one of the support services I provide.  We are currently

6       not in a construction phase for the Levy plant.  We have

7       been in certain phases of the transmission side.  But,

8       no, I am not doing -- at this point there is no

9       construction.

10            Q.   Okay.  Would it ever be contemplated that you

11       would oversee the construction of the nuclear plant if,

12       if it ever comes to pass?

13            A.   When the nuclear plant is constructed, sir, I

14       will provide project control support at the site, but I

15       will not be overseeing direct construction.  That's not

16       my expectation.

17            Q.   Okay.  Do you have what's been identified as

18       Exhibit 208?

19            A.   There's not a number.  I apologize, sir.  Can

20       you provide me a --

21            Q.   It's the Janus interview with Mr. Doughty's --

22            A.   Yes, sir, I do have a copy of that.

23            Q.   Have you had a chance to review this document?

24            A.   I just received this document this week, sir.

25            Q.   Okay.

FLORIDA PUBLIC SERVICE COMMISSION

577

1            A.   It's the first time I had seen it.

2            Q.   Before you took the stand today, have you had

3       a chance to review it?

4            A.   I had a chance to go over it.  Yes, sir.

5            Q.   And this is a, a draft of interview notes that

6       Janus and Mr. Doughty's team conducted of yourself; is

7       that correct?

8            A.   That is correct, sir.

9            Q.   On February 9th of this year?

10            A.   Yes.

11            Q.   Is there anything in these notes that you

12       would consider to be incorrect with respect to the way

13       they're presented?

14            A.   It's difficult to say, sir, because the notes

15       seem to be just a transcript of someone's thoughts, and

16       it's difficult to tell without a question and answer

17       format what the context was.  And some of the words and

18       phrases, sir, frankly were not familiar to me.

19            Q.   Okay.  Is there anything in here that you

20       believe is a mischaracterization of the discussion that

21       you had with Mr. Doughty?

22            A.   Well, again, sir, without it being in a Q and

23       A format and a topic, some of the things seem

24       inconsistent.  If you look at one line, the next line

25       actually doesn't make much sense.  So if you have a

FLORIDA PUBLIC SERVICE COMMISSION

578

1       specific area, sir, you'd like to address, I can look at

2       that.

3            Q.   Okay.  Well, could you give me an example of

4       what you think is inconsistent?

5            A.   Yes, sir.  If you'll refer to page 3.

6            Q.   Yes.

7            A.   From the bottom there's a section called Using

8       Probabilistic Estimates.  And the gist of the discussion

9       seems to be probabilistic risk assessment.  We don't use

10       probabilistic estimates, so that was confusing to me.

11       I'm not sure what the original topic was.

12            Q.   Okay.

13            A.   And there is an area there, sir, where they've

14       typed that I referred to a person as a master of

15       something.  I sincerely hope my words were manager.

16            Q.   Okay.

17            A.   But there are numerous examples like that

18       actually, sir.  So, again, if you could direct me to

19       specifically what you're looking at, that would help.

20            Q.   Okay.  On the second page.

21            A.   Yes, sir.

22            Q.   Page 2 of 4, in the, near the middle, above

23       the bold, there's a heading that says Major Recent

24       Initiatives Accounting/Finance.

25            A.   Oh, yes, sir.

FLORIDA PUBLIC SERVICE COMMISSION

579

1            Q.   Is this essentially, is this a high level

2       description of kind of the way you've approached the EPC

3       contract as it relates to the EP -- to the Levy plant?

4            A.   Yes, sir.  The context of this discussion was

5       that we applied -- my group had been providing financial

6       services support for other major projects in the

7       company.  One of our lessons learned, sir, is that it's

8       very helpful for us to look at the actual assets that

9       are going to be constructed at a very detailed level,

10       and to break the project down into those types of

11       discrete elements.  It allows us better tracking for our

12       project managers and it allows us better variance

13       explanations, if you will.  So we did apply that lesson

14       learned when we moved into merging the Levy plant as

15       part of our responsibilities.

16            Q.   Okay.  This, this would be in the event that

17       construction actually occurs at that site?

18            A.   It would be when construction occurs.  Yes,

19       sir.

20            Q.   Okay.  Well, you're not testifying that

21       construction will occur, are you?

22            A.   No, sir.  I am testifying that we subdivided

23       the accounting projects to be consistent with the assets

24       to be built.

25            Q.   Okay.  If they are built.

FLORIDA PUBLIC SERVICE COMMISSION

580

1            A.   Well, sir, my, my work is to look at it in the

2       context of where it is now, and that is my assumption,

3       sir, is that they will be built.

4            Q.   Okay.  Do you have a copy of Exhibit 209,

5       which is the only other, which is the Levy nuclear

6       project integrated master, integrated master plan?

7            A.   Yes, sir, I do.

8            Q.   Are you familiar with this document?

9            A.   Yes, sir, I am.

10            Q.   Now the first, actually what I have passed

11       out, is it fair to represent, are involving iterations

12       of this document?

13            A.   Yes, sir.  The iterations, as I understand

14       them from this document, were we received a set of

15       information of schedule detail from the consortium, and

16       we did supply on the front side our licensing and

17       permitting scheduling evolution and our, at the bottom

18       our transmission.  The middle part would have come from

19       the consortium per their requirements.

20            Q.   Okay.  And when you say the middle part, is

21       that the part that is in, that is in yellow

22       highlighting?

23            A.   Yes, sir.  It's difficult for me to see yellow

24       highlighting on this one.  I apologize.

25            Q.   Well, I'll just, all I want to do is kind of

FLORIDA PUBLIC SERVICE COMMISSION

581

1       understand what this document says.  Now on the first

2       page of the exhibit, up in the upper right-hand side, it

3       says REV:0 11/1/07.  Do you see that?

4            A.   Yes, sir.

5            Q.   And this would have been the very first

6       iteration of this document; correct?

7            A.   This would have been.

8            Q.   And before your time?

9            A.   Well before my time, sir.

10            Q.   Okay.  And this basically shows the

11       anticipated times at, time frames in November of 2007?

12            A.   Yes, sir.

13            Q.   Okay.  The next page is, upper right-hand

14       corner, REV:1, and it shows January 3rd, 2008.

15            A.   Yes, sir.

16            Q.   And there are some changes between REV:0 and

17       REV:1 to the document.  For instance, on the startup --

18       I guess I should not mention anything in that.

19            A.   No, sir.

20            Q.   In the -- we see the difference, I guess, in

21       2016 column.  If we look down, there's a March 8th date

22       on the first page, in the far right-hand, year 2016.

23            A.   Yes, sir.

24            Q.   Okay.  And if we look to the second page, that

25       date is now March -- is June 2nd, June 6th.

FLORIDA PUBLIC SERVICE COMMISSION

582

1            A.   June 6th.  Yes, sir.  I see that.

2            Q.   Okay.  All right.  And then if we turn to the

3       next page, it is March 7th.

4            A.   I believe it's July 7th, sir; is that correct?

5            Q.   I'm looking -- this is the one that says

6       REV:2.

7            A.   Oh, I'm sorry.  The date of the REV.

8            Q.   Oh, I'm looking -- this is the date of the

9       document.

10            A.   Yes, sir.  Yes, sir.

11            Q.   Okay.  And this says, "Approved Garry Miller,

12       General Manager, MPD."

13            A.   Yes, sir.  Yes, sir.

14            Q.   Okay.  Now was Garry Miller your predecessor

15       in any regard?

16            A.   No, sir, he was not.

17            Q.   Okay.  But he approved this document.  And in

18       the -- now the year is 2017, and the corresponding dates

19       that we looked at on the prior two pages is July 7th of

20       2017; is that right?  That's for a unit, that's for a --

21       I'm sorry.  If we look in 2016, the date is, is, the

22       corresponding date is June 30th.

23            A.   Yes, sir.

24            Q.   Okay.

25            A.   For the previous dates, let me go back, sir,

FLORIDA PUBLIC SERVICE COMMISSION

583

1       that you were looking at for that same item?

2            Q.   Yes.

3            A.   Let me just take a moment.

4            Q.   Just so -- the area we're talking about here,

5       the dates and identified activities are confidential; is

6       that correct?

7            A.   Yes, sir.  And you'll see there has been a

8       further definition for the one Garry Miller has signed

9       on March 7th.

10            Q.   Okay.  And -- all right.  So when we move past

11       this date -- the date of the third integrated master

12       plan is March 7, 2008.  And then if we turn to the next

13       page, it still says REV:2, but it says June 1st, 2009;

14       is that correct?

15            A.   It is correct, sir.

16            Q.   And it says, "Approved," it says, "June 1st,

17       2009 update/analysis," and it says, "Approved Garry

18       Miller/Lew" --

19            A.   Lewis Spragins.  Yes, sir.

20            Q.   Right.  Okay.  And what is Lewis Spragins?

21            A.   Mr. Spragins was previously, until actually

22       just at this date when we came over was the Project

23       Controls Manager.  When we merged at midyear we replaced

24       Mr. Spragins with a different Project Controls Manager.

25            Q.   Okay.  But now what's different about this

FLORIDA PUBLIC SERVICE COMMISSION

584

1       document from the prior in a material way would be a red

2       dotted line here; is that correct?  A red dotted box

3       that, that encircles these activities.

4            A.   Yes, sir.

5            Q.   And what, what does that represent?

6            A.   We have a note on here, sir, because what

7       we've done is frozen this portion of the schedule.  This

8       REV would have been after the partial suspension

9       notification.  And so really this block was frozen until

10       the negotiations and schedule analysis.

11            Q.   Okay.  All right.  And then we start to see

12       above that in the first line licensing and permitting.

13       These blue dates and descriptions are NRC activities.

14            A.   Yes, sir.  For internal.

15            Q.   With the expected dates at these, at this

16       time.

17            A.   At the time this was prepared.  Yes, sir.

18            Q.   Okay.  So we see a draft environmental impact

19       statement expected in October of 2009, a final

20       environmental impact statement in September of 2010, and

21       then in May 5th, 2011, a final safety evaluation report.

22            A.   Yes, sir.  I think the point that you're

23       getting to are these dates have shifted and we do

24       prepare the schedule.  But if you're looking at an

25       understanding, sir, of the date shifts in our NRC, I

FLORIDA PUBLIC SERVICE COMMISSION

585

1       would have to defer you to Mr. Elnitsky.

2            Q.   I understand.

3            A.   Thank you.

4            Q.   The next page, the, it says REV:2 12/31/2009.

5            A.   Yes, sir.

6            Q.   Now this is one that it appears that you --

7            A.   Yes, sir.

8            Q.   -- signed or you initialed in your role.  It

9       says, "General Manager."

10            A.   CDG Business Services.

11            Q.   Okay.  And Lee Formanek?

12            A.   Lee Formanek is the Project Controls Manager.

13            Q.   Okay.  And this shows some revisions to the

14       dates that we just talked about with respect to the NRC.

15            A.   Yes, it does.

16            Q.   And it still says, "Note, EPC and transmission

17       project schedules on hold," and it has your initials

18       inside the box.

19            A.   Yes, sir.

20            Q.   Okay.  Now the next page says REV:2,

21       February 26th, 2010, update.

22            A.   Yes, sir.

23            Q.   And it says, "Note," inside the red box, your

24       initials, it says, "EPC and transmission project

25       schedules on hold until in-service dates are

FLORIDA PUBLIC SERVICE COMMISSION

586

1       determined."

2            A.   Yes, sir.

3            Q.   Now has this document been revised?

4            A.   We have not revised this yet, sir, because we

5       require the consortium to provide us sequencing.  And

6       Mr. Elnitsky could speak to one of the primary drivers

7       right now is the sequencing with our long-lead material,

8       and that is in negotiation.  Rather than spend efforts,

9       sir, we would wait until we got that information data.

10            Q.   So --

11            A.   The changes though, however, sir, if you will

12       allow me, we do continue to track our internal schedules

13       related to our work with the NRC, and these dates

14       referenced here are not any different right now than

15       they are here.

16            Q.   When you say these dates --

17            A.   Well, I apologize, sir.  Our licensing and

18       permitting line at the top.

19            Q.   Okay.  So there have been changes from, if I

20       compare the December 31, 2009, estimates of the NRC

21       activities to the February 2010 activities, there were

22       changes there.  But you're saying the, the dates that

23       you have projected for the February 2010 master plan are

24       your best estimate at this point.

25            A.   The key dates in there, sir, would be the

FLORIDA PUBLIC SERVICE COMMISSION

587

1       issuance of the final environmental impact statement and

2       the final safety evaluation report, which are still

3       expected to be issued in July.  I can't quite read.  I

4       see the, I see them sort of on top of each other, sir.

5       Do you see the FEIS on the top of the line?

6            Q.   Yes.

7            A.   And the FSER (phonetic) on the bottom?

8            Q.   Yes.

9            A.   Those are still the dates that we're showing.

10       And we are still showing, sir, expecting the COLA, and,

11       again, Mr. Elnitsky's testimony addresses this more

12       thoroughly and technically, in the fourth quarter of

13       2012.

14            Q.   Okay.  Thank you.  And I appreciate that

15       clarification.  I want to ask you to go back to the

16       REV:1, which is the January 3rd, 2008.

17            A.   Yes, sir.

18            Q.   And the next to the last line item in this

19       master plan says, "Plant Operation Staffing."  Do you

20       see that?

21            A.   Yes, sir, I do.

22            Q.   And that's, that's -- this is not

23       confidential, this line.

24            A.   No, it's not.

25            Q.   Okay.  And we see a January 3rd, 2011,

FLORIDA PUBLIC SERVICE COMMISSION

588

1       starting point for this dark blue line; is that correct?

2            A.   Yes, sir, we do.

3            Q.   Now the activities that are covered by that

4       line, are, are they generally five years in advance of

5       what was at this time the anticipated in-service date of

6       Levy Unit 1?

7            A.   For the timing of when you bring licensed

8       operators and staff on, sir, I would have to refer to a

9       nuclear engineer.  So I would have to defer that, sir,

10       to Mr. Elnitsky.

11            Q.   Okay.  So you don't know about this?

12            A.   We would have to talk to engineering when we

13       staff that line.  And since I didn't prepare this

14       particular one, sir, I'm sure there were discussions

15       with the appropriate personnel.

16            Q.   Okay.  Well, let me ask you this.  In the

17       documents that we get to in the last part of the exhibit

18       that are signed off by you, are you familiar with the

19       plant operations staffing aspect on those pages?

20            A.   Yes, I am, sir.  But if you'll look, the red

21       dotted line that says all of these elements are on hold

22       until we get the rest of the schedule updated, we have

23       also frozen those.

24            Q.   Okay.  So are you familiar with an issue

25       that's been raised in this docket in the staff audit

FLORIDA PUBLIC SERVICE COMMISSION

589

1       report about the operational readiness group?

2            A.   Oh, yes, sir, I have.

3            Q.   Would the operational readiness group have any

4       relationship to this blue line here?

5            A.   Operational readiness for full staffing, sir,

6       would be related.  But in the context of what's been

7       asked and answered in, I believe, interrogatories with

8       operational readiness, those costs that we're currently

9       incurring now, sir, are not so much staffing as they are

10       activities with our AP 1000 owners group, which is also

11       known as APOG.  Again, Mr. Elnitsky sits on that

12       committee and can speak to it.  But the two primary

13       activities are the development of training and

14       operational manuals, which will be necessary for the

15       AP 1000 fleet, and we are, sir, actively engaged in

16       those activities.  So we characterize that under

17       operational readiness.  But there is no staffing at this

18       point.  I believe it's two individuals and a part-time

19       contractor.

20            Q.   Now when that group was initially established,

21       it was, it was in the time frame where it would have

22       been five years in advance of the then in-service date

23       estimate; correct?

24            A.   Again, sir, it is laid out that way on the

25       schedule.  But as to the timing of when you have to

FLORIDA PUBLIC SERVICE COMMISSION

590

1       bring on the full staff for an operating plant, I would

2       have to defer to Mr. Elnitsky.

3            Q.   Okay.  And I appreciate that, and I will.

4            A.   You're welcome, sir.

5            Q.   With respect to this, you mentioned there's

6       two individuals now.  Is that -- has there been a change

7       in the staffing level of that group since 2009?

8            A.   There's been a change in the level.  We had a

9       vice president retire, sir.  And I believe it was

10       earlier -- I can't remember honestly, sir, if it was

11       earlier this year or last year.  So there's no longer a

12       vice president for that organization, but there are two

13       different individuals.

14            Q.   Now do you expect there to be in 2011 and 2012

15       that the operational readiness group will be --

16            A.   I don't expect any expansion of staff, sir, in

17       the next 24 months.

18            Q.   Do you expect any contracting of staff in the

19       next --

20            A.   I wouldn't expect so, sir.  But I would defer

21       to Mr. Elnitsky and the working group for the AP 1000.

22            Q.   Okay.

23            A.   He would know more about what our activities

24       will be in the next couple of years.

25            Q.   Okay.  Thank you for your, your answers.

FLORIDA PUBLIC SERVICE COMMISSION

591

1            A.   You're welcome, sir.

2                 MR. REHWINKEL:  I have no further questions.

3                 COMMISSIONER SKOP:  Thank you.

4                 Mr. Brew?

5                 MR. BREW:  Thank you.  I have nothing for this

6       witness.

7                 COMMISSIONER SKOP:  Very well.

8                 Ms. Kaufman?

9                 MS. KAUFMAN:  Thank you, Mr. Chairman.  I have

10       no questions.

11                 COMMISSIONER SKOP:  Very well.

12                 SACE?

13                 MR. DAVIS:  No questions.

14                 COMMISSIONER SKOP:  Very well.  Any questions

15       from the bench?

16                 Hearing none, staff?

17                 MR. YOUNG:  No questions.

18                 COMMISSIONER SKOP:  Okay.  Can we take up

19       exhibits --

20                 MR. YOUNG:  Actually redirect, if any.

21                 MS. HUHTA:  No redirect.

22                 COMMISSIONER SKOP:  All right.  Exhibits then?

23                 MS. HUHTA:  Ms. Hardison didn't have any

24       exhibits attached to her prefiled testimony.

25                 COMMISSIONER SKOP:  Okay.

FLORIDA PUBLIC SERVICE COMMISSION

592

1                 Mr. Rehwinkel?

2                 MR. REHWINKEL:  Public Counsel would move

3       2,000 -- I mean 208 and 209.

4                 COMMISSIONER SKOP:  Any objection?

5                 Hearing -- Mr. Burnett?

6                 MR. BURNETT:  Thank you, Commissioner Skop.

7       No objection.  I just did want to note I appreciate

8       Mr. Rehwinkel's caution, but on Exhibit 209, the only

9       elements that remain confidential are the last three

10       pages that we blocked out by a pink box.

11                 COMMISSIONER SKOP:  Yes.

12                 MR. BURNETT:  Those are the only remaining

13       confidential portions.  So I just wanted to make sure

14       that all, that it was clear all the other portions may

15       be entered into the record unredacted.

16                 COMMISSIONER SKOP:  Okay.  Very well.

17                 And, staff, you're aware of that, based on

18       Mr. Burnett's representations.

19                 So hearing no objection, Exhibits 208 and 209

20       will be entered.

21                 (Exhibits 208 and 209 admitted into the

22       record.)

23                 And at this point, this may be a good breaking

24       point for lunch, unless we want to move forward briefly.

25       Is there concern?

FLORIDA PUBLIC SERVICE COMMISSION

593

1                 MS. HUHTA:  I just wanted to ask, Ms. Hardison

2       does not have any rebuttal.  May she be excused from the

3       remainder?

4                 COMMISSIONER SKOP:  Yes, she may be excused.

5       Yes, I was planning on doing that.

6                 MS. HUHTA:  Thank you.

7                 THE WITNESS:  Thank you.  Thank you,

8       Commissioners.

9                 COMMISSIONER SKOP:  Thank you.

10                 MR. WALLS:  Commissioner Skop, I think our

11       next witness is Ken Karp.  And he's a stipulated

12       witness, so we could go --

13                 COMMISSIONER SKOP:  Yes.  Let's take care of

14       that while we have a few minutes.  So if you could move

15       forward with that on Mr. Karp.

16                 MS. HUHTA:  Certainly, Commissioner Skop.

17       PEF's next witness is Mr. Kenneth Karp, and the parties

18       have agreed to waive cross and to stipulate to the

19       entrance of his testimony.  He had two sets of prefiled

20       testimony dated March 1st, 2010, and April 30th, 2010,

21       and we would request that those two prefiled sets of

22       testimony be entered into the record as though read.

23                 COMMISSIONER SKOP:  All right.  Very well.

24       The two sets of prefiled testimony, upon agreement for

25       the parties for Mr. Karp, will be entered into the

FLORIDA PUBLIC SERVICE COMMISSION

594

1       record as though read.

2                 And are there any exhibits that we need to

3       take up for Mr. Karp?

4                 MS. HUHTA:  No exhibits from Progress.

5                 COMMISSIONER SKOP:  All right.  Very well.

6       All right.  Show that done.

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

631

1                 COMMISSIONER SKOP:  And at this point,

2       Commissioners, I think it's a good breaking point for

3       lunch.  And why don't we reconvene at 1:15.  So we'll

4       stand on recess until 1:15.

5                 (Recess taken.)

6                 COMMISSIONER SKOP:  Okay.  At this point we're

7       going to go back on the record.  And Mr. Karp's, where

8       we left off, we had admitted his testimony and exhibits,

9       which he had none, into evidence.  And I believe that

10       concludes Progress's case in chief without the rebuttal

11       testimony that'll come later.  So at this point it takes

12       us to the Intervenor and staff direct testimony.

13                 And my understanding, based on the order of

14       remaining witnesses, is that Dr. Cooper from SACE,

15       Mr. Gundersen both have testimony that will be, and

16       exhibits will be admitted with no questions.  So I'd

17       look to SACE at this time to make those admissions in

18       evidence.

19                 MR. DAVIS:  Thank you, Commissioner.  I would

20       state for the record that Dr. Mark Cooper's testimony

21       has been stipulated to by the parties, and we would move

22       that it be admitted into the record as if read.

23                 COMMISSIONER SKOP:  All right.  Very well.

24       The prefiled testimony of Dr. Mark Cooper will be

25       entered into the record as though read.

FLORIDA PUBLIC SERVICE COMMISSION

632

1                 And do we have any exhibits or rebuttal

2       testimony for Dr. Cooper?

3                 MR. DAVIS:  There will be rebuttal

4       testimony -- no, not by Dr. Cooper.  No.

5                 COMMISSIONER SKOP:  Okay.  All right.

6                 MR. DAVIS:  But he has exhibits.  He has

7       MNC-1 through MNC-20.

8                 COMMISSIONER SKOP:  Okay.

9                 MR. DAVIS:  Which were part of the

10       stipulation, so we would move those.

11                 COMMISSIONER SKOP:  Okay.  Can you repeat

12       those again for me, please?

13                 MR. DAVIS:  Yes.  Thank you.  MNC-1 through

14       MNC-20.

15                 COMMISSIONER SKOP:  Very well.  Those have

16       been marked for hearing ID as Exhibits 34 through 50.

17                 MR. DAVIS:  I'm sorry.  I apologize.  Yes.

18                 COMMISSIONER SKOP:  Okay.  Those have been

19       marked for ID as hearing Exhibits 34 through 53, I

20       believe.

21                 MR. DAVIS:  That's correct.

22                 (Exhibits 34 through 53 marked for

23       identification.)

24                 COMMISSIONER SKOP:  Okay.  Are there any

25       objections to entering those into the record?

FLORIDA PUBLIC SERVICE COMMISSION

633

1                 Okay.  Hearing none, show those entered.

2                 (Exhibits 34 through 53 admitted into the

3       record.)

4

5

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

672

1                 COMMISSIONER SKOP:  And I believe that takes

2       care of Dr. Cooper.  And if you could proceed with

3       Mr. Gundersen.

4                 MR. DAVIS:  Yes.  Commissioner.  We have

5       stipulations from the parties to the admission of the

6       testimony of Mr. Gundersen, and we would move that it be

7       admitted into the record as if read.

8                 COMMISSIONER SKOP:  Okay.  Any objection?  All

9       right.  The prefiled testimony of Mr. Gundersen will be

10       entered into the record as though read.

11                 And are there any exhibits or rebuttal

12       testimony for Mr. Gundersen?

13                 MR. DAVIS:  Yes.  Mr. Gundersen has Exhibit 54

14       through Exhibit 60.

15                 COMMISSIONER SKOP:  Okay.  All right.  Any

16       objections to moving Exhibit 54 through 60 into the

17       record at this time?  All right.  Hearing none, show

18       that done.  And I believe that takes care of

19       Mr. Gundersen.

20                 (Exhibits 54 through 60 marked for

21       identification and admitted into the record.)

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

699

1                 MR. DAVIS:  That takes care of the SACE

2       witnesses.  Thank you.

3                 COMMISSIONER SKOP:  All right.  Very well.  So

4       I believe now we'll look to Public Counsel to call their

5       witness, and I believe that's Dr. Jacobs.

6                 MR. YOUNG:  Mr. Chairman, it's my

7       understanding that Mr. Rehwinkel just stepped out for a

8       second.  He, he brought the wrong testimony as regards

9       to --

10                 COMMISSIONER SKOP:  All right.  We will hold

11       in place then.

12                 MR. YOUNG:  -- Mr. Jacobs.  And here he is

13       right now walking in.

14                 MR. REHWINKEL:  The Citizens call Dr. William

15       Jacobs.

16                 COMMISSIONER SKOP:  And, Mr. Jacobs, have you

17       been previously sworn?

18                 THE WITNESS:  Yes, I have.

19                 COMMISSIONER SKOP:  All right.  Very well.

20       You may proceed.

21                    WILLIAM R. JACOBS, JR., Ph.D.

22       was called as a witness on behalf of the Citizens of the

23       State of Florida and, having been duly sworn, testified

24       as follows:

25                          DIRECT EXAMINATION

FLORIDA PUBLIC SERVICE COMMISSION

700

1       BY MR. REHWINKEL:

2            Q.   Can you state your name?

3            A.   My name is William Jacobs.

4            Q.   And by whom are you employed?

5            A.   By -- I'm Vice President of GDS Associates.

6            Q.   And on whose behalf are you testifying here

7       today?

8            A.   Testifying on behalf of the Florida Office of

9       Public Counsel.

10            Q.   Dr. Jacobs, did you cause to be prepared 22

11       pages of prefiled direct testimony in this matter?

12            A.   Yes, I did.

13            Q.   Do you have any changes or corrections to make

14       to that testimony?

15            A.   Yes, I have one minor typo correction on page

16       13, line 15.  The second word, T-O, to, should be

17       changed to of, O-F, so the sentence would read,

18       "Downplaying the reality of the identified risks."

19       That's all.

20            Q.   Thank you.  Dr. Jacobs, if I, with that

21       correction, if I asked you the questions contained in

22       your prefiled direct testimony today, would your answers

23       be the same?

24            A.   Yes, they would.

25                 MR. REHWINKEL:  Commissioners, I would move at

FLORIDA PUBLIC SERVICE COMMISSION

701

1       this time that Dr. Jacobs' prefiled direct testimony be

2       moved into the record.

3                 COMMISSIONER SKOP:  The prefiled testimony of

4       Dr. William Jacobs will be entered into the record as

5       though read.

6       BY MR. REHWINKEL:

7            Q.   Dr. Jacobs, did you also prepare three

8       exhibits?

9            A.   Yes, I did.

10            Q.   Identified as WRJ(PEF)-1 through 3?

11            A.   That's correct.

12                 MR. REHWINKEL:  And for the, for the record,

13       Exhibits 31 through 33.

14                 (Exhibits 31 through 33 marked for

15       identification.)

16       BY MR. REHWINKEL:

17            Q.   Do you have any changes or corrections to make

18       to those exhibits, Dr. Jacobs?

19            A.   No, I do not.

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

724

1       BY MR. REHWINKEL:

2            Q.   Dr. Jacobs, do you have a summary of your

3       testimony less than five minutes?

4            A.   Yes, I do.

5            Q.   Could you give that at this time?

6            A.   I'd be happy to.

7                 Good afternoon, Madam Chairman and

8       Commissioners.  Again, my name is William Jacobs.  I'm

9       Vice President of GDS Associates, and I'm testifying

10       here this afternoon on behalf of the Florida Office of

11       Public Counsel.  I will address two major issues, the

12       Levy County project and, or two major areas, excuse me,

13       and the Crystal River Unit 3 EPU.

14                 Turning first to the Levy County project, I

15       reviewed the options that the company evaluated for the

16       Levy County project following the decision by the NRC

17       not to grant their limited work authorization as

18       requested.  These options were to cancel the project

19       immediately, to proceed full speed ahead, or the third

20       option would be to delay the project by approximately

21       five years, with the first unit starting up in the year

22       2021.

23                 Following my review of these options, I

24       believe that there was another scenario that should have

25       been evaluated by the company.  This scenario involves

FLORIDA PUBLIC SERVICE COMMISSION

725

1       cancellation of the project following receipt of the

2       combined license, which is, the combined license is

3       anticipated to be received in late 2012, and at that

4       point I believe it is a reasonable scenario that the

5       company would conclude that the project should be

6       canceled at that point.

7                 The reason I believe this is a possible

8       scenario is that there is no indication that the overall

9       enterprise risks that the company has evaluated are

10       declining.  The company metrics required to continue

11       remain in question, and there is no sign of joint owners

12       flocking to join the project at this point.  Therefore,

13       the fourth scenario that I identified must be evaluated

14       in order to make an informed decision.

15                 It actually turns to, becomes a matter of risk

16       versus cost.  If it is certain that the project would

17       continue, then the company's option would be the proper

18       one.  If it is certain that the project would be

19       canceled, then it should be canceled sooner rather than

20       later.

21                 However, if there is uncertainty, as there is,

22       there must be a balance between the risk and the cost to

23       the ratepayers.  And, therefore, I recommend in my

24       testimony that the company be required to analyze the

25       fourth scenario that I have identified, and in light of

FLORIDA PUBLIC SERVICE COMMISSION

726

1       this analysis and the identified risks justify the

2       option that they have, they have chosen.

3                 Turning to the Crystal River Unit 3 EPU

4       project, I believe that the company has chosen a

5       nonconservative approach for implementation of the

6       Crystal River Unit 3 EPU.  They will spend most of the

7       money for the project before it is certain that they

8       will receive permission from the NRC to increase the

9       power level to gain the full 180 megawatts of additional

10       power that the project is intended to deliver.  140 of

11       the 180 megawatts comes from increased reactor power

12       that must be authorized by the NRC by approval of the

13       license amendment request.

14                 They could have initiated the license

15       amendment requests earlier to ensure approval or at

16       least have a good indication of approval prior to

17       spending the bulk of the money.  Many EPUs have been

18       accomplished in the past, but this is the first for a

19       Babcock & Wilcox project, and it is a very technically

20       challenging project.

21                 I want to clarify here that the prudence of

22       their decision is not based on the decision that the NRC

23       makes.  If full power is authorized by the NRC, then

24       there is no impact and the issue of prudence is moot.

25       However, if full power is not issued and there is

FLORIDA PUBLIC SERVICE COMMISSION

727

1       impact, then the prudence of the company's decisions

2       should be reviewed in detail.

3                 That concludes my statement.

4                 MR. REHWINKEL:  Dr. Jacobs is tendered for

5       cross-examination.

6                 COMMISSIONER SKOP:  Very well.

7                 Mr. Walls, you're recognized for

8       cross-examination.

9                          CROSS EXAMINATION

10       BY MR. WALLS:

11            Q.   Good afternoon, Dr. Jacobs.

12            A.   Good afternoon.

13            Q.   Dr. Jacobs, is it your opinion that Progress

14       Energy Florida should cancel the Levy nuclear project?

15            A.   No, that's not my opinion at this time.

16            Q.   And is it your opinion, Dr. Jacobs, that

17       Progress Energy Florida should terminate the EPC

18       agreement and cancel the Levy nuclear project?

19            A.   No, it is not.

20            Q.   And, Dr. Jacobs, you would agree that the

21       feasibility analysis that Progress Energy Florida

22       provided this year was sufficient to demonstrate the

23       feasibility of the Levy nuclear project; correct?

24            A.   Yes, it does, given the assumptions that are

25       in here and in that analysis.

FLORIDA PUBLIC SERVICE COMMISSION

728

1            Q.   And if you could turn to page 6, lines 7

2       through 14 of your direct testimony.

3            A.   Okay.

4            Q.   And there you reference the company's

5       strategic intent and objectives in developing the

6       going-forward path for the Levy nuclear project from a

7       March 8, 2010, senior management committee presentation;

8       correct?

9            A.   That's correct.

10            Q.   Do you have that presentation with you?

11            A.   I do not.

12            Q.   Okay.

13                 MS. HUHTA:  May I approach the witness?

14       Excuse me.  May --

15                 COMMISSIONER SKOP:  Yes, you may.

16                 MS. HUHTA:  Thanks.

17       BY MR. WALLS:

18            Q.   And this senior management presentation is

19       marked as Exhibit JE-2 in John Elnitsky's direct

20       testimony?

21            A.   Yes.  That's correct.  I have it.

22            Q.   Okay.  And the reference in your testimony on

23       page 6 at lines 7 through 14 is to page 2 of 15 of

24       Exhibit Number JE-2; is that correct?

25            A.   That's correct.  Yes.

FLORIDA PUBLIC SERVICE COMMISSION

729

1            Q.   Okay.  And you would agree that given the

2       company's intent and given the objectives that they

3       state in this March 8, 2010, senior management committee

4       presentation that the company's actions were reasonable;

5       correct?

6            A.   Yes, I believe they were reasonable.

7            Q.   And you would agree with me that you expressed

8       no opinion in your testimony that the evaluation process

9       the company undertook to make its decision was

10       unreasonable or imprudent, you just believe they should

11       have evaluated another scenario; is that correct?

12            A.   Yes.  That's correct.

13            Q.   Dr. Jacobs, your assignment included the

14       review and evaluation of Progress Energy Florida's

15       request to collect historical costs associated with the

16       Levy nuclear project; correct?

17            A.   That's correct.

18            Q.   And you would agree with me that nowhere in

19       your direct testimony do you express the opinion that

20       Progress Energy Florida's Levy nuclear project costs for

21       2009 are imprudent; correct?

22            A.   That's correct.

23            Q.   And you also indicate at page 3 of your direct

24       testimony, lines 21 to 23 --

25            A.   Okay.

FLORIDA PUBLIC SERVICE COMMISSION

730

1            Q.   -- that your assignment included reviewing and

2       evaluating Progress Energy Florida's request for

3       authority to collect projected costs associated with the

4       Levy nuclear project; correct?

5            A.   Yes.

6            Q.   And by projected costs, you mean Progress

7       Energy Florida's estimated 2010 and projected 2011 costs

8       associated with the Levy nuclear project; right?

9            A.   That's correct.

10            Q.   And would you agree with me that in your

11       testimony there is no opinion that any specific

12       estimated 2010 or projected 2011 Levy nuclear project

13       cost is unreasonable?

14            A.   That's correct.

15            Q.   And it's fair to say that you don't have an

16       opinion this year that Progress Energy Florida's project

17       management contracting and oversight controls for the

18       Levy nuclear project are imprudent; correct?

19            A.   That's correct.  I don't have an opinion that

20       they're imprudent.  I don't -- I did not make an opinion

21       on those topics.

22            Q.   And you didn't make an opinion this year about

23       the company's project management contracting oversight

24       controls because you reviewed them last year and did not

25       see any significant concerns with them; is that correct?

FLORIDA PUBLIC SERVICE COMMISSION

731

1            A.   That's correct.

2            Q.   And you would also agree with me that nowhere

3       in your testimony do you express the opinion that

4       Progress Energy Florida's 2009 accounting and cost

5       oversight controls for the Levy nuclear project are

6       unreasonable or imprudent.

7            A.   That's correct.

8            Q.   I want to turn to the CR3 uprate project.  And

9       again at page 3, lines 18 to 21 of your direct testimony

10       you indicate your assignment included review and

11       evaluation of Progress Energy Florida's request to

12       collect historical costs for the Crystal River 3 unit

13       uprate project; correct?

14            A.   Yes.

15            Q.   And would you agree with me within your

16       testimony there is no expression of an opinion by you

17       that Progress Energy Florida's CR3 uprate costs for 2009

18       are imprudent?

19            A.   Yes, I agree.

20            Q.   You also indicate at page 3, lines 18 to 21 of

21       your testimony that your assignment included reviewing

22       and evaluating Progress Energy Florida's request for

23       authority to collect projected costs associated with the

24       CR3 uprate or EPU extended power uprate; correct?

25            A.   Yes.

FLORIDA PUBLIC SERVICE COMMISSION

732

1            Q.   And by projected costs, you mean Progress

2       Energy Florida's estimated 2010 and projected 2011 costs

3       associated with the uprate project; correct?

4            A.   That's correct.

5            Q.   And would you agree with me that in your

6       testimony there is no opinion that any specific

7       estimated 2010 or projected 2011 CR3 uprate cost is

8       unreasonable?

9            A.   Yes.

10            Q.   And you would also agree with me that nowhere

11       in your testimony do you express an opinion that

12       Progress Energy Florida's 2009 accounting and cost

13       oversight controls for the CR3 uprate project were

14       unreasonable or imprudent?

15            A.   Yes, I agree.

16            Q.   And it's true, Dr. Jacobs, that with respect

17       to the CR3 uprate schedule, you're not expressing an

18       opinion today that that uprate project schedule was

19       imprudent; correct?

20            A.   That's correct.  I have not done a detailed

21       prudence analysis of the schedule.  If the NRC grants

22       the, the full requested power uprate for the reactor and

23       the full 180 power megawatts is achieved, then that

24       topic is, is moot and doesn't need to be evaluated.

25            Q.   Okay.  As you said, you're not expressing an

FLORIDA PUBLIC SERVICE COMMISSION

733

1       opinion today that their schedule is imprudent; correct?

2            A.   That's correct.

3            Q.   And you would also agree that you are not

4       expressing the opinion that Progress Energy Florida

5       should stop work on the Crystal River Unit 3 uprate

6       project; correct?

7            A.   No.  They should continue to work on it.

8                 MR. WALLS:  That's all the questions I have.

9                 COMMISSIONER SKOP:  Thank you.

10                 Any questions from the bench?

11                 Commissioner Edgar, you're recognized.

12                 COMMISSIONER EDGAR:  Thank you.

13                 Good afternoon.

14                 THE WITNESS:  Good afternoon.

15                 COMMISSIONER EDGAR:  You mentioned in your

16       opening and in your prefiled testimony that you believe

17       another possible scenario is the cancellation of the

18       Levy County project after receipt of the combined

19       license in 2012.

20                 THE WITNESS:  That's correct, yes.  There's,

21       there's a point, once they receive the combined license,

22       a decision must be made whether to continue, authorize

23       the EPC contractor to continue with the project or

24       cancel it at that point.

25                 COMMISSIONER EDGAR:  Okay.  And I, and I

FLORIDA PUBLIC SERVICE COMMISSION

734

1       believe you also testified that in your opinion the risk

2       factors are not declining and that there is not at this

3       point in time a joint partner for the project.

4                 THE WITNESS:  That's correct.

5                 COMMISSIONER EDGAR:  Okay.  Is the lack of a

6       joint partner at this time a risk factor, a risk factor,

7       one of the risk factors that you are mentioning?  And if

8       so, how material is that point or fact?

9                 THE WITNESS:  Yes, it is.  I know early on

10       attaining, achieving a joint partner, joint ownership

11       was very important to the company, and it continually

12       shows up in their internal documents as an important

13       factor that they're, that they're trying to achieve.  I

14       think it would certainly help the economics from a

15       Progress Energy perspective if they could have a joint

16       ownership.  So I think that's an important factor.

17                 COMMISSIONER EDGAR:  What other risk factors

18       do you deem material to support your statement that

19       cancellation after the combined license in 2012 is a

20       realistic scenario, or a scenario of great potential,

21       whatever would be your words?

22                 THE WITNESS:  Let me address that.  You know,

23       Mr. Lyash spent about 30 pages going through these risk

24       factors, and we're kind of generally in agreement with

25       identification of them.

FLORIDA PUBLIC SERVICE COMMISSION

735

1                 There are really three or four main factors I

2       think that are influencing development of new nuclear

3       power plants, and have changed significantly in the last

4       several years.  And those are, one, due to the economic

5       recession, the load growth is not what was projected.

6       Another factor is the low cost of natural gas.  It's low

7       and it's projected to be fairly low for the foreseeable

8       future.  So that cuts against the benefits of nuclear

9       power.  A third factor is the uncertainty in any type of

10       carbon cost or carbon tax on fossil fuel plants.  And,

11       you know, a carbon tax on either gas or a coal-fired

12       plant helps nuclear.  So those are some of the major

13       factors that are affecting the decision.

14                 COMMISSIONER EDGAR:  Okay.  Thank you.

15                 THE WITNESS:  Okay.  Thank you.

16                 COMMISSIONER SKOP:  Any additional questions

17       from the bench?  Okay.

18                 Mr. Jacobs, I just have one brief follow-up to

19       a line of questioning that Mr. Walls asked.

20                 You testified that in considering, in making a

21       prudency determination, that in your opinion management

22       I guess in, as you stated, failed to consider one option

23       that involved termination of the entire project after

24       the combined operating license was issued.  And if I

25       understand your testimony correct, I think the question

FLORIDA PUBLIC SERVICE COMMISSION

736

1       I would have in that regard, in rendering a prudency

2       determination, is it required for the Commission or

3       required for management to anticipate and fully evaluate

4       every possible alternative versus the reasonable

5       alternatives that management has, has chosen to pursue?

6                 THE WITNESS:  Well, I think they need to

7       evaluate all reasonable alternatives that a, that a

8       qualified utility manager should be anticipated would

9       identify, given their, what they knew at the time.

10                 COMMISSIONER SKOP:  Could there be, could

11       there perhaps exist contractual obligations or

12       conditions that would make choosing one course of action

13       more preferable than another in rendering that, or

14       considering such an option?

15                 THE WITNESS:  Yes.  I mean, certainly the

16       contractual items would have an impact on that.

17                 COMMISSIONER SKOP:  Very well.  Thank you.

18                 THE WITNESS:  Thank you.

19                 COMMISSIONER SKOP:  All right.  Any questions

20       from staff before we go to redirect?

21                 MR. DAVIS:  I have one question.

22                 COMMISSIONER SKOP:  Okay.

23                 MR. YOUNG:  I think --

24                 COMMISSIONER SKOP:  SACE.  Okay.  Go down the

25       line.  All right.  Very well.  SACE, you're recognized.

FLORIDA PUBLIC SERVICE COMMISSION

737

1                          CROSS EXAMINATION

2       BY MR. DAVIS:

3            Q.   Dr. Jacobs, Gary Davis representing SACE.

4       Just one question for you.  You would agree that your

5       prefiled testimony expresses no opinion about the

6       feasibility of the Levy nuclear project; correct?

7            A.   That's correct.

8            Q.   And you would also agree that your prefiled

9       testimony expresses no opinion about whether or not

10       Progress's actions that were decided by the board on

11       March 8th, 2010, were reasonable.

12                 MR. WALLS:  I'm going to object to this.  This

13       is not cross-examination.

14                 COMMISSIONER SKOP:  To the objection.

15                 MR. DAVIS:  Why is that?  It certainly is

16       cross-examination.  It's certainly not friendly cross,

17       because I'm just --

18                 COMMISSIONER SKOP:  Mr. Walls, can you be a

19       little bit more specific?

20                 MR. WALLS:  I believe it is friendly cross

21       because he's trying to establish a position consistent

22       with what SACE is taking, and OPC and them are aligned.

23                 COMMISSIONER SKOP:  Again, the Order

24       Establishing Procedure and the Prehearing Order, you

25       know, reflects that friendly cross should be limited.

FLORIDA PUBLIC SERVICE COMMISSION

738

1       Is there a way that perhaps you can reframe the question

2       so that it's not friendly cross?

3                 MR. DAVIS:  I can ask a more direct question

4       rather than a leading question.

5                 COMMISSIONER SKOP:  Okay.  We'll see if that

6       will get us by the objection.  If not, Mr. Walls, you're

7       free to object to the reframing of the question.

8       BY MR. DAVIS:

9            Q.   Does your prefiled testimony, Dr. Jacobs,

10       contain any opinion about the reasonableness of the

11       conduct of Progress Energy with regard to the Levy

12       nuclear plant?

13            A.   Well, it's in my testimony that I believe they

14       should have considered the fourth scenario that I have

15       identified.

16            Q.   Other than that, there's no opinion about the,

17       the scenarios that were analyzed and the actions taken;

18       is that correct?

19                 MR. WALLS:  Objection.

20                 COMMISSIONER SKOP:  What's the basis for the

21       objection?

22                 MR. WALLS:  Again, friendly cross.

23                 COMMISSIONER SKOP:  Okay.  To the objection.

24                 MR. DAVIS:  I'll withdraw the question.  The

25       prefiled testimony speaks for itself.

FLORIDA PUBLIC SERVICE COMMISSION

739

1                 COMMISSIONER SKOP:  All right.  Very well.

2       Any additional questions?

3                 MR. DAVIS:  No.

4                 COMMISSIONER SKOP:  Any other questions for

5       the witness before we go to redirect?

6                 Okay.  Mr. Rehwinkel.

7                 MR. REHWINKEL:  Thank you.  Just a few.  Thank

8       you, Mr. Chairman.

9                         REDIRECT EXAMINATION

10       BY MR. REHWINKEL:

11            Q.   Dr. Jacobs --

12                 MR. YOUNG:  Mr. Chairman, before we go to

13       Mr. Rehwinkel, staff has no questions.

14                 COMMISSIONER SKOP:  All right.  Yeah.  I asked

15       staff before.  Okay.  So, I mean, when we go one way,

16       it's real easy to follow.  In reverse order you got to

17       kind of stop and think.  So, all right, but I thought

18       that staff had said that previously, which is why I went

19       to the Intervenor.  So I think we're on course.

20                 Mr. Rehwinkel, you're recognized.

21                 MR. REHWINKEL:  Thank you, Mr. Chairman.

22       BY MR. REHWINKEL:

23            Q.   Dr. Jacobs, does the silence in your testimony

24       on the Levy nuclear plant historical costs mean that you

25       are affirmatively agreeing with or making an affirmative

FLORIDA PUBLIC SERVICE COMMISSION

740

1       finding about those costs?

2            A.   No, it does not.

3            Q.   Does your silence on the Levy nuclear plant

4       projected costs mean that you're making an affirmative

5       agreement with those costs or making an affirmative

6       finding as to their appropriateness?

7            A.   No.  I have not issued an opinion on those.

8            Q.   Does your silence on management controls and

9       oversight of the Levy nuclear plant mean that you are

10       making, you are affirmatively agreeing or making an

11       affirmative finding with respect to those oversight and

12       control activities?

13            A.   No, it does not.

14            Q.   Does your silence on the CR3 historical costs

15       mean that you are affirmatively agreeing with or making

16       an affirmative finding with respect to those costs?

17            A.   No, it does not.

18            Q.   Does your silence on the CR3 projected costs

19       mean that you're affirmatively agreeing with or making

20       an affirmative finding on those costs?

21            A.   No.

22            Q.   And finally, does your silence on the

23       management controls and oversight activities of Progress

24       with respect to the CR3 plant mean you are affirmatively

25       agreeing with or making an affirmative finding on those

FLORIDA PUBLIC SERVICE COMMISSION

741

1       activities?

2            A.   No.

3            Q.   Dr. Jacobs, you were asked the question about

4       joint owners.

5            A.   Yes.

6            Q.   Are you aware of any other AP 1000 projects

7       with joint owners?

8            A.   Yes, I am.  The two other projects that have

9       signed EPC contracts, one is the Vogtle Unit 3 and 4

10       project being managed by Georgia Power Company has joint

11       owners, and also the Summer Unit 2 and 3 project being

12       managed by South Carolina Electric & Gas also has joint

13       owners.

14            Q.   Do you know the percentage of joint owners for

15       the Vogtle plant?

16            A.   Yes.  Vogtle, Georgia Power owns 45.7 percent,

17       a little under 50 percent of that project, and then

18       Oglethorpe Municipal Energy Authority, Electric

19       Authority of Georgia in the city of Dalton own the rest.

20       And I believe the Summer project is around a 50/50

21       split.  I'm not precisely sure.

22            Q.   Are you aware of the impact of joint ownership

23       on the projected customer bills for the Vogtle plant?

24            A.   Yes, sir.  For the, for the Vogtle project,

25       when both units are in service, which is projected to be

FLORIDA PUBLIC SERVICE COMMISSION

742

1       in 2016 and 2017 for both units, it's anticipated that

2       there would be about a $9 per month per 1,000 kilowatt

3       impact on the average customer.

4            Q.   Okay.  You were asked a question about -- I'll

5       withdraw that.

6                 Those are all the questions I have.  Thank

7       you.

8                 COMMISSIONER SKOP:  Very well.  Thank you.  At

9       this point I guess we need to take up exhibits for

10       Dr. Jacobs.  I believe that's Exhibit 31 through 33, if

11       my memory serves me correctly.

12                 MR. REHWINKEL:  We would move those.

13                 COMMISSIONER SKOP:  All right.  Any

14       objections?  Hearing none, show those Exhibits 31

15       through 33 entered into the record.

16                 (Exhibits 31 through 33 admitted into the

17       record.)

18                 MR. REHWINKEL:  And may Dr. Jacobs be excused

19       from the hearing?

20                 COMMISSIONER SKOP:  He may.  Thank you.

21                 MR. REHWINKEL:  He's -- I take that back.

22                 COMMISSIONER SKOP:  He's coming back for

23       rebuttal.

24                 MR. REHWINKEL:  Well, no.  May he be excused

25       for the Progress portion of the hearing?

FLORIDA PUBLIC SERVICE COMMISSION

743

1                 COMMISSIONER SKOP:  Yes, you may be excused

2       for the Progress portion of the hearing.  Thank you.  I

3       knew there was something there.

4                 MR. REHWINKEL:  I almost got you out.

5                 COMMISSIONER SKOP:  Okay.  I believe that

6       takes us now to the joint testimony of staff witnesses.

7       So, staff, you're recognized to call your witnesses.

8                 MR. YOUNG:  Thank you, Mr. Chairman.  At this

9       time, staff would like to call William Coston and Kevin

10       Carpenter to the stand.

11                 COMMISSIONER SKOP:  And Mr. Coston and

12       Carpenter, have you been sworn, previously sworn?  All

13       right.  Very well.  Thank you.

14                 Mr. Young, you may proceed.

15                 MR. YOUNG:  Mr. Chairman, may we approach?

16                 COMMISSIONER SKOP:  You may.

17                 MR. YOUNG:  All right.  And just a point of

18       information, Mr. Chairman.  What is being handed out by

19       staff is the revised Exhibit CC-1, which is Number 77 on

20       staff's, on the, excuse me, on the Comprehensive Exhibit

21       List.  Also it's my understanding that Mr. Brew has

22       given Ms. Bennett some documents to hand out for his

23       cross-examination of staff's witnesses.  So --

24                 COMMISSIONER SKOP:  Okay.  We'll take these up

25       one at a time at the appropriate time.  Again, I believe

FLORIDA PUBLIC SERVICE COMMISSION

744

1       that staff's confidential document that they've handed

2       out is marked for identification as Exhibit 77, and that

3       is the review of Progress Energy Florida's progress --

4       project management internal controls for nuclear plant

5       uprate and construction projects.

6                 MR. YOUNG:  Yes, sir.  And we will discuss

7       that in terms of the revisions during the appropriate

8       time.

9                 COMMISSIONER SKOP:  All right.  Very well.

10       And, Mr. Brew, and for the purpose of expediency, do we

11       want to put a number on your two exhibits?

12                 MR. BREW:  Yes.  Thank you, Mr. Chairman.  I

13       thought by way of getting things out of the way early,

14       I've handed the witnesses two documents.  One is labeled

15       Staff Response to PCS Interrogatories.  The other is

16       labeled Staff Response to PCS Request for POD, and ask

17       that they be marked for identification as Exhibits

18       210 and 211.

19                 COMMISSIONER SKOP:  All right.  Very well.

20       The first exhibit will be marked for identification as

21       Exhibit 210 and the second one as 211.

22                 (Exhibits 210 and 2ll marked for

23       identification.)

24                 The first, Staff Response to PCS

25       Interrogatories has been marked for identification as

FLORIDA PUBLIC SERVICE COMMISSION

745

1       Exhibit 210, and the Staff Response to PCS Request for

2       POD is going to be marked for identification as Exhibit

3       211.  All right.

4                 And, Mr. Young, you may proceed.

5                 MR. YOUNG:  Thank you, sir.

6                  WILLIAM COSTON and KEVIN CARPENTER

7       were called as witnesses on behalf of Florida Public

8       Service Commission Staff and, having been duly sworn,

9       testified as follows:

10                          DIRECT EXAMINATION

11       BY MR. YOUNG:

12            Q.   Good afternoon.

13            A.   (By Mr. Coston) Good afternoon.

14            A.   (By Mr. Carpenter) Good afternoon.

15            Q.   Have you been sworn?

16            A.   (By Mr. Coston) Yes.

17            A.   (By Mr. Carpenter) yes.

18            Q.   Can both of you please state your name and

19       business address for the record?

20            A.   (By Mr. Coston) William Coston, 2540 Shumard

21       Oak Boulevard, Tallahassee, Florida 32399.

22            A.   (By Mr. Carpenter) Kevin Carpenter, 2540

23       Shumard Oak Boulevard, Tallahassee, Florida 32399.

24            Q.   By whom are you employed and in what capacity?

25            A.   (By Mr. Coston) I'm employed by the Florida

FLORIDA PUBLIC SERVICE COMMISSION

746

1       Public Service Commission as a Government Analyst 2 in

2       the Office of Auditing and Performance Analysis.

3            Q.   Have you jointly prefiled testimony consisting

4       of five pages in this case as it relates to Progress

5       Energy Florida?

6            A.   (By Mr. Coston) Yes, we have.

7            A.   (By Mr. Carpenter) Yes.

8            Q.   Do you have any changes or corrections to that

9       testimony?

10            A.   (By Mr. Coston) Staff notes that we have

11       refiled an updated Exhibit CC-1 to incorporate Progress

12       Energy Florida's revised confidentiality request and to

13       reflect Order No. PSC-10-0534-PCO-EI.  In addition, in

14       our refiled Exhibit CC-1 we corrected the exhibit page

15       numbering in the top right-hand corner of each page and

16       corrected the page numbering.  But I believe you asked

17       me about my testimony, did you not?

18            Q.   All right.  If I were to ask you the same

19       questions in your joint prefiled testimony today, would

20       your answers be the same?

21            A.   (By Mr. Coston) Yes.

22            A.   (By Mr. Carpenter) Yes.

23                 MR. YOUNG:  Mr. Chairman, at this time we ask

24       that the joint prefiled testimony of Mr. William Coston

25       and Kevin Carpenter be entered into the record as though

FLORIDA PUBLIC SERVICE COMMISSION

747

1       read.

2                 COMMISSIONER SKOP:  The joint prefiled

3       testimony of Mr. Coston and Carpenter will be entered

4       into the record as though read.  You may proceed.

5       BY MR. YOUNG:

6            Q.   Did you have one exhibit attached to your

7       testimony as relates to Progress Energy Florida, which

8       is labeled Progress Energy, which is the project

9       management internal controls relating to Progress Energy

10       Florida nuclear plant uprate and construction projects?

11            A.   (By Mr. Coston) Yes, we do.

12            Q.   Do you have any changes or corrections to that

13       exhibit other than the ones you've previously stated?

14            A.   (By Mr. Coston) Not except for the ones I've

15       previously stated.

16                 MR. YOUNG:  Mr. Chairman, I ask that that

17       Exhibit CC-1, which is the revised CC-1, is, and is

18       marked as Number 77 on the Comprehensive Exhibit list be

19       identified as such.

20                 COMMISSIONER SKOP:  Okay.  Show it done.  And

21       that's not yet entered.

22                 MR. YOUNG:  No, sir.

23                 COMMISSIONER SKOP:  All right.  Very well.

24                 (Exhibit 77 marked for identification.)

25

FLORIDA PUBLIC SERVICE COMMISSION

753

1       BY MR. YOUNG:

2            Q.   Do you have a summary of your testimony?

3            A.   (By Mr. Coston) Yes, we do.

4            Q.   Can you please provide a summary of your

5       testimony as it relates to Progress Energy Florida?

6            A.   (By Mr. Coston) Yes.  Good afternoon,

7       Commissioners.  Our testimony presents a management

8       audit review of the project management internal controls

9       that Progress Energy is using in managing the Crystal

10       River nuclear unit uprate and the construction of its

11       Levy nuclear project.

12                 The primary objective of this review was to

13       document and assess the key developments for both

14       projects.  Our review included examining the

15       organizational, management, internal controls and

16       oversight that Progress Energy Florida has in place for

17       these projects.

18                 The internal controls examined were related to

19       the following key areas of project activity:  Planning

20       and project management oversight, management and

21       organization, cost controls and schedule controls,

22       contractor selection and management, and auditing and

23       quality assurance.

24                 For the Levy nuclear project, in 2009 the

25       company evaluated the project's future and made the

FLORIDA PUBLIC SERVICE COMMISSION

754

1       decision to extend the schedule by at least 60 months

2       from its original 2016 in-service date.  Currently the

3       company's focus is to obtain the combined operating

4       license from the Nuclear Regulatory Commission, which

5       the company currently expects in late 2012 or early

6       2013.  The company does not plan to complete any major

7       construction on the Levy nuclear project until after

8       receiving this approval.

9                 In keeping with its decision to shift the

10       construction schedule for the Levy nuclear project,

11       Progress Energy Florida renegotiated its existing

12       engineering procurement and construction contract with

13       the consortium of Westinghouse and Shaw Stone & Webster.

14       The amended contract now allows for this extended shift

15       in schedule.

16                 Additionally, the company anticipated an

17       increase in the total project cost as a result of the

18       schedule shift, and the company has identified these

19       costs in the new estimates in its overall integrated

20       project plan.  Audit staff determined that the

21       management approach and internal controls used to

22       evaluate and select the final decision for the Levy

23       nuclear project were reasonable.

24            A.   (By Mr. Carpenter) In 2009, the company also

25       moved forward with the extended power uprate project for

FLORIDA PUBLIC SERVICE COMMISSION

755

1       its Crystal River 3 unit.  The project management team

2       demonstrated that the work completed during 2009 was

3       within the original schedule range and budget range

4       approved by management.  Overall, the company estimates

5       that the final project costs will be approximately

6       12 percent over the original estimate.

7                 During the 2009 refueling outage, while

8       performing the steam generator replacement, the company

9       identified a delamination in the unit's containment

10       vessel wall.  While this event is not related to the

11       extended power uprate project, the repair timeline will

12       delay the company's future uprate schedule.  Audit staff

13       recommends that the Commission monitor for potential

14       impacts on the uprate schedule and cost estimates as a

15       result of the delamination repairs.

16                 Additionally, the company has experienced

17       challenges with the low pressure turbines it plans to

18       install as part of the uprate project.  Audit staff

19       recommends the Commission continue to monitor the impact

20       of the turbine manufacture and installation to ensure

21       that no unnecessary additional costs are incurred as a

22       result of the manufacturing issues, and that the plan

23       versus, the plan versus achieved megawatt electricity

24       output resulting from any changes is properly handled.

25                 Finally, the company has not submitted its

FLORIDA PUBLIC SERVICE COMMISSION

756

1       license amendment request with the Nuclear Regulatory

2       Commission to operate at the anticipated additional

3       180 megawatts of electricity once the project is

4       complete.  In 2009, the company determined after review

5       by an expert panel that its original draft license

6       amendment request application would not meet the Nuclear

7       Regulatory Commission's expectation or approval.  The

8       company spent the second half of 2009 and the first half

9       of 2010 restructuring and strengthening its application.

10                 Audit staff recommends that the Commission

11       consider whether additional costs incurred as a result

12       of these actions were a result of inadequate management

13       oversight.

14                 That concludes our summary.  Thank you.

15                 MR. YOUNG:  Mr. Chairman, before we tender

16       Mr. Coston and Mr. Carpenter for cross, I'd like to note

17       on page 13 of staff's revised exhibit, we, we

18       highlighted in yellow, it is confidential, so any

19       questions, just a point of information to the parties,

20       if any questions relating to that, please be careful on

21       that.

22                 COMMISSIONER SKOP:  All right.  Very well.  At

23       this point staff has tendered the witness for

24       cross-examination, and who's going first?  We're going

25       to start with the Intervenors or I believe Progress.

FLORIDA PUBLIC SERVICE COMMISSION

757

1                 MR. WALLS:  No questions.

2                 COMMISSIONER SKOP:  Okay.  Very well.  Any

3       questions from the Intervenors?  Mr. Rehwinkel?

4                 MR. REHWINKEL:  Yes.

5                          CROSS EXAMINATION

6       BY MR. REHWINKEL:

7            Q.   Good afternoon.

8            A.   (By Mr. Coston) Good afternoon.

9            A.   (By Mr. Carpenter) Good afternoon.

10            Q.   Charles Rehwinkel with the Public Counsel's

11       Office.  I guess the way I'll ask questions, I'll lob

12       the question out there, and whoever is the right one to

13       answer it, answer it.

14            A.   (Mr. Coston) Okay.

15            Q.   In the testimony on page 4, on lines 1 through

16       7, you state conclusions regarding the nuclear, the Levy

17       nuclear project; is that correct?

18            A.   (By Mr. Coston) Yes.

19            Q.   Okay.  There's a statement in here on lines 6

20       through 7 that says, "Given the uncertainties facing the

21       company, keeping the project progressing without further

22       substantial investment is a reasonable approach at this

23       time -- "is a reasonable approach at this point in

24       time."  Is that correct?

25            A.   (By Mr. Coston) By Progress, yes.

FLORIDA PUBLIC SERVICE COMMISSION

758

1            Q.   Okay.  Now does your testimony make a judgment

2       about whether Progress will ultimately take the

3       appropriate steps to restart the project?

4            A.   (By Mr. Coston) Our testimony speaks to the

5       decision-making process the company went through to make

6       the decision to extend its schedule.  And this, this

7       statement reflects that.

8            Q.   Okay.  So is it true then that your testimony

9       makes no judgment about whether Progress will ultimately

10       build the Levy nuclear plant?

11            A.   (By Mr. Coston) No.  It does not make --

12            Q.   Is it true that it makes no judgment?

13            A.   (By Mr. Coston) It makes no judgment.  Excuse

14       me.

15            Q.   So the answer would be yes for the record.

16            A.   (By Mr. Coston) Okay.

17            Q.   When you made this statement -- let me strike

18       that and say it this way.  Isn't it true that when you

19       provided your testimony, you did not have the

20       information contained in John Elnitsky's rebuttal

21       testimony Exhibit JE-6?

22            A.   (By Mr. Coston) We did not have that specific

23       testimony on hand when we filed our testimony or made

24       this assessment.

25            Q.   Did you review Exhibit JE-6 to John Elnitsky's

FLORIDA PUBLIC SERVICE COMMISSION

759

1       rebuttal testimony?

2            A.   (By Mr. Coston) We have reviewed that.

3            Q.   Okay.  Do you have a copy of that with you?

4       Do you have the confidential version?

5            A.   (By Mr. Coston) We have a redacted version.

6            Q.   Okay.  If I could hand --

7                 MR. REHWINKEL:  Mr. Chairman, if I could

8       approach the witness and hand them a copy of the

9       confidential version.

10       BY MR. REHWINKEL:

11            Q.   This is JE, Exhibit JE-6 attached to the

12       August 3rd, 2010, testimony of John Elnitsky.  And I'm

13       going to ask you questions without asking --

14                 MR. YOUNG:  Mr. Chairman?  I'm sorry.

15                 COMMISSIONER SKOP:  Hold on, Mr. Rehwinkel.

16                 Mr. Young.

17                 MR. YOUNG:  Is it possible I can get the un,

18       the, the confidential version of that testimony?

19                 COMMISSIONER SKOP:  The redacted version or

20       the non-redacted?

21                 MR. YOUNG:  The non-redacted version.

22                 COMMISSIONER SKOP:  Okay.

23                 Mr. Rehwinkel, do you--

24                 MR. YOUNG:  Because he's asking confidential.

25                 COMMISSIONER SKOP:  Do you have a copy of the

FLORIDA PUBLIC SERVICE COMMISSION

760

1       confidential version?

2                 MR. REHWINKEL:  I do not.  I mean, that was my

3       copy.  Yeah.  I think -- yeah.

4                 COMMISSIONER SKOP:  All right.  Is there

5       another copy around or is there a way we can work

6       through this?  Perhaps, you know, staff might be able to

7       look over someone's shoulder.

8                 MR. YOUNG:  Thank you.

9                 MR. REHWINKEL:  I think Mr. Walls is

10       accommodating.  I appreciate that.

11                 COMMISSIONER SKOP:  He's got them working well

12       for you.

13                 MR. REHWINKEL:  I think everybody has been

14       very professional about litigating without taking it

15       personally here.

16                 COMMISSIONER SKOP:  Sharing the workload.

17       It's all good.

18       BY MR. REHWINKEL:

19            Q.   My question to you is, and I don't want you to

20       utter any of the numbers --

21            A.   (By Mr. Coston) Certainly.

22            Q.   -- in this in any answers that I, that I ask,

23       ask for.  This testimony was filed on August 3rd, 2010.

24       Your report was filed in July of 2010; is that correct?

25            A.   (By Mr. Coston) That is correct.

FLORIDA PUBLIC SERVICE COMMISSION

761

1            Q.   Okay.  The number that is contained, that is

2       summarized, that is the summary number in JE-6, is that

3       a number that you considered when drafting your

4       testimony?

5            A.   (By Mr. Coston) You're making reference to the

6       top number or the bottom chart?

7            Q.   The number that is, and I believe I can say

8       this, greater than 400 million.

9            A.   (By Mr. Coston) That number was not -- I do

10       not recall being provided during the course of our

11       review.

12            Q.   Were you aware of the magnitude of that number

13       when you did your review?

14            A.   (By Mr. Coston) Again, that number was not

15       provided and I was not aware of that number.

16            Q.   So you would not have been aware of that?

17            A.   (By Mr. Coston) No.

18            Q.   Okay.  Is that number greater than what you

19       thought it would be at the time you wrote your

20       testimony?

21            A.   (By Mr. Coston) I have not had an opportunity

22       to look at what the number is speaking to.  When we

23       create, wrote our testimony in reference to the, the

24       assertion that we make that we spoke to earlier on page

25       4, that was looking at the decision-making process,

FLORIDA PUBLIC SERVICE COMMISSION

762

1       which looked at costs but looked at the greater totality

2       of the internal controls in the project management

3       approach.  So numbers were one aspect of what we looked

4       at, including the chart listed above, but the bottom

5       number we did not look at, we were not aware of.

6            Q.   Okay.  And your, your opinion that is

7       contained on lines 6 and 7 on page 4 is from a project

8       decision-making standpoint and not necessarily based on

9       a customer impact; is that correct?

10            A.   (By Mr. Coston) That's correct.  We did not

11       look at the customer impact.

12            Q.   Okay.  Okay.  I can relieve you of the burden

13       of that confidential information.

14                 I want to turn now, I want to turn now to the

15       CR3 project, and ask that you turn to page 45 of the, of

16       the audit.  What do I call this exhibit?  This is the

17       audit report.  Okay.  Now at this point in time there's

18       no confidential information on page 45; is that correct?

19            A.   (By Mr. Coston) That's correct.

20            Q.   Okay.  In your review of the CR3 EPU project,

21       did you look at the budget for the project, or cost

22       estimate, I should say?

23            A.   (By Mr. Coston) We did look at the cost

24       estimate.

25            Q.   Okay.  Now in your testimony, or in this, the

FLORIDA PUBLIC SERVICE COMMISSION

763

1       audit report, you state that the project, the initial

2       project cost estimate was approximately $427 million; is

3       that correct?

4            A.   (By Mr. Coston) Yes.

5            Q.   Okay.  And you say there was a base

6       $250 million uprate work estimate.  What do you mean by

7       base?

8            A.   (By Mr. Coston) That number was the number

9       provided by the company as the base for its technical

10       work of the project.  At inception in the 2006 business

11       analyst package, that's what they included in that

12       package.

13            Q.   Okay.  Now did you make any judgment about the

14       $89 million for transmission upgrades as far as whether

15       it -- let me strike that question.

16                 There's a statement in here that there, there

17       was $89 million for transmission upgrades; is that

18       right?

19            A.   (By Mr. Coston) Yes.

20            Q.   Okay.  Did you make any judgment about whether

21       that $89 million should be appropriate for the current

22       budget to be measured against?

23            A.   (By Mr. Coston) We did not.

24            Q.   Okay.  Did you learn anything about whether,

25       in your, in your audit work, about whether the -- well,

FLORIDA PUBLIC SERVICE COMMISSION

764

1       let me strike that question.

2                 In reviewing the company documents, did you

3       look at the July 2nd, 2009, audit of the CR3 EPU?

4            A.   (By Mr. Coston) We did look at that audit.

5            Q.   Okay.  Did you look at the audit work papers

6       associated with that audit?

7            A.   (By Mr. Coston) We looked at the management

8       response to the audit.  I cannot recall if we looked

9       specifically at the work papers themselves.  We spoke

10       with the audit manager who conducted the audit and

11       conducted the interview.

12            Q.   Okay.  Now, as part of your, the opinion that

13       you would render to the Commission in this audit report,

14       this July 2010 audit report, would you be concerned with

15       the company's adherence to the project budget from a

16       cost standpoint?

17            A.   (By Mr. Coston) I don't recall the specifics

18       of that audit report.  If you have a copy, I'd be glad

19       to look at it.

20            Q.   Well, I guess my question was just generally

21       with respect to the audit report that you performed,

22       would, would adherence to the budget, for the overall

23       project budget, is that something that you would look at

24       with respect to developing your opinions in the audit

25       report?

FLORIDA PUBLIC SERVICE COMMISSION

765

1            A.   (By Mr. Coston) Certainly.

2            Q.   Did, did you see any evidence in the July 2nd

3       audit report work papers that the Phase 2 portion of the

4       EPU uprate was 50 percent over budget?

5            A.   (By Mr. Coston) Certainly we looked at the

6       budget aspects of that and looked at the budget in the

7       totality of the original budget that was provided to the

8       IPP, in the IPP for the project and the company's

9       approach to that.  And the management audits, or the

10       audits that we reviewed, we spoke with management on

11       their response to those audits in addressing the

12       concerns that the audit managers had in relation to

13       those audits.

14            Q.   Okay.  If, if the, there was not a specific

15       finding in the company's internal audit by the ASD, the

16       Audit Services Division, would you not then be of any,

17       have any concern if -- if there was not a specific

18       finding in the ASD work product, you would not look

19       behind that?

20            A.   (By Mr. Coston) We requested and received the

21       audits that were completed by the company, the

22       management response to those audits, and spoke with the

23       audit managers for those audits, and certainly looked at

24       those and discussed the, the findings and the company's

25       approach to resolving those findings.  So, and we

FLORIDA PUBLIC SERVICE COMMISSION

766

1       certainly, any time there would be a, an issue or an

2       improvement, requirement or something to that effect,

3       certainly talked through how the company has addressed

4       those.

5            Q.   Okay.  So if there was not a finding in the

6       July 2nd, 2009, report about the Phase 2 portion of the

7       CR3 uprate being 50 percent over budget, then that would

8       not have been something that you would have been aware

9       of; is that correct?

10            A.   (By Mr. Coston) I would have to really look at

11       the July audit and kind of refresh my memory on what the

12       audit said to determine how we approached.

13                 MR. REHWINKEL:  Okay.  Mr. Chairman, I would

14       like to inquire of staff witnesses using an exhibit that

15       was admitted with Mr. Franke's testimony.  I just need

16       to get a hand on it.

17                 COMMISSIONER SKOP:  All right.  We'll hold in

18       place for a moment.

19                 And, staff, since the exhibit has been moved

20       into evidence already, I'm sure that staff would have no

21       objection to the use of the exhibit.

22                 MR. YOUNG:  Not at this time.

23                 COMMISSIONER SKOP:  All right.

24                 MR. REHWINKEL:  This is Exhibit 199 for

25       everybody.

FLORIDA PUBLIC SERVICE COMMISSION

767

1                 COMMISSIONER SKOP:  Very well.

2                 MR. REHWINKEL:  And I would like to hand

3       Mr. Brew's copy of this exhibit to the witness and

4       reference page, Bates stamp page 10 NC OPC

5       POD2-45-000488, and ask the witnesses to review that

6       document.

7                 MR. YOUNG:  And, Mr. Chairman, just for point

8       of clarification.

9                 COMMISSIONER SKOP:  Mr. Young.

10                 MR. YOUNG:  This is -- or point of inquiry.

11       This is a confidential document; correct?

12                 MR. REHWINKEL:  Yes, it is.

13                 MR. YOUNG:  And you're talking about the page,

14       if I'm following correctly, that begins with the word

15       "final."  Or am I mistaken on the page?

16                 MR. REHWINKEL:  Yes.  Which is, which is a

17       line that is not highlighted in yellow.

18                 MR. YOUNG:  Okay.

19                 COMMISSIONER SKOP:  Before the witness answers

20       the questions, let's make sure that the information

21       we're not disseminating is in fact not confidential.

22                 MR. REHWINKEL:  Yes.

23                 COMMISSIONER SKOP:  Everyone in agreement on

24       that?

25                 MR. YOUNG:  Can you repeat?  I'm sorry, sir,

FLORIDA PUBLIC SERVICE COMMISSION

768

1       can you repeat --

2                 COMMISSIONER SKOP:  I just want to make

3       sure -- and I appreciate you taking the time to ask

4       Mr. Rehwinkel.  I just want to make sure that the

5       information contained in his proposed question is not

6       going to be confidential.  So we'll check and balance

7       here.  But as long the parties agree it's not a problem,

8       you may proceed.

9                 But, Mr. Walls, do you have something to add?

10                 MR. WALLS:  Yeah.  Mr. Young is correct.  That

11       line is not highlighted.

12                 COMMISSIONER SKOP:  All right.  Better to be

13       safe than sorry.

14                 MR. YOUNG:  Yes.

15                 COMMISSIONER SKOP:  Thank you.  You may

16       proceed.

17       BY MR. REHWINKEL:

18            Q.   The first page, if you can keep your finger on

19       that page, the first page of this document says, "Audit

20       services department CR3 EPU and SGR projects July 2,

21       2009."  Do you see that?

22            A.   (By Mr. Coston) Yes.

23            Q.   Okay.  Is -- so going back to Bates stamp page

24       488, is this information that's on this first line in

25       that first sentence, is that information you were aware

FLORIDA PUBLIC SERVICE COMMISSION

769

1       of when you prepared your audit report?

2            A.   (By Mr. Coston) Yes.  We did review this

3       document with the company.

4            Q.   Okay.  So were you aware of budget costs for

5       Phase 2 being 50 percent over in the financial view

6       compared to project estimates?

7            A.   (By Mr. Coston) Yes.  We did go through the

8       findings that were outlined in this audit as well as the

9       improvements that the company or the audit staff

10       identified and management's response to how they were

11       managing and tracking the costs.

12            Q.   So does the fact that you offer no opinion

13       about that mean there was not a concern to you about the

14       project being 50 percent over budget, Phase 2 portion of

15       it?

16            A.   (By Mr. Coston) Well, in relation to the

17       audit, we looked at the audit and were satisfied that

18       the, that the items that were identified by the

19       company's Audit Services Department were adequately

20       addressed by management.

21            Q.   Okay.  If the company -- so from the

22       standpoint of the customers and the costs that the

23       company is seeking to recover, does your audit report

24       say that it's okay for them to be over budget, or are

25       you not offering an opinion about that aspect of their

FLORIDA PUBLIC SERVICE COMMISSION

770

1       project?

2                 MR. YOUNG:  Objection.  Asked and answered.

3       Just to be, to expound on the objection, I think the

4       witness has answered that question, that they did not,

5       did not express an opinion as it relates to the

6       50 percent over the financial, 50 percent over the

7       financial view compared to the project estimates.

8                 COMMISSIONER SKOP:  Mr. Rehwinkel, to the

9       objection.

10                 MR. REHWINKEL:  I really don't think that

11       part of my -- I didn't think I asked that question yet.

12       I mean, that's what I want to know.  I don't feel like

13       there's an answer to that.  I mean, my question isn't

14       critical.  I'm just trying to understand the nature of

15       the opinion that is being offered in the audit report.

16                 COMMISSIONER SKOP:  All right.  I'm going to

17       overrule the objection.  You may proceed.

18                 THE WITNESS:  (By Mr. Coston) Could I have you

19       repeat the question?

20                 MR. REHWINKEL:  Okay.  Let me see if I can --

21       can the court reporter read my question back?

22                 (Foregoing question read by the court

23       reporter.)

24                 THE WITNESS:  (By Mr. Coston) Thank you.

25       We're not offering an opinion on the overage or underage

FLORIDA PUBLIC SERVICE COMMISSION

771

1       of the budget.  What we are offering, our review looks

2       at, is how the company monitors and evaluates through

3       its internal control process its costs.  And including

4       in that is the audit review that the internal, that the

5       company does through its audit process.

6       BY MR. REHWINKEL:

7            Q.   Okay.  Thank you.  That's, that's helpful to

8       me.  Thank you.

9                 With respect to the issue regarding the AREVA

10       rewrite, did you ask the company to provide

11       documentation that showed that the, they had planned to

12       have the expert panel participate in the review of the

13       draft LAR?

14            A.   (By Mr. Coston) We did talk through that with

15       the company.

16            Q.   Did they show you any documents before the

17       expert panel review that showed that the expert panel

18       was something that was always planned?

19            A.   (By Mr. Coston) We were not able to identify

20       that in our work papers, any of the work papers provided

21       by the company.

22            A.   (By Mr. Carpenter) I would add that the

23       presentation that was given to the Nuclear Regulatory

24       Commission on April 1st of 2009, I recall that it is,

25       that the expert panel was addressed in one of those

FLORIDA PUBLIC SERVICE COMMISSION

772

1       slides.  And I can get that in front of me, if you need

2       me to.

3            Q.   April 1, 2009?

4            A.   (By Mr. Carpenter) Yes.  The title of this

5       presentation was Crystal River Unit 3 Extended Power

6       Uprate, April 1st, 2009.  This was a presentation from

7       Progress Energy to the NRC, the Nuclear Regulatory

8       Commission.

9                 And the pages are not numbered, but the title

10       of this particular slide is EPU Submittal Approach.  At

11       the bottom of that is a sentence that states -- and I

12       don't believe any of this, since I got it off the

13       website, would be confidential.  But it states that,

14       "Establishing independent expert panel for supplemental

15       review."  That was the first notice that I saw in the

16       documentation that we looked at.

17            Q.   Okay.  So that says establishing as if it is

18       currently going on; correct?

19            A.   (By Mr. Carpenter) It's stating establishing

20       independent expert panel.  So at that point in time I

21       think they were starting to think about having the

22       expert panel review the LAR.  At least that's what I

23       would take from it.

24            Q.   Okay.  But there's no documentation that you

25       were provided that shows that this had always been

FLORIDA PUBLIC SERVICE COMMISSION

773

1       planned as part of the LAR preparation?

2            A.   (By Mr. Carpenter) It was stated to us

3       verbally, but nothing in documentation.

4            Q.   Okay.  What reliance did you place on the IPP

5       with respect to cost, to cost, effective cost control?

6            A.   (By Mr. Coston) IPP for both projects or a

7       particular project?

8            Q.   For the CR3.

9            A.   (By Mr. Coston) CR3.  The IPP, we used that as

10       the document that the company uses to receive approval

11       for the expenditures of the project, and in that

12       document we look at the risk and the feasibility aspects

13       they include in that and present to their senior

14       management for approval.

15            Q.   Did you consider the IPP to be a controlling

16       document with respect to their, the company's

17       performance against the budget with respect to the

18       execution of the project?

19            A.   (By Mr. Coston) Certainly the IPP is the

20       document, the request to the senior management for

21       funding, so the company does use that and the project

22       team uses that for the request for additional funding if

23       there is a budget variance.

24            Q.   Did you understand the IPP to be the official

25       budget for the project until changed by a subsequent

FLORIDA PUBLIC SERVICE COMMISSION

774

1       IPP?

2            A.   (By Mr. Coston) It is my understanding the IPP

3       is not necessarily a budget but an authorization, if you

4       will, of funding.

5                 MR. REHWINKEL:  Those are all the questions I

6       have.  Thank you.

7                 COMMISSIONER SKOP:  Thank you, Mr. Rehwinkel.

8                 Mr. Brew, any cross-examination?

9                 MR. BREW:  Thanks, Mr. Chairman.

10                          CROSS EXAMINATION

11       BY MR. BREW:

12            Q.   Good afternoon, gentlemen.  My name is James

13       Brew, representing PCS Phosphate.

14            A.   (By Mr. Carpenter) Good afternoon.

15            Q.   I'm a little confused about which one is

16       Coston and which one is Carpenter.

17            A.   (By Mr. Carpenter) Coston, Carpenter.

18            Q.   Thank you.

19                 Do you have before you the exhibits I gave you

20       earlier, which are marked for identification as Exhibits

21       210 and 211?

22            A.   (By Mr. Coston) Yes.

23            A.   (By Mr. Carpenter) Yes.

24            Q.   And do you recognize those documents as staff

25       responses to the discovery that PCS did of staff?

FLORIDA PUBLIC SERVICE COMMISSION

775

1            A.   (By Mr. Coston) Yes.

2            Q.   And were you responsible for or involved in

3       the preparation of those responses?

4            A.   (By Mr. Coston) Yes, I was.

5            A.   (By Mr. Carpenter) Yes.

6            Q.   And can you state whether or not those

7       responses are accurate?

8            A.   (By Mr. Coston) If you'll give me a moment, I

9       can.

10            Q.   Sure.

11            A.   (By Mr. Coston) Yes.

12            Q.   Yes?  Thank you.

13                 I'm going to refer you back to the statement

14       you have on page 4 of your prefiled testimony that

15       Mr. Rehwinkel discussed with you regarding the question

16       and answer on the top of page 4 that says, "Please

17       summarize your conclusions regarding the Levy nuclear

18       plant project."  And the statement at line 6 and 7 that,

19       "given the uncertainties facing the company, keeping the

20       project progressing without further substantial

21       investment is a reasonable approach at this time," do

22       you see that?

23            A.   (By Mr. Coston) Yes.

24            Q.   And I've got to admit I was very perplexed by

25       this testimony, and I think we're going to be here for a

FLORIDA PUBLIC SERVICE COMMISSION

776

1       while, but I think I understood you to change your

2       testimony in your summary, and I want to make sure that

3       I understood it right.  I heard you to say that your

4       conclusion was that Progress's management controls for

5       making the Levy decision was reasonable.  Is that a fair

6       statement of your testimony?

7            A.   (By Mr. Coston) I have it in front of me.

8       Could I have you repeat?

9            Q.   What I heard you was that you said that you

10       concluded that Progress's management controls for the

11       Levy decision were reasonable.  Is that right?

12            A.   (By Mr. Coston) I can read back what I, what

13       I --

14            Q.   Please do.

15            A.   (By Mr. Coston) I said audit staff determined

16       that the management approach and internal controls used

17       to evaluate and select the final decision of the Levy

18       nuclear project were reasonable.

19            Q.   Okay.  But what your testimony says is that

20       you have concluded that the company's decision, given

21       the uncertainties that it faced, to progress without

22       further substantial investment is a reasonable approach

23       at this time.  So what I want to understand is, did you

24       reach an independent decision that Progress's decision

25       regarding the revised schedule and the go-slow approach

FLORIDA PUBLIC SERVICE COMMISSION

777

1       for Levy is reasonable?  Is that your opinion, or are

2       you saying that your review of the company's process,

3       their management controls is reasonable, because those

4       are two very different things?

5            A.   (By Mr. Coston) The scope of our audit review

6       was to examine the project management internal controls

7       of Progress Energy and its relationship in constructing

8       this plant, new plant, and that is what we did in our,

9       within our scope.  And that is what our statement here

10       reflects, in that within the scope of our review and the

11       scope that is included within our executive summary, the

12       approach that was taken by the company were within a

13       reasonable, with internal controls -- excuse me.  Let me

14       restate that.

15                 The approach taken by the company and the

16       controls that were in place to reach the decision and

17       the decision-making process were reasonable.  We're not

18       speaking on the decision itself.

19            Q.   Very good.  So to the extent that I asked you

20       questions about the three options that the company

21       considered --

22            A.   Uh-huh.

23            Q.   -- whether they were reasonable, you would say

24       you have no opinion about the decision regarding any of

25       those options, but that the process for the company to

FLORIDA PUBLIC SERVICE COMMISSION

778

1       consider them you thought was reasonable.

2            A.   (By Mr. Coston) Right.  That they were in the

3       totality of the decision-making process, yes.

4            A.   (By Mr. Carpenter) That is correct.

5            Q.   Okay.  And to the extent the company in its

6       rebuttal referred to this statement as a statement that

7       staff considered their actions to be reasonable, that

8       would not be an accurate statement of your actual

9       findings; is that right?

10            A.   (By Mr. Coston) Right.  We're speaking on

11       behalf of the decision-making process --

12            Q.   Process, not the decisions itself.

13                 So when I ask -- I'm sorry.

14                 THE COURT REPORTER:  You were talking over

15       each other.  Would you repeat your answer, please?

16                 THE WITNESS:  (By Mr. Coston) Yes.  We

17       reviewed in relationship to the decision-making process,

18       in relationship to the internal controls in place by the

19       company.

20       BY MR. BREW:

21            Q.   So if I were to ask you the questions of,

22       regarding what would be the appropriate criteria to

23       consider to make an informed decision on that, you again

24       would say that you don't have an opinion on that, again

25       only that the company's process for evaluating the

FLORIDA PUBLIC SERVICE COMMISSION

779

1       criteria it selected was reasonable.

2            A.   (By Mr. Coston) I would say we had a, we

3       looked at the process, and in relationship to that

4       process there are certain criteria that the company

5       looked at and assumptions they made.  And that, we

6       looked at those in the totality of the decision-making

7       process.

8            Q.   Good.  But to the extent I asked you did you

9       use any assumptions of your own or do any of your own

10       evaluation of the decision, the answer would be no,

11       that's not what we did?

12            A.   (By Mr. Coston) No.

13                 Excuse me.

14            Q.   Do you mean yes?

15            A.   (By Mr. Coston) Yes.

16            Q.   Okay.  And so, bottom line, the question of

17       prudence, was their decision reasonable, is not

18       something in your testimony?

19            A.   (By Mr. Coston) No.

20            Q.   Okay.  The same, the beginning of that

21       sentence, "Given the uncertainties facing the company,"

22       again, did you evaluate those uncertainties as to their

23       likely impact on the project, or was your review -- went

24       to -- did your review go to the company's process for

25       evaluating those uncertainties?

FLORIDA PUBLIC SERVICE COMMISSION

780

1            A.   (By Mr. Coston) Our review went to the process

2       for evaluating and identifying those uncertainties.

3            Q.   Okay.  But whether those uncertainties had

4       gotten bigger, smaller, changed was not an evaluation

5       that you performed.

6            A.   (By Mr. Coston) Correct.

7            Q.   Okay.  And, again, to the extent the company

8       made a decision that revised the costs and schedule for

9       the project, you did not evaluate the reasonableness of

10       the proposed cost and schedule; is that correct?

11            A.   (By Mr. Coston) Correct.  The decision process

12       to revise those costs.

13            Q.   Nor did you evaluate the likely ramifications

14       of that in terms of impacts on rates or customer

15       impacts; is that right?

16            A.   (By Mr. Coston) Correct.

17            Q.   Okay.  You're making progress.

18                 To the extent there were other ramifications

19       of the decision to slip the schedule by 60 months,

20       including its impact on potential joint ownership in the

21       project, answers would be the same, you did not evaluate

22       those likely ramifications or the reasonableness?  You

23       simply, again, looked at to the extent to which they

24       were part of the company's process for making its

25       decision; is that right?

FLORIDA PUBLIC SERVICE COMMISSION

781

1            A.   (By Mr. Coston) Correct.  We did look at joint

2       ownership and what the company is doing in that area,

3       but not, you know, in relationship to the decision.

4            Q.   You looked at it in relationship to its

5       process and controls or the reasonableness of its

6       actions?

7            A.   (By Mr. Coston) Process, the process and

8       controls and if it did impact a decision-making -- if it

9       was included in the decision-making process.

10            Q.   Got you.  Not whether they decided that

11       process reasonably.

12            A.   (By Mr. Coston) Correct.

13            Q.   Okay.  In the context of the options that the

14       company considered, in particular the potential for

15       project cancellation, again, my questions are going to

16       be the same.  Did you look at whether they, they

17       considered -- whether the decision not to cancel the

18       project was reasonable or whether or not their process

19       for evaluating that option was reasonable?

20            A.   (By Mr. Coston) The evaluation of the option.

21                 MR. BREW:  Okay.  Thank you.  That's all I

22       have.

23                 COMMISSIONER SKOP:  Thank you, Mr. Brew.

24                 Ms. Kaufman?

25                 MS. KAUFMAN:  Thank you, Mr. Chairman.

FLORIDA PUBLIC SERVICE COMMISSION

782

1                          CROSS EXAMINATION

2       BY MS. KAUFMAN:

3            Q.   Mr. Coston; right?

4            A.   (By Mr. Coston) Yes.

5            Q.   Okay.  Thank you very much for that

6       clarification with Mr. Brew.  That cut out a lot of my

7       questions.  And that statement caused some consternation

8       on this side of the table, so, so thank you for that.

9                 I wanted to have you turn to page 15 of the

10       audit report.  Let me know when you're there.

11            A.   (By Mr. Coston) Okay.  We're there.

12            Q.   Toward the middle of the page you talk about

13       the operational readiness organization.  Do you see

14       that?

15            A.   (By Mr. Coston) Yes.

16            Q.   And in the next paragraph you talk about the

17       importance of that readiness group.  But the very last

18       sentence in that paragraph says, "However, audit staff

19       has concerns about the timing and resources placed on

20       this group during 2009, given the schedule flux and the

21       company's consideration to cancel the project."

22                 Can you explain what concerns you had about

23       the timing and resources related to the operational

24       readiness group?

25            A.   (By Mr. Coston) Yes.  The concerns that are

FLORIDA PUBLIC SERVICE COMMISSION

783

1       referenced in that sentence would be the, again, the

2       timing of the implementation of the operational

3       readiness group within the organization for the Levy

4       project in relation to the evaluation of project

5       schedules that was being considered by the company.

6            Q.   Well, is it your view that dollars were

7       expended on that activity that were perhaps unnecessary

8       given the, how did you put it, the schedule flux?

9            A.   (By Mr. Coston) The company did expend

10       resources on that, within that group in the time frame.

11       The -- as we state in our report, there is value in that

12       organization.  We're not nuclear engineers to under --

13       or recognize the need for training in that, or the time

14       it takes to train for that position.  But given the

15       shift and, that the company was considering and those

16       resources and the implementation of that resources at a

17       senior management level provided some concern to us

18       during the review.

19            Q.   In the course of your work, did you, did you

20       quantify or calculate a dollar amount that was related

21       to the concerns that you referenced there?

22            A.   We did not, no.

23                 MS. KAUFMAN:  Thank you, Mr. Coston.  That's

24       all I have.  Coston.

25                 COMMISSIONER SKOP:  Mr. Jacobs.

FLORIDA PUBLIC SERVICE COMMISSION

784

1                 MR. JACOBS:  Thank you, Mr. Chairman.

2                          CROSS EXAMINATION

3       BY MR. JACOBS:

4            Q.   Good afternoon, gentlemen.

5            A.   (By Mr. Coston) Good afternoon.

6            A.   (By Mr. Carpenter) Good afternoon.

7            Q.   My name is Leon Jacobs.  I'm here representing

8       the Southern Alliance for Clean Energy.  I think my

9       questions can be rather brief as well.  You've answered

10       several of them already.

11                 First of all, let's step back for a moment.

12       You've described this, what we see as Exhibit 77, as a

13       management review; right?

14            A.   (By Mr. Coston) Correct.

15            Q.   Is there, is there a nuance or a technical

16       distinction between a management review and an audit?

17            A.   (By Mr. Coston) This review and the scope of

18       our review was done using the standards established by

19       the Institute for Internal Auditing, and I think it

20       would be comparable to, similar to a management review

21       or an internal audit type review.

22            Q.   Okay.  So you use the standards of an audit,

23       but you actually weren't in the context of traditional

24       Commission audits where you'd go in and perform an

25       official audit; this is not that.  Is that, is that a

FLORIDA PUBLIC SERVICE COMMISSION

785

1       correct statement?

2            A.   (By Mr. Coston) I would say that our audits

3       were not financial audits.

4            Q.   Okay.

5            A.   (By Mr. Coston) In that respect they're not

6       financial-based audits.  They're more internal audits,

7       style audits.

8            Q.   The, the, the text of your report in several

9       places presents statements that, that would make

10       conclusions about various issues that you had, you had

11       done a review of.  And let's go to page 15 since we're

12       there.

13            A.   (By Mr. Coston) Okay.

14            Q.   And we're at the top of the page.  The very

15       last sentence in that -- now I'd caution you there are

16       some, there is some confidential information here, but

17       I'm not, I'm not addressing that.  I'm looking

18       specifically at the very last sentence of the first

19       page.  I'm on the page, the first paragraph on page 15.

20                 That sentence reads, "If the company remains

21       committed to completing the project, the cost

22       differential is necessary."

23                 Could you walk me through what that statement

24       is, is, is meaning to communicate?

25            A.   (By Mr. Coston) Sure.  Just give me a moment

FLORIDA PUBLIC SERVICE COMMISSION

786

1       to refresh with respect to it.

2            Q.   Sure.  Sure.

3            A.   (By Mr. Coston) There are, excuse me, there

4       are two numbers, confidential numbers in that paragraph.

5       The statement, the last sentence that you just read

6       reflects those numbers represent moving forward or

7       canceling the project.  Just simply stating that,

8       because of the differential in those numbers, if the

9       company is choosing to move the project forward on an

10       ongoing basis, then the differential between those two

11       numbers would be necessary because the project is

12       continuing.

13            Q.   Consistent with your prior testimony and line

14       of questioning from Mr. Rehwinkel and from Mr. Brew,

15       you're basically accepting the analysis done by the

16       company and you're looking at the process --

17            A.   (By Mr. Coston) Correct.

18            Q.   -- more so than looking at a qualitative

19       evaluation.

20            A.   (By Mr. Coston) Correct.  We did not analyze

21       the specifics of those two numbers.

22            Q.   Okay.  And if, if we go over to page 58,

23       again, at the top of the page, and again the very last

24       sentence in the first paragraph.  And that sentence

25       reads, "Given the uncertainties facing the company,

FLORIDA PUBLIC SERVICE COMMISSION

787

1       audit staff recognizes that keeping the project

2       progressing without further substantial investment of

3       cost is a reasonable approach by PEF at this point in

4       time."

5                 Your assessment of reasonableness, is that

6       consistent with our prior discussion that you've had

7       along the lines that it's pretty much based on a review

8       of your decision-making process?

9            A.   (By Mr. Coston) Yes.  Our definition of

10       reasonableness in this situation was looking at the

11       approach taken by the company as it relates to the

12       standards established with the Institute of Internal

13       Auditors and summarized in our executive summary on page

14       2 of our report where we talk about the control

15       environment, and that's where we assess the

16       reasonableness, the appropriateness in relation to those

17       controls on a project management internal controls area.

18            Q.   Okay.  As -- you undertook this exercise as

19       employees of the Commission; is that correct?

20            A.   (By Mr. Coston) Correct.

21            Q.   And you're aware that as, as the witnesses

22       testifying here, that basically your role is pretty much

23       as a, as a technical expert and putting evidence into

24       the record, contrasted with technical staff that would

25       in fact advise the Commission during the deliberative

FLORIDA PUBLIC SERVICE COMMISSION

788

1       process; you understand that distinction?

2            A.   (By Mr. Coston) Certainly.  Yes.

3            Q.   Okay.  So that same distinction would go to

4       any statements that are in your conclusions here, would

5       that not?  In other words, if you can't go into the

6       deliberative process and elucidate or expand on these

7       statements for purposes of advising for a final

8       decision, then those statements that you make here you

9       would think have that same limitation, wouldn't they?

10            A.   (By Mr. Coston) I'm sorry.  I --

11                 MR. YOUNG:  Objection.  I'm a little confused

12       as to what Mr. Jacobs is asking.  I think if he is on

13       the lines of the statement, the witnesses' statements

14       being as a regular, as any other ordinary witness in the

15       Commission giving statements of the witnesses the weight

16       it's due, I'm fine with that.  If he's on something

17       other than that, then I'd like some clarification on

18       what he's asking the witnesses.

19                 COMMISSIONER SKOP:  Okay.  Mr. Jacobs, I think

20       to facilitate the objection, and hopefully we can avoid

21       the objection, if you could please restate your question

22       or try and address the concerns, and then I'll leave it

23       free to staff to either take up the objection or allow

24       the question.

25                 MR. JACOBS:  Absolutely.  I think it might be

FLORIDA PUBLIC SERVICE COMMISSION

789

1       helpful, and I'm sorry, I don't have copies, but --

2                 COMMISSIONER SKOP:  Or if you could just

3       restate the question maybe a little bit with a little

4       bit more specificity to --

5                 MR. JACOBS:  By all means.

6       BY MR. JACOBS:

7            Q.   In fact, let me read from, from one of the

8       Commission's guiding rules, and exactly it's where I'm

9       going.  In Rule 25-22.033(5), the very last sentence of

10       that rule reads, "However, a staff member who testifies

11       in a case shall not discuss the merits of that case with

12       any Commissioner during the pendency of that case."

13            A.   (By Mr. Coston) Correct.

14            Q.   Okay.  And my question simply is that these

15       statements here carry that same limitation, wouldn't

16       they not?

17            A.   (By Mr. Coston) Yes.

18            Q.   Okay.  And so they, just as your counsel just

19       stated, I would agree with that, that they sit in the

20       record simply for the weight of evidence in contrast

21       with all the other evidence in the record; correct?

22            A.   (By Mr. Coston) Correct.

23                 MR. JACOBS:  Okay.  Thank you.  No further

24       questions.

25                 COMMISSIONER SKOP:  Thank you, Mr. Jacobs.

FLORIDA PUBLIC SERVICE COMMISSION

790

1                 Any questions from the bench?

2                 I do have one to the witness.  You were asked

3       previously -- and feel free, either one, to answer,

4       Mr. Coston or Mr. Carpenter.  You were asked previously

5       about the staff audit report in relation to the prudency

6       of Progress's management actions and related to the, if

7       my memory serves me correctly, low pressure turbine.  Is

8       there anything that members of internal audit staff in

9       preparing that report, given the confidential

10       information that has been redacted, is there anything

11       that would lead internal audit staff to conclude that

12       Progress was anything but imprudent with respect to the

13       action taken and the business acumen applied in

14       resolving that issue?

15                 THE WITNESS:  (By Mr. Coston) Just for

16       clarity, which, excuse me, which audit report?

17                 COMMISSIONER SKOP:  The -- hold on real quick.

18       It's the confidential exhibit that's been passed out.

19                 THE WITNESS:  (By Mr. Coston) Okay.

20                 COMMISSIONER SKOP:  And let me, let me get to

21       the page.  And to be helpful, what I was talking about,

22       and I probably should have gotten the document out to

23       begin with because there's the Levy 1 and 2 and the EPU,

24       and my question relates to the EPU on page 41,

25       continuing on to page 42 and then page 43.

FLORIDA PUBLIC SERVICE COMMISSION

791

1                 But is there anything -- again, that issue

2       came up in a cross-examination question.  And the

3       question, as I remember it, and, again, that was some

4       questions ago, dealt with the prudency of Progress's

5       action and staff's recommendation related to that

6       specific issue.  And was there anything in the staff

7       audit report, again, noting that some of the information

8       is redacted, to show that Progress was anything less

9       than prudent on addressing that issue, not only to

10       preserve the uprate potential but also to protect the

11       interests of their customers?

12                 THE WITNESS:  (By Mr. Coston) Yes.  We did

13       point out a few unresolved issues at that time, at the

14       time of our audit report, which was in the spring to

15       early summer, in relationship to the low pressure

16       turbine and the negotiations that the company had

17       ongoing at that time to resolve some of the vendor

18       issues that had arisen.

19                 One -- on page 43 specifically, the -- there's

20       a number in paragraph, in the fifth paragraph, the

21       last --

22                 COMMISSIONER SKOP:  I understand.  And I'm not

23       concerned, I'm not concerned with that number because,

24       again, that number seems to be outside the scope of the

25       business acumen involved in addressing the issue with

FLORIDA PUBLIC SERVICE COMMISSION

792

1       the turbine manufacturer.

2                 So, again, in terms of preserving its option,

3       and the issue presented starting on page 41 and, you

4       know, continuing on to page 43, was there anything that

5       internal audit staff found to indicate that Progress was

6       not prudent in taking the actions it took?

7                 THE WITNESS:  (By Mr. Coston) No.  Our review

8       showed that the company up to that point had done -- had

9       proper internal controls in place to monitor that.

10                 COMMISSIONER SKOP:  All right.  So their

11       actions were prudent in relation to addressing that

12       issue?

13                 THE WITNESS:  (By Mr. Coston) (Nods head.)

14                 COMMISSIONER SKOP:  All right.  Thank you.

15                 THE WITNESS:  (By Mr. Carpenter) I would

16       add that --

17                 COMMISSIONER SKOP:  Wait.  I didn't get a yes

18       or no.  I got a head nod.

19                 THE WITNESS:  (By Mr. Coston) Oh, sorry.

20       Excuse me.  Yes.

21                 COMMISSIONER SKOP:  All right.  Thank you.

22                 THE WITNESS:  (By Mr. Carpenter) I would add

23       that the quality assurance that was in place with

24       Progress Energy prevented them from taking acceptance of

25       a defective component.

FLORIDA PUBLIC SERVICE COMMISSION

793

1                 COMMISSIONER SKOP:  I understand.  I don't

2       want to get too far into contractual issues.  But,

3       again, there was a situation that developed, management

4       action, and the question that came up was questioning

5       the prudency of the management action in relation to

6       resolving that issue.  And I think that I just wanted to

7       clarify staff's position in relation to that.  Thank

8       you.

9                 All right.  Any additional questions from the

10       bench?

11                 All right.  Staff for redirect.

12                 MR. YOUNG:  No redirect.  And we move Exhibit

13       Number 77.

14                 COMMISSIONER SKOP:  Very well.  Any objections

15       to entering Exhibit 77 into the record?  All right.

16       Hearing none, show Exhibit 77 --

17                 MR. YOUNG:  And --

18                 COMMISSIONER SKOP:  Hold on.  Let me, let me

19       say what I need to say and then we'll move along.

20       Exhibit 77 will be entered into the record.

21                 And, Mr. Young, you're recognized.

22                 (Exhibit 77 admitted into the record.)

23                 MR. YOUNG:  Mr. Chairman, I just want to point

24       out, to ensure that there were no objections, it was the

25       revised Exhibit Number 77 that, that we passed out.

FLORIDA PUBLIC SERVICE COMMISSION

794

1                 COMMISSIONER SKOP:  I understand.  Right.  And

2       I believe that at the time you mentioned that in that

3       clarification, so that's just to cross the Is and dot

4       the Ts.  Are there any objections to entering the

5       revised Exhibit 77 into the record?

6                 MR. WALLS:  No.

7                 COMMISSIONER SKOP:  Okay.  Very well.  Show it

8       done.

9                 And then I believe, Mr. Brew, you have Exhibit

10       210 and 211?

11                 MR. BREW:  Yes.  Yes, Mr. Chairman.  PCS would

12       move both of those into evidence.

13                 COMMISSIONER SKOP:  Okay.  Any objection to

14       entering what's been marked for identification as

15       Exhibit 210 and 211 into the record at this time?

16                 MR. WALLS:  No objection.

17                 COMMISSIONER SKOP:  All right.  Since there's

18       no objection, show it done.

19                 (Exhibits 210 and 211 admitted into the

20       record.)

21                 And I believe, Mr. Coston and Carpenter, you

22       may step down.

23                 MR. YOUNG:  At this time, Mr. Chairman, can

24       they be excused?

25                 COMMISSIONER SKOP:  Do they need to reappear

FLORIDA PUBLIC SERVICE COMMISSION

795

1       in the FPL portion of the docket?

2                 MR. YOUNG:  No, sir.  It's another set of

3       witnesses.

4                 COMMISSIONER SKOP:  All right.  Very well.

5                 You may be excused.  Thank you.

6                 All right.  I think that takes us now to PF,

7       excuse me, Progress Energy rebuttal.  And the first

8       witness is I believe Mr. Franke again.  So, Mr. Walls,

9       you're free to call your witness.

10                 MR. WALLS:  We'd call Jon Franke to the stand,

11       and he has already been sworn.

12                 COMMISSIONER SKOP:  All right.  Thank you.

13                 At this transition period, I think this is a

14       good time for a break to allow our court reporters to

15       switch out.  And what we'll do is we'll take a brief

16       ten-minute break I believe should be sufficient and

17       allow the parties an opportunity to stretch and get

18       prepared for the next witness.  So we're on recess until

19       five after the hour.  Thank you.

20                 (Recess taken.)

21                 (Transcript continues in sequence in Volume

22       4.)

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION