1490

1                             BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

3                                          DOCKET NO. 100009-EI

4       In the Matter of:

5       NUCLEAR COST RECOVERY CLAUSE.

______________________________/

6

7                               VOLUME 7

8                       Pages 1490 through 1617

9              ELECTRONIC VERSIONS OF THIS TRANSCRIPT ARE

A CONVENIENCE COPY ONLY AND ARE NOT

10               THE OFFICIAL TRANSCRIPT OF THE HEARING,

THE .PDF VERSION INCLUDES PREFILED TESTIMONY.

11

12       PROCEEDINGS:        HEARING

13       COMMISSIONERS

PARTICIPATING:      CHAIRMAN NANCY ARGENZIANO

14                           COMMISSIONER LISA POLAK EDGAR

COMMISSIONER NATHAN A. SKOP

15                           COMMISSIONER ART GRAHAM

COMMISSIONER RONALD A. BRISÉ

16

DATE:               Friday, August 27, 2010

17

TIME:               Commenced at 9:57 a.m.

18

PLACE:              Betty Easley Conference Center

19                           Room 148

4075 Esplanade Way

20                           Tallahassee, Florida

21       REPORTED BY:        LINDA BOLES, RPR, CRR

Official FPSC Reporter

22                           (850) 413-6734

23       APPEARANCES:        (As heretofore noted.)

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1491

1                              I N D E X

2                              WITNESSES

3       NAME:                                        PAGE NO.

4       JOHN J. REED

5       Direct Examination by Mr. Ross                 1506

Cross Examination by Mr. Young                 1509

6       Cross Examination by Mr. McGlothlin            1541

Cross Examination by Mr. Moyle                 1548

7       Cross Examination by Mr. Davis                 1573

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1492

1                              EXHIBITS

2       NUMBER:                                 ID.    ADMTD.

3       243  Redacted Concentric Report        1510

4       244  Transcript of Hearing, Volume 2,  1523

Docket 090009-EI

5

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1493

1                         P R O C E E D I N G S

2                 (Transcript follows in sequence from

3       Volume 6.)

4                 CHAIRMAN ARGENZIANO:  Good morning.  We'll

5       call the meeting to order.  Excuse me.

6                 And, Commissioner Skop, you wanted to be

7       recognized.

8                 COMMISSIONER SKOP:  Thank you, Madam Chair.

9       Just two preliminary matters this morning.  First, I'd

10       like to briefly discuss an aspect related to the

11       proposed stipulation, and ask Mr. Rehwinkel, not, excuse

12       me, I'm sorry, Mr. McGlothlin a follow-up question.

13                 With respect to the proposed stipulation, the

14       stipulations provide for cost recovery and litigate the

15       issue or issues next year.  And what I would note in

16       that regard, in all prior NCRC hearings, the Commission

17       has always required a determination of reasonableness of

18       all costs prior to cost recovery, consistent with the

19       Commission's rule.

20                 Under their proposed stipulation and per Issue

21       23 in the Prehearing Order, this Commission will be

22       allowing FPL to charge its customers a total of

23       $81,317,333 in 2011 for the projected 2011 EPU costs to

24       the capacity cost recovery clause.

25                 Per the proposed stipulation, we're deferring

FLORIDA PUBLIC SERVICE COMMISSION

1494

1       consideration of the reasonableness of this amount, yet

2       cost recovery is allowed.  And that's listed on page 4

3       of the stipulation that was filed with this Commission

4       on August 17th, 2010.  Therefore, this cost recovery

5       goes forward, notwithstanding the company's issues

6       associated with the EPU costs, plans to submit the LAR,

7       and some of the disclosure issues that have been brought

8       to light within the past few weeks.

9                 Rule 25-6.0423(5)(c)(2) states that the

10       Commission shall, prior to October 1st of each year,

11       conduct a hearing and determine the reasonableness of

12       the projected preconstruction expenditures and projected

13       construction expenditures.  The Commission has not

14       conducted a hearing and has not determined the

15       reasonableness of expenditures.  In fact, under their

16       proposed stipulation, we will only be able to consider

17       the reasonableness after the fact, which is counter to

18       the rule's clear intent.

19                 In my view, it may be inappropriate to allow

20       such cost recovery for the projected EPU costs from FPL

21       customers, and at the appropriate time when we get to

22       the motion, I do, you know, have some concerns about

23       that.  But, you know, what it boils down to is without a

24       determination of the reasonableness of any costs

25       proposed for recovery by FPL in this proceeding,

FLORIDA PUBLIC SERVICE COMMISSION

1495

1       particularly in relation to the EPU, none of the costs

2       could be recovered under the NCRC rule.  That's

3       inconsistent because the rule requires a determination

4       of reasonableness.

5                 Now bringing up the point that Mr. Anderson

6       raised trying to, you know, present to the Commission

7       that this is done in the past, clearly we need to shed

8       some light on what the truth really is regarding that

9       representation.

10                 In the 2008 NCRC hearing, by Order

11       PSC-08-0749-FOF-EI, the PSC approved a stipulation among

12       some other parties to defer a prudence review of new

13       power plant costs incurred in 2007, yet allow cost

14       recovery in 2009 capacity cost recovery clause rates.

15       This was done because of the lateness of the Turkey

16       Point 6 and 7 and the St. Lucie need determinations or

17       nuclear, or some other need determinations in which

18       approval was granted after the NCRC filing dates for the

19       final true-ups in March 1, 2008.

20                 But most importantly, staff conducted a review

21       of those costs and made a recommendation on the

22       reasonableness of the costs in full compliance with

23       Rule 25-6.0423(5)(c)(2).  Specifically in that order, on

24       page 3 of the order, it found that the costs were

25       reasonable.

FLORIDA PUBLIC SERVICE COMMISSION

1496

1                 So I guess the question I have to

2       Mr. McGlothlin, or perhaps you might want to confer

3       amongst the parties as we move forward in this

4       proceeding, because I don't want to hold up Mr. Reed's

5       testimony, but the proposed stipulation seems to ignore

6       the reasonableness, the finding of reasonableness

7       requirement that the Commission has pursuant to its own

8       rule.

9                 So I think the question I have is if we're

10       going to defer or if the intent of the proposed

11       stipulation is to defer the entire, or a blanket

12       deferral of the entire FPL case until next year, then

13       perhaps the proposed costs related to the EPU should

14       equally be deferred, because I don't see how we're going

15       to get to a determination of reasonableness.

16                 So, Mr. McGlothlin, if you'd like to briefly

17       respond.  If not, I'll let you ponder that and move on

18       to my next point.

19                 MR. McGLOTHLIN:  Well, you've referred to some

20       orders and other things that I don't have with me, so

21       I'd like a chance to review that before I respond.

22                 COMMISSIONER SKOP:  All right.  Very well.

23       And I'll do that.

24                 Madam Chairman, my second issue that I'd like

25       to address this morning deals with my request to have

FLORIDA PUBLIC SERVICE COMMISSION

1497

1       Mr. Olivera appear before the Commission.  Now I've

2       asked Mr. Anderson at least twice on the record and I am

3       reiterating that request now.  Now it's a reasonable

4       request.  The company could comply.  The company has

5       raised a host of concerns, due process -- you know, we

6       can end all that.

7                 But the bottom line is I have questions

8       related, amongst other things, to the accuracy and

9       timeliness of information that was provided to the

10       Florida Public Service Commission.

11                 Now let's talk about due process in course.

12       The Concentric report, which Mr. Anderson alleged that

13       is the sole basis of my concern, it's not.  There are

14       other issues.  But with respect to the accuracy of

15       information provided to the Florida Public Service

16       Commission, Mr. Jones yesterday testified that

17       Mr. Olivera was in fact in attendance at the July 25th,

18       2009, Executive Steering Committee.  So Mr. Olivera,

19       therefore, has personal knowledge, which I feel is an

20       appropriate line of questioning.

21                 Moreover, as to the timeliness of information

22       provided to this Commission, the fact that FPL did not

23       provide the Florida Public Service Commission with its

24       notice to withdraw its LAR for St. Lucie 1 until ten

25       days after that was filed and hours before the start of

FLORIDA PUBLIC SERVICE COMMISSION

1498

1       this current year's NCRC proceeding in my view

2       constitutes failure to disclose material information.

3       At the very least it's a due process, denial of due

4       process to the Commission and Commission staff.  Okay?

5                 And that seems to be a consistent trend, to

6       disclose at the last minute, to keep staff at bay, to

7       keep Commissioners at bay.  So, again, there is a due

8       process interest there and that has not been

9       controverted.  It's actually been shown the facts are

10       what they are.  FPL knew on or before August 13th that

11       it would be pulling its LAR.  It did so on the 13th.

12       The NCRC, I mean, the NRC, Nuclear Regulatory

13       Commission, responded on the 13th, and we got a

14       one-page, a one-paragraph letter ten days later, only

15       after Commission staff had placed the information in the

16       docket, and it has a serious question whether all the

17       intervening parties were provided due process of that

18       letter also.

19                 So, again, I think that my request is

20       reasonable.  I would ask that the company comply.  You

21       know, certainly I have some relevant lines of questions.

22       In the absence of not complying, I will request my

23       colleagues to honor my request to have Mr. Olivera

24       appear before this Commission so I can ask him some

25       constructive questions in relation to things that are

FLORIDA PUBLIC SERVICE COMMISSION

1499

1       specifically related to documents contained in this

2       record and personal information he may have in that

3       regard.

4                 So, Mr. Anderson, I'm going to ask one final

5       time, does your company plan to make Mr. Olivera

6       available pursuant to my request?  I am not negotiating.

7       It doesn't require a full Commission vote because the

8       Chairman has subpoena power, but I will take it to a

9       vote.  But I'm asking nicely, on behalf of your company

10       in good faith, that Mr. Olivera appear.

11                 COMMISSIONER GRAHAM:  Madam Chair, I've got a

12       point of order.  We had this conversation yesterday, and

13       I believe the motion that we're on, we're supposed to

14       interview both Mr. Reed and Mr. Jones, and then we're

15       supposed to go back and address this issue.

16                 So I guess my question would be, should we

17       even be having this conversation now?  Should we go

18       ahead and continue with these two witnesses and then go

19       back and have this conversation?

20                 COMMISSIONER SKOP:  Madam Chair, to the point

21       of order.

22                 CHAIRMAN ARGENZIANO:  To the point.

23                 COMMISSIONER SKOP:  Commissioner Graham, to

24       your point of order.  A motion was made.  We are hearing

25       from two witnesses.  Staff is asking questions of those

FLORIDA PUBLIC SERVICE COMMISSION

1500

1       witnesses.  I have additional questions, which I've

2       reiterated in my request three times before this

3       Commission.  The situation I see us in and the reason

4       why my request is not out of order, upon the conclusion

5       of Mr. Reed's testimony, I will still have those

6       questions.  And to provide due process and adequate

7       notice, it's important that Mr. Olivera be provided

8       adequate time so he can appear before the Commission.

9       So there is detriment to waiting and that's why I've

10       brought forth my request.

11                 CHAIRMAN ARGENZIANO:  Well, we're in a logjam

12       again, because Commissioner Skop has asked the question

13       before and we have not answered -- well, I think the

14       company did answer his question.  Let me take a

15       five-minute recess and give it some thought.

16                 COMMISSIONER SKOP:  Thank you.

17                 (Recess taken.)

18                 CHAIRMAN ARGENZIANO:  We're back.

19                 COMMISSIONER SKOP:  Thank you, Madam Chair.

20       And, you know, to provide convenience to Mr. Olivera, if

21       there is a way that he could appear telephonically, that

22       would equally be acceptable to me, as long as it would

23       be under oath.

24                 CHAIRMAN ARGENZIANO:  Okay.  We have a point

25       that I have to address.  And the point is well taken

FLORIDA PUBLIC SERVICE COMMISSION

1501

1       since the motion was that we would see, go through the

2       two witnesses, but it is my desire then immediately upon

3       Mr. Reed's questions and answers and immediately upon

4       his release, his freedom from questioning, we will go,

5       revert back to Commissioner Skop's request.

6                 COMMISSIONER SKOP:  Madam Chair.

7                 CHAIRMAN ARGENZIANO:  Commissioner Skop.

8                 COMMISSIONER SKOP:  Thank you.  And thank you,

9       Madam Chair.  I appreciate that.  And, you know, I

10       respect the ruling.  For the record, I'd also like to

11       state that I first stated my request prior to the

12       motion, current motion being adopted, so I do think that

13       I have preserved that.  And I thank the Chair for trying

14       to find a way to harmonize obtaining a result that

15       balances the interests of Commissioner Graham with the

16       interest that I have.  Thank you.

17                 CHAIRMAN ARGENZIANO:  Thank you.  And before

18       we get started, I have a concern that I want to raise,

19       because I don't understand something that's kind of

20       befuddling.

21                 We have in the -- I guess the Prehearing

22       Officer, Commissioner Skop, the Concentric, the staff's

23       audit of the Concentric report to FPL is not

24       confidential except for one individual's name; correct?

25       Wait a minute.  I'm not finished.

FLORIDA PUBLIC SERVICE COMMISSION

1502

1                 COMMISSIONER SKOP:  Okay.

2                 CHAIRMAN ARGENZIANO:  But yet what's not

3       confidential in here leads you to a date and a time of a

4       particular public record where the name of that person

5       is not confidential.  Why is this person's name

6       confidential?

7                 COMMISSIONER SKOP:  Can I explain?

8                 CHAIRMAN ARGENZIANO:  Yes, please.

9                 COMMISSIONER SKOP:  All right.  Madam Chair,

10       in my ruling on the issue, FPL, we had to have an

11       evidentiary hearing.  Unlike Progress, FPL, again,

12       pursuant to OPC's representations, had a very broad, if

13       not overreaching, request for confidentiality.  So we

14       had to go through the evidentiary hearing process.

15                 At hearing we discussed the Concentric report.

16       There were two issues that we took specific testimony

17       on.  One was a third-party audit that was conducted at

18       the direction of internal audit staff that remained

19       confidential.  The second, I believe, was the name of

20       the person who provided live testimony before the

21       Commission.  FPL had agreed to provide or to redact the

22       majority of the information after a long, lengthy

23       discussion during the evidentiary hearing.

24                 However, on that issue, they put forth witness

25       testimony that asserted there would be some sort of

FLORIDA PUBLIC SERVICE COMMISSION

1503

1       competitive harm in relation to disclosing the staff

2       audit report.  Okay?  So the issue became do you hold up

3       disclosure of the document at that point over denying

4       the request for confidentiality over a single name, or

5       do you allow that docket to be properly disclosed so we

6       can have an open discussion?

7                 Please let me finish.  I'm going to get to my

8       point.

9                 Or do you allow that name to remain

10       confidential in that specific document because of the

11       testimony they provided that would have probably been

12       uncontroverted by staff, but staff withdrew its request.

13       So the decision was made on behalf of the Prehearing

14       Officer not to pursue fighting that or ruling against

15       it, because otherwise the entire document would have

16       been cloaked in a cloud of confidentiality pending

17       appeal.

18                 But, Madam Chair, to your point, there is a

19       transcript.  Transcript is a public record and questions

20       can be asked regarding that transcript.

21                 CHAIRMAN ARGENZIANO:  I understand that,

22       Commissioner Skop.  That was my point.

23                 COMMISSIONER SKOP:  Okay.

24                 CHAIRMAN ARGENZIANO:  My point is that it's

25       somewhat ridiculous, to be honest with you, that if you

FLORIDA PUBLIC SERVICE COMMISSION

1504

1       can sit here and everything that's not confidential --

2       I'm not saying your decision was ridiculous, because I

3       understand the need to have the document --

4                 COMMISSIONER SKOP:  I understand.  But --

5                 CHAIRMAN ARGENZIANO:  Excuse me.

6                 COMMISSIONER SKOP:  Okay.

7                 CHAIRMAN ARGENZIANO:  To have the document

8       held not confidential.  I understand the dilemma.

9                 But when one looks at it and can easily say,

10       well, let me go back to such and such a date and you

11       pull up the transcript and here it is.  Now my question

12       to legal staff is if I am referring to the public

13       document, is the name confidential or not?

14                 MR. KISER:  I don't think so.

15                 COMMISSIONER SKOP:  No, it's not.  Madam

16       Chair, may I --

17                 CHAIRMAN ARGENZIANO:  See how ridiculous that

18       is?

19                 COMMISSIONER SKOP:  Madam Chair.

20                 CHAIRMAN ARGENZIANO:  Yes, Commissioner Skop.

21                 COMMISSIONER SKOP:  Okay.  And, again, if you

22       would look at the footnote one in my order, which was --

23       I have to get the order number.  I alluded to that.

24       Footnote 1 said, "Notwithstanding the FPL testimony, in

25       my ruling to maintain confidentiality of FPL employee

FLORIDA PUBLIC SERVICE COMMISSION

1505

1       and former employee names, the Prehearing Officer

2       questions whether the confidentiality provisions were

3       intended to protect the identity of a witness when the

4       veracity of the witness's sworn testimony to the

5       Commission is called into question."

6                 So I did challenge that.  But to rule against

7       that based on the evidence I had before me would have

8       shielded, allowed FPL, and that would have, I'm sure,

9       been to their pleasure, to keep this entire document

10       under wraps and none of this open discussion could be

11       held.  And the workaround for that is that they claim

12       confidentiality specific to the staff audit report.  I

13       knew the transcript existed.

14                 CHAIRMAN ARGENZIANO:  Okay.

15                 COMMISSIONER SKOP:  We can take official

16       recognition of the transcript and read in whatever

17       questions need to be directed to the witness.  Thank

18       you.

19                 CHAIRMAN ARGENZIANO:  I understand.  I just

20       wanted to make sure that if I refer to this public

21       document in any way, that it is not confidential.

22                 COMMISSIONER SKOP:  Yeah.  Well, I think that

23       speaks to FPL's desire to shield much of its information

24       in the cloud of confidentiality, unlike Progress.  But,

25       again, we --

FLORIDA PUBLIC SERVICE COMMISSION

1506

1                 CHAIRMAN ARGENZIANO:  Okay.  Let's, let's move

2       on with our witness and start with Mr. Reed, please.

3                 MR. ROSS:  Madam Chairman, Mr. Reed is on the

4       stand.  He was sworn yesterday.  What I would propose is

5       a couple of questions to briefly introduce him.  He has

6       a brief summary that's prepared for the Commission, then

7       he'd be available for questions.

8                 CHAIRMAN ARGENZIANO:  Fine.  Let's move

9       forward.

10                             JOHN J. REED

11       was called as a witness on behalf of Florida Power &

12       Light Company and, having been duly sworn, testified as

13       follows:

14                          DIRECT EXAMINATION

15       BY MR. ROSS:

16            Q.   Good morning.  Would you please state your

17       name and business address.

18            A.   My name is John Reed.  My business address is

19       293 Boston Post Road, Marlborough, Massachusetts.

20            Q.   By whom are you employed and in what capacity?

21            A.   I am the Chairman and CEO of Concentric Energy

22       Advisors and CE Capital.

23            Q.   Have you prepared a brief summary of your

24       testimony in this proceeding for the Commission?

25            A.   Yes, I have.

FLORIDA PUBLIC SERVICE COMMISSION

1507

1            Q.   Would you please provide that summary to the

2       Commission now?

3            A.   Certainly.

4                 Good morning, Madam Chair and Commissioners.

5       Concentric Energy Advisors was retained by Florida Power

6       & Light in this proceeding for a review of project

7       controls and project management for the EPUs and Turkey

8       Point 6 and 7.  We provided the same services for the

9       last two nuclear cost recovery cases.  We also have been

10       asked to benchmark FPL's Turkey Point 6 and 7 cost

11       estimate and to review the economic feasibility analysis

12       it has presented regarding the EPU and Turkey Point 6

13       and 7.

14                 I have 125 pages of direct testimony on these

15       issues.  However, given the limited purpose for which

16       I'm appearing now, I don't propose to address those

17       issues in my summary.

18                 This year, Concentric was also asked to

19       conduct a separate investigation of a number of concerns

20       regarding the EPU projects raised in a letter sent by an

21       FPL nuclear manager to NextEra's CEO.  These findings

22       are detailed in our separate report on that matter.

23                 Our report has concluded that during the first

24       half of 2009, FPL did not satisfactorily comply with its

25       written procedures regarding cost estimation and changes

FLORIDA PUBLIC SERVICE COMMISSION

1508

1       in scope for the EPU projects.  In addition, we have

2       concluded that in September 2009 in the nuclear cost

3       recovery hearings, certain information was provided by

4       an FPL witness to the FPSC and that information was out

5       of date.

6                 Notwithstanding these findings, we have also

7       concluded that FPL's actions have not led to any

8       imprudently incurred costs or to any incorrect decisions

9       regarding moving forward with the EPU projects.

10                 I want to comment briefly on the process of

11       our investigation.  In launching our investigation in a

12       response to the employee letter, I think FPL did exactly

13       what it should have done.  In granting us the autonomy,

14       independence and access that it did that we requested,

15       again, I think FPL did exactly what it should have done.

16                 Last, but certainly not least, even though FPL

17       does not fully agree with our conclusions and

18       recommendations, it is currently implementing 13 out of

19       14 of our recommendations and further evaluating the one

20       remaining recommendation.  I commend them for that.

21                 I would like to conclude by saying that I have

22       worked with but actually more often across the table

23       from the FPL nuclear organization many times over the

24       past dozen years.  Our findings in our report are not

25       characteristic of the FPL nuclear organization that I

FLORIDA PUBLIC SERVICE COMMISSION

1509

1       have come to know and respect over that time.

2       Furthermore, FPL is a self-critical and learning

3       organization that is committed to continuous

4       improvement, and our report is offered in that vein.

5                 Finally, with regard to the EPU organization

6       which was the subject of our investigation, that

7       organization is focused on the right issues and has made

8       substantial progress to effectively deal with our

9       concerns.

10                 That concludes my summary.  Thank you.

11                 MR. ROSS:  Madam Chairman, Mr. Reed is now

12       available for questions.

13                 CHAIRMAN ARGENZIANO:  Thank you.

14                 Mr. Young.

15                 MR. YOUNG:  Thank you.  Thank you, Madam

16       Chairman.

17                          CROSS EXAMINATION

18       BY MR. YOUNG:

19            Q.   Good morning, Mr. Reed.

20            A.   Good morning, Mr. Young.

21            Q.   You've been sworn; correct?

22            A.   Yes, I have.

23            Q.   Do you have a copy of your Concentric report,

24       the revised copy, the unredacted and the redacted copy?

25            A.   You want me to have both versions in front of

FLORIDA PUBLIC SERVICE COMMISSION

1510

1       me?

2            Q.   Yes.

3                 MR. YOUNG:  And the unredacted copy was passed

4       out yesterday, Madam Chairman.  It was previously marked

5       as Exhibit 242.  It's included in that Exhibit 242 and I

6       think it's at the -- if you open your package and if

7       it's in the order like I thought it is, it's at the end

8       at the back of your package.

9                 MR. MOYLE:  Just a point of clarification, if

10       I could, Madam Chair.

11                 CHAIRMAN ARGENZIANO:  Mr. Moyle.

12                 MR. MOYLE:  242 is the confidential exhibit.

13                 MR. YOUNG:  The confidential exhibit.  242 is

14       a confidential exhibit.

15                 CHAIRMAN ARGENZIANO:  Okay.  Here it comes.

16       Okay.  Thank you.

17                 MR. YOUNG:  Also, Madam Chairman, we are

18       handing out, and we're going to ask that this be marked

19       for identification purposes, the revised, the redacted

20       copy of the Concentric report.  And that will be 243.

21                 (Exhibit 243 marked for identification.)

22                 CHAIRMAN ARGENZIANO:  Commissioner Skop.

23                 COMMISSIONER SKOP:  Thank you, Madam Chair.

24                 As a point of information, Mr. Young, I can

25       reserve this until I ask my question, but does staff

FLORIDA PUBLIC SERVICE COMMISSION

1511

1       intend to mark a copy of the transcript for

2       identification at any future point in time from the

3       September 8th, 2009?

4                 MR. YOUNG:  The, the -- if I could have one

5       second, Madam Chairman.

6                 CHAIRMAN ARGENZIANO:  Uh-huh.  Sure.

7                 (Pause.)

8                 MS. HELTON:  Madam Chairman, we may be able to

9       avoid having to do that if the company would be willing

10       to let us officially recognize the transcript from last

11       year.

12                 COMMISSIONER SKOP:  Madam Chair.

13                 CHAIRMAN ARGENZIANO:  Commissioner Skop.

14                 COMMISSIONER SKOP:  Madam Chair, the company

15       does not let, does not need to allow us to take official

16       recognition of our own document.  So what I would ask is

17       that we can certainly take official recognition of our

18       own document, which is a public record which I printed

19       off our docket file this morning, or we could mark it

20       for identification and enter it into the record subject

21       to objection.

22                 So that's my intent.  Mr. Young, just proceed,

23       and I'll deal with it at the appropriate time.  Thank

24       you.

25                 CHAIRMAN ARGENZIANO:  Mr. Young.

FLORIDA PUBLIC SERVICE COMMISSION

1512

1                 MR. YOUNG:  Thank you, Madam Chairman.

2       BY MR. YOUNG:

3            Q.   Mr. Reed, on March 10th, 2010, you were

4       contacted by FPL regarding an employment letter;

5       correct?

6            A.   Yes.  That's correct.

7            Q.   And you were -- and that contact was by FPL's

8       attorney Mitchell Ross; correct?

9            A.   That's correct.

10            Q.   And on March 11th, 2010, you were given,

11       quote, unquote, soft authorization; correct?

12            A.   Soft authorization to proceed with our work.

13       Yes.

14            Q.   What does soft authorization mean?  What does

15       that mean?

16            A.   Subject to working out the paperwork.

17            Q.   Okay.  And that, just to clarify, that was

18       based on the employee letter; correct?

19            A.   Yes.

20            Q.   And you were given points of contacts as

21       relates to this investigation; correct?

22            A.   Yes.

23            Q.   Who were your point of contacts?

24            A.   Our primary point of contact was Mr. Ross.  We

25       also had a day-to-day coordinator for data information

FLORIDA PUBLIC SERVICE COMMISSION

1513

1       and interview requests.

2            Q.   Okay.  Was there anybody else other than

3       Mr. Ross was your point of contact?

4            A.   Mr. Ross was the primary point of contact.  We

5       had interaction with numerous people, but Mr. Ross was

6       the person to whom we reported and had our primary

7       contact.

8            Q.   All right.  If you can reveal, if it's not

9       confidential, who did you have contact with as relates

10       to your investigation in this report?

11            A.   The FPL legal organization, Mr. Anderson,

12       Mr. Litchfield, the FPL EPU nuclear organization,

13       obviously Mr. Jones and a number of his direct reports.

14       We had access to everyone we asked to have access to.

15       Ms. Tiffany Cohen was our day-to-day data coordinator in

16       interaction.  The specific people that we interviewed,

17       that list is confidential still, so I don't propose to

18       go into that list.

19            Q.   All right.  Did you -- and I think -- were you

20       here yesterday when Mr. Jones was testifying?

21            A.   Yes, I was here.

22                 MR. YOUNG:  Madam Chairman, if I could get one

23       second to confirm something with the parties -- with

24       the, with the company.

25                 CHAIRMAN ARGENZIANO:  Certainly.

FLORIDA PUBLIC SERVICE COMMISSION

1514

1                 COMMISSIONER SKOP:  Madam Chair, may I?

2                 CHAIRMAN ARGENZIANO:  Commissioner Skop, go

3       ahead.

4                 COMMISSIONER SKOP:  Thank you, Madam Chair.

5       Getting to the matters which may be judicially noticed,

6       or in this case official recognition, under Florida

7       Statute 90.202, "The court may take judicial notice of

8       the following matters to the extent they're not embraced

9       within Section 90.201(6).  Records of any court of this

10       state or any court of record in the United States of any

11       state, territory or jurisdiction in the United States;

12       11, facts that are not subject to dispute because

13       they're generally known within the territorial

14       jurisdiction of the court; 12, facts that are not

15       subject to dispute because they're capable of accurate

16       and ready determination by resort to sources whose

17       accuracy cannot be questioned."

18                 This is official, this transcript is in our

19       official public record docket, so I would respectfully

20       disagree with the advice of counsel to the extent that I

21       do not need to ask FPL's permission to take official

22       recognition on behalf of this Commission.  Thank you.

23                 CHAIRMAN ARGENZIANO:  Ms. Helton.

24                 MS. HELTON:  Thank you, Madam Chairman.  I'm

25       in kind of an awkward position here.  I also think it's

FLORIDA PUBLIC SERVICE COMMISSION

1515

1       important that we're to remember that we're under

2       Chapter 120, the Administrative Procedures Act, as

3       adopted by the Legislature.  And in Chapter 120 in the

4       section governing evidentiary proceedings, which we are

5       now in, it states -- and if you'll hold on one minute.

6       These are awkward glasses for me to work with.

7                 CHAIRMAN ARGENZIANO:  Sure.  Go right ahead.

8                 MS. HELTON:  120.569(2)(i), "When official

9       recognition is requested, the parties shall be notified

10       and given an opportunity to examine and contest the

11       material."

12                 I can't remember whether in our, if it's in

13       our Order Establishing Procedure that we give a certain

14       time frame by when parties are expected to identify and

15       notify those participating in the proceeding that they

16       expect to take official recognition of certain

17       information.  I think that it is, and I need one of the

18       younger lawyers who can remember better than me to

19       confirm that.

20                 We as a regular course take official

21       recognition of our orders.  I don't think anyone in our

22       proceedings can dispute that.  However, in my mind, a

23       transcript is a little bit different than an order.  And

24       I believe that it's appropriate to learn whether Florida

25       Power & Light objects, and from there to make an

FLORIDA PUBLIC SERVICE COMMISSION

1516

1       appropriate ruling based on the request made and any

2       discussion that's had on the subject.

3                 CHAIRMAN ARGENZIANO:  Commissioner Skop.

4                 COMMISSIONER SKOP:  Madam Chair, in response,

5       and I've anticipated this, and, again, it's amazing what

6       roadblocks get put up before the Commission.

7                 So, again, in the alternative to avoid this

8       protracted discussion, I intend to mark the transcript

9       for identification purposes in a line of questioning and

10       we'll handle it that way.  Thank you.  Subject to

11       objection by the company at the appropriate time when

12       the exhibit would be entered.

13                 CHAIRMAN ARGENZIANO:  May I ask a question of

14       legal?  If someone off the street walked up to me and

15       handed me that transcript today and said this is the

16       case you're, I'm talking about a customer, says this is

17       the case, this is part of the case you're talking about

18       and how come this has to be confidential if it's there,

19       do I have to submit that to be entered into the record?

20                 MS. HELTON:  Ma'am, I'm not talking about --

21       obviously the transcript is what it is and it speaks for

22       itself.  My concern is notice.  My concern is notice to

23       all --

24                 CHAIRMAN ARGENZIANO:  The question I asked was

25       would I have to enter it into the record because someone

FLORIDA PUBLIC SERVICE COMMISSION

1517

1       approached me with it and said here it is, it's

2       pertaining to a case you're working on?  Would it have

3       to be entered into the record or should it be entered

4       into the record?

5                 MS. HELTON:  If it's something that you want

6       to rely on in making your decision and you want it to be

7       part of the competent, substantial evidence upon which

8       you base your decision, yes, it would need to be entered

9       into the record.

10                 CHAIRMAN ARGENZIANO:  Okay.  Commissioner

11       Skop.

12                 COMMISSIONER SKOP:  Thank you, Madam Chair.

13       And that was my intent on doing it the proper

14       evidentiary way.  Just mark it for identification and

15       I'll ask questions.  And then when we move to enter,

16       then it can be subject to objection.

17                 However, I would note that there is no due

18       process issue.  Excerpts of this transcript have already

19       been declassified with the exception of the witness name

20       in the Concentric report in the -- and it may even be in

21       the staff audit report.  There's been ample notice.  The

22       company was a party to the proceeding last year, the

23       party knows that this is at issue, or should have known

24       it's an issue.  And, you know, I respect advice of

25       counsel, but I disrespect what appear to be -- I'll just

FLORIDA PUBLIC SERVICE COMMISSION

1518

1       stop there.  It's just -- I'll get it in the record.

2       Thank you.

3                 CHAIRMAN ARGENZIANO:  Can I -- I just want to

4       say something, because it's very easy in times when

5       we're talking about very substantial issues for people

6       to get excited, to get emotional, or to have a real

7       strong point of view.  And some may not like it and some

8       may want to just move on for time's sake or whatever.

9       But it is really a very important issue to the

10       companies, to the parties involved and to the people of

11       the State of Florida.

12                 So let's take a breather and let's not get mad

13       if anybody asks questions or has a strong point of view,

14       because that's what we get paid for.  So let's take a

15       breather and let's not get angry.  If we have to stay

16       'til 8:00 tonight and we don't like it, that's too bad,

17       we all get paid a good amount of money, that's what

18       we'll do.

19                 So I'm going to say right now, I'm going to

20       take another five-minute break, and the reason to do

21       that is because I want things to cool off and I want

22       people to think about some things.  And then when --

23       we're going to take a five-minute break and then we'll

24       come back.

25                 (Recess taken.)

FLORIDA PUBLIC SERVICE COMMISSION

1519

1                 If everyone will return to their seats, we'll

2       get started.

3                 Mr. Young, whenever you're ready.

4                 MR. YOUNG:  Thank you, Madam Chairman.

5       BY MR. YOUNG:

6            Q.   Mr. Reed, where we left off, you were telling

7       me what soft authorization was.  Can you repeat that

8       answer, please?

9            A.   Yes.  It is authorization to proceed with our

10       scope of work subject to working out the paperwork.

11            Q.   And you were telling me your point of contacts

12       were, who you spoke with, and you didn't want to reveal

13       the confidential names; correct?

14            A.   I did not want to reveal the names of the

15       people we interviewed.

16            Q.   Okay.  However, one of those persons revealed

17       that you were, he, you -- excuse me.  One of those

18       persons revealed that you interviewed him for this

19       report; correct?

20            A.   Yes.  I believe yesterday Mr. Jones indicated

21       voluntarily that he was one of the interviewees.

22            Q.   Okay.  And Mr. Jones also said that he

23       reviewed copies of the draft reports; correct?

24            A.   Yes.

25            Q.   Did the other interviewees review copies of

FLORIDA PUBLIC SERVICE COMMISSION

1520

1       the draft reports?

2            A.   I don't know to whom the reports were

3       circulated within FPL on a draft basis.  But I can say

4       that in terms of people we received comments from, no

5       other interviewees were people that we received comments

6       from.

7            Q.   But you received comments from Mr. Jones;

8       correct?

9            A.   Orally, yes.

10            Q.   Yes.  Now is it customary for a person who is

11       interviewed for an investigation to give you comments in

12       terms of reviewing your final work product?

13            A.   Yeah.  It's not unusual at all, especially

14       where all of the data that we're counting on and using

15       in our analysis comes from the company.

16            Q.   All right.

17            A.   We want to always fact-check and verify the

18       information we received, so that's part of our fact

19       checking process.

20            Q.   All right.  Did, did he give any other

21       comments to you?  Did Mr. Jones provide any other

22       comments besides the factual basis of your report?

23            A.   He provided qualitative or subjective comments

24       as well, areas in which he disagreed with our

25       conclusions.

FLORIDA PUBLIC SERVICE COMMISSION

1521

1            Q.   Okay.  Now in your statement you made that, in

2       your summary you made a statement that you did not think

3       FPL was imprudent in their actions at all; correct?  Did

4       I summarize your statement correctly?

5            A.   What I said specifically was there are no

6       costs in this proceeding or in the prior proceedings

7       that relate (phonetic) to any imprudent decision.

8            Q.   All right.  Did you have Mr. Jones' letter

9       prior to issuing your report?

10            A.   Yes.  We saw a draft of Mr. Jones' management

11       response shortly before we issued the final report.

12            Q.   Okay.  Can you look at that draft, and it's

13       dated, it's for --

14                 MR. YOUNG:  Point of information, Madam

15       Chairman.  It's the purple cover sheet that was marked

16       as Exhibit Number 243 for identification purposes.  And

17       it is -- one, two -- the fourth to the last page, and

18       it's dated June 21st, 2010.

19                 THE WITNESS:  I have that document.

20       BY MR. YOUNG:

21            Q.   All right.  If you can look in the second full

22       paragraph that starts, "In summary."

23            A.   Yes.

24            Q.   And the last two sentences that starts, "While

25       there was acknowledgment," can you read that aloud,

FLORIDA PUBLIC SERVICE COMMISSION

1522

1       please?

2            A.   I'm sorry.  Where are you on that paragraph?

3            Q.   The last two sentences.  The sentence that

4       starts with, "While there was."  Do you see it?

5            A.   Yes.

6            Q.   Can you read that, can you read that sentence

7       aloud, please?

8            A.   "While there was acknowledgment that as

9       detailed engineering proceeded there would be additional

10       scope and therefore cost, there were also indications

11       that there were opportunities to eliminate scope and

12       reduce costs as well that simply were not being acted

13       upon.  The interactions between FPL and the major

14       vendors -- "

15            Q.   If I can have you stop there.

16            A.   Okay.

17            Q.   Now you just read that statement.  And the

18       last part of that statement, that simply was not acted

19       upon as relates to costs and missed opportunities.  Did

20       you investigate that in your, before you issued your

21       report?

22            A.   Yes.

23            Q.   So you believe that Mr. Jones' statement is

24       incorrect that there were missed opportunities that were

25       not acted upon that potentially could have reduced cost?

FLORIDA PUBLIC SERVICE COMMISSION

1523

1            A.   Let's put this in context.  No, I don't

2       believe his statement is wrong.

3            Q.   Okay.

4            A.   I agree with his statement that we're talking

5       about in mid 2009.

6            Q.   Yes.  Mid 2009.  Now moving forward --

7                 MR. YOUNG:  And, Madam Chairman, what I'd like

8       to do at this time is mark as a placeholder Exhibit 244,

9       and this is a, these are copy, this is a copy of the

10       direct testimony of Mr. Kundalkar, and I have 15 copies

11       that I'll be bringing down shortly.

12                 CHAIRMAN ARGENZIANO:  244?

13                 MR. YOUNG:  Yes.

14                 CHAIRMAN ARGENZIANO:  Okay.

15                 (Exhibit 244 marked for identification.)

16       BY MR. YOUNG:

17            Q.   Now, Mr. Jones, I mean, excuse me, Mr. Reed, I

18       want to ask you a question about Mr. Jones right now.

19       Again, you were in the room when Mr. Jones was giving

20       his testimony; correct?

21            A.   Yes.

22            Q.   And you were, you were here for the discussion

23       as it relates to performance, whether the EPU management

24       was removed because of performance; correct?

25            A.   Yes.

FLORIDA PUBLIC SERVICE COMMISSION

1524

1            Q.   Do you agree with his assessment that they

2       were not removed because of performance?

3            A.   I'm not sure that fully and correctly

4       characterizes his testimony.

5            Q.   Let me, let me stop you there.

6                 Did Mr. Jones, did Mr. Jones state that he

7       does not believe that the EPU, some of the EPU team was

8       removed for performance?

9            A.   I think that's correct.

10            Q.   In your findings did you not find that the

11       EPU, some of the members of the EPU team was removed

12       based on performance?

13            A.   What we found was that the change in

14       management was to enhance the performance of the

15       project.  So, yes, I would say in my mind that phrase

16       includes making the change due to performance.

17            Q.   So you would agree with me that they were

18       removed because of performance, partly because of

19       performance?

20            A.   Again, the management change, I don't think I

21       would characterize that as removal.  It was a

22       reorganization, it was a reassignment, and then other

23       people left voluntarily.  But the management change was

24       to enhance performance of the project.

25            Q.   Okay.

FLORIDA PUBLIC SERVICE COMMISSION

1525

1                 CHAIRMAN ARGENZIANO:  I have just a question,

2       if I can, to that point.  So does that mean in your

3       opinion that management felt that some members of the

4       team were not performing up to their expectations?

5                 THE WITNESS:  In general, yes.  I would say

6       that the senior management seems to have felt that the

7       project needs had changed and that a change was

8       warranted to reflect the change in needs and to align

9       performance with that change.

10                 CHAIRMAN ARGENZIANO:  Thank you.

11       BY MR. YOUNG:

12            Q.   Now, Mr. Jones [sic], let's focus back on the

13       draft of the Concentric report in terms of who edited

14       the report and what feedback they provided to you.

15                 Did you present -- did you meet with FPL to

16       discuss each draft of the Concentric report?

17            A.   No.

18            Q.   How many drafts of the Concentric report are

19       out there?

20            A.   Approximately 20.

21            Q.   Twenty drafts.  Do any of those drafts include

22       feedback from FPL employees?

23            A.   I'm not sure I would use the word include.

24       Some of the revisions reflect comments and feedback from

25       FPL employees.

FLORIDA PUBLIC SERVICE COMMISSION

1526

1            Q.   How often did you meet with FPL employees as

2       relates to receiving feedback as related, for the

3       Concentric report, in your finalization of the

4       Concentric report?

5            A.   If you can give me just a moment.  And just to

6       indicate what I'm looking at, this is a data request

7       response, EPU data request 10-7, which is confidential,

8       but it does list all the occasions in which we met with

9       the company to receive their comments.  And looking at

10       that --

11            Q.   While you're looking for that, let me ask you,

12       did you provide each draft to FPL, to Florida Power &

13       Light?

14            A.   No.  More than half of the drafts were just

15       internal drafts that we revised internally without

16       sending to FPL.  It appears that we had four sessions in

17       which we received comments from FPL.

18            Q.   If you can, I'd like to go through that draft.

19       And with the Commission's --

20                 CHAIRMAN ARGENZIANO:  One second, Mr. Young.

21                 Commissioner Skop.

22                 COMMISSIONER SKOP:  Yes, briefly, Madam Chair.

23                 Mr. Reed, in response to your last question,

24       you said the four sections that you received FPL input.

25       Can you identify what those sections are?

FLORIDA PUBLIC SERVICE COMMISSION

1527

1                 THE WITNESS:  Sessions, sessions of time.

2                 COMMISSIONER SKOP:  Sessions.  Okay.  All

3       right.  Sorry.  Thank you.

4                 CHAIRMAN ARGENZIANO:  Mr. Young, sorry.

5                 MR. YOUNG:  With the Commission's indulgence,

6       I'd like to go through the draft while we wait on

7       Ms. Bennett to come forward with the copies of the

8       testimony so we can move on that line of questioning.

9                 CHAIRMAN ARGENZIANO:  That's fine.

10       BY MR. YOUNG:

11            Q.   Mr. Reed, do you have what is marked as

12       Exhibit Number 243?

13            A.   That's the redacted report?

14            Q.   That's the redacted report.

15            A.   Yes.

16            Q.   242.  Excuse me.

17                 MR. YOUNG:  And, Madam Chairman, I know I'm

18       treading on some confidential information, so I'd like

19       the company to be totally alert and alert me and inform

20       me if I'm moving towards that confidential information

21       so I don't divulge that information.

22                 CHAIRMAN ARGENZIANO:  Mr. Young, did you say

23       243 or 242?

24                 MR. YOUNG:  242, Madam Chairman.

25                 CHAIRMAN ARGENZIANO:  Okay.

FLORIDA PUBLIC SERVICE COMMISSION

1528

1                 MR. MOYLE:  Do you have a Bates number that we

2       might --

3                 MR. YOUNG:  Pardon me?  It's the last draft in

4       the back of the packet.

5                 MR. ROSS:  Mr. Young, is this from the red

6       confidential folder that you passed out?

7                 MR. YOUNG:  Yes, sir.

8                 MR. ROSS:  Mr. Reed, do you have that in front

9       of you?

10                 THE WITNESS:  No.  If we're talking about a

11       draft report, I do not have those.

12                 MR. YOUNG:  Okay.

13                 MR. ROSS:  Can I request that Mr. Reed get a

14       copy of the folder?  Thanks.

15                 CHAIRMAN ARGENZIANO:  Is it marked as draft,

16       as a draft?

17                 MR. YOUNG:  Is it marked -- no, ma'am.  It's

18       marked as document, FPL's response to staff's fourth

19       POD.

20                 CHAIRMAN ARGENZIANO:  Could you give the

21       document number to make sure that I'm on the right one?

22       Is it -- what is the document number on the bottom of

23       the --

24                 MR. YOUNG:  Document Number 06790-10.

25                 CHAIRMAN ARGENZIANO:  Got it.  Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

1529

1       BY MR. YOUNG:

2            Q.   Now, Mr. Reed, before we get there, earlier I

3       asked you was the FPL employee removed because -- some

4       of the EPU management team was removed because of

5       performance; correct?

6            A.   Yes, you did.

7            Q.   Now in your interviews did several

8       interviewees express that they believed, if I'm going

9       confidential information, please alert me, that they

10       believed the EPU, some of the EPU management team was

11       removed because of performance?

12            A.   Yes, they did.

13            Q.   Okay.  And these would be people who were

14       close enough to the information to, to form an opinion

15       as it relates to the EPU management team being removed;

16       correct?

17            A.   They formed an opinion based on perception.

18       Obviously they're not subject to being able to review

19       personnel files, but that was their perception.

20            Q.   Okay.

21                 CHAIRMAN ARGENZIANO:  Commissioner Skop.

22                 COMMISSIONER SKOP:  Yes, Madam Chair.  Thank

23       you.

24                 To Mr. Young.  Mr. Young, can someone from

25       legal, while you continue your cross-examination, find

FLORIDA PUBLIC SERVICE COMMISSION

1530

1       the FPL response to staff data request DR-8.9, please?

2                 MR. YOUNG:  I'm sorry.  I was talking to

3       Ms. Bennett.  Can you --

4                 COMMISSIONER SKOP:  I'm sorry.  Yes.  While

5       you're continuing your cross-examination, can someone

6       from legal staff please provide me with a copy of the

7       FPL response to staff data request DR-8.9?  Thank you.

8                 MR. YOUNG:  And Ms. Bennett is here, Madam

9       Chairman.  So with your indulgence, if I can pass out

10       that document.

11                 CHAIRMAN ARGENZIANO:  Absolutely.  Thank you.

12                 MR. YOUNG:  Okay.

13                 CHAIRMAN EDGAR:  Madam Chair, while that's

14       being passed out, can you tell me, so I'm keeping up,

15       this has been marked and which number and what is the

16       title?  I've got so many pieces of transcript here.

17                 CHAIRMAN ARGENZIANO:  This is 244, copy of

18       direct testimony of Mr. Kundalkar.  I hope I said that

19       right.

20                 MR. YOUNG:  Yeah.  And it would be the entire

21       transcript that is going to be entered.  We just put

22       portion, we just have a portion of it.

23                 CHAIRMAN EDGAR:  All right.  Thank you.  Thank

24       you.

25                 CHAIRMAN ARGENZIANO:  Commissioner Skop.

FLORIDA PUBLIC SERVICE COMMISSION

1531

1                 COMMISSIONER SKOP:  Thank you, Madam Chair.

2                 And to that same point, Mr. Young, the entire

3       transcript will include the Florida PSC Clerk Bates

4       stamp number with the cover page and the clerk seal

5       that's being printed?

6                 MR. YOUNG:  Yes, sir.

7                 COMMISSIONER SKOP:  All right.  Thank you.

8                 MR. YOUNG:  And it'll be just Volume 2 of that

9       transcript.

10                 COMMISSIONER SKOP:  Yes.  Thank you.

11                 CHAIRMAN ARGENZIANO:  Thank you.  Whenever

12       you're ready.

13       BY MR. YOUNG:

14            Q.   All right.  Mr. Reed, what Ms. Bennett has

15       handed you is now marked as Exhibit Number 244.  I want

16       to walk through this document.  It's a public document,

17       so we can discuss really the names as relates to who

18       testified, when they testified, what they said.  Okay?

19            A.   Okay.

20            Q.   All right.  On page 207 of that document,

21       Mr. Anderson said, "Thank you."  Raj S. Kundalkar was

22       called to the stand, and then Mr. Anderson began a

23       direct examination of Mr. Kundalkar.

24            A.   I see that.

25            Q.   Would you agree I summarized that correctly;

FLORIDA PUBLIC SERVICE COMMISSION

1532

1       correct?

2            A.   Yes.

3            Q.   All right.

4                 MR. YOUNG:  And, Madam Chairman, I'd like

5       to --

6       BY MR. YOUNG:

7            Q.   And in the course of this testimony,

8       Mr. Kundalkar made certain statements; correct?

9            A.   Yes.

10            Q.   And one of those statements was as relates to

11       his prefiled direct testimony; correct?

12            A.   Yes.

13            Q.   And in that statement in one of the responses

14       Mr. Kundalkar gave to this, before this Commission was a

15       response when Mr. Anderson asked, "If I asked you the

16       questions as in your prefiled testimony, would your

17       answers be the same"; correct?

18            A.   He did ask that question, yes.

19            Q.   And part of that, part of the testimony to his

20       answers -- part of the answers relates to his May

21       testimony, correct, 2009 testimony?

22            A.   His May 2009 prefiled testimony.  Yes.

23            Q.   All right.  And you have reviewed --

24                 CHAIRMAN ARGENZIANO:  Commissioner Skop.

25                 I'm sorry, Mr. Young.

FLORIDA PUBLIC SERVICE COMMISSION

1533

1                 COMMISSIONER SKOP:  Thank you, Madam Chair.

2                 Mr. Young, just for purposes of your last few

3       questions, that would be on page 208 of the transcripts

4       beginning at lines 23, continuing on to 209, line 2?

5       Actually, hold on.  Wait a second.  I'm confused.  Wait

6       for one second.  Okay.  Yes.  I'm -- beginning on page

7       208 of that transcript, beginning on lines 24,

8       continuing on to page 209 through line 2; is that

9       correct?

10                 MR. YOUNG:  Yes, sir.

11                 COMMISSIONER SKOP:  Okay.  All right.  Thank

12       you.

13       BY MR. YOUNG:

14            Q.   Now his testimony, he said his answers would

15       be the same as relates to his 2009 testimony; correct?

16            A.   That's correct.

17            Q.   All right.  And you have done an

18       investigation.  Part of your investigation was to look

19       at the, whether that statement was correct; correct?

20            A.   Our testimony, I'm sorry, our investigation

21       reviewed all of the testimony from the 2009 proceeding

22       to see if it was correct.

23            Q.   All right.  And what is your opinion as

24       relates to the, Mr. Kundalkar's 2009 testimony, the

25       truthfulness of Mr. Kundalkar's 2009 testimony?

FLORIDA PUBLIC SERVICE COMMISSION

1534

1            A.   My conclusion is that some of the information

2       provided in the prefiled testimony was out of date as of

3       the date of this hearing, September 8th, 2009.

4                 CHAIRMAN ARGENZIANO:  Commissioner Skop.

5                 COMMISSIONER SKOP:  Thank you.

6                 Mr. Reed, in your opinion to that last

7       question, would that mean that the testimony given was

8       in your opinion inaccurate and incomplete?

9                 THE WITNESS:  Incomplete, yes.  Inaccurate may

10       border on a legal opinion.  What I said in our report is

11       it did not meet the standards that we believe apply to

12       testimony before a regulatory agency.

13                 COMMISSIONER SKOP:  Thank you.

14                 CHAIRMAN ARGENZIANO:  Well, that begs the

15       question then, did, was the answer -- the question was,

16       "If I asked you the same questions contained in your

17       prefiled direct testimony, would your answers be the

18       same?"  And the gentleman answered, "Yes, they would

19       be."  Is that accurate?

20                 THE WITNESS:  Well, I think his answers would

21       have been the same and were the same.  I think his

22       answers should have been different.  I think he should

23       have provided updated testimony with regard to the cost

24       estimate.

25                 CHAIRMAN ARGENZIANO:  And that's different

FLORIDA PUBLIC SERVICE COMMISSION

1535

1       than inaccurate?  Or you're meaning that his answers to

2       the original questions on that original day they were

3       asked or contained in the prefiled direct testimony.

4       Because it seems like we're splitting hairs and I'm

5       trying to figure out --

6                 THE WITNESS:  I think perhaps we are splitting

7       hairs.  What our report says is the, we believe the

8       information was appropriately presented in the May and

9       March testimony as of that date.  As of September it was

10       out of date.

11                 CHAIRMAN ARGENZIANO:  Thank you.

12                 Commissioner Skop.

13                 COMMISSIONER SKOP:  Thank you.

14                 And further clarification of that point, Mr.

15       Reed.  I believe in response to my previous question,

16       you indicated that in your professional opinion that the

17       information contained in the, in his testimony on

18       September 9th, 2009, because it had not been amended,

19       was inaccurate.  I believe you stated that; is that

20       correct?

21                 THE WITNESS:  Yes.

22                 COMMISSIONER SKOP:  Okay.  And with respect to

23       whether his testimony was incomplete, you deferred

24       because you thought it would be a legal opinion.  Do you

25       have a layman's person opinion as to whether his

FLORIDA PUBLIC SERVICE COMMISSION

1536

1       testimony was incomplete based on your investigation?

2                 THE WITNESS:  In my lay opinion, again, the

3       information was out of date.  I would characterize that

4       as inaccurate and incomplete.

5                 COMMISSIONER SKOP:  Thank you.

6       BY MR. YOUNG:

7            Q.   Now, Mr. Reed, can you turn to page 37 of your

8       revised rebuttal testimony?

9            A.   Did you say rebuttal testimony?

10            Q.   Yes.  But your -- before we get there, do you

11       believe he, that Mr. Kundalkar should have informed the

12       Commission that his, the forecast in his testimony was

13       out of date?

14            A.   In September 2008, I'm sorry, September 8th,

15       2009, I believe he should have.

16            Q.   And that is based on your report, correct,

17       your investigation, your independent investigation;

18       correct?

19            A.   Yes.

20            Q.   Your interviewing of the, of several FPL

21       employees; correct?

22            A.   Yes.

23            Q.   Your interviewing -- and some of those

24       employees including the EPU management team; correct?

25            A.   Yes.

FLORIDA PUBLIC SERVICE COMMISSION

1537

1            Q.   And the July 25th, 2009, meeting of the upper

2       management; correct?

3            A.   Yes.  Our investigation included a review of

4       the documentation from that meeting.

5            Q.   And that is the, and that is based on the ESC

6       meeting on July 25th, just to be clear.

7            A.   Yes.

8            Q.   Can you please turn to page 37 of your revised

9       rebuttal testimony?

10            A.   Do you mean the report?  My rebuttal testimony

11       doesn't have 37 pages.

12            Q.   Yes, the report.  If I'm not mistaken, I'm

13       looking at your rebuttal testimony, and I'm seeing 39

14       pages.

15            A.   Okay.  I'm sorry.  You did mean the rebuttal.

16       If you'll give me just a moment.  Yes, I'm sorry.

17       Page 37, I have that.

18            Q.   Now looking at line 11 on page 37, do you see

19       the question?

20            A.   Yes, I do.

21            Q.   Can you please read that question aloud?

22            A.   It says, "Has Concentric found any evidence of

23       costs that were imprudently incurred by the EPU project

24       in 2009?"

25            Q.   And your response is?

FLORIDA PUBLIC SERVICE COMMISSION

1538

1            A.   "No.  Concentric thoroughly reviewed the EPU

2       project's 2009 costs.  In neither case did Concentric

3       identify any imprudently incurred costs."

4            Q.   What do you mean, in neither case?  What does

5       that mean?  What do you mean by that?

6            A.   For neither the Turkey Point uprate nor the

7       St. Lucie uprate.

8            Q.   Can you please describe the costs you looked

9       at, the methodology for examining those costs, and

10       indicate whether a separate examination of those costs

11       was done for purposes of the investigation, as distinct

12       from the normal pudency evaluation performed by

13       Concentric?

14            A.   No.  It was not a separate investigation

15       relating to the employee letter.  It was part of our

16       overall review of project controls, procedures, project

17       management and costs that's presented in our direct

18       testimony.

19            Q.   Okay.  Did you examine the work authorization?

20            A.   We examined several work authorizations, yes.

21            Q.   Did you examine the change orders?

22            A.   Yes.

23            Q.   Status reports?

24            A.   Yes.

25            Q.   And other related documents that could reveal

FLORIDA PUBLIC SERVICE COMMISSION

1539

1       potential costs, any potential costs or schedule impact?

2            A.   Yes.

3            Q.   Of the fluctuating project scope?

4            A.   Yes.

5            Q.   Time lines, cost estimates, staffing levels?

6            A.   Yes, all of those.

7            Q.   So if I, I opened my question as relates to

8       pointing you to Witness Jones' letter too, that is

9       including your Concentric report; correct?

10            A.   Yes.  I'm sorry.  I'm not sure I follow your

11       question.

12            Q.   What is marked as -- I haven't gotten to the

13       question.  I'm asking -- I started with this line of

14       questioning as relating to witness Jones' letter that is

15       included in part of your Concentric report, which is

16       Exhibit Number 243.

17            A.   Yes, I have that.

18            Q.   Witness Jones believed that some costs, there

19       were missed opportunities; correct?

20            A.   As missed opportunities in terms of

21       opportunities to reduce costs through negotiations with

22       vendors.  He felt that they had not been fully pursued

23       at that point and that they were going to be.

24            Q.   In fact, you believe they were missed

25       opportunities; correct?

FLORIDA PUBLIC SERVICE COMMISSION

1540

1            A.   Can you be more specific?  Missed

2       opportunities for what?

3            Q.   In terms of the cost overruns as relates to

4       the EPU project.

5            A.   We --

6            Q.   In fact, you stated that there were a

7       five-month window that there was a missed opportunity;

8       correct?

9            A.   Yes.  We stated that there was a missed

10       opportunity in terms of having earlier recognition of

11       the increase in the cost projection.

12            Q.   Now I think, if I'm correct, you believed that

13       imprudent, actions are imprudent, correct, not costs?

14            A.   That's correct.

15                 MR. YOUNG:  No further questions.

16                 CHAIRMAN ARGENZIANO:  Commissioner Skop.

17                 COMMISSIONER SKOP:  Madam Chair, I'm going to

18       have some questions, but I need a few minutes to collect

19       my thoughts.  Perhaps there may be other questions from

20       the Intervenors, or if we could take perhaps a five- or

21       ten-minute break at this point.

22                 CHAIRMAN ARGENZIANO:  Intervenors?

23                 MR. McGLOTHLIN:  I have several.

24                 CHAIRMAN ARGENZIANO:  Okay.  You're

25       recognized.

FLORIDA PUBLIC SERVICE COMMISSION

1541

1                          CROSS EXAMINATION

2       BY MR. McGLOTHLIN:

3            Q.   Mr. Reed, I'm looking at the redacted version

4       of your investigation report.  And I think for my

5       purposes I don't need to get into anything confidential.

6       Attached to your investigation report is a list of the

7       documents on which you relied for the report; is that

8       correct?

9            A.   Yes.

10            Q.   Also you've included a schedule showing the

11       past assignments that you've had with FP&L; correct?

12            A.   Yes, we did.

13            Q.   I noticed that, among other things along the

14       way, you have trained FPL witnesses; correct?

15            A.   I wasn't involved in that, but our firm did,

16       yes.

17            Q.   That was in the, an earlier rate case.  Have

18       you or your firm members trained FPL witnesses since

19       that time?

20            A.   No.  I should comment that I have participated

21       in several witness training sessions, but our firm did

22       not conduct those sessions.

23            Q.   Were any of those sessions related to this

24       docket?

25            A.   Yes.  We had one session related to this

FLORIDA PUBLIC SERVICE COMMISSION

1542

1       docket.

2            Q.   So were you in sessions related to the

3       training of witnesses who are appearing in front of the

4       Commission in this proceeding?

5            A.   Yes, I would say so.

6            Q.   At page 17 of 23 -- let me start again.  I

7       think you replied in response to a question from staff,

8       or perhaps it was in your summary, that as a result of

9       your investigation report, you've made something like 13

10       recommendations to FPL and 12 of them have been

11       accepted; correct?

12            A.   There are 14, 13 of which have been accepted.

13            Q.   Well, I was close.  At page 17 of 23, VIII,

14       there are several recommendations for improvements

15       related to the NCRC; do you see that?

16            A.   I do.

17            Q.   And were some of those recommendations

18       designed to avoid circumstances in the future in which

19       FPL witnesses would be incomplete or inaccurate or fail

20       to update their information when they've testified at

21       the PSC?

22            A.   Yes.

23            Q.   Were those recommendations among those that

24       were accepted by FP&L?

25            A.   Yes.  All four of these recommendations have

FLORIDA PUBLIC SERVICE COMMISSION

1543

1       been accepted by FPL, and I would comment that I think

2       they've been actually implemented quite effectively for

3       this proceeding.

4            Q.   Now in terms of a time line, you submitted

5       your first testimony in March of this year; correct?

6            A.   In this docket, yes.

7            Q.   And I understand that those testimonies have

8       not been sponsored in full, but I want to ask you just a

9       couple of general questions that I think you'll be able

10       to answer without reference.

11                 In your first testimony you devoted, you

12       devoted a great amount of attention to a review of the

13       controls, processes and procedures that the company put

14       in place; correct?

15            A.   Yes.

16            Q.   And your testimony basically approved those as

17       being adequate for the purpose; correct?

18            A.   Yes.

19            Q.   Now subsequently, in your May testimony, you

20       said as a result of the request that you perform an

21       investigation, something had come to light that

22       indicated that some of those procedures had not been

23       fully followed; correct?

24            A.   Correct.

25            Q.   Would you agree with me then, sir, that

FLORIDA PUBLIC SERVICE COMMISSION

1544

1       procedures, mechanisms, controls cannot be effective

2       unless they are implemented and adhered to?

3            A.   That's correct.  There is a performance

4       element as well as a structural element.  The concerns

5       we raised in the report were with regard to performance.

6            Q.   Also in your May testimony you indicated that

7       the, you were going to perform an investigation of those

8       inadequacies and that the report should be considered,

9       or that those details should be considered as supplement

10       to your March testimony.  Do you remember that

11       statement?

12            A.   That's correct.

13            Q.   Now did you file testimony that was designed

14       to supplement your March testimony?

15            A.   We did not file testimony.  We submitted the

16       report.  And if we were to get to the stage of adopting

17       that testimony, it would include that report.

18            Q.   I see.  But the report was not submitted in

19       the form of supplemental testimony per se, was it?

20            A.   No.  It's essentially the equivalent of an

21       exhibit to the testimony.

22            Q.   When did you begin your investigation?

23            A.   On March 11th, 2010.

24            Q.   And your second testimony was submitted on

25       May 3rd, was it not?

FLORIDA PUBLIC SERVICE COMMISSION

1545

1            A.   The second piece, yes.

2            Q.   And in that testimony you said that in neither

3       case did Concentric identify any imprudently incurred

4       costs.  Isn't it true that at that point in time the

5       investigation was work in progress?

6            A.   Yes.

7            Q.   What was the date of your final investigation

8       report?

9            A.   June 21st, 2010.

10            Q.   And if you'll turn to page 11 of 23 of Exhibit

11       243.

12            A.   I have that page.

13            Q.   The section VI is the portion of your

14       investigation report where you provide your conclusions

15       as to those costs; correct?

16            A.   That's correct.

17            Q.   And that section VI consists of the three

18       paragraphs at the top of the page?

19            A.   That's correct.

20            Q.   And would you agree with me that your findings

21       are confined to the third of those three paragraphs?

22            A.   I'm sorry.  Is your question, are our findings

23       only in the third of the three paragraphs?

24            Q.   With respect to the, whether the costs were

25       the result of imprudent decisions or actions.

FLORIDA PUBLIC SERVICE COMMISSION

1546

1            A.   That's true with regard to the costs, yes.

2            Q.   Would you -- without reading the information

3       that's shown to be confidential, would you read that

4       third paragraph that begins "Similarly"?

5            A.   Yes.  "Similarly, Concentric found no

6       indications of costs that were the result of imprudent

7       decisions or actions on the part of FPL's management.

8       This conclusion was reinforced by all interviewees.

9       When asked whether they were aware of any costs that

10       should not be passed along, the unanimous answer was no.

11       Indeed," blank, a redacted name, "acknowledged during

12       our interview that the costs will be what they are, and

13       his concerns are related to what information would be

14       presented to the Florida Public Service Commission.  As

15       a result, Concentric believes there are no costs which

16       should be subject to disallowance by the Florida Public

17       Service Commission on the basis of imprudent

18       decision-making."

19            Q.   Now you referred to interviewees.  Were all of

20       the interviewees FPL employees?

21            A.   No.  Some are contractors, some are former

22       employees.

23            Q.   So they were either employees or contractors

24       engaged by FPL?

25            A.   Or former employees.

FLORIDA PUBLIC SERVICE COMMISSION

1547

1            Q.   When Mr. Young asked you some questions about

2       what you reviewed, one of the first items, one of the

3       first items -- you said you reviewed several of them.

4       Do you remember that question and answer?

5            A.   Yes.

6            Q.   Does that qualification apply to the other

7       types of documents that he listed as well?

8            A.   We reviewed many of the documents in those

9       categories, in each category.  Overall we reviewed many

10       tens of thousands of pages of material.

11            Q.   But you did not review all of the costs

12       incurred by FPL in 2009 for the uprates, did you not?

13            A.   No.  Any audit or review is not going to

14       review every invoice, every cost.  It reviews the

15       decisions and it reviews the costs that stem from those

16       decisions.  But it's not meant to be a, an analysis of

17       every dollar spent.

18            Q.   You, and you also reviewed the controls and

19       mechanisms in place with respect to cost; correct?

20            A.   We did.

21                 MR. McGLOTHLIN:  Those are all of my

22       questions.

23                 CHAIRMAN ARGENZIANO:  Thank you.

24                 Mr. Davis.  Mr. Moyle.

25                 MR. MOYLE:  Thank you.  Thank you, Madam

FLORIDA PUBLIC SERVICE COMMISSION

1548

1       Chairman.

2                          CROSS EXAMINATION

3       BY MR. MOYLE:

4            Q.   Mr. Reed, good morning.  I'm going to go

5       through and ask you some questions primarily about your

6       report and your views on some of the issues that I think

7       are squarely and fairly raised by your report.  And

8       given that this is kind of a limited proceeding, you

9       tailored your opening comments to the report, and I'm

10       going to try to direct my questions to, to the limited

11       basis.

12                 So a couple of, a couple of things.  In

13       response to a question, you said you had to work out

14       some paperwork with FPL and it was a soft authorization.

15       What paperwork did you have to work out with them?

16            A.   Our engagement letter.

17            Q.   Okay.  And have you produced and provided a

18       copy of that to the Commission staff?

19            A.   It has been produced in discovery, yes.

20            Q.   Okay.  And you have been asked some questions

21       about the review of your, you know, of your, of your

22       work product and the fact that you had a number of

23       sessions with FPL to review, I guess, your preliminary

24       findings and your, as you headed down the road, your

25       conclusions; is that right?

FLORIDA PUBLIC SERVICE COMMISSION

1549

1            A.   Yes.

2            Q.   Okay.  And those discussions included, you

3       know, word choices and semantics and, you know,

4       suggested both -- well, I guess I would say subjective

5       wording was kind of debated back and forth during those

6       discussions in certain cases; isn't that right?

7            A.   To be honest, there was no debate.  I listened

8       to FPL's comments and everything from wording to

9       punctuation.

10            Q.   All right.  So let me -- do you have a copy of

11       your confidential report, 242?

12            A.   I do.

13            Q.   Page 21 of 23.

14            A.   Yes.

15            Q.   The third deleted box there and the fourth

16       deleted box, those, those deletions aren't confidential,

17       are they?

18                 MR. ROSS:  Mr. Moyle, could you be more

19       specific as to what you're referring to?

20                 MR. MOYLE:  Sure.  I'm referring to Exhibit

21       242, page 21 of 23.  It's toward the back of the

22       document.

23                 MR. ROSS:  Could we have a Bates number?

24                 MR. MOYLE:  Oh, I'm sorry.  Yeah.  FPL 153507,

25       up at the top right-hand corner.

FLORIDA PUBLIC SERVICE COMMISSION

1550

1                 THE WITNESS:  I'm sorry.  That was FPL 153197?

2       BY MR. MOYLE:

3            Q.   No.  153507.  So it's NCR-10, and it's a draft

4       report.  Page 21 of 23 is what I'm referring to.  And it

5       came out of the big red folder.

6            A.   I'm sorry.  I don't see that document in the

7       folder that's been handed me.  I have that as 153484.

8       Okay.

9            Q.   A lot of documents flying around us.

10            A.   And, Mr. Moyle, just to clarify, this isn't

11       our report.  It's an earlier draft of the report, but go

12       ahead.

13            Q.   Okay.  And I referenced you to the third and

14       fourth deletions on that document.  You don't consider

15       those deletions confidential, do you?

16                 MR. ROSS:  I would object.  This document in

17       all of its entirety is confidential.  It's not what

18       Mr. Reed's opinion is.  That was the ruling of the

19       Prehearing Officer.

20                 CHAIRMAN ARGENZIANO:  Mr. Moyle, to the

21       objection.

22                 MR. MOYLE:  Well, my understanding of

23       confidentiality is it's designed to protect sensitive

24       information with respect that gives somebody a business

25       advantage or, you know, trade secrets and, you know, the

FLORIDA PUBLIC SERVICE COMMISSION

1551

1       use of an, of an adjective.  My initial question was,

2       you know, during the back and forth were there

3       discussions and, you know, about subjective terms.  This

4       is a subjective term, an adjective.  You know, I don't

5       know that the adjective in and of itself is

6       appropriately considered as a trade secret or, or

7       confidential.

8                 CHAIRMAN ARGENZIANO:  Commissioner Skop, and

9       then to staff, please.

10                 COMMISSIONER SKOP:  Thank you.  And just on

11       the document in question.  Again, no ruling has been

12       rendered.  Some of the information probably contained on

13       that page has been redacted in the final report that was

14       declassified, but no ruling has been made on the

15       comments.

16                 Again, as a general proposition, I mean,

17       that's the problem I have with the use of

18       confidentiality statute is, you know, confidentiality

19       should protect numbers and critical business

20       information, not adjectives.  But it gets used a little

21       bit more broadly and sometimes we don't have time to

22       sort all that out.

23                 CHAIRMAN ARGENZIANO:  Ms. Helton.

24                 MS. HELTON:  Madam Chairman, when a request

25       for confidentiality is made, and even if, even if

FLORIDA PUBLIC SERVICE COMMISSION

1552

1       there's an order entered that denies the request, under

2       our rules we keep that information confidential until

3       the time for appeal has run and the court can actually

4       rule whether it's confidential or not.

5                 So it's my understanding that for the

6       information that's in the little red boxes on the side,

7       that a request has been made.  And while that request is

8       pending and until there's a Prehearing Officer's order

9       and until the court has ruled, then we need to maintain

10       the confidentiality of that information.

11                 CHAIRMAN ARGENZIANO:  The objection --

12                 MS. HELTON:  Regardless --

13                 CHAIRMAN ARGENZIANO:  Yeah.  The objection is

14       sustained.

15       BY MR. MOYLE:

16            Q.   The -- you see the boxes I'm referring to, the

17       third and fourth there, Mr. Reed?

18            A.   Yes, I see them.

19            Q.   Were those your deletions or were those

20       deletions of FP&L?

21            A.   All of the additions and deletions in the

22       draft are mine.

23            Q.   Okay.  Did you make those two deletions there

24       after discussions with FP&L?

25            A.   Well, as I said, we had four different

FLORIDA PUBLIC SERVICE COMMISSION

1553

1       sessions in which we discussed our drafts with FPL.  I'm

2       sure this was after one of those sessions.  But I can

3       assure you that the changes made here are changes that I

4       decided to make, not that were urged upon me by FPL.

5            Q.   How did you communicate with FP&L typically?

6            A.   Both by phone and e-mail, as well as a couple

7       of face-to-face meetings.

8            Q.   So when you were having discussions about the

9       report, I presume that most of those discussions were in

10       face-to-face meetings and by telephone, as compared to

11       e-mail; is that right?

12            A.   There were three face-to-face meetings.  So,

13       yes, most of the sessions to review the draft were

14       face-to-face.

15            Q.   Right.  And you produced some e-mails.  I

16       mean, I didn't see a lot of e-mail traffic, so that's

17       why I'm asking the question.  I just assumed most of

18       them were telephones or face-to-face.

19            A.   Most of the review sessions were face-to-face.

20            Q.   You talked about folks you interviewed.  Did

21       you interview anyone who was on the, the, what is it,

22       the ESC committee?

23            A.   We interviewed people that attend those

24       meetings.  I'm not sure that the committee has an

25       official roster of members, but we interviewed people

FLORIDA PUBLIC SERVICE COMMISSION

1554

1       that attend those meetings.

2            Q.   Do you understand the term ESC as to what it

3       means in FPL's hierarchy?

4            A.   It's Executive Steering Committee.

5            Q.   Okay.  And as part of your investigation, did

6       you determine who was on the Executive Steering

7       Committee?

8            A.   Yes.

9            Q.   Okay.  And did you interview any of the

10       members of the Executive Steering Committee pursuant to

11       your investigation?

12            A.   I would say yes, we did.

13            Q.   Okay.  And those would include members who

14       attended the July meeting; correct?

15            A.   Yes.

16            Q.   Okay.  I want to just walk you through a

17       couple of portions of your report.  You've already been

18       asked a lot of questions by staff, so I'm going to try

19       to make this pretty succinct and brief, if I can.

20                 Mr. McGlothlin asked you some questions about,

21       this is on the Exhibit 243 that is a public record as I

22       understand it.  It's been redacted.  And I want to refer

23       you to page 11 of 23.

24            A.   I have that.

25            Q.   Okay.  Do you see the section under 7, the

FLORIDA PUBLIC SERVICE COMMISSION

1555

1       flow of information to the Florida Public Service

2       Commission?

3            A.   Yes.

4            Q.   Okay.  As you described the scope of inquiry,

5       it was whether the information presented by FPL in those

6       proceedings related to the EPU cost estimate schedule

7       and cost-effectiveness was accurate and consistent with

8       the standards expected for testimony before and

9       submissions made to a regulatory agency.  Given your

10       testimony previously, I assume that your answer to that

11       question as you phrased it was no; correct?

12            A.   In the one instance, yes, that's correct.

13            Q.   And on that, on that instance, page 15 of 23,

14       down at the bottom you reach a conclusion that indicates

15       the information, you know, was out of date or inaccurate

16       or not capable of being relied upon.  The reason you

17       reached that conclusion -- all of those things are true,

18       correct, in your view?

19                 MR. ROSS:  I object.  It mischaracterizes

20       Mr. Reed's testimony, especially the last statement.

21                 CHAIRMAN ARGENZIANO:  Mr. Moyle, can you

22       rephrase?

23                 MR. MOYLE:  Sure.

24       BY MR. MOYLE:

25            Q.   Do you believe the information that was

FLORIDA PUBLIC SERVICE COMMISSION

1556

1       provided in live testimony in front of the Commission

2       was, was inaccurate?

3            A.   Yes, I would characterize in this one instance

4       that that information was inaccurate.

5            Q.   Okay.  And all my questions are limited to the

6       one instance.  You believe it was out of date?

7            A.   Yes.

8            Q.   And you believe also it was not capable of

9       being relied upon at that point in time?

10            A.   Not for the purpose for which it was

11       presented.

12            Q.   Okay.  It was wrong, it was false.

13            A.   It was out of date.  It was originally correct

14       and the information had been superseded by new

15       information.

16            Q.   Okay.  So it was not right?

17            A.   It was no longer the best information

18       available.

19            Q.   And the reason you reached the conclusion that

20       you reached was, is that it was wrong to the tune of

21       $300 million; correct?

22            A.   Well, let me again object to the

23       characterization.  When you're talking about a cost

24       forecast like this, there is not a right or wrong

25       number.  What I said was it was out of date.  It was no

FLORIDA PUBLIC SERVICE COMMISSION

1557

1       longer the best information available.  New information

2       had been presented to management.  And even with all of

3       the caveats that that new information was uncertain, it

4       was simply an estimate that could be one of many

5       estimates.  I believed that the prior estimate was no

6       longer the best information available.

7            Q.   Okay.  And it was no longer the best

8       information available to the tune of $300 million;

9       correct?

10            A.   The difference between the updated forecast

11       and the prior forecast was about 300 million.

12            Q.   And on the basis of the overall project, that

13       was over a 27 percent delta; correct?

14            A.   That's correct.

15            Q.   Okay.  And in this whole business of nuclear

16       power plant building and, you know, EPU changes, the

17       best information you have to work with are estimates;

18       correct?

19            A.   Yes.  They are all estimates in terms of cost.

20       Obviously there's some science with specific definable

21       numbers.

22            Q.   Right.

23            A.   But the cost estimates are estimates.

24            Q.   And on page 16 of your report, 16 of 23, I'll

25       just read it.  It might be easier.  The third paragraph,

FLORIDA PUBLIC SERVICE COMMISSION

1558

1       the last sentence, you conclude, quote, "In short, while

2       the July 25th, 2009, and subsequent cost forecasts are

3       and were preliminary, they represented the best

4       information available at that time and were relied upon

5       by FPL and were more advanced that," should have been

6       than, I think, "than the 2007, 2008 cost projections."

7       Correct?

8            A.   Yes.  That's correct.

9            Q.   And, you know, essentially it was an apples to

10       apples comparison.  So the notion that, you know, that

11       these numbers were preliminary, I mean, that's all we're

12       working with in this nuclear business are preliminary

13       numbers, until you get final nuclear design specs;

14       correct?

15            A.   I'm not quite sure what you mean by apples to

16       apples.  I would say that 2007, 2008 was an estimate.

17       The July 2009 number was an estimate.  And you continue

18       to work with estimates and forecasts until the project

19       is completed.

20            Q.   Okay.  The -- you've testified as an expert

21       many, many times; correct?

22            A.   Yes.

23            Q.   Can you give me a ballpark?

24            A.   Something approaching 200 times now.

25            Q.   Okay.  And you did it yesterday and you do it,

FLORIDA PUBLIC SERVICE COMMISSION

1559

1       I believe, in about every proceeding that you testify

2       in, which is before you take the stand, you take an oath

3       to tell the truth; correct?

4            A.   That's correct.

5            Q.   In your opinion, given your review and the

6       conclusions you reached, do you believe that the

7       particular person who testified last year whose actions

8       are being questioned properly fulfilled the oath that

9       was taken?

10                 MR. ROSS:  Objection.  That calls for a legal

11       conclusion and this witness is not here as a legal

12       witness.

13                 CHAIRMAN ARGENZIANO:  Do you want to rephrase?

14                 MR. MOYLE:  I don't, I don't think it, I mean,

15       I would -- the legal conclusion is -- I don't, I don't

16       think it calls for a legal conclusion.  But even if it

17       does, he's able to give his layman's view of it.

18                 CHAIRMAN ARGENZIANO:  Staff?

19                 You're not asking for a legal opinion?

20                 MR. MOYLE:  No.  I'm just asking in his

21       opinion.  I mean, he's put together a report.

22                 CHAIRMAN ARGENZIANO:  In his opinion.

23                 MR. MOYLE:  I think it's --

24                 MS. HELTON:  Let's do it -- Madam Chairman, I

25       suggest, let's see if Mr. Moyle can rephrase the

FLORIDA PUBLIC SERVICE COMMISSION

1560

1       question in a way that won't be objectionable to Florida

2       Power & Light and kind of go from there.

3                 CHAIRMAN ARGENZIANO:  We'll let him try and

4       we'll see what happens.

5                 MR. MOYLE:  This is kind of my last question

6       along these lines, and I have a sneaking feeling that

7       they may not like my last question regardless of how

8       it's phrased.

9                 CHAIRMAN ARGENZIANO:  Okay.  Let's proceed.

10       BY MR. MOYLE:

11            Q.   If you put yourself in the position of the

12       person who testified last year and you were in that

13       position and you were asked the question, if the

14       questions that were posed to you in your prefiled direct

15       testimony were asked of you today, would the answers as

16       set forth in your prefiled testimony be the same, how

17       would you have answered that question?

18            A.   I would have chosen to answer differently and

19       to provide the updated information.

20            Q.   Okay.

21                 CHAIRMAN ARGENZIANO:  Commissioner Skop, did

22       you have a question?

23                 COMMISSIONER SKOP:  If Mr. Moyle is done, I --

24                 MR. MOYLE:  I have a couple more.

25                 CHAIRMAN ARGENZIANO:  I think he has another

FLORIDA PUBLIC SERVICE COMMISSION

1561

1       question.

2                 MR. MOYLE:  I'll defer to --

3                 COMMISSIONER SKOP:  Okay.  No.  Just go -- no,

4       go ahead.

5                 CHAIRMAN ARGENZIANO:  Mr. Moyle.

6       BY MR. MOYLE:

7            Q.   And I appreciate that.  And this isn't an easy

8       topic to discuss, as I think we've gotten a sense over

9       the last couple of days.  But you would agree that it's

10       an important conversation to have in order for the

11       regulatory compact to work; correct?

12            A.   By conversation, you mean this part of the

13       proceeding?

14            Q.   Yes, sir.

15            A.   Yes.

16            Q.   And that is, is because in order for

17       regulators to do their jobs and for companies to be

18       regulated, you have to have true, accurate and complete

19       information provided to a tribunal like this and to

20       intervenors; correct?

21            A.   Yes.  In general I think that's correct.

22            Q.   Okay.  And if you don't have that, then it

23       kind of breaks down the, you know, the regulatory

24       compact that we often hear about; correct?

25            A.   I'm not sure it goes to the regulatory

FLORIDA PUBLIC SERVICE COMMISSION

1562

1       compact.  I agree that regulators are entitled to

2       accurate, correct, truthful and complete information.

3            Q.   And they need that in order to do their job,

4       which is to make, make judgments and make decisions;

5       correct?

6            A.   Yes.

7            Q.   And in this case you don't believe, with the

8       exception we've been, with the instance we've been

9       talking about, that that information was provided to

10       them last year; correct?

11            A.   I think the other way around.  But for that

12       instance I believe it was truthful, correct and

13       complete.

14            Q.   Okay.  But you would agree that the

15       information that was not was pretty significant

16       information as it related to the overall cost of the

17       nuclear uprate project, you know, $300 million,

18       27 percent of the project; correct?

19            A.   I believe that information was material.

20            Q.   Okay.  So as you sit here today, and you've

21       testified over 200 times, the question I think that is

22       sort of begging is what should be done about the fact

23       that inaccurate information was, was provided?  And I

24       want to spend just a couple of minutes and ask you your

25       views on a couple of, a couple of things.  This

FLORIDA PUBLIC SERVICE COMMISSION

1563

1       Commission as currently constituted, there's going to be

2       some, some changes upcoming; you're aware of that?

3            A.   Yes.

4            Q.   Okay.  You would agree that the Commission

5       needs to send a strong message with respect to

6       expectations of full, complete and accurate information;

7       correct?

8            A.   I'm not sure I feel that they have to send

9       that message.  I think that's understood.

10            Q.   Okay.  Do you think if they did nothing, given

11       the evidence and the testimony, that if they did nothing

12       and said, well, you know, we're not going, we're not

13       going to take any action or review it or do anything,

14       that that would be consistent with a message about

15       making sure that you have clear, accurate and complete

16       information?

17                 MR. ROSS:  I'm going to object, Madam

18       Chairman.  This line of questioning is really, it's

19       irrelevant, it's not pertinent to any issue in the case,

20       and it's beyond the scope of Mr. Reed's report and of

21       his testimony.

22                 MR. MOYLE:  Well, I, I think that it is

23       pertinent.  I think it is relevant.  You know, the

24       proceeding has shifted and has focused largely on this

25       report and flow of information and accuracy of

FLORIDA PUBLIC SERVICE COMMISSION

1564

1       information.  And then the question logically flows from

2       there, you know, what's, what's the end result of it,

3       you know, what, what is done about it?  So this

4       gentleman is an expert, he's testified all around the

5       country on it, he probably has some background and

6       experience as to how these things may be handled, and I

7       think it's fair game.

8                 CHAIRMAN ARGENZIANO:  I'll ask our staff.

9                 MS. HELTON:  Madam Chairman, I think it's, if

10       you want to hear the answer to the question, it's within

11       your discretion to hear it, and it's also, the five of

12       you, it's within, it's your responsibility to decide how

13       much weight to give it.

14                 CHAIRMAN ARGENZIANO:  The objection is

15       overruled.

16                 THE WITNESS:  I don't believe this Commission

17       should do nothing, and I want to elaborate on that

18       because I think it's a very important question.  I think

19       the Commission should begin by examining that

20       information that was provided in the last case and ask

21       itself what impact did that have on the decision and

22       what impact did that have on the costs?  I have

23       attempted to do that in our report.  Our report has

24       indicated that even with the new information, the

25       cost-effectiveness of the uprates did not change.  The

FLORIDA PUBLIC SERVICE COMMISSION

1565

1       decision to go forward with the uprates and to continue

2       to pursue them was the right decision.  That I think

3       first and foremost is what needs to be asked and

4       answered.

5                 Secondly, did the information that was

6       provided that was out of date in any way lead to an

7       imprudent decision or to imprudently incurred costs?

8       And once again we have attempted to review that, analyze

9       that, and we have concluded that there were no

10       imprudently incurred costs that stemmed from that

11       provision of out-of-date information.

12                 So I think because those are the issues that

13       this Commission hears and adjudicates upon in these

14       nuclear cost recovery cases, the decision to proceed and

15       the costs, I think those are both important follow-ups

16       for the Commission in light of the information we've

17       provided.

18                 We have attempted to provide the Commission

19       with information that I hope is helpful in addressing

20       those issues.  But I absolutely agree that something

21       should be done, and I think those are the two things

22       that should be done.

23                 CHAIRMAN ARGENZIANO:  Thank you.

24       BY MR. MOYLE:

25            Q.   And in terms of options, I mean, you would

FLORIDA PUBLIC SERVICE COMMISSION

1566

1       agree in your experience that the Commission has the

2       ability to impose administrative penalties or fines.

3       Are you aware of that?

4                 MR. ROSS:  Same objection.  This is, this is

5       not at issue in this limited proceeding.

6                 MR. MOYLE:  I would make the same statement in

7       response.

8                 I tell you what -- well, I only have like two

9       more questions on this.  Let me just substitute in this

10       question instead.

11                 CHAIRMAN ARGENZIANO:  Okay.

12       BY MR. MOYLE:

13            Q.   Wouldn't, wouldn't you think that, given your

14       involvement in the investigation and all the time we

15       spent on this, that it would be appropriate to refund to

16       ratepayers all costs associated with this investigation?

17            A.   Let's clarify that.  The costs of our

18       investigation have not been and will not be charged to

19       ratepayers.

20            Q.   How about with respect to preparation for

21       last, last year's proceeding?

22            A.   Our preparation, is that your question?

23            Q.   The Public Counsel's, Intervenors, others.

24            A.   I think last year's proceeding was

25       appropriately prepared for and conducted.  I don't see

FLORIDA PUBLIC SERVICE COMMISSION

1567

1       the fact that the information that was provided in this

2       one instance being out of date as affecting the cost of

3       preparing or conducting that hearing.

4            Q.   And if I heard your recommendation properly,

5       you said they ought to look into it thoroughly.  I

6       assume that's sort of opening a separate docket to

7       examine that issue.  Would that, would that be your

8       recommendation?

9            A.   No.  That's actually not my recommendation in

10       terms of creating a separate docket.  But I would defer

11       to the Commission's judgment on that point.

12            Q.   And your, your, your end-of-the-day kind of

13       result is -- you've heard the expression "no harm, no

14       foul"?

15            A.   I've heard that expression.

16            Q.   Okay.

17            A.   If you're asking is that my conclusion, no,

18       that is not my conclusion.  I view the matters discussed

19       in our report and the concerns we've raised as being

20       very serious, regardless of whether there was any

21       financial consequence from the actions that occurred.

22            Q.   All right.  And this task that you were asked

23       to do, this work, kind of puts you in a difficult spot

24       in some respects; wouldn't you agree?

25            A.   In some respects.

FLORIDA PUBLIC SERVICE COMMISSION

1568

1            Q.   I mean, here you have a recommendation that

2       the company doesn't agree with with regard to your

3       characterization of the information.  You're aware that

4       they disagree with that; correct?

5            A.   Let's clarify that.  They actually haven't

6       disagreed with any of our recommendations.  They did

7       disagree with one of our conclusions, but they are still

8       implementing 13 out of 14 recommendations and still

9       considering the 14th.

10            Q.   Okay.

11                 MR. MOYLE:  Let's just spend a couple of a

12       minutes, Madam Chairman.  I only have a couple more

13       minutes, but --

14                 CHAIRMAN ARGENZIANO:  Go right ahead.

15                 MR. MOYLE:  And talk about prudency.

16       BY MR. MOYLE:

17            Q.   And you said, as I heard your answer to the

18       question about what should be done, that, well, take a

19       look, but I've looked at it myself and I don't think

20       that there are any costs that are imprudent as it

21       related to the incorrect information; correct?

22            A.   Yes.  I've said I don't think there were any

23       imprudently incurred costs as a result of this provision

24       of outdated information.

25            Q.   Right.  If you had found to the contrary that

FLORIDA PUBLIC SERVICE COMMISSION

1569

1       there were imprudent costs, that would conflict directly

2       with your testimony that you presented in the 2009

3       nuclear cost recovery proceeding; correct?

4            A.   Yes.

5            Q.   And it would also directly conflict with the

6       testimony as filed in this year's nuclear cost recovery

7       proceeding; correct?

8            A.   Except that not all of it had been provided.

9       Short answer is, if I had found that there were any

10       imprudently incurred costs, we would have brought them

11       to the attention of the Commission regardless of what

12       had been said before.  We have new information.  That

13       new information should be considered.  We have

14       considered it.

15            Q.   Right.  You would agree with me that prudent

16       costs and prudency is an issue that ultimately the judge

17       of the Commission -- that the Commission makes; correct?

18            A.   Yes.

19            Q.   And while it's a legal conclusion, prudency,

20       it also is imbued with a lot of facts; correct?

21            A.   That's correct.

22            Q.   Okay.  In your opening you had said that, that

23       you found that FPL did not comply with certain written

24       procedures.  Could you elaborate on what written

25       procedures that they didn't comply with?

FLORIDA PUBLIC SERVICE COMMISSION

1570

1            A.   That's laid out in detail in the report.  It

2       has to do with changes in scope and reflecting those

3       changes in scope in the cost estimate.  It has to do

4       with the release of contingency, it has to do with the

5       development of the contingency, and I think the report

6       speaks for itself.  But those are among the areas that

7       we've highlighted here.

8            Q.   Okay.

9            A.   And that's, again, focusing on the first half

10       of 2009.

11            Q.   And, and procedures and processes are put in

12       place so that you have a pretty good road map about how

13       to conduct business; correct?

14            A.   Yes.

15            Q.   And to the extent that you found that

16       procedures and processes were not followed, you would

17       agree that other people looking at that fact might deem

18       it imprudent; correct?

19            A.   They may deem the conduct to have been

20       imprudent.  But let's be clear what the conduct is.  The

21       conduct relates to the preparation of cost estimates,

22       not to the incurrence of costs.  And we tried to point

23       that out very clearly in the report.

24                 In terms of costs that were incurred in 2008

25       or 2009, there are no cost incurrence consequences of

FLORIDA PUBLIC SERVICE COMMISSION

1571

1       not having followed these procedures, policies and

2       instructions for the preparation of cost estimates.

3            Q.   And why, why is that?  Did FPL back out the

4       cost of their, of their engineer's time and their third

5       party's time associated with preparing these cost

6       estimates?

7            A.   No, they did not back out time.  The point was

8       that there are no costs incurred in terms of

9       construction or processing the EPU, pursuing the EPU

10       related to anything that was imprudent.  I think, as

11       I've said, they did not follow the procedures correctly,

12       they have amended that process and those procedures, and

13       they have amended their conduct.  But, number one, I

14       don't see anything there that's imprudent.  Number two,

15       there aren't any costs incurred relating to that.

16            Q.   So with respect to employee time spent on, on

17       actions that were not consistent with written

18       procedures, you wouldn't think that that cost associated

19       with that employee time should be disallowed?

20            A.   I haven't either examined or determined what

21       costs may have been incurred with result to, with regard

22       to employee time on those matters.  It is a de minimis

23       amount compared to what we're talking about for the

24       uprate.  So, no, I don't think that's the type of thing

25       that either relates to imprudence or should be

FLORIDA PUBLIC SERVICE COMMISSION

1572

1       disallowed.  I think it should be corrected and I think

2       it is being corrected.

3            Q.   As we sit here today, do you know what the

4       estimated cost for, for the nuclear uprate project,

5       projects are?

6            A.   Yes.  The costs at completion are currently

7       estimated to be between 2.1 and $2.3 billion.

8            Q.   Okay.  There's been in, there's been a lot of

9       discussion about a February 19th, 2010, letter that was

10       written to Mr. Hay by an employee.  It's actually

11       attached to your, to the redacted Exhibit 243.

12            A.   Yes.

13            Q.   You're from -- you live in Massachusetts;

14       correct?

15            A.   I live in Washington, DC, and Massachusetts.

16            Q.   Did it concern you that FPL has set forth in

17       this letter that the project controls team developed

18       extensive project indicators patterned after the Big Dig

19       in Boston?

20            A.   To be clear, that was a reference that this

21       individual made in the letter.  That's not an accurate

22       characterization of the project controls that FPL is

23       using.

24            Q.   Yeah.  That project didn't really come in on

25       budget, did it?

FLORIDA PUBLIC SERVICE COMMISSION

1573

1            A.   No, it did not, that project being the Big

2       Dig.

3                 MR. MOYLE:  That's all I have.  Thank you.

4                 CHAIRMAN ARGENZIANO:  Thank you.

5                 Commissioner Skop.

6                 MR. DAVIS:  May I just ask a couple of

7       questions --

8                 CHAIRMAN ARGENZIANO:  Yes, absolutely.

9       Absolutely.

10                 MR. DAVIS:  -- before Commissioner Skop?

11       Because I think you might be longer than me,

12       Commissioner Skop.

13                 CHAIRMAN ARGENZIANO:  Mr. Davis, go right

14       ahead.

15                 MR. DAVIS:  Just a couple of quick questions

16       for the witness.

17                          CROSS EXAMINATION

18       BY MR. DAVIS:

19            Q.   I'm Gary Davis with the Southern Alliance for

20       Clean Energy.  And I think I heard you state in response

21       to a question from Mr. McGlothlin that you reviewed all

22       of the testimony from 2009 from the hearing to see if it

23       was correct; is that right?

24            A.   Yes.

25            Q.   Did you prepare any reports concerning any of

FLORIDA PUBLIC SERVICE COMMISSION

1574

1       the other testimony other than the testimony by

2       Mr. Kundalkar?

3            A.   We prepared a report which offered our

4       conclusions, and that is the only testimony that we

5       found to be inaccurate, incomplete or out of date.

6            Q.   Just -- and has that report been provided to

7       the Commission?

8            A.   Yes.  That's the report that we have marked as

9       Exhibit 243, and of course we have other versions as

10       well.

11            Q.   So is there any discussion in Exhibit 243

12       about testimony other than Mr. Kundalkar's?

13            A.   Yes.

14            Q.   Can you refer us to that, please?

15            A.   Sure.  Beginning on page 11 of 23, we talk

16       about the flow of information to the Florida Public

17       Service Commission.  At the top of page 12 we talk about

18       the four witnesses in that case.  Only one name has not

19       been redacted in the public version.  We talk about as

20       well data request responses that were provided that's in

21       part C beginning on page 14 of the document.  And, of

22       course, then the testimony at the hearing beginning on

23       page 15.  We reviewed the prefiled and oral testimony of

24       all four witnesses, and we reviewed lots, dozens and

25       dozens of data requests in that case.

FLORIDA PUBLIC SERVICE COMMISSION

1575

1            Q.   Let me ask you, you also testified in the 2009

2       docket; correct?

3            A.   That's correct.

4            Q.   And you submitted prefiled testimony in that

5       docket; right?

6            A.   That's correct.

7            Q.   And you testified live in this room on

8       September 8th, 2009; correct?

9            A.   I believe that was the date.

10            Q.   And your testimony concerned, among other

11       things, the reasonableness of the costs of the EPU

12       project; correct?

13            A.   Not specifically.  And that's referred to on

14       page 12.  I offered no estimate of the project, of the

15       projected cost of completion or opinions on the

16       cost-effectiveness of the EPUs.  That statement is on

17       page 12.

18            Q.   Okay.  You can correct me if I'm wrong, but

19       I'm going to quote you from your testimony, your written

20       testimony submitted prior to the hearing.  "Concentric

21       has determined that the costs FPL was seeking to recover

22       in this proceeding are reasonable."

23                 MR. ROSS:  Excuse me.  Could you please refer

24       the witness to the specific testimony page and line

25       number since there are several sets of testimony that

FLORIDA PUBLIC SERVICE COMMISSION

1576

1       were filed?

2                 MR. DAVIS:  I can -- I don't have -- well, I

3       can do that.  It'll take me a minute to do that.  I have

4       a quote from it.

5                 CHAIRMAN ARGENZIANO:  We have time.  Go right

6       ahead.

7       BY MR. DAVIS:

8            Q.   This is from the May 1st, 2009, testimony.  Do

9       you happen to have that with you?

10            A.   No, I do not.

11                 MR. ROSS:  I'd request that a copy be put in

12       front of the witness if he's going to be asked about it.

13                 CHAIRMAN ARGENZIANO:  Okay.  Let's --

14                 MR. DAVIS:  That'll take a minute.

15                 CHAIRMAN ARGENZIANO:  Okay.

16       BY MR. DAVIS:

17            Q.   But without having to do that, let me just ask

18       a question.  Are you saying that you did not provide an

19       opinion that the costs FPL was seeking to recover in

20       that proceeding were reasonable?

21            A.   I did offer that opinion.  Of course that's

22       with regard to the costs incurred in 2008 that are filed

23       for recovery in 2009.

24            Q.   Are you saying you did not provide any opinion

25       about the cost estimates for the project?

FLORIDA PUBLIC SERVICE COMMISSION

1577

1            A.   That's my belief, yes.

2            Q.   Okay.  Now were you provided, as part of your

3       preparation for your testimony at the hearing on

4       September 8th, 2009, information about the July 25th,

5       2009, cost forecasts that FP&L had with the ESC?

6            A.   That's a fair question.  No.  We did not see

7       any of the information relating to the June, July or

8       August ESC meetings until after the hearing, until in

9       fact we were preparing for this year's case.

10            Q.   So by the time you took the stand, the

11       information you presented was out of date, was it not?

12            A.   I don't think so.  I didn't present any

13       information with regard to a cost estimate.

14            Q.   That would have been important to your

15       opinion, however.

16            A.   I'm not sure it would.  Would you direct me to

17       an opinion expressed in that testimony?  And I would

18       agree with you that that information I would like to

19       have had before I took the stand.  I don't think it

20       relates to any opinion that I offered in either the

21       March or the May testimony.

22            Q.   Does it relate to your opinion that the, that

23       FP&L followed proper procedures and processes in

24       arriving at their cost estimates?

25            A.   I don't even recall offering that opinion in

FLORIDA PUBLIC SERVICE COMMISSION

1578

1       March or May.  So I'd have to see the document to answer

2       that question.

3                 I will say that apart from the actual cost

4       estimate, we have raised concerns in our report with

5       regard to compliance with procedures, policies and

6       instructions.  Had I known that in September of 2009

7       when the hearing occurred, I would have raised it.  We

8       obviously became aware of that afterwards and we did

9       raise it.

10            Q.   Now you also presented testimony in 2009 about

11       the Turkey Point 6 and 7 costs as well?

12            A.   That's correct.

13                 MR. ROSS:  Madam Chairman, I'm going to

14       continue to object.  He's asking about testimony that's

15       not been put in front of the witness, it's a year old,

16       and it should be put in front of the witness.

17                 MR. DAVIS:  He can remember the subject of his

18       testimony.

19                 MR. ROSS:  I object.  He's asking specific

20       opinions, specific questions about specific opinions and

21       testimony that's not been put in front of the witness.

22       It's a pretty simple request.

23                 CHAIRMAN ARGENZIANO:  Can we provide a copy?

24                 MR. DAVIS:  It'll take me a while, Madam

25       Chair, to do that, because I thought he could remember

FLORIDA PUBLIC SERVICE COMMISSION

1579

1       the subject matter of his testimony, and I think it's a

2       fair question without having to refer him to it.

3                 MR. YOUNG:  Madam, Madam Chairman?

4                 MR. DAVIS:  I'd call for an opinion on the

5       objection, please.

6                 CHAIRMAN ARGENZIANO:  Okay.

7                 MR. YOUNG:  As relates to providing his

8       testimony, we have part of his testimony and we can get

9       copies of Volume 3.  We have Volume 2, which includes

10       his testimony from last year's proceeding, and we can

11       get Volume 3 for you.

12                 CHAIRMAN ARGENZIANO:  Does that --

13                 MR. DAVIS:  I don't know that we, if he would

14       withdraw the objection, then -- I'm not going to ask

15       specific line-by-line opinions.  It was just a subject

16       matter, and I think the witness probably remembers that

17       question without reference.

18                 MR. ROSS:  I'm not going to withdraw the

19       objection.

20                 CHAIRMAN ARGENZIANO:  You're not going to

21       withdraw.  Let's take the minute, let's make the copies,

22       and we'll move forward.

23                 MR. DAVIS:  That's fine.

24                 CHAIRMAN ARGENZIANO:  Let's take a five-minute

25       break.

FLORIDA PUBLIC SERVICE COMMISSION

1580

1                 MR. DAVIS:  Thank you.

2                 (Recess taken.)

3                 CHAIRMAN ARGENZIANO:  Could I get everyone to

4       take their seats, and let's go first back to where we

5       left off so that Mr. Davis can finish his questions.

6                 And the copies have been provided, and then --

7       BY MR. DAVIS:

8            Q.   Mr. Reed --

9                 CHAIRMAN ARGENZIANO:  Okay.

10       BY MR. DAVIS:

11            Q.   Mr. Reed, do you have the transcript from the

12       2009 cost recovery proceeding in front of you?

13            A.   I have Volume 2.

14            Q.   Okay.  And if you can turn to page 413,

15       please.

16            A.   I have that page.

17            Q.   And that begins your May 1st, 2009, prefiled

18       testimony; correct?

19            A.   Correct.

20            Q.   Okay.  Please turn to page 414.  And starting

21       on line 16, there's a question, "What is the purpose of

22       your testimony in this proceeding?"  And let me just ask

23       a general question.

24                 COMMISSIONER SKOP:  Excuse me.  What --

25                 CHAIRMAN ARGENZIANO:  Commissioner Skop.

FLORIDA PUBLIC SERVICE COMMISSION

1581

1                 COMMISSIONER SKOP:  What Bates number is that

2       on?

3                 CHAIRMAN ARGENZIANO:  358.

4                 COMMISSIONER SKOP:  Okay.  Thank you.

5                 CHAIRMAN ARGENZIANO:  Is that correct?

6                 MR. DAVIS:  This is Volume 2, page 414.

7                 CHAIRMAN ARGENZIANO:  Oh, I'm sorry.  Okay.

8       414.  Thank you.

9                 COMMISSIONER SKOP:  Thank you.

10       BY MR. DAVIS:

11            Q.   Just a general question as you review this,

12       going over to page 415, your testimony in the proceeding

13       that was prefiled on May 1st, 2009, included the Turkey

14       Point 6 and 7 reactor project; correct?

15            A.   Yes.

16            Q.   Okay.  And can you read the, on page 415,

17       starting on line 2, the last sentence of that paragraph?

18            A.   The last sentence reads, "The purpose of my

19       testimony is to present and summarize Concentric's

20       findings with respect to FPL's system of internal

21       control and how compliance with this detailed system of

22       internal control has resulted in reasonable costs and

23       projections of the company's expenditures for 2009 and

24       2010."

25            Q.   And does that sentence refer to both the EPU

FLORIDA PUBLIC SERVICE COMMISSION

1582

1       projects as well as Turkey Point 6 and 7?

2            A.   Yes.

3            Q.   Okay.  So you, for Turkey Point 6 and 7 you

4       were also looking at whether or not costs and

5       projections were reasonable for 2009 and 2010; correct?

6            A.   For those two years, that's correct.

7            Q.   Okay.  And do you know if you were provided

8       all the information from FP&L that would have informed

9       your opinion about that subject for Turkey Point 6 and 7

10       prior to your testimony on September 8th, 2009?

11            A.   Yes, I believe I was.  None of the information

12       that we have since gained access to relates to Turkey

13       Point 6 and 7.

14            Q.   Were there any employee letters or complaints

15       or other information provided about improper cost

16       estimates for Turkey Point 6 and 7?

17            A.   None that I am aware of.  I asked that

18       question, and the answer we received was there are no

19       other letters.

20            Q.   Okay.  Was your review of Turkey Point 6 and 7

21       costs in 2009 as thorough as your review of the EPU

22       costs?

23            A.   I would say that our review of Turkey Point 6

24       and 7 was probably more comprehensive than our review of

25       the EPU costs.

FLORIDA PUBLIC SERVICE COMMISSION

1583

1            Q.   I didn't ask comprehensive.  I said thorough.

2            A.   Same answer.

3            Q.   Okay.

4            A.   Probably more thorough.  Our focus was not on

5       the cost of completion for the EPU.  We did do a

6       broader, more thorough review of the costs estimate for

7       Turkey Point 6 and 7.

8            Q.   And as you sit here, are you confident that

9       FP&L provided you with all the information you needed to

10       arrive at your opinion in 2009?

11            A.   With regard to the cost for Turkey Point 6 and

12       7?

13            Q.   Correct.

14            A.   Yes.  I have no concerns with regard to the

15       adequacy or completeness of that information.

16            Q.   And as we sit here, was your -- I'll ask you

17       the same question about your 2010 testimony.  We're not

18       going to go into any details about that at this point,

19       but you've also provided testimony for this proceeding

20       in 2010 concerning the reasonableness of costs of Turkey

21       Point 6 and 7; correct?

22            A.   Yes.

23            Q.   And do you know if FP&L has withheld any

24       information from you that you would need to provide that

25       opinion?

FLORIDA PUBLIC SERVICE COMMISSION

1584

1            A.   I am satisfied that we have had access to all

2       of the information we need to express that opinion.

3            Q.   And how have you satisfied yourself for that,

4       with regard to Turkey Point 6 and 7?

5            A.   We have asked very detailed data requests of

6       FPL, we have made sure that those requests are complied

7       with, and we have reviewed all the information.  Nothing

8       has been withheld, and we have followed up to make sure

9       there are no other employee letters, investigations or

10       accusations that we should be made aware of.

11            Q.   And with regard to your testimony, have you

12       updated information since you prefiled testimony in this

13       docket in 2010?

14            A.   Yes.

15                 MR. DAVIS:  Okay.  That's all I have right

16       now.

17                 CHAIRMAN ARGENZIANO:  I think what we're going

18       to do -- Commissioner Skop, did you want to ask, did you

19       have questions?

20                 COMMISSIONER SKOP:  I have a few questions for

21       Mr. Reed, but I was going to look to the Chair as to

22       what time we'd break for lunch.  I probably have a few

23       minutes and then I could break it off reasonably quick.

24                 CHAIRMAN ARGENZIANO:  I told the court

25       reporters that we would break for lunch at 1:30 because

FLORIDA PUBLIC SERVICE COMMISSION

1585

1       they have to change out, and if we're going to go late,

2       and I have no idea where we're going to go, I think

3       splitting it between 1:00 to 2:00, which they had

4       requested, 1:30 would be fair and give them an

5       opportunity.  So 1:30.  If you would proceed to ask your

6       questions now and then we'll adjust accordingly.

7                 COMMISSIONER SKOP:  All right.  Very well.

8       Thank you.

9                 CHAIRMAN ARGENZIANO:  And then I think

10       Commissioner Edgar has a few questions and then

11       Commissioner Graham wanted to make a comment, and I also

12       have some things that I wanted to ask before we shift

13       gears.  Thank you.

14                 COMMISSIONER SKOP:  Thank you, Madam Chair.

15                 Good afternoon, Mr. Reed.

16                 THE WITNESS:  Good afternoon, Commissioner

17       Skop.

18                 COMMISSIONER SKOP:  I want to thank you for

19       appearing here before the Commission today, and I do

20       greatly appreciate your candor and the direct manner in

21       which you've responded to the questions that have been

22       presented.

23                 THE WITNESS:  Thank you.

24                 COMMISSIONER SKOP:  I guess my first question,

25       have you discussed the testimony that you're, that

FLORIDA PUBLIC SERVICE COMMISSION

1586

1       you're giving here today with any member of FPL's

2       regulatory affairs or legal department since the start

3       of this proceeding?

4                 THE WITNESS:  I am sure I've discussed it.

5       I've not been coached or told what to say or anything

6       like that.

7                 COMMISSIONER SKOP:  Could you -- who did you

8       discuss your testimony with?

9                 THE WITNESS:  I've discussed it with Mr. Ross

10       and Mr. Anderson with regard to the logistics of the

11       testimony, should I do a summary, shouldn't I do a

12       summary, that kind of thing.

13                 COMMISSIONER SKOP:  All right.  Mr. Silagy or

14       Mr. Hoffman?

15                 THE WITNESS:  Yes.  I've had discussions with

16       both of them about my testimony, as well as the case as

17       a whole.

18                 COMMISSIONER SKOP:  Okay.  All right.  In

19       relation to Mr. Kundalkar's testimony, which was given

20       under oath to the Commission on September 8th, 2010.

21                 THE WITNESS:  2009.

22                 COMMISSIONER SKOP:  Excuse me?

23                 THE WITNESS:  2009.

24                 COMMISSIONER SKOP:  I'm sorry.  Thank you for

25       that correction.  Okay.  Let me reframe that question.

FLORIDA PUBLIC SERVICE COMMISSION

1587

1                 In relation to Mr. Kundalkar's testimony which

2       was given under oath to the Commission on September 8th,

3       2009, Concentric concluded, based on its investigation,

4       that a $300 million or 27 percent increase in the

5       projected cost of the EPU project should have been

6       discussed in the live testimony that was given on

7       September 8th, 2009; correct?

8                 THE WITNESS:  Yes.

9                 COMMISSIONER SKOP:  Okay.  Now with respect to

10       your testimony in response to my question and

11       Mr. Moyle's question, you characterized in your lay

12       opinion that the testimony given by Mr. Kundalkar during

13       his appearance under oath before the Commission on

14       September 8th, 2009, was inaccurate and incomplete on

15       the basis that he did not amend his testimony; is that

16       correct?

17                 THE WITNESS:  Yes, I did say that.

18                 COMMISSIONER SKOP:  Okay.  All right.  If I

19       could turn your attention to the, what has been marked

20       for identification as Exhibit Number 243, please.

21                 THE WITNESS:  I have that.

22                 COMMISSIONER SKOP:  Okay.  And on page 7 of

23       that document, at the bottom of the page.  My -- I would

24       give you the Bates stamp number, but my Bates stamp on

25       that page is cut off.  I believe it would be, subject to

FLORIDA PUBLIC SERVICE COMMISSION

1588

1       check, FPL 152907.

2                 THE WITNESS:  I think I have the page.

3                 COMMISSIONER SKOP:  Okay.  And do you see the

4       second paragraph on that page?

5                 THE WITNESS:  Yes.

6                 COMMISSIONER SKOP:  Okay.  And the second

7       sentence that begins with the EC, the ESC, can you read

8       that sentence, please?

9                 THE WITNESS:  Yes.  It says, "The ESC is

10       charged with corporate governance of the EPU project and

11       includes FPL's President, Chief Nuclear Officer, Chief

12       Financial Officer, FPL Group's President, and several

13       others."

14                 COMMISSIONER SKOP:  All right.  Thank you.

15       And at the bottom of that page there's discussion about

16       the July 2009 EC -- ESC presentations, and also the

17       line-by-line cost review that was prepared for those

18       projects; is that correct?

19                 THE WITNESS:  That's correct.

20                 COMMISSIONER SKOP:  Okay.  And concurrently

21       there was a decision to replace the EPU senior

22       management, or the decision was, to replace the EPU

23       senior management team was made.  Do you see that?

24                 THE WITNESS:  I see that statement, yes.

25                 COMMISSIONER SKOP:  Okay.  All right.  If I

FLORIDA PUBLIC SERVICE COMMISSION

1589

1       could now turn your attention to that same document,

2       Bates page 152930, please.

3                 THE WITNESS:  Can you tell me what page of the

4       report that is?

5                 COMMISSIONER SKOP:  It's probably Exhibit 5,

6       page 1 of 2.  That's the documents relied upon.

7                 THE WITNESS:  Yes, I have that.

8                 COMMISSIONER SKOP:  Okay.  And that page

9       reflects the documents that you and Concentric relied

10       upon in preparing your report; is that correct?

11                 THE WITNESS:  That's correct.

12                 COMMISSIONER SKOP:  All right.  Now do you see

13       what's been marked on that page as item 31?

14                 THE WITNESS:  Yes.

15                 COMMISSIONER SKOP:  Okay.  And can you read

16       that for us, please?

17                 THE WITNESS:  It says, "Meeting request for

18       EPU Saturday session July 25th, 2009, 8:00 a.m. to 3:30

19       p.m."

20                 COMMISSIONER SKOP:  All right.  Thank you.

21       And with respect to that meeting was held, I'm sure you

22       reviewed, or did you review the meeting request document

23       and the list of attendees for that meeting?

24                 THE WITNESS:  It listed invitees to the

25       meeting, yes.

FLORIDA PUBLIC SERVICE COMMISSION

1590

1                 COMMISSIONER SKOP:  Okay.

2                 THE WITNESS:  I did review it.

3                 COMMISSIONER SKOP:  Do you have personal

4       knowledge of who attended that meeting?

5                 THE WITNESS:  I don't have personal knowledge

6       in the sense of I wasn't there, but I did ask that

7       question of many of our interviewees.

8                 COMMISSIONER SKOP:  Okay.  All right.  To the

9       best of your ability in that regard, do you know if

10       Mr. Kundalkar attended that meeting that was held on

11       July 29th, 2009 -- or, I mean, July 25th, 2009?

12                 THE WITNESS:  It is my understanding that

13       Mr. Kundalkar did attend the meeting.

14                 COMMISSIONER SKOP:  Okay.  Is it your

15       understanding that Mr. Olivera attended that meeting?

16                 THE WITNESS:  It is my understanding that

17       Mr. Olivera attended the meeting as well.

18                 COMMISSIONER SKOP:  Okay.  Is it also your

19       understanding that one or more members of the FPL Group

20       executive management team attended that meeting?

21                 THE WITNESS:  Yes.

22                 COMMISSIONER SKOP:  Okay.  And that would

23       include -- to the best of your ability, did that include

24       the Chief Operating Officer of FPL Group?

25                 THE WITNESS:  Yes.  Mr. Robo, I believe, has

FLORIDA PUBLIC SERVICE COMMISSION

1591

1       that title, and it is my understanding he attended the

2       meeting as well.

3                 COMMISSIONER SKOP:  Do you know if Mr. Hay

4       attended that meeting?

5                 THE WITNESS:  I do not believe he did.

6                 COMMISSIONER SKOP:  Okay.  Do you know if

7       Mr. Silagy attended that meeting?

8                 THE WITNESS:  I don't know.

9                 COMMISSIONER SKOP:  Okay.  All right.  Thank

10       you.

11                 With respect to the discussion that was held

12       in your testimony about inaccurate and incomplete

13       information being provided to the Commission, you

14       mentioned out-of-date information was provided that was

15       not the best available at the time.  The, it is true to

16       the best of your opinion, is it not, that there was a

17       line-by-line project review of the EPUs conducted by the

18       Executive Steering Committee on July 25th, 2009; is that

19       correct?

20                 THE WITNESS:  Yes.  Just a slight

21       clarification.  The line-by-line review of the project

22       cost estimate was prepared by the EPU project team,

23       primarily the project controls group, and it was

24       presented to the steering committee on July 25th.

25                 COMMISSIONER SKOP:  Okay.  But at that

FLORIDA PUBLIC SERVICE COMMISSION

1592

1       steering committee meeting, as you've previously

2       testified, there were FPL, Florida Power & Light

3       executives in attendance as well as Mr. Kundalkar, or I

4       may be mispronouncing his name, as well as executive

5       officers from FPL Group in attendance for that review;

6       is that correct?

7                 THE WITNESS:  That is my understanding.

8                 COMMISSIONER SKOP:  Okay.  All right.  So I

9       guess what, what, you know, is concerning me is that

10       there are, I guess in your opinion there were a lot of

11       executive managers not only at the regulated utility

12       level but also at the corporate parent group that were

13       aware of the cost estimates that were being reviewed at

14       that meeting; is that correct?

15                 THE WITNESS:  That's correct.

16                 COMMISSIONER SKOP:  Okay.  So is it fair to

17       say that on July 25th, 2009, with the line-by-line

18       presentation that was given as a result of your

19       investigation, that there were indicators that clearly

20       indicated the magnitude of the cost estimate for the EPU

21       had increased significantly?  I'm not talking about the

22       actual number, what the final number would be.  I'm

23       talking about indicators that there was substantial cost

24       escalation in terms of the EPU.

25                 THE WITNESS:  I would say yes.  There were

FLORIDA PUBLIC SERVICE COMMISSION

1593

1       indicators of substantial cost escalation with regard to

2       the 2008 estimate with regard to the EPU cost forecast.

3       There was considerable uncertainty, but there were

4       certainly indicators that, based upon the current scope,

5       costs were going up substantially.

6                 COMMISSIONER SKOP:  Okay.  And that seems to

7       be my focus of concern as you spoke to the need for

8       regulators to have accurate and truthful information.

9       It seems as if on the July 25th meeting there was

10       substantial discussion and knowledge across both

11       organizations that the magnitude of the cost estimate

12       had increased.  And that's, that's the point I'm trying

13       to hit home on here.

14                 Let's talk for a second about project controls

15       and the adequacy thereof.  When did you -- you gave

16       testimony in last year's NCRC proceeding; is that

17       correct?

18                 THE WITNESS:  That's correct.

19                 COMMISSIONER SKOP:  And you're testifying here

20       today; is that correct?

21                 THE WITNESS:  Yes.

22                 COMMISSIONER SKOP:  Okay.  Did you, in

23       conducting or preparing your testimony, both your

24       prefiled and the amendments to your testimony, did you

25       conduct an independent review of Florida Power & Light's

FLORIDA PUBLIC SERVICE COMMISSION

1594

1       project controls as they relate to the uprate projects?

2                 THE WITNESS:  Yes.  Were you talking about

3       2009 or 2010 in your question?

4                 COMMISSIONER SKOP:  2010 for the moment.

5                 THE WITNESS:  Yes, I did.

6                 COMMISSIONER SKOP:  Okay.  And when did you

7       complete that review?

8                 THE WITNESS:  Our review really was completed

9       with the presentation of our final report on this

10       matter.  The issues were discussed in my March prefiled

11       direct testimony and in my May prefiled direct

12       testimony.  But as indicated there, that testimony

13       really needed to be amended with the results of the

14       investigation.

15                 COMMISSIONER SKOP:  Okay.  So when you

16       performed your initial investigation, the final

17       Concentric report as it related to the information flow

18       to the PSC and other aspects was not yet complete; is

19       that correct?

20                 THE WITNESS:  That's correct.

21                 COMMISSIONER SKOP:  Okay.  Let's go to your

22       prior testimony given in 2009 for a moment.  And, again,

23       I'm not asking this to be inflammatory.  I'm asking this

24       just as a straightforward question.

25                 You also prepared and gave testimony on, as to

FLORIDA PUBLIC SERVICE COMMISSION

1595

1       the adequacy of project controls for the 2009 NCRC

2       proceedings; is that correct?

3                 THE WITNESS:  Yes, I did.

4                 COMMISSIONER SKOP:  Okay.  Now nowhere in your

5       review until such time as you were retained by Florida

6       Power & Light's legal department to conduct a review of

7       the employee letter were you aware of the July 25th,

8       2009, meeting; is that correct?

9                 THE WITNESS:  That's correct.  And let me

10       address that issue briefly.

11                 That speaks to a structural issue that's

12       addressed in one of our recommendations.  In prior

13       years, the structure of the NCRC presentation by FPL has

14       been one in which we came in, or I should say the

15       presentation by us of the project controls work, is we

16       came in in December of the prior year, reviewed all of

17       the documents, interviewed people, and then essentially

18       wrapped up our testimony in March and May.  So the

19       document review in 2009 ended with documents that were

20       in existence as of the date of the submission of the

21       testimony, which was, I think, May 1st of 2009.

22                 Documents after that were considered to be

23       part of the next year's cycle.  We have addressed that

24       with the recommendation here that that no longer be the

25       case, that the annual cycle beginning and ending May 1st

FLORIDA PUBLIC SERVICE COMMISSION

1596

1       should not be the essentially limits of the documents

2       reviewed in a given year.  It's no longer the limit that

3       we use, and we recommend that the company make available

4       information to staff on a more current basis as well so

5       that we don't have this situation where documents can be

6       created between May 1st and the hearing that we don't

7       know about.

8                 COMMISSIONER SKOP:  Okay.  And thank you.  And

9       so but for the employee letter and the resulting

10       independent investigation that you were, Concentric was

11       retained to perform and the conclusions of that

12       investigation, you would not have known about the

13       inaccurate and incomplete information that was

14       previously furnished to the Florida Public Service

15       Commission on September 8th, 2009; is that correct?

16                 THE WITNESS:  I can't say that completely.  We

17       would have had access to the July, for example, 25th

18       presentation to the steering committee as part of our

19       2010 cycle anyway.  I will say that I think the employee

20       letter has been helpful in bringing up issues that has

21       caused us to dig deeper and look at some of the project

22       controls issues, and I think it's helped to develop

23       recommendations that'll be beneficial going forward.

24       But the information would have been part of the 2010

25       cycle anyway.

FLORIDA PUBLIC SERVICE COMMISSION

1597

1                 COMMISSIONER SKOP:  Okay.  I guess what I was

2       trying to get at in terms of, you know, evaluating the

3       adequacy of the project controls that exist and the

4       information flow, you know, certainly the employee

5       letter was beneficial because it prompted the

6       investigation and the outcome thereof.  But you're

7       saying that, if I heard your testimony correctly, that

8       you would have seen the, some information in terms of

9       the projections in the 2010 cycle.  But would that have

10       necessarily allowed this open, candid discussion to have

11       taken place in and of itself?

12                 THE WITNESS:  I think the employee letter was

13       helpful in focusing on this issue.

14                 COMMISSIONER SKOP:  Okay.  All right.

15                 THE WITNESS:  I'll stop there.

16                 ***REPORTER'S NOTE:  CONFIDENTIAL PORTION OF

17       TRANSCRIPT REDACTED.***

18                 COMMISSIONER SKOP:  Okay.  Thank you.

19                 MR. ROSS:  Madam Chairman, in Mr. Skop's

20       question, he linked the name of the employee with a

21       personnel matter.  That's confidential, has been ruled

22       to be confidential in this proceeding.  It did not, his

23       question did not deal with the testimony, which is

24       public, and we understand that.  So I would move that

25       the link of the name with the personnel matters be

FLORIDA PUBLIC SERVICE COMMISSION

1598

1       stricken.

2                 COMMISSIONER SKOP:  Just to prevent it, I'll

3       move to -- I apologize if there was an inadvertent link.

4       I'll move to strike my entire question and response, if

5       that would be acceptable to the company.

6                 MR. ROSS:  And that's fine.  Thank you.

7                 COMMISSIONER SKOP:  All right.

8                 CHAIRMAN ARGENZIANO:  So moved.

9                 COMMISSIONER SKOP:  And if it was done, it was

10       inadvertent.

11                 Mr. Reed, I want to turn your attention to a

12       recent management decision that was made by FPL

13       regarding FPL's request to withdraw the LAR for the

14       St. Lucie 1 nuclear plant on the EPU.  Are you aware of

15       FPL's request regarding that withdrawal?

16                 THE WITNESS:  Yes.

17                 COMMISSIONER SKOP:  Okay.  When were you made

18       aware that FPL would be doing that?

19                 THE WITNESS:  I was first made aware of the

20       issue on August 10th, Tuesday morning.  And that was

21       with regard to the fact that the NRC staff was not

22       likely to approve the, or accept, I should say, not

23       approve, but accept the LAR application as submitted.  I

24       then actually didn't become aware of the decision to

25       implement the withdrawal of the application until that

FLORIDA PUBLIC SERVICE COMMISSION

1599

1       letter was posted on the NRC website.

2                 COMMISSIONER SKOP:  Okay.  With respect to

3       that decision, would you consider the decision to

4       withdraw the application for LAR to be a material event

5       as it relates to the EPU projects?

6                 MR. ROSS:  I would object.  I'm not sure what

7       is being meant by the term "material event."  If there's

8       some definition around it or it can be asked without a

9       legal, without a legal overtone to it.

10                 COMMISSIONER SKOP:  I can refrain.  But,

11       again, I was just asking for his lay opinion whether

12       he -- I mean, he had previously testified in relation to

13       Mr. Moyle's question whether he thought the cost

14       estimate amount of $300 million and 27 percent was

15       material, and he indicated that, yes, it was.  So I

16       don't --

17                 CHAIRMAN ARGENZIANO:  Okay.  To the objection.

18                 COMMISSIONER SKOP:  To the objection, I will

19       try to reframe to avoid the objection.

20                 Mr. Reed, in relation to the FPL request to

21       withdraw the LAR for the St. Lucie 1 EPU, the letter to

22       the NRC, and as it relates to the flow of information to

23       the PSC and project controls, in your opinion should FPL

24       have informed this Commission of that withdrawal or

25       request to withdraw as soon -- contemporaneously with

FLORIDA PUBLIC SERVICE COMMISSION

1600

1       and at the same day that it informed the NRC?

2                 THE WITNESS:  Commissioner Skop, I don't

3       really have an opinion with regard to the timeliness

4       there.  Do I think it's a relevant piece of information?

5       Yes.  I have no doubt that it was going to come before

6       this Commission in this proceeding.  But I don't have an

7       opinion as to the timing.

8                 COMMISSIONER SKOP:  Okay.  And how -- you, you

9       just opined that it would come before the Commission in

10       this proceeding.  Certainly you would agree that it was

11       not disclosed by FPL until such time as Commission

12       staff, to the best of your knowledge, put it in our

13       docket file; is that correct?

14                 THE WITNESS:  My understanding of the sequence

15       is the company's letter came in after the Commission

16       staff posted the document to the website.  But as I

17       said, I have no doubt the information was going to come

18       in.

19                 COMMISSIONER SKOP:  Well, I think the

20       timeliness of the information provided to the

21       Commission, as you testified, it's important that the

22       Commission have timely information, not information that

23       is ten days dated less than 24 hours before the

24       commencement of this proceeding; is that correct?

25                 THE WITNESS:  I agree that having timely

FLORIDA PUBLIC SERVICE COMMISSION

1601

1       information is important.  But, again, I don't have an

2       opinion about the obligation or appropriateness of the

3       timing on this particular letter.

4                 COMMISSIONER SKOP:  Okay.  And just I believe

5       a few more questions.  I think many of my concerns have,

6       have been covered by staff and Mr. Moyle and some of the

7       Intervenors and some of the other questions that I've

8       asked.

9                 In your testimony and in response to

10       Mr. Moyle's question, you indicated that, I believe, and

11       correct me if I'm wrong, the regulatory compact requires

12       that utilities provide accurate and truthful information

13       to the Commission; is that correct?

14                 THE WITNESS:  My earlier answer was I don't

15       think it really goes to the regulatory compact, but I do

16       believe that regulators are entitled to that

17       information.

18                 COMMISSIONER SKOP:  Okay.  Regulators are

19       entitled to accurate and truthful information; is that

20       correct?

21                 THE WITNESS:  Yes.

22                 COMMISSIONER SKOP:  Okay.  And failure to

23       provide -- in your opinion, would failure to provide

24       accurate and truthful information to the Commission

25       reflect upon the credibility of the provider?

FLORIDA PUBLIC SERVICE COMMISSION

1602

1                 THE WITNESS:  It could, depending on the

2       circumstances.

3                 COMMISSIONER SKOP:  Okay.  But certainly you

4       would agree, would you not, that the accuracy and

5       timeliness of information provided to this Commission is

6       of significance, significant importance?

7                 THE WITNESS:  You said accuracy and

8       timeliness?

9                 COMMISSIONER SKOP:  Yes.  Accuracy and

10       timeliness of information provided to this Commission by

11       regulated entities of significant importance.

12                 THE WITNESS:  Yes.  I believe that's

13       important.

14                 COMMISSIONER SKOP:  Okay.  And in terms of

15       ultimate responsibility at the corporate level, who is

16       accountable to ensure in your opinion that that

17       information is provided in a timely and accurate manner?

18                 THE WITNESS:  In my view, it is first and

19       foremost the responsibility of each witness.  And I

20       think, again, those steps have been appropriately taken

21       with regard to the 2010 proceeding.

22                 From a corporate governance perspective,

23       again, it's difficult to say because span of control and

24       management of activities differs within each company.

25       You know, some people would say with the CEO the buck

FLORIDA PUBLIC SERVICE COMMISSION

1603

1       stops there.  I'm CEO of a company, I used to be the CEO

2       of a publicly traded company on the New York Stock

3       Exchange.  I understand that view.  But obviously CEOs

4       don't manage every aspect of every management function

5       and activity.

6                 COMMISSIONER SKOP:  Okay.  And thank you.  I

7       think that that'll give me the basis for my last

8       question.

9                 Given your experience as a former CEO of

10       publicly traded company, I think former, if not

11       currently; right?

12                 THE WITNESS:  Correct.

13                 COMMISSIONER SKOP:  Okay.  Given your

14       experience as a former CEO of a publicly traded company,

15       and noting that the truthfulness, accuracy and veracity

16       of information provided to this Commission was at issue

17       in this proceeding, if you were CEO or President, would

18       you make yourself available to field questions

19       regarding, that the Commission may have in that regard?

20                 THE WITNESS:  I don't have an opinion with

21       regard to the facts here.  Again, I think that's an

22       issue that's always going to be addressed by the CEO's

23       staff, and I would turn to my staff for guidance on

24       that.

25                 COMMISSIONER SKOP:  All right.  Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

1604

1       Madam Chair, I don't believe I have any additional

2       questions at this time.

3                 CHAIRMAN ARGENZIANO:  Okay.  I know, we're

4       still in question mode, so I know Commissioner Edgar had

5       some questions.  You're recognized, Commissioner Edgar.

6                 COMMISSIONER EDGAR:  Thank you.  Just a couple

7       of brief questions.

8                 Switching gears a little bit, I think, but

9       still with the background generally of the report that

10       we have been discussing that we've been kind of

11       referring to as the Concentric report, what is your

12       obligation as CEO of Concentric to provide independent

13       reports to your clients?

14                 THE WITNESS:  We do so when asked.  We have

15       done so before on similar matters.  So I don't think I

16       would describe it as an obligation.  It's a service we

17       provide when asked.

18                 And, again, in this case, obviously FPL's

19       activities in commencing the investigation were

20       voluntary.  They chose to undertake the investigation.

21       They appropriately did so and, again, I commend them for

22       that.

23                 COMMISSIONER EDGAR:  Do you believe that the

24       report that, that is before us, before us as a part of

25       this proceeding represents Concentric's independent

FLORIDA PUBLIC SERVICE COMMISSION

1605

1       assessment and conclusions?

2                 THE WITNESS:  Yes.  Every word, every

3       sentence, every paragraph is ours, and we stand behind

4       it.

5                 COMMISSIONER EDGAR:  And along that same line,

6       who made the final determination as to what edits from

7       FPL were included in the final report?

8                 THE WITNESS:  Me.  I'm the only person that

9       had the approval authority for any change in the report.

10                 COMMISSIONER EDGAR:  Thank you.

11                 CHAIRMAN ARGENZIANO:  Commissioner Skop for a

12       question.

13                 COMMISSIONER SKOP:  Yes.  I had probably about

14       three more brief questions and hopefully I will be done.

15                 CHAIRMAN ARGENZIANO:  Okay.  I've got one

16       question at one point.

17                 COMMISSIONER SKOP:  Okay.  I'll yield.

18                 CHAIRMAN ARGENZIANO:  No.  You go, you go

19       ahead and then I'm going to ask questions, I'm going to

20       ask for any other questions after that and then we'll

21       proceed.  Go ahead.

22                 COMMISSIONER SKOP:  Okay.  Mr. Reed, on -- if

23       I could ask you to turn to page 24 of what has been

24       identified as the staff audit report for Florida Power &

25       Light Company, and I need to -- I believe it's

FLORIDA PUBLIC SERVICE COMMISSION

1606

1       Exhibit 178.  Yes.  Okay.  So it's been marked for

2       identification as Exhibit 178, and it's the staff audit

3       report for Florida Power & Light related to the nuclear

4       projects.

5                 THE WITNESS:  I'll ask someone to provide me

6       with a copy, if they can.

7                 CHAIRMAN ARGENZIANO:  Okay.  Let's give a

8       moment and make sure we get a copy to Mr. Reed.

9                 COMMISSIONER EDGAR:  And could you mention the

10       page number again that you're pointing us to?

11                 COMMISSIONER SKOP:  It's page 24.

12                 COMMISSIONER EDGAR:  Thank you.

13                 CHAIRMAN ARGENZIANO:  24.

14                 THE WITNESS:  Thank you.  I have Exhibit 178,

15       page 24.

16                 COMMISSIONER SKOP:  Okay.  And if I can draw

17       your attention to the paragraph that's entitled Removal

18       of the EPU Senior Management Team.

19                 THE WITNESS:  I see that.

20                 COMMISSIONER SKOP:  Okay.  And do you see the

21       sentence at the bottom of that first paragraph with the

22       footnote?

23                 THE WITNESS:  Yes.

24                 COMMISSIONER SKOP:  Okay.  And basically the

25       indented text on that page refers to data that was

FLORIDA PUBLIC SERVICE COMMISSION

1607

1       provided in an FPL response to a staff data request; is

2       that correct?

3                 THE WITNESS:  Yes.

4                 COMMISSIONER SKOP:  Okay.  And can you read

5       the indented portion of that text, please?

6                 THE WITNESS:  That text reads, "Both

7       previously assigned VP level managers were no longer

8       involved in the EPU project because FPL Group senior

9       management decided that changes to these leadership

10       positions would enhance FPL's ability to bring the EPU

11       projects to successful completion, promote effective

12       succession planning and talent utilization, and improve

13       the quality and timeliness of forecasted project costs."

14                 COMMISSIONER SKOP:  Okay.  So in that it --

15       the timeliness is mentioned in that paragraph; is that

16       correct?

17                 THE WITNESS:  Yes.

18                 COMMISSIONER SKOP:  Okay.  Do you have any

19       knowledge as to why FPL Group senior management would be

20       involved in a Florida Power & Light personnel decision?

21                 THE WITNESS:  I can't answer that from a

22       generic perspective.  I can answer it with regard to

23       this decision, and it is my understanding that FPL Group

24       senior management was involved because they are involved

25       in and essentially chair the ESC.

FLORIDA PUBLIC SERVICE COMMISSION

1608

1                 COMMISSIONER SKOP:  Okay.  So, and then that

2       gets back to the point of the EC -- ESC meeting that was

3       held on July 25th, 2009, FPL Group senior management was

4       involved in that meeting, were they not?

5                 THE WITNESS:  Yes.

6                 COMMISSIONER SKOP:  Okay.  All right.  I want

7       to go on to two follow-up questions that deal with

8       revisions to the Concentric report.  And let me have a

9       moment and I'll get to the right Bates page.

10                 MS. BENNETT:  Madam Chairman, while

11       Commissioner Skop is looking for that, I just wanted to

12       let you know that I had handed out a data request

13       response from FPL that Commissioner Skop had asked for.

14       It's on your desks.  It's EPU DR 8.9, and it's got a

15       little yellow highlight through it.  I just wanted to

16       let you know that is a confidential document.  The

17       attorneys can address it.  There's parts of it that

18       aren't.

19                 CHAIRMAN ARGENZIANO:  Okay.  Thank you.

20                 MR. ROSS:  Madam Chairman, with respect to

21       this data request 8.9, I think that most of these issues

22       now have been discussed in the hearing, so we will

23       withdraw our claim of confidentiality for this

24       particular data request.

25                 CHAIRMAN ARGENZIANO:  Okay.  And that is

FLORIDA PUBLIC SERVICE COMMISSION

1609

1       withdrawn.  Thank you.

2                 COMMISSIONER SKOP:  Madam Chair, I just need a

3       few moments.

4                 Okay.  Mr. Reed, I'd ask you to turn to

5       confidential document 06790-10, which is POD 29 at Bates

6       page 153197.

7                 CHAIRMAN ARGENZIANO:  That's a lot of numbers.

8       Let's make sure everybody has got it.

9                 COMMISSIONER SKOP:  That's the big stack of

10       documents we had last --

11                 CHAIRMAN ARGENZIANO:  Okay.

12                 THE WITNESS:  I'm sorry.  The 153, what was

13       the --

14                 CHAIRMAN ARGENZIANO:  Let's repeat them

15       slowly.

16                 COMMISSIONER SKOP:  Yes.  153197.

17                 THE WITNESS:  I have that.

18                 COMMISSIONER SKOP:  Okay.  With respect -- and

19       if I could draw your attention to the comment on that

20       page.

21                 THE WITNESS:  I see that.

22                 COMMISSIONER SKOP:  Okay.  And was that --

23       who, who, without giving up any confidential

24       information, inserted that comment?

25                 THE WITNESS:  One of my staff members working

FLORIDA PUBLIC SERVICE COMMISSION

1610

1       on the investigation.

2                 COMMISSIONER SKOP:  Okay.

3                 THE WITNESS:  His name is in footnote 2 on

4       that page.

5                 COMMISSIONER SKOP:  Okay.  All right.  Thank

6       you.  And if I could ask you to move forward to, on that

7       same document to what has been marked as Bates page FPL

8       153212.

9                 THE WITNESS:  I see that.

10                 COMMISSIONER SKOP:  Okay.  Is there any

11       significance in that comment?

12                 THE WITNESS:  Well, I think there's probably

13       significance in all comments.  But I don't take any

14       particular significance there.  It was a comment about a

15       question that we should expect on the words that are

16       there.

17                 COMMISSIONER SKOP:  Okay.  All right.  With

18       respect to the revisions of the Concentric, draft

19       Concentric report -- I mean, excuse me.  With respect to

20       the draft Concentric reports and the revisions thereof,

21       were there any members of the Executive Steering

22       Committee that reviewed those drafts and provided

23       comments?

24                 THE WITNESS:  I don't know the answer to that.

25       I did not receive comments from any member of the

FLORIDA PUBLIC SERVICE COMMISSION

1611

1       Executive Steering Committee.  Whether they were

2       received internally within FPL, I don't know.  But none

3       came to me.

4                 COMMISSIONER SKOP:  Did any comments from

5       members of the Executive Steering Committee come to any

6       other members of Concentric staff to your knowledge?

7                 THE WITNESS:  No.  Nothing from the ESC in

8       terms of comments came to our firm.

9                 COMMISSIONER SKOP:  Okay.  As a -- in the

10       course of your investigation, did you discuss the

11       employee allegations or interview members of the

12       Executive Steering Committee in preparation of your

13       report?

14                 THE WITNESS:  No.  No.  We did not interview

15       any, what I would call member of the Executive Steering

16       Committee.

17                 And let's clarify this.  Again, I don't think

18       there is a roster of who's a member versus who's a

19       presenter.  We did interview an individual who attends

20       all of the ESC meetings.

21                 COMMISSIONER SKOP:  Okay.

22                 THE WITNESS:  Whether he's a member of the

23       committee or a presenter is, I suppose, a point of

24       clarity.

25                 COMMISSIONER SKOP:  Well, let me be more

FLORIDA PUBLIC SERVICE COMMISSION

1612

1       specific again.  Again, I'm trying to just ask probably

2       generically and I probably should be more specific.

3                 As a result of the employee letter and

4       resulting investigation, did you interview Mr. Olivera?

5                 THE WITNESS:  No, not for that purpose.

6                 COMMISSIONER SKOP:  Okay.  All right.  Is

7       there a reason why?

8                 THE WITNESS:  I didn't feel it was necessary.

9                 COMMISSIONER SKOP:  Okay.  All right.  As part

10       of your investigation, did you interview Mr. Robo?

11                 THE WITNESS:  No.  The same answer.  We had

12       some issues that came up with regard to ESC member

13       participation, and we were able to address all of our

14       questions with documents.  Therefore, we did not need to

15       go to do interviews with them.

16                 COMMISSIONER SKOP:  Okay.  Madam Chair, I

17       believe I just have one final question.  And I need to

18       find the page, so bear with me for one second.

19                 (Pause.)

20                 If I could turn your attention now, Mr. Reed,

21       to what has been marked for identification as Exhibit

22       Number 243.

23                 THE WITNESS:  I have that.

24                 COMMISSIONER SKOP:  Okay.  And on Exhibit 8 in

25       that document, page 8 of 8.

FLORIDA PUBLIC SERVICE COMMISSION

1613

1                 THE WITNESS:  This is the chronology.  Yes, I

2       have that.

3                 COMMISSIONER SKOP:  Okay.  And if I could just

4       now ask you to look at what is a confidential document.

5       It is Document Number 06789-10, and it is the response

6       to Interrogatory Number 24.

7                 THE WITNESS:  Yes, I have that.

8                 COMMISSIONER SKOP:  Okay.  And I just need to

9       look at one additional thing before I ask my question.

10       Do you see the response that was given by FPL to the

11       staff interrogatory?

12                 THE WITNESS:  Yes.

13                 COMMISSIONER SKOP:  Okay.  In relation to whom

14       the letter was provided to?

15                 THE WITNESS:  Yes.

16                 COMMISSIONER SKOP:  Okay.  As a result of the

17       existence of the employee letter and the conclusions of

18       the Concentric report, do you know whether the

19       Concentric findings were ever provided back to the

20       entity identified in the first line of the response to

21       that interrogatory?

22                 THE WITNESS:  I don't know for sure.  I have

23       no understanding that they did receive it.  My

24       understanding is their involvement in this matter ended

25       with their response.

FLORIDA PUBLIC SERVICE COMMISSION

1614

1                 COMMISSIONER SKOP:  I understand.  And my

2       question goes to the heart of in light of the conclusion

3       and findings as it relates to the veracity of statements

4       given under oath by an FPL witness to the Florida Public

5       Service Commission, my question would be do you know

6       whether that conclusion was ever then provided back to

7       the entity identified in the first line of that

8       interrogatory response?

9                 THE WITNESS:  I don't know.

10                 COMMISSIONER SKOP:  Okay.  Could you offer

11       opinion as to why it might not have?

12                 MR. ROSS:  I'd like to object.  There's no

13       foundation as to this witness's relationship or

14       connection or involvement with the work performed by the

15       entity listed on the first line of the confidential

16       document the Commissioner is referring to.

17                 CHAIRMAN ARGENZIANO:  To the objection.

18                 COMMISSIONER SKOP:  To the objection, Mr. Reed

19       deals with project controls, he deals with the adequacy

20       of project controls, he's testified to the importance of

21       providing accurate and timely information to the

22       Commission.  The matter deals with the veracity of

23       statements made under oath to the Florida Public Service

24       Commission.  Mr. Reed has testified that the testimony

25       in his professional opinion was inaccurate and

FLORIDA PUBLIC SERVICE COMMISSION

1615

1       incomplete.  And as part of a complete review cycle

2       process, seeing that there was a starting point, an

3       investigation, and that's where it ended, I'm merely

4       asking Mr. Reed if he in his professional opinion knows

5       why the findings of the Concentric report were not

6       provided back to the starting point.

7                 MR. ROSS:  And, again, there's no foundation

8       that Mr. Reed can even address that issue.  There's no

9       foundation as to whether he had any involvement with

10       this entity that's listed on the first line of the

11       response to Interrogatory Number 24.

12                 COMMISSIONER SKOP:  Okay.

13                 CHAIRMAN ARGENZIANO:  An opinion from staff.

14       Was that your last question, Commissioner Skop?

15                 MS. HELTON:  Madam Chairman, I need to look at

16       this because I haven't been -- I've been listening but

17       not reading.

18                 CHAIRMAN ARGENZIANO:  Okay.  Do that.  And

19       while I said that we would take lunch at 1:30, depending

20       on how many questions are left to the witness, how about

21       we, after Commissioner Skop finishes his question, I

22       have one question, most of my questions have been asked,

23       and we have two here, and questions now, then we're

24       going to have comments.  Okay.  So it may be that we can

25       get through the questions.  And originally the, I think

FLORIDA PUBLIC SERVICE COMMISSION

1616

1       the court reporter asked for 2:00.  Would that be okay

2       with the court reporter if we extended it to 2:00?

3                 THE COURT REPORTER:  Yes.  But I'm going to

4       need a five-minute --

5                 CHAIRMAN ARGENZIANO:  Okay.  Let's take a

6       five-minute break right now.  Okay.  Thank you.

7                 (Recess taken.)

8                 (Transcript continues in sequence with Volume

9       8.)

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION