1

1                             BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

3                                         DOCKET NO. 100437-EI

4       In the Matter of:

5       EXAMINATION OF THE OUTAGE AND

REPLACEMENT FUEL/POWER COSTS

6       ASSOCIATED WITH THE CR3 STEAM

GENERATOR REPLACEMENT PROJECT,

7       BY PROGRESS ENERGY FLORIDA, INC.

__________________________________/

8

9

10

11

12

13       PROCEEDINGS:             STATUS CONFERENCE

14       COMMISSIONER

PARTICIPATING:           COMMISSIONER EDUARDO E. BALBIS

15                                Prehearing Officer

16

DATE:                    Monday, January 24, 2011

17

18       TIME:                    Commenced at 1:30 p.m.

Concluded at 2:28 p.m.

19

20       PLACE:                   Betty Easley Conference Center

Room 148

21                                4075 Esplanade Way

Tallahassee, Florida

22

REPORTED BY:             JANE FAUROT, RPR

23                                Official FPSC Reporter

(850) 413-6732

24

25

FLORIDA PUBLIC SERVICE COMMISSION

2

1       APPEARANCES:

2                 JOHN T. BURNETT, ESQUIRE, Progress Energy

3       Service Company, LLC, Post Office Box 14042, St.

4       Petersburg, Florida  33733-4042, appearing on behalf

5       of Progress Energy Florida, Inc.

6                 JAMES W. BREW, ESQUIRE and ALVIN F. TAYLOR,

7       ESQUIRE, c/o Brickfield Law Firm, 1025 Thomas Jefferson

8       Street, NW, Eighth Floor, West Tower, Washington D.C.,

9       20007 appearing on behalf of White Springs Agricultural

10       Chemicals, Inc. d/b/a PCS Phosphate.

11                 VICKI GORDON KAUFMAN, ESQUIRE, Keefe, Anchors,

12       Gordon & Moyle, P.A., 118 North Gadsden Street,

13       Tallahassee, Florida 32301, appearing on behalf of

14       Florida Industrial Power Users Group.

15                 CHARLES REHWINKEL, ESQUIRE, Office of Public

16       Counsel, c/o The Florida Legislature, 111 W. Madison

17       St., Room 812, Tallahassee, Florida 32399-1400,

18       appearing on behalf of the Citizens of Florida.

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

3

1       APPEARANCES (continued):

2                 KEINO YOUNG, ESQUIRE, FPSC General Counsel's

3       Office, 2540 Shumard Oak Boulevard, Tallahassee, Florida

4       32399-0850, appearing on behalf of the Florida Public

5       Service Commission Staff.

6                 MARY ANNE HELTON, Deputy General Counsel,

7       Florida Public Service Commission, 2540 Shumard Oak

8       Boulevard, Tallahassee, Florida 32399-0850, Advisor to

9       the Florida Public Service Commission.

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

4

1                        P R O C E E D I N G S

2                 COMMISSIONER BALBIS:  Good afternoon.  I'd

3       like to call this status conference to order.

4                 Staff, could you please read the notice.

5                 MR. YOUNG:  Good afternoon.

6                 By notice issued January 19th, 2011, this time

7       and place was set for a status conference in Docket

8       Number 100437-EI, in re, the examination of the outage

9       and replacement fuel/power costs associated with the

10       CR-3 steam generator replacement project, by Progress

11       Energy Florida, Inc.  The purpose of the status

12       conference is set out in the notice.

13                 COMMISSIONER BALBIS:  Thank you.  And now we

14       can take appearances.  We'll start with Progress Energy

15       of Florida, and just go on down the line.

16                 MR. BURNETT:  Thank you, sir.

17                 Good afternoon.  John Burnett on behalf of

18       Progress Energy Florida.  To my left I have Jon Franke,

19       which is the Vice-President of our Crystal River 3

20       facility, and our General Counsel, Alex Glenn.

21                 MS. KAUFMAN:  Good afternoon, Commissioner.

22                 Vicki Gordon Kaufman.  I'm with the law firm

23       of Keefe Anchors Gordon and Moyle, and I'm here on

24       behalf of the Florida Industrial Power Users Group.

25                 MR. REHWINKEL:  Good afternoon, Commissioner.

FLORIDA PUBLIC SERVICE COMMISSION

5

1       My name is Charles Rehwinkel with the Office of Public

2       Counsel.

3                 COMMISSIONER BALBIS:  Thank you.

4                 I understand we have Mr. Brew and Mr. Taylor

5       via teleconference.  Just checking to see if they are on

6       board.

7                 MR. BREW:  Yes.  James Brew and Alvin F.

8       Taylor for White Springs Agricultural Chemicals, and I

9       appreciate the opportunity to attend remotely.

10                 MR. YOUNG:  Commissioner, Keino Young, legal

11       staff.

12                 MS. HELTON:  And Mary Anne Helton, Advisor to

13       the Commission.

14                 COMMISSIONER BALBIS:  Thank you.

15                 Just a couple of comments about procedural

16       matters.  We'll go on to Section 4 of the script.  And

17       the primary purpose of this status conference is

18       basically to allow Progress Energy of Florida to provide

19       a detailed schedule, if you will, outlining the steps

20       required and appropriate milestones in order to bring

21       the Crystal River 3 Unit back into safe service.

22                 There have been some questions about the

23       schedule of that, so what I want to do is call everyone

24       together, give you the opportunity to present

25       information detailing those steps that need to be taken,

FLORIDA PUBLIC SERVICE COMMISSION

6

1       and then allow the other parties to ask questions, and

2       then move forward and start discussing the schedule of

3       the hearing as we move forward.

4                 Again, from a procedural standpoint, we will

5       allow a presentation from Progress Energy of Florida.

6       One thing I do want to note is I want this to be a

7       looking forward status conference.  I don't want to

8       discuss anything that happened in the past, how we got

9       here.  I think that will be handled in a future matter.

10       But now let's just look at what steps need to happen in

11       moving forward.

12                 And I understand you do have a lengthy

13       presentation.  I will request that if there are points

14       that we can start in this presentation that really from

15       a time standpoint is going forward, that would be

16       appreciated.  But, of course, if there's other

17       information you would like to present, I'll allow you to

18       do that at this time.

19                 MR. REHWINKEL:  Commissioner Balbis, may I say

20       something before we proceed with the presentation by

21       Progress?

22                 COMMISSIONER BALBIS:  Sure.

23                 MR. REHWINKEL:  From the Public Counsel's

24       standpoint, we appreciate the scheduling of this matter,

25       and we fully appreciate Progress Energy bringing their

FLORIDA PUBLIC SERVICE COMMISSION

7

1       station vice-president for Crystal River to make a

2       presentation.  I'm on the record as being someone who

3       thinks quite highly of Mr. Franke, and I think he is a

4       good witness and does an excellent job.

5                 My statement that I'm about to make to you has

6       nothing to do with his testimony here or in any other

7       matter, but we would just like to state for the record

8       that what you're going to hear is not evidence in this

9       matter, and it is purely for the purpose of making

10       scheduling decisions.  And I think that your remarks

11       have already made that point, as well, but we just

12       wanted to state that for the record, that we have no

13       objections to the statements and the testimony that -- I

14       shouldn't say testimony -- that Mr. Franke is going

15       give, but we just want to remind folks, and state for

16       the record that this is purely for scheduling purposes,

17       and not in any way bearing on the evidence that will be

18       taken from here forward.

19                 COMMISSIONER BALBIS:  Okay.  Thank you.

20                 And, again, I think everyone is clear that is

21       the purpose of this proceeding.

22                 MS. KAUFMAN:  Commissioner, if I might add

23       onto that, and a comment that you made earlier about

24       forward-looking.  I have only just received this

25       presentation, and was helpfully pointed to the

FLORIDA PUBLIC SERVICE COMMISSION

8

1       scheduling part by Mr. Burnett.  It looks like a lot of

2       the information prior to that does deal with what has

3       already happened in the past.  And I know that you asked

4       for a status update, and I took that to mean going

5       forward, as well.  So we would echo Public Counsel's

6       comments, and suggest that if you think well of it that

7       the information to be discussed today would be where are

8       we now and what's going to happen in the future.

9       Because those other issues are going to, as you said, be

10       looked at in the hearing, whenever it is that we have

11       it.  Thank you.

12                 COMMISSIONER BALBIS:  Thank you.  Any other

13       questions from parties and Staff?

14                 MR. BURNETT:  Commissioner Balbis?

15                 Thank you, sir.  I appreciate the comments

16       from counsel.  And to that end, it may be helpful just

17       to point you, sir, to Page 32 of the PowerPoint

18       presentation, at this time, just as a preliminary

19       matter.  We fully agree with the comments from counsel.

20       I mean, we don't intend Mr. Franke to testify.  And

21       anything that is in this presentation that is

22       historical, it's just to provide a frame of reference to

23       what we are doing going forward.  Some of the stuff you

24       have to build a foundation on.

25                 Sir, Page 32, I think, answers the two

FLORIDA PUBLIC SERVICE COMMISSION

9

1       questions that you charged us with in your order.  What

2       do we need at a high level to do to get the unit back

3       on, and what is the time estimate for that.  If it is

4       your pleasure, sir, we can stay on that slide the entire

5       time and never leave it, but we are prepared to talk in

6       any level of detail that you or the parties or staff

7       would like to see.

8                 COMMISSIONER BALBIS:  Well, thank you.  And I

9       think, just for my own personal benefit, I would like a

10       little bit of additional information than just that

11       slide.  Again, not to get into the weeds too much, but

12       to show these are the specific steps that need to be

13       taken.  I'm sure that your professional staff have a

14       very detailed schedule of the specific steps that need

15       to be taken.  We don't need get to that level, but I

16       think something in addition to Slide 32.  I think that

17       would be a good summary slide, which is enough of a

18       foundation, again, going forward, and I agree with the

19       other parties' comments that we don't -- we are not

20       building a record here, we're just building a foundation

21       to discuss the schedule of events moving forward, and

22       then we can go into the hearing issues.

23                 MR. BURNETT:  Yes, sir.

24                 And if you guys would let us know, too much,

25       too little, a little more, a little less, we will be

FLORIDA PUBLIC SERVICE COMMISSION

10

1       happy to interactive with the process, sir, to your

2       needs.  Thank you.

3                 COMMISSIONER BALBIS:  Okay.  Any other

4       questions from the parties or staff?  Okay.  With that,

5       we will turn it over to Progress Energy for their

6       presentation.

7                 MR. FRANKE:  Thank you.  And I want to thank

8       the Commission and the interested parties in an

9       opportunity to talk about where we are with Crystal

10       River 3.  There is a lot of material in the

11       presentation, and the reason -- and I encourage anyone

12       that thinks I'm going too far into too much detail to

13       step in.

14                 Part of the problem with talking about just

15       going forward is I can say, for example, over the next

16       many days our primary activity at the plant is

17       retensioning the building, and I can say that.

18       Unfortunately, it doesn't mean much.  The letter we

19       received asked for some detail, so I'm providing some

20       background information to provide what that means and

21       what it takes to do that to provide that detail

22       requested.  It's purely for the purposes of meeting the

23       will of the Commission and being able to inform the

24       parties.

25                 So with that being said, what we'd like to

FLORIDA PUBLIC SERVICE COMMISSION

11

1       cover -- thank you.  This is not working.

2                 A little bit of background information so that

3       when we talk about that forward schedule it's a little

4       clearer what that means.  Give a schedule summary, a

5       status of the remaining repair activities, and I think

6       it is important in talking about the going-forward

7       aspects of our schedule to discuss some uncertainties in

8       the schedule and what items are out there that could

9       potentially affect both the duration as well as the

10       scope of our work going forward.

11                 Thank you.  All right, it's working now.

12       Thank you.

13                 A little on the background.  I'll go very

14       quickly through this.  The issue began with our steam

15       generator replacement project.  That occurred last fall.

16       No need to go into any detail here, but we replaced the

17       steam generators.  As part of that replacement, it

18       required opening up the containment building, and that's

19       what we are talking about repairing at the facility

20       right now.

21                 If you look at a simplified drawing of the

22       building, this shows the steam generators inside our

23       primary containment building.  There are three barriers.

24       This is the third barrier to radioactive release to the

25       public.  The containment building itself, the steel

FLORIDA PUBLIC SERVICE COMMISSION

12

1       liner itself is the barrier.  The concrete provides the

2       strength of the building to hold the liner in place in

3       the event of any high energy transient that would occur

4       inside the buildings.  It's essentially a water pipe

5       rupture that would release steam into the building.

6                 The building itself, if you look at this

7       cutaway, you see the circles to the left and right,

8       those are tendons inside the concrete structure.  So

9       when you make this building, you place tendon sleeves

10       inside the concrete, you pour the concrete, when it

11       cures, you put tendons inside those steel conduits, and

12       you tighten the building to make it compressed in its

13       normal state under operations.  That's important because

14       I'm going to get back to that.  That's actually the

15       evolution we are undergoing right now of compressing the

16       building using those tendons.

17                 Let me explain to you what they are and how

18       they work.  It provides background to the activities

19       that we have ongoing right now and for the next several

20       weeks.  The building itself, this is a picture of the

21       side of the building, and you see steel caps along the

22       edge of a buttress.  Where the concrete comes out, we

23       call that a buttress.  Those steel caps beneath them are

24       the end of tendons.  There are 144 vertical tendons in

25       the building, 282 hoop tendons which wrap around the

FLORIDA PUBLIC SERVICE COMMISSION

13

1       building, and then there's 123 tendons that are involved

2       with the dome structure.  Okay.

3                 The next slide explains how these tendons

4       work.  If you exaggerate the buttresses coming away from

5       the wall, and as I click it, you'll see the tendons

6       start wrapping around the building.  Each tendon goes a

7       third of the way around the building, so it takes three

8       tendons to wrap around once.  And then in order to get

9       the building even, each loop has a set of two loops

10       around the building, making six total a complete loop

11       around the building.  This is how you get a nice even

12       squeeze on the building when you pull the tendons tight.

13                 Over to the right you can see at that tendons

14       are actually meant to be closer together where there is

15       a pair of two tendons that make this loop of essentially

16       six tendons total for a complete loop.  And then there

17       is multiple loops across the building, if that makes

18       sense.

19                 All right.  This is how a tendon works.  It's

20       actually very simple.  This is the end of a tendon.

21       This is what it looks like beneath one of those tendon

22       caps I showed you before.  The tendon is made up of 163

23       carbon steel wires about seven millimeters diameter

24       each.  So it's a lot like a muscle, where it has got

25       many different strands.  They wrap around the building,

FLORIDA PUBLIC SERVICE COMMISSION

14

1       a third of the way around, and on each end those strands

2       stick through what we call a stressing washer, and then

3       the end of each of those strands is mushroomed out to

4       hold it against the stressing washer.

5                 The way the building is tensioned, and this is

6       coming into the detail of what we are doing right now is

7       you have actually grabbed that stressing washer, I'll

8       show you the device in a second, and you stretch the

9       tendon, and then you place a washer back behind it to

10       maintain it's stretch, if that makes sense.  And the

11       pull of the tendon is what applies the tension to the

12       building and compresses the concrete.

13                 On the next slide you can see the tensioning

14       tool, and this is what is actually being used today on

15       the building.  This is a hydraulic ram which is capable

16       of grabbing and threading onto those stressing washers,

17       and then similar to a hydraulic jack that you would jack

18       a car up with, you're jacking against these tendons and

19       stretching them, and then washers -- shims are placed

20       between that stressing washer and the wall to maintain

21       the tendons in tension.  Those are the activities that

22       are ongoing right now.

23                 Real quickly, to get to where we are today,

24       this just shows a couple of photos during the outage

25       last fall that identified the delamination that we have

FLORIDA PUBLIC SERVICE COMMISSION

15

1       subsequently repaired.  This shows the equipment that

2       removed the concrete, and you can see each step as the

3       concrete wall was eaten away.  You can see an outer

4       rebar mesh.  The tendon sleeves themselves are in the

5       photo labeled number two.  Inside these first horizontal

6       tendons, and then in the inner vertical tendons are

7       these tendons that we're currently tensioning.  This is

8       from the original steam generator replacement outage

9       last fall.

10                 Once we opened up -- removed all the concrete,

11       a steel liner plate that is that barrier to radioactive

12       release is on the inside there.  That was removed, which

13       allowed us access in and out of the building.  In photo

14       four, you can see the original delamination as you look

15       up into the opening that was made so that the steam

16       generators could pass into and out of the building.

17       That crack is the delamination that was subsequently

18       repaired.  When we identified it, we did -- this kind of

19       shows a cut-away, by the way, of the way the building is

20       designed.  You see that liner on the far side of the

21       photo, and then coming out is 42 inches of concrete.

22       First are those vertical tendon sleeves, and then the

23       horizontal tendon sleeves, and then that rebar you saw

24       as we ate the wall away.  This kind of gives you a feel

25       for the way the building is constructed.  It also shows

FLORIDA PUBLIC SERVICE COMMISSION

16

1       where that delamination occurred.

2                 At the end of the outage, and after discovery

3       of the delamination, we were able to do nondestructive

4       testing.  The repair area is the area between what we

5       call Buttresses 3 and 4.  You can see those to the left

6       and right of this photograph.  Buttress 4 is actually

7       behind the scaffold staircase to the right in the photo.

8       Buttress 3 is to the left, and you can see the tendon

9       caps.  There was a hourglass shape of delamination that

10       had to be repaired.

11                 Real quickly, for completed repair activities,

12       it is important as we talk about going forward, to first

13       cover our priorities.  Because it explains the scope and

14       schedule for the activities we have going forward.

15       First and foremost, the repair activities was focused on

16       restoring the plant back to its nuclear safety condition

17       to protect the health and safety of the public, and also

18       the work had to be performed in a manner that did not

19       risk our workforce.

20                 Second, and I want to emphasize this point, is

21       our goal is to restore the asset for our customers.

22       While we are not going to go into the cause today of the

23       delamination, there are elements of that cause which

24       drove us to very specific and careful consideration of

25       the techniques used to repair the walls so that we did

FLORIDA PUBLIC SERVICE COMMISSION

17

1       not cause further damage.  The reason being two-fold,

2       and I mention it in bullet three.  First of all, to

3       maintain the NRC license condition.  It's very important

4       for us -- from the work we have done to date, and even

5       more so for the work we have over the next several

6       weeks, to maintain the licensed condition of the plant.

7                 Should we not be able to maintain the current

8       design of the plant per our NRC license, that license

9       would have to be amended, which would cause a

10       significant delay in the return to service of the plant,

11       so we have been focused on that in order to bring the

12       plant back to service sooner for our customers.  And

13       then lastly, of course, to bring the plant back into

14       service and into repair.

15                 Let's talk a little bit about the overview of

16       the repair activities.  First of all, the root cause had

17       to be identified.  I will not go into the root cause

18       today, but it was important because it has driven the

19       schedule to date as well as the schedule going forward

20       with regard to making sure we have the right engineering

21       model to understand how to make this repair both, one,

22       to restore the design of the plant, but also to ensure

23       that no further damage occurred.

24                 In doing so, we had to develop first-of-a-kind

25       engineering techniques that had never been used before

FLORIDA PUBLIC SERVICE COMMISSION

18

1       in the industry.  The delamination was a surprise --

2                 COMMISSIONER BALBIS:  Excuse me.  Is it Mr.

3       Franke?

4                 MR. FRANKE:  Yes, it is.

5                 COMMISSIONER BALBIS:  If we could, again, kind

6       of focus forward on not how we got here, but --

7                 MR. FRANKE:  Sounds good.

8                 I'll have to talk a little bit more about the

9       engineering, because we're currently in that.  Currently

10       we are still doing engineering work, and I'll cover that

11       briefly going forward.

12                 The bottom line, we have detensioned

13       additional tendons since the damage.  We have removed

14       the delaminated concrete, and we have placed concrete.

15       Going forward, we're retensioning the tendons, and

16       that's currently in progress.  After that, the last

17       three bullets -- last four bullets -- I'm sorry, the

18       last three bullets on this slide are the activities that

19       remain.  We have to continue to retension the tendons.

20       That still relies on additional engineering work that is

21       ongoing, and I'll talk about that in a minute.  We have

22       to test the building to validate that it has been

23       restored to design conditions, and then we are going to

24       start to place the plant back in service.  Those are the

25       three big steps that remain.

FLORIDA PUBLIC SERVICE COMMISSION

19

1                 Real quickly, this just kind of gives you an

2       idea of the kind of computer modeling that we had to

3       create in order to understand how to both detension and

4       the going-forward actions of retensioning the building.

5       This gives you a feel for the computer models that were

6       used to determine how that could be done without causing

7       any further damage.  This shows the stresses and the

8       displacements in the wall as you detension -- perform

9       detension and retensioning activities.  Okay.

10                 We have detensioned the building.  We have

11       removed the concrete.  In doing so, and it is important

12       to note in this photo after we performed the original

13       detensioning, we had subsequent cracks in the building.

14       Why it is important that I mention it today is that the

15       identification of these additional cracks that occurred

16       during the detensioning activities last year created a

17       need to go back and revise our engineering model at that

18       time to make sure that in our retensioning activities we

19       caused no further damage.

20                 I don't know if that is understandable, but

21       the bottom line is we knew that we would be placing the

22       building back into conditions similar to what occurred

23       in March last year during the activities we are

24       undergoing right now.  So it was very important that we

25       understood what caused these cracks and how to prevent

FLORIDA PUBLIC SERVICE COMMISSION

20

1       them.  Now, we did anticipate some of these cracks, but

2       it demanded us to go back and re-review the engineering

3       models that had been used to detension the building so

4       that we could retension with confidence that we would

5       cause no further damage.

6                 Let me go ahead and get to a future slide.

7       This kind of steps us through the phases that we have

8       gone through today, and let me talk to you now about

9       what remains.  All right.  First of all, the

10       retensioning itself is being done in two phases.  The

11       first phase is four passes of building, in other words,

12       four sets of tendons that are retensioned, and then you

13       come back to a second pass and retension other tendons

14       that are near the wall.

15                 We are currently in pass two of these first

16       four passes, which make up Phase I of retensioning.  We

17       believe from today that Phase I will be complete within

18       14 days.  In parallel for that, the engineering

19       activities that I talked about before are ongoing in

20       parallel.  We believe 12 days from now, and that's the

21       current schedule, that we will have the engineering in

22       place to start the second phase of retensioning, which

23       is passes 4 through 11.  The second phases right now,

24       the current schedule is 27 days.  The actual duration

25       will depend on a lot of uncertainties that I'll talk

FLORIDA PUBLIC SERVICE COMMISSION

21

1       about in a little bit in some further slides.

2                 There are 16 days of containment testing and

3       post-containment testing recovery with a nine-day start

4       up.  If you add up the critical path days, that's about

5       66 days from today we believe the unit will be returned

6       to service.

7                 Let's talk a little bit about the detail of

8       these activities going forward.  The tendon

9       retensioning; we're at a total scope of 155 horizontal

10       tendons and 64 vertical tendons that are in these 11

11       steps.  We also need to restore 80 of the verticals back

12       to its original state.  We're using a partial tensioning

13       sequence, which meanings of these horizontal tendons

14       they will be first tensioned to 50 percent of their

15       final tension, and then when we come back to the

16       subsequent passes, these tendons will be fully tensioned

17       to their as-left state.

18                 There are 11 passes.  Currently only the first

19       four passes, as I mentioned before, have been approved

20       by engineering, and we are working through the

21       engineering to release the last passes currently.  We

22       were able to release the first four, and the subsequent

23       passes required additional engineering work to verify

24       that no further damage would occur.

25                 The model itself that -- and this is the

FLORIDA PUBLIC SERVICE COMMISSION

22

1       detail of the engineering work that is ongoing right

2       now.  We are using a -- Abaqus is the computer software

3       program.  It's a Visco-Elastic Fracture Energy Model.

4       There are two steps of this model.  The model itself

5       recreates the life of containment showing the original

6       placement of the concrete.  The concrete itself changes

7       over time, and its properties change with the conditions

8       under which it has been.  This model is able to

9       replicate that.

10                 There are two main components:  A global and a

11       microscopic model.  The global model models the entire

12       building itself.  This is a very complex model that has

13       been built.  This model actually shows the shape of the

14       building and the deformations that the building

15       experiences as each of these tendons are stressed;

16       that's very important because we have learned that the

17       shape of the building as it is tensioned and retensioned

18       determines which area of the building are subject to

19       damage.

20                 Once the global model is done, we identify

21       those localized areas that require a very in-depth or

22       microscopic review in engineering space.  We go down to

23       looking at individual blocks as small as one inch by one

24       inch in evaluating the stress and strains in each corner

25       of these blocks.  This work is going on right now.  We

FLORIDA PUBLIC SERVICE COMMISSION

23

1       are looking microscopically at a number of areas in the

2       building to determine the forces in the walls as we

3       complete these final phases, which have yet to be

4       approved by engineering.

5                 This microscopic model is able to identify at

6       what point the building will crack and whether this

7       crack will grow.  The following photos are just some

8       pictures of the engineering model output and shows how

9       the global model and the microscopic models work

10       together to identify potential damage.

11                 All right.  While we are retensioning, we are

12       monitoring the building for damage.  We have three ways

13       we're doing that.  We have strain gauges which are

14       capable of measuring the forces in the wall; we have

15       acoustic emission detectors or sensors, which are

16       listening for any damage as it may occur so that we can

17       stop it before it becomes an issue that would require a

18       repair; as well as we were validating the computer

19       models by using a laser inside the building which

20       actually measures the dimension of the building, and

21       measures the changes in shape of the building as we move

22       forward.

23                 The next photos just kind of show the

24       locations of some of these sensors to demonstrate how

25       complex and how careful we are -- how much care we are

FLORIDA PUBLIC SERVICE COMMISSION

24

1       taking in ensuring we don't cause any further damage to

2       the building.

3                 These are some output from the acoustic

4       monitors.  And then the laser scan itself.  As I

5       mentioned, we are using this data to compare the actual

6       model, the actual building response to the predicted

7       response that the models in engineering space showed us.

8                 We have a number of contingencies.  Should we

9       see any issues from these monitoring activities which

10       need to be resolved, we have contingencies in place to

11       deal with them.

12                 If you remember back on the schedule slide

13       there were a number of post modification testing

14       activities to speak to those details.  We will be doing

15       an impulse response test, which basically validates that

16       the building has not delaminated after the repairs are

17       complete.  We also have a number of visual exams which

18       are required both of the concrete and the steel liner

19       plate, and we have to map any cracks in the concrete

20       which may exist prior to the pressure testing.  We also

21       will be doing a laser scan of the building once all the

22       tendons have been retensioned to understand the shape of

23       the building going into the pressure testing.

24                 The most important tests that require the most

25       amount of time in that sequence and schedule involve

FLORIDA PUBLIC SERVICE COMMISSION

25

1       pressure testing the building.  In this case, we'll

2       pressurize the building to just over 63 pounds per

3       square inch.  This is actually higher than any design

4       pressure required -- I'm sorry, any pressure required by

5       the design in the worst-case conditions.

6                 The structural integrity test follows an ANSI

7       standard in which you measure displacements inside the

8       building as it is pressurized to verify that the

9       structure of the building is reacting the way it was

10       designed.  We will also be looking at those strain

11       gauges, and we map the cracks in the building at the

12       peak pressure.

13                 Once the structural integrity test is

14       completed, we have to depressurize the building and

15       allow the building to stabilize, and then we pressurize

16       it again in order to perform an integrated leak rate

17       test.  This test validates that the leakage boundary,

18       that steel liner, is capable of preventing leakage

19       outside the building at the highest pressure that the

20       building could ever see in any design required

21       conditions after any transience inside the building.

22                 Once the testing is complete and the building

23       is turned back over to the plant staff, we will be

24       starting up the plant.  We have a number of activities

25       that have prepared us for that.  Since the last time the

FLORIDA PUBLIC SERVICE COMMISSION

26

1       plant was operated, we have done a large number of

2       modifications to the facility, both on the steam plant

3       as well as the new steam generators, so there's a lot of

4       testing activities that are involved prior to placing

5       the plant back in service.

6                 We have completed all tests which could be

7       completed with the plant back on line.  But most of the

8       -- many of the steam plant components have to be tested

9       during start up.  The start-up tests are integrated into

10       the start-up testing sequence.  We have performed

11       readiness reviews in order to optimize our restart of

12       the plant, both by the Institute of Nuclear Power

13       Operations as well as the Nuclear Generation Group

14       brought in an assessment to make sure the plant was

15       ready for restart.

16                 Our crews have been back through operations

17       training continuously through the shutdown, but

18       specifically we recertified them with a special focus to

19       get them focused on restart of the plant and their

20       ability to operate the plant after the shutdown.  We

21       have done the same thing for some of our technical staff

22       for those kinds of activities which occur with the plant

23       on-line as opposed to the work they have been performing

24       when the plant is shut down.

25                 There are a number of potential impacts to the

FLORIDA PUBLIC SERVICE COMMISSION

27

1       ability to execute the schedule as I detailed on Slide

2       32.  First of all, the engineering activity that I

3       indicated was working in parallel, that has to be in

4       place prior to the completion of our Phase I

5       retensioning or we will be waiting on engineering before

6       we can go to Pass 5, the first part of Phase II of

7       retensioning.  Since that engineering is not complete

8       yet, it still has the potential to affect that schedule.

9                 Additionally, I went and detailed a little bit

10       the monitoring equipment that is in place.  That

11       monitoring equipment could reach some alert level which

12       would require us to respond to it.  That can slow down

13       the return to service of the plant.

14                 Additionally, this is a first-of-a-kind

15       construction activity.  No other nuclear plant has been

16       through this evolution.  As such, we learn as we go.

17       There are opportunities for construction equipment

18       failures.  We may identify additional work that is

19       required, and this is outside work, so the weather has

20       the ability to delay us.  Obviously there are times when

21       the workers cannot work on the building due to inclement

22       weather.

23                 I also want to indicate that the NRC has the

24       authority to come in and require additional reviews of

25       our engineering design.  We currently have a start-up

FLORIDA PUBLIC SERVICE COMMISSION

28

1       meeting with the NRC prior to restart.  We don't see any

2       holds to that right now, but the NRC has their own

3       authority and they can require additional views prior to

4       plant restart.

5                 And, additionally, we have a number of

6       equipment tests prior to return to service not

7       associated with the containment itself which could delay

8       startup.  There are a large number of new equipment in

9       the facility that have to be tested, and part of our

10       schedule itself, including the schedule that I just

11       detailed, included contingency actions should we have

12       problems with that testing.  For example, in that

13       schedule that I detained, the startup consequence, there

14       are times to respond to equipment challenges that may be

15       revealed.  I'll give you one example.  We have a new

16       statter (phonetic) and new rotor on the generator.

17                 We know that there is a test that requires us

18       to validate the air flow through the generator is as we

19       designed it, and while we have placed it in the

20       condition we believe is the right status to provide that

21       air flow, you can't measure it until the generator has

22       been spun with steam.  We don't have the steam to do

23       that.  Once that test is complete, we may have to go

24       back in to make some adjustments inside the generator.

25       That time right now is currently in the schedule.  So

FLORIDA PUBLIC SERVICE COMMISSION

29

1       all of these potential schedule impacts really lay on

2       both sides of the end date.  And what I mean by that is

3       if the first time we spin that generator up, for

4       example, it is in design, then that return to service

5       will be earlier.  If we run into an emergent work

6       activity with construction, that schedule may be later.

7                 So what I want to emphasize is this is the

8       best information available today.  There is still a lot

9       to learn as we move through the repair and certainly

10       some to learn as the plant comes back in service.  So

11       while I am certain the plant will return to service,

12       right now the specific date is going to be subject to a

13       large number of the uncertainties I just detailed.

14                 MR. BURNETT:  Thank you, Commissioner.

15                 The next slide just discusses very briefly a

16       couple of things.  Three things that have to be done,

17       and one thing that the Commission and the parties may

18       want to consider being done after a return to service.

19       We'll have to calculate the final replacement fuel and

20       power costs, and that should not be a heavy lift.

21       That's something we could do relatively quickly.

22                 Collect and process remaining documents.  As

23       this process goes on, documents that may be relevant to

24       this case are being created, so we are trying to collect

25       them as realtime as possible and process them to have

FLORIDA PUBLIC SERVICE COMMISSION

30

1       them available for staff and the parties.  Again, we are

2       doing pretty well with that and keeping pace.

3                 The next one on here, the bullet of

4       comprehensive briefing and Q&A, I have not vetted this

5       with the parties yet, but it may make sense prior to

6       going in the case at some point if the parties and

7       Progress could agree on a presentation to have Crystal

8       River 3 101.  Perhaps some of the key terms, the

9       acronyms, some of the things just to gain a familiarity,

10       maybe an FAQ, frequently asked question type Q&A.

11       Anything to move it along so we don't have to waste

12       hearing time getting people caught up to some of the

13       more Byzantine nuclear aspects.  And, again, I have not

14       discussed this with the parties yet, but something to

15       think about to maybe streamline.

16                 And then, finally, completed case filings.  If

17       we file before return to service, of course our case

18       filings will not tell all of the story.  So we'll either

19       have to update that or we'll have to wait until return

20       of service and file the entirety.  So those are just

21       some housekeeping next steps.

22                 And that would end our presentation, and we

23       are available for any questions, sir.

24                 COMMISSIONER BALBIS:  Thank you.

25                 And I think that provided a good background

FLORIDA PUBLIC SERVICE COMMISSION

31

1       without stepping in the wrong area.  And I guess I'll

2       now turn it over to the other parties, if you would like

3       to make any comments at this time.

4                 MR. REHWINKEL:  Thank you, Commissioner.

5                 I will go first from Public Counsel.  We

6       appreciate the factual presentation that Mr. Franke has

7       made, and we have been dealing with this issue for over

8       a year.  We believe Progress has kept Public Counsel's

9       Office apprised of the major issues and schedule impacts

10       as they have changed, at least at a high level, and we

11       appreciate that.

12                 Public Counsel's Office believes,

13       Commissioner, that this docket will involve a

14       significant amount of complexity.  Issues of imprudence

15       that may be evaluated exist on several levels.  One of

16       which is the overall project planning, also the specific

17       engineering that lead to the delamination event, also

18       the repair process and time line that you have heard

19       some about today, as well as the replacement power

20       decisions.

21                 These are ones that are manifest, at least to

22       this office at this time, and they represent potential

23       areas where imprudence may be found.  On November 11th

24       of 2010, the Public Counsel served discovery, and at the

25       outset gave Progress Energy 60 days instead of the

FLORIDA PUBLIC SERVICE COMMISSION

32

1       standard 30 days to produce documents due to the

2       holidays, due to the on-going repair work, and with an

3       awareness of the magnitude of the documents that we were

4       requesting.

5                 On January 11th, Progress produced, at current

6       count, over a million pages of documents in their

7       Tallahassee Office, and on that same day the Public

8       Counsel's Office began review of those documents.  Also,

9       on December 22nd, the Public Counsel noticed three

10       depositions for the project planning engineers for the

11       steam generator replacement project.  We had, I should

12       mention to you, asked counsel for Progress to be able to

13       take these depositions earlier, perhaps even in the days

14       before the Christmas holidays.  But we were rightfully

15       reminded by Progress that some of the folks that we

16       might want to talk to were involved in the very

17       activities that you have heard about today, and that was

18       a point well taken.

19                 It has been a fundamental precept of our

20       office in participating informally and formally with

21       Progress in this case is that what is most important is

22       getting the building repaired, as Mr. Franke mentioned,

23       for the benefit of the customers as well as the company.

24                 And we think that is an important thing to be

25       considered both by the parties participation in this

FLORIDA PUBLIC SERVICE COMMISSION

33

1       docket as well as the Commission's scheduling of the

2       docket.  We have no complaints about the pace of

3       discovery or the availability of witnesses, because

4       repair the building is first and foremost, and we do not

5       want to in any way interfere with that.

6                 The depositions that we scheduled by agreement

7       of the parties and the company were combined into two

8       full-day depositions by panel of these three planning

9       engineers, and we concluded those close to the end of

10       the day on this past Friday.  The Public Counsel's

11       Office believes that the issues before the Commission

12       both with respect to the magnitude of the dollars as

13       well as the complexity of the engineering and planning

14       that are involved in this docket are beyond, by a great

15       magnitude, anything that the Commission has seen before

16       in a prudence docket.  And we think that is an important

17       thing to consider in scheduling of this case.

18                 We believe that we owe it to our clients, the

19       customers, to do this case right.  The dollars are too

20       large, the issues are too complex, and the case is too

21       important to rush.  We are very leery of making too much

22       of a connection between the happenstance of an annual

23       fuel factor hearing and the facts of this case which

24       have not, to this date, as you have heard today, become

25       final.

FLORIDA PUBLIC SERVICE COMMISSION

34

1                 The issues in this case will involve not only

2       the past, the root-cause analysis, but the continuation

3       of activities that still have not been completed.  They

4       are significant and crucial engineering that is on-going

5       today, and that will bear in the final valuation on what

6       happened and the steps that the company has taken to

7       mitigate damage that the customers ultimately may have

8       to pay for, both with respect to the engineering as well

9       as the replacement fuel costs.

10                 We don't believe that the schedule of the fuel

11       docket or the fact that a decision has been made and is

12       final with respect to allowing replacement costs should

13       influence this docket.  We think it should be a

14       stand-alone docket dealing with the prudence of the

15       activities of Progress Energy so that it can be fair to

16       both the customers and the company.

17                 And in that regard, we believe that the

18       Commission should allow ample time for the company to

19       complete their repairs, to make their filing, and for

20       parties to then take the proper steps, including the

21       hiring of appropriate expert witnesses to test the

22       testimony that they file.

23                 The Public Counsel has taken it upon itself to

24       begin our efforts to start, in this massive case, well

25       in advance of the filing of the company.  And the

FLORIDA PUBLIC SERVICE COMMISSION

35

1       company has been very forthright and very open to

2       allowing us to do that, because they know that this is a

3       case that may take some time.

4                 So our plea to you in devising a schedule for

5       this case is that there is no reason to rush.  We don't

6       fault parties, or the staff, or the Commission for

7       trying to put some definition in the schedule and to

8       come up with some hearing dates that we can shoot for.

9       We believe August is too soon.  We are much more open to

10       looking at dates later in the year, as long as there are

11       no inordinate or unanticipated delays in the filings

12       that the company makes.

13                 So I have no definite dates to offer to you

14       other than August is too soon, and there is no reason

15       for us to try to cram a square peg into a round hole to

16       meet a filing date for the fuel factor docket, because

17       that's something that happens every year at a certain

18       time of year, and it is agnostic to what the facts are

19       in this case, and the pace of repairs, and the pace of

20       the company's filing.

21                 So we are very mindful of the fact that

22       customers are paying for replacement costs, at least a

23       definite or finite calculation of replacement costs that

24       were determined in the fall.  We don't take that issue

25       lightly, but if there is imprudence and there is refunds

FLORIDA PUBLIC SERVICE COMMISSION

36

1       to be made to the customers, we would rather get it

2       right than to rush and do half a job.

3                 So with those remarks, I would turn it to over

4       to other counsel.  Thank you.

5                 COMMISSIONER BALBIS:  Thank you.

6                 Ms. Kaufman.

7                 MS. KAUFMAN:  Thank you, Commissioner.

8                 Would I be permitted to ask a question or two

9       about the schedule that Progress has presented?

10                 COMMISSIONER BALBIS:  Yes.

11                 MS. KAUFMAN:  And I guess this is for Mr.

12       Franke.  On the Page 32 schedule that you talked

13       about --

14                 MR. FRANKE:  Yes, ma'am.

15                 MS. KAUFMAN:  -- the total duration of the

16       outage that you are now predicting today is about two

17       more months, correct?

18                 MR. FRANKE:  That is correct.

19                 MS. KAUFMAN:  Actually, I tried to count the

20       days out, and it actually comes out to March 31st, which

21       is the last day of the third quarter.  I mean --

22                 MR. FRANKE:  First quarter.

23                 MS. KAUFMAN:  Right.  Sorry.

24                 You also talked, when you were on Slide 50,

25       about some things that -- no, that's Mr. Burnett's

FLORIDA PUBLIC SERVICE COMMISSION

37

1       slide, the slide before, Page 49, some potential impacts

2       to that schedule that might come up.

3                 MR. FRANKE:  Yes, ma'am.

4                 MS. KAUFMAN:  Did I hear you correctly that

5       there is some contingency time built into the Page 32

6       schedule?

7                 MR. FRANKE:  Yes, ma'am.  For example, there

8       are, I think as of this morning, about 1,000 different

9       line items in that schedule, okay.  So we are talking

10       about something very -- a lot of action is required

11       between now and return the plant to service, including

12       all the testing actions.

13                 For example, the generator test I discussed

14       before.  That test right now, if we execute the test and

15       the test is satisfactory, it takes a couple of hours.

16       If we find that the flows inside the generator are not

17       as required, we have got a six-day contingency in that

18       current schedule to secure the turbine, to make it safe

19       to work on, and to go into the generator and move some

20       plates and bolt them in a new position, bolt it all back

21       up and then start the generator again.  Those days will

22       not be required if the test is satisfactory.  So that's

23       an example of some contingency time we have in the

24       schedule.

25                 Now, there are other items that could make it

FLORIDA PUBLIC SERVICE COMMISSION

38

1       go longer.  This is one of those things where to know

2       today precisely when the generator is going to sync to

3       the grid with a high level of confidence on that

4       preciseness is just not reasonable.

5                 MS. KAUFMAN:  I understand that totally, but

6       my point is that the schedule that's on Page 32

7       considers contingencies.  It doesn't assume that every

8       single task is going to be perfectly done, as you said,

9       in six hours, but it builds in some -- I don't know what

10       to call it -- some float time there for things that

11       might not go exactly according to schedule.

12                 MR. FRANKE:  For some activities.  Not all the

13       things that can go wrong are in that schedule.

14                 MS. KAUFMAN:  Okay.  I guess that would be --

15                 MR. FRANKE:  That's impossible.

16                 MS. KAUFMAN:  -- an impossible task, yes.

17                 Thank you for that clarification; I appreciate

18       it.

19                 MR. FRANKE:  Yes, ma'am.

20                 MS. KAUFMAN:  Commissioner, I wanted to follow

21       up, if I might, on Mr. Rehwinkel's comments on the

22       scheduling.  And we certainly agree that bringing this

23       unit back safely to service for the customers is a top

24       priority.  It's a very low-cost unit, and every day that

25       it's out, you know, it's costing the ratepayers money.

FLORIDA PUBLIC SERVICE COMMISSION

39

1       So we certainly think that is a priority.

2                 We also think that while it's true, and I'm

3       not going to go into what happened in the fuel

4       adjustment hearing, that currently, as Mr. Rehwinkel

5       said, customers are paying for their replacement fuel

6       and there has yet to be any determination as to whether

7       or not what occurred in this instance was reasonable and

8       prudent.

9                 So FIPUG is very anxious to have that

10       determination made.  Whether it occurs in conjunction

11       with the fuel hearing is an issue, but I think that

12       there are other mechanisms that the Commission has and

13       that we might discuss with the company that would

14       certainly allow, if a refund is ordered, and, of course,

15       we don't know that at this point, but it would certainly

16       allow the return of those monies more quickly to the

17       customers.

18                 And so what we would like to see is we would

19       like to see this case scheduled and determined not in a

20       rush, but as quickly as possible and as efficiently as

21       it can be so that, you know, we get a determination as

22       to the reasonableness and prudence, or lack thereof, of

23       Progress' decision, and so that we get the pot right,

24       you know, as to who should be paying these fairly large

25       -- I mean, they are quite large replacement fuel costs.

FLORIDA PUBLIC SERVICE COMMISSION

40

1       And FIPUG commits and remains willing to work with

2       Public Counsel, with the parties, and with the

3       Commission to get that done.

4                 I certainly understand Mr. Franke's comments.

5       It's not a precise science where he can say March 15th

6       the unit is coming back on line.  But I think as we saw

7       in our pleading, Progress has been less than accurate, I

8       guess, in the many predictions that they have made in

9       the past, and that does cause us some concern,

10       especially in light of the fuel decisions.

11                 So we don't have an exact date to suggest to

12       you, either, but we certainly would like to see this

13       happen sooner rather than later, but protecting all the

14       parties' rights to discovery and a full and a fair

15       process.

16                 Thank you.

17                 COMMISSIONER BALBIS:  Thank you.

18                 I'll turn it over, I'm sorry, to our

19       teleconferencers.

20                 MR. BREW:  Thank you, Commissioner.

21                 This is Mr. Brew.  I would like to echo Mr.

22       Rehwinkel's comment that in our view the priority is

23       getting the unit back to service.  We are a little leary

24       of the suggestion of the time frame in the Progress

25       motion until we actually see the unit back in service.

FLORIDA PUBLIC SERVICE COMMISSION

41

1       So my suggestion might be that the parties take some

2       time now or off the record to talk about scheduling a

3       little bit, rather than leaving it completely

4       open-ended.

5                 COMMISSIONER BALBIS:  Okay.  Thank you.  And

6       if there are no other comments, I will turn it over to

7       staff.  And let me make sure you answer one question

8       that I had, or at least a reminder, the Commission did

9       approve Progress Energy to collect the replacement fuel

10       costs for this outage, and if you can just state the

11       disposition of those funds as far as being subject to

12       refund or not.

13                 MR. YOUNG:  Yes, sir.  In Order Number

14       PSC-10-0734-FOF-EI, the Commission did approve Progress

15       Energy Florida to collect funds subject to refund for

16       the CR-3 outage, the repurchased power.

17                 I've listened to what all the parties have

18       said, also talking to technical staff throughout the

19       course of the past weeks, and I think two slides -- the

20       slide that's up right now speaks volumes in terms of the

21       complexity of this case, and that is Bullet Point 2 and

22       Bullet Point 4 in terms of collect and process remaining

23       documents.  Because if you go -- my fear is if we go to

24       hearing and we don't have all the documentation that is

25       necessary, I think it leaves the Commission without the

FLORIDA PUBLIC SERVICE COMMISSION

42

1       proper -- potentially can leave the Commission without

2       the necessary information to make a prudence review in

3       terms of the costs.

4                 And like Mr. Rehwinkel said, from my

5       perspective, I have never seen -- I have potentially

6       never seen a case this complex since I've been here.  So

7       I think I would urge the Commissioner to be prudent in

8       this decision before setting a hearing.  And I think the

9       ratepayers -- the money are held subject to refund, so

10       the ratepayers are not being harmed, per se, if this

11       hearing doesn't happen in the next couple of months.

12                 MR. BURNETT:  Commissioner Balbis, I'm sorry,

13       sir, I didn't know if I was going to get a chance to

14       talk about the scheduling element.  May I do so?

15                 COMMISSIONER BALBIS:  Yes, that's fine.

16                 MR. BURNETT:  Thank you, sir.

17                 I echo the comments that I have heard on the

18       complexity of the case.  And just very quickly, to put

19       it in perspective, Mr. Rehwinkel processed in very short

20       order tens of thousand of documents.  We had probably

21       20 hours worth of deposition, and that got us through

22       the planning phase of this project that began in 2002.

23                 As Mr. Rehwinkel said, we've collected all the

24       documents since 2002 until October of 2010 and placed

25       them in our Tallahassee Office.  Right now that is

FLORIDA PUBLIC SERVICE COMMISSION

43

1       spanning about 300 banker's boxes full of documents that

2       we've just put in the room there, and we have

3       categorized into 104 subcategories of potentially

4       relevant topics.  So it is a huge case.

5                 I will say that certainly of all the parties,

6       we're in the best position to try this fast.  And if the

7       objective is to get it done fast, we can do that

8       probably better than anyone, because it's our case, it's

9       our documents, it's our witnesses.

10                 But I agree, you know, to be fair, we want

11       everyone to have the time that they need, and we want a

12       comprehensive look at this.  We don't want to leave the

13       impression that this needs to be fast-tracked quickly so

14       we can have the upper hand on that, so I agree that it

15       does need some time, sir.

16                 COMMISSIONER BALBIS:  Okay.  Thank you.

17                 One of the reasons why I called for this

18       status conference is that one of the parties did raise

19       concern about the schedule of bringing CR-3 back into

20       safe operation.  And I think that, you know, I, for one,

21       would have liked to have seen the thousand line item

22       Gantt chart that shows it, just because I can only

23       assume that the level of complexity with something like

24       this is immense.

25                 And really my main concern was if the hearing

FLORIDA PUBLIC SERVICE COMMISSION

44

1       is scheduled by a certain time is there any benefit.  I

2       mean, are there funds that could possibly be lost?  And,

3       I think with staff's reiteration of what the Commission

4       approved, and that those funds are subject to refund --

5       and one question I do have for Progress, as far as those

6       funds being subject to refund, they are the account

7       holders of record, correct?  So I want to make sure that

8       the account holders at the time that paid for these

9       additional costs, if there is a refund, would recover

10       that amount.

11                 MR. BURNETT:  Commissioner, I've never

12       understood it to work that way, so I think the answer to

13       your question is no.  I believe that those funds, that

14       the amounts are held subject to refund and are

15       redistributed at the time that the refund is ordered

16       with interest.  I'm not aware of any procedure by which

17       those are tagged to certain accounts, just because of

18       the flux of accounts going in and out and changing, even

19       customers changing from account to account.  I think the

20       answer is no.  I have never understood the Commission to

21       ever do that as far as I know.

22                 COMMISSIONER BALBIS:  Okay.  I know there is

23       another item on the discussion, the possibility of

24       bifurcating the hearing.  We can have some discussion on

25       that briefly from staff, but I think we have kind of

FLORIDA PUBLIC SERVICE COMMISSION

45

1       covered that at this point, at least for my benefit.

2                 So with that we'll move on to other matters.

3       From the parties, are there any other matters you would

4       like to discuss?

5                 MR. GLENN:  We would just note one thing --

6       this is Alex Glenn for Progress Energy Florida -- just

7       on fuel costs.  Right now the fuel costs that we have

8       collected were through December of last year.  Progress

9       Energy Florida and not its customers are eating right

10       now all of those, any excess fuel costs that we have

11       associated with CR-3 being down, and will be.

12                 So as this plant, you know, is off-line

13       January, February, what have you, we are essentially

14       paying for those additional costs, not our customers, at

15       this point.  So in a sense there is a protection to

16       customers, at least this year, on that plant being down.

17       I wanted to make that clear.

18                 COMMISSIONER BALBIS:  Okay.  Thank you.

19                 If there are no other matters, I will note

20       that an order memorializing this decision will be

21       afterwards, but I will say, again, I understand the

22       complexity of the process, and I think that having those

23       funds safe, if you will, based on the Commission's past

24       decision is important.  And I think what is of most

25       importance is bringing this unit in operation in a safe

FLORIDA PUBLIC SERVICE COMMISSION

46

1       manner as quickly as possible and move forward in that

2       vein.

3                 So, if there are no other questions, this

4       meeting is adjourned.

5                 (The status conference concluded at 2:28 p.m.)

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

47

1

2       STATE OF FLORIDA    )

3                           :    CERTIFICATE OF REPORTER

4       COUNTY OF LEON      )

5

I, JANE FAUROT, RPR, Chief, Hearing Reporter

6       Services Section, FPSC Division of Commission Clerk, do

hereby certify that the foregoing proceeding was heard

7       at the time and place herein stated.

8                 IT IS FURTHER CERTIFIED that I

stenographically reported the said proceedings; that the

9       same has been transcribed under my direct supervision;

and that this transcript constitutes a true

10       transcription of my notes of said proceedings.

11                 I FURTHER CERTIFY that I am not a relative,

employee, attorney or counsel of any of the parties, nor

12       am I a relative or employee of any of the parties'

attorney or counsel connected with the action, nor am I

13       financially interested in the action.

14                 DATED THIS 27th day of January, 2011.

15

16

___________________________________________

17                         JANE FAUROT, RPR

Official FPSC Hearings Reporter

18                          (850) 413-6732

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION