649

1                              BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

DOCKET NO. 110009-EI

3

4       In the Matter of:

5       NUCLEAR COST RECOVERY CLAUSE.

______________________________/

6

7

8

9

10

11                               VOLUME 5

12                        Pages 649 through 808

13

14       PROCEEDINGS:        HEARING

15       COMMISSIONERS

PARTICIPATING:      CHAIRMAN ART GRAHAM

16                           COMMISSIONER LISA POLAK EDGAR

COMMISSIONER RONALD A. BRISÉ

17                           COMMISSIONER EDUARDO E. BALBIS

COMMISSIONER JULIE I. BROWN

18

DATE:               Wednesday, August 10, 2011

19

TIME:               Commenced at 4:25 p.m.

20                           Concluded at 5:09 p.m.

21       PLACE:              Betty Easley Conference Center

Room 148

22                           4075 Esplanade Way

Tallahassee, Florida

23

REPORTED BY:        JANE FAUROT, RPR

24                           Official FPSC Reporter

(850) 413-6734

25

APPEARANCES:        (As heretofore noted.)

FLORIDA PUBLIC SERVICE COMMISSION

650

1                              I N D E X

2                              WITNESSES

3

NAME:                                           PAGE NO.

4

5       TERRY JONES

6       Direct Examination by Mr. Anderson                652

Prefiled Direct Testimony

7         Extended Power Uprate 2009                      655

Prefiled Direct Testimony

8         Extended Power Uprate 2010                      694

Prefiled Direct Testimony

9         Nuclear Power Plant Cost Recovery,

2011 and 2012                                   732

10       Errata Sheet                                      772

Prefiled Supplemental Direct Testimony            773

11       Cross Examination by Ms. Kaufman                  780

Cross Examination by Mr. McGlothlin               796

12       Redirect Examination by Mr. Anderson              804

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

651

1                              EXHIBITS

2       NUMBER:                                    ID.    ADMTD.

3       49 through 75                                      806

4

5

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

652

1                        P R O C E E D I N G S

2                 (Transcript continues in sequence from

3       Volume 4.)

4                 CHAIRMAN GRAHAM:  You can call your next

5       witness.

6                 MR. ANDERSON:  Thank you.

7                 FPL would call as its next witness Terry

8       Jones.  Mr. Jones has not been in the room to be sworn.

9       I'm sorry, I am told he was.  And I remember that now,

10       too.

11                             TERRY JONES

12       was called as a witness on behalf of Florida Power and

13       Light Company, and having been duly sworn, testified as

14       follows:

15                         DIRECT EXAMINATION

16       BY MR. ANDERSON:

17            Q.   Mr. Jones, if you could just look up when you

18       are settled and ready to go, we'll proceed.

19                 Thank you.  It has been noted on the record

20       that you have been sworn as a witness.  Would you please

21       state your name and your business address?

22            A.   My name is Terry Jones.  My business address

23       is 700 Universe, Juno Beach, Florida.

24            Q.   By whom are you employed and in what capacity?

25            A.   I'm employed by Florida Power and Light; I'm

FLORIDA PUBLIC SERVICE COMMISSION

653

1       the Vice-President for the Extended Power Uprate

2       Project.

3            Q.   Have you prepared and caused to be filed 39

4       pages of Prefiled Direct Testimony in this proceeding on

5       March 1, 2011, entitled Extended Power Uprates, 2009?

6            A.   Yes, I have.

7            Q.   Did you prepare and caused to be filed 38

8       pages of Prefiled Direct Testimony in this proceeding on

9       March 1, 2011, entitled Extended Power Uprates, 2010?

10            A.   Yes, I have.

11            Q.   Have you prepared and caused to be filed 40

12       pages of Prefiled Direct Testimony in this proceeding on

13       May 2nd, 2011, entitled Nuclear Power Plant

14       Cost-Recovery for the Years Ending December 2011 and

15       2012?

16            A.   Yes, I have.

17            Q.   Did you also cause to be filed one page of

18       errata on June 10, 2011?

19            A.   That's correct.

20            Q.   Did you prepare and cause to be filed four

21       pages of Prefiled Supplemental Direct Testimony on

22       July 15th?

23            A.   That is correct.

24            Q.   Do you have any other changes or revisions to

25       your Prefiled Direct Testimony?

FLORIDA PUBLIC SERVICE COMMISSION

654

1            A.   No, I do not.

2            Q.   If I asked you the same questions contained in

3       your Prefiled Direct Testimony, would your answers be

4       the same?

5            A.   Yes, they would.

6                 MR. ANDERSON:  Mr. Chairman, Florida Power and

7       Light Company asks that the Prefiled Direct Testimony be

8       inserted into the record as though read.

9                 CHAIRMAN GRAHAM:  We will insert Mr. Jones'

10       Prefiled Direct Testimony into the record as though

11       read.

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

777

1       BY MR. ANDERSON:

2            Q.   Mr. Jones, you are sponsoring exhibits to your

3       direct testimony?

4            A.   Yes, I am.

5            Q.   These are Exhibits TOJ-1 through TOJ-27, also

6       shown as Exhibits 49 through 75 on staff's exhibit list?

7            A.   That is correct.

8                 MR. ANDERSON:  The exhibits have been

9       premarked, Mr. Chairman.

10                 CHAIRMAN GRAHAM:  Uh-huh.

11       BY MR. ANDERSON:

12            Q.   Mr. Jones, would you please provide a summary

13       of your testimony for the Commission?

14            A.   Yes, I will.

15                 Good afternoon, Chairman Graham and

16       Commissioners.  FPL's project team is safely and

17       cost-effectively implementing the extended power uprate

18       project at St. Lucie and Turkey Point Nuclear Power

19       Plants.  I am responsible for the management and

20       execution of FPL's extended power uprate project.  An

21       extended power uprate project is the largest and most

22       complex uprate that can be approved by the Nuclear

23       Regulatory Commission.  It requires the replacement or

24       modification of a significant number of nuclear plant

25       components and systems in order to generate and

FLORIDA PUBLIC SERVICE COMMISSION

778

1       accommodate higher electrical output.  When completed,

2       the EPU project will provide FPL's customers with an

3       additional 450 megawatts of clean zero-emission

4       electrical generation without expanding the footprints

5       of these plants.

6                 This project will add approximately one-half

7       of the electrical output of a new nuclear unit and will

8       provide significant fuel cost savings to our customers.

9       Our customers began benefiting from fuel savings this

10       past spring following the outage at St. Lucie Unit 2

11       where a new more efficient low-pressure turbine was

12       installed for the extended power uprate, adding

13       approximately 19 megawatts of nuclear generated

14       electrical output.

15                 By design, the extensive license, engineering,

16       equipment procurement, design modification engineering,

17       and implementation work all overlap with major

18       construction being incorporated into scheduled refueling

19       outages for FPL's nuclear units.  We chose this

20       methodology to bring the benefits of additional nuclear

21       generation to FPL's customers as early as practical.

22                 Let me briefly describe FPL's EPU work during

23       the 2009 to 2012 time period under review in this

24       proceeding.  During 2009 and 2010, FPL worked on Nuclear

25       Regulatory Commission licensing, procured major

FLORIDA PUBLIC SERVICE COMMISSION

779

1       equipment, performed detailed design engineering for

2       required modifications, and prepared and implemented

3       many modifications required to increase nuclear

4       generation for our customers.  In 2010, FPL also

5       completed two EPU implementation outages at St. Lucie

6       and Turkey Point.

7                 So far in 2011, we have made good progress on

8       obtaining the required NRC licensing approvals.  We

9       received NRC approval on one of our license amendments

10       with three others accepted for approval.  We have also

11       successfully completed two more EPU implementation

12       outages, including the St. Lucie outage that I mentioned

13       earlier resulting in an increase of 29 megawatts of

14       electrical output for FPL's customers.

15                 During 2012, FPL will continue its

16       engineering, design implementation and construction

17       work, complete additional outages at the plant, and

18       support the NRC's continued licensing review.

19                 It's a big job.  We are employing over ten

20       million manhours of work, or to put it another way, more

21       than 5,000 person years of work to complete the EPU

22       project.  The costs incurred in 2009 and 2010 and those

23       projected for 2011 and 2012 for the EPU project are

24       prudent and reasonable.  FPL's investment in additional

25       nuclear generation approved by this Commission is

FLORIDA PUBLIC SERVICE COMMISSION

780

1       creating thousands of jobs and will provide fuel cost

2       savings for FPL customers for decades.  This concludes

3       my summary.

4                 MR. ANDERSON:  Mr. Jones is available for

5       cross-examination.

6                 CHAIRMAN GRAHAM:  Thank you.  Who's up first?

7                 MS. KAUFMAN:  I guess it's me.

8                 CHAIRMAN GRAHAM:  Ms. Kaufman.

9                 MS. KAUFMAN:  Thank you, Mr. Chairman.

10                          CROSS EXAMINATION

11       BY MS. KAUFMAN:

12            Q.   Good afternoon, Mr. Jones.

13            A.   Good afternoon.

14            Q.   When did you -- you are currently

15       Vice-President of Uprates, is that correct?

16            A.   That is correct.

17            Q.   When did you come into that position?

18            A.   I officially assumed the position August 1st,

19       2009.

20            Q.   So that was obviously right before the

21       September 2009 nuclear cost-recovery hearing, is that

22       correct?

23            A.   That is correct.

24            Q.   Did you have any involvement in the

25       September 2009 hearing?

FLORIDA PUBLIC SERVICE COMMISSION

781

1            A.   No, I did not.

2            Q.   Now, in your testimony -- you have several

3       sets of testimony, so let me get this right.  In your

4       March 1, 2011, testimony you address the activities of

5       the extended power uprate in 2009, correct?

6            A.   That is correct.

7            Q.   But most of this information -- would you

8       agree most of the activity occurred prior to your

9       assuming your position as VP of Uprates?

10            A.   The activity that occurred in 2007, 2008, and

11       up until August 1 of 2009 were before I officially took

12       over the project.  In my prior position as

13       Vice-President for Operations for the Midwest, we're

14       doing extended power uprate across the enterprise, six

15       of the eight reactors.  And so I was involved quite a

16       bit in the extended power uprate as it affected the

17       utility company.  So I was very much aware of what was

18       going on in the extended power uprate in Florida,

19       because at the time it was a corporate, largely

20       corporate-centric organization.

21            Q.   You referenced your prior position and your

22       involvement with uprates.  Where were you located prior

23       to coming to FPL Juno Beach?

24            A.   Prior to coming to FPL Juno Beach, I was

25       located at Turkey Point Nuclear Power Plant, and I came

FLORIDA PUBLIC SERVICE COMMISSION

782

1       to Juno Beach in January of 2007.

2            Q.   You referenced your experience in the midwest.

3       Where were you located then?

4            A.   As the Vice-President of Operations for the

5       Midwest Region, I was located in Juno Beach, Florida.

6       And also as part of that function, it is mentioned in

7       some of the discovery documents about the technical

8       challenge and review boards of which I chaired in

9       regards to scope additions and scope deletions for the

10       Florida units that preceded me taking over as

11       Vice-President of the Extended Power Uprates.

12            Q.   If you would turn to Page 15 of your March

13       testimony we have just been talking about.

14            A.   Is that the March 2011?

15            Q.   The March 1 -- yes, 2011 extended power

16       uprate, 2009, Page 15.  Are you there?

17            A.   I'm there.

18            Q.   Okay.  If you look at the question beginning

19       on Line 7, you are discussing periodic reviews conducted

20       in 2009 regarding key decisions about the EPU project,

21       is that correct?

22            A.   I want to make sure that we have the same --

23            Q.   I know, you have many sets of testimony.  It's

24       March 1, 2011; EPU 2009.  Mine has a purple cover, if

25       that's any help.

FLORIDA PUBLIC SERVICE COMMISSION

783

1            A.   Okay.  Page 15, and the question is whether

2       this is in regard to the answer to the question what

3       periodic reviews were conducted?

4            Q.   Yes.

5            A.   That says conducted in 2010.  Hold on.  Let me

6       go back one.  Sorry.

7                 CHAIRMAN GRAHAM:  That's all right.

8       BY MS. KAUFMAN:

9            Q.   Are you with me?

10            A.   I'm with you.

11            Q.   Okay.  So we are looking at the question on

12       Page 7 about the periodic reviews conducted in 2009.

13       And you talk about regularly scheduled meetings in

14       regard to the uprate project and performance.  Do you

15       see that?

16            A.   Not on page -- Page 15, Line 7, correct?

17            Q.   That's the question.

18            A.   Got it.

19            Q.   And the following answer, and beginning on

20       Line 9 you talk about regularly scheduled meetings.  Do

21       you see where I am?

22            A.   I do.

23            Q.   Okay.  Now that we're at the right place, my

24       question is in regard to those regularly scheduled

25       meetings, prior to your assuming the position of VP

FLORIDA PUBLIC SERVICE COMMISSION

784

1       Uprates, did you attend any of those meetings?

2            A.   No, I did not.

3            Q.   So the information that's contained in the --

4       let's say from Line 12 where the bullets start over to

5       the next page, any information in there that refers to

6       prior to your assuming the VP Uprates, you received that

7       information from other FPL members, staff members?

8            A.   I received that information from other FPL

9       staff members on the projects, as well as an examination

10       of the company's records and documentations, and we

11       provided those in discovery.

12            Q.   Does FPL have a witness that discusses what

13       went on in these meetings prior to your taking over?

14       Have they presented a witness on that topic in this

15       hearing that you are aware of?

16            A.   In this hearing?

17            Q.   Yes.

18            A.   I'm sorry, are you asking me is there a

19       witness that was present in those meetings here at this

20       hearing?

21            Q.   Yes.  Is there a witness that was there and

22       can tell us what occurred in those meetings?

23            A.   There is no witness that is here that was in

24       those meetings, but I as a witness through an

25       examination of the documents from those meetings know

FLORIDA PUBLIC SERVICE COMMISSION

785

1       what occurred in those meetings, based on a review of

2       the documents.  Although I cannot obviously account for

3       100 percent of what occurred or was said in each one of

4       those meetings, not actually having been present.

5                 MR. ANDERSON:  FPL would also just indicate

6       that Mr. Stall, our Chief Nuclear Officer at the time,

7       is a witness in this case.

8       BY MS. KAUFMAN:

9            Q.   If you turn to Page 27 of that same set of

10       testimony, and if you would look at Line 12.  The

11       question asks you about the management of major EPU

12       project vendors in 2009, is that correct?

13            A.   Correct.

14            Q.   Did you have any personal involvement in

15       managing vendors in 2009 prior to your assumption of the

16       VP uprate position?

17            A.   I did not have personal direct involvement in

18       managing the vendors prior to August 1, 2009.  Again,

19       similar to the other question, the same senior people

20       who are on the project, those same people are the ones

21       that were primarily responsible for managing the

22       vendors.

23            Q.   And those individuals are not witnesses in

24       this case, correct?

25            A.   No, I represent them.

FLORIDA PUBLIC SERVICE COMMISSION

786

1            Q.   Turn over to Page 28.  Beginning on Line 12,

2       you're talking about activities occurring in the second

3       quarter of 2009.  Do you see that?

4            A.   That is correct.

5            Q.   You weren't personally involved in those

6       activities, were you?

7            A.   Yes, I got involved with the project in July.

8       Well, July is not in the second quarter.  So, no, I

9       wasn't directly involved.  My involvement was a

10       continuation of those efforts from the second quarter,

11       and that was a part of our transition and turnover as we

12       reorganized the project team.

13            Q.   Okay.  I'm going to switch to another set, and

14       I want to see if we can get on the same page, and that

15       is your EPU 2010 testimony.  Mine has a green cover, if

16       that helps.

17                 I'm sorry, I gave you the wrong reference.

18       I'm going to look at May 2011.  I'm sorry.  And I'm

19       going to look at Page 11, which has to do with schedule

20       change.

21                 CHAIRMAN GRAHAM:  Ms. Kaufman, would you say

22       that reference again?

23                 MS. KAUFMAN:  Yes.  It's May 2011, nuclear

24       power plant cost-recovery for the years ending

25       December 2011 and 2012.  And it's Page 11.  It has a tan

FLORIDA PUBLIC SERVICE COMMISSION

787

1       cover.

2                 THE WITNESS:  May 2, 2011, Page 11.

3       BY MS. KAUFMAN:

4            Q.   And let's wait until everybody gets with us.

5                 Beginning on Line 14, there is a question

6       about unanticipated schedule changes this year.  Do you

7       see that?  The question is, "Were there any

8       unanticipated schedule changes this year?"

9            A.   Yes.

10            Q.   And your answer discusses an outage at the St.

11       Lucie Unit, correct?

12            A.   That is correct.

13            Q.   How long was this outage?

14            A.   I don't recall the exact duration, so I would

15       need to check that, but it was on the order of about,

16       about 120 days.

17            Q.   And you tell us in your testimony here that

18       the outage was related to an incident involving the

19       Siemens' personnel, is that correct?

20            A.   That is correct.  We had a work stoppage due

21       to a human error during the generator rewind, that is

22       correct.

23            Q.   And Siemens in this instance is the vendor

24       working on the turbine generator, is that correct?

25            A.   Yes.  The turbine generators at our Florida

FLORIDA PUBLIC SERVICE COMMISSION

788

1       units, the original equipment manufacturer is the

2       Siemens Corporation, and so they are the -- quite

3       frankly, they supply these machines worldwide, and they

4       were the vendor that we contracted to do the uprate on

5       the machines.  In this particular case, the scope of the

6       work was to replace both the low-pressure turbines which

7       drive the generator, and do a complete rewind and rotor

8       replacement on the generators.  So it's quite extensive

9       work, very labor intensive, and these are the experts

10       that do this for a living.

11            Q.   And there was an issue as you describe it

12       there that required this outage, correct?

13            A.   There was a human error made where as a part

14       of the generator rewind process, they change out a

15       portion of what is called the generator core iron.

16       There is literally thousands of these laminate sheets

17       that make up the generator core, and they can only be

18       removed and installed by hand.  And in that process,

19       they have a tool that they use which looks simply no

20       different than a round bar about a half-inch diameter

21       and about 18 inches long to align in the process.

22                 And, unfortunately, the worker pushed it down

23       one of the ventilation holes and didn't notice it, and

24       then on the close-out inspection it was missed.  And so

25       when we performed an electrical test, because that pin

FLORIDA PUBLIC SERVICE COMMISSION

789

1       was in there, it caused damage to the generator core

2       iron, and so that had to be repaired.

3            Q.   And so when you say human error, we are

4       talking about a mistake that one of the vendor's

5       employees made on the project as you just described it?

6            A.   That is correct.  And like I said, Siemens,

7       they're the equipment experts.  And as typical, not only

8       us, but standard industry practice is you would bring in

9       the OEM for this type of work.  It involves hundreds of

10       workers, actually, 24/7 type of operation for over two

11       months to do just this scope of work.  And obviously it

12       would not be practical for us to employ that number of

13       people and turn them into turbine generator experts.  So

14       the standard practice is to bring in the expert.

15                 We do provide oversight, and logistic support,

16       and audits of their procedures and their training and

17       things like that to ensure quality work.  But, as with

18       any major construction project, you cannot totally

19       eliminate human error.  The standard of perfection is

20       just not achievable.  The best you do is provide

21       intrusive oversight and minimize the risk.

22            Q.   This 120-day outage, is that going to result

23       in some costs that is unanticipated?

24            A.   Yes, there are -- certainly there's a cost

25       impact with the extent of the outage.  There is the cost

FLORIDA PUBLIC SERVICE COMMISSION

790

1       impact to the project itself.  There is cost associated

2       to the plant, because obviously they are in support of

3       the outage, as well as Siemens had some costs involved

4       in that.  And --

5            Q    Excuse me.

6            A    Go ahead.

7            Q.   I was going to ask if you could provide us

8       with an estimate of what you think the cost of this

9       120-day outage was?

10                 MR. ANDERSON:  I'm going to object.  The

11       question is based on facts not in evidence.  There was a

12       120-day refueling outage.  A portion of it was extended

13       due to this item, and this is being continually referred

14       to as if it were a 120-day outage caused by this

15       personnel error.  And I have listened to it a couple of

16       times.  With the third time, I will just ask that the

17       questions reflects accurately what the witness has

18       stated, which is it was a little bit of an outage

19       extension and go from there.

20                 CHAIRMAN GRAHAM:  Ms. Kaufman, can you restate

21       your question.

22                 MS. KAUFMAN:  Yes.  I apologize.  I thought I

23       was repeating what the witness said, which was 120 days.

24                 THE WITNESS:  Can I clarify?

25                 MS. KAUFMAN:  Excuse me.

FLORIDA PUBLIC SERVICE COMMISSION

791

1                 THE WITNESS:  The refueling outage, which

2       obviously involved refueling the reactor, as well as all

3       the preventative maintenance, as well as this uprate

4       that we are doing with other planned major projects that

5       we had not related to EPU, that outage duration was

6       about 120 days.  The work stoppage and this human error,

7       recovery from that did impact that outage duration.  We

8       estimated it about 23 days.

9                 MS. KAUFMAN:  Okay. Thank you for that

10       clarification.

11       BY MS. KAUFMAN:

12            Q.   So the outage time that was related to the

13       human error and the unanticipated schedule change you

14       are talking about was about 23 days, correct?

15            A.   I wish it were that simple.  There's other

16       activities that are also -- you know, other activities,

17       other maintenance, other delays that are occurring in

18       parallel.  If other things would have gone exactly

19       according to plan, let's just say that the impact to

20       Siemens was definitely 23 days.  They were definitely on

21       the project 23 days longer than what they anticipated

22       and longer than what we had anticipated.  There was

23       other drivers in the outage that determined the overall

24       duration that are outside of the EPU scope.

25            Q.   And I just want to discuss with you the

FLORIDA PUBLIC SERVICE COMMISSION

792

1       Siemens issue only, so that will make our discussion

2       more clear, I hope.

3            A.   Okay.

4            Q.   And I think you agreed earlier that there

5       obviously is a cost to the 23 days, correct?

6            A.   That is correct.

7            Q.   Have you or FPL estimated what that cost is?

8            A.   Yes, we have.

9            Q.   And what is that?

10            A.   We're in commercial negotiations right now

11       with Siemens over what we think Siemens is liable for

12       and what they should have to pay.  So I'm a little

13       hesitant to put those numbers out there.  I can say

14       this, that as a part of the EPU project we have what we

15       call a risk register, and so anyone, either internal or

16       external, can identify an issue or problem that could

17       have an impact on schedule, quality costs, any number of

18       factors, and we will capture that in our risk register.

19       And so we identified a potential risk of as much as

20       $15 million impact.  At this stage it's going to be

21       quite a bit less than that, but as I said, we are still

22       in commercial discussion with Siemens over the claim.

23                 Is that a sufficient answer?

24            Q.   Yes.  And I'm certainly not intending to have

25       you divulge anything that is confidential in a public

FLORIDA PUBLIC SERVICE COMMISSION

793

1       forum.  And let me just ask you this:  In regard to the

2       amount that is in contention with Siemens as to who

3       would bear that risk, is it Florida Power and Light's

4       view that the risk of that amount rests with Siemens?

5            A.   There is definitely an amount that goes back

6       to Siemens as standard industry practice.  As I

7       mentioned refueling outages, set EPU aside, refueling

8       outages, a big complex refueling outage is typically

9       30 to 40 days involving hundreds of supplemental workers

10       and contractors.  And to do those outages in a short

11       period -- in as short a practical period of time, you

12       bring in the OEMs to do things like the refueling

13       portion, to the things like --

14                 MS. KAUFMAN:  Chairman Graham, I hate to

15       interrupt, but I think my question was a lot simpler

16       than where Mr. Jones wants to go.

17                 CHAIRMAN GRAHAM:  Ms. Kaufman, I actually have

18       to disagree with you.  Having lived through many, many

19       outages myself, I know just because you schedule one

20       outage and something else happens arbitrarily to that,

21       it's kind of hard to pinpoint and directly align that.

22       And I think what he is trying to do is explain his

23       answer to you; you may want to be more concise about the

24       question you ask.

25

FLORIDA PUBLIC SERVICE COMMISSION

794

1       BY MS. KAUFMAN:

2            Q.   Were you finished?  I think the Chairman --

3            A.   Okay.  What was the question?  Could you

4       repeat the question?

5            Q.   Yes.

6                 I will just try to be more concise, Mr.

7       Chairman.

8                 Between the amount that is in dispute between

9       FPL and Siemens as to this human error incident, just

10       the incident involving the tool that you have explained,

11       is it Florida Power and Light's view that the risk of

12       that is on Siemens rather than on Florida Power and

13       Light?

14            A.   A portion of the risk is on Siemens, a portion

15       is on Florida Power and Light.

16            Q.   And that is an area that you are attempting to

17       continue to work with Siemens on?

18            A.   That is correct.  And all I wanted to add to,

19       if I may, is that there are limits of liability on all

20       of these contracts and major contract vendors.

21       Obviously, it is not practical for me to have a

22       workforce of 3,000 people at a nuclear plant to just

23       accommodate periodic refueling outages.  So we bring in

24       the OEMs for the refueling portion and the turbine

25       generator portion, and they all have LDs because they

FLORIDA PUBLIC SERVICE COMMISSION

795

1       couldn't possibly accept the risk of lost generation or

2       generation replacement.  It would put them out of

3       business.  Thank you.

4                 MR. ANDERSON:  Just for clarification, could

5       the witness say what LDs are?

6                 THE WITNESS:  Limits to liability.

7       BY MS. KAUFMAN:

8            Q.   Do you know if it is the company's intent to

9       come and seek whatever portion of the amount it is that

10       flows to Florida Power and Light from this incident, to

11       seek that from ratepayers?

12            A.   I will only speak to the EPU scope, if I may,

13       and that is that that portion that we are able to hold

14       Siemens liable for, they will be liable for.  And the

15       balance of that is a part of project risk and project

16       expense and, therefore, it is our view, is recoverable.

17                 CHAIRMAN GRAHAM:  Did that answer your

18       question?

19                 MS. KAUFMAN:  Yes.

20       BY MS. KAUFMAN:

21            Q.   So the answer to my question is, yes, you

22       would try to recover that from ratepayers?

23            A.   Yes.

24                 MS. KAUFMAN:  Thank you, Mr. Chairman, for

25       indulging me.  That's all I have.

FLORIDA PUBLIC SERVICE COMMISSION

796

1                 CHAIRMAN GRAHAM:  That's fine.  I didn't

2       really mean to interrupt, but I have lived that life.

3       Any other intervenors?

4                          CROSS EXAMINATION

5       BY MR. McGLOTHLIN:

6            Q.   Hello, Mr. Jones.

7            A.   Hello.

8            Q.   You indicated that you assumed your position

9       of vice-president of uprates in August 2009, is that

10       correct?

11            A.   That's correct.

12            Q.   Now, in earlier portions of the hearing today

13       with the prior witnesses, references were made to the

14       July meeting, or the executive steering committee, and

15       to certain estimates, or revised estimates of capital

16       costs that were the subject of that meeting.

17                 As the incoming Vice-President of Uprates, you

18       would have participated in the presentation to the

19       executive steering committee that was packaged in August

20       and presented in September 2009, were you not?

21            A.   Yes, but I want to be clear in regards to my

22       presentation -- my participation is that I was present

23       for the meeting.  I did not participate in the

24       preparation of the material for the meeting.

25            Q.   Are you familiar with the material that was

FLORIDA PUBLIC SERVICE COMMISSION

797

1       prepared for that meeting?

2            A.   Yes, I am.

3            Q.   Is it true that the project managers revised

4       the estimated capital costs beyond the increase that was

5       reflected in the July presentation?

6            A.   I'm sorry, could you repeat the question?

7            Q.   Yes.  There has been testimony about the

8       revised estimates that Mr. Reed, among others, has

9       described, increasing the estimated capital costs

10       associated with the EPU by $300 million.

11                 My question to you is isn't it true that when

12       the project managers prepared a presentation in August

13       of 2009 that estimate was revised upwards again?

14            A.   To which August presentation are you referring

15       to?

16            Q.   The August presentation to the executive

17       steering -- the August presentation prepared for the

18       meeting of the executive steering committee that

19       occurred on, I think, August or September 9th, 2009?

20            A.   Okay.  I wasn't -- to the best of my

21       recollection, there was no August ESC presentation.  So

22       are you referring to a presentation that was presented

23       on September 9th?

24            Q.   Prepared in August, presented in September.

25            A.   Prepared in August, presented in September.

FLORIDA PUBLIC SERVICE COMMISSION

798

1       The answer to that question is yes, and I would like to

2       clarify that the preliminary numbers to which due

3       diligence was in progress for from the July meeting,

4       those preliminary numbers were retained as a part of the

5       project forecast going forward while the project team

6       continued their due diligence, and so there was scope

7       added and scope deleted and other changes that were

8       captured as a part of that project forecast going

9       forward.  So, yes, it would be expected and did occur

10       that those numbers were different for the September 9

11       presentation.

12            Q.   They were different and they were higher than

13       July, correct?

14            A.   That is correct.  I'd also like to point out

15       that those numbers in July, there was at least

16       $200 million of scope that had not been through enough

17       engineering analysis to have management review or

18       approval, which is an example of the due diligence that

19       I am referring to that had been ongoing from July, and

20       we did not complete until April of 2010.

21            Q.   And when that was completed in April of 2010,

22       did the numbers turn out to be higher than they were

23       either in August or July?

24            A.   Yes.  We revised the nonbinding cost estimate

25       in April of 2010 following our due diligence in regards

FLORIDA PUBLIC SERVICE COMMISSION

799

1       to decisions on whether to continue with that particular

2       engineering procurement contractor, whether to split

3       part of that work out from the EPC self-perform part of

4       the work, and advanced CERT (phonetic) engineering

5       analysis to determine what scope would be retained and

6       what scope would be eliminated.

7            Q.   The net effect of which was to increase the

8       estimates in July, again in September, and again in

9       April, correct?

10            A.   Yes.  And to be clear, the project forecast

11       really changes on a week-to-week basis, but we don't

12       revise the nonbinding cost estimate.  And I mentioned

13       the risk register before, and there's risk register

14       meetings on a weekly basis to which people identify

15       risks associated with the project, and you quantify

16       that, and so that forecast fluctuates on a weekly basis.

17       It is true that at the end of the month we close the

18       book on the project forecast, and it is what it is.  And

19       that is what we communicate to the senior executives

20       with appropriate qualification of the certainty of those

21       numbers.  If you examine the September executive

22       steering committee presentation, which has been provided

23       in discovery, you will see that we qualified those costs

24       as only about 30 percent of those numbers in our view

25       were certain, and that 7 percent were still not very

FLORIDA PUBLIC SERVICE COMMISSION

800

1       well-defined, and that was based on engineering

2       progress.

3            Q.   Thirty percent was certain -- only 30 percent

4       were certain because that represented the status of

5       design engineering at the time, correct?

6            A.   Not entirely.  The status of engineering

7       design, status of identification of long-lead material,

8       and the costs associated with that material, and

9       certainty around near term staffing for the upcoming

10       work.

11            Q.   It is true, however, is it not, that price

12       certainty increases as the design engineering process

13       progresses?

14            A.   It is true that cost certainty does increase

15       as design engineering progresses and construction and

16       planning and implementation advances.

17            Q.   At Page 32 of your May testimony, and I'm

18       looking at the answer that begins at Line 6, you say the

19       progression of project activities over the last several

20       years provides FPL with additional insight to revise its

21       nonbinding cost forecast.  However, the project is still

22       in the design engineering phase, and there remains an

23       expected level of uncertainty with respect to project

24       scope.  Do you see that?

25            A.   Yes.

FLORIDA PUBLIC SERVICE COMMISSION

801

1            Q.   If you would, briefly define what you mean by

2       designing engineering?

3            A.   Yes.  Design engineering is that process which

4       you have identified the need to modify or replace a

5       component to be able to accommodate the higher energy or

6       maybe accommodate a larger structural component,

7       whatever that modification may be.  And so you will have

8       a team of design engineers work through calculations and

9       produce the design similar to if you were going to have

10       a house built.  You would go to an architectural

11       engineer who would design the home and produce the

12       detailed drawings and calculations to support the

13       building of the house.  And that's what I mean by design

14       engineering.

15            Q.   And what percentage of design engineering of

16       the EPU has been completed, as we sit here today?

17            A.   Approximately 70 percent.

18            Q.   And expressed in what terms, Mr. Jones?

19            A.   That 70 percent is derived at by looking at

20       the total forecasted hours it would take to complete all

21       the modifications, which is roughly on the order of

22       about 960,000 engineering hours, and roughly 70 percent

23       of those hours have been earned.  There's several ways

24       to measure engineering progress, and I can explain it in

25       three sentences, if you want.

FLORIDA PUBLIC SERVICE COMMISSION

802

1            Q.   Let me pose a couple of questions that I think

2       will give you that opportunity.  Seventy percent in

3       terms of hours earned, that unit does not differentiate

4       between those modifications that are completed, those

5       modifications that are partially completed, and those

6       modifications that are yet to be initiated, correct?

7            A.   That is correct.  There are over 200

8       modifications that have been identified as needed to

9       support the extended power uprate, and so those

10       modifications are all in some stage of completion.  Does

11       that answer your question?

12            Q.   Yes.  And to the extent that design

13       engineering has not been completed, it is possible,

14       then, that as that work progresses additional scope may

15       be identified, correct?

16            A.   Yes, it is possible as design engineering

17       progresses that additional scope could be identified.

18       And so, to that point, here's two of the considerations

19       when we prioritize the engineering that we want done and

20       when.  We want the engineering done in time to support

21       those modifications that we want to make in the next

22       outage, and so those have the highest priority.  The

23       next highest priority of modifications are those that

24       have the biggest risk to either schedule or cost, or the

25       most complex, and we want to advance that engineering as

FLORIDA PUBLIC SERVICE COMMISSION

803

1       soon as possible because, again, that brings greater

2       certainty to cost and schedule.  And so I really think I

3       need to describe really briefly how we measure

4       engineering progress, if I may.

5                 MR. McGLOTHLIN:  Commissioner, he has answered

6       my question.  I'm ready to go on.

7                 CHAIRMAN GRAHAM:  Okay.  Please continue.

8                 MR. McGLOTHLIN:  I have a handful of

9       additional questions, but I need a bit of guidance from

10       counsel for FPL.  During of the deposition of Mr. Jones,

11       I posed some questions that relate to the nature and

12       aspects of the EPC contract.  I know that FPL filed a

13       request for confidentiality for at least some of that

14       transcript.  I don't have the redacted portion, so I'm

15       not clear as to whether those particular questions and

16       answers were treated as confidential.  And I don't want

17       to tread on anything that is shielded, and I make this

18       offer.  I'm perfectly happy to deal with this by

19       excerpting that portion of the transcript of the

20       deposition and treat that as my cross-examination of the

21       witness.  And I could do that tonight, if you prefer.

22                 MR. ANDERSON:  We appreciate that offer.  We

23       have reviewed and determined the redaction, and we don't

24       have that here, but I think that is a very streamlined

25       and appropriate way to proceed.  We accept that offer.

FLORIDA PUBLIC SERVICE COMMISSION

804

1                 MR. McGLOTHLIN:  Then I have no further

2       questions.

3                 CHAIRMAN GRAHAM:  Okay.

4                 SACE.

5                 MR. WHITLOCK:  No questions, Mr. Chairman.

6                 CHAIRMAN GRAHAM:  Anybody else?  Okay.  Staff?

7                 MR. YOUNG:  No questions.

8                 CHAIRMAN GRAHAM:  Commission board?  Okay.

9                 Redirect.

10                         REDIRECT EXAMINATION

11       BY MR. ANDERSON:

12            Q.   Mr. Jones wants to explain how do you measure

13       engineering certainty, and I am very interested to know,

14       too, so that is my question.

15                 CHAIRMAN GRAHAM:  Why did I know that you were

16       going to ask that question?  (Laughter.)

17                 Mr. Jones.

18            A    The reason I really wanted to explain that is

19       because the executive steering committee slides, you've

20       got to remember they are for the senior executives of

21       the company and not necessarily the people that run

22       construction projects, and there has just been so many

23       occasions where things are taken out of context off the

24       PowerPoint slide, which is not a detailed project

25       control book.

FLORIDA PUBLIC SERVICE COMMISSION

805

1                 We measure engineering progress several ways.

2       As I mentioned, there is roughly 215 modification

3       packages required, and we are implementing this EPU over

4       a number of outages, so we want those engineering

5       modification packages completed for the upcoming outage.

6       And so, for example, for the St. Lucie Unit 1 outage

7       coming up around November the 27th, 33 of the 47 are

8       complete.  Actually what I would call done done.  And

9       that is one way to measure progress.

10                 The other way is that for every single

11       modification there is a detailed analysis or forecast on

12       the number of engineering hours it should take to

13       complete that modification.  And it will involve

14       mechanical, civil, electrical, INC engineering

15       disciplines.  And you create mileposts that says for 100

16       hours worth of engineering, you should have completed so

17       many calculations, or for 1,000 hours of engineering.

18       So some of these design packages we require maybe 20,000

19       hours of work to complete.  And so we use an earned

20       value measurement; and, that is, for the number of hours

21       you have expended on the project, have you actually

22       earned those hours?  So when I say 70 percent complete,

23       that is based on the actual hours earned, actual

24       progress as compared to those milestones.  Thank you.

25                 CHAIRMAN GRAHAM:  Mr. Anderson.

FLORIDA PUBLIC SERVICE COMMISSION

806

1                 MR. ANDERSON:  FPL has nothing further, but we

2       have some exhibits to offer.  FPL offers into evidence

3       what have been premarked on Staff's Exhibit List as

4       Exhibits 49 to 75, please.

5                 CHAIRMAN GRAHAM:  Forty-nine has already been

6       added, but we will do 50 through 79 (sic), but we have

7       already done 60 and 61, and 69 and 70.

8                 MR. YOUNG:  Yes, and 49, I think.

9                 CHAIRMAN GRAHAM:  I'm sorry?

10                 MR. YOUNG:  And 49.

11                 (Exhibits 49 through 75 admitted into

12       evidence.)

13                 CHAIRMAN GRAHAM:  Yes.  Mr. Anderson, anything

14       else?

15                 MR. ANDERSON:  No, sir, there is not.  And we

16       have our next witness prepared to proceed.

17                 CHAIRMAN GRAHAM:  And this witness is coming

18       back as well for rebuttal?

19                 MR. ANDERSON:  This witness, Mr. Jones, is

20       returning for rebuttal.  Yes, he has rebuttal, so he is

21       coming back.  He is shaking his head and smiling at me

22       wishfully.

23                 CHAIRMAN GRAHAM:  Thank you, sir, for your

24       testimony.

25                 THE WITNESS:  Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

807

1                 (Transcript continues in sequence in

2       Volume 7.)

3

4

5

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

808

1

2       STATE OF FLORIDA    )

3                           :    CERTIFICATE OF REPORTER

4       COUNTY OF LEON      )

5

I, JANE FAUROT, RPR, Chief, Hearing Reporter

6       Services Section, FPSC Division of Commission Clerk, do

hereby certify that the foregoing proceeding was heard

7       at the time and place herein stated.

8                 IT IS FURTHER CERTIFIED that I

stenographically reported the said proceedings; that the

9       same has been transcribed under my direct supervision;

and that this transcript constitutes a true

10       transcription of my notes of said proceedings.

11                 I FURTHER CERTIFY that I am not a relative,

employee, attorney or counsel of any of the parties, nor

12       am I a relative or employee of any of the parties'

attorney or counsel connected with the action, nor am I

13       financially interested in the action.

14                 DATED THIS 15th day of August, 2011.

15

16

___________________________________________

17                         JANE FAUROT, RPR

Official FPSC Hearings Reporter

18                          (850) 413-6732

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION