984

1                             BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

3                                     DOCKET NO. 110009-EI

4       In the Matter of:

5       NUCLEAR COST RECOVERY CLAUSE.

______________________________/

6

7                               VOLUME 7

8                        Pages 984 through 1162

9

10       PROCEEDINGS:        HEARING

11       COMMISSIONERS

PARTICIPATING:      CHAIRMAN ART GRAHAM

12                           COMMISSIONER LISA POLAK EDGAR

COMMISSIONER RONALD A. BRISÉ

13                           COMMISSIONER EDUARDO E. BALBIS

COMMISSIONER JULIE I. BROWN

14

DATE:               Thursday, August 11, 2011

15

TIME:               Commenced at 9:33 a.m.

16                           Concluded at 11:38 p.m.

17       PLACE:              Betty Easley Conference Center

Room 148

18                           4075 Esplanade Way

Tallahassee, Florida

19

REPORTED BY:        LINDA BOLES, RPR, CRR

20                           Official FPSC Reporter

(850) 413-6734

21

APPEARANCES:        (As heretofore noted.)

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

985

1                              I N D E X

2                              WITNESSES

3

NAME:                                         PAGE NO.

4

BRIAN D. SMITH

5       Direct Examination by Mr. McGlothlin               989

Prefiled Direct Testimony Inserted                 991

6

WILLIAM R. JACOBS, JR.

7       Direct Examination by Mr. McGlothlin              1003

Prefiled Direct Testimony Inserted                1006

8       Redirect Examination by Mr. McGlothlin            1078

9       DAVID RICH and LYNN FISHER (Panel)

Direct Examination by Mr. Young                   1067

10       Prefiled Direct Testimony Inserted                1071

Cross Examination by Ms. Kaufman                  1078

11       Cross Examination by Mr. Anderson                 1082

Redirect Examination by Mr. Young                 1090

12

KATHY L. WELCH

13       Prefiled Direct Testimony Inserted                1093

14       ARMANDO OLIVERA

Direct Examination by Mr. Anderson                1097

15       Prefiled Rebuttal Testimony Inserted              1099

Cross Examination by Mr. McGlothlin               1102

16       Cross Examination by Ms. Kaufman                  1104

Redirect Examination by Mr. Anderson              1120

17

TERRY DEASON

18       Direct Examination by Mr. Anderson                1123

Prefiled Rebuttal Testimony Inserted              1125

19       Cross Examination by Ms. Kaufman                  1143

Cross Examination by Mr. McGlothlin               1147

20       Redirect Examination by Mr. Anderson              1156

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

986

1                              EXHIBITS

2       NUMBER:                                 ID.      ADMTD.

3       100                                               1003

4       101                                               1003

5       102                                               1066

6       103                                               1066

7       104                                               1066

8       105                                               1066

9       106                                               1066

10       107                                               1066

11       108                                               1066

12       109                                               1066

13       110                                               1066

14       111                                               1066

15       112                                               1066

16       113                                               1066

17       114                                               1066

18       115                                               1091

19       116                                               1091

20       117                                               1092

21       118                                               1092

22       119                                               1092

23       120                                               1092

24       130                                               1160

25

FLORIDA PUBLIC SERVICE COMMISSION

987

1                              EXHIBITS

2       NUMBER:                                 ID.      ADMTD.

3       199       Excerpts from Kundalkar depo  1067      1067

4       200       EPU 2009 Management Change,   1084      1091

FPSC Audit Work Paper

5

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

988

1                         P R O C E E D I N G S

2                 (Transcript follows in sequence from

3       Volume 6.)

4                 CHAIRMAN GRAHAM:  Good morning, everyone.

5       Glad to see everybody made it back here safely today.

6       We seem to be making pretty good headway, so I see no

7       sense in slowing the train down.  Let's keep moving.

8                 We will reconvene, and this is Docket Number

9       110009-EI, nuclear cost recovery clause.  And the date

10       is August the 11th, I believe.  I say all that for the

11       record.

12                 If I remember correctly, we ended with FP&L

13       Witness Steven Sim.

14                 MR. YOUNG:  Yes, sir.

15                 CHAIRMAN GRAHAM:  And we dismissed him, well,

16       for the time being, and so now we're at OPC's Witness

17       Brian Smith.

18                 MR. McGLOTHLIN:  Mr. Smith is here.  He has

19       not been sworn at this point.

20                 CHAIRMAN GRAHAM:  Let's go ahead and swear in

21       everybody that's here that's scheduled to speak today

22       and get that done.

23                 If I can get you to stand and raise your right

24       hand.

25                 (Witnesses collectively sworn.)

FLORIDA PUBLIC SERVICE COMMISSION

989

1                 MR. YOUNG:  Mr. Chairman, as Mr. Smith comes

2       to the stand, I would note that Florida Power & Light

3       has passed out the complete Exhibit Number 195.

4                 CHAIRMAN GRAHAM:  Okay.

5                 MR. YOUNG:  And this is based on the rule of

6       completeness they offered yesterday.

7                 CHAIRMAN GRAHAM:  We've already entered

8       195 into the record?

9                 MR. YOUNG:  Yes, sir.

10                 CHAIRMAN GRAHAM:  Thank you.

11                 Mr. McGlothlin.

12                            BRIAN D. SMITH

13       was called as a witness on behalf of The Citizens of the

14       State of Florida and, having been duly sworn, testified

15       as follows:

16                          DIRECT EXAMINATION

17       BY MR. McGLOTHLIN:

18            Q    Please state your full name and business

19       address, sir.

20            A    My name is Brian Smith, and my business

21       address is 1850 Parkway Place, Suite 800, Marietta,

22       Georgia, 30067.

23            Q    By whom are you employed, Mr. Smith?

24            A    I'm employed by GDS Associates.

25            Q    At our request, did you prepare and submit

FLORIDA PUBLIC SERVICE COMMISSION

990

1       prefiled testimony in this proceeding?

2            A    Yes, I did.

3            Q    Do you have that document before you?

4            A    I do.

5            Q    Do you have any changes, additions or

6       corrections to make to the prefiled testimony?

7            A    I do not.

8            Q    Do you adopt the content of the prefiled

9       testimony as your testimony today?

10            A    Yes.

11                 MR. McGLOTHLIN:  I request that the prefiled

12       testimony be inserted into the record at this point.

13                 CHAIRMAN GRAHAM:  We will insert the prefiled

14       testimony of Mr. Smith into the record as though read.

15       BY MR. McGLOTHLIN:

16            Q    Did you also prepare an exhibit to your

17       testimony, Mr. Smith?

18            A    Yes, I did.

19            Q    Do you have any changes or corrections to that

20       exhibit?

21            A    I do not.

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1000

1       BY MR. McGLOTHLIN:

2            Q    Have you prepared a summary of your testimony?

3            A    I have.

4            Q    Please proceed.

5            A    Thanks.

6                 Good morning.  The purpose of my testimony is

7       to suggest a means of evaluating the total cost of

8       Florida Power & Light's EPU project.  FPL has excluded

9       sunk costs from its annual evaluation of the project,

10       and its witnesses have provided testimony that shows

11       positive benefits to Florida ratepayers using that

12       methodology.

13                 Although I agree that sunk costs are typically

14       excluded from feasibility analyses, I maintain that sunk

15       costs should be included in this process in order to

16       determine if ratepayers are better off with a resource

17       portfolio that includes the EPU project versus a

18       portfolio that does not include the EPU project.

19                 The EPU project is evaluated annually and, for

20       each evaluation, costs spent to date are excluded from

21       the feasibility analysis.  At the same time, total EPU

22       costs have increased since the last evaluation was

23       produced.  The effect of these two things in combination

24       is that the total cost impact of the EPU project will

25       never be reflected in the benefit matrix, which is

FLORIDA PUBLIC SERVICE COMMISSION

1001

1       included in FPL's testimony.

2                 I'm at this hearing on behalf of Florida

3       ratepayers.  I think it's reasonable to show how the EPU

4       portfolio costs to the ratepayer compares to the cost to

5       the ratepayer if the EPU project had not been pursued

6       and an alternate resource portfolio were developed.

7                 The valuations using that approach show that

8       the economics have shifted during the course of project

9       development.  I think it's reasonable to ask why that

10       has happened and to examine the causes of the changes in

11       the projections of total costs.

12                 My testimony shows the impact of an adjustment

13       to FPL's medium fuel and medium environmental compliance

14       cost benefit.  If sunk costs are included in the

15       analysis, FPL's net benefit of $622 million for that

16       scenario turns into a net cost of 156 million.  These

17       values relate to testimony initially filed by FPL.

18                 Subsequent FPL testimony included a revised,

19       slightly lower net benefit for the same case.  When this

20       revised value is adjusted to include estimated impacts

21       of sunk costs, a slightly more negative cost results.

22                 My testimony also contains a recommendation

23       that FPL be required to use a breakeven approach in the

24       evaluation of the EPU project.  This would allow the

25       determination of how much can be invested in the EPU

FLORIDA PUBLIC SERVICE COMMISSION

1002

1       project before that investment yields a present value of

2       revenue requirements that exceeds the present value of

3       revenue requirements associated with a non-EPU

4       portfolio.  This breakeven amount should be the basis

5       used to determine the maximum amount allowed in rate

6       base for the EPU project.

7                 MR. McGLOTHLIN:  Does that conclude your

8       summary?

9                 THE WITNESS:  It does.

10                 MR. McGLOTHLIN:  Mr. Smith is available for

11       cross-examination.

12                 CHAIRMAN GRAHAM:  Okay.

13                 Florida Power & Light.

14                 MR. ANDERSON:  FPL has no cross-exam for the

15       witness, but notes that his testimony remains subject to

16       the standing objection stated in our motion to strike

17       yesterday.

18                 CHAIRMAN GRAHAM:  Okay.  So noted.

19                 Staff?  Other Intervenors?  No?

20                 MR. YOUNG:  No questions.

21                 CHAIRMAN GRAHAM:  Anybody from the board?  .

22                 Okay.  Do we need to enter any exhibits into

23       the record?

24                 MR. McGLOTHLIN:  I move 100 and 101.

25                 CHAIRMAN GRAHAM:  Let's move exhibits marked

FLORIDA PUBLIC SERVICE COMMISSION

1003

1       100 and 101 into the record.

2                 (Exhibits 100 and 101 admitted into evidence.)

3                 If that's -- then we're currently done with

4       this witness; is that correct?

5                 MR. McGLOTHLIN:  We have another witness.

6                 CHAIRMAN GRAHAM:  We're done with this

7       witness?

8                 MR. McGLOTHLIN:  Dr. Jacobs, yes.

9                 CHAIRMAN GRAHAM:  Thank you, sir.

10                 THE WITNESS:  Yes.

11                        WILLIAM R. JACOBS, JR.

12       was called as a witness on behalf of the Citizens of the

13       State of Florida and, having been duly sworn, testified

14       as follows:

15                          DIRECT EXAMINATION

16       BY MR. McGLOTHLIN:

17            Q    Please state your name and business address

18       for the record, sir.

19            A    My name is William Jacobs.  My address is 1850

20       Parkway Place, Marietta, Georgia.

21            Q    By whom are you employed, Dr. Jacobs?

22            A    I'm employed by GDS Associates.

23            Q    On behalf of OPC, did you prepare direct

24       testimony in this case?

25            A    Yes, I did.

FLORIDA PUBLIC SERVICE COMMISSION

1004

1            Q    Do you have that document before you?

2            A    I do.

3            Q    Do you have any changes, additions, or

4       corrections?

5            A    Yes, I do.  I have one change.  On page 16 of

6       my testimony, line 6, the end of that sentence on line

7       6 stating "90% completion of the work" should be

8       deleted.  And in place of that it should read,

9       "Completion of 90 design modification packages."

10                 MR. McGLOTHLIN:  We're in the process of

11       preparing a substitute page to accomplish that change,

12       Mr. Chairman.

13                 CHAIRMAN GRAHAM:  Okay.

14       BY MR. McGLOTHLIN:

15            Q    Do you have any additional corrections to

16       make, Dr. Jacobs?

17            A    No.  That's all.

18            Q    With that correction, do you adopt the

19       questions and answers in your prefiled testimony as your

20       testimony today?

21            A    Yes, I do.

22            Q    Did you also prepare exhibits to your

23       testimony that have since been marked as 102 through

24       114?

25            A    Yes, that's correct.

FLORIDA PUBLIC SERVICE COMMISSION

1005

1            Q    Have you prepared a summary for the

2       Commissioners?

3            A    Yes, I have.

4                 MR. McGLOTHLIN:  Excuse me.  I ask that the

5       prefiled testimony be inserted at this point.

6                 CHAIRMAN GRAHAM:  We will enter Dr. Jacobs'

7       prefiled testimony as though read.

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1049

1       BY MR. McGLOTHLIN:

2            Q    Please summarize your testimony for the

3       Commissioners.

4            A    I will.  Good morning, Mr. Chairman,

5       Commissioners.

6                 My testimony -- in my testimony I address

7       three issues that I have identified related to FPL's EPU

8       projects underway at Turkey Point 3 and 4 and St. Lucie

9       1 and 2.  These issues are FPL's flawed methodology for

10       estimating the long-term feasibility of the EPU

11       projects, exhibiting dramatic and rapid increases in

12       estimated costs, FPL's imprudence in selecting the

13       fast-track project management approach for the extremely

14       complex EPU projects when it had little grasp of what

15       the EPU projects would cost or what they needed to cost

16       to remain economically feasible, and finally FPL's

17       failure to update its estimate of EPU capital costs in

18       the 2009 hearing when it was clear that the then current

19       estimates were far above the costs that FPL maintained

20       was still valued.

21                 In my testimony in the 2010 NCRC proceeding, I

22       explained why the CPVRR methodology used by FPL to

23       demonstrate economic feasibility of the EPU project was

24       not appropriate and would provide misleading results

25       when applied to the EPU project due to the uncertain and

FLORIDA PUBLIC SERVICE COMMISSION

1050

1       rapidly increasing cost estimates.

2                 The continued cost increases experienced this

3       year validate my concerns of last year.  FPL has spent

4       approximately $700 million on the EPU projects, and the

5       original estimate presented in the need case of

6       $1.798 billion has increased $700 million to

7       $2.48 billion.  Since FPL has spent as much on the

8       project as the cost has increased, the estimated cost to

9       complete the project is essentially unchanged, and the

10       projects remain economically feasible, according to

11       FPL's methodology.

12                 This is obviously a situation in which the

13       results are just not credible.  I recommend that the

14       Commission require FPL to implement a breakeven cost

15       methodology for the EPU projects, as they have done for

16       the Turkey Point 6 and 7 project.

17                 I investigated how FPL got itself into this

18       situation.  I found that FPL adopted a fast track

19       management approach for the project in which FPL's

20       normal project development process was abandoned and

21       they committed to the project with essentially no

22       engineering completed, without a good idea of the cost

23       for the project, and without even knowing what the

24       project needed to cost to be economically feasible.

25       Because essentially none of the design was complete, it

FLORIDA PUBLIC SERVICE COMMISSION

1051

1       was not possible to receive fixed or firm price bids,

2       and the work is being constructed on a time and material

3       basis.

4                 Having been in the nuclear power business for

5       many years, this situation seemed unfortunately

6       familiar.  The last generation of nuclear power plants

7       were begun with incomplete designs, extremely optimistic

8       cost estimates, and built on a time and material basis.

9       I believe that most of us in this room know the results

10       of those projects:  Lengthy scheduled delays and massive

11       cost overruns.

12                 Based on the results of my review, I conclude

13       that FPL was imprudent to abandon their normal

14       construction processes and attempt the EPU projects on a

15       fast track basis.

16                 Finally, I was asked to review FPL's decision

17       to not update the Commission on the most recent cost

18       estimates for the EPU project during the 2009 NCRC

19       proceeding.  I reviewed the contemporaneous Executive

20       Steering Committee presentations in the June through

21       September 2009 time frame.  I reviewed e-mail

22       correspondence received in response to discovery.  I

23       reviewed Concentric Energy's report of their

24       investigation of this issue.  OPC issued a data request

25       essentially asking for all of the documents that

FLORIDA PUBLIC SERVICE COMMISSION

1052

1       Concentric reviewed and I reviewed those documents.

2                 By September 2009, the forecast cost of the

3       EPU projects increased by 444 million over the forecast

4       costs presented by FPL in May 2009.  As stated in my

5       testimony, I agree with FPL's consultant John Reed that

6       FPL should have made the Commission aware of those most

7       recent cost estimates.

8                 In my testimony I make the following

9       recommendations for this Commission's consideration.  I

10       recommend that the Commission direct FPL to employ a

11       breakeven analysis as the appropriate tool for which to

12       assess the long-term feasibility of the EPU project.  I

13       recommend that this Commission require FPL to perform

14       separate breakeven analyses for the St. Lucie and Turkey

15       Point EPU projects.  If the Turkey Point EPU project is

16       determined to be uneconomic based on this analysis, FPL

17       should be required to make an affirmative case for

18       continuing this project.

19                 I recommend that this Commission find that

20       FPL's decision to embark on EPU projects using a fast

21       track methodology was imprudent.  The impact of this

22       imprudence should be measured in terms of whether

23       resulting costs exceed the final breakeven analysis as

24       filed by FPL at the conclusion of the project and

25       reviewed and approved by the Commission.

FLORIDA PUBLIC SERVICE COMMISSION

1053

1                 Finally, I recommend that the Commission find

2       that FPL failed to provide the best, most current

3       information regarding its estimate of capital costs

4       during the September 2009 hearing when it elected to not

5       update and revise the May 2009 prefiled testimony with

6       information that was developed between the May filing

7       date and the August 2009 estimates prepared by EPU

8       project managers.

9                 That concludes my opening statement.

10                 MR. McGLOTHLIN:  Dr. Jacobs is available for

11       cross-examination.

12                 CHAIRMAN GRAHAM:  Are there any -- do any, any

13       of the Intervenors have any questions?

14                 MS. KAUFMAN:  I have no questions.  Thank you,

15       Mr. Chairman.

16                 MS. WHITE:  No, sir.  Thanks.

17                 CHAIRMAN GRAHAM:  Florida Power & Light?

18                 MR. ANDERSON:  No questions for the witness.

19       Thank you.

20                 CHAIRMAN GRAHAM:  Staff?

21                 MR. YOUNG:  Mr. Chairman, in lieu of cross for

22       this witness, OPC and the parties have agreed that Staff

23       can enter the deposition transcript of Witness Jacobs

24       into the record in lieu of cross.  And that would be

25       identified -- Staff requests that it be marked for

FLORIDA PUBLIC SERVICE COMMISSION

1054

1       identification purposes as Number 198.

2                 CHAIRMAN GRAHAM:  What will the short title

3       for that be?

4                 MR. YOUNG:  Deposition Transcript of Witness

5       Jacobs.

6                 CHAIRMAN GRAHAM:  Okay.

7                 (Exhibit 198 marked for identification.)

8                 MR. YOUNG:  And that will be provided to you.

9       We're making copies as we speak.

10                 MR. ANDERSON:  Chairman Graham, could the

11       record also reflect FPL's continuing objection to the

12       admissibility of the testimony for the reasons stated in

13       the motion to strike.

14                 CHAIRMAN GRAHAM:  So noted.

15                 Is Staff good?

16                 MR. YOUNG:  And with that, Staff has no

17       questions.

18                 CHAIRMAN GRAHAM:  Okay.

19                 To the Commission board.  Commissioner Edgar.

20                 COMMISSIONER EDGAR:  Thank you, Mr. Chairman.

21                 First, just for my benefit, a clarification

22       I'd like to ask Mr. Anderson.  Is the FPL objection to

23       all of this witness's prefiled testimony?

24                 MR. ANDERSON:  The objection is to the

25       portions which are specified in green and attached to

FLORIDA PUBLIC SERVICE COMMISSION

1055

1       the motion to strike, which address the legal matters

2       that we discussed at length yesterday.

3                 COMMISSIONER EDGAR:  All right.  Thank you.

4       But obviously you have no questions on any of the

5       remainder of the prefiled testimony.

6                 MR. ANDERSON:  That is correct.

7                 COMMISSIONER EDGAR:  I have just one or two,

8       if I may.

9                 CHAIRMAN GRAHAM:  Sure.

10                 COMMISSIONER EDGAR:  Good morning.

11                 THE WITNESS:  Good morning, Commissioner.

12                 COMMISSIONER EDGAR:  Yesterday I asked

13       Mr. Olivera one or two questions, and I said at the time

14       that I would pose a similar question to you, so I want

15       to follow through on that.

16                 And I recognize in your testimony, and you

17       have given it to us also in your summary, that it is

18       your belief that FPL failed to provide information to us

19       that they should have at a certain point in time.

20                 Is it your belief or opinion that FPL withheld

21       information that was required to be submitted to the

22       Commission by either rule or statute?

23                 THE WITNESS:  That seems to me to be more of a

24       legal question, but it's my belief that the -- that FPL

25       should have provided the most up-to-date information

FLORIDA PUBLIC SERVICE COMMISSION

1056

1       available to this Commission in order to allow you to

2       make a decision based on the most current information.

3                 COMMISSIONER EDGAR:  Okay.  And in your

4       testimony at page 42, line 22, and I'll quote, your

5       words are, "I recommend that the Commission find that

6       FPL failed to provide the best, most current information

7       regarding its estimate of capital costs."  How do you

8       define "best information"?

9                 THE WITNESS:  Well, that would be the

10       information of the cost estimate that best reflects

11       their, their current estimate of what the project will

12       ultimately cost at the point in time that the testimony

13       was given.

14                 COMMISSIONER EDGAR:  Is that possibly

15       subjective?

16                 THE WITNESS:  It certainly could be argued.  I

17       guess the company has argued the other side of that.

18       But I believe if the, if there were small fluctuations

19       in the cost estimate, then you could argue that those

20       weren't relevant or material.  However, from, from the

21       cost estimate that the company testified to in May 2009,

22       by the time of the hearing in September, the costs of

23       the project had gone up $444 million, which is a very

24       significant and material change.  So I believe if you

25       have that degree of change, that should have been

FLORIDA PUBLIC SERVICE COMMISSION

1057

1       provided to the Commission.

2                 COMMISSIONER EDGAR:  One second.

3                 CHAIRMAN GRAHAM:  Sure.

4                 COMMISSIONER EDGAR:  One of the things I'm

5       grappling with is the timing of everything, and of

6       course we need to come back and, and look to the

7       statutes and the rules as guidance for our decisions and

8       for processes and procedures.  And I understand your

9       point about there being a legal question, and I'm sure

10       that will be briefed and I look forward to that.  But

11       yet when I'm trying to think timeline of information

12       coming in and going through processes and procedures and

13       our need for, as has been stated, accurate information,

14       I'm trying to find what to hang this fail to provide

15       current information.  Again, it just seems somewhat

16       subjective.  So I realize you've answered this question

17       over and over and over, but I'm going to ask you to do

18       it again.

19                 How do -- how -- what are you basing current

20       and best upon in your testimony before us?

21                 THE WITNESS:  Well, I'm basing it on the

22       review of documents provided by the company, in

23       particular the July 25th, 2009, presentation to the

24       Executive Steering Committee that indicated a

25       $300 million cost increase was recognized in July of

FLORIDA PUBLIC SERVICE COMMISSION

1058

1       2009.  And again an August estimate increased the cost

2       by another $144 million.  So by the time of the

3       September hearing, it just seems clear to me that there

4       was very compelling evidence that the cost of the

5       project was going up dramatically, and so --

6                 COMMISSIONER EDGAR:  Future estimated costs?

7                 THE WITNESS:  Future, yes.  Total, total

8       costs, total estimated costs.

9                 COMMISSIONER EDGAR:  Not costs incurred.

10                 THE WITNESS:  That's right, not costs

11       incurred.  And it continued to go up even beyond that

12       point.  So, I mean, I think there was no credible

13       evidence that those costs were, were not accurate and

14       that the cost testified to in 2009 was, was stale by

15       that time, in May of 2009.  Sorry.

16                 COMMISSIONER EDGAR:  Thank you.

17                 CHAIRMAN GRAHAM:  Commissioner Balbis.

18                 COMMISSIONER BALBIS:  Thank you, Mr. Chairman.

19       And I have a couple of questions for this witness.

20                 And I want to focus on your testimony on page

21       14 concerning the imprudence of FPL's management of the

22       EPU products -- or projects.

23                 THE WITNESS:  Yes.

24                 COMMISSIONER BALBIS:  And not focusing on the

25       decision to fast track or not, where a good portion of

FLORIDA PUBLIC SERVICE COMMISSION

1059

1       your testimony focuses on that, and you did indicate

2       that, I believe it's on page 21, on whether or not the

3       company was concerned about this situation.  And I

4       assume by the situation is the percentage of completion

5       of the design or other preliminary work; is that

6       correct?

7                 THE WITNESS:  Yes.  Uh-huh.

8                 COMMISSIONER BALBIS:  And you indicated that

9       they were concerned.  Again, focusing on 2009 and 2010,

10       did you see or find evidence of any action taken by FPL

11       in 2009 and 2010 was imprudent in reaction to this, this

12       concern?

13                 THE WITNESS:  No.  No, I didn't.  They were,

14       they were committed to a fast track approach.  The

15       results of that commitment were the costs were

16       increasing and the scope of the project was increasing

17       beyond what they had originally estimated it to be.  But

18       by the 2009/2010 time frame they were committed to that

19       approach, and I believe they were addressing those

20       issues prudently at that point in time.

21                 COMMISSIONER BALBIS:  So the, the actions that

22       you list, or at least one of them that you list on page

23       22, where FPL has hired an outside estimating firm to

24       help cost out the completion, there was also the

25       discussion on the option of them self-performing some of

FLORIDA PUBLIC SERVICE COMMISSION

1060

1       the work, those decisions, would you feel those are

2       imprudent or prudent, again in 2009 and 2010?

3                 THE WITNESS:  I believe those are prudent.

4       The reason those are in here was just to demonstrate

5       that, again, that when they initiated this project, they

6       didn't have a firm grasp for the scope or the, or the

7       costs going forward.  So by this time they called in

8       help to help them get a better estimate, and I think

9       that was prudent.

10                 COMMISSIONER BALBIS:  Okay.  And then I have

11       one question on one of your exhibits, and this will be

12       my last question, Mr. Chairman.  It's the graph that

13       shows the percent complete.  I forget which exhibit that

14       is. I believe it's WRJ-FPL-4.

15                 THE WITNESS:  Yes.  Let me, if I may, correct

16       before, we go any further, one thing.  The numbers on

17       the side are not percentage numbers.  Those are the

18       number of modification packages.

19                 COMMISSIONER BALBIS:  Okay.  That was the

20       question that I had.

21                 THE WITNESS:  Okay.

22                 COMMISSIONER BALBIS:  And what does that

23       number represent?

24                 THE WITNESS:  I think there was some confusion

25       earlier about what those numbers represented.  But, in

FLORIDA PUBLIC SERVICE COMMISSION

1061

1       fact, that was the, that was the point of the correction

2       I made to my testimony earlier when I began.

3                 COMMISSIONER BALBIS:  Okay.

4                 THE WITNESS:  Is that those are actually

5       design modification packages, not a percentage complete.

6                 COMMISSIONER BALBIS:  And did you clarify in

7       your testimony -- I believe you did, but, again, I want

8       to avoid confusion.  On the number of mods complete and

9       manhours, there was an assessment on the earned value or

10       actually work that has been done on each one of those

11       mods in order to determine; is that correct?

12                 THE WITNESS:  That's correct.

13                 COMMISSIONER BALBIS:  Okay.  Thank you.  I

14       have no further questions.

15                 CHAIRMAN GRAHAM:  Thank you.

16                 Commissioner Brisé.

17                 COMMISSIONER BRISÉ:  Thank you, Mr. Chairman.

18                 I have two questions, one going back to the

19       line of questioning that Commissioner Edgar was on, and

20       I'm going to ask you a very specific question.

21                 So from your perspective, even if the company

22       hadn't gone through its normal processes of vetting the

23       information, you think that information should have

24       brought, been brought to the Commission; is that your

25       perspective?

FLORIDA PUBLIC SERVICE COMMISSION

1062

1                 THE WITNESS:  Yes, sir.

2                 COMMISSIONER BRISÉ:  Okay.  So then -- but

3       from your perspective you think that that is the best

4       and most accurate information that should be provided to

5       the Commission, providing that all of the processes

6       internally by the company have not been put in place

7       with respect to those numbers?

8                 THE WITNESS:  Yes.  I think they could have

9       presented the information in that light:  Our current

10       formal estimate is the May 2009 estimate; however, we

11       have very strong indications that the costs are going

12       up.  This is our current estimate; it may change

13       slightly.  But I think they should have provided that

14       information in that light.

15                 COMMISSIONER BRISÉ:  But you would agree that

16       reasonable people could disagree on the fact on whether

17       you think that information should have been brought

18       forth from the company's perspective?

19                 THE WITNESS:  Well, I believe reasonable

20       people have disagreed on that, so I would agree with

21       you.

22                 (Laughter.)

23                 COMMISSIONER BRISÉ:  Okay.  All right.

24                 And, and down the path of 2009 and 2010, the

25       actions that the company has taken between 2009 and 2010

FLORIDA PUBLIC SERVICE COMMISSION

1063

1       with respect to projected costs and all of that, from

2       your perspective, limiting to 2009, 2010, were the

3       projected costs and the costs that were incurred

4       actually prudent?

5                 THE WITNESS:  I'm sorry.  I didn't fully

6       understand that.  Could you rephrase that or repeat

7       that?

8                 COMMISSIONER BRISÉ:  Sure.  When looking at

9       2009 and 2010, we will say -- I'm asking you do you

10       think the actions that the company has taken with

11       respect to the project in question were prudent?

12                 THE WITNESS:  Yes.  I believe I addressed that

13       earlier.  But by the time -- once they had committed on

14       the fast track project, they were sort of in the

15       reactive mode and they were, they were reacting as best

16       they could.  And during that time frame I believe they

17       were acting prudently once they got -- initiated the

18       project as they had.

19                 COMMISSIONER BRISÉ:  Okay.  The reason I asked

20       that question is because we're, we're looking at 2009

21       and 2010.

22                 THE WITNESS:  That's correct.

23                 COMMISSIONER BRISÉ:  So -- thank you.

24                 CHAIRMAN GRAHAM:  Commissioner Brown.

25                 COMMISSIONER BROWN:  Thank you, Mr. Chairman.

FLORIDA PUBLIC SERVICE COMMISSION

1064

1                 And now I just have to ask a question as a

2       follow-up to Commissioner Edgar's, because I was not

3       completely satisfied with the answer that you gave

4       regarding -- I know you're not a lawyer, but she asked

5       you a question, Commissioner Edgar asked you a question

6       about whether the company was required under law, under

7       statute or rule to provide that information in

8       September.  And your answer -- if you could just

9       elaborate a little bit more for me.

10                 THE WITNESS:  I'm afraid I'm going to have to

11       give the same answer in that I'm not an attorney and I'm

12       not really able to speak on what's required by rule or

13       by law.  But I think it is inherently the company's

14       responsibility to provide the most up-to-date and

15       accurate information to this Commission so you can have

16       that information in your decision-making process.

17                 COMMISSIONER BROWN:  Okay.  Thank you.

18                 CHAIRMAN GRAHAM:  All right.  OPC for

19       redirect?

20                         REDIRECT EXAMINATION

21       BY MR. McGLOTHLIN:

22            Q    Dr. Jacobs, with respect to the questions from

23       Commissioners regarding your review of documents

24       indicating that the estimate of capital costs had

25       increased after the May 2009 prefiled testimony had been

FLORIDA PUBLIC SERVICE COMMISSION

1065

1       submitted, did your review of those documents give you a

2       sense of whether the project managers regarded the

3       May 2009 estimate or the revised estimates in the

4       July/August time frame as their view of the current

5       situation?

6            A    Yes.  I believe they -- the July 2009 was a

7       very detailed and specific meeting.  And I think after

8       that meeting, they, which indicated an increase of

9       $300 million in costs, I believe after that meeting,

10       that was the cost estimate that was the operative

11       estimate by the FPL managers.

12            Q    And the Commissioners asked you some questions

13       about the actions that FPL took in the 2009/2010 time

14       frame.  Do you have an opinion as to whether those

15       actions have, have fully mitigated the impact on

16       ratepayers or the decision to fast track this project?

17            A    No, they have not.  They've been, they've been

18       reacting to the situation that they found themselves in

19       as a result of the decision to fast track the project,

20       and they have not fully mitigated the costs or impact.

21                 MR. McGLOTHLIN:  Thank you.  I have nothing

22       further.

23                 CHAIRMAN GRAHAM:  Okay.  We have some exhibits

24       to enter into the record.

25                 MR. McGLOTHLIN:  I move Exhibits 102 through

FLORIDA PUBLIC SERVICE COMMISSION

1066

1       114.

2                 CHAIRMAN GRAHAM:  102 through 114.

3                 MR. McGLOTHLIN:  We also have the revised and

4       corrected page to distribute at this point.

5                 CHAIRMAN GRAHAM:  Yes, that as well, if

6       there's no objections.

7                 (Exhibits 102 through 114 admitted into

8       evidence.)

9                 MR. YOUNG:  Mr. Chairman, at this time Staff

10       moves 198.

11                 CHAIRMAN GRAHAM:  Also Staff's 198.  Thank

12       you, sir.

13                 (Exhibit 198 admitted into evidence.)

14                 MR. ANDERSON:  Also, Chairman Graham, as

15       proposed Exhibit 199, FPL offers some additional

16       excerpts from the Kundalkar deposition.  Some pages are

17       in WRJ-11, Dr. Jacobs' attachment, and under the rule of

18       completeness we offer some additional pages.  We'll

19       distribute those now.  That will be Exhibit 199.

20                 CHAIRMAN GRAHAM:  I'll wait for you to

21       distribute to see if there's any objections.

22                 This is Exhibit Number 199.  Is there any

23       objection to entering 199 into the record?

24                 MR. McGLOTHLIN:  None from OPC.

25                 CHAIRMAN GRAHAM:  Staff?

FLORIDA PUBLIC SERVICE COMMISSION

1067

1                 MR. YOUNG:  No objections.

2                 CHAIRMAN GRAHAM:  Okay.  Then it's so.

3                 (Exhibit 199 marked for identification and

4       admitted into evidence.)

5                 Okay.  Are we done with Dr. Jacobs for now?

6                 MR. McGLOTHLIN:  Yes, sir.

7                 CHAIRMAN GRAHAM:  Sir, thank you very much for

8       your testimony today.

9                 THE WITNESS:  Thank you.

10                 CHAIRMAN GRAHAM:  Okay.

11                 OPC, is that it for your witnesses?

12                 MR. McGLOTHLIN:  Yes, sir.

13                 CHAIRMAN GRAHAM:  Staff?

14                 MR. YOUNG:  Mr. Chairman, at this time Staff

15       calls Lynn Fisher and David Rich to the stand.  And I

16       think they have been sworn.

17                 CHAIRMAN GRAHAM:  Let the record show they

18       both indicated they have been sworn.

19                             DAVID RICH

20                                 AND

21                             LYNN FISHER

22       were called as witnesses on behalf of the Florida Public

23       Service Commission and, having been duly sworn,

24       testified as follows:

25                          DIRECT EXAMINATION

FLORIDA PUBLIC SERVICE COMMISSION

1068

1                 MR. YOUNG:  Good morning.

2                 THE WITNESS:  (By Mr. Rich)  Good morning.

3                 THE WITNESS:  (By Mr. Fisher)  Good morning.

4       BY MR. YOUNG:

5            Q    Can you please state your full name and

6       business address for the record.

7            A    (By Mr. Fisher)  My name is Lynn Fisher.  My

8       business address is 2540 Shumard Oak Boulevard,

9       Tallahassee, Florida.

10            Q    By whom are you employed and in what capacity?

11            A    (By Mr. Fisher)  I'm employed by the Florida

12       Public Service Commission as a Government Analyst II in

13       the Office of Auditing and Performance Analysis.

14            Q    All right.  Mr. Rich, can you please state

15       your full name and business address for the record?

16            A    (By Mr. Rich)  Yes.  My name is David Rich.

17       My business address is 2540 Shumard Oak Boulevard,

18       Tallahassee, Florida, 32399.

19            Q    By whom are you employed and in what capacity?

20            A    (By Mr. Rich)  The Florida Public Service

21       Commission.  I'm an Operations Review Specialist.

22            Q    Have you all jointly filed prefiled testimony

23       consisting of five pages in this docket?

24            A    (By Mr. Fisher)  Yes.

25            A    (By Mr. Rich)  Yes, we have.  Yes.

FLORIDA PUBLIC SERVICE COMMISSION

1069

1            Q    Do you have any changes or corrections to that

2       testimony, that joint prefiled testimony?

3            A    (By Mr. Fisher)  No.

4            A    (By Mr. Rich)  No, we don't.

5                 MR. YOUNG:  Mr. Chairman, at this time, I

6       request -- Staff requests that the joint prefiled

7       testimony of Mr. Fisher and Mr. Rich be entered into the

8       record as though read.

9                 CHAIRMAN GRAHAM:  We will enter the joint

10       prefiled testimony of Fish and Rich into the record --

11       I'm sorry -- Fisher and Rich into the record as though

12       read.

13       BY MR. YOUNG:

14            Q    Did you have two exhibits attached to your

15       joint prefiled testimony as relates to Florida Power &

16       Light, which is entitled 2010 Review of Florida Power &

17       Light Company's Project Management Internal Controls for

18       Nuclear Plant Uprate and Construction Projects, and 2009

19       Review of Florida Power & Light Company Project

20       Management Internal Controls for Nuclear Plant Uprate

21       and Construction Projects?

22            A    (By Mr. Rich)  Yes, we did.

23            Q    Do you have any changes or corrections to

24       those exhibits?

25            A    (By Mr. Rich)  No.

FLORIDA PUBLIC SERVICE COMMISSION

1070

1                 MR. YOUNG:  Mr. Chairman, at this time I will

2       identify and ask that those identify, those exhibits be

3       marked as exhibits, which are FR-1 and

4       FR-2 respectively, and FR -- and those are Exhibit

5       Numbers 115 and 116 on Staff's Comprehensive Exhibit

6       List.

7                 CHAIRMAN GRAHAM:  Okay.

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1075

1

2       BY MR. YOUNG:

3            Q    Do you have -- do you all have a prepared

4       summary of your joint prefiled testimony today?

5            A    (By Mr. Rich)  Yes.

6            Q    Can you please provide that summary.

7            A    (By Mr. Rich)  Yes.  Thank you.

8                 Good morning, Mr. Chairman, Commissioners.

9                 Mr. Fisher and my testimony presents, presents

10       a review of the project controls in key events impacting

11       Florida Power & Light's St. Lucie 1 and 2 and Turkey

12       Point 3 and 4 uprate project, and the Turkey Point 6 and

13       7 new nuclear project during 2007 -- correction, 2010

14       into 2011.

15                 Additionally, Staff conducted a follow-up

16       review of events leading to and following the extended

17       power uprate management changes in 2009.  Project

18       controls examined during our review include the areas of

19       planning, management and organization, cost and schedule

20       controls, contractor selection and management, auditing

21       and quality assurance for new nuclear construction.

22                 During 2010, Florida Power & Light slightly

23       revised its cost estimates for new nuclear construction

24       at Turkey Point Units 6 and 7.  The final estimated cost

25       now lies in a range from 12.85 billion to

FLORIDA PUBLIC SERVICE COMMISSION

1076

1       $18.75 billion.  The in-service dates for Turkey Point

2       Units 6 and 7 are 2022 and 2023 respectively.

3                 Florida Power & Light filed its combined

4       operating license application with the Nuclear

5       Regulatory Commission in June 2009 and is currently

6       focused on responding to requests for additional

7       information from the NRC.  The company expects to

8       receive final approval in late 2013, with major site

9       preparation work beginning the following year.

10                 Florida Power & Light's decision to remove the

11       limited work authorization from its application in

12       November 2009 ensures that major construction will not

13       begin until after the full license approval.

14                 Florida Power & Light did not execute an

15       engineering procurement and construction contract for

16       Turkey Point 6 and 7 during the year 2010.  Staff

17       believes that the window of opportunity for negotiating

18       and signing such a contract is still relatively distant,

19       but must be in place by 2013 or 2014 to avoid schedule

20       impact.

21                 The reservation agreement for long-lead

22       forging has again been extended, this time until

23       September of this year.  Staff believes that forging

24       issues likewise must be settled and manufacturing begun

25       by 2015 in order to meet current in-service dates.

FLORIDA PUBLIC SERVICE COMMISSION

1077

1                 Staff made no specific recommendations in this

2       report for the Turkey Point 6 and 7 project, although we

3       believe that the Commission should continue to closely

4       monitor all new nuclear controls, costs, activities, and

5       schedule as the Turkey Point 6 and 7 project transitions

6       from licensing to site preparation and construction.

7                 THE WITNESS:  (By Mr. Fisher)  Commissioners,

8       Florida Power & Light's uprate project for the St. Lucie

9       Units 1 and 2 and Turkey Point Units 3 and 4 experienced

10       several key project developments during 2010.  The

11       current and nonbinding cost estimate for the extended

12       power uprate project is 2.3 billion to $2.48 billion.

13       The high end of this estimate range represents an

14       increase of 37.9% over the original need determination

15       estimate of $1.8 billion.

16                 Several key events impacted the uprates in

17       2010:  The submittal of the St. Lucie Unit 1 EPU LAR,

18       the submittal of the St. Lucie Unit 2 EPU LAR, the

19       submittal of the Turkey Point EPU LAR, and several work

20       stoppages at Turkey Point and St. Lucie.

21                 In addition, three of the four remaining

22       outages have been extended and a vendor project

23       management team at Turkey Point 3 and 4 have been

24       removed.

25                 Additionally, Staff conducted a follow-on

FLORIDA PUBLIC SERVICE COMMISSION

1078

1       review of events leading to the EPU management changes

2       of 2009.  Staff found no evidence of improper or

3       duplicate invoicing, unnecessary work or rework,

4       overpayments, overcharging, or other examples of

5       mismanagement by the former EPU management team.

6                 This concludes our summary.

7                 MR. YOUNG:  Mr. Chairman, I tender the

8       witnesses for cross.

9                 CHAIRMAN GRAHAM:  Intervenors?

10                 MS. KAUFMAN:  I have questions.

11                 CHAIRMAN GRAHAM:  Sure.

12                 MS. KAUFMAN:  Thank you.

13                          CROSS EXAMINATION

14       BY MS. KAUFMAN:

15            Q    Good morning, gentlemen.

16            A    (By Mr. Fisher)  Good morning.

17            A    (By Mr. Rich)  Good morning.

18            Q    Vicki Kaufman for the Florida Industrial Power

19       Users Group.

20                 Can I take from your summary that, Mr. Fisher,

21       you were the person responsible for issues relating to

22       the EPU uprate?

23            A    (By Mr. Fisher)  I wrote the portion of our

24       report that related to EPU.  However, Mr. Rich conducted

25       the follow-up portion, so -- I was involved in a

FLORIDA PUBLIC SERVICE COMMISSION

1079

1       different audit at that time.  So he would be the one

2       that, that would handle most of the questions relating

3       to the follow-up.

4            Q    Okay.

5            A    (By Mr. Rich)  I might also add, Ms. Kaufman,

6       that our work is, is a combined effort, and that

7       although we perhaps spent more time and energy on

8       certain aspects of it and delineated the work in that

9       manner, we're both fully capable of answering.  We'll

10       opine and bump in when we think it's appropriate, if

11       that's all right with you.

12            Q    Absolutely.  And so what I'll do is I'll ask

13       my question, and you gentlemen decide who's the

14       appropriate person.  And if one finishes and the other

15       has a comment to add, that's perfectly fine.

16            A    (By Mr. Rich)  Thank you.

17            Q    The area that I want to talk to you about, and

18       I'm going to be looking at Exhibit 115, which is your

19       2010 review.

20            A    (By Mr. Rich)  Uh-huh.

21            Q    And I want to just talk to you for a moment

22       about the extended power uprate events and developments.

23       And if you can look, on my copy it's Section 1.4.3 in

24       the beginning.

25            A    (By Mr. Rich)  Could you cite a page for me,

FLORIDA PUBLIC SERVICE COMMISSION

1080

1       please?

2            Q    I think it's page 4 of the report, as opposed

3       to your testimony.

4            A    (By Mr. Rich) Page 4.  Thank you.

5            Q    And let me know when you're there.

6                 And I think, Mr. Fisher, you alluded to this

7       area in your summary.  But if you look under Section,

8       it's actually 1.4.3, the third paragraph there, you say,

9       "During 2009, FPL's senior management made the decision

10       to replace the EPU management team.  Senior management

11       appears to have believed the management team could not

12       provide the necessary control of EPC contractor

13       estimates and that more aggressive actions were

14       required."  Do you see that?

15            A    (By Mr. Fisher)  Yes.

16            Q    Can you explain, first of all, how you reached

17       your conclusion that senior management thought that the

18       management team of the EPU project couldn't provide the

19       necessary controls?

20            A    (By Mr. Fisher)  Yes.  Most of this was

21       related to the company's response to our questions

22       related to why, why was there a change made to the team.

23       The response indicated that senior management was not

24       totally happy with the, with the ability to, to question

25       and to push back on the vendor, in this case the EPC

FLORIDA PUBLIC SERVICE COMMISSION

1081

1       vendor, and therefore felt like there needed to be a

2       change in management.

3            Q    Was, was the entire management team replaced

4       for the EPU project?

5            A    (By Mr. Fisher)  At least two, two of the VPs

6       were.  I'm not sure that -- I think there are still

7       people involved there that were on the team that, that

8       are working today.

9            Q    Let me rephrase that inartful question.

10                 Were the, the top managers or top executives

11       on that team replaced?

12            A    (By Mr. Fisher)  Yes.  One I think was going

13       for an additional, a different job and so forth.  So, in

14       other words, was, was, I think continued to work with

15       the company for a while and then later left.

16            Q    In a different capacity they continued to work

17       for FPL.

18            A    (By Mr. Fisher)  Yes.  Yes.  A different

19       capacity.  Thank you.

20            Q    And you make some reference, I guess, to what

21       we've come to call the Concentric report.  You reviewed

22       that report?

23            A    (By Mr. Fisher)  Yes.

24            Q    And Concentric came to a similar opinion

25       regarding the performance of the prior EPU team, did

FLORIDA PUBLIC SERVICE COMMISSION

1082

1       they not?

2            A    (By Mr. Fisher)  I'm sorry?

3            Q    I'm sorry.  In the -- on the same paragraph

4       I've been looking at, 1.4.3, you talk about an

5       investigative report by Concentric.

6            A    (By Mr. Fisher)  Uh-huh.

7            Q    And you say that confirms your opinion

8       regarding the performance problems with the EPU team.

9            A    (By Mr. Fisher)  Yes.  That and the company's

10       response.

11                 MS. KAUFMAN:  Thank you.  That's all I have.

12                 CHAIRMAN GRAHAM:  Okay.

13                 MR. McGLOTHLIN:  No questions.

14                 MR. WHITLOCK:  No questions, Mr. Chairman.

15                 CHAIRMAN GRAHAM:  Florida Power & Light?

16                 MR. ANDERSON:  Yes, FPL does have a few

17       questions.

18                          CROSS EXAMINATION

19       BY MR. ANDERSON:

20            Q    I believe Ms. Kaufman was just asking you some

21       questions about Exhibit 116, is that right, which was

22       the report you prepared in July 2010?

23            A    (By Mr. Rich)  Yes.

24            Q    Okay.

25                 MR. ANDERSON:  I'm going to ask that an

FLORIDA PUBLIC SERVICE COMMISSION

1083

1       exhibit be distributed.

2                 MS. KAUFMAN:  Mr. Chairman, just for clarity,

3       I think it was 115, just so the record is clear.

4                 CHAIRMAN GRAHAM:  Okay.

5                 MR. YOUNG:  I think it's 116.

6                 MS. CANO:  I may be able to help.

7                 CHAIRMAN GRAHAM:  Unless I'm going crazy, I

8       have it down as 115.

9                 MR. YOUNG:  I'm sorry.  It's FR-2, and that's

10       116.

11                 MR. ANDERSON:  Okay.  So --

12                 MR. YOUNG:  That's what Ms. Kaufman was asking

13       about, FR-2.

14                 CHAIRMAN GRAHAM:  I have in my fingers, it's

15       FR-2, but the cover sheet says "July 2010."  And looking

16       at the exhibit sheet, I have 115, FR-1, and the

17       description says "2010 Review of Florida Power & Light."

18                 MS. KAUFMAN:  I'm sorry, Mr. Chairman.  I've

19       created a lot of confusion.  Mr. Anderson or Ms. Cano is

20       correct.  It's 116.  I apologize.

21                 CHAIRMAN GRAHAM:  Okay.  Thanks for confusing

22       me.

23                 (Laughter.)

24                 Let's continue.

25                 MR. ANDERSON:  Great.  Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

1084

1       BY MR. ANDERSON:

2            Q    Now that we're clear, the questions you were

3       just asked pertain to Exhibit 116 from July 2010; is

4       that right?

5            A    (By Mr. Rich)  Yes.

6            Q    And since that time you've prepared a new

7       report, which is the July 2011 report, Exhibit 115; is

8       that correct?

9            A    (By Mr. Rich)  That's correct.  Yes.

10            Q    Okay.  I've distributed a document which we've

11       marked as -- I'd asked be marked as Exhibit Number 200,

12       I think we're up to.  And the short name for this would

13       be EPU 2009 Management Change, FPSC Audit Work Paper.

14       Do you have that before you?

15            A    (By Mr. Rich)  I do, yes.

16                 (Exhibit 200 marked for identification.)

17       BY MR. ANDERSON:

18            Q    Okay.  Is this a document that you gentlemen

19       prepared?

20            A    (By Mr. Rich)  Mr. Fisher was not involved in

21       the EPU look back.  This is a document I prepared.

22            Q    Okay.  Thank you, Mr. Rich.  And in roughly

23       what time period do you prepare this document?

24            A    (By Mr. Rich) We conducted this review between

25       September and December of last year.

FLORIDA PUBLIC SERVICE COMMISSION

1085

1            Q    Okay.  And that's after the report Ms. Kaufman

2       just asked you about; right?

3            A    (By Mr. Rich)  Yes, it is.

4            Q    Okay.  And just directing your attention to

5       this document, it states an issue at the top, "Did the

6       2009 EPU management changes cause or directly lead to

7       cost overruns, unnecessary work or rework?  Was the EPU

8       management changeover the result of mismanagement?"

9       That was the issue you were addressing, Mr. Rich?

10            A    (By Mr. Rich)  Yes, it was.

11            Q    Then directing down about a third of the way

12       down the page under Condition, it says, "What is

13       happening?  In concluding days of the 2010 hearings,

14       several Commissioners had questions they felt were not

15       adequately addressed by FPL during the proceedings.

16       These form the basis of a follow-on review conducted in

17       late 2010.  The majority of questions were directly

18       investigated and answered by a thorough review of

19       circumstances and events leading up to and following the

20       changeover."  Did I read that correctly?

21            A    (By Mr. Rich)  You did.  But I would not place

22       the emphasis on it that you did, sir.

23            Q    Okay.  I understand.  But I read the document

24       correctly?

25            A    (By Mr. Rich)  Yes, you did.

FLORIDA PUBLIC SERVICE COMMISSION

1086

1            Q    And that's what kind of teed up the additional

2       work you did in the latter part of, of 2010 in preparing

3       this report for 2011?

4            A    (By Mr. Rich)  Yes, sir.  If I might, a

5       thorough review was done of the transcript from last

6       year.  The Commissioners' questions, then serving and

7       currently serving, were excerpted from that.  Those

8       questions formed the basis of the following review.

9            Q    Very good.  Thank you.  And it relates here

10       work that you did.  You did five document requests; is

11       that right?

12            A    (By Mr. Rich)  Yes, there were five.

13            Q    Six on-site or phone interviews with FPL

14       personnel?

15            A    (By Mr. Rich)  Yes.

16            Q    You talked to Mr. Reed, the CEO of Concentric

17       Energy Advisors, in person?

18            A    (By Mr. Rich)  We did, yes.

19            Q    And then the third paragraph -- let me see if

20       I've got this right.  "While the documentary evidence

21       and interviews in many places strongly support the

22       Concentric findings, there was no direct or compelling

23       evidence discovered of unnecessary rework, overpayments

24       or overcharging or mismanagement on the part of the

25       former EPU management team."  Did I get that right?

FLORIDA PUBLIC SERVICE COMMISSION

1087

1            A    (By Mr. Rich)  Yes, you did.

2            Q    Okay.  And then going on, "Staff would opine

3       that FPL missed a golden opportunity to be fully

4       forthcoming with the Commission and the public about

5       anticipated cost increases, but was not compelled to

6       divulge more information than they did under current

7       Commission orders or Florida Statutes."  Did I get that

8       right?

9            A    (By Mr. Rich)  That's my opinion.  Yes.

10            Q    Right.

11                 MR. ANDERSON:  FPL has nothing further, but

12       we'll offer Exhibit 200 into evidence.

13                 CHAIRMAN GRAHAM:  Okay.

14                 Staff?  I'm sorry.  These are your witnesses.

15                 Commission board?

16                 Commissioner Balbis.

17                 COMMISSIONER BALBIS:  Thank you, Mr. Chairman.

18                 I have a question for either of you, whoever

19       is best to answer.  And, again, based on this exhibit

20       that was just passed out with the Bureau of Performance

21       Analysis finding summary, with the complete change of

22       the management team, did you find that -- and you have

23       here no examples of overpayments, overcharging, or

24       mismanagement.  I assume that has to do with the vendors

25       that are working for FPL; is that correct?

FLORIDA PUBLIC SERVICE COMMISSION

1088

1                 THE WITNESS:  (By Mr. Rich)  Yes, sir.  If I

2       might explain how we did that.

3                 For a period of three months before the

4       changeover and three months after we looked at 55,

5       correction, 54% of the total expenditures by invoice of

6       the five, five major vendors, and for the three-month

7       period after the EPU changeover we looked at those same

8       five vendors, 64% of expenditures.  In those invoices we

9       saw no evidence of duplicative work, overpayment,

10       overcharging by the contractor.  In fact, we saw

11       evidence of appropriate push back when the vendor tried

12       to overcharge.

13                 COMMISSIONER BALBIS:  And did you analyze any

14       of the work performed by FPL?  And just to clarify, I

15       mean, I would assume that the, the changing of an entire

16       management team would require a lot of time getting up

17       to speed for the personnel, et cetera.  I mean, did your

18       analysis include the internal work by FPL?

19                 THE WITNESS:  (By Mr. Rich)  I don't know what

20       degree to which you're referring as far as our

21       investigation, sir.  But I would answer it in this way,

22       that we queried FPL senior executives on the changeover

23       process and also looked at personnel records for both

24       the incoming and the outgoing personnel involved.  There

25       was no evidence of dissatisfaction on the part of senior

FLORIDA PUBLIC SERVICE COMMISSION

1089

1       FPL executives with the previous management of the EPU.

2       In my investigation or my review it didn't appear that

3       that was a -- was causation for the changeover.

4                 And in querying FPL senior representatives,

5       they, they opined that this was a matter of normal

6       progression and transition in the company that had been

7       done previously in the past and was a normal course of

8       business events, to transition as the project

9       transitioned, to get the right people in the right jobs

10       at the right time.

11                 COMMISSIONER BALBIS:  So you're saying that

12       FPL's response was, it was the normal process to change

13       out the entire management team; is that correct?

14                 THE WITNESS:  (By Mr. Rich)  No, sir, that's

15       not my response.  The response was in changing out

16       Mr. Kundalkar specifically it would have been a normal

17       transition process.

18                 COMMISSIONER BALBIS:  Okay.  And, again, I

19       guess what I'm focusing on is, is I would assume that

20       changing out of a management team for any project

21       requires a lot of -- could require duplicative work by

22       the management team, again, getting up to speed,

23       additional hours spent that, you know, you could

24       consider rework by the management team because the other

25       team was up to speed.  I mean, did you review that?  Do

FLORIDA PUBLIC SERVICE COMMISSION

1090

1       you have any indications of that?

2                 THE WITNESS:  (By Mr. Rich)  No, sir.  We

3       didn't review that.  We focused on the vendor as far as

4       rework or duplicative work went.

5                 COMMISSIONER BALBIS:  Okay.  Thank you.  I

6       have nothing further.

7                 CHAIRMAN GRAHAM:  Staff for redirect.

8                 MR. YOUNG:  Just one question.

9                         REDIRECT EXAMINATION

10       BY MR. YOUNG:

11            Q    Earlier in your, your response to Mr. Anderson

12       under Condition 2, what's happening, you said you would

13       not place the emphasis that Mr. Anderson placed on

14       reading that first paragraph.  Can you explain why you

15       would not place that emphasis on that?

16            A    (By Mr. Rich)  It's a subjective opinion, but

17       I would read the sentence as written without more

18       emphasis on the word "thorough."

19                 MR. YOUNG:  No further questions.

20                 CHAIRMAN GRAHAM:  Okay.  We have some exhibits

21       to enter?

22                 MR. YOUNG:  Yes, sir.  At this time Staff

23       moves 115 and 116 into the record.

24                 CHAIRMAN GRAHAM:  We'll move 115 and 116 into

25       the record.

FLORIDA PUBLIC SERVICE COMMISSION

1091

1                 (Exhibits 115 and 116 admitted into evidence.)

2                 MR. ANDERSON:  FPL offers Exhibit 200 into the

3       record.

4                 MR. YOUNG:  No objection.

5                 CHAIRMAN GRAHAM:  I don't see any objections,

6       so we'll offer, enter -- I'm sorry.  We'll enter Exhibit

7       Number 200 into the record as well.

8                 (Exhibit 200 admitted into evidence.)

9                 Staff, are we finished with this witness?

10                 MR. YOUNG:  Yes, sir.  We ask that the

11       witnesses be excused from the hearing.

12                 CHAIRMAN GRAHAM:  Do we have any objection to

13       the two witnesses being excused?

14                 Seeing none, gentlemen, thank you very much

15       for your testimony today.

16                 THE WITNESS:  (By Mr. Rich)  Thank you, Mr.

17       Chairman.

18                 MR. YOUNG:  Mr. Chairman, at this time, with

19       the witnesses being excused, Staff will ask that

20       Ms. Kathy Welch's prefiled exhibit and -- prefiled

21       testimony and exhibits be entered into the record.  She

22       is a stipulated witness that the parties all agree to

23       stipulate, and the Commissioners do not have any

24       questions for Ms. Welch.  And that's 117 -- I'm sorry.

25       Those are Exhibits 117, 118, 119, and 120, along with

FLORIDA PUBLIC SERVICE COMMISSION

1092

1       her prefiled direct testimony.

2                 CHAIRMAN GRAHAM:  117, 18, 19, and 20.

3       Ms. Welch was already stipulated.  There's no objection

4       to entering those into the record?

5                 Seeing none, we'll do that.

6                 (Exhibits 117, 118, 119, 120 admitted

7       evidence.)

8                 MR. YOUNG:  And just for the record, we did

9       move her testimony into the record.

10                 CHAIRMAN GRAHAM:  Yes.

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1097

1                 MR. YOUNG:  At this time, Mr. Chairman, I

2       think we are on FPL's rebuttal.

3                 CHAIRMAN GRAHAM:  Okay.  It seems like a nice

4       little place to take a pause.  So I have 10:30.  Let's

5       take a five-minute break.  We'll reconvene at 10:35.

6                 (Recess taken.)

7                 Okay.  We will reconvene and we are at

8       rebuttal.

9                 Mr. Anderson, Florida Power & Light's got the

10       floor.

11                 MR. ANDERSON:  Thank you, Chairman Graham.  At

12       this time, FPL would call as its first rebuttal witness

13       our President and Chief Executive Officer, Armando

14       Olivera, who the record will show was previously sworn

15       yesterday afternoon.

16                 CHAIRMAN GRAHAM:  Welcome.

17                 THE WITNESS:  Thank you.

18                           ARMANDO OLIVERA

19       was called as a rebuttal witness on behalf of Florida

20       Power & Light Company and, having been duly sworn,

21       testified as follows:

22                          DIRECT EXAMINATION

23       BY MR. ANDERSON:

24            Q    Good morning, Mr. Olivera.

25            A    Good morning, Mr. Anderson.

FLORIDA PUBLIC SERVICE COMMISSION

1098

1            Q    Will you please reintroduce yourself for the

2       record.

3            A    I'm Armando Olivera.  I work for Florida Power

4       & Light.  I'm President and Chief Executive Officer.

5            Q    Have you prepared and caused to be filed two

6       pages of prefiled rebuttal testimony in this proceeding

7       on July 25, 2011?

8            A    I have.

9            Q    Do you have any changes or revisions to your

10       rebuttal testimony?

11            A    No.

12            Q    If I asked you the same questions contained in

13       your prefiled rebuttal testimony, would your answers be

14       the same?

15            A    Yes.

16                 MR. ANDERSON:  Chairman Graham, FPL requests

17       that the prefiled rebuttal testimony be inserted into

18       the record as though read.

19                 CHAIRMAN GRAHAM:  We will insert into the

20       record, Mr. Olivera's rebuttal into the record as though

21       read.

22                 MR. ANDERSON:  We note for the record there

23       are no exhibits.

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1101

1       BY MR. ANDERSON:

2            Q    Mr. Olivera, would you please provide your

3       summary to the Commission.

4            A    Thank you.

5                 FPL would not have undertaken the extended

6       power uprate project on an expedited basis absent the

7       application of the nuclear cost recovery framework to

8       the project and absent the Commission's need

9       determination approving FPL's pursuit of the uprate

10       project on an expedited basis.

11                 The Office of Public Counsel's assertion that

12       the capital cost of the project should be disallowed to

13       the extent that uprate generation costs may be projected

14       to exceed natural gas generation costs is a heads win,

15       tails you lose approach.  This suggested result is

16       absolutely contrary to the regulatory framework provided

17       by -- for by the Legislature and the Commission aimed at

18       promoting the development of new nuclear generation.

19                 In 2007, the EPU project need determination

20       case, our company made it very clear that the regulatory

21       framework for nuclear cost recovery was essential to

22       FPL's willingness to undertake this capital intensive

23       nuclear investment on an expedited basis.

24                 The Commission should reject the attempt to

25       revisit this decision in hindsight three years after the

FLORIDA PUBLIC SERVICE COMMISSION

1102

1       issuance of the need determination approving the

2       project.

3                 This concludes my summary.

4                 MR. ANDERSON:  Mr. Olivera is available for

5       cross-examination.

6                 CHAIRMAN GRAHAM:  Intervenors?

7                 MR. McGLOTHLIN:  I'll begin.

8                 CHAIRMAN GRAHAM:  Mr. McGlothlin.

9                          CROSS EXAMINATION

10       BY MR. McGLOTHLIN:

11            Q    Sir, refer to page 1 of your prefiled rebuttal

12       testimony, and you also made this statement during your

13       summary.  At lines 20 through 22, you say, "Mr. Jacobs

14       asserts that capital costs of the EPU project should be

15       disallowed to the extent EPU generation costs may be

16       projected to exceed natural gas generation costs."

17                 Isn't it true, Mr. Olivera, that Dr. Jacobs'

18       mechanism would involve not just natural gas generation

19       costs but the present value of the revenue requirements

20       of FPL's entire system?

21            A    Yes.  But the natural gas prices have a huge

22       impact on the analysis.  When this Commission approved

23       the uprate project, natural gas that year was $9.  Today

24       natural gas is under $4, and that would have a big

25       impact on this.  And it's precisely the issue that we're

FLORIDA PUBLIC SERVICE COMMISSION

1103

1       arguing, which is you can't -- we have no control of

2       natural gas, and you want to go back and rewrite the

3       history and say, okay, three years later the price of

4       natural gas has changed, and we're going to rerun the

5       analysis and we're going to rerun the breakeven

6       analysis.  That was precisely what the rule was intended

7       to address, precisely what the legislation was intended

8       to address.

9            Q    You said you would rerun the breakeven

10       analysis.  Isn't it true that, isn't it true that FPL

11       has not performed and quantified the breakeven value for

12       the EPU project?

13            A    I'm sorry.  I didn't follow your question.

14            Q    In your statement a moment ago you said that

15       we're calling on FPL to rerun the breakeven analysis.

16       I'm using breakeven in terms, in terms of the

17       quantification of the maximum value in dollars per KW

18       that FPL could spend on the uprate project and remain at

19       or below the corresponding revenue requirement of the

20       alternative portfolio.

21                 And isn't it true that earlier witnesses for

22       FPL in this case have said that FPL has not performed

23       such a breakeven analysis for the uprate project?

24            A    I believe that Mr. Sim addressed the issue.

25                 But intuitively, when you have a big change in

FLORIDA PUBLIC SERVICE COMMISSION

1104

1       natural gas prices, that would change the economics.

2       Now we have run the analysis based on the current

3       forward prices, and even at the current forward prices

4       the uprate projects still make a lot of economic sense

5       for our customers, not only because they provide real

6       benefits, savings to the customers, but also because

7       they provide fuel diversity.  They represent a hedge on

8       our system.

9                 And I'd just like to give you one example.

10       Last year --

11            Q    Excuse me, sir.

12                 MR. McGLOTHLIN:  I believe that's well beyond

13       the scope of my question, Mr. Chairman.

14                 CHAIRMAN GRAHAM:  I agree.

15                 Mr. Olivera, if you can answer the question,

16       and you get a little latitude to explain your answer.

17                 THE WITNESS:  Yes, sir.

18                 MR. McGLOTHLIN:  And that's my last question.

19                 CHAIRMAN GRAHAM:  Okay.

20                 Any of the other Intervenors?

21                 Ms. Kaufman.

22                          CROSS EXAMINATION

23       BY MS. KAUFMAN:

24            Q    Good morning again, Mr. Olivera.

25            A    Good morning.

FLORIDA PUBLIC SERVICE COMMISSION

1105

1            Q    I just have one question for you, I think, and

2       it had to do with some remarks you made in your summary,

3       and you have them in your prefiled testimony as well.

4       And basically, as I understood what you said, you're

5       contending that the legislative framework that is at

6       issue in this case, that you relied upon that when you

7       moved forward with the EPU project.

8            A    We relied on both the legislation and the rule

9       and the decision made by this Commission when they

10       approved the uprate project.

11            Q    Let me ask you this about the legislative

12       framework and rule.  Is there anywhere in that statute

13       or rule that permits the company to recover costs from

14       ratepayers that are either unreasonable or unnecessary?

15            A    I believe that the -- that --

16            Q    If you wouldn't mind answering yes or no, I

17       would appreciate that.

18            A    No, by my interpretation.  I believe that the

19       determination was prudency versus imprudency, and that's

20       how we proceeded with this project.

21            Q    But you would agree that there's no, there's

22       no language in the rule or statute that you're relying

23       on that would authorize the company to recover costs

24       that are either unnecessary or unreasonable?

25            A    I would define them that any costs that were

FLORIDA PUBLIC SERVICE COMMISSION

1106

1       deemed to be imprudent by the company would not be

2       recoverable.

3            Q    Well --

4            A    Or deemed -- I'm sorry.  Deemed imprudent by

5       this Commission would not be recoverable.

6            Q    Well, aren't costs that are unnecessary -- if

7       you incur unnecessary costs, would that not be an

8       indicator of imprudence?

9            A    I don't know what -- if you could define for

10       me what you mean by "unnecessary."

11            Q    Unnecessary would be a cost that you did not

12       need to incur in order to move forward with the project.

13            A    And thus you would say it would be an

14       imprudent cost?

15            Q    I'm asking you that.  I'm asking you, would

16       you not consider an --

17            A    Look, I'm not -- I didn't -- I'm not an expert

18       on the legislation, and you're trying to get me to

19       define, have a broader definition than the imprudency,

20       and we rely on the imprudency.

21            Q    Okay.  I'm not trying to trick you.  I just

22       wonder that if the company spent dollars that weren't

23       necessary, you don't, you wouldn't find that imprudent

24       as you, as you analyze prudency?

25            A    If we spent dollars --

FLORIDA PUBLIC SERVICE COMMISSION

1107

1                 MR. ANDERSON:  FPL objects to this line of

2       questioning.  It's beyond the scope of Mr. Olivera's

3       testimony, which is very narrowly focused, and we've

4       permitted sufficient, I believe.

5                 MS. KAUFMAN:  Mr. Chairman -- if I could be

6       heard.

7                 CHAIRMAN GRAHAM:  Yes.

8                 MS. KAUFMAN:  Mr. Olivera has, has told us all

9       about his views of the regulatory scheme, and I think

10       that my questions are directly relevant to that, and

11       they're certainly not outside the scope.

12                 CHAIRMAN GRAHAM:  I think they are relevant,

13       and I don't have a problem with the back and forth,

14       because I believe Mr. Olivera is trying to clarify your

15       answer before he answers your answer.  I think we should

16       continue.

17                 MS. KAUFMAN:  Thank you.

18       BY MS. KAUFMAN:

19            Q    So I'll just ask it one more time and maybe we

20       can agree or maybe we'll just continue to disagree, and

21       that's fine, too.

22                 And my question simply was, if the company

23       were to expend costs that were unnecessary or not needed

24       to pursue the project, would you not agree that such

25       costs would be imprudent, as you define imprudency?

FLORIDA PUBLIC SERVICE COMMISSION

1108

1            A    If we -- if the company incurred costs that

2       were not relevant to the project, then obviously they,

3       we shouldn't recover those costs under this regulation.

4                 MS. KAUFMAN:  Thank you.  That's all I have.

5                 CHAIRMAN GRAHAM:  Thank you.

6                 SACE.

7                 MR. WHITLOCK:  No questions, Mr. Chairman.

8       Thank you.

9                 CHAIRMAN GRAHAM:  Staff?

10                 MS. NORRIS:  Staff has no questions.

11                 CHAIRMAN GRAHAM:  Commission board.

12                 Commissioner Brown.

13                 COMMISSIONER BROWN:  Thank you, Mr. Chairman.

14                 Mr. Olivera, as a follow-up to Mr.

15       McGlothlin's question, McGlothlin's question with regard

16       to why is the project still cost-effective, I'm curious

17       in hearing that answer.

18                 THE WITNESS:  It's really cost-effective

19       because the price of fuel, nuclear fuel, it is so, it's

20       so low.  If you look, for example, last year we had a

21       $4 billion fuel bill.  Nuclear produced 20% of the

22       energy, but yet it only represented $160 million of that

23       bill.  When you look at the fuel savings associated with

24       Turkey Point 6 and 7, they, the fuel savings for that

25       project are $75 billion, as calculated by Mr. Sim.  And

FLORIDA PUBLIC SERVICE COMMISSION

1109

1       it's those huge fuel savings that, that I rely on when

2       we go through all this pain and agony of building a very

3       complex project with a lot of technical challenges.

4       It's because the fuel savings are phenomenal, and they,

5       not only are they real, they provide a real hedge and

6       fuel diversity for our customers.

7                 COMMISSIONER BROWN:  Thank you.

8                 CHAIRMAN GRAHAM:  Commissioner Edgar.

9                 COMMISSIONER EDGAR:  Thank you, Mr. Chairman.

10                 Mr. Olivera, in your prefiled testimony and

11       also in your summary you described that, a portion of

12       Mr. Jacobs' testimony as, quote, heads I win, tails you

13       lose.  I'm really not clear on what you mean by that

14       phrase in the context of your testimony or using the

15       flip a coin metaphor.  Could you explain to me the point

16       that you were trying to make by using that phrase?

17                 THE WITNESS:  Yes, I'd be happy to.  In this

18       scenario, it is, it's -- we take all the risk, as laid

19       by Witness Jacobs, with, with these projects.  But, you

20       know, all the benefits accrue to, to the customers.  I

21       mean, in this scenario it assumes, by the way, too, that

22       you could go out and finance these projects, even if you

23       have this scheme where it's breakeven.  So any

24       incremental dollars that we spend would not -- at this

25       particular point in time, taking a snapshot of where we

FLORIDA PUBLIC SERVICE COMMISSION

1110

1       are, which is $4 gas, you know, our -- we -- our

2       shareholders have to absorb any other costs.  And by the

3       way, you're assuming that we could go out and finance

4       this under this scenario, which I'll put that aside.

5                 COMMISSIONER EDGAR:  I'm not.

6                 THE WITNESS:  Okay.  Well, if you want me

7       to --

8                 COMMISSIONER EDGAR:  I'm not making that

9       assumption.

10                 THE WITNESS:  Well, okay.  Good.  I mean, I'm

11       happy to address that as well.  Maybe I should address

12       that and I'll come back to your question.

13                 In this scenario, we, we spend every dollar

14       that FPL generates, all the cash it generates, and then

15       we go out and we borrow more to build these projects.

16       It's not just this; it's the modernizations that we're

17       doing.  These projects have created huge customer value.

18       It's why we have the lowest bills, because they're very

19       efficient generation.

20                 But, you know, over time you have to be able

21       to keep financing that, and that requires going to

22       investors.  I'm the guy that often has to go talk to

23       investors and say, this is a good -- you know, you

24       should allow us to continue to borrow because we are

25       going to recover prudently invested funds.

FLORIDA PUBLIC SERVICE COMMISSION

1111

1                 And so in this scenario it would be very hard

2       to go talk to investors and say, well, anything above

3       the breakeven, if we go over 3, $400 million, we're

4       probably going to be able to recover, but by the way,

5       lend us the money.  That's a tough, that's a tough thing

6       for me to say to an investor.

7                 If you go back to the breakeven, to the

8       witness's recommended approach, that's kind of what

9       you're doing.  You're saying you're going to be

10       spending, you're going to be taking all the risk, but

11       you're not going to get recovered for it.  And by the

12       way, fuel prices go up, and let's assume that gas

13       doubles again, customers get a huge windfall, but we

14       would have lost an opportunity to recover any of those

15       costs.

16                 When you look at these projects, you have to

17       look at not just the math.  And the math is good because

18       they save today, on all of the current assumptions they

19       save customers money.  I think you also have to put on a

20       bigger hat and say, how is Florida best served?  How do

21       we best serve our customers?  How do we bring in fuel

22       diversity, continue to try to build some fuel diversity?

23       And there aren't very many choices to do that right now.

24                 I worry about continuing to build natural gas,

25       but we don't have a lot of choices.  And it's still,

FLORIDA PUBLIC SERVICE COMMISSION

1112

1       it's the right strategy, but any opportunity you have to

2       get more something else, such as nuclear, into the mix,

3       relatively economic nuclear, it's a win for our

4       customers.

5                 COMMISSIONER EDGAR:  When the need

6       determination was granted, it is my belief, and I think

7       it's clear in the order, it's my belief and was my view

8       at the time that the additional fuel diversity was an

9       important component of the project.  I continue to

10       believe that, but I do not believe that we are

11       litigating that today.

12                 THE WITNESS:  Good.  Thank you.

13                 COMMISSIONER EDGAR:  You made the -- and this

14       has taken me a little further than I had intended to go,

15       but you opened the door.  You made the statement a few

16       moments ago that the company is taking on all the risk

17       and all the benefits are accruing to the customers.

18       Some might say, or an alternate view might be that the

19       ratepayers are taking on risk under the statutory,

20       excuse me, statutory scheme that we have, that the

21       ratepayers are taking on risk by paying costs over the

22       years in advance of those fuel cost benefits accruing.

23       Would you agree that the ratepayers are taking on risk

24       by absorbing costs prior to the project being up and

25       running?

FLORIDA PUBLIC SERVICE COMMISSION

1113

1                 THE WITNESS:  Yes, I would agree.  And if I

2       gave, left you with the impression that -- when I said

3       all the risk, I meant under the scheme of Witness

4       Jacobs.

5                 Absolutely, the customers are taking risk.

6       The shareholders are also taking risks.  If you look at

7       the time frame between '11 and '12, we will spend

8       roughly $2.2 billion on these projects.  We will recover

9       about $500 million.  So, you know, we're happy to have

10       that, we're happy to have the direction from this

11       Commission that ultimately there will be a path for the

12       other.  So the customers clearly are taking risk.  I

13       think it's a modest risk relative to the benefits that

14       we believe the customers will get.  But, yes, they

15       certainly are taking risk, and I didn't mean to argue

16       otherwise.

17                 COMMISSIONER EDGAR:  Those benefits down the

18       road.  Some might say that the Commission is also taking

19       some risks.

20                 THE WITNESS:  I understand that too.

21                 COMMISSIONER EDGAR:  Thank you.

22                 CHAIRMAN GRAHAM:  Commissioner Balbis.

23                 COMMISSIONER BALBIS:  Thank you, Mr. Chairman.

24       A few questions for Mr. Olivera.

25                 Mr. Jacobs, in his testimony, discussed the

FLORIDA PUBLIC SERVICE COMMISSION

1114

1       changing of the EPU management team, and I would assume

2       that the changing of the entire team is a difficult

3       decision and one that is not made lightly.

4                 Could you explain how you minimize and what

5       the process was to change the team out so as not to

6       affect those, that project?

7                 THE WITNESS:  Thank you for the opportunity.

8       We essentially only changed two people in the team, and

9       I will tell you why we changed it.

10                 The project -- you know, we have, I think, a

11       fair amount of experience with these large construction

12       projects.  You know, we have built four big power

13       plants:  Turkey Point 5, three West County units.  So I

14       think we have -- we kind of understand what it takes.

15       This is arguably far bigger than those, but, you know,

16       we have a lot of practice and a lot of people that are

17       involved in it.

18                 So we felt that as the project moved along

19       from kind of a general scoping and general, sort of

20       early procurement for the project, and we used a team

21       that had a lot of engineering experience.  The

22       individual who was heading that had ran nuclear

23       engineering for a long time, been working in kind of a

24       support role.  And as it evolved, you know, I for one

25       felt strongly that we wanted somebody -- and because the

FLORIDA PUBLIC SERVICE COMMISSION

1115

1       project was going to be done in operating power plants,

2       which is different than doing this in a plant from

3       scratch, I felt it was important to have somebody that

4       had real operating experience running nuclear plants and

5       had construction experience.  Which these two guys, as

6       good as they are, didn't have that experience.  So that

7       was really the decision behind asking Mr. Jones to

8       really head this up.  We also brought in another

9       individual who has very extensive construction

10       experience and has also dealt a lot with the vendors in

11       procurement, and so we felt that that was kind of a good

12       combination.  And that was kind of -- in summary, that's

13       the reason we made that change.

14                 COMMISSIONER BALBIS:  But the process itself

15       of making the change -- again, I want to focus on my

16       assumption that, that any time you have a management

17       change, that there's going to be some, there's a

18       learning curve, there's -- I mean, what did you do or

19       FPL do to kind of ease that transition?

20                 THE WITNESS:  A lot of the people who were

21       involved in doing the work were the same.  They

22       didn't -- those people didn't change.  It was really

23       more in providing the direction, it was really more in

24       having experience in dealing with vendors in a very

25       complicated project.  And you've already heard a lot

FLORIDA PUBLIC SERVICE COMMISSION

1116

1       about kind of what the sausage (phonetic) making is,

2       what it, what it takes to deal with a -- two very big

3       vendors in Bechtel and Siemens that played a key, play a

4       key role in these projects, and these people had that

5       kind of experience.

6                 And so, you know, the other, the other thing

7       is you look to the rest of the team to provide

8       continuity, and we still had the same oversight people

9       involved.  You know, I continued to be involved.  The

10       Chief Nuclear Officer continued to be monitoring this

11       project pretty closely during that time.

12                 COMMISSIONER BALBIS:  Okay.  And one last

13       question, Mr. Chairman.

14                 There's been a lot of discussion by Mr. Jacobs

15       and others on, and yourself as far as the vendors and

16       large vendors, and one of the concerns I have is that,

17       you know, again, once you go down a certain path, that

18       although decisions may be prudent, you're still somewhat

19       at, at the mercy of the vendor that you've selected or

20       the actions they take.  Do you feel that the existing

21       controls that you have in, in working with those

22       vendors, again, there was discussion on pushing back on

23       the vendor, et cetera, with the management changes or

24       other changes, do you feel there's enough of a control

25       on the vendors to protect FPL and the ratepayers?

FLORIDA PUBLIC SERVICE COMMISSION

1117

1                 THE WITNESS:  I do.  I feel like we have very

2       good processes, very good controls in place.  I take

3       comfort in the Concentric report that's validated that

4       and the Staff report that has also validated that.

5                 COMMISSIONER BALBIS:  Okay.  Thank you.  I

6       have no further questions.

7                 CHAIRMAN GRAHAM:  Thank you.

8                 Commissioner Brisé.

9                 COMMISSIONER BRISÉ:  Thank you, Mr. Chairman.

10       I want to thank Mr. Olivera for being here.

11                 I have two questions for you.  One of them --

12       and both of these are more broad questions.

13                 Referring back to the section of your

14       testimony where you talk about what the Legislature did

15       and what the Commission did with the intention of

16       promoting the development of new nuclear, yesterday part

17       of the discussion was the issue of the option; whether a

18       company can decide to seek an option to build these

19       projects but ultimately decide not to build the

20       projects.  From your understanding, the intent of the

21       Legislature was to actually have projects built.  Would

22       we agree on that?

23                 THE WITNESS:  Absolutely.

24                 COMMISSIONER BRISÉ:  So that would go to the

25       idea that whatever projects that you all have undertaken

FLORIDA PUBLIC SERVICE COMMISSION

1118

1       as a company, your intention is to build them?

2                 THE WITNESS:  Correct.

3                 COMMISSIONER BRISÉ:  Okay.  The second

4       question that I have goes to if the Commission were to

5       disallow the capital costs as asserted by Mr. Jacobs,

6       what do you think it does to the overall framework of

7       nuclear generation moving forward in this state?

8                 THE WITNESS:  I think it would bring it to a

9       halt.  We would do our very best to complete these

10       projects.  But as I mentioned to Commissioner Edgar

11       earlier, I'm not sure that we could go out and get the

12       financing to complete these projects without the right

13       framework and without -- and given -- I mean, if there

14       was a change in, at least in my mind, the nuclear cost

15       recovery rule, it would be a seismic change.  And it

16       would ripple not just through nuclear energy, it would

17       ripple through all other aspects of what we do.

18                 And so I think it would certainly slow -- stop

19       nuclear.  It would challenge us tremendously to finish

20       these projects.  And I would say that it would have

21       ramifications in other projects, including the

22       modernizations on anything else that has large capital,

23       because there would be a concern whether a decision made

24       by one Commission where, that we go out and make huge,

25       huge commitments for very long-term projects, whether

FLORIDA PUBLIC SERVICE COMMISSION

1119

1       that could be readily undone.

2                 COMMISSIONER BRISÉ:  Follow-up, Mr. Chairman.

3                 CHAIRMAN GRAHAM:  Sure.

4                 COMMISSIONER BRISÉ:  But considering that, on

5       the flip side of that, if the Commission looks, looks at

6       a variety of decisions that have been made by the

7       company and begins to question the validity of some of

8       those decisions as being reasonable or not reasonable,

9       you do agree that the Commission then would have the

10       right and would be in its place to stop, or at least

11       seriously question some of these projects, and that

12       should not impact the broader regulatory framework in

13       keeping nuclear projects moving forward in a positive

14       direction in the state.

15                 THE WITNESS:  I agree.  The Commission has

16       wide discretion in, in what you do.  I'm just mentioning

17       in the real world that I -- you know, I have to go out

18       and explain to our investors what these projects

19       represent and why these, these are a good thing.  And so

20       I would hope that as you deliberate you factor into your

21       decisions the impact that goes beyond any specific

22       project.  The decisions that you make, they are

23       extrapolated.  Right or wrong and whether we agree with

24       it or not, they're extrapolated to any number of other

25       investments.  Even things that you want us to do and are

FLORIDA PUBLIC SERVICE COMMISSION

1120

1       in complete agreement and feel that they should go

2       forward, they're extrapolated to those as well.

3                 CHAIRMAN GRAHAM:  Commissioner Brown.

4                 COMMISSIONER BROWN:  Thank you, Mr. Chairman.

5                 Just a follow-up to some of your responses to

6       some of the Commissioners' questions regarding

7       financing.  Mr. Olivera, how do you feel that the

8       current financial market today will affect the company's

9       financing capabilities on these projects?

10                 THE WITNESS:  Like everybody else, it's a

11       little scary to watch the gyrations of the market.  So

12       far, I mean, we've continued to have access to the

13       capital markets.  We have a pretty extensive line of

14       credit that we have frankly barely touched.  We -- sort

15       of that's been our backup.  And so, you know, I can

16       never -- I learned long ago never to say never.  But

17       right now we have access to capital, even if it was on a

18       short-term line of credit, that would allow us to

19       continue working on these projects.

20                 COMMISSIONER BROWN:  Thank you.

21                 CHAIRMAN GRAHAM:  Redirect?

22                 MR. ANDERSON:  Just very briefly.

23                        REDIRECT EXAMINATION

24       BY MR. ANDERSON:

25            Q    Commissioner Brisé was asking you some

FLORIDA PUBLIC SERVICE COMMISSION

1121

1       questions, looking back at the legislation which

2       promoted new nuclear generation, and we've talked about

3       economic fuel diversity benefits and savings for

4       customers.  But was there an electric reliability aspect

5       of that also?

6            A    No, absolutely.  And I think I mentioned that

7       when I was answering Commissioner Edgar's questions.

8                 The nuclear projects, not only do they provide

9       fuel benefit, but they also provide a huge reliability

10       benefit, particularly the units in Miami-Dade County.

11       We have roughly 25% of our customers are in the

12       Miami-Dade County area, and so any generation we have

13       close to the load center is more reliable than having to

14       rely on generation that's far away and you have a lot of

15       transmission lines that run for hundreds of miles.  So

16       we always favor anything that increases the capacity in

17       that area.

18            Q    And we've talked about the company has, has

19       high electric reliability, but should that be taken for

20       granted?  Are there ever close calls that, in terms of

21       electric reliability that nuclear generation can

22       contribute to?

23            A    I'm an old operating guy.  I never take

24       reliability for granted.  It's hour by hour, minute by

25       minute.  And so, no, we can't take that for granted.  We

FLORIDA PUBLIC SERVICE COMMISSION

1122

1       can't take for granted the value of having sufficient

2       generation reserves, and I think this Commission has

3       historically recognized that.

4                 MR. ANDERSON:  We have no further questions.

5       Thank you.

6                 CHAIRMAN GRAHAM:  Okay.  We don't have any

7       exhibits to enter into the record for this witness?  No?

8                 MR. ANDERSON:  We do not.

9                 CHAIRMAN GRAHAM:  Sir, thank you very much for

10       your testimony.

11                 THE WITNESS:  Thank you, sir.

12                 MR. ANDERSON:  With the completion of

13       Mr. Olivera's rebuttal testimony, may he be excused for

14       the balance of the hearing?

15                 CHAIRMAN GRAHAM:  Is there any -- is it okay

16       for everybody for this witness to be excused?

17                 MR. YOUNG:  No objection.

18                 CHAIRMAN GRAHAM:  Intervenors?

19                 Yes.

20                 MR. ANDERSON:  May we proceed with our next

21       witness?

22                 CHAIRMAN GRAHAM:  Yes.

23                 MR. ANDERSON:  FPL calls as its next witness

24       Terry Deason.

25                             TERRY DEASON

FLORIDA PUBLIC SERVICE COMMISSION

1123

1       was called as a rebuttal witness on behalf of Florida

2       Power & Light Company and, having been duly sworn,

3       testified as follows:

4                          DIRECT EXAMINATION

5       BY MR. ANDERSON:

6            Q    Good morning, Mr. Deason.

7            A    Good morning.

8            Q    Have you been sworn?

9            A    Yes, I was sworn this morning.

10            Q    Would you please tell us your name and your

11       business address.

12            A    Yes.  My name is Terry Deason.  And my

13       business address is 301 Bronough Street, Tallahassee,

14       Florida, 32301.

15            Q    By whom are you employed and in what capacity?

16            A    I'm employed by the firm Radey, Thomas, Yon &

17       Clark as a special consultant.

18            Q    Have you prepared and caused to be filed 15

19       pages of prefiled rebuttal testimony in this proceeding

20       on July 25, 2011?

21            A    Yes, I have.

22            Q    Do you have any changes or revisions to your

23       rebuttal testimony?

24            A    I do not.

25            Q    If I asked you the same questions contained in

FLORIDA PUBLIC SERVICE COMMISSION

1124

1       your prefiled rebuttal testimony, would your answers be

2       the same?

3            A    Yes, they would.

4                 MR. ANDERSON:  Chairman Graham, FPL asks that

5       the prefiled rebuttal testimony of the witness be

6       inserted into the record as though read.

7                 CHAIRMAN GRAHAM:  We will insert the

8       prefiled -- we will insert the prefiled rebuttal

9       testimony into the record as though read for Mr. Deason.

10       BY MR. ANDERSON:

11            Q    Mr. Deason, you have one exhibit which you

12       called TD-1.  Is that right?

13            A    Yes.

14                 MR. ANDERSON:  This is shown on Staff's

15       exhibit list, Mr. Chairman, as Exhibit 130.

16                 CHAIRMAN GRAHAM:  Okay.

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1140

1       BY MR. ANDERSON:

2            Q    Mr. Deason, would you please go ahead and

3       introduce, reintroduce yourself to the Commission and

4       provide a summary of your, of your testimony.

5            A    Commissioners, it's a pleasure to be back here

6       in this hearing room again and to have this opportunity

7       to provide testimony to you as you consider this very

8       important matter.

9                 OPC is recommending that FPL should be

10       required to utilize a breakeven analysis to disallow

11       otherwise prudent costs.  This is inappropriate and

12       should be rejected.  OPC's recommendation is a midstream

13       attempt to fundamentally and inappropriately change

14       Florida's policy for determining nuclear cost recovery

15       and feasibility and, if implemented, would have negative

16       implications for FPL's customers.

17                 OPC suggests that the Commission should no

18       longer use the cumulative present value of revenue

19       requirements, which I will refer to as present value

20       analysis, as the means to determine cost-effectiveness

21       and continued project viability.

22                 For many years the Commission has consistently

23       and appropriately used the present value approach to

24       make decisions on cost-effectiveness in need

25       determination proceedings and in the nuclear cost

FLORIDA PUBLIC SERVICE COMMISSION

1141

1       recovery proceedings.  The present value approach

2       appropriately considers forward-looking costs and should

3       not be discontinued.

4                 OPC's suggestion to replace the Commission's

5       use of the present value analysis with a breakeven

6       approach is inappropriate for many reasons and should be

7       rejected.  OPC's proposed breakeven approach

8       inappropriately relies on hindsight and has the effect

9       of disallowing otherwise prudent costs.  This is

10       contrary to the state's policy to promote nuclear

11       generation and violates basic principles of ratemaking.

12       All prudently incurred costs are to be included in

13       rates.  OPC's suggested approach does not do this and

14       violates this basic principle.

15                 OPC's suggestion also materially distorts the

16       balance of risk provided for by the Legislature and the

17       Commission.  This could have severe negative

18       consequences for customers by limiting options for new

19       generation needed to cost-effectively and reliably serve

20       them.  In essence, OPC's suggestion is a risk-sharing

21       mechanism which has been previously rejected and

22       determined by the Commission to be impermissible.

23                 OPC also alleges that FPL's and this decision,

24       this Commission's decision to expedite the extended

25       power uprates was imprudent.  I cannot agree that this

FLORIDA PUBLIC SERVICE COMMISSION

1142

1       decision was imprudent.  At the time FPL proposed and

2       the Commission approved the expedited schedule, FPL was

3       appropriately responding to the circumstances at the

4       time.  After being encouraged to consider ways to

5       increase its fuel diversity, FPL proposed the Glades

6       Power Park, two coal-fired units in Glades County.

7       These units were rejected by the Commission.

8                 FPL then proposed and the Commission approved

9       the expedited schedule for the EPU project.  This was

10       done to cost-effectively meet the need for capacity and

11       energy, to increase fuel diversity, to minimize

12       greenhouse gas emissions, and to achieve fuel savings

13       for customers as quickly as possible.

14                 Such actions by FPL should be encouraged.

15       OPC's allegation of imprudence ignores these realities

16       and penalizes FPL for proposing a cost-effective

17       solution to meet these needs and achieve these goals.

18                 FPL has appropriately relied upon the

19       Commission's decisions to approve the expedited

20       schedule.  It is inappropriate to attempt to litigate

21       that now.  Good regulation should maintain consistent

22       policies that can be relied upon and which encourage

23       utilities to make aggressive and prudent decisions to

24       maximize customer benefits.  OPC's suggestion of

25       imprudence would send the wrong message and have the

FLORIDA PUBLIC SERVICE COMMISSION

1143

1       opposite effect.

2                 That concludes my summary.

3                 MR. ANDERSON:  Thank you, Mr. Deason.

4                 The witness is available for

5       cross-examination, Chairman Graham.

6                 CHAIRMAN GRAHAM:  Thank you.

7                 Intervenors?  Ms. Kaufman.

8                          CROSS EXAMINATION

9       BY MS. KAUFMAN:

10            Q    Good morning, Mr. Deason.  I've often wanted

11       to cross-examine you.

12            A    I bet you have.

13                 (Laughter.)

14                 If I were in your place, I would relish the

15       opportunity.

16            Q    You know I'm just kidding you.

17            A    I think back, was I ever mean to you before?

18            Q    Never.  Always the consummate gentleman.

19                 As I understand your testimony, and I think

20       you referenced this in your summary, you take issue with

21       Mr. Jacobs' suggestion that the Commission look at a

22       breakeven analysis, and you've referenced that.

23                 And you also claim that that kind of analysis

24       would require the Commission to engage in hindsight; is

25       that correct?

FLORIDA PUBLIC SERVICE COMMISSION

1144

1            A    Yes.

2            Q    Okay.  Would you agree with me that as the

3       Commission evaluates the cost-effectiveness of a project

4       each year as it goes forward, it should be able to use

5       the tools that it finds the most appropriate to look at

6       the project?

7            A    Absolutely.  The Commission should avail

8       itself of the tools that it thinks are appropriate.  The

9       present value analysis is an appropriate tool, is one

10       the Commission has relied upon in the past.  And, and a

11       breakeven analysis can also be used to look at whether a

12       project should continue.

13                 The problem I have is with the suggestion that

14       a breakeven analysis, that that tool be used in an

15       inappropriate manner, that manner being to basically put

16       a cap on costs that otherwise would have been determined

17       to be prudent.  That is not the purpose, that is not the

18       intent, that is not correct use of a breakeven analysis.

19            Q    But I think that you agreed that the use of a

20       breakeven analysis in this situation could be

21       appropriate if the Commission deems it to provide

22       information that they find relevant.

23            A    Yes, it could be used by the Commission, not

24       to determine what costs should be recoverable, but to

25       determine the continued viability of the project.

FLORIDA PUBLIC SERVICE COMMISSION

1145

1                 One needs to understand that a breakeven

2       analysis is just a refinement of the present value

3       analysis.  The present value analysis compares two

4       alternatives and determines which of those is the most

5       cost-effective alternative.  A breakeven analysis just

6       takes that one, takes it a step and looks and determines

7       the magnitude of the difference in costs.

8                 And if there are two projects and there's a

9       difference, a beta of one million, that means that one

10       is $1 million more cost-effective than the other, and

11       that the other project, that those costs, there's a $1

12       million difference and that's the breakeven point.

13       Costs for the project that you approve could increase by

14       $1 million and it becomes breakeven with the project

15       that you're comparing it against.

16            Q    But certainly if the Commission wanted to

17       request the company to perform a breakeven analysis,

18       that would -- in your view, would that be something the

19       company would be willing to provide?

20            A    I can't speak for the company in that regard.

21       I believe that question was asked to Mr., perhaps

22       Mr. Sim yesterday.  I think the record speaks for

23       itself.  But as I recall, I think he indicated that is

24       an analysis that FPL can perform, perhaps routinely

25       performs.  But the point that needs to be made to the

FLORIDA PUBLIC SERVICE COMMISSION

1146

1       Commission is that you do not use that analysis as a

2       tool for -- and achieve a purpose for a never -- it was

3       never intended, it was never intended to be a tool to

4       deny the recoverability of otherwise prudently incurred

5       costs.  That's the point.

6            Q    Mr. Deason, I apologize for not recalling.

7       Were you on the Commission when the determination of

8       need for the EPU was granted?

9            A    I was not.

10            Q    Okay.  Have you reviewed the record in that

11       case in preparation for your comments here today?

12            A    To a limited extent.  I would not call it a

13       thorough review of that record.  I do recall that the,

14       that the matter was actually presented to the Commission

15       in the form of a stipulation.  I do recall -- I looked

16       at some of the information requests or interrogatories

17       that the Staff submitted, and it appeared to me the

18       Staff did a very thorough analysis, as they always do on

19       need determination proceedings, but I do not believe

20       there were other -- any other Intervenors in the case.

21            Q    Well, from your limited review, as you've

22       said, of the record, do you recall whether you ever saw

23       the term "fast tracked" used by anybody in the documents

24       that you reviewed?

25            A    No.  I, I did not see the term "fast track" in

FLORIDA PUBLIC SERVICE COMMISSION

1147

1       my limited review, but I did see terms used.  Expedited,

2       quickest feasible manner, or things similar to that.

3       But, no, the term "fast track," I did not see that

4       particular term.

5            Q    Have you, have you been here -- were you here

6       yesterday?  Have you been in the hearing room?

7            A    I was not in the hearing room yesterday.  I

8       did come out here yesterday evening about 5:30, quarter

9       to 6:00, just in case things were moving so rapidly as

10       to whether I would be needed, but that was my limited

11       extent to being here yesterday.

12            Q    Okay.  You reviewed the testimony in this

13       case, have you not?  You certainly reviewed Dr. Jacobs'

14       testimony.

15            A    Yes, I did.

16            Q    Okay.  And you would agree with me that there

17       is a rather strenuous debate among the parties as to

18       whether expedited is the same thing as fast tracked?

19            A    Yes, I do understand that there is a

20       difference of opinion as to whether those terminologies

21       mean something different as they are used in the context

22       of the issues in this case.

23                 MS. KAUFMAN:  Thank you, Mr. Deason.  It was a

24       pleasure.

25                          CROSS EXAMINATION

FLORIDA PUBLIC SERVICE COMMISSION

1148

1       BY MR. McGLOTHLIN:

2            Q    Hello, Mr. Deason.

3            A    Hello.

4            Q    Based upon your prefiled testimony and your

5       summary, as I understand it, you object to the use of a

6       breakeven analysis to disallow costs that would

7       otherwise be deemed prudent; is that correct?

8            A    That is correct.

9                 MR. McGLOTHLIN:  No further questions.

10                 MR. WHITLOCK:  No questions for this witness,

11       Mr. Chairman.

12                 CHAIRMAN GRAHAM:  Staff?

13                 MR. YOUNG:  No questions.

14                 CHAIRMAN GRAHAM:  Commissioner Edgar.

15                 COMMISSIONER EDGAR:  Thank you, Mr. Chairman.

16                 Hello, Mr. Deason.

17                 THE WITNESS:  Hello, Commissioner.

18                 COMMISSIONER EDGAR:  You have in your prefiled

19       and also in response to questions talked to us here

20       today a good amount about that, the issue of the

21       breakeven analysis.  I'd like to approach that from a

22       slightly different point and pose to you, in light of

23       your unique experience working as a consumer advocate

24       and also as a regulator, could you speak to us from your

25       experience and with your expertise about the issue of

FLORIDA PUBLIC SERVICE COMMISSION

1149

1       separate long-term feasibility analyses versus

2       comprehensive?

3                 THE WITNESS:  I need some clarification on

4       your question.  Are you talking about in the context of

5       the EPU uprate project and it being conducted at two

6       different plant sites?

7                 COMMISSIONER EDGAR:  Yes.  Yes, I am.

8                 THE WITNESS:  Okay.  I think it is, it is

9       important for the Commission to consider the context in

10       which the EPU project was presented to it at the time of

11       the need determination.  It was presented as one

12       project, and the cost estimates and the comparison to

13       other alternatives were done in the context of one

14       project.  I think for consistency that it needs to be,

15       to continue to be, to be viewed as one project.

16                 And the reason is because when the decision

17       was made that it was the most cost-effective

18       alternative, there was a need of a certain magnitude

19       that needed to be met, and that need was as a result of

20       the fact that the Commission denied the Glades power

21       project.  I'm not taking issue with the Commission's

22       decision to deny that, but it is a reality.

23                 COMMISSIONER EDGAR:  Which was a vote that I

24       made.

25                 THE WITNESS:  I didn't participate in that

FLORIDA PUBLIC SERVICE COMMISSION

1150

1       case.  But I do recall the Commission strongly

2       encouraging FPL, all of Florida's utilities, perhaps FPL

3       in particular, to look at what I call solid based, solid

4       fuel generating alternatives, which would either be

5       nuclear or coal, because there was concern about a lack

6       of fuel diversity and perhaps an overreliance on natural

7       gas generation.

8                 And it was at the encouragement of the

9       Commission that the Glades project was studied and it

10       was proposed and it was fully vetted at the Commission

11       and a decision was reached.  And that's fine, that's the

12       way the process should work, and a decision was made.

13                 But I think the Commission should be cognizant

14       that it put FPL in the position of having to determine

15       how they could cost-effectively meet the demand that was

16       envisioned in the 2012/2013 time frame, how they could

17       do that while also minimizing greenhouse gas emissions,

18       while increasing fuel diversity, and doing all of that

19       in a cost-effective manner.

20                 And that was as a result that FPL came forward

21       with the EPU project, and it was one project to meet

22       that demand.  Both of these projects, if you want to say

23       they were separate projects, were needed to meet the

24       demand.

25                 But beyond that, the cost-effectiveness was

FLORIDA PUBLIC SERVICE COMMISSION

1151

1       looked at as one project, and to, now to sever that and

2       say that they are standalone projects and one could

3       proceed or one could not, I think that's placing a lot

4       in jeopardy.

5                 There's also been testimony in this proceeding

6       about the location of generation and how that's

7       important for liability purposes and in terms of perhaps

8       additional transmission costs.  I know there's an

9       allegation by FP -- I mean by OPC that one of the, one

10       of the, I think it's Turkey Point, that it may not

11       appear to be as cost-effective because of the fact that

12       the life of that plant is not as great as the remaining

13       life of the other nuclear plant.

14                 Well, I think the Commission should obviously

15       ask whether there's a possibility of the life being

16       extended at Turkey Point.  I don't have an answer to

17       that question, but that is perhaps a possibility.

18                 But also the Commission has heard testimony

19       about the necessity of having generation located close

20       to load.  So that's another aspect.  I think the fact

21       that the, that the generation was going to be, from

22       Turkey Point was going to be closer to load was a

23       consideration.  I know it was something that Staff

24       explored in their interrogatories as they posed them to

25       FPL in terms of whether the project was cost-effective,

FLORIDA PUBLIC SERVICE COMMISSION

1152

1       and it was a factor.

2                 So to ignore the benefits and the cost

3       parameters that were explored in the need determination

4       and at this point, some years later, to sever that -- I

5       think it could be done.  I would use extreme caution

6       before doing so.  I just think that it could, it could,

7       it could put some things in jeopardy.

8                 COMMISSIONER EDGAR:  I remember and recognize

9       and, you know, appreciate the points that you're making,

10       realizing that at the time the project was presented as

11       a whole as opposed to separate components, and that

12       there was the belief and the expectation that that would

13       therefore include some efficiencies and some additional

14       cost-effectiveness and some, you know, additional

15       benefits of, of approaching it that way.

16                 But would you agree that, by virtue of a

17       project being presented in that way, does not preclude

18       the Commission's responsibility or authority to analyze

19       a project as separate components?

20                 THE WITNESS:  I would agree with that,

21       Commissioner.  My only caution would be to look at it,

22       make sure it's the right thing to do, realize that there

23       could be other consequences of breaking it apart.  But,

24       yes, I think it's within the Commission's discretion to

25       do that.

FLORIDA PUBLIC SERVICE COMMISSION

1153

1                 COMMISSIONER EDGAR:  Thank you.

2                 CHAIRMAN GRAHAM:  I'm glad you asked that

3       question.  You took it right out of my mouth.

4                 Commissioner Brisé.

5                 COMMISSIONER BRISÉ:  Thank you, Mr. Chairman.

6                 Mr. Deason, happy to see you again.  I have a

7       couple of questions, and they'll be based from your

8       testimony.  Go to page 3 on your testimony where on line

9       12 -- the question is, "Why do you disagree with the

10       recommendation of Witnesses Jacobs and Smith?"

11                 And, one, you have that the recommendation

12       addresses a midstream attempt to fundamentally,

13       fundamentally and inappropriately change the standard

14       for determining cost recovery through the nuclear

15       recovery clause.  So I suppose that that goes to the

16       issue of finality to a certain degree.

17                 THE WITNESS:  Yes, Commissioner, it does.  It

18       goes to, I think, the need for finality and how that was

19       expressed by the Legislature and how the Commission

20       adopted its rule.  With the annual prudence reviews and

21       the finality of those, I think, yes, it goes to the

22       heart of that.  And I think that OPC's suggestion is, is

23       midstream in the fact that the Commission has already

24       determined a need for the project and it's determined

25       that the, the expedited approach was the appropriate

FLORIDA PUBLIC SERVICE COMMISSION

1154

1       approach.

2                 So, yeah, I would consider that it would be a

3       midstream and it would be counter to the policy of the

4       State of Florida to determine finality of costs based

5       upon annual prudence reviews.

6                 COMMISSIONER BRISÉ:  Now, on, on page 4 you

7       address the issue, starting at line 5, 5 through 14,

8       whether the breakeven alternative is needed to protect

9       customers from unreasonable costs, "Do you agree?"

10                 The question that I have is do you agree for

11       this instant or is that something that the Commission

12       should potentially look at moving forward?

13                 THE WITNESS:  I believe -- the answer to your

14       question is both.  I think that my answer is in terms of

15       where we find us, where we find ourselves at this point,

16       as well on a moving forward basis.

17                 You have to realize, Commissioner, that the

18       breakeven analysis being proposed by OPC, it doesn't

19       find fault with any particular costs.  In fact, I think

20       this testimony in this case is devoid of there being any

21       specific cost that was incurred by FPL that was deemed

22       to be imprudent.

23                 What it does is it relies upon hindsight,

24       relies upon sunk costs, and an ever-changing breakeven

25       analysis which is going to change with time.  That

FLORIDA PUBLIC SERVICE COMMISSION

1155

1       breakeven analysis is going to change as the price of

2       gas changes, perhaps as inflation changes, cost of

3       capital changes, or, or cost of materials change, or --

4       it's going to change as well.

5                 Sitting here today, we don't know what the

6       relationship is going to be with a breakeven analysis at

7       the time that these, this EPU project is completed.  It

8       could be below that, it could be above.  But the fact

9       that it is above does not mean that there has been one

10       dime of cost incurred imprudently, and that's how it

11       violates the policy that has been established by the

12       Legislature and this Commission.

13                 COMMISSIONER BRISÉ:  So final question.  So

14       from your perspective, not only in this instant but as

15       an overarching policy for the Commission, it would be

16       bad policy to pursue that, this, that approach?

17                 THE WITNESS:  Yes, it would be bad policy.  It

18       would be inconsistent with policy already established.

19       And as you heard Mr. Olivera say, he feels like that it

20       would -- could possibly prevent the company from doing

21       additional nuclear projects just from the fact of the

22       adverse impacts on the investment community.

23                 COMMISSIONER BRISÉ:  Thank you.

24                 CHAIRMAN GRAHAM:  Redirect?

25                 MR. ANDERSON:  Thank you, Mr. Chairman.

FLORIDA PUBLIC SERVICE COMMISSION

1156

1                         REDIRECT EXAMINATION

2       BY MR. ANDERSON:

3            Q    Mr. Deason, Ms. Kaufman asked you if you

4       recalled seeing the word "fast track" in the nuclear

5       uprate need determination information.  Do you recall

6       that?

7            A    Yes.

8            Q    And you told us that you saw information about

9       completing the project as soon as practicable and

10       expedited and those things; right?

11            A    Yes.  I did see that terminology.

12            Q    You are -- are you aware that the Commission

13       determined in the 2008 need order that the uprates were

14       approved to fulfill a 2012 reserve resource need for

15       FPL?

16            A    Yes, I saw that.  And that was, that was the

17       need -- that was determined that was the time frame.

18       And the only way that those projects could have been

19       completed is if it had been expedited.  Now whether

20       someone wants to use the term fast track or not, you

21       know, I don't want to quibble with that.  But I think

22       the Commission did recognize to have these plants in

23       place to meet the need for the time frame envisioned,

24       2012 and 2013, that these projects had to be expedited.

25            Q    In the course of your work you mentioned that

FLORIDA PUBLIC SERVICE COMMISSION

1157

1       you reviewed discovery that Staff propounded on the

2       company and the company responded to in that case; is

3       that right?

4            A    Yes, I did review that.

5            Q    From your review was it understood that this

6       was a complex project?

7            A    Yes, it was -- to my -- in my opinion, yes.  I

8       think certainly the, the scope and the, the, the

9       in-depth questions that were asked by Staff in their

10       review, I think it was obvious that it was a complicated

11       project.

12            Q    Was there testing and probing of the inputs to

13       the economic analysis submitted in the proceeding?

14            A    Yes.  It was -- yes.  As, as is the case in

15       all need determinations, it was certainly the case for

16       the need determination for these projects as well.

17       There were a number of scenarios that were reviewed that

18       could affect the outcome of that, and the analysis was

19       done which showed that these projects were -- they were

20       either cost-effective in all scenarios or the vast

21       majority of the scenarios.

22            Q    And you're familiar from your review of

23       Dr. Jacobs' testimony that he points to the geographic

24       distance of the plants and the differences in license

25       terms and things like that, those are the part of the

FLORIDA PUBLIC SERVICE COMMISSION

1158

1       reasons Dr. Jacobs says a different analysis should be

2       done; is that right?

3            A    I'm sorry.  Could you repeat the question?

4            Q    Okay.  Focusing on the discovery you reviewed

5       in the need determination case, did -- was there

6       investigation and probing of the different license lives

7       of the plants?

8            A    Honestly, I just don't remember that at this

9       point based upon my review.

10            Q    Okay.  Okay.  That's fine.

11                 Did Public Counsel submit any testimony in the

12       need determination for your review?

13            A    No, Public Counsel did not.  It was my

14       understanding there were no Intervenors in the case.

15            Q    If Public Counsel had wanted to challenge the

16       timing or method of the project, call it expedited or

17       call it fast track or call it Bob --

18                 MR. McGLOTHLIN:  I object to this line of

19       questioning as beyond the scope of cross-examination.

20                 MR. ANDERSON:  I believe it's directly within

21       the scope because Ms. Kaufman asked about the 2007 need

22       determination proceeding.

23                 MR. McGLOTHLIN:  She didn't ask anything about

24       OPC's participation.

25                 CHAIRMAN GRAHAM:  Wait a second.  I do not

FLORIDA PUBLIC SERVICE COMMISSION

1159

1       remember what the question was.  We can get the court

2       reporter to bring it back.

3                 MR. ANDERSON:  May I rephrase a different

4       question?  Would that be better?

5                 CHAIRMAN GRAHAM:  Let's try that.

6                 MR. ANDERSON:  Okay.

7       BY MR. ANDERSON:

8            Q    Mr. Deason, you noted there were no

9       Intervenors; is that correct?

10            A    That's correct.

11            Q    Is it fair to say that if an Intervenor wanted

12       to participate, they could have challenged the timing or

13       method of the project by whether the project was

14       expedited or fast tracked?

15            A    Yes.  The timing of a project would be a

16       legitimate issue that could be raised in any need

17       determination proceeding as to what -- and as to whether

18       the need actually exists that is being, being presented.

19       And the Commission looks at that and the timing of that

20       and whether there are other alternatives which could

21       meet that need, such as conservation efforts and things

22       of that nature.

23            Q    Regardless of who would have or could have

24       raised that, is it good policy to permit years later

25       relitigation of that?

FLORIDA PUBLIC SERVICE COMMISSION

1160

1            A    Well, I think this --

2                 MS. KAUFMAN:  Chairman, I'm going to object.

3       I think this is way beyond the scope of my

4       cross-examination.  And I think Mr. Deason has already

5       made his opinions clear.

6                 CHAIRMAN GRAHAM:  I have to agree with her.

7                 MR. ANDERSON:  We have no further questions.

8       Thanks.

9                 CHAIRMAN GRAHAM:  Thank you.

10                 We have some exhibits to enter into the

11       record?

12                 MR. ANDERSON:  Yes, we do.  We have Exhibit

13       130.  FPL offers Exhibit 130 into evidence.

14                 CHAIRMAN GRAHAM:  We will enter Exhibit 130

15       into the record.  Any objections to that?

16                 MR. YOUNG:  No objections.

17                 CHAIRMAN GRAHAM:  Okay.  Anything else for

18       this witness?

19                 (Exhibit 130 admitted into evidence.)

20                 MR. ANDERSON:  No, sir.  We would ask that

21       Mr. Deason be excused for the balance of the hearing.

22                 CHAIRMAN GRAHAM:  Any objections to that?

23                 Seeing none, Mr. Deason, thank you for your

24       testimony today.

25                 THE WITNESS:  Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

1161

1                 (Transcript continues in sequence with Volume

2       8.)

3

4

5

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1162

1       STATE OF FLORIDA    )

:         CERTIFICATE OF REPORTER

2       COUNTY OF LEON      )

3

4                 I, LINDA BOLES, RPR, CRR, Official Commission

Reporter, do hereby certify that the foregoing

5       proceeding was heard at the time and place herein

stated.

6

IT IS FURTHER CERTIFIED that I

7       stenographically reported the said proceedings; that the

same has been transcribed under my direct supervision;

8       and that this transcript constitutes a true

transcription of my notes of said proceedings.

9

I FURTHER CERTIFY that I am not a relative,

10       employee, attorney or counsel of any of the parties, nor

am I a relative or employee of any of the parties'

11       attorneys or counsel connected with the action, nor am I

financially interested in the action.

12

DATED THIS _____ day of _____________________,

13       2011.

14

15                  ________________________________

LINDA BOLES, RPR, CRR

16                 FPSC Official Commission Reporter

(850) 413-6734

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION