## REVISED 2 5 08
Energy Supply
5-Year Capital Forecast
Station | Unit | Project Title | 2008 | 2009 | 2010 | 2011 | 2012 | 5 YEAR FORECAST (2008 thru 2012)
BB | 1 | BB1 APH Hot And Inter Basket Repl | [5 empty] | 0
BB | 1 | BB APH Sootblower addition |  | 40000 | 90000 |  |  | 130000
BB | 1 | BB1 APH seals replacement (for SCR) |  | 130291 | 219709 |  |  | 350000
BB | 1 | BB1 BFP Internal Element Repl |  |  | 0 |  |  | 0
BB | 1 | BB1 Boiler Swell System Addition | [5 empty] | 0
BB | 1 | BB1 Boiler 1st Radiant SH Repl. |  |  |  | 0 | 0 | 0
BB | 1 | BB1 Boiler 2nd Radiant SH Repl | 115314 | 2100000 | 2653000 |  |  | 4868314
BB | 1 | BB1 Boiler Burner Front Repl | [5 empty] | 0
BB | 1 | BB1 Boiler Burner Nozzles Repl | [5 empty] | 0
BB | 1 | BB1 Boiler Cold Reheat Vvs & Vent Lines | [5 empty] | 0
BB | 1 | BB1 Boiler Drain System | [5 empty] | 0
BB | 1 | BB1 Boiler economizer Ash Reinjection | 92386 | 368039 | 389900 |  |  | 850325
BB | 1 | BB1 Boiler Furnace Floor Refractory |  |  | 0 |  |  | 0
BB | 1 | BB1 Boiler Furnace Floor Repl with refractory | 0 | 2314000 | 3702000 |  |  | 6016000
BB | 1 | BB1 Boiler HTSH outlet header Repl | 122673 | 1425000 | 2546000 |  |  | 4093673
BB | 1 | BB1 Boiler Ignitors Repl. | [5 empty] | 0
BB | 1 | BB1 Boiler Nose Arch Repl | [5 empty] | 0
BB | 1 | BB1 Boiler West & East Waterwall Weld Overlay | [5 empty] | 0
BB | 1 | BB1 Burners Repl |  |  | 0 |  |  | 0
BB | 1 | BB1 Circ Water Coarse Mesh Screens |  | 600000 | 250000 |  |  | 850000
BB | 1 | BB1 Coal/Chutes/Boxes-3 mills |  | 400000 | 400000 | 0 | 0 | 800000
BB | 1 | BB1 Coal Feeder Repl | [5 empty] | 0
BB | 1 | BB1 Coal Gate / Blast Valves (12) |  |  | 0 |  |  | 0
BB | 1 | BB1 Coal pipe system replacement |  | 1500000 | 1500000 | 0 | 0 | 3000000
BB | 1 | BB1 Condenser Ball Cleaning System | [5 empty] | 0
BB | 1 | BB1 Condenser Bundle Repl. | [5 empty] | 0
BB | 1 | BB1 Condenser Bundle Repl. | [5 empty] | 0
BB | 1 | BB1 Control Rm Relocation/Controls | 241500 | 2316800 | 2371700 |  |  | 4930000
BB | 1 | BB1 Crusher dryer repl (6) |  | 400000 | 400000 | 0 | 0 | 800000
BB | 1 | BB1 Duct -Hot Air Expansion Jt Repl |  |  | 0 |  |  | 0
BB | 1 | BB1 Duct Hardening (scr) |  | 400000 | 600000 |  |  | 1000000
BB | 1 | BB1 Duct-cold gasl-new supports, outage work-???? | [5 empty] | 0
BB | 1 | BB1 Duct-hot gas expansion Jts below dampers repl |  | 0 | 0 |  |  | 0
BB | 1 | BB1 EH2 Repl | 4500 | 631847 | 992361 |  |  | 1628708
BB | 1 | BB1 EH3 Repl | 0 | 500000 | 500000 |  |  | 1000000
BB | 1 | BB1 EH4 Repl | 103032 | 500000 | 500000 |  |  | 1103032
BB | 1 | BB1 EH5 Repl | 0 | 500000 | 500000 |  |  | 1000000
BB | 1 | BB1 EH6 Repl |  | 0 | 0 |  |  | 0
BB | 1 | BB1 EH6 Repl | [5 empty] | 0
BB | 1 | BB1 Exciter | [5 empty] | 0
BB | 1 | BB1 Flash Tank Repl |  |  | 0 |  | 0 | 0
BB | 1 | BB1 Gen H2 Cooler Repl |  | 0 | 200000 |  |  | 200000
BB | 1 | BB1 Generator Rewind with retaining rings | 0 | 6820000 | 8183000 |  |  | 15003000
BB | 1 | BB1 Hydrogen Dryer Repl |  |  | 0 |  |  | 0
BB | 1 | BB1 Main Stm Safety Valves |  |  | 0 |  |  | 0
BB | 1 | BB1 MCC IT1 & IT2 Repl |  | 0 | 0 |  |  | 0
BB | 1 | BB1 mid furnace weld overlay |  | 0 | 1000000 |  | 0 | 1000000
BB | 1 | BB1 PA (1C)Fan Wheel Repl. | [5 empty] | 0
BB | 1 | BB1 PA (1A)Fan Wheel Repl. | 157000 |  |  |  |  | 157000
BB | 1 | BB1 PA Fan Wheel, Shaft and Housing replacement (3) |  | 0 | 0 | 0 | 0 | 0
BB | 1 | BB1 Penthouse Seals/Casing Repl | [5 empty] | 0
BB | 1 | BB1 Precip AVC and rapper control repl. |  |  | 0 |  |  | 0
BB | 1 | BB1 Precip W. Outlet Duct Repl |  | 0 | 0 |  |  | 0
BB | 1 | BB1 Precipitator (E&W) Controls Replacement (new) |  |  | 0 |  |  | 0
BB | 1 | BB1 Precipitator (East) Inlet Nozzle Duct Repl | [5 empty] | 0
BB | 1 | BB1 Precipitator (East) Inlet Nozzle Duct Repl (in process) | [5 empty] | 0
BB | 1 | BB1 Precipitator (East) Outlet Duct Repl (scr) |  | 958884 | 1241713 |  |  | 2200597
BB | 1 | BB1 Precipitator Common Outlet Exp Jts |  |  | 0 |  |  | 0
BB | 1 | BB1 Precipitator Hopper Feeder Replacement (32) | 0 | 350000 | 350000 |  |  | 700000
BB | 1 | BB1 Precipitator W. Inlet Nozzle Duct Repl (in process) | [5 empty] | 0
BB | 1 | BB1 Pulv Isolation Dampers (3) purchased in 2004 |  |  | 0 |  |  | 0
BB | 1 | BB1 Pulv liners replacement (3) |  | 0 |  | 0 | 0 | 0
BB | 1 | BB1 Pulv Lube Oil Sys | [5 empty] | 0
BB | 1 | BB1 Pulv Mn Pinion (3) |  |  | 0 |  | 0 | 0
BB | 1 | BB1 Pulv Ring Gear (3) |  | 0 | 0 |  | 0 | 0
BB | 1 | BB1 Pulverizer Gearbox Repl (3) |  |  | 0 |  | 0 | 0
BB | 1 | BB1 Slag Tank Doghouse Enclosure | [5 empty] | 0
BB | 1 | BB1 Slag Tank Neck Repl | [5 empty] | 0
BB | 1 | BB1 Slag Tank Roofs & Refractory | [5 empty] | 0
BB | 1 | BB1 Slag Tanks/Necks Rep. |  | 1000000 | 1500000 |  |  | 2500000
BB | 1 | BB1 Sootblower Repl. |  | 0 | 500000 | 250000 | 250000 | 1000000
BB | 1 | BB1 Sootblowing Piping System Repl |  | 500000 | 500000 | 0 | 0 | 1000000
BB | 1 | BB1 Throttle Valves Mod |  |  | 0 |  |  | 0
BB | 1 | BB1 Transformer Deluge System | [5 empty] | 0
BB | 1 | BB1 Turbine Improvement | [5 empty] | 0
BB | 1 | BB1 & 2 Turbine Building Roof Replacement | 800000 | 1000000 |  |  |  | 1800000
BB | 1 | BB1 Turbine Lube Oil Cooler Add | [5 empty] | 0
BB | 1 | BB1 Turbine Steam Path Restoration |  | 0 | 0 |  |  | 0
BB | 1 | BB1 Turbine-LP Seals Repl. | [5 empty] | 0
BB | 2 | BB2 APH seals replacement (for SCR) | 130291 | 219709 |  |  |  | 350000
BB | 2 | BB2 APH Sootblower Add | 40412 | 178341 |  |  |  | 218753
BB | 2 | BB2 BFP Internal Element Repl |  | 0 |  |  |  | 0
BB | 2 | BB2 Boiler 1st Radiant SH Repl. |  |  |  |  | 2500000 | 2500000
BB | 2 | BB2 Boiler 2nd Radiant SH Repl | 1954240 | 2538375 |  |  |  | 4492615
BB | 2 | BB2 Boiler Burner Front Repl. | [5 empty] | 0
BB | 2 | BB2 Boiler drain system replacement |  |  | 0 | 0 |  | 0
BB | 2 | BB2 Boiler Flash Tank Repl |  |  | 0 |  |  | 0
BB | 2 | BB2 Boiler Furnace Floor Repl. | 4500000 | 1231000 |  |  | 1000000 | 6731000
BB | 2 | BB2 Boiler Furnace Floor Refractory Repl. | 0 | 0 |  |  |  | 0
BB | 2 | BB2 Boiler HTSH outlet header Repl | 1378036 | 2403857 |  |  |  | 3781893
BB | 2 | BB2 Boiler IGNITOR REPL. |  | 0 |  |  |  | 0
BB | 2 | BB2 Boiler Penthouse Seals And Casing Repl. | [5 empty] | 0
BB | 2 | BB2 Circ Water Coarse Mesh Screens |  | 800000 |  |  |  | 800000
BB | 2 | BB2 Coal Chutes/Boxes-3 mills | 250000 | 550000 |  |  |  | 800000
BB | 2 | BB2 Coal Feeder Repl | 331464 | 0 |  |  |  | 331464
BB | 2 | BB2 Coal Nozzle replacement | 294000 |  |  |  |  | 294000
BB | 2 | BB2 Coal pipe system replacement | 1000000 | 2000000 |  |  | 0 | 3000000
BB | 2 | BB2 Condenser Ball Tube Cleaner (Non-Bud) | [5 empty] | 0
BB | 2 | BB2 Condenser Tube Bundle Repl. | 95000 |  |  |  |  | 95000
BB | 2 | BB2 Control Rm Relocation/ Controls | 2706251 | 1921614 |  |  |  | 4627865
BB | 2 | BB2 Crusher Dryers (6) | 250000 | 550000 |  |  |  | 800000
BB | 2 | BB2 Duct-hot gas expansion Jts below dampers repl | 0 | 0 |  |  |  | 0
BB | 2 | BB2 Duct Hardening (scr) | 308636 | 692124 |  |  |  | 1000760
BB | 2 | BB2 Economizer Ash Reinjection Line | 574975 | 322124 |  |  |  | 897099
BB | 2 | BB2 EH1 Repl. | 570720 | 787500 |  |  | 0 | 1358220
BB | 2 | BB2 EH2 Repl. | 522566 | 745575 |  |  | 0 | 1268141
BB | 2 | BB2 EH4 Repl. | 361483 | 547661 |  |  |  | 909144
BB | 2 | BB2 EH5 Repl. | 359902 | 547400 |  |  | 0 | 907302
BB | 2 | BB2 EH6 Repl | [5 empty] | 0
BB | 2 | BB2 Feedwater Heater Drip Lines Repl | 0 | 0 |  |  |  | 0
BB | 2 | BB2 Generator Rewind with retaining rings | 6494900 | 7792500 |  | 0 |  | 14287400
BB | 2 | BB2 H2 Dryer Repl |  | 0 |  |  |  | 0
BB | 2 | BB2 HP Turbine Steam Path Restoration | 0 | 0 |  |  | 1000000 | 1000000
BB | 2 | BB2 mid furnace weld overlay | 37554 | 1000000 |  | 0 |  | 1037554
BB | 2 | BB2 PA fan/housing replacement/upgrade (3) | 979000 | 485000 |  |  |  | 1464000
BB | 2 | BB2 Precip AVC and rapper control repl. |  | 0 |  |  |  | 0
BB | 2 | BB2 Precip E&W Inlet Ducts/Hoppers (scr) | [5 empty] | 0
BB | 2 | BB2 Precip E&W Outlet Duct Repl | 0 | 0 |  |  |  | 0
BB | 2 | BB2 Precipitator Controls Replacement (new) |  | 0 |  |  |  | 0
BB | 2 | BB2 PPTR (e&w) E&F-ducts,H Roof (scr) | 928636 | 1571364 |  |  |  | 2500000
BB | 2 | BB2 PPTR (e&w) Inlet elbows | 0 | 0 | 0 |  |  | 0
BB | 2 | BB2 PPTR (h) roofs (scr) | 0 | 0 |  |  |  | 0
BB | 2 | BB2 PPTR H Duct Expansion Jts (scr) | 51770 | 37220 |  |  |  | 88990
BB | 2 | BB2 Precipitator Hopper Feeder Replacement (32) | 350000 | 350000 |  |  |  | 700000
BB | 2 | BB2 Pulv Isolation Dampers (2 remaining) | 0 | 0 |  |  |  | 0
BB | 2 | BB2 Pulv liners replacement (3) |  |  |  |  | 0 | 0
BB | 2 | BB2 Pulv Mn Pinion (3) | 0 |  |  |  | 0 | 0
BB | 2 | BB2 Pulv Ring Gear (3) | 0 |  |  |  | 0 | 0
BB | 2 | BB2 Pulverizer Gearbox Repl (3) | 0 |  |  |  | 0 | 0
BB | 2 | BB2 Seal Air Fans |  | 0 |  |  |  | 0
BB | 2 | BB2 SIR Repl. |  |  |  |  | 0 | 0
BB | 2 | BB2 Slag Tank/Neck Repl | 1000000 | 1500000 |  |  | 0 | 2500000
BB | 2 | BB2 Sootblower Repl. | 40400 | 250000 | 250000 | 250000 | 250000 | 1040400
BB | 2 | BB2 Sootblowing Ctrls to Ovation | [5 empty] | 0
BB | 2 | BB2 Sootblowing Piping System Repl | 250000 | 750000 |  |  |  | 1000000
BB | 2 | BB2 Tank Refractory | 0 | 0 |  |  |  | 0
BB | 2 | BB2 Throttle Valve Mods |  | 0 |  |  |  | 0
BB | 2 | BB2 Turbine Roof Replacement |  | 0 |  |  |  | 0
BB | 2 | BB2 Turbine Seals Repl | 0 | 0 |  |  |  | 0
BB | 2 | BB2 Upper Precip Inlet Nozzles Repl (scr) | 650000 | 1250000 |  |  |  | 1900000
BB | 3 | BB3 A&B Air Removal Pumps | 369619 |  |  |  |  | 369619
BB | 3 | BB3 AK25 breakers (30) | 0 |  | 0 |  |  | 0
BB | 3 | BB3 Alterrex Improvements | 0 |  |  |  |  | 0
BB | 3 | BB3 APH seals replacement (for SCR) | 218178 |  |  |  |  | 218178
BB | 3 | BB3 APH Coldside Sootblower addition | 136938 |  |  |  |  | 136938
BB | 3 | BB3 Backup Power Feeds for all Ovation Drops | [5 empty] | 0
BB | 3 | BB3 Battery Repl | 0 |  |  |  |  | 0
BB | 3 | BB3 Blowdown Tank Repl | 0 |  |  | 0 | 0 | 0
BB | 3 | BB3 Boiler Burner Front Repl. | 3387194 |  |  |  |  | 3387194
BB | 3 | BB3 Boiler drain system replacement |  |  |  | 0 | 0 | 0
BB | 3 | BB3 Boiler Buckstay Repl | 104610 |  |  |  |  | 104610
BB | 3 | BB3 Boiler Economizer Tubes | 0 | 0 |  | 2500000 | 2500000 | 5000000
BB | 3 | BB3 Boiler Flame Scanner Repl | 279000 |  |  |  |  | 279000
BB | 3 | BB3 Boiler Furnace Floor Refractory | 0 |  |  |  | 600000 | 600000
BB | 3 | BB3 Boiler Furnace Floor Repl. | 1715568 |  |  |  |  | 1715568
BB | 3 | BB3 Boiler Furnace Water Wall Weld Overlay | [5 empty] | 0
BB | 3 | BB3 Boiler Nose Arch & Rear Wall Repl | 1867194 |  |  |  |  | 1867194
BB | 3 | BB3 Boiler Nose Arch Refractory Repl. | [5 empty] | 0
BB | 3 | BB3 Boiler Sidewall Repl | 1996297 |  |  |  |  | 1996297
BB | 3 | BB3 Boiler Steam Drum Internals Repl | 202702 |  |  |  |  | 202702
BB | 3 | BB3 Boiler Steam Drum Riser Tube Replacement | 317740 |  |  |  |  | 317740
BB | 3 | BB3 Circulators Shaft/Brngs Repl | 248956 |  |  |  |  | 248956
BB | 3 | BB3A Circulator Shaft/bearing Repl | 137300 |  |  |  |  | 137300
BB | 3 | BB3 Classifiers | [5 empty] | 0
BB | 3 | BB3 Coal Blast Gates | 0 |  |  |  |  | 0
BB | 3 | BB3 Coal Feeder Repl | 346667 |  |  |  |  | 346667
BB | 3 | BB3 Coal crushers | 0 |  |  | 600000 | 600000 | 1200000
BB | 3 | BB3 Coal pipe system replacement |  |  |  | 0 | 0 | 0
BB | 3 | BB3 'B' Coarse Mesh Screen Repl. | 320224 |  |  |  |  | 320224
BB | 3 | BB3 'A' Coarse Mesh Screen Repl. | 311440 |  |  |  |  | 311440
BB | 3 | BB3 Circ fine mesh screens |  |  |  |  | 1000000 | 1000000
BB | 3 | BB3 Cold Gas Duct Repl. | [5 empty] | 0
BB | 3 | BB3 Cold Outlet Duct Repl | 0 |  |  |  |  | 0
BB | 3 | BB3 Computer Controls Project | 2157197 |  |  |  |  | 2157197
BB | 3 | BB3 Condenser Ball Cleaning Repl. | 427286 |  |  |  |  | 427286
BB | 3 | BB3 Condenser Discharge Valve Repl. | 99441 |  |  |  |  | 99441
BB | 3 | BB3 Condenser Repl. | 1111254 |  |  |  |  | 1111254
BB | 3 | BB3 Controls/WDPF To Ovation Repl. | [5 empty] | 0
BB | 3 | BB3 Cooling Tower Fill Repl | 124208 |  |  |  |  | 124208
BB | 3 | BB3 Cooling Water Piping Repl. | [5 empty] | 0
BB | 3 | BB3 Control Transmitter Repl | 153600 |  |  |  |  | 153600
BB | 3 | BB3 DA repl. |  |  |  | 1000000 | 2000000 | 3000000
BB | 3 | BB3 Duct E-Roofs (2) (scrs) | 220882 |  |  |  |  | 220882
BB | 3 | BB3 Duct Expansion Jts |  | 0 |  |  |  | 0
BB | 3 | BB3 Duct Hardening (scr) | 604046 |  |  |  |  | 604046
BB | 3 | BB3 Duct Misc. Expansion Joints | 0 |  |  |  |  | 0
BB | 3 | BB3 Duct Tail End Dampers | 210698 |  |  |  |  | 210698
BB | 3 | BB3 Plenum Section Betwn Damper/Econo | 542584 |  |  |  |  | 542584
BB | 3 | BB3 Economizer Ash Reinjection | 349789 |  |  |  |  | 349789
BB | 3 | BB3 Economizer Outlet Elbow Replacement (scrs) | 691978 |  |  |  |  | 691978
BB | 3 | BB3 EH1 Repl |  |  |  | 1000000 | 1200000 | 2200000
BB | 3 | BB3 EH2 Repl | 304917 |  |  |  |  | 304917
BB | 3 | BB3 EH3 Repl |  |  |  | 1000000 | 1200000 | 2200000
BB | 3 | BB3 Exciter Refurbishment | [5 empty] | 0
BB | 3 | BB3 FW Heater Level Control Repl | [5 empty] | 0
BB | 3 | BB3 Generator rewind and retaining rings |  |  |  |  | 0 | 0
BB | 3 | BB3 H2 Dryer Addn | 0 |  |  |  |  | 0
BB | 3 | BB3 Hot Air Gates Install | [5 empty] | 0
BB | 3 | BB3 HP Turbine Seals Replacement | 0 |  |  |  |  | 0
BB | 3 | BB3 HP Turbine Snout Ring Upgrade | 0 |  |  |  |  | 0
BB | 3 | BB3 HP Turbine Steam Path Restoration | 1982052 |  |  |  |  | 1982052
BB | 3 | BB3 LP Turbine Steam Path Restoration | 3440889 |  |  |  |  | 3440889
BB | 3 | BB3 Penthouse Seals And Casing | 0 |  |  |  |  | 0
BB | 3 | BB3 Precip AVC and Rapper Control repl. | [5 empty] | 0
BB | 3 | BB3 Precipitator Controls Replacement (new) | 0 |  |  |  |  | 0
BB | 3 | BB3 Precipitator Hopper Repl (3) (scrs) | 1086968 |  |  |  |  | 1086968
BB | 3 | BB3C Primary Air Fan Wheel Assm Repl | 157000 |  |  |  |  | 157000
BB | 3 | BB3 Pulv 3B1 Trunnion Bearing Repl. | [5 empty] | 0
BB | 3 | BB3 Pulv. Inlet chute replacement (3 mills) |  |  | 0 | 400000 | 600000 | 1000000
BB | 3 | BB3 Pulv. Mill Isolation Dampers | 0 |  |  |  |  | 0
BB | 3 | BB3 Pulv. Shell/Head & Throat Liners | 697793 |  |  |  |  | 697793
BB | 3 | BB3 Replace 480 Volt Emerg. Generator | [5 empty] | 0
BB | 3 | BB3 Salt Water Piping Syst Repl | [5 empty] | 0
BB | 3 | BB3 Service & Recycle Water Piping Repl. | [5 empty] | 0
BB | 3 | BB3 Slag Tank Necks,Gates and grinders | 0 | 0 | 0 | 1000000 | 2000000 | 3000000
BB | 3 | BB3 Slag Tank Repl. | 0 | 0 | 0 | 0 | 0 | 0
BB | 3 | BB3 Slag Tank Enclosure Repl | 576579 |  |  | 0 | 0 | 576579
BB | 3 | BB3 Sootbllower piping replacement (upgrade) | 0 |  | 0 | 500000 | 600000 | 1100000
BB | 3 | BB3 Sootblower Control Valve Repl | [5 empty] | 0
BB | 3 | BB3 Sootblower Repl |  | 0 | 0 | 250000 | 500000 | 750000
BB | 3 | BB3 Stack Liner #2 |  |  |  | 1000000 | 2000000 | 3000000
BB | 3 | BB3 Snubber Repl | 0 |  |  | 250000 | 250000 | 500000
BB | 3 | BB3 Transformer Deluge System | [5 empty] | 0
BB | 3 | BB3 HP Rotor R7 Blades/ Shroud Repl | 0 |  |  |  |  | 0
BB | 3 | BB3 FDF Motor | [5 empty] | 0
BB | 3 | BB3 Upper Precip West Outlet Nozzle | 259559 |  |  |  |  | 259559
BB | 4 | BB3&4 CEM repl. |  | 0 | 250000 | 250000 | 0 | 500000
BB | 4 | BB3&4 Polisher Controls Upgrade | [5 empty] | 0
BB | 4 | BB4 #3 Fly Ash Silo A&B Sec.Collector (B20.07/W54.22) | [5 empty] | 0
BB | 4 | BB4 #3 Fly Ash Silo Stone Replace. (B20.05/W24.22) | [5 empty] | 0
BB | 4 | BB4 125V DC Battery Repl. Set #7 | [5 empty] | 0
BB | 4 | BB4 Air Removal Pumps | 0 |  |  |  |  | 0
BB | 4 | BB4 APH Seal Repl | [5 empty] | 0
BB | 4 | BB4 APH Sootblower Addition | [5 empty] | 0
BB | 4 | BB4 B CWP / Shaft Bearing Repl |  |  |  | 0 |  | 0
BB | 4 | BB4 Batteries,Gould 1800 A/H Battery #2 | [5 empty] | 0
BB | 4 | BB4 Boiler Acid Cleaning |  | 0 |  |  |  | 0
BB | 4 | BB4 Boiler Feed Pp Internal Element Repl. | [5 empty] | 0
BB | 4 | BB4 Boiler Finishing Superheater Repl. | [5 empty] | 0
BB | 4 | BB4 Boiler Front Reheater Replace | [5 empty] | 0
BB | 4 | BB4 Boiler Furnace Floor Slopes | [5 empty] | 0
BB | 4 | BB4 Boiler Ignitor Repl | [5 empty] | 0
BB | 4 | BB4 Boiler Platen SH partial replacement | 0 | 0 | 2000000 | 3500000 |  | 5500000
BB | 4 | BB4 Boiler SH Division Panels Lower Loop Repl. | [5 empty] | 0
BB | 4 | BB4 Boiler SH Outlet Leads (Seamed Pipe) | [5 empty] | 0
BB | 4 | BB4 Boiler HR Repl (mezz level) |  |  | 1500000 | 1500000 |  | 3000000
BB | 4 | BB4 Boiler Upper Furnace Overlay |  | 0 |  | 1000000 |  | 1000000
BB | 4 | BB4 Boiler External Roof Repl |  | 0 |  | 600000 |  | 600000
BB | 4 | BB4 Boiler Waterwall Weld Overlay | [5 empty] | 0
BB | 4 | BB4 Bottom Ash Grinders | [5 empty] | 0
BB | 4 | BB4 Bottom Ash Neck Repl. | [5 empty] | 0
BB | 4 | BB4 Bottom Ash Pump Repl A-'06 /B-'07 | 0 |  |  |  |  | 0
BB | 4 | BB4 HP Bottom Ash Sluice PP Rep (per PSA)l | 0 |  |  |  |  | 0
BB | 4 | BB4 Burner/Air Nozzles & Oil Guns |  |  | 400000 | 600000 | 0 | 1000000
BB | 4 | BB4 Cold Gas Duct Roof Repl. | [5 empty] | 0
BB | 4 | BB4 Control HTPK cards for ID/FD | 0 |  |  |  |  | 0
BB | 4 | BB4 Cooling Water Piping | [5 empty] | 0
BB | 4 | BB4 Condenser Ball Cleaning System |  |  | 5000000 | 8000000 | 0 | 13000000
BB | 4 | BB4 Circ fine Mesh Screens |  |  |  |  | 1000000 | 1000000
BB | 4 | BB4 DA Replacement |  |  |  | 1000000 | 2000000 | 3000000
BB | 4 | BB4 Economizer Ash System Piping Replacement | [5 empty] | 0
BB | 4 | BB4 Economizer Tube Bundle Modification For SCT | [5 empty] | 0
BB | 4 | BB4 EH1 Feedwater Htr Repl |  |  | 1000000 | 1200000 |  | 2200000
BB | 4 | BB4 EH2 Feedwater Htr Repl | 0 | 0 | 1000000 | 1200000 |  | 2200000
BB | 4 | BB4 EH3 Feedwater Htr Repl | [5 empty] | 0
BB | 4 | BB4 FD/ID Fan Inlet Vane Drives | [5 empty] | 0
BB | 4 | BB4 FD/ID Fans VSD Upgrade | [5 empty] | 0
BB | 4 | BB4 FW Heater Level Ctrls | [5 empty] | 0
BB | 4 | BB4 H2 Dryer Repl. | [5 empty] | 0
BB | 4 | BB4 Hot Air Gates Repl | [5 empty] | 0
BB | 4 | BB4 B HP Slag Sluice Pp Repl | [5 empty] | 0
BB | 4 | BB4 HP Rotor R7 Blades and Shroud Replacement | [5 empty] | 0
BB | 4 | BB4 L-0 Turbine Blades | [5 empty] | 0
BB | 4 | BB4 Main & BFP Turbines TSI Repl. | [5 empty] | 0
BB | 4 | BB4 MCC4B6 | [5 empty] | 0
BB | 4 | BB4 Outlet Water Box Manway Add | [5 empty] | 0
BB | 4 | BB4 Precip AVC and rapper control repl. | [5 empty] | 0
BB | 4 | BB4 Process Computer Repl | 17169 |  |  |  |  | 17169
BB | 4 | BB4 Pulv. 4C Grinding Assembly Repl. | [5 empty] | 0
BB | 4 | BB4 Pulv. 4E Journal Grinding Assm. Repl. | [5 empty] | 0
BB | 4 | BB4 Pulv. Mill Fire Protection Addition | [5 empty] | 0
BB | 4 | BB4 Pulverizer Rebuild(3) | 300000 | 450000 | 300000 | 450000 | 300000 | 1800000
BB | 4 | BB4B GRINDING ASSM REPL | [5 empty] | 0
BB | 4 | BB4 Pulverizer Spring Modification | 100000 | 200000 | 100000 | 0 |  | 400000
BB | 4 | BB4 Snubber Repl | [5 empty] | 0
BB | 4 | BB4 Sootblower Control Sys Repl | [5 empty] | 0
BB | 4 | BB4 Sootblower repl |  | 0 | 0 |  | 500000 | 500000
BB | 4 | BB4 Spacer Cooled Tubing Repl. | [5 empty] | 0
BB | 4 | BB4 Stack Liner #3 |  |  | 1000000 | 2000000 |  | 3000000
BB | 4 | BB4 Start up BFP Suction Pipe Upgrade | [5 empty] | 0
BB | 4 | BB4 Turbine Seals |  |  |  | 0 |  | 0
BB | 4 | BB4 Turbine Steam Path Restoration |  |  | 1000000 | 1500000 |  | 2500000
BB | 4 | BB4 Upper Precip Outlet Nozzles | [5 empty] | 0
BB | 4 | BB4 Upper Precip Roof Repl | [5 empty] | 0
BB | COM | BB1&2 CEM repl. |  | 250000 | 250000 | 0 |  | 500000
BB | COM | BB Secondary 480 Fd For Coal Yard Critical Power | [5 empty] | 0
BB | COM | BB1&2 neural F gas repl. |  |  | 250000 |  | 0 | 250000
BB | COM | BB1/2 Stack demo | [5 empty] | 0
BB | COM | BB1-3 Mill Inerting | [5 empty] | 0
BB | Com | BB4 Vib. Monitor Equip. & Ctrls | 2387 |  |  |  |  | 2387
BB | Com | BB4 Boiler Waterwall Weld Overlay Addition | [5 empty] | 0
BB | Com | BBC Admin Bld 3&4 Floor Add | [5 empty] | 0
BB | Com | BBC Air Compressor Closed Loop Cooling Sys | 0 | 0 |  |  |  | 0
BB | Com | BBC Balance to Study Deffered Debit | [5 empty] | 0
BB | COM | BBC Centralized Air Compressor Station |  |  |  |  | 1500000 | 1500000
BB | Com | BBC Coal Blending Bin Fire | [5 empty] | 0
BB | Com | BBC Coal Dock Rail Replacement | 400000 |  |  |  |  | 400000
BB | Com | BBC Coal Field Conv/chutes | 0 | 0 | 0 | 0 |  | 0
BB | Com | BBC PECO Clamshell Bucket Repl | 100000 |  |  |  |  | 100000
BB | Com | BBC Coal field Heavy Equipment | 0 | 1000000 | 0 |  | 1200000 | 2200000
BB | Com | BBC Coal Field Polk Blending Conv. | 112038 |  |  |  |  | 112038
BB | Com | BBC D6 Cat Dozier | [5 empty] | 0
BB | Com | BBC F Conveyor Belt Repl. | [5 empty] | 0
BB | Com | BBC F Conveyor Refurbishment Install | [5 empty] | 0
BB | Com | BBC Fuel Oil Tank Repl |  | 0 |  |  |  | 0
BB | Com | BBC Intercool., Aftercool., & Air Comp. Rebuild | 0 | 0 |  |  |  | 0
BB | Com | BBC New Caterpillar D10 Track Type Tractor | [5 empty] | 0
BB | Com | BBC No. 2 Air Compressor Controls Repl. | [5 empty] | 0
BB | COM | BBC S/R Bucket Wheel Gearbox Refurb | [5 empty] | 0
BB | Com | BBC North Stacker Repl |  | 250000 | 4000000 | 6000000 | 0 | 10250000
BB | Com | BBC P Conveyor Refurbishment Install | [5 empty] | 0
BB | Com | BBC Recycle Piping | 398389 |  | 0 | 0 |  | 398389
BB | Com | BBC Q-2 Conveyor Belt Repl. | [5 empty] | 0
BB | Com | BBC Raygo Repl. | [5 empty] | 0
BB | Com | BBC Slag Sluice Pump #3 Replacement | [5 empty] | 0
BB | COM | BBC #4 Elevator Repl | 156397 |  |  |  |  | 156397
BB | COM | BBC #5 Air compressor | 11000 |  |  |  |  | 11000
BB | COM | BBC Waste Handling Elevator Cab Repl | 162720 |  |  |  |  | 162720
BB | Com | BBC South Stacker MCC Repl | [5 empty] | 0
BB | Com | BBC South Stacker Repl | [5 empty] | 0
BB | Com | BBC South Stacker Slew Bearing Repl | [5 empty] | 0
BB | Com | BBC Stack Lighting- #2 & #3 Stack Repl. | [5 empty] | 0
BB | Com | BBC Upgrade CO2 Fire System Storage Tanks | [5 empty] | 0
BB | Com | BBC VEHICLES | [5 empty] | 0
BB | Com | FGD tank liners | 0 | 0 | 0 | 500000 | 500000 | 1000000
BB | COM | BB PRECIP/EXPANSION JT BLANKETS |  |  |  | 500000 | 500000 | 1000000
BB | COM | BB MOTOR/ELECTRICAL COMP BLANKETS | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 10000000
BB | COM | BB TURB/AUX BLANKETS |  |  | 500000 | 500000 | 500000 | 1500000
BB | COM | BB CONV/SSTRUCTURES BLANKETS | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 5000000
BB | COM | BB PIPING/PUMPS/VVS/GEARBOXES BLANKETS | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 5000000
BB | COM | BB BOILER / AUX BLANKETS |  |  | 500000 | 500000 | 500000 | 1500000
BB | Com | BB INDETERMINATES |  |  | 500000 | 500000 | 1000000 | 2000000
BB | FGD | FGD A&B Tower Outlet Duct Repl | [5 empty] | 0
BB | COM | BBC J-1- Q-1 TRANSFER CHUTE REPL | [5 empty] | 0
BB | FGD | FGD C tower absorber nozzles | [5 empty] | 0
BB | FGD | FGD C&D Tower Outlet Duct |  |  |  | 1500000 | 2000000 | 3500000
BB | FGD | FGD Com Inlet Exp Jt/Damper |  | 0 |  |  |  | 0
BB | FGD | FGD Common Inlet/Outlet Duct Repl | 0 |  |  |  | 0 | 0
BB | FGD | FGD Conveyor Structure Repl. | 0 | 0 | 0 | 0 |  | 0
BB | FGD | FGD Exp Jt Inlet Flue Joining Ducts 5A/6A | [5 empty] | 0
BB | FGD | FGD GE Gypsum Belt Repl | [5 empty] | 0
BB | FGD | FGD GD2/GE Conveyor Structure Repl. | 287147 |  |  |  |  | 287147
BB | FGD | FGD Limestone Mill Liner Repl | 0 | 200000 | 200000 | 200000 | 200000 | 800000
BB | FGD | FGD Oxid. Air Comp. Vibr. Equip. Upgr | [5 empty] | 0
BY | 1 | BS Condenser Cleaning System Unit 1 | [5 empty] | 0
BY | 1 | BS Stack Dampers Unit 1 | [5 empty] | 0
BY | 1 | BS MISC PUMP REPL |  | 200000 |  |  |  | 200000
BY | 1 | BS MISC MOTOR Replacement |  | 20000 |  |  |  | 20000
BY | 1 | BS ELECTRICAL UPGRADES |  | 262000 |  |  |  | 262000
BY | 1 | BS2 HP/IP/LP STEAM TURBINE SEALS | 830000 |  |  |  |  | 830000
BY | 1 | BS CHLORIDE DIOXIDE GENERATOR | [5 empty] | 0
BY | 1 | BS Reserve Bus 2 Switchgear |  | 830000 |  |  |  | 830000
BY | 1 | BS Reserve Bus 3 MCC'S |  | 245000 |  |  |  | 245000
BY | 1 | BS Service Distribution System | [5 empty] | 0
BY | 1 | BS Essential Service Generator | [5 empty] | 0
BY | 1 | BS HRSG SCR CATALYST UNIT1 | [5 empty] | 0
BY | 1 | BS HRSG SCR CATALYST UNIT 2 |  | 1500000 | 2000000 | 0 |  | 3500000
BY | 1 | BS 1A CT OVERHAUL | [5 empty] | 0
BY | 1 | BS1 Circ Wtr PP Discharge vvs | [5 empty] | 0
BY | 1 | BSP CT Purging Bulk CO2 Storage | [5 empty] | 0
BY | 1 | BSP STG Aux Cooling Wtr Chemical Feed Sys | [5 empty] | 0
BY | 1 | Hp&IP Cont. Blowdown Automation | [5 empty] | 0
BY | 2 | BS Condenser Cleaning System Unit 2 | [5 empty] | 0
BY | 2 | BS2 Circ Wtr PP Discharge vvs | [5 empty] | 0
BY | COM | BS DISCHARGE FLUME | 0 | 5500000 | 5000000 |  |  | 10500000
BY | COM | BS 4160V Circuits | [5 empty] | 0
BY | COM | BS Blankets | 1810000 | 1035000 | 2250000 | 2500000 | 2500000 | 10095000
BY | COM | STEAM PLANT BATTERY REPL | [5 empty] | 0
BY | COM | BS Unit 1 CSA | 9777682 | 9882399 | 21575088 | 19678405 | 23044356 | 83957930
BY | COM | BS Unit 2 CSA | 12052888 | 13891261 |  |  |  | 25944149
BY | 1 | BS Inlet Air Filters for Unit 2 | 0 |  |  | 0 |  | 0
EC | ECRC | BB1 PPTR-West electrode/plate repl |  |  | 0 | 0 |  | 0
EC | ECRC | BB3 PPTR-East electrode/plate repl |  |  | 0 | 5000000 | 5000000 | 10000000
EC | ECRC | ECRC BB2 Windbox | [5 empty] | 0
EC | ECRC | ECRC future years | [5 empty] | 0
EC | ECRC | ECRC BB3 COAL/AIR FLOW MON | [5 empty] | 0
EC | ECRC | ECRC BB3 Windbox | 0 |  |  |  |  | 0
EC | ECRC | ECCR BB1 WINDBOX | [5 empty] | 0
EC | ECRC | ECRC BB3 FGD PACKING REPL | [5 empty] | 0
EC | ECRC | ECRC BB3 Secondary Air Controls | 676909 |  |  |  |  | 676909
EC | ECRC | ECRC BB1 Neural Network Combustion Optimization | 0 | 254340 |  |  |  | 254340
EC | ECRC | ECRC BB2 Neural Network Combustion Optimization | 0 | 329158 |  |  |  | 329158
EC | ECRC | ECRC BB3 Neural Network Combustion Optimization | 300000 |  |  |  |  | 300000
EC | ECRC | ECRC BB4 Neural Network Combustion Optimization | 0 |  |  |  |  | 0
EC | ECRC | BB SCR CATALYST |  |  |  | 1050000 | 1050000 | 2100000
EN | ECRC | PK MERCURY TESTING | [5 empty] | 0
EN | ECRC | BB1 MERC TESTING | 2276524 |  |  |  |  | 2276524
EN | ECRC | BB2 MERC TESTING | [5 empty] | 0
EN | ECRC | BB3 MERC TESTING | [5 empty] | 0
EN | ECRC | BB4 MERC TESTING | [5 empty] | 0
EN | ECRC | ECRC MERCURY TESTING PROJECT | 0 | 0 | 0 |  |  | 0
EN | ECRC | ECRC PM/CEMs | 500004 | 0 |  |  |  | 500004
EN | EN | Big Bend Coal Yard Liner | [5 empty] | 0
EN | EN | Big Bend 4 Economizer Ash Pond (Line or Close) | 2003685 | 1996316 |  |  |  | 4000001
EN | EN | Big Bend Dissolved Oxygen | 0 | 0 |  |  |  | 0
OT | OPS | BIG BEND BUFFER LAND ELSBERRY ROAD | [5 empty] | 0
EN | EN | ENV BB 316B STUDY |  |  | 0 | 0 | 0 | 0
EN | EN | ENV GN 316B STUDY |  | 0 | 0 | 1000000 | 2500000 | 3500000
EN | EN | Big Bend Gypsum Conveyor Relocation/Storage | 0 | 0 |  | 1000000 | 3500000 | 4500000
EN | EN | Big Bend Recycling Pond | 8696040 | 3132342 |  |  |  | 11828382
EN | EN | Big Bend Slag Dewatering Bins | 837791 |  |  |  |  | 837791
EN | EN | Big Bend Storm Water System Upgrade | 497403 |  |  |  |  | 497403
EN | ECRC | Environmental AST CONTAINMENT AREAS | 399999 | 399998 |  |  |  | 799997
EN | EV | EHS BLANKETS | 273467 | 160500 | 100000 | 150000 | 150000 | 833967
GN | GN | Dismantlement of coal fired assests | 3900000 | 4400000 | 2400000 | 2500000 | 2600000 | 15800000
OT | COM | BB POLK COAL BLENDING PROJECT | [5 empty] | 0
OT | OPS | WAREHOUSE | 891523 |  |  |  |  | 891523
OT | OPS | ES OPS ADMIN (HERNANDEZ) | 75134 | 200000 | 200000 | 200000 | 200000 | 875134
OT | FS | Energy Trading Business Process/Module (2) | 350000 | 250000 |  |  |  | 600000
OT | OPS | RO Enhancements | 202576 | 125000 | 100000 | 100000 | 100000 | 627576
OT | OPS | ProMOD Upgrade | 350000 | 400000 |  |  | 50000 | 800000
OT | OPS | Resource Planning Data Warehouse | 400000 | 125000 | 100000 | 100000 | 100000 | 825000
OT | E&C | OSI RT WEB PARTS | 100000 |  |  |  |  | 100000
OT | OPS | Warehouse - Flat Bed Truck | [5 empty] | 0
OT | OPS | Warehouse - Pickup Truck | [5 empty] | 0
OT | OPS | ES OPS PLANNING (CURRIER) | 0 | 0 | 0 | 0 | 0 | 0
OT | STI | FLYASH BENEFICIATION | 69457 | 0 | 0 |  |  | 69457
PK | PK | Polk HRSG Floor and Drains | [5 empty] | 0
PK | PK | Polk Blankets/Retirements | 2187000 | 2927799 | 5300000 | 5525000 | 5750000 | 21689799
PK | PK | Polk CDC | [5 empty] | 0
PK | PK | Polk COARSE SLAG SCREEN REPL | 0 |  |  |  |  | 0
PK | PK | Polk E&W CSC Inlet Access Door Repl | [5 empty] | 0
PK | PK | Polk Forced Circ Evap | 50000 |  |  |  |  | 50000
PK | PK | Polk slag screen and #1 settler tank | [5 empty] | 0
PK | PK | Polk Process Burner Repl | 0 |  |  |  |  | 0
PK | PK | Polk Residual Beneficiation Project | 800000 |  |  |  |  | 800000
PK | PK | Polk syngas Stop VV | 112000 |  |  |  |  | 112000
PK | PK | Polk Selinium Project | 300000 |  |  |  |  | 300000
PK | PK | Polk Elevator Repl | 450000 |  |  |  |  | 450000
PK | PK | Polk CSC Quench system | 125000 |  |  |  |  | 125000
PK | PK | Polk Fire Protection System | 250000 |  |  |  |  | 250000
PK | PK | Polk Residual Equipment | [5 empty] | 0
PK | PK | Polk Slag Crusher |  | 126000 |  |  |  | 126000
PK | PK | Polk Mill Liners Repl |  | 400000 |  |  |  | 400000
PK | PK | Polk HRSG Project |  | 375000 |  |  |  | 375000
PK | PK | Polk Outfall Dilution Project |  | 300000 |  |  |  | 300000
PK | PK | Polk Steam turbine Blade Replacements |  | 250000 |  |  |  | 250000
PK | PK | Polk Tools | 98000 | 98000 |  |  |  | 196000
PK | PK | Polk Test Equip | 40000 | 40000 |  |  |  | 80000
PK | PK | POLK 50 TON CRANE | [5 empty] | 0
PK | PK | Polk Gasifier Brick |  | 2300000 |  |  | 1750000 | 4050000
PK | PK | Polk LTSA's | 0 | 0 | 6286000 | 6230000 | 6148000 | 18664000
PK | PK | Polk Expansion LTSA's | [5 empty] | 0
PK | PK | POLK RSC TUBING REPLACEMENT | [5 empty] | 0
PK | PK | Polk Projects | 0 |  |  |  |  | 0
PK | PK | Polk Heavy Equipment | 150000 |  |  |  |  | 150000
PK | PK | Polk Rotor Replacement | [5 empty] | 0
PK | PK | Polk Evaporator Condensate Treatment | [5 empty] | 0
PK | PK | Polk CSC Tube Addition | [5 empty] | 0
PK | PK | POLK CSC TUBE INTERNALS REPL | [5 empty] | 0
PK | PK | Polk CSS Tube Internals Replacement | 750000 | 1250000 |  |  |  | 2000000
PK | PK | Polk SAP Heat Exchanger | 0 |  |  |  |  | 0
PK | PK | Polk scrubber blowdown containment | [5 empty] | 0
PK | PK | Polk Slag Tank | 0 |  |  |  |  | 0
PK | PK | Polk Scrubber underflow to RSC Sump | 250000 |  |  |  |  | 250000
PK | PK | Polk Unit 1 / Gasifer Major Outage Replacements | [5 empty] | 0
PK | PK | Polk Unit 1 LTSA | 4561860 | 4683312 |  |  |  | 9245172
PK | PK | Polk Unit 2 CSA | 925507 | 932745 |  |  |  | 1858252
PK | PK | Polk Unit 3 CSA | 964086 | 962728 |  |  |  | 1926814
PK | PK | Polk Unit 4 CSA | 971000 | 988670 | 2498000 | 2704000 | 2435000 | 9596670
PK | PK | Polk Unit 5 CSA | 971000 | 988670 |  |  |  | 1959670
PK | PK | PolkGasifier Cont Thermo | [5 empty] | 0
PK | PK | POLK ASU PERLITE | [5 empty] | 0
PK | PK | POLK FIXED GAS MONITOR | [5 empty] | 0
PK | PK | POLK CHILLER | [5 empty] | 0
PK | PK | POLK PROCESS FD EJECTOR | 125000 |  |  |  |  | 125000
PK | PK | POLK DRAG CHAIN INTERNALS |  | 300000 |  |  |  | 300000
PK | PK | POLK DRYING TOWER PIPING REPL | [5 empty] | 0
PK | PK | POLK LCI CROSSOVER | [5 empty] | 0
PK | PK | POLK 50 TON CRANE | [5 empty] | 0
PK | PK | POLK HRSG ROOF REPL | [5 empty] | 0
REL | ECRC | BB1-2 Electric Isolation | 50012 | 250000 | 250000 |  |  | 550012
REL | ECRC | BB1-2 FGD Absorber spray pp disch vvs | 0 | 0 |  |  |  | 0
REL | ECRC | BB1-2 Gyspum Filter Vacuum Pump Upgrades | 0 | 0 |  |  |  | 0
REL | ECRC | BB1-2 ME Wash Hdr Upgrades | 833000 | 0 |  |  |  | 833000
REL | ECRC | BB1-2 mist eliminator online cleaning |  | 0 |  |  |  | 0
REL | ECRC | BB1-2 Mist Eliminator Upgrades | 100000 | 1524500 |  |  |  | 1624500
REL | ECRC | BB1-2 Redundant Gypsum Bleed Line | 50000 | 234000 |  |  |  | 284000
REL | ECRC | BB3-4 Tower Nozzle Online Cleaning | 5000 | 0 | 469191 |  |  | 474191
REL | ECRC | BB1-2 Wallpaper Inlet |  | 0 |  |  |  | 0
REL | ECRC | BB1-2Controls Redundancy Upgrades | 18000 | 100000 | 85000 |  |  | 203000
REL | ECRC | BB3-4 BoosterFan Upgrades | 1258935 | 0 |  |  |  | 1258935
REL | ECRC | BB3-4 Electric Isolation | 1189292 | 0 |  |  |  | 1189292
REL | ECRC | BB3-4 mist eliminator online cleaning |  | 0 |  |  |  | 0
REL | ECRC | BB3-4 Mist Eliminator Upgrades | [5 empty] | 0
REL | ECRC | BB3-4 Split Inlet Duct | 330959 |  |  |  |  | 330959
REL | ECRC | BB3-4 Split Outlet Duct |  | 0 |  |  |  | 0
REL | ECRC | BB1-2 Tower Nozzle Online Cleaning | 0 | 0 | 280500 |  |  | 280500
REL | ECRC | BB FGD WASTEWATER TANK RETROFIT | 740390 |  |  |  |  | 740390
REL | ECRC | BB3-4Controls Redundancy Upgrades | 71790 | 0 |  |  |  | 71790
REL | ECRC | Gypsum Fines Filter | 0 | 0 | 3200000 |  |  | 3200000
REL | ECRC | RELIABILITY PROGRAM CONTINGENCY | 0 | 0 | 0 |  |  | 0
SB | SB | DINNER LAKE | [5 empty] | 0
SB | SB | Diesel Engine Component Replacements | 300000 | 300000 | 300000 | 300000 | 300000 | 1500000
|  | Total Non-Generation Expansion Capital | 127551148 | 126595963 | 107483162 | 95037405 | 92927356 | 549595034
SCR | SCR | Big Bend SCR Projects | 72385390 | 52595101 | 13075470 |  |  | 138055961
GL | GS | Gas Line Addition | -5534250 |  |  |  |  | -5534250
RXP | EXP | POLK 4&5 | 0 | 0 |  |  |  | 0
GE | EXP | NGCC | 11400000 | 114953000 | 173846000 | 137913000 | 55920000 | 494032000
GE | GE | Big Bend Aero-Derivative Expansion | 15727300 | 33416000 | 0 | 0 | 0 | 49143300
GE | GE | Bayside Aero-Derivative Expansion | 100247800 | 83782600 | 0 | 0 | 0 | 184030400
GE | GE | Future Aero-Derivative Expansion (units 6-11) |  | 2412000 | 127224000 | 159612000 | 32712000 | 321960000
|  | Total Generation Expansion Capital | 194226240 | 287158701 | 314145470 | 297525000 | 88632000 | 1181687411
|  | TOTAL CAPITAL | 321777388 | 413754664 | 421628632 | 392562405 | 181559356 | 1731282445