## CAPEX_by_Bus_Unit___BU_Detail_
CAPEX by Bus Unit / BU Detail / PE: Admin lock | PE -> Budget Contact | a-YTD-Mar - 2016 | [6 empty] | 2016
|  | CF Gulf - 2016 Official Budget - Live Reforecast | (VID:20160325) CF Gulf - 2016 Official Budget (Preserved) | Dif. (VID:20160325) CF Gulf - 2016 Official Budget (Preserved) | % Dif. (VID:20160325) CF Gulf - 2016 Official Budget (Preserved) |  |  |  |  | CF Gulf - 2016 Official Budget - Live Reforecast | (VID:20160325) CF Gulf - 2016 Official Budget (Preserved) | Dif. (VID:20160325) CF Gulf - 2016 Official Budget (Preserved) | % Dif. (VID:20160325) CF Gulf - 2016 Official Budget (Preserved)
2016-03-01 | Pointer to Budget Contact | YTD Actual | YTD Budget | YTD Variance ($) | YTD Variance (%) | YTD Over/Under Budget | Explanation Required? | YTD Explanation | Year-End Projection | Year-End Calculated | Original Budget | Year-End Variance ($) | Year-End Variance (%) | Year-End Over/Under Budget | YE Projection - YE Calculated
Power Generation
Co Generation
FPC-0040: Co-Generation Misc Projects | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 1500000 | 1500000 | 1500000 | 0 | 0% | On Budget | 0
Sub-Total Co Generation |  | 0 | 0 | 0 | 0% | On Budget |  |  | 1500000 | 1500000 | 1500000 | 0 | 0% | On Budget | 0
Environmental Cost Recovery Clause
FPC-0404: FPC-0404 | FPC - Vicki L. Mack: Vicki | 46599.56 | 0 | 46599.56 | 100% | Over Budget | Yes | 2015 Carryover | 346 | 46599.56 | 0 | 346 | 100% | Over Budget | -46253.56
FPC-0406: ECRC - LAND - SMITH CCR WASTE WATER MANAGEMENT | FPC - Vicki L. Mack: Vicki | 0 | 933750 | -933750 | -100% | Under Budget | Yes | Duplicate project. PE 1641 | 0 | 2728 | 3750000 | -3750000 | -100% | Under Budget | -2728
FPC-0412: ECRC-SMITH DUST MITIGATION WATER TRUCK | FPC - Vicki L. Mack: Vicki | 148937.5 | 100000 | 48937.5 | 48.94% | Over Budget | Yes | Projected project overrun to be absorbed by PE 1600 | 150000 | 148937.5 | 100000 | 50000 | 50% | Over Budget | 1062.5
FPC-0514: ECRC Daniel -Water -Ground Water Well | FPC - Vicki L. Mack: Vicki | 1454.53 | 0 | 1454.53 | 100% | Over Budget | No |  | 1455 | 1454.53 | 0 | 1455 | 100% | Over Budget | 0.47
FPC-1031: ECRC-AIR-CRIST 7 SCR CATALYST REPLACEMENT | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 894961 | 894961 | 894961 | 0 | 0% | On Budget | 0
FPC-1060: ECRC-AIR-CRIST 7 FGAS MONITORS | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 46000 | 46000 | 46000 | 0 | 0% | On Budget | 0
FPC-1158: ECRC-AIR-CRIST 7 SCR MISC | FPC - Vicki L. Mack: Vicki | 1071.82 | 0 | 1071.82 | 100% | Over Budget | No |  | 1072 | 1071.82 | 0 | 1072 | 100% | Over Budget | 0.18
FPC-1193: ECRC-WATER-CRIST 4-7 LOW VOLUME WASTE WATER TREATMENT | FPC - Vicki L. Mack: Vicki | 21894.51 | 752400 | -730505.49 | -97.09% | Under Budget | Yes | Will be done later in year | 3009600 | 2279094.51 | 3009600 | 0 | 0% | On Budget | 730505.49 | 700000 | 77778 | 700002 | 622224 | 77776 | 700000
FPC-1199: ECRC-AIR-CRIST U7 SCR PRECIP RELOCAT | FPC - Vicki L. Mack: Vicki | 262.96 | 6250 | -5987.04 | -95.79% | Under Budget | No |  | 25000 | 19012.96 | 25000 | 0 | 0% | On Budget | 5987.04
FPC-1222: ECRC-AIR-CRIST - SCRUBBER | FPC - Vicki L. Mack: Vicki | 773098.99 | 125000 | 648098.99 | 518.5% | Over Budget | Yes | Add PE 1233 prior year carryover. Not anticipated some projects needed earlier in year | 5573250 | 6221348.99 | 5573250 | 0 | 0% | On Budget | -648098.99 | -650000 | -72222 | -649998 | -577776 | -72224 | -650000
FPC-1233: ECRC-AIR-CRIST SCRUBBER MISCELLANEOUS | FPC - Vicki L. Mack: Vicki | 387925.97 | 0 | 387925.97 | 100% | Over Budget | Yes | Carryover | 387926 | 387925.97 | 0 | 387926 | 100% | Over Budget | 0.03 |  | -87956
FPC-1234: ECRC-AIR-CRIST U7 LOW NOX BURNER REPLACEMENT | FPC - Vicki L. Mack: Vicki | 70968.55 | 0 | 70968.55 | 100% | Over Budget | Yes | Carryover | 70969 | 70968.55 | 0 | 70969 | 100% | Over Budget | 0.45
FPC-1279: ECRC-AIR-CRIST U6 CONTROLS - SCR & ID FANS | FPC - Vicki L. Mack: Vicki | 0 | 2750 | -2750 | -100% | Under Budget | No |  | 11000 | 8250 | 11000 | 0 | 0% | On Budget | 2750
FPC-1287: ECRC-AIR-CRIST 4-6 NOX REDUCTION - DEPR - (SNCR) | FPC - Vicki L. Mack: Vicki | 196129.93 | 646126 | -449996.07 | -69.65% | Under Budget | Yes | Money spent on flame scanners in 2015 | 655500 | 205503.93 | 655500 | 0 | 0% | On Budget | 449996.07 | 450000 | 50000 | 450000 | 400000 | 50000 | 450000
FPC-1288: ECRC-AIR-CRIST-CONSTRUCT GYPSUM STORAGE CELL NO. 1 | FPC - Vicki L. Mack: Vicki | 45812.78 | 151200 | -105387.22 | -69.7% | Under Budget | Yes | Project starting later than expected | 1681246 | 1575858.78 | 1681246 | 0 | 0% | On Budget | 105387.22
FPC-1517: ECRC - AIR- DANIEL BROMINE INJECTION | FPC - Vicki L. Mack: Vicki | -28962.62 | 0 | -28962.62 | -100% | Under Budget | Yes | Carry over credits from A&G ECRC | -28963 | -28962.62 | 0 | -28963 | -100% | Under Budget | -0.38
FPC-1551: ECRC-AIR-DANIEL 1 & 2 SCRUBBER | FPC - Vicki L. Mack: Vicki | 1477529.48 | 2400795 | -923265.52 | -38.46% | Under Budget | Yes | Credits from contract close outs and asset recovery. Credits transferred from A&G | 3095703 | 2393357.48 | 3095703 | 0 | 0% | On Budget | 702345.52 | 700000 | 77778 | 700002 | 622224 | 77776 | 700000
FPC-1601: ECRC-WATER-SMITH RECLAIMED WATER PROJECT UNIT 3 | FPC - Vicki L. Mack: Vicki | 457961.86 | 340807 | 117154.86 | 34.38% | Over Budget | Yes | Projected project overrun to be absorbed by ECRC underruns | 500000 | 695233.86 | 340807 | 159193 | 46.71% | Over Budget | -195233.86 |  | 25926 | 700002 | 34106 | 34164
FPC-1641: ECRC - Smith 1 & 2 Cross Media Retrofit | FPC - Vicki L. Mack: Vicki | 0 | 933750 | -933750 | -100% | Under Budget | Yes | Project has not started | 3750000 | 3069886 | 3750000 | 0 | 0% | On Budget | 680114 | 700000 | 77778 | 700002 | 622224 | 77776 | 700000 | 105956 | 98180
FPC-1809: ECRC -AIR-DANIEL 1 & 2 ACTIVATED CARBON INJECTION C01767 | FPC - Vicki L. Mack: Vicki | -17507.72 | 782117 | -799624.72 | -102.2% | Under Budget | Yes | Accruals in December - Planned scope pushed out to later months | 782117 | 350674.28 | 782117 | 0 | 0% | On Budget | 431442.72 | 450000 | 50000 | 450000 | 400000 | 50000 | 450000
FPC-1909: ECRC-AIR-CIRST MISC SCR COMMON | FPC - Vicki L. Mack: Vicki | 30304.99 | 12498 | 17806.99 | 142.5% | Over Budget | Yes | Project started earlier than anticipted | 50000 | 67806.99 | 50000 | 0 | 0% | On Budget | -17806.99 |  | 90909
FPC-1912: ECRC-AIR-CRIST U4-7 DRY BOTTOM ASH | FPC - Vicki L. Mack: Vicki | 0 | 625002 | -625002 | -100% | Under Budget | Yes | Environmental Affairs Project- Checking to see if gets done | 2500000 | -1 | 2500000 | 0 | 0% | On Budget | 2500001 | 2500000 | 277778 | 2500002 | 2222224 | 277776 | 2500000
FPC-1997: ECRC-LAND-CRIST DISPOSAL OF COAL COMBUSTION RESIDUALS (CCR) | FPC - Vicki L. Mack: Vicki | 68897.94 | 0 | 68897.94 | 100% | Over Budget | Yes | Carryover | 68898 | 68897.94 | 0 | 68898 | 100% | Over Budget | 0.06 |  | 69445 |  |  | 69441
Sub-Total Environmental Cost Recovery Clause |  | 3682381.03 | 7812445 | -4130063.97 | -52.87% | Under Budget |  |  | 23226080 | 18526609.03 | 26265184 | -3039104 | -11.57% | Under Budget | 4699470.97
Environmental (Non-Clause)
FPC-0501: Envir Daniel Unit 1 Pyrite Hoppers/Piping Valves | FPC - Vicki L. Mack: Vicki | -876.41 | 0 | -876.41 | -100% | Under Budget | No |  | -1078 | -876.41 | 0 | -1078 | -100% | Under Budget | -201.59
FPC-1033: ENVIR - WASTE - CRIST FLY ASH LANDFILL STORAGE CELL CAPPING | FPC - Vicki L. Mack: Vicki | 0 | 131196 | -131196 | -100% | Under Budget | Yes | $500 K to offset PE 1220 Governor's Island Headwall | 0 | 393804 | 525000 | -525000 | -100% | Under Budget | -393804
FPC-1220: ENVIR-WATER-CRIST GOVERNORS ISLAND HEADWALL | FPC - Vicki L. Mack: Vicki | 2113971.53 | 0 | 2113971.53 | 100% | Over Budget | Yes | PE approval letter | 3255000 | 2113971.53 | 0 | 3255000 | 100% | Over Budget | 1141028.47 | 1150000 | 127778 | 1150002 | 1022224 | 127776 | 1150000 | 55556 | 55552
FPC-1253: ENVIR-WASTE- CRIST-FLY ASH LANDFILL STORAGE CELL DEVELOPMENT | FPC - Vicki L. Mack: Vicki | 42669.2 | 249900 | -207230.8 | -82.93% | Under Budget | Yes | Actuals are carryover. Budget dollars to be used to offset PE 1220 | 42669 | 2142769.2 | 1000000 | -957331 | -95.73% | Under Budget | -2100100.2 | -2100000 | -233333 | -2099997 | -1866664 | -233336 | -2100000
FPC-1613: ENVIR-WASTE-SMITH CAP ASH LANDFILL CELLS | FPC - Vicki L. Mack: Vicki | 114.37 | 0 | 114.37 | 100% | Over Budget | No |  | 114 | 114.37 | 0 | 114 | 100% | Over Budget | -0.37 |  | -83333 |  |  | -83336
FPC-1701: ENVIR - AIR - SCHERER 3 -MISC ENVIRONMENTAL PROJECTS | FPC - Vicki L. Mack: Vicki | 9714.6 | 25923 | -16208.4 | -62.53% | Under Budget | Yes | less misc Environmental projects needed in 1st quarter | 116935 | 87521.6 | 103730 | 13205 | 12.73% | Over Budget | 29413.4
FPC-1727: ENVIR-AIR-SCHERER SELECTIVE CAYALYTIC REDUCT (SCR) | FPC - Vicki L. Mack: Vicki | -26609.78 | 0 | -26609.78 | -100% | Under Budget | Yes | carryover | 22531 | -26609.78 | 0 | 22531 | 100% | Over Budget | 49140.78
FPC-1728: ENVIR-AIR-SCHERER SCRUBBER | FPC - Vicki L. Mack: Vicki | -262488.5 | 0 | -262488.5 | -100% | Under Budget | Yes | Carryover | -190251 | -262488.5 | 0 | -190251 | -100% | Under Budget | 72237.5
FPC-1729: FPC-1729 | FPC - Vicki L. Mack: Vicki | 37218.01 | 0 | 37218.01 | 100% | Over Budget | Yes | carrupver | -190251 | 37218.01 | 0 | -190251 | -100% | Under Budget | -227469.01
FPC-1755: ENVIR SCHERER-AIR-HG/PM CEMS | FPC - Vicki L. Mack: Vicki | 674.75 | 0 | 674.75 | 100% | Over Budget | No |  | 675 | 674.75 | 0 | 675 | 100% | Over Budget | 0.25
FPC-1762: ENVIR - Air- Scherer 3 Bromine Injection | FPC - Vicki L. Mack: Vicki | 0 | 279000 | -279000 | -100% | Under Budget | Yes | Project later getting started than anticipated | 1116000 | 837000 | 1116000 | 0 | 0% | On Budget | 279000
FPC-1778: ENVIR - SCHERER - ENVIRONMENTAL SITE PLAN | FPC - Vicki L. Mack: Vicki | -48965.78 | 0 | -48965.78 | -100% | Under Budget | Yes | Carryover credit from EC&S | -168070 | -48965.78 | 0 | -168070 | -100% | Under Budget | -119104.22
FPC-1791: FPC-1791 | FPC - Vicki L. Mack: Vicki | -20664.9 | 0 | -20664.9 | -100% | Under Budget | Yes | Carryover credit from EC&S | -20665 | -20664.9 | 0 | -20665 | -100% | Under Budget | -0.1
FPC-1798: ENVIR SCHERER 3 SCR CATALYST REPLACEMENT | FPC - Vicki L. Mack: Vicki | 0 | 170890 | -170890 | -100% | Under Budget | Yes | Project later getting started than anticipated | 341780 | 170890 | 341780 | 0 | 0% | On Budget | 170890
FPC-1878: Environ - Daniel 1 & 2 Dry Ash Equipment | FPC - Vicki L. Mack: Vicki | 25162.52 | 0 | 25162.52 | 100% | Over Budget | Yes | SCS charges related to Load testing, redline redraws and commissioning charges not included in OB | 32577 | 25162.52 | 0 | 32577 | 100% | Over Budget | 7414.48
FPC-6756: Envir - Scherer 3 -LAND CCR ASH MANAGEMENT | FPC - Vicki L. Mack: Vicki | 0 | 79395 | -79395 | -100% | Under Budget | Yes | Project later getting started than anticipated | 317500 | 260271 | 317576 | -76 | -0.02393% | Under Budget | 57229
FPC-6757: Envir - Scherer 3 New Landfill - Phase 1 | FPC - Vicki L. Mack: Vicki | 0 | 50007 | -50007 | -100% | Under Budget | Yes | Project later getting started than anticipated | 200000 | 150021 | 200028 | -28 | -0.014% | Under Budget | 49979
FPC-6759: Envir - Scherer - Land- CCR WW Management | FPC - Vicki L. Mack: Vicki | 0 | 39189 | -39189 | -100% | Under Budget | Yes | Project later getting started than anticipated | 156875 | 117567 | 156756 | 119 | 0.07591% | Over Budget | 39308
Sub-Total Environmental (Non-Clause) |  | 1869919.61 | 1025500 | 844419.61 | 82.34% | Over Budget |  |  | 5032341 | 5977379.61 | 3760870 | 1271471 | 33.81% | Over Budget | -945038.61
Plant Crist
FPC-0803: Crist U 7 BFP Controls Replacement | FPC - Vicki L. Mack: Vicki | 103533.35 | 0 | 103533.35 | 100% | Over Budget | Yes | Moved to beginning of year | 866250 | 969783.35 | 866250 | 0 | 0% | On Budget | -103533.35
FPC-0804: Crist Unit 7 BFPT Overspeed Bolt Replacement | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 890925 | 890925 | -890925 | -100% | Under Budget | -890925
FPC-0805: Crist U7 Main Turbine Overspeed Bolt Replacement | FPC - Vicki L. Mack: Vicki | 45530.24 | 0 | 45530.24 | 100% | Over Budget | Yes | Progress payment made earlier than expected | 1683675 | 838280.24 | 792750 | 890925 | 112.4% | Over Budget | 845394.76 | 850000 | 94444 | 849996 | 755552 | 94448 | 850000
FPC-0806: Crist U6 BFPT Overspeed Bolt Replacement | FPC - Vicki L. Mack: Vicki | 45381.57 | 0 | 45381.57 | 100% | Over Budget | Yes | Material purchased earlier than expected | 280403 | 325784.57 | 280403 | 0 | 0% | On Budget | -45381.57
FPC-0807: Crist U6 Main Turbine Overspeed Bolt Replacement | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 334031 | 334031 | 334031 | 0 | 0% | On Budget | 0
FPC-0808: Crist U7 Airflow Transmitter (Kurz) Replacement | FPC - Vicki L. Mack: Vicki | 5678.32 | 187500 | -181821.68 | -96.97% | Under Budget | Yes | Project started later than budgeted | 399000 | 217178.32 | 399000 | 0 | 0% | On Budget | 181821.68
FPC-0809: Crist A Flyash Compressor | FPC - Vicki L. Mack: Vicki | 0 | 68880 | -68880 | -100% | Under Budget | Yes | Project starting later than budgeted | 68880 | 0 | 68880 | 0 | 0% | On Budget | 68880
FPC-0810: Crist B Flyash Compressor | FPC - Vicki L. Mack: Vicki | 0 | 68880 | -68880 | -100% | Under Budget | Yes | Project starting later than budgeted | 68880 | 0 | 68880 | 0 | 0% | On Budget | 68880
FPC-0812: Crist U4 Turbine Water Induction Protection (TWIP) | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 196925 | 1969250 | -1969250 | -100% | Under Budget | -196925
FPC-0813: Crist U5 Turbine Water Induction Protection (TWIP) | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 196925 | 1969250 | -1969250 | -100% | Under Budget | -196925
FPC-0816: Crist Common Replace Fencing (Security) | FPC - Vicki L. Mack: Vicki | 0 | 137000 | -137000 | -100% | Under Budget | Yes | Project will start later than budgeted | 550000 | 413000 | 550000 | 0 | 0% | On Budget | 137000
FPC-0817: Crist - Replace Units 6 & 7 Elevator | FPC - Vicki L. Mack: Vicki | 0 | 450000 | -450000 | -100% | Under Budget | Yes | Project will start later than budgeted | 1500000 | 1050000 | 1500000 | 0 | 0% | On Budget | 450000
FPC-1003: CRIST 7 BOTTOM ASH PIT TRASH HOPPER | FPC - Vicki L. Mack: Vicki | 0 | 7350 | -7350 | -100% | Under Budget | No |  | 157500 | 150150 | 157500 | 0 | 0% | On Budget | 7350
FPC-1027: CRIST 4 & 5 ASH CONTROLS | FPC - Vicki L. Mack: Vicki | 321.68 | 0 | 321.68 | 100% | Over Budget | No |  | 322 | 321.68 | 0 | 322 | 100% | Over Budget | 0.32
FPC-1041: CRIST 6C 4160 V BUS REPL BREAKERS | FPC - Vicki L. Mack: Vicki | 120401.9 | 40000 | 80401.9 | 201% | Over Budget | Yes | SCS drawings underestimated - other SCS work needed | 160000 | 120401.9 | 40000 | 120000 | 300% | Over Budget | 39598.1
FPC-1042: CRIST 7C 4160 VOLT BUS REPLACE BREAKERS | FPC - Vicki L. Mack: Vicki | 71433.83 | 30000 | 41433.83 | 138.1% | Over Budget | Yes | SCS drawings underestimated | 107000 | 81433.83 | 40000 | 67000 | 167.5% | Over Budget | 25566.17
FPC-1046: CRIST 4-7 SILO ASH MCC REPLACEMENT | FPC - Vicki L. Mack: Vicki | 35903.38 | 3165 | 32738.38 | 1034% | Over Budget | Yes | SCS charges started earlier than anticipated | 265650 | 298388.38 | 265650 | 0 | 0% | On Budget | -32738.38
FPC-1050: CRIST U5 575 VOLT BUS REPLACEMENT | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 15750 | 15750 | 15750 | 0 | 0% | On Budget | 0
FPC-1059: CRIST 5 -- 2300 VOLT BREAKERS | FPC - Vicki L. Mack: Vicki | 20770.38 | 0 | 20770.38 | 100% | Over Budget | Yes | Carryover | 20770 | 20770.38 | 0 | 20770 | 100% | Over Budget | -0.38
FPC-1081: CRIST U4 ASSET PROTECTION - PAG | FPC - Vicki L. Mack: Vicki | 140470.13 | 0 | 140470.13 | 100% | Over Budget | Yes | Scope increased. TWIP added | 2019250 | 1891470.13 | 50000 | 1969250 | 3938% | Over Budget | 127779.87
FPC-1089: CRIST 6 REPLACE ASH HOOPER | FPC - Vicki L. Mack: Vicki | 40.84 | 0 | 40.84 | 100% | Over Budget | No |  | 41 | 40.84 | 0 | 41 | 100% | Over Budget | 0.16
FPC-1091: CRIST 7 AIR HEATER BASKETS | FPC - Vicki L. Mack: Vicki | 1148796.25 | 0 | 1148796.25 | 100% | Over Budget | Yes | Scope increased. TWIP added | 2000000 | 3148796.25 | 2000000 | 0 | 0% | On Budget | -1148796.25 | -1150000 | -127778 | -1150002 | -1022224 | -127776 | -1150000
FPC-1093: CRIST U5 ASSET PROTECTION - PAG | FPC - Vicki L. Mack: Vicki | 146306.39 | 0 | 146306.39 | 100% | Over Budget | Yes | Scope increased. TWIP added | 2019250 | 1906306.39 | 50000 | 1969250 | 3938% | Over Budget | 112943.61
FPC-1096: CRIST U6 ASSET PROTECTION - PAG | FPC - Vicki L. Mack: Vicki | 35780.14 | 0 | 35780.14 | 100% | Over Budget | Yes | Scope increased. TWIP added | 140000 | 85780.14 | 50000 | 90000 | 180% | Over Budget | 54219.86
FPC-1097: CRIST U7 ASSET PROTECTION - PAG | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 50000 | 50000 | 50000 | 0 | 0% | On Budget | 0
FPC-1100: CRIST - MINOR MISC ADDITIONS | FPC - Vicki L. Mack: Vicki | 248489.63 | 187425 | 61064.63 | 32.58% | Over Budget | Yes | More minor miscellaneous jobs than budgeted | 1753393 | 1711064.63 | 750000 | 1003393 | 133.8% | Over Budget | 42328.37
FPC-1108: CRIST 7 FLY ASH CONTROLS | FPC - Vicki L. Mack: Vicki | 293.76 | 26250 | -25956.24 | -98.88% | Under Budget | Yes | Project started later than budgeted | 315000 | 289043.76 | 315000 | 0 | 0% | On Budget | 25956.24
FPC-1143: CRIST 5 MONITORING SYSTEM UPGRADES | FPC - Vicki L. Mack: Vicki | -1607.47 | 0 | -1607.47 | -100% | Under Budget | No |  | -1607 | -1607.47 | 0 | -1607 | -100% | Under Budget | 0.47
FPC-1144: CRIST 7 CONTROL SYSTEM UPGRADES | FPC - Vicki L. Mack: Vicki | 33554.58 | 0 | 33554.58 | 100% | Over Budget | Yes | SCS charges | 33555 | 33554.58 | 0 | 33555 | 100% | Over Budget | 0.42
FPC-1148: CRIST - MAJOR MISC ADDITIONS | FPC - Vicki L. Mack: Vicki | 474671.2 | 249900 | 224771.2 | 89.94% | Over Budget | Yes | More Major miscellaneous jobs needed than Budgeted | 2003394 | 2034771.2 | 1000000 | 1003394 | 100.3% | Over Budget | -31377.2
FPC-1151: CRIST CLEARWATER HDRS & PIPING | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 300300 | 300300 | 300300 | 0 | 0% | On Budget | 0
FPC-1176: CRIST U4 REPL BREAKERS CABLE & SWITCHES FOR ARC FLASH STUDY | FPC - Vicki L. Mack: Vicki | -10716.51 | 0 | -10716.51 | -100% | Under Budget | Yes | carryover | -10717 | -10716.51 | 0 | -10717 | -100% | Under Budget | -0.49
FPC-1210: CRIST CYBER SECURITY | FPC - Vicki L. Mack: Vicki | 0 | 36291 | -36291 | -100% | Under Budget | Yes | Project starting later than budgeted | 145217 | 108926 | 145217 | 0 | 0% | On Budget | 36291
FPC-1223: CRIST 7 BOTTOM ASH HOPPER | FPC - Vicki L. Mack: Vicki | 103736.78 | 2004193 | -1900456.22 | -94.82% | Under Budget | Yes | $1M to offset PE 1220 Governor's Island Headwall, Progress Pymt made in 2015. bid was lower | 5087295 | 5187890.78 | 8446528 | -3359233 | -39.77% | Under Budget | -100595.78
FPC-1254: CRIST COMMON -CONVEYOR BELTS REPLACEMENT | FPC - Vicki L. Mack: Vicki | 921.02 | 0 | 921.02 | 100% | Over Budget | No |  | 105000 | 105921.02 | 105000 | 0 | 0% | On Budget | -921.02
FPC-1282: CRIST UNITS 4 5 6 & 7 CHEMICAL FEED SYSTEM | FPC - Vicki L. Mack: Vicki | 14070.37 | 0 | 14070.37 | 100% | Over Budget | Yes | carryover | 14070 | 14070.37 | 0 | 14070 | 100% | Over Budget | -0.37
FPC-1925: CRIST PURCHASE MOBILE CRANE TO REPL TEREX | FPC - Vicki L. Mack: Vicki | 3463.34 | 0 | 3463.34 | 100% | Over Budget | No |  | 3463 | 3463.34 | 0 | 3463 | 100% | Over Budget | -0.34
FPC-1936: CRIST DRY AIR LAY-UP SYSTEM FOR UNITS 4-7 | FPC - Vicki L. Mack: Vicki | 5239.78 | 0 | 5239.78 | 100% | Over Budget | No |  | 5240 | 372739.78 | 367500 | -362260 | -98.57% | Under Budget | -367499.78
FPC-1937: CRIST U6 PULVERIZER GEARBOX | FPC - Vicki L. Mack: Vicki | 0 | 76581 | -76581 | -100% | Under Budget | Yes | work will be done later in year | 127636 | 51055 | 127636 | 0 | 0% | On Budget | 76581
FPC-1942: CRIST U7 PULVERIZER GEARBOXES | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 127636 | 127636 | 127636 | 0 | 0% | On Budget | 0
FPC-1946: CRIST SILO SUMP PUMP DISCHARGE LINE | FPC - Vicki L. Mack: Vicki | 14572.74 | 0 | 14572.74 | 100% | Over Budget | Yes | Carryover | 14573 | 14572.74 | 0 | 14573 | 100% | Over Budget | 0.26
FPC-1953: CRIST U6 & U7 NEW BREAKER BUILDING | FPC - Vicki L. Mack: Vicki | 3968.19 | 0 | 3968.19 | 100% | Over Budget | No |  | 3968 | 3968.19 | 0 | 3968 | 100% | Over Budget | -0.19
FPC-1960: CRIST PURCHASE NEW RADIOS | FPC - Vicki L. Mack: Vicki | 21129.56 | 0 | 21129.56 | 100% | Over Budget | Yes | carryover | 21130 | 21129.56 | 0 | 21130 | 100% | Over Budget | 0.44
FPC-1963: CRIST Lab Bathrooms | FPC - Vicki L. Mack: Vicki | 0 | 157500 | -157500 | -100% | Under Budget | Yes | Project will start later than budgeted | 703500 | 546000 | 703500 | 0 | 0% | On Budget | 157500
FPC-1973: CRIST SWITCHYARD DRAINS | FPC - Vicki L. Mack: Vicki | -15629.16 | 102375 | -118004.16 | -115.3% | Under Budget | Yes | cancelled | -15629 | 86745.84 | 204750 | -220379 | -107.6% | Under Budget | -102374.84
FPC-1977: CRIST U7 REPLACE PULVERIZER MOTOR | FPC - Vicki L. Mack: Vicki | 120294.74 | 0 | 120294.74 | 100% | Over Budget | Yes | carryover | 120295 | 120294.74 | 0 | 120295 | 100% | Over Budget | 0.26
FPC-1978: CRIST REPLACE B SILO COMPRESSOR | FPC - Vicki L. Mack: Vicki | 12590.3 | 0 | 12590.3 | 100% | Over Budget | Yes | 2015 project moved to 2016 | 194250 | 12590.3 | 0 | 194250 | 100% | Over Budget | 181659.7
FPC-1979: CRIST ASH TRUCK SCALES | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 571165 | 571165 | 571165 | 0 | 0% | On Budget | 0
FPC-1990: CRIST 4&5 COLLING TOWER FIRE PUMP STATION | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 330750 | 330750 | 330750 | 0 | 0% | On Budget | 0
FPC-1991: CRIST U6 575 VOLT BREAKER REPLACEMENT | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 400523 | 400523 | 400523 | 0 | 0% | On Budget | 0
FPC-1992: CRIST U7 575 VOLT BREAKER REPLACEMENT | FPC - Vicki L. Mack: Vicki | 1794.02 | 0 | 1794.02 | 100% | Over Budget | No |  | 1794 | 540444.02 | 538650 | -536856 | -99.67% | Under Budget | -538650.02
Sub-Total Plant Crist |  | 2951185.27 | 3833290 | -882104.73 | -23.01% | Under Budget |  |  | 25061846 | 26178738.27 | 26842674 | -1780828 | -6.634% | Under Budget | -1116892.27
Plant Smith excl LTSA
FPC-0400: FPC-0400 | FPC - Vicki L. Mack: Vicki | 195.55 | 0 | 195.55 | 100% | Over Budget | No |  | 196 | 195.55 | 0 | 196 | 100% | Over Budget | 0.45
FPC-0401: FPC-0401 | FPC - Vicki L. Mack: Vicki | 345.74 | 0 | 345.74 | 100% | Over Budget | No |  | 346 | 345.74 | 0 | 346 | 100% | Over Budget | 0.26
FPC-0407: SMITH - CONSTRUCTION SUB TRANSFORMER (LAGUNA BEACH) | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 181818 | 1000000 | -1000000 | -100% | Under Budget | -181818
FPC-0408: SMITH 3 - COOLING TOWER FILL MEDIA REPLACEMENTS | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 125000 | 125000 | 125000 | 0 | 0% | On Budget | 0
FPC-0409: SMITH 3 - DRIFT ELIMINATOR | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 150000 | 150000 | 150000 | 0 | 0% | On Budget | 0
FPC-0410: SMITH 3 - COOLING TOWER DCS CABINET REPLACEMENTS | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 80000 | 80000 | 80000 | 0 | 0% | On Budget | 0
FPC-0413: Smith 3 - Water Mist Fire Protection System | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 685000 | 685000 | 685000 | 0 | 0% | On Budget | 0
FPC-0414: FPC-0414 | FPC - Vicki L. Mack: Vicki | 0.87 | 0 | 0.87 | 0% | On Budget | No |  | 1 | 0.87 | 0 | 1 | 0% | On Budget | 0.13
FPC-1400: SMITH 1&2 - MISC. STEAM PLANT ADDITIONS | FPC - Vicki L. Mack: Vicki | 3960.17 | 131199 | -127238.83 | -96.98% | Under Budget | Yes | Minimal misc. activity on Smith 1 & 2 to date | 524885 | 397761.17 | 525000 | -115 | -0.0219% | Under Budget | 127123.83
FPC-1401: SMITH 3 - AIR COMPRESSOR REPLACEMENT | FPC - Vicki L. Mack: Vicki | 0 | 75000 | -75000 | -100% | Under Budget | Yes | Project has not started | 100000 | 25000 | 100000 | 0 | 0% | On Budget | 75000
FPC-1428: Smith 3 Water Treatment Plant Transformer | FPC - Vicki L. Mack: Vicki | 1.25 | 0 | 1.25 | 100% | Over Budget | No |  | 1 | 1.25 | 0 | 1 | 0% | On Budget | -0.25
FPC-1437: Smith 3 - Admin Bldg. Expansion | FPC - Vicki L. Mack: Vicki | 601349.98 | 871500 | -270150.02 | -31% | Under Budget | Yes | Project has not started | 4100000 | 4111849.98 | 3500000 | 600000 | 17.14% | Over Budget | -11849.98
FPC-1477: SMITH 3 - REPLACE INLINE AIR FILTERS | FPC - Vicki L. Mack: Vicki | 0 | 400000 | -400000 | -100% | Under Budget | Yes | Project has not started | 400000 | 0 | 400000 | 0 | 0% | On Budget | 400000 | 400000 | 44444 | 399996 | 355552 | 44448 | 400000
FPC-1499: Smith U3 - Simulator | FPC - Vicki L. Mack: Vicki | 872.72 | 0 | 872.72 | 100% | Over Budget | No |  | 27000 | 872.72 | 0 | 27000 | 100% | Over Budget | 26127.28
FPC-1600: SMITH 3 - MISC. STEAM PLANT ADDITIONS | FPC - Vicki L. Mack: Vicki | 60064.58 | 249911 | -189846.42 | -75.97% | Under Budget | Yes | Minimal misc activity on Smith 3 to date | 912254 | 810153.58 | 1000000 | -87746 | -8.775% | Under Budget | 102100.42
FPC-1610: SMITH - CYBER SECURITY | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 39600 | 28634 | 28634 | 10966 | 38.3% | Over Budget | 10966
FPC-1626: SMITH - NERC CIP IMPLEMENTATION | FPC - Vicki L. Mack: Vicki | 0 | 38725 | -38725 | -100% | Under Budget | Yes | project not started-- gwo in process of getting set up | 154900 | 116175 | 154900 | 0 | 0% | On Budget | 38725
FPC-1632: SMITH 3 - REPLACE EVAP COOLER FILL MEDIA | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 150000 | 100000 | 100000 | 50000 | 50% | Over Budget | 50000
FPC-1648: SMITH 3 - STORM WATER SYSTEM | FPC - Vicki L. Mack: Vicki | -762.57 | 0 | -762.57 | -100% | Under Budget | No |  | -763 | -762.57 | 0 | -763 | -100% | Under Budget | -0.43
FPC-1672: SMITH - PROPERTY LINE FENCING | FPC - Vicki L. Mack: Vicki | 0 | 373500 | -373500 | -100% | Under Budget | Yes | Project has not started | 1500000 | 1126500 | 1500000 | 0 | 0% | On Budget | 373500 | 375000 | 41667 | 375003 | 333336 | 41664 | 375000
FPC-1679: SMITH 3 - CORROSION PROJECT | FPC - Vicki L. Mack: Vicki | 326006.01 | 249000 | 77006.01 | 30.93% | Over Budget | Yes | Early materials purchases in preparation to begin corrosion projects | 400000 | 1077006.01 | 1000000 | -600000 | -60% | Under Budget | -677006.01
Sub-Total Plant Smith excl LTSA |  | 992034.3 | 2388835 | -1396800.7 | -58.47% | Under Budget |  |  | 9348420 | 9015551.3 | 10348534 | -1000114 | -9.664% | Under Budget | 332868.7
Plant Smith - LTSA
FPC-1438: SMITH 3 - LTSA | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 27491875 | 27491875 | 27491875 | 0 | 0% | On Budget | 0
Sub-Total Plant Smith - LTSA |  | 0 | 0 | 0 | 0% | On Budget |  |  | 27491875 | 27491875 | 27491875 | 0 | 0% | On Budget | 0
Plant Daniel
FPC-0506: Daniel 1 & 2 Sump Pump | FPC - Vicki L. Mack: Vicki | 182.56 | 0 | 182.56 | 100% | Over Budget | No |  | 183 | 182.56 | 0 | 183 | 100% | Over Budget | 0.44
FPC-0507: Daniel Units 1 & 2 Termon Heat Trace ( Freeze Protection) | FPC - Vicki L. Mack: Vicki | 28389.11 | 0 | 28389.11 | 100% | Over Budget | Yes | Project added to MPC's final OB | 127620 | 28389.11 | 0 | 127620 | 100% | Over Budget | 99230.89
FPC-0510: Daniel U1 LED Lighting - Turbine Floor | FPC - Vicki L. Mack: Vicki | 37470.31 | 68724 | -31253.69 | -45.48% | Under Budget | Yes | Project reduced in MPC's final OB | 132212 | 443746.31 | 475000 | -342788 | -72.17% | Under Budget | -311534.31
FPC-0512: Daniel Common Breakers | FPC - Vicki L. Mack: Vicki | 4249.77 | 0 | 4249.77 | 100% | Over Budget | No |  | 0 | 284249.77 | 280000 | -280000 | -100% | Under Budget | -284249.77
FPC-0515: Daniel Conveyor Equipment- Add Camera to Conveyor Belts | FPC - Vicki L. Mack: Vicki | 0 | 74970 | -74970 | -100% | Under Budget | Yes | Project start date pushed back to April | 59885 | 75030 | 150000 | -90115 | -60.08% | Under Budget | -15145
FPC-0521: Daniel U2 Aux. Air Beck drives and registers | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 195000 | 195000 | -195000 | -100% | Under Budget | -195000
FPC-0523: Daniel Common Replace Coal yard Switchgear | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 95000 | 95000 | -95000 | -100% | Under Budget | -95000
FPC-0524: Daniel U1 Replace Critical AC | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 42867 | 32500 | 32500 | 10367 | 31.9% | Over Budget | 10367
FPC-0525: Daniel 2 Replace Critical AC | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 384302 | 302698 | 302698 | 81604 | 26.96% | Over Budget | 81604
FPC-0532: Daniel DEGP R/R S1 CONVEYOR GEARBOX | FPC - Vicki L. Mack: Vicki | 0 | 45000 | -45000 | -100% | Under Budget | Yes | Project start date pushed back to April and budget reduced in MPC's final budget | 17516 | 30000 | 75000 | -57484 | -76.65% | Under Budget | -12484
FPC-0541: Daniel Generator Rotor Rewind | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 5000 | 5000 | 5000 | 0 | 0% | On Budget | 0
FPC-0543: Daniel U1&2 Common CO2 Tank and Piping | FPC - Vicki L. Mack: Vicki | 22852.64 | 0 | 22852.64 | 100% | Over Budget | Yes | 2015 Carryover | 22853 | 22852.64 | 0 | 22853 | 100% | Over Budget | 0.36
FPC-0547: Daniel Common New cables for Ash Sluice Motors | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 100000 | 100000 | 100000 | 0 | 0% | On Budget | 0
FPC-0551: Daniel Common Emergency Notification System | FPC - Vicki L. Mack: Vicki | 0 | 93714 | -93714 | -100% | Under Budget | Yes | Project removed from MPC's Final OB | 0 | 93786 | 187500 | -187500 | -100% | Under Budget | -93786
FPC-1500: DANIEL-MISC. STEAM PLANT ADDITIONS & | FPC - Vicki L. Mack: Vicki | 136124.06 | 76515 | 59609.06 | 77.91% | Over Budget | Yes | Projects added to MPC's Final OB | 653623 | 365792.06 | 306183 | 347440 | 113.5% | Over Budget | 287830.94
FPC-1544: DANIEL WATER TREATMENT PLANT CONTROLS | FPC - Vicki L. Mack: Vicki | 29908.69 | 0 | 29908.69 | 100% | Over Budget | Yes | Gulf's cash flows are not in-line with MPC's for this project | 340000 | 369908.69 | 340000 | 0 | 0% | On Budget | -29908.69
FPC-1545: DANIEL 1&2 ASH HANDLING CONTROLS | FPC - Vicki L. Mack: Vicki | 77467.33 | 249480 | -172012.67 | -68.95% | Under Budget | Yes | MPC's OB had project spread evenly throughout year | 455306 | 205987.33 | 378000 | 77306 | 20.45% | Over Budget | 249318.67
FPC-1564: DANIEL 2 CAPITAL VALVE REPLACEMENTS | FPC - Vicki L. Mack: Vicki | 0 | 24750 | -24750 | -100% | Under Budget | Yes | Project removed from MPC's Final OB | 0 | 12750 | 37500 | -37500 | -100% | Under Budget | -12750
FPC-1581: DANIEL !&2 CONVEYOR DIRECT DRIVE GEARBOXES | FPC - Vicki L. Mack: Vicki | 9700.56 | 0 | 9700.56 | 100% | Over Budget | No |  | 18098 | 9700.56 | 0 | 18098 | 100% | Over Budget | 8397.44
FPC-1591: DANIEL RELAY MODERNIZATION | FPC - Vicki L. Mack: Vicki | 105754.41 | 74970 | 30784.41 | 41.06% | Over Budget | Yes | MPC Transmission project under estimated budget. | 150000 | 180784.41 | 150000 | 0 | 0% | On Budget | -30784.41
FPC-1800: Daniel Unit 2 Mill Hoist | FPC - Vicki L. Mack: Vicki | 38477.78 | 0 | 38477.78 | 100% | Over Budget | Yes | 2015 Carryover | 38478 | 38477.78 | 0 | 38478 | 100% | Over Budget | 0.22
FPC-1811: DANIEL 1 EXPANSION JOINTS C01693 | FPC - Vicki L. Mack: Vicki | -839.81 | 0 | -839.81 | -100% | Under Budget | No |  | -1033 | -839.81 | 0 | -1033 | -100% | Under Budget | -193.19
FPC-1834: DANIEL 1 REWIND GENERATOR | FPC - Vicki L. Mack: Vicki | -0.01 | 0 | -0.01 | 0% | On Budget | No |  | 0 | -0.01 | 0 | 0 | -100% | On Budget | 0.01
FPC-1861: DANIEL 2 FW HEATER 4 LP | FPC - Vicki L. Mack: Vicki | 0 | 29988 | -29988 | -100% | Under Budget | Yes | Project removed from MPC's Final OB | 0 | 90012 | 120000 | -120000 | -100% | Under Budget | -90012
FPC-1863: DANIEL 1 BOILER FEED PUMPS | FPC - Vicki L. Mack: Vicki | -548.46 | 0 | -548.46 | -100% | Under Budget | No |  | -548 | -548.46 | 0 | -548 | -100% | Under Budget | 0.46
FPC-1874: Daniel 1 & 2 Closed Loop Coolers | FPC - Vicki L. Mack: Vicki | -1551.26 | 0 | -1551.26 | -100% | Under Budget | No |  | -1551 | -1551.26 | 0 | -1551 | -100% | Under Budget | 0.26
FPC-1875: Daniel 1 & 2 CPAT Drum Index | FPC - Vicki L. Mack: Vicki | 1729.49 | 0 | 1729.49 | 100% | Over Budget | No |  | 1729 | 1729.49 | 0 | 1729 | 100% | Over Budget | -0.49
FPC-1879: Daniel 1 & 2 Hot Air Dampers and Cold Air Gates | FPC - Vicki L. Mack: Vicki | -503.89 | 0 | -503.89 | -100% | Under Budget | No |  | -504 | -503.89 | 0 | -504 | -100% | Under Budget | -0.11
FPC-1881: Daniel 1 & 2 Intelligent Sootblowing | FPC - Vicki L. Mack: Vicki | 12062.31 | 0 | 12062.31 | 100% | Over Budget | Yes | 2015 Carryover | 13000 | 49562.31 | 37500 | -24500 | -65.33% | Under Budget | -36562.31
FPC-1882: Daniel 1 & 2 Duct Replacement | FPC - Vicki L. Mack: Vicki | 3289.43 | 0 | 3289.43 | 100% | Over Budget | No |  | 85000 | 88289.43 | 85000 | 0 | 0% | On Budget | -3289.43
FPC-1884: Daniel 1 & 2 Air Heater Basket Replacement | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 54488 | 54488 | 54488 | 0 | 0% | On Budget | 0
FPC-1888: Daniel 1 & 2 Coal Additive System | FPC - Vicki L. Mack: Vicki | 226373.73 | 0 | 226373.73 | 100% | Over Budget | Yes | Project added to MPC's final OB | 226374 | 226373.73 | 0 | 226374 | 100% | Over Budget | 0.27
FPC-1891: Daniel Additional Belt Extension | FPC - Vicki L. Mack: Vicki | 99328.38 | 0 | 99328.38 | 100% | Over Budget | Yes | Project added to MPC's final OB | 124680 | 99328.38 | 0 | 124680 | 100% | Over Budget | 25351.62
FPC-1897: Daniel IK Soot Blower | FPC - Vicki L. Mack: Vicki | -8083.5 | 0 | -8083.5 | -100% | Under Budget | No |  | -8084 | -8083.5 | 0 | -8084 | -100% | Under Budget | -0.5
Sub-Total Plant Daniel |  | 821833.63 | 738111 | 83722.63 | 11.34% | Over Budget |  |  | 3041494 | 3490091.63 | 3406369 | -364875 | -10.71% | Under Budget | -448597.63
Plant Scherer
FPC-1700: SCHERER DEPOSITORY | FPC - Vicki L. Mack: Vicki | 1933168.28 | 0 | 1933168.28 | 100% | Over Budget | Yes | Scherer Depository PE represents the billing account for Scherer Cost. No Budget Dollars. | 0 | -676831.72 | 0 | 0 | -100% | On Budget | 676831.72
FPC-1710: SCHERER U3 INSTALL TRIPPER FLOOR DUST EXTRACTION EQUIPMENT | FPC - Vicki L. Mack: Vicki | 252.76 | 0 | 252.76 | 100% | Over Budget | No |  | 253 | 252.76 | 0 | 253 | 100% | Over Budget | 0.24
FPC-1716: SCHERER PORTABLE EQUIPMENT | FPC - Vicki L. Mack: Vicki | 0 | 2466 | -2466 | -100% | Under Budget | No |  | 9871 | 7405 | 9871 | 0 | 0% | On Budget | 2466
FPC-1726: SCHERER REPLACE SUPERHEAT PENDANT PLATEN | FPC - Vicki L. Mack: Vicki | 239969.73 | 121900 | 118069.73 | 96.86% | Over Budget | Yes | Spent earlier than budgeted but will also be over budget at year end | 252462 | 361869.73 | 243800 | 8662 | 3.553% | Over Budget | -109407.73
FPC-1731: SCHERER NERC CIP V4 IMPLEMETATION | FPC - Vicki L. Mack: Vicki | 2187.42 | 0 | 2187.42 | 100% | Over Budget | No |  | 218 | 2187.42 | 0 | 218 | 100% | Over Budget | -1969.42
FPC-1746: SCHERER U3 REPLACE REHEAT REPLACEMENT | FPC - Vicki L. Mack: Vicki | 433.88 | 6210 | -5776.12 | -93.01% | Under Budget | No |  | 12420 | 6643.88 | 12420 | 0 | 0% | On Budget | 5776.12
FPC-1750: SCHERER MISC ADDITIONS AND IMPROVEMENTS | FPC - Vicki L. Mack: Vicki | 49008.29 | 51069 | -2060.71 | -4.035% | Under Budget | No |  | 204361 | 202300.29 | 204361 | 0 | 0% | On Budget | 2060.71
FPC-1751: SCHERER 3 TURBINE CROSSOVER EXPANSION JOINT | FPC - Vicki L. Mack: Vicki | 0 | 12534 | -12534 | -100% | Under Budget | Yes | Haven't written GWO - late getting started | 79750 | 12536 | 25070 | 54680 | 218.1% | Over Budget | 67214
FPC-1757: SCHERER 3 REPLACE AIR HEATER BASKETS | FPC - Vicki L. Mack: Vicki | 0 | 24840 | -24840 | -100% | Under Budget | Yes | Haven't written GWO - late getting started | 49680 | 24840 | 49680 | 0 | 0% | On Budget | 24840
FPC-1792: Scherer Unit 3 Rewind Main Generator Stator | FPC - Vicki L. Mack: Vicki | 0 | 372600 | -372600 | -100% | Under Budget | Yes | Late starting project | 743200 | 372600 | 745200 | -2000 | -0.2684% | Under Budget | 370600
FPC-1794: SCHERER 3 & 4 REPLACE 3D FIXED TRIPPER CHUTES | FPC - Vicki L. Mack: Vicki | 0 | 6225 | -6225 | -100% | Under Budget | No |  | 12449 | 6224 | 12449 | 0 | 0% | On Budget | 6225
FPC-6502: Scherer 3 Replace Voltage Regulator | FPC - Vicki L. Mack: Vicki | 1320.54 | 4600 | -3279.46 | -71.29% | Under Budget | No |  | 9200 | 5920.54 | 9200 | 0 | 0% | On Budget | 3279.46
FPC-6507: Scherer 3 Replace Condenser Tube | FPC - Vicki L. Mack: Vicki | 0 | 248976 | -248976 | -100% | Under Budget | Yes | Late starting project | 497950 | 248974 | 497950 | 0 | 0% | On Budget | 248976
FPC-6508: Scherer 3 & 4 Replace Crusher House MCC U3 & U4 | FPC - Vicki L. Mack: Vicki | 29382.59 | 29555 | -172.41 | -0.5834% | Under Budget | No |  | 111497 | 58937.59 | 59110 | 52387 | 88.63% | Over Budget | 52559.41
FPC-6513: Scherer 3 & 4 Replace and Move Trestle Feeder | FPC - Vicki L. Mack: Vicki | 0 | 31122 | -31122 | -100% | Under Budget | Yes | Actuals going to PE 6529 | 0 | 31122 | 62244 | -62244 | -100% | Under Budget | -31122
FPC-6520: Scherer 3 Replace Turbine LP Rotor | FPC - Vicki L. Mack: Vicki | 486262.89 | 1760076 | -1273813.11 | -72.37% | Under Budget | Yes | Progess payment… delay but will be on budget year end | 3235393 | 2246336.89 | 3520150 | -284757 | -8.089% | Under Budget | 989056.11 | 1000000 | 11111 | 99999 | 88888 | 11112 | 100000
FPC-6528: Scherer 3 Auto Fire Suppression -Turb/Generatr Lube Oil | FPC - Vicki L. Mack: Vicki | 0 | 5750 | -5750 | -100% | Under Budget | No |  | 11500 | 5750 | 11500 | 0 | 0% | On Budget | 5750 |  | 111111 | 999999
FPC-6529: Scherer 3 & 4 Vibratory Feeders | FPC - Vicki L. Mack: Vicki | 34804.46 | 0 | 34804.46 | 100% | Over Budget | Yes | Budget dollars in PE 6513 | 34804 | 34804.46 | 0 | 34804 | 100% | Over Budget | -0.46
FPC-6534: Scherer 3 Replace BFPT Controls | FPC - Vicki L. Mack: Vicki | 0 | 62100 | -62100 | -100% | Under Budget | Yes | Delay in starting | 124200 | 62100 | 124200 | 0 | 0% | On Budget | 62100
FPC-6542: Scherer 3 Replace Polisher Controls | FPC - Vicki L. Mack: Vicki | 0 | 24840 | -24840 | -100% | Under Budget | Yes | Delay in starting | 49680 | 24840 | 49680 | 0 | 0% | On Budget | 24840
FPC-6543: Scherer Common U 1-4 Generation Step Up Spare (GSU) | FPC - Vicki L. Mack: Vicki | 0 | 43734 | -43734 | -100% | Under Budget | Yes | Delay in starting | 175000 | 131266 | 175000 | 0 | 0% | On Budget | 43734
Sub-Total Plant Scherer |  | 2776790.84 | 2808597 | -31806.16 | -1.132% | Under Budget |  |  | 5613888 | 3170078.84 | 5811885 | -197997 | -3.407% | Under Budget | 2443809.16
Renewables
FPC-0091: PERDIDO LANDFILL GAS ENERGY | FPC - Vicki L. Mack: Vicki | 0 | 30000 | -30000 | -100% | Under Budget | Yes | No misc capital projects needed in 1st quarter | 120000 | 90000 | 120000 | 0 | 0% | On Budget | 30000
FPC-0100: Community Solar One | FPC - Vicki L. Mack: Vicki | 0 | 20000 | -20000 | -100% | Under Budget | Yes | Delay in starting | 3000000 | 2980000 | 3000000 | 0 | 0% | On Budget | 20000
Sub-Total Renewables |  | 0 | 50000 | -50000 | -100% | Under Budget |  |  | 3120000 | 3070000 | 3120000 | 0 | 0% | On Budget | 50000
Sub-Total Power Generation |  | 13094144.68 | 18656778 | -5562633.32 | -29.82% | Under Budget |  |  | 103435944 | 98420323.68 | 108547391 | -5111447 | -4.709% | Under Budget | 5015620.32
Power Delivery
New Business Distribution
FPC-2550: CUSTOMER METERING | FPC - Paul C. Pratofiorito: Paul | 83388.08 | 262000 | -178611.92 | -68.17% | Under Budget | Yes | Timing: Plan to be on budget at year end. | 1046000 | 867388.08 | 1046000 | 0 | 0% | On Budget | 178611.92
FPC-2551: DISTRIBUTION TRANSFORMERS | FPC - Paul C. Pratofiorito: Paul | 1682248.57 | 2094000 | -411751.43 | -19.66% | Under Budget | Yes | Timing: Early in the year. | 8718000 | 8568066.76 | 8718000 | 0 | 0% | On Budget | 149933.24
FPC-2552: NEW BUSINESS - OVERHEAD CONSTRUCTION | FPC - Paul C. Pratofiorito: Paul | 1398333.92 | 1747000 | -348666.08 | -19.96% | Under Budget | Yes | Timing: Early in the year. | 6025000 | 5676333.92 | 6025000 | 0 | 0% | On Budget | 348666.08
FPC-2553: NEW BUSINESS STREET LIGHTS | FPC - Sarah K. Seckinger: Sarah | 44437.32 | 0 | 44437.32 | 100% | Over Budget | Yes | Charges will be moved to 2553 | 44437 | 44437.32 | 0 | 44437 | 100% | Over Budget | -0.32
FPC-2554: NEW BUSINESS - UNDERGROUND CONSTRUCTION | FPC - Paul C. Pratofiorito: Paul | 1950823.65 | 1761000 | 189823.65 | 10.78% | Over Budget | Yes | New Construction in underground areas up slightly. | 7379000 | 7568823.65 | 7379000 | 0 | 0% | On Budget | -189823.65
FPC-2556: PRIVATE STREET & YARD LIGHTS | FPC - Sarah K. Seckinger: Sarah | 1165990.62 | 2300154 | -1134163.38 | -49.31% | Under Budget | Yes | Timing on budget spreads | 8743806 | 7609642.62 | 8743806 | 0 | 0% | On Budget | 1134163.38 | 1100000 | 122222 | 1099998 | 977776 | 122224 | 1100000
FPC-2559: NEW BUSINESS - METERING ACC. ENCL. EQUIP. & DEVICES | FPC - Paul C. Pratofiorito: Paul | 26277.14 | 32000 | -5722.86 | -17.88% | Under Budget | No |  | 149000 | 143277.14 | 149000 | 0 | 0% | On Budget | 5722.86
FPC-4449: Electric Vehicle Charging Stations | FPC - Sarah K. Seckinger: Sarah | 0 | 205875 | -205875 | -100% | Under Budget | Yes | Timing | 823500 | 617625 | 823500 | 0 | 0% | On Budget | 205875
Sub-Total New Business Distribution |  | 6351499.3 | 8402029 | -2050529.7 | -24.41% | Under Budget |  |  | 32928743 | 31095594.49 | 32884306 | 44437 | 0.1351% | Over Budget | 1833148.51
Energy Conservation Cost Recovery
FPC-2558: ADVANCED ENERGY MANAGEMENT (AEM) | FPC - Sarah K. Seckinger: Sarah | 416936.33 | 502519 | -85582.67 | -17.03% | Under Budget | Yes | Timing on budget spreads | 2107992 | 2022409.33 | 2107992 | 0 | 0% | On Budget | 85582.67
Sub-Total Energy Conservation Cost Recovery |  | 416936.33 | 502519 | -85582.67 | -17.03% | Under Budget |  |  | 2107992 | 2022409.33 | 2107992 | 0 | 0% | On Budget | 85582.67
Transmission
FPC-2801: TRANS SUB INFRASTRUCTURE PROJECTS | FPC - Sarah K. Seckinger: Sarah | 57467.27 | 150000 | -92532.73 | -61.69% | Under Budget | Yes | Timing of budget to projects | 850000 | 757467.27 | 850000 | 0 | 0% | On Budget | 92532.73
FPC-2802: TRANS LINE INFRASTRUCTURE PROJECTS | FPC - Sarah K. Seckinger: Sarah | 1522156.77 | 1300000 | 222156.77 | 17.09% | Over Budget | Yes | Matting (crew support) for projects has cost more than originally planned | 5000000 | 5222156.77 | 5000000 | 0 | 0% | On Budget | -222156.77
FPC-2803: ALLIGATOR SWAMP SVC AND ASSOCIATED MODIFICATIONS | FPC - Sarah K. Seckinger: Sarah | 68615.82 | 0 | 68615.82 | 100% | Over Budget | Yes | Part of the SVC contractual price was tools. Original thought was they could go in a special ferc account. After actual cost for the tools from ABB was determined, accounting decided to spread the cost back against the asset. | 75000 | 68615.82 | 0 | 75000 | 100% | Over Budget | 6384.18
FPC-2808: Greenwood - Long Beach | FPC - Sarah K. Seckinger: Sarah | 192923.16 | 0 | 192923.16 | 100% | Over Budget | Yes | Additional contractor (Pike) work not expected | -2200000 | -2007076.84 | -2200000 | 0 | -100% | On Budget | -192923.16
FPC-2813: North Brewton - Alligator Swamp New 230 kV Transmission Line | FPC - Sarah K. Seckinger: Sarah | 2242.2 | 0 | 2242.2 | 100% | Over Budget | No |  | 5000 | 2242.2 | 0 | 5000 | 100% | Over Budget | 2757.8
FPC-2814: LAGUNA BEACH - SANTA ROSA #2 230KV TL | FPC - Sarah K. Seckinger: Sarah | 46854.33 | 0 | 46854.33 | 100% | Over Budget | Yes | Culvert work in January and February at Santa Rosa Substation | 50000 | 46854.33 | 0 | 50000 | 100% | Over Budget | 3145.67
FPC-2816: Backbone Fiber Project | FPC - Sarah K. Seckinger: Sarah | 587.75 | 90000 | -89412.25 | -99.35% | Under Budget | Yes | Design estimated to start in April | 555000 | 465587.75 | 555000 | 0 | 0% | On Budget | 89412.25
FPC-2821: ALLIGATOR SWAMP 230KV EXPANSION | FPC - Sarah K. Seckinger: Sarah | -17399.52 | 0 | -17399.52 | -100% | Under Budget | Yes | Credit due to COR | -20000 | -17399.52 | 0 | -20000 | -100% | Under Budget | -2600.48
FPC-2822: TRANSMISSION LN SWITCH REPL PROJ | FPC - Sarah K. Seckinger: Sarah | 208034.45 | 120000 | 88034.45 | 73.36% | Over Budget | Yes | Timing of contract labor and material | 500000 | 588034.45 | 500000 | 0 | 0% | On Budget | -88034.45
FPC-2829: Highland City +/- 100 MVAR Static VAR compensator (SVC) | FPC - Sarah K. Seckinger: Sarah | 49280.87 | 0 | 49280.87 | 100% | Over Budget | Yes | Part of the SVC contractual price was tools. Original thought was they could go in a special ferc account. After actual cost for the tools from ABB was determined, accounting decided to spread the cost back against the asset. | 60000 | 49280.87 | 0 | 60000 | 100% | Over Budget | 10719.13
FPC-2830: TRANSMISSION BREAKER REPLACEMENT | FPC - Sarah K. Seckinger: Sarah | 0 | 0 | 0 | 0% | On Budget | No |  | 533000 | 533000 | 533000 | 0 | 0% | On Budget | 0
FPC-2835: TRANSMISSION CIP COMPLIANCE | FPC - Sarah K. Seckinger: Sarah | 63435.16 | 243482 | -180046.84 | -73.95% | Under Budget | Yes | Timing of budget spreads from SCS | 911250 | 731203.16 | 911250 | 0 | 0% | On Budget | 180046.84
FPC-2836: Transmission Cyber and Physical Security (NON-CIP) | FPC - Sarah K. Seckinger: Sarah | 130099.94 | 296250 | -166150.06 | -56.08% | Under Budget | Yes | Timing of budget spreads from SCS | 1295000 | 1128849.94 | 1295000 | 0 | 0% | On Budget | 166150.06
FPC-2841: GUYED Y TOWER ANCHOR REPLACEMENTS | FPC - Sarah K. Seckinger: Sarah | 778659.42 | 340000 | 438659.42 | 129% | Over Budget | Yes | work started earlier than originally planned | 1000000 | 1438659.42 | 1000000 | 0 | 0% | On Budget | -438659.42
FPC-2867: HOLMES CREEK - HIGHLAND CITY 230KV | FPC - Sarah K. Seckinger: Sarah | -11320.97 | 0 | -11320.97 | -100% | Under Budget | Yes | Accrual reversal from December - actuals booked to different workorder | -11321 | -11320.97 | 0 | -11321 | -100% | Under Budget | -0.03
FPC-2868: Survey and Renewal of Transmission Corridor Leases | FPC - Sarah K. Seckinger: Sarah | 28834.62 | 0 | 28834.62 | 100% | Over Budget | Yes | Timing | 538000 | 566834.62 | 538000 | 0 | 0% | On Budget | -28834.62
FPC-2881: BARRY-CRIST 230 KV UPGRADE | FPC - Sarah K. Seckinger: Sarah | 0 | 65000 | -65000 | -100% | Under Budget | Yes | Timing, design estimated to start in May | 188500 | 123500 | 188500 | 0 | 0% | On Budget | 65000
FPC-2901: Crist 115kV Substation Reliability Upgrade | FPC - Sarah K. Seckinger: Sarah | 1507764.77 | 430400 | 1077364.77 | 250.3% | Over Budget | Yes | Timing of bugeted materials | 1917000 | 2994364.77 | 1917000 | 0 | 0% | On Budget | -1077364.77 | -1100000 | -122222 | -1099998 | -977776 | -122224 | -1100000
FPC-2905: SMITH CONSTRUCTION | FPC - Sarah K. Seckinger: Sarah | 2264.61 | 0 | 2264.61 | 100% | Over Budget | No |  | 2265 | 2264.61 | 0 | 2265 | 100% | Over Budget | 0.39
FPC-2906: 115KV LINE RATING INCREASE | FPC - Sarah K. Seckinger: Sarah | 9181.19 | 10000 | -818.81 | -8.188% | Under Budget | No |  | 616000 | 615181.19 | 616000 | 0 | 0% | On Budget | 818.81
FPC-2908: Fiber Replacements | FPC - Sarah K. Seckinger: Sarah | 345459.11 | 364500 | -19040.89 | -5.224% | Under Budget | No |  | 1062256 | 1043215.11 | 1062256 | 0 | 0% | On Budget | 19040.89
FPC-2911: SCS Design - Autodesk | FPC - Sarah K. Seckinger: Sarah | 30002.74 | 45156 | -15153.26 | -33.56% | Under Budget | Yes | Timing from SCS | 189679 | 174525.74 | 189679 | 0 | 0% | On Budget | 15153.26
FPC-2912: Solar | FPC - Sarah K. Seckinger: Sarah | -429629.57 | -275000 | -154629.57 | -100% | Under Budget | Yes | Billing did not occur in 2015 as originally budgeted | -200500 | -355129.57 | -200500 | 0 | -100% | On Budget | 154629.57
FPC-2914: FPC-2914 | FPC - Sarah K. Seckinger: Sarah | 14915.02 | 0 | 14915.02 | 100% | Over Budget | Yes | Additional Bay County charges | 15000 | 14915.02 | 0 | 15000 | 100% | Over Budget | 84.98
FPC-2915: Smith 230-115kV P&C Reliability | FPC - Sarah K. Seckinger: Sarah | 0 | 0 | 0 | 0% | On Budget | No |  | 70000 | 70000 | 70000 | 0 | 0% | On Budget | 0
FPC-3401: DIST SUB INFRASTRUCTURE PROJECTS | FPC - Sarah K. Seckinger: Sarah | 245688.11 | 231600 | 14088.11 | 6.083% | Over Budget | No |  | 1000000 | 1014088.11 | 1000000 | 0 | 0% | On Budget | -14088.11
FPC-3420: DESTIN 115 12KV RELIABILITY UPGRADE | FPC - Sarah K. Seckinger: Sarah | 31674.88 | 0 | 31674.88 | 100% | Over Budget | Yes | Timing | 1850384 | 1882058.88 | 1850384 | 0 | 0% | On Budget | -31674.88 | -31558 | -3506 | -31554 | -28048 | -3510 | -31558
FPC-3421: Munson Rd Substation Conversion | FPC - Sarah K. Seckinger: Sarah | 11104.44 | 40000 | -28895.56 | -72.24% | Under Budget | Yes | Timing | 2790500 | 2761604.44 | 2790500 | 0 | 0% | On Budget | 28895.56
FPC-3428: PROACTIVE TRANSFORMER REPLACEMENT | FPC - Sarah K. Seckinger: Sarah | 4975.67 | 0 | 4975.67 | 100% | Over Budget | No |  | 4976 | 4975.67 | 0 | 4976 | 100% | Over Budget | 0.33
FPC-3434: ANTOIOCH NEW SUBSTATION | FPC - Sarah K. Seckinger: Sarah | 2168359.76 | 1444000 | 724359.76 | 50.16% | Over Budget | Yes | Project started earlier to meet the summer need date | 2385000 | 3109359.76 | 2385000 | 0 | 0% | On Budget | -724359.76
FPC-3437: HURLBURT 115/12KV SUBSTATION P & C INFRASTRUCTURE UPGRADE | FPC - Sarah K. Seckinger: Sarah | 387327 | 0 | 387327 | 100% | Over Budget | Yes | Timing | 850000 | 1237327 | 850000 | 0 | 0% | On Budget | -387327
FPC-3490: DEVILLERS LOWSIDE BUS STRUCTURE REBUILD | FPC - Sarah K. Seckinger: Sarah | 343.89 | 0 | 343.89 | 100% | Over Budget | No |  | 344 | 343.89 | 0 | 344 | 100% | Over Budget | 0.11
FPC-3494: PACE 115/12KV SUBSTATION P & C INFRASTRUCTURE UPGRADE | FPC - Sarah K. Seckinger: Sarah | 0 | 0 | 0 | 0% | On Budget | No |  | 125000 | 125000 | 125000 | 0 | 0% | On Budget | 0
FPC-3702: CIRCUIT SWITCHER IMP - TS/DS | FPC - Sarah K. Seckinger: Sarah | 0 | 0 | 0 | 0% | On Budget | No |  | 350000 | 350000 | 350000 | 0 | 0% | On Budget | 0
FPC-3714: P&C INFRASTRUCTURE PROJECTS | FPC - Sarah K. Seckinger: Sarah | 241682.27 | 20000 | 221682.27 | 1108% | Over Budget | Yes | Sinai (3 relays - impending failures (service bulletin), ValP and Eastbay work from last year finished up this year | 100000 | 321682.27 | 100000 | 0 | 0% | On Budget | -221682.27
FPC-3735: Ponce and Carryville Conversion to 115kV | FPC - Sarah K. Seckinger: Sarah | 2606.41 | 0 | 2606.41 | 100% | Over Budget | No |  | 2606 | 2606.41 | 0 | 2606 | 100% | Over Budget | -0.41
FPC-3742: System Operations Additions and Improvements | FPC - Sarah K. Seckinger: Sarah | 3577.22 | 12280 | -8702.78 | -70.87% | Under Budget | No |  | 172280 | 163577.22 | 172280 | 0 | 0% | On Budget | 8702.78
FPC-4395: TCC Furniture | FPC - Sarah K. Seckinger: Sarah | 0 | 200000 | -200000 | -100% | Under Budget | Yes | Holding under run and Facilities will be over | 0 | 0 | 200000 | -200000 | -100% | Under Budget | 0
FPC-4400: TRANSMISSION TOOLS AND TEST EQUIPMENT | FPC - Sarah K. Seckinger: Sarah | 1753.58 | 114400 | -112646.42 | -98.47% | Under Budget | Yes | Timing with budget spreads | 150000 | 37353.58 | 150000 | 0 | 0% | On Budget | 112646.42
Sub-Total Transmission |  | 7699522.37 | 5242068 | 2457454.37 | 46.88% | Over Budget |  |  | 22782219 | 25255803.37 | 22798349 | -16130 | -0.07075% | Under Budget | -2473584.37
Distribution
FPC-3402: MISC OVERHEAD LINE IMPROVEMENTS | FPC - Paul C. Pratofiorito: Paul | 1144599.32 | 1474000 | -329400.68 | -22.35% | Under Budget | Yes | Timing: Early in the year. Plan to be on Budget at year-end. | 5746000 | 5416599.32 | 5746000 | 0 | 0% | On Budget | 329400.68
FPC-3403: DISTRIBUTION ADDITIONS/RETIREMENTS DUE TO HWY & JOINT USE | FPC - Paul C. Pratofiorito: Paul | 555754.48 | 251000 | 304754.48 | 121.4% | Over Budget | Yes | Budget Exception Request: Increased $402k due to DOT's volume change occuring from their new design build requirements. | 1484000 | 1386754.48 | 1082000 | 402000 | 37.15% | Over Budget | 97245.52
FPC-3404: DISTRIBUTION LINE MINOR PROJECTS | FPC - Paul C. Pratofiorito: Paul | 210452.97 | 191000 | 19452.97 | 10.18% | Over Budget | Yes | Timing: Plan to be on budget at year end. | 746000 | 1065452.97 | 1046000 | -300000 | -28.68% | Under Budget | -319452.97
FPC-3405: UNDERGROUND SYSTEM ADDITIONS & IMPROVEMENTS | FPC - Paul C. Pratofiorito: Paul | 811585.95 | 312000 | 499585.95 | 160.1% | Over Budget | Yes | District Projects to replace failed cables and abnormal UG situations. Will be over-budget at Year-End. Project & Technical Servcies to work with Districts to prioritize. | 3200000 | 2975585.95 | 2476000 | 724000 | 29.24% | Over Budget | 224414.05
FPC-3406: DISTRIBUTION UNDERGROUND CONVERSIONS | FPC - Paul C. Pratofiorito: Paul | 116297.2 | 194000 | -77702.8 | -40.05% | Under Budget | Yes | Timing: Plan to be on budget at year-end. | 774000 | 696297.2 | 774000 | 0 | 0% | On Budget | 77702.8
FPC-3407: MISC CAPITAL ACCRUALS | FPC - Paul C. Pratofiorito: Paul | 50954.62 | 0 | 50954.62 | 100% | Over Budget | Yes | This blanket order PE 3407 was set up exclusively to capture monthly entries for Accounts Payable setups and reversals (SOX). Any variance is a timing difference of Accruals setup the previous month. | 0 | 50954.62 | 0 | 0 | -100% | On Budget | -50954.62
FPC-3408: OVERHEAD LINE IMPROVEMENTS - POLE INSPECTION PROGRAM | FPC - Paul C. Pratofiorito: Paul | 240804.83 | 404000 | -163195.17 | -40.39% | Under Budget | Yes | Timing: Early in the year. Pole replacements will ramp up. | 1806000 | 1642804.83 | 1806000 | 0 | 0% | On Budget | 163195.17
FPC-3409: RIGHT OF WAY ACQUISITION | FPC - Paul C. Pratofiorito: Paul | 0 | 177000 | -177000 | -100% | Under Budget | Yes | Timing. Feeders have been chosen. Work to begin on feeder out of Jay Road to Hospital. Plan to be on budget at year end. | 708000 | 531000 | 708000 | 0 | 0% | On Budget | 177000
FPC-3438: NEW DISTRIBUTION FEEDER FOR SUBMARINE CABLE CROSSING | FPC - Paul C. Pratofiorito: Paul | 37951.95 | 0 | 37951.95 | 100% | Over Budget | Yes | Carryover from 2015, plus seagrass mitigation survey, plan, and application requirements. | 55000 | 37951.95 | 0 | 55000 | 100% | Over Budget | 17048.05
FPC-3498: DSCADA MANAGEMENT SYSTEMS - DSCADA | FPC - Paul C. Pratofiorito: Paul | 1727.77 | 0 | 1727.77 | 100% | Over Budget | No |  | 340000 | 1727.77 | 0 | 340000 | 100% | Over Budget | 338272.23
FPC-3499: SO SMART RELIABILITY IMPROVEMENT PROGRAMS | FPC - Paul C. Pratofiorito: Paul | 97946.54 | 373000 | -275053.46 | -73.74% | Under Budget | Yes | Timing | 2043000 | 1767946.54 | 2043000 | 0 | 0% | On Budget | 275053.46
FPC-3500: ASSET MANAGEMENT IMPROVEMENT PROGRAMS | FPC - Paul C. Pratofiorito: Paul | 104531.7 | 403000 | -298468.3 | -74.06% | Under Budget | Yes | Timing | 353000 | 1140531.7 | 1439000 | -1086000 | -75.47% | Under Budget | -787531.7
FPC-3501: MISC DISTRIBUTION LINES SPECIFIC FEEDER IMPROVEMENTS | FPC - Paul C. Pratofiorito: Paul | 86765.68 | 15000 | 71765.68 | 478.4% | Over Budget | Yes | Reduced $250k Fund PE 4304 Addl and $228k new General Plant. | 235000 | 736765.68 | 665000 | -430000 | -64.66% | Under Budget | -501765.68
FPC-3502: MISC DISTRIBUTION SUBSTATION FEEDER RECONFIGURATIONS & UPGRA | FPC - Paul C. Pratofiorito: Paul | 8008.32 | 47000 | -38991.68 | -82.96% | Under Budget | Yes | Reduced to cover overage in PE 3438. Reduced $62 new General Plant. | 57000 | 153008.32 | 192000 | -135000 | -70.31% | Under Budget | -96008.32
FPC-3520: ANTIOCH ROAD SUB NEW FEEDERS | FPC - Paul C. Pratofiorito: Paul | 40373.64 | 200000 | -159626.36 | -79.81% | Under Budget | Yes | Timing. Plan to come under budget $40k at year-end. | 360000 | 240373.64 | 400000 | -40000 | -10% | Under Budget | 119626.36
FPC-3534: EAST BAY 5542 RECONDUCTOR | FPC - Paul C. Pratofiorito: Paul | 0 | 150000 | -150000 | -100% | Under Budget | Yes | Timing. Start in late April. | 350000 | 200000 | 350000 | 0 | 0% | On Budget | 150000
FPC-3539: HATHAWAY 8682 - GRAND LAGOON BRIDGE CROSSING | FPC - Paul C. Pratofiorito: Paul | 0 | 600000 | -600000 | -100% | Under Budget | Yes | Timing - Bay County permit received on March 8th. Presently working on Environmental permit. | 700000 | 100000 | 700000 | 0 | 0% | On Budget | 600000 | 600000 | 66667 | 600003 | 533336 | 66664 | 600000
FPC-3637: SANTA ROSA ISLAND ENHANCEMENTS | FPC - Paul C. Pratofiorito: Paul | 0 | 729000 | -729000 | -100% | Under Budget | Yes | Timing, Expect to be on budget by year end | 972000 | 243000 | 972000 | 0 | 0% | On Budget | 729000 | 700000 | 77778 | 700002 | 622224 | 77776 | 700000
FPC-3652: STORM HARDENING - OVERHEAD | FPC - Paul C. Pratofiorito: Paul | 224836.64 | 222000 | 2836.64 | 1.278% | Over Budget | No |  | 1148000 | 1150836.64 | 1148000 | 0 | 0% | On Budget | -2836.64
FPC-3693: DEVILLIERS SUB - NETWORK UPGRADES | FPC - Paul C. Pratofiorito: Paul | 49222.38 | 0 | 49222.38 | 100% | Over Budget | Yes | Timing. Ahead of schedule. Expect to be on budget at year-end. | 125000 | 174222.38 | 125000 | 0 | 0% | On Budget | -49222.38
FPC-3694: Crystal Beach Feeder 8982 Reconductor | FPC - Paul C. Pratofiorito: Paul | 0 | 185000 | -185000 | -100% | Under Budget | Yes | Timing - Waiting on Customer to decide on conversion. | 185000 | 0 | 185000 | 0 | 0% | On Budget | 185000
FPC-3695: Beulah Feeder 5512 & 5522 Reconductor and Reconfiguration | FPC - Paul C. Pratofiorito: Paul | 86517.81 | 150000 | -63482.19 | -42.32% | Under Budget | Yes | Timing. | 150000 | 86517.81 | 150000 | 0 | 0% | On Budget | 63482.19
FPC-3700: SYSTEM REACTIVE CORRECTIVE CAPACITY | FPC - Paul C. Pratofiorito: Paul | 649270.47 | 229000 | 420270.47 | 183.5% | Over Budget | Yes | Ahead of Schedule to upgrade DCC’s capacitor bank Comverge control paging system, in conjunction with Marketing’s Energy Select Comverge control paging system was retired April 1st. | 1434000 | 1854270.47 | 1434000 | 0 | 0% | On Budget | -420270.47
FPC-4301: TOOLS IMPLEMENTS AND TEST EQUIP. | FPC - Paul C. Pratofiorito: Paul | 42903.47 | 47000 | -4096.53 | -8.716% | Under Budget | No |  | 390000 | 385903.47 | 390000 | 0 | 0% | On Budget | 4096.53
FPC-4308: POWER DELIVERY TECHNOLOGY IMPROVEMENTS | FPC - Paul C. Pratofiorito: Paul | 39431.84 | 34000 | 5431.84 | 15.98% | Over Budget | No |  | 350000 | 355431.84 | 350000 | 0 | 0% | On Budget | -5431.84
FPC-4392: HR - Training Yard Purchases | FPC - Paul C. Pratofiorito: Paul | 26251.66 | 50000 | -23748.34 | -47.5% | Under Budget | Yes | Timing. Transmission additions to the Training Yard for the new Transmission assessments. New sec capacitor ($10k)is planned as well as new switchgear ($100k) | 196000 | 172251.66 | 196000 | 0 | 0% | On Budget | 23748.34
FPC-4408: Cyber Security | FPC - Paul C. Pratofiorito: Paul | 15320.54 | 26000 | -10679.46 | -41.07% | Under Budget | Yes | Revised projection is $215k. $67k in SCS charges, and $133k in shared cost from APCO "system" improvements with the Lancope installation | 215000 | 93320.54 | 104000 | 111000 | 106.7% | Over Budget | 121679.46
FPC-4412: DSCADA MANAGEMENT SYSTEMS | FPC - Paul C. Pratofiorito: Paul | 5348.5 | 154000 | -148651.5 | -96.53% | Under Budget | Yes | Timing: Early in the year, 1st PO issued @ $140k after Tax/Stores. TCMS is being funding through PE 3498. New Forecast of costing expected with may reporting. | 499000 | 490348.5 | 639000 | -140000 | -21.91% | Under Budget | 8651.5
FPC-4413: PINE FOREST OFFICE ROADWAY CONSTRUCTION | FPC - Paul C. Pratofiorito: Paul | 0 | 0 | 0 | 0% | On Budget | No |  | 2000000 | 2000000 | 2000000 | 0 | 0% | On Budget | 0
Sub-Total Distribution |  | 4646858.28 | 6617000 | -1970141.72 | -29.77% | Under Budget | Yes |  | 26621000 | 25149858.28 | 27120000 | -499000 | -1.84% | Under Budget | 1471141.72
Sub-Total Power Delivery |  | 19114816.28 | 20763616 | -1648799.72 | -7.941% | Under Budget |  |  | 84439954 | 83523665.47 | 84910647 | -470693 | -0.5543% | Under Budget | 916288.53
General Plant
Transportation
FPC-4304: AUTOMOBILES AUTO TRUCKS & EQUIP. | FPC - Allison R. Gillespie: Allison | 60911.39 | 463000 | -402088.61 | -86.84% | Under Budget | Yes | Timing. Early in the year. In addition, there is a $33k increase per truck for AWD projected. Addl $250k funded out of PE 3501. | 3559000 | 3217821.39 | 3309000 | 250000 | 7.555% | Over Budget | 341178.61
Sub-Total Transportation |  | 60911.39 | 463000 | -402088.61 | -86.84% | Under Budget |  |  | 3559000 | 3217821.39 | 3309000 | 250000 | 7.555% | Over Budget | 341178.61
Telecommunications/Mobile Systems/Data Network
FPC-4305: TELECOMMUNICATIONS WIRELESS SYSTEM ADDITIONS/IMPROVEMENTS | FPC - Shonda L. Lee: Shonda | 0 | 48000 | -48000 | -100% | Under Budget | Yes | Project work has not started yet; dollars will cover work in 4311 | 41480 | 144000 | 192000 | -150520 | -78.4% | Under Budget | -102520
FPC-4310: VOICE & DATA CONVERGED NETWORK | FPC - Shonda L. Lee: Shonda | 59546.56 | 144000 | -84453.44 | -58.65% | Under Budget | Yes | Project work has just started; should catch up | 576000 | 491546.56 | 576000 | 0 | 0% | On Budget | 84453.44
FPC-4311: TRANSPORT NETWORK | FPC - Shonda L. Lee: Shonda | 19638.76 | 38400 | -18761.24 | -48.86% | Under Budget | Yes | Project work has not started yet | 768000 | 749238.76 | 768000 | 0 | 0% | On Budget | 18761.24
FPC-4385: FIELD COMPUTING | FPC - Shonda L. Lee: Shonda | 2017.98 | 72240 | -70222.02 | -97.21% | Under Budget | Yes | Project work has just started; additional dollars covered by 4310 | 295000 | 74257.98 | 144480 | 150520 | 104.2% | Over Budget | 220742.02
FPC-4386: CSS Data Integration Hub Architecture | FPC - David Oerting: Dave | 37435.9 | 31849 | 5586.9 | 17.54% | Over Budget | No |  | 127400 | 132986.9 | 127400 | 0 | 0% | On Budget | -5586.9
FPC-4410: Long Term Evolution (LTE) | FPC - Paul C. Pratofiorito: Paul | 108495.74 | 378000 | -269504.26 | -71.3% | Under Budget | Yes | Timing… On track per SCS who is coordinating this effort. | 1500000 | 1458195.74 | 1500000 | 0 | 0% | On Budget | 41804.26
FPC-4417: IT Cyber Security Software | FPC - Shonda L. Lee: Shonda | 28010.49 | 99999 | -71988.51 | -71.99% | Under Budget | Yes | Credit due to a double accrual in Dec; dollars will catch up | 400000 | 328011.49 | 400000 | 0 | 0% | On Budget | 71988.51
FPC-4486: On Line Customer Care | FPC - David Oerting: Dave | 139570.19 | 99960 | 39610.19 | 39.63% | Over Budget | Yes | Release 2 estimates coming in higher than expected | 400000 | 439610.19 | 400000 | 0 | 0% | On Budget | -39610.19
FPC-4586: Customer Kiosks | FPC - David Oerting: Dave | 0 | 500000 | -500000 | -100% | Under Budget | Yes | Contractual delays for purchase of kiosks | 500000 | 0 | 500000 | 0 | 0% | On Budget | 500000 | 500000 | 55556 | 500004 | 444448 | 55552 | 500000
Sub-Total Telecommunications/Mobile Systems/Data Network |  | 394715.62 | 1412448 | -1017732.38 | -72.05% | Under Budget |  |  | 4607880 | 3817847.62 | 4607880 | 0 | 0% | On Budget | 790032.38
Accounting
FPC-4376: Maximo/Oracle/Powerplant Upgrades | FPC - Carol Stevens: Carol | 81.19 | 29970 | -29888.81 | -99.73% | Under Budget | Yes | Timing - work moved to later in the year | 119924 | 90035.19 | 119924 | 0 | 0% | On Budget | 29888.81
Sub-Total Accounting |  | 81.19 | 29970 | -29888.81 | -99.73% | Under Budget |  |  | 119924 | 90035.19 | 119924 | 0 | 0% | On Budget | 29888.81
Corporate Services
FPC-4300: OFFICE FURNITURE & MECHANICAL EQUIP. | FPC - Corporate Services: Shirley | 191339.71 | 76500 | 114839.71 | 150.1% | Over Budget | Yes | System control renonvation. Offset in PE 439501 | 726143 | 439679.71 | 324840 | 401303 | 123.5% | Over Budget | 286463.29
FPC-4302: MISC. BUILDINGS LAND AND EQUIP. | FPC - Corporate Services: Shirley | 14813.36 | 120600 | -105786.64 | -87.72% | Under Budget | Yes | Timing | 758203 | 342043.36 | 447000 | 311203 | 69.62% | Over Budget | 416159.64 | 400000 | 44444 | 399996 | 355552 | 44448 | 400000
FPC-4303: SECURITY EQUIPMENT | FPC - Corporate Services: Shirley | 25763.4 | 11792 | 13971.4 | 118.5% | Over Budget | Yes | Timing | 219592 | 198563.4 | 184592 | 35000 | 18.96% | Over Budget | 21028.6 |  | 44536 |  |  | 44542
FPC-4306: AUDIO & VISUAL EQUIPMENT | FPC - Corporate Services: Shirley | 15053.01 | 0 | 15053.01 | 100% | Over Budget | Yes | Timing | 49680 | 64733.01 | 49680 | 0 | 0% | On Budget | -15053.01
FPC-4370: PRINTSHOP EQUIP | FPC - Corporate Services: Shirley | 0 | 24840 | -24840 | -100% | Under Budget | Yes | Timing | 24840 | 0 | 24840 | 0 | 0% | On Budget | 24840
FPC-4387: Defuniak Springs Roof | FPC - Corporate Services: Shirley | 54813.25 | 100000 | -45186.75 | -45.19% | Under Budget | Yes | Bid came in under budget | 54813 | 281813.25 | 327000 | -272187 | -83.24% | Under Budget | -227000.25 |  | -311111 |  |  | -311112
FPC-4398: PANAMA CITY VECHICLE MAINT FACILITY | FPC - Corporate Services: Shirley | 0 | 700000 | -700000 | -100% | Under Budget | Yes | Not approved. | 0 | 10000 | 3500000 | -3500000 | -100% | Under Budget | -10000 | -10000 | -1111 | -9999 | -8888 | -1112 | -10000
FPC-4399: PENS DISTRICT-CONSOL CUST SVC FACIL | FPC - Corporate Services: Shirley | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 819991 | 8200000 | -8200000 | -100% | Under Budget | -819991 | -819991 | -91110 | -819990 | -728880 | -91111 | -819991
FPC-4406: Panama City Admin Chiller | FPC - Corporate Services: Shirley | 135149.1 | 150000 | -14850.9 | -9.901% | Under Budget | No |  | 135149 | 135149.1 | 150000 | -14851 | -9.901% | Under Budget | -0.1
FPC-4407: GEN WHSE CONVERGE ROOF | FPC - Corporate Services: Shirley | 0 | 35000 | -35000 | -100% | Under Budget | Yes | Delayed due to contractor's schedule | 45000 | 37000 | 72000 | -27000 | -37.5% | Under Budget | 8000
FPC-4411: LAND PURCHASE IN CRESTVIEW | FPC - Corporate Services: Shirley | -665.46 | 0 | -665.46 | -100% | Under Budget | No |  | -665 | -665.46 | 0 | -665 | -100% | Under Budget | 0.46
Sub-Total Corporate Services |  | 436266.37 | 1218732 | -782465.63 | -64.2% | Under Budget |  |  | 2012755 | 2328307.37 | 13279952 | -11267197 | -84.84% | Under Budget | -315552.37
T&D Warehouse Equipment Replacement
FPC-4344: T&D WAREHOUSE EQUIPMENT REPLACEMENT | FPC - Beverly D. Day: Beverly | 0 | 73500 | -73500 | -100% | Under Budget | Yes | $100,000 to offset the expediture for the General Warehouse renovation by Corporate Real Estate | 47000 | 73500 | 147000 | -100000 | -68.03% | Under Budget | -26500
Sub-Total T&D Warehouse Equipment Replacement |  | 0 | 73500 | -73500 | -100% | Under Budget |  |  | 47000 | 73500 | 147000 | -100000 | -68.03% | Under Budget | -26500
Sub-Total General Plant |  | 891974.57 | 3197650 | -2305675.43 | -72.11% | Under Budget |  |  | 10346559 | 9527511.57 | 21463756 | -11117197 | -51.8% | Under Budget | 819047.43
Non-Utility
Non-Utility
FPC-4999: NEW PRODUCTS AND SERVICES | FPC - Sarah K. Seckinger: Sarah | 50805.96 | 13301 | 37504.96 | 282% | Over Budget | Yes | Timing | 494664 | 532168.96 | 494664 | 0 | 0% | On Budget | -37504.96
Sub-Total Non-Utility |  | 50805.96 | 13301 | 37504.96 | 282% | Over Budget |  |  | 494664 | 532168.96 | 494664 | 0 | 0% | On Budget | -37504.96
Sub-Total Non-Utility |  | 50805.96 | 13301 | 37504.96 | 282% | Over Budget |  |  | 494664 | 532168.96 | 494664 | 0 | 0% | On Budget | -37504.96
Uncategorized
Uncategorized
FPC-4785: FPC-4785 | FPC - David Oerting: Dave | 340519.08 | 0 | 340519.08 | 100% | Over Budget |  |  | 340519.08 | 340519.08 | 0 | 340519.08 | 100% | Over Budget | 0
FPC-4790: FPC-4790 | FPC - David Oerting: Dave | 41034.95 | 0 | 41034.95 | 100% | Over Budget |  |  | 41034.95 | 41034.95 | 0 | 41034.95 | 100% | Over Budget | 0
Sub-Total Uncategorized |  | 381554.03 | 0 | 381554.03 | 100% | Over Budget |  |  | 381554.03 | 381554.03 | 0 | 381554.03 | 100% | Over Budget | 0
Sub-Total Uncategorized |  | 381554.03 | 0 | 381554.03 | 100% | Over Budget |  |  | 381554.03 | 381554.03 | 0 | 381554.03 | 100% | Over Budget | 0
Total |  | 33533295.52 | 42631345 | -9098049.48 | -21.34% | Under Budget |  |  | 199098675.03 | 192385223.71 | 215416458 | -16317782.97 | -7.575% | Under Budget | 6713451.32 | 6713451
| Sch 73 | 33482489.56 | 42631345 | YTD 2016 Approved Capital Budget
| Non-Utility Reconciling item | 50805.96 | 0
| Adjusted Total | 33533295.52 | 42631345
| Above - per UI | 33533295.52 | 42631345
| Difference | 0 | 0

## CAPEX_variance summary
CAPEX by Bus Unit / BU Detail / PE: Admin lock | PE -> Budget Contact | a-YTD-Mar - 2016 | [6 empty] | 2016
|  | CF Gulf - 2016 Official Budget - Live Reforecast | (VID:20160325) CF Gulf - 2016 Official Budget (Preserved) | Dif. (VID:20160325) CF Gulf - 2016 Official Budget (Preserved) | % Dif. (VID:20160325) CF Gulf - 2016 Official Budget (Preserved) |  |  |  |  | CF Gulf - 2016 Official Budget - Live Reforecast | (VID:20160325) CF Gulf - 2016 Official Budget (Preserved) | Dif. (VID:20160325) CF Gulf - 2016 Official Budget (Preserved) | % Dif. (VID:20160325) CF Gulf - 2016 Official Budget (Preserved)
2016-03-01 | Pointer to Budget Contact | YTD Actual | YTD Budget | YTD Variance ($) | YTD Variance (%) | YTD Over/Under Budget | Explanation Required? | YTD Explanation | Year-End Projection | Year-End Calculated | Original Budget | Year-End Variance ($) | Year-End Variance (%) | Year-End Over/Under Budget | YE Projection - YE Calculated
Power Generation
Co Generation
FPC-0040: Co-Generation Misc Projects | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 1500000 | 1500000 | 1500000 | 0 | 0% | On Budget | 0
Sub-Total Co Generation |  | 0 | 0 | 0 | 0% | On Budget |  |  | 1500000 | 1500000 | 1500000 | 0 | 0% | On Budget | 0
Environmental Cost Recovery Clause
FPC-0404: FPC-0404 | FPC - Vicki L. Mack: Vicki | 46599.56 | 0 | 46599.56 | 100% | Over Budget | Yes | 2015 Carryover | 346 | 46599.56 | 0 | 346 | 100% | Over Budget | -46253.56
FPC-0406: ECRC - LAND - SMITH CCR WASTE WATER MANAGEMENT | FPC - Vicki L. Mack: Vicki | 0 | 933750 | -933750 | -100% | Under Budget | Yes | Duplicate project. PE 1641 | 0 | 2728 | 3750000 | -3750000 | -100% | Under Budget | -2728
FPC-0412: ECRC-SMITH DUST MITIGATION WATER TRUCK | FPC - Vicki L. Mack: Vicki | 148937.5 | 100000 | 48937.5 | 48.94% | Over Budget | Yes | Projected project overrun to be absorbed by PE 1600 | 150000 | 148937.5 | 100000 | 50000 | 50% | Over Budget | 1062.5
FPC-0514: ECRC Daniel -Water -Ground Water Well | FPC - Vicki L. Mack: Vicki | 1454.53 | 0 | 1454.53 | 100% | Over Budget | No |  | 1455 | 1454.53 | 0 | 1455 | 100% | Over Budget | 0.47
FPC-1031: ECRC-AIR-CRIST 7 SCR CATALYST REPLACEMENT | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 894961 | 894961 | 894961 | 0 | 0% | On Budget | 0
FPC-1060: ECRC-AIR-CRIST 7 FGAS MONITORS | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 46000 | 46000 | 46000 | 0 | 0% | On Budget | 0
FPC-1158: ECRC-AIR-CRIST 7 SCR MISC | FPC - Vicki L. Mack: Vicki | 1071.82 | 0 | 1071.82 | 100% | Over Budget | No |  | 1072 | 1071.82 | 0 | 1072 | 100% | Over Budget | 0.18
FPC-1193: ECRC-WATER-CRIST 4-7 LOW VOLUME WASTE WATER TREATMENT | FPC - Vicki L. Mack: Vicki | 21894.51 | 752400 | -730505.49 | -97.09% | Under Budget | Yes | Will be done later in year | 3009600 | 2279094.51 | 3009600 | 0 | 0% | On Budget | 730505.49 | 700000
FPC-1199: ECRC-AIR-CRIST U7 SCR PRECIP RELOCAT | FPC - Vicki L. Mack: Vicki | 262.96 | 6250 | -5987.04 | -95.79% | Under Budget | No |  | 25000 | 19012.96 | 25000 | 0 | 0% | On Budget | 5987.04
FPC-1222: ECRC-AIR-CRIST - SCRUBBER | FPC - Vicki L. Mack: Vicki | 773098.99 | 125000 | 648098.99 | 518.5% | Over Budget | Yes | Add PE 1233 prior year carryover. Not anticipated some projects needed earlier in year | 5573250 | 6221348.99 | 5573250 | 0 | 0% | On Budget | -648098.99 | -650000
FPC-1233: ECRC-AIR-CRIST SCRUBBER MISCELLANEOUS | FPC - Vicki L. Mack: Vicki | 387925.97 | 0 | 387925.97 | 100% | Over Budget | Yes | Carryover | 387926 | 387925.97 | 0 | 387926 | 100% | Over Budget | 0.03
FPC-1234: ECRC-AIR-CRIST U7 LOW NOX BURNER REPLACEMENT | FPC - Vicki L. Mack: Vicki | 70968.55 | 0 | 70968.55 | 100% | Over Budget | Yes | Carryover | 70969 | 70968.55 | 0 | 70969 | 100% | Over Budget | 0.45
FPC-1279: ECRC-AIR-CRIST U6 CONTROLS - SCR & ID FANS | FPC - Vicki L. Mack: Vicki | 0 | 2750 | -2750 | -100% | Under Budget | No |  | 11000 | 8250 | 11000 | 0 | 0% | On Budget | 2750
FPC-1287: ECRC-AIR-CRIST 4-6 NOX REDUCTION - DEPR - (SNCR) | FPC - Vicki L. Mack: Vicki | 196129.93 | 646126 | -449996.07 | -69.65% | Under Budget | Yes | Money spent on flame scanners in 2015 | 655500 | 205503.93 | 655500 | 0 | 0% | On Budget | 449996.07 | 450000
FPC-1288: ECRC-AIR-CRIST-CONSTRUCT GYPSUM STORAGE CELL NO. 1 | FPC - Vicki L. Mack: Vicki | 45812.78 | 151200 | -105387.22 | -69.7% | Under Budget | Yes | Project starting later than expected | 1681246 | 1575858.78 | 1681246 | 0 | 0% | On Budget | 105387.22
FPC-1517: ECRC - AIR- DANIEL BROMINE INJECTION | FPC - Vicki L. Mack: Vicki | -28962.62 | 0 | -28962.62 | -100% | Under Budget | Yes | Carry over credits from A&G ECRC | -28963 | -28962.62 | 0 | -28963 | -100% | Under Budget | -0.38
FPC-1551: ECRC-AIR-DANIEL 1 & 2 SCRUBBER | FPC - Vicki L. Mack: Vicki | 1477529.48 | 2400795 | -923265.52 | -38.46% | Under Budget | Yes | Credits from contract close outs and asset recovery. Credits transferred from A&G | 3095703 | 2393357.48 | 3095703 | 0 | 0% | On Budget | 702345.52 | 700000
FPC-1601: ECRC-WATER-SMITH RECLAIMED WATER PROJECT UNIT 3 | FPC - Vicki L. Mack: Vicki | 457961.86 | 340807 | 117154.86 | 34.38% | Over Budget | Yes | Projected project overrun to be absorbed by ECRC underruns | 500000 | 695233.86 | 340807 | 159193 | 46.71% | Over Budget | -195233.86
FPC-1641: ECRC - Smith 1 & 2 Cross Media Retrofit | FPC - Vicki L. Mack: Vicki | 0 | 933750 | -933750 | -100% | Under Budget | Yes | Project has not started | 3750000 | 3069886 | 3750000 | 0 | 0% | On Budget | 680114 | 700000
FPC-1809: ECRC -AIR-DANIEL 1 & 2 ACTIVATED CARBON INJECTION C01767 | FPC - Vicki L. Mack: Vicki | -17507.72 | 782117 | -799624.72 | -102.2% | Under Budget | Yes | Accruals in December - Planned scope pushed out to later months | 782117 | 350674.28 | 782117 | 0 | 0% | On Budget | 431442.72 | 450000
FPC-1909: ECRC-AIR-CIRST MISC SCR COMMON | FPC - Vicki L. Mack: Vicki | 30304.99 | 12498 | 17806.99 | 142.5% | Over Budget | Yes | Project started earlier than anticipted | 50000 | 67806.99 | 50000 | 0 | 0% | On Budget | -17806.99
FPC-1912: ECRC-AIR-CRIST U4-7 DRY BOTTOM ASH | FPC - Vicki L. Mack: Vicki | 0 | 625002 | -625002 | -100% | Under Budget | Yes | Environmental Affairs Project- Checking to see if gets done | 2500000 | -1 | 2500000 | 0 | 0% | On Budget | 2500001 | 2500000
FPC-1997: ECRC-LAND-CRIST DISPOSAL OF COAL COMBUSTION RESIDUALS (CCR) | FPC - Vicki L. Mack: Vicki | 68897.94 | 0 | 68897.94 | 100% | Over Budget | Yes | Carryover | 68898 | 68897.94 | 0 | 68898 | 100% | Over Budget | 0.06
Sub-Total Environmental Cost Recovery Clause |  | 3682381.03 | 7812445 | -4130063.97 | -52.87% | Under Budget |  |  | 23226080 | 18526609.03 | 26265184 | -3039104 | -11.57% | Under Budget | 4699470.97
Environmental (Non-Clause)
FPC-0501: Envir Daniel Unit 1 Pyrite Hoppers/Piping Valves | FPC - Vicki L. Mack: Vicki | -876.41 | 0 | -876.41 | -100% | Under Budget | No |  | -1078 | -876.41 | 0 | -1078 | -100% | Under Budget | -201.59
FPC-1033: ENVIR - WASTE - CRIST FLY ASH LANDFILL STORAGE CELL CAPPING | FPC - Vicki L. Mack: Vicki | 0 | 131196 | -131196 | -100% | Under Budget | Yes | $500 K to offset PE 1220 Governor's Island Headwall | 0 | 393804 | 525000 | -525000 | -100% | Under Budget | -393804
FPC-1220: ENVIR-WATER-CRIST GOVERNORS ISLAND HEADWALL | FPC - Vicki L. Mack: Vicki | 2113971.53 | 0 | 2113971.53 | 100% | Over Budget | Yes | PE approval letter | 3255000 | 2113971.53 | 0 | 3255000 | 100% | Over Budget | 1141028.47 | 1150000
FPC-1253: ENVIR-WASTE- CRIST-FLY ASH LANDFILL STORAGE CELL DEVELOPMENT | FPC - Vicki L. Mack: Vicki | 42669.2 | 249900 | -207230.8 | -82.93% | Under Budget | Yes | Actuals are carryover. Budget dollars to be used to offset PE 1220 | 42669 | 2142769.2 | 1000000 | -957331 | -95.73% | Under Budget | -2100100.2 | -2100000
FPC-1613: ENVIR-WASTE-SMITH CAP ASH LANDFILL CELLS | FPC - Vicki L. Mack: Vicki | 114.37 | 0 | 114.37 | 100% | Over Budget | No |  | 114 | 114.37 | 0 | 114 | 100% | Over Budget | -0.37
FPC-1701: ENVIR - AIR - SCHERER 3 -MISC ENVIRONMENTAL PROJECTS | FPC - Vicki L. Mack: Vicki | 9714.6 | 25923 | -16208.4 | -62.53% | Under Budget | Yes | less misc Environmental projects needed in 1st quarter | 116935 | 87521.6 | 103730 | 13205 | 12.73% | Over Budget | 29413.4
FPC-1727: ENVIR-AIR-SCHERER SELECTIVE CAYALYTIC REDUCT (SCR) | FPC - Vicki L. Mack: Vicki | -26609.78 | 0 | -26609.78 | -100% | Under Budget | Yes | carryover | 22531 | -26609.78 | 0 | 22531 | 100% | Over Budget | 49140.78
FPC-1728: ENVIR-AIR-SCHERER SCRUBBER | FPC - Vicki L. Mack: Vicki | -262488.5 | 0 | -262488.5 | -100% | Under Budget | Yes | Carryover | -190251 | -262488.5 | 0 | -190251 | -100% | Under Budget | 72237.5
FPC-1729: FPC-1729 | FPC - Vicki L. Mack: Vicki | 37218.01 | 0 | 37218.01 | 100% | Over Budget | Yes | carrupver | -190251 | 37218.01 | 0 | -190251 | -100% | Under Budget | -227469.01
FPC-1755: ENVIR SCHERER-AIR-HG/PM CEMS | FPC - Vicki L. Mack: Vicki | 674.75 | 0 | 674.75 | 100% | Over Budget | No |  | 675 | 674.75 | 0 | 675 | 100% | Over Budget | 0.25
FPC-1762: ENVIR - Air- Scherer 3 Bromine Injection | FPC - Vicki L. Mack: Vicki | 0 | 279000 | -279000 | -100% | Under Budget | Yes | Project later getting started than anticipated | 1116000 | 837000 | 1116000 | 0 | 0% | On Budget | 279000
FPC-1778: ENVIR - SCHERER - ENVIRONMENTAL SITE PLAN | FPC - Vicki L. Mack: Vicki | -48965.78 | 0 | -48965.78 | -100% | Under Budget | Yes | Carryover credit from EC&S | -168070 | -48965.78 | 0 | -168070 | -100% | Under Budget | -119104.22
FPC-1791: FPC-1791 | FPC - Vicki L. Mack: Vicki | -20664.9 | 0 | -20664.9 | -100% | Under Budget | Yes | Carryover credit from EC&S | -20665 | -20664.9 | 0 | -20665 | -100% | Under Budget | -0.1
FPC-1798: ENVIR SCHERER 3 SCR CATALYST REPLACEMENT | FPC - Vicki L. Mack: Vicki | 0 | 170890 | -170890 | -100% | Under Budget | Yes | Project later getting started than anticipated | 341780 | 170890 | 341780 | 0 | 0% | On Budget | 170890
FPC-1878: Environ - Daniel 1 & 2 Dry Ash Equipment | FPC - Vicki L. Mack: Vicki | 25162.52 | 0 | 25162.52 | 100% | Over Budget | Yes | SCS charges related to Load testing, redline redraws and commissioning charges not included in OB | 32577 | 25162.52 | 0 | 32577 | 100% | Over Budget | 7414.48
FPC-6756: Envir - Scherer 3 -LAND CCR ASH MANAGEMENT | FPC - Vicki L. Mack: Vicki | 0 | 79395 | -79395 | -100% | Under Budget | Yes | Project later getting started than anticipated | 317500 | 260271 | 317576 | -76 | -0.02393% | Under Budget | 57229
FPC-6757: Envir - Scherer 3 New Landfill - Phase 1 | FPC - Vicki L. Mack: Vicki | 0 | 50007 | -50007 | -100% | Under Budget | Yes | Project later getting started than anticipated | 200000 | 150021 | 200028 | -28 | -0.014% | Under Budget | 49979
FPC-6759: Envir - Scherer - Land- CCR WW Management | FPC - Vicki L. Mack: Vicki | 0 | 39189 | -39189 | -100% | Under Budget | Yes | Project later getting started than anticipated | 156875 | 117567 | 156756 | 119 | 0.07591% | Over Budget | 39308
Sub-Total Environmental (Non-Clause) |  | 1869919.61 | 1025500 | 844419.61 | 82.34% | Over Budget |  |  | 5032341 | 5977379.61 | 3760870 | 1271471 | 33.81% | Over Budget | -945038.61
Plant Crist
FPC-0803: Crist U 7 BFP Controls Replacement | FPC - Vicki L. Mack: Vicki | 103533.35 | 0 | 103533.35 | 100% | Over Budget | Yes | Moved to beginning of year | 866250 | 969783.35 | 866250 | 0 | 0% | On Budget | -103533.35
FPC-0804: Crist Unit 7 BFPT Overspeed Bolt Replacement | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 890925 | 890925 | -890925 | -100% | Under Budget | -890925
FPC-0805: Crist U7 Main Turbine Overspeed Bolt Replacement | FPC - Vicki L. Mack: Vicki | 45530.24 | 0 | 45530.24 | 100% | Over Budget | Yes | Progress payment made earlier than expected | 1683675 | 838280.24 | 792750 | 890925 | 112.4% | Over Budget | 845394.76 | 850000
FPC-0806: Crist U6 BFPT Overspeed Bolt Replacement | FPC - Vicki L. Mack: Vicki | 45381.57 | 0 | 45381.57 | 100% | Over Budget | Yes | Material purchased earlier than expected | 280403 | 325784.57 | 280403 | 0 | 0% | On Budget | -45381.57
FPC-0807: Crist U6 Main Turbine Overspeed Bolt Replacement | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 334031 | 334031 | 334031 | 0 | 0% | On Budget | 0
FPC-0808: Crist U7 Airflow Transmitter (Kurz) Replacement | FPC - Vicki L. Mack: Vicki | 5678.32 | 187500 | -181821.68 | -96.97% | Under Budget | Yes | Project started later than budgeted | 399000 | 217178.32 | 399000 | 0 | 0% | On Budget | 181821.68
FPC-0809: Crist A Flyash Compressor | FPC - Vicki L. Mack: Vicki | 0 | 68880 | -68880 | -100% | Under Budget | Yes | Project starting later than budgeted | 68880 | 0 | 68880 | 0 | 0% | On Budget | 68880
FPC-0810: Crist B Flyash Compressor | FPC - Vicki L. Mack: Vicki | 0 | 68880 | -68880 | -100% | Under Budget | Yes | Project starting later than budgeted | 68880 | 0 | 68880 | 0 | 0% | On Budget | 68880
FPC-0812: Crist U4 Turbine Water Induction Protection (TWIP) | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 196925 | 1969250 | -1969250 | -100% | Under Budget | -196925
FPC-0813: Crist U5 Turbine Water Induction Protection (TWIP) | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 196925 | 1969250 | -1969250 | -100% | Under Budget | -196925
FPC-0816: Crist Common Replace Fencing (Security) | FPC - Vicki L. Mack: Vicki | 0 | 137000 | -137000 | -100% | Under Budget | Yes | Project will start later than budgeted | 550000 | 413000 | 550000 | 0 | 0% | On Budget | 137000
FPC-0817: Crist - Replace Units 6 & 7 Elevator | FPC - Vicki L. Mack: Vicki | 0 | 450000 | -450000 | -100% | Under Budget | Yes | Project will start later than budgeted | 1500000 | 1050000 | 1500000 | 0 | 0% | On Budget | 450000
FPC-1003: CRIST 7 BOTTOM ASH PIT TRASH HOPPER | FPC - Vicki L. Mack: Vicki | 0 | 7350 | -7350 | -100% | Under Budget | No |  | 157500 | 150150 | 157500 | 0 | 0% | On Budget | 7350
FPC-1027: CRIST 4 & 5 ASH CONTROLS | FPC - Vicki L. Mack: Vicki | 321.68 | 0 | 321.68 | 100% | Over Budget | No |  | 322 | 321.68 | 0 | 322 | 100% | Over Budget | 0.32
FPC-1041: CRIST 6C 4160 V BUS REPL BREAKERS | FPC - Vicki L. Mack: Vicki | 120401.9 | 40000 | 80401.9 | 201% | Over Budget | Yes | SCS drawings underestimated - other SCS work needed | 160000 | 120401.9 | 40000 | 120000 | 300% | Over Budget | 39598.1
FPC-1042: CRIST 7C 4160 VOLT BUS REPLACE BREAKERS | FPC - Vicki L. Mack: Vicki | 71433.83 | 30000 | 41433.83 | 138.1% | Over Budget | Yes | SCS drawings underestimated | 107000 | 81433.83 | 40000 | 67000 | 167.5% | Over Budget | 25566.17
FPC-1046: CRIST 4-7 SILO ASH MCC REPLACEMENT | FPC - Vicki L. Mack: Vicki | 35903.38 | 3165 | 32738.38 | 1034% | Over Budget | Yes | SCS charges started earlier than anticipated | 265650 | 298388.38 | 265650 | 0 | 0% | On Budget | -32738.38
FPC-1050: CRIST U5 575 VOLT BUS REPLACEMENT | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 15750 | 15750 | 15750 | 0 | 0% | On Budget | 0
FPC-1059: CRIST 5 -- 2300 VOLT BREAKERS | FPC - Vicki L. Mack: Vicki | 20770.38 | 0 | 20770.38 | 100% | Over Budget | Yes | Carryover | 20770 | 20770.38 | 0 | 20770 | 100% | Over Budget | -0.38
FPC-1081: CRIST U4 ASSET PROTECTION - PAG | FPC - Vicki L. Mack: Vicki | 140470.13 | 0 | 140470.13 | 100% | Over Budget | Yes | Scope increased. TWIP added | 2019250 | 1891470.13 | 50000 | 1969250 | 3938% | Over Budget | 127779.87
FPC-1089: CRIST 6 REPLACE ASH HOOPER | FPC - Vicki L. Mack: Vicki | 40.84 | 0 | 40.84 | 100% | Over Budget | No |  | 41 | 40.84 | 0 | 41 | 100% | Over Budget | 0.16
FPC-1091: CRIST 7 AIR HEATER BASKETS | FPC - Vicki L. Mack: Vicki | 1148796.25 | 0 | 1148796.25 | 100% | Over Budget | Yes | Scope increased. TWIP added | 2000000 | 3148796.25 | 2000000 | 0 | 0% | On Budget | -1148796.25 | -1150000
FPC-1093: CRIST U5 ASSET PROTECTION - PAG | FPC - Vicki L. Mack: Vicki | 146306.39 | 0 | 146306.39 | 100% | Over Budget | Yes | Scope increased. TWIP added | 2019250 | 1906306.39 | 50000 | 1969250 | 3938% | Over Budget | 112943.61
FPC-1096: CRIST U6 ASSET PROTECTION - PAG | FPC - Vicki L. Mack: Vicki | 35780.14 | 0 | 35780.14 | 100% | Over Budget | Yes | Scope increased. TWIP added | 140000 | 85780.14 | 50000 | 90000 | 180% | Over Budget | 54219.86
FPC-1097: CRIST U7 ASSET PROTECTION - PAG | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 50000 | 50000 | 50000 | 0 | 0% | On Budget | 0
FPC-1100: CRIST - MINOR MISC ADDITIONS | FPC - Vicki L. Mack: Vicki | 248489.63 | 187425 | 61064.63 | 32.58% | Over Budget | Yes | More minor miscellaneous jobs than budgeted | 1753393 | 1711064.63 | 750000 | 1003393 | 133.8% | Over Budget | 42328.37
FPC-1108: CRIST 7 FLY ASH CONTROLS | FPC - Vicki L. Mack: Vicki | 293.76 | 26250 | -25956.24 | -98.88% | Under Budget | Yes | Project started later than budgeted | 315000 | 289043.76 | 315000 | 0 | 0% | On Budget | 25956.24
FPC-1143: CRIST 5 MONITORING SYSTEM UPGRADES | FPC - Vicki L. Mack: Vicki | -1607.47 | 0 | -1607.47 | -100% | Under Budget | No |  | -1607 | -1607.47 | 0 | -1607 | -100% | Under Budget | 0.47
FPC-1144: CRIST 7 CONTROL SYSTEM UPGRADES | FPC - Vicki L. Mack: Vicki | 33554.58 | 0 | 33554.58 | 100% | Over Budget | Yes | SCS charges | 33555 | 33554.58 | 0 | 33555 | 100% | Over Budget | 0.42
FPC-1148: CRIST - MAJOR MISC ADDITIONS | FPC - Vicki L. Mack: Vicki | 474671.2 | 249900 | 224771.2 | 89.94% | Over Budget | Yes | More Major miscellaneous jobs needed than Budgeted | 2003394 | 2034771.2 | 1000000 | 1003394 | 100.3% | Over Budget | -31377.2
FPC-1151: CRIST CLEARWATER HDRS & PIPING | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 300300 | 300300 | 300300 | 0 | 0% | On Budget | 0
FPC-1176: CRIST U4 REPL BREAKERS CABLE & SWITCHES FOR ARC FLASH STUDY | FPC - Vicki L. Mack: Vicki | -10716.51 | 0 | -10716.51 | -100% | Under Budget | Yes | carryover | -10717 | -10716.51 | 0 | -10717 | -100% | Under Budget | -0.49
FPC-1210: CRIST CYBER SECURITY | FPC - Vicki L. Mack: Vicki | 0 | 36291 | -36291 | -100% | Under Budget | Yes | Project starting later than budgeted | 145217 | 108926 | 145217 | 0 | 0% | On Budget | 36291
FPC-1223: CRIST 7 BOTTOM ASH HOPPER | FPC - Vicki L. Mack: Vicki | 103736.78 | 2004193 | -1900456.22 | -94.82% | Under Budget | Yes | $1M to offset PE 1220 Governor's Island Headwall, Progress Pymt made in 2015. bid was lower | 5087295 | 5187890.78 | 8446528 | -3359233 | -39.77% | Under Budget | -100595.78
FPC-1254: CRIST COMMON -CONVEYOR BELTS REPLACEMENT | FPC - Vicki L. Mack: Vicki | 921.02 | 0 | 921.02 | 100% | Over Budget | No |  | 105000 | 105921.02 | 105000 | 0 | 0% | On Budget | -921.02
FPC-1282: CRIST UNITS 4 5 6 & 7 CHEMICAL FEED SYSTEM | FPC - Vicki L. Mack: Vicki | 14070.37 | 0 | 14070.37 | 100% | Over Budget | Yes | carryover | 14070 | 14070.37 | 0 | 14070 | 100% | Over Budget | -0.37
FPC-1925: CRIST PURCHASE MOBILE CRANE TO REPL TEREX | FPC - Vicki L. Mack: Vicki | 3463.34 | 0 | 3463.34 | 100% | Over Budget | No |  | 3463 | 3463.34 | 0 | 3463 | 100% | Over Budget | -0.34
FPC-1936: CRIST DRY AIR LAY-UP SYSTEM FOR UNITS 4-7 | FPC - Vicki L. Mack: Vicki | 5239.78 | 0 | 5239.78 | 100% | Over Budget | No |  | 5240 | 372739.78 | 367500 | -362260 | -98.57% | Under Budget | -367499.78
FPC-1937: CRIST U6 PULVERIZER GEARBOX | FPC - Vicki L. Mack: Vicki | 0 | 76581 | -76581 | -100% | Under Budget | Yes | work will be done later in year | 127636 | 51055 | 127636 | 0 | 0% | On Budget | 76581
FPC-1942: CRIST U7 PULVERIZER GEARBOXES | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 127636 | 127636 | 127636 | 0 | 0% | On Budget | 0
FPC-1946: CRIST SILO SUMP PUMP DISCHARGE LINE | FPC - Vicki L. Mack: Vicki | 14572.74 | 0 | 14572.74 | 100% | Over Budget | Yes | Carryover | 14573 | 14572.74 | 0 | 14573 | 100% | Over Budget | 0.26
FPC-1953: CRIST U6 & U7 NEW BREAKER BUILDING | FPC - Vicki L. Mack: Vicki | 3968.19 | 0 | 3968.19 | 100% | Over Budget | No |  | 3968 | 3968.19 | 0 | 3968 | 100% | Over Budget | -0.19
FPC-1960: CRIST PURCHASE NEW RADIOS | FPC - Vicki L. Mack: Vicki | 21129.56 | 0 | 21129.56 | 100% | Over Budget | Yes | carryover | 21130 | 21129.56 | 0 | 21130 | 100% | Over Budget | 0.44
FPC-1963: CRIST Lab Bathrooms | FPC - Vicki L. Mack: Vicki | 0 | 157500 | -157500 | -100% | Under Budget | Yes | Project will start later than budgeted | 703500 | 546000 | 703500 | 0 | 0% | On Budget | 157500
FPC-1973: CRIST SWITCHYARD DRAINS | FPC - Vicki L. Mack: Vicki | -15629.16 | 102375 | -118004.16 | -115.3% | Under Budget | Yes | cancelled | -15629 | 86745.84 | 204750 | -220379 | -107.6% | Under Budget | -102374.84
FPC-1977: CRIST U7 REPLACE PULVERIZER MOTOR | FPC - Vicki L. Mack: Vicki | 120294.74 | 0 | 120294.74 | 100% | Over Budget | Yes | carryover | 120295 | 120294.74 | 0 | 120295 | 100% | Over Budget | 0.26
FPC-1978: CRIST REPLACE B SILO COMPRESSOR | FPC - Vicki L. Mack: Vicki | 12590.3 | 0 | 12590.3 | 100% | Over Budget | Yes | 2015 project moved to 2016 | 194250 | 12590.3 | 0 | 194250 | 100% | Over Budget | 181659.7
FPC-1979: CRIST ASH TRUCK SCALES | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 571165 | 571165 | 571165 | 0 | 0% | On Budget | 0
FPC-1990: CRIST 4&5 COLLING TOWER FIRE PUMP STATION | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 330750 | 330750 | 330750 | 0 | 0% | On Budget | 0
FPC-1991: CRIST U6 575 VOLT BREAKER REPLACEMENT | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 400523 | 400523 | 400523 | 0 | 0% | On Budget | 0
FPC-1992: CRIST U7 575 VOLT BREAKER REPLACEMENT | FPC - Vicki L. Mack: Vicki | 1794.02 | 0 | 1794.02 | 100% | Over Budget | No |  | 1794 | 540444.02 | 538650 | -536856 | -99.67% | Under Budget | -538650.02
Sub-Total Plant Crist |  | 2951185.27 | 3833290 | -882104.73 | -23.01% | Under Budget |  |  | 25061846 | 26178738.27 | 26842674 | -1780828 | -6.634% | Under Budget | -1116892.27
Plant Smith excl LTSA
FPC-0400: FPC-0400 | FPC - Vicki L. Mack: Vicki | 195.55 | 0 | 195.55 | 100% | Over Budget | No |  | 196 | 195.55 | 0 | 196 | 100% | Over Budget | 0.45
FPC-0401: FPC-0401 | FPC - Vicki L. Mack: Vicki | 345.74 | 0 | 345.74 | 100% | Over Budget | No |  | 346 | 345.74 | 0 | 346 | 100% | Over Budget | 0.26
FPC-0407: SMITH - CONSTRUCTION SUB TRANSFORMER (LAGUNA BEACH) | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 181818 | 1000000 | -1000000 | -100% | Under Budget | -181818
FPC-0408: SMITH 3 - COOLING TOWER FILL MEDIA REPLACEMENTS | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 125000 | 125000 | 125000 | 0 | 0% | On Budget | 0
FPC-0409: SMITH 3 - DRIFT ELIMINATOR | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 150000 | 150000 | 150000 | 0 | 0% | On Budget | 0
FPC-0410: SMITH 3 - COOLING TOWER DCS CABINET REPLACEMENTS | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 80000 | 80000 | 80000 | 0 | 0% | On Budget | 0
FPC-0413: Smith 3 - Water Mist Fire Protection System | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 685000 | 685000 | 685000 | 0 | 0% | On Budget | 0
FPC-0414: FPC-0414 | FPC - Vicki L. Mack: Vicki | 0.87 | 0 | 0.87 | 0% | On Budget | No |  | 1 | 0.87 | 0 | 1 | 0% | On Budget | 0.13
FPC-1400: SMITH 1&2 - MISC. STEAM PLANT ADDITIONS | FPC - Vicki L. Mack: Vicki | 3960.17 | 131199 | -127238.83 | -96.98% | Under Budget | Yes | Minimal misc. activity on Smith 1 & 2 to date | 524885 | 397761.17 | 525000 | -115 | -0.0219% | Under Budget | 127123.83
FPC-1401: SMITH 3 - AIR COMPRESSOR REPLACEMENT | FPC - Vicki L. Mack: Vicki | 0 | 75000 | -75000 | -100% | Under Budget | Yes | Project has not started | 100000 | 25000 | 100000 | 0 | 0% | On Budget | 75000
FPC-1428: Smith 3 Water Treatment Plant Transformer | FPC - Vicki L. Mack: Vicki | 1.25 | 0 | 1.25 | 100% | Over Budget | No |  | 1 | 1.25 | 0 | 1 | 0% | On Budget | -0.25
FPC-1437: Smith 3 - Admin Bldg. Expansion | FPC - Vicki L. Mack: Vicki | 601349.98 | 871500 | -270150.02 | -31% | Under Budget | Yes | Project has not started | 4100000 | 4111849.98 | 3500000 | 600000 | 17.14% | Over Budget | -11849.98
FPC-1477: SMITH 3 - REPLACE INLINE AIR FILTERS | FPC - Vicki L. Mack: Vicki | 0 | 400000 | -400000 | -100% | Under Budget | Yes | Project has not started | 400000 | 0 | 400000 | 0 | 0% | On Budget | 400000 | 400000
FPC-1499: Smith U3 - Simulator | FPC - Vicki L. Mack: Vicki | 872.72 | 0 | 872.72 | 100% | Over Budget | No |  | 27000 | 872.72 | 0 | 27000 | 100% | Over Budget | 26127.28
FPC-1600: SMITH 3 - MISC. STEAM PLANT ADDITIONS | FPC - Vicki L. Mack: Vicki | 60064.58 | 249911 | -189846.42 | -75.97% | Under Budget | Yes | Minimal misc activity on Smith 3 to date | 912254 | 810153.58 | 1000000 | -87746 | -8.775% | Under Budget | 102100.42
FPC-1610: SMITH - CYBER SECURITY | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 39600 | 28634 | 28634 | 10966 | 38.3% | Over Budget | 10966
FPC-1626: SMITH - NERC CIP IMPLEMENTATION | FPC - Vicki L. Mack: Vicki | 0 | 38725 | -38725 | -100% | Under Budget | Yes | project not started-- gwo in process of getting set up | 154900 | 116175 | 154900 | 0 | 0% | On Budget | 38725
FPC-1632: SMITH 3 - REPLACE EVAP COOLER FILL MEDIA | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 150000 | 100000 | 100000 | 50000 | 50% | Over Budget | 50000
FPC-1648: SMITH 3 - STORM WATER SYSTEM | FPC - Vicki L. Mack: Vicki | -762.57 | 0 | -762.57 | -100% | Under Budget | No |  | -763 | -762.57 | 0 | -763 | -100% | Under Budget | -0.43
FPC-1672: SMITH - PROPERTY LINE FENCING | FPC - Vicki L. Mack: Vicki | 0 | 373500 | -373500 | -100% | Under Budget | Yes | Project has not started | 1500000 | 1126500 | 1500000 | 0 | 0% | On Budget | 373500 | 375000
FPC-1679: SMITH 3 - CORROSION PROJECT | FPC - Vicki L. Mack: Vicki | 326006.01 | 249000 | 77006.01 | 30.93% | Over Budget | Yes | Early materials purchases in preparation to begin corrosion projects | 400000 | 1077006.01 | 1000000 | -600000 | -60% | Under Budget | -677006.01
Sub-Total Plant Smith excl LTSA |  | 992034.3 | 2388835 | -1396800.7 | -58.47% | Under Budget |  |  | 9348420 | 9015551.3 | 10348534 | -1000114 | -9.664% | Under Budget | 332868.7
Plant Smith - LTSA
FPC-1438: SMITH 3 - LTSA | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 27491875 | 27491875 | 27491875 | 0 | 0% | On Budget | 0
Sub-Total Plant Smith - LTSA |  | 0 | 0 | 0 | 0% | On Budget |  |  | 27491875 | 27491875 | 27491875 | 0 | 0% | On Budget | 0
Plant Daniel
FPC-0506: Daniel 1 & 2 Sump Pump | FPC - Vicki L. Mack: Vicki | 182.56 | 0 | 182.56 | 100% | Over Budget | No |  | 183 | 182.56 | 0 | 183 | 100% | Over Budget | 0.44
FPC-0507: Daniel Units 1 & 2 Termon Heat Trace ( Freeze Protection) | FPC - Vicki L. Mack: Vicki | 28389.11 | 0 | 28389.11 | 100% | Over Budget | Yes | Project added to MPC's final OB | 127620 | 28389.11 | 0 | 127620 | 100% | Over Budget | 99230.89
FPC-0510: Daniel U1 LED Lighting - Turbine Floor | FPC - Vicki L. Mack: Vicki | 37470.31 | 68724 | -31253.69 | -45.48% | Under Budget | Yes | Project reduced in MPC's final OB | 132212 | 443746.31 | 475000 | -342788 | -72.17% | Under Budget | -311534.31
FPC-0512: Daniel Common Breakers | FPC - Vicki L. Mack: Vicki | 4249.77 | 0 | 4249.77 | 100% | Over Budget | No |  | 0 | 284249.77 | 280000 | -280000 | -100% | Under Budget | -284249.77
FPC-0515: Daniel Conveyor Equipment- Add Camera to Conveyor Belts | FPC - Vicki L. Mack: Vicki | 0 | 74970 | -74970 | -100% | Under Budget | Yes | Project start date pushed back to April | 59885 | 75030 | 150000 | -90115 | -60.08% | Under Budget | -15145
FPC-0521: Daniel U2 Aux. Air Beck drives and registers | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 195000 | 195000 | -195000 | -100% | Under Budget | -195000
FPC-0523: Daniel Common Replace Coal yard Switchgear | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 95000 | 95000 | -95000 | -100% | Under Budget | -95000
FPC-0524: Daniel U1 Replace Critical AC | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 42867 | 32500 | 32500 | 10367 | 31.9% | Over Budget | 10367
FPC-0525: Daniel 2 Replace Critical AC | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 384302 | 302698 | 302698 | 81604 | 26.96% | Over Budget | 81604
FPC-0532: Daniel DEGP R/R S1 CONVEYOR GEARBOX | FPC - Vicki L. Mack: Vicki | 0 | 45000 | -45000 | -100% | Under Budget | Yes | Project start date pushed back to April and budget reduced in MPC's final budget | 17516 | 30000 | 75000 | -57484 | -76.65% | Under Budget | -12484
FPC-0541: Daniel Generator Rotor Rewind | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 5000 | 5000 | 5000 | 0 | 0% | On Budget | 0
FPC-0543: Daniel U1&2 Common CO2 Tank and Piping | FPC - Vicki L. Mack: Vicki | 22852.64 | 0 | 22852.64 | 100% | Over Budget | Yes | 2015 Carryover | 22853 | 22852.64 | 0 | 22853 | 100% | Over Budget | 0.36
FPC-0547: Daniel Common New cables for Ash Sluice Motors | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 100000 | 100000 | 100000 | 0 | 0% | On Budget | 0
FPC-0551: Daniel Common Emergency Notification System | FPC - Vicki L. Mack: Vicki | 0 | 93714 | -93714 | -100% | Under Budget | Yes | Project removed from MPC's Final OB | 0 | 93786 | 187500 | -187500 | -100% | Under Budget | -93786
FPC-1500: DANIEL-MISC. STEAM PLANT ADDITIONS & | FPC - Vicki L. Mack: Vicki | 136124.06 | 76515 | 59609.06 | 77.91% | Over Budget | Yes | Projects added to MPC's Final OB | 653623 | 365792.06 | 306183 | 347440 | 113.5% | Over Budget | 287830.94
FPC-1544: DANIEL WATER TREATMENT PLANT CONTROLS | FPC - Vicki L. Mack: Vicki | 29908.69 | 0 | 29908.69 | 100% | Over Budget | Yes | Gulf's cash flows are not in-line with MPC's for this project | 340000 | 369908.69 | 340000 | 0 | 0% | On Budget | -29908.69
FPC-1545: DANIEL 1&2 ASH HANDLING CONTROLS | FPC - Vicki L. Mack: Vicki | 77467.33 | 249480 | -172012.67 | -68.95% | Under Budget | Yes | MPC's OB had project spread evenly throughout year | 455306 | 205987.33 | 378000 | 77306 | 20.45% | Over Budget | 249318.67
FPC-1564: DANIEL 2 CAPITAL VALVE REPLACEMENTS | FPC - Vicki L. Mack: Vicki | 0 | 24750 | -24750 | -100% | Under Budget | Yes | Project removed from MPC's Final OB | 0 | 12750 | 37500 | -37500 | -100% | Under Budget | -12750
FPC-1581: DANIEL !&2 CONVEYOR DIRECT DRIVE GEARBOXES | FPC - Vicki L. Mack: Vicki | 9700.56 | 0 | 9700.56 | 100% | Over Budget | No |  | 18098 | 9700.56 | 0 | 18098 | 100% | Over Budget | 8397.44
FPC-1591: DANIEL RELAY MODERNIZATION | FPC - Vicki L. Mack: Vicki | 105754.41 | 74970 | 30784.41 | 41.06% | Over Budget | Yes | MPC Transmission project under estimated budget. | 150000 | 180784.41 | 150000 | 0 | 0% | On Budget | -30784.41
FPC-1800: Daniel Unit 2 Mill Hoist | FPC - Vicki L. Mack: Vicki | 38477.78 | 0 | 38477.78 | 100% | Over Budget | Yes | 2015 Carryover | 38478 | 38477.78 | 0 | 38478 | 100% | Over Budget | 0.22
FPC-1811: DANIEL 1 EXPANSION JOINTS C01693 | FPC - Vicki L. Mack: Vicki | -839.81 | 0 | -839.81 | -100% | Under Budget | No |  | -1033 | -839.81 | 0 | -1033 | -100% | Under Budget | -193.19
FPC-1834: DANIEL 1 REWIND GENERATOR | FPC - Vicki L. Mack: Vicki | -0.01 | 0 | -0.01 | 0% | On Budget | No |  | 0 | -0.01 | 0 | 0 | -100% | On Budget | 0.01
FPC-1861: DANIEL 2 FW HEATER 4 LP | FPC - Vicki L. Mack: Vicki | 0 | 29988 | -29988 | -100% | Under Budget | Yes | Project removed from MPC's Final OB | 0 | 90012 | 120000 | -120000 | -100% | Under Budget | -90012
FPC-1863: DANIEL 1 BOILER FEED PUMPS | FPC - Vicki L. Mack: Vicki | -548.46 | 0 | -548.46 | -100% | Under Budget | No |  | -548 | -548.46 | 0 | -548 | -100% | Under Budget | 0.46
FPC-1874: Daniel 1 & 2 Closed Loop Coolers | FPC - Vicki L. Mack: Vicki | -1551.26 | 0 | -1551.26 | -100% | Under Budget | No |  | -1551 | -1551.26 | 0 | -1551 | -100% | Under Budget | 0.26
FPC-1875: Daniel 1 & 2 CPAT Drum Index | FPC - Vicki L. Mack: Vicki | 1729.49 | 0 | 1729.49 | 100% | Over Budget | No |  | 1729 | 1729.49 | 0 | 1729 | 100% | Over Budget | -0.49
FPC-1879: Daniel 1 & 2 Hot Air Dampers and Cold Air Gates | FPC - Vicki L. Mack: Vicki | -503.89 | 0 | -503.89 | -100% | Under Budget | No |  | -504 | -503.89 | 0 | -504 | -100% | Under Budget | -0.11
FPC-1881: Daniel 1 & 2 Intelligent Sootblowing | FPC - Vicki L. Mack: Vicki | 12062.31 | 0 | 12062.31 | 100% | Over Budget | Yes | 2015 Carryover | 13000 | 49562.31 | 37500 | -24500 | -65.33% | Under Budget | -36562.31
FPC-1882: Daniel 1 & 2 Duct Replacement | FPC - Vicki L. Mack: Vicki | 3289.43 | 0 | 3289.43 | 100% | Over Budget | No |  | 85000 | 88289.43 | 85000 | 0 | 0% | On Budget | -3289.43
FPC-1884: Daniel 1 & 2 Air Heater Basket Replacement | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No |  | 54488 | 54488 | 54488 | 0 | 0% | On Budget | 0
FPC-1888: Daniel 1 & 2 Coal Additive System | FPC - Vicki L. Mack: Vicki | 226373.73 | 0 | 226373.73 | 100% | Over Budget | Yes | Project added to MPC's final OB | 226374 | 226373.73 | 0 | 226374 | 100% | Over Budget | 0.27
FPC-1891: Daniel Additional Belt Extension | FPC - Vicki L. Mack: Vicki | 99328.38 | 0 | 99328.38 | 100% | Over Budget | Yes | Project added to MPC's final OB | 124680 | 99328.38 | 0 | 124680 | 100% | Over Budget | 25351.62
FPC-1897: Daniel IK Soot Blower | FPC - Vicki L. Mack: Vicki | -8083.5 | 0 | -8083.5 | -100% | Under Budget | No |  | -8084 | -8083.5 | 0 | -8084 | -100% | Under Budget | -0.5
Sub-Total Plant Daniel |  | 821833.63 | 738111 | 83722.63 | 11.34% | Over Budget |  |  | 3041494 | 3490091.63 | 3406369 | -364875 | -10.71% | Under Budget | -448597.63
Plant Scherer
FPC-1700: SCHERER DEPOSITORY | FPC - Vicki L. Mack: Vicki | 1933168.28 | 0 | 1933168.28 | 100% | Over Budget | Yes | Scherer Depository PE represents the billing account for Scherer Cost. No Budget Dollars. | 0 | -676831.72 | 0 | 0 | -100% | On Budget | 676831.72
FPC-1710: SCHERER U3 INSTALL TRIPPER FLOOR DUST EXTRACTION EQUIPMENT | FPC - Vicki L. Mack: Vicki | 252.76 | 0 | 252.76 | 100% | Over Budget | No |  | 253 | 252.76 | 0 | 253 | 100% | Over Budget | 0.24
FPC-1716: SCHERER PORTABLE EQUIPMENT | FPC - Vicki L. Mack: Vicki | 0 | 2466 | -2466 | -100% | Under Budget | No |  | 9871 | 7405 | 9871 | 0 | 0% | On Budget | 2466
FPC-1726: SCHERER REPLACE SUPERHEAT PENDANT PLATEN | FPC - Vicki L. Mack: Vicki | 239969.73 | 121900 | 118069.73 | 96.86% | Over Budget | Yes | Spent earlier than budgeted but will also be over budget at year end | 252462 | 361869.73 | 243800 | 8662 | 3.553% | Over Budget | -109407.73
FPC-1731: SCHERER NERC CIP V4 IMPLEMETATION | FPC - Vicki L. Mack: Vicki | 2187.42 | 0 | 2187.42 | 100% | Over Budget | No |  | 218 | 2187.42 | 0 | 218 | 100% | Over Budget | -1969.42
FPC-1746: SCHERER U3 REPLACE REHEAT REPLACEMENT | FPC - Vicki L. Mack: Vicki | 433.88 | 6210 | -5776.12 | -93.01% | Under Budget | No |  | 12420 | 6643.88 | 12420 | 0 | 0% | On Budget | 5776.12
FPC-1750: SCHERER MISC ADDITIONS AND IMPROVEMENTS | FPC - Vicki L. Mack: Vicki | 49008.29 | 51069 | -2060.71 | -4.035% | Under Budget | No |  | 204361 | 202300.29 | 204361 | 0 | 0% | On Budget | 2060.71
FPC-1751: SCHERER 3 TURBINE CROSSOVER EXPANSION JOINT | FPC - Vicki L. Mack: Vicki | 0 | 12534 | -12534 | -100% | Under Budget | Yes | Haven't written GWO - late getting started | 79750 | 12536 | 25070 | 54680 | 218.1% | Over Budget | 67214
FPC-1757: SCHERER 3 REPLACE AIR HEATER BASKETS | FPC - Vicki L. Mack: Vicki | 0 | 24840 | -24840 | -100% | Under Budget | Yes | Haven't written GWO - late getting started | 49680 | 24840 | 49680 | 0 | 0% | On Budget | 24840
FPC-1792: Scherer Unit 3 Rewind Main Generator Stator | FPC - Vicki L. Mack: Vicki | 0 | 372600 | -372600 | -100% | Under Budget | Yes | Late starting project | 743200 | 372600 | 745200 | -2000 | -0.2684% | Under Budget | 370600
FPC-1794: SCHERER 3 & 4 REPLACE 3D FIXED TRIPPER CHUTES | FPC - Vicki L. Mack: Vicki | 0 | 6225 | -6225 | -100% | Under Budget | No |  | 12449 | 6224 | 12449 | 0 | 0% | On Budget | 6225
FPC-6502: Scherer 3 Replace Voltage Regulator | FPC - Vicki L. Mack: Vicki | 1320.54 | 4600 | -3279.46 | -71.29% | Under Budget | No |  | 9200 | 5920.54 | 9200 | 0 | 0% | On Budget | 3279.46
FPC-6507: Scherer 3 Replace Condenser Tube | FPC - Vicki L. Mack: Vicki | 0 | 248976 | -248976 | -100% | Under Budget | Yes | Late starting project | 497950 | 248974 | 497950 | 0 | 0% | On Budget | 248976
FPC-6508: Scherer 3 & 4 Replace Crusher House MCC U3 & U4 | FPC - Vicki L. Mack: Vicki | 29382.59 | 29555 | -172.41 | -0.5834% | Under Budget | No |  | 111497 | 58937.59 | 59110 | 52387 | 88.63% | Over Budget | 52559.41
FPC-6513: Scherer 3 & 4 Replace and Move Trestle Feeder | FPC - Vicki L. Mack: Vicki | 0 | 31122 | -31122 | -100% | Under Budget | Yes | Actuals going to PE 6529 | 0 | 31122 | 62244 | -62244 | -100% | Under Budget | -31122
FPC-6520: Scherer 3 Replace Turbine LP Rotor | FPC - Vicki L. Mack: Vicki | 486262.89 | 1760076 | -1273813.11 | -72.37% | Under Budget | Yes | Progess payment… delay but will be on budget year end | 3235393 | 2246336.89 | 3520150 | -284757 | -8.089% | Under Budget | 989056.11 | 1000000
FPC-6528: Scherer 3 Auto Fire Suppression -Turb/Generatr Lube Oil | FPC - Vicki L. Mack: Vicki | 0 | 5750 | -5750 | -100% | Under Budget | No |  | 11500 | 5750 | 11500 | 0 | 0% | On Budget | 5750
FPC-6529: Scherer 3 & 4 Vibratory Feeders | FPC - Vicki L. Mack: Vicki | 34804.46 | 0 | 34804.46 | 100% | Over Budget | Yes | Budget dollars in PE 6513 | 34804 | 34804.46 | 0 | 34804 | 100% | Over Budget | -0.46
FPC-6534: Scherer 3 Replace BFPT Controls | FPC - Vicki L. Mack: Vicki | 0 | 62100 | -62100 | -100% | Under Budget | Yes | Delay in starting | 124200 | 62100 | 124200 | 0 | 0% | On Budget | 62100
FPC-6542: Scherer 3 Replace Polisher Controls | FPC - Vicki L. Mack: Vicki | 0 | 24840 | -24840 | -100% | Under Budget | Yes | Delay in starting | 49680 | 24840 | 49680 | 0 | 0% | On Budget | 24840
FPC-6543: Scherer Common U 1-4 Generation Step Up Spare (GSU) | FPC - Vicki L. Mack: Vicki | 0 | 43734 | -43734 | -100% | Under Budget | Yes | Delay in starting | 175000 | 131266 | 175000 | 0 | 0% | On Budget | 43734
Sub-Total Plant Scherer |  | 2776790.84 | 2808597 | -31806.16 | -1.132% | Under Budget |  |  | 5613888 | 3170078.84 | 5811885 | -197997 | -3.407% | Under Budget | 2443809.16
Renewables
FPC-0091: PERDIDO LANDFILL GAS ENERGY | FPC - Vicki L. Mack: Vicki | 0 | 30000 | -30000 | -100% | Under Budget | Yes | No misc capital projects needed in 1st quarter | 120000 | 90000 | 120000 | 0 | 0% | On Budget | 30000
FPC-0100: Community Solar One | FPC - Vicki L. Mack: Vicki | 0 | 20000 | -20000 | -100% | Under Budget | Yes | Delay in starting | 3000000 | 2980000 | 3000000 | 0 | 0% | On Budget | 20000
Sub-Total Renewables |  | 0 | 50000 | -50000 | -100% | Under Budget |  |  | 3120000 | 3070000 | 3120000 | 0 | 0% | On Budget | 50000
Sub-Total Power Generation |  | 13094144.68 | 18656778 | -5562633.32 | -29.82% | Under Budget |  |  | 103435944 | 98420323.68 | 108547391 | -5111447 | -4.709% | Under Budget | 5015620.32
Power Delivery
New Business Distribution
FPC-2550: CUSTOMER METERING | FPC - Paul C. Pratofiorito: Paul | 83388.08 | 262000 | -178611.92 | -68.17% | Under Budget | Yes | Timing: Plan to be on budget at year end. | 1046000 | 867388.08 | 1046000 | 0 | 0% | On Budget | 178611.92
FPC-2551: DISTRIBUTION TRANSFORMERS | FPC - Paul C. Pratofiorito: Paul | 1682248.57 | 2094000 | -411751.43 | -19.66% | Under Budget | Yes | Timing: Early in the year. | 8718000 | 8568066.76 | 8718000 | 0 | 0% | On Budget | 149933.24
FPC-2552: NEW BUSINESS - OVERHEAD CONSTRUCTION | FPC - Paul C. Pratofiorito: Paul | 1398333.92 | 1747000 | -348666.08 | -19.96% | Under Budget | Yes | Timing: Early in the year. | 6025000 | 5676333.92 | 6025000 | 0 | 0% | On Budget | 348666.08
FPC-2553: NEW BUSINESS STREET LIGHTS | FPC - Sarah K. Seckinger: Sarah | 44437.32 | 0 | 44437.32 | 100% | Over Budget | Yes | Charges will be moved to 2553 | 44437 | 44437.32 | 0 | 44437 | 100% | Over Budget | -0.32
FPC-2554: NEW BUSINESS - UNDERGROUND CONSTRUCTION | FPC - Paul C. Pratofiorito: Paul | 1950823.65 | 1761000 | 189823.65 | 10.78% | Over Budget | Yes | New Construction in underground areas up slightly. | 7379000 | 7568823.65 | 7379000 | 0 | 0% | On Budget | -189823.65
FPC-2556: PRIVATE STREET & YARD LIGHTS | FPC - Sarah K. Seckinger: Sarah | 1165990.62 | 2300154 | -1134163.38 | -49.31% | Under Budget | Yes | Timing on budget spreads | 8743806 | 7609642.62 | 8743806 | 0 | 0% | On Budget | 1134163.38 | 1100000
FPC-2559: NEW BUSINESS - METERING ACC. ENCL. EQUIP. & DEVICES | FPC - Paul C. Pratofiorito: Paul | 26277.14 | 32000 | -5722.86 | -17.88% | Under Budget | No |  | 149000 | 143277.14 | 149000 | 0 | 0% | On Budget | 5722.86
FPC-4449: Electric Vehicle Charging Stations | FPC - Sarah K. Seckinger: Sarah | 0 | 205875 | -205875 | -100% | Under Budget | Yes | Timing | 823500 | 617625 | 823500 | 0 | 0% | On Budget | 205875
Sub-Total New Business Distribution |  | 6351499.3 | 8402029 | -2050529.7 | -24.41% | Under Budget |  |  | 32928743 | 31095594.49 | 32884306 | 44437 | 0.1351% | Over Budget | 1833148.51
Energy Conservation Cost Recovery
FPC-2558: ADVANCED ENERGY MANAGEMENT (AEM) | FPC - Sarah K. Seckinger: Sarah | 416936.33 | 502519 | -85582.67 | -17.03% | Under Budget | Yes | Timing on budget spreads | 2107992 | 2022409.33 | 2107992 | 0 | 0% | On Budget | 85582.67
Sub-Total Energy Conservation Cost Recovery |  | 416936.33 | 502519 | -85582.67 | -17.03% | Under Budget |  |  | 2107992 | 2022409.33 | 2107992 | 0 | 0% | On Budget | 85582.67
Transmission
FPC-2801: TRANS SUB INFRASTRUCTURE PROJECTS | FPC - Sarah K. Seckinger: Sarah | 57467.27 | 150000 | -92532.73 | -61.69% | Under Budget | Yes | Timing of budget to projects | 850000 | 757467.27 | 850000 | 0 | 0% | On Budget | 92532.73
FPC-2802: TRANS LINE INFRASTRUCTURE PROJECTS | FPC - Sarah K. Seckinger: Sarah | 1522156.77 | 1300000 | 222156.77 | 17.09% | Over Budget | Yes | Matting (crew support) for projects has cost more than originally planned | 5000000 | 5222156.77 | 5000000 | 0 | 0% | On Budget | -222156.77
FPC-2803: ALLIGATOR SWAMP SVC AND ASSOCIATED MODIFICATIONS | FPC - Sarah K. Seckinger: Sarah | 68615.82 | 0 | 68615.82 | 100% | Over Budget | Yes | Part of the SVC contractual price was tools. Original thought was they could go in a special ferc account. After actual cost for the tools from ABB was determined, accounting decided to spread the cost back against the asset. | 75000 | 68615.82 | 0 | 75000 | 100% | Over Budget | 6384.18
FPC-2808: Greenwood - Long Beach | FPC - Sarah K. Seckinger: Sarah | 192923.16 | 0 | 192923.16 | 100% | Over Budget | Yes | Additional contractor (Pike) work not expected | -2200000 | -2007076.84 | -2200000 | 0 | -100% | On Budget | -192923.16
FPC-2813: North Brewton - Alligator Swamp New 230 kV Transmission Line | FPC - Sarah K. Seckinger: Sarah | 2242.2 | 0 | 2242.2 | 100% | Over Budget | No |  | 5000 | 2242.2 | 0 | 5000 | 100% | Over Budget | 2757.8
FPC-2814: LAGUNA BEACH - SANTA ROSA #2 230KV TL | FPC - Sarah K. Seckinger: Sarah | 46854.33 | 0 | 46854.33 | 100% | Over Budget | Yes | Culvert work in January and February at Santa Rosa Substation | 50000 | 46854.33 | 0 | 50000 | 100% | Over Budget | 3145.67
FPC-2816: Backbone Fiber Project | FPC - Sarah K. Seckinger: Sarah | 587.75 | 90000 | -89412.25 | -99.35% | Under Budget | Yes | Design estimated to start in April | 555000 | 465587.75 | 555000 | 0 | 0% | On Budget | 89412.25
FPC-2821: ALLIGATOR SWAMP 230KV EXPANSION | FPC - Sarah K. Seckinger: Sarah | -17399.52 | 0 | -17399.52 | -100% | Under Budget | Yes | Credit due to COR | -20000 | -17399.52 | 0 | -20000 | -100% | Under Budget | -2600.48
FPC-2822: TRANSMISSION LN SWITCH REPL PROJ | FPC - Sarah K. Seckinger: Sarah | 208034.45 | 120000 | 88034.45 | 73.36% | Over Budget | Yes | Timing of contract labor and material | 500000 | 588034.45 | 500000 | 0 | 0% | On Budget | -88034.45
FPC-2829: Highland City +/- 100 MVAR Static VAR compensator (SVC) | FPC - Sarah K. Seckinger: Sarah | 49280.87 | 0 | 49280.87 | 100% | Over Budget | Yes | Part of the SVC contractual price was tools. Original thought was they could go in a special ferc account. After actual cost for the tools from ABB was determined, accounting decided to spread the cost back against the asset. | 60000 | 49280.87 | 0 | 60000 | 100% | Over Budget | 10719.13
FPC-2830: TRANSMISSION BREAKER REPLACEMENT | FPC - Sarah K. Seckinger: Sarah | 0 | 0 | 0 | 0% | On Budget | No |  | 533000 | 533000 | 533000 | 0 | 0% | On Budget | 0
FPC-2835: TRANSMISSION CIP COMPLIANCE | FPC - Sarah K. Seckinger: Sarah | 63435.16 | 243482 | -180046.84 | -73.95% | Under Budget | Yes | Timing of budget spreads from SCS | 911250 | 731203.16 | 911250 | 0 | 0% | On Budget | 180046.84
FPC-2836: Transmission Cyber and Physical Security (NON-CIP) | FPC - Sarah K. Seckinger: Sarah | 130099.94 | 296250 | -166150.06 | -56.08% | Under Budget | Yes | Timing of budget spreads from SCS | 1295000 | 1128849.94 | 1295000 | 0 | 0% | On Budget | 166150.06
FPC-2841: GUYED Y TOWER ANCHOR REPLACEMENTS | FPC - Sarah K. Seckinger: Sarah | 778659.42 | 340000 | 438659.42 | 129% | Over Budget | Yes | work started earlier than originally planned | 1000000 | 1438659.42 | 1000000 | 0 | 0% | On Budget | -438659.42
FPC-2867: HOLMES CREEK - HIGHLAND CITY 230KV | FPC - Sarah K. Seckinger: Sarah | -11320.97 | 0 | -11320.97 | -100% | Under Budget | Yes | Accrual reversal from December - actuals booked to different workorder | -11321 | -11320.97 | 0 | -11321 | -100% | Under Budget | -0.03
FPC-2868: Survey and Renewal of Transmission Corridor Leases | FPC - Sarah K. Seckinger: Sarah | 28834.62 | 0 | 28834.62 | 100% | Over Budget | Yes | Timing | 538000 | 566834.62 | 538000 | 0 | 0% | On Budget | -28834.62
FPC-2881: BARRY-CRIST 230 KV UPGRADE | FPC - Sarah K. Seckinger: Sarah | 0 | 65000 | -65000 | -100% | Under Budget | Yes | Timing, design estimated to start in May | 188500 | 123500 | 188500 | 0 | 0% | On Budget | 65000
FPC-2901: Crist 115kV Substation Reliability Upgrade | FPC - Sarah K. Seckinger: Sarah | 1507764.77 | 430400 | 1077364.77 | 250.3% | Over Budget | Yes | Timing of bugeted materials | 1917000 | 2994364.77 | 1917000 | 0 | 0% | On Budget | -1077364.77 | -1100000
FPC-2905: SMITH CONSTRUCTION | FPC - Sarah K. Seckinger: Sarah | 2264.61 | 0 | 2264.61 | 100% | Over Budget | No |  | 2265 | 2264.61 | 0 | 2265 | 100% | Over Budget | 0.39
FPC-2906: 115KV LINE RATING INCREASE | FPC - Sarah K. Seckinger: Sarah | 9181.19 | 10000 | -818.81 | -8.188% | Under Budget | No |  | 616000 | 615181.19 | 616000 | 0 | 0% | On Budget | 818.81
FPC-2908: Fiber Replacements | FPC - Sarah K. Seckinger: Sarah | 345459.11 | 364500 | -19040.89 | -5.224% | Under Budget | No |  | 1062256 | 1043215.11 | 1062256 | 0 | 0% | On Budget | 19040.89
FPC-2911: SCS Design - Autodesk | FPC - Sarah K. Seckinger: Sarah | 30002.74 | 45156 | -15153.26 | -33.56% | Under Budget | Yes | Timing from SCS | 189679 | 174525.74 | 189679 | 0 | 0% | On Budget | 15153.26
FPC-2912: Solar | FPC - Sarah K. Seckinger: Sarah | -429629.57 | -275000 | -154629.57 | -100% | Under Budget | Yes | Billing did not occur in 2015 as originally budgeted | -200500 | -355129.57 | -200500 | 0 | -100% | On Budget | 154629.57
FPC-2914: FPC-2914 | FPC - Sarah K. Seckinger: Sarah | 14915.02 | 0 | 14915.02 | 100% | Over Budget | Yes | Additional Bay County charges | 15000 | 14915.02 | 0 | 15000 | 100% | Over Budget | 84.98
FPC-2915: Smith 230-115kV P&C Reliability | FPC - Sarah K. Seckinger: Sarah | 0 | 0 | 0 | 0% | On Budget | No |  | 70000 | 70000 | 70000 | 0 | 0% | On Budget | 0
FPC-3401: DIST SUB INFRASTRUCTURE PROJECTS | FPC - Sarah K. Seckinger: Sarah | 245688.11 | 231600 | 14088.11 | 6.083% | Over Budget | No |  | 1000000 | 1014088.11 | 1000000 | 0 | 0% | On Budget | -14088.11
FPC-3420: DESTIN 115 12KV RELIABILITY UPGRADE | FPC - Sarah K. Seckinger: Sarah | 31674.88 | 0 | 31674.88 | 100% | Over Budget | Yes | Timing | 1850384 | 1882058.88 | 1850384 | 0 | 0% | On Budget | -31674.88 | -31558
FPC-3421: Munson Rd Substation Conversion | FPC - Sarah K. Seckinger: Sarah | 11104.44 | 40000 | -28895.56 | -72.24% | Under Budget | Yes | Timing | 2790500 | 2761604.44 | 2790500 | 0 | 0% | On Budget | 28895.56
FPC-3428: PROACTIVE TRANSFORMER REPLACEMENT | FPC - Sarah K. Seckinger: Sarah | 4975.67 | 0 | 4975.67 | 100% | Over Budget | No |  | 4976 | 4975.67 | 0 | 4976 | 100% | Over Budget | 0.33
FPC-3434: ANTOIOCH NEW SUBSTATION | FPC - Sarah K. Seckinger: Sarah | 2168359.76 | 1444000 | 724359.76 | 50.16% | Over Budget | Yes | Project started earlier to meet the summer need date | 2385000 | 3109359.76 | 2385000 | 0 | 0% | On Budget | -724359.76
FPC-3437: HURLBURT 115/12KV SUBSTATION P & C INFRASTRUCTURE UPGRADE | FPC - Sarah K. Seckinger: Sarah | 387327 | 0 | 387327 | 100% | Over Budget | Yes | Timing | 850000 | 1237327 | 850000 | 0 | 0% | On Budget | -387327
FPC-3490: DEVILLERS LOWSIDE BUS STRUCTURE REBUILD | FPC - Sarah K. Seckinger: Sarah | 343.89 | 0 | 343.89 | 100% | Over Budget | No |  | 344 | 343.89 | 0 | 344 | 100% | Over Budget | 0.11
FPC-3494: PACE 115/12KV SUBSTATION P & C INFRASTRUCTURE UPGRADE | FPC - Sarah K. Seckinger: Sarah | 0 | 0 | 0 | 0% | On Budget | No |  | 125000 | 125000 | 125000 | 0 | 0% | On Budget | 0
FPC-3702: CIRCUIT SWITCHER IMP - TS/DS | FPC - Sarah K. Seckinger: Sarah | 0 | 0 | 0 | 0% | On Budget | No |  | 350000 | 350000 | 350000 | 0 | 0% | On Budget | 0
FPC-3714: P&C INFRASTRUCTURE PROJECTS | FPC - Sarah K. Seckinger: Sarah | 241682.27 | 20000 | 221682.27 | 1108% | Over Budget | Yes | Sinai (3 relays - impending failures (service bulletin), ValP and Eastbay work from last year finished up this year | 100000 | 321682.27 | 100000 | 0 | 0% | On Budget | -221682.27
FPC-3735: Ponce and Carryville Conversion to 115kV | FPC - Sarah K. Seckinger: Sarah | 2606.41 | 0 | 2606.41 | 100% | Over Budget | No |  | 2606 | 2606.41 | 0 | 2606 | 100% | Over Budget | -0.41
FPC-3742: System Operations Additions and Improvements | FPC - Sarah K. Seckinger: Sarah | 3577.22 | 12280 | -8702.78 | -70.87% | Under Budget | No |  | 172280 | 163577.22 | 172280 | 0 | 0% | On Budget | 8702.78
FPC-4395: TCC Furniture | FPC - Sarah K. Seckinger: Sarah | 0 | 200000 | -200000 | -100% | Under Budget | Yes | Holding under run and Facilities will be over | 0 | 0 | 200000 | -200000 | -100% | Under Budget | 0
FPC-4400: TRANSMISSION TOOLS AND TEST EQUIPMENT | FPC - Sarah K. Seckinger: Sarah | 1753.58 | 114400 | -112646.42 | -98.47% | Under Budget | Yes | Timing with budget spreads | 150000 | 37353.58 | 150000 | 0 | 0% | On Budget | 112646.42
Sub-Total Transmission |  | 7699522.37 | 5242068 | 2457454.37 | 46.88% | Over Budget |  |  | 22782219 | 25255803.37 | 22798349 | -16130 | -0.07075% | Under Budget | -2473584.37
Distribution
FPC-3402: MISC OVERHEAD LINE IMPROVEMENTS | FPC - Paul C. Pratofiorito: Paul | 1144599.32 | 1474000 | -329400.68 | -22.35% | Under Budget | Yes | Timing: Early in the year. Plan to be on Budget at year-end. | 5746000 | 5416599.32 | 5746000 | 0 | 0% | On Budget | 329400.68
FPC-3403: DISTRIBUTION ADDITIONS/RETIREMENTS DUE TO HWY & JOINT USE | FPC - Paul C. Pratofiorito: Paul | 555754.48 | 251000 | 304754.48 | 121.4% | Over Budget | Yes | Budget Exception Request: Increased $402k due to DOT's volume change occuring from their new design build requirements. | 1484000 | 1386754.48 | 1082000 | 402000 | 37.15% | Over Budget | 97245.52
FPC-3404: DISTRIBUTION LINE MINOR PROJECTS | FPC - Paul C. Pratofiorito: Paul | 210452.97 | 191000 | 19452.97 | 10.18% | Over Budget | Yes | Timing: Plan to be on budget at year end. | 746000 | 1065452.97 | 1046000 | -300000 | -28.68% | Under Budget | -319452.97
FPC-3405: UNDERGROUND SYSTEM ADDITIONS & IMPROVEMENTS | FPC - Paul C. Pratofiorito: Paul | 811585.95 | 312000 | 499585.95 | 160.1% | Over Budget | Yes | District Projects to replace failed cables and abnormal UG situations. Will be over-budget at Year-End. Project & Technical Servcies to work with Districts to prioritize. | 3200000 | 2975585.95 | 2476000 | 724000 | 29.24% | Over Budget | 224414.05
FPC-3406: DISTRIBUTION UNDERGROUND CONVERSIONS | FPC - Paul C. Pratofiorito: Paul | 116297.2 | 194000 | -77702.8 | -40.05% | Under Budget | Yes | Timing: Plan to be on budget at year-end. | 774000 | 696297.2 | 774000 | 0 | 0% | On Budget | 77702.8
FPC-3407: MISC CAPITAL ACCRUALS | FPC - Paul C. Pratofiorito: Paul | 50954.62 | 0 | 50954.62 | 100% | Over Budget | Yes | This blanket order PE 3407 was set up exclusively to capture monthly entries for Accounts Payable setups and reversals (SOX). Any variance is a timing difference of Accruals setup the previous month. | 0 | 50954.62 | 0 | 0 | -100% | On Budget | -50954.62
FPC-3408: OVERHEAD LINE IMPROVEMENTS - POLE INSPECTION PROGRAM | FPC - Paul C. Pratofiorito: Paul | 240804.83 | 404000 | -163195.17 | -40.39% | Under Budget | Yes | Timing: Early in the year. Pole replacements will ramp up. | 1806000 | 1642804.83 | 1806000 | 0 | 0% | On Budget | 163195.17
FPC-3409: RIGHT OF WAY ACQUISITION | FPC - Paul C. Pratofiorito: Paul | 0 | 177000 | -177000 | -100% | Under Budget | Yes | Timing. Feeders have been chosen. Work to begin on feeder out of Jay Road to Hospital. Plan to be on budget at year end. | 708000 | 531000 | 708000 | 0 | 0% | On Budget | 177000
FPC-3438: NEW DISTRIBUTION FEEDER FOR SUBMARINE CABLE CROSSING | FPC - Paul C. Pratofiorito: Paul | 37951.95 | 0 | 37951.95 | 100% | Over Budget | Yes | Carryover from 2015, plus seagrass mitigation survey, plan, and application requirements. | 55000 | 37951.95 | 0 | 55000 | 100% | Over Budget | 17048.05
FPC-3498: DSCADA MANAGEMENT SYSTEMS - DSCADA | FPC - Paul C. Pratofiorito: Paul | 1727.77 | 0 | 1727.77 | 100% | Over Budget | No |  | 340000 | 1727.77 | 0 | 340000 | 100% | Over Budget | 338272.23
FPC-3499: SO SMART RELIABILITY IMPROVEMENT PROGRAMS | FPC - Paul C. Pratofiorito: Paul | 97946.54 | 373000 | -275053.46 | -73.74% | Under Budget | Yes | Timing | 2043000 | 1767946.54 | 2043000 | 0 | 0% | On Budget | 275053.46
FPC-3500: ASSET MANAGEMENT IMPROVEMENT PROGRAMS | FPC - Paul C. Pratofiorito: Paul | 104531.7 | 403000 | -298468.3 | -74.06% | Under Budget | Yes | Timing | 353000 | 1140531.7 | 1439000 | -1086000 | -75.47% | Under Budget | -787531.7
FPC-3501: MISC DISTRIBUTION LINES SPECIFIC FEEDER IMPROVEMENTS | FPC - Paul C. Pratofiorito: Paul | 86765.68 | 15000 | 71765.68 | 478.4% | Over Budget | Yes | Reduced $250k Fund PE 4304 Addl and $228k new General Plant. | 235000 | 736765.68 | 665000 | -430000 | -64.66% | Under Budget | -501765.68
FPC-3502: MISC DISTRIBUTION SUBSTATION FEEDER RECONFIGURATIONS & UPGRA | FPC - Paul C. Pratofiorito: Paul | 8008.32 | 47000 | -38991.68 | -82.96% | Under Budget | Yes | Reduced to cover overage in PE 3438. Reduced $62 new General Plant. | 57000 | 153008.32 | 192000 | -135000 | -70.31% | Under Budget | -96008.32
FPC-3520: ANTIOCH ROAD SUB NEW FEEDERS | FPC - Paul C. Pratofiorito: Paul | 40373.64 | 200000 | -159626.36 | -79.81% | Under Budget | Yes | Timing. Plan to come under budget $40k at year-end. | 360000 | 240373.64 | 400000 | -40000 | -10% | Under Budget | 119626.36
FPC-3534: EAST BAY 5542 RECONDUCTOR | FPC - Paul C. Pratofiorito: Paul | 0 | 150000 | -150000 | -100% | Under Budget | Yes | Timing. Start in late April. | 350000 | 200000 | 350000 | 0 | 0% | On Budget | 150000
FPC-3539: HATHAWAY 8682 - GRAND LAGOON BRIDGE CROSSING | FPC - Paul C. Pratofiorito: Paul | 0 | 600000 | -600000 | -100% | Under Budget | Yes | Timing - Bay County permit received on March 8th. Presently working on Environmental permit. | 700000 | 100000 | 700000 | 0 | 0% | On Budget | 600000 | 600000
FPC-3637: SANTA ROSA ISLAND ENHANCEMENTS | FPC - Paul C. Pratofiorito: Paul | 0 | 729000 | -729000 | -100% | Under Budget | Yes | Timing, Expect to be on budget by year end | 972000 | 243000 | 972000 | 0 | 0% | On Budget | 729000 | 700000
FPC-3652: STORM HARDENING - OVERHEAD | FPC - Paul C. Pratofiorito: Paul | 224836.64 | 222000 | 2836.64 | 1.278% | Over Budget | No |  | 1148000 | 1150836.64 | 1148000 | 0 | 0% | On Budget | -2836.64
FPC-3693: DEVILLIERS SUB - NETWORK UPGRADES | FPC - Paul C. Pratofiorito: Paul | 49222.38 | 0 | 49222.38 | 100% | Over Budget | Yes | Timing. Ahead of schedule. Expect to be on budget at year-end. | 125000 | 174222.38 | 125000 | 0 | 0% | On Budget | -49222.38
FPC-3694: Crystal Beach Feeder 8982 Reconductor | FPC - Paul C. Pratofiorito: Paul | 0 | 185000 | -185000 | -100% | Under Budget | Yes | Timing - Waiting on Customer to decide on conversion. | 185000 | 0 | 185000 | 0 | 0% | On Budget | 185000
FPC-3695: Beulah Feeder 5512 & 5522 Reconductor and Reconfiguration | FPC - Paul C. Pratofiorito: Paul | 86517.81 | 150000 | -63482.19 | -42.32% | Under Budget | Yes | Timing. | 150000 | 86517.81 | 150000 | 0 | 0% | On Budget | 63482.19
FPC-3700: SYSTEM REACTIVE CORRECTIVE CAPACITY | FPC - Paul C. Pratofiorito: Paul | 649270.47 | 229000 | 420270.47 | 183.5% | Over Budget | Yes | Ahead of Schedule to upgrade DCC’s capacitor bank Comverge control paging system, in conjunction with Marketing’s Energy Select Comverge control paging system was retired April 1st. | 1434000 | 1854270.47 | 1434000 | 0 | 0% | On Budget | -420270.47
FPC-4301: TOOLS IMPLEMENTS AND TEST EQUIP. | FPC - Paul C. Pratofiorito: Paul | 42903.47 | 47000 | -4096.53 | -8.716% | Under Budget | No |  | 390000 | 385903.47 | 390000 | 0 | 0% | On Budget | 4096.53
FPC-4308: POWER DELIVERY TECHNOLOGY IMPROVEMENTS | FPC - Paul C. Pratofiorito: Paul | 39431.84 | 34000 | 5431.84 | 15.98% | Over Budget | No |  | 350000 | 355431.84 | 350000 | 0 | 0% | On Budget | -5431.84
FPC-4392: HR - Training Yard Purchases | FPC - Paul C. Pratofiorito: Paul | 26251.66 | 50000 | -23748.34 | -47.5% | Under Budget | Yes | Timing. Transmission additions to the Training Yard for the new Transmission assessments. New sec capacitor ($10k)is planned as well as new switchgear ($100k) | 196000 | 172251.66 | 196000 | 0 | 0% | On Budget | 23748.34
FPC-4408: Cyber Security | FPC - Paul C. Pratofiorito: Paul | 15320.54 | 26000 | -10679.46 | -41.07% | Under Budget | Yes | Revised projection is $215k. $67k in SCS charges, and $133k in shared cost from APCO "system" improvements with the Lancope installation | 215000 | 93320.54 | 104000 | 111000 | 106.7% | Over Budget | 121679.46
FPC-4412: DSCADA MANAGEMENT SYSTEMS | FPC - Paul C. Pratofiorito: Paul | 5348.5 | 154000 | -148651.5 | -96.53% | Under Budget | Yes | Timing: Early in the year, 1st PO issued @ $140k after Tax/Stores. TCMS is being funding through PE 3498. New Forecast of costing expected with may reporting. | 499000 | 490348.5 | 639000 | -140000 | -21.91% | Under Budget | 8651.5
FPC-4413: PINE FOREST OFFICE ROADWAY CONSTRUCTION | FPC - Paul C. Pratofiorito: Paul | 0 | 0 | 0 | 0% | On Budget | No |  | 2000000 | 2000000 | 2000000 | 0 | 0% | On Budget | 0
Sub-Total Distribution |  | 4646858.28 | 6617000 | -1970141.72 | -29.77% | Under Budget | Yes |  | 26621000 | 25149858.28 | 27120000 | -499000 | -1.84% | Under Budget | 1471141.72
Sub-Total Power Delivery |  | 19114816.28 | 20763616 | -1648799.72 | -7.941% | Under Budget |  |  | 84439954 | 83523665.47 | 84910647 | -470693 | -0.5543% | Under Budget | 916288.53
General Plant
Transportation
FPC-4304: AUTOMOBILES AUTO TRUCKS & EQUIP. | FPC - Allison R. Gillespie: Allison | 60911.39 | 463000 | -402088.61 | -86.84% | Under Budget | Yes | Timing. Early in the year. In addition, there is a $33k increase per truck for AWD projected. Addl $250k funded out of PE 3501. | 3559000 | 3217821.39 | 3309000 | 250000 | 7.555% | Over Budget | 341178.61
Sub-Total Transportation |  | 60911.39 | 463000 | -402088.61 | -86.84% | Under Budget |  |  | 3559000 | 3217821.39 | 3309000 | 250000 | 7.555% | Over Budget | 341178.61
Telecommunications/Mobile Systems/Data Network
FPC-4305: TELECOMMUNICATIONS WIRELESS SYSTEM ADDITIONS/IMPROVEMENTS | FPC - Shonda L. Lee: Shonda | 0 | 48000 | -48000 | -100% | Under Budget | Yes | Project work has not started yet; dollars will cover work in 4311 | 41480 | 144000 | 192000 | -150520 | -78.4% | Under Budget | -102520
FPC-4310: VOICE & DATA CONVERGED NETWORK | FPC - Shonda L. Lee: Shonda | 59546.56 | 144000 | -84453.44 | -58.65% | Under Budget | Yes | Project work has just started; should catch up | 576000 | 491546.56 | 576000 | 0 | 0% | On Budget | 84453.44
FPC-4311: TRANSPORT NETWORK | FPC - Shonda L. Lee: Shonda | 19638.76 | 38400 | -18761.24 | -48.86% | Under Budget | Yes | Project work has not started yet | 768000 | 749238.76 | 768000 | 0 | 0% | On Budget | 18761.24
FPC-4385: FIELD COMPUTING | FPC - Shonda L. Lee: Shonda | 2017.98 | 72240 | -70222.02 | -97.21% | Under Budget | Yes | Project work has just started; additional dollars covered by 4310 | 295000 | 74257.98 | 144480 | 150520 | 104.2% | Over Budget | 220742.02
FPC-4386: CSS Data Integration Hub Architecture | FPC - David Oerting: Dave | 37435.9 | 31849 | 5586.9 | 17.54% | Over Budget | No |  | 127400 | 132986.9 | 127400 | 0 | 0% | On Budget | -5586.9
FPC-4410: Long Term Evolution (LTE) | FPC - Paul C. Pratofiorito: Paul | 108495.74 | 378000 | -269504.26 | -71.3% | Under Budget | Yes | Timing… On track per SCS who is coordinating this effort. | 1500000 | 1458195.74 | 1500000 | 0 | 0% | On Budget | 41804.26
FPC-4417: IT Cyber Security Software | FPC - Shonda L. Lee: Shonda | 28010.49 | 99999 | -71988.51 | -71.99% | Under Budget | Yes | Credit due to a double accrual in Dec; dollars will catch up | 400000 | 328011.49 | 400000 | 0 | 0% | On Budget | 71988.51
FPC-4486: On Line Customer Care | FPC - David Oerting: Dave | 139570.19 | 99960 | 39610.19 | 39.63% | Over Budget | Yes | Release 2 estimates coming in higher than expected | 400000 | 439610.19 | 400000 | 0 | 0% | On Budget | -39610.19
FPC-4586: Customer Kiosks | FPC - David Oerting: Dave | 0 | 500000 | -500000 | -100% | Under Budget | Yes | Contractual delays for purchase of kiosks | 500000 | 0 | 500000 | 0 | 0% | On Budget | 500000 | 500000
Sub-Total Telecommunications/Mobile Systems/Data Network |  | 394715.62 | 1412448 | -1017732.38 | -72.05% | Under Budget |  |  | 4607880 | 3817847.62 | 4607880 | 0 | 0% | On Budget | 790032.38
Accounting
FPC-4376: Maximo/Oracle/Powerplant Upgrades | FPC - Carol Stevens: Carol | 81.19 | 29970 | -29888.81 | -99.73% | Under Budget | Yes | Timing - work moved to later in the year | 119924 | 90035.19 | 119924 | 0 | 0% | On Budget | 29888.81
Sub-Total Accounting |  | 81.19 | 29970 | -29888.81 | -99.73% | Under Budget |  |  | 119924 | 90035.19 | 119924 | 0 | 0% | On Budget | 29888.81
Corporate Services
FPC-4300: OFFICE FURNITURE & MECHANICAL EQUIP. | FPC - Corporate Services: Shirley | 191339.71 | 76500 | 114839.71 | 150.1% | Over Budget | Yes | System control renonvation. Offset in PE 439501 | 726143 | 439679.71 | 324840 | 401303 | 123.5% | Over Budget | 286463.29
FPC-4302: MISC. BUILDINGS LAND AND EQUIP. | FPC - Corporate Services: Shirley | 14813.36 | 120600 | -105786.64 | -87.72% | Under Budget | Yes | Timing | 758203 | 342043.36 | 447000 | 311203 | 69.62% | Over Budget | 416159.64 | 400000
FPC-4303: SECURITY EQUIPMENT | FPC - Corporate Services: Shirley | 25763.4 | 11792 | 13971.4 | 118.5% | Over Budget | Yes | Timing | 219592 | 198563.4 | 184592 | 35000 | 18.96% | Over Budget | 21028.6
FPC-4306: AUDIO & VISUAL EQUIPMENT | FPC - Corporate Services: Shirley | 15053.01 | 0 | 15053.01 | 100% | Over Budget | Yes | Timing | 49680 | 64733.01 | 49680 | 0 | 0% | On Budget | -15053.01
FPC-4370: PRINTSHOP EQUIP | FPC - Corporate Services: Shirley | 0 | 24840 | -24840 | -100% | Under Budget | Yes | Timing | 24840 | 0 | 24840 | 0 | 0% | On Budget | 24840
FPC-4387: Defuniak Springs Roof | FPC - Corporate Services: Shirley | 54813.25 | 100000 | -45186.75 | -45.19% | Under Budget | Yes | Bid came in under budget | 54813 | 281813.25 | 327000 | -272187 | -83.24% | Under Budget | -227000.25
FPC-4398: PANAMA CITY VECHICLE MAINT FACILITY | FPC - Corporate Services: Shirley | 0 | 700000 | -700000 | -100% | Under Budget | Yes | Not approved. | 0 | 10000 | 3500000 | -3500000 | -100% | Under Budget | -10000 | -10000
FPC-4399: PENS DISTRICT-CONSOL CUST SVC FACIL | FPC - Corporate Services: Shirley | 0 | 0 | 0 | 0% | On Budget | No |  | 0 | 819991 | 8200000 | -8200000 | -100% | Under Budget | -819991 | -819991
FPC-4406: Panama City Admin Chiller | FPC - Corporate Services: Shirley | 135149.1 | 150000 | -14850.9 | -9.901% | Under Budget | No |  | 135149 | 135149.1 | 150000 | -14851 | -9.901% | Under Budget | -0.1
FPC-4407: GEN WHSE CONVERGE ROOF | FPC - Corporate Services: Shirley | 0 | 35000 | -35000 | -100% | Under Budget | Yes | Delayed due to contractor's schedule | 45000 | 37000 | 72000 | -27000 | -37.5% | Under Budget | 8000
FPC-4411: LAND PURCHASE IN CRESTVIEW | FPC - Corporate Services: Shirley | -665.46 | 0 | -665.46 | -100% | Under Budget | No |  | -665 | -665.46 | 0 | -665 | -100% | Under Budget | 0.46
Sub-Total Corporate Services |  | 436266.37 | 1218732 | -782465.63 | -64.2% | Under Budget |  |  | 2012755 | 2328307.37 | 13279952 | -11267197 | -84.84% | Under Budget | -315552.37
T&D Warehouse Equipment Replacement
FPC-4344: T&D WAREHOUSE EQUIPMENT REPLACEMENT | FPC - Beverly D. Day: Beverly | 0 | 73500 | -73500 | -100% | Under Budget | Yes | $100,000 to offset the expediture for the General Warehouse renovation by Corporate Real Estate | 47000 | 73500 | 147000 | -100000 | -68.03% | Under Budget | -26500
Sub-Total T&D Warehouse Equipment Replacement |  | 0 | 73500 | -73500 | -100% | Under Budget |  |  | 47000 | 73500 | 147000 | -100000 | -68.03% | Under Budget | -26500
Sub-Total General Plant |  | 891974.57 | 3197650 | -2305675.43 | -72.11% | Under Budget |  |  | 10346559 | 9527511.57 | 21463756 | -11117197 | -51.8% | Under Budget | 819047.43
Non-Utility
Non-Utility
FPC-4999: NEW PRODUCTS AND SERVICES | FPC - Sarah K. Seckinger: Sarah | 50805.96 | 13301 | 37504.96 | 282% | Over Budget | Yes | Timing | 494664 | 532168.96 | 494664 | 0 | 0% | On Budget | -37504.96
Sub-Total Non-Utility |  | 50805.96 | 13301 | 37504.96 | 282% | Over Budget |  |  | 494664 | 532168.96 | 494664 | 0 | 0% | On Budget | -37504.96
Sub-Total Non-Utility |  | 50805.96 | 13301 | 37504.96 | 282% | Over Budget |  |  | 494664 | 532168.96 | 494664 | 0 | 0% | On Budget | -37504.96
Uncategorized
Uncategorized
FPC-4785: FPC-4785 | FPC - David Oerting: Dave | 340519.08 | 0 | 340519.08 | 100% | Over Budget |  |  | 340519.08 | 340519.08 | 0 | 340519.08 | 100% | Over Budget | 0
FPC-4790: FPC-4790 | FPC - David Oerting: Dave | 41034.95 | 0 | 41034.95 | 100% | Over Budget |  |  | 41034.95 | 41034.95 | 0 | 41034.95 | 100% | Over Budget | 0
Sub-Total Uncategorized |  | 381554.03 | 0 | 381554.03 | 100% | Over Budget |  |  | 381554.03 | 381554.03 | 0 | 381554.03 | 100% | Over Budget | 0
Sub-Total Uncategorized |  | 381554.03 | 0 | 381554.03 | 100% | Over Budget |  |  | 381554.03 | 381554.03 | 0 | 381554.03 | 100% | Over Budget | 0
Total |  | 33533295.52 | 42631345 | -9098049.48 | -21.34% | Under Budget |  |  | 199098675.03 | 192385223.71 | 215416458 | -16317782.97 | -7.575% | Under Budget | 6713451.32 | 6713451
| Sch 73 | 33482489.56 | 42631345 | YTD 2016 Approved Capital Budget
| Non-Utility Reconciling item | 50805.96 | 0
| Adjusted Total | 33533295.52 | 42631345
| Above - per UI | 33533295.52 | 42631345
| Difference | 0 | 0

## Capital Budget Exceptions
Date | Subject | PE/Item | Estimated Project Cost | Budget Impact | Budget Impact | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
|  |  |  | (Current Year) | (Total)
2016-01-07 | Transmission PE 2905-Smith Construction Substation Rebuild | 2905-01 | 1012500 | 0 | 0 | 2016: 1012500; 2019: -1012500
2016-01-15 | PE 2841 - Guyed Y Tower Anchor Replacements | 2841 | 5400000 | 1000000 | 4400000 | 2016: 1000000; 2017: 2500000; 2018: 300000; 2019: 300000; 2020: 300000
2016-01-15 | PE 2916 - Guyed Y Tower Replacements | 2916 | 30550000 | 0 | 10600000 | 2017: 500000; 2018: 500000; 2019: 500000; 2023: 5000000; 2024: 4100000
2016-02-09 | PE 122001 Governor's Island Headwall | 1220-01 | 3255000 | 0 | 0 | 2016: 3255000; 2018: -1050000; 2019: -2205000
2016-04-04 | PE441801 ECRC Generator Fuel Tank | 4418-01 | 8800 | 0 | 0
2016-04-06 | Transmission PE 2921 | 2921-01 | 4000000 | 2000000 | 4000000 | 2016: 2000000; 2017: 2000000
2016-04-06 | Transmission PE 3758 | 3758-01 | 1850000 | 265000 | 1850000 | 2016: 265000; 2017: 1585000
| Transmission PE 3758 | 3758-02 | 472000 | 47000 | 472000 | 2016: 47000; 2017: 425000
2016-04-06 | Transmission PE 2868 | 2868-01 | 155000 | 0 | 745000 |  | 155000 | 155000 | 155000 | 155000 | -345000 | 155000 | 155000 | 155000 | 5000
2016-04-07 | Additional funds for 122001 Governor's Island Headwall | 1220-01 | 6500000 | 6500000 | 6500000 | 2016: 6500000
2016-04-11 | PE 441501 Crestview Line service parking Lot- | 4415-01 | 177000 | 0 | 0
2016-04-13 | PE 441901 General Warehouse renovation | 4419-01 | 169000 | 0 | 0
2016-04-15 | Distribution PE 3403 | 3403-01 | 5384000 | 402000 | 1162000 | 2016: 402000; 2017: 260000; 2020: 500000
2016-04-15 | Distribution PE 3700 | 3700-01 | 2830000 | 1396000 | 1396000 | 2016: 1396000
Budget Impact |  |  |  | 11610000 | 31125000 | 15877500 | 7425000 | -95000 | -2262500 | 955000 | -345000 | 155000 | 5155000 | 4255000 | 5000

## Scenario Data
Scenario Data
Scenario | CF Gulf - 2016 Official Budget - Live Reforecast
Software Release | 10.04.RC
Version ID | 1
Scenario Comments
Date & Time of Shared Run | Never run
Date & Time Exported | 04/08/2016 08:36:06
Case List | [Logic, CF Actuals - FPC, Empty Tree Case: Admin lock, Structure, CF Permanent, CF PowerPlant - GULF, CF Budworks - GULF - 2016 Official Budget - Live Reforecast, CF Temporary - GULF - 2016 Official Budget - Live Reforecast, CF Environmental - GULF - 2016 Official Budget - Live Reforecast, ¦Blank Data¦: Admin lock, CF Data - GULF - 2016 Official Budget - Live Reforecast]
Start Year | 2015
Actuals Through | 03/2016
Years to Run/Run Monthly | 11 (Monthly: 11)
Scenario Type & User-Defined Scenario Type | Budget
Report Data
CAPEX by Bus Unit / BU Detail / PE: Admin lock
Sequence Set | Capital Sequence: Admin lock
View Name | CF Capital Expenditures by Business Unit: Admin lock
Dataset/Calc | CF Capital Expenditures by Business Unit
Row Headers | Project Class -> Business Unit of Project's Project -> Business Unit Class,Project Class -> Business Unit Detail of Project's Project -> Business Unit Class,Imported: Project -> PE of Project
Column Headers | Year 1 YTD-Mar, Year 1 Annual,User Specified Scenario List
Time Setting
Filters | View filter is CF Project Amount Type = Cash, CIAC, AFUDC Debt & Equity CF Project Amount Type = Cash, CIAC, AFUDC Debt & Equity