## Sheet1 (hidden)
FLORIDA REGION PROFORMA CAPITAL PROJECTS | [12 empty] | As of: 12/31/2016
CP# | Job Description | Co | System | TY Ltr 000's | Testimony 000's | Forecast 000's | Status/Comment | BU | Ret's? | Proforma docs on server | Engineering | Other | Project Spending | Cap Time | IDC | Total |  | Reason for 5% variance | NARUC
2014072 | LUSI SCADA | 251 | LUSI | 471 | 2016-07-01 | 470 | Proforma in current R/C | 251105 | N |  |  | 464616.47 | 464616.47 | 75408.77 | 59764.41 | 599789.65 | 27.61% |  | 364.2 | 1365 | 599789.65
2015080 | UIF Ravenna Park/Crystal Lake I/C | 252 | UIF | 645 | 2016-09-09 | 646 | Proforma in current R/C | 252118 | Y |  |  | 646555.89 | 646555.89 | 42802.63 | 48001.88 | 737360.4 | 14.14% |  | 331 | 1125 | 211369.41 | 2311363
[19 empty] | 339.1 | 1055 | 525990.99
2015082 | Eng-UIF WM Replacements | 252 | UIF | N/A | 2016-09-01 | 57 | Proforma in current R/C | 252100 | N |  | 57050 |  | 57050 | 1820.81 | 4192.4 | 63063.21 | 10.64% |  | 331 | 1125 | 63063.21 | 2310105
2015097 | SUC I&I Investigation Ph 2 | 255 | Sanlando | 150 | 2016-07-01 | 152.5 | Proforma in current R/C | 255101 | N |  |  | 138783.86 | 138783.86 | 8678.41 | 9362.08 | 156824.35 | 2.836% |  | 361 | 1350 | 156824.35
2015134 | MC Flow Monitoring & Analysis | 250 | Mid-County | 60 | 2015-12-31 | 81 | Proforma in current R/C | 250100 | N |  | 76898.39 |  | 76898.39 | 6001.25 | 8655.3 | 91554.94 | 13.03% |  | not closed? |  |  | 2307994
2015155 | LG Splitter Box Replacement | 251 | Lake Utility Services | 83.46 | 2016-01-29 | 83.46 | Proforma in current R/C | 251103 | Y |  |  | 78000 | 78000 | 6949.9 | 621.51 | 85571.41 | 2.53% |  | 381.4 | 1410 | 85571.41
2015175 | Eng-LUSI TTHM/HAA5 Alternatives Study | 251 | LUSI | 80 | 2016-11-19 | 79.25 | Proforma in current R/C | 251106 | N |  |  | 72273.47 | 72273.47 | 4569.9 | 3866.05 | 80709.42 | 1.842% |  | 339.2 | 1160 | 80709.42 | 2309384.25
2016041 | SUC Markham Wds Rd Turn Lane WM Relo | 255 | Sanlando Utilities Corp | 70 | 2016-07-31 | 65.9 | Proforma in current R/C | 255100 | Y |  |  | 59970 | 59970 | 3207.75 | 1298.56 | 64476.31 | -2.16% |  | 331 | 1125 | 64476.31
2016075 | Cypress Lakes Sediment Removal | 248 | Cypress Lakes | N/A | 2016-08-31 | 50.2 | Proforma in current R/C | 248101 | Y |  |  | 45095.29 | 45095.29 | 823.4 |  | 45918.69 | -8.529% |  | 380.4 | 1400 | 45918.69 | 2307087.2
2016076 | LB WWTP Sediment Removal | 259 | Labrador | N/A | 2016-09-23 | 61.137 | Proforma in current R/C | 259101 | Y |  |  | 50691.24 | 50691.24 | 1976.16 | 4219.93 | 56887.33 | -6.951% |  | 380.4 | 1400 | 56887.33 | 2318133.137
None | 401 8th Ave GSM Replacement | 241 | Tierra Verde Utilities | 47.3 | 2016-03-03 | 84.673 | Proforma in current R/C | 241100 | Y |  |  |  | 0 | 47300 |  | 47300 | might be missing some spending
None | MC Field office | 250 | Mid-County | 65 | 2016-07-08 | 65 | Proforma in current R/C | 250100 | Y |  |  |  | 0 |  |  | 0
None | C4500 Kodiak upfitting | 855 | UIF | 44 | 2016-09-16 | 46 | Proforma in current R/C | 855100 | N |  |  |  | 46157.33 |  |  | 46157.33 | 0.342%
None | C2500HD Boom Truck | 855 | UIF | N/A | 2016-09-27 | 60 | Chassis/cab/boom truck/upfitting | 855100 | N |  |  |  | 61059.07 |  |  | 61059.07 | 1.765% |  |  |  |  | 898655
None | Fleet replacements | 855 | UIF | N/A | 2016-07-22 | 350 | 10 Colorados | 855100 | Y |  |  |  | 341954.69 |  |  | 341954.69 | -2.299% |  |  | check this total
|  |  |  | 1800.76 |  | 2352.12 | [9 empty] | 2478.6268
2016088 | LW Church Ave FM relocates | 246 | Longwood | 85 | 170 | 253.5 | Contract awarded - Tri-Sure | 246100 | Y |  |  | 164310 | 164310 | 2058.52 |  | 166368.52 | [5 empty] | 2262942.5
None | LW I&I Study Longwood Groves | 246 | Longwood | 50 | 90 | 50 | Either Altair or American InLine | 246100 | N |  |  |  | 0 |  |  | 0 | [5 empty] | 246536
| LW I&I Longwood Groves | 246 | Longwood | 450 | 350 | 350 | Soliciting bids | 246100 | N |  |  |  | 0 |  |  | 0 | [5 empty] | 247496
| Cypress Lake Hydro Tank #1 | 248 | Cypress Lakes | 50 | 30 | 30 | No permitting required, need bids | 248100 | Y |  |  |  | 0 |  |  | 0 | [5 empty] | 248458
| ER EQ tank-headworks-gates-trees | 249 | Eagle Ridge | 350 | 350 | 700 | Eng under way - Excel | 249100 | Y |  |  |  | 0 |  |  | 0 | [5 empty] | 250749
2016032 | MC US 19 sidewalks/ utility relocations | 250 | Mid-County | 250 | 230 | 229 | Contract awarded - EESI & SPT | 250100 | Y |  | 42090.95 | 172901.71 | 214992.66 | 3727.25 | 10057.36 | 228777.27 | [5 empty] | 2267091
2016085 | MC Electrical Improvements & Genset | 250 | Mid-County | 750 | 900 | 1100 | Eng under way - APG, bids open | 250100 | Y |  | 146400 |  | 146400 | 2254.8 | 216.72 | 148871.52 | [5 empty] | 2269185
2016089 | MC Methanol pumps & TN/TP analyzer | 250 | Mid-County | 75 | 102 | 102 | Contract awarded - ASA, EDS, TriNova | 250100 | Y |  |  | 76974.36 | 76974.36 | 858.04 | 1459.52 | 79291.92 | [5 empty] | 2266718
| MC I&I remedies | 250 | Mid-County | 600 | 500 | 600 | Smoke testing done - Altair | 250100 | N |  |  |  | 0 |  |  | 0 | [5 empty] | 252050
2015018 | Lake Groves SolarOrganite | 251 | LUSI | 245 | 245 | 245 | Contract awarded - EcoSciences | 251103 | N |  |  | 236294.98 | 236294.98 | 41267.17 | 36448.36 | 314010.51 | [5 empty] | 2267107
2015083 | Eng-LUSI US 27 Ph 3 Utility relocations | 251 | LUSI | 50 | 63 | 63 | Contract awarded - CPH (Morris) | 251106 | N |  |  | 61214.92 | 61214.92 | 1633.01 | 6353.71 | 69201.64 | [5 empty] | 2266616
2016009 | LUSI US 27 Ph 3 Utility Relocates | 251 | LUSI | 1700 | 1806 | 1671 | Contract awarded - Traverse | 251106 | Y |  |  | 1651330.15 | 1651330.15 | 25424.01 | 105390.84 | 1782145 | [5 empty] | 2272543
2016103 | LUSI Oswalt Rd WM relocates | 251 | LUSI | 50 | 50 | 160.9 | Contract awarded - Traverse | 251106 | Y |  |  | 181399.14 | 181399.14 | 7275.18 | 2796.7 | 191471.02 | [5 empty] | 2267720.9
2016133 | Eng-Lake Groves WTP upgrade TTHM/HAA5 | 251 | LUSI |  | 450 | 330.8 | Contract awarded - K-H (Romano) | 251102 | N |  |  |  | 0 | 305.51 |  | 305.51 | [5 empty] | 2268266.8
2015081 | Eng-UIF LWk & BL Elec Imprvmnts & RTUs | 252 | UIF |  | 85 | 85 | Contract awarded - Bailey | 252104 | Y |  |  | 35640 | 35640 | 618.63 | 2479.66 | 38738.29 | [5 empty] | 2267607
2016068 | UIF LWk & BL Elec Imp & RTUs | 252 | UIF | 250 | 238.23 | 238 | Contract awarded - Thompson | 252104 | Y |  |  | 108085.38 | 108085.38 | 885.17 | 2165.52 | 111136.07 | [5 empty] | 2269150.23
2016091 | UIF Lake Tarpon WM replacement | 252 | UIF | 725 | 800 | 1218.15 | Contract awarded - Rowland | 252128 | Y |  | 28638.75 |  | 28638.75 | 2604.5 | 749.93 | 31993.18 | [5 empty] | 2271214.15
2016093 | UIF Bear Lake WM replacement | 252 | UIF |  | 1485.27 | 1485.27 | Contract awarded - Traverse Grp | 252122 | Y |  |  | 7719.25 | 7719.25 | 502.95 | 9.33 | 8231.53 | [5 empty] | 2271437.54
2016094 | UIF Crescent Heights WM replacement | 252 | UIF | 809 | 1806 | 1806 | Contract awarded - CFT | 252123 | Y |  |  | 6225.1 | 6225.1 | 144.1 | 1.7 | 6370.9 | [5 empty] | 2272890
2016095 | UIF Crystal Lake WM replacement | 252 | UIF |  | 1574 | 1585.933 | Contract awarded - ECO 2000 | 252117 | Y |  |  | 10127.7 | 10127.7 |  |  | 10127.7 | [5 empty] | 2271623.933
2016096 | UIF Little Wekiva WM replacement | 252 | UIF |  | 521.681 | 521.681 | Contract awarded - Traverse Grp | 252114 | Y |  |  | 225200.65 | 225200.65 | 82.34 |  | 225282.99 | [5 empty] | 2269505.362
2016097 | UIF Oakland Shores WM replacement | 252 | UIF | 2425 | 1571.701 | 1571.701 | Contract awarded - Traverse Grp | 252113 | Y |  |  | 114843.38 | 114843.38 | 617.55 | 1.55 | 115462.48 | [5 empty] | 2274030.402
2016098 | UIF Phillips WM replacement & CL I/C | 252 | UIF |  | 1188.247 | 1188.247 | Contract awarded - ECO 2000 | 252116 | Y |  |  | 7748.86 | 7748.86 |  |  | 7748.86 | [5 empty] | 2270842.494
2016099 | UIF Ravenna Park WM replacement | 252 | UIF | 2665 | 2160.808 | 2160.808 | Contract awarded - ECO 2000 | 252118 | Y |  |  | 105787.29 | 105787.29 | 946.91 | 1555.29 | 108289.49 | [5 empty] | 2275455.616
2016102 | UIF Buena Vista/OW WM replacement | 252 | UIF | 1200 | 1200 | 1916.9 | Contract awarded - S&S | 252106 | Y |  |  | 10160 | 10160 | 461.43 | 35.7 | 10657.13 | [5 empty] | 2272776.9
| UIF Summertree Well Abandonment | 252 | UIF | 200 | 200 | 200 | Soliciting bids | 252125 | Y |  |  |  | 0 |  |  | 0 | [5 empty] | 252977
| UIF Northwestern FM relocation | 252 | UIF | 120 | 120 | 450 | Bids due this week | 252110 | Y |  |  |  | 0 |  |  | 0 | [5 empty] | 253052
2015084 | Eng-SUC DP Well 2A & LS A-1 & Genset | 255 | Sanlando |  | 15.8 | 15.8 | Contract awarded - Bailey | 252100 | N |  | 14760 |  | 14760 | 2063.97 | 1181.67 | 18005.64 | [5 empty] | 2303481.88
2016056 | Eng-SUC Shadow Hills diversion, F-2A & FM | 255 | Sanlando |  | 260.423 | 260.423 | Contract awarded - CPH/K-H | 256100 | N |  | 260423 | 3669.4 | 264092.4 | 1364.02 | 3985.95 | 269442.37 | [5 empty] | 2272931.846
2016057 | SUC Myrtle Lake Hills WM | 255 | Sanlando | 700 | 694.45 | 600 | Contract awarded - CFT | 255100 | N |  |  | 605811.45 | 605811.45 | 8998.76 | 12787.54 | 627597.75 | [5 empty] | 2273406.45
2016058 | SUC Wekiva WWTP Rehab | 255 | Sanlando | 1700 | 1803 | 1803 | Contract awarded - Evoqua | 255101 | Y |  |  | 346835.58 | 346835.58 | 4784.39 | 10063.3 | 361683.27 | [5 empty] | 2276720
2016067 | SUC Des Pinar W-2A & LS A-1 & Genset | 255 | Sanlando | 250 | 327.637 | 327.637 | Contract awarded - Thompson | 255101 | Y |  |  | 81564.53 | 81564.53 | 247.03 | 1642.69 | 83454.25 | [5 empty] | 2272328.274
2016074 | SUC I&I Deficiency Corrections Ph 2 | 255 | Sanlando | 1000 | 1573.884 | 1573.884 | Contracted - Insituform/Traverse | 255101 | N |  |  | 1289939.43 | 1289939.43 | 3768.14 | 16781.52 | 1310489.09 | [5 empty] | 2275577.768
2016087 | SUC Autumn Drive WM replacement | 255 | Sanlando | 100 | 98.97 | 98.97 | Contract awarded - Tri-Sure | 255100 | Y |  |  | 65250 | 65250 | 720.48 |  | 65970.48 | [5 empty] | 2271739.94
| SUC Shadow Hills diversion & F-2A | 255 | Sanlando | 4000 | 3983 | 3983 | Bids due 1/11/17 | 255101 | Y |  |  |  | 0 |  |  | 0 | [5 empty] | 267322
| SUC Wekiva blower replacement | 255 | Sanlando | 600 | 600 | 900 | Eng under way - bids at end of Jan? | 255101 | Y |  |  |  | 0 |  |  | 0 | [5 empty] | 257456
2017001 | SUC Lift Station RTU's | 255 | Sanlando | 420 | 353.2 | 591.2 | Contract awarded - North Lake/SCADAOne | 255101 | N |  |  |  | 0 |  |  | 0 | [5 empty] | 2273721.4
2011047 | Eng-SH Placida Rd/CR 775 Widening | 256 | Sandalhaven |  |  | 50 | Contract awarded - CPH & K-H (Wood) | 256100 | N |  | 33983.24 |  | 33983.24 | 407.2 | 12232.59 | 46623.03 | [5 empty] | 2267453
| SH Placida Road Utility Relocates | 256 | Sandalhaven | 250 | 250 | 225 | Bid f/ChCo contractor, need others | 256100 | Y |  |  |  | 0 |  |  | 0 | [5 empty] | 257081
None | Eng - PB WTP Electrical Improvements | 260 | Pennbrooke |  | 19.9 | 20 | Contract awarded - Baily | 260100 | N |  |  |  | 0 |  |  | 0 | [5 empty] | 260399.9
| PB WTP Electrical Improvements | 260 | Pennbrooke | 270 | 250 | 250 | Bid opening this week | 260100 | Y |  |  |  | 0 |  |  | 0 | [5 empty] | 261130
2016025 | UIF GIS Mapping Services | 855 | UIF | 350 | 350 | 244.321 | Contract awarded - K-H (Romano) | 855100 | N |  | 163103 |  | 163103 | 722.87 | 7093.07 | 170918.94 | [5 empty] | 2872924.321
2015191 | 2015 R/C UIF LP | 252 | UIF MR/PS/SM | N/A | N/A | N/A | No captime to be posted | 252109 | [13 empty] | 2267552
2015038 | 2016 R/C UIF Consolidated | 252 | UIF | N/A | N/A | N/A | No captime to be posted | 252109 | [13 empty] | 2267399
2016042 | Enterprise Asset Management/CMMS | 105 | Corporate |  |  |  | Shared Services - B&V | -
| Total CP spend |  |  | 22739 | 30667.961 | 33608.245 |  |  | includes closed CP's | [6 empty] | 6608.6664
need to add IDC and captime
CP# | COMPLETED PROJECTS | CO# |  | TY LETTER | PIS DATE | CAPEX | COMMENT | BU#
2013117 | Pennbrooke GST's | 260 | UI of Pennbrooke |  | 2013-12-23 |  |  | 260100
2012076 | Shangri-La Acquisition | 251 | LUSI |  | 2014-05-15 |  |  | None
2012084 | MC Phase 1 Coll System I&I Corrections | 250 | Mid-County Services Inc. |  | 2014-05-16 |  |  | 250100
2012089 | Weathersfield WTP Elec Improvements | 252 | UI of Florida |  | 2014-05-17 |  |  | 255110
2012105 | Buena Vista WM Phase 3 | 252 | UI of Florida |  | 2014-05-18 |  |  | 252106
2012106 | Summertree W-13 Hydro Tank Replacement | 252 | UI of Florida |  | 2014-05-19 |  |  | 252125
2012107 | LB Eminent Domain Action | 259 | Labrador Utilities Inc |  | 2014-05-20 |  |  | 259102
2012116 | MC Phase 2 Coll System Improvements | 250 | Mid-County Services Inc. |  | 2014-05-21 |  |  | 250100
2013025 | LUSI North Hydro Tank Rehabs | 251 | Lake Utility Services |  | 2014-05-22 |  |  | 251106
2013037 | Wekiva Belt Press | 255 | Sanlando Utilities Corp |  | 2014-05-23 |  |  | 255101 | [7 empty] | 0
2013066 | RP Electrical Improvements | 252 | UI of Florida |  | 2014-05-24 |  |  | 252118
2013067 | PH Electrical Improvements | 252 | UI of Florida |  | 2014-05-25 |  |  | 252116
2013083 | Cypress Lakes Corrosion Control Plant 3 | 248 | Cypress Lakes Utilities |  | 2014-05-26 |  |  | 248101
2013090 | Labrador Odor Control | 259 | Labrador Utilities Inc |  | 2014-05-27 |  | Proforma in prior rate case | 259101
2013093 | Sanlando I&I Investigation | 255 | Sanlando Utilities Corp |  | 2014-05-28 |  |  | 255101 | [7 empty] | 0
2013094 | PR Electrical Improvements | 252 | UI of Florida |  | 2014-05-29 |  |  | 252115
2013106 | Lake Tarpon WM Replacement | 252 | UI of Florida |  | 2014-05-30 |  |  | 252128
2014017 | LG WWTP South Plant Rehab | 251 | Lake Utility Services |  | 2014-12-01 |  |  | 251103
2014053 | Correct I&I deficiencies Sanlando Ph 1 | 255 | Sanlando Utilities Corp |  | 2014-10-07 |  |  | 252101 | [7 empty] | 0
2014065 | LUSI Packed Tower Improvements | 251 | Lake Utility Services |  | 2014-09-19 |  |  | 251102
2014075 | UIF Oakland Shores Elec Improvements | 252 | UI of Florida |  | 2014-12-01 |  |  | 252113
2014093 | US 27 WM Replacement/restoration | 251 | Lake Utility Services |  | 2014-12-01 |  |  | 251102
2012075 | SR 434 Widening, I-4 to Slade Dr | 255 | Sanlando Utilities Corp |  | 2015-10-27 |  | Proforma in prior rate case | 255103 | [7 empty] | 0
2014016 | UIF Golden Hills Service Lateral Replace | 252 | UI of Florida |  | 2015-04-23 |  | Proforma in prior rate case | 252129
2014018 | Summertree WQ Analysis | 252 | UI of Florida |  | 2015-04-15 |  | Proforma in prior rate case | 252125
2014043 | Eng-Wekiva WWTP Elec Improvements | 255 | Sanlando Utilities Corp |  | 2015-12-21 |  | Proforma in prior rate case | 252101 | [7 empty] | 0
2014049 | Wekiva EQ & Headworks | 255 | Sanlando Utilities Corp |  | 2015-05-22 |  | Proforma in prior rate case | 252101 | [7 empty] | 0
2014080 | Lake Groves WWTP Odor Control | 251 | Lake Utility Services |  | 2015-03-13 |  | TY capex | 251103
2014089 | Wekiva WWTP Elec Improvements | 255 | Sanlando Utilities Corp |  | 2015-12-21 |  | TY capex | 252101 | [7 empty] | 0
2014101 | Lake Groves Storage Building | 251 | Lake Utility Services |  | 2015-05-29 |  | TY capex | 251105
2014102 | UIF Bear Lake Elec Improvements | 252 | UI of Florida |  | 2015-02-28 |  | TY capex | 252121
2014119 | Mid-Co L/S 17 (Wilshire@Curlew Creek) | 250 | Mid County Services, Inc. |  | 2015-06-25 |  | TY capex | 250100
2014126 | Sandalhaven I&I Corrections North Area | 256 | UI of Sandalhaven |  | 2015-04-30 |  | TY capex | 256100
2015063 | SH FM & LS 4 Flow Diversion to EWD | 256 | UI of Sandalhaven |  | 2015-04-30 |  | Proforma in prior rate case | 256100
2015129 | SH WWTP Decommissioning | 256 | UI of Sandalhaven |  | 2015-12-29 |  | Proforma in prior rate case | 256100
2015168 | SUC Wekiva Underdrain Decommissioning | 255 | Sanlando Utilities Corp |  | 2015-11-13 |  | TY capex | 255101 | [7 empty] | 0
2014136 | Labrador GST Replacement | 259 | Labrador Utilities Inc |  | 2015-07-17 |  | Proforma in prior rate case | 259100
2014071 | Eng-UIF RP-CL WM Interconnect | 252 | UI of Florida | 85 | 2016-03-31 |  | Proforma in prior rate case | 252117
Co# | Company | Co# | Company |  | Co# |  | Company
241 | Tierra Verde | 250 | Mid-County |  | 256 |  | Sandalhaven | 252100 | Sem/Orange
242 | Lake Placid | 251 | LUSI |  | 259 |  | Labrador | 252101 | Pas/Pin
246 | Longwood | 252 | UIF |  | 260 |  | Pennbrooke | 252102 | Pasco Only
248 | Cypress Lakes | 254 | ACME WATER |  | 802 |  | BU Cost Center | 252103 | Marion
249 | Eagle Ridge/Cross Creek | 255 | Sanlando |  | 855 |  | FL Cost Center | 252104 | Sem Only
CLOSED PROJECTS, prior to 2014
2010148 | Bay County - Divestment | 257 | Bayside Utility Services |  | FL |  | Divestment
2000209 | Manhole rehab at Township Plaza | 246 | UI of Longwood |  | FL |  | Maintenance | 246100
2000958 | Park Ridge WM replacement | 252 | UI of Florida |  | FL |  | Maintenance | 252115
2004274 | Eng-LB WTP HSP Improvements | 259 | Labrador Utilities Inc |  | FL |  | EH&S Compliance | 259100
2009673 | LUSI Alternate Water Supply Plan | 251 | Lake Utility Services |  | FL |  | EH&S Compliance | 251106
2009719 | Des Pinar Raw WW Diversion Activities | 255 | Sanlando Utilities Corp |  | FL |  | EH&S Compliance | 255101
2009733 | Oranges-Vistas Raw WM | 251 | Lake Utility Services |  | FL |  | EH&S Compliance | 251106
2009754 | RP/Lincoln Heights I&I Repairs | 251 | UI of Florida |  | FL |  | EH&S Compliance | 252119
2009811 | Eng - Well #1 Replacement | 260 | Pennbrooke |  | FL |  | EH&S Compliance | 260100
2011006 | Lake Groves Headworks CIAC | 251 | Lake Utility Services Inc |  | FL |  | Maintenance | 251103
2011016 | Eng-Wekiva/Apopka RM | 255 | Sanlando Utilities Corp |  | FL |  | EH&S Compliance | 255102
2011033 | Lake Groves Biofilter Rehab | 251 | Lake Utility Services Inc |  | FL |  | Maintenance | 251102
2011046 | Wekiva filter replacement | 255 | Sanlando Utilities Corp |  | FL |  | EH&S Compliance | 255101
2011074 | Wekiva WWTP Grit Removal | 255 | Sanlando Utilities Corp |  | FL |  | Maintenance | 255101
2012027 | Wekiva - Apopka RM | 255 | Sanlando Utilities Corp |  | FL |  | EH&S Compliance | 255102
2012049 | SF-1 FM Replacement - Ravenna Park | 252 | UI of Florida |  | FL |  | EH&S Compliance | 252119
2012056 | Labrador WTP HSP Improvements | 259 | Labrador Utilities Inc |  | FL |  | Cost reduction | 259100
2012058 | LB Land Appraisal | 259 | Labrador Utilities Inc |  | FL |  | Cost reduction | 259102
2012074 | Weathersfield GV Replacement | 252 | UI of Florida |  | FL |  | EH&S Compliance | 252110
FL Rate Cases (closed)
2009538 | 2006 R/C BAYSIDE | 257 | Bayside Utilities Service |  |  |  | Rate Case
2009539 | 2006 R/C SANDY CREEK | 262 | Sandy Creek Utilities Service |  |  |  | Rate Case
2010162 | 2009 R/C Lake Placid | 242 | Lake Placid Utilities |  |  |  | Rate Case
2010277 | 2010 R/C Sandy Creek | 262 | Sandy Creek Utility Services |  |  |  | Rate Case
2010278 | 2010 R/C Bayside | 257 | Bayside Utility Services |  |  |  | Rate Case
2011004 | 2011 R/C Sanlando | 255 | Sanlando Utilities Corp |  |  |  | Rate Case
2011005 | 2011 R/C Sandalhaven | 256 | UI of Sandalhaven |  |  |  | Rate Case
2011007 | 2011 R/C Eagle Ridge | 249 | UI of Eagle Ridge |  |  |  | Rate Case
2011009 | 2011 R/C Labrador | 259 | Labrador Utilities Inc |  |  |  | Rate Case
2012010 | 2012 R/C Cypress Lakes | 248 | Cypress Lakes Utilitieies |  |  |  | Rate Case
2012011 | 2012 R/C Lake Placid | 242 | Lake Placid Utilities |  |  |  | Rate Case
2012012 | 2012 R/C Pennbrooke | 260 | UI of Pennbrooke |  |  |  | Rate Case
2012017 | 2012 R/C UIF | 262 | UI of Florida |  |  |  | Rate Case
2012015 | 2012 R/C Tierra Verde | 241 | Tierra Verde Utilities |  |  |  | Rate Case
2012053 | Global Docket - PP/Records | 855 | FL Cost Center |  |  |  | Other
2013072 | 2013 R/C Cypress Lakes | 248 | Cypress Lakes Utilities |  |  |  | Rate Case
2013073 | 2013 R/C Lake Placid | 242 | Lake Placid Utilities |  |  |  | Rate Case
2014046 | 2014 R/C Sanlando | 255 | Sanlando Utilities Corp |  |  |  | Rate Case
2014047 | 2014 R/C Mid-County | 250 | Mid County Services, Inc. |  |  |  | Rate Case
2014048 | 2014 R/C Labrador | 259 | Labrador Utilities Inc |  |  |  | Rate Case
2012090 | 2012 Wedgefield | 247 | Pluris Wedgefield |  |  |  | Rate Case
2015039 | 2015 R/C LUSI | 251 | Lake Utility Services |  | FL |  | Rate Case | 251105
2015040 | 2015 R/C Longwood | 246 | UI of Longwood |  | FL |  | Rate Case | 246100
2015041 | 2015 R/C Pennbrooke | 260 | UI of Pennbrooke |  | FL |  | Rate Case | 260102
2015037 | 2015 R/C Sandalhaven | 256 | UI of Sandalhaven |  |  |  | No captime to be posted | 256100
Deleted from proforma list
| MC South Plant Blower | 250 | Mid-County | 400 | 400 |  |  | 250100 | Y | X

## Capital Projects
FLORIDA PROFORMA CAPITAL PROJECTS
Closed Projects as of 12/31/2016
CP# | Job Description | TY Ltr 000's | Closing Date | Current Budget 000's | Status/Comment | BU | Ret's? | Proforma docs on server | Engineering | Other | Project Spend To Date | Cap Time | IDC | Total | Comment | NARUC | OBJ | $ Closed | Retirements
2014072 | LUSI SCADA | 471 | 2016-07-01 | 470 | Proforma in current R/C | 251105 | N |  |  | 464616.47 | 464.6165 | 75.4088 | 59.7644 | 599.7897 |  | 364.2 | 1365 | 599.7897
2015080 | UIF Ravenna Park/Crystal Lake I/C | 645 | 2016-09-09 | 646 | Proforma in current R/C | 252118 | Y |  |  | 646555.89 | 646.5559 | 42.8026 | 48.0019 | 737.3604 |  | 331 | 1125 | 211.3694
[16 empty] | 339.1 | 1055 | 525.991 | Y
2015082 | Eng-UIF WM Replacements | N/A | 2016-09-01 | 57 | Proforma in current R/C | 252100 | N |  | 57050 |  | 57.05 | 1.8208 | 4.1924 | 63.0632 |  | 331 | 1125 | 63.0632
2015097 | SUC I&I Investigation Ph 2 | 150 | 2016-07-01 | 152.5 | Proforma in current R/C | 255101 | N |  |  | 138783.86 | 139 | 8.6784 | 9.3621 | 157.0405 |  | 361 | 1350 | 156.8244
2015155 | LG Splitter Box Replacement | 83.46 | 2016-01-29 | 83.46 | Proforma in current R/C | 251103 | Y |  |  | 78000 | 78 | 6.9499 | 0.62151 | 85.5714 |  | 381.4 | 1410 | 85.5714 | Y
2015175 | Eng-LUSI TTHM/HAA5 Alternatives Study | 80 | 2016-11-19 | 79.25 | Proforma in current R/C | 251106 | N |  |  | 72273.47 | 79 | 4.5699 | 3.866 | 87.436 |  | 339.2 | 1160 | 80.7094
2016041 | SUC Markham Wds Rd Turn Lane WM Relo | 70 | 2016-07-31 | 65.9 | Proforma in current R/C | 255100 | Y |  |  | 59970 | 59.97 | 3.2077 | 1.2986 | 64.4763 |  | 331 | 1125 | 64.4763 | Y
2016075 | Cypress Lakes Sediment Removal | N/A | 2016-08-31 | 50.2 | Proforma in current R/C | 248101 | Y |  |  | 45095.29 | 45.0953 | 0.8234 |  | 45.9187 | Grit volume slightly less than expected. | 380.4 | 1400 | 45.9187
2016076 | LB WWTP Sediment Removal | N/A | 2016-09-23 | 61.137 | Proforma in current R/C | 259101 | Y |  |  | 50691.24 | 50.6912 | 1.9762 | 4.2199 | 56.8873 | Grit disposal costs were less than budgeted. | 380.4 | 1400 | 56.8873
None | 401 8th Ave GSM Replacement | 47.3 | 2016-03-03 | 84.673 | Proforma in current R/C | 241100 | Y |  |  | 47300 | 84 | 9.7738 |  | 93.7738 | Ph. 1 completed in 2015, $37K | 361 | 1350 | 93.7738 | Y
None | MC Field office | 65 | 2016-07-08 | 65 | Proforma in current R/C | 250100 | Y |  |  |  | 86.1137 | 5.941 |  | 92.0547 | Pinellas Co site plan requirements cost $20K | 354.4/390 | 1315/1455/1460 | 92.0547
None | C4500 Kodiak upfitting | 44 | 2016-09-16 | 46 | Proforma in current R/C | 855100 | N |  |  |  | 46.1573 |  |  | 46.1573 |  | 341.5 | 1555 | 46.1573
None | C2500HD Boom Truck | N/A | 2016-09-27 | 60 | Chassis/cab/boom truck/upfitting | 855100 | N |  |  |  | 61.0591 |  |  | 61.0591 |  | 341.5 | 1555 | 61.0591
None | Fleet replacements | N/A | 2016-07-22 | 350 | 10 Colorados | 855100 | Y |  |  |  | 312.5187 |  |  | 312.5187 | Purchased one fewer units than budgeted. | 341.5 | 1555 | 312.5187 | Y
|  | 1800.76 |  | 2352.12 | [9 empty] | 2503.107
Open Projects
CP# | Job Description | TY Ltr 000's | Pre-filed Testimony | Current Budget 000's | Status/Comment | BU | Ret's? | Proforma docs on server | Engineering | Other | Project Spend To Date | Cap Time | IDC | Total | Causes of cost escalators
2016088 | LW Church Ave FM relocates | 85 | 170 | 253.5 | Contract awarded - Tri-Sure | 246100 | Y |  |  | 164310 | 164.31 | 2.0585 | 0 | 166.3685 | City required removal/disposal of AC pipe.
None | LW I&I Study Longwood Groves | 50 | 90 | 50 | Either Altair or American InLine | 246100 | N | [6 empty] | 0
| LW I&I Longwood Groves | 450 | 350 | 350 | Soliciting bids | 246100 | N | [6 empty] | 0
None | Cypress Lake Hydro Tank #1 | 50 | 30 | 30 | No permitting required, need bids | 248100 | Y | [6 empty] | 0
| ER EQ tank-headworks-gates-trees | 350 | 350 | 800 | Eng under way - Excel | 249100 | Y | [6 empty] | 0 | Splitter box, field office, tree removal, fence mods
2015134 | MC Flow Monitoring & Analysis | 60 | 42.369 | 81 | Proforma in current R/C | 250100 | N |  | 76898.39 |  | 76.8984 | 6.0012 | 8.6553 | 91.5549 | Extended rental period by one month to get more data
2016032 | MC US 19 sidewalks/ utility relocations | 250 | 230 | 229 | Contract awarded - EESI & SPT | 250100 | Y |  | 42090.95 | 172901.71 | 214.9927 | 3.7273 | 10.0574 | 228.7773
2016085 | MC Electrical Improvements & Genset | 750 | 900 | 1100 | Eng under way - APG, bids open | 250100 | Y |  | 146400 |  | 146.4 | 2.2548 | 0.21672 | 148.8715 | Construction and materials cost increases
2016089 | MC Methanol pumps & TN/TP analyzer | 75 | 102 | 102 | Contract awarded - ASA, EDS, TriNova | 250100 | Y |  |  | 76974.36 | 76.9744 | 0.85804 | 1.4595 | 79.2919
| MC I&I remedies | 600 | 500 | 400 | Smoke testing done - Altair | 250100 | N | [6 empty] | 0
2015018 | Lake Groves SolarOrganite | 245 | 245 | 245 | Contract awarded - EcoSciences | 251103 | N |  |  | 236294.98 | 236.295 | 41.2672 | 36.4484 | 314.0105
2015083 | Eng-LUSI US 27 Ph 3 Utility relocations | 50 | 63 | 63 | Contract awarded - CPH (Morris) | 251106 | N |  |  | 61214.92 | 61.2149 | 1.633 | 6.3537 | 69.2016
2016009 | LUSI US 27 Ph 3 Utility Relocates | 1700 | 1806 | 1671 | Contract awarded - Traverse | 251106 | Y |  |  | 1651330.15 | 1651.3302 | 25.424 | 105.3908 | 1782.145
2016103 | LUSI Oswalt Rd WM relocates | 50 | 50 | 160.9 | Contract awarded - Traverse | 251106 | Y |  |  | 181399.14 | 181.3991 | 7.2752 | 2.7967 | 191.471 | County required removal/disposal of original WM.
2016133 | Eng-Lake Groves WTP upgrade TTHM/HAA5 |  | 450 | 330.8 | Contract awarded - K-H (Romano) | 251102 | N |  |  |  |  | 0.30551 |  | 0.30551
2015081 | Eng-UIF LWk & BL Elec Imprvmnts & RTUs |  | 85 | 85 | Contract awarded - Bailey | 252104 | Y |  |  | 35640 | 35.64 | 0.61863 | 2.4797 | 38.7383
2016068 | UIF LWk & BL Elec Imp & RTUs | 250 | 238.23 | 238 | Contract awarded - Thompson | 252104 | Y |  |  | 108085.38 | 108.0854 | 0.88517 | 2.1655 | 111.1361
2016091 | UIF Lake Tarpon WM replacement | 725 | 800 | 1218.15 | Contract awarded - Rowland | 252128 | Y |  | 28638.75 |  | 28.6388 | 2.6045 | 0.74993 | 31.9932 | Added cost to install service lines and reconnect.
2016093 | UIF Bear Lake WM replacement |  | 1485.27 | 1485.27 | Contract awarded - Traverse Grp | 252122 | Y |  |  | 7719.25 | 7.7192 | 0.50295 | 0.00933 | 8.2315
2016094 | UIF Crescent Heights WM replacement | 809 | 1806 | 1806 | Contract awarded - CFT | 252123 | Y |  |  | 6225.1 | 6.2251 | 0.1441 | 0.0017 | 6.3709
2016095 | UIF Crystal Lake WM replacement |  | 1574 | 1585.933 | Contract awarded - ECO 2000 | 252117 | Y |  |  | 10127.7 | 10.1277 |  |  | 10.1277
2016096 | UIF Little Wekiva WM replacement |  | 521.681 | 521.681 | Contract awarded - Traverse Grp | 252114 | Y |  |  | 225200.65 | 225.2006 | 0.08234 |  | 225.283
2016097 | UIF Oakland Shores WM replacement | 2425 | 1571.701 | 1571.701 | Contract awarded - Traverse Grp | 252113 | Y |  |  | 114843.38 | 114.8434 | 0.61755 | 0.00155 | 115.4625
2016098 | UIF Phillips WM replacement & CL I/C |  | 1188.247 | 1188.247 | Contract awarded - ECO 2000 | 252116 | Y |  |  | 7748.86 | 7.7489 |  |  | 7.7489
2016099 | UIF Ravenna Park WM replacement | 2665 | 2160.808 | 2160.808 | Contract awarded - ECO 2000 | 252118 | Y |  |  | 105787.29 | 105.7873 | 0.94691 | 1.5553 | 108.2895
2016102 | UIF Buena Vista/OW WM replacement | 1200 | 1200 | 1916.9 | Contract awarded - S&S | 252106 | Y |  |  | 10160 | 10.16 | 0.46143 | 0.0357 | 10.6571 | Added cost to install service lines and reconnect.
2017006 | UIF Summertree Well Abandonment | 200 | 200 | 177 | Soliciting bids | 252125 | Y | [6 empty] | 0
2017004 | UIF Northwestern FM relocation | 120 | 120 | 689 | Bids due this week | 252110 | Y | [6 empty] | 0 | Longer route, AC pipe removal costs
2015084 | Eng-SUC DP Well 2A & LS A-1 & Genset |  | 15.8 | 15.8 | Contract awarded - Bailey | 252100 | N |  | 14760 |  | 14.76 | 2.064 | 1.1817 | 18.0056
2016056 | Eng-SUC Shadow Hills diversion, F-2A & FM |  | 260.423 | 260.423 | Contract awarded - CPH/K-H | 256100 | N |  | 260423 | 3669.4 | 264.0924 | 1.364 | 3.9859 | 269.4424
2016057 | SUC Myrtle Lake Hills WM | 700 | 694.45 | 600 | Contract awarded - CFT | 255100 | N |  |  | 605811.45 | 605.8115 | 8.9988 | 12.7875 | 627.5978
2016058 | SUC Wekiva WWTP Rehab | 1700 | 1803 | 1803 | Contract awarded - Evoqua | 255101 | Y |  |  | 346835.58 | 346.8356 | 4.7844 | 10.0633 | 361.6833
2016067 | SUC Des Pinar W-2A & LS A-1 & Genset | 250 | 327.637 | 327.637 | Contract awarded - Thompson | 255101 | Y |  |  | 81564.53 | 81.5645 | 0.24703 | 1.6427 | 83.4543 | Construction and materials cost increases
2016074 | SUC I&I Deficiency Corrections Ph 2 | 1000 | 1573.884 | 1573.884 | Contracted - Insituform/Traverse | 255101 | N |  |  | 1289939.43 | 1289.9394 | 3.7681 | 16.7815 | 1310.4891 | 15,000 LF additional pipe inspected; deficiencies worse than expected.
2016087 | SUC Autumn Drive WM replacement | 100 | 98.97 | 98.97 | Contract awarded - Tri-Sure | 255100 | Y |  |  | 65250 | 65.25 | 0.72048 |  | 65.9705
| SUC Shadow Hills diversion & F-2A | 4000 | 3983 | 6000 | Bids due 1/11/17 | 255101 | Y | [6 empty] | 0 | Added field office, shed; construction cost increases
| SUC Wekiva blower replacement | 600 | 600 | 1000 | Eng under way - bids at end of Jan? | 255101 | Y | [6 empty] | 0
2017001 | SUC Lift Station RTU's | 420 | 353.2 | 591.2 | Contract awarded - North Lake/SCADAOne | 255101 | N | [6 empty] | 0 | Construction and materials cost increases
2011047 | Eng-SH Placida Rd/CR 775 Widening |  |  | 50 | Contract awarded - CPH & K-H (Wood) | 256100 | N |  | 33983.24 |  | 33.9832 | 0.4072 | 12.2326 | 46.623
| SH Placida Road Utility Relocates | 250 | 250 | 278 | Bid f/ChCo contractor, need others | 256100 | Y | [6 empty] | 0 | Construction and materials cost increases
None | Eng - PB WTP Electrical Improvements |  | 19.9 | 20 | Contract awarded - Baily | 260100 | N | [6 empty] | 0
2017005 | PB WTP Electrical Improvements | 270 | 250 | 250 | Bid opening this week | 260100 | Y |  |  |  | 0 |  |  | 0
2016025 | UIF GIS Mapping Services | 350 | 350 | 244.321 | Contract awarded - K-H (Romano) | 855100 | N |  | 163103 |  | 163.103 | 0.72287 | 7.0931 | 170.9189
| Total CP spend | 22739 | 30667.961 | 35975.245 |  |  | includes closed CP's | [6 empty] | 9203.3283
need to add IDC and captime
CP# | COMPLETED PROJECTS | TY LETTER | PIS DATE | CAPEX | COMMENT | BU#
2013117 | Pennbrooke GST's |  | 2013-12-23 |  |  | 260100
2012076 | Shangri-La Acquisition |  | 2014-05-15 |  |  | None
2012084 | MC Phase 1 Coll System I&I Corrections |  | 2014-05-16 |  |  | 250100
2012089 | Weathersfield WTP Elec Improvements |  | 2014-05-17 |  |  | 255110
2012105 | Buena Vista WM Phase 3 |  | 2014-05-18 |  |  | 252106
2012106 | Summertree W-13 Hydro Tank Replacement |  | 2014-05-19 |  |  | 252125
2012107 | LB Eminent Domain Action |  | 2014-05-20 |  |  | 259102
2012116 | MC Phase 2 Coll System Improvements |  | 2014-05-21 |  |  | 250100
2013025 | LUSI North Hydro Tank Rehabs |  | 2014-05-22 |  |  | 251106
2013037 | Wekiva Belt Press |  | 2014-05-23 |  |  | 255101 | [7 empty] | 0
2013066 | RP Electrical Improvements |  | 2014-05-24 |  |  | 252118
2013067 | PH Electrical Improvements |  | 2014-05-25 |  |  | 252116
2013083 | Cypress Lakes Corrosion Control Plant 3 |  | 2014-05-26 |  |  | 248101
2013090 | Labrador Odor Control |  | 2014-05-27 |  | Proforma in prior rate case | 259101
2013093 | Sanlando I&I Investigation |  | 2014-05-28 |  |  | 255101 | [7 empty] | 0
2013094 | PR Electrical Improvements |  | 2014-05-29 |  |  | 252115
2013106 | Lake Tarpon WM Replacement |  | 2014-05-30 |  |  | 252128
2014017 | LG WWTP South Plant Rehab |  | 2014-12-01 |  |  | 251103
2014053 | Correct I&I deficiencies Sanlando Ph 1 |  | 2014-10-07 |  |  | 252101 | [7 empty] | 0
2014065 | LUSI Packed Tower Improvements |  | 2014-09-19 |  |  | 251102
2014075 | UIF Oakland Shores Elec Improvements |  | 2014-12-01 |  |  | 252113
2014093 | US 27 WM Replacement/restoration |  | 2014-12-01 |  |  | 251102
2012075 | SR 434 Widening, I-4 to Slade Dr |  | 2015-10-27 |  | Proforma in prior rate case | 255103 | [7 empty] | 0
2014016 | UIF Golden Hills Service Lateral Replace |  | 2015-04-23 |  | Proforma in prior rate case | 252129
2014018 | Summertree WQ Analysis |  | 2015-04-15 |  | Proforma in prior rate case | 252125
2014043 | Eng-Wekiva WWTP Elec Improvements |  | 2015-12-21 |  | Proforma in prior rate case | 252101 | [7 empty] | 0
2014049 | Wekiva EQ & Headworks |  | 2015-05-22 |  | Proforma in prior rate case | 252101 | [7 empty] | 0
2014080 | Lake Groves WWTP Odor Control |  | 2015-03-13 |  | TY capex | 251103
2014089 | Wekiva WWTP Elec Improvements |  | 2015-12-21 |  | TY capex | 252101 | [7 empty] | 0
2014101 | Lake Groves Storage Building |  | 2015-05-29 |  | TY capex | 251105
2014102 | UIF Bear Lake Elec Improvements |  | 2015-02-28 |  | TY capex | 252121
2014119 | Mid-Co L/S 17 (Wilshire@Curlew Creek) |  | 2015-06-25 |  | TY capex | 250100
2014126 | Sandalhaven I&I Corrections North Area |  | 2015-04-30 |  | TY capex | 256100
2015063 | SH FM & LS 4 Flow Diversion to EWD |  | 2015-04-30 |  | Proforma in prior rate case | 256100
2015129 | SH WWTP Decommissioning |  | 2015-12-29 |  | Proforma in prior rate case | 256100
2015168 | SUC Wekiva Underdrain Decommissioning |  | 2015-11-13 |  | TY capex | 255101 | [7 empty] | 0
2014136 | Labrador GST Replacement |  | 2015-07-17 |  | Proforma in prior rate case | 259100
2014071 | Eng-UIF RP-CL WM Interconnect | 85 | 2016-03-31 |  | Proforma in prior rate case | 252117
Co# | Company |  | Co# |  | Company
241 | Tierra Verde |  | 256 |  | Sandalhaven | 252100 | Sem/Orange
242 | Lake Placid |  | 259 |  | Labrador | 252101 | Pas/Pin
246 | Longwood |  | 260 |  | Pennbrooke | 252102 | Pasco Only
248 | Cypress Lakes |  | 802 |  | BU Cost Center | 252103 | Marion
249 | Eagle Ridge/Cross Creek |  | 855 |  | FL Cost Center | 252104 | Sem Only
CLOSED PROJECTS, prior to 2014
2010148 | Bay County - Divestment |  | FL |  | Divestment
2000209 | Manhole rehab at Township Plaza |  | FL |  | Maintenance | 246100
2000958 | Park Ridge WM replacement |  | FL |  | Maintenance | 252115
2004274 | Eng-LB WTP HSP Improvements |  | FL |  | EH&S Compliance | 259100
2009673 | LUSI Alternate Water Supply Plan |  | FL |  | EH&S Compliance | 251106
2009719 | Des Pinar Raw WW Diversion Activities |  | FL |  | EH&S Compliance | 255101
2009733 | Oranges-Vistas Raw WM |  | FL |  | EH&S Compliance | 251106
2009754 | RP/Lincoln Heights I&I Repairs |  | FL |  | EH&S Compliance | 252119
2009811 | Eng - Well #1 Replacement |  | FL |  | EH&S Compliance | 260100
2011006 | Lake Groves Headworks CIAC |  | FL |  | Maintenance | 251103
2011016 | Eng-Wekiva/Apopka RM |  | FL |  | EH&S Compliance | 255102
2011033 | Lake Groves Biofilter Rehab |  | FL |  | Maintenance | 251102
2011046 | Wekiva filter replacement |  | FL |  | EH&S Compliance | 255101
2011074 | Wekiva WWTP Grit Removal |  | FL |  | Maintenance | 255101
2012027 | Wekiva - Apopka RM |  | FL |  | EH&S Compliance | 255102
2012049 | SF-1 FM Replacement - Ravenna Park |  | FL |  | EH&S Compliance | 252119
2012056 | Labrador WTP HSP Improvements |  | FL |  | Cost reduction | 259100
2012058 | LB Land Appraisal |  | FL |  | Cost reduction | 259102
2012074 | Weathersfield GV Replacement |  | FL |  | EH&S Compliance | 252110
FL Rate Cases (closed)
2009538 | 2006 R/C BAYSIDE |  |  |  | Rate Case
2009539 | 2006 R/C SANDY CREEK |  |  |  | Rate Case
2010162 | 2009 R/C Lake Placid |  |  |  | Rate Case
2010277 | 2010 R/C Sandy Creek |  |  |  | Rate Case
2010278 | 2010 R/C Bayside |  |  |  | Rate Case
2011004 | 2011 R/C Sanlando |  |  |  | Rate Case
2011005 | 2011 R/C Sandalhaven |  |  |  | Rate Case
2011007 | 2011 R/C Eagle Ridge |  |  |  | Rate Case
2011009 | 2011 R/C Labrador |  |  |  | Rate Case
2012010 | 2012 R/C Cypress Lakes |  |  |  | Rate Case
2012011 | 2012 R/C Lake Placid |  |  |  | Rate Case
2012012 | 2012 R/C Pennbrooke |  |  |  | Rate Case
2012017 | 2012 R/C UIF |  |  |  | Rate Case
2012015 | 2012 R/C Tierra Verde |  |  |  | Rate Case
2012053 | Global Docket - PP/Records |  |  |  | Other
2013072 | 2013 R/C Cypress Lakes |  |  |  | Rate Case
2013073 | 2013 R/C Lake Placid |  |  |  | Rate Case
2014046 | 2014 R/C Sanlando |  |  |  | Rate Case
2014047 | 2014 R/C Mid-County |  |  |  | Rate Case
2014048 | 2014 R/C Labrador |  |  |  | Rate Case
2012090 | 2012 Wedgefield |  |  |  | Rate Case
2015039 | 2015 R/C LUSI |  | FL |  | Rate Case | 251105
2015040 | 2015 R/C Longwood |  | FL |  | Rate Case | 246100
2015041 | 2015 R/C Pennbrooke |  | FL |  | Rate Case | 260102
2015037 | 2015 R/C Sandalhaven |  |  |  | No captime to be posted | 256100
Deleted from proforma list
| MC South Plant Blower | 400 | 400 |  |  | 250100 | Y | X | [6 empty] | Project postponed.

## Retirements
Do Ty | Doc Number | Batch Number | G/L Date | Explanation | LT 1 Amount | Explanation -Remark- | Asset Number | Doc Co | P C | Cur Cod | Exchange Rate | LT | Ledger Type | Batch Type | Batch Date | JE Line Number | Units | Service/ Tax Date | Transaction Originator | User ID | Business Unit | Home Business Unit | Historical Rate | Historical Date | Pha se | Categories Work Order 01
JE | 310408 | 253449 | 2016-11-30 | NOV 16 RETIREMENTS - CP CLOSE | -17040.44 | CP 2015080 RETIREMENT 1990 | 107883 | 00252 | P | USD | 0 | AA | General Ledger | General Accounting | 2016-12-07 | 3 | 0 | 2016-11-30 | PSAMPSEL | DSLODOLC | 252 |  | 0 |  |  | .
JE | 310408 | 253449 | 2016-11-30 | NOV 16 RETIREMENTS - CP CLOSE | -28400.74 | CP 2015080 RETIREMENT 1990 | 107927 | 00252 | P | USD | 0 | AA | General Ledger | General Accounting | 2016-12-07 | 1 | 0 | 2016-11-30 | PSAMPSEL | DSLODOLC | 252 |  | 0 |  |  | .
Retirements for |  |  |  |  | -45441.18
2015080 | UIF Ravenna Park/Crystal Lake I/C |  |  |  | Accumulated Depreciation account 1850 for same amount
NARUC account 339.1
Do Ty | Doc Number | Batch Number | G/L Date | Explanation | LT 1 Amount | Explanation -Remark- | Asset Number | Purchase Order | LT 1 Debit | Business Unit | Doc Co | P C | LT | Ledger Type | Batch Type | Batch Date | Line Extension | JE Line Number | Service/ Tax Date | Transaction Originator | User ID | Home Business Unit | Historical Rate | Historical Date | Pha se | Categories Work Order 01
JE | 307266 | 229084 | 2016-01-31 | JAN 16 RETIREMENTS - CP CLOSE | -27518.66 | CP RETIREMENT 96807 2000 | 96807 |  |  | 251 | 00251 | P | AA | General Ledger | General Accounting | 2016-02-08 |  | 1 | 2016-01-31 | PSAMPSEL | PSAMPSEL |  | 0 |  |  | .
JE | 309865 | 248660 | 2016-09-30 | CP RETIREMENT ADJUSTMENTS 2016 | 5037.31 | CP 2015155 RETIREMENT ADJUSTME | 96807 |  | 5037.31 | 251 | 00182 | P | AA | General Ledger | General Accounting | 2016-10-07 |  | 5 | 2016-09-30 | PSAMPSEL | CKIM |  | 0 |  |  | .
Retirements for |  |  |  |  | -22481.35
2015155 | Eng-LUSI TTHM/HAA5 Alternatives Study |  |  |  | Accumulated Depr. Acct 2170 for same amount
NARUC account 381.4
Do Ty | Doc Number | Batch Number | G/L Date | Explanation | LT 1 Amount | Explanation -Remark- | Asset Number | Purchase Order | CO | Business Unit | Doc Co | P C | LT | Ledger Type | Batch Type | Batch Date | Line Extension | JE Line Number | Service/ Tax Date | Transaction Originator | User ID | Home Business Unit | Historical Rate | Historical Date | Pha se | Categories Work Order 01
JE | 309862 | 248658 | 2016-09-30 | SEPT 16 RETIREMENTS - CP CLOSE | -6920.78 | CP 2016041 RETIREMENT 1980 | 108277 |  | 255 | 182 | P | AA | General Ledger | General Accounting | 2016-10-07 |  | 2 | [10 empty] | 2016-09-30 | PSAMPSEL | CKIM | .
Retirements for: |  |  |  |  | Accumulated Depr. Acct 1920 for same amount
2016041 | SUC Markham Wds Rd Turn Lane WM Relo
NARUC account 331
Co | Document Number | Batch Number | G/L Date | Explanation Alpha Name | Amount | Explanation -Remark- | Business Unit | Obj Acct | Region | Asset ID | Purchase Order | PO Originator | PO Do Ty | Rev Void | Do Ty | Sub | Sub Type | Sub- ledger | Per No | FY | Units | Address Number | LT | Doc Co | Bth Ty | Posted Code | JE Line Number | Line Extension | Reconciled
241 | 308116 | 233704 | 2016-03-31 | RETIREMENT | -21936.23 | Retired: 1991 PO 00209253 | 241 | 1350 | Florida | 100600 |  |  |  |  | AX |  |  |  | 3 | 16 |  |  | AA | 110 | G | P | 566
Retirement for |  |  |  |  | Accumulated Depr. Acct 2110 for same amount
401 8th Ave GSM Replacement |  |  | 241
Co | Business Unit | Obj Acct | Amount | G/L Date | Region | Explanation Alpha Name | Explanation -Remark- | Asset ID | Document Number | Batch Number | Purchase Order | PO Originator | PO Do Ty | Rev Void | Do Ty | Sub | Sub Type | Sub- ledger | Per No | FY | Units | Address Number | LT | Doc Co | Bth Ty | Posted Code | JE Line Number | Line Extension | Reconciled
855 | 855 | 1555 | -16639.11 | 2016-02-18 | Florida | RET SOLD VEH #0739 | TRANSPORTATION EQPT WTR | 160278 | 307343 | 229856 |  |  |  |  | AD |  |  |  | 2 | 16 |  |  | AA | 855 | Z | P | 1
855 | 855 | 1555 | -20347.01 | 2016-03-18 | Florida | RET SOLD VEH 0812 | TRANSPORTATION EQPT WTR | 160295 | 307960 | 232762 |  |  |  |  | AD |  |  |  | 3 | 16 |  |  | AA | 855 | Z | P | 1
855 | 855 | 1555 | -20467.74 | 2016-03-18 | Florida | RET SOLD VEH 0833 | TRANSPORTATION EQPT WTR | 2001697 | 307961 | 232765 |  |  |  |  | AD |  |  |  | 3 | 16 |  |  | AA | 855 | Z | P | 1
855 | 855 | 1555 | -20561.44 | 2016-04-14 | Florida | RET SOLD VEH 0809 | TRANSPORTATION EQPT WTR | 160292 | 308185 | 234363 |  |  |  |  | AD |  |  |  | 4 | 16 |  |  | AA | 855 | Z | P | 1
855 | 855 | 1555 | -16921.83 | 2016-04-26 | Florida | RET VEH 0741 #160279 | TRANSPORTATION EQPT WTR | 160279 | 308241 | 235147 |  |  |  |  | AD |  |  |  | 4 | 16 |  |  | AA | 855 | Z | P | 1
855 | 855 | 1555 | -26093.43 | 2016-10-12 | Florida | RET VEH 1149 #1005597 | TRANSPORTATION EQPT WTR | 1005597 | 309906 | 249001 |  |  |  |  | AD |  |  |  | 10 | 16 |  |  | AA | 855 | Z | P | 1
855 | 855 | 1555 | -24387.14 | 2016-12-12 | Florida | RET VEH 1145 #1005568 | TRANSPORTATION EQPT WTR | 1005568 | 314433 | 253817 |  |  |  |  | AD |  |  |  | 12 | 16 |  |  | AA | 855 | Z | P | 1
855 | 855 | 1555 | -18648.38 | 2016-12-20 | Florida | RET VEH 0901 #1003917 | TRANSPORTATION EQPT WTR | 1003917 | 317729 | 254446 |  |  |  |  | AD |  |  |  | 12 | 16 |  |  | AA | 855 | Z | P | 1
-164066.08
Retired Vehicles |  |  | Accumulated Depr. Acct 2300 for same amount

## Sheet2 (hidden)
CP# | Job Description | Co | System | TY Ltr 000's | Testimony 000's | Forecast 000's
2014072 | LUSI SCADA | 251 | LUSI | 471 | 2016-07-01 | 470