## PD Executive Summary w Inc
2020-2029 Storm Protection Plan 'SPP' Program Cost Activities | [7 empty] | GULF 000140 20200070-EI
($ in Millions)
SPP Programs (1)(2) | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | Total SPP Cost | Annual Average Cost
Distribution Mainline Feeder Patrol Program
Operating Expenses | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 1.6 | 0.16
Capital Expenditures | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 3 | 0.3
Total | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 4.6 | 0.46
Distribution Inspection Program
Operating Expenses | 0.77 | 0.82 | 0.82 | 0.82 | 0.82 | 0.82 | 0.82 | 0.82 | 0.82 | 0.82 | 8.15 | 0.815
Capital Expenditures | 2.2 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 24.7 | 2.47
Total | 2.97 | 3.32 | 3.32 | 3.32 | 3.32 | 3.32 | 3.32 | 3.32 | 3.32 | 3.32 | 32.85 | 3.285
Transmission Inspection Program
Operating Expenses | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 2.5 | 0.25
Capital Expenditures | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 30 | 3
Total | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 32.5 | 3.25
Substation Inspection Program
Operating Expenses | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1 | 0.1
Capital Expenditures | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 1.5 | 0.15
Total | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 2.5 | 0.25
Distribution Feeder Hardening Program
Operating Expenses | 0.58 | 2.13 | 2.13 | 2.13 | 2.13 | 2.13 | 2.13 | 2.13 | 2.13 | 2.13 | 19.75 | 1.975
Capital Expenditures | 6.5 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 26.4 | 244.1 | 24.41
Total | 7.08 | 28.53 | 28.53 | 28.53 | 28.53 | 28.53 | 28.53 | 28.53 | 28.53 | 28.53 | 263.85 | 26.385
Distribution Automation Program
Operating Expenses | 0.2 | 0.38 | 0.3 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 2 | 0.2
Capital Expenditures | 5 | 9.5 | 7.6 | 3.9 | 3.9 | 3.9 | 3.9 | 3.9 | 3.9 | 3.9 | 49.4 | 4.94
Total | 5.2 | 9.88 | 7.9 | 4.06 | 4.06 | 4.06 | 4.06 | 4.06 | 4.06 | 4.06 | 51.4 | 5.14
Distribution Hardening - Lateral Undergrounding Program
Operating Expenses | 0 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 1.62 | 0.162
Capital Expenditures | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 45 | 4.5
Total | 0 | 5.18 | 5.18 | 5.18 | 5.18 | 5.18 | 5.18 | 5.18 | 5.18 | 5.18 | 46.62 | 4.662
Wood Structure Replacement Program
Operating Expenses | 0.07 | 0.4 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 5.27 | 0.527
Capital Expenditures | 3.5 | 19.6 | 29.4 | 29.4 | 29.4 | 29.4 | 29.4 | 29.4 | 29.4 | 29.4 | 258.3 | 25.83
Total | 3.57 | 20 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 263.57 | 26.357
Substation Flood Monitoring Program
Operating Expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capital Expenditures | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0.4
Total | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0.4
Substation Resiliency Program
Operating Expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capital Expenditures | 0.72 | 24.5 | 24.5 | 24.5 | 24.5 | 24.5 | 24.5 | 24.5 | 24.5 | 24.5 | 221.22 | 22.122
Total | 0.72 | 24.5 | 24.5 | 24.5 | 24.5 | 24.5 | 24.5 | 24.5 | 24.5 | 24.5 | 221.22 | 22.122
Vegetation Management - Distribution Program
Operating Expenses | 5.03 | 4.68 | 4.69 | 4.7 | 4.7 | 4.71 | 4.71 | 4.71 | 4.71 | 4.71 | 47.35 | 4.735
Capital Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 5.03 | 4.68 | 4.69 | 4.7 | 4.7 | 4.71 | 4.71 | 4.71 | 4.71 | 4.71 | 47.35 | 4.735
Vegetation Management - Transmission Program
Operating Expenses | 2.5 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 28.33 | 2.833
Capital Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 2.5 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 28.33 | 2.833
Total SPP Cost
Operating Expenses | 9.66 | 11.97 | 12.1 | 11.97 | 11.97 | 11.98 | 11.98 | 11.98 | 11.98 | 11.98 | 117.57 | 11.757
Capital Expenditures | 22.37 | 91.95 | 99.85 | 96.15 | 95.15 | 95.15 | 95.15 | 95.15 | 95.15 | 95.15 | 881.22 | 88.122
Total | 32.03 | 103.92 | 111.95 | 108.12 | 107.12 | 107.13 | 107.13 | 107.13 | 107.13 | 107.13 | 998.79 | 99.879
Imbedded Distribution - Pole Inspection Program
Embedded Operating Expenses | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 4.8 | 0.48
Embedded Capital Expenditures | 1.9167 | 1.9167 | 1.9167 | 1.9167 | 1.9167 | 1.9167 | 1.9167 | 1.9167 | 1.9167 | 1.9167 | 19.1667 | 1.9167
Total Embedded | 2.3967 | 2.3967 | 2.3967 | 2.3967 | 2.3967 | 2.3967 | 2.3967 | 2.3967 | 2.3967 | 2.3967 | 23.9667 | 2.3967
Imbedded Feeder Hardening - Distribution / Mainline Feeder Patrol Programs
Embedded Operating Expenses | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 2.1 | 0.21
Embedded Capital Expenditures | 1.2737 | 1.2737 | 1.2737 | 1.2737 | 1.2737 | 1.2737 | 1.2737 | 1.2737 | 1.2737 | 1.2737 | 12.7371 | 1.2737
Total Embedded | 1.4837 | 1.4837 | 1.4837 | 1.4837 | 1.4837 | 1.4837 | 1.4837 | 1.4837 | 1.4837 | 1.4837 | 14.8371 | 1.4837
Imbedded Distribution Automation Program
Embedded Operating Expenses | 0.016126 | 0.016126 | 0.016126 | 0.016126 | 0.016126 | 0.016126 | 0.016126 | 0.016126 | 0.016126 | 0.016126 | 0.16126 | 0.016126
Embedded Capital Expenditures | 2.0723 | 2.0723 | 2.0723 | 2.0723 | 2.0723 | 2.0723 | 2.0723 | 2.0723 | 2.0723 | 2.0723 | 20.7225 | 2.0723
Total Embedded | 2.0884 | 2.0884 | 2.0884 | 2.0884 | 2.0884 | 2.0884 | 2.0884 | 2.0884 | 2.0884 | 2.0884 | 20.8838 | 2.0884
Imbedded Transmission Structure Inspections and Hardening Program
Embedded Operating Expenses | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 2.4 | 0.24
Embedded Capital Expenditures | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 50 | 5
Total Embedded | 5.24 | 5.24 | 5.24 | 5.24 | 5.24 | 5.24 | 5.24 | 5.24 | 5.24 | 5.24 | 52.4 | 5.24
Imbedded Vegetation Management - Distribution Program
Embedded Operating Expenses | 5.95 | 5.95 | 5.95 | 5.95 | 5.95 | 5.95 | 5.95 | 5.95 | 5.95 | 5.95 | 59.5 | 5.95
Embedded Capital Expenditures | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 7.1 | 0.71
Total Embedded | 6.66 | 6.66 | 6.66 | 6.66 | 6.66 | 6.66 | 6.66 | 6.66 | 6.66 | 6.66 | 66.6 | 6.66
Total Embedded Operating Expenses | 6.8961 | 6.8961 | 6.8961 | 6.8961 | 6.8961 | 6.8961 | 6.8961 | 6.8961 | 6.8961 | 6.8961 | 68.9613 | 6.8961
Total Embedded Capital Expenditures | 10.9726 | 10.9726 | 10.9726 | 10.9726 | 10.9726 | 10.9726 | 10.9726 | 10.9726 | 10.9726 | 10.9726 | 109.7263 | 10.9726
Total Embedded | 17.8688 | 17.8688 | 17.8688 | 17.8688 | 17.8688 | 17.8688 | 17.8688 | 17.8688 | 17.8688 | 17.8688 | 178.6876 | 17.8688
Total Incremental Operating Expenses | 2.7639 | 5.0739 | 5.2039 | 5.0739 | 5.0739 | 5.0839 | 5.0839 | 5.0839 | 5.0839 | 5.0839 | 48.6087 | 4.8609
Total Incremental Capital Expenditures | 11.3974 | 80.9774 | 88.8774 | 85.1774 | 84.1774 | 84.1774 | 84.1774 | 84.1774 | 84.1774 | 84.1774 | 771.4937 | 77.1494
Total Incremental | 14.1612 | 86.0512 | 94.0812 | 90.2512 | 89.2512 | 89.2612 | 89.2612 | 89.2612 | 89.2612 | 89.2612 | 820.1024 | 82.0102
(1) See also 2020 - 2022 project level details provided in Appendix
(2) Costs Include previous year(s) projects carried over to current year, current year's project costs and future year's preliminary project costs (e.g., engineering)

## PD Exec Summary High Lev
2020-2029 Storm Protection Plan 'SPP' Program Cost | [7 empty] | GULF 000141 20200070-EI
($ in Millions)
SPP Programs (1)(2) | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | Total SPP Cost | Annual Average Cost
Distribution Inspection Program
Operating Expenses | 0.93 | 0.98 | 0.98 | 0.98 | 0.98 | 0.98 | 0.98 | 0.98 | 0.98 | 0.98 | 9.75 | 0.975
Capital Expenditures | 2.5 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 27.7 | 2.77
Total | 3.43 | 3.78 | 3.78 | 3.78 | 3.78 | 3.78 | 3.78 | 3.78 | 3.78 | 3.78 | 37.45 | 3.745
Transmission Inspection Program
Operating Expenses | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 3.5 | 0.35
Capital Expenditures | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 31.5 | 3.15
Total | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 35 | 3.5
Distribution Feeder Hardening Program
Operating Expenses | 0.78 | 2.51 | 2.43 | 2.29 | 2.29 | 2.29 | 2.29 | 2.29 | 2.29 | 2.29 | 21.75 | 2.175
Capital Expenditures | 11.5 | 35.9 | 34 | 30.3 | 30.3 | 30.3 | 30.3 | 30.3 | 30.3 | 30.3 | 293.5 | 29.35
Total | 12.28 | 38.41 | 36.43 | 32.59 | 32.59 | 32.59 | 32.59 | 32.59 | 32.59 | 32.59 | 315.25 | 31.525
Distribution Hardening - Lateral Undergrounding Program
Operating Expenses | 0 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 1.62 | 0.162
Capital Expenditures | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 45 | 4.5
Total | 0 | 5.18 | 5.18 | 5.18 | 5.18 | 5.18 | 5.18 | 5.18 | 5.18 | 5.18 | 46.62 | 4.662
Transmission Hardening Program
Operating Expenses | 0.07 | 0.4 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 5.27 | 0.527
Capital Expenditures | 5.22 | 45.1 | 54.9 | 54.9 | 53.9 | 53.9 | 53.9 | 53.9 | 53.9 | 53.9 | 483.52 | 48.352
Total | 5.29 | 45.5 | 55.5 | 55.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 488.79 | 48.879
Vegetation Management - Distribution Program
Operating Expenses | 5.03 | 4.68 | 4.69 | 4.7 | 4.7 | 4.71 | 4.71 | 4.71 | 4.71 | 4.71 | 47.35 | 4.735
Capital Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 5.03 | 4.68 | 4.69 | 4.7 | 4.7 | 4.71 | 4.71 | 4.71 | 4.71 | 4.71 | 47.35 | 4.735
Vegetation Management - Transmission Program
Operating Expenses | 2.5 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 28.33 | 2.833
Capital Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 2.5 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 28.33 | 2.833
Total SPP Cost
Operating Expenses | 9.66 | 11.97 | 12.1 | 11.97 | 11.97 | 11.98 | 11.98 | 11.98 | 11.98 | 11.98 | 117.57 | 11.757
Capital Expenditures | 22.37 | 91.95 | 99.85 | 96.15 | 95.15 | 95.15 | 95.15 | 95.15 | 95.15 | 95.15 | 881.22 | 88.122
Total | 32.03 | 103.92 | 111.95 | 108.12 | 107.12 | 107.13 | 107.13 | 107.13 | 107.13 | 107.13 | 998.79 | 99.879
(1) See also 2020 - 2022 project level details provided in Appendix
(2) Costs Include previous year(s) projects carried over to current year, current year's project costs and future year's preliminary project costs (e.g., engineering)

## PD Summary (2020-2022)
2020 - 2022 Storm Protection Plan Cost Estimates |  |  |  |  | GULF 000142 20200070-EI
Storm Protection Plan 'SPP' Programs | 2020 Plan |  | 2021 Plan |  | 2022 Plan
| Cap | O&M | Cap | O&M | Cap | O&M
Distribution Mainline Feeder Patrol Program | 300000 | 163000 | 300000 | 163000 | 300000 | 163000
Distribution - Pole Inspection Program | 2199999.8212 | 770000 | 2499999.9829 | 820000 | 2500000.0432 | 820000
Transmission Inspection Program | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000
Substation Inspection Program | 150000 | 100000 | 150000 | 100000 | 150000 | 100000
Distribution Feeder Hardening Program | 6500000 | 580000 | 26400000 | 2127000 | 26400000 | 2127000
Distribution Automation Program | 5000000 | 199000 | 9495000 | 377000 | 7595000 | 301000
Distribution Hardening - Lateral Undergrounding Program | 0 | 0 | 5000000 | 180000 | 5000000 | 180000
Wood Structure Replacement Program | 3500000 | 70000 | 19600000 | 400000 | 29400000 | 600000
Substation Flood Monitoring Program | 1000000 | 0 | 1000000 | 0 | 1000000 | 0
Substation Resiliency Program | 720000 | 0 | 24500000 | 0 | 24500000 | 0
Vegetation Management - Distribution Program | 0 | 5030881.2466 | 0 | 4678345.9677 | 0 | 4685488.9859
Vegetation Management - Transmission Program | 0 | 2502932.4 | 0 | 2872936.4 | 0 | 2872936.4
Total SPP Cost | 22369999.8212 | 9665813.6466 | 91944999.9829 | 11968282.3677 | 99845000.0432 | 12099425.3859
| Total Program Cost = $32M |  | Total Program Cost = $104M |  | Total Program Cost = $112M
| Avg Annual Cost = $3M |  | Avg Annual Cost = $10M |  | Avg Annual Cost = $11M

## PD Summary (2019 CWIP)
GULF 000143
20200070-EI
Storm Hardening Plan (YE 2019 CWIP) |  |  | Distribution Feeder Hardening (Year End 2019 Internal Order Charges)
Storm Hardening Plan Programs | 2019 Actuals |  | SAP WBS L1 of WBS L4 | Project Description | IM Program Position of WBS L4 | District | Internal Order | (Cap/COR/O&M) | CAP/COR YE 2019 | In-Service Date | Completion Date | Close Date
| CAPITAL | CWIP | UDST.00022060: Pole Program | 2019 SH GREENWOOD 8472 PH#1 | PD06B-1A: 60A Insp, Treat, Reinfrc | Panama City Management Area-PC | ED100015A4XX | 339281.77 | 278556.9694 | 2019-08-26 | 2019-08-29 | Pending
Distribution Inspection Program | 2227540 | 397301.19 | UDST.00022060: Pole Program | 2019 SH GREENWOOD 8472 PH#2 | PD06B-1A: 60A Insp, Treat, Reinfrc | Panama City Management Area-PC | ED100015A4XY | 739630.37 | 607251.0006 | Construction Work In Progress (03.18.20)
Transmission Inspection Program | 0 | 0 | UDST.00022091: Pole Program | 2019-SH 5512 MOBILE HWY & BLUE ANGE | PD06B-1A: 60A Insp, Treat, Reinfrc | Pensacola Management Area-PN | ED100055AEH3 | 692621.55 | 646114.9281 | 2019-04-01 | 2019-08-29 | 2019-12-19
Distribution Feeder Hardening Program | 5202693 | 2302673.4014 | UDST.00022091: Pole Program | 2019-SH 5512 MOBILE HWY & BLUE ANGE | PD06B-1A: 60A Insp, Treat, Reinfrc | Pensacola Management Area-PN | ED100055AEPE | 694195.97 | 647583.6324 | 2019-08-28 | 2019-08-29 | Pending
Distribution Hardening - Lateral Undergrounding Program | 0 | 0 | UDST.00022091: Pole Program | ST 4 - STORM HARDENING - OH (C.R. 97 Reconductor) | PD06B-1A: 60A Insp, Treat, Reinfrc | Pensacola Management Area-PN | ED100055AFCA | 467184.43 | 435814.9619 | 2019-11-01 | 2020-03-06 | Pending
Transmission Hardening Program | 7397323 | 4461845.74 | UDST.00022026: Feeder Hardening | 9130' U/B RECONDUCTOR 9242 VALPARAI | PD06B-2E: 62H Windzone Feeders | Central Management Area-FW | ED1009193581 | 436824.62 | 387290.5119 | Construction Work In Progress (03.18.20)
Vegetation Management - Distribution Program | 0 | 0 | PD04B-3B: 84C Priority Feeders | 2019 SH GREENWOOD 8472 PH3 | UDST.00022040: Planned Maintenance | Panama City Management Area-PC | ED100015A5H4 | 402646.41 | 352668.0587 | 2020-03-03 | Pending | Pending
Vegetation Management - Transmission Program | 0 | 0 | PD04B-3B: 84C Priority Feeders | 2019 SH GREENWOOD 8472 PH4 | UDST.00022040: Planned Maintenance | Panama City Management Area-PC | ED100015A5J4 | 541877.2 | 474616.8734 | 2020-03-03 | Pending | Pending
Total SPP Cost | 14827556 | 7161820.3314 | PD04B-3B: 84C Priority Feeders | 2019 SH 5512 MOBILE HWY | UDST.00022088: Planned Maintenance | Pensacola Management Area-PN | ED100055AEPN | 1006028.72 | 891949.2175 | 2019-12-05 | Pending | Pending
|  |  | PD04B-3B: 84C Priority Feeders | DEVINE FARM ROAD AT I-10 | UDST.00022088: Planned Maintenance | Pensacola Management Area-PN | ED100055AFPF | 542346.85 | 480846.9568 | Construction Work In Progress (03.18.20)
[7 empty] | 2019 Total = | 5862637.89 | 5202693.1108
Distribution - Pole Inspections (Cyclic)
|  |  | Responsible Cost Center of WBS L4 | IM Program Position of WBS L4 | SAP WBS L1 of WBS L4 | WBS L4 | MOPR YE 2019 | Comments | CWIP | CAP/COR YE 2019
|  |  | 0000682026: Fort Walton Management Area-FW | PD06B-1B: 61A Replacement | UDST.00022074: Pole Program | UDST.00022074.02.01.01: Install | 321487.27 | 560 Internal Orders Use MOPR | 397301.19 | 2227539.8
|  |  | 0000682309: Pensacola Management Area-PN | PD06B-1B: 61A Replacement | UDST.00022091: Pole Program | UDST.00022091.02.01.01: Install | 75813.92
Wood Structure Replacement
|  |  | Responsible Cost Center of WBS L4 | IM Program Position of WBS L4 | SAP WBS L1 of WBS L4 | WBS L4 | MOPR YE 2019 | Comments | CWIP | CAP/COR YE 2019
|  |  | 0000682212: Trans Line-Panama City Dist | PD06A-3: TL Harden Rebuilds | UTRN.00022048: Hardening Rebuilds | UTRN.00022048.01.01.01: Install | 1797829.49 | 14 Internal Orders Use MOPR | 4126672.23 | 6904820.32
|  |  | 0000682213: Trans Line-PNS & FW Dist | PD06A-3: TL Harden Rebuilds | UTRN.00022048: Hardening Rebuilds | UTRN.00022048.02.01.01: Install | 2328842.74
Substation Resiliency
|  |  | Responsible Cost Center of WBS L4 | IM Program Position of WBS L4 | SAP WBS L1 of WBS L4 | WBS L4 | MOPR YE 2019 | Comments | CWIP | CAP/COR YE 2019
|  |  | 0000682203: Substation-Panama City District | PD06A-5: SU Hardening | UTRN.00022120: Hardening Dsbn Facilities Station | UTRN.00022120.01.01.01: Install | 309852.93 | 7 Internal Orders Use MOPR | 335173.51 | 492503.2
|  |  | 0000682205: Substation-Pensacola District | PD06A-5: SU Hardening | UTRN.00022121: Hardening Trmn Facilities Station | UTRN.00022121.04.01.01: Install | 25320.58

## PD Summary (2020-22) High Lev
2020 - 2022 Storm Protection Plan 3 Year Summary By Program | [5 empty] | GULF 000144 20200070-EI
Storm Protection Plan 'SPP' Programs | 2020 Plan |  | 2021 Plan |  | 2022 Plan
| Cap | O&M | Cap | O&M | Cap | O&M
Distribution Inspection Program | 2499999.8212 | 933000 | 2799999.9829 | 983000 | 2800000.0432 | 983000
Transmission Inspection Program | 3150000 | 350000 | 3150000 | 350000 | 3150000 | 350000
Distribution Feeder Hardening Program | 11500000 | 779000 | 35895000 | 2504000 | 33995000 | 2428000
Distribution Hardening - Lateral Undergrounding Program | 0 | 0 | 5000000 | 180000 | 5000000 | 180000
Transmission Hardening Program | 5220000 | 70000 | 45100000 | 400000 | 54900000 | 600000
Vegetation Management - Distribution Program | 0 | 5030881.2466 | 0 | 4678345.9677 | 0 | 4685488.9859
Vegetation Management - Transmission Program | 0 | 2502932.4 | 0 | 2872936.4 | 0 | 2872936.4
Total SPP Cost | 22369999.8212 | 9665813.6466 | 91944999.9829 | 11968282.3677 | 99845000.0432 | 12099425.3859
| Total Program Cost = $32M |  | Total Program Cost = $104M |  | Total Program Cost = $112M
| Avg Annual Cost = $3M |  | Avg Annual Cost = $10M |  | Avg Annual Cost = $11M

## PD Full Details
Storm Protection Plan 'SPP' Cost Estimates (Budget) | [8 empty] | GULF 000145 20200070-EI
SPP | 2020 Plan |  | 2021 Plan |  | 2022 Plan |  | 2023 Plan |  | 2024 Plan |  | 2025 Plan |  | 2026 Plan |  | 2027 Plan |  | 2028 Plan |  | 2029 Plan |  | Total (2020 - 2029)
Programs | Cap | O&M | Cap | O&M | Cap | O&M | Cap | O&M | Cap | O&M | Cap | O&M | Cap | O&M | Cap | O&M | Cap | O&M | Cap | O&M | Cap | O&M
Distribution Mainline Feeder Patrol Program
(Low-Budget) | 300000 |  | 300000 |  | 300000 |  | 300000 |  | 300000 |  | 300000 |  | 300000 |  | 300000 |  | 300000 |  | 300000 |  | 3000000 | 0
(Proposed) | 300000 | 163000 | 300000 | 163000 | 300000 | 163000 | 300000 | 163000 | 300000 | 163000 | 300000 | 163000 | 300000 | 163000 | 300000 | 163000 | 300000 | 163000 | 300000 | 163000 | 3000000 | 1630000
(High) | 300000 | 163000 | 300000 | 163000 | 300000 | 163000 | 300000 | 163000 | 300000 | 163000 | 300000 | 163000 | 300000 | 163000 | 300000 | 163000 | 300000 | 163000 | 300000 | 163000 | 3000000 | 1630000
Distribution - Pole Inspection Program)
(Low-Budget) | 2199999.8212 | 770000 | 2499999.9829 | 820000 | 2500000.0432 | 820000 | 2500000.0012 | 820000 | 2499999.9737 | 820000 | 2500000.0036 | 820000 | 2500000 | 820000 | 2500000 | 820000 | 2500000 | 820000 | 2500000 | 820000 | 24699999.8258 | 8150000
(Proposed) | 2199999.8212 | 770000 | 2499999.9829 | 820000 | 2500000.0432 | 820000 | 2500000.0012 | 820000 | 2499999.9737 | 820000 | 2500000.0036 | 820000 | 2500000 | 820000 | 2500000 | 820000 | 2500000 | 820000 | 2500000 | 820000 | 24699999.8258 | 8150000
(High) | 2199999.8212 | 770000 | 2499999.9829 | 820000 | 2500000.0432 | 820000 | 2500000.0012 | 820000 | 2499999.9737 | 820000 | 2500000.0036 | 820000 | 2500000 | 820000 | 2500000 | 820000 | 2500000 | 820000 | 2500000 | 820000 | 24699999.8258 | 8150000
Transmission Inspection Program
(Low-Budget) | 1100000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 28100000 | 2500000
(Proposed) | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 30000000 | 2500000
(High) | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000 | 30000000 | 2500000
Substation Inspection Program
(Low-Budget) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
(Proposed) | 150000 | 100000 | 150000 | 100000 | 150000 | 100000 | 150000 | 100000 | 150000 | 100000 | 150000 | 100000 | 150000 | 100000 | 150000 | 100000 | 150000 | 100000 | 150000 | 100000 | 1500000 | 1000000
(High) | 150000 | 100000 | 150000 | 100000 | 150000 | 100000 | 150000 | 100000 | 150000 | 100000 | 150000 | 100000 | 150000 | 100000 | 150000 | 100000 | 150000 | 100000 | 150000 | 100000 | 1500000 | 1000000
Distribution Feeder Hardening Program
(Low-Budget) | 6500000 | 580000 | 26400000 | 2127000 | 26400000 | 2127000 | 26400000 | 2127000 | 26400000 | 2127000 | 26400000 | 2127000 | 26400000 | 2127000 | 26400000 | 2127000 | 26400000 | 2127000 | 26400000 | 2127000 | 244100000 | 19723000
(Proposed) | 6500000 | 580000 | 26400000 | 2127000 | 26400000 | 2127000 | 26400000 | 2127000 | 26400000 | 2127000 | 26400000 | 2127000 | 26400000 | 2127000 | 26400000 | 2127000 | 26400000 | 2127000 | 26400000 | 2127000 | 244100000 | 19723000
(High) | 9000000 | 744000 | 26400000 | 2127000 | 41400000 | 3722000 | 41400000 | 3722000 | 41400000 | 3722000 | 66400000 | 6381000 | 66400000 | 6381000 | 66400000 | 6381000 | 66400000 | 6381000 | 66400000 | 7610000 | 491600000 | 47171000
Distribution Automation Program
(Low-Budget) | 5000000 | 199000 | 9495000 | 377000 | 7595000 | 301000 | 3895000 | 155000 | 3895000 | 155000 | 3895000 | 155000 | 3895000 | 155000 | 3895000 | 155000 | 3895000 | 155000 | 3895000 | 155000 | 49355000 | 1962000
(Proposed) | 5000000 | 199000 | 9495000 | 377000 | 7595000 | 301000 | 3895000 | 155000 | 3895000 | 155000 | 3895000 | 155000 | 3895000 | 155000 | 3895000 | 155000 | 3895000 | 155000 | 3895000 | 155000 | 49355000 | 1962000
(High) | 7645000 | 303000 | 9495000 | 377000 | 7595000 | 301000 | 3895000 | 155000 | 3895000 | 155000 | 3895000 | 155000 | 3895000 | 155000 | 3895000 | 155000 | 3895000 | 155000 | 3895000 | 155000 | 52000000 | 2066000
Distribution Hardening - Lateral Undergrounding Program
(Low-Budget) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
(Proposed) | 0 | 0 | 5000000 | 180000 | 5000000 | 180000 | 5000000 | 180000 | 5000000 | 180000 | 5000000 | 180000 | 5000000 | 180000 | 5000000 | 180000 | 5000000 | 180000 | 5000000 | 180000 | 45000000 | 1620000
(High) | 1500000 | 60000 | 10000000 | 370000 | 10000000 | 370000 | 10000000 | 370000 | 10000000 | 370000 | 10000000 | 370000 | 10000000 | 370000 | 10000000 | 370000 | 10000000 | 370000 | 10000000 | 370000 | 91500000 | 3390000
Wood Structure Replacement Program
(Low-Budget) | 3500000 | 70000 | 20000000.0076 | 0 | 20000000.0076 | 0 | 20000000.0076 | 0 | 20000000.0076 | 0 | 20000000.0076 | 0 | 20000000.0076 | 0 | 20000000.0076 | 0 | 20000000.0076 | 0 | 20000000.0076 | 0 | 183500000.0684 | 70000
(Proposed) | 3500000 | 70000 | 19600000 | 400000 | 29400000 | 600000 | 29400000 | 600000 | 29400000 | 600000 | 29400000 | 600000 | 29400000 | 600000 | 29400000 | 600000 | 29400000 | 600000 | 29400000 | 600000 | 258300000 | 5270000
(High) | 7000000 | 139000 | 29400000 | 600000 | 29400000 | 600000 | 29400000 | 600000 | 29400000 | 600000 | 29400000 | 600000 | 29400000 | 600000 | 29400000 | 600000 | 29400000 | 600000 | 29400000 | 600000 | 271600000 | 5539000
Substation Flood Monitoring Program
(Low-Budget) | 1000000 | 0 | 1000000 | 0 | 1000000 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 0
(Proposed) | 1000000 | 0 | 1000000 | 0 | 1000000 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 0
(High) | 1000000 | 0 | 1000000 | 0 | 1000000 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 0
Substation Resiliency Program
(Low-Budget) | 720000 | 0 | 3799999.9901 | 0 | 0 | 0 | 5430000.0194 | 0 | 14999999.9973 | 0 | 14999999.9973 | 0 | 20000000 | 0 | 20000000 | 0 | 20000000 | 0 | 20000000 | 0 | 119950000.0042 | 0
(Proposed) | 720000 | 0 | 24500000 | 0 | 24500000 | 0 | 24500000 | 0 | 24500000 | 0 | 24500000 | 0 | 24500000 | 0 | 24500000 | 0 | 24500000 | 0 | 24500000 | 0 | 221220000 | 0
(High) | 4800000 | 0 | 30000000 | 0 | 30000000 | 0 | 30000000 | 0 | 30000000 | 0 | 30000000 | 0 | 30000000 | 0 | 30000000 | 0 | 30000000 | 0 | 30000000 | 0 | 274800000 | 0
Vegetation Management - Distribution Program
(Low-Budget) | 0 | 5030881.2466 | 0 | 4678345.9677 | 0 | 4685488.9859 | 0 | 4696167.2829 | 0 | 4696167.3662 | 0 | 4705752.7908 | 0 | 4705752.7908 | 0 | 4705752.7908 | 0 | 4705752.7908 | 0 | 4705752.7908 | 0 | 47315814.8033
(Proposed) | 0 | 5030881.2466 | 0 | 4678345.9677 | 0 | 4685488.9859 | 0 | 4696167.2829 | 0 | 4696167.3662 | 0 | 4705752.7908 | 0 | 4705752.7908 | 0 | 4705752.7908 | 0 | 4705752.7908 | 0 | 4705752.7908 | 0 | 47315814.8033
(High) | 0 | 5030881.2466 | 0 | 4678345.9677 | 0 | 4685488.9859 | 0 | 4696167.2829 | 0 | 4696167.3662 | 0 | 4705752.7908 | 0 | 4705752.7908 | 0 | 4705752.7908 | 0 | 4705752.7908 | 0 | 4705752.7908 | 0 | 47315814.8033
Vegetation Management - Transmission Program
(Low-Budget) | 0 | 2502932.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 28359360
(Proposed) | 0 | 2502932.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 28359360
(High) | 0 | 2502932.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 2872936.4 | 0 | 28359360
Total SPP Cost
(Low-Budget) | 20319999.8212 | 9402813.6466 | 66494999.9805 | 11125282.3677 | 60795000.0508 | 11056425.3859 | 62525000.0282 | 10921103.6829 | 71094999.9787 | 10921103.7662 | 71095000.0085 | 10930689.1908 | 76095000.0076 | 10930689.1908 | 76095000.0076 | 10930689.1908 | 76095000.0076 | 10930689.1908 | 76095000.0076 | 10930689.1908 | 656704999.8984 | 108080174.8034
(Proposed) | 22369999.8212 | 9665813.6466 | 91944999.9829 | 11968282.3677 | 99845000.0432 | 12099425.3859 | 96145000.0012 | 11964103.6829 | 95144999.9737 | 11964103.7662 | 95145000.0036 | 11973689.1908 | 95145000 | 11973689.1908 | 95145000 | 11973689.1908 | 95145000 | 11973689.1908 | 95145000 | 11973689.1908 | 881174999.8258 | 117530174.8034
(High) | 36594999.8212 | 10062813.6466 | 112244999.9829 | 12358282.3677 | 125345000.0432 | 13884425.3859 | 121645000.0012 | 13749103.6829 | 120644999.9737 | 13749103.7662 | 145645000.0036 | 16417689.1908 | 145645000 | 16417689.1908 | 145645000 | 16417689.1908 | 145645000 | 16417689.1908 | 145645000 | 17646689.1908 | 1244699999.8258 | 147121174.8034
| Total Program Cost = $32M |  | Total Program Cost = $104M |  | Total Program Cost = $112M |  | Total Program Cost = $108M |  | Total Program Cost = $107M |  | Total Program Cost = $107M |  | Total Program Cost = $107M |  | Total Program Cost = $107M |  | Total Program Cost = $107M |  | Total Program Cost = $107M |  | Total Program Cost = $999M
| Avg Annual Cost = $3M |  | Avg Annual Cost = $10M |  | Avg Annual Cost = $11M |  | Avg Annual Cost = $11M |  | Avg Annual Cost = $11M |  | Avg Annual Cost = $11M |  | Avg Annual Cost = $11M |  | Avg Annual Cost = $11M |  | Avg Annual Cost = $11M |  | Avg Annual Cost = $11M |  | Avg Annual Cost = $100M
I. Executive Summary
| 2020 Cost = $32M | [19 empty] | Total Range Cost = $765 - $1,392M
| 2020-2022 Cost = $248M | [19 empty] | Avg Annual Range Cost = $765 - $139M
2020-2022 Avg/Yr = $83M
A. Distribution Inspection Program
| 2020-2022 Cost = $11.0M | [19 empty] | Total Program Cost = $37.5M
| 2020-2022 Avg/Yr = $3.7M | [19 empty] | Avg Annual Program Cost = $3.7M
B. Transmission Inspection Program
| 2020-2022 Cost = $10.5M | [19 empty] | Total Program Cost = $35.0M
| 2020-2022 Avg/Yr = $3.5M | [19 empty] | Avg Annual Program Cost = $3.5M
C. Distribution Feeder Hardening Program
| 2020-2022 Cost = $87.1M | [19 empty] | Total Program Cost = $315.1M
| 2020-2022 Avg/Yr = $29.0M | [19 empty] | Avg Annual Program Cost = $31.5M
D. Distribution Hardening – Lateral Undergrounding Program
| 2020-2022 Cost = $10.4M | [19 empty] | Total Program Cost = $46.6M
| 2020-2022 Avg/Yr = $3.5M | [19 empty] | Avg Annual Program Cost = $4.7M
E. Transmission Hardening - Substations and Wood Structures Program
| 2020-2022 Cost = $106.3M | [19 empty] | Total Program Cost = $488.8M
| 2020-2022 Avg/Yr = $35.4M | [19 empty] | Avg Annual Program Cost = $48.9M
F. Vegetation Management - Distribution Program
| 2020-2022 Cost = $14.4M | [19 empty] | Total Program Cost = $47.3M
| 2020-2022 Avg/Yr = $4.8M | [19 empty] | Avg Annual Program Cost = $4.7M
G. Vegetation Management - Transmission Program
| 2020-2022 Cost = $8.2M | [19 empty] | Total Program Cost = $28.4M
| 2020-2022 Avg/Yr = $2.7M | [19 empty] | Avg Annual Program Cost = $2.8M

## DBU Inspections
Distribution Inspection Program | [5 empty] | GULF 000146 20200070-EI
(2020-2022)
| 2020 Plan |  | 2021 Plan |  | 2022 Plan
| Cap | O&M | Cap | O&M | Cap | O&M
| 2499999.8212 | 933000 | 2799999.9829 | 983000 | 2800000.0432 | 983000
Distribution Mainline Feeder Patrol | 2020 Plan |  | 2021 Plan |  | 2022 Plan
| Cap | O&M | Cap | O&M | Cap | O&M
Distribution Mainline Feeder Patrol Fort Walton: 71 Feeders; Panama City: 75 Feeders; Pensacola: 159 Feeders | 300000 | 163000 | 300000 | 163000 | 300000 | 163000
Distribution - Pole Inspections (Cyclic) | 2020 Plan |  | 2021 Plan |  | 2022 Plan
| Cap | O&M | Cap | O&M | Cap | O&M
Pole Inspection (Cyclic) - Distribution | 2199999.8212 | 770000 | 2499999.9829 | 820000 | 2500000.0432 | 820000

## TBU Inspections
Transmission Inspection Program | [5 empty] | GULF 000147 20200070-EI
(2020-2022)
| 2020 Plan |  | 2021 Plan |  | 2022 Plan
| Cap | O&M | Cap | O&M | Cap | O&M
| 3150000 | 350000 | 3150000 | 350000 | 3150000 | 350000
| 2020 Plan |  | 2021 Plan |  | 2022 Plan
Transmission Pole Inspections | Cap | O&M | Cap | O&M | Cap | O&M
Pole Inspection - Transmission | 3000000 | 250000 | 3000000 | 250000 | 3000000 | 250000
| 2020 Plan |  | 2021 Plan |  | 2022 Plan
Substation Equipment Inspections | Cap | O&M | Cap | O&M | Cap | O&M
Equipment Inspection - Substation | 150000 | 100000 | 150000 | 100000 | 150000 | 100000

## DBU Feeder Hardening
Distribution Feeder Hardening Program | [7 empty] | GULF 000148 20200070-EI
(2020-2022)
[5 empty] | 2020 Plan |  | 2021 Plan |  | 2022 Plan
[5 empty] | Cap | O&M | Cap | O&M | Cap | O&M
[5 empty] | 11500000 | 779000 | 35895000 | 2504000 | 33995000 | 2428000
Distribution Feeder Hardening
[5 empty] | Estimated Cost |  | Estimated | Estimated | Number of Customers |  | Criteria
2020 Projects | District | Substation | Feeders | Scope | Capital | Expense | Start | Completion | Residential | Com/Industrial
Brentwood 6678 & Oakfield 7922 | Pensacola | Brentwood/Oakfield | 6678/7922 | Replace and hardening 37 poles | 1087000 | 108000 | March 2020 | December 2020 | 4331 | 286 | CIF
Avalon 5792 | Pensacola | Avalon | 5792 | Replace and hardening 68 poles | 1325000 | 121000 | March 2020 | December 2020 | 2974 | 250 | CIF
Bayou Marcus 5572 | Pensacola | Bayou Marcus | 5572 | Replace and hardening 60 poles | 925000 | 84000 | March 2020 | December 2020 | 1371 | 15 | CIF
Turner 5662 | Fort Walton | Turner | 5662 | Replace and hardening 123 poles | 867000 | 54000 | October 2020 | December 2021 | 3105 | 269 | CIF
Hathaway 8642 | Panama City | Hathaway | 8642 | Replace and hardening 150 poles | 1790000 | 169000 | June 2020 | December 2020 | 2560 | 170 | CIF
Redwood 8722 | Panama City | Redwood | 8722 | Replace and hardening 34 poles | 506000 | 44000 | June 2020 | December 2020 | 1789 | 263 | CIF
|  |  |  | Total = | 6500000 | 580000 |  |  |  |  | *CIF = Critical Infrastructure Facility
2021 Program Details | Estimated Projects |  | Feeder Impact | Scope |  |  |  | Estimated Cost
To Be Determined | 6 to 18 |  | 6 to 18 | Hardening range of 12 to 32 miles of feeder, and replacement of approximately 500 - 930 poles |  |  |  | $26.4MM
2022 Program Details | Estimated Projects |  | Feeder Impact | Scope |  |  |  | Estimated Cost
To Be Determined | 6 to 18 |  | 6 to 18 | Hardening range of 12 to 32 miles of feeder, and replacement of approximately 500 - 930 poles |  |  |  | $26.4MM
Distribution Automation |  |  |  |  | 2020 Capital Plan |  | 2021 Capital Plan |  | 2022 Capital Plan
Distribution Automated Feeder Switch 'AFS' Capital; Feeder Recloser & Switched Installations. 2020: Fort Walton: 31 Sites; Panama City: 16 Sites; Pensacola 35 Sites |  |  |  |  | 3200000 |  | 3600000 |  | 1700000
Distribution Automation Other Capital: Communication & Control Equipment for Fault Current Indicators and other field equipment capable of providing SCADA information and controls |  |  |  |  | 1800000 |  | 5895000 |  | 5895000

## DBU Lateral Hardening
GULF 000149 20200070-EI
Distribution Hardening - Lateral Undergrounding Program
(2021-2022)
|  |  |  | 2020 Plan * |  | 2021 Plan |  | 2022 Plan
|  |  |  | Cap | O&M | Cap | O&M | Cap | O&M
|  |  |  | 0 | 0 | 5000000 | 180000 | 5000000 | 180000
2021 Program Details | Estimated Projects | Lateral Impact | Scope | Estimated Cost
To Be Determined | 8 | 8 miles | Replace overhead conductor with underground conductors based on predetermined criteria | $5M
2022 Program Details | Estimated Projects | Lateral Impact | Scope | Estimated Cost
To Be Determined | 8 | 8 miles | Replace overhead conductor with underground conductors based on predetermined criteria | $5M
* 2020 - Gulf Power will begin Evaluating and Engineering Undergrounding of Laterals and Plans to Begin Construction in 2021.

## Transmission Hardening
GULF 000150
20200070-EI
Transmission Hardening Program
(2020-2022)
[5 empty] | 2020 Plan |  | 2021 Plan |  | 2022 Plan
[5 empty] | Cap | O&M | Cap | O&M | Cap | O&M
[5 empty] | 5220000 | 70000 | 45100000 | 400000 | 54900000 | 600000
Substation Hardening
|  | Substation |  |  | Estimated Cost |  | Estimated | Estimated | Number of Customers
2020 Projects | District | Impact | Scope |  | Capital | Expense | Start | Completion | Residential | Commercial/Industrial
Shalimar Substation Storm Hardening | Central | Shalimar | Storm Hardened Control House |  | 300000 | 0 | January 2020 | June 2020 | 4827 | 378
Hurlburt Substation Storm Hardening | Central | Hurlburt | Storm Hardened Control House With Flood monitoring |  | 300000 | 0 | June 2020 | December 2020 | 6054 | 348
Niceville Substation Storm Hardening | Central | Niceville | Storm Hardened Control House |  | 300000 | 0 | June 2020 | December 2020 | 5122 | 462
Naval Air Station North Terminal Station Storm Hardening | Western | NAS North Terminal | Transmission Line Terminal Station Flood Monitoring |  | 20000 | 0 | June 2020 | December 2020 | 0 | 1
Naval Air Station South Terminal Station Storm Hardening | Western | NAS South Terminal | Transmission Line Terminal Station Flood Monitoring |  | 20000 | 0 | June 2020 | December 2020 | 0 | 2
Smith Construction Substation Storm Hardening | Eastern | Smith Construction | Substation Flood Monitoring |  | 20000 | 0 | June 2020 | December 2020 | 0 | 25
Blountstown Substation Storm Hardening | Eastern | Blountstown | Substation Flood Monitoring |  | 20000 | 0 | June 2020 | December 2020 | 0 | 2
Romana Substation Storm Hardening | Western | Romana | Substation Flood Monitoring |  | 20000 | 0 | June 2020 | December 2020 | 1255 | 534
|  |  |  | Total = | 1000000 | 0
| Estimated |  |  |  | Estimated Cost
2021 Program Details | Projects | Impact | Scope |  | Capital | Expense
To Be Determined | 3 | 3 | Storm Hardened Control House |  | 1000000 | 0
| Estimated |  |  |  | Estimated Cost
2022 Program Details | Projects | Impact | Scope |  | Capital | Expense
To Be Determined | 3 | 3 | Storm Hardened Control House |  | 1000000 | 0
Substation Resiliency
|  | Substation/Line |  |  | Estimated Cost |  | Estimated | Estimated | Number of Customers
2020 Projects | District | Impact | Scope |  | Capital | Expense | Start | Completion | Residential | Commercial/Industrial
Valparaiso Substation Transformer Bank Addition | Fort Walton | Substation | Add 2nd Substation Transformer Bank. Design & Civil work in 2020 and Construct in 2021 |  | 75000 | 0 | January 2020 | December 2021 | 5245 | 863
South Crestview Substation Transformer Bank Addition | Fort Walton | Substation | Add 2nd Substation Transformer Bank. Design & Civil work in 2020 and Construct in 2021 |  | 75000 | 0 | January 2020 | December 2021 | 5923 | 1191
Hurlburt Substation Transformer Bank Addition | Fort Walton | Substation | Add 2nd Substation Transformer Bank. Design & Civil work in 2020 and Construct in 2021 |  | 570000 | 0 | January 2020 | December 2021 | 6054 | 348
|  |  |  | Total = | 720000 | 0
| Estimated |  |  |  | Estimated Cost
2021 Program Details | Projects | Impact | Scope |  | Capital | Expense
To Be Determined | 20 | 18 | Transmission/Substation Resiliency Projects |  | 24500000 | 0
| Estimated |  |  |  | Estimated Cost
2022 Program Details | Projects | Impact | Scope |  | Capital | Expense
To Be Determined | 20 | 20 | Transmission/Substation Resiliency Projects |  | 24500000 | 0
Wood Structure Replacement
|  | Number of structures |  |  | Estimated Cost |  | Estimated |  | Number of Customers
2020 Projects | District | to be replaced | Transmission Line |  | Capital | Expense | Start | Completion | Residential | Commercial/Industrial
Caryville Transmission Line Tap | Fort Walton | 30 | Glendale - Ponce De Leon 115 kV |  | 1500000 | 30000 | May 2020 | September 2020 | Transmission System Loop
Santa Rosa - Miramar #1 Transmission Line | Fort Walton | 40 | Santa Rosa - Miramar #1 115 kV |  | 2000000 | 40000 | January 2020 | December 2020 | Transmission System Loop
|  |  |  | Total = | 3500000 | 70000
| Estimated | Number of structures
2021 Program Details | Projects | to be replaced | Line Impact |  | Estimated Cost
To Be Determined | 20 | 400 | 6 |  | $20M
| Estimated | Number of structures
2021 Program Details | Projects | to be replaced | Line Impact |  | Estimated Cost
To Be Determined | 30 | 600 | 10 |  | $30M

## DBU-TBU Vegetation Mngmt
Vegetation Management Program | [6 empty] | GULF 000151 20200070-EI
(2020-2022)
| 2020 Plan |  | 2021 Plan |  | 2022 Plan
Vegetation Management - Distribution Program | Cap | O&M | Cap | O&M | Cap | O&M
Vegetation Management - Distribution Program | 0 | 5030881.2466 | 0 | 4678345.9677 | 0 | 4685488.9859
| 2020 Plan |  | 2021 Plan |  | 2022 Plan
Vegetation Management - Transmission Program | Cap | O&M | Cap | O&M | Cap | O&M
Vegetation Management - Transmission Program | 0 | 2502932.4 | 0 | 2872936.4 | 0 | 2872936.4

## Mngmt Area Map (2019)
GULF 000152 20200070-EI

## GPCO Windloads
GULF 000153 20200070-EI